United Nations Development Program

| Project title: Integrated Approach in Management of Major Biodiversity Corridors in the Philippines |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Philippines | Implementing Partner: Department of Environment and Natural Resources (DENR) |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/ Partnership Framework for Sustainable Development (PFSD)/Country Program Outcome: National and local government and key stakeholders ensure that urbanization, economic growth, and climate change actions are converging for a resilient, sustainable and equitable development path of communities. |  |  |  |  |  |
| UNDP Strategic Plan Output: 1.4.1 Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate Risk |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Project ID 00096757 |  |  | Atlas Output ID 00100687 |  |  |
| UNDP-GEF PIMS ID number: 5886 |  |  | GEF ID number: 9584 |  |  |
| Planned start date: July 2020 |  |  | Planned end date: June 2026 |  |  |
| PAC meeting date: January 31- February 1, 2019 |  |  |  |  |  |
| Brief project description: The project objective is to operationalize integrated management of biodiversity corridors to generate multiple benefits including effective conservation of globally threathened species and high conservation value forests, reduce deforestration and degradation and enhance local biodiversity-friendly livelihoods. It is aimed at addressing the increased degradation of wetland habitats from habitats from deforestation and conversion to agriculture and expanding infrastructure development, pollution, invasive alien species (IAS) and climate change is becoming an ever-increasing threat to critical habitats and ecosystems and their attendant biodiversity. Increasing demand for forest, mineral and wildlife products and cropland and agriculture monocultures and demand for infrastructure and transportation development has accelerated in recent years rapidly changing the landscape with consequential threats to biodiversity and ecosystem services. The project is thus aimed at addressing these multiple threats by harmonizing socio-economic development, sustainable management of land, forests and other natural resources and biodiversity conservation through an integrated management approach in biodiversity corridors in Philippines. To achieve this, actions will be taken to strengthen capacity and coordinated planning at the national and provincial levels on socio-economic development on the one hand as well as demonstrate sustainable agriculture and natural resources management, biodiversity conservation and restoration, and alternative livelihood initiatives, including from a gender and indigenous people perspectives on the other. This will be achieved through the implementation of four inter-related and mutually complementary components that are focussed at addressing existing barriers. The four components of the project are: Component 1: Effective coordination and governance framework for integrated ecosystem management in the Philippines biodiversity corridors system; Component 2: Application of integrated network design and management of biodiversity corridors to ensure continued stability and sustainability of their biological, ecosystem services and socio-economic conservation values; Component 3: Community-based sustainable use and management systems in the two pilot biodiversity corridor systems in the Philippines; and Component 4: Knowledge management, gender mainstreaming, learning, monitoring and evaluation |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund |  |  | USD 12,260,241 |  |  |
| - Total Budget administered by UNDP |  |  | USD 12,260,241 |  |  |
| Parallel co-financing |  |  |  |  |  |
| Government, Department of Environment and Natural Resources |  |  | USD 42,891,028 |  |  |
| Government, Department of Agriculture |  |  | USD 12,293,364 |  |  |
| Government, Department of Trade and Industry |  |  | USD 166,609 |  |  |
| Government, Province of Surigao del Norte |  |  | USD 99,822 |  |  |
| Government, Province of Davao Oriental |  |  | USD 370,042 |  |  |
| CSOs |  |  | USD 2,205,271 |  |  |
| Private Sector |  |  | USD 3,174,871 |  |  |
| UNDP |  |  | USD 1,500,000 |  |  |
| - Total co-financing |  |  | USD 62,701,007 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 74,961,248 |  |  |
| Signatures |  |  |  |  |  |
| Signature: ROY A. CIMATU Secretary |  | Agreed by DENR as Implementing Partner |  | Date/Month/Year: |  |
| Signature: |  | Agreed by NEDA |  | Date/Month/Year: |  |
| Signature: TITON MITRA Resident Representative |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	8

III.	Strategy	18

IV.	Results and Partnerships	26

V.	Project Management	70

VI.	Project Results Framework	72

VII.	Monitoring and Evaluation (M&E) Plan	80

VIII.	Governance and Management Arrangements	90

IX.	Financial Planning and Management	98

X.	Total Budget and Work Plan	102

XI.	Legal Context	112

XII.	Risk Management	113

XIII.	 Annexes	115

1.	Governance and Policy relating to Biodiversity Corridors

2.	Biodiversity Corridor Profiles

3.	Framework for Integrated Ecosystem Management, Consensus Building and Planning and Implementation within Biodiversity Corridors

4.	Sustainable Forest Management for Biodiversity Conservation

5.	Rehabilitating Degraded Agricultural Lands in Mindoro and Eastern Mindanao Biodiversity Corridors

6.	Criteria and procedures for selecting conservation value forests, PAs, and KBAs in target clusters

7.	Biodiversity-friendly livelihood and business enterprises

8.	Improving capacity to manage High Conservation Value Forests, Protected Areas and Key Biodiversity Areas

9.	Capacity Building Strategy for LGUs and regional Offices of National Government Agencies in Biodiversity Corridors

10.	Procedures for Forest Certification System in the Philippines

11.	Potential menu of Conservation, SLM, SFM and Improved Agricultural Investments

12.	Framework for Addressing Knowledge Management and Communication

13.	Gender Analysis and Mainstreaming Action Plan

14.	Stakeholder Engagement Plan

15.	UNDP Risk Log

16.	Indigenous Peoples Planning Framework

17.	UNDP Social and Environmental and Social Screening Template (SESP)

18.	Multi year Work-plan

19.	Tracking Tools (METTs)

20.	LOA with the government in case DPC is applied

21.	Terms of Reference for Key Staff

22.	UNDP Project Quality Assurance Report

23.	Synergy between UNDP and FAO GEF Projects

24.	Framework for Training

25.	Overview and Profiles of Tenure Instruments

26.	Summary of Consultants and Consultancy Services

27.	UNDP Capacity Assessment Scorecard (Annex 27.1 DENR; Annex 27.2 DA; Annex 27.2 NCIP)

28.	Results of the capacity assessment of the project implementing partner and HACT micro assessment

29.	 Carbon Estimates (Annex 29.1 Carbon calculation Notes; Annex 29.2 FAO EX-ACT Worksheet)

30.	Co-financing letters

31.	Consultations and List of People consulted during project preparation

32.	Monitoring Plan

List of Figures and Tables

Figure 1: Threats, root causes and barriers to the long-term solution and GEF strategies to address them

Figure 2:  Theory of Change

Figure 3: Maps of Project Areas

Table 1: Geographical, Biological and Socio-economic Features of Pilot Biodiversity Corridors

- Table 2- Key government funding programs to enable replication of SLM mechanisms

Table 3 -Partnership Arrangements

Table 4: Consultations Meetings

Table 5: Stakeholder Involvement Plan

Table 6: Project Risk and Mitigation Matrix

Table 7: Mandatory GEF M&E Requirements and M&E Budget

Table 8: Work Packages

Acronyms and Abbreviations

| AD | Agricultural Development |
| --- | --- |
| ADB ADSDPP | Asian Development Bank Ancestral Domain Sustainable Development Protection Plan |
| AFMA | Agriculture Fishery and Modernization Plan |
| ASEAN | Association of South East Asian Nations |
| BAF | Bureau of Agriculture and Fisheries |
| BD | Biodiversity Corridor |
| BFAP | Biodiversity Friendly Agricultural Practices |
| BFAR | Bureau of Fisheries and Aquatic Resources |
| BFE | Biodiversity-Friendly Enterprise |
| BMB | Biodiversity Management Bureau |
| BPP | Biodiversity Partnership Project |
| BSWM | Bureau of Soils and Water Management |
| BWISER | Biodiversity and Watersheds Improved for Stronger Economy and Ecosystem Resilience |
| CAAC | Corridor alliance Advisory Committee |
| CADT | Certificates of Ancestral Domain Title |
| CBFM | Community based forest management |
| CBFMA | Community based Forest Management Agreement |
| CCP | Cluster conservation plan |
| CFM | Community Forest Management |
| CH | Critical Habitats |
| CLUP | Comprehensive land use planning |
| C&I | Criteria and Indicators |
| CSO | Civil Society Organizations |
| CSR | Corporate Social Responsibility |
| DA | Department of Agriculture |
| DAO | DENR Administrative Order |
| DAR | Department of Agrarian Reform |
| DENR | Department of Environment and Natural Resources |
| DILG | Department of Interior and Local Government |
| DOLE | Department of Labor and Employment |
| DOT | Department of Tourism |
| EDRB | Ecosystems Restoration and Development Bureau |
| eFIS | Enhanced Forestry Information System |
| EIA | Environment Impact Assessment |
| EMB | Environment Bureau (EMB) |
| EMBC | Eastern Mindanao Biodiversity Corridor |
| ENR | Environment and Natural Resources |
| EO | Executive Order |
| ERDB | Ecosystem Research and Development Bureau |
| FFP | Forest Foundation of the Philippines |
| FLEGT | Forest Law Enforcement, Governance and Trade |
| FLUP | Forest Land Use Plan |
| FMB | Forest Management Bureau |
| FMP | Forestland Management Project |
| FPE | Foundation for Philippine Environment |
| FPIC | Free prior and informed consent |
| FSP | Full Sized Project |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GI | Geographical Indication |
| GIZ | German Development Agency |
| GRM | Grievance redress mechanism |
| HCVA | High Conservation Value Area |
| HLURB | Housing and Land Use Regulatory Board |
| IAS | Invasive Alien Species |
| ICCA | Indigenous Community Conserved Areas |
| IEC | Information, Education and Communication |
| IEM | Integrated Ecosystem Management |
| IFMA | Industrial Forest Management Agreement |
| IKSP | Indigenous knowledge systems and practices |
| INREMP | Integrated Natural Resources Management Program |
| IP | Indigenous Peoples |
| IUCN | International Union for the Conservation of Nature |
| IUUF | Illegal, unregulated, unreported fishing |
| JICA | Japan International Cooperation Agency |
| KBA | Key Biodiversity Area |
| KISS | Knowledge and Information System Section |
| KM | Knowledge Management |
| LCA | Local Conservation Areas |
| LGU | Local Government Unit |
| LMB | Land Management Bureau |
| LPP | League of Provinces of the Philippines |
| M&E | Monitoring and Evaluation |
| METT | Management Effectiveness Tracking Tool |
| MGB | Mines and Geosciences Bureau |
| MLGU | Municipal Local Government Unit |
| MOA | Memorandum of Agreement |
| MRV | Measurable, Reportable and Verification target |
| MSMED | Micro, Small, Medium Enterprises Development |
| MSP | Medium Sized Project |
| MTR | Mid-term Review |
| NAP | National Action Plan |
| NAP-DLDD | National Action Plan to combat Desertification, Land Degradation and Drought |
| NCI | National Convergence Initiative |
| NCIP | National Commission for Indigenous People |
| NEDA | National Economic Development Authority |
| NGA | National Government Agency |
| NIPAS | National Integrated Protected Areas System |
| NOAP | National Organic Agriculture Program |
| NPD | National Project Director |
| NPM | National Project Manager |
| NPMU | National Project Management Unit |
| NSST | National soil sampling and testing |
| NTFP | Non-timber Forest Products |
| OECM | Other Area Based Conservation Measures |
| PA | Protected Areas |
| PACBRMA | Protected area community-based management agreements |
| PAP | Project affected person |
| PB | Project Board |
| PBSAP | Philippine Biodiversity Strategy and Action Plan |
| PCIC | Philippine Crop Insurance Corporation |
| PCS | Philippine Forest Certification System |
| PDRP | Philippine Rural Development Program |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| PLEA | Production Loan Easy Access |
| PLGU | Provincial Local Government Unit |
| PO | People’s Organization |
| POPP | Program and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PRDP | Philippine Rural Development Project |
| PWP | Protect Wildlife Project |
| RBCO | River Basin Coordinating Office |
| RDC | Regional Development Council |
| R/DENR | Regional/Department of Environment and Natural Resources |
| R/NEDA | Regional/ National Economic Development Authority |
| RED | Regional Executive Directors |
| CPD | Regional Project Director |
| CPMU | Regional Project Management Unit |
| RRSP | Risk Resiliency and Sustainability Program |
| RTWG | Regional Technical Working Group |
| SAAD | Special Area for Agricultural Development |
| SDG | Sustainable Development Goal |
| SESP | Social and environmental screening procedures |
| SFM | Sustainable Forest Management |
| SGLG | Seal for Good Local Governance |
| SIFMA | Socialized Industrial Forest Management Agreement |
| SIP | Stakeholder Investment Plan |
| SLM | Sustainable Land Management |
| SME | Small and medium enterprises |
| SOC | Soil organic carbon |
| SSF | Shared Service Facilities |
| STAP | GEF Scientific Technical Advisory Panel |
| TE | Terminal Evaluation |
| TWG | The Working Group |
| UNDP | United Nations Development Program |
| UNDP CO | United Nations Development Program – Country Office |
| UNDP RTA | United Nations Development Program – Regional Technical Advisor |
| UNDP-GEF | UNDP Global Environmental Finance Unit |
| USAID | United States Agency for International Development |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |

# Development Challenge

- This project aims to address the negative impacts of unsustainable sector-led development practices by trying to establish and operationalize a comprehensive planning and management landscape approach that harmonizes socio-economic development, sustainable management of natural resources and conservation biodiversity in major biodiversity corridors in the Philippines. The project’s intervention is to ensure that existing protected areas and surrounding high conservation value forests are managed to support viable populations of globally threatened species and allows for the movement of wildlife, pollination and reproduction, and other processes that support the recovery and improve natural resiliency to external development and climatic shocks. The project comes at a time when increased degradation of natural habitats from deforestation and conversion to agriculture and expanding infrastructure development, pollution, invasive alien species (IAS) and climate change is becoming an ever-increasing threat to critical habitats and ecosystems and their attendant biodiversity. The Philippines Biodiversity Strategy and Action Plan (PBSAP) reported that between 2000 and 2010, the country lost 626,840 hectares of closed forests, while the area of open forests increased by 564,566 hectares and overall forest cover loss between this period was estimated at 328,683 hectares. Based on statistics compiled by the Government of Cambodia, around 1,600 apprehensions, seizures and confiscations of forest products estimated at around USD 1.1 million were made in 2016. In addition, unsustainable practices are leading to over-fishing and destruction of fish habitats, inappropriate aquaculture practices and illegal harvest of non-timber forests products, wildlife and other resources that are aggravating the impact of deforestation and degradation of natural habitats.

- The Philippines comprise more than 7,100 islands covering around 300,000km2 and is the world's second largest archipelagic country after Indonesia. Several deep-water channels subdivide the Philippine archipelago itself. In turn, these have prevented the formation of land bridges between certain individual islands and groups of islands thereby limiting the sharing of species across the archipelago. The isolation of these ice-age islands, coupled with their long history of geological isolation, has had an enormous influence on the country's biological diversity and has resulted in very high rates of speciation and endemism. Of more than 1,130 terrestrial wildlife species recorded for the Philippines, almost half are found nowhere else. Thus at the species level 64% of land mammals, 44% of birds, 65% of reptiles and 77% of amphibians are endemic to the Philippine archipelago. The floral diversity is equally diverse, with between 10,000 and 15,000 species of vascular and non-vascular plants, more than half of them endemic to the Philippines, representing 5% of all species globally described so far. Also like the diverse flora and fauna of the archipelago, over a hundred diverse ethno-linguistic groups comprising the ancestry of the Philippines, mirror to a great extent the precious biological and ecological variety of the country. These indigenous people and cultural communities make their home in different ecological territories, from the coasts to the highlands.  Despite the great ecological diversity of the country, the Philippines ranks among the top ten globally with the largest number of species threatened with extinction.

Key Threats to natural resources management and biodiversity

- The primary threats to biodiversity and direct causes of ecosystem degradation in the Philippines are:

- Loss and degradation of natural habitat stem from deforestation due to conversion of forest areas to agriculture, poor agricultural practices, incoherent agricultural and natural resources policies, informal settlements, (illegal) logging, irresponsible mining, forest fire, and infrastructure development (roads, residential and commercial establishment). In the coastal and marine ecosystems, this is due to conversion of mangroves to fishponds and other coastal developments, damages to coral reefs and sea grass, pollution from industrial sources, agricultural runoff, and siltation. Weak management of protected areas and other natural habitats are also contributory factors to loss of biologically important habitats of globally threatened species and unique ecosystems. Expansion of settlements follows after clearing and conversion of degraded forests into open permanent settlements and agriculture. Underlying drivers are poverty in the rural areas, landlessness, and weak tenure security that discourage sustainable upland farming practices. Once agriculture has set in, intensive use of fertilizers and unsustainable land management practices further erode the soil of essential nutrients thus resulting in diminishing harvests, which leads to further expansion of agriculture in forest areas to meet socio economic needs. Deteriorating productivity of upland farms has forced many indigenous communities to shorten their fallow periods in between forest clearings thus limiting the time for open forest areas to recover naturally. As a result of these processes, the Philippines posted a total of 11.13 million ha of degraded lands in 2017. Despite the high number of population in the forestlands, only less than a million people have long-term tenure arrangements with government through the community based forest management agreements (CBFMAs), covering around 1.62 million hectares. Indigenous Peoples (IP) communities on the other hand, claim an estimated 7.7 million hectares of land (mainly within classified forestlands), but only 4.39 million hectares have been issued certificates of ancestral domain titles (CADTs), as of 2014. Illicit logging activities still persist despite the ban on logging in old growth forests. Based on 2015 data, the total forest cover of the Philippines was estimated at 7,015,944 million ha, of which open forests accounted for 4,347,654 million hectares, or about 67% of the total forest cover in the Philippines. Moreover, between 2010 and 2015 total forest cover increased (partly due to the country’s National Greening Program); however, the total areas of ‘closed’ and ‘open’ forests decreased. Also, the amount of newly degraded forests (i.e. forests that were ‘closed’ in 2010 but were classified as ‘open’ in 2015) amounted to 330,689 hectares.

- Based on the analysis in the Philippine Biodiversity Strategy and Action Plan (PBSAP), “mining claims and rights overlap with defined areas for Protected Areas (PAs), ancestral lands including those planned for conservation areas that threaten ecological sustainability. The Philippines is a significant producer of gold, copper, nickel and chromite and is also abundant in non-metallic and industrial minerals such as marble, limestone, clay, feldspar and aggregates. Since the Supreme Court upheld key provisions of the Mining Code in 2004, there has been a heavy influx of mining activity and investment. As of 2013, about 339 Mineral Production Sharing Agreements within 602,012 ha had been issued (DENR-MGB 2013). Since most of the country’s priority conservation areas sit on top of huge mineral reserves, many significant biodiversity areas are in conflict with prescribed land uses and management objectives”. Although mining is not allowed in existing National Integrated Protected Areas System (NIPAS) declared PAs, there is high likelihood that the remaining biodiversity rich Key Biodiversity Areas (KBAs) which are not yet established as PAs will be allocated to mining in the absence of a national or corridor level land use allocation framework.

- Weak enforcement and management capacities, and limited funding, have resulted in PAs where boundaries have been encroached upon by settlers and converted into agriculture and settlements. In some cases, fragmentation of habitats has occurred, thereby failing to provide the essential protection for key highly vulnerable species within protected areas. In many cases, the lack of synergy between the Department of Environment and Natural Resources (DENR) National Greening Program and protected area management have resulted in mismatch in habitat restoration efforts, thereby further contributing to irreversible transformation of original habitats to other ecosystem types. In the coastal areas, threats to coastal and marine biodiversity include industrial development, sand and gravel quarrying, development of coastal infrastructure, destructive fishing behavior, illegal fishing, and siltation due to mining, deforestation, and land degradation from the agricultural areas.

- Unsustainable resource use practices are leading to over exploitation of natural resources including overfishing and destructive fishing practices [e.g. dulong fishery, live fish trading, use of fine mesh nets, illegal, unregulated, unreported fishing (IUUF)]; inappropriate aquaculture practices (such as overstocking of fish pens); and illegal harvesting and collection of non-timber forest products (NTFPs), wildlife and other resources. In terrestrial ecosystems, over exploitation comes in the form of massive fuelwood gathering for both domestic and commercial use, as well as annual forest opening through slash and burn agriculture. While this activity can be considered small scale, the aggregate impact on deforestation and degradation is huge when multiplied by the number of households involved and the frequency of occurrence. Unsustainable production and consumption of medicinal and ornamental plants and wild animals for trade and domestic use is also widely practiced. These contribute to habitat degradation and in certain cases, reduction in species populations. The most sought after and highly valued ornamental plants include the Jade vine (Strongylodon macrobotrys), Giant Staghorn fern (Platycerium grande), Waling waling (Euanthe sanderiana) and many tree fern species. Because of high demand for pet trade, a significant number of animals, such as the Palawan peacock pheasant (Polyplectron emphanum), Philippine cockatoo (Cacatua haematuropygia), talking mynah (Gracula religiosa), Blue napped parrot (Tanygnathus lucionensis), and Asian small-clawed otter (Amblonyx cinereus), are also overharvested. The exploitation of some by- products of wildlife species also endangers their survival, such as the nests produced by the Edible-nest swiftlets (Collocalia fuciphaga) as easy targets of illegal harvesting and wildlife trade. The harvesting of black corals, the massive smuggling of pangolins, and the recent discovery of thousands of forest turtles smuggled in Palawan are just a few examples of how the lucrative wildlife trade works.

- Pollution is leading to collapse of ecosystems, compromising their ability to provide ecological services. One of the major causes is agricultural run-off, mining, navigation, illegal reclamation of lakeshores and shoreland areas and encroachment on easements along rivers and waterways, sometimes endangering human lives. This is most particularly acute in freshwater ecosystems, where the over application of fertilizers and pesticides, and improper land management practices result in siltation, and deterioration of habitats of aquatic species. In the terrestrial areas, soil contamination due to excessive use of fertilizers and pesticides has rendered other agricultural areas unproductive.

- Invasive alien species (IAS) pose one of the greatest threats to aquatic biodiversity. IAS can hasten the extinction of threatened species and reduce the diversity of indigenous and endemic species through predation, competition, parasitism, diseases, hybridization, and species displacement caused by environmental and habitat change. Some of the well documented IAS that have had damaging effects on wetland biodiversity include: Janitor fish (Pterygoplichthys spp.), Knifefish, (Chitala sp.), Giant catfish and Black bass; toads and frogs, including the marine toad (Bufo marinus), the American bullfrog (Rana catesbeiana) and Leopard frog (Rana tigrina); and aquatic plants like the water hyacinth and water fern. Another IAS that poses destruction to the natural habitat is Buyo-buyo (Piper aduncum), a highly aggressive shrub that invades agricultural areas and natural forests.  A total of 70 invasive alien species under 40 families were classified in a profiling done in 16 protected areas in the Philippines. Introduction of exotic species in critical ecosystems, use of inappropriate species for restoration and heavy reliance on “fast growing”, “high yielding” agricultural and terrestrial crops and aquatic species had the unintended effects of invasion of ecosystems. The uncontrolled spread of IAS is due in part to lack of awareness of IAS and their impacts on the ecosystem to which they are introduced, poor understanding of their ecology, life cycle growth; lack of assessment of the environmental impacts of newly introduced species; and lack of regulation. Contributing to these are the disjointed policies and programs that promote agricultural productivity and biodiversity conservation objectives, thereby failing to consider the holistic view and recognize the long-term net effects of IAS introduction on farm income, natural resilience of agriculture, and quality and quantity of food production.

- Climate Change:	The Philippines is one of the most climate change vulnerable areas in Southeast Asia. The country’s vulnerability is exacerbated by the continued attrition of its forests. The unique biodiversity in the country are therefore becoming particularly vulnerable to the deleterious effects of climate change. The link between climate change and biodiversity has long been established. Evidence across the globe indicate that rapid climate change affects ecosystems and species ability to adapt and so biodiversity loss increases. According to the Millennium Ecosystem Assessment, climate change is likely to become one of the most significant drivers of biodiversity loss by the end of the century. Climate change is already forcing biodiversity to adapt either through shifting habitat, changing life cycles, or the development of new physical traits.

- It is clear that the above threats can trace their root causes to rural poverty in the Philippines, owing to landlessness amidst a rapidly growing population. Based on 2015 data, 21.6% of the population lived below the poverty line, with 25.2% recorded in 2012. These are exacerbated by weak enforcement and lack of capacities to sustainably manage natural resources and proper allocation of land among competing uses. The de facto “open access” condition of forestland, critical coastal area and watershed has encouraged settlements of forestlands and conversion to agriculture, unsustainable harvests and improper resource management practices. The absence of secure property and resource use rights by most local communities and indigenous peoples occupying large portions of forest lands have not provided the necessary incentives to properly internalize the costs and benefits of natural resources management, thereby creating a cyclical pattern of degradation, biodiversity loss and poverty. The long-term solution in dealing with the above-mentioned threats to biodiversity and causes of ecosystem degradation is to harmonize socio-economic development, sustainable management of natural resources and biodiversity conservation in biodiversity-rich areas using a landscape planning and management approach. One such approach is through integrated corridor planning and management. Corridors are areas comprising terrestrial, marine and coastal ecosystems that promote solutions reconciling the conservation of biodiversity with its sustainable use. They also provide an opportunity for testing interdisciplinary approaches to understanding and managing changes and interactions between social and ecological systems, including conflict prevention and management of biodiversity.

- Project conceptual model: The complex interacting web of factors that threaten globally significant marine biodiversity in Philippines is illustrated in a conceptual model in Figure 1. This indicates the key areas (indirect and direct factors) and the points where project intervention can contribute towards a reduction in the level of threats, and therefore contribute towards the conservation of biological ecosystems and globally threatened species – and the integrity of the ecosystems they inhabit. The main project intervention strategies are shown as yellow hexagons in Figure 1. The main elements of these strategies are summarized in the Theory of Change diagram in the following section (Figure 2).

Root Causes and barriers that need to be addressed

- The inter-relationships between the different barriers and threats are defined in Figure 1. The three barriers are the following:

- Barrier 1:  Policies, regulations and approaches that breed disjointed governance, planning, management,  and financing of activities within the biodiversity corridors: Currently relevant agencies within DENR and among agencies in PA management and those that have remit over lands identified as biodiversity corridors are guided by their respective mandates and deliver on stated outcomes.  The interplay of various policies and programs in the same landscape often times result in unintended results due to the absence of a commonly agreed planning and management framework for all sectors to follow. For example, the Department of Agriculture (DA) promotes agricultural production   and   intensification, with limited consideration of biodiversity or ecosystem issues even when farms are located in forested lands or within or adjacent to KBAs or PAs. Furthermore, between Forest Management Bureau (FMB) and Biodiversity Management Bureau (BMB), there is a need to reconcile definitions and approach to “forest protection”. Other policies and programs in the landscape, particularly those that support production forest and community-based forest management, require review to determine their compliance with sustainable forest management principles. All this is compounded by the inadequacy of long-term spatial planning framework at the national and sub-national levels that considers sustainable development objectives and specific safeguards– thus, creating an environment where there is competition for “locking” of important lands for specific purposes without regard for their potential longterm impacts on biodiversity, ecosystem services, agricultural productivity, and community livelihoods. Related to the above barrier is the limited capacity to integrate biodiversity considerations in corridor level planning and management and to enforce what legal measures have been adopted  – four out of five identified threats arise from the lack of (or weak and ineffective) compliance monitoring and enforcement of plans, policies, strategies, laws and other measures. Local Government Units (LGUs) have a very crucial role in landscape level actions because of mandates to reflect the above concerns in land use and local investment programs.  However current policy/programs guidance to LGUs tend to be unclear and fragmented that can occasionally act as disincentive for LGU action. Annex 1 describes in more detail how this barrier can be addressed as far as general governance and policies are concerned, both at the national level (BMB, FMB) and at the LGU level and Annex 2 also outlines how governance issues at the corridor level can be addressed.

- Barrier 2:  Fragmented implementation of key programs that fails to effectively address threats to  Biodiversity corridor connectivity and natural resources decline: The absence of an integrated planning framework within biodiversity corridors that takes  into  account connectivity  within  the  corridor  is manifested  by programs  being  implemented  with  limited attention on addressing threats to habitat loss, maintaining ecosystem flows, fragmentation, conversion of high conservation value forests to agriculture. Thus, existing biodiversity corridors remain a mosaic of disjointed land management units with incompatible objectives.  The biodiversity corridors consist of a number of KBAs and PAs, including other areas of high conservation value. However, management plans for these areas are prepared independently, without regard to connectivity of habitats. In the Cordillera corridor for example, which is a center of mammalian endemism in Luzon, there are 14 PAs and six KBAs but no integrated approach exists to link these together to ensure connectivity. Additionally, critical ecosystems such as marshlands and coral reefs are also not integrated into broader seascape management approaches. Further, there is an obvious governance gap pertaining to forestlands. Often referred to as de facto open access areas, these are usually located between forests managed by DENR and the local governments and those under community-based forest management or other regimes, and are usually left without effective management or governance.  Similarly, agricultural areas such as plantations, private farms, and areas previously forests but converted to agriculture continue to be exposed to various degrees and types of degradation in the absence of access to technologies and best practices in sustainable land management. Neither, the DENR or DA is officially responsible to address needs of upland agriculture communities in areas classified as forestlands.   Moreover, indigenous agricultural practices by the many indigenous communities, have helped protect remaining forests while swidden farming have helped in sustaining food supply, agro-biodiversity and their livelihood for generations.   Ironically the same swidden farming is blamed for deforestation due to the overall increase in the aggregate number of households that practice this type of farming and the reduction of the fallow periods in between swidden cultivation cycles. The National Commission for Indigenous People (NCIP) and related agencies currently lack capacity to develop effective programs that foster the forest custodial roles of indigenous communities while managing the impacts of swidden farming as part of their overall customary land governance.  Annex 3 provides a more comprehensive description of how this barrier can be addressed. The proposed integrated ecosystem management approach, including consensus building and planning and implementation within the biodiversity corridor is described in more detail, particularly institutional arrangements between and among concerned agencies and institutions.

- Barrier 3: Weak community level mechanisms to incentivize conservation of biodiversity, promote sustainable natural resource utilization, and monitor compliance: The biodiversity corridors consist of areas that are managed under various tenure regimes including communally and privately-owned lands. A system of incentives is essential to encourage private or land tenure holders in critical spaces within the biological corridors to contribute to providing stepping stones, or expand  the pathways of target species while ensuring improvement in ecosystem services and resilience. Within private lands and other tenured areas, transforming land management practices through such mechanisms as conservation agreements need to be tested while certification systems can promote improved practices. In areas managed for agriculture, the promotion of organic farming and agro-ecosystem technologies are important. While a number of these mechanisms exist, they have not been applied at the corridor level in a way that will result in changes in at a corridor or network level. In addition, review and approval of management plans of tenure holders (CBFMAs, Industrial Forest Management Agreement or IFMAs) should recognize the role of these management units in habitat connectivity, as stepping stones and/or in linking the network of protected areas and conservation areas within the corridor. Annex 4 and Annex 5 describe the incentive mechanisms proposed in the project to communities who are selected to practice and conduct sustainable forest management activities and sustainable land management initiatives, respectively, within the corridors.

- There seems to be no single initiative in the country that is currently addressing all three aforementioned barriers. However, the proposed GEF-financed project will work in coordination with ongoing efforts and partners to build on recent advances in biodiversity conservation efforts.  The project is consistent with the priorities defined in the Philippine Development Plan (2011 to 2016). The Plan proposes the strengthening the network of protected areas within three priority biodiversity corridors. The project will demonstrate how the network approach to PA system management can be demonstrated at the corridor level. The project is also aligned with the strategic priorities of the PBSAP 2015-2028, in particular the following: Under the theme of Conservation targets: Target 1. By 2028, the conservation status of nationally and globally threatened species in the country from 2016 levels is maintained or improved; Target 2. By 2028, there will be no net loss in natural forest cover; Under the Ecosystem services provided theme: Target 7. By 2028, as result of improved conservation, ecosystem services provided by key biodiversity areas will be enhanced; Under the Human wellbeing target theme: Target 9. By 2028, there will be an annual increase of at least 5% in biodiversity conservation related jobs (ecotourism, sustainable agriculture, ecosystem restoration); Under the Results related to reducing threats to biodiversity theme: Target 10. By 2028, the key threats to biodiversity will be reduced, controlled or managed; Under the Results related to addressing drivers of threats theme: Target 11. there will be a 10% increase in agricultural areas devoted to all types of biodiversity-friendly agriculture; Target 12. By 2028, capacity for biodiversity conservation of public and private sector groups in terrestrial and marine PAs/KBAs will be strengthened; Target 13. By 2028, 50% of LGUs will have formulated and adopted the enhanced Comprehensive Land Use Plan (CLUP) using revised HLURB framework; Target 14. By 2028, 1 million ha of degraded ecosystems will be restored and/or will be under various stages of restoration; Target 17. By 2020, relevant biodiversity conservation policies to address existing gaps are in place; Target 18. By 2028, there will be a 10% annual increase from the 2015 baseline in the number of schools, People’s Organization (POs), media organizations, LGU, private companies, policy makers, government offices that are aware and supportive of biodiversity, its importance, threats and benefits of protecting it; and Target 19. By 2028, there will be a 10% increase in total area from 2015 levels of terrestrial including inland wetlands PAs managed through NIPAS and other conservation measures (indigenous community conserved areas, local conservation areas, critical habitats) that overlap with KBAs.

- The Project will also contribute to the attainment of Sustainable Development Goal (SDG) Target 15: Life on Land (Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss). In the Philippines, forests are home to about 20 million people, including about 7 – 8 million indigenous people. Sustainable management of forests will help ensure equal access to resources, and bring about improved living conditions for these communities. More importantly, the Project will directly address the threats to sustainable forest management and help in delivering ecosystem benefits to affected population. A large portion of corridors are also devoted to agriculture, and subjected to all forms of degradation and unsustainable land management practices.  The Project will work with selected communities to influence their practices to reverse the current conditions. The net effect is the transformation of degraded lands into sustainably managed farms to support increased yields and higher farmer incomes. Finally, arresting the threats to biodiversity loss would be a direct outcome of the Project, through its work  in  tackling  the  institutional  and  policy  constraints  that  impact  on fragmentation and degradation of habitats; as well as practices that encourage unsustainable use of biodiversity resources. The impact of the Project would be felt by communities and resource managers living within and around the biodiversity corridors contributing to the attainment of SDG 1: End poverty in all its forms everywhere.

Baseline Scenario and Associated Baseline Projects

- There have been a number of initiatives to upscale the level of biodiversity planning,  management  and monitoring; as well as mainstream biodiversity considerations into the broader production landscape. For many years, the National Convergence Initiative (NCI) has brought 4 agencies [i.e. DENR, DA, Department of Agrarian Reform (DAR) and Department of Interior and Local Government (DILG)] to pilot collaborative delivery of services on targeted, usually watershed-based landscapes. At the same time several inter- LGU programs exist that aim to manage ecosystems especially watersheds and coastal areas.  A proposal has been put forward to DENR to adopt the integrated ecosystems management approach that is, to consider the wide array of tenure instruments and public land managers (de facto and formally recognized) and ensure every inch of land within the major watershed or landscape is allocated to a manager – whether it be an individual, family, organization, community, or government institution such as a local government unit (LGU) or agency. It also provides for a process that brings sectors and stakeholders together to “jointly plan, design, and manage their landscapes and institutional resources for improved agricultural production, biodiversity and ecosystem conservation and sustainable livelihoods.” This proposal is still under review and could form the basis for a sharper but more inclusive expanded definition of the integrated approach in biodiversity corridors, or other well-defined landscapes, such as river basins, island ecosystems, or watersheds.  The current government is designing a program the builds on the area-based management approach, to achieve coherence in implementation of environment and natural resources (ENR) programs through integrated resource assessments, planning, budgeting and implementation among DENR programs, and between DENR and other agencies. Both the Integrated Ecosystem Management (IEM) and areas-based approach initiatives can help provide the compelling case to adopt the Biodiversity Corridor as one of the ways by which such approach can be operationalized to provide multiple local, national, and global benefits.

- The Biodiversity Management Bureau (BMB) is pursuing the preparation of the PA System Master Plan that seeks to improve the design of the Philippines PA system, i.e. ensure greater cohesion and ecological representativeness, and strengthen its links with the surrounding landscape and to improve the capacity to manage protected areas. A number of donors are also active in the sector. The United States Agency for International Development (USAID), through its Project  –  Biodiversity  and  Watersheds  Improved  for  Stronger Economy and Ecosystem Resilience (BWISER), is operating in seven protected areas  such as Lake Naujan in Mindoro, to improve the management effectiveness. Two other projects – the Asian Development Bank (ADB) supported Integrated Natural Resources Environment Project (INREMP), as well as the Japan International Cooperation Agency (JICA) assisted Forestland Management Project, are implemented using the ridge to reef and ecosystem-based approach, covering seven river basins. The BMU-GIZ is designing a program covering two major river basins that will adopt the integrated ecosystems management approach. The baseline project consists mainly of DENR’s programs as described below.

- Expansion and diversification of Protected Area system: The Philippines recently enacted the Expanded National Integrated Protected Areas System (NIPAS) law that expanded the number of protected areas (PAs) formally gazetted. Through the on-going National PA System Master Planning exercise that is currently ongoing, the government is rationalizing   the   expansion   of   the   existing   PA   system   to   improve   coherence   and   complementarity, representativeness, and connection with the broader landscape. Following the experience and lessons from a recently concluded UNDP-GEF NewCAPP project, and the on-going UNDP GEF ICCA project, the PA System master Planning will include recognition of other area-based conservation measures (OECMs) such as indigenous community conserved areas (ICCAs) and local conservation areas (LCAs) managed by local government units (LGUs).

- Moratorium on cutting and harvesting naturally growing trees in the natural and residual forests: This is made possible by the Executive Order (EO) of 23 February 2011. Through this EO, the DENR was able to reduce illegal logging hotspot areas from 197 municipalities in 2010 to 13, or a reduction by 93%. To strengthen the program, there is a National Forest Protection Program wherein a total of USD 106.8 Million were invested over the  period  2011-2016  to  protect  the remaining natural forests,  thus contributing to biodiversity enhancement in the process. The DENR, is working with local governments to strengthen the Multi-sectoral Forest Protection Committees, to improve monitoring of forest protection using an IT assisted approach called LAWIN which is being piloted under the DENR - USAID BWISER Project. Related concerns are 143 such watersheds that support irrigation and power facilities, many of which were identified as initial components of the National Integrated Protected Areas System (NIPAS). Management plans, including vulnerability assessment, have been prepared for 106 watersheds.

- National Greening Program: As of 2015, a total of 1.35 million hectares of open, denuded, and degraded forestlands, including protected areas and mangroves, have been planted under the program involving USD 706 Million. Through Executive Order 193, the program has been expanded to 2016-2028 to support implementation of the Updated Philippine Forestry Master Plan.  Based on the DENR budget for 2018, the Enhanced National Greening Program gets USD equivalent of 0.12 billion, to plant some 198 million seedlings in 210,852 hectares.

- Mainstreaming Biodiversity Friendly Agriculture. The Philippines updated its National Action Plan to combat Desertification, Land Degradation and Drought (NAP-DLDD) in 2015.  To support the NAP DLDD and global Land Degradation Neutrality (LDN) commitments the Philippines is addressing 11.13 million ha of degraded lands by 2030, and is integrating voluntary LDN targets into the national action plan (NAP) for key UN Conventions  and national development strategies, particularly in the agriculture and natural resources management sectors. At the same time, the DA and DENR, with support of the recently completed UNDP GEF Biodiversity Partnerships Project (BPP) are currently finalizing a joint policy framework for biodiversity friendly agriculture initially for protected areas. This targets LGU agricultural extension systems in these areas.  The Department of Agriculture is also updating its Agriculture Fishery and Modernization Plan (AFMA) for 2017 – 2023.  Opportunities for incorporating biodiversity biological corridor concerns can be tapped during the midterm review of AFMA in 2020.

- People Oriented Forestry Program. Per Executive Order 318, the Community Based Forest Management Program was institutionalized to support long-term agreements with organized forest communities. Plans are in train, with support from the ASEAN Forest Cooperation Agreement, to update the community plans using remote sensing technology. A draft Memorandum Circular has also been prepared to provide to update the engagement of private sector investments in community forest management.  On the other hand, the Corporate Forestry Program involves engagement of corporations through the Industrial Forest Management Agreements (IFMA) and Socialized Industrial Forest Management Agreements (SIFMA). Most of the legal sourced raw material requirements of the wood industry come from these areas. There are moves to use the forest criteria and indicators system to review the program.

- Biodiversity friendly enterprises:  The DENR and the Department of Tourism currently collaborate to support initiatives in PAs to establish community-based ecotourism enterprises in support of PA plans. At the same the DENR and the Department of Trade and industry (DTI) have agreed on a policy framework for and pilots in criteria based and value chain-oriented community biodiversity friendly enterprises.

- Mining audits.  More recently, the government has taken bold steps to undertake mining audits to determine compliance to environmental laws. To date, the DENR has issued suspension orders to five mining companies operating in Mindanao. This campaign is foreseen to intensify in the near future as mining audits continue; with stated priority given to biodiversity conservation and environmental protection over unsustainable mining operations.

- Environment and Natural Resources oriented land use at LGU level Because traditional comprehensive land use planning (CLUPs) do not provide details about forest land allocation, the DENR is developing capacities of local governments to develop their   forest land use plans or FLUPS (protecting and production) as part of to the LGUs’ planning processes. A total of 442 municipalities have completed their FLUPs, with plans to finish the remaining 982 municipalities by 2018. In addition, two other projects – the ADB supported Integrated Natural Resources Environment Project (INREMP), as well as the JICA assisted Forestland Management Project covers seven river basins. Under the GEF UNDP Biodiversity Partnership Project, DENR collaborated with the Housing and Land Use Regulatory Board or HLURB to assist mainstream biodiversity in CLUPs of pilot LGUs and have issued supplemental guidelines for mainstreaming biodiversity in CLUPS.  Some of the pilots are in Eastern Mindanao Biodiversity Corridor. In 2018, the Supreme Court clarified the definition of automatic share of internal revenues for LGUs by broadening its financial base and increasing it by up to 40% of the current receivables. This could enhance LGU capacity for enforcement of its Environment and Natural Resources plans.

Figure 1: Threats, root causes and barriers to the long-term solution and GEF strategies to address them

# Strategy

- The long-term goal of the project is to establish a comprehensive and integrated planning and management framework to mainstream land and natural resource management and biodiversity conservation objectives into sub-national and sector socio-economic development and community resource management within key biodiversity corridors in the Philippines. Its objective is to operationalize integrated management of biodiversity corridors to generate multiple benefits including effective conservation of globally threathened species and high conservation value forests, reduce deforestration and degradation and enhance local biodiversity-friendly livelihoods. The project recognizes that these biodiversity corridors underpin the lives and livelihoods of a large number of local communities and that implementation of such an integrated strategy is an integral part of achieving a balanced approach to development and community resource use that conserves biodiversity. To achieve this objective, the GEF alternative aims to (i) take into account the interconnectivity of various ecosystems in the biodiversity corridors and their impacts on biodiversity, ecological processes and functions of sector development and local community activities; (ii) ensure that relevant agencies and actors have adequate capacities to promote integrated approaches and tackle the threat to biodiversity and effective natural resources management; and (c) advocate science based approaches and use of indigenous knowledge systems and practices to restore degraded areas while promoting sustainable forestry, agricultural and livelihood practices. The project will be implemented over a 6-year period based on the following principles:

- Promoting a holistic, multi-sectoral and integrated ecosystem management (IEM) approach to resource governance as compared to the exclusive protected area centric approach to facilitate the maintenance of the ecological integrity of the biodiversity corridors and its constituent parts;

- Supporting and implementing a participatory/consultative bottom-up planning and implementation approach that focuses on provincial, municipal and local community priorities and decisions that integrate conservation, sustainable resource use, climate risk management and livelihood outcomes;

- Strengthening the role of communities (including indigenous communities), local provincial, regional and municipal government institutions, community-based organizations and non-governmental organizations and increasing their potential for becoming agents of change in promoting sustainable natural resource management, climate risk management and biodiversity conservation;

- Strengthening capacities of communities and private sector for implementing effective biodiversity-friendly income generation and livelihood activities;

- Ensuring that in its development and implementation, gender is mainstreamed so that the project contributes to equality and equity, through the creation of equitable opportunities and benefits for both women and men

- Ensuring an adaptive management approach that progressively identifies and addresses threats to biodiversity and natural resources and associated challenges, including those related to ecological, demographical, climatic, market, technological and economic factors in the biological corridors;

- Ensuring free prior and informed consent (FPIC) patterned after National Commission of Indigenous Peoples Administrative Order No 1 or the FPIC Guidelines of 2006 as the basis for negotiating investments for local communities, including in particular, indigenous communities, and ensuring that any displacement of incomes or access to resources are adequately compensated through alternative livelihood improvement plans;

- Being selective in terms of identification of locations and nature of interventions to serve as demonstration models in the biodiversity corridors and in addressing the nature of challenges that operate therein taking into considerations the existing institutional capacity and resource constraints; and

- Improving awareness and knowledge and strengthening gender mainstreaming and monitoring and evaluation as means to improve conservation impacts.

- In order to ensure a clear, practical and cohesive implementation strategy, the proposed project will introduce a structured planning and integrated framework for managing biodiversity corridors in the Philippines. This framework will engender a two-pronged, mutually re-enforcing approach of (i) strengthening efforts for conservation of biodiversity in large landscapes/seascapes (biodiversity corridors), and (ii) demonstrating sustainable economic and livelihood initiatives for tackling reduction of pressures and threats to biodiversity while strengthening benefits to local communities. Targeted activities under both directional focuses will be implemented under a linked national and sub-national level coordinated planning and management umbrella platform, supported by updated legal-regulatory documents and planning guidelines as well as the strengthened corridor-level planning and management mechanisms. Through this approach, on-the-ground initiatives in biodiversity corridors will both be guided by, and provide feedback loops into, enabling policy, institutional and regulatory initiatives at the national level, while linking conservation-oriented actions with socio-economic, sectoral and livelihood-focused actions at the biodiversity corridor level.

- In order to ensure investment activities (Components 2 and 3) in the project biodiversity corridors are strategically located to demonstrate tangible impacts and outcomes and avoid the ineffective spread of activities, the project will attempt to locate a suitable mix of project investments in selected target clusters of high conservation value areas within the biodiversity corridors, where tangible impacts on biodiversity conservation and threat reduction can be demonstrated. The selection of target cluster areas is based on specific criteria that will help determine areas that are most biologically significant for conservation and threat reduction and thus serve to ensure the long-term maintenance of the biological and ecological integrity of the biodiversity corridor itself. Consequently, the key biodiversity areas (KBAs) within the corridor will form the backbone of defining the strategic target cluster areas for demonstration of investments and achievement of conservation outcomes.  Each target cluster will encompass KBAs [existing PAs, new Indigenous People’s Conservation Areas (ICCAs), Local Government Conservation Areas (LCAs), privately owned conservation estates and Indigenous People’s Ancestral domains] and areas adjacent to the KBAs that are necessary to provide critical conservation linkages necessary to maintain ecological integrity and species dispersal within the system of KBAs.  The strategy of using biodiversity rich clusters as the basis for demonstrating project on-the-ground investments is based on the premise that conservation of biodiversity within the clusters and maintenance of critical species and ecosystem linkages will to a large extent help ensure the maintenance of the viability and vitality of the entire (overall) corridor itself.  Using this strategy as the basis for project interventions will necessitate that all PA/OECM-related, SLM, SFM, sustainable livelihood and community and private sector related bio-friendly business solutions are developed and implemented within the target clusters themselves rather than be diffused throughout the corridor given the constraints of GEF resources, institutional capacity and timeframe of the project.   This is reflected in a number of Outputs with the intent of showing that the range of project SLM, SFM, livelihood, biodiversity-friendly business and PA-related investments are to be identified and implemented in an integrated fashion, rather be implemented independent of each other.

- A three-tiered evaluation process (see Annex 6) has been employed to facilitate the identification of the biodiversity rich clusters within the biodiversity corridors, ensure connectivity between fragmented habitats and improve the viability of species, by enlarging habitats, ensuring dispersal of young animals and the re-occupation of “disturbed” habitats.  The first tier entails the use of biological criteria to identify the best “umbrella” sites, namely those sites that are representative of a suite of vulnerable species and habitats (based on species irreplaceability, habitat connectivity, ecological permanence and having representative bio-indicators). Once these important biological sites are identified, these were subjected to a second-tier evaluation in terms of threats where historical and future trends of land-use changes, land use conflicts) and drivers of degradation and predicted response of biodiversity to these trends are assessed.  The third tier involves the assessment of the demonstration potential of the proposed sites in terms of resource use conflict reduction, enabling policy environment and potential trade-offs.

- The project objective is to be achieved through the implementation of four inter-related and mutually complementary Components that are focussed at addressing the barriers discussed in the previous section of this report and represented in Figure 1. The three Components of the project are:

- Component 1: Effective coordination and governance framework for integrated ecosystem management in the Philippines biodiversity corridors system;

- Component 2: Application of integrated network design and management of biodiversity corridors to ensure continued stability and sustainability of their biological, ecosystem services and socio-economic conservation values;

- Component 3: Community-based sustainable use and management systems in the two pilot biodiversity corridor system in the Philippines; and

- Component 4: Knowledge management, gender mainstreaming and monitoring and evaluation

- The project strategy was approved by national and provincial-level stakeholders at well-attended validation workshops (see Table 4).

- To achieve this objective the project will utilize 4 strategies (Project Components) with intervention pathways described in the theory of change diagram in Figure 2 below. The Components (as the GEF project alternative) aims to remove the barriers to accomplishing the long-term solution (see Fig. 1).  The details of the suggested Theory of Change are shown in Figure 2.

Figure 2:  Theory of Change

Project Areas:

- The two project biodiversity corridors have been chosen mainly because of their critical importance as centers of endemism and biodiversity hotspot and economic significance. Other criteria include poverty incidence, vulnerability, extent of extractive industries and/or extent of land use conversion and infrastructure development and land degradation. The selection was made following an evaluation of all biological corridors in the country and determination of their biological importance, threat level and potential for demonstration of integrated approaches. A series of technical discussions were also held during the PPG stage to confirm the selection of the two priority candidate corridors to be included in the Project.

- The two biodiversity corridors selected below represent distinct biodiversity characteristics and forest formations, located in different biogeographic zones. Each site offers different sets of challenges for integrated biodiversity management, due to the nature and degree of threats they are exposed to. These are discussed in more detail below. A total of 16 KBAs are located in the two biodiversity corridors, with a total area of 1.026 Million hectares. The two corridors host 185,046 hectares of old growth forests and 657,214 hectares of open forests. Figures 3 and 4 provide maps of the two corridors and Table 1 of geographic, biological and socio-economic features of the two corridors. In addition, Annex 2 provides a profile of the two biodiversity corridors and additional maps are found in Annex 6.

Figure 3: Maps of Project Areas

Table 1: Geographical, Biological and Socio-economic Features of Pilot Biodiversity Corridors

| Geographic and Biological Features of biodiversity corridors | Socio-Economic Features of Biodiversity Corridors |
| --- | --- |
| Central Mindoro Biodiversity Corridor |  |
| Total Land Area: 436,470 hectares Vegetation types on Mindoro include lowland evergreen rain forest to approximately 400 m or higher, open forest from about 650 to 1,000 m, and mossy forest above. Only small patches remain of the lowland evergreen dipterocarp rain forest that would have dominated the lowland eastern portions of the island. Semi-deciduous forest would have predominated on the western half of the island. Limited stands of Mindoro pine (Pinus merkusii) are found at elevations of 600 m or less in the northern portions of the island. Because of its geological history, the island has evolved as a unique center of biodiversity, with very high endemism. Recent assessments have documented 94 species of hepetofauna; 10 restricted range bird species, of which five are concurrently globally threatened and endemic; at least 70 endemic species of flora unique to Mindoro island; at least 17 endemic species and taxa out of a total 50 species/sub species of butterflies; at least 10 endemic species of mammals, of which six are threatened while four await formal description; more than 300 species of birds, one quarter of which are endemic to the Philippines. Among the other important mammals found in Mindoro include the tamaraw (Bubalus mindorensis) and Philippine warty pig (Sus philippensis), which is considered by IUCN as rare and declining. Also found are endemic subspecies of the Philippine deer (Cervus mariannus barandanus) found only in Mindoro; the critically endangered Illin hairy-tailed cloud rat (Crateromys paulus), the endangered Mindoro shrew (Crocidura mindorus) and the more Philippine widespread but endangered golden-crowned fruit bat (Acerodon jubatus). The island of Mindoro is composed of a mosaic of landscapes and ecosystems – grasslands, disturbed lowland forests, agricultural areas, high elevation pine forests, freshwater lake, extensive river systems and watersheds – all supporting the socio economic and cultural development of the island. Unfortunately, Mindoro is one of the most severely deforested islands in the country. Only the most rugged portions of the island's central spine have been spared from commercial logging, and the forest is still under pressure. In 2010, only 30% of the island’s forest lands have forest cover; of which only 4% is closed forest. Some 180,000 hectares are open, highly fragmented; while the rest of the forest lands have been converted to agriculture and other uses. The rapid decline in population of Mindoro hornbill (Penelopides mindorensis) for example, has been attributed to forest loss, fragmentation, and degradation of lowland forests; compounded by hunting pressure | ###### Occidental Mindoro - Major producer of agricultural products and fishery and aquaculture products such as tuna, milkfish, and tiger prawns - Region’s top producer of corn - Region’s top producer of onion - Top producer of salt in the region, which supplies neighboring provinces of Southern Luzon, Visayas, Mindanao and Metro Manila from its production of iodized and non-iodized salt - Tourism attraction, which offers cultural/historic heritages, fine sandy beaches, coral reefs, mangrove forests and nature sports and recreational sites New Emerging Industries - Agribusiness (tuna, picked fruits and vegetables, aquamarine processing, salt industry, seaweeds, pastillas, handicrafts) Oriental Mindoro - Gateway for trade and investments in the eastern side of the country - One of the premier tourism destinations in the country: Puerto Galera as “One of the Most Beautiful Bays in the World,” declared in 2005 by the Most Beautiful Bays in the World Club, a French-based organization supported by UNESCO, Naujan Lake as one of the Ramsar’s Wetland of International Importance declared in November 1999 - Food basket for Luzon and Visayas Regions, providing a reliable stable supply of agri-based, aquaculture, marine products and livestock to CALABARZON, National Capital Region, and provinces of Aklan, Iloilo, Capiz, Guimaras, Negros Oriental and Antique - Region and country’s top producer of calamansi - Region’s top producer of banana - Region’s top producer of palay - Agri-business (babana chips; rice-based delicacies; calamansi purees and concentrates; virgin coconut oil; bamboo-based products; lamayo, dried biya and seaweeds; handicrafts and novelties; and crafts from abaca, buri and cogon) The island of Mindoro is a host to Mangyan indigenous peoples, which is composed of the following eight sub-tribes: Iraya, Alangan, Tadyawan, Tau-buid, Bangon, Bhuid, Hanunuo, and Ratagnon. Each sub IP group has its own language, set of customs, and way of life. Mangyans practice swidden farming and the most well documented practice is amongst Hanunuo. Their swidden farming is different from the "kaingin" system practiced by non-Mangyans, which is often very destructive when it is done with no proper safeguards to prevent the fire from spreading to the surrounding vegetation. A fallow period is also observed so that the swidden farm will revert back to forest. The Mangyans managed their swidden farms skillfully (Conklin, 1953). Recent study on Hanunuo’s swidden farming revealed that such practice has prevented land deterioration in spite of the fact that forest land degradation is now evident in their territory due to various factors such as pressures on land from migrants occupying the fringes of their domains (Atsuko, 1995). Fuelwood gathering is also on the rise, the key factor behind forest degradation. |
| Eastern Mindanao Biodiversity Corridor |  |
| The Eastern Mindanao Biodiversity Corridor (EMBC) is a long stretch of lowland and mid - to high elevation forests along the east coast of Mindanao. Dinagat Island marks its northernmost boundary while Mt. Hamiguitan Range is at its southern tip. Region 11 and Region 13 (Caraga), in seven provinces, four cities and 88 municipalities. The corridor hosts a large proportion of the country's unique plants and animals. At least 370 species of forest vertebrates (i.e. birds, mammals, amphibians and reptiles) are currently known. Out of these, nearly half (181 species) are found only in the country. The corridor's plant diversity is also very high, with more than 2,300 species known there (31% of the total species known for the Philippines). Among vertebrates, the EMBC has at least 196 species of birds and 91 (or 46 %) of them are endemic, which is more than half (51 %) of the country's total endemic birds. For mammals, at least 66 species (27 non-flying mammals and 39 bats) are known, and almost half of these (31 species) are endemic. The figure includes two new species of rodents, a new species of fruit bat, and a probable new species of insect-eating bat. The corridor also houses at least 31 amphibians (frogs and caecilians), 16 of which are endemic. There are also at least 77 species of reptiles (snakes, turtles, and lizards) and more than half of these (43 species) are endemic. The eastern portion of Mindanao, where the corridor is located, holds one of the largest remaining blocks of dipterocarp forest in the country. In fact, this region is called the timber corridor, because of the favorable climatic condition that enables the growing of forest tree plantations highly profitable. Both regions have a very active timber industry, which host 33 industrial forest management agreements (IFMAs) covering almost 400,000 hectares. These regions supply most of the country’s wood requirements, with active sawmills having combined annual log requirement comprising almost 60% of the country’s total. | The region is noted for its wood-based economy, its extensive water resources and its rich mineral deposits such as iron, gold, silver, nickel, chromite, manganese and copper. Its leading crops are palay, banana and coconut. The region features several beaches, abundant seafood, hot and cold springs, evergreen forests and balmy weather. (Source: https://www.dti.gov.ph/64-main-content/caraga-article/9826-caraga-regional-profile The primary source of income in Eastern Mindanao biodiversity corridor is agriculture, followed by forestry, fishing, and mining, albeit the thriving commercial trade and services in towns and cities also provide employment. The indigenous people are known for their traditional ‘slash-and-burn’ or swidden farming, which was originally sound and sustainable when the population was smaller. Multiple cropping is also practiced throughout the year, although mono-cropping of corn and banana is still commonly practiced. The average farm size ranges from 1 to 5 hectares, and production is primarily for subsistence only. Some SLM practices adopted by farmers include contour farming, agroforestry, and organic farming particularly for cacao and coffee. Upland farmers, including IPs are also involved in forest farming, and maintain fruit orchards and small plantations of abaca and coffee, and high-value vegetables. The region is the country’s timber corridor due to its dominant timber industry. Farmers managing community-based forests harvest logs to jumpstart community-based enterprises. Bamboo production also provides income, as well as NTFPs e.g., rattan, nipa palms and nito fern, which are used as raw materials for handicrafts and thatched roofing. Hunting wild pig, deer, monkeys, palm civets, large rats, monitor lizards, and medium to large birds for food continue, while backyard livestock raising such as for pig and chicken provides supplemental income. The corridor offers scenic landscapes, unique life forms and water bodies that are being developed for eco-tourism. There are 182 community-based forest management agreements (CBFMAs) – long term tenure instruments given to organized forest communities, covering 306,366 hectares, involving approximately 150,000 households. Private land owners are also engaged in timber production, as well as growing of long term and other high value crops. There is an active corporate sector involved in large plantations such as oil palm, rubber, and other high value crops. Based on the EMBC Conservation Framework which was prepared in 2008, the major threats to the corridor’s biodiversity include: rapid population growth in the uplands; illegal logging (the region is classified as a hotspot); forest conversion to agriculture; land use conversion and crop shifting; wildlife hunting and collection for food and trade; and irresponsible mining. |

# Results and Partnerships

- Expected Results:

- Long-term solution:  The project is designed to achieve long-term environmental impacts of reduction of direct threats on critical species, ecosystems and biodiversity.  This will be achieved through establishing the following institutional and regulatory measures for integrating biodiversity conservation and sustainable natural resource use into sector specific and sub-national socio-economic development planning and community resource management of biodiversity corridors:

- A national policy, regulatory and governance framework for planning, managing, compliance, monitoring, enforcement and decision-making for integrated ecosystem management process and utilized for biodiversity corridor;

- Improved site-level planning, regulatory, monitoring and implementation framework for demonstration of integrated ecosystem planning and management of pilot biodiversity corridors;

- Improved site-level sustainable use and management systems for rich ecosystems and sustainable community and private sector use through biodiversity friendly, sustainable land and forest management, and sustainable and better targeted community livelihood investments and business ventures; and

- Improved awareness and knowledge on biodiversity conservation and its threats that encourage support and commitment from policy makers, planners and local communities to conservation.

- The Project Objective is to operationalize an integrated ecosystem management of biodiversity corridors to generate multiple benefits including effective conservation of globally significant biodiversity, reduced deforestation and degradation and enhanced community livelihoods. To achieve this ojective, the project is designed to develop and test a holistic and well-integrated multi-sectoral and multi-stakeholder approach to planning and management within the pilot biodiversity corridors.  This is underpinned by mechanism(s) that address current limitations in multi-stakeholder and sub-national integrated development planning and coordination between key stakeholders within the corridors, and improved local community and indigenous people’s access and control of resource use to generate improved livelihoods, incomes and benefits.

- The project’s incremental value lies in demonstrating the development of participatory natural resources management, enterprise based sustainable natural resource practices and sustainable livelihoods for local communities in the selected biodiversity corridors. This approach will concurrently strengthen the conservation of biodiversity, rehabilitate degraded agricultural and forest lands, maintain the connectivity and ecosystem values of these biodiversity corridors, and ameliorate climate change impacts. A biodiversity corridor Information Management System and maps will be developed for each of these target corridors which will provide the following: (i) land use in biodiversity corridors using existing information; (ii) areas of high biodiversity conservation significance, (iii) spatial tools on land and forest degradation and Invasive Alien Species (IAS), and (iv) data needed to support planning for ensuring sustainable agriculture and forestry, sustainable tourism development, and land rehabilitation and improvement, climate change adaptation, and community sustainable resource use. The information system will allow for defining which ecosystems can be sustainably used and which should be conserved in order to retain critical biodiversity, habitat and ecosystem integrity and ensure productivity of agriculture, forestry, sustainable resource use and tourism in the long term. It will also help develop capacities and required enabling frameworks through "learning-by-doing" approaches in the selected target biodiversity corridors. Sustainable biodiversity corridor management approaches will be based on assessments of key biodiversity and ecosystem services and will build on capacities and concepts established during the interventions of the past GEF and donor projects in Philippines, as well as similar initiatives elsewhere. The project will be able to develop and demonstrate a matrix of best practices for Philippine ecosystems and biodiversity conservation for scaling up and replication in other biodiversity corridors nationally and regionally. A series of knowledge management publications and awareness events will support the achievement of these targets.

Component 1: Effective coordination and governance framework for integrated ecosystem management of Philippines biodiversity corridors system

Total Cost: US$13,845,178; GEF project grant requested: $1,283,653; Co-financing: US$12,561,525

Outcome 1: Effective policy, coordination, regulatory and institutional framework for planning, management, compliance monitoring, enforcement and decision making for integrated management of biodiversity corridors developed

Baseline conditions for this outcome (without GEF project):

- At systematic level, Philippine’s Wildlife Protection and Protected Areas laws that provide regulations on biodiversity conservation will continue with limited guidance on (i) applying integrated ecosystem management approaches at the landscape or corridor level, (iii) developing policy instruments to enhance biodiversity outcomes in sectoral and national and local development planning; and (iii) ensuring effective monitoring and compliance of existing laws. The importance of biodiversity corridor systems (including KBAs) will remain unclear resulting in these corridors being managed less effectively, and threats to biodiversity will be poorly controlled. Institutionally, The Biodiversity Management Bureau (BMB) within DENR is the focal agency for overall biodiversity conservation, but its staff have limited capacity for implementation of comprehensive integrated ecosystem management approaches at a PA, OECM and corridor levels.  Further, within DENR there will continue to be a lack of synergy among the policies and programs of the different Bureaus that translate into uncoordinated implementation of activities within biodiversity corridors/landscapes. Therefore, responsibilities and institutional arrangements at national and sub-national levels to manage biodiversity corridors will continue to remain uncertain. Without GEF financing, the DENR and other national and sub-national coordination mechanisms which has limited sector agency representation, will not be able to guarantee: (i) an effective multi-level integration between national and sub-national governments in terms of biodiversity corridor planning and management, (ii) an effective consultation between different institutional levels and sectors at the national or sub-national level in support of biodiversity conservation, (iii) an effective integration of biodiversity conservation targets and outcomes in provincial, regional and municipal social and economic development planning; (vi) an effective means to integrate Indigenous People’s knowledge and traditional resource management systems into biodiversity corridor management, nor (v) an expanded national-level coordination membership and procedures to include sub-national and sector representation and better use of technical expertise to implement national policies.

- Consequently, without the GEF Project, there will continue to be an incomplete institutional framework on biodiversity corridors at the national and sub-national levels for mainstreaming natural resource management, as well as biodiversity and critical ecosystems conservation objectives into socio-economic development planning and biodiversity corridor management.  Development will continue to be dominated by single sector-based interventions that lack a more holistic vision and approach.  As a consequence, private and public sector development would continue without a clear policy or regulations on biological and natural resources use within the corridors. Currently most relationships between resource owners and private sector resource developers will remain weak, informal or ad hoc, despite the fact that there are numerous groups and processes in place to facilitate joint planning and implementation to achieve biodiversity goals. Planning process are likely to ignore issues at corridor level and as a consequence the downhill trend of degradation of natural systems will continue unabated, which will further increase fragmentation of natural systems with the biological corridors.

Alternative for this outcome (with GEF project):

- Under this Outcome, the GEF increment will support strengthening coordination, governance and regulatory arrangements for mainstreaming natural resource management and biodiversity conservation objectives into sub-national level development planning in biodiversity corridors in the Philippines.  This will include establishing an institutional coordination framework for IEM management in biological corridors to facilitate information sharing, engagement, consultation, planning and mobilization on the strategies and decision-making tools. The national coordination mechanism will provide leadership where mandated by various existing laws and agreements or where existing capacities exist to enhance support to sub-national governments on the issues relevant to biodiversity corridors. Guidelines, plans and best practices for mainstreaming biodiversity concerns in development planning will be formulated for agriculture, forestry, extractive industry among others, including a set of minimum standards, to guide responsible practices in these sectors while providing a concrete strategy and resource mobilization plan for their sustainable development to enhance economic sectors in Philippines. These plans will build on and integrate relevant and existing tools, strategies and lessons gained through the baseline work. These tools will also be used to provide a stronger regulatory, monitoring and enforcement framework to avoid, reduce and mitigate adverse impacts of these sectors on biodiversity, and emphasis will specifically be placed on maintaining the ecological integrity of the biodiversity corridors, in particular, in PAs and KBAs. At the same time, the project will strengthen the capacity of environmental authorities to develop new, improve existing and implement regulations and practices, such as Environment Impact assessment (EIA) and Strategic Environment Assessment (SEA) guidelines to be specifically adopted for management of impacts on biodiversity and ecosystems in development activities within and outside of the biodiversity corridors. The outcome would be a national coordination and governance structure that promotes an IEM approach within the corridors.  This approach takes into cognizance sustainable resource management, biodiversity conservation and biodiversity-friendly socio-economic planning and enforcement, climate change as well as strengthened relevant capacity and skills within key national agencies, notably DENR, DA and NCIP, as well as Local Governments and support the ability to balance development and environmental needs at the biodiversity corridor level.

- This Outcome would be achieved through three outputs, which will contribute to achieving the overall goal of developing national frameworks for integrated ecosystem-based planning, management and enforcement in Philippines to conserve biodiversity and in establishing capacity for planning, implementation and monitoring of conservation outcomes and threats. Annex 3 provides a discussion of the objectives and outcomes, and step-by-step guide to the design and implementation of IEM framework for biodiversity corridors in the Philippines.

Output 1.1: Functional governance and coordination mechanism established at national level to facilitate integrated ecosystem planning and management of Biodiversity Corridors

- The Project will develop and demonstrate a planning and coordination processes that can be embedded in current land use and socio-economic development planning structure and processes at both national and sub-national levels for enabling effective governance of the nineteen biodiversity corridors in the Philippines. Output 1.1 will recommend a inter agency planning and coordination platform at the national level to oversee the nineteen biodiversity corridors based on the experience of the managing two pilot corridors (described in Outcome 2). The national platform to be developed will ensure relevant national sector representation to facilitate engagement, transparency and coordination among key decision-makers, sectors and stakeholders towards strengthening capacities and institutional arrangements for planning and management of biodiversity corridors. The Project will ensure that sectors beyond the perceived traditional ambit of the biodiversity (extractive industries, tourism, agriculture, etc.) are meaningfully involved in this institutional structure. It will lead advocacy efforts and provide science-based policy advice for biodiversity integration in sector and local-level planning and define roles and responsibilities of different stakeholders in management of biodiversity corridors.  A key design feature of the platform is to avoid creating unsustainable structures.  The Project will undertake the following actions that will lead to the adoption of such national platform to:

- Creation of national technical working group (TWG) on biodiversity corridors to serve as interim forum for national dialogue as well as provide interim cross-sectoral advice for the integration of biodiversity corridor concerns in planning and coordination processes;

- Support ongoing DENR efforts to strengthen cross-sectoral planning functions within the agency to enable more effective technical guidance for project implementation; advocacy strategy for creation of awareness and support for integrated biodiversity management;

- Support Government decision  for the installation of a sustainable National and Sub-National Planning and Coordination mechanisms for strengthening the integration of biodiversity and gender safeguards within sector planning, regional development investment planning, provincial physical framework planning, municipal LGU comprehensive land use planning, indigenous conservation management planning, extractive industry planning, etc. This mechanism will define the roles and responsibilities for resource management by the different stakeholders, institutional structures and operational modalities for management of individual biodiversity corridors. The government  decision will be made in consultation with the NBSAP Steering Committee, and also  build on the experience of the Project Board/Steering Committee.

- A relevant DENR Service Office will be strengthened to support the national coordination and governance mechanism with capacity development and operating support. DENR will define the national coordination mechanism’s decision-making criteria and operational and coordination functionality.

Output 1.2: Policy instruments (biodiversity and community safeguard standards and guidelines) for improving biodiversity outcomes within the biodiversity corridors developed and adopted

- In Output 1.2, the Project will work towards developing an overall framework for promoting integrated ecosystem management approaches in biodiversity corridors the Philippines. The GEF increment will support the following activities under this Output:

- Review of existing policy relating to sectoral and sub-national development planning to identify entry points, key gaps in promoting biodiversity friendly development with special emphasis on resource use planning in biodiversity corridors;

- Technical support to update and support sector policies and standards towards biodiversity-friendly agriculture, biodiversity sensitive extractive industries (including conservation estates) and biodiversity-friendly enterprise to mainstreaming biodiversity conservation considerations in development practices, and;

- Based on experience and best practices provide technical support to analyze and update rules and guidelines for implementation and incentivization of environment and natural resources (ENR) management as well as preparation of guidelines and performance standards for application in different land-use sub-sets of functions at local government level, as well as for ancestral domain planning processes.

Output 1.3:	Compliance monitoring and enforcement strategy developed and adopted to measure progress towards measuring agreed biodiversity outcomes, threat reduction, sustainable natural resources management, apprehension of violators and prosecutions

- Currently, there is no comprehensive and coordinated system for effective monitoring and compliance with existing laws across sectors or between national and sub-national governments. The DENR (and its Bureaus) and law enforcement agencies are tasked to enforce laws on protection of wildlife and wildlife resources, including those listed as endangered species. DENR also has an active Forest Protection Program. There are also monitoring and compliance mechanisms with respect to mining activities, and oversight on implementation of EIA conditions.  However, reporting differs across the DENR Bureaus, and across agencies. For example, the FMB, through the DENR Administrative Order (DAO) 2018-21 (Adoption of LAWIN Forest and Biodiversity System as a National Strategy for Forest and Biodiversity Protection in the Philippines) prescribes the use of LAWIN, an integrated science-based assessment, user-friendly and adopts an innovative technology developed for monitoring the status of the forest. DENR, through this DAO sees LAWIN as a tool to assist in environmental monitoring especially with respect to forest and biodiversity of high conservation value areas. The system is currently being used as the primary protection monitoring system by DENR. Meanwhile, BMB, through the DENR Technical Bulletin 2016-05 (Guidelines on Biodiversity Assessment and Monitoring System for Terrestrial Ecosystems) also lays down a science-based assessment and monitoring system for terrestrial biodiversity. This Technical Bulletin recognizes both LAWIN and Biodiversity Monitoring System (BMS). The purpose of the BMS is to ensure that information is captured and available to support decision making in protected areas in pursuit of effective biodiversity conservation and resource utilization. The current approach of manual (paper-based) capturing of the data therefore limits its use. FMB, through the Knowledge and Information System Section (KISS) has developed and adopted an enhanced Forestry Information System (eFIS). The e-FIS is a web-based database integrated forestry application system that provides efficient management of forest data. The data infrastructure of eFIS is developed so that it can provide and facilitate adequate data support for policy formulation and decision-making. It also features the integration of geographical information system that the digital maps of tenured areas, protection forest and production forest and other land use to determine the right forest management system and tenured instruments. As currently configured, eFIS can be a useful reference for the M&E during its development. For example, M&E data and indicators for monitoring the progress of this project can be imbedded in eFIS so that collection and monitoring of these data is mainstreamed in DENR, which has already adopted eFIS.

- Given all of these systems of data capture and management, it is imperative that these must draw on the same credible scientific data. At the highest level, the biodiversity monitoring outcomes must also be used to report against the Biodiversity Strategy and Action Plan for the Philippines (PBSAP). The data that is collected at site level must be aligned to these national objectives to ensure that the work is anchored in a policy-relevant context. Given the varied structure and capacity at the sub-national level, the project intends that feasible interventions be initially trialed, assessed, and improved in the pilot corridors (under Component 2) before scaling up more widely in the country. The project will review these existing national and sub-national systems for monitoring, surveillance and enforcement/compliance and then support cross-agency planning, training, technical assistance and capacity and skills improvements to monitor, detect and enforce laws. Based on the review, where needed the project will develop and improve legislation and enforcement systems for threatened biodiversity and ecosystems.

- The GEF increment will support the following key activities:

- Reviewing of existing biodiversity and threat monitoring methods and capacities across the relevant entities to assess data and information collection constraints and weaknesses and opportunities for improving data collection, verification, timely reporting and analysis;

- Supporting the improvement of data collection and analysis through development of mobile and software applications for data input and management;

- Improving server facilities at national level;

- Development of appropriate protocols/guidelines and enforceable standards for biodiversity and IAS and subsequent biosecurity measures for land, forest and seascape restoration;

- Forging of multi-partite agreements with key stakeholders for the adoption of shared monitoring platform; and

- Training in evidence collection, basic forensics, 	monitoring, surveillance and enforcement, in particular for protected species, resource extraction, and IAS control in the selected biological corridors.

Component 2: Application of network design and management of biological corridors to ensure continued stability and sustainability of their biological, ecosystem services and socio-economic conservation values.

Total Cost: US$24,164,993; GEF project grant requested: US$5,174,882; Co-financing: US$18,990,111

Outcome 2: Improved site-level planning, regulatory, monitoring and implementation framework for demonstration of integrated ecosystem planning and management of pilot biodiversity corridors

Baseline conditions for this outcome (without GEF project):

- While, around 2.4 million hectares of land are within the two biodiversity corridors, about 500,000 ha considered to be biologically important areas i.e. KBAs under nationally recognized PAs or Other Effective Area-based Conservation Measures (OECMs) will likely continue to be managed in isolation with little consideration of the extensive natural habitats beyond its boundaries and the threats that emanate from outside its boundaries. Consequently, protected areas, including KBAs will continue to remain as islands and threats from surrounding landscapes will likely continue to increase, undermining the conservation values of these KBAs and increase fragmentation of the corridor habitats.  Although, the potential role of indigenous people and local governments in directly supporting biodiversity conservation has been recognized, these areas would continue to be managed independent of their surrounding areas and thus lose the opportunity to contribute to ecological connectivity.  In addition, the immense potential for production systems in agriculture and extractive industries to incorporate standards based and measurable biodiversity-friendly practices may likely not be recognized. Designation of new other OECMs will come too late after heavy degradation of the habitats and there will be insufficient resources and capacity to properly manage the areas even after establishment. KBAs would continue to be inadequately managed to achieve no net loss to biodiversity and human well being.

- There are already efforts through the Biodiversity Partnership Project (BPP) to address habitat fragmentation brought about by inadequate policies, tools and capacities to encourage the participation of local government units (LGUs) in mainstreaming biodiversity conservation in local agricultural landscapes. However, while the BPP and other efforts for integration of biodiversity and ecosystem values in local planning, ensuring consistency of LGU CLUPs with (i) provincial physical framework plans and (ii) regional and river basin development plans; and that both adequately incorporate biodiversity level connectivity objectives will take place at a slow rate. This delay could lead to forest and natural resource degradation, with a concomitant loss of high conservation value forests and critical ecosystems within and outside of the traditional protected areas thereby affecting ecosystem functions and increased fragmentation of the biological habitats.

- In addition, sectoral and geo-political approaches that prevail in terms of land-use decision-making in forest and watershed planning will not incorporate KBAs and ecosystem, landscape considerations nor community forest management approaches.  National and sub-national policies and planning systems are likley to continue to pay less attention to support land use optimization to sustain resource resilience and facilitate operationalization of the KBAs and ecosystem services considerations. Enforcement capacities to ensure compliance with ecological standards in land use and reduction of high levels of trespassing in use of forests will remain weak.

Alternative for this outcome (with GEF project):

- Under this outcome, the GEF increment will support the extension and improved management of a network of areas under some form of protection within the two corridors, including in particular, (i) the improved management of 300,000 hectares of existing protected areas, and (ii) the establishment and recognition of OECMs to improve the protection and sustainable management of at least 200,000 hectares of KBAs that are currently outside of the PA system through Indigenous groups management and other co-management approaches. The project will provide an opportunity to monitor progress in implementation of METT (Management Effectiveness Tracking Tool) in order to evaluate the management effectiveness and efficiency of existing PAs through the coming years. Support will also be provided for capacity building and training of PA staff (within the two biodiversity corridors), community organizations and other relevant personnel to support effective PA management and operationalization, including for law enforcement. Existing KBAs will form the core of the cluster areas and will include land within the KBAs that need to be rehabilitated and sustainably managed to enhance connectivity and improve conservation outcomes. The project will also train and equip forest and wildlife managers (PA staff and community organizations) for implementing monitoring and enforcement systems to reduce violations and wildlife crime. Overall, the aim of this cross-training and co-involvement of PA staff and community organizations/local communities, largely through protected area community based management agreements (PACBRMA), ICCAs, LCAs and other co-management arrangements will improve efforts not only within PAs, but also coordination and integration of these efforts across the larger landscape (within the corridor and rehabilitation zones spanning both PA and non-PA regions).

- Following the development of IEM frameworks for the two corridors, the project will support mainstreaming of biodiversity conservation aspects in a limited number of regional development investment planning frameworks, provincial physical planning frameworks and municipal LGU comprehensive land use plans (CLUPs) through extensive community consultation and in cooperation with local organizations. Regional development investment plans are prepared by the National Economic Development Authority (NEDA) to document the pathways and drivers of inclusive sustainable development in an administrative region. These plans will, inter alia: (a) identify high biodiversity areas to receive higher protection status under the National Integrated Protected Areas System (NIPAS) Act and other means; (b) identify gaps and measures to enhance management effectiveness of PAs; and (c) prescribe appropriate land uses and management practices, and forest management measures in production landscapes thus avoiding, reducing and mitigating the impacts to biodiversity.  It is anticipated that, through the mainstreaming of IEM principles and SLM and SFM strategies in local and regional development planning mechanisms, there will be an increase in budget allocation and program prioritization in ecosystem stability.

- This outcome will be achieved through the following five outputs, which will contribute to achieving the overall goal of expansion and impoved management of biological habitats within the two biological corridors.

Output 2.1: Integrated ecosystem management framework developed and adopted for two biodiversity corridors

- Under this output, the Project will support the elaboration of multi-stakeholder and multi-sector integrated biodiversity management planning of the Central Mindoro and Eastern Mindanano Biodiversity Corridors.  The intent is to facilitate the mainstreaming of improved PA management, other effective conservation management measures (OECMs), sustainable land and forest management and convergence in provincial, regional, municipal and sector planning systems. The planning process will culminate in the elaboration, sharing and adoption of integrated approaches through a participatory process, involving key players (national and sub-national institutions, NGOs, civil society, Indigenous Peoples groups, local communities, private sector, etc.), under the supervision of the national and sub-national corridor-level governance and coordination mechanism discussed under Outputs 1.1 and 2.1. A step-by-step guide to the design and implementation of IEM framework for biodiversity corridors in the Philippines corridors is provided in Annex 3.

- This Output will be achieved through the following actions:

- Conduct of internal dialogue and planning among DENR Bureaus and DENR regional offices as preliminary input to support corridor consensus building (recognizing HCV criteria as additional parameter for land-use allocation and management within DENR, e.g. presentation and agreement on HCVAs);

- Assembling existing information, stocktaking and preparation of corridor level maps reflecting the various land use and management regimes under different sectors (agriculture, forestry, mining, tourism etc.) that impact biodiversity. This can build on current DENR control maps and aim to update the same;

- Conduct inter-disciplinary expert discussion to assemble, review available baseline information on biodiversity corridors, review proposed updates of KBAs and proposed target project cluster and prioritize information gaps to be addressed;

- Organization of, and support to the multi-sectoral corridor advisory committees through co-facilitation of the R/DENR, R/NEDA and PLGUs concerned;

- In-depth Assessment and Mapping of biological, socio-economic, environmental and institutional aspects, including assessment of biodiversity and ecosystem services values and threats, identification of KBAs, identification of HCVAs within the KBAs, land and forest degradation, agricultural land degradation, biological connectivity and recommendations for mitigating these aspects within the individual biodiversity corridors;

- Based on the mapping exercise, recognition of an integrated ecosystem management framework (including EIA process improvements) as well as governance arrangements for ecologically sound land use management), and agreements among LGUs and line agencies on overarching outcome oriented targets and strategies;

- Consensus on application and enforcement of strengthened biodiversity standards in the EIA process (based on guidance developed under Output 1.3);

- Support the operations of the corridor management teams; and

- End of project change detection study

- In the long-term, the mapping and strategic planning exercises would provide information for future elaborated zonation and management of the biodiversity corridors for various additional conservation outcomes and uses, facilitate environmental assessment that meet conservation norms, and help develop appropriate governance and enforcement systems to ensure that future development is sustainable and environmentally appropriate and helps conserve the important biological elements in the corridors.

- The above activities will be spread out during the 6-year project period. Agreements on Corridor framework of action will be an iterative process such that the visioning and initial planning process would be done expeditiously in Year 1 so that this in turn will guide the cluster level planning process (Output 2.2) which would start before the end of Year 1. The action plan would be refined through the project period based on the learning from pilot activities on the ground. Due to the sheer size of the Eastern Mindanao Corridor, this corridor planning exercise will be done in two parts, one each for Region 11 and Region 13.

Output 2.2:  Site-specific integrated cluster conservation plans (CCPs) designed through stakeholder and community consensus and decision-making for areas of critical high biodiversity within the biodiversity corridors

- Under this Output, the GEF increment will support development and coordination of cluster conservation plans (CCPs) for a total 12 clusters in the two biodiversity corridors.  Cascading the overall corridor vision and framework of the biodiversity corridors, the CCPs will guide specific actions for improved conservation and co-management within PAs, Ancestral Domains, CBFMA networks and privately-owned conservation estates. For sustainability, the CCPs will also help guide the planning processes of Provincial LGUs (PLUGs) and Municipal LGUs (MLGUs) and local offices of agencies to be able to provide sustained support for the actions of entities (PAs, ADs etc.)  on the ground.

- The CCPs will include outcome-oriented conservation targets as the basis for actions within PAs within the clusters and guide the creation and management (and co-management, where relevant) of OECM such as ICCAs, LCAs, as deemed necessary (refer Output 2.3 and 2.4).  This shall also specific actions to cover sustainable forest land and agricultural land management, non-timber forest products harvest and monitoring protocols for management of such resource uses, integration of conservation and livelihood options at the community level, biodiversity-friendly enterprises, and the modification of sub-national plans to integrate conservation considerations.  Developed CCPs will be agreed by key stakeholders and approved by relevant sub-national government agencies and implemented. A bottom-up participatory cluster-level conservation planning process will be established that complements existing planning processes at the local level (Annex 3) to develop the CCPs.  The CCPs will include in particular, actions to improve existing, and develop new SLM and SFM actions and diversified livelihood options and test and promote community-based natural resources co-management strategies as a means to diversify governance arrangements and clearly defined community and IP rights and responsibilities, technical support and skills, funding and extension support.

- This Output will be achieved through the following actions:

- Convening and organization (led by DENR and key PLGUs) of multi-sectoral discussion at the target cluster levels and creation of the corridor sub-committee as appropriate to tackle cluster management needs;

- In-depth mapping and assessment of socioeconomic and ecological profile of the clusters will inform the identification and extent of specific conservation, sustainable forest, land and agricultural resource use and management and alternative livelihood needs as well as threats to be managed. Key stakeholders including municipal government entities and local communities (and IPs) will be involved during assessment and mapping exercises. Training will be provided to community and IP members and other stakeholders in conservation management planning, SFM and SLM techniques and sustainable livelihood ventures. National and regional best practices in protection of existing and disturbed forests, restoration of agricultural upland, biodiversity-friendly enterprise development will be reviewed and discussed with stakeholders. The partner NGOs will be responsible for the conduct of participatory resource assessments/surveys that will be used as the basis for identifying the problems and conservation needs of each cluster, particularly in terms of habitat connectivity, SLM, SFM and livelihood options. The project will provide backstopping/assistance in GIS-based mapping by collecting and analyzing remote sensing data and satellite imageries. Local communities and local level stakeholders will be trained and involved in ground-truthing of the maps;

- Conduct of dialogue with marginalized communities (including IPs) of effective means of their participation in the cluster planning process using FPIC guidelines as defined by NCIP AO 1;

- Conduct of a participatory cluster-based planning process to define options (based on community preferences) for improving conservation, sustainable land and forest use and livelihood outcomes. The CCP will be an indicative road map for action, reflecting short-term and long-term investments needed from LGUs, National Government Agencies (NGAs) and other entities, with counterpart support from the project. It will be owned by the cluster level stakeholders and local government (PLGU and MLGU) as they will be fully involved in the planning process. The plans will include among others, interventions focusing on biodiversity conservation Output 2.3 and 2.4), SLM (Outputs 3.2), SFM (3.1 and 3.3) and livelihood improvement (Output 3.4), that would include a mix of agroforestry and soil conservation practices, and community protection and maintenance measures; establishment and maintenance of a suitable mix of protection and other sustainable measures such as social fencing to reduce grazing, wood collection and forest product extraction pressures; zoning for conservation and sustainable resource use; management prescriptions for various components of the protected area; options for livelihood improvement and diversification and effective monitoring and law enforcement governing wildlife poaching and trade;

- Initiation of dialogue for establishment/strengthening of existing local community institutions (CBFM, IP organizations, farmer cooperatives, resource use groups, etc.). Conservation issues will then be discussed with reference to their interface with locally perceived developmental and resource management needs. Key community mobilizers will be identified to act as motivators for conservation and play a strong role in institutional networking to realize the objectives of ecosystems management;

- Review and endorsement of individual actions plans for participating stakeholders (PAs, Ancestral domain committees, CBFM communities, volunteer business firms, LGUs, local conservation area committees, etc.) based on the cluster conservation plans and adoption of TORs and agreements for project support to implement such action plans;

- Support the implementation of the CCPs through the respective plans of stakeholder entities with interventions within the different parcels of land to enhance conservation of key species (Output 2.3), livelihood and ecosystem benefits (under Output 3.4), adoption of SFM (Output 3.1 and 3.4) and SLM (Output 3.2) practices to improve agricultural production and accelerate land rehabilitation, including from a gender perspective within the framework of the overall landscape vision or framework for the biological corridor (Output 2.1). These plans will be shared with potential and interested local, national and regional donors including NGOs, national and regional governments and private sector for additional funding support.  If required cooperation agreements will be signed with the donor and coordinating agencies; and

- Support to the coordination and monitoring of, and learning from, activities at the cluster level (on behalf of the corridor coordination committee).

- The project will support 12 clusters that will encompass a total of around 15,000 households (around 65,000 persons around 50% of whom are women, with which 25% are IP women). While the project will support these clusters through focused investments, additional areas outside the clusters would be either supported through existing NGOs and government programs or be considered for less intensive or targeted project support to the extent feasible, particularly in implementation of specific project related investments.   The clusters have selected based on the following criteria:

- Extent of coverage of KBAs (high biodiversity areas), that are defined as areas that represent a suite of vulnerable, endangered and rare species and habitats (based on species irreplaceability, habitat connectivity, ecological permanence and having representative bio-indicators).

- Sites where there exist clear and present threats, including land-use changes, land-use conflicts and land degradation trajectory; and

- Sites where there is demonstration potential in terms of conflict reduction, enabling policy environment, political and social support, and potential for trade-offs and synergies.

- Institutional arrangements for planning (Output 2.1) and implementation of cluster conservation plans (Output 2.2) will entail the competitive selection of a local NGO for each cluster (based on criteria as defined in Section VIII).  Contracted NGOs and local government (LGUs) will be responsible for engaging local community, private sector entities, farmer organizations and IP members in the planning exercise leading to the development of CCPs, for overseeing implementation of the CCPs, and for building and maintaining cluster-level linkages at the biodiversity corridor level to ensure wider ecosystem management. NGO activities supporting communities will be done collaboratively with LGUs. Conservation issues will then be discussed with reference to their interface with locally perceived developmental and resource management needs. Key community facilitators will be identified to act as motivators for conservation and play a strong role in institutional networking to realize the objectives of ecosystems management. Women, indigenous peoples groups and disadvantaged communities will be specially targeted.  Training will be provided to community and IP members and other stakeholders in conservation management planning, SFM and SLM techniques and sustainable livelihood ventures. Support to participating local community groups under the project would be provided through a Terms of Partnership (ToP) agreement that sets out the mutual obligations of contractual parties and provides checks and balances to enforce conservation measures. The selected NGO would have expertise in conservation, SLM, SFM, livelihood and enterprise development, social mobilization and tenure applications. Planning and implementation teams at the cluster level will include the above-mentioned expertise from the NGO, and incorporate key technical staff from the LGU in its area of operation, the latter inclusion in the planning and implementation activities will facilitate later integration of biodiversity consideration into the LGU CLUPs.

Output 2.3: Improved management effectiveness of existing protected areas within the two biological corridors

- Under this Output, the project will support the implementation of PA management measures in eleven PAs covering an estimated 300,000 hectares within the two corridors. This will enhance management effectiveness of these PAs (as measured by the METT tool) and ensure sustainability and improved habitat connectivity within the corridors. Following a network design, the relative importance and role of each of 11 PAs in the ecological functioning of the corridor will be defined, which will guide the configuration of the existing PAs. Management measures that will be implemented include:

- Identification of conservation values within PAs in the corridors that will inform later decisions on management planning;

- Conduct of census on PA occupants;

- Preparation of new and updated protected area management and financial plans based on in-depth baseline establishment, as well as measures for resource mobilization;

- Capacity building and training of PA wardens and rangers to reduce human-wildlife conflict, improve enforcement and visitor management;

- Based on 5-year PA management plans, the development of annual operational plans for biodiversity conservation, soil and water conservation, fire management, restoration of degraded ecosystems through assisted natural regeneration, weed management, etc.;

- Support government efforts at defining restoration measures for habitat for critically endangered species such as Bubalus mindorensis and other species through habitat improvement measures, such as grassland management, reduction of pressures from domestic livestock, etc.;

- Development and implementation of MRVs (Measurable, reportable and verification targets) and protocols for monitoring of key threatened species and their habitats in PAs to inform management;

- Supporting the implementation of conservation management interventions [including delineation of PA boundaries and management zoning, improvement of facilities and skills of the Protected Area staff and offices] within PAs; and

- Strengthening law enforcement to address illegal hunting and monitor and enforce infringements to PA regimes

Output 2.4:  Recognition of a network of other effective area-based conservation measures (OECM) such as ICCAs, LCAs to accord improved protection and conservation within key biodiversity areas

- This Output will finance detailed assessments of existing Key Biodiversity Areas (KBAs), high conservation value areas (HCVAs) using range of biological and socio-ecological information such as the species distribution, habitat suitability maps and threats, on the basis of which at least 200,000 hectares of biologically rich areas will be afforded improved protection through engagement of IPs and communities within the two biodiversity corridors.  These new OECMs will be largely co-managed by local communities, LGUs and Indigenous People (or combination thereof) and also establishment of private conservation estates (e.g. biodiversity set-asides in extractive industry tenements, agri-business plantation estates, etc.). Annexes 4, 5, 6 and 7 provide more descriptions on how this network of OECM can be identified, and how investments, incentives and management plans should be drafted and implemented for these identified OECMs.

- The following action will be undertaken to achieve this output:

- Assessment of existing KBAs, HCVAs covered by the PAs in the two corridors to ascertain opportunities to link KBAs, HCVAs to improve species and ecological viability; or their coverage and effectiveness to support endangered and threatened species, ecosystems and ecosystems services, human use values and traditional values (see Annex 8);

- Identification of areas (outside PAs) for supporting community conservation efforts through support to Ancestral Domains (including recognition of ICCAs), support to LGU-based Local Conservation Areas (LCAs) and conservation set-asides in extractive industry and agri-business estates;

- Negotiation of collaborative arrangements through ICCAs with indigenous people in at least 9 Ancestral Domains (including development of ICCAs) and at least 4 LGUs and other arrangements with extractive industry and agri-business estates;

- Management plans developed and implemented to operationalize the new ICCAs (taking into consideration specific requirements for application of FPIC, facilitating improved understanding of relationships between IPs and their interactions with the land and resources, and enhancing cultural norms and practices in terms of land and resource use and conservation) and related agreements with LGUs and business firms;

- Investments for improved management and protection of these areas including provision of benefit sharing arrangements for local communities; and

- Development and implementation of protocols for monitoring progress (including key threatened species and their habitats) and identifying learning from field experiences.

Output 2.5: Capacitating national and sub-national governments, sector stakeholders, local communities and indigenous peoples to mainstream biodiversity conservation measures tested in the pilot corridors into their policies, planning and monitoring systems

- The project will develop the IBM framework for the two biological corridors (Output 2.1) and the preparation of enabling guidelines, best practices and protocols for integration of biodiversity conservation into sector plans and programs and sub-national (provincial, regional and municipal) planning and management systems, local resource planning systems (Output 1.2).  However, institutionalization of the objectives of IBM frameworks, which is mainstreaming of biodiversity considerations into the relevant sector and sub-national policies, plans, budgets and monitoring systems requires the adoption of planning guidelines, convergence of planning systems, integration with other sustainable area-based initiatives, capacity building, technical assistance and adjustment of current practices in relation to planning and budgeting. Annex 9 provides a strategy for building capacity of LGUs and Regional Offices of national government agencies for mainstreaming of biodiversity in local and provincial planning systems.

- The project will target this effort in particular, in those sub-national LGUs (24 LGUs) that are located within the cluster areas in the biodiversity corridors, through involvement of sub-national government staff in the IEM planning exercises particularly with DENR, DA and NCIP, in the elaboration of cluster conservation plans, in the oversight and implementation of activities defined under the respective cluster plans and in monitoring progress, impacts and best practices, capacity development and training.  Through, the mainstreaming of IEM (including SLM and SFM) principles and policies to be developed under Component 1, it is anticipated that there will be an prioritization and increase in program investment and budget for SLM and SFM activities in the Municipal Comprehensive Land Use Plans (CLUPs) and related local strategic socioeconomic development plans that are to be revised during the project period in the 24 LGUs.  LGU plans will likewise be reinforced by the mainstreaming of IEM principles in the larger Provincial Development and Physical Framework Plans as well as Regional Development Plans.  The latter will guide investments by national agencies located in the biological corridors. Building on the best practices and incentive mechanisms developed under Outputs 3.2 and 3.3 it is anticipated that there will be increased program investment and budget prioritization by the respective LGUs in their CLUPs covering a collective area of 150,000 ha of agricultural lands for avoided degradation and 100,000 ha of degraded forest lands for restoration. This Output will support the following activities:

- Undertaking of corridor-based assessments to define extent to which current sector and sub-national planning systems integrate biodiversity and identify barriers, gaps and entry points for improving integration;

- Participation LGU staff in cluster conservation planning, management and monitoring who will interact with National Government Agencies, as well as civil society and private sector such as extractive industries;

- Provide information support for LGUs to make strategic choices on options for integration of biodiversity conservation measures into their planning and budgeting processes;

- Support the integration of biodiversity concerns and proven strategies in provincial development and physical framework planning and MLGU comprehensive land use planning;

- Develop specific business cases for locally supported initiatives in biodiversity, with its inherent economic and social outcomes, to demonstrate value of integration;

- Capacity building for Regional Offices of agencies, Sector agencies and LGU staff (including local sectoral consultative councils) in tools and practices for biodiversity mainstreaming;

- Integration of learning into strategic programs and staff capacity building programs in environment, agriculture and IP affairs among participating LGUs;

- Integration of learning into strategic investment program proposals of the respective regional offices of DENR, DA and NCIP; in cluster conservation planning, piloting innovations at the community level and the identification and analysis of learning and best practices; and

- Preparation and application of a facilitators manual for helping LGUs and regional offices of DENR, DA and NCIP for incorporating biodiversity concerns in local strategic programs (to complement existing guidelines.

Component 3:  Community-based sustainable use and management systems in the two pilot biodiversity corridors in the Philippines.

Total Cost: US$20,031,211; GEF project grant requested: US$4,326,495; Co-financing: US$15,704,716

Outcome 3: Sustainable use and management systems for land and forest resources that are compatible with integrated ecosystem management corridor objectives implemented

Baseline conditions for this outcome (without GEF project):

- Without the GEF project, the Mindoro and Eastern Mindanao biological corridors will continue to undergo rapid land degradation viz a viz forest and wildlife habitat fragmentation as a result of dramatic forest cover change arising from conversion to agriculture and built-up areas, and proliferation of extractive industries such as logging, mining and other economic activities. Unsustainable agricultural practices on farmlands will exacerbate different forms of land degradation such as soil fertility loss, declining productivity and low soil organic carbon (SOC). Sustainable land and forest management practices will be slow to materialize and intensive cultivation with excessive external input in lowland areas will continue, while more serious problem arising from land degradation in the uplands, as a result of soil erosion, and consequential loss of top soil and changes in the chemical, biological and physical endowments of the soil will likely persist. Key Biodiversity Areas, of which, large tracts are located in rolling to steep-sloping areas (up to 50% slope or more) that are easily eroded, too shallow, dry or rough for cultivation will continue to be lost.

- In the absence of the GEF project, there will be slow progress in developing sustainable land and agricultural management practices and alternative livelihoods resulting in continued unsustainable farming systems, unsustainable production and consumption of non-timber forests products (including medicinal and oriental plants and wild animals for trade and domestic consumption) and other forms of resource extraction, particularly within KBAs and adjacent areas. Competition for forestlands and wetland habitats will continue unchecked resulting in increased human-wildlife conflict and loss of critical biodiversity and ecosystem services. Traditional practices of sustainable use of natural resources will continue to decline, resulting to more open access regimes that are critical habitat for many key species. At the same time, undocumented and uncontrolled expansion of swidden farming will accelerate forest fragmentation. Markets for agricultural, forestry, livestock and tourism products will continue to be poorly developed thereby acting as a constraint for improving the lives and livelihoods of local communities. In addition, business approaches and opportunities to enhance and mobilize funds (tourism, sustainable hunting, production of local crafts, catering, etc.) will be largely limited. Consequently, local communities will continue to depend on natural resources, resulting in further degradation of wildlife habitats and severing connectivity between important wildlife habitats. Key biodiversity and ecosystems within and outside the traditional protected areas will face intense pressures and threats, with likely reductions in fauna and flora diversity and species population sizes, thereby threatening the survival of these species over their overall biological range.

- As majority of the people living in the corridors are poor, the continued degradation of land and forests and loss of agricultural productivity will increase poverty and food insecurity, particularly as agriculture provides the economic base for the people living in these areas, that is further exacerbated by natural climatic conditions, small farm sizes, lack of capital and low access to other productive resources.

Alternative conditions for this outcome (with GEF project):

- The project would support a range of forest and land improvement measures, including (i) threat reduction in existing forests, particular those areas that are critical for maintenance of biological linkages, (ii) rehabilitation of degraded agricultural lands through improved and sustainable agricultural and land management practices, (iii) support agricultural and enterprise developments that have built in biodiversity safeguards to achieve no net loss, including from a gender perspective for communities and private sector and pilot SLM incentive mechanisms and (iv) a voluntary forest certification system for local communities and privately managed forests, all within specific high biodiversity cluster areas within the corridors, with the intent to test an integrated and multi-stakeholder approach to management of biological corridors.

- Through the range of SLM, SFM and livelihood activities, the GEF increment will support improvement and diversification of rural livelihoods, including from a gender perspective building on the biodiversity-friendly enterprise framework recently launched by the DENR and DTI as means to strengthen to strengthen agricultural and non-agricultural based incomes. The community-based models currently proposed are aimed at (i) supporting voluntary forest certification for local communities and privately managed forests; (ii) sustainable land management and agricultural practices through various institutional and collaborative mechanisms, including farmer cooperatives; and (iii) biodiversity friendly livelihood and business management practices. These activities will be implemented through existing community institutions, such as farmer cooperatives, CBFMAs, fisher folk, IP organizations, community and private sector groups, as relevant.

- To address the immediate and near-term threats, the project will explore provision of targeted financial support to IPs and local communities that are linked to changes in practices and behaviors (e.g., adoption of SLM measures) so that such support acts as an incentive to change. Local government units and NCIP local offices will be supported in developing their own incentive mechanisms and create partnerships and co-investments for SLM. While specific activities are to be confirmed through a participatory approach, some examples of such targeted incentive mechanisms include direct payments, socialized micro-credit, crop insurance, access to investment funds, etc. In order to make sure these mechanisms are sustainable and viable in the long run, the project will seek collaboration and align with existing initiatives under relevant agencies including the Philippine Crop Insurance Corporation (PCIC), Land Bank of the Philippines, Department of Trade and Industry (DTI), Development Bank of the Philippines, especially in support of community and private sector engagement on biodiversity-friendly enterprises. Further, other measures will include support in granting and strengthening of land tenure rights to forest communities, in securing certificates of ancestral domain titles (CADTs), for indigenous peoples, developing local community forest management plans, and ADSDPPs, which incorporate conservation actions, and recognition of ICCAs. These are linked to the project strategy to promote biodiversity-friendly enterprises, ensuring local government revenues from extractive industries are allocated to poverty reduction programs, certification systems for communities engaged in SFM and sustainable agriculture etc.

- Further, the project will support development of protocols to protect community rights over biodiversity resources. Sustainable development and protection plans will be prepared and will serve as excellent entry points for integrating biodiversity considerations. The project will also establish at least 2 conservation agreements that will reward novel and effective conservation actions carried out with groups such as communities, indigenous peoples and farmer groups. Finally, it will train community leaders, agencies, and LGUs to undertake proper screening of programs and business propositions to determine alignment with the integrated biodiversity management framework for the two corridors.

Output 3.1:  Voluntary forest certification system piloted for local communities and privately managed forests

- Under this Output, the project aims to: (i) assist DENR in its ongoing effort to develop a Philippine Forest Certification System (PFCS), and (ii) pilot test the system at selected forest areas within the biological corridors. The aim of the forest certification system is to pursue and advocate for sustainable forest management and help revitalize the local forest industry (see Annex 10) for procedures for forest certification). To the extent relevant and based on the learning of the pilot activities, the government would consider the development of policy for promotion of PFCS in the country. To initiate the setting up of PFCS, DENR created an Interim National Governing Body co-chaired by the Society of Filipino Foresters and the Forest Management Bureau. Preparatory efforts towards the development of the system should include the following activities:

- Review and analyze previously developed National Set of Criteria and Indicators (C&I). The review will select ‘key’ or significant C&I from the national set which will be applied to the selected pilot sites in the two biological corridors

- Review current forest certification systems (e.g. Forest Stewardship Council Certification System, Pan-European Forest Certification System, Indonesian Forest Certification System) and examine their procedures, processes, standards and guidelines

- Learn from the reviews and possibly adopt parts of the systems that are relevant and practicable in the Philippines

- In supporting the further development of PFCS, the project will undertake the following actions:

- Develop a set of standards based on the initial review of the National Set of Criteria and Indicators (C&I);

- Develop policies, processes, and procedures, including Guidelines, for implementing the PFCS

- Draft an Administrative Order (or a regulating instrument governing the implementation of the PFCS)

- Support the organizational and institutional infrastructure needed to implement the PFCS such as:

  - Mechanism for accreditation of possible ‘Certifying organizations’; and

  - Mechanism for accreditation of ‘Auditors’ and other professionals involved in the PFCS

- Institute capacity building activities for ‘Certifiers’, ‘Auditors’ and other ‘Agents; involved in the PFCS

- Develop communication and other information materials needed for the implementation of PFCS

- To pilot test the PFCS, the project will conduct a number of activities, including the collection and analysis of biological, social, environmental and institutional data to facilitate the testing and validation of the PFCS and identify any specific gaps that need to be further addressed. The community and private sector groups participating in this process will be expected to provide information and feedback to help validate and/or improve the PFCS process. While the GEF project will finance the review and validation process through provision of consultancy support, the participating communities and private sector agency will not be allocated any financial resources from the project. The following activities with appropriate consultancy services:

- A mapping and forest inventory of pilot cluster sites for PFCS.  Areas within the clusters identified would be prioritized for selection of potential pilot areas (note: approximately 300 ha of CBFM or CADC/CADT and 1,000 ha for IFMA).

- Select two sites, namely 1 CBFM or CADC/CADT and 1 SFMA where PFCS can be piloted.

- Through the support and collaboration of FMB, seek the engagement of a private company to partner the selected two pilot sites and conduct focus group discussions with the selected sites to explain about Forest Certification

- Seek the collaboration of the selected local forest communities’ organizations to participate in the Forest Certification Pilot Study

- Follow the Set-up, Procedures, and Processes developed for the Forest Certification System within the context of the local communities.

- Support technical support to pilot areas to address areas of concern identified by the auditors;

- Forge partnership agreement (that spell out responsibilities and mutual benefits from the partnership such as carbon credits for private company and financial assistance to forest community) between private company and pilot site based on PFCS results and subsequently examine, document, and monitor the implementation of the proposed PFCS in the pilot sites, the funding for any future investments to enable compliance with the validated PFCS standards will be borne by the private company.

- Prepare Report on the results of the Pilot Study

- Stakeholder presentation of the results of the pilot study of PFCS; and

- Prepare final report

Output 3.2:  Sustainable land management applied to degraded agricultural lands through a suite of SLM technologies/practices and incentives

- This Output will facilitate wider adoption of SLM measures and biodiversity-friendly agricultural systems defined under the Department of Agriculture and Department of Environment and Natural Resources Biodiversity Friendly Agricultural Practices (DA-DENR BFAP) Framework, as well as viable traditional farming methods.  This is to ensure increased food production and income, livelihoods, whilst improving agro-ecosystems resilience and reducing pressures on PAs and natural forests, resulting in improved habitat connectivity. These include but not limited to simple measures such as contouring, terracing with natural/planted hedgerows, conservation tillage, residue management, relay/cover cropping, improved fallow management, natural composting and integrated pest management (IPM), to the more complex hedgerow system, multi-strata agroforestry, and the comprehensive sloping agricultural land technology (SALT). Recognizing that smallholders and indigenous (IP) communities are poorly resourced and not in a position to incur the costs associated with these measures, ‘incentive mechanisms’ are needed, and will be piloted to stimulate wider adoption.  SLM measures and incentives are targeted to address degradation and improve the productivity of 15,000 ha of agricultural lands along protected area (PA) boundaries, in other area-based conservation measures (OECM) such as those with Certificates of Ancestral Domain Titles (CADT) and local conservation areas (LCAs), and private farmlands. Under this Output, the project will employ two parallel interventions: (i) Establishment of SLM exemplars; and (ii) Incentive mechanisms and programming for wider adoption of SLM and biodiversity-friendly agricultural systems. Refer to Annex 5 for detailed activity description under this Output.

- Setting up of NGO recruitment, partners meetings and workshops agreements and finalizing institutional arrangements for exemplars and upscaling;

- Selection of SLM exemplars: 30 gender resposnive SLM exemplars (18 in Mindoro and 12 in Eastern Mindanao) covering 150 ha, involving individual farmers and farmer associations/cooperatives, will be established as ‘proof of practice’ sites across the corridors, demonstrating the viability and benefits of a range of SLM measures and biodiversity-friendly agricultural systems, increasing at least, 15% in productivity and income while simultaneously contributing to land rehabilitation and biodiversity conservation outcomes.

- The exemplars will serve as ‘learning nodes’ that trigger farmer adaptation and innovation in wider areas.  Specific activities include (i) site selection; (ii) social preparation; (iii) participatory assessment of on-farm degradation and farming systems; (iv) tree-crop suitability assessment; (v) design and management of SLM exemplars; (vi) monitoring; and (vii) knowledge management. The project will ensure that SLM measures are gender-responsive, and do not further harm or impose drudgery on women, and radically alter traditional cultures.

- Design and implementation of SLM exemplars: The exemplars will serve as ‘learning nodes’ that trigger farmer adaptation and innovation in wider areas.  Specific activities include (i) site selection; (ii) social preparation; (iii) participatory assessment of on-farm degradation and farming systems; (iv) tree-crop suitability assessment; (v) design and management of SLM exemplars; (vi) monitoring; and (vii) knowledge management. The project will ensure that SLM measures are gender-responsive, and do not further harm or impose drudgery on women, and radically alter traditional cultures;

- Incentive mechanisms and programming for wide-scale adoption of SLM and biodiversity-friendly agricultural systems: To bolster wide-scale adoption of SLM measures and biodiversity-friendly agriculutural systems in the corridors, the project will assist local communities develop and implement SLM incentive mechanisms through technical assistance, and leveraging project funds primarily with municipal local governments and IP community resources. Performance and outcome-based incentive mechanisms, which include cash and in-kind (farm inputs, small farm implements, materials, credit access, insurance schemes, social protection and/or direct payments), will be deployed to incentivize and stimulate wider adoption of a range of SLM measures by at least 15,000 households/farmers, cultivating 15,000 ha of degraded agricultural lands in the corridors.  The project will also assist municipal governments and IP communities generate support and create partnerships with relevant national-regional-local government programs, non-government organizations (NGOs), and the business sector, to generate ‘co-investments’ for the sustainable financing of SLM, and for mainstreaming SLM goals into their regular programs (e.g. Corporate Social Responsibility (CSR) for the business sector). A number of national and regional programs implemented in the corridors, which can be tapped for SLM co-investments and partnerships is shown in Table 2 below. This will lead to the creation of an umbrella of non-GEF financed programs that support farmers transition to a land degradation neutral and sustainable agricultural production, thereby contributing to forest connectivity and habitat recovery. Specific actitivities include (i) sensitization of local stakeholders; (ii) leveraging project funds with local resources; (ii) desiging and implementation of incentive mechanisms; (iv) implementing trainings, workshops, meetings, donor and business forums and awareness raising; (v) providing technical assitance in SLM programming and incentive policy development; and (vi) monitoring. Through the best practices introduced under this Output and the mainstreaming of SLM principles and policies in the Municipal Comprehensive Land Use Plans (CLUPs) as described in Output 2.5, it is anticipated that there will be program investment and budget prioritization by the respective LGUs in their CLUPs covering  a total of 150,000 ha of degraded agricultural lands.

- Documenting best practices and M&E.

- Table 2- Key government funding programs to enable replication of SLM mechanisms

| National /Regional Programs | Description |
| --- | --- |
| National Organic Agriculture Program (NOAP) | Led by the Department of Agriculture (DA), NOAP aims to promote, further develop, and implement organic agriculture in the country. NOAP extends incentives for the production of organic farm inputs by maximizing their use in all government and government-supported agricultural production, research and demonstration programs. Government agencies, Land Bank of the Philippines, lending and non-lending institutions assist organic input producers and farmers with adequate financial, technical, marketing and other services and resources. |
| Special Area for Agricultural Development (SAAD) | Led by the DA, SAAD is currently implemented in 8 regions, including the Eastern Mindanao BD corridor envisions that by 2022, it becomes the lead agricultural development program and resource mobilization service of the DA undertaking intensified social venture initiatives to increase food production and alleviate poverty. |
| Philippine Rural Development Program (PRDP) | Led by the DA, the PRDP is designed to establish the government platform for a modern, climate-smart and market-oriented agri-fishery sector. PRDP partners with the LGUs and the private sector in providing key infrastructure, facilities, technologies, and information that will raise incomes, productivity, and competitiveness in the countryside. |
| Philippine Crop Insurance Program | The Philippine Crop Insurance Corporation program provides insurance protection to the country’s agricultural producers particularly subsistence farmers against loss of their crops and/or non-crop agricultural assets on account of natural calamities. |
| Production Loan Easy Access (PLEA) | Led by DA-Agricultural Credit Policy Council, PLEA is implemented nationally to address the financial needs of marginal and small farmers and fisher folks. Non-collateralized and low-interest rate loans are provided for agri-fishery production through cooperative and rural banks, and NGOs as lending conduits. |
| Sustainable corn production in sloping lands; Small-scale irrigation; National soil sampling and testing (NSST) | Implemented by Bureau of Soils and Water Management (BSWM) and DA Regional Field Offices, these projects provide support services in form of technical assistance, materials, and technical trainings to farmers. |

Output 3.3: Fragmentation of biodiversity habitats reduced through SFM approaches and collaborative management

- Under this output, the project will adopt different sustainable forest management approaches in order to reduce the threat of further fragmentation and degradation of key biodiversity areas consistent with the goals of integrated ecosystem management. The intent of SFM under the project is to promote multiple combined objectives such as maintenance of biodiversity, ecological integrity and connectivity, enhancement of human benefits through sustainable forest product use, enhancing land productivity and providing other environmental benefits (e.g. water and soil conservation), climate mitigation, etc. The objective, strategy and action plan for SFM will be customized to the specific conditions of the sites and forest condition, including its biophysical conditions and its stakeholders, and taking into account their interests and the decisions they make. To achieve this objective, the project will fund the following planning, extension and oversight activities as the basis for galvanizing government and private sector co-financing for the actual restoration efforts. The following activities will be funded with project support:

- Conduct of field/scoping survey to identify project areas for restoration

- Initiate, facilitate, and provide support for a consultative process bringing together the forest communities, private sector (including the mining sector) and the government to define suitable approaches for forest restoration

- Through a participatory process involving forest communities, private sector and the government agencies, lead and facilitate the preparation of restoration and management plans for these selected project areas, including adoption of agroforestry and restoration activities, defining appropriate silvicultural practices with the intent of improving biodiversity conservation and promoting connectivity between KBAs;

- Develop and support monitoring on the progress of the implementation of the restoration and management plans

- Provide technical support and oversight for the subsequent restoration effort of the government and/or private companies

- The project approach is aimed at financing the planning, extension and management process, with the basic aim to ‘leverage’ its project funds in three ways to obtain co-financing for the actual restoration costs: First, the project can collaborate with FMB, particularly on NGP and other CBFM projects, where much of the ‘direct’ costs will be borne by the government. Secondly, the project can work directly with forest communities (POs) within their existing CBFM areas by providing planning and extension support for enhancing/expanding/improving existing, (or establishing new agroforestry) areas within their CBFM areas. Thirdly, the project can also work collaboratively with private companies, such as mining companies, where the private companies can provide funds to forest communities for direct activities like site preparation and planting. Mining companies have expressed interest in pursuing such leveraging and co-funding of restoration activities in part because they are mandated to do so as part of the conditions of the permits issued to them for their mining activities. These restoration activities bundled with leveraged funds will be spelled out in the forest restoration plan that will be prepared collaboratively by the project and the forest communities and funded adopting the community development funding scheme described in Annex 4. The primary goal being to help reduce the threats of fragmentation and degradation of critical biodiversity habitats and Improve connectivity of fragmented key biodiversity areas.  These objectives will be achieved through promotion of approaches such as agroforestry and Assisted Natural Regeneration (ANR). ANR will essentially involve brushing and weeding around preferred or desired species, fire protection through construction of fire line, and seeding and enrichment planting where appropriate

- In general, implementation of the SFM approaches will be guided by the following principles:

- Priority sites to be protected are those close to, or could adversely affect, key biodiversity and protected areas within the identified clusters,

- Ensure that forest protection and rehabilitation activities at the site level fits within the overall environmental, social and economic objectives at the cluster level;

- Activities and protection initiatives are identified through a participatory process involving local stakeholders.

- Activities will offer multiple local benefits and/or improve rural livelihoods (e.g. use of species that can have economic value to the stakeholders like fruits or other valuable species; and

- Activities will help reduce the threat of fragmentation through forest protection and enhance connectivity of fragmented biodiversity habitats

- SFM approaches will be planned and implemented following a sequence of steps described below:

- Identification of priority forest areas:  A participatory cluster mapping exercise would be conducted to help identify key priority areas where SFM strategies will be conducted using the following criteria: (i) disturbed forest areas either within or adjacent to critical biodiversity habitats that are vulnerable to potential fragmentation of habitats; (ii) areas that have potential for cost-effective assisted natural regeneration approaches; (iii) areas that can provide significant forest-based economic benefits to local communities; and (iv) sites where there is strong community interest and commitment to forest conservation that has  potential for livelihood opportunities;

- Identify forest communities (including IPs) and other stakeholders as potential partners and implementers of SFM approach consistent with the general principles summarized above;

- Conduct workshops, capacity building seminars and focus group discussions about potential SFM approaches, including customary forest management techniques currently practiced by IPs and local communities;

- Secure the commitment from local community and IPs to participate these SFM efforts and subsequently mobilize stakeholders and communities in implementing SFM.

- Review existing viable management and governance systems operating in the selected sites including those effectively practiced among indigenous communities

- Preparing technical guidelines on SFM approaches;

- Support strengthening of existing community institutions and organization of such groups where existing collaborative community institutions are absent (such as CBFMs, community cooperative groups, people organizations, etc.);

- With direct and active participation of stakeholders, develop a sustainable forest management plan for selected priority areas for intervention.  This should involve agreement on shared goals, including provision of incentive systems to encourage communities to conduct and sustain the implementation of SFM approaches in a collaborative manner;

- Devise appropriate benefit sharing arrangements to ensure equitable distribution of benefits among participants;

- Provide technical support to better integrate sustainable forest management and benefit sharing practices;

- Support the implementation of the sustainable forest management plan (with co-financing support from government and private sector, the latter in particular from the mining industry) under a collaborative forest management platform, including incentive mechanisms to encourage long-term participation and improved benefits for local communities; and

- Conduct monitoring of progress and impacts of SFM, including assessment of biological, ecological and community benefits to evaluate progress in particular to assess reduction in fragmentation of biodiversity habitats, improved forest cover and condition and community benefits.

Output 3.4: Biodiversity-friendly livelihood and business enterprises promoted to avoid biodiversity loss and lead to natural resources use sustainability

- In order to address the lack of opportunities for alternative livelihoods for rural communities and stem the impacts of unsustainable practices, this Output will be part of the effort of improving direct financial benefits from biological resources by engaging communities and the private sector in promotion of economically important biodiversity-friendly livelihoods and business enterprises within the target clusters. Creation of new and/or enhancing existing value chains will be the strategy to secure local livelihoods. Some value chains identified are non-timber forest products, including bamboo, mushroom and honey, as well as high value fruit trees and other perennials such as banana, cacao and coffee. Activities under this Output will be carried out in partnership with the Department of Trade and Industry (DTI), private sector business houses, NGOs, research institutions, and government-led initiatives such as Oriental Mindoro’s Agri-prenuer incubator.

- Using the DENR BFE Framework, the project will undertake inventories, evaluation and profiling of existing biodiversity-friendly enterprises (agricultural products, NTFPs, ecotourism) to (i) create databases for best practice biodiversity-friendly enterprises; (ii) recognize their practices/operations and provide necessary support; and (iii) use them for knowledge-sharing and learning (see Annex 6 for details of procedures for establishing biodiversity-friendly livelihood and business enterprises). In particular this Output would entail the following:

- Setting up through NGO recruitment, partner meetings, agreements and establishment of institutional arrangements;

- Inventory and development of database on biodiversity-friendly enterprises;

- Identification of biodiversity-friendly enterprises and analysis of value chains based on market potential, economic and environmental feasibility, and will require mapping of (i) market potential of product/services; (ii) customer requirements; and (iii) the challenges faced by marketers/customers. Based on market data, existing value chain gaps will be assessed, and based on identified gaps and the DA-DENR BFAP and DENR Biodiversity-Friendly Enterprises (BFE) Frameworks, interventions will be designed and implemented to complement and enhance ongoing interventions of the government, donor agencies and the private sector. Annex 11 provides an indicative list of biodiversity-friendly products/enterprises and services that the project can explore further;

- Capacity building and linkages with service providers for supporting 250 small start-up grants for product development, branding and commercialization, including smallholders/IP producers and service providers to help them understand customer requirements, increase productivity, learn business and marketing skills, and develop new products/services. The project will help access technical, financial and infrastructure support (small processing, storage and marketing facilities) from DTI and local programs such as the Agri-prenuer Incubator of Oriental Mindoro. It will also explore the potential of local branding, and GI registration to the extent relevant;

- Community grants for co-investment in biodiversity-friendly micro-small-medium enterprises (MSMEs) involving at least five existing or new cooperatives will be organized and/or existing ones supported, to initiate collective production and marketing of biodiversity-friendly products, in partnership with private institutional buyers. The project will directly support co-investment schemes to establish biodiversity-friendly MSMEs;

- Promoting community-based ecotourism ventures through the following means: (i) assessing tourism opportunities and opportunities for participation of IP communities; (ii) designing and promoting voluntary application of biological corridor tourism certification program for hotels, guesthouses and tourism facilities, tourism activities, and tourism products; and (iii) strengthening selected tourism products and services that recognize biological corridor conservation principles; and

- Creating partnerships with lending institutions for financing small biodiversity-friendly businesses to deserving producer groups. The microfinance will be linked to satisfactory performance of, and delivery of outcomes.  Other financing mechanisms such as the REDD+ program will also be explored, for bundling ecosystem services and incentives to include LDN and biodiversity, as well as local companies directly benefiting from improved management of the corridors.

Component 4: Knowledge management, gender mainstreaming and monitoring and evaluation

Total Cost: US$6,349,602; GEF project grant requested: US$891,390; Co-financing: US$5,458,212

Outcome 4: Awareness and collaborative decision-making on Integrated Ecosystem Management enhanced through effective knowledge management and gender mainstreaming.

Baseline conditions for this outcome (without GEF project):

- Many gender and other inequities exist in terms of gaps in information sharing, knowledge, and attitudes. Traditional knowledge while it exist, will likely continue to be guarded and segregated by gender, and while there is effort at sharing knowledge using public media and other social networks, this is likely to continue to advance at its own slow pace. Knowledge and understanding of the relationship between biodiversity conservation, protected areas and sustainable forest and land management and human welfare is low. Likewise, priorities for information collection to include gender, indigenous people and vulnerable people’s concerns have also remained low. Significant gaps in understanding of terrestrial, coastal and marine habitats, both at the institutional level and at the community level will continue to exist, and impacts of poor land and exploitative practices will remain poorly understood. Management of land and coastal and marine data will continue to be limited. While much information is generated through “projects”, this information is likely to continue to be compartmentalized and not widely shared outside of the close circle of project implementers.

Alternative for this outcome (with GEF project):

- The goals of Outcome 4 are: (i) improving knowledge and information collection and management systems to enhance awareness about best practices on conservation of land and seascapes and their associated biodiversity and ecosystems through communication, documentation and dissemination; (ii) supporting the strengthening policies and programs that support conservation and sustainable use; (iii) ensuring gender considerations are mainstreamed into natural resources planning and management; and (iv) monitoring and evaluating project investments to ensure that these are meeting project outcomes and contribute to Philippine’s conservation and ongoing development agendas. To achieve such an objective requires the improved understanding and participation of key target groups (decision makers and staff from key sectors), non-governmental organizations, as well as community groups (including indigenous people), researchers and others, including in particular women and the most vulnerable segments of the population.

- The development of a knowledge management and communication strategy (see Annex 12) is intended to promote meaningful stakeholder awareness, understanding decision-making and collaboration in biodiversity conservation, sustainable natural resource use and biodiversity-friendly livelihoods as well as document, disseminate and scale up successful lessons and best practices in resource conservation more widely in the biological corridors (and associated landscapes and seascapes) and beyond. This will be accomplished through awareness campaigns, and creation and maintenance of an accessible information system for decision makers (including online public access database and documentation repository). Expanding the role of knowledge management is key to moving towards parity. The GEF alternative will also enable a gender-equity perspective and analysis of the way that information is prioritized.  In accordance with this a Gender Analysis and Mainstreaming Action Plan (see Annex 13) has been developed.

Output 4.1: Knowledge Management and Communications, Gender Mainstreaming and Monitoring and Evaluation strategies developed and implemented

- The implementation of the Knowledge Management and Communication Strategy and Gender Analysis and Mainstreaming Action Plan will be key to the overall goal of building bridges between the stakeholders from the grass-root to the national, provincial, municipal and village levels to support decision-making. This will include documenting best practices and results of the project and ensuring the flow of information, exchange of ideas and implementation and mainstreaming of gender in community-based conservation and sustainable natural resources management. The communication strategy is aimed at making “mainstreaming biodiversity and sustainable natural resource use” a national and corridor level priority for large terrestrial and marine ecosystems (including biological corridors, in particular). The strategy will help build visibility to the conservation needs of these ecosystems (as relevant depending on the biological corridor site) and connecting stakeholders - policy makers, media, research and academic institutes, private sector, NGO’s and general public - through a comprehensive program, from consultations, brand building to outreach and awareness. The intent is to create systems that facilitate and generate a common vision for “mainstreaming biodiversity and sustainable natural resource use” and supporting a horizontal and vertical exchange of information and knowledge to strengthen decision support systems available to local communities, local governments and sectoral agencies. It will also facilitate knowledge exchange through field visits and awareness trainings, identify and document promising and good practice and promote establishment of model demonstrations by involving local communities, protected areas and local governments. The intent of the gender analysis and mainstreaming action plan is to enhance the role of women in conservation-based actions, that provides a voice for women in the local decision-making process related to conservation, sustainable resource management, livelihood and other local level activities.

- This Output would be supported through the following activities:

- Development of knowledge management and communication action plans for each biological corridor based on overall knowledge management and communication strategy so that (i) the project is well understood, accepted, and implemented effectively and equitably; (ii) information and knowledge about biodiversity corridor planning and management is made available for decision making and improved collaboration; (iii) training programs are oriented towards application of knowledge to corridor practices; (iv) knowledge and lessons learned from the implementation of this project are captured, documented and used to improve current and future project practices;  (v) implementation and upscaling of best practices is improved; and (v) the public has an increased awareness and understanding of biodiversity conservation and threats, and (vi) knowledge management products are shared and used:

- Implementation of a gender analysis and mainstreaming action plan so that: (i) a gender and socially inclusive perspective is applied to every set of activities; (ii) research on gender and social roles in Biological corridors informs resulting plans and ensures equitable distribution of benefits; and (iii) information is collected and shared across gender and social divides. Training of staff on application of gender mainstreaming in project communication and project activities;

- Design of communication materials and programs (local language, teaching materials for schools, etc.)

- Conduct of awareness and outreach activities for a variety of stakeholders at the national, provincial and local levels such as competitions, website, mass media, video and film, festivals, etc.

- Conduct of gender, indigenous people’s and biodiversity focused training and training materials;

- Review and regular update of M&E plan, including results framework baselines, tracking tools, Theory of Change to subsequently adopt these findings to implement all aspects of the project; and

- Conduct mid-term and terminal evaluation in line with UNDP/GEF requirements and incorporate and adapt recommendations of MTR to revised project plans and monitor their implementation.

Output 4.2: Harmonized information management system to integrate lessons from the biological corridors and user friendly operational

- By implementing the Knowledge Management and Communication Strategy (see Annex 12) the project will ensure that best practices are captured, documented and shared widely, and together with implementing the Gender Analysis and Mainstreaming Action Plan (see Annex 13), the project would ensure that information collection and sharing is inclusive and thus highly useful for future scaling up and replication. The Project will make good use of more modern techniques for knowledge management, including sharing via web-based platforms and social media. Knowledge Management will prioritize spatial knowledge arising from the terrestrial, coastal and marine planning processes employed within the biological corridors; written and oral knowledge of best practices; and a wide range of mapped, written, and traditional knowledge of biodiversity conservation and natural resources management.

- There are numerous databases in the Philippines, and the project will contribute to these existing databases and information sharing platforms, including at the DENR Regional Level. Data collection at biological corridor level will be integrated along with an improvement of the existing Knowledge Information System Service (KISS) database housed at DENR. Standards developed in Outcomes 1, 2 and 3 will include transferring all information into a digital format as well as establishing regular periods for information transfer. This database will support the collection and documentation of detailed information on species, habitats, threats, and conservation actions, ultimately improving the overall national and sub-national capacity and the ability to effectively target threats and risks.  Relevant information and knowledge will also be made available to existing key information systems of the DA and NCIP serving the needs of communities as well as that of DILG that serve the needs of Local Governments.  The project will catalog best practices and make them available via the web. For all categories (terrestrial/marine plans, and best practices), efforts will also be made to collect the discrete packages of information that are scattered throughout the country. Output 4.2 will support the following activities:

- Development of a simplified, standardized and dedicated information management system (including website and social media platforms) for biological corridors, including standards for information collection and sharing; and

- Biological Corridor Information Management System operationalized in each biological corridor, including data collection, input, on-line website and dissemination;

- Support for strengthening an information support system for the local federation of IP tribal councils to support sharing of good practices. In Year 3 for each of the 5 selected local IP small grants of USD20,000 per network to support consensus building and strengthening IK management;

- Setting up information collection standards that are: gender and socially inclusive; facilitate standardized inputting and recording of information; and provide for digital access and sharing, including compatibility with existing databases as feasible; and

- A cross-agency and cross-sector effort to collect and digitally catalog existing information on biological corridor planning, biodiversity and natural resources management best practices, resulting in a highly accessible, usable, and catalogued bibliography of available resources in support of replication and upscaling.

Output 4.3: Knowledge Management and project experiences contributes to learning and facilitates replication and scaling up of integrated biodiversity management approaches elsewhere in the country.

- Promotion of biological corridor IBM practices, as well as innovative approaches to conservation, sustainable terrestrial and marine resource use management, and sustainable livelihoods will be facilitated through a set of recommendations that can guide and influence future national and sub-national level policies, regulations and practices. Consultations with stakeholders from government, research organizations and others would be conducted to assess needs and gaps in policy outreach and advocacy.

- A replication strategy will be formulated in the second half of the project based on lessons learned at the field level that will ensure that the integrated biodiversity management planning approaches and models developed and tested in the two biological corridors are scaled up to other biological corridors within the country. This Output would support the analysis, documentation and dissemination of best practices and lessons learned that deliver tangible improvements in biodiversity and natural resources status to provide examples for replication. It would also entail participation in regional and international workshops, conferences and field visits for national and sub-national staff to improve learning and exchange of experiences in mainstreaming biodiversity considerations, and integrated biodiversity management and sectoral planning and practices. Based on these best practices and lessons learned, the replication strategy will provide a basis for actions in other key landscapes and areas, identify required institutional and coordination arrangements, resources and partnership commitments. Key activities under this Output will include:

- Documentation and dissemination of case studies, best practices and lessons learned from the project for use by targeted decision-making bodies in the corridors such as such as relevant committees of the local consultative councils, Protected Area Management Boards, networks of LGUs and networks of Ancestral Domain holders;

- Development of policy guidance notes that addresses current constraints and gaps in existing policies and legislation;

- Technical reports, publications and other knowledge management products (including in local languages and accessible to IPs) documented and disseminated via mass media;

- Documentation of Indigenous People’s cultural system related to natural resources management and disseminated to constrain or avoid the erosion of Indigenous Peoples’ cultures and justify increased public investments support to ancestral domains;

- National and sub-national workshops to facilitate dissemination of field lessons and help inform legal and policy reform relevant to biological corridor conservation practice. The initial documentation of these lessons will be included as part of the participatory monitoring process, that would be complemented by additional national technical support to distil and document lessons and experiences. The project will support workshops at the sub-national level (Year 5) to share lessons and experiences and a national workshop at the end of Year 6 (included in Output 4.3) to facilitate the sharing of lessons more widely, but importantly to be able to further develop and refine successful approaches for replication nationally;

- Efforts would be made to institutionalize some of the best practices through promotion of sectoral and/or national regulatory instruments in order to secure sector/nation-wide replication and upscaling. In order to expand access to finance for replication and up-scaling the project will collaborate with the private and public sector financial institutions to support local associations, landowners and other land users;

- Inclusion of public engagement pages on national and sub-national websites and social media platforms that link to information about the project and its products, including development of a specific public information sharing platform.  This in particular could serve to share information with PA managers, ICCA and LCA proponents and beneficiaries, local communities and NGO and government entities

- Preparation of a replication and scaling up strategy based on project experiences and best practices for promotion of integrated biodiversity management in biological corridors, including institutional, financial and resource requirements, partners and coordination arrangements;

- A DENR based Implementer’s Manual and Lessons Learned guide (with contributions from project partners) that captures the process of project implementation, and describes Integrated Biodiversity Management Strategies for biological corridors and SFM, SLM, OECMs (Other Effective Conservation Measures) approaches, Sustainable Livelihood improvements, mainstreaming of biodiversity in sector planning at sub-national level, etc. within biological corridors; and

- End of project national seminar on outcomes and replication for integrated biological corridor management practices in Philippines

- Partnerships:

- The proposed project will coordinate with selected government programs and specific projects associated with them to generate positive results through combined action (where appropriate) and to share lessons learned and best practices. They key national Environment and Natural Resources programs to work with include: National Greening Program (NGP), Community Based Forestry Program (CBFM), Master Planning for Agusan River Basin, and the ENR framework planning exercise of the DENR.  In the agriculture sector, the key national programs to work with would be the High Value Crops Program (HVC), the National Organic Agriculture Program (NOAP), the National Action Plan to Combat Desertification and Land Degradation and Drought (NAP DLDD) and the Special Assistance for Agricultural Development (SAAD).  On Indigenous People’s concerns, the project would work closely with the National Commission on Indigenous People (NCIP) proposed project entitled the Philippine Indigenous Peoples Ethnographies (PIPEs) which aims to accelerate support to ancestral domain management based on indigenous knowledge systems and practices (IKSP). To support mainstreaming ENR and biodiversity concerns into LGU programs, the project will collaborate with the Department of Interior and Local Government’s (DILG) program on Seal for Good Local Governance (SGLG). In support of biodiversity friendly enterprise promotion, the project will also work closely with the National Ecotourism Program co-managed by the DENR and the Department of Tourism (DOT) as well as the Strike Team Program for Indigenous Peoples (IPs), the Micro, Small, Medium Enterprises Development (MSMED)- Shared Service Facilities (SSF) Project, and Gender Responsive Economic Actions for the Transformation of Women (GREAT WOMEN) program of the Department of Trade and Industry (DTI), Department of Science and Technology (DOST), Department of Agriculture (DA), Bureau of Fisheries and Aquatic Resources (BFAR), Department of Labor and Employment (DOLE), small and medium enterprises (SMEs), and private sector representatives.

- In the context of the above and related core programs, the project will collaborate with agencies on knowledge and lessons learned from important, recently completed projects (which are described in the various sections of the project design), as well as ongoing and pipeline projects (usually assisted by donor/development partners). Collaboration with ongoing and pipeline projects would primarily aim to synergize planning and implementation with concerned projects in common sites. For projects without common sites, the main purpose is to build on each other’s field methodologies and share information needed for policy dialogue. The following are the key ongoing and pipeline projects

Table 3. Partnership Arrangements

| Name of on-going and planned program/project, years of implementation and sites | Program/project objectives and targets | How proposed UNDP/GEF project will collaborate with the program/project? |
| --- | --- | --- |
| Biodiversity Finance Initiative (UNDP-EU/BIOFIN) 2014 to 2018 | Enable government to build a business case for increased financing for biodiversity at national and subnational levels. | Build on the gains of resource mobilization assistance that BIOFIN provided to Mindoro Island LGUs. |
| Protect Wildlife Project (USAID/PWP) 2016-2020 | Capacity building for LGUs to address wildlife trade using IEM approach. | Learn from thematic learnings on IEM approach on biodiversity as used in their sites for possible adaptation |
| Enhancing Biodiversity, Maintaining Ecosystem Flows and Enhancing Carbon Stocks through Sustainable Management of Forest Resources and Restoration of Degraded Forestlands (GEF Trust Fund-FAO) 2019 | To deliver multiple and integrated environmental, livelihood and development benefits through the promotion of cost-effective and sustainable restoration of the biological and productive capacities of degraded forest and ecosystem. | Collaboration in common sites in Mindanao |
| Integrated Natural Resources Management Program (ADB/INREMP) 2013-2020 | With focus on indigenous peoples and resource-poor communities, address degradation of upper river basins and apply forest restoration alternatives. | Synergize with INREMP in terms of adopting successful forest restoration modalities used by INREMP. |
| Community-Based Forest Management AFoCO/CFM) 2014-2019 | Strengthen participatory CBFM planning using Geographic Information System and Remote Sensing Technologies. | Synergize activities in common site in Davao and CARAGA regions. |
| Forest Law Enforcement, Governance and Trade (EU-FAO/FLEGT) 2016-2020 | Strengthen forest governance through improved trade of legal forest products. | Synergize with FLEGT in common sites in CARAGA Region through improvements in trade. |
| Forestland Management Project JICA/FMP) 2012-2022 | Integrate conservation and development-oriented activities with full participation and capacitation of local communities. | Complement current activities of the Forestland Management Project at the selected sites. |
| Risk Resiliency and Sustainability Program (Climate Investment Funds - Pilot Program for Climate Resilience [CIF -PPCR]/RRSP) Under Preparation | Strengthen locally based climate risk resiliency in 5 regions in the country. | Synergize activities in Surigao Del Norte and Surigao del Sur in Eastern Mindanao by incorporating biodiversity management in local climate change adaptation systems. |
| Ecosystem-Based Management and Ecosystem Services Valuation in Two (2) River Basins in the Philippines (BMUB-GIZ) 2019 - 2022 | Demonstrate improved river basin management though ecosystems services valuation and ecosystems-based management. | Collaborate to incorporate high biodiversity conservation values in river basin planning interventions in Agusan River Basin in Eastern Mindanao Corridor. |
| Responsible Land Governance in Mindanao (BMX-GIZ) 2019 -2021 | Strengthen multi sectoral approach in improving land governance systems in Mindanao. | Collaborate to incorporate high biodiversity conservation values in land administration planning to support the updating of Region 13 Physical Framework plan. |
| Philippine Rural Development Project (World Bank/PRRDP 2014-2021 | Develop the platform for climate smart and market oriented agri- fishery sectors through infrastructure and value chain studies. | Collaborate in common sites in Eastern Mindanao for the promotion of agroforestry based - perennial tree crops through value chain approach. |
| Land Degradation Neutrality (LDN) Demonstration Projects (Under preparation) | Support land degradation neutrality actions in 5 River basins. | Collaborate to incorporate biodiversity conservation concerns in multi sectoral river basin-based planning in common sites (one candidate is in CARAGA). Demonstrate the methodology to become part of the Philippine UNCCD - LDN Program. |
| Strengthening National Systems to Improve Governance and Management of Indigenous People and Local Communities Conserved Areas and Territories (GEF-UNDP/Phil-ICCA 2015- 2019 | Institutionalize the ICCA mechanism as a sustainable addition to the network of biodiversity conservation areas. | Synergize in common sites in CARAGA Region and build on the lessons learned as basis for planning support to ICCAs under this project. |
| Conflict Sensitive Resource and Asset Management-Indigenous Practices for Conservation of Biodiversity Program-Phase 2 BMUB-GIZ/COSERAM- IP4Biodiv) 2015-2018 | Improve preconditions for peaceful collaboration between IPs and other population groups on biodiversity conservation in Agusan Wildlife Sanctuary. | Build on the recent COSERAM innovations and experience in supporting ancestral domain planning, ICCAS and Local Conservation Area (LCA) planning in CARAGA Region. |
| Small Grant Agusan Marsh Sanctuary Support (Foundation for Philippine Environment) | Support community participation in the development of Agusan Marsh Sanctuary | Collaborate with FPE and upcoming grantees to enhance the role of local IP network in Agusan Marsh Sanctuary programs. |
| Fifth Operational Phase of GEF Small Grants Programme (UNDP-GEF-NZAID/SGP-5) 2013- 2018 | Secure global environmental benefits through community-based biodiversity conservation initiatives and actions in selected priority sites. | Collaborate with BMB (oversight of GEF-SGP) to communicate learning and good practices of IP community grantees. |

- Stakeholder engagement

- A wide range of consultations with stakeholders have been conducted during the PPG stage. Initial stakeholder analysis during the PIF stage was followed up with consultation during the PPG stage in terms of the design of the project. During the PPG stage, the stakeholder analysis was updated and elaborated following consultations undertaken by international and national consultants at the biological corridor sites and with the provincial and municipal governments addressing both institutional stakeholders in the context of their statutory involvement in the project, and more broadly for non-governmental stakeholders including natural resource-dependent communities. A number of corridor level stakeholder workshops were conducted to obtain the perspective of the different stakeholders during the period April through November 2018. A number of bilateral meetings with future partners were also conducted. Series of validation workshops were conducted in Manila and the two provinces between December 2018 and February 2019 to discuss the project design and reach general consensus on project outcomes, outputs, activities and institutional arrangements for the project. See Table 4 below of listing of consultations. The list of stakeholders consulted has been downloaded in PIMS.

Table 4: Consultations Meetings

| KEY ACTIVITIES | DATE | STAKEHOLDERS |
| --- | --- | --- |
| 1st Technical Working Group (TWG) Meeting | April 16, 2018 | TWG Members (DENR-FASPS, DENR-BMB, DENR-FMB, DENR-Planning, DA-BSWM, DA-Planning, HLURB, NEDA, NCIP, FAO) |
| 2nd TWG Meeting | 2nd TWG Meeting | TWG Members |
| National Inception Workshop | April 26-27, 2018 | National Agencies, Regional Agencies, Civil Society Organizations (CSOs), Non-Government Organizations (NGOs) and other key stakeholders |
| Oriental Mindoro Inception Workshop | May 2, 2018 | Regional/Provincial Agencies, Local Government Units (LGUs) Indigenous Peoples (IP) representatives, NGOs, and other key stakeholders |
| Occidental Mindoro Inception Workshop | June 5-6, 2018 | Regional/Provincial Agencies, Local Government Units (LGUs) IP Representatives, NGOs, and other key stakeholders |
| Courtesy Meetings in Region 13 | June 12-14, 2018 | Region 13 National Agencies and other key stakeholders |
| National Commission of Indigenous Peoples (NCIP) En Banc 1st presentation | June 20, 2018 | NCIP commissioners and directors |
| Department of Environment and Natural Resources Divisions, Line Agencies and Bureaus Inception Workshop | July 6, 2018 | Key DENR Bureaus |
| NCIP En Banc Meeting 2nd presentation | August 16, 2018 | NCIP commissioners and directors |
| Eastern Mindanao Inception Workshop | August 23-24, 2018 | Regional Agencies, IP reps, NGOs, Mining Companies and other key stakeholders |
| Theory of Change Workshop | September 5-6, 2018 | TWG members, and key regional/provincial stakeholders |
| Region 13 Field visits to Regional Agencies, Provincial LGUs and IP consultation | September 10-13, 2018 | Regional Agencies, Provincial LGUs and IP representatives from different municipal LGUs |
| Capacity Assessment Workshops - DENR - DA - NCIP | August 31, 2018 October 18, 2018 December 20. 2018 | Key DENR bureaus DA Planning and BSWM NCIP Divisions |
| CSO/ NGO Meeting | November 5, 2018 | Key CSO and NGO stakeholders |
| 3rd TWG Meeting | November 6, 2018 | TWG Members, DENR-MGB |
| NCIP En Banc Meeting 3rd presentation | November 15, 2018 |  |
| Meeting with Mining Companies | November 16, 2018 | Select Mining Companies from Region 11 and 13, Chamber of Mines |
| Region 11 Courtesy Meetings | November 21-22, 2018 | Region 11 Agencies, IP leaders, NGOs and other key stakeholders |
| Eastern Mindanao Validation Workshop | November 27-28, 2018 | Regional Agencies, IP reps, NGOs, and other key stakeholders |
| Meeting IP leaders of Mindoro Island | November 29, 2018 | CENTRO (Mindoro IP Leaders) |
| Presentation to DA | January 4, 2019 | Key Offices and Bureaus of the Department of Agriculture |
| Davao Validation Workshop | January 10-11 2019 | Regional Agencies, IP reps, NGOs, and other key stakeholders |
| Region 4B Validation Workshop | January 15-16 2019 | Regional Agencies, IP reps, NGOs, and other key stakeholders |
| National Validation Workshop | January 31 – February 1 | National Agencies, Regional Agencies, NGOs, IP Reps and other key stakeholders |

- The purpose of the Stakeholder Involvement Plan (SIP) for the project is to ensure long-term sustainability of the project achievements, based on transparency and the effective participation of the key stakeholders. The objectives include the following: (a) to identify the main stakeholders of the project and their basic roles and responsibilities in relation to the project; and (b) to take advantage of the experience and skills of the main stakeholders, safeguard their active participation in different activities, reduce obstacles in project implementation, and sustain gains after project completion. The approach is based on the principles of fairness and transparency in selection of stakeholders, ensuring consultation, engagement and empowerment of relevant stakeholders. This is to ensure: (i) better coordination between them from planning to monitoring and assessment of project interventions; (ii) access of information and results to relevant persons; (iii) accountability of stakeholders; (iv) implementation of grievance and redress mechanism; and (v) sustainability of project interventions after its completion.

- Stakeholder involvement will enhance the planning and management of biological corridors in Philippines. Their engagement will secure the conservation of globally and nationally important biodiversity within these corridors, and mainstream biodiversity and sustainable natural resource use in socio-economic activities. DENR will be instrumental in establishing collaborative links with other national and local governments, CSOs and local communities, while local governments will coordinate with sector and local level stakeholders. The Project may solicit the services of NGOs/Civil Society Organizations (CSOs) to implement project activities.

Identification of Potential Stakeholders

- The SIP involves the identification of stakeholders at the national and subnational levels that would be engaged as project partners.  These include government entities, CSOs and local communities.

Role and responsibilities of key stakeholders and their Involvement Mechanisms and Strategies

- Mechanisms and strategies for stakeholder involvement will ensure that relevant shareholders: (i) receive and share information, (ii) provide inputs in the planning, design, implementation, monitoring and evaluation of project initiatives, and (iii) play a role in sustaining the initiatives during and after the closure of the project. Roles and responsibilities of main stakeholders of the project are summarized in Table 5 below.  Early in project implementation, the DENR will develop a more detailed Stakeholder Engagement plan that would ensure: (a) stakeholders’ involvement in project planning, implementation and monitoring; (b) stakeholders engagement in social and environmental screening and risk monitoring; (c) free, fair and transparent methods of information sharing; (d) implementation of gender mainstreaming strategy and action plan; (e) measures to empower stakeholders and potential project beneficiaries; and (f) disclosure and accessibility of information.

Table 5: Stakeholder Involvement Plan

| Key Stakeholder | Role and responsibilities / mandate | Proposed role in the project and involvement mechanism |
| --- | --- | --- |
| DENR HQ offices: - USEC /ASEC for Planning - Policy and Planning Services (PPS); - Human Resource Management Services (HRMS): - Knowledge and Information Services (KISS) - Foreign Assisted and Special Projects Service (FASPS) - Field Operations Office (including Asecs for Luzon and Mindanao Operations - GEF Operational Focal Point/Usec for Climate Change | USEC/ASEC for PP: Executive oversight of integrated policy formulation /planning. PPS: Oversees overall planning and programming and review of policy initiatives. HRMS: Develop and manage overall HR capacity building program. KISS: Plan and oversee interventions for KM and information management. FASPS: Oversight for project management and monitoring. Field Operations: Supervision of all field related program implementation. GEF Operational Focal Point: monitoring and evaluation of GEF programs | USEC/ASEC for PP: Convene IEM /IBM consensus building among DENER bureaus and among corridor multi stakeholders. PPS: Serve as advocate for integrated approach to planning, coordination and monitoring by DENR subsectors along IEM principles & oversees policy review. HRMS and KISS: Incorporate IEM & IBM in HR capacity; and knowledge management initiatives. FASPS: Facilitate linkages with other ongoing and planned programs and sharing of lessons from similar past or completed projects. Will also undertake overall coordination of implementation and M and E for DENR and reporting to oversight agencies. Field Operations: Facilitate synergy and mainstreaming in DENR wide program operations (cross sectoral); support sharing and lessons learning with other regions and sectors. GEF Operational Focal Point: Undertake portfolio level M and E; provide guidance and facilitate reporting to GEF. |
| DENR Bureaus: - Biodiversity Mgt. Bureau (BMB) - Forest Mgt. Bureau (FMB) - Mines & Geosciences Bureau (MGB) - Environment Bureau (EMB) - Land Management Bureau (LMB) - River Basin Coordinating Office (RBCO) - Ecosystems Res. and Devpt. Bureau (ERDB) | BMB: Coordinate implementation of NBSAP and of the NIPAS. FMB: Oversees forest management and National Greening Program & Forestland Tenure instruments. MGB: Oversees the mining sector development. EMB: Oversee the EIA process. LMB: Oversees land administration programs. RBCO: Coordinates River Basins master planning. ERDB: Serve as DENR’s ecosystems research arm. | Coordinated by USEC for Planning, all cited bureaus will be supported to incorporate BD corridor concerns in their respective subsector formulation of policy and standards and safeguards; national planning and implementation and technical assistance to LGUS and communities. BMB will serve as technical secretariat to Project Board and provide direct assistance to Corridor Councils through the R/DENR. Enter into MOAs with responsible partners for delivery of outputs. MGB: Will provide support in development/updating of policies to establish conservation areas within mining areas; and mainstreaming of BD in the management of mining companies’ Sustainable Development and Management Plan (SDMPs); and other applicable policies and guidelines. EMB will support in review of EIA guidelines for extractive industries in BD Corridors. FMB will support in strengthening alignment of the FAO GEF Project Enhancing Biodiversity, Maintaining Ecosystem Flows and Enhancing Carbon Stocks through Sustainable Management of Forest Resources and Restoration of Degraded Forestlands with this Project, and in review of Forest Certification Systems, incorporation of BD concerns in CBFMAs, and other forestry programs. RBCO will participate actively to ensure congruence with RB Master Plans and Strategies, and in implementation of these in the BD Corridors. LMB will support in alignment of their land management and titling programs with the BD Corridor strategies in the two sites and in the rest of the corridors eventually. ERDB will support through provision of expertise and assistance in research agenda for the BD Corridors. |
| DENR Regional offices - R/DENR for IV-B, 11 and 13 - Regional offices of MGB - Regional office of EMB | Implement national DENR programs at regional, provincial and district levels. Provide direct technical support to LGUs, and other stakeholder organizations. | All DENR regional offices: Incorporate BD corridor concerns in their respective programs and support for LGUS/communities. R/DENR: Act as convener of the Biodiversity Corridor and cluster committees (together with PLGU concerned). Provide operational leadership of implementation at corridor level. |
| Department of Agriculture - Policy & Planning Service Bureau of Soils and Water Management (BSWM) - Buresu of Agirculture and Fisheries Standards (BAFS) - Reg offices (IV-B, 11, 13) | DA develops and implements policies and programs for agricultural development. It also serves as the country focal point for land degradation neutrality and sustainable land management. Regional offices guide and enables LGUs implement devolved agricultural functions. | Policy and Planning Offices: Serve as PB member, oversee formulation of targeted policy instruments, and incorporation of BD corridor concerns in mid-term review of AFMA. DA-BSWM: Develop approaches for SLM and download to R/DA. BAFS: Complete recognition system for BD-friendly agriculture. Support LGU initiatives to include IP domains in OA programs. R/DA: Serve as core member of corridor /cluster committee, guide LGU in implementing BD friendly agriculture, and incorporate learning in DA strategic regional programs of work. |
| National Commission for Indigenous Peoples ( NCIP) - National HQ - Regional Offices (including provincial & area offices) in IV-B, II, and I3 | NCIP formulates and implements policies for the enhancement of IP welfare. It facilitates land security, ancestral domain planning and IKSP documentation and mandatory IP representation in governance. | National NCIP office: Serve as PB member and oversee preparation/updating of agreed upon policy instruments/ guidelines. R/NCIP: Serve as core member of corridor / cluster advisory committee, Facilitate interventions at Ancestral Domain levels (with supporting NGO) and factor learning in strategic regional program of work. |
| Reg Development Council (RDC ) & NEDA - RDC- Economics Committee (RDC/EC) - RDC- IP Committee (RDC/IP) - NEDA Agricultgue and Nautural Resources Service - NEDA Reg Offices( NRO) | RDC Economics Committee and IP Committee: Reviews sectoral plans for agriculture and NRM and IP affairs among others. NEDA NROs: Serve as the secretariat of the Regional Development Council and oversees preparation of Regional Plans. ANRES: NEDA HQ focal office for Agriculture and ENR affairs. | NEDA NROs will support in mainstreaming of BD Corridor Strategic Plans with Regional Development Investment Programs; Regional Physical Framework Plans and Provincial Physical Framework Plans |
| Other key agencies such as DILG, DTI, DoT, DOST, DEPED, CHED | Regional Agencies involved in planning and implementation of sectoral programs in the corridors particularly on local governance, trade & industry; Science and Technology, Education and Tertiary education | Their participation would be crucial in the formulation of the IEM framework, and in ensuring that their programs are aligned. |
| Department of Interior and local government (DILG) - Provincial, Municipal LGUs | DILG: Supervises /capacitates LGUs implement mandates. LGUs: Formulate and implement local policies /programs following the Philippines Development Plan (PDP). | DILG: Together with DENR review and update ENR guidelines for LGUs (incorporating incentives and capacity building). LGUS: Co- convene and serve as core members of corridor/cluster committee and plan and implement agreed upon priorities in respective areas. |
| National and local NGOs Such as Conservation International (CI), Haribon Foundation, Center for Conservation Innovations (CCI), Philippine Biodiversity Conservation Foundation Incorporated (PBCFI), Phil Association for Indigenous Peoples Development (PAFID), ANTHOWATCH, PANLIPI, RARE Philippines, Philippine Eagle Foundation (PEF), Mindoro Island Biodiversity Conservation Foundation, Inc. etc. etc. | These NGOs have ongoing activities in the project sites and have active partnership with BMB in advocacy, national PA system planning, monitoring and management. They undertake technical studies to provide scientific basis for establishment and better management of PAs and conservation areas; and in engagement with local stakeholders in addressing threats to BD loss. | These NGOs are expected to work with the DENR and corridor/cluster committees to ensure the best partnership arrangements of communities in their areas with the project. The DENR will execute MOAs with these groups to assume responsibilities for the implementation of defined activities in each site. |
| NGO networks and grant funding mechanisms such as Forest Foundation of the Philippines (FFP) and Foundation for Philippine Environment (FPE) | They support initiatives of local communities in sustainable management of natural resources in KBAs within the corridors. | They will be engaged to provide co-financing to support activities of local communities and local NGOs in implementation of identified priority actions to address threats to biodiversity consistent with the agreed upon framework. |
| Indigenous peoples such as IP networks and local communities (farmers engaged in agriculture, upland forestry, and other economic activities in the corridor) | They are the direct and primary stakeholders in the Project. They stand to benefit from the Project and suffer the consequences of environmental degradation in the corridor. IP communities have strong historical and cultural ties to their domains, which coincide with existing PAs and potential conservation areas. Their indigenous practices and knowledge systems are mainly consistent with conservation objectives. Some communities are engaged in unsustainable practices, while some are already engaged in conservation activities in their farms. Some would have secure tenure while others may have no secure tenure yet. | IP communities will be supported in the preparation of ADSDPPs identification and mapping of ICCAs, and that are consistent with the corridor framework. A representative of national IP Federation will be selected to be a member of the Project Board. Together with IP communities, local communities will be the Project’s target in terms of incentives, information and extension campaigns, and promotion of sustainable agriculture and biodiversity-friendly livelihood practices The Project will also enter into partnerships with organized communities to influence their farm planning and management practices to ensure consistency with the IEM framework. |
| Women and youth | They are generally a neglected group in the management structures and decision making at the community level. However, they have a lot of potentials to contribute to changing practices and attitudes particularly from those that lead to excessive utilization of natural resources. | They will be provided with ample opportunity to take part in the formulation of the project. They will provide their special perspective to the preparation team so that their potential can be harnessed during implementation. Furthermore, their concerns will be fully considered in management planning. |
| Academic and Research Institutions | They undertake research and other advocacy activities in the regions/provinces where the corridors are located. | They will advise on the necessary research and other studies and in sharing of scientific information on the sites. The Project will enter into MOA with these organizations to carry out baselines and long-term monitoring of changes and impacts on the corridor. |
| Private sector such as: holders of industrial forest management agreements, investors in ecotourism, mining operators, etc. Business associations and Partnership initiatives for green business and corporate reforms such as the EITI | Most companies have policies on corporate social responsibility that can potentially support direct conservation efforts. Their actions directly impact on use of biodiversity resources. | The Project will engage actively with the private sector to explore and access potential investment opportunities to support BD friendly enterprises based on the corridor framework. Selected mining firms will be engaged to voluntarily apply updated biodiversity conservation protocols. |
| Development partners such as: ADB, World Bank, GIZ, USAID etc. | They have ongoing and planned initiatives in the sector. They engage in active dialogue with BMB and DENR in assessing overall sector performance, and in defining areas of future support. | The project preparation team will ensure that there is synergy with other Projects, and that all initiatives are consistent with the overall strategic directions and policy framework. |

- Outputs 2.1 and 2.2 and Annex 3 (Framework for IEM, Consensus building and Planning and Implementation) further describe the various planning and implementation processes that engaged stakeholders in substantive ways throughout the project period (see Annex 14 for Stakeholder Engagement Plan).

- Gender equality and empowering women:

- Women are directly engaged in agriculture and natural resources management, particularly among local communities in the corridors. They are expected to significantly influence current practices, and can be effective community advocates of sustainable natural resources management strategies. Among IP communities, there are clear roles for women as leaders, resource managers, trainers of the youth, and peacemakers.  Among farming and fishing communities, women make important decisions regarding production, and have vital roles in marketing of the produce, allocation of domestic resources and harvests. As nurturers of families, women are most directly affected by resource degradation or drastic changes in natural resources productivity.

- In the Philippines, earlier gender analysis done by the Department of Environment (DENR) and the Philippine Commission on Women (PCW) in ENR sector revealed inequalities in status and condition of women and men in different areas and are manifested in the following:

- Norms, attitudes, and institutions that limit women’s and men’s life options

- Women’s limited access to land and natural resources

- Low participation of women in governance and decision-making processes and in project activities

- Gender-role stereotyping and women’s multiple burdens and various forms of violence against women and girls

- Unequal access to resources and services to improve their productive and reproductive work

- Limited access to education and health services

- In this regard, this project will seek to understand and expose gender-differentiated biodiversity practices, gendered knowledge acquisition and usage of, as well as gender inequalities in control over resources in selected biodiversity corridor sites in Regions XIII (CARAGA), XI (Davao), and IV-B (Oriental and Occidental Mindoro), which will inform policies regarding biodiversity conservation, sustainable use and the sharing of its benefits. It will also consider the influences of gender differences and inequalities on the conservation and sustainable use of biodiversity, and the ways in which these differences and inequalities influence how women and men in selected sites are affected by biodiversity policies, planning and programming.

- The direct beneficiaries will be at least 65,000 individuals belonging to 15,000 households (at least 50% of beneficiaries are women, with which 25% are IP women) who will benefit from four inter-related components of the project. Likewise, the project will support 24 Municipalities in selected landscape that are expected to benefit from capacity building programs under this project.

- A screening of the UNDP social and environmental screening (SESP) (see Annex revealed a potential risk related to gender: “Project potentially may limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services while also facing potential of having adverse impacts on gender equality and/or the situation of women and girls”. This risk will be managed through the project. A gender analysis was undertaken at PPG stage to determine the differentiated roles of women and men in biodiversity conservation and natural resources management, the impacts of biodiversity loss and resource degradation on women, and their potential role in reversing these trends. The results have been used to develop gender-responsive project interventions including sex-disaggregated indicators that will become the basis for monitoring and evaluation of the Project’s impact on promoting gender equality and empowerment of women and youth including through the application of the UNDP gender maker. In addition, this gender assessment will also identify areas where negative impacts can be reduced and positive ones enhanced.  During the implementation period, the project will  ensure  equal opportunities for women and men to participate in decision making. Steps will be taken to ensure that women’s needs and interests are taken into account in management arrangements set up by the community, including encouraging women (particularly IP and rural women) to actively participate in community meetings and platforms that discuss project activities. In addition, gender and social inclusion considerations have been integrated into the project design (under Output 4.1).

- Gender mainstreaming in the project will be addressed (see Annex 13) through the following actions:

- Ensure that project materials, including meeting agendas, reporting templates, communications materials, and all written policies include gender and social mainstreaming.

- Create and require minimum standards for planning teams, including representation from multiple gender and social groups and/or tasking of planning team members to speak for vulnerable peoples.

- Capacity building and training for project staff and planning team facilitators to include the input of multiple groups into resulting plans.

- Support research and mapping of: (i) current gender roles and how they have changed between generations in each of the development sectors (agriculture, NTFP collection, grazing, and tourism, etc.; (ii) gender and social group uses and use patterns of land habitats; (iii) market access by gender; (iv) mapping of the tourism sector by gender and social group; and (vi) applying a gender and socially inclusive lens to all research plans and priorities to ensure that multiple groups’ data needs are filled.

- Invest in staff to enable adequate connections with multiple groups. Instead of general community meetings, meetings with (i) women’s groups; (ii) men’s groups; (iii) youth groups; and (iv) individuals with access to or influence over vulnerable people (e.g. IP leaders, landowners, or church leaders).

- Capacity building and training for project staff and planning team facilitators to better engage multiple gender and social groups.

- Apply a gender and socially inclusive lens to every meeting, report, plan, and activity.

- Apply sex disaggregated targets and baselines where appropriate, as part of project monitoring plan.

- Conduct economic and social analyses of proposed land and forest plans resulting from the project, and all other outputs (such as proposed protected areas and implementation plans for best practices).

- Implement the Communications Strategy, including holding multiple, targeted meetings by disaggregated groups.

- Make better use of digital platforms in order to create oral/audio content, with less emphasis on writing to better communicate with IP groups, rural women, farmers, and youth.

- Incorporate gender and socially-sensitive indicators and collect sex disaggregated data for monitoring and evaluating project results.

- Recruitment of gender specialist to facilitate the implementation and monitoring of the gender plans and for capacity building and training of key implementing agency staff.

- Risk Management:

- As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log (Annex 15).  Risks will be reported as critical when the impact and probablity are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR.

Table 6: Project Risk and Mitigation Matrix

| Project risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A. General Risks |  |  |  |  |  |
| Description | Type | Impact, Probability and Risk Level | Mitigation Measures | Owner | Status |
| Risk 1 - Agencies will fail to agree on the IEM framework as basis for integrated planning, management and implementation of programs in the corridor. The inherent conflicts in policies and orientation of mandates and programs will make it difficult for agency representatives to be flexible in their interpretation, thus hindering them to agree to a re orientation of their planning and management frameworks. | Institutional | I =1, P=2 Low | The Project will undertake studies to demonstrate the interrelationships and cross-sectoral impacts of various programs on the ability of the corridor to sustainably deliver ecosystem goods and services. The study will involve the active participation of agency staff at the central and field levels in each of the corridors to engender ownership and joint analyses of results. The Project will use this information to make the case for a multisectoral approach to deliver sustainable benefits. There have been examples of interagency cooperation towards common objectives. These mechanisms shall be explored to achieve convergence of agency programs based on mutually agreed strategies. The Project will progressively work towards this institutional set up, and will find existing mechanisms as venues for corridor level coordination of efforts. Such arrangements will be a product of the processes to be undertaken under the Project rather than as a precondition to implementation. Efforts will be made by the Project to make the case for greater cooperation by demonstrating the added benefits of doing so, rather than the traditional independent approach to natural resources management and BD conservation. | NPD, DENR | Implementation phase |
| Risk 2. It will take time for inherent resource conflicts to be resolved which could delay Project start up and progress. In many of these resource rich areas, the reality on the ground is that administrative failures, fragmented mapping, absence of coherent management framework, have brought about overlaps in community tenure and long term commercial leases on public lands. | Socio-political | I- 3 P- 3 Moderate | The Project duration is proposed to be 6 years to account for time for negotiations and settlement of resource use conflicts. Nonetheless, the essence of the Project is really to minimize such ‘conflicts’ and ensure synergy by developing a common framework for BD corridor management that is based on sufficient information, system of incentives, and mechanisms for resolving inconsistencies in natural resources use. | NPD DENR | Implementation phase |
| Risk 3: Long gestation periods for alternative livelihoods, and restoration of forest resources can undermine community participation | Social-Political | I-3 P-2 Moderate | Cluster Conservation Plan activities will entail a menu of options (including activities with short-term gestation periods as buffer until longer-term investments generate sustainable benefits) to help diversify the livelihood and resource base, including linkage with on-going governmental and NGO programs to supplement and complement project activities. The project will also seek to identify additional options (PES, REDD+) as means to improve incentives for local people | NPD DENR | Implementation phase |
| Risk 4 – Financial sustainability of BCs beyond the duration of the project is not ensured | Institutional | I-3 P-3 Moderate | The prevailing limited capacity on benefits from conserving ecosystem services to the economy and livelihoods, and continued Government primary focus on economic development results in financing for biodiversity conservation remaining significantly lower than their needs. Output 4.3 of the project entails the preparation of a sustainability plan for promotion of biodiversity conservation in biological corridors that would entail a number of key actions to guarantee financial sustainability. | NPD DENR | Implementation phase |
| Risk 5 – Security in some selected sites | Political | I-3 P-3 Moderate | Some sites are located within areas that are reported to have had security issues before in terms of military activities and the presence of armed groups from 2 or three rebel organizations. All field activities of the project will follow standard health and safety regulation set by both DENR and UNDP. This will involve securing mandatory security checks, clearances and coordination with local and provincial law enforcement authorities. | GOP | Implementation phase |
| B. Social and Environmental Risks |  |  |  |  |  |
| Risk 6. The two corridors have resource conflicts within PAs (e.g. within ancestral domain/CATC/CATD; ICCA; LCA) that could be exacerbated if the activities are not well implemented | Socio-political | I- 3 P- 3 Moderate | (i) At the PPG stage, a master list of clusters, geopolitical jurisdiction, coverage of protected areas and ancestral domains was prepared to serve as a guide for the PMU so that “conflicts” are minimized (Annex 6). (ii) A Participatory Framework for IEM, Consensus Building and Planning and Implementation (Annex 3) will be applied to ensure that community (including IP) concerns are addressed in a timely and efficient manner using FPIC procedures as defined by NCIP AO 1 (ii) A screening checklist based on the SESP that will be developed early in project implementation (to screen all investments to ensure that they comply with sound social and environmental principles and is sustainable; (iv) The project grievance redressal system (refer Section IV, Part iii of UNDP Project Document) provides a mechanism to address any specific community concerns and resolve conflicts. (v) An Indigenous Peoples’ Strategy (Annex 16) prepared at the PPG stage has mapped out existing resource conflicts in potential pilot ancestral domains and this will be updated as the project implementation progresses. | NPD | Implementation phase |
| Risk 7: Development interventions (e.g. MSMEs, eco-tourism etc.) can have adverse impacts on species and habitats if not well implemented. | Environmental | I - 3 P -2 Moderate | (i) The criteria for the selection of clusters (Annex 6) for intervention, conformed to the project’s objective of ‘enhancing the conservation of biodiversity through mainstreaming of biodiversity into planning policies and practices into Philippine’s biodiversity landscapes. (ii) All community agriculture and production systems and livelihood activities will take place outside the key biodiversity areas through appropriate zoning arrangements. (iii) The Preparation of a screening checklist developed using SESP will be applied to screen all investments to ensure that they comply with sound social and environmental principles (iv) Setting acceptable sustainable limits on harvest of non-timber forest products based on status and health of such populations and establishment of monitoring protocols. | NPD | Implementation phase |
| Risk 8: Improved zoning of the corridors for multiple different uses, community human rights, including access may be restricted in twelve clusters of the two biodiversity corridors in Eastern Mindanao and Mindoro. This will include indigenous communities located in ancestral domain areas, and CADCs/CADTs. | Social | I - 3 P – 3 Moderate | (i) Apply the Framework for IEM (Annex 3) to ensure that project activities are detailed in collaboration with Provincial and Municipal governments and local communities, to delineate areas to be set asides in a manner to avoid limitations on existing community resource use rights and access; (ii) The establishment of KBAs, HCVFs (refer Annex 6) that will be planned and managed under community governance mechanisms will take into consideration current uses of these resources (iii) The development and use of a screening checklist for project investments based on SESP to screen all investments; (iv) Project planning will ensure that decisions regarding restrictions, if any, on resource use will not be imposed, but will involve through an informed, transparent and consultative community consensus building process (refer Annex 6), and any restrictions, if any will be adequately compensated to match or exceed loss of incomes or livelihoods. An alternative livelihood development plan will be prepared early in project implementation (Year 1) for any households that are likely to be denied access to resources or current livelihood practice and (v) The project grievance redressal system (refer Section IV, Part iii of UNDP Project Document) provides a mechanism to address any specific community concerns. (vi) Use of FPIC procedures patterned after NCIP AO No. 1 to ensure consent regarding project investments | NPD | Implementation phase |
| Risk 9: The project could possibly affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources of marginalized groups and indigenous people | Social | I – 3 P – 3 Moderate | (i). The Implementation of participatory IEM planning processes (Annex 3) to ensure that consultations and feasibility studies, particular related to lands claimed by IP community is carried out early project implementation to ensure that effective consultation takes place and community consent based on FPIC procedures prior to deciding on specific location, nature and scope of project investments. under ancestral domains. (ii) MoUs will be agreed to between the IP communities and project proponents on project investments before activities are implemented on the ground. (III) Engagement of parties through under the Grievance Redressal System to address any conflict between the government/municipal entities and IPs. (iv) Use of project screening checklist based on SESP to ensure that they comply with sound social and environmental principles, and in particular do not conflict with IP community resource uses. (iv) Preparation of an Indigenous Peoples Plan (Annex 16) at the PPG stage addresses specific concerns relating to IPs, including tenure issues. | NPD | Implementation phase |
| Risk 10: Women (IP and rural women in particular) and other marginalized groups may not be fully involved in planning, implementation and monitoring of project interventions and getting benefits from such initiatives, rather influential leaders and/or groups at the local level may have more control on local level decision making. | Social | I - 3 P – 2 Moderate | (i). A number of extensive consultations were held during the PPG stage to access the level of participation of women in the implementation phase of the project and to design measures to ensure their active participation in all stages of the project. (ii) The “Gender Analysis and Mainstreaming Action Plan” (Annex 13) discusses how perspectives, rights, and interests of men and women are addressed will be applied to ensure that the project contributes to gender equality and creates equitable opportunities for women and men (iii) A gender and socially inclusive lens will be applied to every project activity and output to further analyze impacts on the rights of women and vulnerable peoples. (iv) Special investments would be planned based on women’s requirements. (v) A series of capacity building programs would be conducted to enhance the capacity of women and vulnerable members to take an active part in the planning and decision making process at the corridor/cluster level. (vi) At the program and project level implementation arrangements, a Gender Specialist will be posted at the Project Management Unit. (vii) Monitoring Plan has gender responsive indicators to access gender dimensions, including that the project scores a Gender Scorecard 2 Marker. |  |  |
| Risk 11 Natural disasters and climate change may affect the implementation and results of project initiatives | Environmental | I – 3 P – 3 Moderate | (i). The Implementation of participatory planning processes for IEM (Annex 3) will be carried out ensuring that activities are environmentally sustainable and supporting best practices managed for their climate risks. (ii). Enhanced Protected Areas management, Other Effective Area-Based Conservation Efforts (OECMs) and conservation practices would improve protection and management of critical ecosystems services which should help to increase the overall resilience of the natural systems. (iii) In terms of the Monitoring Plan, the condition of the natural ecosystems would be monitored to ensure that activities do not damage these sensitive ecosystems (iv). The KM and Communications Strategy (Annex 12) is a key framework to improve awareness of climate and ensuring measures to improve climate resilience | NPD | Implementation phase |
| Risk 12 – Free and Prior Informed Consent (FPIC) has not yet been secured | Institutional/Political | I - 3 P – 3 Moderate | (i) Use of NCIP AO No. 1 or the FPIC Guidelines of 2006 as means to obtain consent. (ii) The Implementation of participatory planning processes for IEM (Annex 3) to ensure that consultations and feasibility studies, particularly related to lands claimed by IP community is carried out early project implementation to ensure that FPIC procedures are applied (iii) MoUs will be agreed through an open and free dialogue between the IP communities and project proponents on project investments before activities are implemented on the ground (v) Engagement of parties through under the Grievance Redressal System to address any conflict between the government/municipal entities and in particular to ensure that there is FPIC before project activities and their locations are decided on. | NPD | Implementation phase |
| Risk 13 – The cultural identity of the IP might not be respected and/or IP knowledge (or other forms of cultural heritage) might be inadvertently harmed during project activities that intend to preserve and/or utilize it. | Political | I-3 P-3 Moderate | (i) The use of the IP Plan prepared during the PPG stage of the project will form the basis for dealing with the interests of the IPs (ii) The effective use of the grievance redressal system Section IV, Part iv) to address these specific concerns; (iii) The use of a screening checklist based on SESP to screen all investments from an environmental, social and cultural perspective (iv) Any project related economic development initiatives proposed by IP communities will rest on the maintenance of the integrity of IP culture and defined through the use of FPIC procedures | NPD | Implementation phase |

- Social and environmental safeguards:

- The Social and Environmental Screening Procedure (SESP) was followed during project preparation, as required by the SESP Guidance Note of the UNDP. Accordingly, the social and environmental sustainability of project activities is in compliance with the SESP for the project (see Annex 17). The SESP identified high social (particularly as there are IPs in the project areas) and environmental risks for this project that would have potential negative impacts in the absence of safeguards. To avoid any potential for any likely impacts, the project will ensure Social and environmental screening of all proposed investments to determine if there are any impacts. If the impacts are considered significant or cannot be managed by simple and practical mitigation measures that can be implemented within the capacity of the communities, these activities will be avoided. When impacts are easily manageable, the PMU would include responsibilities for ensuring oversight for these measures and monitoring of its implementation. Annually supervision missions will assess the extent to which the risks have been identified and managed. Overall, the project is expected to result in positive impacts for biodiversity conservation and socio-economic benefits through the greater participation of local communities in biodiversity corridor management processes, sustainable use of forest and resources, and improved natural resources-based livelihood activities.

- Specific efforts will be made while evaluating the condition of resources that will be used in livelihood and value chain programs to ensure that extraction is permissible within sustainable limits. Harvest of non-timber forest products (such as abaca, rattan, nito, medicinal plants and other products) that are currently practiced will follow ecologically friendly and sustainable practices. The project will ensure defining specific areas and harvest rates on the basis of good practice criteria backed by scientific information and close monitoring.

- The project does not involve large-scale infrastructure development. The project will not support employment or livelihoods interventions that may pose a potential risk to health and safety of communities and/or individuals or to biodiversity and ecosystem functions. While the project will not propose any temporary or permanent physical displacement, nor will there be the need for land acquisition or access restrictions, in cases where this is unavoidable, the project will prepare a Livelihood Action Plan for affected households to ensure that this risk is effectively managed and affected households have access to similar or better land and livelihood options.

- Any restrictions on access to and use of natural resources would not be imposed by the project proponents but would evolve through a collective decision-making process amongst the community members and be supported by alternative livelihood and resource measures that adequately compensate for any loss of income or resources. Grievance redress mechanisms will facilitate the resolution of any conflict related to resource use and access.  An Indigenous People’s Framework has been developed that provides guidance for preparation of an IP Plan during early project implementation for ensuring that Indigenous peoples and vulnerable groups (such as IP and rural women) are fully involved in decision-making in terms of resource use, livelihood and income generation investments and conservation action. The project will support the recruitment of IP consultants to help develop and monitor the application of FPIC principles, preparation of the IP plan, undertake social assessments in IP areas and train and sensitize staff in the application of FPIC principles and practices. Specific institutional and administrative arrangements have been defined that encourages active participation of all households in a village and capacity building programs. For further information on social and environmental aspects and management measures refer UNDP SESP in Annex 17 and IP Strategy (see Annex 14). A screening checklist will be developed based on the SESP during early project implementation to screen all investments to ensure that they comply with sound social and environmental principles. Project proponents will apply FPICs as discussed in the Indigenous Peoples’ Plan as the basis for involvement of IPs in project related activities.

- In line with UNDP standard procedures, the Project will set up and manage a grievance redress mechanism (GRM) as recommended by UNDP (2014) that would address project affected persons’ (PAP) grievances, complaints, and suggestions. The GRM will be managed and regularly monitored by the CPMUs and NPMU. It will comply with the following requirements.

- The intent of the GRM is to (i) receive and address concerns, complaints, emerging situations or conflicts, grievances and any harm arising from the project; (ii) assist in resolution of grievances between and among stakeholders, including project implementing agencies; and (iii) ensure flexibility, transparency and collaboration with the aim of problem solving and consensus building.

- The functions of the GRM would be to: (i) receive, log and track grievances; (ii) provide regular updates on grievances resolution; (iii) engage all necessary stakeholders to facilitate grievance resolution; (iv) propose solutions to resolve grievances in a defined timeframe (around 60 days); (v) recommend possible precautionary measures to avoid the more common grievances; (vi) make available bi-annual reports on grievances and resolution measures available to the public; (vii) Increase awareness, accessibility, transparency and credibility to the GRM process; (viii) collaborate with partner institutions and CSOs to increase awareness to the GRM and its access; (ix) ensure continuing education of project entities to laws and policies related to GRM; and (x) monitor grievance resolutions and solutions.

- Management of GRM: The GRM will be managed by DENR (national level), DENR Regional/Provincial Offices, CPMUs within the Biological Corridors and LGUs.

- Communicating a Grievance through multiple locations and channels from grassroots level up to the Provincial and National Level: A simplified system of informing about the grievance redress system and also actual management of grievances will be developed under the project. Multiple ways (manual as well as virtual) of submitting complaints or suggestions at various levels will be provisioned in the project. Grievances and suggestions will reach the LGUs in person, via mail, email, via special page of the Project website, and phone.  These channels will be locally-appropriate, widely accessible, and publicized in written and verbal forms on all project communication materials, and in public locations in the project areas. Since the project will be dealing with local community and IP members, natural resources based small entrepreneurs and producers of non-farm products and services at the local level, they will be facilitated to communicate their problems through their collectives like CBOs, NGOs, IP groups, etc. They will also be able to communicate directly to the CPMUs. These teams will be responsible for the functioning as an interface for the grievance redress mechanism.

- Process of informing and registering grievances at various levels: All grievances, whether received through LGUs, DENR Regional Offices and CPMUs or to a member of the Corridor Advisory Committee, will be registered by either the LGU, DENR Regional Offices or CPMU. The complaint will be assigned a unique tracking number upon its submission. The CPMUs will maintain a database with full information on all submitted complaints, responses taken and solutions of the problems.

- Complaint Resolution System: A clear system of complaint resolution will be developed to ensure timely resolution of grievances of the stakeholders. The grievances of the stakeholders will be of different types therefore the grievance will be classified into three types:

- Local level problems related to compensation/payments etc. (LGUs)

- Project implementation related problems (DENR Regional Offices or CPMUs)

- Grievances / Problems that require policy decisions/ decisions (DENR National Level)

- Procedures will be developed and observed, and personnel at provincial level will be assigned to handle the grievances. LGUs, Regional DENR Offices and/or CPMUs will follow nationally developed clear and strict grievance redress procedures, and assign responsibilities. Difficult situations and conflicts will be brought to the attention of DENR and UNDP CO if the State Government is unable to find appropriate solution.

- Repository of grievances and solutions and sharing it on the project website: A repository of all the grievances received from the different stakeholders will be maintained at DENR for monitoring and evaluation purposes and also for learning.  The grievances and their solutions will be shared through the project website so that each province will be able to learn from the other. This aspect will be facilitated through Outcome 4 relating to communication and knowledge sharing. Further, this information will be used to assess trends and patterns of grievances across the project landscapes and for monitoring and evaluation purposes.

- Maintaining Communications and Status Update and provision of feedback about the compliance of grievances: A system of giving feedback will be developed to give response to all registered grievances. DENR Regional Offices and CPMUs will provide feedback by contacting the complainant directly or their state coordinating committees so that complainants are aware about the status of their complaint. Once some decisions/actions are taken on the complaint, the complainant will be informed about the same. If complainants are not satisfied with the DENR Regional Offices and CPMUs response to their grievance, they will be able to appeal the DENR/NPMU decision and UNDP CO via mail, e-mail or the Project website.

- Investigation and Consensus Building: (i) within one week of receiving a Grievance, the implementing partner will notify the relevant manager of the GRM at local, provincial or national level Management Team of the receipt of the grievance; (ii) the relevant manager of the GRM will identify a specific team of individuals to develop a response to the Grievance; (iii) this team will engage the Claimant and any other relevant Stakeholders deemed appropriate, to gather all necessary information regarding the Grievance; (iv) make a request to the appropriate institutions any information (documents or otherwise) relevant to resolving the Grievance and avoiding future Grievances of the same nature; (v) convene a meeting relevant individuals and credible local institutions as needed; (vi) develop a thorough understanding of the issues and concerns raised in the Grievance and facilitate consensus around a proposed solution and way forward; and (vii) seek any advise required  to resolve the Grievance.

- Making proposed actions and solutions public and overseeing implementation: Communicate to the Claimant proposed actions or resolutions and clearly articulate reasons and basis and way forward, and suggest alternative options if the Claimant is not satisfied with the proposed actions.

- Mediation: If mediation is required ensure professional expertise and impartial mediation; ensure mediation in local language; and ensure that mediators are willing to mediate without prejudice to personal relationships and interests.

- Monitoring and evaluation: The performance of the GRM will be regularly monitored.  All information about the grievances and their resolution will be recorded and monitored. This data will be used to conduct in-depth analyses of complaint trends and patterns, identify potential weaknesses in the Project implementation, and consider improvements. Environmental and social grievances will be reported to the GEF in the annual PIR. The full Social and Environment Screening Procedures (SESP) report is included in Annex 17.

- Sustainability and Scaling Up:

- The project will address sustainability as follows:

- Financial sustainability will be achieved through: (i) ensuring that through the integrated biodiversity management planning exercise for the corridors, the provincial, regional and municipal entities will facilitate the convergence of sub-national government financial resources to support conservation and sustainable community livelihoods that would help financially sustain activities beyond the life of the project; (ii) ensure a partnership arrangement between provincial, municipal, community, NGO and private sector partners within the biological corridors that will ensure complementarity and cost-effectiveness of multiple partners and investments; (iii) develop new business models for biological corridor conservation, livelihood and value chains that recognize the full range of environmental ecosystem services provided by biological corridors and their attendant ecosystems. Developing market linkages for sustainable forest and agriculture products and services, ecotourism and local handicrafts and establishment of “brand” labels will ensure financial sustainability of local livelihoods; (iv) support for establishment of Community level revolving funds that will help to financially sustain and expand investments beyond the project period; (v) facilitating market linkages, green certification of biological corridor products and services to improve sustainability and value addition; and (vi) training of local entrepreneurs and enterprises.  Implementation of such models through carefully developed business plans could lead to a diversification of funding base from sources such as ecotourism, NTFPs and other mechanisms, when these becomes available.

- Institutional sustainability will be improved through systematic capacity development of existing public institutions (particularly that of DENR, DA, NCIP, etc.), local government, networks of Indigenous People and civil society organizations and local community groups, and other relevant sectors in the biological corridors. By engaging these stakeholders in conservation and livelihood investment planning, the project will help establish alliances for conservation and sustainable use of biological corridor resources that is expected to continue beyond the project period. Capacity building measures will be improved by integrating these programs into the curricula of training institutes (including farmer field schools and locally-based agricultural schools). Carefully tailored training and capacity building to enhance the skills of local communities in relation to sustainable NTFP, SLM, SFM, ecotourism and other local producers will provide institutional sustainability. The project’s institutional arrangements will further help build coordination structures at the national and corridor level with representation from different development sectors and stakeholders (including sub-national government entities, NGOs and private sector) to implement joint biological corridor planning and to ensure that development plans mainstream biodiversity policies. To ensure sustainability of institutional arrangements for integrated biodiversity management planning and ensuring mainstreaming of biodiversity policies into socio-economic development plans, the Government of Philippines will work towards institutionalization of these coordination mechanisms as part of its long-term strategy to streamline and support biodiversity goals. Formalization of these coordination arrangements will enable sustaining and scaling up of benefits of the project in terms of integrated ecosystem management planning and biodiversity mainstreaming within the biological corridors.

- Social sustainability will be improved through the development/strengthening of stakeholder participation mechanisms for the target biological corridors. A Knowledge Management and Communication strategy (see Annex 12) has been developed to facilitate awareness and enhance stakeholder participation. The Participatory Framework for Integrated Ecosystem Management, Consensus Building and Planning and Implementation (see Annex 3) was designed during PPG stage to ensure adequate consultation and participatory decision making to ensure that project activities are detailed in collaboration with local communities, so that extensive consultation including all affected groups is undertaken prior to delineation of areas to be set asides, so as to avoid excessive community resource use areas or to improve the management of such uses.  Social sustainability will also be achieved by strengthening of community institutions, ensuring their active participation in planning and implementation of conservation and sustainable natural resources management, improving community capacity for management of CCPs and for improving grievance redressal mechanisms that will ensure social sustainability.

- Environmental sustainability will be achieved through a coordinated approach involving improved protected area management approaches, sustainable natural resources, forest and fisheries management, securing improved forest restoration and sustainable NTFP use, improving incentives for conservation and community participation. It would also help in reduction of external threats on PAs and wildlife through biological corridor level partnerships, will enhance controls on poaching, and improve inter-provincial collaboration. This work at biological corridors is aimed at ensuring environmental and socio-economic sustainability through improved institutional capacity, policies and legislation.

- Innovation: The project design is innovative in several ways. First, it proposes to pilot the first programs in Philippines for integrated ecosystem planning and management planning and management in large landscapes and seascapes (or biological corridors). The project seeks to mainstream biodiversity conservation outcomes in sectoral and provincial economic planning.  This approach, that would involve multi-stakeholder planning and an inter-sectoral coordination approach to biological corridor management in Philippines would propose the following approaches: (i) a biological corridor should be viewed as a system in itself, comprised of various natural, cultural and socio-economic components; in turn, it is part of the bigger national, regional, thematic, and global networks of biological corridors; (ii) biological corridors would be appropriately zoned by ecology-based planning using a patch-corridor-matrix model for biodiversity conservation, taking account of landscape ecology, inter-connectedness, vegetation zoning, regional land-use planning, nature and cultural landscape integration, etc. (i.e. landscape planning); (iii) bringing actors from the provinces, market and civil society sectors together to achieve mutual understanding and negotiate and implement mutually agreeable plans, combining top-down and bottom-up approaches and promotion of community participation (i.e. intersectoral coordination); and (iv) promoting a conservation-based economy in biological corridors, with value creation and increased economic benefits for local people; labeling of goods and services from biological corridors (e.g. tourism products and services; sustainable agricultural products; NTFPs, etc.); consumption and production in line with sustainable development; fair distribution; and awareness of conservation of nature and culture. Lessons learned on collaboration with the tourism and other sectors can be shared with other biological corridors and protected areas in the region.  Secondly, it is innovative because it would seek to link “set-asides” and forest restoration as part of a larger effort to improve biodiversity conservation outcomes in HCVFs and KBAs and improve connectivity of individual parts of the larger biological corridor. Thirdly, it would serve as a pilot to develop and test sustainable financing mechanisms at the local level (community or village level) to improve incentive for community engagement in conservation, including establishment of local level revolving funds, tourism concession fees, accommodation surcharges, etc.).

- Potential for scaling up: The project is designed to provide demonstration models for up-scaling in the Philippines. In particular, the capacity building and the development of legislation, guidelines and regulations for each aspect of the project will strongly support up-scaling. Ensuring that activities, impacts and lessons learnt from the demonstration sites are disseminated widely helps generate a bottom-up demand for similar activities throughout the country. The Project’s investment component will seek to develop synergies among rural development actors and programs with an objective of raising additional investments that will fund and expand models of resource use and alternative livelihood activities within and outside of the targeted biological corridors.  The replication and scaling up strategy to be developed (Output 4.3) will assess sustainable financial and institutional arrangements for scaling up, support identification of new biological corridor sites, develop a best practice manual and conduct dissemination events to encourage uptake of IEM approaches in other sites.  In particular activities to be undertaken as part of the effort of scaling up include the following:

- Development of a replication strategy based on lessons learned at the field level that will ensure that the integrated ecosystem management planning approach and models developed and pilot tested in the two biological corridors are scaled up to include all other biological corridors in the country. Output 4.3 would support the analysis, documentation and dissemination of best practices and lessons learned that deliver tangible improvements in biodiversity and natural resources status to provide examples for replication. It would also entail participation in regional and international workshops, conferences and field visits for national and provincial staff to improve learning and exchange of experiences in mainstreaming biodiversity considerations, and integrated ecosystem management planning and practices. Based on these best practices and lessons, the replication strategy will provide a basis for actions at other key biological corridors, identify required institutional and coordination arrangements resources and partnership commitments (including with NGOs), select interventions and potential sites for replication by the fifth year of the project.

- Providing technical support to facilitate identification of new biological corridors and initiation of planning for integrated approaches in other biological corridors;

- Annual seminars for key staff and decision makers on best practices, experiences and needs;

- Financial mechanisms identified to strengthen and upscale financial support to conservation and sustainable land use/natural resource management in biological corridors.

- Publishing of best practice manuals/handbooks/compendiums of integrated biodiversity management approaches; and

- End of project national seminar on outcomes and replication for IBM approaches in the Philippines

# Project  Management

Cost efficiency and effectiveness:

- The project has been designed to reflect the most cost-effective approach. A number of strategies were evaluated during the project formulation stage to identify those strategies and activities that demonstrate this cost-effective approach.  The cost-effective approaches that have been applied to the project are the following:

- Defining a holistic and integrated approach to project formulation: The project adopts an integrated biodiversity management approach that connects biologically rich landscape and seascapes and their various interactions to maximize opportunities for synergies, such that selected actions and interventions generate multiple benefits. This is accomplished through development and implementation of well-designed conservation actions (KBAs, HCVF open access forest management with tenure arrangements and ecosystem restoration) and community resource management and livelihood measures in agriculture, fisheries, non-timber forest products and tourism that incorporate mainstreamed biodiversity policies and best practices in terms of carbon sequestration, improved food security and more resilience to climate events, whilst improving livelihood benefits, biodiversity conservation and ecosystem services.

- Sites were selected using a tiered-approach adopting a systematic and spatially explicit method that optimally captured the best multiple criteria-based choice of the project sites. The approach considered globally significant and nationally important species in identifying the sites to ensure their protection and better management.

- Sequencing of activities: Project design and sequencing of project activities ensures that foundational activities are completed first, to the extent feasible, or in parallel, such as (i) establishing functional governance and coordinating mechanisms at the national and provincial levels; (ii) legislative and regulatory changes clarifying responsibilities of biological corridor IEM planning, management and oversight; legislative and regulatory changes to facilitate to mainstreaming biodiversity into sector and environmental planning; and (iii) capacity improvements are developed to provide the necessary groundwork for later demonstration of best practices in a limited number of biological corridors (2) under Outcomes 2 and 3. The project includes subsequent documentation, dissemination of best practices for scaling up under Outcome 4 and feedback mechanisms to influence further policy and legislative changes, as appropriate.

- Models to demonstrate benefits:  Project design ensures selectivity in the identification and development of on-the-ground demonstration investments (in Outcomes 2 and 3) so as to ensure cost-effectiveness in terms of avoiding duplication and ineffective spread of activities.  Locating these mixes of management and restoration activities in selected high value biodiversity areas or clusters within the biological corridors will help demonstrate tangible impacts on the ground rather than spreading activities widely and in a scattered manner throughout the biological corridors. It would also support demonstration of community revolving funds as a mechanism to ensure community participation and financing of investments, improve financial sustainability and long-term financial commitments for community livelihood activities, rather than have to depend on government hand-outs, thus empowering communities in the management of their own enterprises.

- Building on existing lessons and best practices: As a measure to ensure cost-effectivity, project design focuses on use of available resource to the extent possible building on the existing PA management planning foundation, existing resource management plans, existing mechanisms for integration of biodiversity consideration into sub-national level planning and using NGOs that are already active in the area to support local level planning, capacity building and provision of implementation support. Rather than invest in extensive Integrated Natural Resources Management Plans that cannot be implemented without high levels of zoning and rural and urban land planning expertise, this project will invest in IEM plans that are specific to the biological corridors and narrower in its scope and reach. The process for IEM planning advocated here is both effective and cost-efficient.  Rather than hire expensive external consultants, local planning teams consisting of NGOs and local government technical specialists will make use of available information and extensive stakeholder consultations to develop plans that follow the “No Regrets” principle adopted by national policies. This results in plans that have higher levels of participation and buy-in. It would also build and replicate lessons from REDD+, PES, GEF small grants program and other initiatives.

- Data management systems: The project will focus on the development of standardized, but simple information collection and databases at biological corridor (including cost-effective GIS solutions) that is also a proven and effective way to collect and share data. The Knowledge Management and Communication Strategy in particular makes use of simple and effective local forms of communication.

- Co-financing Cost-effectiveness: The total GEF investment of US$ 12,260,241 for this project will leverage a minimum of US$ 62,330,965 in cofinancing, a cost-effective ratio of 1:5.1 with additional associated financing inputs anticipated during project implementation.

- Project management:  A national project management unit in DENR at Manila will coordinate the national and corridor activities. The project sites will be located at Mindoro and Eastern Mindanao and Corridor Project Management Units will be set up in each corridor. The project will work through Provincial and local government institutions and regional sectoral agencies for implementation of the project.

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): SDG Target 15: Life on Land (Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss Target 15.1: By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements Target 15.2 By 2020, promote the implementation of sustainable management of all types of forests, halt deforestation, restore degraded forests and substantially increase afforestation and reforestation globally Target 15.5: Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species Target 15.9: By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts SDG Target 1: End Poverty in all its form everywhere: Target 1.1. By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including microfinance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Program Document: National and local government and key stakeholders ensure that urbanization, economic growth, and climate change actions are converging for a resilient, sustainable and equitable development path of communities. |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: 2.4.1 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| Project Objective: Operationalizing integrated management of biological corridors to generate multiple benefits including effective conservation of globally significant biodiversity, reduced deforestation and degradation and enhanced community livelihoods | Indicator 1: GEF Core Indicator 4: Area of landscapes under improved practices (excluding Protected areas), including: - Area of landscapes under improved management to benefit biodiversity; | Around 4-7% of forests within biodiversity hot-spots in selected clusters under threat of further fragmentation | Biological corridor integrated frameworks agreed among all stakeholders, including specific long-term conservation outcomes to be achieved management planning and management within the corridors | At least 200,000 hectares of biological corridors under improved management practices through establishment and improved management of Other Effective Area-based Conservation Efforts (OECMs) through ICCAs, LCAs and privately-owned conservation estates, | Data Collection Methods: Project progress reports Field survey reports Community consultation and survey reports FAO EXACT reports Assumptions: -Local communities, provincial and municipal governments understand livelihood benefits and ecological security from cooperation with and sustainable management of land, forest and seascape resources. Thus, they will participate in sustainable management and ecosystem restoration work. -The National and Provincial Governments consider it their priority to support integrated ecosystem management planning of its biological corridors and implement target oriented activities with local communities to improve conservation and sustainable use of such resources. -Provinces, Municipalities, CBOs, private sector and communities collaborate closely for preparation of IEM plans. Risks: -Natural disaster/climate change may affect the restoration work. -Lack of capacity in government and communities to meet obligations related to project. -Political transitions leave plans unused. -Livelihood benefits from sustainable management may be limited and slow for communities to give up current unsustainable practices - Lack of involvement from private sector and/or resource users (including vulnerable people) with continued unsustainable practices -Conflicts over territorial issues between provincial, municipal and national sector entities could undermine efforts at promoting integrated planning approaches. |
|  | Indicator 2: GEF Core Indicator 6: Greenhouse gas emissions mitigated (metric tons of carbon dioxide equivalent) as measured by: - Carbon sequestrated or emissions avoided in the sector of agriculture, forestry and other land uses | Limited efforts within project biodiversity corridors to assess carbon values | Monitoring systems for estimation of carbon sequestrated and/or avoided established | Total C benefits of 17,503,045 metric tons of CO2 over 20-year period as follows: (a) C sequestrated in agriculture, forestry and other land uses of 5,396,078 metric tons of CO2 over 20-year period and (b) avoided emissions of 12,106,967 metric tons of CO2 over 20-year period |  |
|  | Indicator 3: GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefits of GEF investment | Baseline of households participating in improved and alternative livelihoods and sustainable resource management will be established through the community cluster conservation planning process in Year 1 | At least 9,000 individuals (belonging 2,250 households) are directly benefiting from sustainable natural resources management and improved and alternative livelihoods and incomes (at least 50% of beneficiaries are women) | At least 65,000 individuals, with which 30% are indigenous peoples (belonging to 15,000 households) directly benefit through sustainable natural resource management and livelihood improvement approaches and increase of 15% in average economic benefit (at least 50% of beneficiaries are women, with which 25% are IP women) |  |
| Component 1: Effective coordination and governance framework for integrated ecosystem management in the Philippines biodiversity corridors system; | Indicator 4: Number of policy instruments that are in place and applied to integrate biodiversity outcomes in sector and national and local planning policy and programs | Current policies are limited to detection of presence or absence of listed species rather than looking at impacts on broader ecological principles and processes for the survival of species, maintenance of ecological services, and habitat connectivity. | Policies reviewed, gap assessed and draft policy instruments under review | At least four instruments (updated safeguard standards and guidelines) for improving biodiversity outcomes within the biodiversity corridors developed and adopted | Data Collection Methods: Project progress reports Policy instruments UNDP Capacity Scorecard Assumption: -The national government will develop appropriate legislative, policy, institutional and technical measures that facilitate integrated IEM planning and management in a timely manner. -Development strategies and IEM management strategies and plans will be officially agreed with Provincial governments with allocation of appropriate staff and funding for their implementation -The Provinces will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced mainstreaming biodiversity into key development sectors is in their long-term interests Risks: -Priorities of provincial government, municipalities and local communities might shift if development benefits take long to manifest |
|  | Indicator 5: Level of institutional capacities for planning, implementation and monitoring integrated biodiversity management planning in biodiversity corridors as measured by UNDP’s capacity development scorecard for the following institutions: - Department of Environment and Natural Resources (DENR) - Department of Agriculture (DA) - National Commission for Indigenous People (NCIP) | Limited institutional capacities for planning, implementation and monitoring of multiple use IBM planning and management in biological corridors as measured by UNDP Capacity Development Scorecard baseline values as indicated below: DENR- 47/74 DA: 28/42 NCIP: 16/39 | Average increase of institutional capacity as measured by a 5-point increase in UNDP Capacity Development Scorecard baseline values | Average increase of institutional capacity as measured by 15-20 points in UNDP Capacity Development Scorecard from baseline values |  |
|  | Indicator 6: Extent to which the network of protected areas and other Effective Area-based Conservation Measures (OECMs) within corridors have adopted automated biodiversity monitoring system for biodiversity and threat assessment | Monitoring system in protected areas paper-based and inefficient to capture real-time monitoring of biodiversity and threats. No monitoring system exists in OECMs | All eleven PAs within the two corridors have moved to automated biodiversity monitoring systems and design for OECMs completed | All protected areas (11) and OECMs (at least 9 ICCAs and 4 LCAs) within two biodiversity corridors have moved to automated system of monitoring of biodiversity and threats |  |
| Component 2: Application of integrated network design and management of biodiversity corridors to ensure continued stability and sustainability of their biological, ecosystem services and socio-economic conservation values; | Indicator 7 (GEF Core Indicator 1.2): Management effectiveness of terrestrial protected areas within designated biological corridors supported by tenure security and improved resource access and sustainable use | Baseline METT scores: PA 1: Mts. Iglit Baco NP: 67 PA 2: Mt. Calavite WS: 67 PA 3: Agusan Marsh WS: 55 PA 4: Alamio, Buayan, Caracan, Panikian River and Sipangpang Falls Watershed FR: 15 PA 5: Aliwagwag Protected Landscape: 26 PA 6: Andanan Watershed FR: 30 PA 7: Cabadbaran Watershed: 20 PA 8: Mainit Hotspring Protected Landscape: 42 PA 9: Mati Protected Landscape: 20 PA 10: Mt. Hamiguitan Range WS: 59 PA 11: Surigao Watershed FR: 17 | Average increase by at least 10 points in METT | Average increase by at least 20 points in METT from current PAs baselines covering 300,000 ha | Data Collection Methods: Project progress reports METT updates Biological survey and monitoring reports Assumption: -Development strategies and management plans will be officially approved by Provincial and Municipal governments with allocation of appropriate funding for their implementation -The Provinces and Municipalities will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced that critical habitats in their vicinities will benefit livelihoods and ecological security to them and they will participate in conservation and restoration work. -Local community-based institutions would establish an effective institutional mechanism to facilitate conservation outcomes Risk: -Administrative/political changes may undermine the implementation of the management plan strategies -Lack of capacity in government and communities to meet obligations related to project -Conflicts between provincial, municipal and sector entities and local communities regarding management and access to natural resources may undermine integrated planning approaches |
|  | Indicator 8: Status of status of key species remaining stable or increasing from the baseline: Central Mindoro: Forest obligate species such as Tamaraw (Bubalus mindorensis ); and Mindoro Bleeding heart pigeon (Gallicolumba platanae) Eastern Mindanao: Forest obligate species such as Mindanao Bleeding heart pigeon (Gallicolumba crinigera) and Philippine eagle (Pithecophaga jefferyi) | Key species under continued threat from forest loss and degradation and poaching. Baselines are: Mindoro: Tamaraw + 500 (DENR 2018): Mindoro Bleeding Heart pigeon -50-249 mature adults (Birdlife 2018) Mindanao Mindanao Bleeding Heart Pigeon -1,000-2,499 mature adults (Birdlife 2018); Philippine Eagle -180-500 mature adults (Birdlife 2018) | Baseline populations validated and monitoring protocols established | Key species populations stable or increasing from baseline values | Assumption: -Adequate technical capacity available for undertaking monitoring species populations -Certain species are declining because of hunting, and improved enforcement will increase population -Tamaraw populations depend on grassland availability and the removal of grazing pressure from domestic animals will lead to an increase in numbers Risk: -External factors beyond the control of the project (e.g. climate change) might affect bird populations negatively |
|  | Indicator 9: Number of regional, provincial and local plans that mainstream objectives of integrated ecosystem management (IEM) within the biodiversity corridors: RDIPs, PPFPs, CLUPs/CDPs, ADSPPs Indicator 10: Number of hectares impacted by the mainstreaming of SLM and SFM in relevant local planning instruments, measured by: (a) Area of degraded agricultural lands prioritized for avoiding degradation in relevant local planning instruments (b) Area of forest land prioritized for restoration in relevant local planning instruments | Indicator 9: RDIPs, PPFPs and LGU CLUPs have limited attention to mainstreaming ecosystem consideration into their planning systems Indicator 10: Limited attention and prioritization of SLM and SFM activities in RDIPs, PPFPs and LGU CLUPs | Indicator 9: Guidelines, regulations and frameworks and capacity improvements being undertaken to facilitate biodiversity and ecosystem mainstreaming into sub-national planning systems Indicator 10: Capacity building for LGU staff for mainstreaming completed, mainstreaming guidelines in place and CLUPs revision ongoing to incorporate and prioritize conservation investments, | Indicator 9: Sub-national plans fully integrate IEM considerations within the two biological corridors as follows: RDIPs – 3 PPFPs – 9, and LGU CLUPs/CDPs – 24 ADSDPP – 9 (a) At least 150,000 hectares of agricultural lands prioritized for avoiding degradation in relevant local planning instruments (b) At least 100,000 hectares of forest lands prioritized for avoiding degradation in relevant local planning instruments | Data Collection Methods: Project progress reports LGU and regional development plans Assumption: -The national government will develop appropriate legislative, policy, institutional and technical measures that facilitate integrated local planning and management in a timely manner. -Development strategies and management plans will be officially approved by provincial and local governments with allocation of appropriate staff and funding for implementation -The LGUs will take active part in developing strategies and implementation using new knowledge and skills provided by the project Risks: -Priorities of local governments might shift if development benefits take long to manifest - Plans are developed but not used, particularly by resource users - Planning bodies that build capacity may not be adequately motivated for change |
| Component 3: Community-based sustainable use and management systems in the two pilot biodiversity corridor systems in the Philippines | Indicator 11: GEF Core Indicator 3: Area of lands restored, segregated by: (a) Area of degraded agricultural lands restored (b) Area of forest land restored | Natural habitats under continued fragmentation due to agricultural expansion as result of declining productivity of existing agricultural lands and loss of livelihoods | At least: (a) 1,000 ha of degraded agricultural lands restored under SLM production systems; and (b) 1,000 ha under of disturbed forest lands under improved SFM | At least the following targets will be achieved: (a) 15,000 ha of degraded agricultural lands restored under SLM production systems; and (b) 15,000 ha under of disturbed forest lands under improved SFM | Data Collection Methods: Project progress reports Field survey reports Community consultation reports Productivity assessment reports Assumption: -Development strategies and management plans will be officially approved by Provincial and local governments with allocation of appropriate funding for their implementation -LGUs will take active part in developing strategies and implementation using knowledge and skills from project. -Local communities are convinced that critical habitats in their vicinities will benefit livelihoods and ecological security to them and will participate in conservation and restoration work. -Local community based institutions would establish an effective institutional mechanism to facilitate conservation outcomes - LGU capacity enhanced to provide adequate leadership and support to states Risk: -Administrative/political changes may undermine the implementation of the management plan strategies -Lack of capacity in government and communities to meet obligations related to project -Conflicts between national, provincial, LGUs and local communities regarding management and access to natural resources may undermine integrated planning approaches - Natural disasters/climate drivers exacerbate degradation |
|  | Indicator 12: Number of Voluntary forest certification system piloted with local communities and privately managed forests for encouraging sustainable forest management | National criteria and indicators and governance for sustainable forest management not finalized | Forest certification system piloted in 2 sites including one community managed forest and one privately managed forest | Forest certification systems updated based on lessons from 2 sites including one community managed forest and one privately managed forest pilot and adopted by DENR and stakeholders |  |
| Component 4: Knowledge management, gender mainstreaming, learning and monitoring and evaluation | Indicator 13: Level of awareness on IEM within the biodiversity corridors as indicated by KAP survey. | Coordinated outreach on conservation threats lacking. Limited awareness of impact of unplanned development among general public. Baseline survey established in Year 1 | At least 40% sampled community members, government and sector agency staff, private sector and other stakeholders (at least 40% women) aware of potential conservation threats and adverse impacts of unplanned developments and actions needed for corridor conservation | At least 60% (of which at least 40% women) of sampled community members, government and sector agency staff, private sector and other stakeholders aware of potential conservation threats and adverse impacts of unplanned developments and behavior change for biodiversity outcomes | Data Collection Methods: Project progress reports KAP survey reports Good practice documents Data use reports Assumption: -Stakeholders willing to actively participate in the review process. -Project management will be able to identify, document and disseminate the best practices -Mid Term Review and End of Project Evaluation of the project will also contribute to identifying the best practices -Best practices from sustainable resource management readily available to resource users Risks: -Government priorities may change from due to political pressure from resource users -Actions among the assorted agencies and NGOs remain uncoordinated -Community diversity will not be a hindrance to outreach activities |
|  | Indicator 14: Integrated decision support system/ integrated information management system to monitor biodiversity threats and outcomes in place and effectively used. | All data collection in paper form with limited scope, quality, accessibility and use. Baseline to be established in Year 1 | Automated information management system established and operational | 100 % increase in number of inter-sectoral users from baseline |  |
|  | Indicator 15: Number of good practice conservation and sustainable resource management approaches applicable to different actors codified, disseminated nationally and adapted | Limited number of good practices in conservation and sustainable resource management codified, disseminated and applied | At least ten good practices in conservation and sustainable resource management codified and applied | At least thirty good practice in conservation and sustainable resource management codified and disseminated nationally and adapted |  |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results. Supported by Component Four:  “Knowledge management, gender mainstreaming, learning and monitoring and evaluation”, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Director:  The Project Director is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Director will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Director will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Director will develop annual work plans based on the multi-year work plan included in 19, including annual output targets to support the efficient implementation of the project. The Project Director will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. ESMP, gender action plan, stakeholder engagement plan etc.) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used and generated by the project supports national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Director as needed, including through annual supervision and/or monitoring missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision and/or monitoring mission reports will be circulated to the project team and Project Board within one month after the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Director.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

a) Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

b) Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

c) Review the results framework and finalize the indicators, means of verification and monitoring plan;

d) Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

e) Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP, Environmental and Social Management Plan and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

f) Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

g) Plan and schedule Project Board meetings and finalize the first year annual work plan.

- The Project Director will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The Project Director, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Director will ensure that the indicators included in the project results framework is monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Focal Area Tracking Tools:  The following GEF Tracking Tool(s) will be used to monitor global environmental benefits: METTs, and GEF Core Indicator Worksheet. The baseline/CEO Endorsement GEF Focal Area Tracking Tool(s) – submitted as Annex 19 to this project document – will be updated by the Project Director/Team (not the evaluation consultants hired to undertake the MTR or the TE) and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated GEF Tracking Tool(s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

- GEF Focal Area Tracking Tools:  The following GEF Tracking Tool(s) will be used to monitor global environmental benefits:

- Capacity Assessment Scorecard

- METT Scorecards

- GEF Core Indicators (as listed below)

# Core Indicator 1: Terrestrial protected areas created or under improved management for conservation and sustainable use (hectares)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 300,000 | 300,000 |  |  |

Figure at a given stage must be the sum of all figures reported under the two sub-indicators (1.1 and 1.2) for that stage.

1.1 Terrestrial protected areas newly created

| Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- |
| NA |  |  |  |

Figure at a given stage must be the sum of all individual PAs reported in the next table, for that stage.

| Name of Protected Area | WDPA ID | IUCN Category | Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- | --- | --- | --- |
| NA |  |  |  |  |  |  |

| Name of Protected Area | METT Score at CEO Endorsement | METT Score at MTR | METT Score at TE |
| --- | --- | --- | --- |
| NA |  |  |  |

1.2 Terrestrial protected areas under improved management effectiveness

| Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- |
| 300,000 | 300,000 |  |  |

| Name of Protected Area | WDPA ID | IUCN Category | Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- | --- | --- | --- |
| Mts. Iglit-Baco Natural Park | 1337 | II | 106,000 | 106,000 |  |  |
| Mount Calavite Wildlife Sanctuary | 14729 | IV | 14,707 | 14,707 |  |  |
| Agusan Marsh Wildlife Santuary | 145492 | IV | 40,752 | 40,752 |  |  |
| Alamio, Buyaan, Carac-an, Panikian Rivers and Sipangpang Falls Watershed Forest Reserve | 555583095 | V | 5,784 | 5,784 |  |  |
| Aliwagwag Protected Landscape | 555583080 | V | 11,570 | 11,570 |  |  |
| Andanan River Watershed Forest Reserve | 306540 | V | 15,097 | 15,097 |  |  |
| Cabadbaran Watershed Forest Reserve | 306541 | VI | 15,776 | 15,776 |  |  |
| Mainit Hot Spring Protected Landscape | 7232 | V | 8,098 | 8,098 |  |  |
| Mati Protected Landscape | 306531 | V | 1,067 | 1,067 |  |  |
| Mount Hamiguitan Range Wildlife Sanctuary | 555583083 | IV | 15,830 | 15,830 |  |  |
| Surigao Watershed Forest Reserve | 306539 | V | 967 | 967 |  |  |
| Expansion of existing PAs above |  |  | 65,000 | 65,000 |  |  |
| TOTAL |  |  | 300,000 | 300,000 |  |  |

| Name of Protected Area | METT Score at CEO Endorsement | METT Score at MTR | METT Score at TE |
| --- | --- | --- | --- |
| Mts. Iglit-Baco Natural Park | 67 | 77 | 87 |
| Mount Calavite Wildlife Sanctuary | 67 | 76 | 87 |
| Agusan Marsh Wildlife Santuary | 55 | 67 | 75 |
| Alamio, Buyaan, Carac-an, Panikian Rivers and Sipangpang Falls Watershed Forest Reserve | 15 | 39 | 56 |
| Aliwagwag Protected Landscape | 26 | 56 | 72 |
| Andanan River Watershed Forest Reserve | 30 | 58 | 65 |
| Cabadbaran Watershed Forest Reserve | 20 | 46 | 65 |
| Mainit Hot Spring Protected Landscape | 42 | 61 | 71 |
| Mati Protected Landscape | 20 | 46 | 66 |
| Mount Hamiguitan Range Wildlife Sanctuary | 59 | 69 | 79 |
| Surigao Watershed Forest Reserve | 17 | 56 | 66 |

# Core Indicator 3: Area of land restored (hectares)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 530,000 | 30,000 |  |  |

3.1 Area of degraded agricultural lands restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 300,000 | 15,000 |  |  |

3.2 Area of forest and forest land restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 200,000 | 15,000 |  |  |

# Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 200,000 | 200,000 |  |  |

4.1 Area of landscapes under improved management to benefit biodiversity (qualitative assessment, noncertified)

| Ha (expected at PIF) | Qualitative description at PIF | Ha (expected at CEO Endorsement) | Qualitative description at CEO ER | Ha (achieved at MTR) | Qualitative description at MTR | Ha (achieved at TE) | Qualitative description at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 200,000 | A network of other effective area-based conservation measures (OECM) | 200,000 | A network of other effective area-based conservation measures (OECM) |  |  |  |  |

4.2 Area of landscapes that meet national or international third-party certification and that incorporates biodiversity considerations

| Ha (expected at PIF) | Type of Certification at PIF | Ha (expected at CEO Endorsement) | Type of Certification at CEO ER | Ha (achieved at MTR) | Type of Certification at MTR | Ha (achieved at TE) | Type of Certification at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NA |  |  |  |  |  |  |  |

4.3 Area of landscapes under sustainable land management in production systems

| Ha (expected at PIF) | Description of Management Practices at PIF | Ha (expected at CEO Endorsement) | Description of Management Practices at CEO ER | Ha (achieved at MTR) | Description of Management Practices at MTR | Ha (achieved at TE) | Description of Management Practices at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NA |  |  |  |  |  |  |  |

4.4 Area of High Conservation Value forest loss avoided

| Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- |
| NA |  |  |  |

| Name of HCVF | Ha (expected at PIF) | Counterfactual at PIF | Ha (expected at CEO Endorsement) | Counterfactual at CEO ER | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- | --- | --- | --- |
| NA |  |  |  |  |  |  |

Sub Indicator 6.1 Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry and Other Land Use

| GHG emission type | Ha (expected at PIF) | Metric tons CO2-eq (baseline at PIF) | Ha (expected at CEO ER) | Metric tons CO2-eq (baseline at CEO ER) | Ha (expected at MTR) | Metric tons CO2-eq (above baseline at MTR) | Ha (expected at TE) | Metric tons CO2-eq (above baseline at TE) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lifetime direct project GHG emissions mitigated | 1,130,000 | 44.3 Million Metric tons over 20 years | 530,000 | 7.271 Million Metric tons over 20 years | Not determined | 3 million Metric tons | Not determined | 7.271 Million Metric tons over 20 years |
| Lifetime direct post-project emissions mitigated | 1,130,000 | Not determined | 530,000 | 10.232 Million Metric tons over next 14 years | Not determined | Not determined | Not determined | 10.232 Million Metric tons over next 14 years |
| Total GHG emissions mitigated | 1,130,000 | Not determined | 530,000 | 17.503 Million Metric tons over 20 years | Not determined | Not determined | Not determined | 17.503 Million Metric tons over 20 years |

# Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment

|  | Total number (expected at PIF) | Total number (expected at CEO Endorsement) | Total number (achieved at MTR) | Total number (achieved at TE) |
| --- | --- | --- | --- | --- |
| Women | NA | 32,500 |  |  |
| Men | NA | 32,500 |  |  |
| Total | NA | 65,000 |  |  |

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Director will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publically available in English on the UNDP ERC.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Table 7: Mandatory GEF M&E Requirements and M&E Budget:  needs revision once budget is done

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop(s) | UNDP Country Office | 15,000 | 10,000 | Within two months of project document signature |
| Inception Report | National Project Director | 3,000 | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | National Project Director Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | National Project Director and Monitoring Specialist | 64,000 | 30,000 | Annually before PIR |
| GEF Project Implementation Report (PIR) | National Project Director and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| Lessons learned and knowledge generation | National Project Director and consultants | 62,500 | 25,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | National Project Director and Monitoring Specialist UNDP Country Office | Covered above under Monitoring of indicators in project results framework | 25,000 | On-going |
| Stakeholder Engagement Plan | National Project Director and PMU UNDP Country Office |  | 25,000 | On-going |
| Monitoring/M&E aspects of Gender Action | National Project Director and PMU UNDP Country Office | Per year: USD 1,000 (Total: USD 6,000) | USD 30,000 | On-going |
| Addressing environmental and social grievances | National Project Director UNDP Country Office | Covered above under Monitoring of indicators in project results framework | 20,000 | On-going |
| Addressing and monitoring IP issues | National Project Director and consultants (IP policy/practice and IKSP) | 45,500 | 30,000 | On-going |
| Project Board meetings | Project Board UNDP Country Office National Project Director | None | 30,000 | At minimum annually |
| Supervision missions | UNDP Country Office | None | 20,000 | Annually |
| Oversight missions | UNDP-GEF team | None33 |  | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and National Project Director and UNDP-GEF team | None | 5,000 | To be determined. |
| Mid-term GEF Tracking Tool to be updated | National Project Director and Monitoring Specialist | Covered above under Monitoring of indicators in project results framework | 5,000 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | 39,000 | 15,000 | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool to be updated | National Project Director and Monitoring Specialist | Covered above under Monitoring of indicators in project results framework | 5,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | 39,000 | 20,000 | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | 5,000 |  |  |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | 278,000 | 315,000 |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism: The project will be implemented following UNDP’s National Implementation Modality (NIM), according to the Standard Basic Assistance Agreement between UNDP and the Government of Philippines and the Country Program.

- The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document. The Implementing Partner is responsible for executing this project.

- The DENR will serve as the National Implementing Partner for the Project. As a representative of the Government, the DENR has the main responsibility to ensure that the project is executed in accordance with Government priorities, as well as with the Project Document and the UNDP guidelines. Expectations for the National Implementing Partner include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year;

- Signing the financial report or the funding authorization and certificate of expenditures;

- Designate a focal office within the Department to provide secretariat support to the PB and facilitate the operation of the National Program Management Unit (NPMU) to be established under the project;

- Ensure a synchronized contribution of all key bureaus and regional offices of the Department to project objectives, including a mechanism by which Department staff could be assigned and supported by the project;

- Approve on behalf of the Government and the PB, quarterly work plans and reports, including quarterly progress reports, expenditure plans and financial report (s) of the Project;

- Integrate project plans as well as project learning into appropriate plans and operations of Department;

- Provide guidance and facilitate coordination and consistency of approaches across the two corridors and among the different partners;

- Provide advice to the PB and direction to the NPMU as necessary, to over-come conflicts, constraints, mitigate risks and resolve implementation problems;

- Represent the Project at meetings with key partners/stakeholders including line departments, provincial governments, inter agency bodies, civil society and development /donor partners;

- Assist in the coordination of the Project activities that involve other agencies of Government;

- A senior official of DENR will serve as National Project Director (NPD) to personally oversee the tasks of the Department as National Implementing Partner as described above. The NPD will convene the first meetings of the Corridor Advisory Committee in collaboration with the respective RDCs and NEDA Regional Offices. The National Project Director will work closely with UNDP and NPMU staff in all aspects of planning, implementation and management of the Project. Tasks are defined indicated in Annex 21.

- An inter-office forum will be convened regularly within the DENR to provide regular technical advice to the NPD on harmonizing sectoral concerns to support project objectives while at the same time ensuring that project outcomes can support the strategic concerns of sectors offices. The regular forum will be composed of representatives from the planning offices of FMB, MGB, BMB, LMB, EMB and ERDB plus other subject matter specialists on an on-call basis. The National Project Management Unit (NPMU) will be put under the umbrella of the office of the NPD.

- At the corridor level, the DENR and NPD will be represented by respective Regional Executive Directors (RED) who will concurrently serve as Corridor Project Director (CPD). As CPD, the RED will convene (joinlty with the senior RDC representative) the regular meetings of the Corridor Advisory Commitees; ensure harmonized delivery of support by DENR subsectoral offices; engage the  local political leadership for their support; and provide operational leadership of the project at the corridor level to ensure the  outcome orientation of activities. Tasks  of the CPD are further described in Annex 21. The CPD will regularly convene a task force composed of regional focal person of key sectors that mirror that of the national level task force assisting the NPD, These sectors include forestry, mining, land management, biodiversity, environmental management and ecosystems research.

- At the corridor level, responsible partners will be identified to implement work packages/TORs for the delivery of specific project activities and outputs. Work packages will be executed through Memorandum of Understanding (MOU) that will be signed between DENR and each Responsible Partner. The table below illustrates the list of work packages that may be identified during project level planning and corridor level planning, as well as the list of candidate responsible partners who can implement the same with financial support from the Project. Work packages are designed to be TORs for mainstream or emerging institutions that have long-term stake in corridor management. They involve planning and field level implementation activities that the Project aims to institutionalize.   This list does not include the work of individual staff and individual consultants who will have separate TORs. Their TORs may also include providing expert assistance to responsible partners in their tasks.

Table 8: Work Packages

| Work Package (Illustrative List) | Candidate Responsible Partner |
| --- | --- |
| - Overall coordination and management of the project. | DENR |
| - Provision of technical services for national policy formulation. | Relevant Bureaus and offices of the DENR, DA, NCIP |
| - Facilitation of Corridor and cluster consensus and planning and monitoring processes. | State University /College, NGO, |
| - Provision of mapping and analytical services to corridor planning processes. | Relevant DENR Unit, State University/ College |
| - Provision of policy guidance & technical services to corridor planning and guidance to PAs, LGUs and communities. | R/DENR, R/DA, R/NCIP |
| - Support to strengthening of PA plans, governance and resource mobilization | R/DENR, PASUs |
| - Facilitation of support to Ancestral Domains and ICCA. | NCIP, NGO |
| - Strengthening of Local IP network on KM and upscaling | NCIP, IP Federation |
| - Support for establishment of Local Conservation Area | LGU, NGO |
| - Conduct of Training for LGUS on CLUP preparation | HLURB, State University/College |
| k Facilitation of LGU program formulation and team building of offices (AGRI, ENR and IP affairs) | DENR, DA, NGO State University, |
| l Facilitation of program formulation for regional offices of DENR, DA and NCIP based on project learning | Relevant Bureaus of DENR DA or NCIP, State University, |
| m. Management of training program for SFM, SLM and associated topics | State University /College, NGO, |
| n. Facilitation of SLM and SFM incentive support systems for LGUs and communities | State University /College, NGO, |
| o Conduct of IEC campaign and production of IEC products. | State University /College, NGO, |

- Based on the annual workplan, corridor strategies and targets, the PMUs (NPMU, CPMU)  would define the TORs of work packages facilitate the execution of  MOA between the DENR and the identified agencies who will serve as Responsible Partners to implement these work packages. A responsible partner may undertake several work packages.  The PMU would jointly prepare project-level annual  workplans with  responsible partners. The CPD would review and endorse work packages and workplans for approval by the PB or by the NPD as delegated by the PB. Responsible partners would prepare reports, for review, endorsement, and approval either by the NPD or CPD depending on the scope of the work package.

- Institutional arrangements for planning and implementation of cluster conservation plans (Output 2.2) will entail the competitive selection of a local NGO for each cluster. Contracted NGOs and local government (LGUs) will be responsible for engaging local community, private sector entities, farmer organizations and IP members in the planning exercise leading to the development of CCPs, for overseeing implementation of the CCPs, and for building and maintaining cluster-level linkages at the biodiversity corridor level to ensure wider ecosystem management. NGO activities supporting communities will be done collaboratively with LGUs. The selected NGO would have expertise in conservation, SLM, SFM, livelihood and enterprise development, social mobilization and tenure applications. Planning and implementation teams at the cluster level will include the above-mentioned expertise from the NGO and incorporate key technical staff from the LGU in its area of operation, the latter inclusion in the planning and implementation activities will facilitate later integration of biodiversity consideration into the LGU CLUPs.  Criteria for engagement of NGOs will be further reviewed and finalized during the launch workshop.

- Criteria for engagement of NGOs could include the following:

- Local stragetic presence in the target area so that there will be a long term commitment to these communities and the objectives of the project;

- Good understanding of local government functioning and linkages to enable opportunities for integration of mainstreaming actions in CLUP planning processes;

- Demonstrated experiences in ability to nuture communities and establish business partnership for improving community productive resources and livelihood development;

- Experiences in working on conservation, SLM, SFM, livelihood and small scale enterprise development

- Experience in establishing community financial support mechanims for sustainability

- Practices knowledge management and experience faciliation of consenus building processes; and

- Ability to mobilize additional financila resources and financial track record.

- The governance role of project target groups is  discussed in detail in Annex 3 on Framework for Integrated Ecosystem Management, Consensus Building and Planning and Implementation within Biodiversity Corridors.

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is responsible for the Project Assurance role of the Project Board/Steering Committee.

- The project organisation structure is as follows:

PROJECT BOARD

- The Project Board (also called Project Steering Committee) is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition. In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- The PB will be composed of representatives from the following agencies: DENR, NEDA, DA , NCIP, DILG, HLURB, a representative of IP Federation, League of Provinces of the Philippines (LPP), and the Business Sector, and  will be chaired by a DENR Sub Cabinet Official.   Specific tasks of the PB include the following:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Approve annual work-plans and budgets, and as needed, any essential deviations from the original plans and budgets;

- Approve key work packages and TORs for implementation by responsible partners, and establish a system to delegate approving authorities to the NPD and the PMU to ensure efficient and effective project implementation;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project manager’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year; Oversee and support the commitment for funding and other support for the project;

- Regularly consult with the Philippine Biodiversity Strategy and Action Plan (PBSAP) Steering Committee for mutual updates on relevant strategic information vital for respective implementation of the project and of the PBSAP;

- Oversee the development and piloting of the process to embed recommended planning and coordination measures for biological corridors in the formal planning and coordination systems of the DENR;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Decide on conceptual and design changes and other recommendations of external mid-term review; and

- Serve as a conflict management /resolution venue for implementing agencies and key stakeholders i.e. concerned ministries, provincial line departments, and relevant research institutions;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up;

- Provide guidance on post-project sustainability, institutional and financial arrangements, keeping in view the recommendations of external reviews.

The composition of the Project Board must include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Board. The Executive is normally the national counterpart for nationally implemented projects. The Project Executive is: DENR.

- Beneficiary Representatives: Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. The Beneficiary representatives are: NEDA, IP Federation, and the League of Provinces of the Philippines (LPP).

- Development Partners: Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partners are: DA , NCIP, DILG, HLURB), and the Business Sector.

- Project Assurance: UNDP performs the quality assurance role and supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. UNDP provides a three - tier oversight services involving the UNDP Country Offices and UNDP at regional and headquarters levels. Project assurance is totally independent of the Project Management function.

- The PB and the NPD will be assisted by a National Technical Working Group (TWG). The TWG will be composed of senior technical experts representing  the PB member institutions: DENR Planning Office, BMB, FMB, NEDA, DA, NCIP, DILG, HLURB and IP Federation as well as from other key agencies such as the DTI, DOT  DOST, NGO community, business and science commmunity or a total of 16 agencies. Other agencies with critical roles for specific activities will be invited to selected sessions of the TWG or the PB. The NTWG may meet en banc or by thematic clusters as determined by the TWG membership. The PMU will assist the  TWG through the provision of resource persons and facilitation of sessions. The tasks of the TWG would include the following:

- Identify assemble and review available updated scientific and instituional information for use by PB  in its decision making processes;

- Recommend guidelines for Corridor level planning and investment planning  and capacity building, based on  cross sectoral perspective in the analysis of corridor situation;

- Provide advice on the design for large work packages and TORs needed for implementation by responsible partners;

- Provide policy guidance to the design of proposed policy instruments and standards;

- Provide feedback to reports of responsible partners on progress towards outcome;

- Serve as venue for updating the project of updates from respective sectors on policies and good practices that can enhance implementation;

- Serve as venue for communicating project learnings and good practices to the respective sectoral agencies to enhance sustainablity

CORRIDOR CONSENSUS BUILDING MECHANISMS

- Corridor Alliance Advisory Committee. A Corridor alliance Advisory Committee (CAAC) will be formed in each Corridor throgh collaborative action of the R/DENR, NEDA and key Provincial Local Government Units (PLGUs).  The CAAC will serve a venue for multisectorsl forum in the corridor be resposible for the following:

- Develop a common understanding of strategic issues and opportunities in the corridor;

- Develop consensus on outstanding vision priorities, strategies and actul consevation targets based on situation analysis that use updated information on environmental and natural resources trends;

- Adopt a recommended land use framework for the corridor to  guide the development of mandated regional and land use plans;

- Validate pre-identified clusters as planning units of the corridor, and establish subcomittees who will oversee the planning, coordination, monitoring and learning processes

- Allocate roles for each participating national agencies, LGUs, ancestral domains, and other key entities in the corridor in support of common conservation targets;

- Launch a Corridor advocacy campaign for multi-sectoral Corridor Aliance to achieve corridor targets. The  key target audience of the campaign would be the respective  Economics Committee of the Regional Development Council and the Provincial Development Councils who review and endorse investment programs of NGAs and LGUs.

- Review and endorse a strategic governance mechanism which will oversee corridor management in the long term

- Members of the CAAC would include the R/DENR and a senior political representative of the RDC as Co-Chair. Members would include senior representatives of the PLGUs concerned and key agencies mirroring the membership of the PB (DA,NCIP, DILG, HLURB,  and reperesentation from the League of Municipalities in the region, IP Federation, business and science community.

- CAAC Sub Committees- Due to the sheer size of the Corridor, the Project has pre-identified discrete geographic portions of the corridor referred to as clusters, that would serve as basic planning units for multi-sectoral landscape action. A cluster would consist of pre-delineated portion of the corridor landscape with high conservation value as well as different entities that are involved in its direct physical management. For this purpose, the CAAC in each corridor may create sub-committees to manage individual geographic clusters or networks of adjacent clusters within the concerned corridor, depending on preference of stakeholders concerned. Provincial Governments whose territories overlap in  a major way with the area of clusters will chair the cluster or network of clusters. With project support, the CAAC sub-committee for each cluster would replicate the funcions of the CAAC (as described above) at the cluster level.

- Achieve  consensus on outstanding vision, priorities, strategies and actul conservation targets based on situation analysis that use updated information on ENR trends;

- Allocate roles and targets  for each entity in the cluster i.e. LGUs, ancestral domains and other key entities who have a stake in the corridor in support of common conservation targets;

- Provide guidance to participating agencies in translating agreed upon consevation targets into ageny workplans and budgets;

- Monitor implementatoin of agreed upon actions towards outcome by cooperating entities in the cluster, identify learnings, and communicate the same to the CAAC.

- Serve as venue for updating the project of updates from respective sectors on policies and good practices that can enhance implementation;

- Serve as venue for communicating project innovations and learnings to the respective sectoral agencies in the region as well as to LGUS  to enhance sustainablity

- The CAAC may also establish its own Convenor SubCommittee who can convene more frquently than the full CAAC and provide programmatic advice to the DENR and CPMU.The  DENR, DA and NCIP and DILG  plus another to be identified would be the recommened members.

- Details are provided in  Annex 3 on Framework for Integrated Biodiversity Management, Consensus Building and Planning and Implementation within Biodiversity Corridors.

PROJECT MANAGEMENT UNIT

- A DENR based National Project Management Unit (NPMU), reporting to the NPD and composed of full time project personnel will be estabished to manage the day to day project operations. It will consist of National Project Director,  Deputy Project Director, National Project Manager (NPM) as well as one CPMU for each corridor. The PMU will support the NPD and CPD for the  day to day operations. Key functions include: (a) preparation of agenda of PB and CAAC including information sets to support decision making (to be done in collaboration with the TWG snd RTWGs); (b) facilitation of workplans, work packages and TORs, negotiation of partnership agreeements and contracts with Responsbile Partners and deployment of consultants;  and (c) monitoring and facilitation of evaluation and learning.

- The NPMU will be headed by the  NPM and will consist of Project Staff namely the:  National Planning and M&E officer, NRM Officer, Communication Officer,  an Operations Officer (HR, Finance, Procurement & Admin), and Finance and Admin Assistant.  Corridor PMU will be created for each corridor. Each CPMU will consist of a Corridor Project Director (CPD), a Co-Project Director, Corridor Project Manager (CPM); a Landscape Planning & M&E Officer, Stakeholder Engagement Officer and a Finance and Administrative Assistant.  Additional staff complement can be decided by the NPMU in consultation with UNDP and DENR and subject to fund availability.

- The NPM will be responsible for overall management and administration  of the project under the guidance of the NPD. He/she will also serve as the PB Secretary, The key resposibilities include: (a) managing the national policy dialogue and  provide guidance for corridor level planning and implementation; (b) preparation  of  work packages by responsible partners, (c) knowledge management, training, and IEC towards mainstreaming into agency programs; (d) communication of project progress and learnings to the PB and partners; and (e) providing oversight for SESP risk management, gender mainstreaming and ensuring IP FPIC and integration and monitoring of results indicators.  Annex 21 provides more details.

- The key tasks of the CPM would  mirror that of the NPD but at the corridor level. This would include the following: (a) facilitation of corridor and cluster level planning and programming; (b) execution  of work packages by responsible partners; (c) execution of KM training and IBM plans; (d) M&E management; and (e) faciltation of mainstreaming project innovations and learnings into  local land use and development plans.

- The NPMU will be supported by short term, interim consultants to support technical analysis and M&E/KM and comunication planning.  The R/PMUs for Mindoro Corridor wil be based in San Jose Mindoro, Occidental, while the R/PMU for Eastern Mindanao will be based in Butuan City, Agusan Norte--both sites for regional headquarters are based on the greater level of project  presence in these areas. The NPMU will be supported by a pool of technical experts.

- Annex 21 describes the list of responsibilities and qualifications of NPD and NPMU and CPMU key staff.

# Financial Planning and Management

- The total cost of the project is USD 74,961,248. This is financed through a GEF grant of USD12,260,241 and USD 62,701,007 in parallel co-financing. UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Co-financing source | Co-financing type | Co-financing amount (USD) | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Department of Environment and Natural Resources | Grant and In-Kind | 42,891,028 (Grant: 39,539,455; In-Kind: 3,351,573) | Ongoing programs in expanding and developing PAs; biodiversity conservation and watershed management, national greening and reforestation programs, etc. | Limited risk related to ensuring the delivery of agreed commitments | The PMU, as annual monitoring will assess extent to which co-financing commitments are met and seek remedial actions through Steering committee, if necessary |
| Department of Agriculture | Grant and in-kind | 12,293,364 (Grant: 11,936,960 and In-Kind: 356,404) | Ongoing programs in support of developing biodiversity-friendly agriculture; IP focused highland agriculture, etc. and staff support | Limited risk related to ensuring the delivery of agreed commitments | The PMU, as annual monitoring will assess extent to which co-financing commitments are met and seek remedial actions through Steering committee, if necessary |
| Department of Trade and Industry –Philippine Trade Training Center | In-kind | 166,609 | Conduct of training in small and medium scale entrepreneurship development programs | No significant risk | This is core mandate of agency |
| Province of Surigao del Norte | In-kind | 99,822 | Office space, vehicle, and office equipment, etc. | No significant risk | This is core mandate of agency |
| Province of Davao Oriental | Grant/In-Kind | 370,042 (Grant: 348,581; In-Kind 21,461) | Supporting environment and natural resources oriented land use planning at local government level | No significant risk | This is core mandate of agency |
| Private Sector (Mining Companies) (i) Agala Mining Ventures, Inc (ii) Taganito Mining Corp.; (iii) Taganito HPAL Nickel Corp.; (iv) Philsaga Mining Corp.; (v) Mindanao Mining Processing & Refining Corp.; (vi) Marcventures Mining & Dev Corp.; (vii) CTP Construction & Mining Corp.- Adlay Project; (viii) CTP Construction & Mining Corp. – Dahican Nickel Project (ix) Platinum Group Metals; (x) Greenstone Resources Corp.; (xi) Carrascal Nickel Corp. | Grants | 3,174,871 | Ongoing programs on nursery development and reforestation of mined out areas; landscaping; protection of existing plantations; establishment and protection of conservation areas, monitoring, etc., | Limited risk, in particular related to maintenance of reforested areas | These programs represent commitments by the mining companies as part of legal agreement with application of mining contracts. Maintenance efforts will be monitored by project staff |
| CSO – Center for Conservation Innovations | Grant | 1,000,000 | Ongoing programs on biodiversity conservation and regenerative livelihoods; HCVA assessments and capacity building | No significant risk | Core mandate of CSO with committed programs and funding |
| CSO – Haribon Foundation | Grant | 546,260 | Ongoing programs on community-based management, communication, awareness, scientific research and policy advocacy | No significant risk | Core mandate of CSO with committed programs and funding |
| CSO – Mindoro Biodiversity Conservation Foundation | Grant | 326,923 | Ongoing programs on conservation of Mindoro’s natural resources; scientific research and collaborative and participatory efforts | No significant risk | Core mandate of CSO with committed programs and funding |
| CSO – Philippine Eagle Foundation | Grant | 19,231 | Ongoing programs on saving the Philippine Eagle, including protection, monitoring, awareness generation and information generation | No significant risk | Core mandate of CSO with committed programs and funding |
| CSO-Conservation International | Grant | 312,857 | Ongoing programs related to science, policy and field work to provide innovative solutions to environmental issues to address deforestation, climate change, unsustainable fishing and legal wildlife trade | No significant risk | Core mandate of CSO with committed programs and funding |
| GEF Agency (UNDP) | Grant | 1,500,000 | Ongoing UNDP supported programs in PA management, natural resources management and community development and quality assurance | No significant risk | Co-financing from already committed programs with fund availability |
| Total (USD) | 62,701,007 |  |  |  |  |

- UNDP Direct Project Services as requested by Government (if any): none

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Director and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP program manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Award ID: | 00096757 | Project ID(s): | 00100687 |
| --- | --- | --- | --- |
| Award Title: | Integrated Approach in Management of Major Biodiversity Corridors in the Philippines |  |  |
| Business Unit: | PHL10 |  |  |
| Project Title: | Integrated Approach in Management of Major Biodiversity Corridors in the Philippines |  |  |
| PIMS no. | 5886 |  |  |
| Implementing Partner (Executing Agency): | Department of Environment and Natural Resources (DENR) |  |  |

| GEF Component/Atlas Activity | Responsible Party/ (Atlas Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1 (10%) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effective coordination and governance framework for integrated ecosystem management in the Philippines biodiversity corridors system | DENR | 62000 | GEF | 71300 | Local Consultant | 0 | 109,000 | 117,500 | 95,000 | 13,000 | 13,000 | 347,500 | 1 |
|  |  |  |  | 71400 | Contractual Services - Individual | 10,804 | 22,806 | 22,806 | 22,806 | 22,806 | 22,806 | 124,834 | 2 |
|  |  |  |  | 71600 | Travel | 7,016 | 43,452 | 34,452 | 29,052 | 29,052 | 25,052 | 168,076 | 3 |
|  |  |  |  | 72400 | Communication & Audio Visual Equipment | 135 | 1,080 | 1,080 | 1,382 | 1,080 | 1,080 | 5,837 | 4 |
|  |  |  |  | 72500 | Supplies | 336 | 4,318 | 2,688 | 2,688 | 2,688 | 2,688 | 15,406 | 5 |
|  |  |  |  | 72800 | Information Technology Equipment | 30,000 | 0 | 45,000 | 45,000 | 0 | 0 | 120,000 | 6 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 19,750 | 130,750 | 126,250 | 73,750 | 66,750 | 84,750 | 502,000 | 7 |
|  |  |  |  |  | Sub-Total Component 1 | 68,041 | 311,406 | 349,776 | 269,678 | 135,376 | 149,376 | 1,283,653 |  |
| COMPONENT 2 (44%) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Application of integrated network design and management of biodiversity corridors to ensure continued stability and sustainability of their biological, ecosystem services and socio-economic conservation values | DENR | 62000 | GEF | 71300 | Local Consultant | 4,000 | 53,700 | 87,000 | 23,000 | 18,000 | 9,000 | 194,700 | 8 |
|  |  |  |  | 71400 | Contractual Services - Individual | 1,946 | 146,682 | 146,682 | 146,682 | 146,682 | 146,682 | 735,356 | 9 |
|  |  |  |  | 71600 | Travel | 13,350 | 10,900 | 25,900 | 10,900 | 12,900 | 16,900 | 90,850 | 10 |
|  |  |  |  | 72100 | Contractual Service - Companies | 0 | 975,000 | 908,600 | 881,400 | 187,000 | 215,000 | 3,167,000 | 11 |
|  |  |  |  | 72200 | Equipment & Furniture | 1,800 | 102,000 | 0 | 0 | 0 | 0 | 103,800 | 12 |
|  |  |  |  | 72400 | Communication & Audio Visual Equip | 1,350 | 1,620 | 1,620 | 1,620 | 1,620 | 1,620 | 9,450 | 4 |
|  |  |  |  | 72500 | Supplies | 672 | 1,344 | 1,344 | 1,344 | 1,344 | 1,344 | 7,392 | 5 |
|  |  |  |  | 73300 | Maintenance of Equipment | 500 | 500 | 500 | 500 | 500 | 500 | 3,000 | 14 |
|  |  |  |  | 72800 | IT Equipment | 18,000 | 0 | 10,800 | 0 | 0 | 0 | 28,800 | 6 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 1,500 | 57,750 | 222,500 | 254,500 | 150,500 | 147,784 | 834,534 | 15 |
|  |  |  |  |  | Sub-Total Component 2 | 43,118 | 1,349,496 | 1,404,946 | 1,319,946 | 518,546 | 538,830 | 5,174,882 |  |
| COMPONENT 3 (33%) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community-based sustainable use and management systems in the two pilot biodiversity corridor systems in the Philippines | DENR | 62000 | GEF | 71300 | Local Consultant | 0 | 43,300 | 28,500 | 11,600 | 3,800 | 0 | 87,200 | 16 |
|  |  |  |  | 71400 | Contractual Services - Individual | 10,888 | 41,706 | 41,706 | 28,206 | 28,206 | 20,806 | 171,518 | 2 |
|  |  |  |  | 71600 | Travel | 7,676 | 12,000 | 11,969 | 8,676 | 8,676 | 7,676 | 56,673 | 3 |
|  |  |  |  | 72100 | Contractual Service - Companies | 0 | 250,000 | 805,000 | 970,000 | 466,000 | 100,000 | 2,591,000 | 17 |
|  |  |  |  | 72200 | Equipment & Furniture | 0 | 8,100 | 0 | 0 | 0 | 0 | 8,100 | 18 |
|  |  |  |  | 72400 | Communication & Audio Visual Equipment | 0 | 1,200 | 1,200 | 1,200 | 1,200 | 1,200 | 6,000 | 4 |
|  |  |  |  | 72500 | Supplies | 1,200 | 1,344 | 1,344 | 1,244 | 1,244 | 1,128 | 7,504 | 5 |
|  |  |  |  | 72600 | Grants | 0 | 0 | 192,000 | 373,000 | 300,000 | 150,000 | 1,015,000 | 19 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 0 | 10,000 | 100,000 | 128,500 | 86,000 | 59,000 | 383,500 | 20 |
|  |  |  |  |  | Sub-Total Component 3 | 19,764 | 367,650 | 1,181,719 | 1,522,426 | 895,126 | 339,810 | 4,326,495 |  |
| COMPONENT 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Knowledge management, gender mainstreaming, learning and monitoring and evaluation | DENR | 62000 | GEF | 71200 | International Consultant | 0 | 0 | 22,000 | 0 | 0 | 22,000 | 44,000 | 21 |
|  |  |  |  | 71300 | Local Consultant | 30,000 | 33,750 | 30,750 | 27,750 | 11,750 | 32,000 | 166,000 | 22 |
|  |  |  |  | 71400 | Contractual Services – Individual | 8,458 | 40,057 | 40,057 | 40,057 | 36,645 | 33,057 | 198,331 | 23 |
|  |  |  |  | 71600 | Travel | 5,673 | 10,500 | 10,500 | 22,000 | 10,000 | 7,750 | 66,423 | 3 |
|  |  |  |  | 72100 | Contractual Service - Companies | 0 | 15,000 | 79,000 | 0 | 0 | 10,000 | 104,000 | 24 |
|  |  |  |  | 72200 | Equipment & Furniture | 0 | 4,500 | 0 | 1,200 | 1,200 | 1,200 | 8,100 | 25 |
|  |  |  |  | 72400 | Communication & Audio Visual Equip | 270 | 270 | 540 | 540 | 540 | 340 | 2,500 | 4 |
|  |  |  |  | 72500 | Supplies | 716 | 1,344 | 1,344 | 1,344 | 1,144 | 1,144 | 7,036 | 5 |
|  |  |  |  | 74200 | Printing & Publication | 0 | 5,000 | 10,000 | 0 | 25,000 | 55,000 | 95,000 | 26 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 19,200 | 33,344 | 29,844 | 57,344 | 23,344 | 36,924 | 200,000 | 27 |
|  |  |  |  |  | Sub-Total Component 4 | 64,317 | 143,765 | 224,035 | 150,235 | 109,623 | 199,415 | 891,390 |  |
| Project managemenT (5%) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DENR | 62000 | GEF | 71300 | Local Consultant | 6,000 | 2,000 | 0 | 0 | 0 | 6,000 | 14,000 | 28 |
|  |  |  |  | 71400 | Contractual Services - Individual | 29,370 | 60,959 | 60,959 | 60,959 | 60,959 | 60,959 | 334,165 | 29 |
|  |  |  |  | 71600 | Travel | 6,283 | 15,964 | 7,757 | 7,034 | 7,539 | 6,214 | 50,791 | 3 |
|  |  |  |  | 72100 | Contractual Service - Companies | 0 | 15,000 | 0 | 0 | 0 | 0 | 15,000 | 30 |
|  |  |  |  | 72200 | Equipment & Furniture | 3,300 | 0 | 0 | 0 | 0 | 0 | 3,300 | 31 |
|  |  |  |  | 72400 | Communication & Audio Visual Equip | 0 | 1,200 | 1,200 | 1,200 | 1,200 | 1,200 | 6,000 | 4 |
|  |  |  |  | 72500 | Supplies | 2,736 | 6,357 | 2,839 | 2,529 | 3,418 | 2,850 | 20,729 | 5 |
|  |  |  |  | 72800 | Information Technology Equipment | 12,000 | 0 | 0 | 0 | 0 | 0 | 12,000 | 32 |
|  |  |  |  | 73400 | Rental & Maintenance of Other Equip | 0 | 700 | 700 | 700 | 700 | 700 | 3,500 | 33 |
|  |  |  |  | 74100 | Professional Services | 0 | 0 | 19,200 | 19,200 | 19,200 | 19,200 | 76,800 | 34 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 19,836 | 1,900 | 1,900 | 1,000 | 21,000 | 1,900 | 47,536 | 35 |
|  |  |  |  |  | Sub-Total Project Management | 79,525 | 104,080 | 94,555 | 92,622 | 114,016 | 99,023 | 583,821 |  |
| GRAND PROJECT TOTAL |  |  |  |  |  | 274,765 | 2,276,397 | 3,255,031 | 3,354,907 | 1,772,687 | 1,326,454 | 12,260,241 |  |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Amount Year 1 |  |  | Amount Year 2 | Amount Year 3 | Amount Year 4 |  | Amount Year 5 | Amount Year 6 | Total |
|  |  |  |  |  |  | GEF |  | 274,765 |  |  | 2,276,397 | 3,255,031 | 3,354,907 |  | 1,772,687 | 1,326,454 | 12,260,241 |
|  |  |  |  |  |  | UNDP |  | 359,081 |  |  | 359,084 | 359,084 | 140,917 |  | 140,917 | 140,917 | 1,500,000 |
|  |  |  |  |  |  | Other Co-financing |  | 1,710,426 |  |  | 10,800,000 | 16,318,800 | 16,649,000 |  | 8,806,100 | 6,916,681 | 61,201,007 |
|  |  |  |  |  |  | TOTAL |  | 2,344,272 |  |  | 13,435,481 | 19,932,915 | 20,144,824 |  | 10,719,704 | 8,384,052 | 74,961,248 |

Budget notes

| Budget note number | Comments |
| --- | --- |
| Component 1/Outcome 1: |  |
| 1 | 71300. Local consultants. Institutional Development Specialist supporting all outputs under Component 1 and 2 (Outputs 1.1, 1.2, 2.1, 2.2, 2.5) in particular to provide technical support: (i) to DENR for strengthening cross-sectoral planning and establishing national and sub-national coordination mechanism; (ii) identifying policy instruments related to national and sub-national planning that needs revisions; (iii) organizational requirements for multi-sectoral corridor advisory needs; (iv) assessing institutional and planning needs for participatory cluster planning and measures for strengthening local community institutions, including IP organizations. CBFM committees, farmer cooperatives, etc.) and (v) requirements for strengthening regional agency and LGUs for mainstreaming biodiversity into planning systems. (18 weeks over 5 years at USD 1,950 per week; Total: USD 35,100); BD Specialist supporting outputs under Component 1 and 2 (Outputs 1.2, 1.3, 2.1, 2.2) (i) Help establish BD baselines in 12 clusters using the HCVA approach and propose biodiversity standards to the EIA approach and process; (ii) identify policy gaps related to sectoral and sub-national agency planning for biodiversity mainstreaming; (iii) identifying biodiversity and threat monitoring protocols; and (iv) assessment and mapping of biological and ecosystem features in corridors and target clusters and improving biodiversity standards in EIA processes. (9 weeks over 5 years at USD2,100 per week – Total: USD18,900). BD Friendly Agriculture Practice Specialist for Output 3.2. (i) Help draft the operational guidelines for the implementation of BDFAP at small, medium and large scales in BD corridor sites; develop standards for the recognition of BDFAP in KBAs and PAs; (ii) facilitating training and capacity development (including preparation of training modules) for promoting BDFAPs (11 weeks @ USD2100 per week, total: USD23,100). IP Policy and Practice Consultant will support Output 1.2 and 2.1 (8 weeks @USD2700 per week, total: USD21,600). The consultant is tasked to (i) help revise the operations manual of ADSDPP, annotate folio of relevant existing IP-based good practices, help in identifying capacity building strategies for NCIP; (ii) identifying FPIC approaches for ensuring adequate consultation with IPs and conduct of participatory planning systems including oversight and providing guidance for preparation and implementation of IP plans BD Monitoring/GIS Specialist (18 weeks at USD1,750 per week, total – USD31,500). This consultant will support Output 1.3, 2.1 & 2.2. (i) Help develop monitoring systems and technologies, generate maps reflecting HCVA status and trends in 12 clusters within the 2 corridors; and (ii) defining monitoring indicators to be measured as part of cluster planning and implementation. Capacity Development Specialist will support all capacity development activities under Outcomes 1, 2, 3 and 4. He/she will also help in the conduct of KAP assessment, capacity assessment and identify training needs at the national and corridor level for all aspects of the project in consultation with other technical staff (including guidance for preparation of training modules)(40 weeks @USD2000, total: USD80,000) Local Governance Specialist will support Output 2.1, 2.5. He/she will collaborate with HLURB, DENR and DILG to provide advise on program design and staff capacity development strategy for at least 5 PLGUs and 24 MLGUs and facilitate the identification of appropriate approaches and entry points for integration of biodiversity considerations into LGU CLUP planning processes (14 weeks @USD2000 per week; Total 28,000) Technical Assistance to ERDB and DA for defining development assessment agenda in particular to identify for key areas for assessment of merits of best agricultural practices and habitat restoration (Outputs 2.4, 3.2 and 3.3) 9 weeks at USD1400 per week, total: USD12,600) IT Specialist will support Output 1.3 and Output 4.2 on the development of information and database system of the project (13 weeks @USD2,100 per week, total: USD27,300) Investment Specialist will help identify alternative investment options other than extractive industries and recommend priority investments in the 2 corridors (Output 3.4) (14 weeks @USD2100 per week; total USD29,400) Workshop Organizer (USD2,000 per workshop with a total estimated 20 workshops in 6 years, total: USD40,000). This will include facilitation and documentation of workshops Total: USD347,500 |
| 2 | 71400. Contractual Services- Individual. Project management and technical oversight and inputs of the Project Manager and relevant technical project staff on relevant outputs for Outcome 1 (Project Manager – 20% of USD3,806 monthly for 6 years; 2 technical staffs – 30% of USD1,621 monthly for 6 years). This includes preparation of work plan and budget, ensuring alignment of activities in the approved workplan, risk management addressing bottlenecks and issues in implementing activities, partnership building, participation and monitoring of activities, review of project progress and capturing the outputs and accomplishments for Outcome 1 in project reports. Total: USD124,834 |
| 3 | 71600. Travel. Project sites are in far flung areas of the Philippines. Travel to these areas from Manila is either by ship or by plane. Local travel by project staff, government representatives and consultants to project sites to organize, participate and/or monitor activities. Costs include domestic air tickets, bus and local rental of vehicles, if required and DSA. Total: USD168,076 |
| 4 | 72400 Communication. Cost of communication during pre, actual and post conduct of activities such as workshops, trainings, etc. Total: USD5,837 |
| 5 | 72500 Supplies Cost of office supplies in the implementation of activities and workshops such bond papers, kits, printing supplies, etc. Total: USD15,406 |
| 6 | 72800 It Equipment Cost of IT equipment that will be used for the BD monitoring, database and knowledge management under Output 1.3, 2.5 and 4.2. Total: USD120,000 |
| 7 | 75700 Learning Cost. Cost of venue, food and accommodation of participants during workshops, meetings, trainings, consensus building relevant to developing a governance framework for the BD corridor management. Initial meetings, workshops and trainings identified are: TWG meetings, sectoral meetings, policy reviews and development workshops, monitoring system development workshops, biodiversity monitoring trainings, among others. Total: USD502,000 |
| Component 2/ Outcome 2 |  |
| 8 | 71300 Local Consultants Institutional Development Specialist supporting all outputs under Component 1 and 2 (Outputs 1.1, 1.2, 2.1, 2.2, 2.5) (10 weeks for the 1st year at USD 1,000 per week; Total: USD 10,000); BD Specialist supporting outputs under Component 1 and 2 (Outputs 1.2, 1.3, 2.1, 2.2) (20 weeks for the 1st 2 years at USD1,200 per week – Total: USD24000). Help establish BD baselines in 12 clusters using the HCVA approach, propose biodiversity standards to the EIA approach and process PA Specialist/PA Governance Specialist will provide advisory support to 9 PAs in the project sites including resource mobilization. He/she will (i) facilitate the formulation of updated PA management plans; (ii) capacity building for key staff in management planning; and (iii) guidance for strengthening law enforcement within PAs (Output 2.3) (25 weeks @USD2100, total: USD52,200) Restoration Specialist will provide technical support for habitat restoration for Tamaraw in Mindoro BD Corridor including identifying carrying capacity of grasslands and methods for management and improvement of grasslands, including restoration techniques (Output 2.3) (4 weeks @USD2100 per week, total: USD9,000) Capacity Development Specialist will support all capacity development activities under Outcomes 1, 2,3 and 4. He/she will also help in the conduct of KAP assessment, capacity assessment and identify training needs at the national and corridor level (46.25 weeks @USD1200, total: USD55,500) Land Tenure Consultant will support the assessment of the typology of land tenure management issues in the 2 corridors and provide recommendations to address land tenure issues, including in particular related to Ancestral domains (Output 2.4) (15 weeks @USD1200, total: USD18,000) Workshop Organizer (USD2,000 per workshop with a total estimated 13 workshops in 6 years, total: USD26,000). This will include facilitation and documentation of workshops. Total: USD194,700 |
| 9 | 71400. Contractual Services- Individual. Project management and technical oversight, inputs and operational support of Project Management Unit from the national and corridor levels: Corridor Project Managers and relevant technical and admin/financial project staff on relevant outputs for Outcome 2 (2 Corridor Project Managers– 100% of USD1,924 monthly for 5 years; 4 technical staffs – 100% of USD1,250 monthly for 5 years, 2 Finance and Admin Staff – 100% of USD894 for 5 years, PMU technical support – 100% of USD1,619.93 monthly for 5 years). This includes preparation of workplan and budget, ensuring alignment of activities in the approved work plan, risk management, addressing bottlenecks and issues in implementing activities, partnership building, participation and monitoring of activities, review of project progress and capturing the outputs and accomplishments for Outcome 2 in project reports. Total: USD735,356 |
| 10 | 71600 Travel. Local travel by project staff, government representatives and consultants to project sites to organize, participate and/or monitor activities. Cost include domestic air tickets, bus and local rental of vehicles, if required and DSA. Total: USD90,850 |
| 11 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers for the following outputs: Output 2.1 – change detection study on Year 6 to determine localized and regional changes in the corridors in terms of land use changes, forest cover changes, agricultural use changes and forest connectivity to assess success of project interventions; Output 2.2 – in-depth HCVA assessment in 12 clusters of the 2 BD Corridors to identify the extent of specific conservation, sustainable forest, land and agricultural resource use and management and alternative livelihood needs as well as threats to be managed. Key stakeholders including municipal government entities and local communities (and IPs) will be involved during assessment and mapping exercises; Output 2.4 – ICCA and LCA documentation & establishment including specifically support to Ancestral Domains to identify areas for creation of ICCAs), technical and training support to LGU-based Local Conservation Areas (LCAs) and conservation set-asides in extractive industry and agri-business estates as well as guidance for negotiation of collaborative agreements in at least 9 Ancestral Domains (including development of ICCAs) and at least 4 LGUs and other arrangements with extractive industry and agri-business estates; Output 2.5 – Support to CLUP/CDP and PPFP updating or formulation of CLUPs and Provincial pans for mainstreaming conservation and habitat connectivity principles Total: USD3,167,000 |
| 12 | 72200 Equipment & Furniture These are equipment and furniture to be procured for use of project staff at the corridor level project management units (eg. Office tables, chairs, conference tables, etc.). It also includes the purchase of 3 4-wheel vehicles amounting to USD34,000 each which will be provided to 2 corridors ( 2 for Eastern Mindanao and 1 for Mindoro). Total: 103,800 |
| 4 | 72400 Communication and Audio-Visual Equipment. Cost of communication during pre, actual and post conduct of activities such as workshops, trainings, e-mail subscription, etc. Total: USD9,450 |
| 5 | 72500 Supplies Cost of office supplies in the implementation of activities and workshops such bond papers, kits, printing supplies, etc. Total: USD7,392 |
| 14 | 73300 Rental & Maintenance of IT Equipment. This includes maintenance costs and insurance requirement for all equipment, vehicles of the Project. Total: USD3,000 |
| 6 | 72800 IT Equipment. Cost of IT equipment that will be used by the project staff at the Corridor Level and the Regional DENR focal persons in implementing the Project; tablets to be issued to PAs which will be used in BD monitoring. Total: USD28,800 |
| 15 | 75700 Learning Cost. Cost of venue, food and accommodation of participants during workshops, meetings, trainings under Outcome 2: cluster meetings, PA management planning, PA capacity building, restoration planning, enforcement-related trainings, capacity building for ICCA management, cross visits, annual regional assessment and planning, capacity assessment, among others. Total: USD834,534 |
| Component 3 / Outcome 3: |  |
| 16 | 71300 Local Consultants. SFM Specialist will help in the review of forest certification, pilot forest certification and support the implementation of SFM methodologies in project sites (18 weeks @USD1,500 per week, total: USD27,000) SLM Specialist will help in the establishment of SLM exemplars and in the setting-up incentive systems for SLM in the LGUs (14 weeks @USD2100 per week, Total: USD27,300) BDFE Consultant will help in establishing database of BDFEs in the 2 corridors for systematic monitoring, conduct feasibility studies of BDFE, support at least 250 BDFEs in improving their marketing strategies and product development (14 weeks @USD2,100 per week, total: USD29,400) Documenter will help in documenting the establishment of SLM and SFM exemplars (5 weeks @700 per week, total: USD3,500) Total:USD87,200 |
| 2 | 71400 Contractual Services – Individual. Project management and technical oversight and inputs of the Project Manager and relevant technical project staff on relevant outputs for Outcome 1 (Project Manager – 20% of USD3,806 monthly for 6 years; 2 technical staffs – 50% of USD1,621 monthly for 6 years). This includes preparation of workplan and budget, ensuring alignment of activities in the approved workplan, risk management, addressing bottlenecks and issues in activity implementation, partnership building, participation and monitoring of activities, review of project progress and capturing the outputs and accomplishments for Outcome 3 in project reports. Total: USD171,518 |
| 3 | 71600 Travel. Project sites are in far flung areas of the Philippines. Travel to these areas from Manila is either by ship or by plane. Local travel by project staff, government representatives and consultants to project sites to organize, participate and/or monitor activities. Cost include domestic air tickets, bus and local rental of vehicles, if required and DSA. Total: USD56,673 |
| 17 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers for the following outputs: Output 3.2 – SLM guidance and support for identification and establishment of exemplars in 2 corridors in particular for supporting farmer associations/cooperatives and demonstrating the viability and benefits of a range of SLM measures and biodiversity-friendly agricultural systems that would entail (i) site selection; (ii) social preparation; (iii) participatory assessment of on-farm degradation and farming systems; (iv) tree-crop suitability assessment; (v) design and management of SLM exemplars; (vi) monitoring; and (vii) knowledge management and design of exemplars. In addition providing support for wide scale adoption, through training, demonstration of best practices, technical support, awareness and monitoring Output 3.3 – SFM planning, management & monitoring to facilitate: (i) identification of degraded forest areas for restoration to create biological linkages with KBAs; (ii) support to forest communities and private sector, including training for implementation of restoration/ANR measures; (iii) assess and recommend viable management arrangements at community and IP level; (iv) support for implementation of technical guidelines on SFM approaches; and establish monitoring systems for measuring effectiveness and restoration. Actual forest restoration costs borne by DENR and private sector. Output 3.4 – BDFE development, implementation and skills training including in particular: (i) identification of BDFE best practices; (ii) evaluate options and viability of specific value chains; (iii) facilitate training and capacity development and linkages for value chain promotion; (iv) training and capacity development to facilitate community update of BDFEs and value chains; (v) facilitate creation of partnerships with private sector for promotion of BDFEs, value chains products and services, ecotourism; Total: USD2,591,000 |
| 18 | 72200 Equipment & Furniture. These are equipment to be procured for the piloting of the forest certification and mapping/survey of forest areas. Total: USD8,100 |
| 4 | 72400 Communication and Audio Visual Equipment. Cost of communication during pre, actual and post conduct of activities such as workshops, trainings, e-mail subscription, etc. Total: USD6,000 |
| 5 | 72500 Supplies Cost of office supplies in the implementation of activities and workshops such bond papers, kits, printing supplies, etc. Total: USD7,504 |
| 19 | 72600. Grants. Microgrant schemes implemented consistent with the UNDP on-granting facility and managed by a contracted service provider. Microgrants include: under Output 3.3 for the SFM implementation of Community Based Forest Management tenure holders (USD3,000 per grant for maximum of 180 grantees); under Output 3.4 for the support on the development and implementation of biodiversity-friendly enterprises (USD1,600 per grant with maximum 250 grantees in the 2 corridors and co-financing for 5 MSMEs engaging on biodiversity-friendly businesses @USD15,000 per MSME). Instrument to be used for on-granting can either be UNDP’s Low Value Grant Agreement or that of the Governments Total: USD1,015,000 |
| 20 | 75700 Learning Cost. Cost of venue, food and accommodation of participants during workshops, meetings, trainings under Outcome 3: mapping & survey of forest under for certification, training on certification, agroforestry, and other SFM methodologies, training on the use of LAWIN, SLM-related trainings, BDFE business planning among others. Total: USD383,500 |
| Component 4 / Outcome 4: |  |
| 21 | 71200 International Consultant. Midterm review consultant under Output 4.1 (8 weeks at USD 2,750 per week, in Year 3; Total: USD 22,000); Terminal evaluation consultant under Output 4.1 (8 weeks at USD 2,750 per week, in Year 6; Total: USD 22,000); Total: USD44,000 |
| 22 | 71300. Local consultants. IEC/KM Consultants will help develop Communication, KM and IEC plan and strategies for the corridors, advise its implementation, support for production of IEC products and train local practitioners (Output 4.1) (20 weeks @USD1,750, total: USD35,000) National Evaluation Consultant Midterm review consultant under Output 4.1 (8 weeks at USD1,500 per week, in Year 3; Total: USD 12,000); Terminal evaluation consultant under Output 4.1 (8 weeks at USD1,500 per week, in Year 6; Total: USD 12,000); Total USD24,000 IT Specialist/Programmer will support Output 1.3 and Output 4.2 on the development of information and database system of the project (10 weeks @USD2,000 per week, total: USD20,000) IKSP Documentation Consultant will directly support NCIP in implementing its work package for IP communities, document of NRM aspect of IKSP and development of communication products for IP communities (Output 4.3) (10 weeks @USD1,700, total: USD17,000) Gender Specialist will support the gender mainstreaming strategies of the Project to ensure gender participation in project activities, train staff in gender mainstreaming and monitoring of gender participation (25 weeks @USD2000 per week, total: USD50,000) M&E Specialist will support the development and setting up of M&E system of the project and advise the M&E staff in the implementation of M&E plan, including in particular framework for monitoring of RFA indicators (10 weeks @USD2000 per week, total USD20,000) Total: USD166,000 |
| 23 | 71400 Contractual Services – Individual. Project management and technical oversight and inputs of the Project Manager and relevant technical project staff on relevant outputs for Outcome 1 (Project Manager – 20% of USD3,806 monthly for 6 years; 2 technical staffs – 20% of USD1,621 monthly for 6 years, Communication Officer – 100% of USD 1,345 monthly for 6 years) . This includes preparation of workplan and budget, ensuring alignment of activities in the approved workplan, risk management, addressing bottlenecks and issues in implementing project activities, partnership building, participation and monitoring of activities, review of project progress and capturing the outputs and accomplishments for Outcome 4 in project reports. Total: USD198,331 |
| 3 | 71600 Travel. Project sites are in far flung areas of the Philippines. Travel to these areas from Manila is either by ship or by plane. Local travel by project staff, government representatives and consultants to project sites to organize, participate and/or monitor activities. Cost include domestic air tickets, bus and local rental of vehicles, if required and DSA. Total: USD66,423 |
| 24 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers to support: Output 4.1 To (i) support implementation of KM and communications strategy; and (ii) design of communication materials and programs; Output 4.2 design of biological information management system and setting it up Output 4.3 Technical support for development of scaling up and replication strategy Total: USD104,000 |
| 25 | 72200 Equipment & Furniture. This includes the costs of camera and the fee for hosting the project website for the duration of the project. Total: USD8,100 |
| 4 | 72400 Communication and Audio Visual Equipment. Cost of communication during pre, actual and post conduct of activities such as workshops, trainings, e-mail subscription, etc. Total: USD2,500 |
| 5 | 72500 Supplies Cost of office supplies in the implementation of activities and workshops such bond papers, kits, printing supplies, etc. Total: USD7,036 |
| 26 | 74200 Printing & Publication. This will cover the costs of video production and preparation and publication of project’s knowledge products and IEC materials. Total: USD95,000 |
| 27 | 75700 Learning Cost. Cost of venue, food and accommodation of participants during workshops, meetings, trainings under Outcome 4: KM, IEC planning and implementation, IEC-related capacity building activities, M&E orientation and training, gender mainstreaming workshops and trainings, among others. Total: USD200,000 |
| Project Management: |  |
| 28 | Local Consultant Workshop Organizer – this will be hired for the conduct of the Inception Workshops both at the national and site levels. It also includes the facilitation, documentation and logistical arrangements for the workshops. (7 weeks @USD2,000 per week, total: USD14,000) Total: USD14,000 |
| 29 | 71400 Contractual Services – Individual. Project management oversight and day to day management inputs of the Project Manager and Operations and Admin staff of the Project (Project Manager – 40% of USD3,806 monthly for 6 years; Operations Officer – 100% of USD1,621 monthly for 6 years, PMU Finance/Admin Staff 100% of USD 1,000 for 6 years;, Procurement Assistant – part time at USD 896 monthly salary for 40 months ). This includes preparation of workplan and budget, ensuring alignment of activities in the approved workplan, risk management, addressing bottlenecks and issues in implementing project activities, partnership building, review of project progress, participation and monitoring of activities, capturing the outputs and accomplishments of the Project, secretariat support to the Project Board meetings. Total: USD334,165 |
| 3 | 71600 Travel This includes local travel by project staff, government representatives and consultants to project sites to organize, participate and/or monitor activities. Cost include domestic air tickets, bus and local rental of vehicles, if required and DSA. Total: USD50,791 |
| 30 | 72100 Contractual Services – Companies. The project will avail the services of a firm to help in the launch of the Project on the 1st year. Total: USD15,000 |
| 31 | 72200 Equipment & Furniture These are equipment and furniture to be procured for use of project staff at the national level project management units (eg. Office tables, chairs, conference tables, etc.). Total: USD3,300 |
| 4 | 72400 Communication and Audio Visual Equipment. Cost of communication during pre, actual and post conduct of activities such as workshops, trainings, e-mail subscription, etc. Total: USD6,000 |
| 5 | 72500 Supplies. Cost of office supplies in the implementation of activities and workshops such bond papers, kits, printing supplies, paper, maps, etc. Total: USD20,729 |
| 32 | 72800 IT Equipment. These are costs of IT equipment to be procured for use of project staff at the national level PMU and IP focal persons (8 laptops, printer/scanner, LCD projector) Total: USD12,000 |
| 33 | 73300 Rental & Maintenance of IT Equipment. This include maintenance costs and insurance requirement for all equipment of the Project. Total: USD3,500 |
| 34 | 74100. Professional Services. Financial NIM audit and spot-checks (USD19,200 starting Year 3 to Year 6). Total: USD76,800 |
| 35 | 75700 Learning Cost. This includes the costs of PMU regular meetings, TWG meetings, project orientation meetings, annual year-end assessments and planning of the Project, among others. Total: USD47,536 |

# Legal Context

Guidance to project developer:

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Option c. For Global and Regional Projects

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity]  (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

Option a. Government Entity (NIM)

Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

The Implementing Partner shall: (a) conduct project and program-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or program to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any program or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programs. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

1.	Governance and Policy relating to Biodiversity Corridors

2.	Biodiversity Corridor Profiles

3.	Framework for Integrated Ecosystem Management, Consensus Building and Planning and Implementation within Biodiversity Corridors

4.	Sustainable Forest Management for Biodiversity Conservation

5.	Rehabilitating Degraded Agricultural Lands in Mindoro and Eastern Mindanao Biodiversity Corridors

6.	Criteria and procedures for selecting conservation value forests, PAs, and KBAs in target clusters

7.	Biodiversity-friendly livelihood and business enterprises

8.	Improving capacity to manage High Conservation Value Forests, Protected Areas and Key Biodiversity Areas

9.	Capacity Building Strategy for LGUs and regional Offices of National Government Agencies in Biodiversity Corridors

10.	Procedures for Forest Certification System in the Philippines

11.	Potential menu of Conservation, SLM, SFM and Improved Agricultural Investments

12.	Framework for Addressing Knowledge Management and Communication

13.	Gender Analysis and Mainstreaming Action Plan

14.	Stakeholder Engagement Plan

15.	UNDP Risk Log

16.	Indigenous Peoples Planning Framework

17.	UNDP Social and Environmental and Social Screening Template (SESP)

18.	Multi-year Work-plan

19.	Tracking Tools (METTs)

20.	LOA with the government in case DPC is applied

21.	Terms of Reference for Key Staff

22.	UNDP Project Quality Assurance Report

23.	Synergy between UNDP and FAO GEF Projects

24.	Framework for Training

25.	Overview and Profiles of Tenure Instruments

26.	Summary of Consultants and Consultancy Services

27.	UNDP Capacity Assessment Scorecard (DENR, DA and NCIP)

27.1	DENR

27.2	DA

27.3	NCIP

28.	Results of the capacity assessment of the project implementing partner and HACT micro assessment

29.	Carbon Estimates

29.1	Carbon Calculation Notes

29.2	FAO EX-ACT

30.	Co-financing letters

31.	Consultations and List of People consulted during project preparation

32.	Monitoring Plan

The CSOs providing co-financing are: Center for Conservation Innovations, Haribon Foundation, Mindoro Biodiversity Conservation Foundation, Conservation International (Philippines) and Philippine Eagle Foundation

Biodiversity Management Bureau – DENR. Draft Philippine Biodiversity Strategy and Action Plan, September, 2015.

Conservation International (2013)

Philippines Land Degradation Neutrality (LDN) Report 2018

refers usually to  a variety of small, often immature fishes in both marine and fresh water systems

Despite the decline in these numbers, poverty continues to be concentrated in specific segments of the total population. Five of the nine basic sectors of the population determined by the PSA – farmers (34.3 percent), fishers (34 percent), children belonging to families with income below the official poverty threshold (31.4 percent), the self-employed and unpaid family workers (25 percent) and women from poor families (22.5 percent) – have higher poverty rates than the general population (21.6 percent) for the year 2015 (PSA, 2015b). Farmers and fishers have consistently registered as the two basic sectors with the highest poverty incidence in the general population since 2006

https://psa.gov.ph/content/poverty-incidence-among-filipinos-registered-216-2015-psa

Winterbottom etal. (2013). As cited by Guiang, E.S. 2015. Integrated  Approach in  Managing Major Biodiversity Corridors in the Philippines:  Some Ideas for Discussion. Presentation made at the Technical Discussion on Draft PIF of BD Corridor Project. November 11, 2015. Ninoy Aquino Visitors Center, Quezon City.

The DENR Administrative Order on IEM of 2013 defines IEM as “a holistic and integrated approach in the governance and management of ecosystems for conservation, socio-cultural preservation and economic development”

While the concept of IEM is more broadly defined in the Philippines, in the context of the project, the aim is adhere to the principles of No-Net-Loss for biodiversity where interventions are aimed at ensuring that there is no net reduction overall in the type, extent and condition of high conservation value areas or even if possible where HCV gains will exceed a specific set of losses.

The NBSAP Steering Committee has an overall perspective of implementation issues and opportunities of the NBSAP and can thus help define the nature and scope of the governance of corridors in the context of these realities.

The list includes Projects that officially end in Dec 2018, although some may be extended. They would have important knowledge products that can help in the implementation planning of this Project.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See Annex 32 for Monitoring Plan

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and need to be quantified. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the project through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Data collection methods should outline specific tools used to collect data and additional information as necessary to support monitoring. The PIR cannot be used as a source of verification.

The PIF suggested that PA system be expanded through gazettal of new PAs/OECMs covering 200,000 ha of high biological significance within the corridors, but PPG consultations revealed that IPs were reluctant to convert their ancestral domains into PAs, but rather would prefer to enhance conservation outcomes in these areas through improved conservation-friendly management practices and improved protection afforded by the IP themselves. As such, the project would support efforts for recognition of ancestral domains as ICCAs, support LGU-based local conservation areas (LCAs) and conservation set-asides in extractive industry and agri-business estates. Agreements include the following: (i) registry for ICCAs; (ii) co-management agreements between LGU and DENR, and subsidiary co-management arrangements between LGUs and local communities; and (iii) MOUs between private estates and DENR for privately owned conservation areas.

The 200,000 ha of new set-asides will be established following the mapping and be achieved through new management planning and participatory management agreements and developed and implementation of basic management and resource use plans

Specifically includes policies to incorporate biodiversity and gender considerations in biodiversity-friendly agriculture policy, extractive industries policy, biodiversity-friendly enterprise policy and local governance policy and improved guidelines (based on experiences from the ground) for integration of biodiversity safeguards

These baseline METT scores will be validated in Year 1, in particular PAs 1, 2, 3 and 10 that have high baseline METT scores.  All METT scores were developed through 2015-2017

These numbers will be validated in Year 1 of the project

Refer Indicators 9 and 10 on additional SLM and SFM projections through increased program investments in CLUPs

The Knowledge, Attitude and Practices (KAP) approach will collect reference qualitative and quantitative declarative information on misunderstanding and barriers to behavior change, using appropriate tools including survey questionnaires, Focus Group Discussions and Key Informant Interviews, among others.

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Assumes that 40% and 45% of the total carbon emission mitigated are achieved in the first 6 years for avoided deforestation and carbon sequestration respectively

Assumes that 60% and 55% of the total carbon emissions are achieved for the next 14 years post-project for avoided deforestation and carbon sequestration respectively

Excluding project team staff time and UNDP staff time and travel expenses.

Cost covered under Component 4

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

The representative of the IP groups will be identified through a vetting process with the National IP Federation, the federations at the corridor level and NCIP.

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

Only the responsible parties to be created as Atlas Implementing Agent as part of the COAs should be entered here. Sub-level responsible parties reporting directly to NIM Implementing Partners should not entered here. For example, if under NIM, UNOPS signs LOA with the IP to manage component 2, and a department of Ministry X will manage component 3, this means that UNOPS will be listed as the responsible party under component 2.  The rest of the components will list the IP as the responsible party.

Only cash co-financing actually transferring to UNDP bank accounts and to be budgeted and used under this project should be entered in the main TBWP table and in Atlas. Other co-financing should only be shown in the summary table.

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc...