## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | #NAME?
3

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Europe and Central Asia (REU)
Country(ies): | Türkiye
Project Title: | Contributing to Land Degradation Neutrality (LDN) Target Setting by Demonstrating the LDN Approach in the Upper Sakarya Basin for Scaling up at National Level
FAO Project Symbol: | GCP /TUR/065/GFF
GEF ID: | 9586
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Land Degradation
Project Executing Partners: | Ministry of Agriculture and Forestry (MAF), Ministry of Environment Urbanization and Climate Change (MEUCC)
Initial project duration (years): | 4
Project Dates
GEF CEO Endorsement Date: | 2019-01-24
Actual Agency Approval Date | 2019-05-02
Project Implementation Start Date/EOD: | 2019-08-15
First Disbursement Date | 2019-10-29
Planned Project End Date/NTE1: | 2022-02-28
Revised project implementation End date (if approved)2: | 2025-12-31
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2026-12-31
Funding
GEF Grant Amount (USD): | 2388584
Total GEF grant delivery (as of June 30, 2025 (USD): | 2262978.93
Total Co-financing amount (USD)3: | 13600000
Total estimated co-financing materialized as of June 30, 2025: | 38438491.98
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | N/A
Expected Mid-term Review date5: | N/A
Actual Mid-term review date (if already completed): | 2023-02-02
Expected Terminal Evaluation Date6: | ongoing
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Highly Satisfactory
Overall implementation progess rating: | Satisfactory
Overall risk rating: | Low
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 5th PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Sibel Nihal Tekin, NPC (FETUR) |  | sibelnihal.tekin@csb.gov.tr
Budget Holder (BH) | Viorel Gutu, SEC-SRC and FAO Representative in Türkiye |  | Viorel.Gutu@fao.org
GEF Operational Focal Point (GEF OFP) | Ahmet Bağcı , Deputy Minister; Ministry of Agriculture and Forestry |  | ahmet.bagci@tarimorman.gov.tr
Lead Technical Officer (LTO) | Sara Marjani Zadeh, Land and Water Officer |  | Sara.MarjaniZadeh@fao.org
GEF Technical Officer (GTO) | Kaan Evren Basaran, REU-GEF Support Specialist |  | Kaan.Basaran@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
National Project Coordinator | Yes | Sibel Nihal Tekin sibelnihal.tekin@csb.gov.tr |  | The NPC was not on board since 31 December 2024
Operations Specialist | Yes | Isilay Ozcan, isilay.ozcan@fao.org
Operations Associate | Yes | Gozde Aras, Aras, Gozde.Aras@fao.org
Project Assistant | Yes | Nagme Demirbas, Nagme.Demirbas@fao.org

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
Outcome 1.1: Enhanced enabling Environment for LDN | Number of institutional training courses that integrate LDN Number of people trained at local and central level | Knowledge of LDN and how to operationalize it at local and national level is limited despite the earlier LDN pilot project | At least one institutional training programme that integrates LDN At least 30 people trained at central level and 15 at local | At least two central-level training programmes and one local that integrates LDN At least 150 people trained (at least 50 women) | Project inception workshops in 3 Project provinces, -4 technical workshops, -One online training on FFS, 1 inception and 1 curricula workshop on FFS -2 Stakeholder meetings -Numerous online meetings by Ministry partners; -2 online trainings (due to covid -19) on combatting desertification and land degradation were conducted with participation of 144 experts from African countries. -3 other training were conducted by Ministry partners. 194 people were trained in these trainings in this reporting period. -National Strategy and Action Plan on Combatting Desertification was renewed and a workshop was conducted by CEM, with participation of 34 people - in the final year 187 people received training organized by Ministry partners through 2 workshops and 1 technical workshop conducted by the project (approximately 50:50 male to female) across a broad cross-section of institutions (inter alia: agriculture, forestry, spatial planning, environment, water management, nature conservation). Target was exceeded including contributions to regional and global training. | 100% | Highly Satisfactory (HS)
| National and international symposiums International LDN exchange |  | National LDN symposium At least 5 people participate in national symposium related to LDN At least 35 people participate in international LDN exchange programmes | International LDN Symposium At least 5 people participate in national and 2 in an international symposiums related to LDN At least 50 people participate in international LDN exchange programmes | "Workshop on the Development of the Project for Combating LD and Desertification in the ECO Region" was held in Türkiye between 14-16 December 2021. Project lead agency organized a joint workshop with UNCCD with participation of 40 experts, namely ``Capacity building on the Implementation of the Convention to Combat Desertification` Ministry partner participated to the online First G20 Environment and Climate Sustainability WG Meeting on `Arrest Land Degradation, Restore Ecosystem.– the project has contributed widely to international symposium on LDN and promoting the DSS | 100% | Highly Satisfactory (HS)
| National Online Information Sharing Forum on LDN | No LDN platform exists | 1 National Online Information Sharing Forum on LDN | 1 National Online Information Sharing Forum on LDN | National Online Information Sharing Forum on LDN website is established | 100% | Highly Satisfactory (HS)
| Number of Farmer Field Schools (FFS) established on modern and sustainable production methods Number of local people trained, including how many women | Knowledge of modern and sustainable production methods is limited at local village level | At least 3 FFS established At least 30 local people trained of which 50% are women | At least 3 FFS established At least 60 local people trained of which 50% are women | 4 FFS were established and 97 local people were trained, which 47 are women. 4 more FFS were established in Eskisehir and Kutahya, and trained 80 farmers – target was exceeded and to a high quality. | 100% | Highly Satisfactory (HS)
| Mass media campaigns on LDN | No mass media campaigns on LDN | At least 1 mass media campaign | At least 2 mass media campaign | One introductory film was prepared on LDN and combatting desertification. High level managers of the Ministry Partners presented on LDN on TV programs, delivered interviews and published. LDN related information from official social media accounts of the Ministry. 3 public service announcements published on desertification. Press statements announced on LDN and desertification. LDN and desertification is highlighted on XV World Forestry Congress through presentations. | 100% | Highly Satisfactory (HS)
| New and/or revised legislation that operationalize the LDN approach | LDN is not currently integrated into any legislation or regulations | Gap analysis of relevant legislation New and/or revised legislation | Gap analysis of relevant legislation New and/or revised legislation | A GAP analysis was prepared during the preparation of LDN action plan process. At the LDN target-setting workshop, participants discussed the necessity for new and/or revised legislation to operationalize the LDN approach. Feedback highlighted that creating an umbrella framework or a presidency note dedicated to the implementation of LDN could facilitate the mainstreaming and upscaling of the LDN approach effectively. This would provide a cohesive structure for aligning various legislative and policy efforts, ensuring a more streamlined and coordinated approach to achieving LDN goals. | 100% | Highly Satisfactory (HS)
Outcome 2.1: Decision-support system (DSS) for LDN target setting and planning established | DSS established with calibrated metrics for LDN indicators | There are many DSS for NRM in Türkiye, but none that focuses on LDN | DSS for LDN in place with calibrated metrics for LDN indicators | DSS for LDN in place with calibrated metrics for LDN indicators and upscaled | The LDN DSS is now functioning as a tool that allows any user to select a particular area of interest, (for example a water catchment), and obtain summary statistics, charts and tables integrating the available data. One of its key functionalities is to make multi criteria analysis and show areas that meet certain criteria. The tool's adaptability and broad applications make it suitable for replication in other countries and regions, informing the target-setting process and enhancing the monitoring and evaluation of land degradation. The DSS has been effectively tested in the Upper Sakarya Basin to very good effect. The DSS has been upscaled to cover all of Türkiye (78.4 million ha.). | 100% | Highly Satisfactory (HS)
| Calibrated metrics for LDN indicators available | Information on the three LDN indicators – land cover, SOC and productivity – is available but needs to be calibrated | Calibrated data on land cover, SOC and productivity available for the Upper Sakarya Basin | Calibrated data on land cover, SOC and productivity available for the whole of Türkiye | The DSS has been effectively tested in the Upper Sakarya Basin to very good effect. The DSS has been upscaled to cover all of Türkiye (78.4 million ha.). -SOC and land productivity indicators are calibrated, -Türkiye`s desertification model is calibrated. | 100% | Highly Satisfactory (HS)
| Integration for LDN DSS | Software for other DSS exist that will be used to integrate the LDN DSS | LDN DSS available | LDN DSS integrated, tested and used | LDN DSS integrated, tested and used. | 100% | Highly Satisfactory (HS)
| Land cover classes and land degradation levels in the Upper Sakarya Basin verified | Land cover classes and land degradation levels in the Upper Sakarya Basin have been determined, but need verification | Land cover classes and land degradation levels in the Upper Sakarya Basin verified | Land cover classes and land degradation levels in the Upper Sakarya Basin verified | UASIS Corine maps is integrated to DSS | 100% | Highly Satisfactory (HS)
Outcome 2.2: Monitoring system and related capacity for LDN in place | LDN monitoring system in place with target setting agreed | Many monitoring approaches have been tested in Türkiye that will provide the baseline | LDN monitoring system in place with target setting agreed | LDN monitoring system in place with target setting agreed | LDN DSS is established and is capable to monitor changes in LDN indicators LDN DSS results were used for LDN reporting to UNCCD (PRAIS-4) National targets were refined using the LDN DSS Project partners requested to use DSS for prioritizing the implementation sites under the national watershed management strategy DSS assessments were used to support LDN measures in the 12th National Development Plan. Turkiye is one of the participating country in the LDN TSP 2.0. Project for Land Degradation Neutrality Target Setting | 100% | Highly Satisfactory (HS)
| Target setting and hot spots and cold spots for gains and losses identified | Many monitoring approaches have been tested in Türkiye, including the ‘land productivity dynamics (LPD) approach’ that the target setting will build on | Target setting completed and hot spots and cold spots for gains and losses identified | Target setting completed and hot spots and cold spots for gains and losses identified | LDN DSS enables users to identify hot and cold spots for gains and losses using LPD. Türkiye was assigned as one of the 18 countries by UNCCD that will set/renew LDN targets. DSS is going to be used to set and monitor new LDN targets. Existing national LDN targets are to be revised using the DSS, prioritizing implementation sites in the national Watershed Management Strategy, losses and gains in productivity are generated and mapped. | 100% | Highly Satisfactory (HS)
| Agreed soil organic carbon monitoring approach | The Soil Organic Carbon Monitoring Model and Mapping Project of Türkiye will serve as the baseline | Agreed soil organic carbon monitoring approach | Agreed soil organic carbon monitoring approach disseminated | Türkiye has set a model for SOC and national SOC model was used as a base in DSS. In addition, a potential carbon sequestration map was produced for the whole country. For plot-level SOC monitoring, soil samples were taken from pilot sites. Agreed soil organic carbon monitoring approach disseminated. | 100% | Highly Satisfactory (HS)
| TCM and LPD Models tested | The existing TCM model needs field calibration | TCM and LPD Models tested in the Upper Sakarya Basin | TCM and LPD Models compared on an area basis | The DSS allows comparison of TCM and LPD, and both can be used for multi criteria analysis. | 100% | Highly Satisfactory (HS)
| Web-based Monitoring, Evaluation and Reporting System (IDR) operationalized Training of decision-makers and technical staff | The IDR has been developed, but further capacity in using it is needed | The IDR operationalized and 20 decision-makers and 30 technical staff trained of which 50% are women | A total of 30 decision-makers and 50 technical staff trained | The capacity to use the DSS has been developed and will continue further with human resources training to ensure sufficient capacity, especially at provincial and district levels. 4 online trainings were carried out on IDR. More than 200 people trained. | 100% | Highly Satisfactory (HS)
| Sub-indicators of climate variability tested in the Upper Sakarya Basin for the TCM and SOC Models | The TCM and SOC models have not been calibrated for climate variability | Sub-indicators of climate variability tested in the Upper Sakaria Basin for the TCM and SOC models | Sub-indicators of climate variability tested in the Upper Sakaria Basin for the TCM and SOC models | A Climate section is added to DSS that allows user compare 3 different climate models. Climate layers for 10-year periods integrated under DSS. Creating statistics and integrated maps that allow comparison of models are completed. | 100% | Highly Satisfactory (HS)
Outcome 3.1: Improved land management, land cover, and increased soil | Area covered by SLM and SFM best practices | 0 | 7,000 | 14,000 | The total area with improved land management based upon project records is: 20,675 ha of cultivated land 2,975 ha of rangeland 33,708 ha of forest land | 100% | Highly Satisfactory (HS)
| Ha of land covered by landscape-specific improvement plans | 0 covered, but the LDN planning will be integrated into the existing integrated watershed planning processes | 2,000,000 | 4,313,827 | Finalized. The neutrality mechanism supports the achievement of LDN through a proactive focus on planning; it comprises the counterbalancing of anticipated losses in land-based natural capital with planned gains, within unique land types. LDN DSS now allows any user and decision-maker to counterbalance in any landscape, which was first targeted for Upper Sakarya Basin which is 4,313, 827 ha has now been extended to the whole country. | 100% | Highly Satisfactory (HS)
| Area covered by SLM and SFM best practices Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry, and Other Land (metric tons of CO2e) | 0 covered, but the project will build on BPs tested elsewhere in Türkiye Mid term target: More than 1,000,000 metric tons of CO2e avoided (10 year period of capitalization) | 7,000 Final target: More than 3,065,415 metric tons of CO2e avoided (3 years of Implementation + 10 years of capitalization) | 14,000 | 57,649 ha of lands in total; 20,657 ha of cultivated land 3,025 ha of rangeland 33,708 ha of forest land The target of 3,065,415 metric tons of CO2e avoided is achieved | 100% | Highly Satisfactory (HS)
| Number of climate-smart measures and approaches integrated into SLM/SFM | 0 | 5 | 10 | 12 Climate smart measures and approaches were integrated under SLMs. 6 activities planned in previous planning period were completed | 100% | Highly Satisfactory (HS)
| Implementation plan for achieving LDN targets in the Upper Sakarya Basin | No such plan exists | 1 implementation plan for achieving LDN targets in the whole Sakarya Basin | 1 implementation plan for achieving LDN targets in the whole Sakarya Basin | The implementation plan is prepared and implementation of the plan is upscaled to the whole Sakarya Basin. | 100% | Highly Satisfactory (HS)
Outcome 3.2: Land productivity increased and livelihoods for local communities strengthened | Increase in annual land productivity trends in Upper Sakarya Basin | Land productivity and incomes are low in the Upper Sakarya basin due to outdated SLM and SFM practices | Mid-term target: Negative trends of LPD are reverted (𝑡𝑎𝑟𝑔𝑒𝑡: Δ𝑁𝑃𝑃≥0,𝑤ℎ𝑒𝑟𝑒 Δ𝑁𝑃𝑃 𝑁𝑃𝑃2021−𝑁𝑃𝑃2018) | Final Target: Positive trend in NPP achieved (𝑡𝑎𝑟𝑔𝑒𝑡: Δ𝑁𝑃𝑃0,𝑤ℎ𝑒𝑟𝑒 Δ𝑁𝑃𝑃= 𝑁𝑃𝑃2021−𝑁𝑃𝑃2018 300 households with improved living conditions 300 women trained in entrepreneurship | A positive NPP trend has been achieved. | 100% | Highly Satisfactory (HS)
| Gender Action Plan for the Upper Sakarya Basin | No such plan exists | Gender Action Plan for the Upper Sakarya Basin | Gender Action Plan for the Upper Sakarya Basin | Gender action plan was developed. The project has made important contributions towards gender equality in the target communities in the Upper Sakarya Basin. | 100% | Highly Satisfactory (HS)
| Number of gender sensitive climate resilient practices Area covered | Existing practices are not climate resilient | 5 practices/200 women 150 ha | 10 practices/300 women 200ha | 11 Practices were implemented: soil and land management practices, crop and pasture management practices and alternative practices; - Honeybee Colonies, Beehives and Bee Kits, trainings were provided for 5 women farmers - Rangeland rehabilitation in 10 ha of land with salt bushes, to provide forage -Drip irrigation systems applied in 200 da of land in onion, sugar beet and maize fields - Crop rotation in 300 da with Hungarian vetch with direct seedling, 500 da with oat -Organic soil conditioner (leonardite) and local chickpea variety applied in 300 da, which resulted with 50% yield increase -A greenhouse was established for vegetable production, where members of a women cooperative were trained -Wooden sales booths were established in a pilot sites which is in a dam area, that will help the community members create alternative income -Milk storage and cooling tank and forage pelletizer were procured under the project, where main income of local people is livestock. The aim was to increase the animal nutrition by using pelletizer (farmers were trained on this) and supporting them to increase the income earned from milk by collecting, storing and selling milk directly to the companies -Procurement of home-type biogas plants is finalized to avoid uncontrolled manure storage and greenhouse gas emissions. The installation of the systems were completed. However, the operinalization of the systems are not completed yet. -Provision of Solar Powered Submersible Pump System and Off-Grid Photovoltaic System is finalized. Solar-powered submersible pump system will be used to transmission spring drinking tap water with the solar-powered pump system. Operationilization of 25 biogas systems and training are continuing Coverage: project sites; Kütahya-Yayla Baba, Ankara-Polatlı, and Eskişehir-Sivrihisar. | 90% | Satisfactory (S)
| Number of households with improved living conditions |  | 150 households | 300 households | In scope of the improvement of living conditions small-scaled biogas systems are being established to prevent uncontrolled manure storage, to provide heating as well as reduce CO2 emissions benefiting 150 people. Gender sensitive and climate smart practices implemented contribute local people`s income and living conditions, | 90% | Satisfactory (S)
| Number of women trained | Not existing | 50 women | 100 women | 15 women were trained on beekeeping; 47 women were trained on vegetable production and livestock under FFSs; 30 women in 2024. | 100% | Satisfactory (S)
Outcome 4.1: Upscaling of the LDN DSS to national level covering all of Türkiye (78.4 million ha) | Area covered by the LDN DSS | No national LDN DSS is in place | Land cover classes for the whole of Türkiye identified based on the 6 IPCC classes | National LDN DSS covers the national territory of 78.4 million ha | DSS upscaled to national level (78.4 million ha.) | 100% | Highly Satisfactory (HS)
| LDN metrics for the whole of Türkiye available in DSS | No national LDN DSS or metrics is in place | Land cover classes for the whole of Türkiye identified based on the 6 IPCC classes | LDN metrics for the whole of Türkiye available in DSS | Finalized | 100% | Highly Satisfactory (HS)
| LDN target setting in place | No LDN target setting at the national scale | Alternative indicators examined for use at the national scale (socio-economic) | National LDN target setting in place | Finalized | 100% | Highly Satisfactory (HS)
| Number of bankable projects for the LDN fund | No projects for the LDN fund developed in Türkiye | 0 | 1 bankable project | An online informative workshop to inform the Ministry partners to formulate project proposals was held. | 50% | Moderately Satisfactory (MS)
Outcome 4.2: Monitoring of project results, lessons learned and dissemination | M&E system is in place |  |  |  |  | 100% | Highly Satisfactory (HS)
| Baseline and targets for GEB indicators refined | 0 | Project M&E system delivers expected reports and informs project management | Project M&E system delivers expected reports and informs project management | Project M&E system delivers expected reports and informs project management | 100% | Highly Satisfactory (HS)
| Mid-term and final evaluation reports | 0 | Mid-project review recommendations implemented | Final evaluation | Conducted and recommendations considered. | 100% | Highly Satisfactory (HS)
| Experience sharing notes | 0 | 2 Experience sharing notes | 3 experience sharing notes | An LDN Publication was developed titled ``Monitoring the Land Degradation Neutrality impact pathway across scales and sectors based on experiences from Türkiye`. Two more publications have not been finalized, however, published in FAO Newsletter, namely: 1. Assessing Land Degradation Neutrality in Türkiye Incorporating Multi-Criteria Analysis towards Sustainable Land Management; 2. Harvesting Resilience: Farmer Field Schools in Promoting Sustainable Practices and Advancing Land Degradation Neutrality. (FAO Newsletter https://openknowledge.fao.org/server/api/core/bitstreams/0a074de6- 2613-4497-a9b7-9eb257813e11/content https://openknowledge.fao.org/server/api/core/bitstreams/884b94b5- 57c1-443d-832a-eb96bae6a952/content ) The project experience has been widely promoted through the Cem, PIU and FAO at various international LDN workshops and through other forums. A video recording and documentation of CEM Academy Educational Programs to enhance the visibility of the project and promote its results on international platforms is continuing. | 95% | Highly Satisfactory (HS)
| National LDN Guideline | 1 LDN guideline | National LDN Guideline | 1 LDN guideline | This co-financed activity, planned to be performed by Ministry partner CEM, was delivered during the LDN TSP 2.0 process. As a part of the target setting program, 9 different reports have been developed, and the final document reflects all the steps. This process was presented during UNCCD COP 16 2024. | 80% | Satisfactory (S)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
97.29% | 239.2% | 94.74%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
| Highly Satisfactory (HS) | Highly Satisfactory (HS) | Highly Satisfactory (HS) |  | Highly Satisfactory (HS)
Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project contributed to Turkey's LDN Targets by developing DSS system and empower the local people through the field implementations | As one of the first Land Degradation Neutrality (LDN) projects, it has produced valuable results demonstrating the LDN approach in the field. The project has contributed to the establishment of new LDN targets for the country. The project results and the model developed can be disseminated by other projects. | Despite significant challenges posed by the COVID-19 pandemic, which considerably affected planned field work and in-person stakeholder engagement, the project team demonstrated strong adaptability and commitment. The Project Coordinator and partners effectively adjusted implementation modalities, catching up on delayed activities and ensuring that key outputs were delivered on time. Importantly, the project developed the Decision Support System for Land Degradation Neutrality (LDN Tool) — the first of its kind — which has since been replicated in other countries (LDN Turkey Tool: https://projectgeffao.users.earthengine.app/view/ldn-turkey). This innovative achievement, combined with targeted capacity-building and integration of modeling tools, significantly strengthened the impact and sustainability of project outcomes |  | The project has made highly satisfactory progress across nearly all outcome areas. It has a strong contribution to LDN mainstreaming in Türkiye, with transformative potential for replication at regional and global levels.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 3.2: Land productivity increased and livelihoods for local communities strengthened |  | Operationalization of house type Biogas Systems |  | Contractor |  | by project closure, which is 31 December 2025
Outcome 4.2: Monitoring of project results, lessons learned and dissemination |  | Video Recording and documentation of CEM Academy Educational Programs to enhance the visibility of the project and promote its results on international platforms |  | Project government partner |  | by project closure, which is 31 December 2025
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.Enhanced enabling Environment for LDN
Output 1.1: Capacity development program in place on LDN target setting and its implementation for local and central government staff | Number of institutional training courses that integrate LDN Number of people trained at local and central level National and international symposia International LDN exchange | All capacity building programs such as Informative meetings , Awareness-raising activities, Institutional-level training courses, National LDN Symposium, International LDN Symposium are completed. |  |  | N/A
Output 1.3.Capacity development program in place for farmers, herders and forest villages in the Upper Sakarya Basin | Number of Farmer Field Schools (FFS) established on modern and sustainable production methods Number of local people trained, including how many women Mass media campaigns on LDN Mass media campaigns on LDN | Certified herders training, Farmer exposure visits for demonstration of best practices on SLM and SFM, Mass media campaigns on LDN were conducted. |  |  | N/A
Output 1.5.Integration of the LDN approach and priorities into strategic planning processes at sub-national and national levels | Strengthening of the LDN intersectoral working group | Information dissemination meetings with the central administrative and strategic planners of LDN-related institutions and the administrative and planners of local institutions, Information dissemination meetings with stakeholders and Information dissemination meetings with NGOs (Upper Sakarya Basin) were conducted. |  |  | N/A
Outcome 2.2.Monitoring system and related capacity for LDN in place
Output 2.2.1.LDN target setting based on current and existing monitoring infrastructure and metrics agreed | Target setting and hot spots and cold spots for gains and losses identified | LDN target setting using the existing land degradation monitoring systems at national and sub-national level (TCM/TOK/POS/DEMIS) is completed |  |  | N/A
Output 2.2.5: Climate variability integrated into the LDN DSS and tested in the Upper Sakarya Basin | Sub-indicators of climate variability tested in the Upper Sakarya Basin for the TCM and SOC Models | Monitoring, testing and analyzing sub-indicators of climate factor of the TCM and Soil Organic Carbon (TOK) Models in the Upper Sakarya Basin is completed |  |  | N/A
Outcome 3.1: Improved land management, land cover, and increased soil
Output 3.1.2.Demonstrations of SLM and SFM best practices in forests, rangelands and croplands that provide carbon benefits on 14,000 ha of land | Area covered by SLM and SFM best practices | Implementation of sustainable pasture management practices and implementation of the best SFM on forest areas were completed. |  |  | N/A
Output 3.1.3.Measures and approaches for reducing the impacts of climate variability integrated into SLM and SFM practices | Number of climatesmart measures and approaches integrated into SLM/SFM | Technical assistance on climate-friendly agricultural/forestry practices, Integration of measures and approaches for climate resilience into SLM and SFM practices and monitoring and evaluating climate resilience of SLM and SFM measures using SHARP like assessment were completed. |  |  | N/A
Outcome 3.2.Land productivity increased and livelihoods for local communities strengthened
3.2.2: Introduction of gender-sensitive climate resilient practices to enhance land productivity | Number of gender sensitive climate resilient practices Number of women trained | Operatonalization of 25 biogas systems are not completed yet. |  |  | Some part of the systems are not designed user friendly, thus the users stopped feeding the tanks. The contactor will handle the problems.
Outcome 4.1: Upscaling of the LDN DSS to national level covering all of Turkey (78.4 million ha)
Output 4.1.2: LDN target setting at national scale in place | LDN target setting is in place | Analyzing socio-economic indicators for a new input for LDN was completed as of December 2024. |  |  | N/A
Output 4.1.3: Development of bankable projects for the LDN fund (at least 1) | Number of bankable projects for the LDN fund | Development of one bankable project for the LDN fund was completed as of December 2024. |  |  | N/A
Outcome 4.2: Monitoring of project results, lessons learned and dissemination
Output .4.2.1: Global Environmental Benefits monitored and assessed | M&E system is in place Lessons learned disseminated | M&E of GEB indicators are completed as of September 2024. |  |  | N/A
Output 4.2.2: Mid- term and final evaluation conducted | Mid-term and final evaluation reports | Conducted. Draft final Evaluation report is shared with the stakeholders for their comments |  |  | N/A
Output 4.2.3: Experience sharing on Project-related “lessons-learned” and a national LDN guideline published | Experience sharing Notes LDN guideline | Preparation of a National LDN guideline was completed as of December 2024.Video Recording and documentation of CEM Academy Educational Programs to enhance the visibility of the project and promote its results on international platforms is contunuing. |  |  | Government request from FAO to prepare an educational program for CEM academy to disseminate project results in the last quarter of the project implementation, wil be finalized December 2025.
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) |  | Satisfactory (S)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | All delivarables of the project included in its LFM were completed as of December 2024 and the final evaluation process of the project is continuing. | The project has progressed in line with the revised work plan, with all major deliverables completed on time and interim outputs meeting expected quality standards. Technical backstopping was consistently provided to ensure compliance with GEF requirements and alignment with FAO’s strategic priorities. Even though the project was significantly affected by COVID-19, which limited and delayed field work, the project coordinator and team managed to adapt implementation strategies, recover lost time, and successfully catch up on planned activities, ensuring that objectives remained on track | The DSS developed by the project have already been upscaled to at least 18 countries and it’s utility, effectiveness and cost efficiency has been recognised by the UNCCD and the GEF amongst others in this reporting period. | Comments | The project has made highly satisfactory progress across nearly all outcome areas. It has a strong contribution to LDN mainstreaming in Türkiye, with transformative potential for replication at regional and global levels.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Some of the following activities, which continued in the previous reporting period, were completed in the first six months of this reporting period. •Informative meetings, awareness-raising activities, institutional-level training courses, national and international LDN Symposium •Certified herders training, farmer exposure visits for demonstration of best practices on SLM and SFM, mass media campaigns on LDN •Information dissemination meetings with the central administrative and strategic planners of LDN-related institutions and the administrative and planners of local institutions, information dissemination meetings with stakeholders and information dissemination meetings with NGOs •LDN target setting using the existing land degradation monitoring systems at national and sub-national level (TCM/TOK/POS/DEMIS) •Monitoring, testing and analyzing sub-indicators of climate factors of the TCM and Soil Organic Carbon (TOK) Models in the Upper Sakarya Basin •Implementation of sustainable pasture management practices and implementation of the best SFM on forest areas •Technical assistance on climate-friendly agricultural/forestry practices, Integration of measures and approaches for climate resilience into SLM and SFM practices and monitoring and evaluating climate resilience of SLM and SFM measures using SHARP like assessment •Analyzing socio-economic indicators for a new input for LDN •Development of one bankable project for the LDN fund •Preparation of a National LDN guideline. The final evaluation of the project continues with the process of collecting of the stakeholders's comments on the report.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The challange that the project encountered in this reporting period is the operationalization of household biogas systems. It has been observed in the project sites that there is a general concern among users regarding the operation of the systems due to problems encountered during use. For this reason, many users have turned off the power supply and turned off the system. To overcome this challange, following the field visit with the participation of representatives from contractor, FAO, and Provincial Directorates of Agriculture and Forestry—a meeting was held. During this meeting, the issues related to the biogas systems and potential solutions were discussed and resulted that contractor promptly adopts a solution-driven strategy aimed at optimizing system performance. Furthermore, in order to enhance user adaptation, it is recommended to deploy increased on-site guidance, training, and support mechanisms.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | No
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The project does not have an Exit strategy but all measures have been taken to ensure the sustainability of the project results by the contribution of project partners. The DSS is upscaled for different GEF projects; capacity building is provided and Ministry partners already started using it for their institutional planning. On the other hand, the Project is now contributing to refining national LDN targets, which means setting more specific, time-bound, policy-coherent, quantitative, spatially explicit, gender-responsive, and adequately integrated targets and integrating them into land use planning frameworks. In addition, the project has developed 3 publications that reflect the lessons learned and methodology on LDN monitoring, preparation of national action plan and strategies, and FFS.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low
New environmental and social risks. | No new risks identified.
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | N/A
Grievance Redress Mechanism (GRM) | N/A

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Partnership & Coordination |  | High | Yes | Lack of close and collaborative cooperation between many institutional stakeholders | Close and collaborative cooperation between many institutional stakeholders is essential for the project to achieve its stated goal and objectives. This was achieved through involvement of all stakeholders from the early beginning of the project, preparation of project document and through establishment of working group for the project implementation as well as the project steering committee. Promotional materials and communication strategy were developed and, regular meetings and presentation of project results in different phases of the project implementation were organised.
2 | Institutional |  | Moderate | Yes | Unclear responsibilities of institutions at national and local level | Clearly defined and legally prescribed responsibilities of different institutions as well as involvement of all of responsible institutions are the main project goals. Moreover, the project supported improvement of institutional framework and through that will ensure sustainability of the project results after its finalization.
3 | Institutional |  | Moderate | Yes | Low technical capacity at national and local level | Capacity and technical expertise of stakeholders are weak. To mitigate this risk, the project supported capacity building through development of program for trainings during the project, taking into account specific needs of stakeholders. It also supported a national Information Sharing Forum.
4 | Environmental |  | Moderate | Yes | Natural disasters | Natural disasters, such as drought and floods, did not impede the adoption of new technologies. even so, the project was designed as a multi-year intervention, where demonstrations could be run over several seasons. The project was also linked to the drought early warning services of the MAF.
5 | Environmental |  | Low | Yes | Climate change | The MAF, with support of FAO technical expertise, are in a good position to adopt new research results on how to enhance resilience of SLM and SFM practices to climate change and, when necessary, adapt local livelihood strategies, which was supported under output 2.2.1 of the project.
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Low | Low | No new risk identified in this planning period.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 4: Dedicated activity to target institutions and organizations to raise awareness of the DSS and its usefulness in supporting the planning process. This would include identifying target audiences (e.g. MoAF, OGM, TRGM, but also other organisations which would not normally consider LD within their planning remit) and tailoring the awareness and any training to their needs under component 3. Awareness and basic training workshops should be run and tailored to the specificities of their institutional remit. 2 – 3-day workshop/s should be organized with the following purpose: • Introduction of DSS. • Analysis techniques in planning. • How to use DSS in micro basin analysis. • Developing a micro basin development plan. The expected output of this workshop is a “developed micro basin development plan by using DSS”. Depending on the budget, two or more regional workshops could be organized. | Informative meetings with the instutions, National LDN Symposium, instutional level trainings, Information dissemination meetings with the central administrative and strategic planners of LDN-related institutions and the administrative and planners of local institutions
Recommendation 7: Expand the range of crops and technologies currently included in the FFSs. This should be accompanied by a set of agreed performance and impact indicators (including financial data for farmers) for participatory evaluation by farmers | Farmer exposure visits for demonstration of best practices, Implementation of sustainable pasture management practices and implementation of the best SFM on forest areas
Recommendation…
Recommendation …
Recommendation…
Activities carried out during the first six months of the planning period supported the implementation of the MTR Recommendations, particularly Recommedation 4 and Reccomendation 7.

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | N/A
Components and cost | N/A
Institutional and implementation arrangements | N/A
Financial management
Implementation schedule | The project duration was extended until 31 December 2025 | 6 months | PSC
Executing Entity | N/A
Executing Entity Category | N/A
Minor project objective change | N/A
Safeguards | N/A
Risk analysis | N/A
Increase of GEF project financing up to 5% | N/A
Co-financing | N/A
Location of project activity | N/A
Other minor project amendment (define) | N/A
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
N/A-project has no stakeholder enengagement plan, the information obtained from prodoc.
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | General Directorate of Combating Desertification and Erosion | Lead institute/Chair of PSC | Provide strategic guidance and mobilize required technical expertise/resources
Government Institutions | General Directorate of Forestry | Member of PSC | Provide strategic guidance and mobilize required technical expertise/resources
Government Institutions | General Directorate of Agricultural Researches and Policies | Member of PSC | Provide strategic guidance and mobilize required technical expertise/resources
Government Institutions | General Directorate of Agricultural Reform | Project partner/Member of PSC | Provide strategic guidance and mobilize required technical expertise/resources
Others | FAO Representation in Turkey | Implementing agency | Implement project according to FAO and GEF policies and guidelines
Government Institutions | 5th Regional Directorate-Afyonkarahisar of MAF | Local partner | Supported local project activities
Government Institutions | 9. Regional Directorate-Ankara of MAF | Local partner | Supported local project activities
Government Institutions | Ankara Regional Directorate of Forestry of GDF | Local partner | Supported local project activities
Government Institutions | Eskişehir Regional Directorate of Forestry of GDF | Local partner | Supported local project activities
Government Institutions | Kütahya Regional Directorate of Forestry of GDF | Local partner | Supported local project activities
Government Institutions | 3.Regional Directorate-Eskisehir of General Directorate of State Hidrolic Works | Local partner | Supported local project activities
Government Institutions | 5.Regional Directorate-Ankara of General Directorate of State Hidrolic Works | Local partner | Supported local project activities
Government Institutions | 3.Regional Directorate-Ankara of General Directorate of Meteorology | Local partner | Supported local project activities
Government Institutions | 9.Regional Directorate-Ankara of General Directorate of Meteorology | Local partner | Supported local project activities
Government Institutions | Directorate of Central Anatolia Forestry Research Institute-Ankara | Stratejic partner | Providing technical expertise
Government Institutions | Directorate of Forest Trees and Seeds Breeding Research Institute-Ankara | Stratejic partner | Providing technical expertise
Government Institutions | Directorate of Forest Soil and Ecology Research Institute-Eskisehir | Stratejic partner | Providing technical expertise
Government Institutions | Directorate of Soil, Fertilizer and Water Resources Central Research Institute-Ankara | Stratejic partner | Providing technical expertise
Government Institutions | Directorate of Transition Belt Agricultural Research Institute-Eskisehir | Stratejic partner | Providing technical expertise
Government Institutions | Directorate of Soil, Water and Desertification Research Institute-Konya | Stratejic partner | Providing technical expertise
Government Institutions | Provincial Directorates of Ankara, Eskişehir and Kütahya of Ministry of Environment Urbanisation Climate Change | Local partner | Supported local project activities
Government Institutions | Governorships and District Governorships in Ankara, Eskişehir and Kütahya of Ministry of Interior | Local partner | Supported local project activities
Government Institutions | Ankara and Eskisehir Metropolitan Municipality and district municipalities, Kütahya Municipality and District Municipalities of Ministry of Interior | Local partner | Supported local project activities
Government Institutions | Ankara Development Agency of the Ministry of Industry and Technology | Local partner | Supported local project activities
Government Institutions | Zafer Development Agency-Afyonkarahisar of the Ministry of Industry and Technology | Local partner | Supported local project activities
Government Institutions | BEBKA - Bursa Eskişehir Bilecik Development Agency-Bursa of the Ministry of Industry and Technology | Local partner | Supported local project activities

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | Women farmers were targeted in project activities conducted in the project sites and encouraged to benefit from project inputs. There was a strong focus on women in agriculture mostly through the Component 3 activities with very good success.
b. Improving women's participation and decision making | Yes | The project continued the support of women cooperatives by including in the project activities.
c. generating socio-economic benefits or services for women | Yes | The cooperatives supported by the project in previous periods, continued generating socio-economic benefits to the women and will continue providing the benefits in post project period.
Any other good practices on gender |  | N/A

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The project disseminated its results through trainings and informative meetings held with the instutions and NGOs at basin level and national level. The project and government also develop a web-based platform called CEM Academia to disseminate the project results at national and international level.
If NO, how does the project identify, collect and document good practices? | n/a
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | n/a
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | Since the project is in its closing phase and no activity has been carried out during this period that could serve as a focus for communication, it has been a relatively weak period in terms of communication efforts. The biogas instolation process and the work on the training portal, which was planned as a project activity, are still ongoing. Within this framework, communication activities will be carried out once these two components are completed.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | n/a
Please provide links to related website, social media account | Since no meetings, trainings, or workshops took place as part of the project activities during this period, no public relations or content activities were conducted on social media or the project website.
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | Since the project is in its closing phase, no videos, brochures, or communication materials have been produced.
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Şafak Toros / safak.toros@fao.org

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. N/A Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | CEM, OGM, TRGM, TAGEM (local government) | Cash & in-kind | 13200000 | 38038491.98
Recipient Country Government |  | Cash & in-kind
Recipient Country Government |  | Cash & in-kind
Recipient Country Government |  | Cash & in-kind
GEF Agency | FAO | Cash & in-kind | 400000 | 400000
Total |  | Total | 13600000 | 38438491.98
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.