DEVELOPMENT BANK OF LATIN AMERICA (CAF)

PROJECT DOCUMENT

ON A

PROPOSED GLOBAL ENVIRONMENTAL FACILITY TRUST GrANT IN THE AMOUNT OF US $3,519,725 MILLION

TO THE ASOCIACION NACIONAL PARA LA CONSERVACION DE LA NATURALEZA (ANCON)

FOR A PROJECT: ECOSYSTEM-BASED BIODIVERSITY FRIENDLY CATTLE PRODUCTION FRAMEWORK FOR THE DARIEN REGION OF PANAMA.

DATE: November 2018

| Executive President: |  | Luis Carranza Ugarte |
| --- | --- | --- |
| Sustainable Development Vice President : |  | Julian Suarez |
| CAF-GEF Unit Coordinator: |  | René Gómez-García Palao |

CURRENCY EQUIVALENTS

(Exchange Rate Effective ____________, 2017)

| Currency Unit | = | US$ |
| --- | --- | --- |

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

ANAGAN		National Association of Cattle Ranchers

ANATI		National Authority for Land Administration

ANCON		National Association for the Conservation of Nature

AXM			Alliance for one million of reforested hectares

BD			Biodiversity

BDA			Agriculture Development Bank

CAF			Development Bank of Latin America

CATIE			Tropical Agronomic Centre for Research and Education

CBD			Convention on Biological Diversity

CBOs			Community Based Organizations

COPEG	Panama-United States Commission for the Eradication and Prevention of Cattle Screw Worm

CRU-Darien		Regional University Centre of Darien

ECODIC		Santa Fé Pastoral Center Herbs and Aromatic Plants

FUNAT		United for Nature Foundation

GAMMA		CATIE/ Livestock and Environmental Management Program

GEF			Global Environmental Facility

GIS			Geographic Information System

GoP			Government of Panama

Ha			Hectare

JAAR			Boards of Rural Aqueducts

LD			Land Degradation

MEDUCA		Ministry of Education

MIDA			Ministry of Agricultural Development

MINSA		Ministry of Health

MIVIOT		Ministry of Housing and Territorial

PAs			Protected Areas

PSC			Project Steering Committee

RBM			Results Based Management

SENAFRONT		National Border Service

SLM			Sustainable Land Management

SMART		Specific, Measurable, Achievable, Replicable, Time-Bound

SPS			Silvo-Pastoral Systems

STAP			Scientific and Technical Advisory Panel

TA 			Technical Assistance

TAC			Technical Advisory Committee

TF			Trust Fund

UNCCD		United Nation Convention to Combat Desertification

UNSDG		United Nations Sustainable Development Goals

USAID		United States Agency for International Development

WWF			World Wildlife Fund

TABLE OF Contents

page

I.	STRATEGIC CONTEXT	8

A. Country Context	8

B. Sectorial and Institutional Context	10

C. Project’s Baseline Scenario	16

D. Higher Level Objectives to which the Project Contributes	21

II.	PROJECT DEVELOPMENT OBJECTIVES	23

A. Proposed Development Objective	23

B. Project Beneficiaries	23

C. Proposed PDO (Outcome) Level Results Indicators & GEF-7 Core Indicators	30

III.	PROJECT DESCRIPTION	31

A. Project Rationale	31

B. Global Environmental Benefits	31

C. Project Components	33

D. Project Financing	36

E. Lessons Learned and Reflected in Project Design	37

F. Coordination with Other Initiatives Including Relevant GEF Funded Initiatives	38

G. Incremental Cost Reasoning	39

IV.	IMPLEMENTATION	43

A. Institutional and Implementation Arrangements	43

B. Results Monitoring and Evaluation (M&E)	44

C. Innovativeness, Sustainability and Up-scaling	45

V.	KEY RISKS AND MITIGATION MEASURES	48

VI.	SUMMARY PROJECT ANALYSES	50

A. Economic and Financial Analysis	50

B. Technical	51

C. Financial Management	52

D. Procurement	52

E. Environmental and Social (including Safeguards)	53

F. Gender Mainstreaming	53

G. Socio-Economic Benefits	55

H.  Stakeholder Participation	55

Annex 1: Results Framework	57

Annex 2: Detailed Project Description	66

Annex 3: Implementation Arrangements	73

Annex 4: Incremental Cost Analysis Matrix	80

Annex 5: Summarized Project Implementation Schedule	85

Annex 6: Budgeted Monitoring and Evaluation Plan	88

PROJECT DATASHEET

Countries:	Republic of Panama

Project Title:	Ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panama.

GEF Project ID:			9589

CAF Project ID:			CAF03/GEF9589

GEF Agency:				Development Bank of Latin America (CAF)

Project Executing Organization:	Asociación Nacional para la Conservación de la Naturaleza (ANCON)

Other Executing Partners:	Ministry of Agricultural Development, Agricultural Development Bank (BDA); Ministry of Environment

GEF Focal Area:			Biodiversity; Land Degradation

GEF Strategic Objective:		BD 4 Program 9; LD1 Program 1

CAF Priority				Environmental Sustainability and Climate Change

Duration:				48 months

Estimated Starting Date: 		January 2019

Estimated Completion:		December 2022

Financing Plan:								USD		%

GEF Allocation:

GEFTF			3,519,725	19.70

Co-financing:

Government (In Kind)		2,346,572	13.13

Government (Cash)	          12,000,000	67.17

Sub-Total Co-Financing        14,346,572

Total Project Budget		17,866,297	100%

| Estimated Disbursements (CAF FY/US$M) | FY1 | FY2 | FY3 | FY4 | Total |
| --- | --- | --- | --- | --- | --- |
| Annual | 703,945 | 1,055,917.5 | 1,055,917.5 | 703,945 | 3,519,725 |
| Cumulative | 703,945 | 1,759862.5 | 2,815780 | 3,519,725 | 3,519,725 |

# STRATEGIC CONTEXT

## A. Country Context

- Panama is a biodiversity rich country, covering 7,551,700 hectares of the large isthmus that joins Central and South America. Conforming one of the most crucial migratory routes in the Western Hemisphere it has facilitated the migration of species from North to South America since its formation playing a critical role in the preservation and evolution of biodiversity. Panama is also among the eight countries with the greatest diversity in amphibians in Latin America and the Caribbean and includes the eco-region with greatest number of vascular plant species.

- Politically, Panama is organized in ten different regions. Of these, the Darien region is the most extended, remote and unpopulated. Totalling 1,667,100 ha the Darien borders with Colombia on the East and with the Emberá-Wounaan and Guna Yala indigenous reserves to the West. The Darien region not only sustains Panama’s highest levels of biodiversity but also forms part of the Choco-Darien eco-region shared with Colombia and listed by WWF among the highest priority eco-regions for conservation due to its high levels of endemism and globally significant biodiversity (Figure 1).

- The Darien's high levels of biodiversity include 2,638 species of plants (27.7% of all registered for the country); 166 species of mammals (78% of the total for the country); 670 species of birds (69% of those registered in the country); 78 species of amphibians and 127 species of reptiles (the later corresponding to 60.4% of registered species in Panama). With respect to freshwater fauna, 72 species of fish have been recorded in the Darien, including 168 saltwater and brackish water fish, as well as 15 commercial species of bivalves and eight commercial species of gastropods (ANCON, 2010, Plan de Conservación de Sitio, Darién, The Nature Conservancy).

- Recognizing the Darien's ecological value, the Government of Panama (GoP) has progressively established nine different natural conservation areas encompassing over 46% of this biologically endowed region, with eight of these areas being in the National Protected Areas System, plus one private reserve. These are: (i) the Darien National Park, (ii) the Biological Corridor Serrania de Bagre, (iii) the Filo del Tallo-Canglón Hydrological Reserve, (iv) the Chepigana Forest Reserve, (v) the Bosque Protector Alto Darien, (vi) the Serrania del Darien Hydrological reserve, (vii) the Punta Patiño Wetland and Ramsar Site and (viii) the recently created Wildlife Refuge Laguna de Matusagarati, a globally recognized wetland, adjacent to the Filo del Tallo–Canglón Hydrological Reserve, and (ix) the Natural Private Reserve of Punta Patiño. The Darien National Park is the largest in Panama and the second largest protected tropical forest in Central America. Part of the Darien region is also covered by two indigenous reserves, the Emberá-Wounaan and Wargandí reserves both of which are independently managed by these communities. This network of protected areas was established in recognition of the region’s unique value and biological diversity, as well as the socio-economic and vital ecosystems services it provides, including water supply and regulation, carbon capture, cultural services, eco-tourism, and medicinal plant extracts.

Figure 1: The Darien Region of Panama

- In spite of the GoP’s efforts to safeguard the region’s outstanding biodiversity through protected area designations, land use changes have progressively affected the area since the 1950s. After 1978 these became more evident with the construction of the new stretch of the Pan-American Highway connecting Panama City to the town of Yaviza (just outside the Darien National Park). Satellite imagery from the 1970s confirms the dramatic trends of deforestation expectedly along the Pan-American Highway. In this regard, the Darien's biodiversity faces similar threats as other tropical forests in the world. The third "Global Environment Outlook" report for Latin America and the Caribbean further confirms that the greatest threats to biodiversity stem from changes in land use with the resulting reduction, fragmentation and loss of habitats (Alkemade et al. 2009). Illegal logging of commercially valued timber species, the expansion of land for agriculture, and the clearing of forests for cattle ranching have resulted in the highest deforestation rates in the country (almost twice the national rate). Unsurprisingly, land use changes have also caused the loss of native species communities, shrinking and fragmented habitats, encroachment of protected areas and the progressive disruption of ecological processes and the multiple services these provide.

## B. Sectorial and Institutional Context

Threats to globally important biodiversity and ecosystem integrity

- In Panama, the conversion of natural habitat for agriculture and specifically cattle ranching, as in the case of the Darien, constitutes one of the major threats to its biodiversity. As stated by MiAmbiente (2018), one of the greatest drivers of deforestation and degradation in Panama is the agricultural sector. Although in recent years the agricultural sector has had a decrease in its share of GDP, which in 2016 reached just 1.01%, the conversion of forest to unsustainable agricultural activities remains one of the causes of deforestation and degradation in the country. This happens since many of these activities take place in forest areas, that is to say, where there must be forests according to eco-climatic conditions. The conversion of forest lands (mature, secondary, mature forest, mangrove and forest plantation) to other uses (grazing pastures, stubble, agricultural lands, and annual crops represented 13,267 ha/year for the period 2006-2015, being 2009 the year of greater conversion.

- Almost all areas presently under cattle use and are now mainly covered by degraded pasture, were originally Mesoamerican Tropical Forests. In the case of the Darien, the expansion of traditional livestock production has been the unintentional result of past policies to improve access to food, respond to rising demand and promote economic development in a resource rich albeit economically depressed area. Unfortunately, agricultural growth has transpired without the considerations for production in highly diverse and fragile ecosystems (tropical forest-soils) thereby quickly becoming degrading and unsustainable. Vital ecosystem services such as carbon sequestration, soil preservation, flood and temperature regulation, and the conservation of biological diversity along with its attendant benefits have all been negatively and progressively affected.

- Annual habitat conversion rates in the Darien (or percentage of intact habitat degraded each year) between 2006 and 2012 stand at 1.53% (Ministry of Environment, 2016). Threats to biodiversity and ecosystem services are also on the rise from cattle ranching which has become the region's main economic activity and a growing share of its gross domestic product over the last decade. The agricultural census of 2011 counted a total of 1,136 cattle ranchers; however, the National Association of Cattle Ranchers (ANAGAN) recorded 6,500 members in its registry in 2016, with a total of 1,539,000 heads of cattle at the national level, with the last recorded number for the Darien region being 194,400 heads in 2014, corresponding to a six-fold increase since 1991. Data provided by COPEG (2018), reported that for the Filo del Tallo-Canglon Hydrological Reserve, the primary proposed project intervention area, there were 21,979 heads of cattle, and 55,518 heads in the buffer zone. This same data source also reported that there are 412 cattle ranches located within the Filo del Tallo-Canglon Hydrological Reserve, with 739 more cattle ranches in its buffer zone. As noted, the expansion of cattle in the Darien has lead to progressive deforestation and continuous clearing for pastures with important habitat loss, fragmentation and ensuing land degradation. Cattle rearing is now threatening untouched and pristine areas, and dangerously infringing upon existing protected ones, threatening their integrity, overall functionality and the indispensable ecosystem services they collectively provide.

- Nevertheless, in spite of agricultural expansion, 78% of the Darien forest remains mature forest, 13.9% secondary forest and 3.8% mangroves (Ministry of Environment's 2016 figures). Figures however also confirm that deforestation, primarily for ranching may now be the most serious problem. Of the nine protected areas of the Darien, perhaps the most highly threatened is the Filo del Tallo-Canglón Hydrological Reserve, particularly due to its proximity to the Pan American Highway and the easy access it confers to prospective cattle ranchers seeking new lands.

Primary root causes of identified threats

- Nationally, a displacement from "established cattle rearing provinces” towards the Darien has been occurring as resources (water, soil, pastures) have become progressively depleted from overuse and exploitation in these traditional cattle producing regions. The prospect of new lands with bountiful resources, a reliable water supply, and the possibility of purchasing plots at comparatively lower prices has attracted cattle producers to either rent or buy land and "clearing" these new areas for the expansion of the sector. Rising meat consumption has also contributed to production increases to meet growing demand. Furthermore, most cattle rearing in the Darien has been conducted "the traditional old fashioned way" occupying large swaths of land, deliberately deforested and cleared for pasture, further exacerbating the impact and pressure on the area's unique and highly delicate resource base. As reported in the ‘Estrategia Nacional REDD+ en Panama (2015)’, a rough comparison with the soil classification according to USDA suggests an important inadequate use of the soil resource and confirms the expansion of cattle ranching as the cause of deforestation. Panama has 1,537,326 hectares of pasture land and, but the availability of soils with livestock production capacity is only 891,300 ha, with an over-use for pastures representing 646,000 hectares of arable land.

- Extension services and technical assistance with regards to livestock production have been obsolete, sporadic and practically non-existent in the Darien. The prevalence of conventional cattle rearing practices in the Darien is partly the result of cultural trends (the vast majority of ranchers came from traditional cattle producing regions in the country) but also the fact that technical assistance, whenever available, has been limited to supporting the basic fundamentals of traditional livestock rearing (vaccination, plague control, etc.) rather than the promotion of innovative and less degrading alternatives. The few initiatives promoting sustainable cattle ranching in bio-diverse ecosystems, although noteworthy in several aspects, have been experimental, limited in coverage and scope, purposefully site-specific, fragmented in their approach, and generally ineffective in altering long established production paradigms in this traditional sector. Valuable lessons derived from these initiatives have however been analyzed for relevance and applied to this project, as appropriate and as detailed in multiple sections of this Project Document. A review of the GEF portfolio experience in productive landscapes, entitled “Biodiversity Mainstreaming in Practice” will also inform project design with the aim of “further refining the GEF’s investment strategy at the productive landscape level and the GEF Theory of Change for biodiversity mainstreaming.”

- Land use plans have not been implemented in the Darien, leading to deforestation for agricultural expansion and the progressive deterioration of ecosystem services. Land use planning in the Darien has been primarily directed at establishing protected areas under varying management and protection categories. The remainder of the region is comprised of open lands, nestled among protected areas, with no specific designations, regulations, or enforcement mechanisms. The region's unsuitability for agriculture coupled with its inaccessibility has generally detracted government institutions from establishing a permanent presence in the area. Land use planning and the sustainable use of resources in productive systems was never regarded as a priority and consequently not pursued. The last decade has thus witnessed an unprecedented expansion of unsustainable land use practices in agriculture, and more specifically cattle ranching, as no regulatory frameworks, clear land use zoning, reliable technical support, alternative production practices, or enforcement frameworks have provided the necessary controls or permanent oversight for productive activities and land use.

- The Darien's isolation, scarce population, limited social services and infrastructure, have made technical assistance and reliable extension services a challenge for past government administrations. Addressing the challenges inherent to the Darien have not always constituted a priority for the GoP as competing development needs elsewhere in the country have taken precedent over issues in one of the continent's last frontiers. This situation however has now become a pressing concern as inadequate technical and institutional support has further exacerbated the disorganized, degrading, and unprecedented pace of agricultural expansion.

Barriers to sustainable cattle production systems

- Cattle ranchers continue to use and rely on traditional practices and methods for cattle production. The concepts of integrated resource management and the application of silvo-pastoral systems (SPS) remain unfamiliar to Darien’s cattle producers. The sustainable intensification of existing farm-lands and the application of alternative production practices, including crop rotation, crop diversification, water-saving techniques, and the application of conservation-oriented SPS, among others, are neither practiced, promoted nor sufficiently understood. Neither are the socio-economic benefits and environmental services silvo-pastoral systems can provide by way of: healthy watersheds, soil preservation, carbon sequestration, habitat preservation, functionality and maintenance of vegetative cover in agro-ecosystems, productivity gains and additional income sources. Unfortunately, cattle producers moving to the Darien often apply the same unsustainable methods utilized in their place of origin, irrespective of the environmental consequences these practices have progressively had on the resource base they depend on. A knowledge and opportunity vacuum is thereby disempowering producers from engaging in sustainable alternatives, and impeding the opportunities, efficiencies, and numerous benefits conservation oriented SPS would offer to their livelihoods on a variety of fronts.

- Extension services and technical support remain conventional, outdated and scarce. Specialized assistance and institutional backing for cattle producers has been limited in both quantity and quality. As mentioned, cattle ranchers are neither empowered nor appraised of new technologies, conservation oriented neither production methods, nor the win-win situations and productivity gains sustainable alternatives can generate. Dependence on conventional inputs and “standard” production practices remains the norm as does the environmental degradation associated with these long-established production scenarios. The resulting patterns of degradation and unsustainable land uses are both evident at the farm and landscape level. Extension agents also reflect a generational gap in technical knowledge and the perceptions of what constitutes sustainable production models. In this regard, a new generation of extension professionals needs to be nurtured, promoted and established to replace unsustainable production paradigms.

- Cattle rancher associations and networks are disorganized and weak, minimizing the potential socio-economic benefits a collective approach within this productive sector could generate. Networking structures and cattle ranchers’ associations remain incipient and disorganized compared to those in other regions in the country, as well as other agricultural sectors. This constitutes an important organizational barrier preventing ranchers from defining common needs, mutual goals, the scope and frequency of assistance requirements, and the possible economies of scale in delivering and optimizing technical support. Improved networking structures and consolidated cattle ranchers’ associations could assist producers in reaching their full potential in terms of productive sustainability. In the same vein, a united front of cattle producers could significantly leverage a reconversion from traditional cattle production towards eco-friendly systems both within farms and the productive landscape alike. Consolidated producers’ networks are significant structures for establishing a critical stakeholder mass, unifying support needs, facilitating the delivery of technical assistance, promoting the permanent exchange of experiential learning, and ultimately ensuring the replication and emulation of best practices in this increasingly relevant productive sector.

- Awareness of the multiple benefits associated with eco-friendly silvo-pastoral systems within a sustainable land management framework is limited among producers and consumers alike. The socio-economic and ecological benefits of sustainable cattle ranching - through the application of conservation-based practices within a sustainable integrated land use management model - remains elusive at local and national levels. Conversely, the socio-economic costs and ramifications of engaging in "business as usual ranching" along with the environmental degradation it entails have not been internalized, costed, nor fully understood by producers and consumers alike. This lack of awareness results in unrealized potential for improvements, as well as missed opportunities for modifications and innovations along the productive chain. This needed “awareness raising” could be significantly addressed through well articulated informational campaigns and communication strategies purposefully designed for a variety of stakeholder groups at local and national levels, including producers and consumers, policy makers, land use planners and decision-makers, as well as financial institutions, among others.

- Land use planning and regulatory frameworks in the Darien are inadequate and do not incorporate conservation objectives at the wider landscape level. The Darien does not have a cohesive land use plan which integrates conservation, ecosystem services, and sustainable resource use objectives. Of note, however, are efforts by WWF between 2007 & 2008 in which early versions of land use plans were produced for the Darien, Cemaco and Sambu; there also is a land use plan for the Pinogana region.  Most of the protected areas in the Darien do not have a management plan. In other administrative areas where there are no land use plans, development is guided by the zoning specifications defined in the original charter governing their creation. A holistic integrated land-use management plan, adjusted to current developmental challenges and consistent with productive sector pressures (agriculture/livestock) is now a pressing requirement for the region's sustainable development. This planning tool is indispensable to safeguard biodiversity, (both within and outside protected areas) the functionality of protected areas and the multiple services these provide on an individual and collective basis. The establishment of a sustainable land use management plan is also critical considering the uncontrolled expansion of agricultural production. In this regard, an integrated zoning and conservation land use framework would merge conservation and sustainability concerns within its planning objectives, operational structures, enforcement mechanisms, and financing considerations. Without this land use plan and regulatory framework, productive activity in this resource rich, albeit fragile ecosystem, could irreversibly jeopardize the Darien’s unique and globally significant ecological attributes.

- Government institutions (Economy & Finance, Agriculture, Environment) and their respective technical departments are neither sufficiently coordinated nor trained to address the challenges facing the Darien nor able to provide the required support for implementing sustainable productive options. Government institutions, namely the Ministry of Environment and the Ministry for Agricultural Development, have made commendable efforts in recent years to establish and maintain a small local presence in the Darien. Nevertheless, technical assistance for cattle rearing in the Darien remains limited to basic sanitation and inoculation priorities, censuses, and to certain extent maintenance of road access for livestock transportation purposes. Also, while ad hoc communications exist between government institutions at local levels, these do not replace a formal, coordinated, inter-institutional framework that would allow these government entities to deliver local stakeholders the technical support required by their respective mandates.

- Financial resources (credits/loans) are not complemented by the technical assistance, nor extension support required for the adoption of on-farm reforms in the cattle sector’s productive systems. The absence of technical expertise to ensure that financial mechanisms deliver transformational changes within productive systems at the farm and landscape level, constitutes a significant impediment that will need to be addressed if alternatives are to be sustainably implemented by producers. To date, the absence of reliable, specialized and informed technical assistance to facilitate and guide cattle ranchers in accessing capital, particularly among small to medium sized producers, has undermined progress towards the application of SPS and the possibility of achieving lasting productive changes in the Darien. Experience has also shown that even with accessible financing at attractive rates cattle farmers remain reticent to engage in alternative production practices if they do not receive a commensurate amount of reliable technical assistance to support them in the implementation of these changes. The case in the Darien illustrates that the successful adoption of conservation-oriented SPS, requires both technical assistance and financial resources to mitigate the perceived risk these proposed alternatives represent for traditional cattle producers. In brief, changing "how things are done" amongst ranchers implies a meaningful shift in their established customs and mind-sets. This attitudinal change represents a commitment for which both resources and technical assistance are required in equal measure. Experience has repeatedly shown that without reliable technical assistance for implementing, monitoring, and replicating these changes, financial resources alone - even if readily available – will not be sufficient to effect lasting change. Consequently, a two-pronged approach, pairing financial resources with ample technical assistance is considered indispensable for long-lasting productive changes.

- Cattle farmers in the Darien do not have the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles. To access credit farmers will have to prepare “Planes de Finca” (farm plans) as a requirement for financial institutions. In these plans, farmers will need to detail and cost how they will transition from a “business as usual” scenario to a situation in which production practices based on conservation objectives and silvo-pastoral systems will prevail. Among other elements, these “Planes de Finca/Farm Plans” will need to include; the specific practices that they will be adopting in their farms, the costs of corresponding inputs and staff, expected time-frames and yields, as well as the means to monitor positive changes in the preservation and rehabilitation of environmental resources (soil, water, biodiversity, etc.) and the services they provide. With these considerations in mind, these Farm Plans will differ considerably from the practices currently guiding production in the Darien. However, the technical support needed to move from “business as usual” to the proposed “alternative scenario” is currently unavailable thus constituting a significant barrier to optimize the potential of available credit. Practical training in SPS and immersion in the techniques they entail at the farm and landscape level, in addition to the investments and inputs these require, is precisely what prospective farmers will need technical assistance in and one of the barriers this project proposes to overcome.

- Banks and other financing institutions have not incorporated sustainability considerations, nor social and environmental risk management assessments in their lending operations and sectoral portfolios. Credit for agricultural development has been easily granted on favourable terms for “business as usual” production in a variety of sectors including cattle rearing, irrespective of resulting socio-environmental impacts. This prevailing situation in the banking sector has been a defining variable in inadvertently maintaining unsustainable agricultural production patterns in the Darien and elsewhere. According to the ‘Estrategia Nacional REDD+ en Panama’, the livestock GDP grew 59% from 1998-2008, while benefitting from financing which lacked considerations for sustainability, environmental and social risks. Consequently, the portfolio of financing to the Panamanian agricultural sector went from US$1,200 million in 2014 to US$1,908 million in 2017, among which two state banks stand out, earmarking more than US$699 million more for the sector through to March 2017. Today, leading national banks are re-examining and modernizing their corporate policies, directives and guidelines to fully integrate sustainability considerations into their lending portfolios, including the efficient use and conservation of natural resources. Risk management assessments are progressively becoming part of credit operations thereby incentivizing significant modifications in the agricultural sector through the adoption of sustainable alternatives in production practices. A notable example is the Bank for Agricultural Development, the principal financier of the agricultural sector and the financial arm of the Ministry of Agricultural Development. The Bank is currently leading this process at national levels, and in the context of this project encouraging the application of SPS within its existing preferential financing.

## C. Project’s Baseline Scenario

- Recognizing the importance of cattle ranching in Panama's agricultural sector and acknowledging its impact on fragile ecosystems in a “business as usual context”, the GoP is actively encouraging the adoption of conservation-oriented approaches and sustainable productive practices in this sector. Current efforts form part of a greater paradigm shift geared towards the sustainable modernization of agriculture in which sustainable production, conservation priorities, ecological integrity and the preservation of key environmental assets are integrated into decision-making, policy formulation, and sectoral development objectives. In this regard while past projects could be construed as one-off interventions yielding limited results, current efforts, will be implemented in an enabling environment characterized by: supportive policies, legal and regulatory frameworks at the sector and landscape levels; technical assistance linked to credit from key banking entities; and the inter-institutional alignment and coordination required for systemic change at the scale of the Darien and nation-wide.

- To this end, the GoP through its Ministry of Agricultural Development and the Ministry of Environment is implementing a series of indispensable baseline measures and policies designed to progressively address the barriers and challenges mentioned above. As a result, today’s programmatic baseline provides a far more enabling institutional, financial, legal and regulatory environment for the implementation of sustainable cattle production in biodiversity rich landscapes, than at any other time in the country's history and in the development of the sector itself.

- The following initiatives provide baseline foundations for the proposed project and are considered indispensable for the delivery of its intended objectives.

- "The National Outreach and Extension Programme for Cattle Farming" led by the Ministry of Agricultural Development. The programme operating at local, regional and national levels reflects the Ministry’s new strategy to modify production patterns in the agricultural sector along environmentally sound and socio-economically viable parameters. This has led to corresponding reforms and modifications in the quality and substance of its outreach and extension programmes. Among the agricultural sub-sector targeted for these changes is cattle production. Through its outreach and extension programme, the Ministry of Agricultural Development aims at strengthening its technical capacities to underscore resource efficiency and conservation, whilst maintaining productive output. To this end, a new cadre of technical staff versed in environmentally sound production systems will be trained as part of this broader institutional and sectoral goal. This new outreach programme will be decisive in supporting the implementation, replication and sustainability of conservation-oriented SPS in the Darien but also ensuring its subsequent expansion at national levels.

- Among the activities conducted so far under this programme is the selection of pilot ranches in cattle producing regions in order to begin the introduction and implementation of technological shifts in cattle management, including the efficient use of land, soil, water and vegetation in production practices. Pilot ranches are responsible for supporting a number of other ranches to ensure the transfer of technologies and know-how in a cascade model. The proposed project will partner with this outreach and extension programme complementing its activities in the Darien with its own strategy for "farmer to farmer” knowledge transfer and dissemination. This will reinforce the efficacy of experiential learning for biodiversity-friendly cattle production systems and subsequently facilitate the replication of project objectives both in the Darien and nationwide. In this regard the National Outreach and Extension Programme represents a fundamental tool for imparting alternative production systems in the cattle ranching sector, both within farms and at the broader landscape level. Unlike prior efforts, which to a great extent constituted limited interventions, the current mainstreaming of conservation practices into established national extension programmes for cattle rearing confirms that project goals are consistent with the systemic changes taking place in the agricultural sector, its leading institutions, and the GoP’s sustainability goals.

- The “Pilot for Sustainable Livestock and Agro-forestry Systems in selected areas of the Darien”. Developed by the Ministry of Agricultural Development, the U.S. Agency for International Development (USAID) and The Tropical Agronomic Centre for Research and Education (CATIE), the pilot developed a “Manual of 15 Good Practices for Sustainable Cattle Ranching" exclusively for ranchers. The proposed project will illustrate the application of these best productive practices in the Darien both at the farm and broader landscape level. The field implementation of these conservation-oriented practices through this project will produce the Ministry of Agriculture’s first official “Technical Chapter on Sustainable Cattle Production” and form part of its "Operational and Technical Procedures Manual" (equivalent to the “how-to” book of the Ministry in technical matters). In addition, the (USAID/MIDA) project also identified practical and reliable indicators to demonstrate livestock profitability and ecosystem services generation as a result of SPS implementation.

- The "National Livestock Traceability Programme" implemented by Ministry of Agricultural Development. The programme, regulated by the traceability law issued in 2013, involves the establishment of a single national agricultural record that identifies: each ranch and farm; a record of all species managed in the ranch; an ID for each single animal or group of animals; a record of the animal movements; the corresponding means of transportation; and a centralized and Official Information System of Livestock Traceability. This important programme will support – among other efforts - the proposed eco-labelling component of the project, providing consumers with critical sector information along its productive chain and the assurance that they are buying meat produced in biodiversity-friendly ranches. In the absence of such a traceability programme any efforts pertaining to labelling or providing any specifications regarding the practices and processes by which cattle is produced would neither be credible nor viable thereby making the National livestock traceability Programme a centrepiece of this proposed project’s baseline.

- "Mainstreaming of environmental and sustainability considerations into banking operations”. As part of a broader strategy for establishing environmental and social risk assessments into its lending portfolio, the Bank for Agricultural Development (BDA) is incorporating biodiversity-friendly SPS within its agricultural credit lines, beginning with this project in the Darien. The National Association for the Conservation of Nature (ANCON), the non-governmental entity spearheading this project, in a collaborative agreement with the Bank, will complement these credits with the technical assistance and oversight required for the effective implementation of sustainable management practices at the farm and landscape level. As previously noted, a lesson learned from past experiences, and a significant barrier limiting the impact of credit to farmers, has been the absence of sufficient technical backstopping to cattle producers. This “technical assistance void” has also been the recurrent reason why producers have been averse to engage in credit ventures involving and/or promoting "innovative" and "alternative" conservation-oriented production practices. Through ANCON’s technical assistance, ranchers acquiring these loans will receive, as part and parcel of this financial support, the necessary guidance to prepare their “Farm Plans/Planes de Finca” in accordance to a set of established “best practice criteria”. The availability of permanent technical assistance will allow farmers to implement the proposed suite of conservation-oriented sustainable use practices designed to minimize socio-economic risks and environmental degradation whilst maximizing productivity and economic gains. In brief, a fundamental barrier affecting the outcome of previous efforts will be addressed through a new receptiveness on the part of farmers to access available funding for SPS production practices, as a result of having access to targeted assistance. ANCON’s assistance to the project will supplement that of extension services service providers, also benefiting from the project.

- “Authority for the Control of Certification of Agricultural Organic Production”. This newly established entity ascribed to the Ministry of Agriculture has been in operation since January 2017. Its creation illustrates the steady growth in the production of organic produce in Panama and the corresponding rising demand at national and local levels. Currently, over 6,000 hectares, managed by 271,000 farmers are under organic production. Previously, only four private entities, all international, had the ability to certify producers in Panama along internationally established criteria (i.e. recognized in the US and Europe.) In addition to being the first national certification body, the Authority’s mandate is to provide tangible assurances to consumers regarding the organic, biodiversity-friendly, and ecologically compatible attributes of a variety of agricultural produce. In addition, the Authority’s responsibilities include furthering consumers’ understanding regarding the different kinds of existing labels and/or certifications, resulting in an official authoritative guide to understanding the productive origins and specificities of a variety of goods, including their associated socio-economic and environmental benefits. Another critical part of the Authority’s mandate is to facilitate the engagement of small-scale producers in applying and accessing certification. In sum, in addition to generating eco-labelling information, proof of origin, and trustworthiness among discerning consumers, the Authority seeks to encourage and foment a new generation of small-scale producers to join the more experienced private sector operatives linked to private international certification entities. A group of Ministry staff has been trained in certification requirements and the support it will be providing, particularly to smaller-scale producers. Henceforth all certification in Panama will need to pass through this new Authority, regardless of previous arrangement with international certifying agents.  During the preparatory stage (PPG) this project will liaise with the Authority regarding the eco-labelling activities envisaged by the project for products emanating from SPS farms.

- The “Alliance for one million of reforested hectares” is public-private partnership by the GoP officially presented at the 2014 Climate Change Summit and representing one of Panama’s commitments and contributions to mitigate climate change. The Alliance brings a host of key players, including the National Chamber of Commerce, industry representatives, the Ministries of agriculture and Environment, and The National Association for the Conservation of Nature (ANCON) among others, working together in their respective fields and capacities to reforest a million hectares in the next 20 years. Aimed at reducing and reversing current deforestation rates in natural forests (including those in the Darien) this public-private partnership seeks to recover degraded areas in key critical watersheds and protected areas, including areas such as Filo del Tallo Canglón Hydrological Reserve in the Darien. Reforestation activities in the project area will be geared towards establishing connecting corridors in intervened areas in the buffer zone and within the reserve itself, thereby also supporting the application of SPS. Cognizant that currently 25% of the national territory is mostly dedicated to ranching, this effort also implies a significant partnership with cattle ranchers and their respective national organization (ANAGAN), independent cattle ranchers, and those belonging to other local organizations, included those beneficiaries and stakeholder organizations identified in this Project Document. In practical terms it demands a shift in production paradigms towards the application of best management practices (i.e. planting scattered trees to ensure connectivity, establishing live fences, protecting water sources and reforesting and restoring hillsides, etc.) and the incorporation of conservation and sustainable resource use considerations in the overall management of fragile biodiversity rich productive landscapes.

- Land use planning. While some land use plans exist as part of the project's baseline in the Darien they do not represent a cohesive and articulated landscape management model tailored to the complex nature and current development needs of this biodiverse region. In order to better inform project interventions, existing plans were analyzed to determine gaps, required modifications, needed updates, as well as information that can be optimized and expanded upon. Among the land management plans and initiatives analyzed are: The Sustainable Development Program for the Darien; the land use plan for the Pinogana district prepared by the Housing and Land Use Ministry; the existing management plans for the protected areas located in the Darien; the forest management plans prepared with the support of USAID for a percentage of the two districts of the Comarca Emberá-Wounaan and the Comarca Wargandí, among others to identify elements applicable to productive forest landscapes. On-going baseline programmes addressing, albeit imperfectly, land use planning and protected area management, will thus be complemented by the integrated landscape management plan proposed by the project in order to ensure that existing efforts collectively deliver their intended conservation and sustainable development objectives.

- The total estimated investments in the baseline to date are US$18,722,590, as per the list below:

- "National Outreach and Extension Programme for Cattle Farming" [USD 1,812,000]

- “Capacity building programme for improving extension services” [USD 1,767,600]

- The Ministry of Agriculture's “Programme to finance and support conservation oriented cattle production in the Darien” [USD 12 million].

- The Ministry of Environment's objective to consolidate and develop an integrated and conservation oriented land use plan for the Darien [USD 1,283,590]

- The National Livestock Traceability Programme. [US 1,859,400] (Ministry of Agricultural Development).

## D. Higher Level Objectives to which the Project Contributes

Value Added of CAF

- CAF has a unique present and background record in supporting and implementing projects, programs and financial operations not only aimed for a single country, but to enhance sound regional integration between CAF country members. CAF´s success in the region is linked to 48 years of work with governments, private sector and social organizations at regional, national and local levels, complying successfully with CAF´s mission to promote sustainable development and integration in partnership with country members.

- The project objectives are aligned with CAF’s agenda for Environmental Sustainability and Climate Change under its Integrated Vision for Sustainable Development. The project shows very strong alignment with the CAF Strategic Biodiversity Program 2015-2020 (BIOCAF) and its Vision, which states “For 2050, CAF member countries will have incorporated biodiversity into the scope of their government and society, and will have adopted concrete measures for the conservation, sustainable use, and distribution of the benefits derived from biological resources, achieving an improvement of the situation of biodiversity in the region and directly contributing to the vision of the Aichi targets”. Four strategic objectives of the CAF Strategic Biodiversity Program 2015-2020 show the strongest linkage with the project’s proposed outcomes and outputs:  Strategic Objective 2. Promote the valorization of biological resources and the ecosystem services that they provide, as an incentive for conservation; Strategic Objective 3. Foster sustainable practices to decrease the pressure placed on natural habitats; Strategic Objective 6. Strengthen access to markets through the creation of added value; and Strategic Objective 12. Produce and disseminate information on biodiversity management to promote the exchange of experiences and increased awareness among society.

Consistency with National Priorities

- Panama became a signatory the Convention on Biological Diversity (CBD) on the 13th June 1992 and ratified the convention on the 17th January 1995. Similarly, Panama became a signatory to the United Nations Convention to Combat Desertification (UNCCD) on the 22nd February 1995 and ratified the convention on the 4th April 1996. Both of these conventions enable Panama to access GEF resources. The proposed project is fully aligned and supportive of Panama's National Biodiversity Strategy and Action Plan (NBSAP-2000) and it’s National Strategy and Action Plan to Combat Desertification (NAP-2004) under the UNCCD.

- Panama’s National Action Plans under the CBD and the UNCCD are complementary, coinciding in their efforts to: (i) promote sustainability objectives in production systems - particularly those whose practices are destructive for biodiversity; (ii) promote compatibility between development policies and the sustainable use of biological resources; (iii) prevent, control and minimize the negative impacts that drive environmental contamination and/or alter ecological processes in natural systems; (iv) reduce soil degradation, erosion and overall productivity loss through the application of productive methods consistent with conservation and sustainability objectives; (v) promote the application of productive practices geared towards the efficient use of resources, including water, soil, and vegetative cover; (vi) promote and enable integrated land-use planning along with the development of required institutional and regulatory mechanisms; (vi) promote and establish institutional collaboration in productive landscapes, including shared mechanisms for monitoring resource use, and the maintenance of ecosystem services, among other actions.

- The proposed project is thus reflective of national priorities, supportive of Panama’s commitments and Action Plans under both the CBD and UNCCD conventions, and is also aligned with national priorities and UNSDG (UN Sustainable Development Goals) as summarized in Table 1 below:

Table 1: Project Alignment with National Priorities

| GEF-6 Biodiversity and Land Degradation Focal Area Strategy Objectives | United Nations Sustainable Development Goals | Objectives of the Government of Panama's 2014-2019 Environmental Action Plan |
| --- | --- | --- |
| Reduce Threats to Globally Significant Biodiversity | No. 13 Take urgent action to combat climate change and its impact. | Support environmental management and the sustainable use of natural resources (soil, water resources, geological and mining resources, forests and natural vegetation, biodiversity resources, landscapes, etc.) particularly in productive landscapes. |
| Improve Sustainability of Protected Area Systems | No.15 Protect, restore and promote the sustainable use of terrestrial ecosystems sustainably manage forests, combating desertification and halting and reversing land degradation and loss of biodiversity. | A National System of Protected Areas able to ensure the protection of national ecosystems and the biological diversity they contain through their efficient management, and the conservation of ecological corridors and connecting areas in productive landscapes. |
| Mainstream Biodiversity Conservation and Sustainable Use into Production Landscapes/Seascapes and Sectors Maintain or improve flow of agro-ecosystem services to sustain food production and livelihoods. SLM for Climate Smart Agriculture | No.2 End hunger, achieve food security, better nutrition, sustainable agriculture. No.12 Ensuring sustainable patterns of consumption and production. | Mitigate and/or eliminate environmental degradation processes associated with inappropriate land use and human activities, and reduce potential effects associated with natural hazards, as measured by: -Improvements in the relationship between the uses and productivity of soils Addressing use conflicts in areas of high natural value. Sustained improvement of biodiversity indicators and ecosystem health Improving the quality and availability of water resources for productive uses and human consumption Promotion of activities related to the Alliance for the Million Hectares - - Improving the competitiveness of the primary sector, boosting productivity, diversification and the generation of added value of local production, as measured by: Improved productivity of small farmers with assistance in the production process. |

# PROJECT DEVELOPMENT OBJECTIVES

## A. Proposed Development Objective

- Establishment of an ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panama.

## B. Project Beneficiaries

- The identification and engagement of beneficiaries and stakeholders during project preparation was guided by those who could have the most relevant and direct impact on project activities and outcomes, as well as those who will be direct project beneficiaries. The project’s direct beneficiaries are those that bear the closest and strongest link to the cattle productive sector both at local and national levels and in the Darien in particular, but also those who may be instrumental for the implementation of project activities and the sustainability of planned project outcomes. These include local Darien ranchers, the National Cattle Producers’ Association (ANAGAN), the Ministry of Agricultural Development (MIDA), the Ministry of Environment, the National Association for the Conservation of Nature (ANCON), the National Authority for Land Administration (ANATI), the Agriculture Development Bank (BDA), supermarket chains, and organic produce distributors. Other key actors with potentially high influence on project implementation include CATIE/ Livestock and Environmental Management Program (GAMMA), with established experience in the design of Silvo-Pastoral Systems (SPS) and timber production in the Darien; the Administrative Board for Rural Aqueducts (JAARS); United for Nature Foundation (FUNAT), as primary technical partner in the implementation of the Strategic Environmental Plan of ANAGAN and where applicable, its correlation with project activities in the Darien, and thus is a primary source of information and key coordinating partner; Community Based Organizations (CBOs), which can have a high influence in the dissemination of the project’s communication strategy and in spreading the main messages and project results at the local level; and the Association of Agricultural Women Producers of Quebrada Honda, Zapallal. Zapallal is in the area of ​​influence of the project and this group can participate in activities to consolidate the participation of women, in the development of nurseries that promote forestry in the SPS farms and to provide fruit and forest trees for the grazing areas as well as other species for live fences to establish the SPS in the farms.

- Table 2 below presents the results of a stakeholder mapping exercise conducted to identify key project stakeholders, their present relevance or role in the project’s area of influence, and the potential impact they may have during and beyond project implementation.

Table 2: Primary Stakeholders and Beneficiaries of the Project

| Stakeholder | Relevance to the Project | Responsibility/Influence on the Project | Level of Impact on Project Implementation |
| --- | --- | --- | --- |
| Ministry of Environment of Panama | Governmental Agency GEF Political and Technical Focal Point Responsible for the management of all protected areas including the area of ​​influence of the project. | -Responsible for environmental management of production systems particularly within PA -Provide information on biodiversity, forest cover, boundaries of the PA -Association of project activities -Designation of a national focal point for the project -Designation of a regional focal point for the project -Provide spaces for meetings and workshops in central and / or regional offices. -Provide support for field trips. Guide to strategic points -Support equipment for field tours (use of boats, vehicles) -Support in convening workshops. -Secures high level participation: Minister and Advisors /Directors (project governance) | HIGH |
| Ministry of Agricultural Development (MIDA) | Government agency. Seek food security in the country; raise the quality of life of the rural population through a competitive agricultural sector. | - Presides the Board of the BDA. -Technical arm of the Agricultural Development Bank and main counterpart of the project. -Long term policies regarding sustainable production -Participate in the project from its agricultural and environmental directorates, both regional and national. -The extension team participates and is trained in the new techniques of SPS -All the institutions concerned with agriculture and the environment participate and are trained in new livestock environmental practices. -The environmental perspective is institutionalized in livestock practice. -Key information about productive units | HIGH |
| Agriculture Development Bank (BDA) | It provides financing to agricultural development programs, providing special attention to micro, small and medium producers. | -Commercial arm of the Ministry of Agriculture. -BDA commits its participation and counterpart commitment of US $12 million in loans to the livestock sector in the target area (Darien). -Participate in the Training Program in SPS oriented to the conservation of biodiversity. -Implement the manual of good livestock practices (checklist) for the financial sector. Credit officers, account executives, account analyst managers, animal technicians, technical assistant from the BDA regional offices in Santa Fé and La Palma participate. | HIGH |
| Ministry of Health (MINSA) | Regional Directorates of Darién | -Responsible for the Rural Water Supply Administration Boards (JAAR), which are key since one of their objectives is the protection of the basins where said aqueducts are supplied. These JAARs are one of the most solid organizations in the area of ​​influence of the project. | MEDIUM |
| Ministry of Education (MEDUCA) | Regional Directorates of Darién | -Participation of regional directorates in local training. Especially the agro-forestry schools must participate, both students and teachers, to learn the concepts of SPS. -Use of spaces for conducting workshops and trainings. -Actors who must be informed of project activities (communication strategy) | MEDIUM |
| Ministry of Housing and Territorial Planning (MIVIOT) | Government agency National housing policy and territorial planning. | -Relevant for the coordination of the Land Management Plan of Darien. | MEDIUM |
| National Authority for Land Administration (ANATI) | Direct, regulate and ensure the compliance and application of the national land policy, through the regularization of the national cadastre. | -Relevant for the application of the guidelines of the Land Management Plan when legalizing or providing land titles. | HIGH |
| National Cattle Ranchers Association (ANAGAN) | Main organized group of cattle ranchers in Panama. It has a Strategic Environmental Plan for the sector with goals similar to those of the project. Has formal/official representative in Darién | -High influence on and high interest in the project. -Close collaboration in all activities for the establishment of SPS at farm level. -Support in convening associates within Filo del Tallo-Canglón -Provide support in the identification of 200 farms (direct project participants) to implement SPS. -Adoption /validation of new SPS. -Support in exchange of experiences between model farms and other satellite farms. | HIGH |
| Panama-United States Commission for the Eradication and Prevention of Cattle Screw Worm (COPEG) | The COPEG was created through a cooperative agreement signed on February 11, 1994, between Panama and the United States, and later recognized as an international mission. Its main objective is to eradicate the screwworm of cattle. | -Key source of information on farms in Filo del Tallo-Canglón, their location, maps, farm sizes, and type of exploitation. Can provide information and best practices for the application of extension services to promote SPS. -It has control over screwworm in livestock farms including those in the area of ​​influence of the project. | MEDIUM |
| CATIE/ Livestock and Environmental Management Program (GAMMA) | Design of silvo-pastoral systems as a strategy for the adaptation and mitigation to climate change of livestock systems of the Central American tropics (Arco Seco de Panamá) | - High interest in the project. -Key agent in the design of SPS. -Presence in Darien with previous projects on model farms in SPS -Knowledge in timber production in SPS in Panama. -Provider of information on Darién’s cartography related to biodiversity and livestock use. -Potential ally to implement activities in the field. | MEDIUM |
| Community Based Organizations (CBOs) | Civil organizations recognized by law, organized by community | - High Influence -Potential allies for the diffusion of the communication strategy, to spread the main messages and project results at the local level. | HIGH |
| Regional University Centre (CRU- Darién) | Among others, it has the careers of: Faculty of agricultural sciences Agro-forestry Technician Agro-forestry Engineering. They have field extension officers in agro-forestry. Coordinates with MIDA for its extension programs. | -Students participate in SPS training modules -Student candidates to carry out technical support in the implementation of SPS -The center can provide training / meeting spaces | LOW |
| Agro-forestry School of Tierra Nueva de Canglón | Training center for young ‘Darienitas’ interested in the protection and conservation of resources. It has a forest reserve and a trail that leads to the Chucunaque River. | -They may participate in some training on SPS to be offered by the project -The school can provide training / meeting spaces -It is a receiving entity of information about the key messages of the communication strategy of the project. | LOW |
| Pro-Children Foundation of Darién | They have coverage throughout the province. They have farms that produce traditional crops | -Participation in local SPS training | LOW |
| Planters of Hope Foundation | Work together with CRU. They have a nursery, and intend to create a biological conservation corridor of 14 km between a secondary forest and the Filo del Tallo Reserve. | -If the nursery has forest species, it can be a provider of forestry seedlings for the SPS. | LOW |
| Association of Agricultural Women Producers of Quebrada Honda, Zapallal | They are dedicated to the production of traditional agricultural products and are legally established. | -It is a legally constituted association that has had relevance in the implementation of productive projects in the area. Zapallal is in the area of ​​influence of the project and this group can participate in activities to consolidate the gender perspective, in the development of nurseries that promote forestry in the SPS farms. | LOW |
| Santa Fé Pastoral Center Herbs and Aromatic Plants (ECODIC) | Organization of producers involved with the preparation of alternative and natural products for the improvement of health. Reforestation, recycling, garbage management, etc. | They can be allies in training for alternative uses of natural resources in agro-forestry systems within the SPS. | LOW |
| Boards of Rural Aqueducts (JAAR) | They ensure that the water service is functional and permanent. They look for the water inlets to be in good condition. | - Source of information on good / bad livestock practices in centers / water points. -High influence given their interest in key watersheds within the PA | MEDIUM |
| Voz sin Fronteras | Most listened to station in the Darien region | -High influence on the project -Disseminate the project: invitations, messages, partial results, meetings, bring participants together through media, private radio programs, support in the communication campaign of the project. -Key actor | MEDIUM |
| La Nueva | Radio station of the Darien region. | -High Influence in the project. - Key actor. - Disseminate the project: calls, messages, partial results, meetings, agglutinate participations, particular radio programs, support in the communication campaign of the project. | MEDIUM |
| Office of the First Lady- Bio-communities | Has a community development program in the following communities of Darien: Zapallal La Cantera Quebrada Honda Cemaco Lajas Blancas Marragantí El Salto | -They do not work with the SPS perspective, but groups of women can be identified to identify and strengthen gender-relevant indicators, with activities complementary to the SPS in the communities of influence of the project. | MEDIUM |
| National Border Service (SENAFRONT) | Conserve public order, prevent, investigate and repress criminal acts and faults, and protect the land and river borders of the Republic of Panama | -Provide safety in remote field trips when and if necessary. -Support in travel logistics (land and river transport) | LOW |
| Municipal Government of Pinogana | Authority for the District of Pinogana | -It is an instance of local government that must be informed of the progress of the project. Because of its remoteness, the municipality would not be considered as a meeting and / or meeting point. -Have decentralization resources for potential leveraging of strategic activities complementary to the project. | LOW |
| Municipal Government of Chepigana | Authority for the District of Chepigana | -It is an instance of local government that must be informed of the progress of the project. -The Mayor's Office is located on La Palma and can be the center for meetings, workshops or other project events. -Have decentralization resources for potential leveraging of strategic activities complementary to the project. | MEDIUM |
| Municipal Government of de Santa Fé | Authority for the District of Santa Fé | -It is an instance of local government that must be informed of the progress of the project. The Mayor's Office can be a point of convergence for workshops and other project events. | MEDIUM |
| Filo del tallo Lodge Canopy Lodge | Tourism and support for conservation initiatives with JAARs | -Key stakeholder that is reliant on the health of the ecosystem and the services they provide. | LOW |
| Corregimiento (Village level/Community Centres) Representatives | Most immediate local authority within the area of ​​influence of the project | - They can serve as facilitators with the communities and have decentralization resources for potential leveraging of strategic activities complementary to the project. | MEDIUM |
| COPEG (Comision Panama los Estados Unidos para la Erradicacion y Prevencion del Gusano Barrenador del Ganado) | COPEG has an established presence on the ground and excellent working relationship with cattle ranchers. | Will be instrumental in supporting the project with extension services to ranchers and in on-the-ground promotion of project objectives. | MEDIUM |

## C. Proposed PDO (Outcome) Level Results Indicators & GEF-7 Core Indicators

- Overall PDO (outcome) Indicators include the following and are applicable to the project’s intervention area:

(i) Sector policies and regulatory frameworks incorporate new considerations for the biodiversity of the Darien region.

(ii) Land area under effective management in production systems with improved vegetative cover (ha) in the Darien.

(iii) Financial institution applying conservation and sustainable use parameters into their lending portfolios.

- GEF-7 Core Indicators & Sub-Indicators applicable to this project

| GEF-7 Core Indicator | Global Target | GEF-7 Sub-Indicator | Project Target |
| --- | --- | --- | --- |
| 4. Area of landscapes under improved practices (hectares; excluding protected areas) | 320 million hectares | Area of landscapes under improved management to benefit biodiversity (qualitative assessment, non-certified) | 4,500 ha |
|  |  | Area of landscapes under sustainable land management in production systems | 5,000 ha |
| 11. Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | n/a but will be monitored | Number of women working on cattle ranches and benefitting directly from the project Number of men cattle ranchers working with women and benefitting directly from the project | No. of women: 40 No. of men: 158 |

# PROJECT DESCRIPTION

## A. Project Rationale

- Notwithstanding the recognition by the Government of Panama that cattle ranching may have substantial negative impacts on fragile ecosystems, efforts to date are not enough to reduce the barriers to sustainable cattle ranching.  Cattle ranchers continue to use and rely on traditional practices and methods for cattle production; extension services and technical support remain conventional, outdated and scarce; cattle rancher associations and networks are disorganized and weak, minimizing the potential socio-economic benefits a collective approach within this productive sector could generate; awareness of the multiple benefits associated with eco-friendly silvo-pastoral systems within a sustainable land management framework is limited among producers and consumers alike; land use planning and regulatory frameworks in the Darien are inadequate and do not incorporate conservation objectives at the wider landscape level; government institutions (Economy & Finance, Agriculture, Environment) and their respective technical departments are neither sufficiently coordinated nor trained to address the challenges facing the Darien nor able to provide the required support for implementing sustainable productive options; financial resources (credits/loans) are not complemented by the technical assistance, nor extension support required for the adoption of on-farm reforms in the cattle sector’s productive systems; cattle farmers in the Darien do not have the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles; and commercial banks and other financing institutions have not incorporated sustainability considerations, nor social and environmental risk management assessments in their lending operations and sectoral portfolios.

- As outlined in the baseline scenario, sustainable modernization of the sector is necessary in which sustainable production, conservation priorities, ecological integrity and the preservation of key environmental assets are integrated into decision-making, policy formulation, and sectoral development objectives. To this end, the project seeks to establish an ecosystem-based biodiversity friendly cattle production framework for the Darien Region.

## B. Global Environmental Benefits

- Global environmental benefits will be achieved through the project’s robust alignment with the GEF’s focal area objectives and programmatic outcomes. The project is consistent with the GEF’s BD and LD focal area objectives and their corresponding operational programmes:

BD-4: Mainstream Biodiversity Conservation and Sustainable Use into Production Landscapes/Seascapes and Sectors; OP #9: Managing the Human-Biodiversity Interface; and

LD-1: Maintain or improve flow of agro-ecosystem services to sustain food production and

Livelihoods; OP#1: Agro-ecological Intensification

- Specifically, the project will operate in a mixed-use landscape in the Darien region in which protected areas harbouring globally significant biodiversity and generating a suite of environmental services are interspersed with productive activities, e.g. the livestock sector. The project will seek to manage this "human-biodiversity interface" by: (i) promoting innovative silvo-pastoral productive practices in cattle rearing farms and the productive landscape; (ii) improving and regulating livestock grazing pressure through sustainable intensification and rotational grazing systems, (iii) increasing diversity of animal and grass species; (iv) implementing integrated approaches to soil fertility and water management; (v) conserving and improving hydrological functions and critical ecosystem services for agro-ecosystem productivity; (vi) enhancing ecosystem resilience (including water availability) and risk management through sustainable land management (SLM) practices; (vii) providing the necessary technical support and backstopping for the application and internalization of SPS at the farm and broader landscape level; (viii) establishing land use planning, regulatory frameworks, and enforcement measures for both protected areas and the wider production landscape; and (ix) integrating conservation and sustainable use principles into banking operations, credit and loans, to motivate and empower actors to substitute degrading practices by sustainable alternatives.

- The project is based on the premise that biodiversity and ecosystem services can be sustained in mixed landscapes through conservation-oriented production practices (in this case SPS) and sustainable land management plans. Under BD4, Programme #9, expected GEF Programmatic Outcomes include: (i) increasing the area of production landscapes that integrate conservation and sustainable use into management - demonstrated by objective data or independent certification - and (ii) developing sector policies and regulatory frameworks which incorporate BD considerations - illustrated by the degree in which sector policies and regulatory frameworks incorporate BD concerns and implement regulations.

- Under LD-1, Programme #1 expected GEF Programmatic Outcomes include: (i) improved agricultural rangeland and pastoral management, measured by the area under effective agricultural, rangeland, and pastoral management practices, and (ii) the functionality and cover of agro-ecosystems maintained, measured by the land area under effective management in production systems with improved vegetative cover.

- Additionally, by changing cattle production practices to be more biodiversity friendly, the project will contribute to the Aichi targets of the Convention on Biological Diversity. More specifically on Target #1, regarding awareness of the values of biodiversity; Target #2 on the integration of biodiversity values into local development; Target #4 with regards to actions taken by governments and stakeholders towards sustainable production and consumption; Target #5 associated with the reduction of degradation and fragmentation of natural habitats; Target #7 promoting areas under agriculture, aquaculture and forestry to be managed sustainably; Target #11 focusing on areas of importance for biodiversity and targeting ecosystems services under effective management; and Target #14 on restoration and safeguarding of ecosystems; Target #19 regarding to knowledge learned, shared and applied.

- In summary, the project will generate measurable global environmental benefits by incorporating conservation principles into productive activities, namely cattle ranching, occurring in the productive landscape. Global environmental benefits will result from the establishment of a new conservation model and development paradigm in the Darien designed to arrest land degradation, reverse deforestation and ensure the productivity of agro-ecosystems nestled between protected areas. In addition, reducing the pressures associated with ineffective land use will be addressed through sustainable land management plans designed to manage productive systems, in this case cattle ranching, within the context of a wider conservation model. Specifically, the implementation of Silvo-pastoral systems and the increase of hectares under effective management will support resource regeneration and conservation, and promote a sustainable landscape model in which productive activities can co-exist with conservation goals.

- The global benefits resulting from the application of conservation techniques in cattle production include: safeguarding biodiversity, reducing deforestation and increasing tree cover, reducing soil erosion and securing gains in soil health and quality, storing and sequestering carbon, supporting water availability, nutrient cycles and the overall functionality of hydrological services. Areas such as the Filo del Tallo-Canglón hydrological reserve, where the project will be operating, host 55% of the population's drinking water, thereby providing a crucial hydrological service.

- In addition, Silvo-pastoral Systems greatly reduce, if not eliminate, the use of chemical inputs in the soil thereby reducing the incidence of water contamination and securing additional benefits for fresh water biodiversity. Avoided contamination and turbidity due to reduced soil erosion is particularly important in the Darien as its marine and coastal areas host some of the most productive coral reefs in the Pacific.

- This project also is aligned with the GEF-7 Core Indicator 4: ‘Area of landscapes under improved practices (hectares; excluding protected areas)’, and its corresponding Sub-Indicators (1) Area of landscapes under improved management to benefit biodiversity (qualitative assessment, non-certified) and (2) Area of landscapes under sustainable land management in production systems. The project’s targets are 4,500 ha and 5,000 ha for Sub-Indicators 1and 2, respectively. The project’s Results Framework has been modified to include the above-mentioned GEF-7 Core Indicator 4, as well as GEF-7 Core Indicator 11: ‘Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment’.

## C. Project Components

- The project's objective is the establishment of an ecosystem based biodiversity-friendly cattle production framework for the Darien Region of Panamá. Specifically, the project seeks to ensure that conservation oriented Silvo-Pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of biodiversity conservation and land restoration landscape model, while supporting cattle producers to obtain the technical know-how and managerial skills for implementing conservation-oriented SPS within cattle farms and productive landscapes.

- The project will also support capacity building to ensure that technical government counterparts and extension agents are able to deliver timely quality support in the application, oversight, and replication of SPS. Cattle ranches in the Darien will be able to access project support in order to demonstrate the socio-economic and environmental benefits of SPS, including eco-labelling for SPS farm products; this demonstration will be critical in securing the support of institutions and relevant stakeholders groups (i.e. producers, consumers, extension agents, policy-makers, sector representatives and land use planners) for the application, and replication of SPS in the Darien and nationwide. A primary outcome of the project will be the development of a consolidated and integrated Land Use Management Plan to guide productive activity (cattle ranching), land use zoning and conservation efforts in the Darien. This plan will be complemented by targeted support to financial institutions, to develop and implement systemic changes in the appraisal of credits by incorporating conservation and sustainable use into their lending portfolios and mitigating the environmental, social and economic risks of their operations.

- The proposed Project with a total GEF budget of US$3,519,725 (US$1,759,862.5 GEFTF-BD and US$1,759,862.5 from GEFTF-LD) will be implemented over a period of four years and comprises the following three components: (1) Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains; (2) Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks; and (3) Monitoring, evaluation and knowledge sharing. Though budgeted separately, provisions will also be made for Project Management and the Project Close-out Period under this component.

- Component 1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains (LD: US$1,518,715; plus BD: US$425,095; total: US$1,945,810). This component aims to directly support activities that will result in more farms implementing SPS, the restoration of connective corridors and degraded areas within the productive landscape and between PAs, effective management in production systems with improved vegetative cover, technical training to the productive sector (cattle ranching) in SPS, capacity building to enhance extension services and technical support to cattle farmers  in the application of SPS, the promotion of SPS eco-labelling for farms under SPS management, and the strengthening of buy-in for SPS.

- Key outputs to support the objectives of this component will include Conservation-oriented Farm Management Plans, to be informed based on granulometric, physical and chemical analyses to be conducted of soils within the Darien that will further inform soil management requirements and species suitability for SPS.  Additionally, the Conservation-oriented Farm Management Plans must be guided by research on the economics of conversion to SPS, based on economic scenarios to be developed for select sites in the Darien in the first year of project implementation.  Other outputs will include a connectivity and restoration strategy for the establishment of conjoining corridors, training programmes for cattle ranchers, “Rancher to rancher” SPS exchange programmes, capacity building programmes for extension service providers in SPS are strengthened, an SPS eco-labelling designation, a training and entrepreneurial skill enhancement programme, and a Communication and Awareness Raising Strategy.

- The implementation of activities under this component will rely on close coordination and collaboration between ANCON, the Agricultural Development Bank (BDA), the Ministry of Agricultural Development (MIDA), National Cattle Ranchers Association (ANAGAN), CATIE/ Livestock and Environmental Management Program (GAMMA), Association of Agricultural Women Producers of Quebrada Honda, Zapallal, Community Based Organizations, and to a lesser extent, Voz sin Fronteras, and La Nueva radio stations.

- Component 2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks (BD: 1,145,810; LD: 54,190; total US$1,200,000). This component seeks to develop and initiate the implementation of a consolidated and integrated Land Use Management Plan that guides productive activity (cattle ranching), land use zoning and conservation efforts in the Darien. Other project interventions under this component will seek to consolidate the support of the BDA as the first financial institution to be engaged in systemic changes in the appraisal of credits by incorporating conservation and sustainable use into its lending portfolios and mitigating the environmental, social, and economic risks of its operations. Based on the progress to be made with the BDA, the project will explore, to the extent possible, the recruitment of other banks on the national level which may be amenable and ready to embrace the incorporation of conservation and sustainable use into their lending portfolios.

- Outputs to support the objectives of this component will include a conservation oriented Land Use Management Plan and corresponding regulatory frameworks; an online geographic information system for government officials, planners and resource users; inter-institutional agreements and multi-sectoral partnerships to be formalized at local and national levels for institutional coordination; environmental and social risks assessments and appraisal processes to be implemented and guide credit approvals; training programmes, knowledge management tools, and instructive manuals for risk assessment and appraisals to be developed as part of corporate policy to actively mainstream conservation objectives into lending operations; and a  national programme for exchanging experiences amongst banking institutions and disseminating best practices to be implemented to further mainstream sustainable use and conservation measures into loan and credit programmes.

- The implementation of activities under this component will need close coordination and collaboration between ANCON and the Agricultural Development Bank (BDA), the National Cattle Ranchers Association (ANAGAN), National Authority for Land Administration (ANATI), and the Ministry of Housing and Territorial Planning (MIVIOT), and to a lesser extent, Regional University Centre (CRU- Darién), Agro-forestry College of Tierra Nueva de Canglón, Planters of Hope Foundation, and Community Based Organizations, whose relevance and influence on the project have been described above in Table 2.

- Component 3: Monitoring, evaluation and knowledge sharing (BD: US$103,155 plus LD: US$103,154, total US$206,309). Project interventions under this component are focused at developing and implementing systems and processes to ensure project implementation follows a Results Based Management framework (RBM), applies SMART indicators for measuring progress and impact (PDO level and results level), and employs adaptive management principles to systematically re-incorporate monitoring and evaluation feedback (results, experiences, and lessons learnt) into project performance.

- Planned outputs to support the objectives of this component will include  the development and implementation of a Project Monitoring and Evaluation Strategy, including annual work-plans, technical and financial progress reports with progress and impact indicators, annual budget allocations, and independent evaluation requirements; the definition of baselines for biological indicators (BD and LD) at the farm and productive landscape level for the project intervention area; consistent with explicit recommendations of the STAP for GEF projects engaging in any form of eco-labelling, a  monitoring plan will be developed to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation; and a project website will be developed, launched and maintained to provide updated information on project progress, measureable results, lessons learned, including links to relevant government websites, the on-line GIS, and blogs pertaining to SPS issues, ranching, conservation, and sustainable resource use topics, etc. A Knowledge Management Strategy will be developed within the first semester of project implementation to ensure systemic documentation and uptake of results, experiences and lessons learnt is realized through-out project implementation, and not just as a consequence of periodic monitoring of time-bound project milestones. The development of this strategy will be guided by globally accepted elements affecting the successful implementation of Knowledge Management Systems: adoption, acceptance and assimilation. The institutionalization of knowledge management initiatives and processes developed by the project will be a specific objective of the Knowledge Management Strategy, and will be a critical element for the sustained storage, access and dissemination of project results and outcomes beyond the life of the project. Details on performance monitoring are provided in the Project Results Framework in Annex 1 and a further description of project activities, outputs and outcomes is presented in Annex 2.

## D. Project Financing

- The Project has obtained GEFTF-BD and GEFTF-LD financing for US$3,519,725, all of which will be devoted to technical assistance. Counterpart funding from the Government of Panama and the Bank for Agricultural Development is estimated at US$14,346,572, for a total project cost of US$17,866,297.

- Summary Budget:

| Components | GEFTF-BD US$ | GEFTF-LD US$ | Total GEF project Funds (US$) | Matching Gov’t + Other Contribution (US$) |  | TOTAL US$ |
| --- | --- | --- | --- | --- | --- | --- |
| C-1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains | 425,095 | 1,518,715 | 1,945,810 | 12,000,000 |  | 13,945,810 |
| C-2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks | 1,145,810 | 54,190 | 1,200,000 | 1,600,167 |  | 2,800,167 |
| C-3: Monitoring, evaluation and knowledge sharing | 103,155 | 103,154 | 206,309 | 63,235 |  | 269,544 |
| Project Management Costs | 83,802.50 | 83,803.50 | 167,606 | 683,170 |  | 850,776 |
| Total Project Cost | 1,676,060 | 1,676,059 | 3,519,725 | 14,346,572 |  | 17,866,297 |

## E. Lessons Learned and Reflected in Project Design

- The establishment of silvo-pastoral systems and biodiversity-friendly production practices are relatively new concepts in the Darien. Analyses of prior experiences have shown that two critical variables need to be addressed in tandem to ensure SPS success, these are: (i) the availability of financial resources and (ii) the simultaneous provision of technical assistance. Former efforts have typically focused on one at the expense of the other with results confirming that any disconnect between the two will negatively affect project outcomes in terms of their sustainability and their potential for replication. In cases when resources were available (grants, loans, credit, subsidies) producers were not provided with the required technical assistance. Targeted training or capacity building measures were simply insufficiently incorporated into project design to support the sustainability or the replication of achievements. The result was a quick and predictable return to a “business as usual scenario” and the unsustainable productive practices cattle producers felt more familiar and comfortable with. Lessons learned by the GEF Small Grants Programme in community engagement and outreach in the Darien will be valuable in planning and implementing community-based interventions, and in particular in the direct engagement of women in project interventions.

- Lessons learned by CATIE/ Livestock and Environmental Management Program, for the design of silvo-pastoral systems as a strategy for the adaptation and mitigation to climate change of livestock systems of the Central American tropics will be valuable, with substantial lessons learned in tropical agro-forestry, animal production and food safety. Experience of the Agricultural Development Bank in providing financing to agricultural development programs with focus on micro, small and medium producers will be instrumental in the quest to further define and incorporate sustainable production principles into the credit appraisal process for farmers seeking to access credit for production and expansion. The extension program of the Ministry of Agricultural Development will form a baseline upon which to define and expand technical assistance programmes to be offered to cattle ranchers by the project, and also to update the extension manual of the said ministry. Lastly, ANCON has a wealth of experience working with local communities in the Darien, and this will be crucial in defining the best intervention strategies in approaching community based organizations and in ensuring the involvement of women in project-sponsored activities.

## F. Coordination with Other Initiatives Including Relevant GEF Funded Initiatives

- As described above, there are several initiatives as well as GEF financed activities past and present with which the project may be able to associate based on relevance of activities and/or opportunities for collaboration. However, one the most relevant program seems to be the GEF’s Small Grants Programme as it constitutes an on-going initiative with relevant community experience in the Darien region. Coordination arrangements with relevant on-going initiatives at the national level (for example with CATIE/ Livestock and Environmental Management Program) will entail formal participation in project coordination meetings, bi-annual workshops at the field level, as well as visits and exchanges with project teams of similar initiatives (whether GEF financed or not). The project will seek to specifically identify coordination opportunities with the following initiatives and/or agencies, to be guided by recommendations of the Project Steering Committee and the Technical Advisory Committee:

- "The National Outreach and Extension Programme for Cattle Farming" led by the Ministry of Agricultural Development, in areas related to the modification of production patterns in the agricultural sector along environmentally sound and socio-economically viable parameters.

- The Ministry of Agricultural Development and the Tropical Agronomic Centre for Research and Education (CATIE). Coordination will focus on matters relating to “Good Practices for Sustainable Cattle Ranching" and in the definition of indicators to demonstrate livestock profitability and ecosystem services generation as a result of SPS implementation.

- The "National Livestock Traceability Programme" implemented by Ministry of Agricultural Development. Collaboration will focus on the proposed eco-labelling component of the project, to provide consumers with critical sector information along its productive chain and the assurance that they are buying meat produced in biodiversity-friendly ranches.

- The Bank for Agricultural Development (BDA), in all matters related to the incorporation of environmental sustainability criteria into the appraisal process of credits to farmers.

- The “Authority for the Control of Certification of Agricultural Organic Production”. Collaboration will focus on all matters relating to the assurance of to consumers regarding the organic, biodiversity-friendly, and ecologically compatible attributes of a variety of agricultural produce, eco-labelling information, proof of origin, and trustworthiness of produce.

- Collaboration with the “Alliance for one million of reforested hectares” will focus at all matters relating to the reducing and reversing of current deforestation rates in natural forests in the Darien, and particularly in areas such as Filo del Tallo Canglón Hydrological Reserve.

## G. Incremental Cost Reasoning

Summary Baseline Analysis

- As described above in the Project Baseline Scenario, there have been many admirable efforts and progress to date towards sustainable cattle ranching, especially by the Ministry of Environment, the Ministry for Agricultural Development, USAID, CATIE and ANCON. Some successful stories and progress to date include the selection of pilot ranches in cattle producing regions of the Darien, specifically in the sub-basins of the Chucunaque River and the Congo River, in order to begin the introduction and implementation of technological shifts in cattle management, including the efficient use of land, soil, water and vegetation in production practices; .the “Manual of 15 Good Practices for Sustainable Cattle Ranching" exclusively for ranchers; and the establishment of a single national agricultural record that identifies: each ranch and farm, a record of all species managed in the ranch, an ID for each single animal or group of animals, a record of the animal movements, the corresponding means of transportation, and a centralized and Official Information System of Livestock Traceability.

- Another success story worthy of mention is the establishment of the “Authority for the Control of Certification of Agricultural Organic Production”, with a mandate to provide tangible assurances to consumers regarding the organic, biodiversity-friendly, and ecologically compatible attributes of a variety of agricultural produce, furthering consumers’ understanding regarding the different kinds of existing labels and/or certifications, resulting in an official authoritative guide to understanding the productive origins and specificities of a variety of goods, including their associated socio-economic and environmental benefits.

- The “Alliance for one million of reforested hectares” (AXM) as a public-private partnership seeks to reforest a million hectares in the next 20 years, with the aim of reducing and reversing current deforestation rates in natural forests and degraded lands in Panama, including areas such as Filo del Tallo Canglón Hydrological Reserve in the Darien.

- Notwithstanding the above, however, there are still significant barriers to overcome in order to establish an ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panamá. The concepts of integrated resource management and the application of silvo-pastoral systems (SPS) remain unfamiliar to Darien’s cattle producers. The sustainable intensification of existing farm-lands and the application of alternative production practices, including crop rotation, crop diversification, water-saving techniques, and the application of conservation-oriented SPS, among others, are neither practiced, promoted nor sufficiently understood. Specialized assistance and institutional backing for cattle producers has been limited in both quantity and quality. Networking structures and cattle ranchers’ associations remain incipient and disorganized compared to those in other regions in the country, as well as other agricultural sectors. This constitutes an important organizational barrier preventing ranchers from defining common needs, mutual goals, the scope and frequency of assistance requirements, and the possible economies of scale in delivering and optimizing technical support.

- The socio-economic and ecological benefits of sustainable cattle ranching - through the application of conservation-based practices within a sustainable integrated land use management model - remains elusive at local and national levels; and the socio-economic costs and ramifications of engaging in "business as usual ranching" along with the environmental degradation it entails have not been internalized, costed, nor fully understood by producers and consumers alike. The Darien does not have a cohesive land use plan which integrates conservation, ecosystem services, and sustainable resource use objectives. Existing plans are not legally binding and do not take into consideration the wider multi-functional landscape in which these reside.

- Technical assistance for cattle rearing in the Darien remains limited to basic sanitation and inoculation priorities, censuses, and to certain extent maintenance of road access for livestock transportation purposes. There is an absence of reliable, specialized and informed technical assistance to facilitate and guide cattle ranchers in accessing capital, particularly among small to medium sized producers; this has undermined progress towards the application of SPS and the possibility of achieving lasting productive changes in the Darien. Cattle farmers in the Darien do not have the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles. However, the technical support needed to move from “business as usual” to the proposed “alternative scenario” is currently unavailable thus constituting a significant barrier to optimize the potential of available credit. Credit for agricultural development continues to be granted easily on favourable terms for “business as usual” production in a variety of sectors including cattle rearing, irrespective of resulting socio-environmental impacts.

Without the GEF’s Intervention

- In the absence of GEF support, cattle ranchers will continue to use and rely on traditional practices and methods for cattle production. Cattle producers moving to the Darien will continue to apply the same unsustainable methods utilized in their place of origin, irrespective of the environmental consequences these practices have progressively had on the resource base they depend on. Dependence on conventional inputs and “standard” production practices will continue to be the norm, as does the environmental degradation associated with these long-established production scenarios.

- Without GEF resources, extension services and technical support will remain conventional, outdated and scarce. Extension agents will continue to suffer from a generational gap in technical knowledge and there will be no SPS models at a larger scale to change perceptions of what constitutes sustainable production models. Cattle rancher associations and networks will remain unfocused implementing the same unsustainable and unproductive ranching practices, minimizing the potential socio-economic benefits of a new productive approach within this  sector could generate. Consumers and producers will continue to be unaware of the multiple benefits associated with eco-friendly silvo-pastoral systems within a sustainable land management framework.

- Land use planning and regulatory frameworks in the Darien will remain inadequate in the short term, and not incorporate conservation objectives at the wider landscape level. Government institutions (Land Planning, Agriculture, Environment) and their respective technical departments will see minimal improvements in coordination and training to address the challenges facing the Darien and to provide the required support for implementing sustainable productive options. Technical assistance and extension support will continue to be absent from financial resources (credits/loans) as a necessary complement to extension support required for the adoption of on-farm reforms in the cattle sector’s productive systems. Cattle farmers in the Darien will continue to lack the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles, in order to access credit from financial institutions. And finally, banks and other financing institutions will make slow progress in incorporating sustainability considerations, and social and environmental risk management assessments in their lending operations and sectoral portfolios, with continued “business as usual” practices.

The GEF Alternative

- The alternative scenario summarized below is based on the following considerations: (i) an assessment of the threats and root causes affecting biodiversity conservation and sustainable land use in the Darien; (ii) an appraisal of the principal barriers impeding conservation-oriented cattle production in the Darien and access to credit, including the efficient use of its natural resource base; (iii) consultations and inputs from relevant stakeholder groups at local and national levels; (iv) a supportive programmatic baseline well poised to benefit from incremental funding to deliver global conservation benefits; and (v) full consistency with sector plans, national development objectives and conservation priorities.

- The project will target the expanding ranching activity occurring in the productive landscape of the Darien and more specifically the area surrounding the Filo del Tallo-Canglón Hydrological Reserve, including the productive cattle plots spreading within the reserve before these expand any further. Several important considerations have informed the selection of this area and are worthy of mention. Located at the entrance of the Darien region, the Filo del Tallo-Canglón Hydrological Reserve spans 38,014 ha and is critically important not only because of its biological relevance but primarily because of the strategic and vital ecosystem services it confers. In this regard, the Reserve harbours 32 water sources providing 55% of the Darien population’s drinking water (Ministry of Health, 2015). In addition, the Reserve’s close proximity to the Pan American Highway has made it more vulnerable to cattle ranching settlements and encroachment. The landscape around the Filo del Tallo-Canglón Hydrological Reserve while attesting to cattle expansion is also a strategic site from which to showcase conservation-oriented SPS for demonstrative purposes, due to its visibility, the number of stakeholder groups converging in the area, and the scale of the impact that could be accomplished through a single intervention.

- GEF resources will specifically support the development of Conservation-oriented Farm Management Plans, to be informed based on granulometric, physical and chemical analyses to be conducted of soils within the Darien that will further inform soil management requirements and species suitability for SPS; a connectivity and restoration strategy for the establishment of conjoining corridors, training programmes for cattle ranchers, “Rancher to rancher” SPS exchange programmes, capacity building programmes for extension service providers in SPS are strengthened, an SPS eco-labelling designation, a training and entrepreneurial skill enhancement programme, and a Communication and Awareness Raising Strategy.

- A Land Use Management Plan and corresponding regulatory frameworks will be developed, an online geographic information system for government officials, planners and resource users; inter-institutional agreements and multi-sectoral partnerships will be formalized at local and national levels for institutional coordination; environmental and social risks assessments and appraisal processes will be implemented and guide credit approvals; training programmes, knowledge management tools, and instructive manuals for risk assessment and appraisals to be developed as part of corporate policy to actively mainstreaming conservation objectives into lending operations; and a  national programme for exchanging experiences amongst banking institutions and disseminating best practices to be implemented to further mainstream sustainable use and conservation measures into loan and credit programmes.

- The GEF alternative also will support the development and implementation of a Project Monitoring and Evaluation Strategy, the definition of baselines for biological indicators (BD and LD) at the farm and productive landscape level for the project intervention area; a  monitoring plan will be developed to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation; the development, launch and maintenance of a project website to provide updated information on project progress, measureable results, lessons learned, including links to relevant government websites, the on-line GIS, and blogs pertaining to SPS issues, ranching, conservation, and sustainable resource use topics, etc. A Knowledge Management Strategy also will be developed with GEF resources to ensure systemic documentation and uptake of results, experiences and lessons learnt is realized through-out project implementation, and not just as a consequence of periodic monitoring of time-bound project milestones. An Incremental Cost Matrix is provided in Annex 4.

# IMPLEMENTATION

## A. Institutional and Implementation Arrangements

- Project execution and coordination among the variety of actors of the project will be lead by ANCON (the National Association for the Conservation of Nature) a non-profit, non-governmental organization founded in Panama in 1985 with the mission of conserving Panama’s biodiversity and natural resources for the benefit of present and future generations. ANCON is dedicated to promoting environmental education, sustainable development projects in rural communities, and the development and promotion of biodiversity conservation projects. ANCON, which is also responsible for the management of a 30,000 ha private reserve in the Darien region, will be in charge of project implementation. ANCON not only counts with extensive experience in the project area, which is its main geographic focus area, but also in the implementation of projects promoting sustainable development in rural communities, mechanisms for promoting civil society engagement, as well as policy advocacy at the highest decision-making levels. ANCON is a highly respected and credible actor in conservation efforts at local, regional and national levels, with an impressive convening capacity, including the ability to leverage and mobilize high level expertise in a diversity of technical fields.

- A Project Coordinating Unit (PCU) will be established by ANCON to oversee day-today project execution. The PCU is responsible for the fiduciary oversight and reporting of the project, including financial management and procurement consolidation according to the projects operational manual and procurement plan. It is also responsible for monitoring and evaluation (M&E), provides and coordinates technical advice, and coordinates and assists overall orientation concerning project conception, strategies, criteria and methodologies, as well as organizes and supports regional activities. The PCU will be staffed with A Project Coordinator, a Sustainable Agriculture Specialist, an Accountant, and an Administrative Assistant. Financial management and procurement services will be provided by ANCON, and technical delivery of project outputs will be complemented by specialist consultants on an as needed basis.

- Two key governing bodies will be established for the project: a Project Steering Committee (PSC) and a Technical Advisory Committee (TAC). In practical terms the PSC is responsible for ensuring that the project meets goals announced in the Project Result Framework by helping to balance conflicting priorities and resources.  Conclusions and recommendations produced by the PSC will be used by ANCON to modify implementation strategies, annual work plans and resources allocation budget and, when necessary, to adjust the project’s Result Framework. This committee will meet every six months, either physically or virtually. The Technical Advisory Committee (TAC) is to provide technical oversight, guidance and support during project implementation. The TAC is also responsible for reviewing and providing recommendations on project processes (operational guidelines) and activities, to the Project Steering Committee (PSC) for their review and endorsement. Further details on implementation arrangements are provided in Annex 3.

## B. Results Monitoring and Evaluation (M&E)

- The project will follow CAF standard monitoring, reporting and evaluation processes and procedures. Reporting requirements and templates will be provided by CAF and will be an integral part of the legal instrument to be signed by the executing agency and CAF. The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Annex 1 includes SMART indicators and means of verification for each expected outcome. These indicators will be the main tools for assessing project implementation progress and whether project expected results are being achieved. A costed project M&E Plan is presented in Annex 6.

- An inception workshop will be held at the onset of project implementation to ensure all actors understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Indicators and their means of verification may be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of ANCON and the project management team. It is the responsibility of ANCON to inform CAF of any delays or difficulties faced during project implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

- The PSC will issue reports every 6 months on progress by the project and make recommendations concerning the need to revise any aspects of the Project Results Framework, or the M&E plan. Supervision to ensure that the project meets CAF and GEF policies and procedures is the responsibility to the CAF-GEF Task Manager. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of project outputs in close collaboration with ANCON.

- ANCON will develop an initial supervision plan that will be communicated to the project partners during the inception workshop for comments.  The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring.  Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed by CAF. Project risks and assumptions will be regularly monitored both by the PSC and CAF. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective in the use of financial resources.

- A Mid-Term Evaluation will be conducted at the mid-point in the project. An independent consultant will be hired to conduct this evaluation. ANCON will manage the mid-term evaluation (MTE) process, under close supervision of CAF. The MTE will address evaluation parameters recommended by the GEF Evaluation Office and will verify information gathered through the project’s monitoring and evaluation efforts, as relevant. The PSC will participate in the mid-term evaluation and will support ANCON in the development of a management response to the evaluation recommendations along with an implementation plan. It is the responsibility of the CAF-GEF Task Manager to monitor whether the agreed recommendations are being implemented.

- An Independent Terminal Evaluation will take place within the last semester of project implementation. CAF will manage the terminal evaluation process. A review of the quality of the evaluation report will be done by CAF and submitted along with the report to the GEF Evaluation Office not later than 6 months after the completion of the evaluation.

## C. Innovativeness, Sustainability and Up-scaling

- Past lessons in sustainability and up-scaling: The establishment of silvo-pastoral systems and biodiversity-friendly production practices are relatively new concepts in the Darien. Analyses of prior experiences have shown that two critical variables need to be addressed in tandem to ensure SPS success, these are: (i) the availability of financial resources and (ii) the simultaneous provision of technical assistance. Former efforts have typically focused on one at the expense of the other with results confirming that any disconnect between the two will negatively affect project outcomes in terms of their sustainability and their potential for replication. In cases when resources were available (grants, loans, credit, subsidies) producers were not provided with the required technical assistance during or beyond the life of the project (nor did projects contemplate this as a potential long-term need). Targeted training or capacity building measures were simply insufficiently incorporated into project design to support the sustainability or the replication of achievements. The result was a quick and predictable return to a “business as usual scenario” and the unsustainable productive practices cattle producers felt more familiar and comfortable with.

- Another fundamental and decisive factor for sustainability and replicability refers to the policy and regulatory framework guiding the cattle sector’s development. In the past, while initiatives might have benefited from sporadic funding to implement sustainable production, efforts were not simultaneously supported by the necessary “in-country” conditions to make them lasting propositions. In this sense, prior initiatives lacked the institutional backing of a system wide enabling policy environment, supportive regulatory instruments, targeted capacity building measures, and financial incentives, which collectively combined, could have realistically delivered long-term changes and replication. In brief, prior efforts did not benefit from the policies and institutional frameworks needed for sustainable productive practices to have any lasting impact nor the means to expand beyond a given location.

- Conversely, Panama is now deliberately investing in the sustainability of its agricultural sector, promoting the application of sound ecological principles and the efficient use of its resource base, including the safeguarding of its ecosystem services and the contribution these confer to sustained productivity. As such, a favourable and encouraging institutional and policy environment, previously inexistent or too incipient to make a notable difference, is now available to support the success and replication of forward thinking initiatives such as the one proposed by this project.

- In today's institutional and financial context, the proposed project will thus benefit from three fundamental variables with regards to sustainability and replication: (i) the availability of established and preferential financial mechanisms, (ii) supportive policies and regulatory frameworks, and (iii) a coordinated and united institutional presence, at local and regional levels, delivering tailored technical assistance for implementation oversight and support. This assistance will be available for the necessary amount of time needed for producers to: (i) gain the required expertise and confidence in the application of conservation oriented SPS; (ii) directly witness and experience the beneficial results of these practices on their farms; and (iii) become themselves the promoters and advocates of these conservation oriented SPS. Consultations with all relevant stakeholder groups confirm that the above mentioned elements should provide the requisite contextual framework for sustainable changes in cattle rearing to become a lasting and replicable proposition.

- Sustainability and Up-scaling: The establishment of SPS practices in the Darien will be sustained by the favourable institutional and policy changes in the agricultural and financing sector, as well as those pertaining to land use planning and regulations for productive activity and sustainable resource use. In this regard key determinants of mainstreaming success exist in the context of this project and project design considerations have been deliberately embedded within this changing framework.

- More specifically, with regards to agriculture, the GoP through its Ministry of Agricultural Development is moving towards “modernizing” the sector through: (i) the promotion of efficiencies in the use of resources, (ii) mainstreaming conservation and sustainability concerns in its operations and policies, (iii) addressing and prioritizing sectors with “inappropriate practices” currently affecting biodiversity and ecosystem services critical to maintaining production potential, (iv) exploring regulatory tools and incentives to encourage behavioural change and the application of conservation-oriented parameters and standards; and (v) identifying optimal entry points and “sector-specific” tools through which to conduct lasting interventions.

- The same strategic alignment is reflected in the policies of the Bank for Agricultural Development, the financial arm of the Ministry of Agricultural Development. Consistently with the Ministry, the Bank is moving towards the progressive inclusion of the same conservation priorities and sustainable use principles within its lending operations by developing enabling tools and incentives and discouraging degrading “business as usual” scenarios. The adoption of social-economic and environmental risk assessments for credit appraisals in agriculture, coupled with the use of “Guiding principles for conservation-oriented livestock rearing” (guía bancaria para la ganadería sostenible) for cattle sector loans developed by ANCON for the BDA and Panama´s National Bank, will be decisive in promoting, sustaining, and replicating these changes at scale.

- In addition, a cross-sectoral approach including dialogue, cooperation and high-level support between the key institutions needed to impart lasting change in cattle production and land use planning is actively present. The Ministry of Agricultural Development, The Ministry of Environment, The Bank for Agricultural Development, in addition to other indispensable counterparts such as the National Association of Cattle Ranchers, and The National Land Authority (which works alongside the Ministry of Environment in matters pertaining to zoning and land use planning) are equally invested in this project and fully endorse its objectives.

- In parallel, a growing awareness in the public and private domain is leading towards behavioural and attitudinal changes supportive of conservation-oriented production practices and the products resulting from these modified production models.

- Innovation: An important and innovative variable in the financing context of this project refers to the mainstreaming of socio-economic and environmental risk assessments into the lending portfolios of the Bank for Agricultural Development. These risk assessments reflect the policy reforms and sustainability objectives of the Ministry of Agricultural Development with regards to the livestock sector and how the GoP foresees its development in the coming years. These systemic changes also illustrate an unprecedented institutional alignment between the Ministries of Agriculture and the Ministry of Environment with regards to the management of productive activities in biodiversity rich areas and the mainstreaming of conservation concerns into key institutions and sectors. The project will provide an important testing ground for the banking sector in the application of risk appraisal measures geared towards the adoption of significant changes in the “business as usual” cattle rearing sector. From the standpoint of the Bank for Agricultural Development, this endeavour will also prove valuable for other banking institutions within Panama and the region. The project will document this experience to facilitate its adoption in other financial institutions granting credits and loans for agricultural development.

- Furthermore, to build upon existing SPS practices and further innovate in their application, project proponents will maintain regular contact with institutions and technical staff engaged in SPS experiences particularly in Costa Rica and Colombia, i.e. CATIE, CIPAV, and CGIAR to name a few. Just recently, the national associations of cattle ranchers, along with staff from the Ministry of Agricultural Development, extension agents and university students visited a cattle farm in the coffee producing region of Colombia which serves as a demonstration center for the application of SPS, conservation practices, and organic produce. As part of the project’s capacity building strategy and training programmes, it is expected that these technical institutions (among others) will train national producers, as well as extension staff in order to establish a critical knowledge base at local and national levels able to support and oversee the implementation of SPS in the long term. In this regard, literally a new generation of both producers and extension agents is being formed to lead the development of the cattle sector in Panama. During the project design stage (PPG), training programmes, field visits, workshops, and technical exchanges with a range of successful initiatives in the region will be scheduled to fully tap into the best expertise and the most successful experiences.

# KEY RISKS AND MITIGATION MEASURES

- Estimated risks are summarized in the table along with their rating category and mitigation measures as appropriate.

| Risk | Level | Mitigation approach |
| --- | --- | --- |
| Farmers are not willing to join the project | Low | On-going communications with individual farmers in the project area as well as ANAGAN have confirmed their interest in participating in the project. The economic benefits of SPS, mainly to increase productivity in comparison with traditional types of management have been proven in Panama as well as other countries of the region, and are strongly supported by cattle ranchers. These individuals and the organizations and cooperatives they form part of have expressed their full interest and support for project objectives provided that on-site technical support is available. |
| The project will unwittingly encourage the expansion of cattle ranching and deforestation | Low | Firstly, the project will only work in areas that are already under cattle farming. Secondly, SPS are geared to improve productivity, intensity, and on-farm efficiencies avoiding the need to expand to new untouched areas that would generate further deforestation. Furthermore land use planning and zoning, along with regulations and enforcement measures will further ensure that the risk of expansion is null. |
| MIDA’s personnel on site is not available to cooperate with the project with the expected rate of involvement. | Medium | The Ministry for Agricultural Development is significantly invested in the project at its highest levels. This commitment is equally reflected amongst its staff, particularly those entrusted with extension work and technical support in the field. The Ministry is fully cognizant of the need for permanent on site-support as this is a requirement cattle ranchers have emphasized and requested. On the other hand, the Bank for Agricultural Development (the financial arm of the MIDA) has made a formal financial commitment to ensure and facilitate the project’s success and measurable impact. Furthermore, both the MIDA and the Bank for Agricultural Development will be part of the project’s Steering Committee and will be appraised of implementation progress on a regular basis. |
| Market is resistant to accept products from the biodiversity friendly farms. | Low-low | Market indicators and demand for organic produce has steadily risen for the past decade in Panama and most notably during the last five years. The newly established Authority for National Certification (Jan 2017) further confirms this growth pattern and the need to satisfy both consumers and producers in formalizing criteria and overall credibility in certification standards. The market, private sector operators, supermarket chains, consumers, and now small-scale producers are eager to meet rising demand and participate in environmentally sound production. There is a growing demand for these products in Panama and an expansion of private sector ventures and investment supporting these endeavours. |
| Lack of coordination among the institutions and organizations contributing to the project. | Low | The lead organizations committed to the project at the national level, namely the Ministry of Agricultural Development, the Bank for Agricultural Development, the Ministry of Environment, the Alliance for One Million Reforested Hectares (AXM), and ANCON consider this project a priority in their respective programming portfolios. Their complementary roles, functions and responsibilities have been mutually discussed, as have the forthcoming institutional arrangements and coordination structures designed to guide project development and provide implementation oversight. There is a political and institutional commitment supported at Ministerial levels. This risk is considered very low. |
| Traceability of eco-brand products from producer to consumer cannot be guaranteed. | Low | MIDA is implementing a traceability programme that will provide consumers with all the relevant information regarding the origins of the produce they are purchasing they will purchase and the project will make full use of this programme. |
| Difficulties facing the approval of a regulatory instrument such as a law for the land use plan in the region. | Medium-low | A regulatory framework in the form of a ministerial regulation or an executive decree, instead of a law, is an essential first step to facilitate the subsequent adoption of a comprehensive land use plan for the Darien. The lead institutions with responsibilities and interests in the region, namely the Ministry of Environment and the Ministry of Agriculture are committed to establishing and actively supporting the necessary land use planning and regulatory frameworks needed to facilitate sustainable production practices, both at the farm and productive landscape level. |

# SUMMARY PROJECT ANALYSES

## A. Economic and Financial Analysis

- Based on an understanding of the socio-economic and environmental conditions of the project intervention areas within the Darien and on the circumstances surrounding the participation and management of the various social and institutional actors in the area, the portfolio of possible measures to establish an ecosystem-based biodiversity friendly cattle production framework was defined, according to three major groups: i) SPS implementation and the restoration of connective corridors and degraded areas within productive landscape and PAs; (ii) Land area (in ha) under effective management in production systems with improved vegetative cover; and (iii) Avoided deforestation of natural habitats in the productive landscape of the project area. The prioritization of project intervention measures was done through technical reasoning (use of criteria such as predominant ecosystem types, conservation status of the nine (9) conservation areas in the Darien, magnitude of cattle ranching activities, general state of human intervention in the basin, presence of other uses and users of water in the basins, presence of organizational structures for cattle ranching or other uses of the area, etc.) and knowledge based on previous experiences of attempts made by agencies such as ANAGAN and CATIE to address sustainable cattle production. The intervention measures were chosen based on a qualitative analysis of their feasibility and not necessarily on individual costs, probable execution times, availability of favourable frameworks (in the legal, institutional, private sector willingness, and environmental aspects), and the estimated time for their design and implementation. Those measures that were estimated can be implemented in relatively short times, have the highest probability of co-financing, and those that are most likely to consolidate alliances, were favoured.

- Firstly, the project is expected to be cost-effective by complementing the baseline investments defined under the ‘GEF Alternative’. Secondly, the project is expected to be cost-effective as a result of its ability to bring together various partners from regulatory, productive and financing agencies relevant to the cattle ranching sector, including environment, agriculture, water, education, banking, and health. Additionally, project activities will contribute to the achievement of GEF focal area strategies relating to management of the human-biodiversity interface and agro-ecological intensification. The project therefore will achieve a far-reaching impact with the relatively limited amount of resources available, at the local, national and global scale, with direct socio economic benefits to 198 cattle ranchers including 40 women cattle ranchers, and increasing sustainable cattle production by up to 30% within the Filo del Tallo-Canglon Hydrological Reserve. Investments in the generation and exchange of knowledge, technology transfer, institutional strengthening; mainstreaming of biodiversity into cattle production and into policies, strategies and programs and the incorporation of environmental sustainability measures into banks’ financing policies will provide opportunities for South-South transboundary collaboration (especially with Colombia and Costa Rica), while achieving tangible economy of scale in knowledge management through the maximization of experiences and lessons learned.

- The anticipated fiscal impact of the project on the Republic of Panama is expected to be modest. Counterpart contributions are largely in kind, in terms of staff, the provision of office space, and the recurrent costs for fuel, equipment maintenance and consumables, which are already absorbed into the existing budgets of the implementing agencies, and should therefore not be a challenge in the future. An exception is the 12,000,000 in credit facilities being made available by the Agricultural Development Bank to the cattle ranching sector, which is expected to translate into a 30% increase in revenue to ranchers from successful SPS implementation.  Finally, the cost-effectiveness of the project is further strengthened through the involvement of CAF as the GEF Implementing Agency and ANCON as Project Executing Agency, together with the Ministries of Environment and Agriculture, and the Agricultural Development Bank. This ensures that a competent with substantial project management experience is able to support project execution and strengthen the administrative, financial and technical oversight of the project, with priority on efficient execution of funds, achievement of economies of scale, and the maximization of return on project investments.

## B. Technical

- The project is considered to be technically sound, given that:

  - Conservation-oriented Farm Management Plans will be developed based on sound technical and scientific analysis including soil mechanics, species suitability, and economic scenarios.

  - A conservation-oriented Land Use Management Plan and corresponding regulatory frameworks will bring together multiple regulatory agencies and private sector actors in an unprecedented process to develop and consolidate sustainable cattle ranching in Panama.

  - The Project will minimize technical difficulties in applying innovative approaches by developing and implementing agreed protocols for collection, processing and dissemination of information, technology transfer and knowledge management, extending to South-South collaboration.

  - The involvement of the private sector (both cattle ranching and banking) brings years of experience and technical know-how, thus providing a high degree of assurance to the quality of projects outputs and outcomes.

  - The Ministry of Agriculture Development and ANAGAN are perfectly poised to lead and consolidate SPS implementation in the Darien, based on their decisive move towards institutionalizing measures for SPS, which will complement GEF investments in SPS.

  - The project employs decentralized structures that ensure the participation and contribution of local stakeholders at the level of communities in the Darien region, municipalities, and productive sectors.

## C. Financial Management

- All activities related to financial management will follow the Financial Procedures Agreement (inclusive of all annexes) between the Development Bank of Latin America (CAF) and the International Bank for Reconstruction and Development (IBRD) as Trustee of the Global Environmental Facility Trust Fund (GEFTF), signed on September 28th, 2015. This agreement contains provisions for project operations to meet and exceed all internationally-accepted financial and fiduciary management standards, to be evidenced in annual, final independent audits, and other periodic audits of the project accounts, as may be necessary. Staff of the project’s executing agency that are involved in the day-to-day management of project resources will be trained in financial management policies consistent with the provisions of the above-mentioned agreement, during and after the Project’s Inception.

## D. Procurement

- All activities related to procurement will follow the Procurement Policies of CAF as defined in the Procurement and Contracting of Goods, Services and Works Manual, published on March 17th, 2015 by the Directorate of Physical Infrastructure, Logistics, and Administration, Version MN/DIOFLA 038 of February 2016. These policies contain provisions for operations to meet and exceed all internationally-accepted financial and fiduciary management standards, to be evidenced in annual and final independent audits of the project’s procurement and disbursement processes. Staff of the project’s executing agency that are involved in the day-to-day management of project resources will be trained in CAF’s procurement policies as described above and in procurement planning during and after the Project’s Inception.

## E. Environmental and Social (including Safeguards)

- The implementation of project activities will be in accordance with the Environmental and Social Safeguards for CAF/GEF Projects Manual, Version 1 of May 2015. The Project is classified as Category B, according to the Guidelines and Procedures on Environmental and Social Safeguards for CAF/GEF Projects Manual (Section V.I.2 Annex I). Project interventions are not expected to cause major adverse environmental impacts, and instead, in many cases will improve the environmental and social conditions prevailing in the areas of intervention, including greater resilience capabilities to deal with extreme events, impacts of climate variability and climate change. Minor site-specific environmental impacts in natural habitats and forests may be expected from some on-the-ground interventions, but mostly temporary.

## F. Gender Mainstreaming

- The project will ensure the participation of women in all training activities, including farm planning. It is important to note that women play an important role in various aspects of farm management particularly with regards to the information registries key to monitoring biodiversity and economic indicators. In the case of dairy farms, women play an even more relevant role in dairy production activities. Also, with regards to forest restoration activities supportive of SPS, native species are typically grown in nurseries tended and managed by women.

- Statistics from the last agricultural census (2011) indicate that there are over 14,000 parcels dedicated to cattle ranching nationwide, of which 15.5% (over 2,000) are managed by women. In the Darien, however, women work mainly as employees on different aspects of ranching operations. Of the 198 cattle farms to be targeted by the project in the Filo del Tallo-Canglon Hydrological Reserve and its buffer zone in the Darien, the women on at least 20% of these farms will be specifically targeted to access project benefits and participate in the project’s activities in the field. Also, it is important to note that women play a significant role in the management of ranches and in the decision-making process related to their operations, even though they may not be ranch owners. It is therefore indispensable to include them in project activities regardless of their specific role. Women will therefore be invited to participate with their partners in the relevant activities proposed by the project. Women will also participate in the running of a local nurseries network which provides native seedlings to ranchers, following successful models implemented in the Panama Canal Watershed project mentioned in the baseline.

- In the context of training and capacity building programmes in the case of the Bank for Agricultural Development and the Ministry of Agriculture's personnel, both women and men will be involved in a balanced way, respecting the gender distribution that compose these organizations at each relevant level. The gender aspect will also be taken into account in the information and communication strategy of the project, by formulating messages specifically tailored to women and men independently, whenever relevant, and by taking into account gender aspects and the representation of both genders in all communication and information materials. In addition to the data and information available on gender distribution among cattle ranchers in Darien, a gender analysis will be carried out during project preparation to ensure that project design incorporates and recognizes the relevant differences between gender labor, knowledge, needs, priorities, and responsibilities at the productive farm level. The project will use the relevant core gender indicators for portfolio level monitoring and reporting purposes.

- In its efforts to fully integrate gender mainstreaming, the Project will be guided by the principles that gender elements are important drivers and incentives for achieving global environmental benefits, and in ensuring gender equity and social inclusion. The Project also embraces the fact that the needs, interest, and capabilities of women are habitually structurally different from those of men, in relation to the access, use, and management of biodiversity resources within project intervention areas, and thus, must be given special consideration in ensuring equal access to the resources and services of the Project.

- The Project will seek to institutionalize gender mainstreaming at all levels of intervention and operation of the project, through the development and implementation of a Gender Mainstreaming Action Plan, which will follow the Gender Analysis Approach, Guidelines and Procedures described in Section XIII of the Environmental and Social Safeguards for CAF/GEF Projects Manual, with particular attention to the potential roles, benefits, impacts and risks for women and men to ensure meaningful participation and the equitable distribution of benefits among women and men to be derived from project interventions. In consultation and with the participation of women at the levels of relevant government ministries and operational governance structures of the Project, special efforts will be made to ensure that gender equity concerns are voiced during project consultations at all levels, in all policy, program, administrative and financial activities and procedures of the project, thereby contributing to a profound organizational transformation in all entities directly involved in the Project; gender training for both men and women in all opportunities provided by the Project; increasing women’s access to opportunities for continued personal growth, increasing their leadership, and their capacity as agents of change in the communities in which they live.

- In order for the Gender Mainstreaming Action Plan to be most effective and have the intended impact on project implementation and results, this would have to be developed as an early priority at Project Inception, and specifically within the first 3 months of project implementation. Since early project planning would typically define major strategies and actions which would influence the life of the project, it will be crucial for gender involvement and mainstreaming be secured in the early planning stage to ensure maximum and meaningful gender participation from the onset. A Gender Mainstreaming Action Plan will be a mandatory project policy document to be consulted and followed in the definition, conceptualization and implementation of all project components and investments, and will form part of the required monitoring and evaluation of the project.

- Consistent with the need to ensure gender mainstreaming through-out the project, the Results Framework has been modified to indicate the specific number of women and men directly benefitting from the project, which is also consistent with GEF-7 Core Indicator 11. Compliance with the required outputs and standards of the Gender Mainstreaming Action Plan will be subject to independent external auditing to be explicitly referenced in the Project Operations Manual, in all Subsidiary Agreements between CAF and the project’s Executing Agency, and in the Terms of Reference for the Mid-Term Evaluation and the Terminal Evaluation of the project.

## G. Socio-Economic Benefits

- At the level of the individual farmer, Silvo-pastoral practices bring higher yields; at the community level, besides directly benefitting 198 cattle ranchers, the recovery of the farms that are located in critical areas of the sub-basins that originate in the Darien are vital because that area provides water to 55% of the population of the Darien. At the level of the livestock sector, they would gain in improving the image of the Darien cows that have been considered as not of such good quality, in addition that it would di-mitify the rancher in the Darien that is considered the predator of the forests. There are 158 men and 40 women associated with cattle ranching in the Darien who would benefit directly from project interventions at the farm management and enhanced revenue levels. In the case of women who do not own or manage a cattle farm, these will benefit directly from their engagement in project-sponsored nurseries that the farms have to establish in order to recover riverbank areas, sloping areas, mangas, fences, etc. Where farms are also engaged in other types of complementary crops, women could also engaged in those as part of a complementary conservation-oriented farm management plan.

## H.  Stakeholder Participation

- Stakeholders participated in the identification of project priorities and in the definition of planned outputs and outcomes during interviews and consultations. Project stakeholders had the opportunity to review and comment on proposed project activities and to provide specific inputs to the project formulation process. During project implementation, stakeholder participation will include the provision of co-financing, participation of technical staff in workshops, training, and tools development, the facilitation of local project events and processes, the provision of project oversight through participation on the PSC or TAC, as data sources, technical expertise and knowledge management through the institutionalization of project results and lessons learned to allow for up-scaling, replication, and sustainability.

- The inclusion and engagement of Civil Society Organizations (CSOs) and the public in the implementation of the project will be ensured via their direct participation in the governance and decision-making bodies of the project. Special effort will be made to ensure that CSOs active or present in the area of influence of the project are represented in project decision-making and in interventions which may affect their interests. In all instances, the standards and guidelines of the Environmental and Social Safeguards for CAF/GEF Projects Manual applies, including safeguards addressing indigenous peoples.

- It must be noted that, typically, cattle ranching farms in the Darien are not managed by indigenous communities on a substantive scale, as these are primarily dedicated to subsistence agriculture, handicraft production and small-scale tourism activities. Afro-Darienitas, are also rarely cattle ranchers as they are located in coastal areas and make their living from artisanal fishing. Cattle rearing activities in the Darien are mostly carried out by internal immigrants (colonos) coming from other cattle producing regions of the country and recently established in Darien in search for new lands and resources.

## Annex 1: Results Framework

Republic of Panama: Ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panama

| GEF-7 Core Indicator | Global Target | GEF-7 Sub-Indicator | Project Baseline | Mid-Term Target | End of Project Target | Means of Verification | Responsibility | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Area of landscapes under improved practices (hectares; excluding protected areas) | 320 million hectares | Area of landscapes under improved management to benefit biodiversity (qualitative assessment, non-certified) | 0 ha | 1,000 ha | 4,500 ha | Farm Management Plans (Planes de Gestion de Finca) Project Progress Reports Remote Sensing Data and or drones | Ministry of Environment Ministry of Agricultural Development ANCON | Project is able to work constructively with the Ministry of Environment, the Ministry of Agricultural Development, and cattle ranchers in the successful development and implementation of Farm Management Plans |
|  |  | Area of landscapes under sustainable land management in production systems | 0 ha | 1,000 ha | 5,000 ha | Farm Management Plans Remote sensing data and field reports with ground-truthing data Annual Cattle Production sector Reports | Ministry of Environment Ministry of Agricultural Development Ministry of Housing ANATI | ANAGAN or other productive associations and ANATI truly embrace the project’s objectives and champion necessary processes to achieve enhanced management in production systems |
| 11. Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | n/a but will be monitored | Number of women working on cattle ranches and benefitting directly from the project Number of men cattle ranchers working with women and benefitting directly from the project | 0 Women 0 Men | 15 Women 60 Men | 40 Women 158 Men | Annual Cattle Production sector Reports Project Progress Reports | Ministry of Environment Ministry of Agricultural Development and other institutions ANCON | Cultural differences do not interfere with the project’s attempts to treat women and men equally in terms of access to project support. |

| Project Development Objective: Establishment of an ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panamá. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PDO Level Results Indicators | Baseline & Unit of Measure | Mid-Term Target | End-of-Project Target | Means of Verification | Responsibility | Assumptions |
| Indicator 1: Sector policies and regulatory frameworks incorporate new considerations for the biodiversity of the Darien region. | 0 # of policies and/or regulatory instruments | 1 | 2 | Published or gazzetted polices, norms or decrees | Ministry of Environment Ministry of Agricultural Development Ministry of Housing ANATI | The project is able to provide sound technical, social and economic basis to garner private sector and political support. Relevant institutions provide support needed for the sector policies. |
| Indicator 2: Land area under effective management in production systems with improved vegetative cover (ha) in the Darien. | 0 Area in ha | 1,000 ha | 4,500 ha | Remote sensing data and/or drones and field reports with ground-truthing data Annual Cattle Production sector Reports | Ministry of Environment Ministry of Agricultural Development National Land Administration Authority/ANATI | ANAGAN or other productive associations and ANATI truly embrace the project’s objectives and champion necessary processes to achieve enhanced management in production systems |
| Indicator 3: Financial institutions applying conservation and sustainable use parameters into their lending portfolios. | 0 # of institutions | 1 | 1 | Copy of the financial institution’s procedural handbook for loans and credits Credit portfolio reports | Agricultural Development Bank/BDA ANCON Ministry of Environment Ministry of Agricultural Development | ANCON as project lead is able to engage and maintain the interest and enthusiasm of the BDA and ANAGAN in the pursuit of environmentally-friendly credit facilities. |

| Objectives, Outcomes and Outputs | Indicators | Baseline | Mid-Term Targets | End-of-Project Targets | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| INTERMEDIATE RESULTS |  |  |  |  |  |  |
| Intermediate Result (Component 1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains) |  |  |  |  |  |  |
| Outcome 1.1: Conservation oriented Silvo-Pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of a biodiversity conservation and land restoration landscape model. | # of farms implementing SPS in the Filo del Tallo-Canglon Hydrological Reserve and its buffer zone # of hectares restored to become connective corridors and degraded areas within the productive landscape and between PAs (ha) of the Darien | 0 0 ha | 50 farms 20 ha | 198 farms 85 ha | Project Progress Reports ANAGAN’s Annual Report Remote sensing data and maps Aerial Photography | The project is successful in advocating for ANAGAN to lead and champion SPS campaign with cattle ranchers. The project secures resources and prioritizes the acquisition of necessary data to confirm restoration. |
| Outcome 1.2: Cattle producer have the technical know-how and managerial skills for implementing conservation-oriented SPS within cattle farms and productive landscapes. | (x) % of cattle producers in the project area which receive technical training in SPS | 0 | 80 | 198 | Training Participants Lists Training Evaluation Reports | Training courses are attractive to secure interest of producers |
| Outcome 1.3: Technical government counterparts and extension agents are able to deliver timely quality support in the application, oversight, and replication of SPS. | (#) of extension agents providing technical support in the application of SPS in the Darien. | 0 | 15 | 40 | Extension Services Reports from the Ministry of Agricultural Development, ANAGAN and COPEG Project Progress Reports | Relevant institutions prioritize extension services and accountability through systematic reporting |
| Outcome 1.4: Cattle ranches in the Darien demonstrate the socio-economic and environmental benefits of SPS, including eco-labelling for SPS farm products. | (x) % of farms under SPS management which receive an SPS eco-labelling designation. | 0 | 10 | 30 | Project Progress reports Farm-specific reports | Cattle ranchers assertive embrace SPS eco-labelling and is open to information sharing |
| Outcome 1.5: Institutions and relevant stakeholders’ groups (i.e. producers, consumers, extension agents, policy-makers, sector representatives and land use planners) actively support the application, and replication of SPS in the Darien and nationwide. | (#) of relevant institutions and stakeholders actively supporting the application and replication of SPS | 2 | 3 | 5 | Public statements; website blogs, press releases, institutional policies | Relevant partners and stakeholders truly embrace SPS and champion its cause. |

COMPONENT 1 - OUTPUTS: For Outcome 1.1: Conservation oriented Silvo-pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of a biodiversity conservation and land restoration landscape model. 1.1.1: Conservation-oriented Farm Management Plans guide the application of Silvo-pastoral Systems and the sustainable use of resources within farm plots. 1.1.2: A connectivity and restoration strategy for the establishment of conjoining corridors and restoration activities between cattle farms, the productive landscape and protected areas. For Outcome 1.2: Cattle producer have the technical know-how and managerial skills for implementing conservation-oriented SPS within cattle farms and productive landscapes. 1.2.1: Training Programmes for cattle ranchers are developed by government counterparts and vocational skill training institutions for the long-term application of conservation-oriented silvo-pastoral systems. 1.2.2: “Rancher to rancher” SPS exchange programmes are organized to illustrate the benefits of SPS and facilitate their application under diverse farming scenarios and investment options. For Outcome 1.3: Technical government counterparts and extension agents are able to deliver timely quality support in the application, oversight, and replication of SPS. 1.3.1: Capacity building programmes for extension service providers in SPS are tested and delivered by government institutions and technical training institutes. For Outcome 1.4: Cattle ranches in the Darien demonstrate the socio-economic and environmental benefits of SPS, including eco-labelling for SPS farm products. 1.4.1: An SPS eco-labelling designation under a single SPS logo is registered with The National Certification Authority. 1.4.2: A training and entrepreneurial skill enhancement programme detailing production and marketing requirements for SPS eco-labelling is tested and available from public and private institutions. For Outcome 1.5: Institutions and relevant stakeholders’ groups (i.e. producers, consumers, extension agents, policy-makers, sector representatives and land use planners) actively support the application, and replication of SPS in the Darien and nationwide. 1.5.1: A communication and awareness raising strategy targeted for producers, consumers, and decision-makers is disseminated by various institutions highlighting the environmental, social and economic benefits of SPS.

| Objectives, Outcomes and Outputs | Indicators | Baseline | Mid-Term Targets | End-of-Project Targets | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Intermediate Result (Component 2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks). |  |  |  |  |  |  |
| Outcome 2.1: A consolidated and integrated Land Use Management Plan guides productive activity (cattle ranching), land use zoning and conservation efforts in the Darien. | Avoided deforestation of natural habitats in the productive landscape of the project area in ha. # of institutions (i.e. Ministry of Environment, Ministry of Agricultural Development, National Land Authority ANATI, etc.) which consult and abide by the land use categories detailed on the on-line GIS. (#) of agreements formalized among relevant Ministries for coordinating resources and staff for technical assistance, extension services, and enforcement. | 0 ha 0 0 | 1,000 ha 3 3 | 5,000 ha 3 3 | Remote sensing data and maps Aerial Photography Online Traffic Monitoring and confirmation with individual institutions Copies of resolutions regarding land use permits Copies of agreements either through hard copies, digital or posted on websites for public viewing | The project secures resources and prioritizes the acquisition of necessary data to confirm avoided deforestation. Relevant institutions are open to sharing resolutions and discuss decision-making process with project staff Relevant institutions are open to sharing copies of agreements Enforcement reports evidencing joint operations and coordination. |
| Outcome 2.2: Financial institutions support systemic changes in the appraisal of credits by incorporating conservation and sustainable use into their lending portfolios and mitigating the environmental, social and economic risks of their operations. | (#) of credits approved in which conservation and sustainability measures are incorporated | 0 | 50 | 100 | Credit Portfolio Reports | Agricultural Development Bank open to scrutiny of its reports. |

COMPONENT 2 - OUTPUTS: For Outcome 2.1: A consolidated and integrated Land Use Management Plan guides productive activity (cattle ranching), land use zoning and conservation efforts in the Darien. 2.1.1: A conservation oriented Land Use Management Plan and corresponding regulatory frameworks are prepared by relevant institutions for the Darien with local and national stakeholder participation 2.1.2 An online geographic information system for government officials, planners and resource users, provides updated information on land use categories, zoning and demarcation, as well as guidelines for productive activity in the Darien region 2.1.3: Inter-institutional Agreements and multi-sectoral partnerships are formalized at local and national levels to ensure institutional coordination, operational consistency and collective oversight in the implementation of designated land-uses. For Outcome 2.2: Financial institution support systemic changes in the appraisal of credits by incorporating conservation and sustainable use into their lending portfolios and mitigating the environmental, social and economic risks of their operations. 2.2.1: Environmental and social risks assessments and appraisal processes are implemented and guide credit approvals. 2.2.2: Training Programmes, knowledge management tools, and instructive manuals for risk assessment and appraisals are developed as part of corporate policy to actively mainstreaming conservation objectives into lending operations. 2.2.3: A national programme for exchanging experiences amongst banking institutions and disseminating best practices is implemented to further mainstream sustainable use and conservation measures into loan and credit programmes as part of the systemic adoption of risk management considerations in financing portfolios.

| Objectives, Outcomes and Outputs | Indicators | Baseline | Mid-Term Targets | End-of-Project Targets | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Intermediate Result (Component 3: Monitoring, evaluation and knowledge sharing) |  |  |  |  |  |  |
| Outcome 3.1: Project implementation follows a Results Based Management framework (RBM), applies SMART indicators for measuring progress and impact, and employs adaptive management principles to systematically re-incorporate monitoring and evaluation feedback into project performance. | Number of Work Plans prepared Number of Project Steering Committee meetings Number of Technical Advisory Committee Meetings Number of organizations involved in systemic implementation of Knowledge Management Strategy Ratings and % of project implementation obtained in Project Implementation Reviews (PIRs) and external evaluations | 0 0 0 0 0% completion | 2 4 8 3 The results of the mid-term evaluation are favourable, showing at least 40% of project activities completed or on schedule | 4 8 16 6 The Terminal Evaluation shows the project obtained favourable results; with 80% of activities completed | Work Plans posted on Project Website. Project reports reflect priorities as agreed in Work Plans, and % implementation achieved Project progress reports reflect recommendations of TAC M&E Plan of the KM strategy indicates specific names of agencies targeted and involved. PIR Reports Mid-Term and Terminal Evaluation Reports | ANCON exercises assertive leadership in project delivery. National agencies, beneficiaries, and relevant stakeholders take an interest in promoting collaboration, and participate in the exchange of lessons learned and experiences |

COMPONENT 3 - OUTPUTS: For Outcome 3.1: Project implementation follows a Results Based Management framework (RBM), applies SMART indicators for measuring progress and impact, and employs adaptive management principles to systematically re-incorporate monitoring and evaluation feedback into project performance. 3.1.1: A Project Monitoring and Evaluation Strategy is developed, including annual work-plans, progress and impact indicators, annual budget allocations, and independent evaluation requirements. 3.1.2: Baselines for biological indicators (BD and LD) at the farm and productive landscape level are available for the project intervention area. 3.1.3: A monitoring plan is developed to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation 3.1.4: A project website provides updated information on project progress, measureable results, lessons learned, including links to the Ministerial websites, the on-line GIS, and blogs pertaining to SPS issues, ranching, conservation, and sustainable resource use topics, etc.

## Annex 2: Detailed Project Description

Republic of Panama: Ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panama.

A. Proposed Development Objective

- It has been recognized in Panama that cattle ranchers continue to use and rely on traditional practices and methods for cattle production, while extension services and technical support remain conventional, outdated and scarce. Cattle rancher associations and networks are disorganized and weak, minimizing the potential socio-economic benefits a collective approach within this productive sector could generate. Awareness of the multiple benefits associated with eco-friendly silvo-pastoral systems within a sustainable land management framework is limited among producers and consumers alike, and land use planning and regulatory frameworks in the Darien are inadequate and do not incorporate conservation objectives at the wider landscape level. Government institutions (Economy & Finance, Agriculture, Environment) and their respective technical departments are neither sufficiently coordinated nor trained to address the challenges facing the Darien nor able to provide the required support for implementing sustainable productive options. Financial resources (credits/loans) are not complemented by the technical assistance, nor extension support required for the adoption of on-farm reforms in the cattle sector’s productive systems. Cattle farmers in the Darien do not have the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles, and commercial banks and other financing institutions have not incorporated sustainability considerations, nor social and environmental risk management assessments in their lending operations and sectoral portfolios.

- Sustainable modernization of the sector is necessary in which sustainable production, conservation priorities, ecological integrity and the preservation of key environmental assets are integrated into decision-making, policy formulation, and sectoral development objectives.

- The Project Development Objective is the establishment of an ecosystem based biodiversity-friendly cattle production framework for the Darien Region of Panamá. Specifically, the project seeks to ensure that conservation oriented Silvo-pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of biodiversity conservation and land restoration landscape model, while supporting cattle producers to obtain the technical know-how and managerial skills for implementing conservation-oriented SPS within cattle farms and productive landscapes.

B. Project Components & Outcomes

Component 1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains (LD: US$1,518,715; plus BD: US$425,095; total: US$1,945,810).

Outcome 1.1: Conservation-oriented Silvo-pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of a biodiversity conservation and land restoration landscape model.

- Output 1.1.1: Conservation-oriented Farm Management Plans guide the application of silvo-pastoral systems (SPS) and the sustainable use of resources within farm plots. Farm Plans/“Planes de Finca” will include a menu of silvo-pastoral practices designed to ensure conservation-oriented production but also sustainable farm diversification. Silvo-pastoral practices will be consistent with the characteristics of the farms in question and include grazing management options in accordance to herd size, defining the percentage of forest cover remaining on the farm and determining viable and potential increases, identifying connectivity options, detecting restoration needs for degraded pastures and/or riparian forests, etc. Farm plans will include an assessment of inputs, corresponding costs, and estimated time-frames for the establishment of conservation-oriented SPS, along with related technical assistance requirements. SPS at the farm level will form part of a larger landscape improvement model (detailed in component 2) designed to maintain critical ecosystem services and functions, establish sustainable land management principles, and increase farm productivity whilst generating measurable environmental and socio-economic benefits for local producers. In this regard, Conservation-oriented Farm Management Plans will be informed based on granulometric, physical and chemical analyses to be conducted of soils within the Darien that will further inform soil management requirements and ultimately species suitability for SPS.  Additionally, these Conservation-oriented Farm Management Plans also must be guided by research on the economics of conversion to SPS (beyond just the cost of conversion), based on economic scenarios to be developed for select sites in the Darien in the first year of project implementation.

- Output 1.1.2: A connectivity and restoration strategy for the establishment of conjoining corridors and restoration activities between cattle farms, the productive landscape and protected areas.  The definition of corridors and land restoration activities will be conducted as part of farm management plans but also at the wider landscape level as part of the proposed integrated land use management plan for the Darien described in Component 2.

Outcome 1.2: Cattle producers have the technical know-how and managerial skills for implementing biodiversity conservation-oriented SPS within cattle farms and productive landscapes.

- Output 1.2.1: Training Programme for cattle ranchers are developed by government counterparts and vocational skills training institutions for the long-term application of conservation-oriented silvo-pastoral systems. Capacity needs assessments will be conducted with local producers and cattle associations at local and national levels to ensure that training programmes are tailored to the current challenges and opportunities of the Darien, meet the diversity of stakeholder needs, and are consistent with the preferred mechanisms for their delivery. Cattle ranchers’ support requirements will in turn inform the Ministry of Agricultural Development’s training programme for extension service providers as part of the GoP’s strategy to improve the efficiency of government institutions in fulfilling their mandates and extension’s responsibilities at local and national levels. Training and extension services in SPS for sustainable cattle production will be integrated in the Ministry’s extension programmes and continue beyond the life of the project, as a key sustainability element.

- Output 1.2.2: “Rancher to rancher” SPS exchange programmes are organized to illustrate the benefits of SPS and facilitate their application under diverse farming scenarios and investment options. These will include cattle ranchers from the Darien but also those from other regions of the country successfully implementing SPS within their farms. In addition to promoting and exemplifying the on-farm and landscape benefits of these practices, these direct exchanges will also serve a critical role in: (i) consolidating producers’ associations and local networks, and (ii) establishing and consolidating these “rancher to rancher” exchange mechanisms and offering proof of evidence regarding the benefits resulting from SPS practices. The National Association of Cattle Ranchers (ANAGAN) will be an indispensable partner in organizing, promoting and endorsing these exchanges, further leveraging their credibility and effectiveness in promoting the necessary productive paradigm shifts. These exchanges will also explore visits to model silvo-pastoral farms, (notably in Colombia and Costa Rica) following a practice which ANAGAN has begun to promote in recent months, and may also include visits to pilot farms in Panama.

Outcome 1.3: Technical government counterparts and extension agents are able to deliver timely quality support in the application, oversight and replication of SPS.

- Output 1.3.1: Capacity Building Programmes for extension service providers in SPS are tested and delivered by government institutions and technical training institutes. As part of a larger national GoP effort to modernize its agricultural sector and incorporate within its productive activities sustainability and conservation considerations, technical staff and extension service providers will receive the training and practical tools to deliver the knowledge and skills required for the application of conservation-oriented SPS techniques at the field level. Productive activity (i.e. cattle ranching) in areas of recognized high biodiversity and ecosystem value will be prioritized. The capacity building plan for technical staff will reflect the needs expressed by producer groups to meet the challenges and opportunities inherent in the application of conservation SPS in biodiversity rich ecosystems.

Outcome 1.4:  Cattle ranches in the Darien demonstrate the socio-economic and environmental benefits of SPS including eco-labelling for SPS farm products.

- Output 1.4.1: An SPS eco-labelling designation under a single logo is registered with the National Certification Authority. An Eco-labelling Suitability & Readiness Assessment will be conducted in PY1 for goods produced in farms applying SPS in the Darien, through a participatory scientifically robust methodology. The results of this readiness assessment will inform the baseline indicators and targets to be delivered (number of farms with required level of readiness and number of goods meeting a readiness criteria for eco-labelling) as a consequence of project interventions. This process will be cognizant of the fact that barriers which previously discouraged farmers from engaging in certified ventures are now being pro-actively addressed as part of the project’s baseline. Developments at the national level which bode well for eco-labelling initiatives, include: (i) growth of national demand for certified organic produce; (ii) private sector and supermarket chains expressing interest in supplying these products; (iii) new legislation detailing consumers and producers alike what eco-labelling and certification processes entails; (iv) a National Certification Authority facilitating user-friendly information and support to producers engaging in eco-labelling ventures; (v) available capital for producers willing to engage in eco-based production alternatives; (vi) established traceability procedures for meat, developed and implemented by the Ministry of Agricultural Development (a critical tool for labelling); and most importantly (vii) a growing body of technical expertise available to guide producers.

- Output 1.4.2: A training and entrepreneurial skill enhancement programme detailing production and marketing requirements for SPS eco-labelling is tested and available from public and private institutions. This will include guidance, coaching and instruction in the technical, legal, informational, and marketing requirements associated with goods produced in conservation oriented SPS farms.

Outcome 1.5: Institutions and relevant stakeholders’ groups, (i.e. producers, consumers, extension agents, policy-makers, sector representatives and land use planners) actively support the application and replication of SPS in the Darien and nationwide.

- Output 1.5.1: A communication and awareness raising strategy targeted for producers, consumers, policy and decision-makers is disseminated by various institutions highlighting the environmental, social and economic benefits of SPS. The strategy will promote and encourage replication potential, assist in catalyzing systemic change, and inform audiences of progress achieved regarding these experiences at local and national levels. Similarly to capacity building efforts, communication and awareness raising activities will need to be tailored to intended recipients and delivered in the effective and most appropriate manner, i.e. radio, newsletters, television, websites, etc. based on the preference and receptiveness of the intended beneficiaries and the target audience in question. Communication strategies will operate at local, regional, and national levels and include a variety of means such as testimonies, presentation of experiences, interviews, thematic discussions, workshops, all related to different aspects of sustainable cattle production, SPS, land use management, conservation in productive landscapes, efficient resource use, etc. Awareness raising activities, while touching on similar issues and targeting similar stakeholder groups at local, regional and national levels, will cover a wider audience and frame conservation and sustainability issues in a development policy context, but with the same goal of fostering and promoting wide scale support, adoption and replication.

Component 2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks (BD: 1,145,810; LD: 54,190; total US$1,200,000).

Outcome 2.1: A consolidated and integrated sustainable land use management plan guides productive activity (cattle ranching), land use zoning, and conservation efforts in the Darien.

- Output 2.1.1: A conservation oriented Land Use Management Plan and corresponding regulatory frameworks are prepared by relevant institutions for the Darien with local and national stakeholder participation. Presently, a network of nine protected areas of different management categories covers over 46% of the Darien region. With few exceptions these conservation efforts have not included considerations pertaining to connectivity, optimal size, or other ecological parameters resulting in scattered non-protected lands void of the management required for their sustainable use, the productive suitability of their soils, the integrity of the ecosystems they conform, or the maintenance of the vital environmental services they provide. Considering the growing development pressures affecting the region, it is imperative to consolidate and establish an integrated region-wide land use plan able to: (i) acknowledge the Darien's unique biodiversity status and its implications for productive activities;(ii) incorporate and revitalize its existing PA network and indigenous Comarcas as interdependent functional systems; and (iii) ensure that the intervening landscape is managed in a cohesive integral manner consistent with the region's fragility, sustainability objectives, and current productive trends. Essentially, a sustainable land-use management plan that would illustrate the possible co-existence of conservation and sustainable development objectives in a globally significant biodiversity area.

- Output 2.1.2: An online geographic information system for government officials, planners and resource users, provides updated information on land use categories (including protected areas) zoning and demarcation, as well as new guidelines and regulations, for land use, productive activity and conservation in the Darien region.  An updated region-wide land use plan, detailing a multi-functional landscape comprised of protected areas, buffer zones, and multiple use areas of varying categories and degrees of conservation and productive uses will be reflected in a GIS tool accessible on-line to all relevant institutions and stakeholder groups. Productive activities will rely on this guiding framework, as will the development plans and strategies of institutions entrusted with resource use, regional development, planning, zoning and enforcement. This GIS will reflect a participatory process with regards to its content, and serve as a transparent and widely accessible instrument making its users the real custodians of its objectives and sustainable conservation goals. The project will provide training to key institutions relevant to the Darien in the use of the GIS tool.

- Output 2.1.3: Inter-institutional Agreements and multi-sectoral partnerships are formalized at local and national levels to ensure institutional coordination, operational consistency and collective oversight in the implementation of designated land-uses. Commitments at the ministerial level with the Ministry of Agricultural Development and the Ministry of Environment have confirmed the disposition, viability and expressed necessity both institutions view as imperative to establish a new conservation-oriented development paradigm in the Darien. Past experience has shown that without the required institutional alignment and collaborative arrangements it will be impossible to generate the systemic changes and economies of scale (in terms of training, capacity building, monitoring, regulatory oversight) needed to effectively implement the proposed conservation oriented land use management plan.

Outcome 2.2: Financial institution support systemic changes in the appraisal of credits by incorporating conservation and sustainable use into their lending portfolios and mitigating the environmental, social and economic risks of their operations.

- Output 2.2.1: Environmental and social risks assessments and appraisal processes are implemented and guide credit approvals. Consistent with larger programmatic and corporate objectives, the lead national bank for agricultural development is mainstreaming sustainable use and conservation objectives into its lending operations and development portfolios. This entails the applications of new tools, considerations and appraisal processes in the assessment of credit requests and their subsequent approvals on the basis of potential socio-economic and environmental implications.

- Output 2.2.2: Training Programmes, knowledge management tools, and instructive manuals for risk assessment and appraisals are developed as part of corporate policy to actively mainstreaming conservation objectives into lending operations. To this end, targeted technical training programmes will be developed for all banking personnel responsible for agricultural credit programmes including the cattle sector.

- Output 2.2.3: A national programme for exchanging experiences amongst banking institutions and disseminating best practices is implemented to further mainstream sustainable use and conservation measures into loan and credit programmes as part of the systemic adoption of risk management considerations in financing portfolios. The national programme intends to further mainstream sustainable use and conservation measures into loan and credit programmes of other banking institutions (national and regional) as part of the systemic adoption of risk management considerations into financing portfolios.

Component 3: Monitoring, evaluation and knowledge sharing (BD: US$103,155 plus LD: US$103,154, total US$206,309).

Outcome 3.1: Project implementation follows a Results Based Management framework (RBM), applies SMART indicators for measuring progress and impact, and employs adaptive management principles to systematically re-incorporate monitoring and evaluation feedback into project performance.

- Output 3.1.1: A Project Monitoring and Evaluation Strategy is developed, including annual work-plans, measurable and verifiable progress and impact indicators, annual budget allocations, and independent evaluation requirements. The preparation of work-plans and the corresponding definition of SMART indicators for each project component will occur annually along with associated budgetary requirements. Project preparation will follow the GEF's Monitoring and Evaluation policy which provides norms and standards for GEF funded projects.

- Output 3.1.2: Baselines for biological indicators at the landscape level are available for the project intervention area (selected farms and adjacent landscapes), including the tools and methodologies for assessing BD and LD impacts over time. This information will be revised during forthcoming preparation work (PPG). Since an exhaustive inventory of biological indicators cannot be realistically compiled, a representative selection will need to be identified as the best means to assess progress and the sustainable impact of the proposed interventions on biodiversity status and ecosystem services. The project will use drone technology in complement to high-resolution satellite imagery to support field observations and to monitor expected changes at both the farm and productive landscape level (as part of the project’s M&E strategy and at different intervals of project implementation). The use of drones will prove to be an innovative and cost-saving measure, at the farm level but also in effectively and accurately monitoring project progress with regards to intended conservation goals in the broader productive landscape. Monitoring results will inform any required changes or modifications in the project’s components and overall implementation strategy.

- Output 3.1.3: A monitoring plan is developed to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation. Following GEF-STAP guidance and recommendations on certification and eco-labelling, practical mechanisms will be identified to determine -  to the extent possible - the causal links and benefits of eco-labelling on: (i) biodiversity conservation objectives; (ii) maintaining producers’ commitment to eco-labelling; and (iii) the additional socio-economic benefits this activity confers to producers’ livelihoods and conservation-oriented SPS in general. Despite the amount of eco-labelling or certification programs in the region, according to the aforementioned GEF/STAP analysis, few have been able to measure the environmental and/or socio-economic impacts of these activities.

- Output 3.1.4: A project website provides updated information on project progress, measureable results, lessons learned, including links to the Ministerial websites, the on-line GIS, and blogs pertaining to SPS issues, ranching, conservation, and sustainable resource use topics, etc. Notwithstanding the knowledge management tools specific to activities in Component 2 mentioned above, a Knowledge Management Strategy will be developed within the first semester of project implementation to ensure systemic documentation and uptake of results, experiences and lessons learnt is realized through-out project implementation, and not just as a consequence of periodic monitoring of time-bound project milestones. The development of this strategy will be guided by globally accepted elements affecting the successful implementation of Knowledge Management Systems: adoption, acceptance and assimilation. The institutionalization of knowledge management initiatives and processes developed by the project will be a specific objective of the Knowledge Management Strategy, and will be a critical element for the sustained storage, access and dissemination of project results and outcomes beyond the life of the project.

## Annex 3: Implementation Arrangements

Republic of Panama: Ecosystem-based biodiversity friendly cattle production framework for the Darien Region of Panama.

Project Administration and Implementation Arrangements

- Project execution and coordination among the variety of actors of the project will be lead by ANCON (the National Association for the Conservation of Nature) a non-profit, non-governmental organization founded in Panama in 1985 with the mission of conserving Panama’s biodiversity and natural resources for the benefit of present and future generations.

- A Project Coordinating Unit (PCU) will be established by ANCON to oversee day-today project execution. The PCU is responsible for the fiduciary oversight and reporting of the project, including financial management and procurement consolidation according to the projects operational manual and procurement plan. It is also responsible for monitoring and evaluation (M&E), provides and coordinates technical advice, and coordinates and assists overall orientation concerning project conception, strategies, criteria and methodologies, as well as organizes and supports regional activities. The PCU will be staffed with A Project Coordinator, a Sustainable Agriculture Specialist, an Accountant, and an Administrative Assistant. Financial management and procurement services will be provided by ANCON, and technical delivery of project outputs will be complemented by specialist consultants on an as needed basis.

- Two key governing bodies will be established for the project: a Project Steering Committee (PSC) and a Technical Advisory Committee (TAC). In practical terms the PSC is responsible for ensuring that the project meets goals announced in the Project Result Framework by helping to balance conflicting priorities and resources.  Conclusions and recommendations produced by the PSC will be used by ANCON to modify implementation strategies, annual work plans and resources allocation budget and, when necessary, to adjust the project’s Result Framework. This committee will meet every six months, either physically or virtually. The composition of the PSC will be defined in the Project Operations Manual (POM). The specific roles and responsibilities of the Project steering Committee are as follows:

- Provide input into planning and coordination of the project

- Review and approve the Project Operational Manual in consultation with ANCON and CAF; as well as approving subsequent changes and amendments to be introduced to the POM upon prior approval by ANCON and CAF;

- Review and approve Annual Operational Plans, Procurement Plans, quarterly and semi-annual reports. The PSC is the authority that signs off on the completion of each quarterly plan and authorizes the start of the next quarterly plan.

- Review quarterly or other periodic and/or exceptional reports submitted by the Project Coordinator or ANCON on project status, activities performed, annual budget execution, the project’s financial situation, and/or other topics as may be requested;

- Review the progress of the project and ensure activities are in line with approved annual operational plan and budget;

- Ensures that required resources are committed and arbitrates any conflicts within the project or negotiates a solution to any problems between the project and external entities

- Promote partnerships with relevant Government Ministries/agencies/departments for preparation, monitoring and execution of the project; and

- Facilitate the coordination of project financed activities with other related investments in Panama where applicable;

- Ensure accountability by making decisions in accordance with standards that ensure management brings about development results, best value for the money, fairness, integrity, transparency, and effective international competition.

- The Technical Advisory Committee (TAC) is to provide technical oversight, guidance and support during project implementation. The TAC is also responsible for reviewing and providing recommendations on project processes (operational guidelines) and activities to the Project Steering Committee (PSC) for their review and endorsement. The TAC will meet at least quarterly. The composition of the TAC will be defined in the Project Operations Manual. The specific roles and responsibilities of the Project steering Committee are as follows:

- Review and make recommendations to the PSC on matters related to the Annual Operational Plans, Procurement Plan, Annual Reports and Project Progress Reports;

- Ensure that project activities adhere to the Annual Operating Plan, the POM and CAF Social & Environmental Safeguards, and those of the Government of Panama;

- Review progress reports to ensure that the project is being implemented according to the Annual Work Plan;

- Participate in key meetings, workshops, consultations, trainings and other related activities as required;

- Provide technical oversight and advice to the PCU (virtually or in person);

- Make at least one visit to the project´s site to evaluate the project and be able to provide solutions to problems encountered by the PCU.

- Ensure accountability by making decisions in accordance with standards that ensure management brings about development results, best value for the money, fairness, integrity, transparency, and effective international competition.

- The Project Steering Committee will be chaired by the Ministry of Environment, with the Ministry of Agricultural Development serving as Vice-Chair and the BDA as Deputy Vice Chair. The Technical Advisory Committee will be chaired by ANCON, with the National Cattle Ranchers Association (ANAGAN) serving as Vice-Chair. In all instances, the PSC and the TAC will do all that may be necessary to ensure expediency in project processes, and will consider virtual meetings as a valid and legitimate form of meeting, but with at least one physical meeting per year in the case of the PSC, and at least two meetings per year in the case of the TAC. The institutional structure for project implementation is provided below.

Institutional Structure of the Project

Financial Management

- All activities related to financial management will follow the Financial Procedures Agreement (inclusive of all annexes) between the Development Bank of Latin America (CAF) and the International Bank for Reconstruction and Development (IBRD) as Trustee of the Global Environmental Facility Trust Fund (GEFTF), signed on September 28th, 2015. This agreement contains provisions for project operations to meet and exceed all internationally-accepted financial and fiduciary management standards, to be evidenced in annual, final independent audits, and other periodic audits of the project accounts, as may be necessary. Staff of the project’s executing agency that are involved in the day-to-day management of project resources will be trained in financial management policies consistent with the provisions of the above-mentioned agreement, during and after the Project’s Inception.

- Specifically, the project will implement an adequate integrated financial management system for the Project, including internal control systems that: (i) are in accordance with international accounting standards; (ii) reliably record and report all assets, liabilities and financial transactions of the Project; (iii) provide sufficient financial information for managing and monitoring Project activities; and (iv) integrate financial information, disbursements, purchasing, physical and financial progress of Project indicators, procurement, and control of contracts, to allow the generation of quarterly programmatic financial reports on the financial and physical advance of each component, as well as financial information by disbursement category. The detail of these procedures will be contained in the Project Operations Manual.

Disbursements

- Disbursements will be made against Project Annual Work Plans (AWP) approved by the Project Steering Committee and CAF. Disbursement shall be in accordance with guidelines defined in CAF Disbursement Policies. Statement of Expenses (SOE) documentation will be maintained by the PCU for post-review and audit purposes. The authorized transfers to ANCON for project expenditures will be set at a level sufficient to cover approximately six months of estimated expenditures eligible for financing as per the approved Annual Work Plan. Replenishments of funds will be made on evidence of satisfactory utilization of the previous advance(s) as evidenced by the documentation submitted in support of disbursement applications. Deposits into the ANCON project account and its replenishments, up to an amount of 6 months of eligible project needs, will be made on the basis of Applications for Withdrawals accompanied by the supporting and other documentation specified in the CAF Disbursement Policies.

- The Project funds will be transferred to ANCON by CAF, where funds will be maintained in a project-specific account in US Dollars, in a local bank in Panama City, Panama. The PCU will be responsible for submitting to CAF, appropriate disbursement applications to request the disbursement of funds. Replenishments of funds under SOEs will be made on evidence of satisfactory utilization of the previous advance(s) as evidenced by the documentation submitted in support of disbursement applications.

Procurement

- All activities related to procurement will follow the Procurement Policies of CAF as defined in the Procurement and Contracting of Goods, Services and Works Manual, published on March 17th, 2015 by the Directorate of Physical Infrastructure, Logistics, and Administration, Version MN/DIOFLA 038 of February 2016. These policies contain provisions for operations to meet and exceed all internationally-accepted financial and fiduciary management standards, to be evidenced in annual and final independent audits of the project’s procurement and disbursement processes. Staff of the project’s executing agency that are involved in the day-to-day management of project resources will be trained in CAF’s procurement policies as described above and in procurement planning during and after the Project’s Inception.

Environmental and Social (including safeguards)

- The implementation of project activities will be in accordance with the Environmental and Social Safeguards for CAF/GEF Projects Manual, Version 1 of May 2015. The Project is classified as Category B, according to the Guidelines and Procedures on Environmental and Social Safeguards for CAF/GEF Projects Manual (Section V.I.2 Annex I). Project interventions are not expected to cause major adverse environmental impacts, and instead, in many cases will improve the environmental and social conditions prevailing in the areas of intervention, including greater resilience capabilities to deal with extreme events, impacts of climate variability and climate change. Minor site-specific environmental impacts in natural habitats and forests may be expected from some on-the-ground interventions, but mostly temporary.

Monitoring and Evaluation

- The project will follow CAF standard monitoring, reporting and evaluation processes and procedures. Reporting requirements and templates will be provided by CAF and will be an integral part of the legal instrument to be signed by the executing agency and CAF. The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Annex 1 includes SMART indicators and means of verification for each expected outcome. These indicators will be the main tools for assessing project implementation progress and whether project expected results are being achieved. A costed project M&E Plan is presented in Annex 6.

- An inception workshop will be held at the onset of project implementation to ensure all actors understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Indicators and their means of verification may be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of ANCON and the project management team. It is the responsibility of ANCON to inform CAF of any delays or difficulties faced during project implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

- The PSC will issue reports every 6 months on progress by the project and make recommendations concerning the need to revise any aspects of the Project Results Framework, or the M&E plan. Supervision to ensure that the project meets CAF and GEF policies and procedures is the responsibility to the CAF-GEF Task Manager. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of project outputs in close collaboration with ANCON.

- ANCON will develop an initial supervision plan that will be communicated to the project partners during the inception workshop for comments.  The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring.  Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed by CAF. Project risks and assumptions will be regularly monitored both by the PSC and CAF. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

- A Mid-Term Evaluation will be conducted at the mid-point in the project. An independent consultant will be hired to conduct this evaluation. ANCON will manage the mid-term evaluation (MTE) process, under close supervision of CAF. The MTE will address evaluation parameters recommended by the GEF Evaluation Office and will verify information gathered through the GEF tracking tools, as relevant. The PSC will participate in the mid-term evaluation and will support ANCON in the development of a management response to the evaluation recommendations along with an implementation plan. It is the responsibility of the CAF-GEF Task Manager to monitor whether the agreed recommendations are being implemented.

- An Independent Terminal Evaluation will take place within the last semester of project implementation. CAF will manage the terminal evaluation process. A review of the quality of the evaluation report will be done by CAF and submitted along with the report to the GEF Evaluation Office not later than 6 months after the completion of the evaluation.

Stakeholder Participation

- Stakeholders participated in the identification of project priorities and in the definition of planned outputs and outcomes during interviews and consultations. Project stakeholders had the opportunity to review and comment on proposed project activities and to provide specific inputs to the project formulation process. During project implementation, stakeholder participation will include the provision of co-financing, participation of technical staff in workshops, training, and tools development, the facilitation of local project events and processes, the provision of project oversight through participation on the PSC or TAC, as data sources, technical expertise and knowledge management through the institutionalization of project results and lessons learned to allow for up-scaling, replication, and sustainability.

- ANCON will continue to work in close and direct coordination with CAF, the Ministry of Agriculture, the Bank for Agricultural Development, the Ministry of Environment, and ANAGAN (the National Cattle Ranchers Association - Asociación Nacional de Ganaderos) as well as other relevant entities and local stakeholder groups. It is important to note that ANAGAN, a critical partner is the national cattle ranchers’ association and a key ally of the project and its objectives. ANAGAN's credibility, representativeness and convening power with its cattle ranchers’ constituents has been very useful during the conceptual stage of project design and will continue to be an important partner during project implementation. Operationally, ANAGAN's support, feedback and permanent guidance will be secured via their on-going participation and consultative meetings. ANAGAN's priority objectives, as recently presented and confirmed in their "Strategic Environmental Plan for 2016-2021", are fully consistent and aligned with those of the project. Local producers’ associations and organizations will be actively involved in project activities either through their representation in ANAGAN or on an individual basis. COPEG ( Comision Panama – Estados Unidos para la Erradicacion y Prevencion del Gusano Barrenador del Ganado) will also be an important player and partner to the project, especially in the provision of support in extension services and an ’on-the-ground’ promotor of the project’s objectives.

- The inclusion and engagement of Civil Society Organizations (CSOs) and the public in the implementation of the project will be ensured via their direct participation in the governance and decision-making bodies of the project. Special effort will be made to ensure that CSOs active or present in the area of influence of the project are represented in project decision-making and in interventions which may affect their interests. In all instances, the standards and guidelines of the Environmental and Social Safeguards for CAF/GEF Projects Manual applies, including safeguards addressing indigenous peoples.

- It must be noted that, typically, cattle ranching farms in the Darien are not managed by indigenous communities as these are primarily dedicated to subsistence agriculture, handicraft production and small-scale tourism activities. Afro-Darienitas, are also rarely cattle ranchers as they are located in coastal areas and make their living from artisanal fishing. Cattle rearing activities in the Darien are mostly carried out by internal immigrant (colonos) coming from other cattle producing regions of the country and recently established in Darien in search for new lands and resources.

## Annex 4: Incremental Cost Analysis Matrix

| BASELINE | ALTERNATIVE | INCREMENT |
| --- | --- | --- |
| (A) | (B) | (B) – (A) |
| COMPONENT 1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains. |  |  |
| Component Result: Conservation oriented Silvo-pastoral Systems are adopted in cattle farms and the productive landscape of the Darien, with cattle producers having the technical know-how and managerial skills for implementing conservation-oriented SPS, and government counterparts and extension agents are able to deliver timely quality support in SPS implementation. The socio-economic and environmental benefits of SPS demonstrated, with active support for SPS implementation in the Darien and nationwide from institutions and relevant stakeholders. |  |  |
| Outcome 1.1: The concepts of integrated resource management and the application of silvo-pastoral systems (SPS) remain unfamiliar to Darien’s cattle producers. The sustainable intensification of existing farm-lands and the application of alternative production practices, including crop rotation, crop diversification, water-saving techniques, and the application of conservation-oriented SPS, among others, are neither practiced, promoted nor sufficiently understood. | GEF resources will specifically support the development of Conservation-oriented Farm Management Plans, to be informed based on granulometric, physical and chemical analyses to be conducted of soils within the Darien that will further inform soil management requirements and species suitability for SPS, as well as a connectivity and restoration strategy for the establishment of conjoining corridors. | Required technical and scientific due diligence lead to the development of Conservation-oriented Farm Management Plans, a restoration and connectivity strategy, the development of training programmes and tools, the establishment of a single-logo eco-labelling program and marketing requirements, communication and awareness strategy results in active support for SPS implementation in the Darien and nationwide from institutions and relevant stakeholders. |
| Outcome 1.2: The socio-economic and ecological benefits of sustainable cattle ranching - through the application of conservation-based practices within a sustainable integrated land use management model - remains elusive at local and national levels; and the socio-economic costs and ramifications of engaging in "business as usual ranching" along with the environmental degradation it entails have not been internalized, costed, nor fully understood by producers and consumers alike. | The GEF will fund capacity needs assessments, and develop and implement training programme for cattle ranchers by government counterparts and vocational skills training institutions for the long-term application of conservation-oriented silvo-pastoral systems. |  |
| Outcome 1.3: Extension services and technical support to cattle ranchers are limited and are not readily available in the quantity, quality or frequency required, to ensure a true transition to SPS systems and other forms of sustainable cattle production. | The GEF alternative will develop training manuals and practical tools to deliver the knowledge and skills required for the application of conservation-oriented SPS techniques at the field level, to be delivered by government institutions and technical training institutes. |  |
| Outcome 1.4: Cattle production in the Darien and all the associated products are currently not conducted according to any sustainable certification standards, thus the production practices invariably contribute to deforestation and land and soil degradation. Cattle ranchers are therefore are not trained in production techniques required for eco-labelling and/or how to access markets for eco-labelled produce, | GEF resources will fund an Eco-labelling Suitability & Readiness Assessment for goods produced in farms applying SPS in the Darien, through a participatory scientifically robust methodology, in support of implementing an SPS eco-labelling designation under a single logo; as well as a training and entrepreneurial skill enhancement programme detailing production and marketing requirements for SPS eco-labelling to be available from public and private institutions. |  |
| Outcome 1.5 There is no structured public awareness mechanism in place which targets cattle ranchers and associated communities in the Darien, on the environmental, social and economic benefits of SPS, or on the individual responsibilities of ranchers and opportunities available from sustainable conducting cattle ranching. | The GEF alternative will fund the development and implementation of a communication and awareness raising strategy targeting producers, consumers, policy and decision-makers is, to be disseminated by various institutions highlighting the environmental, social and economic benefits of SPS. |  |
| COMPONENT 2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, financial mechanisms, and policy and regulatory frameworks. |  |  |
| Component Result: A consolidated and integrated Land Use Management Plan developed and being implemented to guide productive activity, and in particular cattle ranching, land use zoning and conservation efforts in the Darien; and systemic changes in the appraisal of credits are implemented by incorporating conservation and sustainable use into lending portfolios to mitigate the environmental, social and economic risks. |  |  |
| Outcome 2.1: The Darien does not have a cohesive land use plan which integrates conservation, ecosystem services, and sustainable resource use objectives. Existing plans almost exclusively focus on protected areas with no consideration to the wider multi-functional landscape in which these reside. Coordination among relevant institutions at both the public and private levels are sub-optimal, resulting in lost opportunities for collective oversight and support for sustainable land use practices. | The GEF will fund the development of a conservation oriented Land Use Management Plan and corresponding regulatory frameworks; as well as an online geographic information system for government officials, planners and resource users, to provide updated information on land use categories (including protected areas) zoning and demarcation, as well as new guidelines and regulations, for land use, productive activity and conservation in the Darien region. The GEF resources will also be used for the development and formalization of Inter-institutional Agreements and multi-sectoral partnerships at local and national levels to ensure institutional coordination, operational consistency and collective oversight in the implementation of designated land-uses. | A consolidated and integrated Land Use Management Plan developed and being implemented to guide productive activity, and in particular cattle ranching, land use zoning and conservation efforts in the Darien; and systemic changes in the appraisal of credits are implemented by incorporating conservation and sustainable use into lending portfolios to mitigate the environmental, social and economic risks. |
| Outcome 2.2: Cattle farmers in the Darien do not have the required information, knowledge or experience to develop farm management plans based on SPS and conservation-oriented principles. However, the technical support needed to move from “business as usual” to the proposed “alternative scenario” is currently unavailable thus constituting a significant barrier to optimize the potential of available credit. Credit for agricultural development continues to be granted easily on favourable terms for “business as usual” production in a variety of sectors including cattle rearing, irrespective of resulting socio-environmental impacts. | The GEF alternative will support the development of new tools, considerations and appraisal processes for the assessment of credit requests, in an effort to ensure that environmental and social risks assessments and appraisal processes are implemented and guide credit approvals; as well as training Programmes, knowledge management tools, and instructive manuals for risk assessment and appraisals to be used as part of corporate policy to actively mainstream conservation objectives into lending operations. A national programme for exchanging experiences amongst banking institutions and disseminating best practices will also be supported by GEF funds. |  |
| COMPONENT 3: Monitoring, evaluation and knowledge sharing. |  |  |
| Component Result: Project is implemented according to Results Based Management principles and embraces an assertive knowledge management approach to systematize project results and experiences and re-incorporate into project performance and project sustainability. |  |  |
| Outcome 3.1: Biological indicators are not available at the landscape level for the project intervention area, or the tools and methodologies for assessing BD and LD impacts over time. There is no monitoring system in place to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation. A structured and institutionalized public awareness strategy and knowledge management strategy targeting SPS and broader sustainable cattle ranching and eco-labelling are not available in any of the key project stakeholder institutions, in support of the long-term sustainability of planned project outcomes. | The GEF will fund the development and implementation of a Project Monitoring and Evaluation Strategy, including annual work-plans, measurable and verifiable progress and impact indicators, annual budget allocations, and independent evaluation requirements. GEF resources will also be used to develop baselines for biological indicators at the landscape level for the project intervention area, including the tools and methodologies for assessing BD and LD impacts over time, and the development of a monitoring plan to determine the benefits and impacts of eco-labelling on sustainable resource use and biodiversity conservation. The GEF alternative will support the development, launch and maintenance of a project website, to provide updated information on project progress, measureable results, lessons learned, including links to the Ministerial websites, the on-line GIS, and blogs pertaining to SPS issues, ranching, conservation, and sustainable resource use topics. GEF resources will support the development and implementation of a Knowledge Management Strategy to ensure systemic documentation and uptake of results, experiences and lessons learnt is realized through-out project implementation, and not just as a consequence of periodic monitoring of time-bound project milestones. | Project is implemented according to Results Based Management principles and embraces an assertive knowledge management approach to systematize project results and experiences and re-incorporate into project performance and project sustainability. |
| BASELINE COSTS TOTAL: $18,722,590 | ALTERNATIVE COST TOTAL: $35,588,887 | GEF: US$3,519,725 Co-Financing: US$14,346,572 TOTAL: $17,866,297 |

## Annex 5: Summarized Project Implementation Schedule

| COMPONENT 1: Cattle production shifts to Silvo-pastoral systems (SPS) delivering environmental and socio-economic gains. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outcomes/Activities | IMPLEMENTATION |  |  |  |
|  | PY1 | PY2 | PY3 | PY4 |
| Outcome 1.1: Conservation oriented Silvo-pastoral Systems are adopted in cattle farms and the productive landscape of the Darien as part of a biodiversity conservation and land restoration landscape model. |  |  |  |  |
| Main activities: |  |  |  |  |
| 1.1.1 Feasibility Assessments (including Soil & Species Suitability) in the Darien |  |  |  |  |
| 1.1.2 Economic scenarios assessment |  |  |  |  |
| 1.1.3 Conservation-oriented Farm Management Plans |  |  |  |  |
| 1.1.4. Connectivity & Restoration Strategy |  |  |  |  |
| Outcome 1.2: Cattle producer have the technical know-how and managerial skills for implementing conservation-oriented SPS within cattle farms and productive landscapes. |  |  |  |  |
| Main activities: |  |  |  |  |
| 1.2.1 Capacity needs assessments |  |  |  |  |
| 1.2.2 Training Programme Manual for cattle ranchers |  |  |  |  |
| 1.2.3 Training for cattle ranchers |  |  |  |  |
| 1.2.4 Integrated SPS Training Plan for the Ministry of Agricultural Development |  |  |  |  |
| 1.2.5 Development of “Rancher to rancher” SPS exchange programme |  |  |  |  |
| 1.2.6 Implementation of “Rancher to rancher” SPS exchange programme |  |  |  |  |
| Outcome 1.3: Technical government counterparts and extension agents are able to deliver timely quality support in the application, oversight, and replication of SPS. |  |  |  |  |
| Main activities: |  |  |  |  |
| 1.3.1 Capacity building plan for technical staff in SPS extension services |  |  |  |  |
| 1.3.2 Training to technical staff and extension service providers |  |  |  |  |
| Outcome 1.4: Cattle ranches in the Darien demonstrate the socio-economic and environmental benefits of SPS, including eco-labelling for SPS farm products. |  |  |  |  |
| Main activities: |  |  |  |  |
| 1.4.1 Eco-labelling Suitability & Readiness Assessment |  |  |  |  |
| 1.4.2 Development & Designation of SPS eco-labelling |  |  |  |  |
| 1.4.3 Training and entrepreneurial skill enhancement programme |  |  |  |  |
| Outcome 1.5: Institutions and relevant stakeholders’ groups (i.e. producers, consumers, extension agents, policy-makers, sector representatives and land use planners) actively support the application, and replication of SPS in the Darien and nationwide |  |  |  |  |
| Main activities: |  |  |  |  |
| 1.5.1 Development of communication and awareness raising strategy document |  |  |  |  |
| 1.5.2 Implementation of communication and awareness raising strategy actions |  |  |  |  |
| COMPONENT 2: Biodiversity conservation and sustainable land use is mainstreamed into integrated land use planning, Financial mechanisms, and policy and regulatory frameworks. |  |  |  |  |
| Outcomes/Activities | IMPLEMENTATION |  |  |  |
|  | PY1 | PY2 | PY3 | PY4 |
| Outcome 2.1: A consolidated and integrated Land Use Management Plan guides productive activity (cattle ranching), land use zoning and conservation efforts in the Darien. |  |  |  |  |
| Main activities: |  |  |  |  |
| 2.1.1 Conservation-oriented Land Use Management Plan |  |  |  |  |
| 2.1.2 Regulatory Framework for conservation oriented Land Use Management Plan |  |  |  |  |
| 2.1.3 Develop online geographic information system |  |  |  |  |
| 2.1.4 Equipment for Online Geographic Information System |  |  |  |  |
| 2.1.5 Development of data access and use guidelines and protocols |  |  |  |  |
| 2.1.6 Training in use of online geographic information system tools |  |  |  |  |
| Outcome 2.2: Financial institutions support systemic changes in the appraisal of credits by incorporating conservation and sustainable use into their lending portfolios and mitigating the environmental, social and economic risks of their operations. |  |  |  |  |
| Main activities: |  |  |  |  |
| 2.1.1 Training Manual for mainstreaming conservation into lending operations |  |  |  |  |
| 2.1.2 Training to BDA Personnel |  |  |  |  |
| 2.1.3 National exchange program for banking institutions |  |  |  |  |
| COMPONENT 3: Monitoring, evaluation and knowledge sharing. |  |  |  |  |
| Outcomes/Activities | IMPLEMENTATION |  |  |  |
|  | PY1 | PY2 | PY3 | PY4 |
| Outcome 3.1: Project implementation follows a Results Based Management framework (RBM), applies SMART indicators for measuring progress and impact, and employs adaptive management principles to systematically re-incorporate monitoring and evaluation feedback into project performance. |  |  |  |  |
| Main activities: |  |  |  |  |
| 3.1.1 Hire Project Team |  |  |  |  |
| 3.1.2 Project Inception Workshop |  |  |  |  |
| 3.1.3 Baselines for Biological Indicators |  |  |  |  |
| 3.1.4 Knowledge Management Strategy |  |  |  |  |
| 3.1.5 Develop Gender Mainstreaming Action Plan as per CAF/GEF Project Manual on Social & Environmental Safeguards |  |  |  |  |
| 3.1.6 Project M&E Strategy (Annual Work Plans, Technical & Financial Progress Reports, PIRs) |  |  |  |  |
| 3.1.7 Develop and launch Project Website |  |  |  |  |
| 3.1.8 Eco-labelling Monitoring Plan |  |  |  |  |
| 3.1.9 Application of GEF Tracking Tool |  |  |  |  |
| 3.1.10 Audit of Project Activities |  |  |  |  |
| 3.1.11 Project Steering Committee Meetings |  |  |  |  |
| 3.1.12 Project Technical Committee Meetings |  |  |  |  |
| 3.1.13 Project Mid-Term Evaluation |  |  |  |  |
| 3.1.14 Project Terminal Evaluation |  |  |  |  |

## Annex 6: Budgeted Monitoring and Evaluation Plan

| M & E Activity | Responsibility | Estimated Budget (US$) (Excluding Staff Time) | Time Frame |
| --- | --- | --- | --- |
| Inception Workshop (one day) to produce: Annual Work Plan; Discuss Project Operations Manual; Discuss Roles, Responsibilities, and Decision-making Structures; Discuss need for Gender Action Plan; and Discuss Financial Reporting and Project Progress Reporting | - CAF - ANCON-PCU/Project Coordinator - Consultant to assist with planning and facilitation | Indicative Cost: $6,000 | Within first 6 weeks of project start-up |
| Baseline for Biological Indicators | - ANCON-PCU/Project Coordinator | Indicative Cost: $15,000 | Within the first 6 months of project start-up |
| Knowledge Management Strategy | - ANCON-PCU/Project Coordinator | Indicative Cost: $10,000 | Within the first 4 months of project start-up |
| Gender Mainstreaming Action Plan | - ANCON-PCU/Project Coordinator | Indicative Cost: $10,000 | Within the first 4 months of project start-up |
| Eco-labelling Monitoring Plan | - ANCON-PCU/Project Coordinator | Indicative Cost: $15,000 | Project Year 2 |
| Design & Launch Project Website | - ANCON-PCU/Project Coordinator | Indicative Cost: $5,000 | Within the first 6 months of project start-up |
| Develop long-term M&E Plan | - Project Coordinator will develop TORs to be vetted by CAF - Consultant hired to assist with development of long-term M&E Plan. | Indicative Cost: $10,000 (Consultant’s cost plus costs associated with vetting of means of verification in the field through-out project implementation) | To be developed at start up, and applied at start-up, mid-term and end of project |
| Project Steering Committee Meetings and Project Technical Committee Meetings (with formally prepared minutes and resolutions) | - CAF - ANCON-PCU | Indicative Cost: $18,000 | At least 2 meetings per year by each of the two committees (16 total in 4 years) |
| Quarterly Financial Reports & SOEs | - ANCON-PCU | Indicative Cost: PMC cost | Within 30 days of each completed quarter |
| Project Progress Reports | - ANCON-PCU - Project Team - National Project Focal Points - National Committees | Indicative Cost: PMC cost | At least every 6 months and due within 30 days of each completed semester. |
| Publication of Project Progress Reports and other informative materials | - ANCON-PCU - Project Team | Indicative Cost: $10,000 | Every semester (bi-annually) |
| External Mid-Term Review | - CAF - ANCON-PCU - Project Team - International Consultants (2) - National Consultants (4) | Indicative Cost: $22,500 (Professional Fees and logistical costs for Consultant) (To be covered by CAF) | Within 90 days of completion of the project’s mid-term |
| External Final Evaluation | - CAF - ANCON-PCU - Project Team - International Consultant - National Consultants (4) | Indicative Cost: $25,000 (Professional Fees and logistical costs of Consultant) | At the end of project implementation |
| Terminal Report | - ANCON-PCU - Project Team - Consultant | Indicative Cost: $10,000 | At least one month before the end of the project |
| Audits | - ANCON-PCU develops TORs to be vetted by CAF - Audit Firm to be hired by RCU, after no objection from CAF | Indicative Cost: $21,809 | At least annually CAF reserves the right to request a partial or complete audit at any time |
| Monitoring Visits to Project Sites | - ANCON-PCU - CAF - Project Team | Indicative Cost: $28,000 | At least yearly |
| TOTAL INDICATIVE COST EXCLUDING CAF STAFF TRAVEL |  | US$206,309 |  |

Annex 7: Endorsement by GEF Focal Point

Annex 8: Co-Financing Letters

Created in 1980, the Darien National Park was declared by UNESCO a World Heritage Site in 1982 and a Biosphere Reserve in 1983.

Biodiversity Mainstreaming in Practice: A Review of the GEF Experience over 25 years.

Other than the region’s protected area network and indigenous Comarcas which have no specific land use plans but for the most part are considered as forest reserves.

Subject to the implementation or adoption of BMP and socio-economic risk analysis

Manual of 15 best practices for establishing Silvo-pastoral Systems. USAID, ANAGAN, MIDA and COPEG.

Past initiatives while contextually very different in scope, time-frame, location, and stake-holder group do provide valuable lessons that contribute to the design, development, and implementation of the proposed project.

AED/CATIE, 2006. Pilot Sustainable Livestock and Agroforestry Systems in elected areas of the Darien. Academy for Educational Development/ Tropical   Agronomic Centre for Research and Education, funded by USAID.

The riparian forests on river banks should be no less than 10 meters on each side of existing water sources in order to: ensure water quantity and quality, the prevention of soil erosion, flooding and mitigate the effects of droughts during extreme weather events.

Comarcas are independently managed and therefore have their own management and land use plans. Existing ones will be reviewed in case valuable insights and relevant features can be applied, as appropriate, to the larger management plan proposed for the Darien region.

GEF6 Programming Directions.

In the GEF Programming Directions (BD4) two main outcomes under OP#9 are presented. The project will include complementary ones which will result from the PPG stage

GEF Programming Directions, Biodiversity Focal Area Strategy.

In the GEF Programming Directions (BD4) two main outcomes under OP#9 are presented. The project will include complementary ones which will result from the PPG stage

Knowledge Management Tools. https://www.knowledge-management-tools.net/knowledge-management-systems.html

Mainstreaming Biodiversity in Practice: A STAP Advisory Document.

Menu of best practices prepared by the Ministry of Agricultural Development (MIDA) in conjunction with the national Cattle Rancher Association (ANAGAN).

Guidance from the the following “Environmental Certification and the GEF: A STAP Advisory Document, 2010” will be applied in the definition of potential options. During the preparation phase (PPG), recommendations emitted by the STAP, based on prior GEF project experience and best practices for determining certification feasibility, will be applied. Product options considered will thus need to be analyzed against four main threats identified by STAP as likely to impact the effectiveness of certification programs, these include: (i) weak standards; (ii) non-compliance; (iii) limited participation; and (iv) adverse self-selection.

Knowledge Management Tools. https://www.knowledge-management-tools.net/knowledge-management-systems.html