FINAL REPORT

Mid-Term Evaluation of the Project

“Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R)”

GEF Project ID: 5765

WWF-US GEF Project ID: G003

Prepared by:

May 16, 2022

Acknowledgments

The evaluation team wishes to express its gratitude and acknowledgment to all the key Project stakeholders and partners who have been interviewed. Their contributions were highly valued, and the facts and opinions they provided played a fundamental role in conducting this evaluation. Special recognition to the members of the WWF-US and Mesoamerica and the CCAD-MAR2R for their kind support throughout the evaluation, in addition to the country teams in Belize, Guatemala, Honduras, and Mexico for their information and support during the fieldwork. The evaluation has been developed in very comfortable and cooperative interactions with all members

Table of Contents

Executive Summary	5

Project Summary Table	5

Project Description	6

Overview of Evaluation Ratings	6

Summary of findings	11

Conclusion & Recommendations	14

Recommendations	15

Acronyms and Abbreviations	19

1.	Introduction	21

1.1	Purpose of the evaluation	21

1.2	Statement of independence, lack of conflict of interest	21

1.3	Scope & Methodology	21

1.4	Composition of evaluation team	22

1.5	Limitations of the evaluation	23

1.6	Structure of the evaluation report	23

2.	Project description and development context	23

2.1	Project start and duration	23

2.2	Area of intervention	23

2.3	Summary of Project theory of change and evolution	24

2.4	Main stakeholders and beneficiaries	24

2.5	Discussion of baseline (of indicators) and expected results	24

3.	Findings	26

3.1	Project Design / Formulation	26

Relevance / Coherence	26

Assessment of the Theory of Change (ToC)	28

Replication approach and linkages between the Project and other interventions within the sector	31

Country ownership	31

Finance	32

Co-financing	33

3.2	Project Implementation	34

Effectiveness	34

Efficiency	42

Analysis of Adaptive Capacity	44

Impact	47

3.3	Equality and Mainstreaming	49

3.4	Stakeholder Engagement	49

Governance and management arrangements	49

3.5	Safeguards Review	54

4.	Conclusions, Recommendations & Lessons	56

4.1	Conclusion	56

4.2	Key lessons learned	57

4.3	Practices for other similar projects to replicate or avoid	59

4.4	Recommendations	60

5.	Annexes	64

5.1	MTE ToR (excluding ToR annexes)	64

5.2	MTE evaluation matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)	70

5.3	Questionnaire	85

5.4	Rating Scale for the criteria	91

5.5	List of stakeholders interviewed	93

5.6	MTE field mission itinerary	96

5.7	List of Documents reviewed	100

5.8	Flowchart of the Mid-Term Evaluation of the Project	101

5.9	Results Chains (from PRODOC)	102

5.10	Effectiveness in achieving planned results	106

5.11	SMART Analysis for the indicators	113

5.12	Audit Trail (Comments on Draft Report)	121

List of figures

Figure 1: Illustration of Project components	6

Figure 2: General arrangements for Project management and coordination	50

List of tables

Table 1: Project Information Table	5

Table 2: Project Components	25

Table 3: Financial information by component at the mid-term	32

Table 4: Informed on co-financing agreements	33

Table 5: Detailed assessment by Project partners	53

# Executive Summary

## Project Summary Table

Table 1: Project Information Table

| PROJECT DATA |  |
| --- | --- |
| Project Title | Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R) |
| GEF Project ID | 5765 |
| WWF-US Project ID | G003 |
| Implementing Agency(s) | WWF |
| Executing Agency | Central American Commission on Environment and Development (CCAD) |
| Executing Partner(s) | Ministries of Natural Resources in Belize, Guatemala, Honduras, and Mexico |
| Countries | Belize, Guatemala, Honduras, Mexico |
| Focal Area(s) | International Waters |
| GEF Operational Program | GEF 5 |
| Duration | 60 months |
| Total GEF Approved Budget | $ 9,830,000 |
| Total Co-financing | $51,277,908 |
| RELEVANT DATES |  |
| CEO Endorsement/Approval | 04/04/2017 |
| Agency Approval Date | 10/27/2017 |
| Implementation Start | 11/01/2018 |
| Midterm Evaluation | October-December 2021 |
| Project Completion Date (proposed or actual) | 06/30/2023 |

## Project Description

Project objective: To support regional collaboration for integrated ridge to reef management of the MAR ecoregion by demonstrating its advantages and improving regional, national, and local capacities for integrated management and governance of its freshwater, coastal and marine resources.

Component 1

Strengthen resource governance and regional collaboration for integrated ridge to reef management.

Component 2

Integrated ridge to reef management of watersheds and freshwater resources.

Component 3

Integrated ridge to reef management of coastal and marine resources.

Component 4: Project monitoring and evaluation, knowledge sharing.

Source: Based on the ToR and PRODOC

Figure 1: Illustration of Project components

This document presents the final report for the Mid-Term Evaluation (MTE) of the Global Environmental Facility (GEF) Project titled “Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R)”, hereafter referred to as the “Project”, implemented by the Central American Commission on Environment and Development (CCAD), and executed by the Ministries of Natural Resources in Belize, Guatemala, Honduras, and Mexico. The expected outcomes of the Project are depicted in the figure below.

The Project was to be executed in 65 months according to anticipated project execution established in agreement signed by GEF and WWF from 02/01/2018 to 06/30/2023, with a financial allocation of US$ 9,830,000 from the GEF, in addition to a co-financing of US$ 51,277,908, coming principally from CCAD, Ministries of the Environment and Government institutions of the four participating countries and partner NGOs.

## Overview of Evaluation Ratings

| A. Assessment of Project Outcomes | Rating | Justification |
| --- | --- | --- |
| Were Project outcomes Relevant when compared to focal area/operational program strategies, WWF strategies, country priorities, and mandates of the Agencies? Was the design appropriate for delivering the expected outcomes? | Satisfactory | The Project has an appropriate design and is relevant to the GEF, WWF, the Central American Integration System (SICA), the CCAD and regional partners. The Project outcomes contribute to the entire GEF Focal Area and Operational Program, are part of a regional vision and strategy developed by WWF and have been built with the support from local and regional stakeholders. The four countries highlight the Project's alignment with their national and regional priorities and support this regional integration initiative. The overall relevance of the Project is supported by its way of complementing and adding value. The design is satisfactory to achieve the expected results and commitments, with some outputs (i.e., certifications) at risk of not being achieved. |
| How do you assess the Effectiveness of Project outcomes? Were the actual outcomes commensurate with the expected outcomes? If assessment of outcome achievements is not feasible, output achievement can be used as a proxy. | Moderately Satisfactory | The Project is progressing towards the outcomes and is achieving outputs despite initial delays, now solved. The Project is accelerating its progress, aiming to reach its goals through proper adaptive management and implementation. The Project was delayed, in part, as it suffered unexpected climate, political and health events; costly impacts from two hurricanes (Eta & Lota), changes in governmental administrations, and the COVID-19 pandemic. While the Project design was ambitious for the available resources, most of the output targets are being achieved, though with delays, and the Project is expected to reach the intended outcomes to a large extent. Overall, the effectiveness of the Project is considered moderately satisfactory. |
| How do you assess Project Efficiency? Was the Project cost-effective? How does the Project cost/time versus output/outcomes equation compares to that of a similar Project? | Satisfactory | The Project inputs appear to have been adequately budgeted and planned, attaining significant co-financing to cover its costs. A general financial analysis would show the efficiency of some actions that contribute towards the sustainable use of natural resources. Delays in Project activities were due to lack of appropriate human resources and bureaucratic decision making in governmental institutions, with clear steps to reach agreement for approval of Project’s needs; however, as shown in the analysis, all these aspects were addressed and remediated. The efficiency of the Project is satisfactory since it has managed to optimize the available resources and attract complementary funds while achieving the expected results in the process. Project partners have been able to adapt their work rapidly, and the Project was able to achieve more co-financing when other commitments were not fulfilled. |
| Using above criteria, please provide an overall rating for the achievement of the Project outcomes. This assessment should analyze both the achievement and shortcomings of these results as stated in the Project document. | Satisfactory | The Project was well designed and is progressing to achieve its objectives. Even with delays and challenges encountered during the first year of implementation. An extension period to securely reach Project objectives has been requested by focal points and this evaluation. under specific control of planned activities. The Project is adequately staffed in the second half of the first mid-term, with specialists and partners, and Project beneficiaries have shown their satisfaction while implementing local actions with national and regional impact. Close monitoring and coordination between executing partners and components is a key strategy for the PMU during this final phase. |
| B. Assessment of Risks to Sustainability of Project Outcomes Please describe these risks below, considering likelihood and magnitude: |  |  |
| Financial Risks |  |  |
| Sustainability is rated likely. Governments recognize integrated watershed and marine ecosystem management as important actions to sustain economic growth, social and environmental health. Commitments and alliances developed and strengthened as a result of the MAR2R could serve as strong foundations for collaborative actions moving forward. The CCAD has gained much experience as the executing partner and sees MAR2R as a political platform to leverage financial and political resources to establish themselves as the main executing institution for sustainable development and climate change adaptation and mitigation projects. Nevertheless, regional financial resources at the national level continue to be limited for natural resource management and depend on external financial support to continue. A sustainability strategy for this final phase and beyond should be developed. Preparing the exit route and clarifying the road map ahead for all stakeholders involved. Furthermore, such strategy should systematize and help guarantee the institutionalization of the processes, lessons learned and the adoption of good practices, both at the national and regional levels that were gained through the Project. Sustainability Rating: Likely |  |  |
| Socio-Political Risks |  |  |
| The Project presents a regional vision aligned to all four national government commitments,and the pertinent interaction from the CCAD and other SICA institutions, reducing vulnerability to political changes. The Project is achieving unprecedented uptake from executing partners and stakeholders in the issues of restoration, the blue economy protocol, and positioning the R2R language at the highest-levels on the history of WWF Mesoamerica in the region. It has managed to combine and promote uptake of environmental, tourism, fishing, and blue economy aspects. However, Project implementation might be influenced by changing governmental priorities. The Project Management Unit (PMU) has developed a good relationship and interaction with the Project Steering Committee (PSC) and Project partners and beneficiaries. Due to climatic conditions (hurricanes), the COVID-19 pandemic, and fluctuating market conditions (tourism), the socio-economic situation needs to be monitored by the PMU and the Project governance, and anticipate potential risks and their possible mitigation measures. Sustainability Rating: Moderately Likely |  |  |
| Institutional Framework and Governance Risks |  |  |
| Institutional and governance risks are considered low. These risks stemmed from unexpected events and changes in political administration and were counteracted with adequate adaptive management coordinated by the PMU and WWF. Focal points and local stakeholders in the four countries are working in synergy with MAR2R components and benefit from the project activities. Yet, there is still room for consolidating the mechanisms and processes to mitigate and adapt to such risks at both the national and regional levels. Doing so should increase Project sustainability under such circumstances. Sustainability Rating: Moderately Likely |  |  |
| Environmental Risks |  |  |
| Covid-19 pandemic and hurricane events impacted the Project directly. According to stakeholders interviewed, these may still affect the implementation of the second phase. Systematization and use of lessons learned may help mitigate risks during the second phase. Indirectly, identified coral diseases can affect coral reef integrity and may be considered as a risk for the remaining part of the Project. However, these risks are considered limited, and unlikely to take place. In general, environmental risks and potential impacts exist and have to be adequately managed to secure sustainability. Sustainability Rating: Moderately Likely |  |  |
| Overall Rating of Sustainability of Project Outcomes | Rating | Justification |
| Using above criteria, please provide an overall rating for the risks to sustainability of Project outcomes. | Moderately Likely | Sustainability is moderately likely as it is affected by different aspects. At the same time, there is agreement on the Project's economic, environmental, and social benefits by the partners, beneficiaries, and national authorities. Key elements of the outputs are expected to be achieved in a reduced period of implementation such as governmental endorsement of Transboundary Diagnostic Analysis (TDA)/ Strategic Action Plan (SAP), producers and voluntary certifications, and the hectares of watersheds under Integrated Water Resource Management (IWRM) Project activities. There is a sense of ownership from the national focal points. Some partners have shown interest in continuing the efforts, including CCAD's regional vision, despite facing a range of obstacles. A sustainability strategy should be prepared to clarify what is needed to keep the Project's effects, ensure the institutionalization of the lessons learned, and adopt good practices, both at the national and regional levels. |

| C. Assessment of Monitoring and Evaluation (M&E) Systems | Remarks |  |
| --- | --- | --- |
| M&E Design – Was the M&E plan at the CEO endorsement practical and sufficient? Did the M&E plan include baseline data? Did it: specify clear targets and appropriate SMART indicators to track environmental, gender, and socioeconomic results; a proper methodological approach; specify practical organization and logistics of M&E activities including schedule and responsibilities for data collection; and budget adequate funds for M&E activities? | The Monitoring and Evaluation (M&E) design is rated as satisfactory as it allows to capture the information and keep track to meet indicator targets and mitigate Project conflicts. The Results Framework is the primary tool for M&E; the design included baseline data for most of the indicators that are adequate and clear, though some improvement could be considered based on a SMART analysis with adjustments proposed to be considered for the second phase (see annex 5.11) to make the monitoring of implementation more efficient. The M&E system, including human resources and budget (14% of the budget), are considered adequate. |  |
| M&E implementation – Did the M&E system operate as per the M&E plan? Where necessary, was the M&E plan revised in a timely manner? Was information on specified indicators and relevant GEF focal area indicators gathered in a systematic manner? Were appropriate methodological approaches used to analyze data? Were resources for M&E sufficient? How was the information from the M&E system used during Project implementation? Did it facilitate transparency, sharing and adaptive management? | M&E implementation is rated as satisfactory. Adaptive management has been used wisely during Project implementation. There is a system in place, which allows systematization. All activities have been duly tracked, and the IW GEF Tracking tool was prepared and incorporated into the system. Reports have been submitted on time, and the system has provided identified benefits. |  |
| Overall Rating of M&E During Implementation | Rating | Justification |
| Using above information as guidance, please provide an overall rating for M&E during Project design /implementation. | Satisfactory | Design and implementation are rated as satisfactory. |

| D. Implementation and Execution Rating | Rating | Justification |
| --- | --- | --- |
| Please rate the WWF GEF Agency on the Project implementation. | Satisfactory | The Implementing Agency has played an essential role in providing Project support, guidance, and follow-up. |
| Please rate the Executing Agency on Project execution. | Satisfactory | The Executing Agency has implemented and operationalized the Project accordingly to expected results despite delays up to the mid-term and has maintained a good relationship with partners and beneficiaries. |
| Overall quality of implementation and execution | Satisfactory | The Project is progressing towards its goals after a slow beginning. An earlier attempt to do the mid-term evaluation by another team who did not complete the exercise the Project may have been rated unsatisfactory; however, given the current implementation and plans, the final rate is satisfactory. |

## Summary of findings

Relevance

The MAR2R Project is of great relevance for the countries of the Mesoamerican Reef System (MAR) ecoregion. It addresses regional and national priorities by focusing on in the terrestrial, coastal and marine ecosystems of the MAR. In addition, it supports biodiversity conservation and encourages the application of best environmental and social practices, benefiting inhabitants of the ecoregion. Collaboration through the Project framework makes it possible to seek joint solutions to common problems in the main transboundary watersheds that impact the MAR. From the point of view of GEF, the Implementing Agency, and the SICA, the Project is relevant since it complements national and regional actions and adds value. Furthermore, it contributes to the GEF focal area and its Operational Program. There is an overall satisfaction with its design, and it has been recognized as relevant by all government representatives involved. For the Executing Agency, MAR2R is a prominent part of the conservation agenda in Mesoamerica. The Project has been built based on WWF's experience of the region’s ecosystems, the support from national and regional partners, and lessons learned from best practices acquired through their action globally. Project design is satisfactory in regards to the scope and promised results. It could improve in its capacity to facilitate execution at the SICA, CCAD and Governmental levels, considering the inherent bureaucracy and slow adaptability of these institutions.

Coherence

The MAR2R Project is strengthening national initiatives on integrated management of water resources, public policies, soil conservation, best management practices for agriculture and aquaculture, integrated management and governance of freshwater, coastal and marine resources in the countries involved. The Project’s approach and desired outcomes are welcomed by its partners and its beneficiaries. Each country recognizes how the MAR2R Project strengthened the comprehensive management of water and the national policy for the conservation of biodiversity, watersheds, and marine spatial planning.

Effectiveness

Progress toward results is different across all four components (see annex 5.10 for details). Progress is being made towards achieving goals; however, there is disparity between the financial resources invested and the Project activities accomplished. Until month 29/60, (50% of implementation), the Project executed 26% of the budget (US$ 2,365,537 / US$ 9,018,349) of funds assigned by the GEF. By the time of this evaluation, the Project has disbursed 36% of its budget and there is the challenge to execute the remaining 64% of the budget - equal to US$ 5,771,743. Several factors affected the start of a project, including the agility of the host institution's administrative, procurement, and contracting processes. Two of the three objective indicators have already been achieved. The number of regional policy tools has been surpassed, as three policies were approved as of year 3. In year 4, two more will be approved: The Regional Blue Economy Protocol and the Regional Harmonization of Wastewater Standards Protocol. In terms of the components, Component 1 was delayed due to several administrative processes; however, there has been progress during year 3, and the proposed goals should be achieved. Component 2 has several limitations regarding certifications. Fulfilling the goals established for Component 3 has been difficult, mainly in matters related to certifications. Delay in certification was due to a series of events affecting each country differently such as: extreme weather events in November 2020, COVID-19 and internal changes in offices in Guatemala and changes in the focal point in Mexico. In Component 4, the proposed goals have been widely accomplished. Regarding the coordination and communication between the executing agent, the focal points, the partners and the beneficiaries, the Project has maintained appropriate communication. Despite the delays generated by the COVID-19 pandemic, the 2020 tropical storms, the internal changes in the Ministries of Environment and focal points, the Project has been able to adapt to these circumstances and continue advancing. In the short time between the actual mid-term (March 2021) and the beginning of this evaluation (October 2021), it seems that there is planning and risk management that suggests the activities will be carried out to meet most of the expected results within the stipulated period (60 months). Nevertheless, a 12-month extension has been already requested and assessed as pertinent by this evaluation to ensure that all planned activities are performed.

Efficiency

The implementation plans of the Project seem adequate; however, there are implementation challenges with the experience of this first phase given delays and the permanence of the qualified team members. A thorough analysis by outputs and components is presented under Section 3 - Efficiency. The financial resources appear to be adequate for the Project's ambitions, and the Project inputs appear to have been adequately budgeted and planned, attaining significant co-financing to cover the Project costs. There are differences between the amount of co-financing committed and those achieved, and up to the mid-term the disbursement of the co-financing is equivalent to 58% of the total amount, with efforts being made to attain the necessary co-matching funds. The PMU maintains a close relationship with partners, beneficiaries, and focal points, as well as constant communication and leadership regarding the four components of the Project.

Results/ Impact

Several aspects of impact deserve recognition, such as the great and important experience of the WWF Mesoamerica in the design and formulation of the Project, a satisfactory, well-designed, and participatory theory of change, and a monitoring and evaluation system well used during the execution of the Project. Also, the selection of the CCAD as an executing agency for its political leadership and because it has ensured the involvement of national governments and the strengthening of their capacities. This facilitates interaction with different SICA agencies such as OPESCA and SITCA, through the CCAD, as well as with other regional projects, such as the Project “Capacity Development in Integral Management and Conservation of Biodiversity in the SICA Region” with resources from Japanese cooperation (JICA), and the Caribbean Large Marine Ecosystem Project (CLME+). This also promotes the strengthening of regional cooperation, as well as the CCAD’s relationship with Mexico, and supports the implementation of the Tulum Declaration with a focused strengthening of national and regional initiatives. The Project has been key and strategic in addressing governmental priorities such as the Blue Economy, Tulum Agreement and Stony Coral Tissue Loss Disease (SCTLD). The Project Management Unit (PMU) is appropriate, adequate, and operates effectively and efficiently from the CCAD and this has proposed CCAD for ideas to manage and operate other projects. The Regional Environmental Observatory (REO) for systematization and dissemination of information and promoting a regional vision of development and conservation are two valuable Project results. Two examples of this are the Regional Vision of Social and Sustainable Tourism in the MBRS, developed in a participatory manner, and the Regional Strategy for Mangrove Management, Conservation, Restoration, and Monitoring in the Mesoamerican Reef. As a result of the ability to adapt to virtual modalities, the Project has been able to facilitate/implement virtual training and workshops. However, the standardization of information collection has room for improvement. Based on the results obtained and the resources invested up to this evaluation, the execution of the fourth Annual Operating Plan (POA 4) should substantially improve the investment of resources and, therefore, the delivery of results according to the programmed activities. The actors involved in the implementation of the Project consider that the expected results can be achieved if the progress continues throughout the third year of execution. Mayor Project challenges which need to be duly addressed in the second phase to reach the impact are: (a) establish alliances, agreements and coordination platforms which do not take longer than expected, to avoid affecting the budget execution; (b) the procedures harmonization used by the SG-SICA and the GEF requirements to improve administrative/financial process; (c) partners with problems complying with the due diligence standards required by the SG-SICA to be surely addressed; (d) pertinent follow up to reach the output of the TDA/SAP with R2R approach; and (e) establish an agreement to solve the possible impact of not achieving the certifications of the productive sectors of components 2 and 3.

Sustainability

The Project’s sustainability is moderately likely as it can be supported by the commitments and alliances with the Ministries of the Environment of the four countries of the ecoregion, which will continue to manage the improvement projects for reef management, integrated water management, and marine conservation. These are national priorities in which other stakeholders such as the private sector and the communities have been involved together in dialogue platforms in some watersheds. This is based on the agreements on priorities and all the documentation that the Project has produced. All these inputs are essential for sustainability and an exit strategy needs to be developed to sustain the results and outcomes beyond the life of the Project. The counterpart commitments achieved demonstrate the potential contribution to sustainability, such as new projects that will bring further financial resources to the continuation of planned activities and the actions transformed into public policies that will allow sustainability in the management of natural resources. Financial, sociopolitical, institutional, and environmental risks have been analyzed by the PMU and are monitored and controlled; lessons learned are applied, and adjustments are made based on adaptive management as reported by the interviews with the PMU members and the stakeholders. The Project is highly relevant to CCAD and its partners. Its structure and governance are being applied in other projects both on a smaller (binational) and larger scale (in other Central American and Caribbean countries) where the pilots and some of the structures will have the appropriate accompaniment.

Adaptive capacity

M&E, lessons learned, and adaptive management have been used to achieve the progress in this first phase, where many of the indicator targets were fulfilled. The Project overcame different obstacles given its operational complexity, and all the elements that the design contemplated have been implemented. The Project developers and currently the PMU and the partners have reported practical use of lessons learned and good practices from other experiences and during the interviews. Lessons learned are found in the semi-annual and annual progress reports of year 2. They identify and document a range of experiences that stakeholders and partners encountered on the Blue Economy protocol, Safeguards application, and the updating of Guatemala’s public policy. These are effective in narrating how these developed as institutions interacted, found challenges and new paths forward. Still, we consider this section can further analyze the root causes and practical links of these lessons to project implementation and design. Furthermore, following objective 4.2.2, there are two reports from international conferences, in Colombia and Morocco, where MAR2R lessons learned were presented. Reports could add direct benefit to the project if they were to provide information or technology exchange discussed during the events that may be useful for MAR2R. Monitoring tools have been acknowledged, including dissemination mechanisms. On the other hand, several actors mentioned not receiving enough information about the Project’s progress, which should be addressed to understand the importance of their contribution to achieving the results and promoting constructive interaction. Project progress indicators are duly captured and contrasted with the existing baseline, with a pending aspect to address documents with questioned quality during supervision. An environment of trust and work was established with the focal points, and the different challenges were properly addressed, taking opportunities, and reducing risks. Adaptive management has been used in emergent circumstances. The robust M&E system based on a systematic capture of information and able to be compared with projected (and baseline) indicators, and the lessons learned, and adaptive management are used to monitor and meet the indicator goals and mitigate the Project's problems, as well as possible design failures (certification) or any adverse situation that affects the development of the Project (pandemic). The M&E system provides information for decision-making and considers the actual and the financial implementation of the actions.

Equality and Mainstreaming

The Project has a transversal strategy on gender outlined from its formulation in the Project document (PRODOC, p.86), which adheres to the WWF Gender Policy, to guarantee that both women and men can participate equally in Project activities and have access to Project benefits, do not suffer adverse effects during the development process, and enjoy respect for their dignity and human rights. Thus, the participation of women in Project activities is considered in Project planning and management activities, training, and technical assistance activities, and in decision-making structures. In addition, the gender transversal strategy is monitored through the application of gender-sensitive indicators. In addition, an Environmental and Social Management Framework (ESMF) has been prepared for the MAR2R Project to guide the design of the demonstration projects and assess and address their potential impacts.

COVID-19

The COVID-19 pandemic affected the execution of the Project, since: (a) mobility restrictions prevented carrying out the training and consultation activities programmed in the field; (b) some partners did not use resources for workshops and field visits due to the confinement measures; and (c) some stakeholders had significant economic losses, such as oil palm producers and sugar mills, for which they changed their priorities and lost interest in participating in certification processes; though the interest in promoting best practices is maintained and this has to be capitalized by the Project in its second phase of execution.

## Conclusion & Recommendations

The Project’s overall progress is satisfactory, and its implementation is moving towards achieving the expected results. The CCAD is effective in leading and facilitating decision-making for the four MAR country governments (Belize, Guatemala, Honduras, and Mexico) in adopting a ridge-to-reef approach to the governance and management of a shared transboundary ecoregion. While WWF showed comparative advantage as the implementing agency with great experience in the region. This evaluation concludes that the Project design and formulation, including the Theory of Change (TOC), was and remains relevant. This is evidenced by widespread support for the TOC, as well as signs of regional and national government support for the R2R approach and the Project in general. The Project was found relevant for strengthening national efforts and responding to governmental needs, complementing other projects, expanding, and consolidating the work WWF Mesoamerica has been doing while promoting collaboration and discussion between stakeholders involved in this ecoregional landscape. The work done thus far has been led by a strong Project Management Unit (PMU), that played a crucial role in strengthening the CCAD and interacting positively with SICA. The demonstrative projects and the study developed at the mid-term indicate that the Project is contributing to maintaining and improving the ecological integrity of the watersheds and the coastal-marine ecosystems of the MAR. Replication is ensured by a communication and dissemination strategy that is functioning well. This evaluation concludes that the Project presents strong internal and external coherence, aligning with multiple regional and national policy instruments and trends.

While the Project design was ambitious for the available resources, most of the output targets are being achieved across all the components, with differential progress. Addressing the delays and reaching targets must be prioritized to balance and advance homogeneously towards completing the four Project components. The low disbursement at mid-term (26%) is explained by a series of external and internal factors that delayed investment. The PMU guided overall Project adaptation, strengthening current capacity and creating the enabling conditions to move forward. Disbursement by 3rd year is at a low 36%. Nevertheless, the annual operating plan (POA) for year 4 provides the roadmap to reach a high level of disbursement (80%), leaving a 20% for the last implementation year. The likelihood of reaching this 80% greatly depends on the control and monitoring of activities. Projections are correct, and most grant agreements have already been signed; thus, there are two sets of data for the budgetary situation, the amount spent (already paid) and the amount committed (with contracts signed but not disbursed yet).

Finally, based on the evidenced findings and conclusions regarding effectiveness and efficiency, reciprocal collaboration between the Implementing Agency and the Executing Agency is necessary to advance towards the successful implementation of the Project with a potential extension of the Project time to secure the pertinent deliverables. Below are lessons learned and recommendations that could inform and better guide this and other processes.

## Recommendations

| Effectiveness |  |
| --- | --- |
| Finding 1: Since 70% of the Project duration has elapsed with only 36% of resources executed, the remaining 64% must be invested in the 15 months remaining (30%). |  |
| Recommendations | Responsible Entity |
| - Organize a workshop with the participation of the Implementing and the Executing Agencies to adopt a clear road map to guide diligent efforts to improve and accelerate the implementation of the remaining outcomes/outputs, with the spirit of adaptive management and under the leadership of the PMU and the accompaniment of the PSC. - Strengthen the capacity of focal points (with the identification of needs) in each Project implementation zone to contribute to timely delivery of Project outcomes. This could be done through routine performance analysis to identify the strengths and opportunities for improvement. - Establish adaptive management changes to components 2 and 3. See recommendations included under Adaptive Capacity. - Assure progress towards objective indicator “Area (ha) of watershed under IWRM Project activities.” According to annex 5.10, the percentage obtained at year three is 84.18%: 1,336,652.69 ha out of 1,587,934 ha. - Present a proposal for extension of ideally 12 months with a clear justification and action plan to achieve pending outputs. - Reschedule and continue to prepare a critical route path to align activities related to certifications in components 2 and 3 to the targets defined in the results framework to contribute to their achievement. - Identify all stakeholders with/in the process of certification and coordinate meetings/encounters to foster collaboration and knowledge sharing, helping them contribute to each other’s process. Bring case studies that are in the Project’s scope such as DIGEPESCA and the RARE experience in Honduras. | PMU, Steering Committee, and Focal Points |
| Efficiency |  |
| Finding 2: Internal and external communication gaps affect timely Project implementation |  |
| Recommendations | Responsible Entity |
| - Prepare a critical route with specific steps to implement the communication strategy developed in 2019 to ensure that the Project’s constituency have all the necessary information. - Review and adjust the communication channels between the PMU and the executing partners to support opportune and informed decision-making processes. - Identify and implement best communication strategies, tailored for target beneficiary groups to improve project transparency and communication (i.e. e-mail newsletters, website, videos). - Use the Regional Environmental Observatory (REO) platform as a communication channel, based on established safeguards. - Monitor and implement the Risk Management Measures related to effective communication. - Evaluate the M&E capacity to ensure compliance with deadlines and follow-up activities, identify best strategies when necessary. - Ensure that focal points use the detailed critical path with dynamic Project management software and hold regular meetings. - Hold periodic progress reporting meetings with the participation of key execution partners so that they better understand Project results and promote the exchange of experiences. | PMU, Steering Committee, and Focal Points |
| Finding 3: Some disagreements or complaints from project level stakeholders lack adequate channels for being duly communicated and pertinently addressed. |  |
| Recommendations | Responsible Entity |
| - Appraise the need for a simple but effective online grievance mechanism for complaints from project level stakeholders and beneficiaries to submit their complaints to the PMU. An anonymous option for presenting a complaint is recommended. - Designate a person within the PMU to address complaints effectively. | PMU and Focal Points |
| Finding 4: Lessons learned from Project implementation, good practices, gaps, and general interaction meetings should be improved. |  |
| Recommendations | Responsible Entity |
| - Identify, systematize, and disseminate lessons learned opportunely through the REO from the Project to be shared with the entire constituency. - Conduct periodic workshops where partners, beneficiaries, and key stakeholders can share and learn about Project progress and lessons learned. Ensure there is adequate systematization and dissemination of the information, conclusion and recommendations for their implementation. | PMU and Focal Points |
| Sustainability |  |
| Finding 5: The Project has received great support from the Ministries of the Environment of the four countries in the MAR ecoregion and is very relevant to CCAD and its partners. An exit strategy needs to be developed to sustain the results and outcomes beyond the life of the Project. |  |
| Recommendations | Responsible Entity |
| - Plan a sustainability strategy or exit strategy that makes explicit what is needed to keep the effects of the Project. The strategy should define a transition to ensure the institutionalization of the lessons learned, and the adoption of good practices, both at the national and regional levels. The budget of the responsible entities should be ensured when relevant. - Once the term is extended, coordinate the preparation of the exit strategy; the PSC must endorse this strategy. - Improving data gathering across the collaborative network and to facilitate capacity building towards R2R regional governance with quality mapping and decision making instruments such as the REO platform. Which needs to be evaluated and improved. Integrating the REO platform to data sources from the project activities and ground participant/partner activities at the watershed, coastal and regional levels. | PMU and Steering Committee |
| Adaptive Capacity |  |
| Finding 6: There are areas of improvement in the application of the Logical Framework Matrix. |  |
| Recommendations | Responsible Entity |
| - Validate the Logical Framework Matrix to prioritize actions as part of the strategic planning for the remaining Project implementation. - Rewrite indicators for some outcomes to improve their understanding. For example, it would be recommendable to rewrite the indicator for outcome 1.4, which does not reflect the expected result. Other indicators that should be rewritten are highlighted in annex 5.11. - Solve the differences found in outputs 2.1, 3.1, and 3.2 between what is stated in the Results Framework in the Project Document (pages 182 and 183) and detailed in the Project reports (see comments in annex 5.11). | PMU with Steering Committee and Implementing Agency |
| Finding 7: The M&E reporting does not reach all stakeholders (direct and indirect). |  |
| Recommendations | Responsible Entity |
| - Develop a more effective online M&E system to reach more beneficiaries. - Enhance the M&E function to ensure better reporting and monitor the technical quality of the documents presented as Project outcomes. M&E responsibilities should include providing feedback to the Project staff, executing partners, and relevant stakeholders. - Ensure that the M&E responsible staff prepares timely reports (including changes, risks, lessons learned, gaps, among others) to share with all Project partners, and stakeholders and disseminate through periodic newsletters based on Project reports (through Mailchimp, for example). | PMU and Focal Points |
| Finding 8: The Project might not achieve the outcomes related to certifications of the productive sector. |  |
| Recommendations | Responsible Entity |
| - Modify the indicators regarding reaching or maintaining compliance of certifications to reflect the current needs of each productive sector involved. The PMU has already prepared a proposal to modify the indicators. The evaluation team concludes that it is coherent and recommends to: - Prioritize activities to identify potential companies to be certified. - Develop a certification guide based on lessons learned, including the current needs of each productive sector. - Consider enabling the productive sector for future certifications (e.g., Better Management Practices). - The recognition of ecosystem service provision through R2R management must be coupled with strong data and analysis to effectively improve and maintain biodiversity and ecosystem services quality. The REO platform, TDA/SAP instruments and reports and documentation provided by components 2 and 3 are a strong basis towards it. | PMU and Implementing Agency |
| Equality and Mainstreaming |  |
| Finding 9: The Project did not formally consider a gender approach though most Project activities have encouraged gender inclusion |  |
| Recommendations | Responsible Entity |
| - Develop a Project policy and Monitoring, Reporting and Verification (MRV) on gender mainstreaming based on current social safeguards. - Strengthen the proposal based on gender safeguards, linked to WWF’s gender policy (mentioned in PRODOC), as a basis for equity in access to Project benefits and ensure equitable participation of all parties. | PMU and Focal Points |

# Acronyms and Abbreviations

| AIPAH | Industrial Association of Palm Oil Producers of Honduras |
| --- | --- |
| APAH | Sugar Producers Association of Honduras |
| BONSUCRO | Better Sugar Cane Initiative |
| CCAD | Central American Commission on Environment and Development |
| CLME+ | Caribbean Large Marine Ecosystem |
| CONAGUA | National Water Commission - Mexico |
| CONANP | National Commission on Natural Protected Areas - Mexico |
| CZMAI | Coastal Zone Management Authority and Institute - Belize |
| DIGEPESCA | Fisheries General Directorate – Honduras |
| ERAM | Framework Regional Environmental Strategy 2015-2020 (Estrategia Regional Ambiental Marco 2015-2020 in Spanish) |
| ERCA | Blue Growth Regional Strategy (Estrategia Regional de Crecimiento Azul in Spanish) |
| ESMF | Environmental and Social Management Framework |
| FIP | Fishery Improvement Project |
| FP | Focal Point |
| FUNDAECO | Foundation for Ecodevelopment and Conservation |
| GEF | Global Environment Facility |
| HRI | Healthy Reefs for Healthy People Initiative |
| ICMM | Integrated Coastal Marine Management |
| IDB | Inter-American Development Bank |
| ISNC | Intersectoral National Committee |
| ICZM | Integrated Coastal Zone Management |
| IWRM | Integrated Water Resource Management |
| M&E | Monitoring and Evaluation |
| MAR | Mesoamerican Reef |
| MAR2R | Integrated Ridge to Reef Management of the Mesoamerican Reef Project |
| MARN | Ministry of the Environment and Natural Resources - Guatemala |
| MARTI | Mesoamerican Reef Tourism Initiative |
| MBRS | Mesoamerican Barrier Reef System |
| MiAmbiente | Secretariat for Energy, Natural Resources, Environment and Mines - Honduras |
| MMC | MAR Ministerial Council |
| MoU MRV | Memorandum of Understanding Monitoring, Reporting and Verification |
| MSC | Marine Stewardship Council |
| MSP | Marine Spatial Planning in Belize |
| MT | Mid-term |
| MTWG | MAR Technical Working Group |
| OSPESCA | Central American Fisheries and Aquaculture Organization |
| PMU | Project Management Unit |
| PPG | Project Preparation Grant |
| PPMS | WWF Program and Project Management Standards |
| PRODOC | Project Document |
| PSC | Project Steering Committee |
| REO | Regional Environmental Observatory |
| RSPO | Roundtable for Sustainable Palm Oil |
| SAP | Strategic Action Plan |
| SCLTD | Stony Coral Tissue Loss Disease |
| SEMARNAT | Environmental and Natural Resources Secretariat-Mexico |
| SICA | Central American Integration Secretariat |
| SITCA | Secretaría de Integración Turística Centroamericana |
| SPAW | Specially Protected Areas and Wildlife |
| TDA | Transboundary Diagnostic Analysis |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environment Programme |
| WWF | World Wide Fund for Nature |

# Introduction

## Purpose of the evaluation

This document presents the final report of the Mid-Term Evaluation (MTE) for the Global Environmental Facility (GEF) Project titled “Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R),” hereafter referred to as the “Project”, implemented by the Central American Commission on Environment and Development (CCAD), and executed by the Ministries of Natural Resources in Belize, Guatemala, Honduras, and Mexico. The specific objectives of the MTE are to examine the extent, magnitude, and sustainability of Project results to date; identify any opportunities to improve Project design; assess progress towards Project outcomes and outputs; and draw lessons learned that can improve the Project effectiveness, efficiency, and sustainability of Project benefits. And based on this assessment, to provide feasible recommendations that could be applied for the remaining duration of the Project.

## Statement of independence, lack of conflict of interest

Following GEF terminal evaluation guidelines, the MTE was conducted by an external team of consultants, ensuring the independence of the evaluators, contributing to the credibility of the evaluation, and avoiding bias in findings, analyses, and conclusions. The absence of bias and the methodological approach used to achieve the TE imply that all stakeholders' views were considered.

Additionally, the external team of consultants certify that they have no affiliations with or involvement in any organization or entity with any financial interest or non-financial interest in the subject matter or materials discussed in this document.

## Scope & Methodology

The evaluation followed an approach that emphasized the participation of diverse actors, and was based on the guidance, rules, and procedures established by WWF, the Terms of Reference (ToR) (annex 5.1), the guidelines from the GEF TE, and the Guidance for conducting UNDP-supported terminal evaluations, GEF-financed projects. The core criteria for this evaluation included relevance, coherence, effectiveness, efficiency, results/impacts, sustainability, adaptive capacity, in addition to gender-equity, safeguards, and COVID-19 impacts.

Detailed information on the evaluation criteria, key questions, indicators, sources of information, and methodology is depicted in annex 5.2. Information to be gathered by different stakeholders followed the example in annex 5.3. All the information collected, and the recording of the interviews were kept confidential. Interviewees were informed that if they needed to be quoted, this would only be done with their previous consent. The information collected during fieldwork was also based on the evaluation matrix (annex 5.2), and the interview questionnaire (annex 5.3). annex 5.4 explains the rating scale for the different criteria, while annex 5.5 identifies the stakeholders interviewed. One team member visited Project interventions in Honduras, and another one conducted in-person interviews in Mexico. The general mission itinerary is depicted in annex 5.6. Several documents were desk-reviewed, most of them provided by the evidence required in the M&E; though others were provided by the interviewees or found online, these are shown in annex 5.7. annex 5.8 includes the methodological stages of this evaluation.

Due to the sanitary conditions of the COVID-19 pandemic, interviews were mostly conducted virtually, and a total of 49 professional stakeholders were interviewed across the countries (annex 5.6). The duration of the in-depth interviews, as well as the focus groups, were between 0.40 and 2 hours, and the evaluation team conducted 26 interviews/focus (including the 49 professionals previously mentioned). The two final annexes are: a table describing progress per outcome (5.10) and a SMART analysis for the indicators (annex 5.11).

## Composition of evaluation team

The evaluation was led by an international experienced consultant, supported by a qualified team, including local consultants from two of the countries of intervention (Honduras and Mexico), and a supporting M&E team, all part of Quorsus Consulting LLC.

| Composition of Evaluation Team |  |
| --- | --- |
| Ángel Alberto Yanosky | Team Leader |
| Martha Ileana Rosas | Senior Local Consultant Mexico |
| Elias Suazo Lizardo | Senior Local Consultant Honduras |
| Javier Jahnsen | Monitoring and Evaluation Expert |
| Adriana Bustillo | Director of M&E |
| Alondra Maradiaga | M&E Assistant |

## Limitations of the evaluation

Due to the sanitary conditions of the COVID-19 pandemic, the evaluation team conducted interviews in-person and virtually. Field visits were only possible in Honduras and Mexico, where conditions allowed it and using the sanitary protocols. Key people responsible for the Project were interviewed.

## Structure of the evaluation report

The document is divided into five sections: the introduction (1), the Project description and development context (2), the findings (3), the conclusions, recommendations, and lessons learned (4), and the annexes (5). Each section has subsections that are listed in the table of contents.

# Project description and development context

## Project start and duration

The Project started its implementation in February 2018 and the completion is scheduled for June 2023, after a period of 65 months of implementation. This evaluation was expected to happen at mid-term and include a period of 36 months from February 2018 to March 2021. However, this evaluation is being developed in the 42nd month of implementation (70%) with 13 months remaining (30%) for Project completion. Therefore, the evaluation considers the original period of 36 months, but has reviewed actions developed in the third year of implementation and the operational plan for the 4th year, which was presented to the Steering Committee and approved on November 29, 2021.

## Area of intervention

The Project has an area of intervention through the governmental institutions of 564,263 km2 of oceans, coasts, and watersheds in four countries (Belize, Guatemala, Honduras, and Mexico) known as the Mesoamerican Reef Ecoregion (MAR). This hotspot comprises the coast of the Mexican State of Quintana Roo, Belize and Guatemala’s national coasts, the central and eastern coast, and the Bay Islands of Honduras. The area is home to 2 to 12 million people and is considered a biodiversity hotspot. It is one of the richest ecoregions with the most diverse coral reefs in the Western Atlantic and watersheds that host a range of forest ecosystems from cloud to broadleaf jungles and mangroves in the coastal lowlands.

## Summary of Project theory of change and evolution

The MAR2R Project’s Theory of Change proposed that if CCAD effectively leads and facilitates decision-making for the four MAR country governments to adopt a ridge to reef approach to the governance and management of the shared transboundary MAR ecoregion, and the national governments, in turn, can engage civil society, private sector and local communities in the process, then the MAR countries’ ability to maintain or improve the ecological integrity of the watersheds and the coastal and marine ecosystems of the MAR can be integrated and strengthened. A coordinated regional vision is expected to be achieved in line with previous political agreements and the development of local capacities in sustainable management of the land, water, and coastal-marine resources. The Project was designed with four components: one to address governance and collaboration, a second one to work on watersheds and freshwater resources, the third one for coastal-marine resources, and a fourth component with the Project monitoring and evaluation and knowledge management.

## Main stakeholders and beneficiaries

Stakeholder engagement was done at the country and regional levels to validate the Project strategy, align it with national priorities, and determine the most impactful interventions and the most appropriate organizations to execute the work. A range of stakeholders from Belize, Guatemala, Honduras, and Mexico, including government representatives and focal points, civil society (both national and regional), and the private sector, were consulted through meetings and interviews. Several areas of opportunity were identified to capture information, increase the level of Project information and evidence, and discuss the general criteria which were the basis for this evaluation. The Project Document has clearly identified partners and potential beneficiaries.

## Discussion of baseline (of indicators) and expected results

The Project goal is to contribute to the conservation and sustainable use of shared freshwater, coastal and marine resources of the transboundary MAR ecoregion by implementing the ridge to reef approach and hence securing sustainable economic benefits and livelihoods for the countries and their communities, its objective is to support regional collaboration for the integrated ridge to reef management of the transboundary MAR ecoregion by demonstrating its advantages and improving regional, national, and local capacities for the integrated management and governance of its freshwater, coastal, and marine resources.

The strategy of the Project is based on the coordinated regional vision that is in line with the Tulum+8 Regional Action Plan for the MAR and the CCAD’S Regional Framework Strategy of the Environment.

The Project aims to achieve its goal and objectives by:

- Strengthening regional capacity and collaboration between the four MAR countries through CCAD and create a favorable political and regulatory harmonized framework, including regional demonstration programs of collaboration and the necessary tools and instruments for monitoring and evaluation (M&E) for decision making;

- Building regional, national, and local capacity for a scaled- up ridge to reef integrated management in the MAR; and

- Engage multiple stakeholders from the governments, communities, and the private sector in implementing sustainable management practices to reduce threats to the MAR.

The Project established baseline indicators that were compared with Project indicators, which respond to the activities that help achieve the goals proposed for each component and their respective results (outcomes) and products (outputs). The following table presents the Project components alongside its budget.

Table 2: Project Components

| Project Component | Expected Outcomes | Budget |  |
| --- | --- | --- | --- |
|  |  | Grant | Co-financing |
| Component 1: Strengthen resource governance and regional collaboration for integrated ridge to reef management in the MAR | Outcome 1.1: The countries have the enabling conditions for MAR R2R management Outcome 1.2: MAR national R2R policy (IWRM and ICM) frameworks are strengthened Outcome 1.3: MAR has a TDA and an SAP that will guide the ecoregional R2R management. Outcome 1.4: MAR strategic planning, policy making, management and monitoring supported with updated reliable information accessed via Regional Environmental Observatory (REO). | $ 858,890 | $ 21,699,497 |
| Component 2: Integrated ridge to reef management of watersheds and freshwater resources | Outcome 2.1: IWRM in priority watersheds increased Outcome 2.2: Public-private mechanisms for integrated watershed management are consolidated and supported by stakeholders. Outcome 2.3: Stakeholders engaged in IWRM in priority watersheds. | $ 4,294,452 | $ 23,128,401 |
| Component 3: Integrated ridge to reef management of coastal and marine resources | Outcome 3.1: ICMM strengthened through capacity building and strategic planning. Outcome 3.2: Stakeholders engaged in ICMM in coastal marine prioritized areas | $ 2,576,671 | $ 18,744,734 |
| Component 4: Project monitoring and evaluation, and knowledge sharing | Outcome 4.1: The Project's monitoring and evaluation system employs participatory methods throughout Project lifetime. Outcome 4.2: Advantages of the ridge-to-reef approach shared with local and international audiences, including the GEF IW: LEARN community. | $ 858,890 | $ 3,243,621 |
| Subtotal |  | $ 8,588,903 | $ 66,816,253 |
| Project Management Cost (PMU) |  | $ 429,446 | $ 2,641,573 |
| Total Project Cost |  | $ 9,018,349 | $ 69,457,826 |

# Findings

## Project Design / Formulation

### Relevance / Coherence

The Project is highly relevant to the four MAR countries, addresses regional and national priorities, and is aligned with the GEF Strategic Priorities. Its existence has been promoted by the GEF to fill in gaps of conservation actions. Furthermore, collective learning and action through the Project makes it possible to recognize best regional governance strategies that seek joint solutions to common problems in terrestrial and marine ecosystems of the MAR.

The Project’s strategy and approach are valid and appropriate. The R2R strategy was being implemented and evaluated since 2002 by WWF Guatemala/Mesoamerica. Based on their experience with the approach and issues encountered during a similar project called BMRS, during the 1990s, Project design aimed to strengthen regional collaboration between the four MAR countries (Belize, Guatemala, Honduras, Mexico) by addressing common problems and providing conservation solutions from an environmental, economic, and social points of view. Moreover, the Project supported the implementation of the Tulum Declaration. The Project strengthens alliances and coalitions between key stakeholders in the four countries and beyond the MAR, such as the Caribbean Large Marine Ecosystem (CLME+).

The benefits of this strategy and approach is further discussed in Effectiveness and Sustainability sections.

During its design, WWF-GEF requested WWF-Guatemala/Mesoamerica for great detail in the elaboration of the PIF; identifying and directing specific procedures for small and large investments. The design team took a different route, designing the PIF as clear guidelines rather than rules. An example is the general and open language used in Component 3, compared to the greater detail in Component 2. The intention was to leave sufficient space for dynamic change and adaptation. The PRODOC was then elaborated by CATIE. As the project progressed, evaluation on its design and implementation demonstrated that tighter limits and adequate weighing on the indicators per result would have benefited the project.

Lack of intermediate indicators, to monitor and evaluate steps towards results, and the adequate valuation of general indicators would give project execution and its M&E component more stability as it develops. This is the case of the TDA/SAP, which has only one indicator, number 12. Throughout its process, given the proper valuation, TDA/SAP is of high priority, and needed to be executed in year 1. Not in year 3, treated similarly to outcomes with less priority.

The Implementing Agency’s experience was vital for preparing the Project and considered their holistic and comprehensive expertise. Furthermore, the need for a comprehensive approach to a critical area (hotspot) for biodiversity and its prominent role globally among the planet's threatened ecoregions with the potential contribution to global biodiversity conservation made the Project essential to the GEF and WWF.

Hence, TDA/SAP’s completion is essential to achieve the project objectives as it provides the building blocks for a long-term natural capital management system. TDA/SAP can facilitate the establishment of regional ecosystem services baseline along with guidelines for regional governance that recognizes and captures natural capital through market-based mechanisms.

### Assessment of the Theory of Change (ToC)

The Theory of Change (ToC) was developed to inform and design the Project’s results chain and its logical framework matrix. It states that: If CCAD effectively leads and facilitates decision-making for the four MAR country governments to adopt a ridge to reef approach to the governance and management of the shared transboundary MAR ecoregion, and the national governments in turn can engage civil society, private sector and local communities in the process, THEN the MAR countries’ ability to maintain or improve the ecological integrity of the watersheds and the coastal and marine ecosystems of the MAR can be integrated and strengthened.

ToC evaluation is based on the analysis of the PRODOC and main findings during MTE. In the following paragraphs the ToC will be evaluated together with the Results Chain, with recommendations at the end of this section.

Results chain of the components is evaluated using the ROtI (Review of Outcomes to Impacts) tool (see annex 5.9). The aim of this evaluation is to better guide project performance and contribute to the scope of its impacts.

The ROtI approach is made up of three main stages:

- Identification of the expected impacts of the Project.

- Review of the logical framework of the Project.

- Analysis of the results-impacts pathways of the Project.

The Project aims to guide and strengthen policy, stakeholder behavior and terrestrial and marine ecosystem level management to integrate the Ridge to Reef approach at the national and regional levels. This contributes to securing sustainable economic benefits and livelihoods for the countries and their communities.

The steps towards this goal are divided in eleven outcomes organized in four components. The MAR2R Logical Framework further specifies these outcomes into outputs and activities. Following the 30 outputs and 100 activities project completion should demonstrate that:

- The countries have the enabling conditions for MAR R2R management (1.1), MAR national R2R policy (IWRM and ICM) frameworks are strengthened [linking Components 2 and 3] (1.2); MAR has a TDA and an SAP that will guide the ecoregional R2R management (1.3), and MAR strategic planning, policymaking, management, and monitoring supported with updated, reliable information accessed via Regional Environmental Observatory (REO) (1.4).

- IWRM in priority watersheds is increased (2.1); Public-private mechanisms for integrated watershed management are consolidated and supported by stakeholders (2.2), and Stakeholders engaged in IWRM in priority watersheds (2.3).

- ICMM is strengthened through capacity building and strategic planning (3.1), and Stakeholders engaged in ICMM in coastal marine prioritized areas (3.2).

- The Project’s monitoring and evaluation system employs participatory methods throughout its lifetime (4.1), and the Advantages of the ridge-to-reef approach are shared with local and international audiences, including the GEF IW: LEARN community (4.2).

The main drivers of impact identified were:

      - Financial: Close collaboration and capacity building with the private sector and other partner organizations to improve and certify sustainable practices in agriculture and aquaculture commodities, fisheries, and tourism operations.

      - Institutional: Central American Commission on Environment and Development (CCAD) effectively leads and facilitates decision-making for the four MAR country governments to adopt a ridge to reef approach to the governance and management of the shared transboundary MAR ecoregion, and the national governments, in turn, can engage civil society, private sector, and local communities in the process.

      - Sociopolitical: A coordinated regional vision is aligned with the Tulum + 8 Regional Action Plan for the MAR and CCAD’s Regional Framework Strategy on the Environment 2015–2020. Both of them were approved by the Ministers of the Environment of each country. This enhanced capacity development will prioritize gender and social inclusion as an integral component of the overall initiative.

General assumptions

- Financial: Financial commitments between many institutions support the strengthening of coastal ecosystem management in the long term.

- Institutional: Strengthening resource governance in and collaboration between all institutions involved in the focus countries (CCAD, CLME+, WWF, ASC, and others) enables them to work jointly and in an organized manner to fulfill the Project objectives.

- Sociopolitical: Implemented socio-environmental safeguards reduced risks to local communities and other vulnerable groups.

- Economic: IWRM and ICMM are most effective approaches to resource management.

- Technical: Awareness and installed technical capacities on tourism, sustainable fishing, and agricultural production are present in the MAR ecoregion.

Assumptions by component

Component 1: Strengthen resource governance and regional collaboration for integrated ridge to reef management in the MAR:

(a) CCAD has the capacity to lead regional collaboration, (b) the countries involved facilitated the development of the Project through efficient government actions, (c) regional collaboration is showcased via demonstration projects, (d) MAR regional and R2R decisions rely on updated and science-based information.

Component 2: Integrated ridge to reef management of watersheds and freshwater resources are: (a) Awareness in watersheds and freshwater increased, (b) Public-private mechanisms for integrated watershed management supported by stakeholders, (c) Stakeholders engaged in IWRM in priority watersheds.

Component 3: Integrated ridge to reef management of coastal and marine resources are: (a) technical assistance and training are well used by stakeholders, (b) Stakeholders engaged in coastal marine prioritized areas.

Component 4: Project monitoring and evaluation and knowledge sharing are: (a) participatory evaluation methods are implemented, (b) local and international audiences takes advantages from the knowledge sharing

The Theory of Change (ToC) implementation is considered satisfactory, well designed, and participatory. Stakeholders confirmed they know about it, and it has been reviewed and validated during implementation. Products and results are consistent with the ToC.

ToC and its results chains allow an understanding of the general approach, explaining the forms and logical causes of the interventions. The above identified driving factors and assumptions linked to intermediate states (regional, national, and local key actors) . The ToC presents a harmonized approach to the management of the ecoregion through strengthening the CCAD to lead and unite the environmental authorities of the four MAR countries and thus achieve a common objective.

Following ToC’s guidance to adopt a R2R approach to the governance and management of the shared transboundary ecoregion requires quality biophysical, social and economic data as input. This baseline is then analyzed by an interdisciplinary team, validated by committees like the ISNCs and made accessible to all stakeholders for effective decision making and future ecosystem governance design and implementation. Results chain fails to identify and provide appropriate ranking to key intermediate results or to show full feedback loops or explore synergies that would follow ToC as it stands. An example of this is Outcome 1.4 MAR strategic planning, policy making, management and monitoring supported with updated reliable information accessed via REO. The platform’s potential for R2R approach capacity building and decision making tool are hardly explored. An analysis of the site and information available to date shows that much work is to be done for this outcome to align with ToC. Other examples are explored in the following sections.

### Replication approach and linkages between the Project and other interventions within the sector

As mentioned above, the Project executed by CCAD through the PMU allowed direct and effective interaction with different agencies of SICA, such as OSPESCA and SITCA. The Project is also considered as model to follow to design other projects and initiatives and interact with existing ones to strengthen the regional vision and include other countries requiring a watershed approach for reef conservation. For this reason, SICA is beginning to discuss developing projects that involve other countries like Panama and the Dominican Republic, a Caribbean country that is also part of SICA. The Project also interacts with other regional projects, such as “Development of Capacities in Management and Integral Conservation of Biodiversity in the SICA Region,” with resources from the Japan International Cooperation Agency (JICA) and the Caribbean Large Marine Ecosystem (CLME+) GEF Project.

The Intersectoral National Committees (ISNC) have contributed to enhancing national watershed governance by incorporating representatives from the private sector, academia, civil society organizations, and local governments. In Guatemala, the Technical Table for the Protection of the Coastal Marine Zone functions as an ISNC to inform, discuss, and analyze Project priorities. The Ministry of the Environment leads this ISNC through one of its Local Departmental delegations.

### Country ownership

From the information collected and analyzed and the interaction with the different authorities, the evaluation team recognizes that the four countries have taken ownership of the Project and its outcomes. The PMU has been very careful to seek the approval of the national governments for the definition of the Project actions. Thus, the PMU coordinates with national authorities to address their priorities, allowing countries to take ownership of the Project results. The Project faced administration and priority changes given some concerns during supervision for administrative aspects, and the PMU presented proposals for adjustments to the PSC. The work to strengthen the actors’ capacities, including government representatives, has been vital. The involvement of governments in the development and validation of action plans, IWRM plans in 2.1.1.4 and ICMM strategic plan in 3.1.3.2., that align to with regional priorities is crucial. If governments do not accept them, the plans might not work even if the proposals are technically very sound. Their involvement allows actions to be implemented more effectively.

### Finance

The following table presents the financial information by component:

Table 3: Financial information by component at the mid-term

| Component | Expenditure to April 30, 2021 | Approved Budget | Balance | % Execution (Expenditure/approved budget) |
| --- | --- | --- | --- | --- |
| Component 1 | $ 323,089 | $ 858,890 | $ 535,801 | 38% |
| Component 2 | $ 794,099 | $ 4,294,453 | $ 3,500,354 | 18% |
| Component 3 | $ 736,885 | $ 2,576,671 | $ 1,839,786 | 29% |
| Component 4 | $ 320,679 | $ 858,890 | $ 538,211 | 37% |
| Project Management Costs | $ 190,785 | $ 429,445 | $ 238,660 | 44% |
| Total | $ 2,365,537 | $ 9,018,349 | $ 6,652,812 | 26% |

Source: CCAD-181-21 WWF GEF MAR2R Project Financial Reporting 01022021-30042021

Up to the mid-term of the Project (month 29/60), the Project executed US$ 2,365,537 / US$ 9,018,349 of the funds assigned by the GEF. It is equivalent to 26% of its budget, and by the time of this evaluation, the Project has disbursed 36% of its budget, indicating that, for the remaining life of the Project, 64% of the budget -equal to US$ 5,771,743- must be executed.

The extended delay in disbursements is due to the setbacks in the Project implementation caused mainly by the COVID-19 pandemic, the process of approvals within the constituency of the Project that set delays in recruitment and putting in place adequate staff, and climate change events that affected the MAR ecoregion, among other reasons.

Component 2 has the most considerable delays, followed by Component 3. To increase the financial execution, the PMU has been working on agreements, the signature of grants with Project partners and beneficiaries. Additionally, the CCAD has proposed to the Steering Committee to finalize the 4th year with an 80% of the disbursement, based on the accelerated scheme of the 3rd year and the commitment of the national focal points. During the interviews, focal points have confirmed this commitment and the high likelihood of Project implementation as planned.

### Co-financing

Table 4: Informed on co-financing agreements

| Source | Amount anticipated (US$) | Amount contributed at MTE | Balance |
| --- | --- | --- | --- |
| Secretariat of Ecology and Environment, Chetumal- Quintana Roo, Mexico | $ - | $ 16,405,911 | $ (16,405,911) |
| Government of Belize (Ministry of Agriculture, Fisheries, Forestry, the Environment, Sustainable Development, and Immigration | $ 7,691,252 | $ 1,157,576 | $ 6,533,676 |
| Secretariat of Environment and Natural Resources /National Commission of Protected Natural Areas -Yucatán Peninsula and Mexican Caribbean- (CONANP) | $ 3,734,685 | $3,451,464 | $ 283,221 |
| Central American commission on environment and development (CCAD) | $ 10,665,000 | $4,266,000 | $ 6,399,000 |
| Ministry of Environment and Natural Resources of Guatemala | $ 4,000,348 | $ 709,492 | $ 3,290,856 |
| Secretary of Natural Resources and Environment MiAmbiente+ Honduras | $ 9,100,000 | $ 867,527 | $ 8,232,473 |
| Global Water Partnership Central America (GWP) Honduras | $ - | $ 172,390 | $ (172,390) |
| Coastal Zone Management Authority and Institute of Belize (CZMAI) | $ 310,000 | $ 62,000 | $ 248,000 |
| SUSTENTUR | $ - | $ 310,000 | $ (310,000) |
| Fundación Defensores de la Naturaleza, Guatemala | $ 2,154,294 | $ 312,505 | $ 1,841,789 |
| FUNDAECO, Guatemala | $ 5,670,000 | $ - | $ 5,670,000 |
| MARFUND, Guatemala | $ 1,764,292 | $1,833,530 | $ (69,238) |
| Amigos de Sian Ka’an, Mexico | $ - | $ 253,199 | $ (253,199) |
| The Coca-Cola Company | $ 2,150,000 | $ - | $ 2,150,000 |
| Wetlands International | $ 160,500 | $ - | $ 160,500 |
| WWF-MAR | $ 2,000,000 | $ - | $ 2,000,000 |
| WWF-US | $ 1,137,540 | $ - | $ 1,137,540 |
| Healthy Reefs Initiative | $ 740,000 | $ - | $ 740,000 |
| Total | $ 51,277,911 | $ 29,801,594 | $ 21,476,317 |

Source: CCAD-181-21 WWF GEF MAR2R Project Financial Reporting 01022021-30042021

Up to the mid-term, the disbursement of the co-financing of the Project counterparts was US$ 29,801,594 / US$ 51,277,911. It is equivalent to 58% of the total amount. MARFund, Guatemala has already disbursed 104% of the agreed co-financing, and the Secretariat of Environment and Natural Resources /National Commission of Protected Natural Areas -Yucatan Peninsula and Mexican Caribbean (CONANP) has disbursed 92% of the agreed co-financing. The Project also received additional co-financing that was not anticipated during the Project design from the Secretariat of Ecology and Environment, Chetumal- Quintana Roo, Mexico, Global Water Partnership Central America (GWP) Honduras, SUSTENTUR, and Amigos de Sian Ka’an, Mexico. The documentation of the Project demonstrates the ability to find new sources of co-financing for some Project activities. This indicates the Project’s likelihood to secure the commitment and potentially more than the committed co-finance.

## Project Implementation

### Effectiveness

This section will evaluate progress made by outcome, based on the analysis of Project reports and documentation received in October 2021 as part of the MTR process, including information provided through interviews.

Objective level indicators

Two objectives have been fully achieved and surpassed, and one is achieved at 78%:

- By mid-term three policies are approved. Two more regional policy instruments: the Regional Blue Economy Protocol and the Regional Harmonization of Wastewater Standards Protocol await to be approved by year 4.

- Total area planned for ICMM project implementation was exceeded, with 323,600 hectares under ICCM.

- A total of 1,336,652.69 ha of watersheds are reported to be under IWRM project activities by mid-term, with 1,315,016.31 ha pending.

See table below for further details:

| Objective Level Indicators | Final Target | At Mid-Term |  |
| --- | --- | --- | --- |
| Number of regional policy instruments that promote ridge to reef management of the MAR ecoregion approved due to project activities | 2 approved | 3 approved | 150% of the target Highly Satisfactory |
| Area (ha) of watersheds under IWRM project activities | 1,699,512 ha | 1,336,652.69 ha | 78% of the target Satisfactory |
| Area (ha) of coastal and marine ecosystems under ICMM project activities | 157,800 ha | 323,600 ha | 205% of the target Highly Satisfactory |

Outcome Level Indicators

There is uneven outcome level progress across components. This is summarized below, with additional details in Annex 5.10, "Effectiveness in achieving planned results", presents a table comparing the targets set per year in the PRODOC and achieved at mid-term.

Effectiveness by Component

Component 1

Year 1 was used to learn about the project needs and necessary governance dynamics. Lack of technical ability and inherent bureaucracy impacted the progress in Outcome 1.3 and the delay to design and implement the ISNC and the MMC. WWF provided technical support to SICA/CCAD to improve their processes; decreasing bureaucratic blockages and improving their capacity to evaluate the quality and relevance of their procurement design. As a result, on December 21, 2020, a consulting firm was hired under an 18-months contract to prepare these two documents. The TDA and the SAP being prepared are estimated to be ready between the second quarter of year 4 and the end of year 5. With enough time to obtain Political Endorsement from the four MAR environmental ministries since they have been kept informed and involved in the entire process under CCAD’s leadership.

Lack of intermediate indicators, to monitor and evaluate steps towards results, and the adequate valuation of general indicators would give project execution and its M&E component more stability and effectiveness as it develops. This is the case of the TDA/SAP outcome, which has only one indicator. Given the proper valuation, TDA/SAP stands as high priority, and needed to be executed in year 1. Not in year 3. This aspect is also discussed in the ToC and results chains evaluation.

By mid-term, technical reports signalize Belize’s and Honduras’ water policies are in process, as is Mexico’s coastal policy. Finally, it was possible to exceed the goal concerning the REO, reaching more than 3,400 visitors during year 3.

Summary evaluation Component 1:

| Outcome | Effectiveness evaluation |
| --- | --- |
| 1.1. The countries have the enabling conditions for MAR R2R management | Highly satisfactory (achieved). This outcome is measured by the number of regional policy instruments developed. At mid-term, the target has been surpassed, and the approval of other policy instruments is underway. |
| 1.2. MAR national R2R policy (IWRM and ICM) frameworks are strengthened | Satisfactory (on track). The Project has strengthened the R2R approach in Belize, Honduras, Mexico, and Guatemala policy frameworks. The set target will be achieved by year 3: 2 policy instruments in Honduras (1 presented), and 2 in Mexico (NOM 001 and Coast Policy for Quintana Roo) in process, plus Water Policies for Belize and Honduras. |
| 1.3. MAR has a TDA and an SAP that will guide the ecoregional R2R management | Satisfactory (on track). The indicator is the number of countries in the MAR endorsing TDA and SAP: TDA is on a validation route, expected by Q2 of year 4. SAP preparation is a parallel process and is expected to be endorsed in December 2022. It should be noted that, although there are some delays in product delivery, according to the project results framework, the SAP is programmed to be endorsed by the Council of Ministers in year 5. |
| 1.4 MAR strategic planning, policy making, management and monitoring supported with updated reliable information accessed via Regional Environmental Observatory (REO). | Highly satisfactory (achieved). The indicator measures the number of unique visitors consulting REO in one full year; by year 3, the REO has received 3,465 visits and provided more than 400 documents. |

Component 2 
Faced by the same challenges mentioned above, the MAR2R Project was unable to engage the private sector to apply voluntary and certification standards (output 2.3.1). National priorities moved from environmental issues to health and emergency care, postponing; developing IWRM plans, contributing to public-private mechanisms, implementing demonstrations projects, and fieldwork. Moreover, the excessive workload of the Safeguard Specialists delayed the application of safeguards on demonstration projects.

Therefore, the Executing Agency requested an adaptive management approach for outputs 2.3.1 and 2.3.2, changing them to “Number of sugar and oil palm producers in the Project area implementing Better Management Practices (BMP),” and modifying their indicators accordingly.

Nevertheless, additional financial resources (161,825 USD) were raised through public-private mechanisms; therefore, only 13,175 USD are pending to meet the target (outputs 2.2.1 and 2.2.2). And it was possible to reach the target number of tourism and tourism development sector actors implementing BMPs (output 2.3.2) and the amount of participants (men and women) in IWRM workshops (output 2.3.4).

Summary evaluation Component 2:

| Outcome | Evaluation |
| --- | --- |
| 2.1. IWRM in priority watersheds increased | Satisfactory (on track). This outcome supports the development of participatory watershed or micro-watershed management plans. This is measured by the number of demonstration projects implemented and the number of stakeholders trained. By year 3, 152 women and 358 men were trained in IWRM through Project activities by year 3 (output 2.1.3), almost meeting the target set. It should be noted that documents submitted meet the target (output 2.1.1), although the IA’s technical reviewers questioned their quality in the Year 2 Support Mission Report |
| 2.2. Public-private mechanisms for integrated watershed management are strengthened and supported by stakeholders. | Satisfactory (on track). This outcome is considered satisfactory as measured by the increase (USD) in funding available for public private mechanisms in BZ, GT and HN. By year 3 there is an incremental US$ 161,825; only 13,175 USD are pending to meet the Year 5 target. |
| 2.3. Stakeholders engaged in IWRM in priority watersheds. | Moderately unsatisfactory (adaptive management requested). The Implementing Agency reported delays on year 2 due to the COVID pandemic and commented on the lack of evidence on the stakeholder analysis. |

Component 3

This component suffered delays due to:

- Inability to prepare technical proposals.

- Late arrival of the Coastal Marine Specialist as the first public tender was declared null.

- Pandemic and hurricane events put Honduras, specially, in an unprecedented situation of vulnerability.

- After a vulnerability analysis, it was shown that 9 out of 13 shrimp farm/fisheries were not interested in certification due to pandemic and administrative delays.

- Certification agencies increased standard requirements, placing the Belizean shrimp industry and the Caribbean spiny lobster management plans for Honduras at risk of not being able to comply.

The Executing Agency has requested an adaptive management approach for outputs 3.2.1 and 3.2.2 as their targets will not be achieved. Although the involvement of four communities in implementing BMP in issues related to ICMM is pending, the annual targets have been exceeded, including tourism sector actors (another exceeded final target).

Summary evaluation Component 3:

| Outcome | Evaluation |
| --- | --- |
| 3.1. ICMM strengthened through capacity building and strategic planning | Highly satisfactory (achieved). The outcome is measured by the number of stakeholders trained in ICMM through Project activities. Although some of the activities were affected due to the COVID pandemic, with 290 men and 252 women trained, the target has been achieved. |
| 3.2. Stakeholders engaged in ICMM in coastal marine prioritized areas | Moderately unsatisfactory (adaptive management requested). The number of shrimp farms and fisheries in the Project area that are reaching and/or maintaining compliance with Voluntary Standards (Marine Stewardship Council –MSC– and Aquaculture Stewardship Council –ASC) is not advancing. The Executing Agency requested an adaptive management approach for output 3.2.1 as its targets will not be achieved. However, the number of tourism and tourism development sector actors and communities implementing better management practices (BMP) to protect coastal and marine habitats under Project activities are on track (outputs 3.2.2 and 3.2.3). |

Through Component 3, the Project helped fill policy gaps by preparing the Integrated Marine Coastal Management Program for the Guatemalan Caribbean, which will follow the guidelines established in the Pacific Integrated Marine Coastal Management Program (PGIMC) for Guatemala. Both Programs will comply with Guatemala’s Comprehensive Management of the Coastal Marine Zones Policy and its National Development Plan, K'atun 2032. The Project is also consistent with the Belize National Development Framework. In Belize, the Coastal Zone Management Authority and Institute (CZMAI) has been actively involved in the Project. The Project supported updating the Belize National Integrated Coastal Zone Management Plan and sharing its lessons learned and recommendations on marine spatial planning with other countries. The plan is recognized as a best practice and model in the region, and must be updated every two years as stated by law.

Component 4

Its targets have been widely accomplished, with significant progress on content development to disseminate this Project. However, the national workshops and the IW conference suffered significant delays due to the pandemic.

The Project's products and activities have been disseminated through a communication plan, and the interviewees, in general, recognize the value of these knowledge products. Although a quality evaluation of the products obtained were not carried out, the interviewees expressed satisfaction with them. However, it should be noted that not all beneficiaries or partners are aware of all the knowledge products generated by the Project. This information was revealed while asking for particular knowledge products prepared by the Project.

By the nature of the project, quality monitoring and evaluation of results, starting at procurements, can be challenging activities as they require a more interdisciplinary view. This is why it is suggested that the implementing agency continues having a direct, clear and collaborative dialogue with the CCAD executive secretary. Likewise, collaboration between operations and financial management of the project with the technicians and staff engaged in implementation allows them to better evaluate connections and order of actions within a R2R approach. Already the result of this collaboration is embodied in the internal CCAD processes and the connection established between WWF Mesoamerica, CCAD, SICA and the INSCs. There is need to maintain this exchange of information and lessons learned for the duration of the project to increase its effectiveness.

As a final recommendation on this matter, and one that is offered in other sections of the MTE for its potential to strengthen data gathering across the network and to facilitate capacity building is to improve the REO platform. Integrating REO to data sources from the project activities and ground participant/partner activities at the watershed, coastal and regional levels.

The Project supported the development of the Regional Environmental Observatory (REO) together with other regional projects financed by JICA and GIZ. The REO will facilitate the management of environmental knowledge on the related issues of the Project. In addition, there are commitments from other initiatives and projects to continue the REO after the MAR2R Project concludes.

Summary evaluation Component 4:

| Outcome | Evaluation |
| --- | --- |
| 4.1. The Project’s monitoring and evaluation system employs participatory methods throughout the Project’s lifetime | Satisfactory (on track). This outcome is measured by the number of MAR2R progress reports completed, including the mid-term evaluation’s development. |
| 4.2. Advantages of the ridge-to-reef approach shared with local and international audiences, including the GEF IW: LEARN community | Highly satisfactory (on track). The outcome is measured by the number of communication and knowledge management products disseminated. |

Despite the fact that current disbursement is at 36%, project is well positioned; currently benefiting 50% of the total area of watersheds selected for the project, and having an above target number of regional policy and management instruments for the coastal/marine areas. Furthermore, much progress was made in capacity building and institutional alignment to integrate the R2R approach at the regional level and ready the executing partners with the necessary capacities to execute the grant agreements. It is expected for POA 4 to be substantially better in the delivery of quality products and financial resources investment.

There are plans and projections in place to achieve the expected results. For year 4, the progress projections are estimated to reach 86% of disbursement. According to the PMU, there are grants for POA 4 (provisional) to support compliance with the established percentage. To ensure its implementation, a strict follow-up and control must be carried out by the PMU, executing partners, and Steering Committee focused on intensifying field supervision, assistance, and technical execution. An additional person will be hired to ensure that the PMU has sufficient capacity to obtain all the expected results during the short remaining time and support each component manager in field supervision tasks.

Overall factors affecting effectiveness

For all components there are two main external factors that caused delays and pauses in all activities: Hurricanes Eta and Lota struck the coast on November 2020 and the COVID-19 pandemic. It was only possible to accelerate the development of the Project activities until year 3. According to the focal points and other stakeholders, the project managed to adapt to these circumstances and continue with its activities. In response to the justified delays, the Steering Committee redefined priorities regarding the actions already planned to continue implementing the Project and keep moving forward.

Internally, the start of the Project was affected by the rigidity of the host institution's administrative, procurement and contracting processes. Additionally, there was a learning curve for the Project staff and other actors involved. Nonetheless, by mid-term, this aspect was improved, as explained in Component 1, and the expected technical levels were partially achieved.

Product quality management

The executing partner’s technical capacity to receive and effectively respond to project product technical evaluation feedback from the implementing agency was mentioned to be challenging or lacking. The quality of products created during the first year were considered below par by some interviewees. We recommend further reviewing the quality of the documentation listed below:

Component 1

- Regional demonstration project (1.1.1.)

- Analysis of national policies that may include the R2R approach (1.1.2)

- Protocols for harmonized data and methods for data collection in MAR countries (1.4.1.2)

Component 2

- IWRM opportunity analysis and the IWRM action plans (2.1.1)

- On the instruments for the establishment of water reserves in MAR watersheds, review 2.1.2.1 and 2.1.2.3.

- Increase detail on the Strategy to increase membership for the Water fund, including a schedule and risk analysis and the business case study.

- Analysis of the IWRM mechanisms concerning Belize and integrate evidence mentioned in MTE.

Although the quality of the results in the documents listed above has been questioned, other stakeholders have considered they are appropriate, technically sound and have been endorsed by the PSC.

### Efficiency

Efficiency was evaluated by assessing whether the inputs or resources destined to generate products (outputs) have been converted into results (outcomes) in an economic way.

Project inputs were adequately budgeted and planned, attaining significant co-financing to cover the Project costs. Project efficiency is satisfactory despite the remaining 64% of the resources to be spent in the final year of the project. Efficiency is rated satisfactory because the project managed to optimize the resources expended and attract complementary funds while achieving or moving towards the expected results, as will be discussed below. Project partners have been able to adapt their work rapidly, and the Project was able to achieve more co-financing when other commitments were not fulfilled. A general financial analysis would show the efficiency of some actions that contribute towards the sustainable use of natural resources.

Component 1 obtained a budget of GEF USD 858,890; Co-financing USD 8,420,685, equivalent to 15% of the total budget. By mid-term Outcome level execution was at 75%, with 25% depending on the completion of the TDA/SAP Outcome 1.3. TDA is expected to be developed and approved by all ministries by the fourth quarter of year 4 (Output 1.3.1.), while the subsequent Strategic Action Plan is expected to be presented and approved by all countries by year 5. These outputs were adequately allocated 45% of Component 1 resources, and, as established in the efficiency section, the enabling technical and institutional conditions are in place for a smooth execution of these outputs.

Component 2 had expenses with a value of GEF USD 4,294,452; Co-financing: USD 24,176,566, which is 47% of the total budget. By mid-term, outcome level execution was satisfactory at 67%, with Outcome 2.1 and 2.2 fulfilling and/or exceeding indicator targets. Nevertheless, output level efficiency is low, leaving the component at a risk of non-completion. Budget allocation for Year 4 seems adequate for each output. Aggregating resources and managing activities and results in synergies could prove efficient for this component. In essence, component 2 activities and expected results aim to establish the stakeholder capacity for management and governance, data measuring protocols and market mechanisms for a multiple agro-ecosystem governance in the MAR. Following this logic component 2 could aggregate resources and collaboration in this manner:

- Stakeholder capacity building for management and governance could be established through collaboration between Output 2.1.1., 2.1.3, 2.2.1 (activity#1) Output 2.2.2 (activity#2), 2.3.3. and 2.3.4. It would be ideal if Belize River was considered in both, output 2.1.1. and 2.3.3, instead of New River, cutting cost for the responsible agent DOE/PACT and improving the detail and quality of the product for the country and lessons learned for all stakeholders involved.

- This could include Output 2.3.1, which is recommended in this MTE to focus on establishing BMPs for palm oil and sugar cane as stepping stones towards certification.

- Ecosystem services baseline and indicators and data measuring protocols (i.e. for water quantity and quality) could advance between Output 2.2.1 (activity#2) and Output 2.2.2. (activity#1). The baseline and indicators can be better informed by establishing a link with Output 2.1.2. activities.

- Finally, market mechanism strengthening and design are a combination of output 2.2.1 and 2.2.2 (activity#3). Which combines lessons learned from an established fund with the private sectors perspective (CNPLH) on the matter.

Component 3 had expenses with a value of GEF USD 2,576,671; Co-financing: USD 9,653,332, equivalent to 20% of the total budget.

By mid-term, Component 3 outcomes are rated moderately unsatisfactory, with outcome 3.1 on track and exceeding targets, while 3.2 shows no progress. The Component was allocated 23% of total budget for year 4. Resources are equally shared by both Outcomes. Outcome 3.1 focuses on developing strategic planning instruments for integrated coastal marine management and capacity building for a variety of stakeholders in the region. Outputs 3.1.2. and 3.1.3 are fully funded and with activities carried over from previous years. Other activities seem to be on track. No further information is provided on the current status of these activities. Outcome 3.2. is in need of adaptive management, as it suffered delays and may not attain its target for output 3.2.1. An interview with DIGEPESCA sheds light on the potential positive turnaround in this output. It is worth noting that 66% of funds in the outcome are allocated to output 3.2.3. There is not enough information as to determine whether this is due to activity #2, or if this activity is linked to REO and other mapping instruments in the project.

Component 4 had expenses of GEF USD 858,890; Co-financing: USD 7,537,325 equivalent to 14% of the total budget. Support costs were US$ 2,731,097, equivalent to 4% of the budget. Indirect support costs were included in this component.

Planning and projections are relevant with a view to executing slightly more than 80% of the remaining budget in the fourth year of implementation, and the Project has detailed documentation and monitoring of co-financing, including the substitution of unfulfilled commitments. The Project has attracted additional resources, and 62% of the co-financing committed in the PRODOC has been obtained. It is estimated that it will be possible to get the rest of the counterpart resources before the end of the Project. According to the Project Steering Committee (focal points of the four countries), care has been taken to prevent counterparts from duplicating other efforts both regionally and nationally, and this is presented very clearly in the progress reports.

The coordination and flow of regional and national information are mixed. Regarding the coordination and communication between the Executing Agency, the focal points, the partners, and the beneficiaries, the Project has maintained constant contact. However, among some factors that have contributed to the Project's performance are communication problems between focal points and executing partners and response times from government actors, as collected during interviews. Establishing a unifying, easy-to-use, platform for communication could help solve this issue in an efficient way. Summarized progress reports could be obtained from the platform and easily shared with executing actors and stakeholders in meetings or otherwise. Hence the importance of strengthening communication and coordination mechanisms between the PMU and the Project's executing partners within and between countries.

Capacity building in local partners and beneficiaries has been appropriate. During the interviews, the stakeholders mentioned evaluated the capacities created in the partners and beneficiaries positively. However, some institutions already had a solid structure. In other cases, the stakeholders valued the support from the technical and financial-administrative perspective and in terms of environmental and social safeguards. The Project's contribution to the finances of the different institutions was variable, with organizations that had an annual budget much higher than the Project's financial contribution and others in which the financial contribution was the main one and represented a large part of the financial resources.

The planning and annual validation have been carried out on time, and no complaints or claims have been presented between the planning of activities and the associated budget and their presentation and validation at the Steering Committee level.

### Analysis of Adaptive Capacity

The design of the Monitoring and Evaluation system, as is described in the PRODOC, is considered relevant and satisfactory. The Project developed a solid Monitoring and Evaluation (M&E) system, and it uses the lessons learned and adaptive management to monitor and meet indicator goals and mitigate project issues or any adverse impacts to the Project (pandemic). With the leadership of WWF Mesoamerica and its partners, the Project design capitalized on previous experiences.

The M&E system reviews the different levels of indicators, assumptions, and verification mechanisms. The implemented system does not differ from conventional systems. A professional oversees this activity, and necessary communication mechanisms were established to collect, verify, and report the indicators.

The M&E system is simple and updated as needed. Focal points are asked to complete it with sufficient time in advance. Nevertheless, it would be appropriate to create a dynamic, easy-to-use online system to facilitate data gathering. Similarly, interviewees noted a lack of information flow on the Project’s progress. The suggested online system can be also used as hub for sharing lessons learned and relevant data across countries and stakeholders for improved collaboration. It is important that all actors receive reports or regular feedback on the state of the Project, which would help them to understand the importance of their contributions for the achievement of the results and to promote a constructive interaction.

Regarding the indicators, some could have improvements to make the monitoring of implementation more efficient, and based on the information gathered in the logical framework and the theory of change. A column of proposed improvements are presented at the indicator level in annex 5.11. These adjustments could be taken into consideration during the analysis of the possibilities for the second phase.

Concerning the SMART analysis of the Project objectives, indicators, and targets, although the proposed results are specific, measurable, achievable, relevant, and timely. Nevertheless, it should be stressed that it is possible to measure some outcomes through the indicators, while others do not confirm attaining the outcome. In Component 1, outcome 1.4 is a case where the indicator does not really measure if REO information is updated but the number of users who visit the platform; thus, any user can visit this platform without acquiring updated information. It is recommendable that the outcome focuses on the scope of the platform. Regarding component 2, outcomes 2.1 and 2.2 stand out. In the first outcome, the number of stakeholders trained does not reflect if IWRM has been implemented. It is recommendable to include the number of Project activities that include IWRM or rewrite the outcome as 3.1. Concerning outcome 2.2, including the number of public-private mechanisms that implement IWRM is recommendable. In component 3, outcome 3.1 does not include an indicator related to strategic planning but only the number of people trained. Finally, in component 4, including a measurable goal in outcome 4.2 would be recommendable. Thus, it is recommended to consider the suggestions mentioned above and rewrite the outcomes to meet SMART criteria.

It is important to highlight that inconsistencies have been identified (See annex 5.11) between final targets in the results framework and targets included in the PRODOC. To cite an example, in “Outcome 2.1: IWRM in priority watersheds increased,” included in the PRODOC, the target for year 5 is 350 women and 350 men with increased capacities to implement IWRM management plans. However, in the results framework (annex 5.11), this final objective is reduced by half: 175 women and 175 men with increased capacities to implement IWRM management plans.

Regarding adaptive management, it has been properly proposed and validated. It has been possible to address emerging priorities of the countries, such as the Action Plan to address the white syndrome (stony coral tissue loss) , at the request of Mexico, and the Regional Strategy for Blue Growth, and the Regional Protocol for Blue Economy in response to the interest of the governments of the region, but, in particular, of the Honduran government. In addition, products and activities with possible future problems were identified and revised in advance. For instance, several actors involved in conjunction with the PMU identified problems with obtaining the certifications of the productive sector.

The COVID-19 pandemic affected the execution of the Project as mobility restrictions prevented some partners from executing some resources due to the cancellation of workshops and field visits due to the confinement measures. This affected Honduras and Mexico in particular. In addition, some actors had significant economic losses, such as oil palm producers and sugar mills, for which they changed their priorities and lost interest in participating in the certification process.

Sustainability

CCAD’s executive secretary was considered by many of the interviewees as a dynamic and trustworthy leader for the MAR2R Project and the R2R approach. This motivated and promoted an effective collaborative space between WWF and SICA/CCAD. WWF gave them technical support to improve their processes, decreasing bureaucratic blockages and improving their capacity to evaluate the quality and relevance of their procurement design. Quality checking and making processes more dynamic helped them increase their execution rate in year 3, while maintaining monitoring and transparency. CCAD’s established institutional commitment and maturing autonomy to execute the R2R approach in the MAR is a strong aspect for the project objective’s sustainability.

The expected Transborder Diagnostic Analysis (TDA) and the Strategic Action Plan (SAP) are valued by government actors. Government actors consider the application of the SAP through a second phase of the current Project or obtaining funds for its implementation. In this way, the sustainability of the Project could be executed. Socio-political actors consider all sustainable actions with public policies that will go beyond administrative periods, and that part of the success and continuity of the actions depend on external factors (market, climate).

The Project supported the development of the REO together with other regional projects financed by JICA and GIZ. The REO will facilitate the management of environmental knowledge on the related issues of the Project. In addition, there are commitments from other initiatives and projects to continue the REO after the MAR2R Project concludes.

The demonstration projects are expected to be replicable. The different pilots and demonstration projects are vital to ecoregion conservation and a priority for the countries through their national authorities. The Project was designed so that these pilot or demonstration projects could test good practices and modes of operation that give sustainability to the use of resources, and with this, different interventions could be replicated.

By year 4, private sector and public society is better informed and able to collaborate through appropriate platforms established by the project, such as ISNCs. As the project comes to an end, it is important that all documentation is accessible and useful, while agreements are upheld and updated as they are executed. All these inputs are essential for sustainability though there is no evidence for sustained actions once the Project is finished.

The counterpart commitments can support channeling more financial resources and strengthen sustainability on planned activities and public policy making processes for natural resource management following R2R approach.

Financial, sociopolitical, institutional, and environmental risks have been analyzed by the PMU and are monitored and controlled; lessons learned are applied, and adjustments are made based on adaptive management as reported by the interviews with the PMU members and the stakeholders.

### Impact

Impact level results are likely to be achieved at the regional level. Execution of all components, although faced with challenges and delays, was successful at demonstrating the advantages of the R2R approach to a wide range of stakeholders. The R2R approach manages watershed and the coastal/marine zones as multiple yet interdependent ecosystems. The interaction among environmental authorities in the MAR and the collaboration with partners both from civil society and the productive sector facilitates understanding and decision making in the region to advance in an integrated watershed and coastal/marine management through (a) policy instruments of national importance with a transboundary impact, (b) best practices to integrate sustainable practices in the productive and tourism sectors and promote public-private partnerships, (c) information sharing, training, capacity building and public awareness. The outcomes and the outputs analyzed contribute to the global objectives and the anticipated outcomes.

Several aspects of impact deserve recognition, as they are influencing the impact of the project, such as the great and important experience of the WWF Mesoamerica in the design and formulation of the Project, a satisfactory, well-designed, and participatory theory of change, and a monitoring and evaluation system well used during the execution of the Project. Also, the selection of the CCAD as an executing agency for its political leadership and because it has ensured the involvement of national governments and the strengthening of their capacities. Appropriation, involvement and empowerment by the four countries in the MAR with the interaction of the CCAD as the regional political entity. This facilitates interaction with different SICA agencies such as OPESCA and SITCA, through the CCAD, as well as with other regional projects, such as the Project “Capacity Development in Integral Management and Conservation of Biodiversity in the SICA Region” with resources from Japanese cooperation (JICA), and the Caribbean Large Marine Ecosystem Project (CLME+).

This also promotes the strengthening of regional cooperation, as well as the CCAD’s relationship with Mexico, and supports the implementation of the Tulum Declaration with a focused strengthening of national and regional initiatives. The Project has been key and strategic in addressing governmental priorities such as the Blue Economy, Tulum Agreement and Stony Coral Tissue Loss Disease (SCTLD). The Project Management Unit (PMU) is appropriate, adequate, and operates effectively and efficiently from the CCAD and this has proposed CCAD for ideas to manage and operate other projects.

The Project is showing impacts on the ground, combining and articulating agricultural, environmental, tourism, fishing, and blue economy aspects. Stakeholders and partners interviewed have identified how the project is contributing to the conservation of both biodiversity and ecosystem services while generating better environmental quality conditions for human wellbeing. The recognition of ecosystem service provision through R2R management must be coupled with strong data and analysis to effectively improve and maintain biodiversity and ecosystem services quality. The REO platform, TDA/SAP instruments and reports and documentation provided by components 2 and 3 are a strong basis towards it.

## Equality and Mainstreaming

Since the MAR2R Project is a GEF 5 Project, the GEF's Policy on Gender Equality does not apply to it. However, gender is acknowledged as a cross-cutting issue for the Project and the PRODOC (p.86) includes a section on Gender Mainstreaming with guidelines on integrating women in specific Project activities included in components 2 and 3. For example, Component 2 specifies that capacity building on participatory watershed planning, adaptation to climate change, and other IWRM relevant topics should include men and women representatives of community-based organizations, local water committees, associations, and women-specific organizations and committees in the selected watersheds. Another example is output 3.1, “ICMM strengthened through capacity building and strategic planning,” which requires equal participation of women and men in the Integrated Coastal and Marine Management activities. The gender mainstreaming is rated as highly satisfactory, since the participation of women in Project activities is considered and promoted in Project planning and management activities, training, technical assistance activities, and decision-making structures. The gender transversal strategy is monitored through the application of gender-sensitive indicators in components 2 and 3, and the Project reports include a section with information on the progress on gender-responsive measures. In addition, an Environmental and Social Management Framework (ESMF) has been prepared for the MAR2R Project to guide the design of the demonstration projects and assess and address their potential impacts.

## Stakeholder Engagement

The different partners considered in the PRODOC have played their expected roles during the implementation stage, without making any comments regarding their expected participation versus their actual participation. During the interviews, none of the interviewees highlighted that there was a lack of stakeholder involvement, and all those who had to participate and give their opinion did so. A system for the reception and treatment of complaints and claims has not been detected.

### Governance and management arrangements

The WWF-GEF Agency leads Project implementation, with CCAD as the executing partner. The Project Management Unit (PMU) is based in CCAD’s headquarters in El Salvador and has the necessary human resources. The Project Director responds to the Executive Secretary of CCAD. There is a specialist for each Project component, and there is constant communication with the focal points.

Figure 2: General arrangements for Project management and coordination

Source: PRODOC

The PMU staff hiring process was very complex. It is unclear why both the Implementing Agency and CCAD started the Project without full staffing, when adequate staffing is specifically required in the grant agreement.

Most of the actors interviewed consider the PMU personnel as appropriate, adequate, and operating effectively and efficiently from the CCAD. Nevertheless, because the next few months will be intense in terms of allocating the remaining resources, there are plans to hire an additional professional to support each component manager to strengthen field supervision tasks during the final stage of the Project.

The CCAD is the Project execution partner, and it is the regional body of the Central American Integration System (SICA) responsible for Central America’s environmental agenda. CCAD’s Executive Secretariat (ES) is responsible for overseeing the work of the Project Manager and acting as liaison between the PMU and the MAR Ministerial Council (MMC). The MMC, formed by the Environment Ministers of the four MAR countries, follows up on Project activities by approving/endorsing relevant products, and offers political coordination, and support to the Project.

The selection of the CCAD for the execution of the Project, which requires political leadership, is considered satisfactory. Although the institution had to face the challenges of having an operational unit within its structure, it recognizes that this allowed institutional strengthening, and more efficient management of information. According to the CCAD and other regional actors, the Project's design success derives from the PMU’s insertion within CCAD’s Executive Secretariat, facilitating internal communication. Thus, the PMU has provided technical support to CCAD beyond the Project, such as for developing the 2021-2025 Central America’s Regional Environmental Strategy (ERAM).

In addition, the institutional location of the CCAD has: (a) enhanced the relationship with the different authorities of the countries involved; (b) favored the relationship with SICA staff, especially in administrative terms; (c) fostered interaction with other SICA bodies and institutions, such as the Organization of the Fisheries and Aquaculture Sector of the Central American Isthmus (OSPESCA) and the Central American Tourism Integration Secretariat (SITCA); and (d) facilitated the relationship with other regional projects, such as the Project “Development of Capacities in Management and Integral Conservation of Biodiversity in the SICA Region” financed by JICA, and the Caribbean Large Marine Ecosystem (CLME +) Project.

The MAR2R Project is considered a flagship Project because CCAD had not directly executed projects for many years. This experience has shown that CCAD has the institutional capacity for it. CCAD is negotiating more international cooperation following this same governance, administration, and territorial model. Thus, the MAR2R Project was presented at one of the COP26 side events in Glasgow as a flagship Project. Moreover, there is an opportunity to use this same model with the ridge to the reef approach for other countries (Costa Rica and Panama, for example).

The MAR Technical Working Group (MTWG) is integrated by the National Focal Points (FPs) from the four countries. The FPs, named by the Ministers of Environment of each MAR country, affirm that the PMU considers them for joint decision-making as part of the Project Steering Committee (PSC). Periodic meetings are held to discuss relevant issues, present progress reports, solicit their opinions, and support decision-making. The PMU works with the FP and the executing partners to coordinate Project activities and define demonstration Projects at the national and regional levels based on the logical framework.

The MTWG collaborates closely with the PMU, the MMC, and the CCAD ES, and it also serves as the PSC. The PSC is integrated by the four focal points (one for each country), the CCAD ES, the Project coordinator, and representatives of the Project’s four components. The National Focal Points (FPs) liaison with the Ministers of Environment of their respective countries and the different actors involved in the Project. Projects are presented for their approval at the PSC meetings. Through their participation in the PSC, each FP is always aware of everything being done in all four countries. The PMU works in each country through the focal points.

The Project strengthened regional collaboration between the four MAR countries (Belize, Guatemala, Honduras, Mexico), due to the participation of the four Focal Points in the PSC and their close relationship with the CCAD, as Executing Agency. The engagement of the PSC has been strategic and ensures effective participation of and oversight by the four countries. According to FPs, the Steering Committee has met its functions, and their opinions regarding budget decisions are considered. However, it is recognized that there is room for improvement in interinstitutional communication and decision-making for Project execution. The workload of the four FPs was underestimated during the design process, making it difficult for them to fulfill all the responsibilities related to Project implementation. Understaffing, changes in government administrations, among other circumstances, have led to communication problems between FPs and executing partners. Thus, it is recommended to better guide each FPs’ ability to contribute to the timely delivery of Project outcomes.

At the national level, the Project aims to support the Inter-sectoral National Committees (ISNC) integration under the leadership of the environmental ministries and FPs. According to the PRODOC (pp. 80-81), the ISNCs act as national liaisons for the Project to advance and validate national-level policy and demonstration Project actions, with participants from the public and private sectors and civil society. Public and private sector stakeholders include those related to protected areas, agriculture, fishing, forestry, planning, hydrology, and tourism. The PMU and MTWG coordinate with the ISNCs to advance and validate national-level policy and demonstration Project actions.

ISNCs in each country have been established by building upon already existing groups expanded to include representatives from the ridge to reef continuum. In all four countries, ISNCs have contributed to enhancing national watershed governance. In Belize it is proposed the strengthening of the inter-sectoral dialogue based on a national working committee with a government base and supporting governance processes in priority watersheds (Belize River and New River). In Guatemala, the Technical Table for the Protection of the Coastal Marine Zone, specifically the Caribbean Territorial Table, which involves key local stakeholders, functions as an ISNC to inform, discuss, and analyze Project priorities. Honduras has launched a proposal to bring together multiple stakeholders in a dialogue that will ensure an integrated and focused R2R management of the Chamelecón, Motagua, and Ulúa rivers and its adjacent marine zone through effective governance mechanisms. In Mexico, the ISNC is based on watershed governance institutions; though them, the Project has supported updating the Rio Hondo Watershed Management Plan and strengthening the dialogue to address the Stony Coral Tissue Loss Disease (SCTLD) emergency. As stated before, the ISNCs have contributed to enhancing national watershed governance by incorporating representatives from the private sector, academia, civil society organizations, and local governments. The ISNCs are key for the TDA/SAP process.

Coordination and communication between Executing and Implementing Agencies for the benefit of the Project performance appear not to have been ideal at the beginning of Project implementation. WWF’s experience in executing projects led to expectations of the PMU and executing entities to deliver in a certain way and with expediency. The Implementing Agency offered training and induction processes to the PMU, CCAD, and SICA’s administrative staff to address these initial difficulties. Moreover, WWF-GEF Agency has been continuously available to provide technical assistance and training as required by the PMU. In 2021, there were changes in WWF-GEF Agency’s personnel in charge of supervision to improve coordination and communication and benefit Project implementation as approved and agreed in the PRODOC and the different work plans.

The PMU and CCAD recognize the excellent technical advice from the WWF-GEF Agency on shrimp and lobster certification processes and mangrove restoration, subjects on which it is evident that the Agency has paid a great degree of attention, providing extensive feedback. Moreover, interviewees considered that the support received for strengthening capacities for applying safeguards has been outstanding.

Table 6 includes an assessment of the most relevant Project partners.

Table 5: Detailed assessment by Project partners

| Partners | Role | Assessment |
| --- | --- | --- |
| Amigos de Sian Ka’an | Participate-coordinate in IWRM and ICMM activities related to aquifer and freshwater critical habitats, and to coastal and marine habitats development stakeholders in Project areas. | The relationship with this organization has been highly satisfactory. Amigos de Sian Ka’an has been working as an executing partner, with CONANP as focal point, coordinating IWRM and ICMM activities in Mexico. They have complied with safeguards and have led several activities, such as involving the private sector in the conservation of aquifers and critical habitats, by implementing a better practice guide, in coordination with CONANP and CONAGUA. Centinelas del Agua has been working in areas also related to those of Amigos de Sian Ka’an. |
| Centinelas del Agua | Participate-coordinate in IWRM activities related to aquifer and freshwater critical habitats with development stakeholders in Project areas. | The relationship with Centinelas del Agua has been highly satisfactory. Centinelas del Agua began its participation as an executing partner at the request of CONANP, since the beginning of 2021. It has worked in the development of two watershed management programs and in the proposal of a demonstration Project in the north of Quintana Roo and, in particular, in the Tulum watershed. This organization had to develop its capacities to address social and environmental safeguards. |
| CZMAI-Belize | Act as the core of the ISNC in Belize, and participate-coordinate ICMM activities | The relationship with Belize’s CZMAI has been highly satisfactory. They have shared their experience and lessons learned on ICMM with other countries through a webinar on coastal-marine planning. They have also shared the software used and will further develop training and capacity building. They have participated actively in regional activities. |
| Fundación Defensores de la Naturaleza, FUNDAECO, and MAR Fund | Participate-coordinate in IWRM and ICMM activities with community stakeholders in the Project areas and related to coral and mangrove restoration. | The relationship with these civil society organizations has been highly satisfactory. They have actively participated in the implementation of the Project as executing partners and their capacities for the application of safeguards have been strengthened thanks to this collaboration. MarFund is involved in regional activities related to the Regional Demonstration Project in mangrove and coral restoration, REO, and work with regional networks and platforms, among others. Moreover, MARFund is involved in essential regional activities related to the Regional Demonstration Project and other demonstration Projects, mangrove and coral restoration, the REO, and other regional networks and platforms |
| OSPESCA and SITCA | Responsible for activities related to fishing and tourism under their responsibility, at the SICA level. | The relationship with these regional SICA organizations has been highly satisfactory. Thanks to the Project's link with these two regional organizations, the Project has transcended the MAR region and has influenced the positioning of the ridge-to-reef approach in other SICA countries. |

## Safeguards Review

Environmental and social safeguards were present and recognized by all parties. The gender approach is reflected in the PRODOC (Project document), and the equitable participation of women in all Project activities has been encouraged. Nevertheless, risks and potential impacts were identified, except for the pandemic. As a conservation initiative Project, adverse or unforeseen environmental and social impacts are greatly reduced by creating positive and long-lasting environmental and social benefits, including better agriculture practices and restoration of critical coastal and marine habitats like coral reefs. All of these within the framework of gender equality.

The application of safeguards has favorably influenced the execution of the Project. In the interviews carried out with implementing partners, it was possible to perceive that the safeguards contribute to issues that they had already been working on previously, and in other instances, it was a new issue to apply and required training from the executing and implementing agencies. The evaluation team perceived that the application of the safeguards favored the implementation of the demonstration projects. Until the moment of the MTE, there have been no mishaps in environmental and social terms. On the other hand, as these are projects that support the environment and social benefits, the good acceptance of the communities involved in the demonstration projects is determined. Partners have recognized its implementation, and some have capitalized on the approach.

The executing partners could apply the safeguards and strengthen their inclusion and transparency policies, among others. In Guatemala, work was done to ensure that some of the materials were accessible in the languages of the Mayan Quekchí and Garífuna peoples. For this, they will coordinate with the Academy of Mayan Languages of Guatemala. In Honduras, the Safeguards Week had the purpose of raising awareness and learning to implement them, with the active participation of Project representatives. Additionally, a virtual diploma course that focuses on explaining and implementing the safeguards is being prepared. Several actors consider that the support received by the WWF-GEF Implementing Agency to strengthen the capacities of the executing partners in the application of safeguards has been very important.

According to the focal points, identifying risks in the formulation phase allowed one to know in detail through interviews and visits to the sites where the Project would be carried out, the types of possible risks, and implementing a plan to mitigate them. For example, in Honduras, one aspect that could have generated a conflict according to the focal point was the creation of micro-watershed councils that meant organizing people from the interior of the country; however, this has been possible.

The original incomplete MTE report carried out by a different evaluation team concluded that compliance with safeguards was progressing well. Even though there were concerns regarding the pace of preparation and approval of safeguards documents, this was not considered a bottleneck. Regarding whether appropriate environmental and social safeguards were taken during Project design and implementation, the original MTE report only determined that safeguards were implemented in the demonstration projects and that some grantees required support from the Executing Agency (who had some delays in responding) to develop their environmental and social safeguards. This finding could be linked to the Project progress reached when preparing the original MTE report. The previous MTE reviewed the final approved safeguard document of one of the grantees and agreed with it. The safeguards were rated as highly satisfactory.

This evaluation team agrees with the original MTE regarding some grantees' request for support to the executing agency for the development of environmental and social safeguards in their demonstration projects.

# Conclusions, Recommendations & Lessons

## Conclusion

The Project’s overall progress is satisfactory, and its implementation is moving towards achieving the expected results. The CCAD is effective in leading and facilitating decision-making for the four MAR country governments (Belize, Guatemala, Honduras, and Mexico) in adopting a ridge-to-reef approach to the governance and management of a shared transboundary ecoregion. WWF showed comparative advantage as the implementing agency with great experience in the region. This evaluation concludes that the Project design and formulation, including the TOC, was and remains relevant. This is evidenced by widespread support for the TOC, as well as signs of regional and national government support for the R2R approach and the Project in general. The Project was found relevant for strengthening national efforts and responding to governmental needs, complementing other projects, expanding, and consolidating the work WWF Mesoamerica has been doing while promoting collaboration and discussion between stakeholders involved in this ecoregional landscape. The work done thus far has been led by a strong PMU, that played a crucial role in strengthening the CCAD and interacting positively with SICA. The demonstrative projects and the study developed at the mid-term indicate that the Project is contributing to maintaining and improving the ecological integrity of the watersheds and the coastal-marine ecosystems of the MAR. Replication is ensured by a communication and dissemination strategy that is functioning well. This evaluation concludes that the Project presents strong internal and external coherence, aligning with multiple regional and national policy instruments and trends. Progress toward results is different across all four components.

While the Project design was ambitious for the available resources, most of the output targets are being achieved across all the components, with differential progress. Addressing the delays and reaching targets must be prioritized to balance and advance homogeneously towards completing the four Project components. The low disbursement at mid-term (26%) is explained by a series of external and internal factors that delayed investment. PMU guided overall project adaptation, strengthening current capacity and creating the enabling conditions to move forward. Disbursement by 3rd year is at a low 36%. Nevertheless, POA for year 4 provides the roadmap to reach a high level of disbursement (80%), leaving a 20% for the last implementation year. The likelihood of reaching this 80% greatly depends on the control and monitoring of activities. Projections are correct, and most grant agreements have already been signed; thus, there are two sets of data for the budgetary situation, the amount spent (already paid) and the amount committed (with contracts signed but not disbursed yet).

Finally, based on the evidenced findings and conclusions regarding effectiveness and efficiency, reciprocal collaboration between the Implementing Agency and the Executing Agency is necessary to advance towards the successful implementation of the Project with a potential extension of the Project time to secure the pertinent deliverables. Below are lessons learned and recommendations that could inform and better guide this and other processes.

## Key lessons learned

- The PMU is inserted within the Executive Secretariat of the CCAD. In a political body with regional characteristics, the implementation and coordination unit of a Project part of the institutional arrangement has advantages and improves the relationship among the different political bodies and the reception to the territory based on a regional vision.

- The integration and support of the Project (MAR2R) to the activities planned by the countries in the MAR ecoregion. Any Project inserted in a regional political entity must ensure that planning with a regional perspective, respects and complements national priorities under a cross-border regional vision. This is considered an essential practice envisaged during the Project design phase.

- Prioritization of actions and optimization of resources. Reformulating priority activities due to situations such as the pandemic and extreme weather phenomena serves as the basis for reinventing and adapting Project activities. Therefore, every Project must foresee the prioritization of actions and the optimization of resources in the face of emerging situations. It must lay the foundations for a plan of action. This is important to consider during Project design to facilitate adaptation during implementation, especially in changing socio-political environments.

- Capacity of Project partners. It is essential to identify the technical and administrative capacity of all partners and beneficiary groups. If applicable, pertinent diagnoses must be made to implement improvement plans, and not delay the implementation processes. Partners identified in Project design or those identified during implementation should consider capacity assessments as a key step to ensure field activities.

- The importance of roles and responsibilities in the Steering Committee and PMU. The Implementing and Executing Agencies and their authorities must have roles and responsibilities that are clear and agreed in advance, with a monitoring plan and frequent meetings that allow progress to be evaluated and specified appropriate control and intervention measures. This applies to both the Project design stage and agreements during implementation.

- Capacity and volume of work of the focal points. There is a need to assess the capacity and volume of work and due diligence of the national focal points. These are political instances of national environmental agencies with an additional workload at the national level and in need of supranational coordination. Therefore, availability and capabilities must be known in advance, if possible, at Project design stage and reinforced if necessary. Reinforcement may mean recruiting personnel to facilitate internal processes within the scope of focal points’ tasks.

- Result specificity is a commitment that has risks. It is crucial to establish the objective and impact of a specific product in this type of Project. However, demanding details so far in advance with changing socio-political and environmental situations increases the chances of non-compliance. Therefore, results should be more general and not so specific. This is a common aspect of some projects requiring particular actions that may not be adapted to the changing environments during Project implementation.

- Addressing changes in government authorities. One of the aspects that facilitated rapid response to changes in government authorities is that the PMU’s team has not changed. Personnel continuity has ensured the continuance of Project activities, and PMU staff have provided information and accompanied the new government representatives throughout their learning curve. This lesson learned is common to many projects in which governmental bodies are involved; however, mitigation measures are hard to determine. The role of a strong PMU is crucial.

- Adaptive management is key to providing flexibility so that the Project can deliver the expected results even in highly changing environments. There are always different ways to reach the same goal, so that this flexibility must be considered preferably before Project implementation or, if possible, during Project design.

- The M&E function is critical in identifying the information needs of the diverse stakeholders. Adaptive and flexible skills have to be built in to respond to the information needs as different circumstances may arise during the various stages of the Project’s life. A clear function and how the M&E is linked to the Project life cycle must be clearly designed and controlled during implementation.

Box 1. Several positive aspects deserve highlighting, among them:

- The Project Management Unit (PMU) is appropriate, adequate, and operates effectively and efficiently from the CCAD. Satisfactory selection of the CCAD as an executing agency for its political leadership and ability to facilitate interaction between different SICA agencies and other regional projects. The institution is also strengthened by its involvement and actions in the project.

- Satisfactory, well-designed, and participatory theory of change.

- M&E system relevant and satisfactory, and well used during the execution of the Project.

- CCAD has ensured the involvement of national governments and the strengthening of their capacities.

- Promoting the strengthening of regional cooperation, as well as the CCAD's relationship with Mexico, and supports the implementation of the Tulum Declaration.

- Inclusion of the Blue Economy, Tulum Agreement and Stony Coral Tissue Loss Disease (SCTLD) to address government priorities.

- Lobbying with local governments and partnerships to define priorities.

- Environmental observatory platform for systematization and dissemination of information (Regional Environmental Observatory – REO)

- Regional vision of development and conservation: as an example, the vision of tourism through the Regional Vision of Social and Sustainable Tourism in the MBRS, developed in a participatory manner and the Regional Strategy for Mangrove Management, Conservation, Restoration and Monitoring in the Mesoamerican Reef.

- Training is important and has been developed thanks to virtuality (although the standardization of information collection needs to be improved).

- Optimization of resources adapting to virtual modalities.

- Sustainability of the project through partnerships with the ministries of environment of the countries of the ecoregion which commit the continuation to manage the conservation projects from the ridge to the reef as national priorities.

- Adaptability to climate challenges and the COVID-19 pandemic, capacity, and management of adaptation to challenging and emerging situations.

- Application of safeguards and strengthening the capacities of implementing partners to implement them.

## Practices for other similar projects to replicate or avoid

Best practices emerging from the Project include:

- Adaptive capacity and management to challenging and emergent situations, taking the necessary measures to identify the risks and mitigate the impacts, including the COVID-19 pandemic.

- Effective engagement and use of cloud-based video conferencing platforms to carry out events virtually with new skills applied and the acquisition of other practices of interaction. This may reduce costs and possibilities of constraints, maximizing the time devoted to personal interactions.

- The expertise of a global civil society organization such as WWF is delivered to a regional and integrated governmental coalition to advance the conservation of a highly important biodiversity area.

- Strong Project team, with emergent personality whose capacity for communication, technical advice, cooperation willingness, leadership and commitment stand out.

- Integration of Project activities in regional strategies already being developed in target sites and ecosystems brought together in one vision for a biodiversity hotspot.

Practices to improve include:

- Monitoring could be more meaningful at the outcome level. The level of outcome/impact should be broadened to capture and disseminate the positive effects and how this could be institutionalized in public and/or private sectors to make them sustainable.

- Communication and knowledge exchange at program level is mandatory to disseminate good practices and errors, enrich the learning and feedback processes, and secure that the technical information provided is controlled.

- Elaboration of a gender analysis and action plan during the Project development phase to ensure integration and proper mainstreaming of gender equality issues and women's empowerment.

- Appraise the need of a grievance mechanism for the Project level beneficiaries and the public, in general, to provide not only complaints but also recommendations or views from the field to better improve the Project.

## Recommendations

A list of recommendations is provided in response to the 9 findings in effectiveness, efficiency, sustainability, adaptive capacity, and gender. In areas of Project relevance and coherence, there are no specific recommendations.

| Effectiveness |  |
| --- | --- |
| Finding 1: Since 70% of the Project duration has elapsed with only 36% of resources executed, the remaining 64% must be invested in the 15 months remaining (30%). |  |
| Recommendations | Responsible Entity |
| - Organize a workshop with the participation of the Implementing and the Executing Agencies to adopt a clear road map to guide diligent efforts to improve and accelerate the implementation of the remaining outcomes/outputs, with the spirit of adaptive management and under the leadership of the PMU and the accompaniment of the PSC. - Strengthen the capacity of focal points (with the identification of needs) in each Project implementation zone to contribute to timely delivery of Project outcomes. This could be done through routine performance analysis to identify the strengths and opportunities for improvement. - Establish adaptive management changes to components 2 and 3. See recommendations included under Adaptive Capacity. - Assure progress towards objective indicator “Area (ha) of watershed under IWRM Project activities.” According to annex 5.10, the percentage obtained at year three is 84.18%: 1,336,652.69 ha out of 1,587,934 ha. - Present a proposal for extension of ideally 12 months with a clear justification and action plan to achieve pending outputs. - Reschedule and continue to prepare a critical route path to align activities related to certifications in components 2 and 3 to the targets defined in the results framework to contribute to their achievement. - Identify all stakeholders with/in the process of certification and coordinate meetings/encounters to foster collaboration and knowledge sharing, helping them contribute to each other’s process. Bring case studies that are in the Project’s scope such as DIGEPESCA and the RARE experience in Honduras. | PMU, Steering Committee, and Focal Points |
| Efficiency |  |
| Finding 2: Internal and external communication gaps affect timely Project implementation |  |
| Recommendations | Responsible Entity |
| - Prepare a critical route with specific steps to implement the communication strategy developed in 2019 to ensure that the Project’s constituency have all the necessary information. - Review and adjust the communication channels between the PMU and the executing partners to support opportune and informed decision-making processes. - Identify and Implement best communication strategies, tailored for target beneficiary groups to improve project transparency and communication (i.e. e-mail newsletters, website, videos). - Use the Regional Environmental Observatory platform as a communication channel, based on established safeguards. - Monitor and implement the Risk Management Measures related to effective communication. - Evaluate the M&E capacity to ensure compliance with deadlines and follow-up activities, identify best strategies when necessary. - Ensure that focal points use the detailed critical path with dynamic Project management software and hold regular meetings. - Hold periodic progress reporting meetings with the participation of key execution partners so that they better understand Project results and promote the exchange of experiences. | PMU, Steering Committee, and Focal Points |
| Finding 3: Some disagreements or complaints from project level stakeholders lack adequate channels for being duly communicated and pertinently addressed. |  |
| Recommendations | Responsible Entity |
| - Appraise the need for a simple but effective online grievance mechanism for complaints from project level stakeholders and beneficiaries to submit their complaints to the PMU. An anonymous option for presenting a complaint is recommended. - Designate a person within the PMU to address complaints effectively. | PMU and Focal Points |
| Finding 4: Lessons learned from Project implementation, good practices, gaps, and general interaction meetings should be improved. |  |
| Recommendations | Responsible Entity |
| - Identify, systematize, and disseminate lessons learned opportunely through the REO from the Project to be shared with the entire constituency. - Conduct periodic workshops where partners, beneficiaries, and key stakeholders can share and learn about Project progress and lessons learned. Ensure there is adequate systematization and dissemination of the information, conclusion and recommendations for their implementation. | PMU and Focal Points |
| Sustainability |  |
| Finding 5: The Project has received great support from the Ministries of the Environment of the four countries in the MAR ecoregion and is very relevant to CCAD and its partners. An exit strategy needs to be developed to sustain the results and outcomes beyond the life of the Project. |  |
| Recommendations | Responsible Entity |
| - Plan a sustainability strategy or exit strategy that makes explicit what is needed to keep the effects of the Project. The strategy should define a transition to ensure the institutionalization of the lessons learned, and the adoption of good practices, both at the national and regional levels. The budget of the responsible entities should be ensured when relevant. - Once the term is extended, coordinate the preparation of the exit strategy; the PSC must endorse this strategy. - Improving data gathering across the collaborative network and to facilitate capacity building towards R2R regional governance with quality mapping and decision making instruments such as the REO platform. Which needs to be evaluated and improved. Integrating REO to data sources from the project activities and ground participant/partner activities at the watershed, coastal and regional levels. | PMU and Steering Committee |
| Adaptive Capacity |  |
| Finding 6: There are areas of improvement in the application of the Logical Framework Matrix. |  |
| Recommendations | Responsible Entity |
| - Validate the Logical Framework Matrix to prioritize actions as part of the strategic planning for the remaining Project implementation. - Rewrite indicators for some outcomes to improve their understanding. For example, it would be recommendable to rewrite the indicator for outcome 1.4, which does not reflect the expected result. Other indicators that should be rewritten are highlighted in annex 5.11. - Solve the differences found in outputs 2.1, 3.1, and 3.2 between what is stated in the Results Framework in the Project Document (pages 182 and 183) and detailed in the Project reports (see comments in annex 5.11). | PMU with Steering Committee and Implementing Agency |
| Finding 7: The M&E reporting does not reach all stakeholders (direct and indirect). |  |
| Recommendations | Responsible Entity |
| - Develop a more effective online M&E system to reach more beneficiaries. - Enhance the M&E function to ensure better reporting and monitor the technical quality of the documents presented as Project outcomes. M&E responsibilities should include providing feedback to the Project staff, executing partners, and relevant stakeholders. - Ensure that the M&E responsible staff prepares timely reports (including changes, risks, lessons learned, gaps, among others) to share with all Project partners, and stakeholders and disseminate through periodic newsletters based on Project reports (through Mailchimp, for example). | PMU and Focal Points |
| Finding 8: The Project might not achieve the outcomes related to certifications of the productive sector. |  |
| Recommendations | Responsible Entity |
| - Modify the indicators regarding reaching or maintaining compliance of certifications to reflect the current needs of each productive sector involved. The PMU has already prepared a proposal to modify the indicators. The evaluation team concludes that it is coherent and recommends to: - Prioritize activities to identify potential companies to be certified. - Develop a certification guide based on lessons learned, including the current needs of each productive sector. - Consider enabling the productive sector for future certifications (e.g., Better Management Practices). - The recognition of ecosystem service provision through R2R management must be coupled with strong data and analysis to effectively improve and maintain biodiversity and ecosystem services quality. The REO platform, TDA/SAP instruments and reports and documentation provided by components 2 and 3 are a strong basis towards it. | PMU and Implementing Agency |
| Equality and Mainstreaming |  |
| Finding 9: The Project did not formally consider a gender approach though most Project activities have encouraged gender inclusion |  |
| Recommendations | Responsible Entity |
| - Develop a Project policy and Monitoring, Reporting and Verification (MRV) on gender mainstreaming based on current social safeguards. - Strengthen the proposal based on gender safeguards, linked to WWF’s gender policy (mentioned in PRODOC), as a basis for equity in access to Project benefits and ensure equitable participation of all parties. | PMU and Focal Points |

# Annexes

## MTE ToR (excluding ToR annexes)

Cover Page

| POSITION DETAILS |  |
| --- | --- |
| Location | Mesoamerican Reef ecoregion (Mexico, Belize, Guatemala and Honduras) |
| Reporting to | Amelia Kissick |
| Preferred timeframe | September 2021 - November 2021 |
| Potential sites to visit | TBD. Recommended: Cancún, Mexico and San Pedro, Honduras |
| Maximum budget | $25,000 |
| PROJECT DATA |  |
| Project/Program Title | Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R) |
| GEF Project ID | 5765 |
| WWF (Agency) Project ID | G003 |
| Implementing Agency(s) | World Wildlife Fund |
| Executing Agency | Central American Commission on Environment and Development |
| Executing Partner(s) | Ministries of Natural Resources Belize, Guatemala, Honduras and Mexico |
| Countries | Belize, Guatemala, Honduras, Mexico |
| Focal Area(s) | International Waters |
| GEF Operational Program | GEF 5 |
| Total GEF Approved Budget | $ 9,830,000 |
| Total Co-financing Approved | $ 51,277,908 |
| RELEVANT DATES |  |
| CEO Endorsement/Approval | 04/04/2017 |
| Agency Approval Date | 27/10/2017 |
| Implementation Start | 01/11/2018 |
| Project Completion Date (proposed or actual) | 31/12/2022 |
| Period to Be Evaluated | 01/11/2018 – 04/30/21 |

Introduction and Project overview

World Wildlife Fund, Inc. (WWF) policies and procedures for all GEF financed full-sized projects require midterm evaluation (MTE) and the identification of relevant recommendations. The following terms of reference (TOR) sets out the expectations for the MTE for the project: Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R), hereafter referred to as the “Project.” The technical consultant selected to conduct this evaluation will hereafter be referred to as “evaluator.”

The Project seeks to support regional collaboration for integrated ridge to reef management of the MAR ecoregion by demonstrating its advantages and improving regional, national, and local capacities for

integrated management and governance of its freshwater, coastal, and marine resources. The Project has four interrelated components designed to scale up existing baseline programs to address key threats and barriers to the integrated management and conservation of the MAR. The Project was organized into the following components:

- Strengthen resource governance and regional collaboration for integrated ridge to reef management;

- Integrated ridge to reef management of watersheds and freshwater resources;

- Integrated ridge to reef management of coastal and marine resources; and

- Project monitoring and evaluation, and knowledge sharing.

Scope and Objective for the evaluation

WWF is seeking an independent consultancy to undertake a Midterm Evaluation (MTE) of the Project. The scope of the MTE will cover the GEF financed components.

The objective of this MTE is to examine the extent, magnitude, and sustainability for Project results to date; identify any opportunities to improve Project design; assess progress towards Project outcomes and outputs; and draw lessons learned that can improve the Project effectiveness, efficiency, and sustainability of Project benefits. Based on this assessment, it is expected that the evaluator will provide feasible recommendations that could be applied for the remaining duration of the Project.

An MTE has already been conducted under challenging circumstances in 2020, and this new MTE shares the above purpose and scope, with additional interviews and data collection, the identification of relevant recommendations, as well as the review of the preliminary findings of that MTE.

Evaluation approach and method

The evaluation will adhere to the relevant guidance, rules and procedures established by WWF and align with guidance from the GEF Terminal Evaluation and Ethical Guidelines. The evaluation must provide evidence‐based information that is independent, participatory, transparent, and ethical. The evaluator must be unbiased and free of any conflicts of interest with the Project. The evaluator is expected to reflect all stakeholder views and follow a participatory, inclusive and consultative approach. There should be close engagement with WWF GEF Agency (IA), government counterparts, the GEF operational focal points in each country, CCAD as the Executing Agency (EA) / Project management unit (PMU), partners and key stakeholders. Contact information will be provided.

The Evaluation process will include the following, with deliverables marked by “*”:

- Inception meeting with WWF, CCAD, and Project Steering Committee to gather input from select Project stakeholders on evaluation approach, to agree on methodology, and to inform the inception report;

- Desk review, including but not limited to the following documents:

  - Project Document and CEO Endorsement Letter;

  - Support Mission Reports;

  - Annual Work Plans (AWP) and Budgets;

  - Project Progress Reports (PPR) including Results Framework and AWP Tracking;

  - Inputs from original MTE, including interview transcripts, original evaluation debrief and draft report with consolidated feedback.

- A succinct inception report* in English that outlines evaluation approach and methodology (will be reviewed by EA and IA);

- Key informant interviews to include members of the Executing Agency, members of the steering committee, members from WWF-US and implementing agency (IA) and any additional stakeholders deemed relevant to include by above Project stakeholders. The exact number of interviews will be determined in the inception report and will be relative to any other data collection method utilized and the compressed timeframe of this exercise. Focus groups may include Project Steering Committee, thematic champions and platform/alliance leaders. Ensuring participation in interviews, focus groups and workshops to ensure all stakeholder voices are heard is essential;

- To be determined during the inception phase, additional data collection methods may be triangulated with the KIIs, however this will need to be carefully considered relative to what is realistic, necessary, and efficient. This will be determined in consultation with IA, EA and Evaluation Manager. Examples of additional methods include a survey for key stakeholders enumerated online, and/or a participatory workshop for collective opinion sharing and analysis;

- Debrief and presentation* of initial findings to select Project stakeholders (e.g., the EA, PMU, PSC and GEF Agency) for feedback and final data collection. Feedback log requested to record responses to comments received;

- Draft MTE report in English and Spanish* shared with select Project stakeholders for review and feedback. A sample outline is provided and will be agreed at inception phase; and

- Final MTE report* that has addressed any inaccuracies and taken into consideration any feedback and comments. This report should be prepared in English. Note that WWF GEF Agency Management Response and CCAD Review Response will be annexed to report submitted to GEF.

The WWF methodology for conducting Project evaluations is a key element of our adaptive management approach. Typically, the MTE is framed using seven (7) core criteria of relevance, coherence, effectiveness, efficiency, results/impact, and adaptive capacity, where relevant and feasible, (for which definitions and templates are annexed in this ToR). However, for the second round of the MTE, (potential for) impact is not to be included, unless particular findings become apparent and useful to share.

Another key consideration for the MTE methodology is existing stakeholder sensitivities of preliminary evaluation findings. Given this, the method refinement during the inception period will consider what would best support establishing credibility and legitimacy for the MTE with key Project stakeholder input to inform the process.

Expected Outputs of Evaluation Report

The Midterm Evaluation report will include:

  - Information on the evaluation, including when the evaluation took place, participants and key questions.

  - Key findings by core criteria. Should interrogate preliminary findings already identified, include identification of progress made, key strengths, successes, challenges and shortcomings;

  - Rating Summary Table with ratings for Outcomes, Risks to Sustainability, Implementation, Execution, M&E design and M&E implementation;

  - Analysis of risks to the sustainability of Project outcomes;

  - Review of Monitoring and Evaluation systems: design and implementation;

  - Previous MTE assessment on gender responsive measures may be adopted, supplemented with further assessment of stakeholder engagement;

  - Include previous MTE assessment findings and conclusions on whether appropriate environmental and social safeguards were taken during design and implementation; and inclusion of new assessments /monitoring/ plans or reports relating to environmental and social safeguards as necessary;

  - Assessment of WWF GEF Agency, PMU and Project partners;

  - Lessons learned regarding: Project design, objectives, and technical approach; use of adaptive management; administration and governance arrangements; relevance; implementation of the work plan; achievement of impact; environmental and social safeguards, etc.;

  - Conclusions, and recommendations that include practical and short-term corrective actions per evaluation criteria to address issues and findings; recommendations on best communication and support practices, best practices towards achieving Project outcomes and replication for other Projects of similar scope.

Desired Qualifications

- Minimum 15 years of relevant professional experience (e.g., as a lead or member of an evaluation team);

- Experience with GEF financed projects and knowledge of GEF Monitoring and Evaluation policies;

- Experience with participatory evaluation, social assessments, and both quantitative and qualitative evaluation methods;

- Experience in the region and familiarity with intergovernmental organizations, particularly CCAD / SICA.

- Technical knowledge related to the Project (e.g., integrated watershed management, International Waters GEF Focal Area, etc.) is an asset;

- Familiarity with Conservation Standards or WWF Project and Programme Management Standards, including emphasis on theory of change is an asset;

- Knowledge and experience implementing or reviewing application of social and environmental safeguards policies in GEF (or similar) projects preferred;

- Fluent in written and spoken English and Spanish;

Payment modalities and specifications

Payment, expense reimbursement, and other contractual terms and conditions are outlined in the consultant agreement made between WWF and the evaluator(s). Payments are according to deliverables submitted. Twenty-five percent of payment will correspond with completion of Inception Report and data collection tools. Fifty percent of payment will correspond with submission and approval of the Draft Report. The final twenty-five percent will be delivered with the submission and approval of the Final Report.

Application Process

Applicants are requested to e-mail their applications to amelia.kissick@wwfus.org by August 27, 2021. Consultants are invited to submit a technical proposal and financial proposal with their curriculum vitae. The price offer should include daily fee, per diem and travel costs and should not exceed USD $25,000. The selection of candidates and contractual agreements will be in compliance with WWF procurement policies and subject to GEF requirements.

WWF applies a fair and transparent selection process that will take into account the competencies/skills of the applicants as well as their financial proposals. Women and members of social minorities are encouraged to apply.

## MTE evaluation matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)

| Criteria / Evaluation Question | What to look for? / Possible indicators | Information sources | Information collection methods |
| --- | --- | --- | --- |
| Relevance |  |  |  |
| The extent to which the Project design, outcomes, indicators, and targets remain valid and consistent with local and national development priorities and organizational policies, including the context of the changing circumstances of the country (e.g., political context); |  |  |  |
| Is the current strategy, and the theory of change that it’s based on, clear and is it still valid? Are the strategies and approaches still the most appropriate? | Level of coherence between Project strategy and implementation approach. Analysis of the achievements by the interviewees. | - PRODOC - Project strategy - Project Framework - Theory of Change | - Document review - Interviews with Project staff and key stakeholders |
| Is it necessary to make any changes to the Project concept that have not yet been made? | Clarity, relevance and feasibility of the objectives and results. | - PRODOC - Project Framework - Theory of Change - Results framework | - PRODOC - Project Framework - Theory of Change |
| Are the objectives and expected results realistic and concrete? | Clarity, relevance and feasibility of the objectives and results. | - PRODOC - Project Framework - Theory of Change - Results framework | - Document review - Interviews |
| Are the components and results of the Project clear, practical, and feasible? | Clarity, practicality, and feasibility within Project time frame of the components and results of the Project. | - PRODOC - Project Framework - Theory of Change - Results framework | - Document review - Interviews |
| Was the inclusion and / or adjustment of some indicators proposed? | Indicators of the Project. Analyze modifications. | - PRODOC - Project Framework - Results framework - Stakeholder interviews | - Document review - Interviews |
| Were the lessons of other similar projects appropriately incorporated into the Project design? | Lessons learned about the design of similar projects. Integration of lessons from other Projects. | - Project strategy - PRODOC - Project Framework - Theory of Change - Lessons from other relevant projects | - Document review - Interviews |
| Does the Project’s objective align with the priorities of the local government and local communities? | Alignment with local government and local communities’ priorities. | - National and local development plans or strategies | - Document review - Interviews |
| Does the Project’s objective fit within the national environment and development priorities of the countries and regional priorities of intervention? | Alignment with each country national environment and development priorities, strategies, and legislation. | - PRODOC - National environment and development priorities as stated in government plans or legislation in each country | - Document review - Interviews |
| Did the Project concept originate from local or national stakeholders, and/or were relevant stakeholders sufficiently involved in Project development? | Stakeholder engagement approach during the Project design and implementation. | - Reports on enquiries made - Inception Workshop Report - WWF Environmental and Social Safeguards compliance report - Actors interviewed | - Document review - Interviews |
| Is the Project objective aligned with GEF strategic priorities? | Alignment / compliance of the Project with GEF's policies and strategies. | - PRODOC - GEF representatives / specialists | - Document review - Interviews |
| Was the Project linked with and in-line with WWF and country´s priorities and strategies for the countries of intervention? | Alignment / compliance of the Project with WWF's policies and strategies. | - PRODOC - WWF representatives / specialists | - Document review - Interviews |
| Coherence |  |  |  |
| The compatibility of a Project intervention with other interventions (particularly policies) in a country, sector, or institution. This can include internal coherence and external coherence. Internal coherence addresses the synergies and interlinkages between the Project interventions and those carried about by the same sector or institution in country. External coherence measures consistency and compatibility of the interventions among different sectors, but in the same context. |  |  |  |
| To what extent is the Project aligned with other interventions in the same focal area? | Alignment of the Project with other interventions. | - PRODOC - National/ local strategies, actors, institutions participating in the same area - greater Caribbean and outside the region | - Document review - Interviews |
| Do the Project interventions provide an added value and complement/coordinate with other sector’ interventions in the same context/landscape? | Alliances and partnerships created. Additional Project impact not listed. | - Local and national government, institutional actors - Progress reports | - Document review - Interviews |
| Effectiveness |  |  |  |
| The extent to which the outputs, outcomes and Project objective have been or are likely to be achieved, taking into account their relative importance. Identify the major factors which have facilitated or impeded this achievement. Review the management structure of the Project and determine whether the organizational structure of the Project, the resources, the distribution of responsibilities and coordination mechanisms are appropriate for achieving progress towards Project outcomes. |  |  |  |
| Has the Project made progress towards its purpose (objectives and, if appropriate, goal)? | Project outcome indicators and objectives. Achievement of results. | - PRODOC - Progress reports - Actors interviewed | - Document review - Interviews |
| What are the key factors contributing to Project success or underachievement? | Contributing factors to success or underachievement. Results achieved. | - M&E Reports - Progress reports - Workplans | - Document review - Interviews |
| Has there been any unexpected / unintended negative / positive impacts and what are the reasons for this? | Unexpected results, both positive and negative. Contributing factors to unexpected results. | - M&E Reports - Progress reports - Actors interviewed - Hurricane events in the area | - Document review - Interviews |
| To what extent has coordination/communication been effective within and between the implementation team, stakeholders, partners, and participants, as well as donor offices in the Network and external donors? | Stakeholders’ engagement. Participation and inclusiveness tools. Level of participation/support of actors. | - PRODOC - Progress reports - Workplans - Social Safeguards compliance report - Actors interviewed | - Document review - Interviews |
| Which strategies are proving to be effective, and which are not? And what are the reasons for this? | Consistency between the Project strategy and the expected results. Analysis of the achievements by the interviewees. Alternative strategies for achieving objectives. | - PRODOC - Project strategy - Project Framework - Theory of Change - Progress reports - Workplans - Strategies and agreements developed at the regional level | - Document review - Interviews |
| What lessons can be taken and applied to improve effectiveness in the coming years? Lessons provided by the implementing agency as well the PMU, MTWG and executing partners will be collected. | Lessons learned | - PRODOC - Project strategy - Project Framework - Progress reports - Workplans - Results framework | - Document review - Interviews |
| Efficiency |  |  |  |
| The extent to which results have been delivered with the least costly resources possible. This includes efficiency of funding availability, Project management and human resources, coordination, and information flow among the Project partners. |  |  |  |
| Is the Project cost-effective? | Efficiency of budget execution and its relation to product/outcome indicators. Budget deviations. Cash disbursements timing. | - Project Framework - Financial Progress Reports - Annual Workplans | - Document review - Interviews |
| Is the Project implementation approach efficient for delivering the planned Project results? | Efficiency in execution. Management mechanisms and tools. Management Arrangements. Use of Results Framework as management tool. | - PRODOC - Operational plans - M&E Reports - Progress reports | - Document review - Interviews |
| Is the Project implementation delayed? If so, has that affected cost-effectiveness? | Effectiveness and efficiency in execution. Planned time frames. Change in timeline for the workplan. | - PRODOC - Workplans - Progress reports - Results framework | - Document review - Interviews |
| What is the contribution of cash and in-kind co-financing to Project implementation? | Relationship between co-financing and results. Level of Co-financing to date versus target. | - Co-financing reports | - Document review - Interviews |
| To what extent is the Project leveraging additional resources? | Efficiency of budget execution and its relation to product/outcome indicators. Changes to fund allocations as a result of budget revisions. Additional co-financing. | - Financial Progress Reports | - Document review - Interviews |
| Are human resources (Project staff, coalition members, and via partnerships) appropriate, adequate, efficiently organized and operating effectively (e.g., include considerations of capacity needs and gaps, communications, division and clarity of roles and responsibilities, processes for evaluation and improvement)? | Clarity of organizational management. Effectiveness of communication and feedback. | - PRODOC - Organizational manuals - Project team | - Document review - Interviews |
| Are there thorough, well founded work plans being implemented according to plan, monitored, and adapted as necessary? | Consistency between operational/ strategic plans and the Project/results framework. Result based workplan. Monitoring tools. Adequacy of work and budget. | - Workplans - Results Framework - Budget documents - M&E plan and reports | - Document review - Interviews |
| Results/Impact |  |  |  |
| The extent of intended or unforeseen effects that Project interventions or strategies will have on the Project objective, conservation targets and Global Environmental Benefits (GEB), whether positive or negative. Assess the Project’s logic or theory of change and the potential to scale up or replicate the Project outcomes and impact. |  |  |  |
| Are impact level results likely to be achieved? Are they likely to be at the scale sufficient to be considered Global Environmental Benefits? | Results achieved. Project indicators and objectives. Project impact. | - PRODOC - Progress Reports - Theory of Change | - Document review - Interviews |
| Are the anticipated outcomes likely to be achieved? Are the outcomes likely to contribute to the achievement of the Project objective? | Results achieved. Project indicators and objectives. | - PRODOC - Progress Reports - Theory of Change - MAR2R Progress Report | - Document review - Interviews |
| To what extent has the Project attained its stated vision and goals, in terms of outcomes effecting positive change in biodiversity quality, ecosystem services and, in turn if relevant, human wellbeing? | Results achieved. Project indicators and objectives. | - PRODOC - Progress Reports - M&E reports | - Document review - Interviews |
| Were there any unforeseen results/impacts (whether positive or negative)? | Additional Project results/impacts not listed in the Project Framework. | - PRODOC - Progress reports - MAR2R Progress Report | - Document review - Interviews |
| Were the indicators in the Results Framework SMART (Specific, Measurable, Attributable, Relevant, Time-bound/Timely/Trackable/Targeted)? | "SMARTNESS" of indicators and objectives of the Project. | - PRODOC - Project Framework - Theory of change | - Document review - Interviews |
| Theory of change |  |  |  |
| Were the outcomes and outputs consistent with the Theory of Change? | Alignment between the Theory of change and the outcomes, outputs and indicators in the Project Framework. | - PRODOC - Project Framework - Theory of change - Progress reports | - Document review - Interviews with key stakeholders |
| Was there a clearly defined and robust Theory of Change? Both, written and diagramed? | Clearness and robustness of the Theory of Change of the Project. | - PRODOC - Project strategy - Project Framework - Theory of change | - Document review - Interviews with key stakeholders |
| Did the Theory of Change clearly explain the logical/causal pathways from intervention to expected results? Are there adequate incentives for behavior change? Is there anything that the Theory of Change has not considered or made explicit, in terms of assumptions or logic? | Consistency of the Theory of Change of the Project. Clearness and consistency of the assumptions. Achievement of results. | - PRODOC - Project strategy - Project Framework - Theory of change | - Document review - Interviews with key stakeholders |
| Was the Theory of Change supported by the Project? Did M&E data support the logic or were there assumptions invalidated such that the Project interventions did not have the intended results? | Alignment between the Theory of change and the outcomes, outputs, and indicators in the Project Framework. | - PRODOC - Project strategy - Project Framework - Theory of change | - Document review - Interviews |
| Was the Projects’ Theory of Change reviewed and refined during implementation? | Changes in the Theory of Change since the Project started. | - PRODOC - Project strategy - Project Framework - Theory of change - Minutes of the Board meetings | - Document review - Interviews |
| Sustainability |  |  |  |
| The likely ability of an intervention to continue to deliver benefits, progress and impact after external support has ended. Determine the degree of support and buy-in given to the Project at the national and local level. |  |  |  |
| Is there evidence that aspects of sustainability are being established or exist to the extent necessary to ensure the desired long-term impacts of the Project? | Planning of an exit strategy. | - PRODOC - Project team - WWF/GEF representatives | - Document review - Interviews |
| What external factors could have a high or medium likelihood of undoing or undermining the future sustainability of Project’s positive impacts? | Risks for the sustainability of activities. | - Project team - Local and national institutions - Actors interviewed | - Document review - Interviews |
| Do relevant stakeholders have or are likely to achieve an adequate level of “ownership” of results, to have the interest in ensuring that Project benefits are maintained? | Opinions on the suitability of the continuity of the benefits of the Project. Country ownership in the different mechanisms of the Project. Beneficiary planning. | - PRODOC - Actors interviewed - Organizational manuals - Exit strategy | - Document review - Interviews |
| Do relevant stakeholders have the necessary technical capacity to ensure that Project benefits are maintained? | Existence of necessary mechanisms for accountability, transparency, and transfer of technical knowledge. | - Legal frameworks - Public policies - Exit strategy | - Document review - Interviews |
| To what extent are the Project results dependent on sociopolitical factors? | Changes of national and local governments that could affect the Project results. Modifications of public policy agendas. | - Project team - WWF/GEF representatives - Government institutions - Exit strategy | - Document review - Interviews |
| Are there any environmental risks that can undermine the future flow of Project impacts and Global Environmental Benefits? | Environmental risks for the sustainability of activities. | - Project team - Local and national institutions - Actors interviewed | - Document review - Interviews |
| Is the Project adequately anticipating and taking measures to ensure resilience to these external factors? | Main risks identified. Planning. | - PRODOC - Risk analysis and management documents - Project team - WWF/GEF representatives | - Document review - Interviews |
| Adaptive Capacity |  |  |  |
| The extent to which the use of M&E, lessons learned, and adaptive management are used to meet indicator targets and mitigate Project issues (such as design flaws or any adverse impacts of the Project). |  |  |  |
| Did the team examine good practice lessons from other conservation/ development experiences and consider these experiences in the Project design? | Integration of lessons/good practices from other experiences in the Project design. | - PRODOC - Project strategy - Project Framework - Theory of Change, - Lessons from other relevant projects | - Document review - Interviews |
| To what extent is monitoring information, including risk monitoring, being appropriately recorded, stored, disseminated, and used to inform future plans? | Effectiveness and frequency of use of monitoring tools. Dissemination mechanisms. | - M&E reports - Actors involved in M&E | - Document review - Interviews |
| Did the Project establish a baseline status of conservation targets and key contextual factors? Is there ongoing systematic monitoring of these? | Project progress indicators. Baseline. | - PRODOC - Project Framework - Progress reports | - Document review - Interviews |
| Does the Project track intermediate results that are part of a theory of change (including results chains) that clearly lay out anticipated cause-effect relationships and enable definition of appropriate indicators? | Results achieved. Effectiveness and frequency of use of tracking tools. | - PRODOC - Project Framework - Theory of Change - M&E reports - Actors involved in M&E | - Document review - Interviews |
| Is there ongoing, systematic, rigorous monitoring of output delivery, outcome attainment, and impact measurement, with plausible attribution to WWF’s actions? | Effectiveness and frequency of use of monitoring tools. Results achieved. Effects of Project interventions. | - M&E reports - Actors involved in M&E | - Document review - Interviews |
| To what extent lessons are documented and shared in a manner that is promoting learning by the Project management team and key stakeholders? | Documentation and management of lessons. Dissemination mechanisms. | - Project team - Reports | - Document review - Interviews |
| What are the lessons learned from the Project, failures / opportunities, losses to date? What could have been done better or differently? | Lessons learned identified to date. | - Project team - WWF / GEF representatives | - Document review - Interviews |
| Safeguards |  |  |  |
| Assess if safeguards were adequately considered in design and implementation; | WWF & GEF safeguards reports. | - PRODOC - WWF Environmental and Social Safeguards compliance report - Project team. - Project Safeguards Specialist | - Document review - Interviews with key stakeholders |
| Assess Project activities for any additional adverse or unforeseen environmental or social impacts and include potential measures to address these | WWF & GEF safeguards. Main environmental or social risks. Additional environmental or social impact/risks not listed. | - PRODOC - WWF Environmental and Social Safeguards compliance report - Progress reports - Project team | - Document review - Interviews with key stakeholders |
| Gender-equity |  |  |  |
| To what extent were gender issues addressed in the Project design? | Gender strategy. | - PRODOC - Gender representatives/ specialists | - Document review - Interviews |
| How has the Project contributed to improving the status and position of women? | Gender strategy. Women participatory planning. Gender progress indicators. Opinions on improved status of women. | - PRODOC - Gender representatives/ specialists | - Document review - Interviews |
| Are financial resources / Project activities explicitly allocated to allow women to benefit from Project interventions? | Actors and roles chart. Women participatory planning. Percentage of funds allocated to women participation. | - PRODOC - Organizational manuals - Budget documents | - Document review - Interviews |
| In what ways did the Project’s gender results advance or contribute to the Project’s biodiversity outcomes? | Gender disaggregated indicators. Gender progress indicators. | - PRODOC - Project Framework - Progress reports - M&E reports | - Document review - Interviews |
| COVID-19 |  |  |  |
| To what extent has the context generated by COVID-19 affected the execution of the Project in terms of the activities planned? | Additional Project impacts not listed. Planned and actual time frames. | - Progress reports - Project team - M&E reports | - Document review - Interviews |
| Have measures been taken to mitigate the risk posed by COVID-19 in the implementation of the Project? | Decisions taken due to COVID-19 pandemic. Existence of COVID-19 mitigation plan. | - Progress reports - Project team - M&E reports | - Document review - Interviews |

## Questionnaire

| Mid-Term Evaluation Consultancy |  |  |
| --- | --- | --- |
| Objective of the questionnaire: to collect data on the quality of the Project implementation |  |  |
|  |  | Answers |
| Name of interviewee |  |  |
| Country |  |  |
| Position |  |  |
| Institution |  |  |
| Could you describe your role within the Project? |  |  |
| Relevance |  |  |
| ALL | How relevant is the Project to the conservation and sustainable use of shared freshwater, coastal and marine resources of the transboundary MAR ecoregion? |  |
|  | Were the objectives and expected results realistic and concrete? |  |
|  | Are the components and results of the Project clear, practical, and feasible? |  |
| PMU & WWF GEF | Do you consider pertinent the inclusion and / or adjustment of some indicators to those proposed? If so, what changes should be implemented? Please specify them |  |
|  | Were the lessons of other similar projects appropriately incorporated into the Project design? |  |
| ALL | Does the Project’s objective align with the priorities of the national and local governments, and local communities? |  |
|  | Does the Project’s objective fit within the transboundary and national environment and development priorities of the countries of intervention? |  |
| PMU & WWF GEF | Did the Project concept originate from local or national stakeholders, and/or were relevant stakeholders sufficiently involved in Project development? |  |
|  | Is the Project objective aligned with GEF strategic priorities? |  |
|  | Was the Project linked with and in-line with WWF priorities and strategies for the countries of intervention? |  |
| Coherence |  |  |
| ALL | To what extent is the Project aligned with other interventions in the same focal area? |  |
|  | Do the Project interventions provide an added value and complement/coordinate with other sector’ interventions in the same context/landscape? |  |
| Effectiveness |  |  |
| ALL | Are the Project objectives likely to be met according to the advances obtained so far? To what extent are they likely to be met? |  |
|  | What are the key factors contributing to Project success or underachievement? |  |
|  | What are the key risks and barriers that remain to achieve the Project objective and generate Global Environmental Benefits? |  |
|  | Has there been any unexpected / unintended negative / positive impacts and what are the reasons for this? |  |
|  | To what extent has coordination/communication been effective within and between the executing team, stakeholders, partners, and participants, as well as donor offices in the Network and external donors? |  |
|  | Which strategies are proving to be effective, and which are not? And what are the reasons for this? |  |
|  | What is your opinion on the quality of execution of the Project and the executing partners and grantees? |  |
|  | Is communication regular and effective? Are there key actors that are left out of communication? |  |
|  | How do you rate the role of the Project Steering Committee? Do they have a strategic role in the Project? |  |
|  | Does communication with stakeholders and partners contribute to their understanding about Project results and activities and investment in the sustainability of Project results? |  |
| Partners / Grantees | How do you rate the PMU (CCAD)? Have you received all the necessary support from the Project Management Unit/Executing Agency? |  |
|  | How much coordination and lessons sharing, have you had with the other partners and grantees of the Project? |  |
|  | Did you have the opportunity to connect and learn from other projects that share the same objectives? |  |
| PMU | How do you rate the WWF GEF Agency? Have you received all the necessary support from the implementing agency? |  |
| Efficiency |  |  |
| PMU, WWF GEF/ Finance | What is the Project cost-effectiveness relation in terms of invested resources and achieved results? |  |
| ALL | Is the Project implementation approach efficient for delivering the planned Project results? |  |
| PMU, WWF GEF/ Finance | Is the Project implementation activities delayed? If so, may this delay affect its cost-effectiveness? |  |
|  | To what extent is the Project leveraging additional resources? |  |
|  | Has the co-financing been used strategically to help the objectives of the Project? |  |
|  | Did the Project Team meet with all co-financing partners regularly in order to align financing priorities and annual work plans? |  |
|  | Were there any changes to fund allocations as a result of budget revisions? Was it appropriate and relevant? |  |
| ALL | Are human resources (Project staff, coalition members, and via partnerships) appropriate, adequate, efficiently organized and operating effectively? |  |
|  | Are there thorough, well founded work plans being implemented according to plan, monitored, and adapted as necessary? |  |
| Results / Impact |  |  |
| PMU & WWF GEF | Are impact level results likely to be achieved? Are they likely to be at the scale sufficient to be considered Global Environmental Benefits? |  |
| ALL | Are the anticipated outcomes likely to be achieved? Are the outcomes likely to contribute to the achievement of the Project objective? |  |
|  | Were there any unforeseen results/impacts (whether positive or negative)? |  |
| PMU, M&E WWF GEF | Were the indicators in the Results Framework SMART (Specific, Measurable, Attributable, Relevant, Time-bound/Timely/Trackable/Targeted)? |  |
|  | What is your assessment of regional and international cooperation and knowledge management at national, regional, and international level? Could you give some recommendations for improvement? |  |
| ALL | Have appropriate means been established for external communication about the progress of the Project and the expected impact to the public? Please indicate them |  |
| Theory of change |  |  |
| PMU & WWF GEF | Are the outcomes and outputs up to now consistent with the Theory of Change? |  |
|  | Do you consider the Theory of Change is clearly defined and robust? Both, written and diagramed? Has it been discussed, reviewed or any refinement considered so far? |  |
|  | Did the Theory of Change clearly explain the logical/causal pathways from intervention to expected results? Are there adequate incentives for behavior change? |  |
|  | In your opinion, is there anything that the Theory of Change has not considered or made explicit in terms of assumptions or logic? |  |
|  | Was the Theory of Change supported by the Project? Did M&E data support the logic or were there assumptions invalidated? |  |
| Sustainability |  |  |
| ALL | To what extent are Project results likely to be dependent on continued financial support? What is the likelihood that any required financial resources will be available to sustain the Project results once the GEF assistance ends? |  |
|  | Do relevant stakeholders have or are likely to achieve an adequate level of “ownership” of results, to have the interest in ensuring that Project benefits are maintained? |  |
|  | To what extent are the Project results dependent on sociopolitical factors? |  |
|  | Are there any environmental risks that can undermine the future flow of Project impacts and Global Environmental Benefits? |  |
|  | Is the Project adequately anticipating and taking measures to ensure resilience to these external factors? |  |
|  | Has an exit strategy been prepared and is being implemented to ensure sustainability? How do you rate the exit strategy? |  |
| Adaptive Capacity |  |  |
| PMU & WWF GEF | Did the team examine good practice lessons from other conservation/ development experiences and consider these experiences in the Project design? |  |
| ALL | What significant changes do you consider, if any, the Project should undergo as a result of recommendations from this Mid-Term Evaluation? Please explain |  |
|  | To what extent was the monitoring information, including risk monitoring, being appropriately recorded, stored, disseminated with key partners and inside teams? |  |
|  | How do you rate the M&E function of the Project? |  |
|  | How do you rate the adaptive management section in the progress reports? Have any of the suggestions applied during the Project? If yes, how were they applied? |  |
| PMU, M&E WWF GEF | Are the M&E tools aligned or integrated with national systems? |  |
|  | Are the M&E tools efficient? Do you think additional tools were needed? |  |
|  | Have sufficient resources been allocated to monitoring and evaluation? Have these resources been allocated effectively? |  |
|  | Did the Project track intermediate results that are part of a theory of change (including results chains) that clearly lay out anticipated cause-effect relationships and enable definition of appropriate indicators? |  |
|  | Is there ongoing, systematic, rigorous monitoring of output delivery, outcome attainment, and impact measurement, with plausible attribution to WWF’s actions? |  |
| ALL | To what extent lessons are documented and shared in a manner that is promoting learning by the Project management team and key stakeholders? |  |
|  | What are the lessons learned from the Project, failures / opportunities, losses to date? What could have been done better or differently? |  |
| Safeguards |  |  |
| PMU, M&E WWF GEF | Were safeguards adequately considered in design and implementation? |  |
| PMU & WWF GEF | Were there any adverse or unforeseen environmental or social impacts caused by the Project? If so, how have they been addressed? |  |
| Gender-equity |  |  |
| ALL | To what extent were gender issues addressed in the Project design? |  |
| Partners | What has been done to integrate the gender strategy in your activities? |  |
| ALL | How has the Project contributed to improving the status and position of women? |  |
|  | Are financial resources / Project activities explicitly allocated to allow women to benefit from Project interventions? |  |
| PMU, WWF GEF, Gender Specialist | In what ways did the Project’s gender results advance or contribute to the Project’s biodiversity outcomes? |  |
| ALL | Are there lessons learned on gender equality? |  |
| COVID-19 |  |  |
| ALL | To what extent has the context generated by COVID-19 affected the execution of the Project in terms of the activities planned? |  |
|  | Have measures been taken to mitigate the risk posed by COVID-19 in the implementation of the Project? |  |

## Rating Scale for the criteria

| Outcoming Rating Classification: |  |
| --- | --- |
| Highly satisfactory (HS) | Level of outcomes achieved clearly exceeds expectations and/or there were not shortcomings. |
| Satisfactory (S) | Level of outcomes achieved was as expected and/or there were no or minor shortcomings. |
| Moderately satisfactory (MS) | Level of outcomes achieved more or less as expected and/or there were moderate shortcomings. |
| Moderately unsatisfactory (MU) | Level of outcomes achieved somewhat lower than expected and/or there were significant shortcomings. |
| Unsatisfactory (U) | Level of outcomes achieved substantially lower than expected and/or there were major shortcomings. |
| Highly unsatisfactory (HU) | Only a negligible level of outcomes achieved and/or there were severe shortcomings. |
| Unable to assess (UA) | The available information does not allow an assessment of the level of outcome achievements. |
| Sustainability/ Risk Rating Classification: |  |
| Likely (L) | There are little or no risks to sustainability. |
| Moderately likely (ML) | There are moderate risks to sustainability. |
| Moderately unlikely (MU) | There are significant risks to sustainability. |
| Unlikely (U) | There are severe risks to sustainability. |
| Unable to assess (UA) | Unable to assess the expected incidence and magnitude of risks to sustainability. |
| M&E Rating classification: |  |
| Highly satisfactory (HS) | There were no shortcomings and quality of M&E design / implementation exceeded expectations. |
| Satisfactory (S) | There were no or minor shortcomings and quality of M&E design / implementation meets expectations. |
| Moderately satisfactory (MS) | There were some shortcomings and quality of M&E design / implementation more or less meets expectations. |
| Moderately unsatisfactory (MU) | There were significant shortcomings and quality of M&E design/ implementation somewhat lower than expected. |
| Unsatisfactory (U) | There were major shortcomings and quality of M&E design/ implementation substantially lower than expected. |
| Highly unsatisfactory (HU) | There were severe shortcomings in M&E design / implementation. |
| Unable to assess (UA) | The available information does not allow an assessment of the quality of M&E design /implementation. |
| Implementation and Execution Rating Classification: |  |
| Highly satisfactory (HS) | There were no shortcomings and quality implementation / execution exceeded expectations. |
| Satisfactory (S) | There were no or minor shortcomings and quality implementation /execution meets expectations. |
| Moderately satisfactory (MS) | There were some shortcomings and quality of implementation /execution more or less meets expectations. |
| Moderately unsatisfactory (MU) | There were significant shortcomings and quality of implementation /execution somewhat lower than expected. |
| Unsatisfactory (U) | There were major shortcomings and quality of implementation /execution substantially lower than expected. |
| Highly unsatisfactory (HU) | There were severe shortcomings in quality of implementation/ execution. |
| Unable to assess (UA) | The available information does not allow an assessment of the quality of implementation / execution. |

Source: Based on TOR information

## List of stakeholders interviewed

|  | Name | Role / Organization |
| --- | --- | --- |
| SC | Edgar Ek | Department of Enviroment, Ministry of Enviroment and focal point to MTWG/Steering Committee- BZ |
|  | Luisa Fernandez/Gabriela Castellanos | Ministerio Ambiente y Recursos Naturales – GT; focal point to MTWG/Steering Committee- GT" |
|  | Yadira Gómez | Comisión Nacional de Áreas Naturales Protegidas México. CONANP. Focal point to MTWG/Steering Committee - Mx |
|  | Skarleth Pineda Lim | Dirección de Biodiversidad Mi Ambiente – Focal Point to MTWG/ Steering Commitee HN |
| IA | Isabel Filiberto | WWF GEF |
|  | Lilian Marquez | WWF GEF |
|  | Karen Rosales | WWF GEF F&A |
|  | Tracey Smith | WWF GEF F&A |
|  | Andreas Lehnhoff | WWF Guatemala/Mesoamerica Director |
| WWF | Mauricio Mejía | Senior Food Production Officer |
|  | Sonia Solís | Freshwater Officer |
| EA CCAD | Jair Urriola | Executive Secretary CCAD. Project Steering Committee -CCAD. EA |
|  | Julio Lazo | PMU - F&A Manager |
|  | Mario Escobedo | PMU Director |
|  | Jorge Garza | PMU - M&E Officer |
|  | José Ricardo Calles | PMU - IWR Specialist |
|  | Carlos Rodríguez Olivet | PMU – ICM Specialist/Safeguards Specialist |
| Belize | Arlene Young | Coastal Zone Management Authority and Institute – BZ |
|  | Tennielle Williams | National Hidrology Service (principal) |
|  | Stacey Alpuche | Technical Officer. DOE-PACT |
| Guatemala | José Luis Portillo | Director de Cuencas y Asuntos Estratégicos MARN. Guatemala |
|  | Marco Cerezo | Fundación para el Ecodesarrollo de Guatemala |
|  | Ingrid Arias | Fundación para el Ecodesarrollo de Guatemala |
| Honduras | Carmen Cartagena | Dirección General de Recursos Hídricos Mi Ambiente - HN |
|  | Ricardo Sierra | Asociación de Productores de Azúcar de Honduras |
|  | Daniel Ayes | Centro de Producción Más Limpia de Honduras |
|  | Héctor Castro | Asociación Industrial de Productores de Aceite de Honduras |
|  | Claudia Amaya |  |
|  | Nathaly Cardona | SAG -DIGEPESCA |
|  | Ilsa Diaz | Fundación Merendón |
|  | Jonan Madrid |  |
|  | Alexandra Fajardo |  |
|  | Graciela Martinez |  |
| Mexico | Gonzalo Merediz | Amigos de Sian Ka’an/ Consejo de cuenca de la Península de Yucatán - MX |
|  | Vicente Ferreyra | SUSTENTUR |
|  | Martha Leticia Otero | CONAGUA – MX |
|  | Alejandro López Tamayo | Centinelas del Agua. México |
| REGIONAL | María José González | Mesoamerican Reef Fund |
|  | Ana Giró | RRA-SAM Red de Restauración de Corales |
|  | Fabiola Tábora | Global Water Partnership Centroamérica |
|  | Patrick Debels | CLME+ "Catalyzing Implementation of the Strategic Action Program for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems" |
|  | Steven Canthy | Smithsonian Institute |
|  | Ramiro Batzín | CICA. Consejo Indígena Centroamericano |
|  | Masaki Osawa | JICA. El Salvador. Coordinador de Proyecto Regional |
|  | Ilka Aguilar Valle | Secretaria Ejecutiva del Consejo Centroamericano de Turismo; Secretaría de Integración Turística Centroamericana-SITCA- |
|  | Gladis Argumendo de Gómez | Secretaria Ejecutiva del Consejo Centroamericano de Turismo; Secretaría de Integración Turística Centroamericana-SITCA- |
|  | Violeta Reina | OSPESCA |

## MTE field mission itinerary

| Time (Central America) | Country | Role / Organization | Interviewed |
| --- | --- | --- | --- |
| Thursday, October 7, 2021 |  |  |  |
| 9:00 – 10:00 | Regional | CCAD | Jair Urriola (Executive Secretary) Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| Monday, October 11, 2021 |  |  |  |
| 9:00 – 10:30 | Belize | National Hidrology Service (principal) | Tennielle Williams |
|  |  | Technical Officer DOE-PACT | Stacey Alpuche |
| Tuesday, October 12, 2021 |  |  |  |
| 11:00 – 13:00 | Regional | CCAD | Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| Wednesday, October 13, 2021 |  |  |  |
| 9:00 – 10:00 | Regional | RRA-SAM Red de Restauración de Corales | Ana Giró |
| 11:00 – 12:30 | Guatemala | Fundación para el Ecodesarrollo de Guatemala | Marco Cerezo |
|  |  |  | Ingrid Arias |
| 13:00 – 14:00 | Belize | Coastal Zone Management Authority and Institute | Arlene Young |
| Thursday, October 14, 2021 |  |  |  |
| 11:00 – 12:30 | Regional | WWF GEF | Karen Rosales |
|  |  |  | Lilian Marquez |
| 15:00 – 16:30 | Guatemala | MARN | Luisa Fernandez Regina Sanchez |
| Friday, October 15, 2021 |  |  |  |
| 11:00 – 13:00 | Regional | CCAD | Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| Monday, October 18, 2021 |  |  |  |
| 9:00 – 10:30 | Regional | WWF GEF | Isabel Filiberto |
|  |  |  | Tracey Smith |
| 11:00 – 12:30 | Regional | WWF | Mauricio Mejía |
|  |  |  | Sonia Solís |
| Tuesday, October 19, 2021 |  |  |  |
| 8:30 – 9:30 | Honduras | Asociación Industrial de Productores de Aceite de Honduras | Héctor Castro Carmen Amaya |
| 11:00 – 12:30 | Honduras | Fundación Merendón] | Ilsa Diaz Jonan Madrid Alexandra Fajardo Graciela Martinez |
| 15:00 – 16:00 | Regional | WWF Guatemala/Mesoamerica Director | Andreas Lehnhoff |
| Wednesday, October 20, 2021 |  |  |  |
| 9:00 – 10:00 | Regional | CICA. Consejo Indígena Centroamericano | Ramiro Batzín |
| 11:00 – 12:30 | Regional | CCAD | Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| 15:00 – 16:30 |  |  |  |
| Thursday, October 21, 2021 |  |  |  |
| 9:00 – 10:00 | Regional | CLME+ "Catalyzing Implementation of the Strategic Action Program for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems" | Patrick Debels |
| 11:30 – 12:30 | Honduras | Centro de Producción Más Limpia de Honduras | Daniel Ayes |
| 14:00 – 15:30 | Regional | CCAD | Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| 16:00 – 17:00 | Regional | Global Water Partnership Centroamérica | Fabiola Tábora |
| Friday, October 22, 2021 |  |  |  |
| 09:00 – 10:00 | Regional | Smithsonian Institute | Steven Canthy |
| 16:00 – 17:30 | Regional | Secretaria Ejecutiva del Consejo Centroamericano de Turismo; Secretaría de Integración Turística Centroamericana-SITCA- | Ilka Aguilar Valle |
|  |  |  | Gladis Argumendo de Gómez |
| Monday, October 25, 2021 |  |  |  |
| 9:00 – 10:30 | Mexico | Amigos de Sian Ka’an/ Consejo de cuenca de la Península de Yucatán | Gonzalo Merediz |
| 11:00 – 12:00 | Mexico | CONANP | Yadira Gómez |
| 13:30 – 15:00 | Mexico | SUSTENTUR | Vicente Ferreyra |
| Tuesday, October 26, 2021 |  |  |  |
| 8:30 – 10:00 | Mexico | CONAGUA | Martha Leticia Otero |
| 13:30 – 15:00 |  | Centinelas del Agua | Alejandro López Tamayo |
| Wednesday, October 27, 2021 |  |  |  |
| 9:00 – 11:00 | Regional | CCAD | Mario Escobedo |
| 9:00 – 11:30 | Honduras | Dirección General de Recursos Hídricos Mi Ambiente | Carmen Cartagena |
| 11:30 – 12:30 | Regional | JICA. El Salvador. Coordinador de Proyecto Regional | Masaki Osawa |
| 15:30 – 17:00 | Regional | Executive Secretary CCAD. Project Steering Committee -CCAD. EA | Jair Urriola |
| Thursday, October 28, 2021 |  |  |  |
| 14:00 – 15:00 | Honduras | SAG -DIGEPESCA | Nathaly Cardona |
| 15:00 – 17:00 | Regional | PSC | Edgar Ek (Department of Enviroment, Ministry of Enviroment and focal point to MTWG/Steering Committee- BZ) |
|  |  |  | Luisa Fernandez (Ministerio Ambiente y Recursos Naturales – GT; focal point to MTWG/Steering Committee- GT) |
|  |  |  | Yadira Gómez (Comisión Nacional de Areas Naturales Protegidas México. CONANP. Focal point to MTWG/Steering Committee – Mx) |
|  |  |  | Skarleth Pineda Lim (Dirección de Biodiversidad Mi Ambiente – Focal Point to MTWG/ Steering Commitee HN) |
| Friday, October 29, 2021 |  |  |  |
| 9:00 – 10:00 | Regional | CCAD | Mario Escobedo (PMU Director) Julio Lazo (PMU - F&A Manager) Jorge Garza (PMU - M&E Officer) José Ricardo Calles (PMU - IWR Specialist) Carlos Rodríguez Olivet (PMU – ICM Specialist/Safeguards Specialist) Sandra Serrano (Communications) |
| 11:00 – 12:00 | Regional | OSPESCA | Violeta Reina |
| Tuesday, November 2, 2021 |  |  |  |
| 13:00 – 14:00 | Honduras | Asociación de Productores de Azúcar de Honduras | Ricardo Sierra |
| Thursday, November 11, 2021 |  |  |  |
| 17:00 – 18:00 | Regional | Mesoamerican Reef Fund | María José González |

## List of Documents reviewed

| Document Name | Received (YES/NO) | Notes |
| --- | --- | --- |
| Project contacts for MTE | YES | Under analysis |
| Project Document and CEO Endorsement Letter | YES | Under analysis |
| Support Mission Reports and Aide-memoirs | YES | Under analysis |
| Annual Work Plans (AWP) and Budgets | YES | Under analysis. Only years 1 and 2 |
| Project Progress Reports (PPR) including Results Framework and AWP Tracking | YES | Under analysis. Only years 1 and 2 |
| Inputs from original MTE | NO | Requested if considered pertinent |
| Pre-implementation documentation | YES | Under analysis |
| Terms of reference for grantees | YES | Under analysis |
| Communication products | YES | Under analysis |
| Gender & safeguards documents | YES | Under analysis |
| Minutes from meetings and memos | YES | Under analysis |
| Reports produced | YES | Under analysis. Only years 1 and 2 |
| Logical Framework and Project Timetable | YES | Under analysis |
| Project Financial Reports | YES | Under analysis. |

## Flowchart of the Mid-Term Evaluation of the Project

## Results Chains (from PRODOC)

Component 1

Component 2

Component 3

Component 4

## Effectiveness in achieving planned results

| Indicator | Disaggregation | Base line | Time |  |  |  |  |  | Year 5 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 |  | Year 2 |  | Year 3 |  |  |  |
|  |  | (Year 0) | Target | Achieved | Target | Achieved | Target | Achieved | Final Target |  |
| Project Objective: To support regional collaboration for the integrated ridge to reef management of the transboundary MAR ecoregion by demonstrating its advantages and improving regional, national, and local capacities for the integrated management and governance of its freshwater, coastal and marine resources |  |  |  |  |  |  |  |  |  |  |
| Number of regional policy instruments that promote ridge to reef management of the MAR ecoregion approved due to Project activities | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2 | This indicator has achieved and surpassed its target. By year 3 regional policy instruments have been approved: (1) Decade of Restoration; (2) MOU SEMARNAT – CCAD; and (3) Mangrove restoration. By year 4 the Blue Economy Regional Protocol is expected to be finalized and by year 5 the Wastewater Standards Harmonization Protocol will be endorsed. |
| Area (ha) of watersheds under IWRM Project activities | N/A | 0 | 0 | 0 | 1,401,434 | 803,934 | 1,587,934 | 1,336,652.69 | 2,651,669 | This indicator has achieved 59.88% of its target. By year 3 1,587,934 ha of watersheds are under IWRM |
| Area (ha) of coastal and marine ecosystems under ICMM Project activities | N/A | 0 | N/A | N/A | 115,800 | 300,000 | 115,800 | 323,600 | 157,800 | This indicator has achieved and surpassed its target. By year 3 323,600 ha of coastal and marine ecosystems are under ICMM Project activities. |
| Component 1: Strengthen resource governance and regional collaboration for integrated ridge to reef management in the MAR |  |  |  |  |  |  |  |  |  |  |
| Outcome 1.1: The countries have the enabling conditions for MAR R2R management |  |  |  |  |  |  |  |  |  |  |
| Number of regional policy instruments developed | N/A | 0 | N/A | N/A | N/A | N/A | 2 | 3 | N/A | This outcome has achieved and surpassed its target (see objetive 1 above). |
| Outcome 1.2: MAR national R2R policy (IWRM and ICMM) frameworks are strengthened [linking Components 2 and 3]. |  |  |  |  |  |  |  |  |  |  |
| Number of national policy instruments developed | Country | 1 in GT (Coastal Marine Policy) | N/A | N/A | N/A | N/A | 2 | 3 | N/A | This outcome is in progress to achieve its target. By year 3, 2 in HN (1 presented), and 2 in MX Nom 001 and Coast Policies of QRoo. In process: Water Policy Hn; Water Policy Bz; Coastal Policy Q.Roo Mx |
|  |  | 1 in BZ (ICZM Plan) | N/A | N/A | N/A | N/A | 4 |  |  |  |
| Resultado 1.3: SAM tiene un ADT y un SAP que guiará la gestión de la R2R ecorregional. |  |  |  |  |  |  |  |  |  |  |
| Number of countries in the MAR endorsing TDA and SAP | Country | 0 | N/A | N/A | N/A | N/A | 4 | 0 | N/A | This outcome is delayed in achieving its target. TDA has a validation route and its validation is expected for Q2 of year 4. SAP preparation in parallel process, and is expected to be endorsed on Dec 2022. |
|  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 4 |  |
| Outcome 1.4: MAR strategic planning, policy making, management and monitoring supported with updated reliable information accessed via REO. |  |  |  |  |  |  |  |  |  |  |
| Number of unique visitors consulting REO (Regional Environmental Observatory) in one full year | N/A | 0 | N/A | N/A | 25 | 0 | 50 | 3,465 | 100 | This outcome has achieved and surpassed its target. By year 3 the REO had a total of 3,465 visits. Consulting provided more than 400 documents for REO. |
| Component 2: Integrated ridge to reef management of watersheds and freshwater |  |  |  |  |  |  |  |  |  |  |
| Outcome 2.1: IWRM in priority watersheds increased. |  |  |  |  |  |  |  |  |  |  |
| Number of stakeholders trained in IWRM through Project activities | Trained in IWRM - women | 0 | 25 | 56 | 65 | 107 | 100 | 152 | 175 | This outcome is in progress toward achieving its target. By year 3, 152 women and 358 men has been trained in IWRM through Project activities. This outcome has different goals between the PRODOC, where the goal was 350 trained men and 350 trained women in IWRM, and the progress reports, where the goal is 175 men and 175 women. Documents submitted meet the goals, but their quality has been questioned by external reviewers, with a lack of further analysis and technical criteria. |
|  | Trained in IWRM - men | 0 | 25 | 71 | 65 | 149 | 100 | 358 | 175 |  |
| Outcome 2.2. Public-private mechanisms for integrated watershed management are strengthened and supported by stakeholders. |  |  |  |  |  |  |  |  |  |  |
| Increase (USD) in funding available for public private mechanisms in BZ, GT and HN | N/A | 50,000 | 50,000 | 46,130 | 100,000 | 96,130 | 125,000 | 161,825 | 175,000 | This outcome is in progress toward achieving its target. By year 3, the funding available for public private mechanisms in BZ, GT and HN has increased to US$ 161,825. |
| Outcome 2.3. Stakeholders engaged in IWRM in priority watersheds. |  |  |  |  |  |  |  |  |  |  |
| Number of sugar and oil palm producers in Project area that are reaching and/or maintaining compliance with Voluntary Standards | Sugar producers | 0 | 0 | 0 | 1 | 0 | 1 | 0 | N/A | Some indicators are at risk of not achieving its target by the end of the Project. Adaptative management has been proposed for this outcome. Quality improvement is needed. No evidence of stakeholder analysis and on year 2. There have been delays in activities due to the COVID-19 pandemic. |
|  | Reach compliance for certification |  |  |  |  |  |  |  |  |  |
|  | Sugar producers Maintain certification | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 |  |
|  | Oil palm producers reach compliance for certification | 0 | 2 | 2 | 2 | 0 | 2 | 0 | N/A |  |
|  | Oil palm producers maintain certification | 4 | 4 | 3 | 6 | 4 | 8 | 2 | 11 |  |
| Number of tourism and tourism development sector actors adopting better management practices (BMP) to protect aquifers and freshwater critical habitats under Project activities | N/A | 0 | N/A | N/A | 20 | 28 | 24 | 32 | 32 |  |
| Component 3: Integrated ridge to reef management of coastal and marine resources |  |  |  |  |  |  |  |  |  |  |
| Outcome 3.1. ICMM strengthened through capacity building and strategic planning. |  |  |  |  |  |  |  |  |  |  |
| Number of stakeholders trained in ICMM through Project activities | Trained in ICMM - men | 0 | 25 | 194 | 65 | 267 | 100 | 290 | 175 | This outcome is in progress toward achieving its initial target. By year 3, 290 men and 252 women has been trained in ICMM through Project activities. This outcome has different goals between the PRODOC, where the goal was 350 trained men and 350 trained women in IWRM, and the progress reports, where the goal is 175 men and 175 women. |
|  | Trained in ICMM - women | 0 | 25 | 159 | 65 | 239 | 100 | 252 | 175 |  |
| Outcome 3.2. Stakeholders engaged in ICMM in coastal marine prioritized areas. |  |  |  |  |  |  |  |  |  |  |
| Number of shrimp farms and fisheries in Project area that are reaching and/or maintaining compliance with Voluntary Standards (Marine Stewardship Council –MSC- and Aquaculture Stewardship Council -ASC) | Shrimp farm | 0ASC | 0 ASC | 0 | 11 ASC | 0 | 13ASC | 0 | 13ASC | This outcome is at risk of not achieving its target by the end of the Project. Adaptative management has been proposed for this outcome to address delays and inabilities to comply with the activities. |
|  | ASC certified |  |  |  |  |  |  |  |  |  |
|  | Shrimp farm ASC AIPs | 0AIPs | 0 AIPs | 0 | 0 AIPs | 0 | 2 AIPs | 0 | N/A |  |
|  | Fisheries | 0 MSC | 0 MSC | 0 | 0 MSC | 0 | 0 MSC | 0 | 1MSC |  |
|  | MSC certified |  |  |  |  |  |  |  |  |  |
|  | Fisheries | 0 FIPs | 0 FIPs | 0 | 0 FIPs | 0 | 1 FIPs | 0 | 2FIPs |  |
|  | MSC FIPs |  |  |  |  |  |  |  |  |  |
| Number of tourism and tourism development sector actors, and communities implementing better management practices (BMP) to protect coastal and marine habitats under Project activities. | Number of tourism sector actors | 0 | N/A | N/A | 20 | 20 | 24 | 47 | 32 |  |
|  | Number of communities | 8 | 8 | 8 | 12 | 12 | 16 | 20 | 24 |  |
| Component 4: Project monitoring and evaluation and knowledge sharing |  |  |  |  |  |  |  |  |  |  |
| Outcome 4.1. The Project's monitoring and evaluation system employs participatory methods throughout Project lifetime. |  |  |  |  |  |  |  |  |  |  |
| Number of MAR2R progress reports completed (including mid-term and final evaluations and GEF IW Tracking Tool) | Progress reports | 0 | 2 | 2 | 4 | 4 | 6 | 6 | 10 | This outcome is in progress toward achieving its target. 6 progress reports have been presented, 1 GEF IW Tracking tool report has been presented, and the Mid-term evaluation was delayed but it is in progress. |
|  | Mid-term evaluation | 0 | N/A | N/A | N/A | N/A | 1 | 0 | N/A |  |
|  | Final evaluation | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 1 |  |
|  | GEF IW Tracking tool | 0 | 1 | 1 | N/A | N/A | 1 | 1 | 1 |  |
| Outcome 4.2. Advantages of the ridge to reef approach shared with local and international audiences, including the GEF IW: LEARN community. |  |  |  |  |  |  |  |  |  |  |
| Number of communication and knowledge management products disseminated | WP | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | This outcome is in progress toward achieving its target. Communication and knowledge management products have been disseminated and continue to have progress. |
|  | SM | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |
|  | Pubs | 0 | 0 | 0 | 1 | 7 | 3 | 9 | 10 |  |
|  | V/A | 0 | 0 | 0 | 1 | 2 | 2 | 18 | 4 |  |
|  | WB | 0 | 0 | 0 | 1 | 9 | 2 | 13 | 4 |  |
|  | NW | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 36 |  |
|  | IW | 0 | 0 | 0 | N/A | N/A | 1 | 0 | 2 |  |

## SMART Analysis for the indicators

| Indicator | Definition | Disaggregation | Method & Source | Responsible | Smart indicators (Y: Yes; N: No) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | SMART (S: Specific; M: Measurable; A: Achievable; R: Relevant; T: Temporary) |  |  |  |  |  |
|  |  |  |  |  | S | M | A | R | T | Comments |
| Component 1: Strengthen resource governance and regional collaboration for integrated ridge to reef management in the MAR |  |  |  |  |  |  |  |  |  |  |
| Outcome 1.1: The countries have the enabling conditions for MAR R2R management |  |  |  |  |  |  |  |  |  |  |
| Number of regional policy instruments developed | Policy instrument = protocols, standards, agreements. | N/A | Policy instrument documents | CCAD, PMU | Y | Y | Y | Y | Y | The outcome should include the number of policies instruments developed in an expected year/period. This is reflected on the indicators and year goals, but not on the outcome. |
|  | Regional = 2 or more MAR countries |  |  |  |  |  |  |  |  |  |
|  | Established = Prepared by PMU and validated by focal points |  |  |  |  |  |  |  |  |  |
| Outcome 1.2: MAR national R2R policy (IWRM and ICMM) frameworks are strengthened [linking Components 2 and 3]. |  |  |  |  |  |  |  |  |  |  |
| Number of national policy instruments developed | Policy instrument = protocols, standards, other | Country | Policy instrument documents | PMU, ISNC, IWRM and ICMM Specialists | Y | Y | Y | Y | Y | The outcome should include the number of national policies instruments developed in an expected year/period. This is reflected on the indicators and year goals, but not on the outcome. |
|  | Developed = Prepared by PMU and validated by ISNC (Intersectoral National Committees) |  |  |  |  |  |  |  |  |  |
| Outcome 1.3 The MAR has a TDA and SAP that will guide the ecoregional R2R management. |  |  |  |  |  |  |  |  |  |  |
| Number of countries in the MAR endorsing TDA and SAP | TDA = Transboundary Diagnostic Analysis | Country | Endorsement letters from Ministry of Environment approving TDA | PMU | Y | Y | Y | Y | Y | The outcome should include the number of countries that endorsed the TDA and SAP in an expected year/period. This is reflected on the indicators and year goals, but not on the outcome |
|  | SAP = Strategic Action Plan |  |  |  |  |  |  |  |  |  |
|  | Endorsed = TDA is approved by Ministers of Environment |  |  |  |  |  |  |  |  |  |
|  | Submission for approval= |  |  |  |  |  |  |  |  |  |
|  | Final version of SAP is presented by CCAD to the Ministers of Environment for approval |  | Letters of Submission for SAP approval to Ministry of Environment | PMU |  |  |  |  |  |  |
| Outcome 1.4: MAR strategic planning, policy making, management and monitoring supported with updated reliable information accessed via REO. |  |  |  |  |  |  |  |  |  |  |
| Number of unique visitors consulting REO (Regional Environmental Observatory) in one full year | Unique users = distinct individuals requesting pages from REO website regardless of how often they visit. | N/A | REO website reports | REO specialist | Y | Y | N | Y | Y | The indicators of this outcome do not measure the updated reliable information of the REO but the number of users that visit the observatory. Any user could visit the REO without receiving updated information. The outcome should focus on the scope of the platform in an expected year/period. |
| Component 2: Integrated ridge to reef management of watersheds and freshwater |  |  |  |  |  |  |  |  |  |  |
| Outcome 2.1: IWRM in priority watersheds increased. |  |  |  |  |  |  |  |  |  |  |
| Number of stakeholders trained in IWRM through Project activities | IWRM Project activities = management plans, water reserves, tree planting, soil conservation agroforestry systems, etc. Stakeholders = community, local authority, government, NGOs, private sector, and beneficiaries. | Trained in IWRM - women | Attendance lists to workshops (including at least name, gender, organization, title, email, country.) | IWRM Specialist | Y | Y | Y | Y | Y | The outcome should include an expected year/period and a measurable indicator. The stakeholders trained by themselves does not reflect the priority on IWRM, it should include number of Project activities that involve IWRM or rewrite like outcome 3.1. |
|  |  | Trained in IWRM - men |  | IWRM Specialist |  |  |  |  |  |  |
| Outcome 2.2. Public-private mechanisms for integrated watershed management are strengthened and supported by stakeholders. |  |  |  |  |  |  |  |  |  |  |
| Increase (USD) in funding available for public private mechanisms in BZ, GT and HN | Funding = Voluntary contributions paid or pledged to public private mechanisms (including Sierra de las Minas Water Fund) for IWRM. | N/A | Letters of pledged contributions or receipts for paid contributions | IWRM Specialist | Y | Y | Y | Y | Y | The outcome should include an expected year/period and a measurable indicator. It could be better to include the number of public-private mechanisms implemented for integrated watershed management. |
| Outcome 2.3. Stakeholders engaged in IWRM in priority watersheds. |  |  |  |  |  |  |  |  |  |  |
| Number of sugar and oil palm producers in Project area that are reaching and/or maintaining compliance with Voluntary Standards | Voluntary Standards = BONSUCRO for sugar and RSPO for oil palm | Sugar producers | BONSUCRO certificates, BONSUCRO webpage listing certified producers | Producers, IWRM Specialist | Y | Y | Y | Y | Y | The outcome should include an expected year/period and a measurable indicator, e.g., “By 2025, at least 20 stakeholders engaged in IWRM in priority watersheds”. |
|  | Reaching compliance = Industries that have not previously reached certification meet certification criteria. The target is that they become certified. | Reach compliance for certification |  |  |  |  |  |  |  |  |
|  | Maintaining compliance = Industries that have already been certified and remain certified after yearly audit. | Sugar producers Maintain certification |  |  |  |  |  |  |  |  |
|  |  | Oil palm producers reach compliance for certification | RSPO certificates, RSPO webpage listing certified producers | Producers, IWRM Specialist |  |  |  |  |  |  |
|  |  | Oil palm producers maintain certification |  |  |  |  |  |  |  |  |
| Number of tourism and tourism development sector actors adopting better management practices (BMP) to protect aquifers and freshwater critical habitats under Project activities | BMP = protection or restoration activities to protect aquifers or critical habitats | N/A | Baseline developed by grantee or consultant prior to technical assistance, grantees, or consultant’s progress reports after technical assistance | Grantees, |  |  |  |  |  |  |
|  | Tourism sector = hotel and other tourism related businesses and tour operators, |  |  | IWRM Specialist |  |  |  |  |  |  |
|  | Tourism development sector = construction businesses associated with tourism sector |  |  |  |  |  |  |  |  |  |
| Component 3: Integrated ridge to reef management of coastal and marine resources |  |  |  |  |  |  |  |  |  |  |
| Outcome 3.1. ICMM strengthened through capacity building and strategic planning. |  |  |  |  |  |  |  |  |  |  |
| Number of stakeholders trained in ICMM through Project activities | Stakeholder = Government, local authorities, NGOs, fishers, shrimp farmers, tourism sector, tourism development sector, private sector, civil society, communities | Trained in ICMM - men | Attendance lists to workshops (including at least name, gender, organization, title, email, country.) | ICMM Specialist | Y | Y | Y | Y | Y | The outcome should include an expected year/period and a measurable indicator. The indicator only shows capacity building but there is no indicator about the strategic plan (number of Project activities including ICMM developed?) |
|  | ICMM Project activities = Management plans, strategies, and ICMM BMPs | Trained in ICMM - women |  |  |  |  |  |  |  |  |
| Outcome 3.2. Stakeholders engaged in ICMM in coastal marine prioritized areas. |  |  |  |  |  |  |  |  |  |  |
| Number of shrimp farms and fisheries in Project area that are reaching and/or maintaining compliance with Voluntary Standards (Marine Stewardship Council –MSC- and Aquaculture Stewardship Council -ASC) | Reaching compliance = Shrimp farms and fisheries that have not been previously certified that are implementing improvement projects (AIPs and FIPs) and meet the standard’s certification criteria. The target is that they become certified. | Shrimp farm | Voluntary Standards certificates, Records of ASC webpage listing certified producers | Shrimp farms, fisheries, ICMM Specialist | Y | Y | Y | Y | Y | The outcome should include an expected year/period and a measurable indicator, e.g., “By 2025, at least 20 stakeholders engaged in ICMM in coastal marine prioritized areas.” |
|  | Maintaining compliance = Shrimp farms and fisheries that have already been certified (ASC and MSC) and remain certified after yearly audit. | ASC certified |  |  |  |  |  |  |  |  |
|  |  | Shrimp farm ASC AIPs | FIP Action Plan and Benchmarking and Tracking Tool |  |  |  |  |  |  |  |
|  |  | Fisheries |  |  |  |  |  |  |  |  |
|  |  | MSC certified |  |  |  |  |  |  |  |  |
|  |  | Fisheries |  |  |  |  |  |  |  |  |
|  |  | MSC FIPs |  |  |  |  |  |  |  |  |
| Number of tourism and tourism development sector actors, and communities implementing better management practices (BMP) to protect coastal and marine habitats under Project activities. | BMP = protection or restoration activities[13] to protect coastal and marine habitats. | Number of tourism sector actors | Baseline developed by grantee or consultant prior to technical assistance, grantees, or consultant’s progress reports after technical assistance | Grantees, consultants and ICMM Specialist |  |  |  |  |  |  |
|  | Tourism sector = hotel and other tourism related businesses and tour operators, |  |  |  |  |  |  |  |  |  |
|  | Tourism development sector = construction businesses associated with tourism sector | Number of communities |  |  |  |  |  |  |  |  |
| Component 4: Project monitoring and evaluation and knowledge sharing |  |  |  |  |  |  |  |  |  |  |
| Outcome 4.1. The Project's monitoring and evaluation system employs participatory methods throughout Project lifetime. |  |  |  |  |  |  |  |  |  |  |
| Number of MAR2R progress reports completed (including mid-term and final evaluations and GEF IW Tracking Tool) |  | Progress reports | Report-evaluation documents | PMU | Y | Y | Y | Y | Y | Rewrite the outcome “By 2020, a participatory M&E system has been developed and implemented for the entire duration of the Project.” |
|  |  | Mid-term evaluation | Report-evaluation documents | M&E |  |  |  |  |  |  |
|  |  | Final evaluation |  |  |  |  |  |  |  |  |
|  |  | GEF IW Tracking tool |  |  |  |  |  |  |  |  |
| Outcome 4.2. Advantages of the ridge to reef approach shared with local and international audiences, including the GEF IW: LEARN community. |  |  |  |  |  |  |  |  |  |  |
| Number of communication and knowledge management products disseminated | Communication and KM products include: | WP | Webpage statistics | M&E | Y | Y | Y | Y | Y | It could include a measurable goal for the end of the Project |
|  | WP = Webpage |  |  |  |  |  |  |  |  |  |
|  | SM = Social media accounts | SM | Social media statistics |  |  |  |  |  |  |  |
|  | Pubs = Publications | Pubs | Publications produced |  |  |  |  |  |  |  |
|  | V/A = Video/Animation | V/A | Videos/animations produced |  |  |  |  |  |  |  |
|  | WB = Webinars | WB | Webinars hosted |  |  |  |  |  |  |  |
|  | NW = National Workshops | NW | Attendance lists to workshops hosted |  |  |  |  |  |  |  |
|  | IW = IW Conference | IW | Presentations made in IW conference |  |  |  |  |  |  |  |

## Audit Trail (Comments on Draft Report)

| Comments on Draft Report for MTE of MAR2R Project |  |  |  |
| --- | --- | --- | --- |
| Name / organization | Page number | Section, paragraph or statement being referenced | Evaluation Team Comment (e.g. correction, clarification, suggested text or adding context) |
| María Porta WWF Guatemala / Mesoamerican Reef | 5 | See Ana Victoria´s comment in the next page (Regarding Project completion date) | Updated the dates accordingly |
| Isabel Filiberto WWF-GEF | 6 | I would delete this. It seems to say that the project was designed to start on 01/11, which is not the case. The first disbursement was done on January 31st and the objective was to start much earlier, but due to problems in hiring the PMU, the project could not start as early as initially expected. | Updated the dates accordingly |
| Elizabeth O'Neill WWF WWF | 7 | Check English here. Confusing wording. “Negative aspects are related to delays in initiating some Project activities (e.g., due to lack of appropriate human resources, bureaucracy in terms of decision making)… | Paragraph modified |
| CCAD |  | Describe in a better way, taking into account that in the ministries and institutions there are natural and defined routes to make decisions and approve products. | Paragraph modified |
| CCAD | 8 | Sustainability of outputs, outcomes and impacts are planned and have been supported by various actions by governments, partners and CCAD with a high probability of success. It has been declared as highly satisfactory. Examples have been cited in financial, political, technical, productive and market actions. There are products and results that are sustained beyond the project. For example, measures with an R2R approach have been incorporated into the multiple policy instruments supported by the project (ERAM, ERCA, national policies, regional protocols, capacities, implementation of best practices, etc.). CCAD's institutional pathway includes the development of sustainability strategies or pathways. | Paragraph modified |
|  |  | Sustainability is provided by the institutional framework. In the commentary of the previous review, we argued the reasons why CCAD considers a high probability of sustainability. We do not agree that it is Moderate. | Clarification. The reason is described in the text itself. It is the need for an exit strategy and external resources to finance the continuation of resources at the national level. In any case, this score serves as a reinforcement to address these needs. |
| CCAD | 8 | there are products and results that are sustained beyond the project. For example, measures with an R2R approach have been incorporated into the multiple policy instruments supported by the project (ERAM, ERCA, national policies, regional protocols, capacities, implementation of best practices, etc.). CCAD's institutional pathway includes the development of sustainability strategies or pathways. | Paragraph modified |
| CCAD | 9 | The approach is unfounded. CCAD and its relationship with Mexico ensure sustainability with multiple actions and follow-up. CCAD through the Council of Ministers and the formalized relationship with SEMARNAT provides evidence of the sustainability of regional actions. The commitment of political and technical endorsement of regional instruments is one such evidence. In fact CCAD believes that regional sustainability is achieved by this route. An NGO or other external agency could not offer this guarantee of political endorsement and action. | The position is understood and we could clarify it; however, the consulting team considers that there is still no evidence of sustainability, yes with several additional efforts and issues that remain to be accomplished |
| Ana Rodríguez WWF-Guatemala | 9 | If the risks are low, why is the sustainability rating moderately likely? |  |
| Elizabeth O'Neill WWF | 9 | The language of the edit is too difficult to understand and vague. | Paragraph modified |
| Isabel Filiberto WWF-GEF | 10 | "Accordingly" to what? If we compare to the prodoc timeline, the project has been executed with delays. This report should explain why | Added: "accordingly to expected results despite delays up to the mid-term " |
| Amelia Kissick WWF WWF | 10 | Suggest adding: “by another evaluation team who did not complete the exercise” if you are going to write about the original evaluation at all, which you can decide if it is helpful. If you do mention it, please cite Integrated Sustainability Solutions in footnote. | Paragraph modified |
| Elizabeth O'Neill WWF | 11 | Is this referring to the first attempt at the evaluation? Need to fix the wording here. | Added: "evaluation the Project may have been rated..." |
| Isabel Filiberto WWF-GEF, Elizabeth O'Neill WWF | 11 | Why in the executive summary there are two summaries of relevance, coherence, etc. / The evaluation team was specifically asked to eliminate this redundancy but this apparently has not been fixed. | The first chart is a summary of the ratings per criteria as requested in the ToR, and the summary of findings summarizes each criteria |
| María Porta WWF Guatemala / Mesoamerican Reef / Isabel Filiberto WWF-GEF | 11 | From our experience, it was possible to achieve the targets related to certification in four years. It was ambitious but we knew that some of the companies were already in the process and the project´s support would have them reach certification. In fact, in the MAR countries the number of companies that reached certification during these four years are almost the same with the target in the Prodoc. Of course there were unforeseen situations like the one in Belize, but in fact the project has been able to work with the existing companies, although the number in smaller as some of them are not longer existing/working. Even though I am not in agreement with this part of the sentence, I made a change in the text to keep it and not change it completely. / So then, what is the problem? If there are facilitators that are already supporting the focal points… what is the issue? | Paragraph modified |
| Isabel Filiberto WWF-GEF | 11 | “Acceptance is perceived?” Unclear. Reword. | Paragraph modified |
|  |  | What do you mean? Improvement in what specifically? |  |
| Elizabeth O'Neill WWF | 11 | This section should provide a brief summary, component-by-component of extent of delivery on planned results, to support the opening statement “progress toward results is different across all four components.” The summary for each component should also discuss what has particularly supported or impeded delivery on planned results. / Can affect or did affect? This is written as a hypothetical versus a conclusion or finding. I think this is attempting to answer Isabel’s why above, but the statement should be reframed as an answer to that question versus hypotheticals. Why do the evaluators believe the rate of spend was significantly less than intended in the first half of the project implementation period? | Paragraph modified |
|  |  | To vague. This is explored in the recommendations. Sentence is deleted. |  |
| Elizabeth O'Neill WWF, Isabel Filiberto WWF-GEF | 11 | Two out of how many and which ones? It appears only one is described (# of policy instruments). What’s the other one? / I think the eval team needs to refer to the Result Framework and provide a systematic assessment of targets achieved per result indicator, indicating those that are behind and those at risk of not being achieved. |  |
|  |  | Why have such a vague statement when you could say something more informative, like “Progress toward planned results under Components 1, 2, and 3 is (choose: very behind, behind, on track, ahead, achieved) while attainment of planned results under Component 4 is on track and even ahead to some extent.” |  |
| Amelia Kissick WWF | 11 | I’m not sure where the claim comes from that the logical framework was designed due to “inherent bureaucracy and slow adaptability.” As far as I know, the workplan and results framework were not designed with that in mind – and are fairly standard for GEF projects. | Paragraph modified to clarify. Please review. The suggestion is for the logical framework to take the ‘inherent bureaucracy...’ into consideration, thus improving capacity to facilitate project execution at the mentioned institutions. |
| Amelia Kissick WWF | 12 | Since components2 and 3 were affected due to difficulties with certifications, can you summarize in a sentence or two what was the reason (eg covid)? | Clarified |
| Elizabeth O'Neill WWF, CCAD | 12 | These are Effectiveness findings, not Efficiency / In another chapter, they refer to the positive aspects of the team's permanency | Paragraph modified |
|  |  | Again, ambiguous wording. And possibly incorrect. The project is behind both in its spend and in its delivery of results, so in fact there isn’t a disparity but a consistency, right? The disparity is between what has been achieved/spent versus what was planned. |  |
| CCAD, Elizabeth O'Neill WWF | 12 | We believe it is also relevant to highlight the broad ownership, involvement and empowerment of the project by the four MAR countries and the CCAD as a regional political body. This is at the level of impacts, results and products. Under the premise that it is a GEF collaboration for the countries focused on global objectives addressing national and regional priorities under the national circumstances of the countries. / None of this is about Impact. Unless you are trying to say these are factors that have influenced the impact of the project thus far? Overall, the approach to this section is curious b/c it doesn't seem to attempt to summarize the evaluation's responses to the Results/Impact questions in the TOR: | This is mentioned later in the document |
|  |  | Why? This needs to be analyzed. Where the activities over budgeted and we are going to have savings, or the indicators were not good to really measure impact attributable to project activities? We need to explain this phenomenon. | Paragraph modified |
| Elizabeth O'Neill WWF | 13 | These are all Effectiveness issues – i.e., key challenges to be overcome to deliver on intended outcomes in order to ultimately deliver on ultimate impact. | Paragraph modified |
| CCAD | 13 | Through the implementation of the ERAM, CCAD has a broad portfolio of projects under development and others under management that complement and guarantee the sustainability of actions. In Selva Maya, the Moskitia, (as large forests in the region) the SAM, Dry Corridor, (for amounts over $150 million dollars for the next 5 years). | Thank you for the information |
| Elizabeth O'Neill WWF | 13 | Another inflammatory statement that is not well supported. | Paragraph modified |
| Isabel Filiberto WWF-GEF | 13 | Have those lessons learnt been documented? | Added: "though these have not been systematized and documented yet" |
| Amelia Kissick WWF | 13 | Note that lessons learned are documented in the semi-annual progress reports | Verified and Modified. Lessons learned are found in the semi-annual and annual progress reports of year 2. |
| Elizabeth O'Neill WWF, CCAD | 13 | Ambiguous wording. And possibly incorrect. The project is behind both in its spend and in its delivery of results, so in fact there isn’t a disparity but a consistency, right? The disparity is between what has been achieved/spent versus what was planned. / CCAD does not agree with this assertion. There is progress in the process, a consulting firm working on the facilitation of the process, involvement of stakeholders and commitment of the highest political level of CCAD ministries to endorse the product. The SAP is on target for completion in year 5. | Conclusion was modified |
| Isabel Filiberto WWF-GEF | 14 | How? ("Regarding strenghten the capacity") | We left this open for the focal points |
| Isabel Filiberto WWF-GEF | 15 | The findings and recommendations are very general and don’t dig in enough on the outcomes of the project. There are no recommendations for the TDA SAP or any other outcomes that present challenges. | Recommendations modified |
|  |  | Control of what and by whom? |  |
| Renae Stenhouse WWF-GEF | 15 | Regarding the recommendations, there is only one (finding 10 - The Project might not achieve the certifications of the productive sector) that relates to results/impact – so do we assume that all other work streams are progressing to be achieved? |  |
|  |  | Is this information presented in the report? Very important to present this information in a simple table. Please make reference here to the page where this information is being presented. |  |
| Isabel Filiberto WWF-GEF | 15 | The PSC doesn’t have an executing role. And the ET has said we are requesting too much from them. This should be lead by the PMU but should very much tailored to specific outcomes/outputs. What Outcomes should we focus on? The ET should advice on that. | Modified |
| Isabel Filiberto WWF-GEF | 15 | This is very general….. is not very useful | Deleted |
| Elizabeth O'Neill WWF | 15 | These are Adaptive Capacity issues | Modified |
| Isabel Filiberto WWF-GEF | 15 | Can you reword, what needs to be improved? Is the project knowledge management? | Modified |
| Isabel Filiberto WWF-GEF | 16 | I don’t think we need the PMU to lose time in implementing another software. The review of M&E has said above that the system was working. | Deleted |
| CCAD | 16 | For the CCAD as EA there is a surprise and contradiction, because in some parts of the document it says that the communication has been done well, but when looking at the recommendation it seems that it has not. However, making adjustments to improve is good and is taken well. A clarification is in order here, since the recommendation focuses on the OAR as a communication channel for the safeguards issue and omits the MAR2R portal, which is the project's own means of communication. Perhaps there is some confusion (both the OAR and the MAR2R portal are hosted on the SG SICA IT platform). | Taken into consideration |
| Isabel Filiberto WWF-GEF | 16 | How is this finding related to the recommendations below? They don’t match with the finding… | Modified |
| Renae Stenhouse WWF-GEF, Isabel Filiberto WWF-GEF | 16 | This is the only finding related to results. The evaluation team is confident that, with the above points addressed, all other outcomes will be achieved with no need for change in targets or scale? / Agree. Also, this is an action that is already ongoing. The PMU and the Agency are already discussing this issue and putting a solution to this. So it should say continue to prepare a critical path, or continue to work to modify indicators… | Taken into consideration |
| María Porta WWF Guatemala / Mesoamerican Reef | 17 | Some problems from whom? PMU? please state this in the text. In No. 19, there should be no difference between is stated in the Results Framework and what has been reported if the PMU followed the Prodoc. I don´t agree with how No. 19 is written. | Modified |
| Elizabeth O'Neill WWF | 18 | These recommendations speak to improving delivery on project outcomes, while Adaptive Capacity should speak to the quality of and improvement in M&E practice. | Taken into consideration |
| Amelia Kissick WWF |  | Yes, please move 28-29 effectiveness. | Modified |
| Isabel Filiberto WWF-GEF | 23 | MRV? | Added the clarification |
| María Porta WWF Guatemala / Mesoamerican Reef | 25 | I don’t´agree with this. Based on the experience from WWF Mesoamerica and our experience of what was happening in the region, this was achievable in the five years of the project. Also important to mention is that CCAD was the one that developed the Prodoc. We supported the CCAD to finish the Prodoc, as they had to end the contract of CATIE, but this support was provided to CCAD and in coordination with the focal points | Paragraph modified |
| María Porta WWF Guatemala / Mesoamerican Reef | 25 | Yes, I agree. WWF Mesoamerica was not the project designer. CCAD hired CATIE to develop the prodoc based on the PIF that WWF Mesoamerica developed together with CCAD and the focal points of the countries. WWF Mesoamerica supported to end the development of the Prodoc, based on the advanced by CATIE, given that CCAD had to end the contract with them. CCAD was given a grant by WWF to develop the Prodoc. I think you should put some of this in your answer. |  |
| CCAD | 26 | A clarification: regarding the institutions responsible for the strategies. The ERCA is the responsibility of OSPESCA and CCAD with MAR2R have been part of the design and consultation team. | Taken into consideration |
| Elizabeth O'Neill WWF | 26 | The following and preceding text wanders a lot into assessment of effectiveness versus relevance. But not worth making edits to address at this stage. | Taken into consideration |
| Amelia Kissick WWF | 28 | I’m not sure what this is trying to say; perhaps the English can be checked? I think what is trying to be said is that the TDA/SAP was important to achieve as so much of the Project depends on its completion? | Modified |
| Elizabeth O'Neill WWF | 29 | Not sure what this is trying to say. This seems to be a different author from the Relevance section. I wonder if that author could do a final edit for language and clarity to generate the final report, because there are a lot of issues with how things are framed. / I’m also totally unclear as to what this section is trying to say. What can be explicit or implicit? And what does “If it is implicit…” mean? And then what does the “critical analysis” accomplish? | Paragraph modified |
| Elizabeth O'Neill WWF | 29 | This is a very long single sentence and is really unclear. | Paragraph modified |
| Elizabeth O'Neill WWF | 30 | Another very long run-on sentence, the meaning of which is unclear. | Paragraph modified |
| Elizabeth O'Neill WWF | 30 | I’m also not clear what this text is trying to say. | Paragraph modified |
| Elizabeth O'Neill WWF | 32 | What is the purpose of this section? It seems to be a listing of all of the planned outputs by outcome by component? Why do that? | Paragraph modified |
| Elizabeth O'Neill WWF | 32 | There were extensive edits from here to just before “Impact Probability.” It was hard to discern what was done and why so I just accepted the changes so I could read the new version. | Paragraph modified |
| Isabel Filiberto WWF-GEF | 32 | How is this done? What action plans are you referring to? | Paragraph modified |
| Amelia Kissick WWF | 32 | Is this % expenditure of each component or % execution of the workplan budgeted for each component? | Explained |
| Elizabeth O'Neill WWF | 33 | Where did these questions come from? Why these instead of the questions in the TOR? | Paragraph modified |
| Elizabeth O'Neill WWF | 33 | I’m not sure what is meant by “compliance” in these questions, but I don’t think that is the right word, because wherever it is used, the question is difficult to understand. | Paragraph modified |
| CCAD | 33 | The Yucatan Peninsula Watershed Council and its auxiliary bodies (commissions and committees) are also a clear example of how an ISNC works within the framework of the project. | Taken into consideration |
| Isabel Filiberto WWF-GEF | 33 | It is surprising that in the document there isn´t an analysis or a mention to the ISNCs. These are important institutional national level structures for the project. They are key for the TDA / SAP process. The ET should have reviewed what is the level of work done to date with ISNCs and if this is aligned with what was defined in the prodoc. (page 81) or if there are any recommendations for improvement. | This was mentioned in the previous section |
| Isabel Filiberto WWF-GEF | 35 | How is this done? What action plans are you referring to? | Added: created in components 2 and 3, that align with regional priorities…' |
| Isabel Filiberto WWF-GEF | 35 | Because of the way this is written, I’d recommend moving this section to become the first section under Project Implementation below. | We consider leaving this section here |
| Isabel Filiberto WWF-GEF | 35 | Review and ensure this section answers the following EFFECTIVENESS and RESULTS/IMPAC QUESTIONS from the TOR.EFFECTIVENESS IS ALMOST 30 PAGES OF REPEATED INFORMATION WITHOUT STRUCTURE. This section needs a good structure. It is impossible to read what are the key messages, findings, and recommendations with a text so disorganized. | Section re-written |
| Amelia Kissick WWF | 35 | I think this section still lacks structure. Please use sub-headings to support the flow and comprehension. | Accepted and modified |
| Elizabeth O'Neill WWF | 36 | Not sure what this is trying to say. Maybe “a rate of spending that was behind what was projected”? | Deleted |
| Isabel Filiberto WWF-GEF | 36 | What does this mean? Delays in the schedule of grant agreements. What is the reason for that_ What is the specific recommendation to solve this issue. Same with delays in contracting consultants. None of this appear to be covered with specific recommendations in the recommendation table. | Deleted |
| CCAD | 37 | Institutional procedures are defined in each country, ministry, institution. They are solid and do not block. | Modified |
| Amelia Kissick WWF | 37 | By who? | Modified |
| Isabel Filiberto WWF-GEF | 38 | Same comments as when this text appears in the Exec Sum. Which two indicators? It appears only one is discussed. And two out of how many? Findings regarding extent of achievement should always be written in relative terms. E.g., something like, “Of the five indicators for the project objective, two have been achieved, one is on track, and the other two are behind.” | Section re-written |
| Ana Rodríguez WWF-Guatemala | 39 | According to their planning this should be achieved by the end of 2022. However, we have not received feedback from Mario on how the TDA/SAP process is going, which we should have at the monthly meeting in March 2. |  |
| Ana Rodríguez WWF-Guatemala | 39 | According to information that Mario shared with me, because I had the same concern, an update was made to the results framework and therefore the correct thing would be 175 men and 175 women. The update was made in Dec.2019. |  |
| Elizabeth O'Neill WWF | 40 | At this stage, I would recommend that you move the summary statement of achievement that appears at the end of each outcome section up to the start of the section and add in the relevant indicator(s) and a brief summary of what data on that indicator tells us in terms of behind/on track/achieved. This can be done very briefly and then the existing text can serve to support that short summary of outcome attainment. |  |
| Amelia Kissick WWF | 41 | I think this is an English mistake. I think you are referring to disbursement or expenditure, not the execution of the workplan activities, right? Please clarify. | Modified |
| Amelia Kissick WWF | 41 | Please check the English. This is unclear. Do you mean 50% of the watersheds of the Mesoamerican reef are influenced by project activities? I am not sure. | Modified |
| Amelia Kissick WWF | 41 | Execution of workplan activities or disbursement of projected funds? | Modified |
| CCAD | 41 | The ISNCs are fundamental in the development of the project, and although there is no explicit objective/output/outcome in the project results framework, they have been worked on because of the fundamental importance they represent. In fact there are a number of lessons learned that are being compiled around the ISNCs taking into account their relevance for dialogue and participation, and also because the dynamics of these are based on national circumstances that go beyond the competence of any cooperation project. | Modified |
| Isabel Filiberto WWF-GEF | 41 | It is not clear if ISNC are up and running or not yet working. Have those committees been stablished and have started being operational or not? | Modified |
| Amelia Kissick WWF | 42 | You’re recommending these documents be revised at this point in the project? | Clarified |
| Amelia Kissick WWF | 42 | What section is this supposed to be under? It is currently sitting under Product Quality Management, which I guess is under “Effectiveness” sub-heading under Implementation heading. However, it is introduced as the most ‘relevant’ results. | Accepted and modified |
| Ana Rodríguez WWF-Guatemala | 43 | According to PPR the regional demonstration project has been updated and they have continued to work on it. It would be necessary to see in detail what the discrepancies are. | Section re-written |
| CCAD | 43 | It is requested to eliminate or improve the wording of the paragraph, based on the explanations described below. The project document is validated by the Committee and experts. It clearly identifies the objectives, products and activities. it is provided by Marfund within the framework of the governance set up to implement it. The Regional Dialogue Group. It is ongoing and the products that come out are reviewed and validated by this group. Regarding national policies, they have a national process of approval and official publication (in the official gazette of Honduras, for example). Regional instruments are endorsed by the CCAD Council. |  |
| Elizabeth O'Neill WWF | 43 | I’d move these overarching summary statements of attainment of each outcome to the start of the outcome analysis (as a thesis statement) versus leaving them to the very end. |  |
| Isabel Filiberto WWF-GEF | 44 | And what is the status of this work? |  |
| Isabel Filiberto WWF-GEF | 44 | The verbal tense of this paragraph doesn’t make sense. Review. The TORs are not being reviewed. The consultancy is running. |  |
| Isabel Filiberto WWF-GEF | 44 | Do you mean WWF GEF Agency? |  |
| Isabel Filiberto WWF-GEF | 44 | What is the current status of this work? |  |
| CCAD | 44 | According to the results framework, the SAP endorsed by the council of ministers in year 5. |  |
| Elizabeth O'Neill WWF | 44 | I don’t understand this finding. It is satisfactory due to delays? Wouldn’t delays reduce the rating somewhat? Just confusing. |  |
| Isabel Filiberto WWF-GEF | 45 | Apart from that, what can you conclude of the national processes for updating information in the REO_ Are they advancing satisfactorily? |  |
| CCAD | 45 | The protocol is developed and validated by the 4 countries (there is one regional and one per country). there is probably a confusion in the verifying annex. we can compare the correct ones. At the time of the evaluation the route was probably in process. |  |
| Elizabeth O'Neill WWF, Isabel Filiberto WWF-GEF | 45 | This is useful content. I’d move this into an introductory paragraph for the component 1 section and so similar for each of the component analyses (noting Isabel’s comment below that summaries like this should speak to the period evaluated, not just year 1). / What about year 2 and year 3? What is the status at the time of the MTE? We are not assessing only Y1 |  |
| CCAD | 46 | The project has worked to adapt the generic concept of "water reserves" with which prodoc was designed to national circumstances, policies and regulations. In this sense, progress has been made in capacity building. For example, in the case of Honduras, the concept of "water reserves" has been adopted by the country within the framework of the policy and the "Special Regulations for Water Recharge and Water Producing Reserve Zones". |  |
| CCAD | 46 | A public policy instrument is developed by internal and external experts of an institution (ministry), and are validated in open public processes also with experts and approved by the ministries according to their internal process. In this sense it is a bold assertion if a reviewer has an opinion of "questionable quality" of a document that has had a process as described above. I believe that here should go the opinion of the Ministry that is developing the instrument. Where the usefulness and application that this will have is made evident; and in this way, this strong assertion should be refuted. It is requested to be eliminated |  |
| CCAD | 47 | Clarification. Both territories have priority and follow the same process. a) management program and b) demonstration project. It is only a matter of order. rio Hondo was done first and then Tulum (that is why at the date of evaluation it was at draft level). |  |
| CCAD | 47 | this confirms the usefulness and priority that the Honduran government has given to the issue of water reserves, obviously under national considerations. |  |
| Isabel Filiberto WWF-GEF | 47 | The involvement of governments in the development and validation of action plans, created in components 2 and 3, that align to comply with regional priorities nationally with the regional Project is crucial. What plans are we referring here? Can you specify? | Clarified |
| Elizabeth O'Neill WWF | 48 | At this stage, if Ana is correct with her statement above, I would clarify that this text is based on the Year 2 Support Mission and note where the questions re: quality were documented. Cite the source. | Section re-written |
| CCAD | 48 | What is the quality questioned? for example, the diploma course in reference was developed by FLACSO, which is a serious academic entity and has met all the academic standards and quality of the experts who developed it. wwf gef questions this? We request to delete this comment. |  |
| CCAD | 48 | this statement is from the evaluators? |  |
| CCAD, Isabel Filiberto WWF-GEF | 49 | this is an ongoing process, it has not been concluded. It is having the attention and leadership of the government of Belize / Again, the ET should make its own assessments and present its conclusions based on those "independent" assessments of the project documentation. |  |
| Ana Rodríguez WWF-Guatemala | 50 | What year? |  |
| CCAD | 50 | moderately unsatisfactory but for other reasons. for which adaptive management has been requested. For example those that have been described previously about the difficulty of achieving certifications. For example, the PTAR treatment plants diploma course is an outcome with institutional political support by CONAGUA and CONANP; academic support by specialized universities, technical field work and follow-up to improve PTAR performance by local partners such as ASK. The Mexican government, stakeholders and operators will not consider this as unsatisfactory. |  |
| Isabel Filiberto WWF-GEF | 50 | the wording of this sentence is poor. Its very hard to understand. Documents where? What documents are you referring to? What is the recommendation? |  |
| Isabel Filiberto WWF-GEF | 50 | Workload of whom? What is the recommendation to this issue? |  |
| CCAD | 50 | we assume you are referring to the wwf gef safeguards experts. |  |
| Ana Rodríguez WWF-Guatemala | 52 | It would be good to know on what dates they were. |  |
| Isabel Filiberto WWF-GEF | 52 | If we don’t do this assessment in a systematic way, indicator by indicator. We cannot know to which targets are this activities contributing to. |  |
| Isabel Filiberto WWF-GEF | 55 | Adaptive management on what with what purpose? |  |
| Isabel Filiberto WWF-GEF | 55 | For all the challenges and limitations presented in this section, what are the recommendations of the ET? |  |
| CCAD | 57 | It is not CCAD's web site as such, since the organization has an institutional one and the MAR2R project has its own. However, it is also disseminated through CCAD's institutional website. It has also been clarified above that both sites. CCAD and MAR2R are hosted in the infrastructure of the SG-SICA. |  |
| Isabel Filiberto WWF-GEF | 57 | What does this means? What is the challenge? |  |
| Isabel Filiberto WWF-GEF | 57 | The text that starts from here is very hard to read and understand. You should have inserted your indicator assessment above |  |
| Renae Stenhouse WWF-GEF | 58 | I don’t think I have seen ratings at outcome level before, and don’t know what 1.3 or 1.4 means, is that outcome number? Can you note what the outcome is and what the achievement to date is? e.g For Outcome 1.3: MAR has a TDA and an SAP that will guide the ecoregional R2R management, key progress to date has included xxx / Which outcomes are these and what is the level of achievement? |  |
| Renae Stenhouse WWF-GEF | 58 | By who? |  |
| CCAD | 58 | This is an issue that has been discussed in depth. there was little receptiveness to the issues related to the difficulty of achieving certification. this is currently a matter of mutual understanding between the implementing agency and the executing agency. The solution route is clearly defined. For this reason it is suggested to modify the text. Or delete the comment. |  |
| Elizabeth O'Neill WWF | 58 | Page 46 says With specific recommendations on particular targets and their concept, the PMU and the CCAD confirm that the enabling conditions are now in place to advance towards achieving these targets on time. We don´t know if the ET agrees with this statement or not, since they haven´t done a proper technical assessment of the situation. But then on page 66 they say: Significant improvement is needed to implement the remaining activities. Based on the above findings and conclusions regarding Effectiveness and Efficiency, as well as the extremely poor relationship with the Implementing Agency (IA), the Executing Agency has to find a way to work productively (with reciprocal collaboration) with the IA. It would be very helpful to present the assessment that justifies this claim, the priorities where we need to focus and the specific recommendations for improvement. |  |
| Isabel Filiberto WWF-GEF | 58 | Relevant outcomes for what? |  |
| Isabel Filiberto WWF-GEF | 59 | This is not a challenge, what was the challenge |  |
| Isabel Filiberto WWF-GEF | 59 | Which ones? This is very important to highlight. Also in the summary of the report, at the beginning |  |
| CCAD | 60 | and SAP endorsement for year 5 according to results framework. |  |
| CCAD | 61 | In this regard, it has been explained that the validation and approval of final products involves the participation of authorities, experts and platforms, as the case may be. |  |
| CCAD | 61 | This question has been requested to be removed, taking into account that it is a sovereign decision of the governments of the countries involved to define how to address the issue of water reserves. The project has provided technical assistance through experts including high level experts from the WWF Mexico office. |  |
| Isabel Filiberto WWF-GEF | 43 | What is the finding of the ET and what is the recommendation? | Accepted and modified |
| Amelia Kissick WWF |  | I don’t know what #2 is trying to say. | Accepted and modified |
| Amelia Kissick WWF | 43 | I’m confused about the structure here and for the remaining paragraphs below. Can you put a sub-heading to explain these next few paragraphs and try to clean up the structure and flow? | Accepted and modified |
| Amelia Kissick WWF | 43 | Are you saying that despite the partner assessments indicating appropriate capacity, it turns out they did not? Or what is meant by the evaluation of their capacities? Was this done after the fact to understand their weaknesses to build their capacity? Sorry, I just don’t understand the intention of this statement. | Paragraph was edited and partly moved to Sustainability. Text referred to in Amelia’s comment was deleted |
| Amelia Kissick WWF | 43 | Does this belong under sustainability? | Accepted and modified |
| Isabel Filiberto WWF-GEF | 44 | Which ones? This is very important to highlight. Also in the summary of the report, at the beginning | This is stated in the Effectiveness evaluation by Component and Summary findings section. Deleted to decrease repetition |
| Amelia Kissick WWF | 44 | Back to summarizing challenges… | Accepted and deleted |
| Amelia Kissick WWF | 44 | Out of place? Sustainability? | Accepted and modified |
| Amelia Kissick WWF | 44 | This must be here in error. This looks like the description for efficiency. Please erase. | Accepted and modified |
| Elizabeth Oneill / Isabel Filiberto WWF-GEF | 44 | At this stage, if Ana is correct with her statement above, I would clarify that this text is based on the Year 2 Support Mission and note where the questions re: quality were documented. Cite the source. | Accepted and modified |
| Elizabeth O'Neill WWF | 45 | This sentence is really difficult to understand. | Modified |
| CCAD | 36 / 45 | We suggest complementing the conclusion, indicating that one of the reasons for this is due to the multiplicity of actors and sectors involved, for example small community coffee producers in the Merendón mountain range, and community members who are restoring corals in the Mayan Riviera. And we would like to have a specific recommendation on how to address this scenario. | Taken into consideration |
| Amelia Kissick WWF | 53 | This statement is not correct. Please revise. There are targets set during the proposed measurement periods. The M is not to determine whether or not the results are measurable only at the end of the project. Instead, “measurable” should mean that the indicator has capacity to be counted, observed analysed, etc to be measured for progress. Is there a clear means by which to measure each indicator? “No” was given for both M and T across all indicators, and I suggest that the evaluation team look at this again . | Accepted and modified |
| Amelia Kissick WWF | 54 | What terminal evaluation? | Revised and modified |
| Elizabeth O'Neill WWF | 55 | I am still confused by this finding of satisfactory efficiency given that the remaining 64% of the resources will need to be spent in the final year of the project. Are you saying that for the results obtained with the resources expended so far, they have been efficient? But when it comes to overall execution during the intended timeframe, they have been inefficient? | Section modified |
| Elizabeth O'Neill WWF | 55 | This should probably be the first sentence of this section, followed by the primary findings re: Efficiency, then supported by detailed analysis. | Modified |
| Elizabeth O'Neill WWF | 55 | This detail here and in the following paragraphs doesn’t add any value. The number of outputs is irrelevant. It’s the nature of the outcomes and outputs that’s important. | Deleted |
| Elizabeth O'Neill WWF | 55 | Ensure that this section responds to the following SUSTAINABILITY QUESTIONS from the TOR: Is there evidence that aspects of sustainability are being established or exist to the extent necessary to ensure the desired long-term impacts of the Project? What external factors could have a high or medium likelihood of undoing or undermining the future sustainability of Project’s positive impacts? Do relevant stakeholders have or are likely to achieve an adequate level of “ownership” of results, to have the interest in ensuring that project benefits are maintained? Do relevant stakeholders have the necessary technical capacity to ensure that project benefits are maintained? To what extent are the project results dependent on sociopolitical factors? Are there any environmental risks that can undermine the future flow of project impacts and Global Environmental Benefits? Is the project adequately anticipating and taking measures to ensure resilience to these external factors? | Section modified |
| Isabel Filiberto WWF-GEF | 57 | I think this section should compare what the project has implemented versus what the prodoc was proposing. Are all structures and stakeholders engagement mechanism planned in the prodoc been implemented? | The Governance and Management arrangements section already includes that information and is now part of this section |
| CCAD | 58 | Capacity building and strengthening of implementing partners is carried out directly by the PCU safeguards specialist. The WWF GEF specialist supports the PCU specialist in the review of the instruments developed by the partners and the PCU specialist. It is a joint work. | Taken into consideration |
|  |  | Again, the MAR2R safeguards specialist is the one who provides the training to the partners, in coordination with the WWF GEF safeguards expert. | Accepted modified |
| CCAD | 59 | Are you referring to the first draft of the EMT? | Modified |
| CCAD | 59 | Please standardize the language in the same way as it is written on the cover page and throughout the content of the report. The MTE is one, the one done by Quorsus. | Accepted and modified |
| Amelia Kissick WWF | 59 | It is asked in the TOR to review and validate the original MTE on safeguards, so it is ok to reference here, but I agree clarification was needed. |  |
| Amelia Kissick WWF | 59 | Also, please provide footnote reference to Integrated Sustainability Solutions (ISS) if no annex to the original SG findings. |  |
| Amelia Kissick WWF | 59 | Based on the information captured by THIS evaluation team, do you validate the findings of the original report? I think it would be helpful to state if so or if not here. | Clarified |
| Elizabeth O'Neill WWF | 60 | As commented where this sentence first appears, this is confusing. Disparity would suggest that they have spent a lot and achieved very little, or vice versa. That would not be consistent with other findings in this report. | Modified |
| Isabel Filiberto WWF-GEF | 60 | Reaching the targets of delays? Not sure if the sentence is correct | Modified |
| Isabel Filiberto WWF-GEF | 60 | What do you mean? Improvement in what specifically? | Deleted |
| Amelia Kissick WWF | 60 | My opinion is that most of the lessons here are so generic and obvious to not be very helpful. Is there anything more specific to this project, relating to the REO or demonstration projects, certifications or its application of safeguards and stakeholder engagement? | Taken into consideration |
| Amelia Kissick WWF | 60 | The reception? | Accepted |
| Amelia Kissick WWF | 62 | I assume you mean results? I took the liberty of revising. | Accepted |
| Amelia Kissick WWF | 62 | I’m pretty sure I read the opposite statement earlier in the document, that the outcome language was too vague even if for flexibility purposes. Please align throughout the document whatever the finding is. As a side, can’t targets be set and then with proper justification be modified with GEF approvals? Also, isn’t this the opposite of SMART concept? (see pg 114-115). | Accepted |
| Amelia Kissick WWF | 63 | Selection of CCAD as EA is stated #1,#2,#5, as well as #7. Perhaps consolidate to remove redundancy. | Accepted and modified. |
| Amelia Kissick WWF | 63 | PMU? In what way did the PMU interact with the PSC that was particularly unique? Did they meet an unusual number of times or was it the way that they interacted…. Etc? | Accepted and deleted |
| Amelia Kissick WWF | 63 | Any specific technologies to note? | Clarified |
| Amelia Kissick WWF | 64 | Could you suggest (in efficiency probably) how to improve this more specifically than just ‘communication channels’? | Accepted and deleted |
| Amelia Kissick WWF | 64 | Not accurate according to WWF GEF Safeguards specialist who states, “there is no project level GRM, but they're supposed to be using our GEF Agency GRM for the project, and each demonstration project (under component 2) has developed their own GRM. We didn't need a project-level GRM because there aren't many risks for Component 1 and the high level policy work, so we just said they could use the WWF GEF GRM. But for the demonstration projects, since there are actually on the ground activities that could have an impact, we said that each organization doing a demonstration project needs to have one.” Please revise. | Accepted and modified. |
| Isabel Filiberto WWF-GEF | 65 | In the context of what outcome? To support the delivery of what project strategy? | Accepted and deleted |
| Isabel Filiberto WWF-GEF | 65 | Annex 3 of what document? What is the specific recommendation here_ | Annex 5.11 |
| Amelia Kissick WWF | 65 | Anything specific to replication? Findings 4, 5 and 7 cover it somewhat but not explicitly | Taken into consideration |
| Amelia Kissick WWF | 65 | 84% achievement is satisfactory, so I am confused why this is specifically mentioned to monitor. | Accepted and modified |
| Amelia Kissick WWF | 65 | Specifics here could be helpful. | Accepted and modified |
| Amelia Kissick WWF | 66 | You may be mistaken here – see comment above and be specific here. | Accepted and modified. Also see recommendation modification below |
| Amelia Kissick WWF | 66 | Please see comment above from WWF GEF Safeguards specialist. There are already GRMs in place. | Accepted and modified. |
|  |  | Erika Drazen, WWF GEF Safeguards Specialist states on the WWF GEF GRM, “we have an email that they can submit complaints to, and then there's the third-party provider, Ethics point. https://secure.ethicspoint.com/domain/media/en/gui/59041/index.html The complaints submitted here go directly to our legal team” On demo project level GRMs, Erika is not sure if they are anonymous or only confidential – the PMU safeguards specialist would know. | Modified |
| María Porta WWF Guatemala / Mesoamerican Reef | 67 | Some problems from whom? PMU? please state this in the text. In No. 19 (now 57), there should be no difference between is stated in the Results Framework and what has been reported if the PMU followed the Prodoc. I don´t agree with how No. 19 is written. | Modified |
| Amelia Kissick WWF | 67 | See comments about SMART I already provided –about M and T analysis | Accepted and deleted. |
| Isabel Filiberto WWF-GEF | 77 | 36 is still very low at mid term. ET should explain why | Explained in finance section |
| Elizabeth O'Neill WWF | 78 | This is the 4th time findings are summarized. At this point, we can leave as is. But there remains a lot of redundancy in the report. Assuming this table is the same as the one in the Exec Sum, please refer to comments there to edit this one. | Deleted |

# Management Response to Evaluation Report

| Project title | Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R) |
| --- | --- |
| GEF ID/WWF GEF ID | 5765 |
| Evaluation completion date | May 2022 |
| Response completion date | November 2022 |

| Copy of MTE evaluation provided to: | GEF Secretariat, PMU (in turn will provide to PSC and project partners) |
| --- | --- |

# Introduction

This management response presents feedback from the WWF GEF Implementation Agency to the GEF regarding the Mid Term Evaluation report for the project “Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R)”. This feedback has been prepared by WWF GEF Agency, in collaboration with the Project Management Unit (PMU) at CCAD, the Project Executing Agency.  The management response clarifies some inaccuracies of the MTE report that were not adequately addressed by the Evaluation Team and presents a follow-up Action Plan to respond to the key MTE recommendations.  The WWF GEF Agency looks forward to continuing working with CCAD to conclude the project in a successful way, considering the opportunities for improvement identified in the follow-up Action Plan.

# Part I. Quality of the Report

The rate of this report is Satisfactory. Findings were consistent with some issues/topics that were already identified by the PMU and WWF GEF AI.  However, recommendations were listed without any guidance on which should be addressed before or with higher priority and some of them seemed repeated, or at least the detail of the information provided in the recommendation did not provide enough information to defined whether they were different.

PMU and WWF Mesoamerica did not agree with some of the recommendations.

Clarifications to inaccuracies and gaps identified in the MTE report include:

- Page 6 wrongly states that the Project is implemented by the Central American Commission on Environment and Development (CCAD).  WWF US GEF is the Implementing Agency (IA) and CCAD is the Executing Agency (EA).

- Page 6 wrongly states that the Ministries of Natural Resources in Belize, Guatemala, Honduras and Mexico are executing the Project.  The Executing Agency is CCAD.

- Page 7 states that while the Project design was ambitious for the available resources, most of the output targets are being achieved and the Project is expected to reach the intended outcomes to a large extent.  WWF GEF IA does not agree with this, as the outputs and outcomes were defined based on WWF´s knowledge and experience in what could be reached in the 5 years of the project, with the available resources from GEF and from the co-financing. The statement contradicts the stated in the table in the same page in the line “How do you assess Project Efficiency? where it says: “The Project inputs appear to have been adequately budgeted and planned, attaining significant co-financing to cover its costs”.

- Page 8 states that the project is adequately staffed, however in some recommendations it indicates that there is a need to evaluate the M&E capacities to ensure compliance with deadlines and follow up activities, identify best strategies, when necessary (page 16 number 13), and enhance the M&E function to ensure better reporting and monitor the technical quality of the documents presented as Project outcomes (page 17 number 27).

- Page 12 the name from OSPESCA is incorrect.

- Page 36 states that 1.3. is “satisfactory (on track)”.  WWF GEF IA does not agree with this as the TAD and SAP should have been completed by Year 3, not under development by this year.

- Page 58 No. 7 states “Result specificity is a commitment that has risks”.  WWF GEF IA does not agree with this as GEF projects are characterized by specificity of actions that have to be defined in the ProDoc for approval by GEF.  The Project´s results cannot be general to get the approval from GEF.  This is why the governments of the countries and other stakeholders were included in the design of the Project and during the elaboration of the ProDoc, so they could raise concerns and identify risks that the project had to take into consideration during implementation.

- Page 59 No. 7 states “Lobbying with local government and partnerships to define priorities.  No lobbying has been done.

# Part II. Follow-up Actions to Recommendations

| Specific Recommendations | Response and Priority | Response Actions | Timeframe | Person or Office Responsible | Tracking Status | Comments |
| --- | --- | --- | --- | --- | --- | --- |
|  | Do you agree/? What priority would you place on the recommendation (low, medium, high)? | Indicate what actions should be taken in response to the recommendation. | Deadline for each action. | Who will carry out? | Indicate date and if each action is Complete, Partially Complete or Pending. | Provide any comments related to the status of each action. |
| Effectiveness / Finding 1: Since 70% of the Project duration has elapsed with only 36% of resources executed, the remaining 64% must be invested in the 15 months remaining (30%). |  |  |  |  |  |  |
| 1. Organize a workshop with the participation of the Implementing and the Executing Agencies to adopt a clear road map to guide diligent efforts to improve and accelerate the implementation of the remaining outcomes/outputs, with the spirit of adaptive management and under the leadership of the PMU and the accompaniment of the PSC. | Agree. High priority. | - Carry out monthly calls between IA and PMU/EA. - Carry out Pause and Reflect workshop. | - Jun, 2022 - Nov, 2022 - Jan, 2023 (during Support Mission) | - WWF - PMU | - On-going, since Feb 2022 - Pending - Pending | Monthly meetings have been organized and carried out since February, 2022. |
| 2. Strengthen the capacity of focal points (with the identification of needs) in each Project implementation zone to contribute to timely delivery of Project outcomes. This could be done through routine performance analysis to identify the strengths and opportunities for improvement. | Agree Partially. Medium priority. The focal points are not responsible for the project outcomes. However, the Project has increase coordination with focal points through periodical meetings for timely information and decision making. | - Carry out periodic meetings with Project Steering Committee to analyze needs by country and regionally. - Hire specific consultancies to support management, supervision and execution of project activities. | - May to August 2022 - May to June 2023 | - PMU - PMU | - Completed - On going | Minutes of the meetings are available. Specific consultancies have been hired to support focal points. |
| 3. Establish adaptive management changes to components 2 and 3. See recommendations included under Adaptive Capacity. | Agree. High priority. | - Develop and implement road map for adaptive management, including requesting changes in some indicators of these components. | - Dic 2021 to May, 2022 | - PMU (Mario Escobedo, PSC, and WWF) | - Completed | - The road map was developed and the action were taken, including requesting changes for indicators related to these components. |
| 4. Assure progress towards objective indicator “Area (ha) of watershed under IWRM Project activities.” According to annex 5.10, the percentage obtained at year three is 84.18%: 1,336,652.69 ha out of 1,587,934 ha. | Agree, but already happening. Medium priority. | - Action plan for Y4 includes a clear path to comply with the target of the project, through additional demonstrative projects within Component 2. | - Oct 2021 | PMU | - Completed | - Several demonstrative projects have been identified and started to meet the target: a. Tulum management plan b. New River management plan c. Belize River management plan |
| 5. Present a proposal for extension of ideally 12 months with a clear justification and action plan to achieve pending outputs. | Agree. High priority. | - Develop and implement a road map for the extension of the project execution period. | - Dic 2021 to May, 2022 | PMU, PSC, and WWF | - Completed | - PMU implemented the road map and requested the extension of the project execution period to WWF GEF IA, which was approved on April 27, 2022. The amendment was fully execute by May 13, 2022 and received by WWF GEF IA on May 16th, 2022. |
| 6. Reschedule and continue to prepare a critical route path to align activities related to certifications in components 2 and 3 to the targets defined in the results framework to contribute to their achievement. | Agree. High priority. | - See No. 3 | - Dic 2021 to May, 2022 | - PMU | - Completed | - See No. 3 |
| 7. Identify all stakeholders with/in the process of certification and coordinate meetings/encounters to foster collaboration and knowledge sharing, helping them contribute to each other’s process. Bring case studies that are in the Project’s scope such as DIGEPESCA and the RARE experience in Honduras. | Agree. High priority. | - Carry out workshop with stakeholder to foster collaboration and knowledge sharing. | - March, 2023 | - PMU | - Pending | - The workshop is planned for the second quarter of Y5 Work Plan. Also, the development of regional guides for specific productive sector related to certification is included. |
| Efficiency / Finding 2: Internal and external communication gaps affect timely Project implementation |  |  |  |  |  |  |
| 8. Prepare a critical route with specific steps to implement the communication strategy developed in 2019 to ensure that the Project’s constituency have all the necessary information. | Agree. Low priority. | - Review communication plan to better reach beneficiaries and partners with the knowledge products developed by the project. | - Jan, 2022 to Jun 2023 | - PMU (Sandra Serrano) | - Ongoing | - There is a communication plan that is being implemented and have met the targets. The MTE report mentions that project has developed content and disseminated the project knowledge products. However, not all beneficiaries or partners are aware of the knowledge products. The implementation of the communications plan during Y4 and Y5 has taken this into consideration. |
| 9. Review and adjust the communication channels between the PMU and the executing partners to support opportune and informed decision-making processes. | Agree. Medium priority. | - Carry out monthly meetings with executing partners to support opportune and informed decision-making processes. | - Jan 2022 to Jun 2023 | - PMU | - On going | - The PMU is carry out monthly meetings with executing partners to monitor progress of activities and budget execution. Additional meetings are carried out with the participation of all the executing partners in the country to exchange experiences and lessons learned and inform about the project progress. |
| 10. Identify and Implement best communication strategies, tailored for target beneficiary groups to improve project transparency and communication (i.e. e-mail newsletters, website, videos). | Agree. Low priority. We agree with the importance of identifying and implementing best communication strategies, however we consider that communications have been carried out in a transparent way. | - See No. 8 | - Jan, 2022 to Jun 2023 | - PMU | - On going | - The Project has developed e-mail newsletter, website, videos that are limited to certain beneficiary groups that have access to internet. Additional communication products should be developed during Y4 (revisit) and Y5 communications plans to take this into consideration. |
| 11. Use the Regional Environmental Observatory platform as a communication channel, based on established safeguards. | Agree. Low priority. | - Revise Y4 Work Plan and include in Y5 Work Plan to include specific activities to establish the REO as a communication channel. - Develop a specific chapter in the Sustainability Strategy for the REO, that will include the explanation of the usefulness of the tool related to information access, knowledge sharing and communication. | - Dec, 2021 to Jun 2023 - Jun, 2023 | - PMU - PMU | - On going - Pending | - The REO warranties that information can be access openly. |
| 12. Monitor and implement the Risk Management Measures related to effective communication. | Disagree During the implementation of the communication plan no risks have been identified. |  |  |  |  |  |
| 13. Evaluate the M&E capacity to ensure compliance with deadlines and follow-up activities, identify best strategies when necessary. | Agree. High priority. | - Evaluate need to strengthen M&E and take actions accordingly - Develop a color-coded tool for M&E - Develop actions to follow up and supervise executing partners (See No. 9) | - Nov 2021 to Jun 2023 - Nov 2021 - Jun 2022 to Jun 2023 | - PMU - PMU - PMU | - On going - Completed - On going | - Hired a person to support monitoring activities (Enriqueta Ramírez). Based on the evaluation it has been decided to strengthen the M&E capacity through the participation of the whole PMU in M&E activities. - The color-coded tool for M&E was developed and is being used. - See No. 9 |
| 14. Ensure that focal points use the detailed critical path with dynamic Project management software and hold regular meetings. | Disagree. The focal points are not responsible for the day-to-day management of the project. However, the Project has developed ways to keep them informed and participate in the planning of Project activities. |  |  |  |  | The Project has established the means to engage and promote participation of the focal points. Regular meetings are carried out with the Project Steering Committee, of which the focal points are part. They participate in the preparation and approval of the Work Plans, and progress reviews. |
| 15. Hold periodic progress reporting meetings with the participation of key execution partners so that they better understand Project results and promote the exchange of experiences. | Agree. High priority. | - Carry out meetings with executing partners to discuss on progress activities and experience exchange, including lessons learned | - Jan 2022 to Jun 2023 | - PMU | - On going | - PMU is already carrying out activities to follow up on activities with executing partners and meetings to promote exchange of experiences, including key partners. However, they need to foster experience exchange between executing partners. This is already included in Y5 Work Plan. The methodology of this experience exchange will be developed. |
| Effieciency / Finding 3: Some disagreements or complaints from project level stakeholders lack adequate channels for being duly communicated and pertinently addressed. |  |  |  |  |  |  |
| 16. Appraise the need for a simple but effective online grievance mechanism for complaints from project level stakeholders and beneficiaries to submit their complaints to the PMU. An anonymous option for presenting a complaint is recommended. | Agree. High priority. | - Develop a grievance mechanism for the project to be included MAR2R website. | - Aug 2022 | - PMU | - Completed | The online grievance mechanism at Project level has been developed. Additionally, each demonstrative project has its grievance mechanisms. |
| 17. Designate a person within the PMU to address complaints effectively. | Agree. High priority. | - Designate the responsible persons of the PMU to follow up on complaints received and addressing them. | - Aug 2022 | - PMU | - Completed | The online grievance mechanism has an email address for submitting grievances. There is a procedure established for addressing grievances received. The person of the PMU responsible for addressing grievances is the Safeguards Specialist. The Project Manager receives the grievances submitted through this mechanism. |
| Effiency / Finding 4: Lessons learned from Project implementation, good practices, gaps, and general interaction meetings should be improved. |  |  |  |  |  |  |
| 18. Identify, systematize, and disseminate lessons learned opportunely through the REO from the Project to be shared with the entire constituency. | Agree, but already happening. Medium priority. | - Include in Y4 and Y5 Work Plans activities to identify, systematize, and disseminate lessons learned through REO. | - Jul 2022 to Jun 2023 | - PMU | - On going | - Y4 Work Plan includes these activities already. |
| 19. Conduct periodic workshops where partners, beneficiaries, and key stakeholders can share and learn about Project progress and lessons learned. Ensure there is adequate systematization and dissemination of the information, conclusion and recommendations for their implementation. | Agree. High priority. | - See No. 15 | - May 2022 to Jun 2023 | - PMU | - On going | - Y4 Work Plan includes activities for this: workshops within components 1, 2, 3, and 4, and in-country meetings with the participation of executing partners, beneficiaries, and stakeholders for experience and lessons learned exchange. In Y5 Work Plan these activities will also be include. |
| Sustainability / Finding 5: The Project has received great support from the Ministries of the Environment of the four countries in the MAR ecoregion and is very relevant to CCAD and its partners. An exit strategy needs to be developed to sustain the results and outcomes beyond the life of the Project. |  |  |  |  |  |  |
| 20. Plan a sustainability strategy or exit strategy that makes explicit what is needed to keep the effects of the Project. The strategy should define a transition to ensure the institutionalization of the lessons learned, and the adoption of good practices, both at the national and regional levels. The budget of the responsible entities should be ensured when relevant. | Agree. High priority. | - Carry out an internal workshop to elaborate an exit strategy and address sustainability of Project activities. - Get approval of exit strategy by PSC. | - Mar 2023 - May 2023 | - PMU with support of WWF GEF IA and PSC - PMU with support of WWF GEF IA and PSC | - Pending - Pending | - The SAP is part of the sustainability of the Project actions. There are other tools that the Project has considered for the sustainability of the effort such as: Management plans, policies, etc. - It is part of Project activities to get endorsement of SAP by PSC and governments of the 4 countries of the MAR, for its sustainability. |
| 21. Once the term is extended, coordinate the preparation of the exit strategy; the PSC must endorse this strategy. | Agree. High priority. | See No. 20 | - Nov 2022 | - PMU with support of WWF GEF IA and PSC | - Pending |  |
| 22. Improving data gathering across the collaborative network and to facilitate capacity building towards R2R regional governance with quality mapping and decision making instruments such as the REO platform. Which needs to be evaluated and improved. Integrating REO to data sources from the project activities and ground participant/partner activities at the watershed, coastal and regional levels. | Agree, but already happening. Medium priority. | -Build capacity in the government representatives on how to access and upload information to REO. - Input R2R information in the REO for supporting decision making. - Implement activities for project partners can use REO for project activities. | - Jan 2022 to Sep 2022 - Nov 2021 to June 2023 - Nov 2021 to June 2023 | - PMU with support of WWF GEF IA and PSC | - Completed - On going - On going | - Protocols (2021) for accessing and uploading information to REO have been developed and government representatives have been training using these protocols. The Communication specialist has developed materials to promote de REO. |
| Adaptive Capacity / Finding 6: There are areas of improvement in the application of the Logical Framework Matrix. |  |  |  |  |  |  |
| 23. Validate the Logical Framework Matrix to prioritize actions as part of the strategic planning for the remaining Project implementation. | Disagree. There is no need to validate, in any case is to prioritize. No changes in the main activities included in the Logical Framework Matrix are considered. |  |  |  |  | PMU has already prioritized activities in Y4 Work Plan and will do the same for Y5. |
| 24. Rewrite indicators for some outcomes to improve their understanding. For example, it would be recommendable to rewrite the indicator for outcome 1.4, which does not reflect the expected result (measure updated reliable information of REO (p.114). Other indicators that should be rewritten are highlighted in annex 5.11. | Agree Partially. Low priority. We don´t agree with rewriting the existing indicators as they are part of the approved Prodoc. At this moment, the most effective way is to carry out an analysis of the impacts of the project, beyond those measured by the result framework indicators. | - Carry out Project impact analysis. | - Nov 2022 to Apr 2023 | - PMU with the support of WWF GEF AI | - Pending | - The monitoring and evaluation plan included in the Prodoc was approved by GEF and it was reviewed and changed in Y1 and Y4 of the project. |
| 25. Solve the differences found in outputs 2.1, 3.1, and 3.2 between what is stated in the Results Framework in the Project Document (pages 182 and 183) and detailed in the Project reports (see comments in annex 5.11). | Disagree. |  |  |  |  | The monitoring and evaluation plan included in the Prodoc was approved by GEF and it was reviewed and changed in Y1 and Y4 of the project. There are no differences between the plan and the Project reports. |
| Adaptive Capacity / Finding 7: The M&E reporting does not reach all stakeholders (direct and indirect). |  |  |  |  |  |  |
| 26. Develop a more effective online M&E system to reach more beneficiaries. | Disagree. The is not connection between M&E and reaching more beneficiaries. M&E is an internal tool of the Project. |  |  |  |  | See No. 8 and 10. |
| 27. Enhance the M&E function to ensure better reporting and monitor the technical quality of the documents presented as Project outcomes. M&E responsibilities should include providing feedback to the Project staff, executing partners, and relevant stakeholders. | Disagree. There are established procedures to review the quality of the documents presented. The review of documents is not a responsibility of the M&E. Quality assurance is a shared responsibility between the Project Specialist and the governance mechanisms established. For a few others, the Specialist is the responsible for the quality assurance. | See No. 13 |  |  |  | M&E provides feedback to Project staff that guides the adaptive management actions. Also provides feedback to executing partners. |
| 28. Ensure that the M&E responsible staff prepares timely reports (including changes, risks, lessons learned, gaps, among others) to share with all Project partners, and stakeholders and disseminate through periodic newsletters based on Project reports (through Mailchimp, for example). | Agree. High priority. | - Include in the Y4 and Y5 Work Plans the development of newsletters (including changes, risks, lessons learned, gaps, results, etc.) -Disseminate the information to project partners and stakeholder that do not have access to internet. | - Nov 2021 to Jun 2023 - Nov 2022 | - PMU - PMU | - On going - On going | - Newsletters including lessons learned, gaps, etc. have been developed and shared. Additional newsletters will be prepared during Y5. - Several printed communications materials have been developed and disseminated with project partners, beneficiaries and stakeholders. This will continue until the of the Project. |
| Adaptive Capacity / Finding 8: The Project might not achieve the outcomes related to certifications of the productive sector. |  |  |  |  |  |  |
| 29. Modify the indicators regarding reaching or maintaining compliance of certifications to reflect the current needs of each productive sector involved. The PMU has already prepared a proposal to modify the indicators. The evaluation team concludes that it is coherent and recommends to: ▪ Prioritize activities to identify potential companies to be certified. ▪ Develop a certification guide based on lessons learned, including the current needs of each productive sector. ▪ Consider enabling the productive sector for future certifications (e.g., Better Management Practices). | Agree. High priority. | See No. 3, 6, and 7. |  |  |  |  |
| 30. The recognition of ecosystem service provision through R2R management must be coupled with strong data and analysis to effectively improve and maintain biodiversity and ecosystem services quality. The REO platform, TDA/SAP instruments and reports and documentation provided by components 2 and 3 are a strong basis towards it. | Agree. High priority. | - Carry out workshops to generate knowledge products on Project impacts and results focused on R2R. | - Nov 2022 to Jun 2023 | - PMU | - Pending | - The knowledge products will include those processes, strategies, platforms, among others, where the R2R approach internalization showed to be successful. |
| Equality and Mainstreaming / Finding 9: The Project did not formally consider a gender approach though most Project activities have encouraged gender inclusion. |  |  |  |  |  |  |
| 31. Develop a Project policy and Monitoring, Reporting and Verification (MRV) on gender mainstreaming based on current social safeguards. | Disagree. This is a GEF5 project which does not require a policy and a MRV on gender. However, the Project is reporting disaggregated data related to gender. | - Develop lessons learned to gender. | - Nov 2022 to Jun 2023 | - PMU | - Pending | The proposal cannot be strengthened at this point in time. This project is GEF 5, so GEF´s Policy on Gender Equality does not apply to it. The Project follows the guidelines in Gender Mainstreaming on integrating women in specific Project activities in components 2 and 3. However it will benefit from generating lessons learned related to gender and additional indicators that show the participation of women in demonstrative projects, not only in trainings. |
| 32. Strengthen the proposal based on gender safeguards, linked to WWF’s gender policy (mentioned in PRODOC), as a basis for equity in access to Project benefits and ensure equitable participation of all parties. | Agree. Medium priority | See No. 31 | - Nov 2022 to Jun 2023 | - PMU | - Pending | Analysis will be done based on demonstrative projects. |
| Other recommendations from body of report |  |  |  |  |  |  |
| 33. In Outcome 2.1, number of stakeholders trained does not reflect if IWRM has been implemented. It is recommended to include the number of project activities that include IWRM or rewrite outcome 3.1 (p.45, 115) | Agree. Low priority. | - Record the number of project activities that include IWRM in the Project impact analysis (See No. 24) | - Nov 2022 to Apr 2023 | - PMU with the support of WWF GEF AI | - Pending | - The monitoring and evaluation plan included in the Prodoc was approved by GEF and it was reviewed and changed in Y1 and Y4 of the project. |
| 34. For outcome 2.2, including the number of public-private mechanisms that implement IWRM is recommendable (p 45, 115) | Agree. Low priority. | - Record the number of public-private mechanisms that implement IWRM in the Project impact analysis (See No. 24) | - Nov 2022 to Apr 2023 | - PMU with the support of WWF GEF AI | - Pending | - The monitoring and evaluation plan included in the Prodoc was approved by GEF and it was reviewed and changed in Y1 and Y4 of the project. |
| 35. In 3.1, should include an indicator related to strategic planning, not only the number of people trained (p. 45, 117) | Agree. Low priority. | - Record the number of plans in the Project impact analysis (See No. 24) | - Nov 2022 to Apr 2023 | - PMU with the support of WWF GEF AI | - Pending | - The monitoring and evaluation plan included in the Prodoc was approved by GEF and it was reviewed and changed in Y1 and Y4 of the project. |
| 36. For outcome 4.2, would be recommendable to include a measurable goal. (p. 45) | Disagree This indicator includes a measurable goal. |  |  |  |  |  |
| 37. For outcome 2.3, recommend "number of stakeholders engaged in IWRM in priority watersheds" | Disagree This indicator includes stakeholders engaged in IWRM in priority watershed. |  |  |  |  |  |

Integrated Sustainability Solutions

Risk Management Measures included in the PRODOC (p. 61) are: Maintain[ing] the regional dynamic through activation and strengthening of regional committees for knowledge transfer, and Create[ing] information and communication mechanisms (links in the website) to socialize minutes of meetings, reports, lessons learned, and use of project information.

Guidelines for GEF Agencies in Conducting Terminal Evaluation for Full-sized Projects. Available in: https://www.gefieo.org/sites/default/files/documents/reports/gef-guidelines-te-fsp-2017.pdf

Guidance for conducting terminal evaluations of undp-supported, gef-financed projects. Available in: http://web.undp.org/evaluation/guideline/documents/GEF/TE_GuidanceforUNDP-supportedGEF-financedProjects.pdf

The Mesoamerican Reef Ecoregional Assessment: Setting Priorities for Marine Conservation. Available in: https://nsgl.gso.uri.edu/flsgp/flsgpw07001/data/papers/075.pdf

According to the PRODOC.

Extracted literally from the PRODOC (p. 41).

Source: PRODOC

The “Mesoamerican Caribbean Reef Systems Initiative,” known as the “Tulum Declaration,” was signed on June 5, 1997, by the Presidents of the Republics of Guatemala and Honduras, the Prime Minister of Belize, and the President of the United Mexican States. On July 11, 2006, in Panama City, the leaders of these four countries ratified the Declaration of Tulum (Tulum+8), and thus the political commitment to strengthen the development and conservation of the second largest barrier reef in the world, the Mesoamerican Barrier Reef System. (MAR). Available in: https://www.sica.int/busqueda/Noticias.aspx?IDItem=9964&IDCat=3&IdEnt=‌2&Idm=1&IdmStyle=1

See information on the CLME+ Project: “Catalyzing Implementation of the Strategic Action Program for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems” Available in: https://www.clmeproject.org/

More information about this project “Catalyzing Implementation of the Strategic Action Program for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems.” Available in https://www.clmeproject.org/

December 2021.

In 2020, as a result of Eta and Iota, damages estimated at US $ 2.16 billion were recorded. Massive floods depressed subsistence and commercial agricultural yields in Honduras. Addressing these damages had consequences in the change of priorities of some actors linked to the Project.

Action plan for white syndrome in the reefs of the Mexican Caribbean. Available in: https://www.gob.mx/conanp/documentos/plan-de-accion-del-sindrome-blanco-en-los-arrecifes-del-caribe-mexicano

Read information about this project “Catalyzing Implementation of the Strategic Action Program for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems.” Available in: https://www.clmeproject.org/

Integrated Sustainability Solutions (ISS)

Risk Management Measures included in the PRODOC (p. 61) are: Maintain[ing] the regional dynamic through activation and strengthening of regional committees for knowledge transfer, and Create[ing] information and communication mechanisms (links in the website) to socialize minutes of meetings, reports, lessons learned, and use of project information.

For additional information on evaluation methods adopted by WWF, see the WWF Evaluation Guidelines , published on our WWF Program Standards public website.

For additional information on the GEF Terminal Evaluation Guidelines, see the GEF Terminal Evaluation Guidelines , published on the GEF Evaluation Office website.

Please see the GEF Ethical Guidelines as published on GEF website.

Please note that some company information may be sensitive and cannot be made public. The Evaluator will be notified ahead of time what information is sensitive.

It is estimated the number of KIIs will around 25.  Focus groups may be used to interview multiple individuals at once, where applicable.

See annex A

WWF Procurement Policy