WWF GEF Agency

Project Implementation Report

Title: Integrated Ridge to Reef Management of the Mesoamerican Reef Ecoregion (MAR2R) (5765)

Project Report information:

| Report Author(s) | María Amalia Porta |
| --- | --- |
| Report Completion Date | August 15th, 2022 |

| 1. General Information | PIR Submission Date | August 22nd, 2022 |
| --- | --- | --- |
|  | Agency Approval Date | October 27th, 2017 |
|  | Fiscal Year | July 1st, 2021 – June 30th, 2022 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 3rd PIR |
| 2. Current Year Ratings | Overall DO rating | Moderately Satisfactory |
|  | Overall IP rating | Moderately Satisfactory |
|  | Overall Risk rating | Substantial |
| 3. Key dates | Actual Implementation Start Date | November 1st, 2018 |
|  | First Disbursement Date | January 30th, 2018 |
|  | Expected Mid-Term Review Date | May 18, 2022 |
|  | Expected Completion Date | June 30th, 2023 |
|  | Expected Financial Closure | December 31st, 2023 |
|  | Actual Completion Date | N/A - Project in implementation |
| 4. BUDGET | Total GEF disbursement through June 30 of the FY (USD) for project that has been in implementation for at least 1 FY | US$ 6,062,582.64 (disbursed to June 30, 2022) |
|  | Total Project Budget | $ 9,830,000 |

Project Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Mario Escobedo | mescobedo@sica.int |
| M&E Officer | Jorge Garza | jgarza@sica.int |
| F&A Manager | Julio Lazo | jlazo@sica.int |
| IWRM Specialist | Ricardo Calles | jcalles@sica.int |
| ICM & Safeguards Specialist | Carlos Rodríguez | clrodriguez@sica.int |
| Procurement Officer | Juan R. Cortez | jcortez@sica.int |
| Accounting Officer | Eunice Gómez | elizabeth.gomez@sica.int |
| Administrative Assistant | Rocio Flores | rflores@sica.int |
| Communication Technical Assistance | Sandra Serrano | sandraserrano2010@gmail.com |
| Community Monitoring Technical Assistance | Enriqueta Ramirez | enriquetarsv@gmail.com |

### Ratings

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year X |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective | MS | MS | MS |  |  |  |  |
| Implementation Progress | S | MS | MS |  |  |  |  |
| Risk | S | S | S |  |  |  |  |

Justification for Current Year Ratings:

The project’s Development Objective Rating is Moderately Satisfactory as 76% of the Y3 indicator targets in the results framework have been achieved. The project´s Implementation Progress Rating is calculated as Moderately Satisfactory as the project achieved an average of 77% of the activities of in Y3 workplan. The Risk Rating is Substantial, due to several risks and challenges identified. Y3 was a difficult year with Covid-19 lockdown, as well as Y2, and travel restrictions hindering implementation. The project was able to execute only 40% of Y3 budget. With only 1.3 years of project time left, WWF GEF Agency is worried that project implementation may have difficulties to catch up and complete all project outcomes. The PSC was aware of the difficulties previously explained and recommended and committed to support a no-cost extension, which was granted. Project execution was extended to June 30th, 2023. Other risks were identified. One of the most critical external risks identified was the significant delay of partners to deliver products on a timely manner. This was addressed by more frequent follow up visits by the MAR2R F&A and M&E Officers An internal risk identified was the capacity to advance in outcomes of the project that are delayed, specially 2.3 and 3.2 that needed to be adjusted to the current conditions that have changed due to: extreme weather events (Eta and Iota) that affected the productive sector by changing or redirecting investment priorities or specific activities within the production process; COVID-19 pandemic that modified the productive dynamics due to personnel cuts, production cuts, limited mobilization and partial or total closure of some shrimp farms. PMU requested a change of these indicators, which was accepted. These risks were reflected on the low budget execution.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

The project objective is to support regional collaboration for integrated ridge to reef management of the Mesoamerican Reef ecoregion by demonstrating its advantages and improving regional, national, and local capacities for integrated management and governance of its freshwater, coastal, and marine resources. The project has picked up on activities and several grants have been issued since Y2 and also during Y3. There is a significant delay due to the Covid-19 pandemic, so project activities were not able to progress adequately towards achieving the objective level indicator´s targets for Y3. In Y3, the most important project achievement was the recognition of the Ridge to Reef (R2R) approach by different stakeholders and sectors in regional and national policies, which goes beyond the CCAD to bodies as SICA, SITCA and others. Another important impact is the involvement of productive sectors such as tourism, oil palm, and sugar cane with strengthened capacities in the R2R approach and implementing actions (best practices) aimed at promoting this integration of management from the basin to the reef. Component 1. Strengthen resource governance and regional collaboration for integrated ridge to reef management in the MAR. The project achieved 77.40% of Y3 work plan targets and activities for Component 1, which has four Outcome-level indicators: • O.1.1. Number of regional policy instruments developed (target 2/achieved 3) During Y3 three regional policies were developed: the agreement signed between CCAD-SITCA and SUSTENTUR to promote sustainable tourism actions in the MAR ecoregion and the entire territory of Central America and the Dominican Republic; the policy declaration to promote the UN Decade on Ecosystem Restoration with a R2R approach endorsed and published by CCAD Council of Ministers; and the technical protocol for mangrove restoration to support MAR countries in the process of landscape restoration designed in a participatory way between MAR Fund, UNEP Cartagena Convention, and MAR2R and adopted by Mangrove Restoration Network. Two additional instruments have been developed and presented for endorsement. The Intersectoral National Committees (ISNC) have been established and are part of the governance structure, as well a key in the development of the TDA/SAP process. • O.1.2. Number of national policy instruments developed (target 2/achieved 3) The project has advanced in the development of three national policies: in Mexico, NOM 001 (it has been submitted by CONANP and CONAGUA to the Federal Authorities) and two in Honduras, Biodiversity Policy and Wetlands and Coastal Marine Resource Policy (validated by MiAmbiente). The project is supporting: In Guatemala, the policy instrument for Water Reserves; in Belize the update of the National Water Resource Policy; in Mexico the development of the Seas and Coasts Policy with R2R approach for the Quintana Roo State; and in Honduras the completion of the Integrated Management Policy for Water Resources, with a R2R approach and water reserves management. • O.1.3 Number of countries in the MAR endorsing TDA and SAP (TDA-target 4; achieved 4) The TDA has been developed and is in the process of review and validation by ISNCs, the Project Steering Committee, the WWF GEF Advisory Panel, and a group of thematic experts. The process of development of the TDA had some difficulties accessing stakeholders in the field due country restrictions because COVID 19 pandemic. However, the document was produced in consultation with multi-stakeholders in MAR ecoregion. The first version of the SAP has been developed and the final version will be validated and endorsed in Y4. The four countries are committed to support the conclusion and endorsement of the SAP. • O.1.4. Number of unique visitors consulting REO (Regional Environmental Observatory) in one full year (target 50; achieved 5,969) The REO has been launched and is operating. To April, 2022 it had additional 189 visits to the Mesoamerican Reef Ecoregion (https://www.sica.int/oar/arrecife/incio) and 2,504 visits to the section of MAR2R project (https://www.sica.int/mar2r). During this reporting period 20 new information items were uploaded to the specialized section on the Mesoamerican Reef Ecoregion. Component 2. Integrated ridge to reef management of watersheds and freshwater resources. The project achieved 88.51% of Y3 work plan targets and activities for Component 2, which has four Outcome-level indicators: • O.2.1. Number of stakeholders trained in IWRM through project activities (target 200; achieved 891) Through various trainings the project has trained to date 703 persons (230 women and 473 men) in various IWRM activities. • O.2.2. Increase (USD) in funding available for public private mechanisms in BZ, GT and HN (target 125,000; achieved 188,983) The project has been able to secure USD 188,983 from private sector sources for the public private mechanisms in Guatemala and Honduras. • O.2.3. Number of sugar and oil palm producers in project area that are reaching and/or maintaining compliance with Voluntary Standards Two sugarcane producers and two oil palm producers have been able to maintain its certification. The project has been unable to secure certification of new sugar and oil palm producers. Delays are due in part to the economic impact of the COVID 19 pandemic that modified the productive dynamics due to personnel cuts, production cuts, limited mobilization; extreme weather events as Eta and Iota that hit the region and partial or total closure of some shrimp farms, among others. Analyzing this scenario, the accomplishment of this Outcome was not possible, and the PMU request the modification to the Result Framework. The original indicator was number of sugar producers that reach compliance for certification/maintain certification (target 3) and number of palm oil producers that reach compliance for certification/maintain certification (target 10). The indicator was changed to: Percentage of sugar and palm oil producers in project area on track to reach or maintain voluntary standards, per their own management/action plans. • O.2.4. Number of tourism and tourism development sector actors adopting better management practices (BMP) to protect aquifers and freshwater critical habitats under project activities (target 24/achieved 63) The project has trained to date 63 tourism stakeholders on better management practices for wastewater management to improve the protection of aquifers and freshwater habitats in the MAR. Component 3. Integrated ridge to reef management of coastal and marine resources. The project achieved 60.40% of Y3 work plan targets and activities for Component 3, which has three Outcome-level indicators: • O.3.1. Number of stakeholders trained in ICMM through project activities (target 200; achieved 694) The project has been able to train 188 stakeholders in Y3 (113 women and 75 men) on ICMM topics. To date 694 stakeholders have been reached. • O.3.2. Number of shrimp farms and fisheries in project area that are reaching and/or maintaining compliance with Voluntary Standards (Marine Stewardship Council –MSC- and Aquaculture Stewardship Council -ASC) The project is supporting the existing shrimp farms in Belize for re-certification in ASC. However, due to the pandemic and the impact on the economy, re-certification is difficult to achieve and consequently this Outcome. This is the same case as the MSC certification of Honduran lobster fishery. For that reason, a modification was requested by the PMU. The original indicator was number shrimp farms and fisheries in project area that are reaching and/or maintaining compliance with Voluntary Standards (Marine Stewardship Council –MSC- and Aquaculture Stewardship Council -ASC) (target 16). The indicator was changed to: Percentage of farms and fisheries in project area on track to reach Voluntary Standards, per their own management/action plans. To date, 8 shrimp farms in Belize are under ASC audit process. This represents 100% of the shrimp farms in Belize. • O.3.3. Number of tourism and tourism development sector actors, and communities implementing better management practices (BMP) to protect coastal and marine habitats under project activities (target 40; achieved 31). In Y3 the project is implementing BMP with 21 stakeholders and 10 communities. Component 4. Project monitoring and evaluation and knowledge sharing. The project achieved 97.50% of Y3 work plan targets and activities for Component 4, which has two Outcome-level indicators: • O.4.1. Number of MAR2R progress reports completed All the progress reports have been completed as planned. • O.4.2. Number of communication and knowledge management products disseminated The project prepared communication products as planned in the communication strategy and were disseminated. The project webpage and social media (2) are active, maintained and updated; 9 publications and 16 videos/animations were disseminated, and 4 webinars were carried out in Y3. The key challenges and risks are: - The project has only executed 40% of the project’s overall budget to its third year according to PMU (October 31, 2021) and according to the Mid-Term Evaluation it was 36% through April 30, 2021. The project still presents challenges regarding implementation and budget execution. Y3 had an increase in financial execution and in important achievements. - The development of the TDA/SAP is delayed and has faced some limitations: one was that the meetings had to be carried out mainly virtually and just in some cases it was possible to have them in person. Another limitation was the lack of specialist on this topic in the region, so it was not possible to have the final document of TDA for this year (originally expected 2021). The consultant team is working in parallel the SAP expecting to finalize both documents in 2022. - The project’s Y3 budget was originally set at US$ 9,018,349. Due to the COVID19 pandemic restrictions and ETA and IOTA natural disasters, the execution was of US$ 3,587,961 which represents 40% of the budget, being Component 2 the one with the lowest execution of 31% (US$ 1,334,757). Regarding the other three components the Y3 budget expenditure was: Component 1 US$ 444,740 which represents 52%; Component 3 US$ 1,189,528 which represents 46%; and Component 4 US$ 397,700 which represents 46%. - Some demonstration projects are delayed, so are at risk of not being finished on time given that the project has only one more year of execution. A no-cost extension was recommended by the MTE as well as the PSC. The PMU requested a no-cost extension that was approved by WWF. - The activities under the responsibility of some partners have problems or are delayed. To address this, some mitigation measures were recommended by the F&A Officer, including more frequent visits by the MAR2R F&A and M&E Officers. This mitigation measures have been implemented by the PMU and there has been some improvements on the execution of activities and funds by the partners. In terms of safeguards, all identified demonstration projects are screened, necessary safeguards plans and measures are put in place, and partners have clarity on their responsibilities in this regard. To date, safeguards have been approved for all demonstration projects: Component 2: Fundación Merendón – Honduras; Fundación Defensores de la Naturaleza – Guatemala; Amigos de Sian Kan - México; and Centinelas del Agua – México; Component 3: MARFund - Regional; and Ecologic - Guatemala. No safeguards issues have arisen from project activities. No complaint has been received through the mechanism established for the demonstration projects.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

MAR2R is a GEF 5 project and does not have a stakeholder engagement plan but continues to have a focus on stakeholder engagement to achieve project outcomes. The project´s Steering Committee continues to be active and engaged. The Intersectoral National Committees have been established and have met 8 times during Y3. The project continues to engage civil society successfully. Several capacity building events have been carried out in the four countries focused on diverse stakeholders. The demonstration projects are implemented using already established governance mechanisms such as Watershed committees, technical round tables, etc. The mechanisms have been used to select the activities within the demonstration projects, so these have been designed jointly with them. The design of the demonstration projects also included the participation of the local communities, to address their priorities and specific needs. Also, local communities’ representatives in the majority of cases are members of the governance mechanisms. The implementation of the project activities includes the participation of local communities, for example: in Sierra de las Minas, they are implementing farm management plans and participating in forest fire prevention and control activities; in Sierra Meredon they are involved in activities related to sustainable coffee, forest protection, and strengthening of water boards; in Belize they are participating in mangrove restoration activities; and in Mexico, Honduras and Guatemala they are participating in coral and mangrove restoration.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

MAR2R project is a GEF 5 project and therefore does not have a specific gender action plan, nonetheless a gender and social inclusion lens has been applied to some extent. The project reports disaggregated by sex records on stakeholder participation. Project records continue to show effective engagement of men and women in several project activities. Capacities have been strengthened in integrated management resources to 891 participants, from which 38.4% are women. It was recommended by the WWF GEF Gender Specialist to ensure that the project always uses a gender-sensitive approach to stakeholder engagement and also to include in the trainings/workshops the number of youth and information relating to other marginalized groups as relevant. The PMU will ensure that lessons learned on gender and social inclusion will be considered in the monitoring and documentation in Y4 of the project.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

According to Outcome 4.2 the number of communications and knowledge management products disseminated have been achieved is 100% for Y3. The project website was launched in Y3. Depending on the different audiences, communication to inform about project activities is via the IW learn platform, project newsletter, social media, etc. The R2R approach is shared through different media: infographic, videos, factsheet, publications, articles in newspapers and other sites (36 in Y3). Capacities have been strengthened in integrated management resources to 891 participants (women 343 and men 548) in different sectors as governmental agencies, local and regional actors, municipalities, and others in topics as: wastewater, cross-border planning, water funds, integrated management of water resources, standards and certifications, mangroves, ecosystem services, marine spatial planning, integrated management of cenotes, caves and springs, and environmental and social safeguards. However, the MTE recommended a model for systematising lessons learned that can be useful internally in the Project for adaptive management, but also to be used by partners and beneficiaries in their own projects. Each Component has its own lessons learned that are not share with the rest of stakeholders or among the different components.

### Adaptive Management

Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☒ Results framework; Minor change to indicators and the targets in the Results Framework for outputs 2.3.1 and 3.2.1.; May 23rd, 2022. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. ☒Implementation scheduleI; Request for no-cost extension; March 30th, 2022. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. Anticipated change to the project this coming year: No additional changes are foreseen.

### Geolocation Information

Please provide a location name, latitude and longitude (04 decimal points) or, as applicable, a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide as a reference. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Mexico; 21.1742; 86.8464; Cancun. Belize; 17.2500; 88.7500; Belize. Guatemala; 15.7278; 88.5944; San Pedro Sula. Honduras; 15.5042; 88.0250; Puerto Barrios.

Annex I: Rating Scales and Guidance

### Development Objective Rating

The project Development Objective (DO) rating is quantified by analyzing progress against the Results Framework according to the rating scale below. Note that the average is not taken across component averages, but rather across all indicators in the Results Framework. No percent achieved should surpass 100% even if the target is exceeded.

DO Rating scale

| Rating | % Achievement of Results Framework targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100% |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate DO Rating from Results Framework

| Objective/Component/ Outcome | Indicator | Unit | Target Y1 | Achieved Y1 | Percent achieved Y1 |
| --- | --- | --- | --- | --- | --- |
| Project Objective | Indicator 1 | # policies | 5 | 4 | 80 |
|  | Indicator 2 | # ha | 1,000,000 | 900,354 | 90 |
| Component 1 |  |  |  |  |  |
| Outcome 1.1 | Indicator 3 | # beneficiaries | 500 | 410 | 82 |
| Outcome 1.2 | Indicator 4 | # sites | 10 | 12 | 100 |
| Component 2 |  |  |  |  |  |
| Outcome 2.1 | Indicator 5 | % score | 80% | 75% | 93.75 |
| Average of total |  |  |  |  | 89.15 |

### Implementation Progress Rating

The project Implementation Progress (IP) rating is based on progress against the annual workplan, based on the rating scale provided below.  Note that the average is not taken of the component averages, but rather across all indicators in the workplan. No percent achieved should surpass 100% even if the target is exceeded.

IP Rating scale

| Rating | % Achievement of annual workplan targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100 |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate IP Rating from AWP&B

| Project Activities Y1 | Unit | Target | Achieved | Percent Achieved |
| --- | --- | --- | --- | --- |
| Component 1 |  |  |  |  |
| Activity 1.1.1 | Sites | 5 | 4 | 80 |
| Activity 1.1.2 | Households | 120 | 122 | 100 |
| Average Component 1 |  |  |  | 90 |
| Component 2 |  |  |  |  |
| Activity 2.1.1 | Plans | 6 | 5 | 83 |
| Activity 2.1.2 | Reports | 2 | 2 | 100 |
| Activity 2.1.3 | Proposals | 10 | 7 | 70 |
| Average Component 2 |  |  |  | 84.3 |
| Component 3 |  |  |  |  |
| Activity 3.1.1 | Trips | 2 | 0 | 0 |
| Activity 3.1.2 | Trainings | 4 | 3 | 75 |
| Average Component 3 |  |  |  | 37.5 |
| Average achievement of all activities in workplan |  |  |  | 72.57 |

### Risks

Examine whether the project faces substantial risks in terms of the sustainability of project results. Please rate individually identified project risks (reference ProDoc, previous reports, Safeguards documents, etc) according to the rating scale and use all assessed risks to determine an overall or average risk.

Risk Rating Scale

| Rating |  |
| --- | --- |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold, and/or the project may face substantial risks. |
| Modest Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |
| Low Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |

Guiding example: How to determine Risk Rating from Risk Analysis in PPR

| Risk Description | Risk Rating | Notes |
| --- | --- | --- |
| Elections – change of leadership lead to not holding up to commitments | Substantial | If there is a party change, the MOU protected area designation may be thrown out. From our research, the party change is highly likely. See mitigation plan. |
| The newly established coordination mechanism does not meet regularly, and coordination fails | Modest | There is a history of newly established mechanisms not having the intended effects – which is partially due to limited resources and partially due to lack of buy-in. See mitigation plan. |
| The new equipment given to rangers will fail at some point and there will be no expert or replacement parts available to fix. | Substantial | Focal person of the lead ministry is engaged in multiple work. So has given very least priority to the project, wanted to take the position as PCC coordinator, however, has least concern in project implementation. |

After assessing each individual risk according to the risk rating scale, the overall risk is identified as Substantial given that two of the three risks are Substantial, and one is Moderate. This rating is qualitative in nature and considered the best estimate for the average risk the project is facing.

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).