Implementation Plan of Recommendations

| Project Title and Reference No.: | Low Carbon Solutions through Nature Based Urban Development for Kutaisi City (GEF ID10643) |
| --- | --- |
| Contact Person (TM/PM): | Lesya Nikolayeva / Johan Robinson |

|  | PLANS |  |  |  |
| --- | --- | --- | --- | --- |
| RECOMMENDATIONS | ACCEPTED (YES/NO/PARTIALLY) | WHAT WILL BE DONE? | EXPECTED COMPLETION DATE | REPONSIBLE OFFICER/ UNIT/ DIVISION/ AGENCY |
| Recommendation 1: Approval of the 1.5-year no-cost extension of the Project There is a strong case for the extension of the Project for sufficient time to: a) Be able to finalize LEDS document to get their approval by the City Council (before the Project’s end). b) Further guide the elaboration of vision, goals, and measures in ISUMP and act as an intermediary with stakeholders (including private sector companies) and groups of beneficiaries. b) Guide and monitor (in a gender-sensitive way) the implementation of the e-buses pilot (number of trips and number and type of passengers; electricity consumption; daily mileage; customer satisfaction; driver’s experience; maintenance and operation, etc.). c) Start implementing and successfully finalize the second pilot on urban forest management (Mukhrani Forest). d) Follow-up on the finalization of the GCF/ADB proposal for sustainable transport in Kutaisi and subsequent successful submission. e) Elaborate an exit strategy for (i) LEDS-related activities other than transport (sustainable energy use in buildings and built environment, and (ii) related to sustainable land/forest management, including identification of partners, donors and funding and cooperation opportunities with ongoing/upcoming projects, and/or possibility for replication in Imereti region. |  |  |  |  |
| Recommendation 2: Devote increasing time and resources to sustainable (urban) forest/land management In the second part of the project, it is suggested to focus on the implementation of the planned activities in the Mukhrani pilot within the project allocated funds and initiate the start of the activities in the earliest convenience. The EA is encouraged to continue close cooperation with the Kutaisi municipality and other relevant departments to ensure that the subject of SLN/SFM is appropriately addressed and reflected in the future Kutaisi General Master Plan. Despite the limited impact and involvement of the project team in the Plan’s final formulation, the EA (REC Caucasus), thanks to its experience in green economy, land and forest management topics is recommended to continue providing advisory support. |  |  |  |  |
| Recommendation 3: Website and knowledge management A web-based Knowledge Management (KM) system still needs to be developed. Dissemination and use of the collected project’s knowledge and materials by various national and local stakeholders is critical for the successful exit strategy and the future socio-economic benefits in the region. Currently, the placement of the website (i.e. the Kutaisi City website or an alternative project’s informational hub) is under discussion between the EA (REC Caucasus) and Kutaisi City Hall. It is recommended to arrange the knowledge management website at the most accessible place for the purpose of city residents. Rather than being just a project gateway, which often stops when a project ends, such a website should function with a long-term vision as a post-project KM system communication and exchange gateway and as an InfoBase with best practices on green city development concept. |  |  |  |  |
| Recommendation 4: Integration of gender equality, human rights, and social inclusion It is recommended that all draft or outline of planning documents (i.e. ISUMP, LEDS, ToR Phase 2 of General Master Plan) reflect elements on gender equality, human rights, and social inclusion. Given that the EBRD-Ernst and Young KTC Baseline and Assessment Report has also highlighted the importance of gender and human rights issues, its recommendations can be additionally integrated in the above-mentioned planning documents. |  |  |  |  |

The following is a summary of lessons learned from some of the project’s experiences and based upon explicit findings of the review. They briefly describe the context from which the lessons are derived, and the potential for wider application:

| Lesson Learned #1: | Solid counterpart support and country-drivenness |
| --- | --- |
| Context/comment: | It is important to have a counterpart (executing agency) that can provide solid support with a dedicated full-time team, at both the project coordination, administrative and technical levels, to ensure timely and quality dedication to the delivery of outputs and outcomes, reporting and quality control needs of the project. For the longer-term goals, the country-drivenness is important, i.e. commitment of the counterpart organization (EA and or the partner government agency, if not the same) not only to implement the activities of the project itself but also provide post-project follow-up with expansion or replication of planning and related investments. Good stakeholder relations (with governmental and non-governmental organizations) are clearly desirable in the process of pursuing sustainability options for project information systems and sustaining public awareness and knowledge management initiatives of the project. |

| Lesson Learned #2: | Finding the right mix of project (and post-project) interventions to support the diffusion of a technology in a market |
| --- | --- |
| Context/comment: | The success of a project is partly dependent on the market penetration of the technology concerned. In the case of electric buses, these are now widely demonstrated worldwide as part of a global trend towards a higher market share of electric vehicles (EV) in general. In Georgia, the electric buses are still in a ‘demonstration’ phase, and this is the phase that the UNEP/GEF project has supported in Kutaisi by demonstration, creating awareness and knowledge dissemination. In the technology innovation cycle, the next phase after ‘demonstration’ is ‘deployment’ (followed by commercial scale ‘diffusion’). Actions in the various phases can be stimulated by a mix of policy instruments, such as soft finance, subvention (as required), knowledge management, and encouraging behavioral change, tailored to the needs of each phase in the cycle. In many technical assistance projects, in the reviewer’s experience, such demonstrations do not have an (immediate) follow-up. It is very positive that, in the UNEP/GEF Project design, this transition to the next level (‘deployment’ with market diffusion on a larger scale) is already foreseen and proposed to be supported by a GCF/ADB project on e-mobility to financially support investments in e-buses. |

| Lesson Learned #3: | Assessment of technical options during project design |
| --- | --- |
| Context/comment: | An essential element in the GEF climate change projects is the estimation of the benefits of a technology. The design could have benefitted not only from a more detailed technical analysis of energy savings and GHG emission reduction of electric buses but also extended to cover cost and benefits (investment cost and operating costs) and an assessment of infrastructure and service needs (charging, training needs of drivers and maintenance personnel). Such an analysis could also serve to appropriately position the technology in one of the phases of the technology phases (mentioned in Lesson Learned #2) and tailor project activities according to the phase’s support needs. |

| Lesson Learned #4: | Integration of gender equity and social inclusion aspects |
| --- | --- |
| Context/comment: | The project’s Gender Action Plan hints at gender-specific activities or aspects in each of the project’s outputs. However, the GAP table would have benefitted from linking gender-relevant activities in GAP with the numbered activities in the output-activities table under each component in the CEO ER/Project document. It now has the risk of becoming a ‘tick box’ without follow-up in terms of real activities, for example, in Component 1 (on planning and policy formulation; discussed further as part of Recommendation #4). A good example, of such a real activity is the capacity Baseline and Assessment Report (carried out as part of the Project’s co-financing) which covers a quantitative and qualitative assessment of gender equality and social inclusion regarding staff in and clients (commuters) of the Kutaisi Transport Company. |

| Lesson Learned #5: | Greenhouse emission (direct and indirect) estimates and co-financing |
| --- | --- |
| Context/comment: | The original project documentation (ProDoc/CEO ER document) does not clearly describe the methodology for defining direct and in direct GHG emission reduction targets and it is difficult to find how sources of co-financing can be linked with direct GHG emission reduction. To make a consistent comparison at MTR (and final evaluation) stage with the originally planned targets possible, full details of methodology and assumptions should be annexed to documentation in future project designs. |

This system is planned to be integrated into the existing Kutaisi City website. However, website governance, format, and content restrictions, etc., may not favor linking it with the City website.