## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 0
2

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Africa (RAF)
Country(ies): | Kenya
Project Title: | Integrated Landscape Management for conservation and restoration of the Mt. Elgon Ecosystem in Western Kenya
FAO Project Symbol: | GCP/KEN/905/GFF
GEF ID: | 10598
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Biodiversity, Land Degradation, IP FOLUR, MFA
Project Executing Partners: | Kenya Forest Service (KFS) & Kenya Agriculture and Livestock Research Organization (KALRO)
Initial project duration (years): | 5 Years
Project Dates
GEF CEO Endorsement Date: | 2022-04-18
Actual Agency Approval Date | 2021-12-09
Project Implementation Start Date/EOD: | 2024-04-01
First Disbursement Date | 2024-04-30
Planned Project End Date/NTE1: | 2027-05-31
Revised project implementation End date (if approved)2: | 2029-03-31
Actual Completion Date: | n/a
Expected Financial Closure Date: | 2030-03-31
Funding
GEF Grant Amount (USD): | 5354587
Total GEF grant delivery (as of June 30, 2025 (USD): | 1179808.98
Total Co-financing amount (USD)3: | 46506320
Total estimated co-financing materialized as of June 30, 20254: | n/a
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 2024-10-17
Expected Mid-term Review date5: | 2026-04-18
Actual Mid-term review date (if already completed): | n/a
Expected Terminal Evaluation Date6: | 2028-09-30
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Moderately Unsatisfactory (MU)
Overall implementation progess rating: | Moderately Unsatisfactory (MU)
Overall risk rating: | Moderate
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 1st PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | James Mwang'ombe |  | mwangombejames@yahoo.co.uk
Budget Holder (BH) | Tipo, Nyabenyi Tito |  | Nyabenyi.Tipo@fao.org
GEF Operational Focal Point (GEF OFP) | Dr. Eng. Festus K. Ng’eno |  | psoffice@environment.go.ke
Lead Technical Officer (LTO) | Irie, Yuka |  | Yuka.Irie@fao.org
GEF Technical Officer (GTO) | Morebotsane, Kuena |  | Kuena.Morebotsane@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
National Project Coordinator | Yes | James Mwang'ombe - mwangombejames@yahoo.co.uk |  | National Project Coordinator (KFS) was changed July 2025
Finance/Procurement officer | Yes | Margaret Chiera - magiechiera2020@gmail.com |  | Seconded to the Project from KFS
Knowledge and M&E Officer | Yes | Samuel Muriithi - smuriithi2000@yahoo.co.uk |  | Recruited in June 2025
Project Assistant | Yes | Benard Lemangi - benny.lemash@gmail.com |  | Recruited in December 2024
ESS safeguard (IP) Expert | Yes | Philip Kisoyan - Philip.Kisoyan@fao.org |  | FAO
Communications Officer |  | Rhodah Mbatiany - rmbatiany046@gmail.com |  | Recruited in July 2025

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
| Outcome 1.1: Mt. Elgon landscape managed sustainably with Integrated Landscape Management plans under implementation | # of hectares covered by ILM plans, informed by inclusive multi-stakeholder dialogue | 0 | 50,000 hectares | 178,880 ha covered by ILM plans | Participatory Informed Landscape Approach (PILA) is being used to develop the Mt. Elgon Ecosystem Management plan (To cover the entire landscape); multiple trainings held with government and stakeholder officers. Bio-physical baseline assessment for the landscape completed | 30% | Satisfactory (S)
|  | # of effective multi-stakeholder platforms operational to promote ILM | 0 | one (1) intercounty and four (4) sub-county multi-stakeholder platforms established to promote ILM | One (1) intercounty and four (4) sub-county multi-stakeholder platforms established to promote ILM | Four sub-county multi-stakeholder platforms (Cheptais, Mt. Elgon, Saboti, Endebess) and two County multi-stakeholder platforms (Bungoma & Trans-Nzoia) established to promote ILM and project implementation; Multi-stakeholder gap analysis conducted in Bungoma and Trans-nzoia to identify areas of intervention. Development and alignment of various PILA training packages for ILM planning i.e. PILA TAPE survey; PILA Behavioural Change Assessment; PILA Geospatial tool; PILA Stakeholder analysis. | 30% | Satisfactory (S)
|  | # of gender-responsive policy frameworks updated/developed supporting ILM | 0 | At least 1 county policy | At least 2 county policy frameworks updated/developed to promote ILM | FPIC carried out and completed for the indigenous Ogiek community in Bungoma and Trans-Nzoia counties Socio-economic baseline assessment of the landscape completed Development and alignment of various PILA tools and guidlines for ILM planning i.e. PILA TAPE survey; PILA Behavioural Change Assessment; PILA Geospatial tool; PILA Stakeholder analysis. | 30% | Satisfactory (S)
| Outcome 2.1: Improved efficiency and sustainability of coffee and maize production systems | # of farmers (at least 30 % women) benefited from training and access to services to support sustainable coffee and maize production and marketing | 0 | 15000 | 43,000 smallholder farmers with enhanced capacity on sustainable coffee and maize production and marketing | Not yet started due to delays in the KALRO Operational Partners Agreement (OPA) | 0% | Unsatisfactory (U)
|  | # of hectares of landscapes under improved practices | 0 | 10,000 Ha | 50,000 ha | Not yet started due to delays in the KALRO OPA | 0% | Unsatisfactory (U)
|  | # of hectares in the process of certification | 0 | 300 Ha | 1,000 ha | Assessment of 26 coffee cooperatives on compliance with the European Union Deforestation Regulation completed | 10% | Moderately Unsatisfactory (MU)
|  | % of Increase in coffee and maize yield per tree/hectare for smallholder farmers by the end of the project | 0 | 10% increase | At least 30% increase | No activites in 1st year | 0% | Not Rated
|  | # of entrepreneurs/community groups (50% women and youth, Ogiek community) supported through small grants to develop nature-based enterprises for economic empowerment and livelihood diversification | 0 | 10 | 40 | No activites in 1st year | 0% | Not Rated
|  | # of county coffee platforms established to promote inclusive and sustainable value chain approach | 0 | 2 | 2 | Not yet started due to delays in the KALRO OPA | 0% | Unsatisfactory (U)
| Outcome 3.1: Increased Mt Elgon landscape area under conservation and restoration | # Hectares of degraded forest and forest land restored | 0 | 1,000 ha | 7,000 ha | Not yet started | 0% | Unsatisfactory (U)
|  | # Hectares of degraded farmland restored | 0 | 1,000 ha | 3,000 ha | Not yet started | 0% | Unsatisfactory (U)
|  | # people trained and engaged in on-the-ground restoration activities (disaggregated by gender, at least 30% women) | 0 | 3000 | 10000 | Two community tree nurseries established (Kaberwa and Kiptogot forest stations) | 10% | Moderately Unsatisfactory (MU)
| Outcome 4.1: Effective knowledge management and M&E supporting scale-up and impact at national and global level | Project M&E system operational | 0 | 1 Quality M&E information and reports, as scheduled | "1 Quality M&E information and reports, as scheduled " | M&E officer recruited by KFS and work to develop the M&E system is underway | 20% | Moderately Unsatisfactory (MU)
|  | # of knowledge products and tools shared and/or adopted from the Global FOLUR Platform, regional and national platforms | 0 | At least 5 annually | At least 5 annually | FOLUR PILA tool is being implemented in component one of the project. | 10% | Moderately Satisfactory (MS)
|  | # of people reached through Transboundary Knowledge sharing platform | 0 | At least 500 people have interacted through the platform | At least 1,000 people have interacted through the platform | No activites in 1st year | 0% | Not Rated
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
9.333% | 45.8% | 22.03%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
|  | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer | GEF Operational Focal Point | GEF Technical Officer (GTO)
| FY2025 Development Objective rating | Moderately Unsatisfactory (MU) | Moderately Unsatisfactory (MU) | Moderately Unsatisfactory (MU) | Not Rated | Moderately Unsatisfactory
| Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | This is rated due to the delays in some of the activities and delayed recruitment of the M&E Officer | There rating is based on delays in the implementation of the project due to challenges in the OPIM modality, delays in the operationalization of the KALRO OPA as well as late constitution of the Project Management Unit | While some progress has been made, the delays the project is facing is impacting the achievements that it is supposed to achieve, with significant number of activities not started yet under one of the operational partners. |  | There has been a delay in the implementation of key components of the project due to KALRO's challenges in obtaining necessary approvals from Treasury. FAO Kenya in consultation with the GEF OFP is exploring options to help address this situation.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 2.1: Improved efficiency and sustainability of coffee and maize production systems |  | KALRO OPA is facing delays in operationalization due to issues related to the operation of a project bank account. FAO to explore alternative implementation modalities |  | KALRO/FAO |  | Immediately
Outcome 3.1: Increased Mt Elgon landscape area under conservation and restoration |  | Delays in component 3 due to initiatl delays in KFS OPA and delays in component 1. KFS to ensure all Community Forest Associations have active Participatory Forest Mnagament plans/Forest Managament Agreements KFS to ensure Community Forest Association Tree Nurseries are operational to provide seedlings for restoration |  | KFS |  | Immediately
Outcome 4.1: Effective knowledge management and M&E supporting scale-up and impact at national and global level |  | KFS to ensure PMU is in place and roles and responsibilities of each member is clearly stipulated. The PMU should consist of: National Project Coordinator, M&E officer; Communications officer; procurement/Finance officer and the project assistant As the lead implementing agency KFS should ensure: effective project coordination, project reporting, prparation of project implementation reports (PIRs); represent the project in national, regional and international events; organize project steering committee meetings etc. KFS to ensure the Knowledge management plan is developed and implemented KFS to ensure the M&E Plan development is completed and implemented |  | KFS |  | Immediately
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1: Development of integrated landscape management (ILM) systems
Output 1.1.1: Multi-stakeholders dialogue and County Environment Committees strengthened to harmonize and influence policies, actions, and catalyze and scale-up green investments | # of hectares covered by ILM plans, informed by inclusive multi-stakeholder dialogue | Piloting of Participatory Informed Landscape Approach (PILA) with multiple trainings with government and stakeholder officers. Bio-Physical baseline survey for Mt. Elgon Ecosystem conducted |  |  | Implementation of output 1.1.1 is behind schedule due to late role-out of the PILA piloting (due to realignment of the KFS OPA). Implementation schedule for output 1.1.1 - 1.1.3 has been aligned with the PILA process.
Output 1.1.2: Capacity building programs implemented to support inclusive and equitable participatory development and implementation of ILM | # of effective multi-stakeholder platforms operational to promote ILM | Four sub-county (Cheptais, Mt. Elgon, Saboti, Endebess) multi-stakeholder platforms established Two county (Bungoma, Trans-Nzoia) multi stakeholder platforms established Two gap analysis for the strengthening of the multi-stakeholder platforms conducted with roadmap Development and alignment of various PILA training packages for ILM planning i.e. PILA TAPE survey; PILA Behavioural Change Assessment; PILA Geospatial tool; PILA Stakeholder analysis. |  |  | Implementation of output 1.1.2 is behind schedule due to late role-out of the PILA piloting (due to realignment of the KFS OPA). Implementation schedule for output 1.1.1 - 1.1.3 has been aligned with the PILA process.
Output 1.1.3: Integrated participatory landscape management plans developed in the Mt. Elgon landscape | # of gender-responsive policy frameworks updated/developed supporting ILM | Free, Prior, and Informed Consent (FPIC) have been conducted and completed for the Ogiek and forest adjecent community in the Mt. Elgon landscape. Socio-ecoomic baseline survey for Mt. Elgon Ecosystem conducted Development and alignment of various PILA tools and guidlines for ILM planning i.e. PILA TAPE survey; PILA Behavioural Change Assessment; PILA Geospatial tool; PILA Stakeholder analysis. |  |  | Implementation of output 1.1.3 is behind schedule due to late role-out of the PILA piloting (due to realignment of the KFS OPA). Implementation schedule for output 1.1.1 - 1.1.3 has been aligned with the PILA process.
Outcome 2: Promoting sustainable and inclusive coffee and maize value chains
Output 2.1.1: Capacity development programs implemented for smallholder farmers, cooperatives and other value chain actors to promote Climate-Smart coffee and maize production | # of farmers (at least 30 % women) benefited from training and access to services to support sustainable coffee and maize production and marketing | N/A |  |  | Activities planned for year one (role out of farmer field schools, setting up of agroforestry nurseries/clonal gardens) under the output are delayed due to challeneges with operationalization of KALRO OPA
Output 2.1.2: Innovative Business hubs established to promote market access and service delivery to smallholder farmers. | # of hectares of landscapes under improved practices | N/A |  |  | Activities planned for year one (Village aggregation centers, trainings, certification of warehouses, access to farm inputs etc) have been delayed due to challenges with operationalization of KALRO OPA. Most activities have under oputput 2.1.2 have been off-loaded from the OPA and will be implemented through LoAs - process underway
Output 2.1.3: Sustainable coffee standards, certification and traceability systems developed and promoted with innovative incentive mechanisms. | # of hectares in the process of certification | Assessment of 26 coffee cooperatives in the Mt. Elgon Landscape on compliance with the European Union Deforestation Regulation completed with roadmap for support to compliance |  |  | Certification of the coffee value chain expected from year two of project implementation. However, due to the EUDR, the project has moved the implementation ahead to support the coffee cooperatives in the project site in the compliance process.
Output 2.1.4: Gender responsive incentive mechanisms established to promote sustainable coffee value chain development. | % of Increase in coffee and maize yield per tree/hectare for smallholder farmers by the end of the project # of county coffee platforms established to promote inclusive and sustainable value chain approach | N/A |  |  | Activities to start year two of project implementation
Output 2.1.5: Capacities of entrepreneurs/community groups strengthened on nature-based business development | # of entrepreneurs/community groups (50% women and youth, Ogiek community) supported through small grants to develop nature-based enterprises for economic empowerment and livelihood diversification | N/A |  |  | Activities to start year two of project implementation
Output 2.1.6: Livelihood Enterprises of the Chepkitale Ogiek Community of the Mt. Elgon Ecosystem promoted through sustainable enterprise development |  | N/A |  |  | Activities to start year two of project implementation
Outcome 3: Conservation and restoration of natural habitat
Output 3.1.1: Capacity of county and community-level institutions for conservation, restoration and rehabilitation of degraded lands and forest habitats strengthened in both degraded forest and agricultural landscapes. | # people trained and engaged in on-the-ground restoration activities (disaggregated by gender, at least 30% women) | N/A |  |  | Activities not yet started due to delays in operationalization of the KFS OPA. Activities planned for year one will be roled out in the next reporting period.
Output 3.1.2: Highly degraded forest sites are restored and sustainably managed. | # Hectares of degraded forest and forest land restored | Two community tree nurseries established (Kaberwa and Kiptogot forest stations) |  |  | Restoration activities with the Ogiek community were delayed awaiting the FPIC process and to align with wider restoration activities for the landscape planned for year two of implementation
Output 3.1.3: Highly degraded agricultural lands are restored. | # Hectares of degraded farmland restored | N/A |  |  | Activities planned for year one (Establishment of school tree nurseries, promotion of agroforestry etc.) under the output are delayed due to challeneges with operationalization of KALRO OPA
Output 3.1.4: Sustainable and innovative financing mechanisms identified and piloted for conservation and restoration |  | N/A |  |  | Roll out planned for the second year of implementation. KFS has developed TORs for service contract.
Outcome 4: Project Coordination, Collaboration, Communication and M&E
Output 4.1.1: Gender-responsive knowledge products, tools and approaches developed and shared through the FOLUR IP Global platform and other relevant value chain platforms. | # of knowledge products and tools shared and/or adopted from the Global FOLUR Platform, regional and national platforms | Piloting of PILA tool is underway with a number of trainings and meetings held |  |  | Piloting of FOLUR tool PILA underway. Due to limited implementation in other project areas, other knowledge products to be shared are awaiting futher implementation
Output 4.1.2: Effective M&E system established for the project | Project M&E system operational | M&E officer recruited |  |  | Late recruitment of M&E officer to the PMU by KFS has resulted in M&E system being delayed. This will be completed in the next reporting period
Output 4.1.3: Transboundary integrated knowledge sharing system established for the Kenyan and the Ugandan Mt. Elgon landscape | # of people reached through Transboundary Knowledge sharing platform | N/A |  |  | In the second year of project implementation
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Unsatisfactory (U) | Moderately Unsatisfactory (MU) | Moderately Unsatisfactory (MU) | Not Rated | Moderately Unsatisfactory (MU)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | Delayed operalisation of KFS OPA and KALRO OPA. Delayed recruitment of M&E Officer. | Progress has been slow due to the delays the project is facing under one of the Operational Partner' challenges in operationalizing the Operational Partner's Agreement. The other Operational Partner is making progress in implementation, although it has also faced some delayed start. | There rating is based on delays in the implementation of the project due to challenges in the OPIM modality, delays in the operationalization of the KALRO OPA as well as late constitution of the Project Management Unit | Comments | There has been a delay in the implementation of key components of the project due to challenges in operationalizing KALRO's Operational Partners Agreement - KALRO has not obtained necessary approvals from Treasury. FAO Kenya in consultation with the GEF OFP is exploring options to help address this situation.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
During the reporting period, progress has been made toward achieving the project’s development objectives, particularly under Outcome 1 focused on Integrated Landscape Management (ILM) in the Mt. Elgon ecosystem. The Participatory Informed Landscape Approach (PILA) has been rolled out, including the development and alignment of a suite of planning tools such as the PILA TAPE survey, Behavioural Change Assessment, Stakeholder Analysis, and Geospatial Mapping Tool. These tools are supporting the participatory development of the Mt. Elgon Ecosystem Management Plan, which will cover over 178,000 hectares. Multi-stakeholder engagement has been progressed, with the establishment of four sub-county platforms (Cheptais, Mt. Elgon, Saboti, Endebess) and two county-level platforms (Bungoma and Trans-Nzoia), along with gap assessments and roadmaps to strengthen their function. Socio-economic and bio-physical baseline surveys have been completed, and Free, Prior, and Informed Consent (FPIC) processes with the Ogiek and forest-adjacent communities have been finalized, laying a foundation for inclusive implementation. Under Outcome 2, the project undertook an assessment of 26 coffee cooperatives for compliance with the EU Deforestation Regulation (EUDR), with proposed support now in place to support compliance. Additionally, two community tree nurseries have been established at Kaberwa and Kiptogot forest stations under the restoration component.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Implementation has progressed at a slower pace than anticipated due largely to delays in operationalizing key Operational Partnership Agreements (OPAs) with the Kenya Forest Service (KFS) and the Kenya Agricultural and Livestock Research Organization (KALRO). These delays have had a cross-cutting impact on several components, affecting the timely initiation of activities under Outcomes 1, 2, 3 and 4. For Outcome 1, the realignment of the KFS OPA contributed to a delayed rollout of the Participatory Informed Landscape Approach (PILA), which in turn affected the timing of integrated landscape planning and capacity-building activities. Similarly, under Outcome 2, challenges related to the setup of KALRO’s project bank account and internal procedures delayed the implementation of activities such as farmer field schools, agroforestry nurseries, and support for climate-smart production systems. As a result, key targets related to sustainable agricultural practices and value chain strengthening are expected to be realized later than initially planned. To mitigate these challenges, the project has worked to prioritize the PILA process to ensure the Mt. Elgon Ecosystem Management Plan is in place to guide implementation of the project as well shifting selected activities from OPAs to Letters of Agreement (LoAs), enabling more flexible implementation with various partners. Under Outcome 4, the recruitment of an M&E officer as well as the communication officer was delayed, the positions are now filled, and the work is under development. Despite these delays, critical groundwork—including FPIC processes, baseline assessments, and stakeholder platform establishment has been completed with project activities being scheduled for implementation for the next reporting period.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | N/A
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The project has established two county (Bungoma and Trans-nzoia) county multi-stakeholder platforms and four sub-county (Cheptais, Mt. Elgon, Saboti and Endebess) multi-stakeholder platforms to oversee and guide project implementation and ensure both local and national ownership of the project implementation and results. The project implementation is led by Kenya Forest Service and Kenya Agriculture and Livestock Research Organization who are the mandated government institutions in the area of implementation with officers from these instutions spearheading activity implementation and trainings. Project component one (1) on integrated land management (ILM) planning is piloting PILA which ensures wide participation from community, local and national stakeholders. The PILA process has been adapted to the Kenyan context and follows established procedures on Ecosystem Management Plan development to ensure ownership and use of the plan.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Moderate Risk
New environmental and social risks. | No changes/new risks identified during the implementation period
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | Type of risks: * Biodiversity, ecosystems,, natural habitats * Plant genetic resources for food and agriculture *Pest and Pesticide management * Indigenous people and culutral herritage Mitigation Actions: * The project will work in buffer zones of protected areas; multi-stakeholder platform to develop the Mt. Elgon Ecosystem Management plan to guide on restoration interventions; Capacity buidling of local stakeholders and communities; only use indigenous tree seedlings for restoration activities; * Suistainable agricultural intensification through the promotion of well proven and well tested (in the Kenyan context) coffee varities through clonal gardens; development of community tree nureries for agroforestry and crop diversification * Promotion of agro-ecological/good agricutural practices through the use of farmer field schools, extension support, promotion of traditional knowedge * Ogiek/IP community representation in project management, integration of IP needs/wishes in project implementation; Free, Prior and Informed Concent (FPIC) applied to project implementation Status of implementation: * Multi-stakeholder platforms established at county and sub-county level to oversee and guide project implementation; the development of Mt. Elgon Ecosystem Management plan is underway * Consultations maintained with key partners in project steering committee meeting and IP community integrated in the PSC * FPIC process completed and endorsed
Grievance Redress Mechanism (GRM) | The community of Ogiek in the Mt. Elgon landscape had raised some concerns on delays in project implementation. This was solved through on-site consultations with community representatives; FPIC process completed and areas of interventions for first phase of implementation agreed on.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Political |  | Low | Yes | Limited national government support: Key approaches promoted by the project, such as ILM, inclusive and effective VC development require strong government support | National project steering committee established chaired by the Ministry of Environment, Climate Change and Forestry and other relevant national/local stakeholders
2 | Political |  | Moderate | Yes | Limited County government support: After devolution, counties are in the driving seat to guide sustainable development, including spatial planning | Multi-stakeholder platforms established at county and sub-county level to guide and oversee project implementation
3 | Social |  | Low | Yes | Limited buy-in from local communities on integrated landscape approach | Multi-stakeholder platforms established at county and sub-county level to guide and oversee project implementation.
4 | Social |  | Moderate | Yes | Land conflict | FPIC process completed for IP and forest adjecent communities
5 | Social |  | Low | Yes | Security risk | The project area has been stable for the past 10 years and no changes in the security situation has occured in the reporting period
6 | Social |  | Moderate | Yes | Fragility of global price/market (coffee/maize) | The introduction of the European Union Deforestation Regulations may impact the livelihoods of coffee farmers in the project site significantly. The 26 coffee cooperatives in the project site has been informed of the EUDR, rediness assessment has been conducted and the project plan to support the cooperatives in the compliance process in the next reporting period
7 | Social |  | Low | Yes | Community fatigue | The project area has not received as much investments and projects as other areas in Kenya. FPIC process completed to ensure alignment of interventions with community priorties.
8 | Social |  | Low | Yes | Disruption during national elections | No elections during the reporting period
9 | Social |  | Moderate | Yes | Limited technological awareness | The project will enagage with partners and service providers who will adapt training and capacity building to the needs and demands of these organizations
10 | Environmental |  | Moderate | Yes | Climate change risk | The project is supported by KFS and KALRO which possess a strong knowledge base on environmental management in the region so as to ensure that activities implemented do no harm.
11 | Environmental |  | Low | Yes | The COVID-19 crisis extends over time and has operational impacts on the implementation and institutional/governance arrangements of the project. This also can result in both higher costs for inputs as well as increased demand. | No restrictions based on Covid-19 or other health/disease related events during the reporting period
12 | Partnership & Coordination |  | Moderate | Yes | Co-financing does not materialize. | Esablishment of project management unit and some of the implementation modalities has delayed. The newly established PMU will be tasked to monitor co-finance materialization
13 | Partnership & Coordination |  | Low | Yes | Complexity of partners implementation in the project area | Multi-stakeholder project steering committee established (Gov, County Gov, FAO, CSOs, Community and IPs represented); multi-stakeholder platforms at county and sub-county level established to oversee and guide project implementation.
14 | Partnership & Coordination |  | Moderate | No | Alignment of Operational Partnerts Implementation Modality (OPIM) in relation to government regulations & protocols in Kenya | Numerious trainings and consultative meetings have been held with implementing partners. Alternative implementation arangements are being explored
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Moderate | Moderate | Due to challenges in operationalizing a key component of the project - which is affecting overall implementation of the project.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | No change
Components and cost | No change
Institutional and implementation arrangements | No change
Financial management | No change
Implementation schedule | Update of EOD/NTE date (to reflect the start of implementation) | 2024-06-01 | LTO
Executing Entity | No change
Executing Entity Category | No change
Minor project objective change | No change
Safeguards | No change
Risk analysis | No change
Increase of GEF project financing up to 5% | No change
Co-financing | No change
Location of project activity | No change
Other minor project amendment (define) | No change
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Ministry Of Environment, Climate Change and Forestry | Strategic partner | Chair of project steering committee meetings Lean staff and lengthy processes in policy/strategy and adoption
Government Institutions | Ministry of Agriculture, Livestock, Fisheries and Cooperatives (MoALFC) | Strategic partner | At the County level, the Ministry will play a strategic role in promotion and coordination of agriculture extension services through the FFS and farmer field days.
Government Institutions | Ministry of Industrialization, Trade and Enterprise Development (MoITED) | Strategic partner | The project will develop synergies with MoITED through its Kenya Industry and Entrepreneurship Project (KIEP) to support the G-Business hubs.
Government Institutions | Kenya Forest Service | Project coordinator and lead implementing partner | KFS is responsible for overall coordination of implementation and reporting to FAO, subcontracting relevant partners for certain activities and take lead in implementation of other activities. KFS also facilitates the steering committee meetings. The implementation by KFS has been delayed due to late operationalization of the OPA agreement as well as reporting on the same
Government Institutions | Kenya Agriculture, Livestock Research Organization (KALRO) | Lead implementing partner | Implementation of KALRO OPA has been delayed due to challenges in operationalization of KALRO OPA
Government Institutions | Kenya Water Tower Agency (KWTA) | Implementing partner | KWTA has been dissolved following the expiry of its legal framework and a government rationalization initiative. Planned activities for KWTA has been integrated in the KFS OPA
Government Institutions | Kenya Wildlife Service (KWS) | Implementing partner | KWS manages the Mt Elgon National Park and the wildlife in the larger mountain ecosystem, while KFS manages forest reserves in the mountain
Government Institutions | Water Resources Authority (WRA) | Strategic partner | WRA normally implements catchment conservation and restoration interventions through WRUAs using the Integrated Water Resources Management (IWRM) approach.
Government Institutions | National Environment Management Authority (NEMA) | Strategic partner | NEMA will provide coordination of and guidance on environmental issues and participate in the ILM planning and policy dialogues through the multi-stakeholder platforms
Government Institutions | Bungoma County Government | Strategic partner | While the counties have and will engage throughout the project cycle it is expected that they will also provide co-financing for various activities planned in the project, incorporate restoration of their respective degraded agricultural landscapes into their development planning (CIDPs 2022-2027).
Government Institutions | Trans Nzoia County Government | Strategic partner | While the counties have and will engage throughout the project cycle it is expected that they will also provide co-financing for various activities planned in the project, incorporate restoration of their respective degraded agricultural landscapes into their development planning (CIDPs 2022-2027).
NGOs | Rainforest Alliance (RA) | Strategic partner | RA has a wealth of experience in providing support to smallholder farmers and cooperatives in the certification process, while strengthening their internal management and knowledge systems. RA will support in the coffee certifcation process
NGOs | World Resource Institution (WRI) | Strategic partner | Technical expertise in ILM planning and data collection
NGOs | Solidaridad | Strategic partner | Technical expertise and coordination of coffee interventions in the project site
NGOs | Mt Elgon Elephant Project, Mt Elgon Foundation & Mt.Elgon Ecosystem Restoration Trust | Strategic partner | Support to community conservation and restoration interventions and support to development and implmenetation of participatory forest management
NGOs | International Crane Foundation/ Endangered Wildlife Trust Partnership | Strategic partner | Technical expertise and interventions in sustainable management of wetland ecosystems in the project site
NGOs | East Africa Grain Council (EAGC) | Strategic partner | Technical expertise and interventions in the maize value chain, delivery of extension support, input etc in the maize value chain
NGOs | E4IMPACT Foundation | Strategic partner | Expertise and support in the delivery of community grants
Others | Ogiek community | Community | The Ogiek are engaged trhougout the project implementation: in decision making, implementation and as beneficiaries
Others | CFAs/WRUAs | Community | The project will engage CFAs/WRUAs organizations in building their capacities and restoration work in the landscape, community policing, fire control and riparian land conservation, among others. They will be instrumental in setting up nurseries for the production of seedlings to be used in the restoration sites.
Private Sector entities | Western Tree Planters Association (WETPA) | Farmer cooperative | Provide technical expertise and coordination of agroforestry interventions in the project site
Private Sector entities | Coffee/Maize Cooperatives | Farmer cooperative | The cooperatives will be engaged both as implementers and beneficiaries and will represent the smallholder farmers in the landscape. They will implement the various activities meant to attain certification, improve coffee quality and access to markets.
Private Sector entities | Private Sector | Private sector | Will be engaged as service providers, off takers etc.

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources |  | Gender mainstreamed in ILM planning process and tools developed for the Participatory, Informed Landscapes Approach (PILA) such as PILA TAPE, Behavioural change assessment, Stakeholder assessment tool.
b. Improving women's participation and decision making |  | Minimum of 30% inclusion of women in all decision making platforms
c. generating socio-economic benefits or services for women |  | Due to delays in operationalization of OPAs, progress is expected for the next reporting period
Any other good practices on gender |  | N/A

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The project has a Knowledge mananagment plan which will be futher defined by the on-boarded M&E specialist. The Kenya FOLUR project is part of the global FOLUR Impact programme and interacts with other participating countries and shares experiences, lessons learnt and best practices through webinars, community of practice, bilateral meetings etc. Information is shared through webinars, regional events and FOLUR workshops. Once restoration/livelihood activities are in full implementatio ,good practices will be shared and published in the Framework for Ecosystem Restoration monitoring(FERM)
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | The Participatory, Informed Landscapes Approach (PILA) is being piloted/rolled out in Kenya for the development of the Mt. Elgon Ecosystem Management Plan.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | Project launch was attended by Cabinet Secritary of Environment, Climate Change and Forestry. Event was well attened and featured in media. Launch of Mt. Elgon transboundary bio-sphere reserve (Kenya/Uganda) Limited communication due to delays in implementation of activities and late onboarding of communications specialist who will operationalize the communications plan
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | N/A
Please provide links to related website, social media account | https://www.the-star.co.ke/counties/western/2025-01-31-two-counties-kfs-roll-out-sh600m-project-in-mt-elgon https://www.the-star.co.ke/news/2024-11-07-kaberua-tree-nursery-expanded-to-boost-forest-cover-in-mt-elgon https://www.the-star.co.ke/news/2024-11-07-kaberua-tree-nursery-expanded-to-boost-forest-cover-in-mt-elgon
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | N/A
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | M&E:Samuel Muriithi - smuriithi2000@yahoo.co.uk Communication: Rhodah Mbatiany - rmbatiany046@gmail.com

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. The Free and Prior Consent Process was successfully conducted with indigenous and forest adjacent communities in Mt. Elgon. The process involved informing the community members about the project objectives and the expected outputs and potential livelihoods impacts to the community in a participatory manner. Seven consultative meetings were convened in different locations. From the FPIC assessment the community identified key cultural and environmental considerations that need to be considered by the project. Key sacred and important conservation sites which require protection and conservation were identified by the communities in all the 4 Forest stations (Cheptais, Kaboywo, Kaberwa, Saboti and Suam). The community members also identified and prioritized indigenous trees of cultural and economic importance for restoration. The process was guided by the FPIC principles of ensuring their adequate consultation, transparency in disclosure of project information, ensuring inclusiveness of all stakeholders in Mount Elgon landscape and respecting the cultural ways of the Indigenous Ogiek People. Based on review of the reports the following steps were applied; 1. Gathering of information • We gathered information on Mt. Elgon landscape including geographic and demographic information, economic activities, degradation levels and the Indigenous Peoples’ 2. Stakeholder identification and analysis • Information on the primary stakeholders involved in restoration activities within the landscape was collected and their roles were assessed. • Analysis of how decisions are made within the community. • Identification of legitimate representatives of the community • Identification of indigenous people and vulnerable community members who require special consideration by the project. 3. Project information sharing and consultation • We presented the GEF 7 FAO Elgon FOLUR Project to community representatives, outlining its objectives, components, outputs, and specific interventions. • Community members were given an opportunity to freely engage and interrogate the projects planned activities and provide feedback and suggestions for inclusion. • Community representatives mapped culturally sensitive areas in the adjacent forests, such as shrines, water sources, grazing grounds, and initiation sites. The community was assured that the project will respect their cultural values and not interfere with these important sites. 4. Documentation of Communication Structure • Through a Venn diagram the stakeholders were able to map out how stakeholders communicate and who is involved (mode of communication and reporting structures within the community. 5. Analysis of Governance structure • An analysis of the community's governance structure was conducted, concentrating on the bylaws followed by the community. The analysis documented customary laws and practices related to restoration and the environment. 6. Conflict resolutions mechanism and complaints • A detailed discussion was carried out on the potential conflicts that may arise during project implementation, how they will be resolved and whether the community has established mechanisms for reporting and conflict resolution. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. Indigenous people and local communties are activly engaged in the project throughout the various steps of implementation. IPs and loacl communities are represented in the project steering committee as well as the newly established multi-stakeholder platforms at county and sub-county levels. In line with manuals for development of participatory management plans and ecosystem management plans, the communities are activly involved in the development of the ecosystem management plan and will later be the core implementers/beneficiaries in restoration and livelihood activities through the community based organizations such as Community Forest Associations, Water Resource User Organizations; coffee and Maize farmer cooperatives etc. Local communities are also represented by the officers and officials from the county governments who are involved/integrated in all project implementation. The Ogiek community will be engaged directly by FAO for implementation which directly relates to priorities identified in the FPIC process.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
GEF CoFinancing Guidelines 2018

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.