Project Implementation Report (PIR)

01/07/2024– 30/06/2025

Renforcement de la coopération transfrontalière pour une meilleure gestion et restauration des écosystèmes dans le delta du Sénégal

(Mauritanie et Sénégal)

www.rbtds.org

Table of Contents

A	Basic Data	2

B. Overall Ratings	3

C. Outcomes achievements and outputs delivery	Erreur ! Signet non défini.

D. Ratings and Overall Assessments	46

E.	Adjustments	46

F.	Implementation Progress	47

G. Critical Risk Management	49

H. Gender	50

I.	Implementing the Stakeholder Engagement Plan	51

J.	Environmental and Social Safeguards	53

K.Knowledge management	59

Annex -  Ratings definitions	64

# Basic Data

| Project Information |  |
| --- | --- |
| IUCN Project ID | ID UICN P0 3248 |
| GEF ID | ID GEF: 9594 |
| Title | Strengthening transboundary cooperation for improved ecosystem management and restoration in the Senegal Delta (Mauritania and Senegal) |
| Country(ies) | Mauritania and Senegal |
| Regional Programme | Water |
| Global Thematic Programme | International Waters |
| Joint Agency (if relevant) |  |
| Executing Agency(ies) | Direction du Parc National du Diawling en Mauritanie et Direction des Parcs Nationaux du Sénégal |
| Project Type | FSP |

Project Description

The GEF-funded project "Strengthening Transboundary Cooperation for Better Ecosystem Management and Restoration in the Senegal Delta (Mauritania and Senegal)" is implemented by the Ministries of Environment and Sustainable Development of Senegal and Mauritania (MEDD-SN and MEDD-MR, respectively) in close coordination with the International Union for Conservation of Nature (IUCN). The project's objective is to "support improved governance, socioeconomic development, and ecosystem management in the Senegal Delta Transboundary Biosphere Reserve (SDTBR)." To achieve this objective, the project was designed taking into account the national priorities of Mauritania and Senegal, and the findings of the most recent Transboundary Diagnostic Analysis (TDA) for the Senegal River Basin. The project responds directly to the priority measures carried out in the Strategic Action Program (SAP) 2017-2037 of the Organization for the Development of the Senegal River (OMVS) and to the strategic actions described in the Strategy of the Man and the Biosphere Program (MAB) for 2015 to 2025. To achieve the project objective, it will be implemented through three (3) main components: Component 1 : RBTDS Governance, which aims to strengthen and operationalize the governance and management of the RBTDS. Component 2 : Integrated Ecosystem Management and Restoration in the Lower Senegal River Delta, which aims to advance ecosystem restoration and integrated ecosystem management in the Lower Senegal River Delta. Component 3 : Scientific Cooperation, Knowledge Acquisition and Sharing, and Ecosystem Monitoring and Assessment, which recognizes the importance of promoting an integrated problem-solving approach to addressing the challenges facing the RBTDS. By supporting knowledge acquisition, scientific cooperation, and information sharing among stakeholders, it aims to ensure that sustainability science is applied to improve the effectiveness of RBTDS management. As part of this process, the project ensures a shared understanding and formal recognition of a contemporary vision, mandate, and legal framework for the RBTDS, and will support the development and implementation of a scientifically sound management plan for the RBTDS. The management plan is accompanied by frameworks for advancing applied research and learning, capacity building, communications, and financial sustainability. The project works with stakeholders to design and implement interventions aimed at restoring ecosystems, improving the sustainability of resource use, and advancing sustainable income-generating initiatives. These interventions address priority environmental issues affecting the Senegal River Delta ecosystems and help ensure that critical ecosystems and key habitats within the RBTDS are restored and sustainably managed to protect water resources, forests, and fisheries, and enhance ecosystem services. The interventions also increase the resilience of ecosystems and local communities and provide important biodiversity benefits.

| Project Contacts |  |
| --- | --- |
| Task Manager (Implementing Agency) |  |
| Global Thematic Lead (Implementing Agency) | UICN |
| Project Manager (Executing Agency) | PND- DPN |
| GEF Operational Focal Point |  |

# Overall Ratings

| Overall Development Outcomes Rating |  |
| --- | --- |
| Overall Implementation Rating |  |
| Overall Risk Rating |  |

# C. Outcomes achievements and outputs delivery

- Provide an overview of high level outcomes achieved since project started against overall objective and targets.

- Provide an overview of outcomes achieved during this reporting period against overall objective and targets.

- In case of deviation from the intended outcomes, provide (a) a short description of the challenge encountered and (b) a description of the solutions applied to mitigate their impact

(Delete the above guidance after reporting - max 500 words)

Please fill in the table below building on your result framework Please fill in the table below building on your result framework.

| Objective: Improving governance, ecosystem management and socio-economic development in the Senegal Delta Transboundary Biosphere Reserve (RBTDS) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes Results (Copy and paste outcomes from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024- 30/06/2025) | Result to Date (from project start) | Progr ess rating (HS, S,MS, MU,U, SU) |
| Outcome 1.1: Governance and management structures and institutional planning processes established and operational | 1.1.a: Number of hectares of the Senegal River delta under improved integrated water resource management | 1.1.a: 52,000 ha |  | 1.1.a: 562,470 ha | We consider that 562,470 hectares of the Senegal River delta are under improved integrated water resource management. The project has revitalised the governance and management bodies for the RBTDS and developed the RBTDS Transboundary Management Plan. These poses provide an important framework for stakeholders to consider water needs and how to conservation of water resources and the maintenance of the water |  | SS |

|  |  |  |  |  | cycle can be managed within the RBTDS. |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.b: Effectiveness of the management of the RBTDS (to be measured using the additional PR and PAME indicators) indicators) | 1.1.b: N/A |  | 1.1.b: An effectively effectively managed 1.1.b: TBD | The RBTDS periodAic report is produced and validated in September 2023. |  | HS H |
| Outcome 1.1.1 - The vision, mandate and legal framework of the RBTDS are reviewed and the governance and management bodies are functional. | 1.1.c: Number of legal texts formally recognising the RBTDS framework | 1.1.c: 0 |  | 1.1.c: Up to 3 | The legal framework document is finalised. Texts for formal recognition are proposed and will be signed. |  | MS |
|  | 1.1.d: Number of functional RBTDS governance and management bodies. | 1.1.d: 0 |  | 1.1.d: 5 | The governance and management bodies have been set up on a provisional basis pending formalisation. However, the - Transnational Steering Committee is operational, - The two national committees in Senegal and Mauritania are operational and meet regularly. meetings, |  | HS |

|  |  |  |  |  | - The Scientific and Technical Committee was set up in July 2024. - The Transfrontier Management Unit of the project currently plays the role of the RBTDS Management Unit - The project's GTU, which acts as the permanent secretariat of the of the RBTDS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.e: % of members of individual management and governance bodies who are women and/or members of vulnerable groups | 1.1.e: N/A |  | 1.1.e: 50% |  |  | MS |
| Outcome 1.1.2. - The RBTDS management plan is produced and being implemented | 1.1.f: Number of management plans produced and approved (including explicit objectives, strategies and actions) | 1.1.f: 0 |  | 1.1.f: 1 | The RBTDS management plan has been produced and validated in a participatory manner since December 2023. |  | HS S |

|  | 1.1.g: Number of targeted social assessments carried out | 1.1.g: 0 |  | 1.1.g: At least at least 3 |  |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.h: % completion of planned annual activities | 1.1.h: N/A |  | 1.1.h: 100% |  |  | S |
|  | 1.1.i: Number of grievance mediation and conflict resolution mechanisms put in place in collaboration with RBTDS management. | 1.1.i: 0 |  | 1.1.i: 1 | A grievance mediation and conflict resolution mechanism is proposed in the RBTDS management plan. It has yet to be implemented. |  | MS |
| Outcome 1.1.3 - Cross-border coordination between local platforms is functional | 1.1.j: Number of opportunities for cross-border coordination between local platforms achieved. | 1.1.j: 0 |  | 1.1.j: 9 | The coordination mechanism between local platforms is being developed |  | S |

|  | 1.1.k: % of participants who are GEFmes and/or members of vulnerable groups | 1.1.k: 0 |  | 1.1.k: 60% | 60% of women and members of vulnerable groups took part in the meetings the UGT held with organisations in the RBTDS during the period July 2024 to June 2025 |  | MS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1.1.4 - Partnerships with the private sector support the objectives of the RBTDS | 1.1.l: Number of partnerships with private sector actors that contribute to the conservation and sustainable development objectives of the RBTDS or to its sustainability | 1.1.l: 0 |  | 1.1.l: 2 |  |  |  |
|  |  |  |  |  |  |  | U |
|  |  |  |  |  |  |  | U |
| Outcome 1.1.5 - The annual budget of the RBTDS Secretariat is approved and resources are secured for the next 5 years. | 1.1.m: Number of business plans produced | 1.1.m: 0 |  | 1.1.m: 1 |  |  | U |

| years (2024- 2028) | 1.1.n: % of guaranteed budget (broken down by source) | 1.1.n: 0 |  | 1.1.n: Not yet achieved |  |  | U |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.o: National (Senegal and Mauritania) funding commitments AFTER publication | 1.1.o: 0 |  | 1.1.o: 2 |  |  | U |
|  | 1.1.p: Number of other financial contributions secured (e.g. donor contributions, income generation, effective partnerships) | 1.1.p: 0 |  | 1.1.p: 1 | The WACA programme intervenes in the RBTDS in terms of restoration and support for populations |  | U |
| Result 1.1.6 - The communication strategy and the RBTDS action plan are in place | 1.1.q: Number of communication strategies and action plans produced | 1.1.q: 0 |  | 1.1.q: 1 | The communication strategy and action plan are produced and implemented. |  | HS |

| produced and implemented | 1.1.r: Number of communication products produced | 1.1.r: 0 |  | 1.1.r: 4 | For the period 13 Rollups, 500 leaflets, 700 T-shirts and caps were produced to publicise the project and the RBTDS The RBTDS website has been operational since November 2023 - A radio programme was launched in collaboration with the Saint Louis radio station to publicise the objectives, strategy and vision of the RBTDS. of the RBTDS |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.s: Number of annual communication events organised and implemented | 1.1.s: 0 |  | 1.1.s: 4 | - The UGT organised the Delta Days, which were an intense moment of communion between the Senegalese and Mauritanian peoples, - the International Day for Biodiversity and took part in - World Wetlands Day and World Migratory Bird Day. Migratory birds |  | S |

|  | 1.1.t: Estimated number of target beneficiaries of the communication strategy (products and event participants) | 1.1.t: 0 |  | 1.1.t: 50,000 | The number of beneficiaries reached is estimated at over 50,000 stakeholders. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1.u: % of increased recognition and understanding of the vision, objectives and management strategies of the RBTDS among target audiences |  |  |  |  |  | S |
|  |  | 1.1.u: 0 |  | 1.1.u: 100% | Stakeholders are 90% aware of the vision, objectives and management strategies of the RBTDS. |  |  |

| Outcome 1.2: Capacity-building and training for key stakeholders have strengthened governance, management and action on the ground. on the ground | 1.2.a: Percentage of targeted stakeholders (disaggregated by type) with increased skills and opportunities to contribute to the management and objectives of the RBTDS | 1.2.a: 0 |  | 1.2.a: 100% | 80% of targeted stakeholders have benefited from increased skills and opportunities to contribute to the management and objectives of the RBTDS |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1.2.1 - The capacity development strategy and action plan are produced and implemented. | 1.2.b: Number of capacity building strategies and action plans produced (based on an assessment of capacity constraints and opportunities in relation to the objectives of the RBTDS and including | 1.2.b: 0 |  | 1.2.b: 1 | RBTDS capacity building strategy and action plan produced and validated |  | HS |

|  | Specific strategies targeting GEFmes and vulnerable groups) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Annual project monitoring report |  |  |
|  | 1.2.c: Number of training events and participants (broken down by gender) | 1.2.c: N/A |  | 1.2.c: 24 (300 participants, 50% GEFmes) | 30 capacity-building sessions are organised. 800 participants, 70% women. |  | HS |
|  | 1.2.d: Number of interventions designed to strengthen the capacities of GEFmes and vulnerable groups, types (e.g. vocational training, access to financial resources, promoting inclusion in decision- making processes, etc.) and number of beneficiaries (broken down by gender). by gender) | 1.2.d: N/A |  | 1.2.d: At at least 32 intervention s (240 beneficiarie s) | 20 interventions designed to strengthen the professional capacities of women's groups and vulnerable groups with 660 beneficiaries |  | HS |

| Outcome 2.1: Critical ecosystems and key habitats are managed sustainably to protect water resources, forests and fisheries and improve ecosystem services | 2.1.a: Number of hectares of wetlands under improved protection | 2.1.a: 0 |  | 2.1.a: 58,440 | Wetlands (flood-prone bare soils, bodies of water, lakes, and marshes) in the RBTDS component cover 167,561 hectares. With the project, 113,973 hectares benefit from improved protection. |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.1.b: Number of areas (and number of hectares) benefiting from restored habitat (disaggregated by habitat type) | 2.1.b: 0 |  | 2.1.b: At least at least 4 | -Reforestation of 10 ha of filaos in the Saint Louis MPA, -Reforestation of 22 ha of filaos in the Langue de Barbarie, -Reforestation of 12 ha of avicennia in the Langue de Barbarie, -Reforestation of 10 ha of rizhofora in the Langue de Barbarie, -Reforestation of 200 vines of trees in the commune of Gnith |  | MS |

|  | 2.1.c: Number of areas (and number of hectares) benefiting from a reduction in invasive species | 2.1.c: 0 |  | 2.1.c: At least at least 2 | Clean-up of 6 ha of typha in the Tocc Tocc basin, Clean-up of 40 ha of typha in the Bell and Diawling basins, Clean-up of 10 ha of typha and invasive vegetation in the Djoudj water bodies, -Cleaning up 11 ha of typha in the Ndiael reserve, Cleaning up 2 ha of cactus in the in the Gueumbeul reserve, |  | MS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.1.d: Number of people (disaggregated by sex) benefiting from improved or alternative livelihoods | 2.1.d: 0 |  | 2.1.d: 1,800 (50% GEFmes) | We consider that 1,360 RBTDS stakeholders are benefiting from improved livelihoods because the UGT has already trained 680 actors in income-generating occupations who come from different households and can therefore impact at least one household. so can impact at least one person, which would make 680x2, so 1360 actors 90% of whom are women/ |  | S |
|  | 2.1.e: Quality and quantity of ecosystem services (disaggregated by type) provided by restored habitat areas (indicators) | 2.1.e: None |  | 2.1.e: To be to be determined |  |  |  |

|  | More specific additional measures to be determined on the basis of the strategies developed under Outcome 2.1.2 and Outcome 2.2) | baseline available |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 2.1.1 - Knowledge gaps relating to key management issues for the TBRDS are identified, prioritised and used to inform an operational master plan for monitoring and research of the RBTDS | 2.1.f: Number of plans produced | 2.1.f: 0 |  | 2.1.f: 1 | The RBTDS monitoring and research master plan has been produced since April 2025 |  | S |

| Output 2.1.2 - At least four local site or catchment action plans for restoration, adaptation and support of livelihoods and biodiversity c o n s e r v a t i o n produced and implemented | 2.1.g: Number of local restoration plans produced | 2.1.g: 0 |  | 2.1.g: At least 4 or more | Four local ecosystem restoration plans are available for : - Dioudj - Ndiael - Diawling - Aftout |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.1.h: Number of local capacity assessments (integrating gender considerations and the needs of vulnerable groups) | 2.1.h: 0 |  | 2.1.h: At least 4 or more |  |  | MS |
|  | 2.1.i: Number of areas implementing local restoration plans | 2.1.i: 0 |  | 2.1.i: At at least 4 | Dioudj, Diawling, Ndiael and Aftout catchment sites implement local ecosystem restoration plans |  | MS |

| Outcome 2.2: RBTDS stakeholders and management mechanisms mobilised to achieve better use of natural resources and demonstrate sustainable practices | 2.2.a: Impact of sustainable use strategies and income- generating initiatives on the resource base and local livelihoods | 2.2.a: N/A |  | 2.2.a: High in terms of positive impacts on service provision and local livelihoods and low in terms of negative impacts (based o n qualitative and quantitative assessment of indicators to be defined for each strategy implemente d). implem ented) | Regular impact assessments |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Outcome 2.2.1 - At least two strategies for the sustainable management or use of land, water resources or inland fisheries developed and implemented | 2.2.b: Number Sustainable management and use strategies developed and implemented | 2.2.b: 0 |  | 2.2.b: At least at least 2 | The study on sustainable natural resource management strategies made 3 proposals: - Strategy and sustainable management of fisheries - Sustainable livestock strategy and management - Strategy and sustainable management of harvesting and forestry resources |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.1.c: Number of targeted capacity assessments (integrating gender considerations and the needs of vulnerable groups) | 2.2.c: 0 |  | 2.2.c: At least at least 2 |  |  | MS |

| Outcome 2.2.2 - At least three sustainable income- generation strategies that strengthen community engagement and resilience are developed and implemented, and the capacity of local user groups, including GEFmes, youth and other marginalised groups, is improved to benefit from said strategies | 2.2.d: Number of natural resource-based product value chains analysed | 2.2.d: 0 |  | 2.2.d: At least at least 3 | The value chain analysis study analysed 4 natural resource- based product value chains in the RBTDS Fishing, fruit picking salt farming and livestock farming |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.2.e: Number of households participating i n and benefiting from income-generating initiatives | 2.2.e: 0 |  | 2.2.e: 300 households | 500 households have already benefited from and participated in income-generating initiatives such as fish processing, local cereal processing and soap making, processing of fried foods and vegetables. |  | S |
|  | 2.2.f: % of household income resulting from project initiatives | 2.2.f: 0 |  | 2.2.f: 15% | This evaluation has not yet been carried out. |  |  |

|  | 2.2.g: Number of small subsidies granted | 2.2.g: 0 |  | 2.2.g: 60 | 40 small grants have already been awarded. |  | MS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 3.1: Scientific cooperation is strengthened to improve data collection, analysis and learning | 3.1.a: Quality and content of the joint research agenda | 3.1.a: N/A |  | 3.1.a: High in terms of quality and applicability to the managemen t, monitoring and learning of the RBTDS |  |  | MU |
| Outcome 3.1.1 - Cross-border data collection processes, the information management system and the research network provide up-to- date analyses that serve as a basis for decision making and monitoring. and policy-making. | 3.1.b: Number of functional mechanisms for cross- border information management (including data management policies) | 3.1.b: 0 |  | 3.1.b: 1 | The mechanism for cross-border information management is being developed |  | U |
|  | 3.1.c: Number and type of participants in the cross-border research network | 3.1.c: 0 |  | 3.1.c: 20 | The members of the Scientific and Technical Committee constitute the cross-border research network of the RBTDS |  | MU |

| Participatory management of the RBTDS | 3.1.d: Number of collaborative research or monitoring activities undertaken by the network | 3.1.d: 0 |  | 3.1.d: 4 | 08 research topics on RBTDS issues are in progress |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 3.1.e: Number of knowledge exchange activities organised and implemented | 3.1.e: 0 |  | 3.1.e: 4 | 4 exchange visits already organised |  | MS |
|  | 3.1.f: Number of cross-border beneficiaries of planned knowledge exchange activities (disaggregated by RBTDS role and gender) | 3.1.f: 0 |  | 3.1.f: 120 (50% GEFmes) | 100 RBTDS stakeholders, 50% of whom are women, have already benefited from best practice exchange visits on mangrove reforestation between the PND, the PNLB and participation in exhibition and sales fairs in Dakar, Nouakchott and Saint Louis. |  | MS |

| Outcome 3.2: The project monitoring and evaluation system is in place | 3.2.a: Number of functional M&E systems | 3.2.a: 0 |  | 3.2.a: 1 | The project's monitoring and evaluation system is functional, with a monitoring and evaluation manager and a monitoring and evaluation plan. |  | S |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 3.2.1 - The project's monitoring and evaluation plan is developed and implemented | 3.2.b: Number of M&E plans produced | 3.2.b: 0 |  | 3.2.b: 1 | 1 project M&E plan produced |  | S |
|  | 3.2.c: Number of annual M&E reports produced | 3.2.c: 0 |  | 3.2.c: 4 | 3 annual reports produced |  | S |
| Outcome 3.2.2 - Mid-term and final evaluations of the evaluations of the project are completed | 3.2.d: Number of evaluation reports produced | 3.2.d: 0 |  | 3.2.d: 2 | (1) The mid-term evaluation document is available. |  | S |

The activities implemented during the period from July 1, 2024 to June 30, 2025, are as follows :

COMPONENT 1 : RBTDS GOVERNANCE

Component 1 of the project aims to strengthen and operationalize the governance and management of the RBTDS.

a. Assessment and analysis of the results of component 1

For this component, the planned activities are part of the achievement of the following results:

Outcome 1.1: Governance and management structures and institutional planning processes established and operational

Outcome 1.2: Capacity building and training of key stakeholders have strengthened governance, management, and actions on the ground

The planned activities have achieved the following levels of achievement :

 1. Review, consolidate, and approve the RBTDS vision, as well as the mandate, legal framework, and governance and management bodies

The document has been developed and validated since June 8, 2023. https://rbtds.org/wp-content/uploads/2025/07/CADRE-JURIDIQUE-DE-LA-RBTDS.pdf

 2. Establish and operationalize the RBTDS governance and management bodies

This activity will aim to establish and operationalize the RBTDS governance and management bodies.

The governance and management bodies are :

- The Transnational Steering Committee (COT)

- The Scientific and Technical Committee (CST) (https://rbtds.org/2024/07/12/reunion-du-comite-scientifique-et-technique-de-la-rbtds/)

- The Cross-Border Management Unit (UGT) https://rbtds.org/notre-equipe/

- The two National Committees (NC)

Within the framework of this activity, the UGT is well established and operational.

The national committees are operational and meet regularly.

The Scientific and Technical Committee met on July 12, 2024. The Transnational Steering Committee held its third meeting on January 22, 2025.

The members of the transnational steering committee, which serves as the RBTDS project steering committee, approved the budgeted work plan for 2025 (PTBA 2025).

 3. Develop and approve the RBTDS management plan

The RBTDS management plan was developed and presented in December 2023 in Saint Louis and Nouakchott. For dissemination purposes, it was presented on April 26, 2024, at the FOMACO in Guinea-Bissau.

 4. Develop a communications strategy and action plan to raise awareness among target audiences about the RBTDS's vision, objectives, and management strategies. ( https://www.youtube.com/watch?v=nETTv1Ro-ws)

The communications strategy and action plan were developed and validated on June 7, 2023. https://rbtds.org/wp-content/uploads/2025/07/STRATEGIE-COMMUNICATION-DE-LA-RBTDS.pdf

 5. Implement a communications action plan, including the creation and dissemination of communications products and the organization of public events.

As part of this activity, roll-ups, t-shirts, caps, and brochures were produced as communication materials about the project and the RBTDS.

1,000 copies of the RBTDS Atlas are available.

The RBTDS website is operational (www.rbtds.org) .

The project's UGT produced around ten signage panels positioned at various points along the RBTDS.

Communication events on the RBTDS with the celebration of days dedicated to the environment and biodiversity : (https://www.youtube.com/watch?v=kaKw5ImJGgg&t=33s) (https://www.youtube.com/watch?v=zD0qis5QWKY) (https://www.youtube.com/watch?v=A-KftfqqzFA&t=122s)

The most notable event during the reporting period was the Delta Days, held on February 1, 2, and 3, 2025, between Mauritania and Senegal. This second edition of the RBTDS days was rich in activities with the visit of the Ministers of the Environment of Senegal and Mauritania to the Dioudj and Diawling Bird Parks on February 1, 2025

The official ceremony coincided with February 2nd, World Wetlands Day, under the theme: "Protecting Wetlands for Our Common Future." It was marked by the planting of avicennia plants in the Bell Basin by the ministers and officials present.

These days also served to highlight the contribution of the late Amadou Makhtar Mbow and Abdellahi Magrega to the establishment of the Senegal River Delta Biosphere Reserve, among other achievements. ( https://www.youtube.com/watch?v=vH3F6lvN9FY)

They also served to further strengthen the sacred bonds of neighborliness between two sister countries, Mauritania and Senegal, united by history and geography.

The presence of strong ministerial delegations, administrative authorities, local elected officials, technical and financial partners, communities, and distinguished guests gave this event a symbolic and special character. The need for these two countries to combine their efforts for the sustainable protection of the environment and biodiversity in a comprehensive manner is no longer in dispute. This commitment was materialized through the signing of the declaration relating to the legal status of the RBTDS. In the same spirit, the two Ministers also prefaced the Management Plan, which is a key decision-making tool in the RBTDS. Moreover, beyond the festivities, this second edition devoted a day to reflection and scientific exchanges between experts, researchers, and representatives of other stakeholders (communities, managers, students, development partners, etc.), thus serving as a reminder that research is essential to the reserve's management process. The three themes addressed and presented in panels made it possible to address this essential dimension in strengthening the resilience of the RBTDS. (https://www.youtube.com/watch?v=Xk5slkR7i4U)

http://www.environnement.gov.mr/fr/index.php/accueil/actualite/547-celebration-de-la-2eme-edition-des-journees-de-la-reserve-de-biosphere-transfrontiere-du-delta-du-fleuve-senegal

 6. Develop a capacity building strategy and action plan to meet the needs of RBTDS stakeholders

The capacity building strategy and action plan were developed and validated on September 14, 2023. https://rbtds.org/wp-content/uploads/2025/07/STRATEGIE-DE-RENFORCEMENT-DE-CAPACITE-EN-FAVEUR-DES-ACTEURS-DE-LA-RBTDS.pdf  https://rbtds.org/2024/03/06/restitution-des-etudes-sur-lidentification-des-besoins-des-parties-prenantes-pour-mettre-en-oeuvre-des-initiatives-generatrices-de-revenus-inclusives-et-durables-et-sur-les-chaines-de-valeur/

 7. Implement the capacity building action plan

Approximately twenty sessions were organized for RBTDS stakeholders:

- Training for 40 women from Thilla on local grain processing,

- Training for 40 women from Gandon on local grain processing,

- Training for 30 women from NGnith on local grain processing,

- Training for 30 women from Ronkh on local grain processing,

- Training for 40 women from Mpal on fruit and vegetable processing,

- Training for 40 women from the outskirts of Langue de Barbarie on fruit and vegetable processing,

- Training for 40 women from the outskirts of Gueumbeul on fruit and vegetable processing,

- Training for 40 RBTDS agents and eco-guards on DIOE,

- Training for 40 women from the commune of Ross Bethio on soap making,

- Training for 40 women from Birette and Bouhajra on soap making techniques,

- Training for 120 women from the outskirts of Diawling on agroecology and sustainable market gardening techniques,

- Training of 30 protected area management officers on waterbird counting and data reporting, management with the IREF of Saint Louis,

- Training of 30 journalists on the biosphere reserve concept,

- Training of 30 protected area management officers on ecosystem restoration,

- Training of 40 women in the commune of Ndiébéne Gandiole on local grain processing,

- Training of 30 young people from the commune of Ross Bethio on poultry farming.

- Training of 20 PND officers and local residents on techniques for guiding and welcoming visitors and tourists in protected areas.

COMPONENT 2: INTEGRATED MANAGEMENT AND ECOSYSTEM RESTORATION IN THE SENEGAL RIVER DELTA

Component 2 of the project focuses on advancing ecosystem restoration and integrated ecosystem-based management in the Senegal River Delta.

a. Assessment and Analysis of Results for Component 2

For this component, the expected results for achieving this objective are as follows:

Outcome 2.1: Critical ecosystems and key habitats are sustainably managed to protect water resources, forests, and fisheries and enhance ecosystem services.

Outcome 2.2: RBTDS stakeholders and management mechanisms are mobilized to achieve better use of natural resources and demonstrate sustainable practices.Pour l’atteinte de ces résultats, les activités réalisées se présente comme suit:

• 1. Develop and approve a master plan for monitoring and research for the RBTDS

The master plan for monitoring and research for the RBTDS has been developed and validated since July 2024. https://rbtds.org/wp-content/uploads/2025/07/PLAN-DIRECTEUR-DE-SUIVI-ET-DE-RECHERCHE-DE-LA-RBTDS.pdf  https://web.facebook.com/photo/?fbid=122154178034450982&set=pcb.122154179198450982

Monitoring and research areas have been defined in a participatory manner.

• 2. Use a participatory process to identify and prioritize sites/catchments within the RBTDS that require restoration to maintain or improve shared benefits

The document on the identification and prioritization of sites/catchments within the RBTDS has been produced. Four local restoration plans for degraded sites are proposed to improve shared benefits. This work was carried out in a participatory manner and validated by stakeholders.

It is within this framework that the UGT supported the implementation of the actions prescribed in the local plans. https://rbtds.org/wp-content/uploads/2025/07/RAPPORT-DIAGNOSTIC-DES-SITES-CAPTAGE-RIVE-GAUCHE-RBTDS.pdf

https://rbtds.org/wp-content/uploads/2025/07/RAPPORT-DIAGNOSTIC-DES-SITES-CAPTAGES-DE-LA-RIVE-DROITE.pdf

3. Support the implementation of the actions prescribed in the local plans

Support for ecosystem restoration actions focused on:

- Clearing 6 hectares of typha in the Tocc Tocc basin,

- Clearing 80 hectares of typha in the Bell and Diawling basins,

- Clearing 20 hectares of typha and invasive plants in the Djoudj water bodies,

- Clearing 30 hectares of typha in the Ndiael reserve,

- Clearing 10 hectares of cactus in the Gueumbeul reserve,

- Reforestation of 10 hectares of casuarina trees in the Saint Louis MPA,

- Reforestation of 22 hectares of casuarina trees in the Langue de Barbarie,

-Reforestation of 12 hectares of avicennia in the Langue de Barbarie,

- Reforestation of 10 hectares of rizhofora in the Langue de Barbarie,

- Reforestation of 200 trees in the commune of Gnith,

• 4. Lead and strengthen initiatives to implement sustainable management and use strategies within the RBTDS

The project, in partnership with Mauritanian and Senegalese consultants, produced a document on sustainable natural resource management strategies, validated on May 8, 2025. This document proposed three sustainable management strategies for fishing, livestock, gathering, and forestry products.

• 5. Analyze the value chains of water and natural resource products from the RBTDS

The strategy on the value chains of water and natural resource products from the RBTDS was produced and validated on March 7, 2024. https://rbtds.org/wp-content/uploads/2025/07/RAPPORT-FINAL-CHAINES-DE-VALEUR-RBTDS.pdf

Four value chains were selected : fishing, gathering, salt production, and livestock in the RBTDS.

The UGT supported the development of these sectors by providing a set of equipment to stakeholders.

For the fishing sector, around ten solar streetlights and fermentation tanks were distributed to women's processing groups on the outskirts of the Saint Louis MPA. A batch of equipment consisting of canoes, nets, hooks, gloves, fishing gear, drying keys, and three tricycles was distributed to artisanal fishermen on the outskirts of Diawling.

The salt processing and packaging building of the Taty Mbaye group in the commune of Gandon is currently undergoing renovations.

- A building for harvesting and processing local produce is currently being built in the village of Thilla Boye, in the Trois Marigots area. A set of equipment, including basins, cutters, overalls, gloves, and boots for harvesting gowé and water lilies, is being distributed to women's groups on the outskirts of Dioudj. ( https://www.youtube.com/watch?v=GKNIFXJtQss)

- As part of the livestock sector, two training sessions on poultry farming were held, as well as the installation of two chicken coops for women on the outskirts of Dioudj and for young people from the commune of Ross Béthio.

- A set of poultry farming equipment is being distributed to populations on the outskirts of Diawling in the commune of Ndiago and the towns of Birette, Bouhajra, Moidina, and Kahra.( https://www.pnd.mr/actualites/le-projet-rbtds-appui-les-unions-des-metiers-du-parc-diawling-pour-favoriser-lamelioration-des-moyens-de-subsistance-des-communautes/)

6. Identify the capacity needs of local stakeholders to implement inclusive and sustainable income-generating initiatives, and identify capacity gaps that need to be addressed through the RBTDS capacity building strategy and action plan.

The document identifying the capacity needs of local stakeholders to implement inclusive and sustainable income-generating initiatives was produced and validated on March 6, 2024. https://rbtds.org/2024/03/06/restitution-des-etudes-sur-lidentification-des-besoins-des-parties-prenantes-pour-mettre-en-oeuvre-des-initiatives-generatrices-de-revenus-inclusives-et-durables-et-sur-les-chaines-de-valeur/

The UGT supported the income-generating initiatives by providing equipment and financing. Training sessions will also be held on:

- Local grain processing for women's groups in the commune of Ross Bethio, the Ndiael AIV, the commune of Gandon, the village of Thilla Boye, the commune of Gnith, and the commune of Ronkh, ( https://web.facebook.com/61563529470443/videos/621948507511184?locale=fr_FR)

- Fruit and vegetable processing for women's groups in the Barbarie language, Gueumbeul, and Mpal, (https://www.ndarinfo.com/%E2%80%8BReserve-de-Gueumbeul-Quarante-femmes-formees-sur-la-conservation-et-la-transformation-des-fruits-et-legumes_a39758.html);https://www.youtube.com/watch?v=m21UtePTJTQ https://web.facebook.com/photo/?fbid=122154432146450982&set=pcb.122154432464450982&locale=fr_FR,

- Soap and bleach production for women's groups on the outskirts of Diawling, the commune of Diama, the commune of Ross Bethio, and the Ndiael AIV.

https://web.facebook.com/photo?fbid=122154175742450982&set=pcb.122154176006450982; https://www.youtube.com/watch?v=o75pYl6sYzs

- Sustainable agricultural practices for women market gardeners on the outskirts of Diawling.

- Financial and administrative management of grassroots organizations for groups on the outskirts of Diawling, the commune of Mpal, and ecoguards and ecoguides from the central hubs of the RBTDS. https://www.youtube.com/watch?v=lwBxQaqDc1E&t=41s ; https://www.pnd.mr/actualites/le-projet-rbtds-appui-les-unions-des-metiers-du-parc-diawling-pour-favoriser-lamelioration-des-moyens-de-subsistance-des-communautes/

All of these training sessions were accompanied by the provision of inputs and equipment for processing local grains, fruits and vegetables, soap and bleach production, and market gardening, with the aim of sustaining the activities initiated with the project.

On the left bank, equipment for the establishment of two market gardening areas was provided to women from the RNCTT and to women from the outskirts of Dioudj. https://rbtds.org/2025/07/21/appui-a-la-communaute-de-la-reserve-naturelle-communautaire-de-tocc-tocc/

Three millet mills, four freezers, three tricycles, equipment for processing local grains and fruits and vegetables, chairs, tarpaulins, sound equipment, pots, and accessories were distributed to 30 women's groups on the left bank of the RBTDS. On the right bank, a large batch of solar-powered freezers and refrigerators, parasol tents, wire mesh, poultry waterers and feeders, hand-operated dusters, wheelbarrows, shovels, picks, pruning shears, and sprinklers will be donated to support market gardening and poultry farming activities. Five sewing machines will also be donated to support income-generating activities for the peripheral populations of Diawling.

Support is also provided to technical services, such as the canoe for the RNC Tocc Tocc, the canoe engine for the PNOD, computer equipment for the commune of Ndiago, air conditioners for the commune of Diama, the regional planning department of Saint Louis, and the Northern Parks and Reserves Information Office in Saint Louis.

Regarding microcredit, the management committee of the RBTDS Left Bank Credit Fund has granted 40 small loans of 500,000 CFA francs each, repayable over a period of six months, to organized groups within the RBTDS

https://rbtds.org/2024/10/16/assemblee-generale-fonds-de-dotation-du-credit-rbtds-saint-louis/

COMPONENT 3: SCIENTIFIC COOPERATION, KNOWLEDGE ACQUISITION AND SHARING, MONITORING AND ASSESSMENT OF ECOSYSTEMS

This component recognizes the importance of promoting an integrated problem-solving approach to addressing the challenges facing the RBTDS. By supporting knowledge acquisition, scientific cooperation, and information sharing among stakeholders, it aims to ensure that sustainability science is applied to improve the effectiveness of RBTDS management.

Assessment and Analysis of Results for Component 3

For this component, the planned activities are part of the achievement of the following results :

Result 3.1: Scientific cooperation is strengthened to improve data collection, analysis, and learning.

Result 3.2: The project's monitoring and evaluation system is in place.

The activities carried out are as follows :

1. Ensure a functional mechanism for cross-border data collection and information management

For this activity, an upgrading workshop on the monitoring and evaluation system was organized on the RBT premises.

The RBTDS research and monitoring master plan document has been under development since May 2024 https://rbtds.org/wp-content/uploads/2025/07/PLAN-DIRECTEUR-DE-SUIVI-ET-DE-RECHERCHE-DE-LA-RBTDS.pdf

2. Support collaborative and applied research and monitoring by members of the cross-border research network, as part of the RBTDS Research Plan

As part of this activity, the project has supported a number of students working on RBTDS issues.

08 students have worked on the following themes :

- Analysis of the ecological and socio-economic impacts of restoring the coastal ecosystems of the Saint Louis MPA.

- Study of the socio-economic contribution of tourism in the RBTDS.

- Contribution to knowledge of the specific habitat of Afro-tropical birds in the Senegal River Delta Biosphere Reserve: the case of the dwarf flaman.

- Bird hazard and rice farming : analysis of the governance of the red-billed worker population control system in the Senegal River Delta.

- Modalities of occupation of the lower Delta by dwarf flamingos : the case of the Diawling National Park.

- Contribution to the study of the ecology of the crowned crane.

- Bird conservation status and habitats in the Langue de Barbarie National Park.

- The protection of the Gambian armed goose and the use of pesticides in agriculture : the case of Dioudj.

3. Promoting cross-border knowledge exchange

Under this activity, the project works for cross-border knowledge exchange to foster collaboration, eliminate knowledge gaps and accelerate the development of effective solutions for the efficient management of RBTDS. The forms of cross-border knowledge exchange implemented include workshops, cross-border training courses and exchange visits.

During this period, RBTDS women producers took part in exchange visits :

- at the International Fair for Agricultural and Animal Products :

- at the Abidjan Convention COP 14 exhibition in Nouakchott

- at the Saint Louis Jazz Festival fair.

Constraints and lessons learned

The cross-border dimension of the project presents significant challenges, such as conflicting agendas of stakeholders and difficulties in accessing the project area during the rainy season (wintering).

The delay in making available funds requested in November 2024 and only received at the end of March 2025 and in May 2025, which had still not arrived by mid-July 2025, was a major constraint on the completion of certain planned activities.

GEF Core Indicators /Indicateurs de base du FEM

Please report on GEF core indicators that are relevant to your project using guidance provided by GEF on the implementation of the GEF-8 results measurement framework

Table 1. Eleven GEF Core Program Indicators / Onze indicateurs du programme de base du FEM

| Indicator # As per GEF portal | Indicator | Baseline | Project Target | Progress to date (from project start) | Mean of Verification |
| --- | --- | --- | --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management This indicator will be reported as the aggregate total of the following Sub-Indicators. - Terrestrial protected areas newly created - Terrestrial protected areas under improved management effectiveness | 0 ha | 100 000 ha | 83209 ha | The protected areas of the RBTDS are now experiencing an improvement in management efficiency with actors from the periphery who are actively involved in the management |
| 2 | Marine protected areas created or under improved management This indicator will be reported as the aggregate total of the following Sub-Indicators. - Marine protected areas newly created - Marine protected areas under improved management effectiveness |  | 51000 ha | 49000 ha | The marine protected areas of Saint Louis and Langue de Barbarie are developing reforestation and coastal protection actions with peripheral populations. |
| 3 | Area of land and ecosystems under restoration This indicator will be reported as the aggregate total of the following Sub-Indicators. - Area of degraded agricultural lands under restoration - Area of forest and forest land under restoration - Area of natural grass and woodlands under restoration - Area of natural grass and woodlands under restoration |  | 562 470 ha | 320367 | The central and buffer zones are being restored and the populations living in the vicinity are being supported to develop income-generating activities. The populations also intervene at the level of the management committees for the management of the sites. |
| 4 | Area of landscapes under improved practices (excluding protected areas) This indicator will be reported as the aggregate total of the following Sub-Indicators. - Area of landscapes under improved management to benefit biodiversity - Area of landscapes under third-party certification incorporating biodiversity considerations - Area of landscapes under sustainable land management in production systems - Area of High Conservation Value or other forest loss avoided - Terrestrial OECMs supported |  | 562470 ha | 558558 ha | Buffer and transition zones in the RBTDS are subject to sustainable practices |
| 5 | Area of marine habitat under improved practices to benefit biodiversity This indicator will be reported as the aggregate total of the following Sub-Indicators. - Fisheries under third-party certification incorporating biodiversity considerations - Large Marine Ecosystems with reduced pollution and hypoxia - Marine OECMs supported |  | 100 000 HA | 49000ha | The RBTDS is trying to put its marine fringe under sustainable management with improved practices |
| 6 | Greenhouse gas emissions mitigated This indicator will be reported through the following Sub-Indicators - Greenhouse gas emission mitigated in the AFOLU sector - Greenhouse gas emission mitigated outside of the AFOLU sector - Carbon sequestered or emissions avoided in the AFOLU sector (Direct) - Carbon sequestered or emissions avoided in the AFOLU sector (Indirect) - Emissions avoided outside AFOLU sector (Direct) - Emissions avoided outside AFOLU sector (Indirect) - Energy saved - Increase in installed renewable energy capacity per technology |  |  | N/A |  |
| 7 | Shared water ecosystems under new or improved cooperative management This indicator will be reported through the following Sub-Indicators - Level of Regional Legal Agreements and Regional Management Institutions to support its implementation - Level of Transboundary Diagnostic Analysis and Strategic Action Program (TDA/SAP) formulation and implementation - Level of National/Local reforms and active participation of Inter-Ministerial Committees - Level of engagement in IW LEARN through participation and delivery of key products |  |  | N/A |  |
| 8 | Globally over-exploited fisheries moved to more sustainable levels |  |  | N/A |  |
| 9 | Chemicals of global concern and their waste reduced This indicator will be reported through the following Sub-Indicators - Solid and liquid Persistent Organic Pollutants (POPs) removed or disposed (POPs type) - Quantity of mercury reduced - Hydrochlorofluorocarbons reduced/phased out - Countries with legislation and policy implemented to control chemicals and waste - Low-chemical/non-chemical systems implemented, particularly in food production, manufacturing and cities - POPs/Mercury containing materials and products directly avoided - Highly Hazardous Pesticides eliminated - Avoided residual plastic waste |  |  | N/A |  |
| 10 | Persistent organic pollutants to air reduced This indicator will be reported through the following Sub-Indicators - Countries with legislation and policy implemented to control emissions of POPs to air - Emission control technologies/practices implemented |  |  | N/A |  |
| 11 | People benefiting from GEF-financed investments This indicator will be reported as the aggregate total of the following Sub-Indicators. - Female - Male |  | 1800 | 1360 |  |

# Ratings and Overall Assessments  D. Notations et évaluations globales

| Role | YEAR Development Objective Progress Rating | YEAR Implementation Progress Rating |
| --- | --- | --- |
| Project Manager / Coordinator | Overall Assessment | Overall Assessment |
|  | Please provide justification for overall assessment | Please provide justification for overall assessment |
| IUCN Regional/Country Office (IA) | Overall Assessment | Overall Assessment |
|  | Please provide justification for overall assessment | Please provide justification for overall assessment |
|  | The RBTDS project, which will come to an end in two months, has made significant progress in strengthening cross-border cooperation and implementing conservation actions in the Senegal Delta Transboundary Biosphere Reserve. Major results include improved local governance, the creation of ecological restoration infrastructure and the development of monitoring tools shared between countries. Collaboration with national and regional stakeholders has been significantly strengthened, promoting ownership of the project. However, some delays related to the implementation of activities and administrative processes have limited the full achievement of certain indicators. Overall, the project is considered satisfactory, with a tangible impact on the resilience of ecosystems and communities, and provides a solid basis for a future consolidation and scaling-up project. |  |
| IUCN Global Thematic Programme (IA) | Overall Assessment | Overall Assessment |
|  | Please provide justification for overall assessment | Please provide justification for overall assessment |

# Adjustments

Please provide comments on delays this reporting period in achieving any of the following key project milestones: inception workshop, mid-term review, terminal evaluation and/or project closure.

Le retard de démarrage des activités du projet a entrainé le retard de l’examen à mi-parcours.

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines.

Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of the change that occurred in the textbox. You may attach supporting documents as appropriate within this PIR submission.

|  | Results framework |
| --- | --- |
|  | Components and cost |
|  | Institutional and implementation arrangements |
|  | Financial management |
| x | Implementation schedule |
|  | Executing Entity |
|  | Executing Entity Category |
|  | Minor project objective change |
|  | Safeguards |
|  | Risk analysis |
|  | Increase of GEF project financing up to 5% |
|  | Co-financing |
|  | Location of project activity |
|  | Other |

| Minor amendments | Change description |
| --- | --- |

# Implementation Progress

Please insert graph below showing cumulative disbursements on quarterly and yearly basis since project launch

Disbursements for the period from July 2022 to June 2023

Disbursements for the period from July 2023 to June 2024

Disbursements for the period from July 2024 to June 2025

| Cumulative Disbursements |  |
| --- | --- |
| Cumulative general ledger delivery against total approved amount (in Project Document) - % | % 3061009 USD |
| Cumulative general ledger delivery against expected delivery as of this year - % | % 817537,33 USD |
| Cumulative disbursement as of 30 June 2024 (note: amount to be updated in later August) | 2 243 471,67 USD |

| Key Financing Amounts |  |
| --- | --- |
| PPG Amount | USD |
| GEF Grant Amount | 3 061 009 USD |
| Planned Co-Financing Co-Financing to date | USD USD |

| Key Project Dates |  |
| --- | --- |
| PIF Approval Date | Octobre 2019 |
| CEO Endorsement Date |  |
| Project Document Signature Date (Project start date) | 04 Octobre 2021 |
| Date of Inception workshop (Project launch) | 09 Mars 2022 |
| Expected date of mid-term review | Octobre 2023 |
| Actual date of mid-term review | Février 2024 |
| Expected date of Terminal Evaluation |  |
| Original planned closing date | 30 Octobre 2024 |
| Revised Planned closing date | 30 Octobre 2025 |

Dates of Project Steering Committee / Board Meetings during reporting period (June to July)

LE 22 Janvier 2025

# Critical Risk Management

Please complete the table below (Only risk with High or Medium rating / level should be recorded) by using the information in the Project Risk register (excel file provided with PIR templates). If a project risk register has already been completed for the project, please provide any updates for High or Medium risk from this reporting period – e.g. changing in risk rating, risk owners or additional risk identified etc. in the table below.

| Risk Category | Risk description | Rating / Level (H, M) | Mitigation measures undertaken in this reporting period | Risk Owner | Updates / Changes |
| --- | --- | --- | --- | --- | --- |

Project overall risk rating (Low, Moderate, Substantial or High). Please see Annex – Ratings definition for guidance.

| 2022 rating (H, S, M, L) | 2023 rating (H, S, M, L) | Comments/reasons for the rating for 2024 and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| S | S | In 2024, the project made satisfactory progress in carrying out its activities. This coincided with the initial completion date, but since there were residual activities due to the delayed start, an extension was granted. |

# Gender

Progress in advancing Gender equality and women’s empowerment

Please note that all projects approved since GEF 6 are required to carry out a gender analysis and provide gender-responsive measures to address differences, identified impacts and risks, and opportunities through a Gender Action Plan (GAP) or equivalent.

Does this project specifically target woman or girls as direct beneficiaries?

Gender defines the social and cultural construction of roles, behaviors, expressions, and identities attributed to men and women, as well as the relationships between them. The RBTDS project specifically targets marginalized groups in the area, particularly women.

In case a gender analysis was not undertaken during project preparation (PPG), has it been carried out in this reporting period? If yes, what were the main findings? If an analysis during project design had been undertaken, but further updates have been carried out during the reporting period, please indicate this below. Please also report on additional site level gender analyses if they were undertaken during this reporting period.

A gender analysis was undertaken during project preparation and further developed during this reporting period. The analysis showed that women and vulnerable groups are disadvantaged in the area. Thus, in supporting stakeholders in the development of income-generating initiatives, the UGT favored them and 90% of the training sessions have targeted them.

Please describe progress in implementing the Gender Action Plan (GAP); you could also add the GAP in form of a GAP progress report as annex. Please also specify results achieved this reporting period through implementing gender-responsive measures.

At this stage of the project, the UGT has held meetings with stakeholders to plan and prioritize capacity-building activities, financial support, and material assistance. Women and vulnerable groups are the primary beneficiaries. There is a real impact in terms of awareness-raising.

Please report on gender-sensitive indicators and sex-disaggregated targets as established in the results framework

# Implementing the Stakeholder Engagement Plan

The GEF Stakeholder Engagement Policy Guidelines  requires that Agencies prepare a Stakeholder Engagement Plan to describe how Stakeholders will be engaged in the project, and means of engagement throughout the project/program cycle.  Agencies should include information on progress,

challenges and outcomes of stakeholder engagement in their annual Project Implementation

Reports.

Either provide the Stakeholder Engagement Plan and its respective progress report as annex or complete the below table by specifying the engagement strategies and achievements for the most important stakeholder groups. This can include demonstrating how different stakeholders were engaged in decisions on project governance (e.g. as member of the steering group), in the management or monitoring of the project or in programmatic activities. Forms of engagement include direct consultation or exchange with representative groups as well as indirect forms such as through media or other communication channels. Please also specify how the engagement is documented to provide evidence of such activities.

Please note that the data may be used for reporting to the GEF or IUCN web site, and for other internal and external knowledge and learning efforts. The global thematic programme involved should review and edit/elaborate on the information entered here. All projects must complete this section. Please enter N/A in cells that are not applicable to your project.

Information on progress, challenges and outcomes of Stakeholder Engagement

Civil society organisations

During the design of the project, consultations were held with stakeholders in Mauritania and Senegal. These consultations included meetings with the government ministries responsible for protected area management that form the core of the RBTDS and other stakeholders at national and regional levels. During the consultations, stakeholders were invited to share their thoughts on the environmental and social problems they face and to discuss the main obstacles to solving these problems through the RBTDS. At this stage of the project, civil society organisations such as NCD and BIDEV are taking part in the activities and often take the initiative by inviting the project's UGT to support them. Reforestation activities are carried out in communes such as Ngnith by organisations such as BIDEV AFRICA and AULAC, which are civil society organisations working to protect the environment.

Local communities

The local communities at the various sites within the RBTDS play an important role in the project. First, they are considered the primary beneficiaries of training sessions provided by the project, the provision of equipment and other support. All activities within the RBTDS are carried out with the target forms of participation of local communities. Individual participation in the activities implemented by the project is on a voluntary basis, within the framework of pre-existing groups that share common objectives with the project (“working to protect nature”). For the most arduous activities (such as invasive plant removal campaigns), the project provides for individual financial compensation. Community members participate in awareness-raising activities and are advocates for the proper maintenance of ecosystems, understanding the vision, objectives and strategies of the RBTDS, including: the state of governance and management systems; the values of natural ecosystems and priority environmental issues; the characteristics of current production systems; the identification of vulnerable groups likely to be impacted by the project; and the level of commitment of key stakeholders in the RBTDS process.

Indigenous Peoples

The ESMS Screening and the ESMS supervision mission have concluded that there are no indigenous people living in the project area.

Private sector

The private sector is an important part of the RBTDS. It plays an important role in decision-making concerning the preservation of ecosystems. The private sector has been called upon to participate in the development of the RBTDS MANAGEMENT PLAN, which is being drawn up in a participatory manner. The donors' round table is scheduled to take place before October, and the private sector will play an important role.

Other relevant stakeholders as identified in the projects’ Stakeholder Analysis

# Environmental and Social Safeguards

This section of the PIR describes the progress made towards complying with the Environmental and Social Management Plans or other safeguard tools, when appropriate. Note that this only applies to projects classified as moderate or high risk, not to low risk projects.

For reporting progress on the implementation of ESMS plans or tools, please either provide the ESMP Monitoring Table as annex (see ESMP guidance note and template) or complete the below table.

| Progress of implementing the Environmental and Social Management Plan (ESMP) or other safeguard tools |  |  |  |  |
| --- | --- | --- | --- | --- |
| Environmental and Social Risks | Risks identified by ESMS Screening or during any update of ESMP since project start | Actions taken during this FY; explain how you engaged with groups affected by the identified risks and the outcomes achieved | Are the measures considered sufficient? Are there any outstanding issues relevant for next FY? |
| Adverse gender-related impacts | While it is a fact that women have historically suffered from inequality in the project area including through discrimination in terms of allocation to land, lack of access to productive resources (e.g., financial resources, credit, land, labor, equipment), lack of access to information and technical expertise, facing obstacles in accessing water which results in their food security and livelihoods being particularly precarious. The project aims to promote greater gender equality through the implementation of socio-economic support activities that specifically target women's collectives in the RBTDS and is not expected to trigger gender risks. | The project ensured that women's roles are recognized and that they are included in decision-making processes. This has been confirmed during the E&S supervision mission in December 2024. Gender considerations have also be taken into account in the criteria used to prioritize inclusive and sustainable income-generating initiatives that contribute to the conservation and sustainable development objectives of local communities within the RBTDS. The project is working with traditional leaders to bring about a change in attitudes towards women's rights to land/resources and supports for greater representation of women in village land councils and other resource management structures. | To be continued as per project design In terms of GBV, the project management team (PMU) is aware of gender-based violence (GBV). Although no incidents have been reported to date in the context of the project, it is essential to ensure that the project's many subcontractors (mobilized to implement the various project activities (assessments, training, construction/rehabilitation of infrastructure, etc.) do not engage in acts of gender-based violence. Hence, it is recommended to conduct induction sessions on GBV and respect for fundamental human rights for project contractors and subcontractors. And to inform contractors and subcontractors of the existence of an internal grievance mechanism within the project that includes the handling of potential complaints related to GBV. |
| Risks of affecting vulnerable groups | The project was designed to have a positive impact on vulnerable groups by ensuring their representation in decision-making bodies and should not have a negative impact on vulnerable groups. Apart from the prism of gender and the intrinsic vulnerability of women in the communities, vulnerability is primarily understood in the project implementation area as economic vulnerability, which is measured at the household level rather than at the individual level. Vulnerability is not considered in the RBTDS area from an ethnic perspective. According to the local stakeholders consulted, the commonly recognized factors of economic vulnerability in the area are as follows: - No or limited access to land/farmland - Households headed by single women - Households headed by a sick and/or disabled and/or elderly person (unable to work) - Young women not yet living with a partner - Illiterate people / people with a low general level of education The project recognizes that equitable benefit sharing is an important consideration in the design of strategies to support income-generating activities, and will strive to avoid any potentially discriminatory strategies. | A process of ongoing engagement with the full range of identified local stakeholders (multiple interlocutors in each target community) ensures that activities do not discriminate against particular groups, especially women and economically vulnerable households. | The effective inclusion of vulnerable groups in decision-making bodies may require capacity-building or empowerment measures. Functional literacy courses could, for example, be considered for women's group |
| Risk of undermining human rights | There is a small risk of project activities to result in unjustified preferential treatment of individuals or groups in terms of access to resources or services provided by the project For logistical reasons (the extent of the project area of influence) and efficiency (maximizing the number of beneficiaries), the project primarily targets pre-existing groups of individuals (women's collectives, grassroots community organizations, etc.) that internally manage the allocation of resources made available to the project (training, equipment donations, etc.). On the one hand, it is possible that some of these resources may be captured by a small group of individuals within the targeted collectives, and on the other hand, individuals who are not members of these collectives, may not be able to benefit from the resources and services provided by the project. | The project is involved in selecting direct beneficiaries within the targeted groups (e.g. through strict definition of criteria for participation in activities, participation in the selection process), and ensures that participation in activities is not restricted to active members of the groups alone. | Measure will be continued |
| Community health, safety and security risks | Community conflicts: The project is not expected to inadvertently exacerbate or aggravate social tensions between or among communities. Balancing water needs is an important management issue within the RBTDS. Management strategies will be developed in a participatory manner, taking into account potential impacts. Their effects will be monitored and adjusted if necessary. Human wildlife conflict: Some Mauritanian nationals complain about the resurgence of warthogs and the damage they can cause (as well as threatening behavior towards young children), but this situation predates the project and should not be exacerbated by project activities, which, on the contrary, aim to protect certain resource areas valued by local communities (creation of new protected areas, installation of fences around market gardening areas, etc.). Risks of accidents: The activities promoted as part of the project are likely to generate risks for beneficiaries: use of electrical equipment for food processing (mills, juice presses, gas cookers, etc.), means of transport (canoes, tricycles, etc.), handling of hazardous products (e.g., soda for saponification). | During technical training courses on economic activities carried out by women, modules on health and safety are included and personal protective equipment (gloves, smocks, masks, etc.) is distributed to participants. The provision of canoes or motorized tricycles is systematically coupled with the distribution of safety equipment (helmets, life jackets, etc.). Support for the agricultural sector (women's market gardening) excludes the use of phytosanitary products that are dangerous for users and the environment; only agroecological practices and the use of bio-inputs are promoted in the training courses. | These preventive actions will be continued |
| Labour and working conditions | At the local community level, all individual participation in the activities implemented by the project is on a voluntary basis, within the framework of pre-existing groups that share common objectives with the project (“working to protect nature”). For the most arduous activities (such as invasive plant removal campaigns), the project provides for individual financial compensation. The project team's exposure to occupational health and safety risks is typical for this type of project: traveling in motorized vehicles on roads in varying conditions, working outdoors, presence of wildlife in the areas where activities are carried out, presence of infectious diseases common to the region (including malaria). There is no functioning health center in Bouhajra (the main place of residence of the PMU, on the Mauritanian side). Risk of child labour: It is possible that some women who practise salt farming on the Langue de Barbarie involve their children in the activity, which is known to be arduous and labour-intensive. | The project has put in place basic road safety rules, including wearing seat belts, observing speed limits and adjusting speed to the circumstances, avoiding driving after dark where possible, regular and thorough maintenance of vehicles and workplaces and residences, anticipating the need to stockpile drinking water and recharge communication devices in preparation for field activities. Regular monitoring demonstrated that the working condition for women employed in the artisanal salt industry in the RBTDS have greatly improved thanks to the project's support, including their incomes. Solar power lighting has been installed to improve their working conditions as they used to work in the dark in the early morning and even at dusk. They used whatever means they had available to light their workplace. Currently, around ten solar posts have been installed and provide lighting. No children work in this operation has been observed, except for those who occasionally accompany their parents and, in rare cases, during the holidays, just to find out what their parents do. Awareness-raising sessions on this issue have been organised when the opportunity arise, including induction sessions on respect for fundamental human rights for project stakeholders (child labour, gender-based violence), for example during the induction on the grievance settlement mechanism. | To be continued |
| Resource efficiency, pollution, wastes, chemicals | Emission: Combustion residues from fossil fuels (diesel generator) can be considered negligible at the project level. Pesticides: Water pollution caused by widespread use of pesticides in the RBTDS primarily concerns the large agro-industrial companies operating in the area. The use of these products by local populations in the context of subsistence farming is negligible or even non-existent. . | The project has installed ten solar posts lighting. The project prohibits the promotion/minimisation of the use of chemical inputs (plant protection products) in activities supporting the agricultural sector for local communities. |  |
| New risks emerged | n/a | n/a | n/a |

| ESMS Standards | Required management measures/plans (when standard triggered) | Actions taken during this FY – for each safeguard plan, please indicate if actions are on schedule; explainhow you engaged with groups affected by the identified risks and the outcomes achieved |  | Are the measures considered sufficient? Are there any outstanding issues relevant for next FY? |
| --- | --- | --- | --- | --- |
| Involuntary Resettlement & Access Restrictions ☐ yes ☒ no ☐ TBD | ☐ Resettlement Action Plan ☐ Resettlement Policy Framework ☐ Action Plan to Mitigate Impacts Access Restriction ☐ Access Restrictions Mitigation Process Framework ☐ Other: | The ESMS supervision mission has concluded that the standard is not triggered based on the draft versions of the local management plans developed as part of the project and the consultations with local stakeholders. As such the provision to develop an abbreviated Process Framework was removed. Rationale: No changes to the management plans for the core areas of the RBTDS are envisaged in the management plan produced for the entire RBTDS (result 1.1.2.), nor are any changes to the status of the transition areas. Strategies for the sustainable use of RBTDS resources, under outcome 2.2.1, are concentrated in the transition zones of the RBTDS, but are not yet available. Any restrictions proposed must in any case be the result of dialogue and compromise between stakeholders. On the basis of these discussions, these stakeholders could theoretically negotiate access rules and temporary restrictions (such as the establishment of new protected areas), but these would then be implemented on a voluntary and consensual basis. None of the local stakeholders interviewed expressed any intention to support proposals to restrict access by local populations, and women in particular, to land or natural resources, beyond the rules already in place in the core areas of protected areas. Under outcome 2.1.2, the project must finally produce and implement at least four local ecosystem and habitat restoration plans in two to four villages. The plans, which have not yet been finalised, do not include concrete measures to put an end to hypothetical unsustainable practices on communal land and related to water use (apart from those of large agro-industrial companies located on the outskirts of the reserve's central areas). The plans have yet to be validated by local stakeholders and translated into concrete actions, but any decision that could lead to restrictions on the use of resources will have to be developed collectively and accepted by those likely to be affected. The project's support for the teams responsible for managing the RBTDS core areas, particularly through the provision and/or improvement of their means of transport (boats), could in theory lead to increased monitoring of prohibited activities in the protected areas. But on the one hand, the management of core areas is theoretically outside the project's mandate, and on the other hand, the conservation teams, who live alongside and interact daily with representatives of local communities and community eco-guards, have shown no intention of stepping up enforcement of activities, focusing instead on preventive and ongoing awareness-raising efforts, regardless of the protected area in question. According to PRODOC, abuses are primarily reported by the user communities themselves rather than being detected during surveillance activities by the authorities. |  | The grievance mechanism will enable any cases of economic displacement caused by the project to be dealt with quickly. As precautionary measure, the project will ensure that meetings and consultation workshops of the stakeholders who will be involved in the operationalisation of local management plans or strategies for the sustainable use of resources are properly document (e.g. signing in of participants, systematic drafting and dissemination of meeting minutes, signing of minutes by stakeholders in the event of decisions that commit them). Only this documentation will be able to justify that potential restrictions on use or changes to access rules are taken in consultation with the users of these resources (voluntary, appropriate decision-making based on the informed consensus of all rights holders concerned). |
| Indigenous Peoples ☐ yes ☒ no ☐ TBD | ☐ Indigenous Peoples Plan ☐ Indigenous Peoples Planning Framework ☐ Other: | Not applicable |  | Not applicable |
| Cultural Heritage ☐ yes ☒ no ☐ TBD | ☐ Chance Find Procedures ☐ Other: | There is no proven risk of damage to cultural resources, and hypothetical access restrictions are not expected to have a negative impact on cultural practices. According to Robert Vernet (1991), who studied Mauritania for several decades, there are no prehistoric archaeological sites in the Senegal Delta. The archaeological heritage is therefore mainly recent and of limited scientific interest. Burial sites are generally respected by communities; however, tourists loot medieval pottery shards, fishing weights and other archaeological remains outside the core areas. The authorities responsible for protected areas actively discourage such interventions, but their enforcement capabilities are limited. No new infrastructure is planned as part of the project, with the possible exception of small-scale economic infrastructure (food processing workshop, chicken coop), which will be built exclusively within already urbanised areas (village concessions). |  | Not applicable |
| Biodiversity & Sustainable Use Natural Resources ☐ yes ☐ no ☐ TBD | ☐ Pest Management Plan ☐ Other: | The Standard has not been triggered by the ESMS Screening. Additional cinclusions from the ESMS supervision mission: Invasive species: It was reaffirmed during project preparation phase that no species would be introduced or transferred. On the contrary, the project will strive to combat existing invasive species as part of the RBTDS management strategies: -Reforestation campaigns using species already present in the RBTDS (mangrove species, casuarina trees) -Support for market gardening does not involve the introduction of species other than those already cultivated in the area Changes water flow: The project aims to promote the rewetting of degraded areas (catchment areas selected for the implementation of local management plans), where positive results can be expected in terms of biodiversity and improved provision of ecosystem services to vulnerable groups. Any diversion or intervention on water flows will aim to mimic the rhythms, extent, heights and duration of natural floods perceived as positive by local users (with the exception of agribusiness promoters). The project plans to work closely with OMVS to reduce the negative impacts of dams and agricultural production activities. Risk of migration to the area risk: The possibility of a massive influx of transhumant herders from outside the RBTDS into the area in the event of a severe drought at the sub-regional level is clearly identified as a major risk to natural ecosystems (particularly on the Mauritanian side). |  | While an influx of migration hasn’t been observed, the risk continues to be monitored |
| ESMS Risk Category (as per ESMS Screening) |  |  | ☐ Low Risk ☒ Moderate Risk ☐ High Risk |  |  |
| Have findings during implementation triggered any changes to the ESMS Risk Category? If yes, explain the issues and justification for the new rating. |  |  | Because risks of livelihood losses due to Access Restrictions has not been confirmed, the standard is not triggered. As this has figured as the main risk during ESMS screening supporting the classification as moderate risk, the project is now re-classified as low risk project. |  |  |
| List all risk issues that are now rated as high risk (if any) |  |  | Not applicable |  |  |
| Has a list of relevant host country regulations on environmental and social matters been established? What is the status of the project’s compliance with the applicable laws and regulations? |  |  | Full compliance |  |  |
| In case any changes of regulations have occurred since project design, have these changes been reflected in project implementation? |  |  | Not applicable |  |  |

In addition, please indicate whether any grievances as per IUCN and GEF ESS policies have been received during this reporting period. If yes, please answer the below questions and attach the grievance log as annex in order to describe status and progress of the case. The latter should also be done in case grievances had been received in earlier reporting period.

Please explain the grievance

The UGT has not yet received any formal grievances during this reporting period.

Please indicate how it is being/has been addressed

N/A

# Knowledge Management

Knowledge activities / products (when applicable), as outlined in Knowledge Management Approach approved at CEO Endorsement / Approval during this reporting period.

Does the project have a knowledge management strategy? How does the project collect, document and share good practices? Please list relevant good practices from this year that can be learned and shared from the project.

The knowledge management mechanism takes the form of exchange visits between the populations of the two shores, and participation in trade activities such as fairs. Women producers from the RBTDS took part in two trade meetings and in COP 14 in Nouakchott to exchange views with other women producers. Good practice also includes exchange visits between stakeholders from different sites and from either side of the border on issues relating to ecosystem restoration and natural resource management. https://web.facebook.com/61563529470443/videos/1633523733975353?locale=fr_FR https://rbtds.org/2025/05/22/side-event-cop-14-de-la-convention-dabidjan-a-nouakchott-date-le-22-mai-2025-de-15h-a-17h-organise-par-le-parc-national-du-diawling/ https://web.facebook.com/photo/?fbid=122161327904450982&set=pcb.122161328114450982&locale=fr_FR

Does the project have a communication strategy? Please provide a brief overview of the communications successes and challenges this year.

The project's communication strategy has been developed and validated since 2023. The UGT has produced 1,000 copies of the RBTDS atlas prepared between 2024 and 2025. This is a document for sharing knowledge on the ecological, economic and tourism potential of the RBTDS. The UGT, in collaboration with the project's implementing agencies, organised the RBTDS days, which were a great success in terms of communication, with the presence of high-level authorities such as the ministers responsible for the environment in the two countries and the governors of the Saint Louis region and the wilaya of Trarza, as well as technical and financial partners involved in preserving the environment.

Communication material

Please provide a list of publications, project website, project page on the IUCN website, any other facebook, twitter, flickr or youtube account related to the project, as well as hyperlinks to any media coverage of the project, for example stories written by an outside source. Please upload any supporting files, including photos, videos, stories, and other documents.

www.rbtds.org https://web.facebook.com/profile.php?id=61563529470443 https://www.instagram.com/rbtds_officiel?igsh=ajl2M21jem40dzBu

Lessons learned

Please share any particular lessons learnt in the context of project implementation (e.g. successfully tested tools, unexpected positive or negative impacts) and/or lessons learnt regarding one of your key outcomes

As a lesson learned, the project's GTU has succeeded in using communication events to remobilise stakeholders in the RBTDS in their commitment to ecosystem restoration and transboundary cooperation. The RBTDS Management Plan, which is an important management tool, was drawn up in a participatory manner with most of the stakeholders. (http://www.environnement.gov.mr/fr/index.php/accueil/actualite/554-adoption-du-plan-de-gestion-de-la-reserve-de-biosphere-transfrontiere-du-delta-du-fleuve-senegal) ; https://bacomab.org/actualites/atelier-de-concertation-pour-la-realisation-du-plan-de-gestion-de-la-rbtds/ ) https://rbtds.org/wp-content/uploads/2025/07/PLAN-DE-GESTION-DE-LA-RBTDS.pdf We can now consider that the communication strategy has enabled the RBTDS's stakeholders to rally around its vision. https://www.youtube.com/watch?v=9J7xu79ADLE https://www.youtube.com/watch?v=A-KftfqqzFA ; https://www.youtube.com/watch?v=Kptxrghw5wc&t=82s Stakeholders recognise themselves in the RBTDS and integrate it into most ecosystem re storation activities. https://web.facebook.com/photo?fbid=122167426352450982&set=pcb.122167426820450982&locale=fr_FR, https://web.facebook.com/photo/?fbid=122167423868450982&set=pcb.122167425584450982&locale=fr_FR https://web.facebook.com/photo?fbid=122167456388450982&set=pcb.122167456766450982&locale=fr_FR https://www.youtube.com/watch?v=zD0qis5QWKY&t=49s https://web.facebook.com/61563529470443/videos/1190891745655871?locale=fr_FR https://web.facebook.com/photo/?fbid=122158965308450982&set=pcb.122158965776450982&locale=fr_FR https://rbtds.org/2023/08/20/visite-dechange-lancement-camp-de-reboisement-filao-et-mangrove-dans-le-parc-national-de-la-langue-de-barbarie/ - https://rbtds.org/2024/09/26/week-end-de-reboisement-a-ngnith/; The UGT supported the development of these sectors by providing a set of equipment to stakeholders. For the fishing sector, around ten solar streetlights and fermentation tanks were distributed to women's processing groups on the outskirts of the Saint Louis MPA. A batch of equipment consisting of canoes, nets, hooks, gloves, fishing gear, drying keys, and three tricycles was distributed to artisanal fishermen on the outskirts of Diawling. (https://rbtds.org/) (https://web.facebook.com/photo?fbid=122163638696450982&set=pcb.122163639824450982&locale=fr_FR) ; https://www.pnd.mr/actualites/le-projet-rbtds-appui-les-unions-des-metiers-du-parc-diawling-pour-favoriser-lamelioration-des-moyens-de-subsistance-des-communautes/ ; https://rbtds.org/2025/06/24/remise-dun-lot-de-materiels-destines-aux-groupements-et-cooperatives-de-femmes-au-niveau-de-la-commune-de-diama-de-la-zone-des-trois-marigot-de-la-peripherie-du-parc-national-des-oiseaux-du/ https://web.facebook.com/photo?fbid=122167426352450982&set=pcb.122167426820450982&locale=fr_FR, https://web.facebook.com/photo/?fbid=122167423868450982&set=pcb.122167425584450982&locale=fr_FR Support for income-generating initiatives and value chains has enabled local communities to boost their economic activities. https://web.facebook.com/61563529470443/videos/pcb.122158886030450982/1217373376596334) https://web.facebook.com/61563529470443/videos/pcb.122158886030450982/1376909703628523) https://www.youtube.com/watch?v=r0KsxYXpIGs - https://www.youtube.com/watch?v=lwBxQaqDc1E&t=66s) - (https://www.youtube.com/watch?v=b4oo9vU1IB4) - (https://www.youtube.com/watch?v=WulXIq5bjJw) https://rbtds.org/2024/01/05/formation-des-parties-prenantes-de-la-rbtds-sur-les-techniques-didentification-des-oiseaux-deau-et-sur-le-remplissage-des-fiches-de-collectes-du-denombrement-international-des-oiseau/ https://www.youtube.com/watch?v=5JSBH3OTthg&t=55s) https://www.youtube.com/watch?v=o75pYl6sYzs https://web.facebook.com/reel/1819602075268468?locale=fr_FR (https://rbtds.org/2024/01/05/formation-des-parties-prenantes-de-la-rbtds-sur-les-techniques-didentification-des-oiseaux-deau-et-sur-le-remplissage-des-fiches-de-collectes-du-denombrement-international-des-oiseau/) https://rbtds.org/2024/04/16/focus-sur-les-technologies-modernes-comme-outils-essentiels-de-gestion-au-niveau-des-aires-protegees-zones-centrales-de-la-rbtds/ https://web.facebook.com/photo/?fbid=122167397306450982&set=pcb.122167398350450982&locale=fr_FR (https://www.youtube.com/watch?v=9J7xu79ADLE) (https://www.youtube.com/watch?v=DPM2aJOamDM) https://www.youtube.com/watch?v=m21UtePTJTQ https://www.youtube.com/watch?v=MA-1c_d0a0Y) https://www.facebook.com/100094881662129/posts/formation-des-%C3%A9coguides-de-la-zone-du-parc-diawling-sur-les-techniques-de-guidag/417444978094888/ https://web.facebook.com/photo/?fbid=122167397306450982&set=pcb.122167398350450982&locale=fr_FR https://www.youtube.com/watch?v=DPM2aJOamDM https://www.youtube.com/watch?v=m21UtePTJTQ https://www.youtube.com/watch?v=MA-1c_d0a0Y The UGT succeeded in securing the presence of the Senegalese and Mauritanian ministers responsible for the environment, as well as technical and financial partners, at the RBTDS days, which brought together more than 200 people from a variety of backgrounds to talk about the positive impacts of the biosphere reserve, to exhibit local products with added economic value, and to take part in a scientific panel discussion on important subjects relating to the future of the RBTDS. http://www.environnement.gov.mr/fr/index.php/accueil/actualite/547-celebration-de-la-2eme-edition-des-journees-de-la-reserve-de-biosphere-transfrontiere-du-delta-du-fleuve-senegal) (https://www.linformation.net/node/6726

Communicating impact

Tell us the story of the project focusing on how the project has helped to improve people’s lives and biodiversity and how it contributed to the target(s) pledged through internal conventions (UNCCD LDN, UNFCCC NDCs, CBD NBSAPs, SDGs, etc) and/or national policies (The text will be used for IUCN Corporate Communications, the IUCN-GEF web-site, and/or other internal and external knowledge and learning efforts) Please also note you can share your success story and solution on the IUCN PANORAMA web platform. This will allow for knowledge retention and dissemination of project outcomes and success factors.

This project promotes cooperation for better management and restoration of ecosystems in the Senegal River Delta between Mauritania and Senegal. It provides an essential means for establishing cross-border dialogue on water and environmental management issues and facilitates the implementation of coordinated actions across the RBTDS's multiple land-use zones. Like any functional biosphere reserve, the RBTDS has functioning governance and management bodies. The Transnational Steering Committee (CTO), the Scientific and Technical Committee (CST), and two National Committees (NC) hold regular meetings. The UGT, which acts as the management body, undertakes communication activities with all stakeholders and regularly organizes site visits to assess the state of the ecosystems and the living standards of the local populations. To date, the project has produced approximately ten framework documents that guide its actions. By 2024, restoration activities had affected more than 200 hectares, including reforestation and clearing of typha and other plants that colonize the RBTDS's water bodies. Training sessions on income-generating professions reached nearly 700 women who had no fixed income. A large batch of equipment was provided to RBTDS groups, enabling them to continue their activities initiated with the project. The fishing, livestock, and salt farming sectors are now supported with equipment for their development. Scientific research is carried out with the support of students working on topics of interest to the RBTDS. To date, eight students have been supported to work on biodiversity, restoration activities, and ecotourism in the RBTDS.

What is the most significant change that has resulted from the project this reporting period?

The renewed interest that stakeholders have in the RBTDS is the most important change noted as a result of the project. The functionality of the RBTDS governing bodies is positively appreciated. Stakeholder participation in RBTDS activities is effective. Local people are increasingly coming to the RBTDS to show their interest in restoration activities. Within the framework of the monitoring and research master plan, the scientific community has invested a great deal of time and effort in proposing relevant research themes on the problems of the RBTDS.

# Annex -  Ratings definitions

Implementation Progress Ratings

Highly Satisfactory (HS): Implementation of all components is in substantial compliance

with the original/formally revised implementation plan for the project. The project can be presented as “good practice”.

Satisfactory (S): Implementation of most components is in substantial compliance with the original/formally revised plan except for only a few that are subject to remedial action.

Moderately Satisfactory (MS): Implementation of some components is in substantial compliance with the original/formally revised plan with some components requiring remedial action.

Moderately Unsatisfactory (MU): Implementation of some components is not in substantial compliance with the original/formally revised plan with most components requiring remedial action.

Unsatisfactory (U): Implementation of most components is not in substantial compliance with the original/formally revised plan.

Highly Unsatisfactory (HU): Implementation of none of the components is in substantial compliance with the original/formally revised plan.

Global Environment Objective/Development Objective Ratings

Highly Satisfactory (HS): Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice”.

Satisfactory (S): Project is expected to achieve most of its major global environmental objectives, and yield satisfactory global environmental benefits, with only minor shortcomings.

Moderately Satisfactory (MS): Project is expected to achieve most of its major relevant objectives, but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environment benefits.

Moderately Unsatisfactory (MU): Project is expected to achieve its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives.

Unsatisfactory (U): Project is expected not to achieve most of its major global environment objectives or to yield any satisfactory global environmental benefits

Highly Unsatisfactory (HU): The project has failed to achieve, and is not expected to achieve, any of its major global environment objectives with no worthwhile benefits.

Development/Adaptation Objective Ratings (For LDCF/SCCF/GCF Adaptation)

Highly Satisfactory (HS): Project is expected to achieve or exceed all its major development/adaptation objectives, and yield substantial adaptation benefits, without major shortcomings. The project can be presented as “good practice”.

Satisfactory (S): Project is expected to achieve most of its major development/adaptation objectives, and yield satisfactory adaptation benefits, with only minor shortcomings.

Marginally Satisfactory (MS): Project is expected to achieve most of its major relevant development/adaptation objectives, but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major development objectives or yield some of the expected adaptation benefits.

Marginally Unsatisfactory (MU): Project is expected to achieve its major development/adaptation objectives with major shortcomings or is expected to achieve only some of its major adaptation objectives.

Unsatisfactory (U): Project is expected not to achieve most of its major development/adaptation objectives or to yield any satisfactory adaptation benefits.

Highly Unsatisfactory (HU): The project has failed to achieve, and is not expected to achieve, any of its major development/adaptation objectives with no worthwhile adaptation benefits.

Risk ratings

Risk ratings will assess the overall risk of factors internal or external to the project that may affect implementation or prospects for achieving project objectives. Risks of projects should be rated on the following scale:

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

| The table below illustrates how the risk categories used by GEF and IUCN align with one another. |  |
| --- | --- |
| GEF risk categories | IUCN risk categories |
| Climate | External |
| Environment & Social | Part of ESMS risk assessment |
| Political and Governance | External |
| Macro-economic | External |
| Strategies and policies | Strategic |
| Technical design of project or program | Operational |
| Institutional capacity for implementation and sustainability | Operational |
| Fiduciary: financial management and procurement | Finance |
| Stakeholder engagement | Part of ESMS risk assessment |
| Other | People management; Legal / Compliance; Information systems |
| Financial risks for NGI projects | N/A |

| The table below illustrates how the risk rating/level used by GEF and IUCN align with one another. |  |
| --- | --- |
| GEF risk rating / level | IUCN risk rating / level |
| High | High |
| Substantial | High |
| Moderate | Medium |
| Low | Low |

https://www.youtube.com/watch?v=vEY_z7ThW5I

This section will use the scale used by the GEF and outlined in Annex L of this document: 1) Highly satisfactory, 2) Satisfactory, 3) Moderately Satisfactory, 4) Moderately Unsatisfactory, 5) Unsatisfactory, 6) Highly Unsatisfactory

Idem

This section will use the scale used by the GEF and outlined in the Annex of this document: 1) High Risk, 2) Substantial Risk, 3) Moderate Risk, 4) Low Risk

This section will use the scale used by the GEF and outlined in Annex of this document: 1) Highly satisfactory, 2) Satisfactory, 3) Moderately Satisfactory, 4) Moderately Unsatisfactory, 5) Unsatisfactory, 6) Highly Unsatisfactory

Idem

IUCN risk categories: Strategic, Financial, People management, Operational, Legal/Compliance, Information systems, External

Stakeholder Engagement Policy Guidelines (SD/GN/01), December 20, 2018

# https://www.iucn.org/sites/dev/files/esms_esmp_guidance_note_and_template.docx

Add n/a if the respective risk issues has neither been identified during the ESMS screening nor in any update of the ESMP.

Please check the respective box to indicate the decision at Screening stage: whether a standards has been triggered or not, or the decision was deferred to the implementation phase. If the latter, please explain the status of this decision.