FAO/GEF PROJECT DOCUMENT

| Project Title: Enhancing and bridging knowledge gaps in Sri Lanka's NDC implementation of AFOLU sector for Enhanced Transparency Framework (ETF) |  |
| --- | --- |
| FAO Project symbol: | GCP/SRL/074/CBT |
| GEF Project ID: | 10040 |
| Recipient Country(ies): | Sri Lanka |
| Executing partners: | Ministry of Mahaweli Development and Environment (Climate Change Secratariate), Ministry of Tourism Development, Wildlife and Christian Religious Affairs (Department of Wildlife), Mnistry of Agriculture and Ministry of Land |
| Expected EOD (Starting Date): | September 2019 |
| Expected NTE (End Date): | August 2021 |
| Contribution to FAO’s Strategic Framework: (Indicate as appropriate) | - Strategic Objective 2: Increase and improve provision of goods and services from agriculture, forestry, and fisheries in a sustainable manner. - Outcome 204: Stakeholders make evidence-based decisions in the planning and management of the agricultural sectors and natural resources to support the transition to sustainable agricultural sector production systems through monitoring, statistics, assessment, and analysis. - Regional initiatives: Regional Rice Initiative, Climate Change, One Health, Blue Growth |
| Contribution to GEF TF Focal Area Strategic Objectives and Programs: | - OI3: MRV systems for emissions reductions in place and reporting verified data - OI7: Number of countries meeting convention reporting requirements and including mitigation contributions |
| Environmental and Social Risk Classification | low risk |
| Gender Marker | G0 G1 G2a G2b |
| Financing Plan: GEF allocation: Co-financing: | USD 863,242 GEF Trust Fund USD 1,596,000 Min. of Mahaweli Development and Environment (in-kind) USD 200,000 FAO (in-kind) |
| Sub-total co-financing | USD 1,796,000 |
| Total budget: | USD 2,659,442 |
| # Executive Summary This project strengthens Sri Lanka’s capacities for measurement, reporting, and verification (MRV) in the agricultural and land-use sub-sector in order to help Sri Lanka to meet its commitments associated with the Enhanced Transparency Framework (ETF) of the Paris Agreement under the United Nations Framework Convention on Climate Change (UNFCCC). As a Non-Annex I party to the Paris Agreement under the UNFCCC, Sri Lanka has submitted Nationally Determined Contributions (NDC) to help keep climate change below a global rise of two degrees Celsius. As part of the ETF, Sri Lanka has committed to certain protocols for MRV regarding progress toward its NDC targets. This project avails of multiple sources of funding—including from the Global Environment Facility’s (GEF) Capacity-building Initiative for Transparency (CBIT)—to strengthen Sri Lanka’s MRV systems within the agriculture, forestry, and other land-uses (AFOLU) sector in order to fulfil Sri Lanka’s ETF commitments and improve the quality of climate-related decision-making at international, national, provincial, district, and local/ village levels. Sri Lanka’s estimated total emissions as 12,588.9 Gg CO2e from all sectors, whereas the agriculture sub-sector contributes 4709.4 Gg CO2e These estimates come from GHG estimation of second National Communication of Sri Lanka to UNFCCC. Sri Lanka also reported LUCF CO2 Removals as -6254.0 Gg CO2e. Moreover, the AFOLU sector features prominently in Sri Lanka’s NDC and predominates the section on climate-change adaptation, though strategies and capacities for adaptation-related monitoring and reporting (M&R) significantly lag behind those for mitigation-related MRV. It was widely agreed during stakeholder consultation meeting that Climate change adaptation NDC needs to be enhanced and updated. However, gaps remain in Sri Lanka’s AFOLU MRV systems, for example, with respect to (i) establishment of nationally specific emissions factors and activity data (for 26 guidelines of IPCC Tier 2 reporting for key categories), (ii) full determination of key sub-categories, (iii) uncertainty estimates, (iv) establishment of metadata and quality-control protocols, (v) reliable measurement of activity data for key IPCC AFOLU categories, (vi) feasibility studies for adaptation-related interventions, (vii) prioritization and specification of adaptation-related metrics, and (viii) ensuring the financial and operational sustainability of MRV initiatives. Closing these gaps requires addressing some important barriers, namely: - Inadequate institutional arrangements to support the transition to ETF; - Inadequate technological and technical capacities for mitigation-related MRV; and - Inadequate technological and technical capacities for adaptation-related M&R. This project is structured into three components to address these barriers. Component 1. Institutional arrangements to coordinate preparation of ETF reports for agriculture, land-use and other relevant sectors enhanced - 1.1 Institutional arrangements coordinating information and data collection from the agriculture and land use sectors into ETF processes and reports enhanced. - 1.1.1 Coordination mechanism established/strengthened integrating relevant authorities from the agriculture and land use sector into national UNFCCC reporting processes. - 1.1.2. Assessment prepared to assess institutional, data collection, analysis and reporting capacity gas and needs for meeting ETF requirements with specific focus on the priority NDC actions for the agriculture and land-use sectors. - 1.1.3. National ETF monitoring and reporting roadmap for the agriculture and land-use sectors prepared and adopted - 1.1.4. Capacity developed to clarify measurement and reporting of key NDC information (baselines, Business-As-Usual targets) and support provided for ETF reporting in the agriculture and land-use sectors. - 1.1.5. Sri Lanka's engagement strengthened in the agriculture and land-use sectors with international transparency-related processes under the UNFCCC. - 1.2 Best practices on ETF reporting processes, information gathering, system infrastructure, methodologies in the agriculture and land-use sectors disseminated to relevant priority sectors (e.g. energy, industry/trade, transportation). - 1.2.1 Multi-sectoral coordination mechanism strengthened integrating relevant authorities into national UNFCCC reporting processes. - 1.2.2 ETF lessons learned from agriculture and land-use sectors monitored, captured, scaled up and shared to enhance wider national reporting. - 1.2.3 Peer exchange program on transparency activities established for relevant priority sectors. Component 2. Capacity to assess and report emissions and removals from land-use sectors and to design and monitor related emission reduction activities strengthened and adaptation capacity in agriculture sector enhanced” - 2.1. Reporting on inventories of emissions sources and sinks and mitigation activities from agriculture and land-use sectors strengthened - 2.1.1. Regular and systematic documentation and archiving process established to ensure accuracy and sustainability of the inventory, including quality assurance and quality control, in the agriculture and land-use sectors - 2.1.2. GHG Information Management System (IMS) and infrastructure for agriculture and land-use sectors upgraded (interface w/ 3.1.3) - 2.1.3. Capacity and system hardware developed for relevant institutions at different levels to adopt and mainstream latest tools and methodologies to develop country-specific emission factors (EFs), improve activity data (AD) and better quantify the impact of mitigation policy measures in the agriculture and land-use sectors (inter-face w/ 3.1.4). - 2.1.4. National/sectoral reports prepared and submitted on inventory of emissions sources and sinks and emissions reduction activities from agriculture and land-use sectors consistent with latest UNFCCC guidance Component 3. Capacity to monitor and report adaptation activities in agriculture and land-use sectors strengthened - 3.1. Strengthened capacity to measure climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors. - 3.1.1. Measurement framework developed for climate-change impacts, vulnerabilities, and adaptation-related activities prioritized in the NDC for the agriculture, forestry and land-use sectors. - 3.1.2. Information technology systems upgraded to integrate and analyze adaptation-related data. - 3.1.3. Capacity and technology upgraded in relevant institutions to strengthen M&R for adaptation priorities identified in the NDC for the agricultural and land-use sectors. (Coordinates with 2.1.3.) - 3.1.4. Relevant measures validated and piloted for adaptation priorities identified in the NDC for the agricultural and land-use sectors. The primary execution partner for the project will be Climate Change Secretariat under the Ministry of Mahaweli Development and Environment. Several other execution partners will deliver substantial portions of the project’s outputs, with the aim of transitioning to sustainable, scalable, long-term operational arrangements for climate-related MRV in the AFOLU sector. |  |

# Table of Contents

Executive Summary	2

Table of Contents	5

List of Acronyms and Abbreviations	7

Section 1:  Project Rationale	10

1.1.	Context Analysis	10

1.1.1.	Global context	10

1.1.2.	National context	14

1.1.3.	AFOLU priorities in Sri Lanka’s Nationally Determined Contribution	19

1.2.	Status of MRV for Climate Change in the AFOLU Sector	22

1.2.1.	Gaps and barriers identified in previous reports	22

1.2.2.	Gap assessments during the project-preparation phase	26

1.2.3.	Differences between mitigation and adaptation capacities	30

1.2.4.	Baseline ratings for CBIT tracking tool	30

1.3.	Project Description	31

1.3.1.	Project objective and approach	31

1.3.2.	Component 1	32

1.3.3.	Component 2	39

1.3.4.	Component 3	42

1.4.	Alignment and Strategic Fit	49

1.4.1.	Alignment with national priorities	49

1.4.2.	Alignment with GEF priorities	50

1.4.3.	Alignment with FAO priorities	50

1.5.	Institutional Stakeholders and Baseline Initiatives	51

1.5.1.	Institutional programs	51

1.5.2.	Projects	53

1.5.2.1.	GEF Projects	53

1.5.2.2.	Other UN/MDA projects	53

Section 2:  Project Governance and Operational Arrangements	55

2.1.	Stakeholder Engagement	55

2.2.	Project Governance	55

2.2.1.	Operational mode	55

2.2.2.	Institutional framework	57

2.2.3.	FAO’s comparative advantages	57

2.2.4.	Priorities for the inception phase	59

2.2.5.	Grievance mechanism	59

2.2.6.	Disclosure	59

2.2.7.	Planning and financial management	59

2.2.8.	Financial plan (by components, outcome and co-financiers)	59

2.2.9.	GEF Contribution	60

2.2.10.	Government Contribution	60

2.2.11.	FAO Contribution	60

2.2.12.	Financial management of and reporting on GEF resources	60

2.3.	Procurement	62

2.4.	Monitoring and Evaluation (M&E)	62

2.4.1.	Monitoring and reporting	62

2.4.2.	Evaluation	64

2.4.3.	Summary of M&E Arrangements	65

2.4.4.	Communication	66

2.5.	Risk Management	67

2.5.1.	Incorporation of lessons learned	67

2.5.2.	Risks and risk-mitigation measures	69

Section 3:  Innovation, Potential for Scaling-up, and Sustainability	71

3.1.	Innovation	71

3.2.	Potential for Scaling-up	72

3.3.	Sustainability	72

3.3.1.	Capacity development	73

3.3.2.	Decent rural employment	74

3.3.3.	Environmental sustainability	74

3.3.4.	Gender equity	75

3.3.5.	Indigenous groups and people	75

List of Appendices and Annexes	76

Appendix 1:  Results Matrix	77

Appendix 2:  Work-plan	82

Appendix 3:  Budget	89

Appendix 4.  Project Steering Committee’s Terms of Reference and Provisional Membership	92

Appendix 5.  Technical Working Group’s Terms of Reference and Proposed Membership	96

Appendix 6.  Abbreviated Terms of Reference for Members of the Project Staff	99

Appendix 7.  Co-financing Letter - Ministry of Mahaweli Development and Environment	105

Appendix 8.  Co-financing Letter - FAO	106

# List of Acronyms and Abbreviations

| Abbreviation | Description |
| --- | --- |
| °C | Degrees Celsius (centigrade) |
| AFOLU | Agriculture, forestry, and other land-use |
| AWP/B | Annual work-plan and budget |
| BH | Budget Holder |
| BUR | Biennial Update Report (under UNFCCC) |
| C | Carbon |
| CBIT | Capacity-building Initiative for Transparency (via GEF) |
| CBNRM | Community-based natural resource management |
| CCA | Climate-change adaptation |
| CCM | Climate-change mitigation |
| CCS | Climate Change Secretariat |
| CH4 | Methane |
| CO2 | Carbon dioxide |
| CO2e | Carbon dioxide equivalent in global warming potential |
| CSO | Civil society organization |
| DAPH | Department of Animal Production and Health |
| DoA | Department of Agriculture |
| DEX | Direct execution |
| DCS | Department of Census and Statistics |
| DFAR | Department of Fisheries and Aquatic Resources |
| ETF | Enhanced Transparency Framework (under the Paris Agreement and UNFCCC) |
| ExACT | Ex-ante Carbon-balance Tool |
| FAO | Food and Agriculture Organization of the United Nations |
| FCPF | Forest Carbon Partnership Facility |
| FD | Forest Department of Sri Lanka |
| GEF | Global Environment Facility |
| GEF-6 | Sixth funding cycle for GEF’s System of Transparent Allocation of Resources (STAR) (1 July 2014 – 30 June 2018) |
| Gg | Gigagram (1 billion grams; 1 kiloton; 0.1 megaton) |
| GHG | Greenhouse gas |
| GHGI | Greenhouse gas inventory |
| GIS | Geographic information system |
| GWP | Global-warming potential |
| ha | Hectare (10,000 square meters; 0.01 square kilometer) |
| INDC | Intended Nationally Determined Contribution |
| IPCC | Intergovernmental Panel on Climate Change |
| km | Kilometer (1,000 meters) |
| km2 | Square kilometer (100 hectares) |
| LoA | Letter of agreement |
| M- | (prefix) mega-, million, 106 |
| M&E | Monitoring and evaluation |
| M&R | Measurement and reporting |
| MCC | Millennium Challenge Corporation |
| MEA | Multi-lateral environmental agreement |
| Mha | Million hectares (10,000 km2) |
| MMDE | Ministry of Mahaweli Development and Environment |
| MoU | Memorandum of understanding |
| MPGs | Modalities, procedures, and guidelines (under the ETF) |
| MR(V) | Measurement and reporting, plus verification in the case of climate-change mitigation |
| MRV | Measurement, reporting, and verification |
| MTR | Mid-term review |
| MULS | University of Life Science |
| N | Nitrogen |
| N2O | Nitrous oxide |
| NCSA | National Capacity Needs Self-Assessment for Global Environmental Management |
| NDA | Nationally Designated Authority |
| NDC | Nationally Determined Contribution |
| NOx | Oxides of nitrogen |
| NPD | National Project Director |
| PPG | Project Preparation Grant |
| PPR | Project Progress Report |
| PSC | Project Steering Committee |
| PTF | Project Task Force |
| REDD | Reduced Emissions from Deforestation and Forest Degradation |
| TBD | To be determined |
| TE | Terminal evaluation |
| TNA | Technical needs assessment |
| ToR | Terms of reference |
| TWG | Technical working group |
| UNFCCC | United Nations Framework Convention on Climate Change |

Section 1:  Project Rationale

## Context Analysis

The primary aim of this project is to improve the quality of information available to stakeholders regarding climate change in Sri Lanka’s agriculture, forestry, and other land uses (AFOLU) sector.

### Global context

The Paris Agreement was adopted at the 21st Conference of the Parties (COP) to the United Nations Framework Convention on Climate Change (UNFCCC) in December, 2015, and entered into force on 4 November 2016. The landmark agreement aims to strengthen the global response to the threat of climate change by limiting a global temperature rise in the 21st century to a maximum of 2 degrees Celsius (° C) above pre-industrial levels and to try to limit the temperature increase to 1.5° C. Additionally, the Paris Agreement aims to strengthen the ability of countries to respond and adapt to climate change.

The agreement requires all parties to communicate associated national commitments via Nationally Determined Contributions (NDCs). A country’s NDC establishes targets for sector-specific greenhouse gas (GHG) emissions and sinks, as well as intended efforts to achieve those targets.  NDCs are submitted at least 5 years prior to the start of the 5-year period covered by an NDC.  Under the agreement, all parties commit to provide this information on mitigation targets and efforts via national communications (NCs), with interim updates submitted via biennial update reports (BURs).

Article 13 of the Paris Agreement describes a planned Enhanced Transparency Framework (ETF) for measurement, reporting, and verification (MRV) associated with UNFCCC commitments.  Although parts of the ETF and associated modalities, procedures, and guidelines (MPGs) are still under development, the MPG for the transparency framework stipulated use of the Intergovernmental Panel on Climate Change (IPCC)  2006 Guidelines for National Greenhouse Gas Inventories or subsequent versions, which explain standards and good practices related to MRV for climate change, particularly under UNFCCC.

Non-Annex I parties to the Paris Agreement, such as Sri Lanka, commit to MRV associated with climate-change mitigation (CCM) and are encouraged to conduct measurement and reporting (M&R) associated with climate-change adaptation (CCA).   In order to facilitate international aggregation of information and periodic global GHG stock-taking, country-level mitigation-related MRV entails reporting on (i) carbon stocks and GHG fluxes (GHG emissions and removals) and (ii) progress on mitigation-related actions established in a country’s NDC.  Table 1 presents the types of information to be collected and reported on climate-change mitigation and adaptation under the modalities, procedures and guidelines for the transparency framework.

- Table 1.  Information to be collected and reported for climate-change Mitigation and Adaptation under the Modalities, Procedures, and Guidelines (MPGs) for the transparency framework for actions and support referred to in Article 13 of the Paris Agreement

|  | Mitigation MPG article III: Information necessary to track progress made in implementing and achieving nationally determined contributions under Article 4 of the Paris Agreement. | Adaptation MPG article IV: Information related to climate change impacts and adaptation under Article 7 of the Paris Agreement. |
| --- | --- | --- |
|  | - National circumstances and institutional arrangements | - National circumstances, institutional arrangements and legal frameworks |
|  | - Description of a Party’s nationally determined contribution under Article 4 of the Paris Agreement, including updates | - Impacts, risks and vulnerabilities |
|  | - Information necessary to track progress made in implementing and achieving its nationally determined contribution under Article 4 of the Paris Agreement | - Adaptation priorities and barriers |
|  | - Mitigation policies and measures, actions and plans, including those with mitigation co-benefits resulting from adaptation actions and economic diversification plans, related to implementing and achieving a nationally determined contribution under Article 4 of the Paris Agreement | - Adaptation strategies, policies, plans, goals and actions to integrate adaptation into national policies and strategies |
|  | - Summary of greenhouse gas emissions and removals | - Progress on implementation of adaptation |
|  | - Projections of greenhouse gas emissions and removals, as applicable | - Monitoring and evaluation of adaptation actions and processes |
|  | - Other information | - Information related to averting, minimizing and addressing loss and damage associated with climate change impacts |
|  |  | Cooperation, good practices, experience and lessons learned |
|  |  | - Any other information related to climate change impacts and adaptation under Article 7 of the Paris Agreement. |

Mitigation-related MRV is conducted for four standard sectors:  Energy, Industrial Processes and Product Use, AFOLU, and Waste.  Each sector encompasses standard categories and sub-categories, though parties are encouraged to identify and conduct MRV on nationally relevant and appropriate sub-categories.  Within each category, emissions and removals are estimated for each relevant GHG (e.g., CO2, CH4, N2O).  Figure 1 depicts an overview of IPCC’s standard reporting structure for the AFOLU sector.

Figure 1.  Overview of IPCC’s Standard Reporting Structure for AFOLU

Parties are encouraged to identify nationally appropriate key categories, which are specific sources and sinks that play especially influential roles in a country’s mitigation or adaptation strategies.  Particular sources or sinks may be key categories due to their absolute level, trend, or uncertainty.  Key categories and sub-categories generally merit greater rigor in MRV approaches, which is reflected in tiers.  Tier 1 is the minimum level of rigor for meeting MRV commitments and generally relies on basic country-level data combined with standard (i.e., global or regional, but not country-specific) parameters, such as emissions factors.  Tier 2 is the minimum reporting level appropriate for key categories and sub-categories, and relies on country-specific parameters, including quantified, estimated uncertainties.  Tier 3 is the highest level of MRV rigor, which entails extensive country-specific parameters and nationally appropriate calculation methods that have been empirically verified.

The purposes of identifying key categories and sub-categories are to help parties (i) prioritize uses of limited resources, (ii) determine which categories and sub-categories merit higher-tier methods, and (iii) identify which categories and sub-categories merit greater focus for quality control (QC) and quality assurance (QA).

Under the Paris Agreement, the global community offers financial assistance to Non-Annex I parties seeking to build capacities to comply with the ETF via the Capacity-building Initiative for Transparency (CBIT), administered by the Global Environment Facility (GEF).   This project is substantially funded through GEF-CBIT.

### National context

Sri Lanka signed the UNFCCC on 10 June 1992 and ratified it 23 November 1993. Sri Lanka acceded to the Kyoto Protocol on 3 September 2002.  Likewise, Sri Lanka continues to play a proactive role in the process to draft, adopt, ratify, and operationalize the Paris Agreement.  Sri Lanka signed the Paris Agreement at the earliest opportunity, 22 April 2016, and ratified the agreement on 21 September 2016. It submitted its INDC on 25 April 2016 and NDC in September 2016. Ministry of Mahaweli Development and Environment (MMDE) is the national focal institution.

Sri Lanka submitted its 1st National Communication under the UNFCCC on 6 November 2000, its 2nd National Communication on 16 March 2012, and its 3rd National Communication preparation is underway. While INDC and NDC have been submitted, the BUR is yet to be submitted. The communications are submitted by the Climate Change Secretariat (CCS) of MMDE. CCS is the national focal point and the coordinating institution for  CC communication.

As emphasized in prior national reports and communications, forestry and agriculture play significant roles in Sri Lanka’s efforts to mitigate and adapt to climate change.  Table 2 presents an overview of Sri Lanka’s GHG fluxes by sector in 2012 as reported in 2nd National Communication. According to the second national communication of Sri Lanka, total CO2 equivalent emission from agriculture is 4,709 Mt comprising 3,888 MtCO2e of CH4 and 821 MtCO2e of N2O. Rice cultivation is the major contributor while enteric fermentation, soil, manure management and residue burning are also significant sources of these emissions.  In Sri Lanka, about 71% of agricultural land holdings are less than one hectare (Department of Census and Statistics, 2004), while 66% of cropland is rain-fed Relatively high dependence on rains make agriculture vulnerable to impacts of climate variability and extremes. In 2009, agricultural sector growth was stifled by the impact of drought and delayed monsoon rains on the production of two principal crops paddy and tea (Central Bank of Sri Lanka, 2010).

- Table 2.  Sri Lanka’s Emission and Removals

Agricultural Sector. Over the past few decades, the importance of the agricultural sector has declined. In year 2017, it was estimated that agriculture, forestry and fisheries contributed only 7.71% (11.9% in year 2010) to the country’s GDP, against 27.20% (28.7% in year 2010) from industry and 55.77% (59.3% in year 2010) from the service sector. However, over 26.68% of all employed were employed in the agricultural sector in 2017 (World Bank, 2017).

Sri Lanka is a fertile tropical land with the potential for the cultivation of a variety of crops. Sri Lanka’s primary food crop is rice. Rice is cultivated during two seasons. Plantation crops, tea, rubber and coconut, are cultivated and these crops are a major source of foreign exchange income. Vegetables, fruits and oilseed crops are also cultivated in the country. One of the main objectives of the Sri Lanka’s National Agriculture Policy is to enhance agriculture production and ensure sustainable growth.

Climate Change vulnerabilities in the agriculture sector. Being an island with a mountainous central-region, Sri Lanka has been historically affected by floods, droughts, landslides, coastal storms and erosion, cyclones and storm surges. Changes in rainfall distribution is clearly manifest in a higher number of intense/heavy rainfall incidents leading to floods and longer periods of consecutive dry days leading to deeper periods of drought during the dry season. Climate change will undoubtedly trigger serious impacts on the country’s food insecurity and vulnerability patterns. This has been highlighted in study of ESCAP (2010), with Sri Lanka identified as one of the potential hotspots of food insecurity in the Asia-Pacific region. Climate change in Sri Lanka is manifest through a slow but steadily rising temperature and erratic and unpredictable rainfall seasons. A number of meteorological studies point to a clear warming trend with both day-time maximum and night time minimum air temperatures showing increased trend at most meteorological stations in the country. Change in the temporal distribution of rainfall across these four seasons is already observable. Data show increased variability in three out of four monsoons, but especially pronounced during the north-east monsoon which supports agriculture in the Dry zone, especially the staple crop, rice. This spatial and intra-annual variability of rainfall has dramatically affected seasonal cropping patterns, irrigation potential and hydropower generation. Sri Lanka is affected by a number of climatic hazards and extreme events, and these are projected to worsen with climate change.

Livestock: The livestock sector of Sri Lanka recorded 8% growth during 2015 with 0.6% contribution to GDP at present. The main livestock categories related to GHG emissions are buffalo, cattle, goats and swine. In year 2015 cattle population increased by 10% while buffalo population increased by 2% compared to 2014. Goat production is still recognized as a traditional form of livestock production among farmers especially in the dry zone. However, marked growth in both the population and number of farms were noted in 2015. Out of the total (358,233) goat population main part is concentrated in the dry and intermediate zones. The highest population (95,259) reported in Northern Province and 63% of total goat population is located in Eastern, Northern and North Western provinces. Swine production is mainly concentrated in western coastal belt of Sri Lanka. Total pig population has increased in 2015 by 32% while new farm registration does show a marginal growth. Out of total population (94,612) 83% of pigs are reared by farmers in Western and North Western provinces of the country.

Dairy cattle sector in Sri Lanka emits about 2.3 million tonnes carbon dioxide eq. The emission profile of milk is dominated by methane (approx. 95 percent), while the nitrous oxide and carbon dioxide contribute approx. 5% of the total emissions. The highest emission intensities are observed in the low input-output dairy systems in the Dry Lowland zone and the lowest in the intensive systems of Upland and Mid-country production zone. Emissions were on average, 13.8, 6.8, 4.8 and 2.3 kg CO2 eq./kg of milk  for the Dry Lowland, Coconut Triangle, Wet Lowland and Upland and Mid-Country systems respectively.

Fisheries: The fisheries sector plays a key role in Sri Lanka's social and economic life. Fish products are an important source of animal protein for the population and the sector contributes  1.3 % to GDP in 2017. The total fish production in 2016 was 530,920 Mt, mainly dominated by marine fish production (456,990 Mt). Exports of fish and fishery products was 17,593 Mt valued US$ 169.61 million in 2016, while imports of fish products (mostly dried and canned) amounted to 115,693Mt in 2016. From an economic viewpoint, there is significant scope for increasing the level of contribution from the sector through increased output, exploiting the potential for value addition and import substitution. The fisheries sector of Sri Lanka consists of three main subsectors, namely coastal; offshore and deep sea; and inland and aquaculture. These three subsectors employ around 250 000 active fishers and another 100 000 in support services. This workforce represents a population of approx.. 1 million people.

On 26 December 2004, the fisheries sector was severely affected by tsunami tidal waves that hit two-thirds of the coastline of the island. It is estimated that nearly 80% of active fishers were affected and more than 75% of the fishing fleet was destroyed or damaged by the tsunami. In addition, a large number of small-scale fishing craft and fishing gear were destroyed. Of the 12 fishing harbors, 10 were severely damaged, including breakwaters, shore facilities, buildings, machinery and equipment. In addition, public and private utilities, such as ice plants, landing ports, markets and the homes of the fishing community were destroyed. Recovery of the fishing industry since the tsunami, and the changing patterns of practice in the fisheries industry in terms of the balance between offshore fisheries and onshore aquaculture (often in association with mangrove areas, or clearance of mangroves) are of significant relevance to the impact of the sector on both climate change mitigation and adaptive capacity of a significant proportion of the population.

Forestry: The total dense and open forest cover of the island (excluding forest plantations and other forms of vegetation) was estimated at 1.952 million ha in 2017 (Central bank report, 2018) .  This is mainly in closed canopy (1.4 million ha) and sparse forest (0.4 million ha). 15,700 ha of mangroves and 79,941 ha of forest plantations are included as well. Based on the facts given in Sri Lanka Forestry Outlook, 2009, the demand for wood and wood products is mainly met from home gardens, rubber, coconut and tea plantations, and privately held woodlots, considerably reducing the pressure on natural forests. Major challenges in the forest mapping and GHG inventory are lack of emission factors for major group of tree species. Still Sri Lanka is using Tier-1 emission factors. Forest Reference Level of Sri Lanka suggests that total emission of from Sri Lanka’s deforestation, is estimated at 4378 MtCO2 eq per year, whereas carbon sequestration is estimated to be only 72 MtCO2 eq. per year.

Sri Lanka’s forests are also important biodiversity hotspots. The importance of Sri Lanka’s forests at the global level is apparent by the presence of four International Biosphere Reserves (i.e. the Sinharaja forest, Hurulu Forest Reserve, Kanneliya-Dediyagala-Nakiyadeniya Forest Reserve Complex and the Bundala National Park) and two Natural World Heritage Sites (Sinharaja forest and the Central Highlands Serial World Heritage Site comprising, Knuckles Conservation Forest (KCF), Peak Wilderness Protected Area (PWPA), and Horton Plains National Park (HPNP). High biodiversity and endemism of the Wet Zone forests, is also partly why Sri Lanka (together with the Western Ghats of India) is ranked among the world’s 34 biodiversity hotspots.

Status of MRV of agriculture, forestry, livestock and fisheries sector: In agriculture, there are annual crop forecasts which are updated based on data on the ground. The DoA, DoAA, HARTI are government agencies mandated to measure, report and verify activity and other key performance indicators of the sector. For forestry, Forest Department is mandated with NFI. The record keeping and reporting relationships are either internal annual reporting or for mandated disclosures to Forest Department. DoA, DAPH, and DFAR have the in-house record keeping apparatus conducted by regional offices or by the representatives at local government offices. MRV roles are not performed independently by external parties.

The UN-REDD program in Sri Lanka provided extensive and productive support to strengthening Sri Lanka’s forest-related MRV capacities, notably via the support to the development of  Sri Lanka’s National Forest Inventory and submission of Sri Lanka’s Forest Reference Level to the UNFCCC. This CBIT project constitutes an important mechanism to carry forward the momentum of that work in terms of (i) the enabling environment for strengthened MRV, (ii) broader application of the capacities developed by the UN-REDD program (especially to other land-use sub-sectors), and (iii) maintained engagement and continuity of relevant national expertise.

National land-use classifications.  The Centre for Remote Sensing (CRS) of the Survey Department is in the process of developing a new digital topographical database for maps of 1:50,000 scale, with digital layers on transport, hydrography and land cover/ land uses, prepared using ALOS satellite imagery. Out of a total of 92 map sheets, 42 map sheets were completed at the time of the preparation of this data catalogue. The balance is scheduled to be completed by year 2016. The land use categories of the new map series and their characteristics are given in table -3. The maps include forests in three categories; (i) dense forests, (ii) open forests, and (iii) Forest Plantations.  Mangroves and marshes are categorized under ‘Bogey Areas’ and grasslands and scrubland under ‘Bare Lands’. It should be noted that the image interpretation for the map series is done mostly by remote sensing technicians, who participated in the previous land use mapping work under the Sri Lanka/Swiss Remote Sensing Project (1980-1986). This classification system will ensure that nationally appropriate land-use sub-categories are reflected in future AFOLU MRV.

- Table 3. Sri Lanka’s national Land Use Land Cover (LULC) classification and corresponding IPCC Land-use Classes

| Sri Lanka’s National LULC Classification |  | DESCRIPTION |
| --- | --- | --- |
| LEVEL 1 | LEVEL 2 |  |
| Cultivation Area | Tea | Land under men cultivation, both seeding and vegetative propagated tea, land under rehabilitation (Guatemala or Mana grass), partly inter-planted with shade trees |
|  | Rubber | Systematic, continues cultivation of rubber trees in plantations |
|  | Coconut | Systematic, continues planting of coconut trees in plantations |
|  | Paddy | Asweddumized paddy area i.e. bunded and ridged land intended for cultivation of rain fed or irrigated wet rice |
|  | Palmyrah | Systematic, continues planting of Palmyra trees plantation (may be possible) |
|  | Other cultivation | Tobacco, vegetables, other cash crops (cashew &corn), and rain fed highland crops in continues cultivation |
|  | Chena | Un irrigated rain fed upland cultivation based on slashing and burning of preferably forest but also scrubs or grassland (shifting cultivation of perennial crops) |
|  | Sparsely used cropland | Chena (shifting cultivation), recently abandoned Chena, sparsely used rain fed cropland (permanent dry cropping), neglected or abandoned tea, rubber and coconut land under development |
| Forest area | Dense Forest | High growing, natural trees with more than approx. 75% crown coverage |
|  | Open Forest | Dense natural vegetation covers with between 45 and 75% trees crown coverage |
|  | Forest Plantation | Man-made, mostly mono-cultural forests of teak, eucalyptus, pines and other species |
| Boggy area | Mangroves | Salt-tolerant and woody vegetation along sea coasts, lagoons and river months |
|  | Marsh | Permanently wet and muddy, uncultivable and frequently inundated areas |
| Bare area | Grassland | Open park country with less than approx. 50% scrub coverage (damana and savannah) villus and other temporary flooded land an patana (up-country grassland) |
|  | Scrubland | Low-growing vegetation with more than 50% area coverage, including trees with less than 45% crown closure |
|  | Barren land | Rock outcrops, sand dunes, beached, earth slides and other unproductive land |
| Built up area | Aquatic Farms | Pawn farming, fish breeding and aquatic ponds, etc. |
|  | Built up area | Residential (including hotels), industrial, commercial, institutional, administrative, transportation, power plants and urban open spaces |
|  | Homesteads/Garden | Family residential until surrounded by home gardens and open space, cultivation includes fruit trees, spices, vegetables and small holdings of coconut, rubber tea and other plantation crops |
|  | Playground | Flat & geometric shape areas located near schools, universities, etc. in Urban areas |
| Rock area | Rock | Areas cover with large stones (rocky surfaces) |
| Sand area | Sand | Areas between sea water and vegetation boundary specially along the shore line |
| Unclassified areas | same | Unidentifiable areas (confirmed after field verification) |

### AFOLU priorities in Sri Lanka’s Nationally Determined Contribution

Sri Lanka’s NDC indicates the national priorities for mitigating and adapting to climate change, as well as the anticipated benefits of addressing those priorities.  Sri Lanka’s NDCs comprise of following four areas;

  - Mitigation - Reducing the GHG emissions against the Business-As-Usual (BAU) scenarios in the sectors of energy (electricity generation), transportation, industry, waste and forestry. The key contributors to GHG are Carbon Dioxide (CO2), Methane (CH4) and Nitrous Oxide (N2O).

  - Adaptation - Building resilience in most vulnerable communities, sectors and areas to adverse effects of climate change. Adaptation will focus on human health, food security (agriculture, livestock and fisheries), water and irrigation, coastal and marine, biodiversity, urban infrastructure and human settlement, tourism and recreation. Adaptation initiatives that derive mitigation co-benefits will be prioritized.

  - Loss and Damage - In order to address issues related to losses and damages resulting from extreme weather events, a local mechanism will be developed in accordance with the Warsaw International Mechanism for Loss and Damage.

  - Means of Implementation- External support for Finance, Technology Development and Transfer, and Capacity Building for the above sectors are considered in the implementation process of the NDCs of Sri Lanka.

Sector Vulnerability Profiles and National Climate Change Adaptation Strategy (NCCAS) for Sri Lanka (2011 – 2016), developed by the Ministry of Environment in 2010 have identified the following five key sectors as the most vulnerable sectors in the Sri Lankan context:

- Agriculture and Fisheries

- Water

- Health

- Urban Development, Human Settlements & Economic Infrastructure

- Biodiversity and Ecosystem Services

Sri Lanka’s Agriculture sector NDC: The following NDC priorities have been identified for the agriculture sectors in Sri Lanka’s NDC;

- Promote/introduce/develop Integrated Pest Management (IPM) practices to minimize pest damages to improve environmental impacts and health

- Introduce environmentally friendly bio-degradable pesticides for IPM.

- Introduce /promote/develop suitable bio pesticides and bio control agents for IPM.

- Introduce/promote/develop post-harvest management with environmentally friendly technology packages.

- Develop/introduce varieties resistant/tolerance to biotic and abiotic stresses arising from climate change

- Introduce/promote/develop heat, draught, flood and salt tolerant varieties

- Develop and promote mature varieties

- Re-demarcating Agro-Ecological Regions (AERS) maps of Sri Lanka with current climate and future climate, and recommend appropriate crops for different areas to reduce vulnerability to climate change impacts.

- Introduce suitable land and water management practices for central highlands and other marginal areas to minimize land degradation and to improve land and water productivity.

Sri Lanka’s Livestock sector NDC: Livestock is an integral part of agricultural economy in Sri Lanka and it ensures food security, helps in reducing malnutrition and poverty. There are approximately 560,000 families directly engaged in livestock sector, i.e. dairy, poultry, goat, swine and other livestock. Dairy industry is earmarked as the priority area for investment and development in the livestock sector. The development programs launched by the Ministry of Rural Economic Affairs enabled the country to reach 42% self-sufficiency in local milk production in 2015. A major driving factor of livestock dynamics in Sri Lanka appears to be climatic variability. The rising temperature and uncertainties in rainfall associated with global warming are likely to increase the frequency and magnitude of climate variability and extremes.

Furthermore, changes in climate would also increase the risk of unexpected changes in nature and environment. The key risks from climate change to livestock are increased incidence of drought, flood and heat. In this context, Sri Lanka identified the following NDCs for the livestock sector in order to build resilience in the livestock sector to meet adverse impacts of climate change.

- Identification of vulnerability in the livestock sector, with relation to the following variables:

  - livestock species; agro-climate areas; farming communities; production systems; processing pathways

- Introduction of adoptive measures to avoid or minimize the adverse effects of technological innovations on animal production systems and traditional knowledge and practices, through collection and dissemination of information, capacity building and technical skills development

- Introduction of alternative measures to minimize adverse effects of climate change

- Identification of potential clean and renewable energy sources for livestock related activities

- Adaptation of integrated waste management systems

- Promotion of responsible consumption and sustainable production through promotion of green livestock procedures & processing techniques, and consumption of green livestock products

- Enhancement of education, awareness, knowledge exchange and capacity building on emerging green technologies in livestock and agriculture sectors

Figure 2 depicts some of the ways in which climate change affects various sub-sectors and stakeholders, giving a sense of the breadth of issues the project—largely via the MRV Technical Working Group (see Activity 1.1.2.1)—will consider in establishing a nationally appropriate M&R system for CCA.

- Figure 2.  Climate-change Effects in the AFOLU Sector

Sri Lanka’s Forestry sector NDC: Proposed NDC priorities in this sector directly or indirectly influence in reduction of GHG emission by increasing the forest cover in the country to a healthy level, managing deforestation and enriching usage by introducing perennial crops during the period 2020-2030.  The NDC of forestry sector of Sri Lanka are increasing the forest cover of Sri Lanka from 29.7% to 32% by 2030; identify land for reforestation/afforestation by conducting land use planning at national scale; improving quality of growing stock of natural forests and forest plantations by forest boundary demarcation and development of plantation management plans for sustainable forest management practices for productive and protective purposes; restoring degraded forests and hilltops (shrubs, grasslands and state lands); improving river basin management for major rivers of Sri Lanka through catchment-level multi-hazard prioritization; preparation of catchment management plans; demarcation and protection of riverine vegetation; afforestation of underutilized private lands and marginal tea lands, including piloting of Payment for Ecosystem Services (PES) mechanism; urban forestry (roadside planting, urban parks and other state lands); establishing a functional National Forest Monitoring System (NFMS); and promoting investment of private and public-sector companies in environmental conservation projects through Corporate Social Responsibility (CSR) programs.

The implementation of the above actions requires improved institutional coordination and a robust system for capturing precise data and information that is accurate and credible in reporting on GHG estimates (e.g. by sources and sinks).  This requires that Sri Lanka have systems in place to track progress in achieving NDCs across priorities covering both mitigation and adaptation actions, as well as a wide range of sectors (e.g. AFOLU, energy, transport) and related sub-sectors (e.g. livestock, field crops, water and forestry).

Implementation challenges for forestry sector NDC: The rate of reforestation and afforestation at the moment is not adequate for reaching the primary target of 32% of land area under forests. For instance, the extent deforested and area reforested 1,241 ha and 956 ha respectively in 2017. The stakeholder workshop conducted on 25 February 2019 revealed that there is a mismatch between goal setting in NDC and the targets of DFC. DFC, while mandated to carry out the bulk of NDCs in forestry sector has only partial control of the forest  cover. DWC and LRC are in charge of nearly 50% of the forested areas in the country

## Status of MRV for Climate Change in the AFOLU Sector

Sri Lanka’s MRV capacities are currently under-developed for the AFOLU sector. Second National Communication and FRL are two most recent AFOLU MRV reports.  As noted above, AFOLU reporting in both reports are Tier 1 defaults. Tier 1 enables a foundational basis for planning, but does not reflect best practices.

There are several challenges associated with regular and comprehensive reporting of anthropogenic emissions inventories by sources and removals prepared using good practices methodology. Major challenges are lack of activity data and local emission factors, reliance on outdated IPCC methodologies for measurement and monitoring of emissions from the agriculture sectors, harmonization of land use land cover with IPCC land use classes, insufficient financial support for regular inventory preparation. This also results in limiting experience with measuring, reporting and verification (MRV) systems for emissions from the agriculture and land-use sectors. This is also resulting in of lack of harmonized indicator and monitoring systems for adaptation based on national priorities.

NCs to the UNFCCC are dependent on a sound MRV framework. While Sri Lanka was able to submit first and second NCs, the delay in BUR and TNC is mainly due to lapses in the MRV framework. For the past communications, Sri Lanka has adopted revised IPCC (1999) and IPCC (2006) guidelines. The activity data has been sourced through consultation and Tier 1 EFs (and Tier 2 equivalent National factors in SNC) have been used.  Tier 2 comparable estimates from literature reviews have been discussed in the FRL and literature cited under Sri Lanka REDD documentation.

CCS identified the lack of data sharing agreements between government institutions and the lack of technical and expertise within the CCS to manage the technical coordination process for MRV as the most severe challenges. Activity data from agriculture is mainly available for annual crops under the DoA planning framework. Plantation and perennials, tree species data from home gardens are assessed by DCS occasionally on representative sample basis. Livestock and Fisheries activity data are less organised but regional offices maintain records of activity in terms of boats operated by landing site. Livestock Census and GPS data on fishing fleets are available for secondary processing in order to match the format for AFOLU MRV. Forest cover map was also generated during 2010 and it has been used since then for GHG estimation from forestry sector. This needs to be updated. Data processing, except for mapping, is not under the mandates of any of the key ministries involved. The universities and the research institutes are the parties which perform data processing and analysis using statistical methods. Findings from forecasting and meta-analysis are important inputs to verification and validation process, but there is no direct mechanism to solicit studies for relevant estimations, forecasts and meta-analyses.

### Gaps and barriers identified in previous reports

Sri Lanka’s previous climate-related reports have identified numerous priorities and gaps relevant to MRV in the AFOLU sector. In summary, various reports indicate the following thematic barriers to strengthened climate-related MRV in Sri Lanka’s AFOLU sector.

Food sector which includes agriculture (Rice, Fruits & Vegetables, Other Field Crops, Sugar Cane, Tea, Coconut, Export Agricultural Crops etc.), Livestock (Dairy, Poultry etc.) and Fishery is one of the most vulnerable sectors to climate change impacts in Sri Lanka. Changing climate and weather patterns suggest high potential of negative impacts on food production, food security and natural resources in the country. The impending vagaries of climate change such as intense, uncertain, highly variable rainfall pattern and temperature, sea level rise, combined with deterioration and dwindling of natural resources emphasize the necessity of sustainable climate change adaptation technologies to increase the productivity, stability and resilience of the food sector.

With a view to utilize technological approaches that can be quickly harnessed for developing adaptation technologies to reduce vulnerability to climate change, Nine (9) adaptation options were identified as priority technologies for consideration. The identification of technologies was guided by factors such as the adequacy of information available on the proposed technology, the probability of success or failure of the technology, cost, potential risks and the level of confidence of the sector specialists in the choice of the proposed technology. The technologies thus identified fall under the broad categories of crop/livestock/fishery management, sustainable water use and management, capacity building of stakeholder organization and sustainable land management. The adaptation technology options identified are as follows;

- Sustainable Land Management

- Crop Diversification & Precision Farming

- Ecological Pest and Disease Control

- Rain Water Harvesting

- Solar-powered Drip Irrigation

- Development of Appropriate Breeds

- Development of Appropriate Varieties

- Responsive Agricultural Extension

- Sustainable Culture-Based Fisheries

All the technologies identified are currently available in Sri Lanka. Of the proposed technologies, Rain Water Harvesting, Solar-powered Drip Irrigation, Responsive Agricultural Extension and Sustainable Culture-Based Fisheries are proposed for short term implementation while the other technologies are to be implemented on long term basis.

The technology prioritization (mentioned in paragraph 39) resulted in outlining three most important and technologies to be introduced in Sri Lanka. (1) Culture-based fisheries Crop diversification and precision farming, (2) Crop diversification and precision farming and (3) Sustainable land management.

Based on Second National Communication, the total aggregate emission was 20,798 GgCO2eq which comprised 61.4% from the energy sector (including transport), 25.0% from the agriculture sector, 10.8% from the waste sector, 2.6% from the industry sector and 0.2% from the land use change and forestry sector. Total removals from land use change and forestry was estimated to be 6,254 GgCO2eq.

Forest Reference Level (FRL) reported emission level is 4,529 GgCO2eq and removal level is 79 GgCO2eq on annual basis. FRL used Tier-1 approach and global emission factors to estimate emission and removal which needs to be updated. This is a major area in forestry sector where national species specific emission factors needs be generated. There is also a major challenge associated with activity data in forestry sector. Although Sri Lanka has its nationally classified forest cover maps but accuracy of these maps and activity data needs to improved. This needs adoption of improved methodology and technology, both at office and field level. Most of the gaps areas are identified in NDC (paragraph-31).

Other land use sectors are also major concerns. With respect to water, several authorities are directly involved: Mahaweli authority, Irrigation Department, Water resources Board and the provincial and local administrative councils. All the UNFCCC reporting  so far, and the training and sensitization efforts have  been focused around divisions under Ministerial portfolio of Environment which does not have complete jurisdiction over the water and waste sectors.  There are other crucial concerns such wetland restoration which is also under number of central agencies as well as local administrative agencies. A good example is the wetland restoration work around Colombo which was prioritized to control flash floods. Ministry of Disaster Management and Ministry of Western Development and Megapolis are other agencies in charge of land-use related critical decision making.

MRV of AFOLU sectors is burdened with extensive coordination needs and efficient protocols for data sharing, data access and transparency. The current institutional linkages of CCS are not conducive to efficient MRV practices. The CCS proposes establishing a climate unit/cell within each key stakeholder institutions at regional level to procure and report to CCS. For agriculture, it is proposed to install the climate cell at Provincial Dept. of Agrarian Development, Provincial Dept. of Agriculture, and Provincial Dept. of Animal Production and Health. For forestry sector, CCS proposes climate cells at Forest Department, State Timber Corporation (nationally and provincially). For other land use sectors, climate cells are recommended at UDA, RDA, and LUPPD, both at National and at Provincial level.

Operations and CC communications to UNFCCC have been so far conducted under project funding through international agencies. While there is a very significant in–kind contribution by state agencies in facilitating the UNFCCC reporting obligations, the capacity development of MRV is hindered by the lack of resources. The annual budgets of the line ministries are not sufficient to conduct programming related to MRV recommended by UNFCCC and IPCC guidelines. The institutional processes are needed in place of consultancy-driven framework for sustainability and local ownership. The budgeted cost of programming on CC related work with a substantive MRV component were recorded as approx. LKR 498 million for 2016 (annual performance report, 2016 MMDE).

Current institutional arrangements do not fully facilitate meeting Sri Lanka’s MRV commitments under the Paris Agreement. Sri Lanka’s commitments under multi-lateral environmental agreements (MEAs) are generally not institutionalized beyond the nationally designated authority (NDA). For example, obligations for data-collection and reporting for national communications are generally not reflected in the mandates, performance criteria, or budgets of line agencies.

Technical and budgetary challenges have impeded intention to provide guidance to supporting agencies on ETF-compliant data-collection and data-sharing. Drafting of those guidelines has stalled due to uncertainties about how to (i) overcome certain technical and operational challenges and (ii) provide contributing agencies with adequate funding and technical assistance. Although relevant information exists, stakeholders have limited awareness of its availability and means of access. Agencies that maintain the relevant information are sometimes uncertain of constraints on sharing the data.  Therefore, there is limited, ad hoc coordination and information-sharing between agencies.

Funding is not reliably sufficient to conduct regular MRV or to maintain staffing. There are significant uncertainties about the sources, preconditions, amounts, and reliability of potential long-term funding sources. In general, MRV outputs are public goods that are not easily linked to market-based funding sources.  A single window mechanism should be in place for MRV related activity data.

Most MRV activities are conducted with project-based funding, which supports relevant cadre positions for the duration of a project.  Breaks between projects and insufficient funding for full period of task result in employee turnover, which increases costs for capacity development and technical assistance.  These challenges are compounded by contextual factors.  Thus, data-collection—the foundation of MRV—poses a substantial technical and budgetary challenge.  Measurement is a precondition for reporting, which is a precondition for verification.  At present, insufficient measurement is the primary constraint on AFOLU MRV in Sri Lanka.  Thus, cost-efficient options (e.g., proxy measures; improving existing data and systems based on assessments of accuracy and quality) are important for the financial sustainability of these systems.

Sri Lanka has insufficient capacities for (i) country-specific ETF reporting and (ii) reporting on climate-related adaptation with adequate quality to guide national policies.  These shortfalls in capacity relate to funding (as above), human resources, technology, and technical training.  For example, Climate Change Secretariat (CCS) hires consultants according to project-based funding.  This arrangement often means that a given topic is addressed by different consultants for different reports.  Therefore, CCS faces the added challenge of coordinating knowledge-management and knowledge-retention to ensure consistency and continuity across reports.  These capacity-related shortcomings also extend laterally to other supporting institutions.

Table 4.  Previously Identified Barriers and Needs Related to AFOLU MRV,

National Capacity Needs Self-assessment (2007)

Recommendations for Capacity Intervention in National Capacity Needs Self Assessment Report of Sri Lanka I. Cross cutting capacity development: - Formulate and institute national policies, as required, through a wide consultative process. For example, development of policy for; - Access to genetic resources & benefit sharing, including traditional knowledge associated with genetic resources and benefit sharing with TK holders; - Biotechnology using genetic resources within ABS regime; - data & information management; - on national network of protected areas; - on conservation & sustainable use of livestock biodiversity, in livestock development policy; - on agrobiodiversity, in agriculture policy; - emphasis on land degradation in land use policy; - on land alienation & regularisation of encroachments; and - policy on climate change. - Enhance capacity for communication, education and public awareness on conservation and sustainable use of resources to mobilize commitment and participation of all stakeholders. - Enhance capacity to integrate (mainstream) environment concerns into sectoral and cross sectoral policies and programmes of public agencies. - Enhance capacity to obtain adequate national budgetary allocations (and external funds, as necessary) and capacity to use funds efficiently. - Adopt measures to engage the business sector effectively in conservation and sustainable use of natural resources. - Strengthen enforcement of laws and regulations to promote conservation and sustainable use. - Strengthen system and capacity for information management and information sharing as relevant for the three Rio Conventions. - Enhance capacity to negotiate effectively at COPs of the Three Rio Conventions and other global forums to fulfil national needs and interests. - Harmonize authority and responsibility for policy determination and implementation between the central and provincial authorities - Strengthen capacity of institutions to carry out research on relevant areas of biodiversity, climate change and land degradation. - Establish an institutional structure effective planning and implementation of work programmes. II. Theme specific capacity development: - Develop competence of land users to benefit optimally from land while conserving. - Enhance capacity to provide technology for conservation and sustainable use of land and water resources. - Adopt measures to promote use of renewable energy resources and means for alternative livelihoods, to reduce land degradation. - Improve capacity of authorities concerned to forecast and warn of adverse climatic situations. - Enhance the capacity for vulnerability assessments and measures for adaptation to climate change: - Identify, map and demarcate areas vulnerable to sea level rise - Assess effect of CC on ground water, especially in areas prone to drought and in areas subject to sea level rise - Assess change in impact of waves on the coast - Assess effect of CC on flora and fauna - Assess effect of CC on food and export/ plantation crops - Assess effect of CC on health - Assess effect of CC on hydro power generation potential - Developing and transfer of technology to facilitate developing adaptive measures - Enhance institutional capacity for multi stakeholder participation to promote conservation, management, recovery of threatened species and sustainable use of commercially important species. - Implement a multi-institutional coordinated programme to identify, design and establish a rational network of areas needing protection in accordance with the ecosystem approach. - Develop and institute an effective system to regulate and control the provision of access to genetic resources by external parties, in order to ensure fair and equitable benefits to Sri Lanka from the resources so provided. - Develop and introduce measures to enhance national capacity for biotechnology using genetic resources. - Establish an effective inter- institutional mechanism to identify and monitor critical components of biodiversity and threats to biodiversity. - Enhance institutional capacity for participatory and integrated in-situ conservation and management of ecosystems with perspectives on poverty eradication. - Strengthen the legal framework for biodiversity conservation and sustainable use. In particular; NCSA report refers to baseline appraisal done under NCSA project, which states that while capacity building to address specific convention obligations has been done to some extent, the following requirements of the convention have been neglected with respect to capacity development. - Preparing national communications (2 NCs have been submitted and third in progress) - Developing national climate change programmes (on going) - Preparing and managing greenhouse gas inventories, including emission database management - Assessing mitigation options - Developing and transferring technology - Improved decision-making, including assistance for participation in international negotiations - Institutional capacity-building, notably through secretariats or focal points - Enhancement of the enabling environment

### Gap assessments during the project-preparation phase

Gap assessment were conducted during stakeholder meeting as well as by conducting separate meetings with stakeholder organizations. Major gaps identified are (a) institutional arrangement for GHG activity data collection from various stakeholders. Climate change secretariat is working on establishing a Climate Cell at each provincial level for activity data collection from all sectors. (b) Knowledge of activity data and its type and units are also major concerns while data collection. Training to enhance human and infrastructure resources are required. (c) Up to date Data availability of forestry, livestock and fisheries are also major concerns. These needs updates with proper methodologies, QA and QA guidelines. (d) Emission factor improvements in forestry and livestock sectors were of immediate concerns. (e) Adaptation sectors NDC are less defined and it needs more national capacity building. (f) National agro-ecologial zone maps needs to re-defined which will result in refinement of emission factors too. This project will help in achieving such challenges which will improve national ability to report better with enhanced accuracy.

Institutional arrangements.  Institutional arrangements are generally established for mitigation-related ETF functions. The arrangements are less developed for adaptation-related M&R, though are expected to be similar as adaptation-related arrangements develop.  Figure 8 depicts the institutional arrangements for Sri Lanka’s national GHG inventory process. Ministry of Mahaweli Development and Environment, is the UNFCCC focal point under which Climate Change Secretariat acts with a mandate to estimate GHG emissions and removals.  CCS is responsible for Climate Change technical reports and national greenhouse gas inventory (GHGI) as well as the submission of NCs, BURs, and BTRs to the UNFCCC Secretariat. CCS is establishing provincial level climate cells to coordinate data collection. Capacity building for enhanced transparency in data collection from all stakeholders will be one of the major initiatives under this project.

UNFCCC Secretariat

Central Change Secretariat

As national entity for GHG inventory, reviews and endorses GHG inventory

Ministry of Mahaweli Development and Environment

UNFCCC National Focal Point

Ministry of Mahaweli Development and Environment

Reviews, endorses, and submits GHG inventory

Data Collectiona

Reporting

Figure 8.  Institutional arrangement for GHG inventory

a For AFOLU reporting, data are collected primarily from these departments.

- Dept. of Agriculture

- Dept. of Animal Production and Health

- Dept. of Census and Statistics

- Dept. of Agrarian Development

- Land Use Policy Planning Department (LUPPD)

- Survey Department

- Forest Department

- State Timber Corporation

- Sri Lanka Sustainable Energy Authority (Biomass usage data)

- Urban Development Authority (UDA)

- Road Development Authority (RDA)

- Tea, Rubber, Coconut Research Institutes

- Ministry of Plantation Industries

- Dept. of Export Agriculture

- Mahaweli Authority of Sri Lanka

- Ministry of Mahaweli Development and Environment

- National Fertilizer Secretariat

- et.al.

Budget.  Climate Change Secretariat’s budget comprises project-based funding, which results in challenges for staffing, knowledge management, and strategic planning for GHG inventory. The national budget does not provide additional resources for ETF-related functions. Therefore, additional data-collection, analyses, reporting, and verification will not be conducted without additional resources.

Key-category analysis.  Although available data are not sufficiently complete for a full key-category analysis, a provisional key-category analysis is conducted as part of the Third National Communication. Key categories within the AFOLU sector identified are;

- Enteric Fermentation

- Manure Management

- Biomass Burning in Cropland

- Liming

- Urea Fertilization

- Direct and Indirect N2O emission from managed soil

- Indirect N2O emissions from manure management

- CH4 Emissions from Rice cultivation

- Forestland Remained Forestland

- Land converted to forestland

- Cropland remaining cropland

- Land converted to cropland

- Wetland remaining wetland

- Biomass burning in forestland

Out of above mentioned key categories, Enteric fermentation, CH4 Emission from rice cultivation and Urea application are of prime importance for capacity building during this project period.

As noted above, MRV for the agricultural and LULUC sub-sectors is currently conducted at Tier 1, with some Tier 2 non-validated information available.  MMDE - CCS continues to increase the rigor of climate-related MRV.  The next step is to ensure Tier 2 reporting for key categories in a step wise manner.  The prioritized key categories will be selected for capacity building to generate Tier 2 emission factors. This project will capacitate relevant stakeholders for that endeavour.  However, it is presently unclear whether sufficient resources (e.g., funding, personnel) will be available from other sources to support collection of the requisite data—either on a one-time or recurrent basis.

Quality control.  Quality control and Quality Assurance of activity data is a technical barrier in Sri Lanka. It has a provisional quality-control and quality-assurance plan that describes procedures to check, document, and improve the quality of the GHG inventory.  The drafted plan includes guidelines on data-collection methods, processes for obtaining peer review and public comments, and plans for uncertainty assessments.  The drafted plan has been initially reviewed and requires substantial further revision before adopting and operationalizing it.  There are no such QC arrangements for adaptation-related M&R, given that the numerous proposed adaptive approaches have not yet been prioritized, nor indicators determined.

Data-collection and -provision.  Various agencies collect ETF-relevant data, though generally for other purposes, according to funding and mandates.  Therefore, data are available according to the methods and timing of those funding sources and mandates, and are not generally alterable for ETF alignment.  CCS gathers data from these other agencies on an ad hoc basis via ad hoc methods and arrangements, as reporting requires and project-related funding enables.  CCS relies on AFOLU data primarily from below mentioned departments in Sri Lanka.

- Dept. of Agriculture

- Dept. of Animal Production and Health

- Dept. of Census and Statistics

- Dept. of Agrarian Development

- Land Use Policy Planning Department (LUPPD)

- Survey Department

- Forest Department

- State Timber Corporation

- Sri Lanka Sustainable Energy Authority (Biomass usage data)

- Urban Development Authority (UDA)

- Road Development Authority (RDA)

- Tea, Rubber, Coconut Research Institutes

- Ministry of Plantation Industries

- Dept. of Export Agriculture

- Mahaweli Authority of Sri Lanka

- Ministry of Mahaweli Development and Environment

- National Fertilizer Secretariat

- Department of meteorology

- Department of Irrigation

Various agencies maintain separate public data portals.  Department of Census and Statistics (DCS) (http://www.statistics.gov.lk) website provides a uniform interface and data-extraction tools (e.g., data export; tables and graphics by selected data fields for various databases compiled by this department.  However, the site offers scant information on metadata, sources, and data-collection methods. While summary compilations of census and routine survey data are publicly accessible, much of the metadata is not conducive to reporting in line with IPCC’s 2006 Guidelines.

There is no central database system which can cater national GHG inventory. During stakeholder meeting, various technical barriers were presented which are given below;

- Quality Control (QC) and Quality Assurance (QA) of Activity Data

- Lack of Measuring, Reporting and Verification system (for GHGI and MO)

- Variations in estimates of  Activity Data

- Variations in estimates of in Emission Factors

- Unavailability of regular data collection mechanism and a Database

- Lack of Knowledge on Climate Change, GHG emission sources and mitigation measures at ground level data collectors

- Lack of routine studies to generate ‘Tier 2’ and ‘tier 3’ country and sector specific emission factors

Further, the TNC faces some challenges such as need for capacity improvements in sourcing updated information of AFOLU sectors due to limited technical expertise and capacity of CCS in this regard. In addition, the obligations of BUR and thematic studies also have been delayed through lack of data and coordination between stakeholders

Data-archiving. A host agency has not been designated for an archival system, and no such system is operational.  Related SOPs have not been drafted and there are no plans to fund the associated human and technological resources, operation and maintenance, etc.

Uncertainty analyses.  This is a major technical challenge in Sri Lanka’s GHG estimation process. Many institutions  do not hold data in the format which is required for GHG inventory, which makes CCS’s job difficult for analysis and it leads to higher uncertainty in results. Some uncertainty analyses have been conducted based on expert judgement and comparisons with default global and regional values.  The process is hindered by the fact that few data providers communicate their data-collection methodology or uncertainty estimates (e.g., confidence intervals of estimates or standard errors). MMDE seeks funding for a full survey of relevant metadata, including methods and uncertainties..

Verification and quality assurance (QA).  It is a major technical barrier as presented by CCS during stakeholder’s consultation workshop. CCS plans to prepare a Relational Normalized Database system with proper data entry forms to collect data from various departments which would also allow more timeline quality assurance processes. This is a challenging task requiring funding, capacity and coordination support. The improvement of data management is a high priority in the Sri Lanka. This is very important for the commitment to enhance transparency of National Status, NCs, BTRs and thematic assessments (Article 13, The Paris Agreement), to establish and implement National MRV system on GHGI and MO, to set NDC targets and assess the progress of achieving NDC targets and AFOLU sector needs for both Climate Change Mitigation and Adaptation measures .

### Differences between mitigation and adaptation capacities

Sri Lanka came up with National Adaptation Plans for 2016 to 2025, which outlines details of priority actions in food security, water resource, coastal and marine sector, health, human settlement and infrastructure, ecosystem and biodiversity, tourism and recreation, export agriculture, industry energy and transportation and several cross-cutting needs of adaptation in various sectors.  The National Adaptation Plan of Sri Lanka identified agriculture, fisheries, water, human health, coastal and marine, ecosystems and biodiversity, infrastructure and human settlements as the most vulnerable sectors to the adverse effects of climate change. The details of desired action are listed in the NAP document. On the other hand, mitigation MRV process is at a better status.. This difference is largely a function of the global nature of mitigation concerns, which are more amenable to common approaches (e.g., via international MRV guidelines, protocols, default values, etc.), versus the local nature of adaptation concerns, which require tailoring to national circumstances.

Although the details of climate-related adaptation are country-specific, the challenges of a tailored approach are not unique to Sri Lanka.  As described in greater detail under Component 3, this project will make use of the substantial resources available to guide a structured approach to addressing the particular challenges of creating a nationally tailored approach to climate-change adaptation related NDC targets.

### Baseline ratings for CBIT tracking tool

Based on stakeholder consultations during this project’s design phase and stakeholder ratings during the PPG inception workshop, the following baseline ratings have been determined for the CBIT tracking tool (see Table 5).  These ratings comport with those estimated in the PIF.

- Table 5.  Baseline Ratings for CBIT Tracking Tool

| - Indicator | - Scale | - Rating | - Description |
| --- | --- | --- | --- |
| - 3. Quality of MRV systems | - 1 – 10 | - 2 | Measurement systems are in place for a few activities, improved data quality and methodologies, but not cost or time efficient; wider access to reporting is still limited and information is partial; verification is rudimentary/non-standardized |
| - 5. Qualitative assessment of institutional capacity for transparency-related activities | - 1 – 4 | - 2 | Designated transparency institution exists, but with limited staff and capacity to support and coordinate implementation of transparency activities under Article 13 of Paris Agreement. Institution needs to upgrade to coordinate transparency activities under Article 13. |

## Project Description

### Project objective and approach

Purpose.  Sri Lanka’s various climate-related national communications articulate the national priorities in moving toward resilient, low-carbon economic development.  The aim of this project is not to conduct activities that directly mitigate climate change or improve Sri Lanka’s climate-related adaption, but rather to enhance the quality of information related to those issues by aligning MRV practices with global standards.  Specifically, the objective of this project is to enable Sri Lanka to report to the UNFCCC under the Paris Agreement’s Enhanced Transparency Framework (ETF) with strengthened agricultural and land-use sector components including inventories of greenhouse gases by sources and sinks, and information necessary to track progress against priority actions identified in Sri Lanka’s NDC for these sectors.

Priorities.  The overall aim of this project is to improve the quality of information available to all stakeholders regarding climate change in Sri Lanka’s AFOLU sector.  That aim is reflected in several considerations in the design of the project.  First, implementation of this project will work to ensure that all stakeholders benefit from the resulting MRV improvements.  In order to ensure that the project efficiently yields benefits, implementation will focus foremost on addressing coordination and measurement gaps that preclude reporting.  That is, the project will first ensure complete reporting, even if only at Tier 1.  Then, the project will work to ensure broad accessibility and Tier 2 information for key categories.

The project will prioritize ensuring that Sri Lanka fulfils its commitment for mitigation-related reporting under the Paris Agreement while supporting efforts to advance Sri Lanka’s adaptation-related M&R, for which the National Adaptation Plan is prepared.  The project places equal emphasis on strengthening systems for mitigation and adaption, though gaps are more relevant to adaptation. The project will emplace scalable solutions in order to facilitate future MRV enhancements. Lastly, the project’s overall approach emphasizes financial sustainability by identifying cost-efficient options (e.g., proxy measures) and facilitating a transition to nationally sustainable financing of AFOLU MRV.

Intra-sectoral focus.  Baseline capacity and MRV assessments during this project’s preparatory phase indicate that the forestry sector has stronger MRV capacities compared to the rest of the AFOLU sectors, as a result of substantial and sustained forestry efforts from the MMDE, Government of Sri Lanka and supportive initiatives, such as REDD+.  Therefore, this project’s interventions will build on those advances to enhance related capacities for agriculture and other land uses.

Delineating between measurement, reporting, and verification. Sri Lanka’s institutional arrangements for climate-related MRV take advantage of existing capacities and decentralization across various governmental agencies.  Many ETF-related measurement requirements entail extensive collection efforts throughout the country, where different governmental agencies have local offices that regularly collect various information, some of which pertains to the ETF.  In order to achieve efficiencies and reduce data-collection redundancies, CCS primarily coordinates and compiles information collected by other agencies. Various agencies collect the data (the “measurement” of MRV) and CCS compiles it for analysis and reporting (the “reporting” of MRV).  CCS is also tasked with ensuring that relevant governmental agencies collect and provide data sufficient to fulfil Sri Lanka’s commitments under the Paris Agreement.  Capacity building initiatives under this project will help Sri Lanka establish guidelines for (meta)data parameters, collection and documentation protocols, etc. that ensure QC, establish a basis for QA, and enable reporting and verification.

The design of this project reflects the existing delineation in institutional coordination between measurement (data-collection and QC), reporting (sharing, compiling, analyzing, and reporting), and verification (documentation and QA).  Component 1 covers activities related to reporting functions, such as information-sharing and stakeholder coordination. Component 2 covers activities related to measurement and verification for climate-change mitigation. Component 3 covers activities related to measurement for climate-change adaptation.  Thus, Components 2 and 3 focus on what data are collected, how, and by whom, whereas Component 1 focuses on how those data are shared, analyzed, and reported.  Component 1 also facilitates operationalization of Sri Lanka’s reporting commitments under the Paris Agreement.

### Component 1

Component 1: Institutional arrangements to coordinate preparation of ETF reports for agriculture, forestry, land-use and other relevant sectors enhanced

Component 1 addresses the institutional barriers to ETF-compliant AFOLU MRV by improving stakeholders’ awareness, capacities, and coordination.  As noted above, Component 1 focuses on defining Sri Lanka’s reporting commitments and facilitating stakeholder coordination to fulfil those commitments.

Outcome 1.1: Institutional arrangements coordinating information and data collection from the agriculture and land use sectors into ETF processes and reports enhanced.

Output: 1.1.1 Coordination mechanism established/strengthened integrating relevant authorities from the agriculture and land use sector into national UNFCCC reporting processes.

#### Activity 1.1.1.1.  Conduct a stakeholder/coordination mapping for AFOLU sectors

While a listing of the agencies linked by function and by information provision related to CC considerations in AFOLU sectors already exists, a detailed mapping with respect to the nature of information and frequency of generation, type of data collection methodology and the details of verification (if any) are not available. This mapping exercise becomes complex due to the fact that nearly 30 different government agencies alone are directly involved. The stakeholder mapping will have to accommodate mitigation and adaptation separately while noting cross-cutting relations. The purpose of this activity to create a detailed understanding and readiness among the different parties involved, without leaving any significant contributors or stakeholders while making ETF compliant MRV framework an institutional priority for each agency.

#### "Activity 1.1.1.2.  Create an AFOLU MRV technical working group (TWG)s and link TWGs to the advisory responsibilities for NCs.

Various extant technical working groups (TWGs) exist on a project-by-project basis, constituting and dissolving with each project, often with limited overlap.  This project will attempt to involve a wide range of stakeholders who are relevant to AFOLU sector including both policy and technical expertise.  The intention is to constitute a group that persists over a wide span of time, which will greatly improve the quality of engagement and the consistency of approach.

The TWG, including any potential sub-committees, will provide relevant technical expertise for the design and conduct of AFOLU MRV approaches during and after this project, including the the roles under activity 1.1.1.2 above.  Input from the working group will not only benefit the technical soundness of MRV approaches and take advantage of existing national capacities, but will also achieve broader and deeper inter-agency engagement in processes pertaining to MEAs and UNFCCC.  CCS will coordinate the membership, activities, and inputs of the TWG.

The composition and focus of the TWG may evolve, but it is currently anticipated that the project will ensure functional working groups or sub-committees for a. crops, b. livestock, c. fisheries,  d. forestry,  e. land-use and land-use change (including issues of land management, tenure, and administration), f. climate-change adaptation, and g. data and information management.  The TWG will comprise members of relevant governmental agencies, academic/ research institutions, private sector, and NGOs/ CSOs representing small-holders or vulnerable groups (at least one representative per sub-committee).  The TWG will directly advise on numerous activities and outputs in this project, such as by recommending cost-effective proxy measures.

#### Activity 1.1.1.3.  Build a framework for CCS to obtain TWG support for ETF transition and management.

This activity will focus on an appropriate institutional scheme that will enable the continuity and active participation of TWG membership. Also, the terms of reference of the TWG to the CCS and vice versa need to be identified for smooth functioning. While the TWG will primarily work on the MRV framework, it will advise on adopting the ETF needs both to the routines of CCS and the procedures of the line agencies. In this respect, the terms of engagement of the TWG with authorities of stakeholder agencies also need to be clarified.

#### Activity 1.1.1.4.  Create multi-party Internal arrangements (agreements/circulars/memo) for relevant data-sharing.

CCS has to play a major part in playing the convenor role among many AFOLU stakeholders in order to achieve the necessary coordination/ management necessities of ETF-compliant MRV.  In addition to liaising with local authorities CCS has to possess the capacity to successfully engage with international agencies, donors, scientific and academic bodies in building links. This activity attempts to first build the necessary capacities relative to (i) establishing systematic data-sharing arrangements between stakeholders, (ii) developing MRV and decision-support capacities related to climate adaptation, and (iii) establishing cost-efficient proxy measures.

Currently, information-sharing and reporting is conducted pursuant to ad hoc requests for information and information gathering visits to various agencies. With respect to data sharing on climate related activities, there are no existing internal arrangements exist between agencies.  The only substantive understanding on data sharing is between the DFC and the national focal point to UNFCCC. This is mainly due to REDD+ activities which involved FRL estimations. In the other AFOLU sectors, reporting relationships across agencies are either weak or non-existent.

#### Activity 1.1.1.5.  Create an online portal for ETF-related information on CCS with mobile uploading capability.

Considering the distance and time constraints related to communicating effectively between central agencies and local offices, the need for an online portal with mobile uploading options was highlighted at the stakeholder workshop.  Such a portal, if configured correctly, will enable conversion of the measurements that the line agencies collect into the format that CCS requires for reporting. On the other hand, a well-designed mobile application can be part of the training of field staff of the relevant agencies. Once measures are recorded, the application can be programmed to automatically convert to the format required by CCS.

#### Output: 1.1.2. Assessment prepared to assess institutional, data collection, analysis and reporting capacity gaps and needs for meeting ETF requirements with specific focus on the  NDC actions for the agriculture, forestry and land-use sectors.

This output will facilitate the broader, deeper, and more systematic engagement of governmental stakeholders across multiple agencies and levels.  This strengthened engagement will not only benefit the MRV processes, but will also help to improve awareness of various agencies’ roles in fulfilling international commitments under MEAs, particularly the Paris Agreement.  When possible, the project will strengthen or consolidate existing coordination mechanisms rather than duplicating them.

#### Activity 1.1.1.1.  Develop a AFOLU MRV assessment framework.

While it is nearly impossible to capture all activities of AFOLU sector in a single analytical /logical framework, it is important to identify the key pathways of emissions and related vulnerabilities. An AFOLU MRV framework will be a laborious exercise compared to similar frameworks in energy or transport sectors. The MRV framework development will have to be conducted through multidisciplinary expertise in the sector using a participatory methodology. AFOLU is an area where national circumstances will emerge very significantly. Measurement routines have to integrate with the existing information collection process but frequencies will have to synchronised. The cross institutional reporting role of the framework will be borne by CCS. Verification steps will need the participation of stakeholders and independent external agencies.

#### Output: 1.1.3. National ETF monitoring and reporting roadmap for the AFOLU sectors prepared and adopted

Activity 1.1.3.1.  Produce an ETF-compliant MRV protocol for the agricultural and land-use sectors.

#### A national AFOLU sector ETF compliant MRV protocol will enable fulfilling the following objectives: (a) Improve monitoring and reporting of activity data and/or emission data; (b) Improve data validation and verification processes; (c) Build awareness and confidence in the estimates for AFOLU sector; (d) Track and document Sri Lanka’s contributions to climate change mitigation and adaptation in AFOLU sectors; (e) Facilitate data sharing among agencies; and (f) Build institutional capacity within CCS with respect to AFOLU sectors.

#### Output: 1.1.4. Capacity developed to clarify measurement and reporting of key NDC information (baselines, Business-As-Usual targets) and support provided for ETF reporting in AFOLUsectors.

#### "Activity 1.1.4.1.  Provide training and necessary capacity for CCS to liaise with AFOLU stakeholders: to train stakeholders to generate data necessary for UNFCCC reporting.

#### Sri Lanka formulated a “Readiness Plan for NDC implementation” in 2016 to identify policy and institutional gaps, as well as the technical capacity and resources required to implement policies and actions under its NDC. The plan is intended to inform the work plan for relevant ministries during the “Readiness Phase” between 2017 and 2019. This period is earmarked for training and capacity building. This activity will carry out a chain of such capacity building efforts in all AFOLU agencies. The agencies will be sensitised to the data requirement for UNFCCC reporting and presented with appropriate terms of engagement with CCS which includes institutional support and training opportunities for the stakeholder agencies.

#### Activity 1.1.4.2.  Create national ETF-complaint reports covering mitigation and adaptation-related activities in accordance with NDC commitments for the AFOLU sector.

This activity identifies the need for a comprehensive reporting framework which is peer-reviewed and subjected to the verification process after a window for public review. The reporting should take into account and treat the following types of reporting requirements separately:

- Statutory reporting: The domestic and international legal obligations placed on administrators to report specific data at specific times within the ‘compliance’ cycle.

- Ad-hoc reporting: requests from internal or external parties interested in specific data queries.

- Progress reporting: the degree of completion in various MRV cycles.

- Annual reporting: summary compilation of mitigation and adaptation related information

#### Output: 1.1.5. Sri Lanka's engagement strengthened in the AFOLU sectors with international transparency-related processes under the UNFCCC.

#### Activity 1.1.5.1.  Publish a peer-reviewed AFOLU sector ETF-compliant MRV document concurrently with National Communications.

. AFOLU MRV document has to be compiled to support the process of national communications. Its release has to be timetables based on the key national reporting requirements to UNFCCC. The ETF compliance has to verified by a review study and best practices in  terms of ETF has to be highlighted and communicated to stakeholders. CCS will conduct a dissemination workshop for release of ETF compliant MRV document.

#### Outcome 1.2 Best practices on ETF reporting processes, information gathering, system infrastructure, methodologies in the agriculture and land-use sectors disseminated to relevant priority sectors (e.g. energy, industry/trade, transportation).

Outputs and activities under Outcome 1.2 complement the sectoral work conducted under Outcome 1.1.  Many of the MRV challenges faced in Sri Lanka’s AFOLU sector are also faced in other sectors as well as by AFOLU counterparts in other countries.  Outcome 1.2 ensures that innovations and lessons learned from this project inform MRV solutions in other sectors and countries, and vice versa.  CCS will coordinate work under this outcome.

Output 1.2.1 Multi-sectoral coordination mechanism strengthened integrating relevant authorities into national UNFCCC reporting processes.

This output addresses the need to increase MRV efficiencies by reducing inter-sectoral redundancies.  Activities under this output will align closely with Outputs 1.1.2 and 1.1.3, particularly Activities 1.1.2.1, 1.1.2.2, and 1.1.2.5.  As a matter of practicality, work under this output will largely be conducted via improved coordination between sectoral TWGs.

Activity 1.2.1.1.  Identify opportunities for inter-sectoral efficiencies and reduce redundancies in measurement and primary data storage.

Various agencies and sectors gather data using resources and methods with which AFOLU MRV can be integrated, thereby improving cost-efficiency and reducing redundancy (e.g., for survey respondents). Such cross-institution learning can be facilitated by a bi-annual stakeholder forum targeting the data and information processing divisions of all agencies in the MRV loop. The practices of each institution need to be documented in terms of methodologies and key indicators. The data storage mechanism also needs to be highlighted. The lessons and highlights of inter-institution consultations will be reported to the TWG for validation and secondary reporting to CCS.

Activity 1.2.1.2.  Ensure that AFOLU data-sharing processes are integrated with broader inter-sectoral and national coordination for data-sharing.

MRV challenges are not unique to AFOLU  sectors. In fact, there are similar problems in other sectors such as energy, transport and waste. This compatibility can be ensured only by CCS since a reliable and regular coordination mechanisms or platforms  between AFOLU sectors and key sectors in NDC are not available under the current institutional setting in Sri Lanka. In particular, the AFOLU portal, data-sharing MOUs, and other approaches should integrate with other sectors’ approaches.  This requires alignment of systems, protocols, and metadata as far as such alignments are within the limits of practical implementation subject to institution mandates.

Activity 1.2.1.3.  Establish QC protocols for collecting, managing, and archiving data.

While a robust collection of data is mandatory for a sound MRV framework, importance of management of database and archiving practices cannot be overstated This activity should not limit itself to ICT infrastructure and data administration which is a basic requirement of the activity. Compilation of data for secondary processing and modelling of data for scenario analysis are also part of quality control and needs guidance from expertise in related areas.

Output 1.2.2 ETF lessons learned from AFOLU sectors monitored, captured, scaled up and shared to enhance wider national reporting.

Activities under this output ensure that lessons learned in enhancing MRV in Sri Lanka’s AFOLU sector also benefit other sectors and countries.  Activities under this output are under the mandate of the national focal point, CCS.

Activity 1.2.2.1.  Conduct bi-annual Stakeholder feedback sessions.

In addition to obtaining regular feedback from stakeholders throughout the project’s implementation, structured stakeholder feedback will be sought explicitly on every six monthly basis.  Feedback will be sought regarding best practices, opportunities for improvement (including regarding quality and efficiency), and approaches to target for up-scaling (sectorally and geographically).  In each instance, feedback will be analyzed and summarized in a succinct report.

Activity 1.2.2.2.  Compile AFOLU MRV best practices with relation to similar practices in other NDC sectors.

A core feature in the  UNFCCC is sharing best practices across boundaries. Reporting across sectors means that best practices in the AFOLU sector benefit other sectors.  Additionally, CCS’s role in coordinating relevant TWGs ensures a convenient inter-sectoral venue for shared best practices.  This activity strengthens that process by formalizing and supporting the identification of best practices (e.g., see 1.2.2.1) and increasing the consistency of TWG membership (e.g., see 1.1.2.1).

Activity 1.2.2.3.  Contribute to efforts via the CBIT global projects to share and up-scale relevant AFOLU MRV best practices and lessons learned.

The specific modes of this activity will depend on the engagement mechanisms established by the CBIT global projects.  The preceding activities ensure that the project is well positioned to contribute to those efforts. The membership and participation of CCS in such regional and international forums will help bring global and regional evidence. It is important that visit reports be compiled and presented within two weeks of such meetings for timely dissemination. The progress of global CBIT projects can also expedite the adoption of tier 2 and tier 3 estimates which are more relevant to NDCs.

Output 1.2.3 Peer exchange program on transparency activities established for relevant priority sectors.

Activity 1.2.3.1.  Create a capacity building and conferencing platform for transparency improving modifications of MRV across sectors

The high priority areas of AFOLU sectors need constant knowledge sharing and updating of the personnel involved. Harmonising peer review protocols and sharing of background studies among different agencies can facilitate the transparency of the MRV practices. Such processes can also ensure the consistency of methods and practices across time and across agencies.

Figure 9 depicts the provisional framework for a MRV portal.  The portal will post ETF-relevant national publications and metadata for linked datasets.  Supporting agencies will provide timely updates to agency-hosted data and to respective links on the portal.  Enhancements to the portal will initially focus on core capabilities for the AFOLU sector, but the enhancements will be designed to be scalable for other sectors, functions, and content.  It is expected that CCS will coordinate enhancement and continued operation of the portal.  The project will coordinate with global CBIT projects to learn from other projects.  This activity will also raise awareness about the portal and how to use it.

National

Agency 5

Agency 4

Agency 2

Agency 1

Agency 3

Data Collection

Agency Databasea

MRV Portal

Sectoral Node

Data Usersb

AFOLU

Energy

Others.

MRV Portal

Public

Research Inst.

Gov. Agencies

Int’l. Agencies

CSOs/ NGOs

Data providers

data dissemination

Figure 9.  Simplified Diagram of Preliminary Structure for Sharing ETF-related Measurement Data

a This diagram simplifies the multi-layered database structure that exists in many agencies.  Most agencies have databases with at least two levels:  one that is publicly inaccessible and one that is publicly accessible (a periodic mirror of a restricted subset of the non-public data).

b For clarity, this diagram omits the dashed lines connecting data users to the sectoral nodes and some publicly accessible agency data.  It is anticipated that data users will be able to access the sectoral nodes directly or via the MRV portal.  Likewise, some agencies’ websites will continue to allow direct public access to some data.

### Component 2

Component 2. Strengthened capacity to measure emissions, removals, and emission-reduction activities from the agricultural and land-use sectors.

Component 2 addresses the barriers to improved measurement of carbon sinks, GHG emissions and removals, and progress related to NDC mitigation activities in the AFOLU sector (compliant with the ETF and the 2006 IPCC Guidelines).  Activities under this component involve generation of appropriate metadata parameters, measurement protocols, and emissions factors, as well as to strengthen decentralized monitoring.  This component also builds the technological and human capacities for QC, measurement, primary data management, and QA.  In short, Component 2 works with various stakeholders to facilitate mitigation-related measurement and verification for the AFOLU sector, whereas Component 1 coordinates between stakeholders to facilitate effective reporting.

#### Outcome 2.1.  Strengthened capacity to estimate  GHG emissions, removals, and emission-reduction activities from agricultural and land-use sectors.

Activities under this outcome will draw substantially from IPCC guidelines, FAO’s Estimating Greenhouse Gas Emissions in Agriculture:  A Manual to Address Data Requirements for Developing Countries (2015). Numerous relevant tools and other resources are available via FAO’s Mitigation of Climate Change in Agriculture (MICCA) program.

Output 2.1.1. Quality-control (QC) protocols established for regular, systematic estimates  of emissions, removals, and emission-reduction activities in the agricultural and land-use sectors.

Activities under this output will ensure systematic, rigorous, consistent protocols for mitigation-related measurement and archiving of relevant data for the AFOLU sector, which will also provide a basis for corresponding validation.  Forestry sector activity data updation to be carried out using 2019 – 2020 satellite imagery to ensure more Protocols stipulate the use of Tier 1 defaults for non-key categories or for periods of transition to more rigorous and transparent QC/QA systems

Activity 2.1.1.1.  Establish data entry templates and specifiy updating frequency for partner agencies to match with national GHG inventory/ reporting cycles.

QC protocols define how required data will be collected, when (e.g., timing, circumstances), where, and by whom.  They include methodological guidelines on sampling, technology, and data-handling.  QC protocols also define capacity requirements, such as the technical skills required for various roles associated with data collection.  QC protocols will be developed in close collaboration with the establishment of (meta)data parameters (Activity 2.1.1.1). This activity will work with stakeholders to establish metadata parameters for the metrics, fields, types, frequencies, formats, etc. for the data to be collected and provided.  Metadata parameters will be established for both primary and proxy measures .

Activity 2.1.1.2.  Estimate resource requirements and sources for initial and sustained support (e.g., technology, personnel, funding, etc.).

This activity builds on the investment framework of the National Climate change Mitigation strategy and informs those estimates of resource requirements and sources.  The technical specificity under this output enables more precise estimates of necessary resources for near-term and steady-state measurement and data-archiving.  These estimates will aim to ensure the financial sustainability of the system by proposing cost-efficient approaches (including proxy measures, reduced redundancy, engagement with diverse stakeholders, etc.) and reliable, adequate, and preferably diverse sources of resource support (including technology, personnel, funding, on-going updating of skills, operation, maintenance, recapitalization, etc.).

On a regular basis, CCS will estimate the cost of mitigation investments and loss prevention expenses in the AFOLU sectors. CCS will also update the cost of these investments to governmental and private-sector financial institutions, involved in financing “green development” projects. However, in this regard, CCS potentially lack technical expertise to assess relevant environmental benefits and risks to perform cost-benefit analysis.  CCS will seek to identify pragmatic metrics that borrowers and financial institutions might use to substantiate and facilitate such investments and inform related financial considerations (e.g., including loan conditions, rate reductions, risk assessments for due diligence valuations, etc.).

Activity 2.1.1.3.  Draft AFOLU ETF data-provision guidelines.  (related to Output 1.1.3.)

This activity will formalize guidelines to agencies and stakeholders for reporting or providing ETF-related data for the AFOLU sector (and potentially for other sectors).  These data-reporting guidelines will indicate which agencies are expected to provide what types of data, as well as standards for methods, data quality, frequency, formatting, etc.  The project will work to strengthen the commitments of data-providing agencies as well as the associated mechanisms for enabling and accountability

Output 2.1.2. Information technology systems upgraded to integrate, analyze, and archive diverse data types.

Activity 2.1.2.1.  Develop a dedicated ICT infrastructure for parallel updating by stakeholder and partner institutions with appropriate security clearances

The stakeholder workshop highlighted the absence of adequate and reliable ICT infrastructure to host a database capable of real time updating at CCS. It is not only storing data but also a setting which can be managed by an appropriately decentralised administrative platform. Also, necessary improvements pertain to data connectivity and integration of a broader range of geospatial and non-geospatial data.  Technological upgrades of the database and the ICT infrastructure will be supported by capacity development as needed.

Output 2.1.3. Capacity and technology upgraded in relevant institutions to strengthen mitigation-related MRV, including country-specific emissions factors, activity data, and Tier 2 reporting for key sub-categories in the agriculture, forestry and land-use sectors.  (Coordinates with 3.1.3.)

In coordination with activities under Output 3.1.3, activities under this output will ensure that relevant agencies have the technology and knowledge to follow the protocols established under Outputs 1.1.3 and 2.1.1.

Activity 2.1.3.1.  Update forest cover maps, develop allometric equations for updated estimates of emission from source and removals from sinks in forestry sector

This activity will focus on updating forest cover map of Sri Lanka and will provide foundation for updating emission and removal capacity from forestry sector. At present Sri Lanka uses year 2010 forest cover map which is very old. Forest Department is conducting National Forest Inventory which is expected to be completed in three years. This activity will also support current on-going initiatives of forest department and will have incremental benefits in forest carbon estimation using non-destructive methods. It will also lead to updating Forest Reference Level of Sri Lanka which was submitted to UNFCCC in year 2017.

Activity 2.1.3.2. Capacity development for three priority key categories

Referring to the paragraph 16,17, 28, 29 and 56, the project will contribute to capacity building for three key categories i.e, Enteric fermentation, CH4 Emission from rice cultivation and Urea application. Currently Sri Lanka is using default emission factor and country feels that it needs to be updated using national parameters.

Activity 2.1.3.3.  Provide relevant stakeholders with the equipment and software necessary for decentralized data collection, storage, and uploading in line with data-provision guidelines

This activity accords with recommendations made by the participants at the stakeholder workshop.  It will facilitate an efficient technological and operational approach, such as by aligning existing and MRV/ ETF-related operations and technologies to reduce redundancies.  For efficiency and data accuracy, when possible, the project will use technology that entails automatic uploading and synchronization from data-collection hardware to primary databases.  These procurement activities need to be fast tracked under special permissions and generated through the TWG.

Activity 2.1.3.4.  Produce training materials, including materials for training of trainers, for associated technologies and QC protocols.

Currently, there is no standard training and development guidelines for human resources involved in MRV related reporting in climate change mitigation. Different agencies receive various technical training exposure opportunities mostly organised by international agencies such as FAO. In-house protocols are sometimes developed but not validated by outside parties. The same is true about QC protocols. There are numerous instances of training manuals developed through various projects but not adopted consistently due to the absence of a broad validating process, In this regard, it is also important to develop the expert guidelines to perform the roles of trainers within the agencies and CCS.

Activity 2.1.3.5.  Conduct training of relevant stakeholders, including training of trainers, to enable measurements in line with data-provision guidelines.

As highlighted in activity 2.1.3.2., training sessions should be planned for data collecting personnel and officers in AFOLU sector related mitigation activities. CCS representation in such training sessions is also necessary in order to maintain consistency of training protocols. It is important that training related to MRV follow a systematic path with various levels of human resources trained according to the respective role in the MRV chain.

Output 2.1.4. Relevant measures validated and piloted for key mitigation sub-categories in the agriculture, forestry and other land-use sectors.

Activities under this output pilot and validate proposed measures in order to identify technical and operational issues (e.g., challenges and opportunities for improvement) and calibrate proxy measures.

Activity 2.1.4.1.  Commission meta-analysis studies to review relevant research literature to determine provisional Tier 2 estimates where possible and, as needed, uncertainty assessments for estimates in key sub-categories.

This activity suggests conducting reviews, met-analyses and validation studies to generate provisional estimates of emissions factors that are more appropriate for national circumstances and sub-categories than are the global Tier 1 estimates. Even in the previous National Communication by Sri Lanka, provisional estimates equivalent to Tier 1 have been discussed.  A comprehensive review provides a solid basis for Tier 2 estimations and validation of nationally conducted estimates of emissions factors, which would be expected to be more or less in line with prior research findings. This activity can be started with Forestry sector activity data to move from tier 1 to tier 2 through linking/supporting AE development.

Activity 2.1.4.2.  Conduct pilot tests of measurement protocols and revise protocols as needed.

It is necessary to pilot the MRV protocols developed, specially, in the mitigation activities, because of instrumentation and scientific guidelines used. A piloting process will illustrate the process to the diverse agencies involved in the AFOLU sector. Since most authorities in the AFOLU sector  do not have experience in Climate change mitigation reporting, demonstrations are crucial once the personnel are trained.

Activity 2.1.4.3.  Conduct validation pilot studies of proxy measures and introduce an updating frequency for proxy measures.

It is necessary to pilot the MRV protocols developed, specially, in the mitigation activities, because of instrumentation and scientific guidelines used. A piloting process will illustrate the process to the diverse agencies involved in the AFOLU sector. Since most authorities in the AFOLU sector  do not have experience in Climate change mitigation reporting, demonstrations are crucial once the personnel are trained.

Activity 2.1.4.4.  Conduct preliminary validations of proxy measures.

This activity establishes the accuracy and reliability of proposed proxy measures as compared to more rigorous (primary) measurement methods with known or calibrated validities. Proxy measures are regularly updated in global and local literature. Their validity is often limited to the sample that is used in the respective study. A common issue is the generalizability of such measures to different context. Therefore, there is a need to validate appropriately. The generation of tier 2 level factors will benefit from this activity. This activity coordinates with Outputs 1.1.3, and 2.1.1.

### Component 3

Component 3. Strengthened capacity to measure climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors.

Whereas Component 2 builds capacities for improved measurement of climate-change mitigation, Component 3 builds the corresponding capacities for climate-change adaptation.  Adaptation-related reporting is encouraged under the Paris Agreement and effectively tracking adaption progress is critical for informing climate-related policies, which largely focus on adaptation issues and are closely linked to strategies for socio-economic development.  Importantly, this component will ensure that there is capacity to establish specific, well informed targets and indicators on adaptation which are specific to Sri Lanka. Enhanced capacity will enable the AFOLU sectors achieve goals specified in National Adaptation Plan for Climate Change Impacts for Sri Lanka 2016 – 2025 (NAP).

#### Outcome 3.1. Strengthened capacity to measure climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors.

Activities under this outcome will improve the quality of information that influences decisions on climate-change adaptation.  This outcome establishes a nationally appropriate measurement framework and develops relevant capacities in order to provide stakeholders with relevant, accurate, timely, efficient, and well-structured information.  Activities under this outcome will draw substantially from FAO’s Tracking Adaptation in Agricultural Sectors:  Climate Change Adaptation Indicators (2017).

Output 3.1.1.  Measurement framework developed for climate-change impacts, vulnerabilities, and adaptation-related activities prioritized in the NDC for the agriculture, forestry  and land-use sectors.

Activities under this output will ensure systematic, rigorous, consistent protocols for adaptation-related measurement and archiving of relevant data for the AFOLU sector.  As with the corresponding mitigation-related activities under Output 2.1.1, activities under this output will strive for cost-efficiency through the identification and use of proxy measures and through reduced operational redundancies (e.g., common definitions, non-overlapping mandates for data-provision, alignment between CCA and CCM protocols, alignment with other data-collection initiatives, etc.)

Activities under this output rely on guidance from activities under Output 1.1.3 and coordinate with activities under Output 2.1.1.

"Activity 3.1.1.1.  Generate a typology of adaptation processes in AFOLU sectors using expertise in adaptation-related sciences and multi-disciplinary expertise.

Sri Lanka’s framework for measuring and reporting  the status and trends of factors related to climate-change adaptation is not as developed as the framework for climate-change mitigation.  This difference has been due in part to two major factors.  First, climate-change adaptation is less amenable to standardized approaches that are often available for climate-change mitigation (e.g., technologies, reporting frameworks, global and regional default emissions factors, etc.).  Adaptation in large part requires country-specific initiatives and measurement frameworks.  Although standardized international M&E tools are available for project-based adaptation interventions, they are in most cases designed to facilitate aggregation of generalized outcomes across an international portfolio rather than to track progress on specific national goals or to inform specific decisions at national and sub-national levels.  Thus, a developing country-appropriate M&R framework typically requires more efforts to formulate with respect to adaptation than mitigation.  Second, so far, relatively more international support has been available for mitigation.

Even so, numerous documents are available to guide countries in addressing the challenges of establishing tailored M&R framework for adaptation.  Table 6 presents several resources that are expected to inform the delivery of Component 3.  The listed resources highlight the need to establish a national M&R framework and indicators that can be applied at different levels (national to local) for different stakeholders (e.g., ministries, local  government, international donor project teams, etc.) to inform an array of relevant decisions.

- Table 6.  References to Inform the Design of Measurement Frameworks for Climate-change Adaptation

| - Reference | - Topic(s) | - Level | - Sector - (intended users) |
| --- | --- | --- | --- |
| Tracking Adaptation in Agricultural Sectors: Climate Change Adaptation Indicators (FAO, 2017) | Methods and indicators for tracking climate-change adaptation | National and sub-national | AFOLU (national decision-makers and MRV practitioners) |
| Monitoring and reporting toolkit of PPCR (CIF, 2015) | Processes related to adaptation planning and mainstreaming | National and program/ project level | Multi-sectoral (national policy-makers) |
| Framework for the assessment of skills for national adaptation planning (Mackay et al., 2015) | Assessment of capacities to design NAP processes | National | Multi-sectoral (stakeholders involved in NAP processes) |
| Stocktaking for national adaptation planning (SNAP) tool (GIZ, 2014) | Self-assessment of capacities to undertake NAP processes | National | Multi-sectoral (stakeholders involved in NAP processes) |
| Tool for monitoring progress, effectiveness, and gaps (PEG) under NAP processes (UNFCCC, 2015) | Assessment of the essential functions of NAP processes | National | Multi-sectoral (stakeholders involved in NAP processes) |
| Index for risk assessment (INFORM) (De Groeve et al., 2015) | Assessment of country resilience and ranking | National | Multi-sectoral (national decision-makers and international organizations) |
| Framework on making adaptation count (Spearman and McGray, 2011) | Monitoring and evaluation of adaptation processes and outcomes | National and local | Multi-sectoral (adaptation practitioners) |
| Tracking adaptation and measuring development (TAMD) approach (Brooks et al., 2011) | Monitoring of climate risk management processes and outcomes | National and local | Multi-sectoral (adaptation practitioners) |
| The Vulnerability Sourcebook (Fritzsche et al., 2014) | Changes in outcomes, with a specific focus on vulnerability | National and sub-national | Multi-sectoral (adaptation practitioners) |
| Impact evaluation guidebook for climate change adaptation projects (GIZ, 2015) | Assessment of adaptation interventions contributing to a given outcome | National | Multi-sectoral (adaptation practitioners) |
| Participatory monitoring, evaluation, reflection and learning (PMERL) for community-based adaptation (CARE International, 2014) | Participatory monitoring, evaluation, reflection and learning to help design and implement community-based adaptation | Community | Multi-sectoral (communities) |
| Resilience index measurement and analysis (RIMA) (FAO, 2016) | Assessment of households’ reactions to shocks and stressors | Household | Agriculture (households) |
| Self-evaluation and holistic assessment of climate resilience of farmers and pastoralists (SHARP) (FAO, 2015) | Farmers’ self-evaluations to assess resilience | Program/ project (household/ community) | Agriculture (farmers and pastoralists) |
| Adaptation monitoring and assessment tool (AMAT) (GEF, 2012) | Assessment of project-specific processes, outputs, and outcomes | Program/ project | Multi-sectoral (GEF projects’ executing partners) |
| Strengthening Monitoring and Evaluation of Climate Change Adaptation (GEF STAP, 2017) | M&E challenges and frameworks | Program/ project | Multi-sectoral (development agencies and financial institutions) |
| International and Donor Agency Portfolio Evaluations: Trends in Monitoring and Evaluation of Climate Change Adaptation Programmes (Sea Change & UKCIP, 2017) | Trends in M&E approaches from donor and development agencies | Program/ project | Multi-sectoral (donor agencies and development agencies) |
| Guidance Note 1: Twelve Reasons Why Climate Change Adaptation M&E is Challenging (Sea Change & UKCIP, 2014) | Strategies for addressing common challenges for CCA M&E | Program/ project | Multi-sectoral (donor agencies and development agencies) |
| Guidance Note 2: Selecting Indicators for Climate Change Adaptation Programming (Sea Change & UKCIP, 2014) | Considerations and frameworks for CCA indicators | Program/ project | Multi-sectoral (donor agencies and development agencies) |
| Guidance Note 3: Theory of Change Approach to Climate Change Adaptation Programming (Sea Change & UKCIP, 2014) | How to apply a “Theory of Change” approach to designing CCA projects and programs | Program/ project | Multi-sectoral (donor agencies and development agencies) |

Activity 3.1.1.2.  Develop an analytical framework to assess adaptation challenges and opportunities in AFOLU sector through a stakeholder consultation.

Sri Lanka stands at fourth position in the Global Climate Risk Index in 2018 for vulnerability to climate change and natural disasters. The vulnerabilities are multifaceted and overlapping. Separating those relevant to AFOLU sectors and identifying as challenges and opportunities could be challenging depending on data availability on adaptation. The activity is aimed at specifically defining the data requirements for the CCA measurement framework.  The upstream and downstream adaptation opportunities will be listed clearly with respect to climate change scenarios in AFOLU sectors. This activity should be performed at a sufficient level of disaggregation and detail focusing on priority settings in order to be useful for implementation. The process of MRV development for adaptation is inherently complicated compared to the same for mitigation since the freedom to use proxies is not necessarily helpful in the adaptation settings.

- Activity  3.1.1.3. Capacity building for development of land use policy and regulations to reduce land and environmental degradation

- This is one of the prime important activities in Sri Lanka to reduce land and environmental degradation and create awareness for better land use planning. This activity will result in better planned policy inputs and planned development.

- Activity  3.1.1.4.  Development of Good Practice Guidelines for land use planning

- Good Practice Guidelines for land use planning will help in bringing more scientific and advanced environmental dimensions to protect environmental degradation. This activity will also provide better scientific inputs for reduction of consequences (environmental and soci-economical) from natural hazards, soil loss, impacts on hydrologic systems, ecological degradations etc.

- Activity  3.1.1.5.  Conduct an assessment of vulnerability based on a revalidation of agroecological zoning

The stakeholder workshop highlighted the need to update the agro-ecological zones, building on the same focus listed in Sri Lanka’s NDCs.  It was argued that with climate change, the conditions under which the above zoning was documented have changed and the existing parameters of determining the zones are not helpful in land use planning. The current classification of agroecological zones considers three-man criteria as the basis. Of these, the precipitation parameter is the one which merits a relook for classification. Especially in the agricultural sector, the type of vegetation suited for each of the 46 zonal identities is dynamically evolving as the climate conditions evolve over time. It is important that the reclassifications be considered in sufficiently long intervals to keep up with the changing conditions.

Activity 3.1.1.6.  Estimate resource requirements and sources for initial and sustained support (e.g., technology, personnel, funding, etc.) for MRV of adaptation activities in AFOLU sectors.

As Sri Lanka’s climate related risk exposure rises in comparison to other countries in the world, various estimates of adaptation costs have emerged. In the ADB funded project in formulating National Climate Change Adaptation Strategy for Sri Lanka (2011 to 2016), a total cost was estimated to LKR 47 billion over the five years. The MRV component was not identified in isolation in the above costing. Therefore, it is important to estimate the cost of MRV process capable of streamlining adaptation activities into the CC strategy of the country. As in the case of institutional mapping, the costing of adaptation is inherently harder compared to the same valuation with respect to mitigation. The technical specificity under this output enables more precise estimates of necessary resources for near-term and longer term.  This activity should lead to prioritizing cost-efficient approaches (including proxy measures, reduced redundancy, engagement with diverse stakeholders, etc.) and reliable, adequate, and preferably diverse sources of resource support (including technology, personnel, funding, skills-upgrades, operation, maintenance etc.).

For the already prioritised adaptation technologies, a scaling up plan should be identified for implementation based on  location specific cost-benefit analyses.  Among the 9 technologies, two technologies  in  particular are amenable for rapid implementation, namely,  Rain Water Harvesting and Solar-powered Drip Irrigation. It is important to identify the public and private investments needed in these and others as part of the scaling up exercise. With respect to MRV process, it is important to classify these and other adaptation technologies in conjunction with their potential activity data since the application of adaptation technologies are not always publicly observable, and even when observable, the incremental contribution to climate impacts  will be hard to measure.

Activity 3.1.1.7.  Prepare knowledge-management plan, products and demonstrate for adaptation activities.

A key aspect of success in adaptation planning is building awareness and generating critical information on alternatives available to stakeholders. This is ensured through multiple strategies. From basic information dissemination to public to introduction climate information products, the scope of knowledge management can be relevant in all adaptation and mitigation work. In addition, specialised support services such as climate indexed insurance play a vital role in adapting to CC, and knowledge and information of such services should be readily available. Knowledge management products and its demonstration will be carried out under this activity.

Output 3.1.2. Information technology systems upgraded to integrate and analyze adaptation-related data.

Activity 3.1.2.1.  Develop an information system onCC adaptation priorities at national and local levels by development initiatives as a preliminary adaptation safeguards check for development projects

This activity refers to an intermediate result of the MRV process. The initial situation will be assessed by Baseline information surveys and database that CCS can update need to be established with respect to sectoral divisions and geographical identity. Such a database can offer numerous indirect benefits such as acting as a baseline and a sample frame for future analysis of adaptation impacts.

Output 3.1.3. Capacity and technology upgraded in relevant institutions to strengthen M&R for adaptation priorities identified in the NDC for the agricultural and land-use sectors.  (Coordinates with 2.1.3.)

This output ensures that relevant agencies and institutions have the technology and training they need to fulfil their responsibilities towards CC adaptation in general while ably contributing to the Adaptation specific NDC activities.

Activity 3.1.3.1.  Provide relevant stakeholders with the equipment and software necessary for decentralized data collection, storage, and uploading in line with data-provision guidelines

For efficiency and data accuracy, when possible, the project will use technology that facilitates automatic uploading and synchronization from data-collection modalities to primary databases. This aspect was identified as highly lacking by the stakeholders. A data-sharing ICT platform is not available as of now. Also missing are efficient data-recording equipment that enables automatic and effortless transfer of data to central database.

Activity 3.1.3.2.  Produce training materials, including materials for training of trainers, for QC and associated technologies.

Adaptation-related training programming and relevant MRV practices are lacking in the public sector agencies involved in the AFOLU sectors due to poor sensitisation of the methodologies and content of training provided to technical personnel. This is due to lack of a suitable platform to share experience gained from the existing training opportunities provided by various international agencies on an ad-hoc basis. The physical separation and isolation of agencies working in related topics also contribute to weak peer learning. It is important that training be organised using an integrated methodology which enables relating different training opportunities to each other and there are sequential improvement in objectives of training. Equally crucial is the need to create opportunities for personnel to display the benefits of training by combining training to earmarked tasks relevant to the training.

Development of training material should be performed in consultation with relevant expertise in CC adaptation including resource persons trained in adaptation related to AFOLU sectors. CCS will collaborate with each line agency for training needs and share the contents of training through MOUs that will establish the continuity of such training programs .

Activity 3.1.3.3.  Conduct training of relevant stakeholders, including training of trainers, to enable measurements in line with data-provision guidelines.

Measurement compatibility across AFOLU sectors will be facilitated through a sequence  of training programs aimed at building coaching capacity within institutes though creating ToTs. Training will have to be carried out by the international agencies such as FAO under the guidance of MRV expertise. It is important to obtain third party support and guidance from academia and research community also in developing ToT programs

Output 3.1.4. Relevant measures validated and piloted for adaptation priorities identified in the NDC for the agricultural and land-use sectors.

Delivery of this output will coordinate closely with delivery of Output 2.1.4.  As with Output 2.1.4, preparation and capacitation to conduct mitigation-related measurements will be supported by project funds and co-financing, whereas nation-wide measurements will be funded primarily via co-financing.

Activity 3.1.4.1.  Review relevant research literature to determine provisional estimates where possible and conduct uncertainty assessments for estimates for key indicators.

This activity serves multiple purposes.  First, it gives a sense of common approaches and options for addressing national CCA measurement needs, including ideas for proxy measures.  Second, it provides interim estimates so that limited resources can be directed to important measures for which estimates are currently unavailable.  Third, the review gives a sense of an expected range for national measures, such that an outlier or erroneous measure would draw more scrutiny.  Fourth, the uncertainty estimates from this activity provide decision-makers with a sense of the degree of precision the estimates afford for pragmatic decisions.

Activity 3.1.4.2.  Conduct pilot tests of measurement protocols and revise protocols as needed.

This activity will be conducted in close collaboration with the corresponding piloting for CCM (Activity 2.1.4.3).  These pilot tests will help identify best practices and opportunities for improvement of the documented protocols for measurements.  Pilot testing will also enable training of the field staff before the full implementation of the MRV in the AFOLU sector.

Activity 3.1.4.3.  Conduct preliminary validations of proxy measures.

There are number of grey areas with relation to the AFOLU sectors and activities that come under them. For instance, with respect to Agriculture, provisional estimates on home garden fertiliser use, soil management practices in perennial and plantations crops, use of carbon trapping soil improvements such as bio-char are all poorly defined areas of climate impact. Environmentally-Adaptive and resource conserving technologies are also a key component of adaptation. The emission or removal factors associated with such innovations are also necessary to be established based on empirical tests and subsequent validation.

## Alignment and Strategic Fit

### Alignment with national priorities

This project directly assists Sri Lanka’s in fulfilling its commitments under the Paris Agreement and UNFCCC.  The project’s objective and outcomes also directly support several domestic priorities and initiatives, including:

Sri Lanka NEXT - A Blue Green Era (2016) initiated to support a “blue-green” development strategy to help Sri Lanka sustainably manage its vast marine and coastal resources, whilst identifying actions for low carbon development in key sectors. “Blue development” strategy involves enhancing offshore wind and oceanic thermal energy conversation; sustainable utilization of oceanic fish and other marine biological resources; explore oceanic mineral resources. “Green” development involves scaling up green energy generation; sustainable agriculture; green buildings and transport; and eco-friendly industrial production.

National climate change strategy : National Climate Change Policy was developed in 2012 to highlight the country’s most pressing climate concerns and outlines several principles that should be considered when developing actions in NDC priority sectors such as energy, transport, industry, waste management, as well as other sectors, such as agriculture and livestock. As a policy relevant to a vibrant topic in global environment and development dialogue, climate change policy has seen many useful developments over the last 15 years. While the policy has evolved, its linkages to other policies and ordinances have not received equal attention.

National Heritage Wilderness Area Act No. 3 of 1988: This act was enacted to enable the preservation of unique natural ecosystems under the jurisdiction of the Forest Department. Thus far, only Sinharaja forest has been declared under this Act.

Fauna and Flora Protection Ordinance (revised in 2009, Act No. 22 of 2009): This act has formalised the preparation of management plans for the national reserves or sanctuaries mandatory, establishes buffer zones for PAs, and contains many other new features that facilitate an efficient management of reserves by the DWLC. There have been many amendments to this Act for the purpose of strengthening it, but enforcement remains fairly weak with regard to protected species and encroachments.

National Environmental Act (2000): The NEA served to create the Central Environmental Authority, while its amendment of 1988 empowers all project approving agencies to obtain an EIA for prescribed developmental projects from any developer (including the State). The NEA provides for the establishment of District Environmental Agencies (DEAs) in each administrative district for devolution of powers to the regions in relation to environmental management through the Provincial Councils and the DEAs.

Soil Conservation Act, 1996: This act empowers the Minister of Agriculture to declare and acquire “erodible areas’; to specify measures regulating the use of land in such areas; and to acquire land for carrying out measures to prevent erosion. Deficiencies in the original Act have been rectified in the Amended Act of 1996. Accordingly, there has also been a shift of focus from the control of soil erosion to land resource management, while covering damage by floods, stream bank erosion, salinity, alkalinity and water logging.

National Agricultural Policy of 2007: Amongst other matters, this policy promotes home gardening and urban agriculture to enhance household nutrition and income; conservation of water resources, efficient water management and soil moisture retention techniques; prevention of water pollution from agriculture; adhering to the National Land Use Policy when allocating land for cultivation purposes; land conservation within watershed areas; enforcing the provisions of the Soil Conservation Act; and facilitating exchange of relevant knowledge among the farming community.

National Environmental Policy of 2003: This policy aims to ensure sound environmental management within a framework of sustainable development in the country to balance the needs for social and economic development and environment integrity. It presents the course of action to be taken by Sri Lanka for safeguarding the environment and ensuring that economic development is sustainable. The policy addresses environmental dimensions under conservation and management of four basic groupings of  natural resources, namely: land, water, atmosphere and biological diversity

### Alignment with GEF priorities

This project directly contributes to achieving CBIT’s goals.  Namely, as is manifest in the above description of the project’s activities and outputs, the project (i) strengthens national institutions for transparency-related activities in line with national priorities, (ii) provides relevant tools, training, and assistance for meeting the provisions stipulated in Article 13 of the Paris Agreement, and (iii) assists Sri Lanka in improving the transparency of climate-related MRV over time.  The project also directly contributes to GEF-6’s Climate Change Mitigation focal-area objectives in line with Indicator 3:  “MRV systems for emissions reductions in place and reporting verified data.”

Under global CC related conventions, Sri Lanka is part of programming under the following conventions and covenants: Convention on Biological Diversity (1992) , Convention on Wetlands of International Importance (1971), Convention concerning the protection of the World Cultural and Natural Heritage (1972), United Nations Framework Convention on Climate Change (1992), Vienna Convention for the Protection of the Ozone Layer (1985), Montreal Protocol on Substances that deplete the Ozone Layer (1987), Kyoto Protocol on Climate Change , Convention on International Trade in Endangered Species Of Wild Fauna and Flora (1973), International Plant Protection Convention 1952 and United Nations Convention to combat Desertification  (1996).

### Alignment with FAO priorities

The project aligns primarily with FAO’s Strategic Objective 2, which is to increase and improve provision of goods and services from agriculture, forestry and fisheries in a sustainable manner.  In particular, the project aligns with:

  - Organizational Outcome 2.3: stakeholders endorse/adopt international (including regional) instruments and support related governance mechanisms for sustainable agricultural production systems;

  - Organizational Outcome 2.4: stakeholders make evidence-based decisions in the planning and management of the agricultural sectors and natural resources to support the transition to sustainable agricultural sector production systems through monitoring, statistics, assessment and analysis.

In particular, the project will serve to deliver the following outputs:

  - Organizational Output 2.3.2: capacities of institutions strengthened to implement policies and international instruments that foster sustainable production and address climate change and environmental degradation;

  - Organizational Output 2.4.2: capacities of institutions are strengthened to collect, analyse and report data for decision-making on sustainable production, climate change and environmental degradation, including relevant SDGs, notably goals 2, 7, 12, 13, 14 and 15.

## Institutional Stakeholders and Baseline Initiatives

The baseline initiatives to address the identified barriers and root causes comprise both institutional programs (i.e., institutional mandates and long-term initiatives) and discrete projects—overviews of which are presented below.

### Institutional programs

The climate agenda of Sri Lanka is guided by two overarching policies: (a)  National Climate Change Policy, which outlines key principles that should be considered when developing climate actions in the energy, transport, industry, waste and agricultural sectors; and (b) “Sri Lanka NEXT - A Blue Green Era” Program, which identifies priority technologies and subsectors for a low carbon economy based on the country’s sustainable development priorities. Sri Lanka plans to achieve its NDC goals from 2021 to 2030, after following a readiness phase for NDC implementation from 2017 to 2020.

The Ministry of Mahaweli Development and Environment is the designated national institutions for CC related commitments. It has established a planning and monitoring committee, consisting of officials of the central and provincial governments, scientists and research groups to inform the development of strategic policies and implementation plans for each sector included in the NDC. A “Readiness Plan for Implementation of INDCs was therefore published by MMDE in 2016 to facilitate the implementation process of NDCs by identifying policy and institutional gaps, as well as technical capacity and resources required to implement the NDCs. The plan was developed in consultation with relevant line Ministries that cover all 14 sectors covered by the NDCs

The Ministry of Agriculture oversees national policies and strategies relevant to food production, agricultural extension, policy support, agricultural marketing and agricultural research.  MoA oversees (i) the proper use of raw materials and resources, (ii) production of staples and field crops, (iii) support of value chain functions and agrarian affairs, (iv) strategies and policies to improve productivity, profitability, and competitiveness and to promote sustainable economic growth in the industry.  In addition to policy implementation and coordination, DoA produces estimates related to crops, harvests, and fertilizer usage.

The Department of Meteorology, provides information on weather forecasting, hydro-meteorology, and environmental changes to governmental and private organizations, and coordinates all hydro-meteorological observation networks.  With respect to the scope of adaptation, it is a key provider of data and information on weather for agricultural and fishery sectors. It has its own established MRV framework and regional stations

Department of Census and statistics provides integrated management and coordination of national statistical activities and collects, compiles, processes, and disseminates census and industry survey data. The department has its own data producing channels and also depends on ground staff of other state agencies to generate data. This is the agency with the most comprehensive collection of survey and census based information on the population. With respect to AFOLU sector, DCS surveys on agriculture and the standard household survey captures the land use decisions. DCS surveys use the largest representative samples among alls age agencies and number of other state agencies triangulate their evidence and reporting based on DCS resources.

Survey department administers cadastral database, land database, and land-cover image database, and remote sensed information related to area demarcations. The department carries a heavy mandate as key input provider for land use policy and physical planning. In this sense, it has a direct stake in the MRV process related to CC.

Land Use Policy and Planning department (LUPPD) is the land use policy making arm of the government. It has the mandate to recommend and advise the state on the natural, social and economic impacts of land use decisions and land use conversions. In the MRV protocols of the AFOLU sector, this is a key stakeholder with a large network of regional offices. Its roles are relevant to both mitigation and adaptation activities.

National Physical Planning department (NPPD) is in charge of physical mapping and zoning in the country. It performs the space and resource allocations for prospective development projects nationally and provincially.  Its functions are important to land use decision making and, reciprocally, land use conversion processes are essential inputs to prospective mapping tasks performed. In mitigation related decision making, NPD has a direct role to play and  has a key role in MRV process.

The Department of Disaster Management performs several key functions related to land use planning, i.e. (i) develops environmental legislation on disaster protection, (ii) provides strategic management of disaster-related prevention, preparedness, and recovery, (iii) evaluates disaster-related risks, (iv) builds disaster-related capacities, (v) organizes searches and rescues, (vi) responds to disasters by restoring and rehabilitating the main infrastructures, and (vii) monitors relevant laws and legislation.  DDM coordinates disaster-related activities of various stakeholders, including non-governmental and governmental organizations, the private sector, community groups, and international organizations.

The Department of Animal Production and Health administers the livestock development program including the regular livestock census and researches a wide range of animal-related health issues, including efforts to diagnose, treat, cure, and prevent diseases  in livestock.  Given the role of enteric fermentation in methane released to atmosphere and land use impact of free-range grazing, this institution is a key partner in the MRV efforts for climate change mitigation and adaptation

The NRMC conducts relevant information generation, geo-spatial analysis and research related  to agricultural ecosystems in Sri Lanka. Operating under the DoA, as the custodian center for Soil conservation Act, NRMC is a key institute in agroecological zoning and updating the ecological indicators to support land use decision and policy. NRMC has expertise regarding  environmental assessments, meteorology, hydrology, soil science, and environmental protection technology.

The State Timber Corporation is a state-owned enterprise that oversees forest plantations, forest management, reforestation, and timber development and marketing. It is directly revevant to the forestry sector and indirectly to AFOLU sector. The MRV processes can benefit from STC’s longstanding experience with forest tree seedling establishments, rotational felling and adding value to timber products.

The Water Resources Board conducts research and studies on water-related challenges, including those related to climate change mitigation and adaptation. Given the crucial role water plays in AFOLU sector of Sri Lanka, this board has significant roles to play in planning for surface and underground water resources.

Central Environmental Authority (CEA) is responsible for specifying environmental standards, as well as coordinating/carrying out reports related to the environmental management of natural resources, fisheries, wildlife, forestry and soil conservation. In accordance with the environmental protection standards and other criteria set out by CEA, sectoral agencies are required to submit an environmental impact assessment report to ensure that environmental considerations are integrated into policies and plans.

### Projects

Many of the identified baseline projects address NDC-related priorities.  Therefore, those projects pertain to the ways in which the NDC’s priorities are operationalized, which includes aligning project-based M&E systems with the national approach to climate-related MRV activities.  Because this CBIT project is focused on the agricultural and land-use sub-sectors, this list of relevant projects pertains to the AFOLU sector.  These are the projects with which this CBIT project will most closely coordinate.  However, this CBIT project will also coordinate with climate-related projects in other sectors.  In addition to those listed, this CBIT project will coordinate closely with the CBIT Global Coordination Platform and FAO’s Global Capacity-building Towards Enhanced Transparency in the AFOLU Sector.

### GEF Projects

GEF-UNDP funded National Capacity Needs Self Assessment (NCSA) from 2005- 2006 This project was carried out by the Ministry of Environment. The National Capacity Needs Self Assessment Project (NCSA) resulted in preparation of the NCSA Action Plan based on a thematic assessment of existing capacity to address climate change, biodiversity conservation and land degradation by the Ministry of Environment (and Natural Resources).

Enhancing Biodiversity Conservation and Sustenance of Ecosystem Services in Environmentally Sensitive Areas in Sri Lanka (2013) is a biodiversity focused  project under 	United Nations Development Programme. It aims to To operationalize Environment Sensitive Areas (ESAs) as a mechanism for mainstreaming biodiversity management into development in areas of high conservation significance.

Healthy Landscapes: Managing Agricultural Landscapes in Socio-ecologically Sensitive Areas to Promote Food Security, Well-being and Ecosystem Health (2017) is addressing Biodiversity and Land Degradation in ecologically sensitive areas under UNDP coordination and participation of Ministry of Mahaweli Development and Environment, Mahaweli Authority of Sri Lanka, Ministry of Agriculture, Department of Agriculture,  and Bioversity International.

Third National Communication (TNC) to the UNFCCC (2016) is a project aimed at supporting the CCS to generate the TNC under the coordination of UNDP.

Rehabilitation of Degraded Agricultural Lands in the Central Highlands (2014) is joint project of GEF with FAO to address land degradation in the vulnerable landscapes of the mountainous areas of the country. The MMDE is the coordination partner from the government.

Mainstreaming Agrobiodiversity Conservation and Use in Sri Lankan Agro-ecosystems for Livelihoods and Adaptation to Climate Change (2010) is a joint GEF –UNEP project implemented through The Ministry of Environment and natural Resources, Sri Lanka; Department of Agriculture, Sri Lanka, Platform for Agrobiodiversity Research and Biodiversity International aiming at conserving biodiversity in selected locations of the country.

Protected Areas and Wildlife Conservation Project (2001) was conducted in liaison with ADB and WB in order to promote biodiversity.

### Other UN/MDA projects

UN-REDD:  The UN-REDD National Program will complete its current phase of operations in November 2018.  The program continues to yield significant advances in technical and technological capacities that are well suited to scaling-up to the rest of AFOLU sector, other sectors, and other countries.  Lessons learned to date from UN-REDD in strengthening MRV as a basis for building access to results-based payments will also inform this CBIT project’s guidance on aligning the broader AFOLU MRV approach to facilitate potential future access to international off-set markets (e.g., carbon markets).

Man and the Biosphere Programme (MAB) programme of UNESCO convened by the National Science Foundation (NSF).The Sri Lanka MAB Programme has been in existence since the 1980s. A main aim of this programme is to adopt the MAB concept for management and conservation of forests in four international Biosphere Reserves belonging to Category IX under the IUCN system of classification. These sites are established to promote and demonstrate a balanced relationship between humans and the biosphere, and thereby take a people-centred approach, and are designed to offer solutions to conserving the environment to ensure sustainable development for people through reconciling the objectives of conserving biological resources with sustainable use of the environment and its resources.

Sri Lanka Australia Natural Resources Management Project (SLANRMP): This was a  very comprehensive  initiative for poverty reduction through improved natural resource management in selected areas of the Intermediate and Dry Zone with the participation of local people. Its contributions in the area of improving livelihoods associated with farming and forestry have been prominent in the 1990s. The project was also influential in consolidatinf Sri Lanka’s social forestry program under the extension division of DFC.

Protected Area Management and Wildlife Conservation (PAM&WLC) Project (2001- 2008): This project was carried out by the DWLC to implement participatory adaptive management in pilot protected Areas and to facilitate community participation for buffer zone development. Component D of this project dealt with Sustainable Financing for Community Partnership Building. Under this, a new feature for the DWLC was the establishment or strengthening CBOs in the buffer zones of eight Protected Areas and providing them with micro credit facilities to establish new ventures. CBOs were strengthened with funds from the Protected Area Conservation Fund (PACF) designed to provide assistance to the fringe dwellers around the selected PAs to establish a range of ventures including agriculture development, carpentry work, poultry farming, retail shops, computer training centres, cottage industries and manufacturing dairy products to reduce illegal forest use.

ADB-assisted Plantation Reform Project (1998-2004): Leaseholders were given the right to harvest trees on their premises on prescriptions of management plans approved by the FD through the formulation of 21 Regional Plantation Companies in the latter part of the 1990s and by clustering government-owned tea, coconut and rubber plantations and leasing them on 99-year lease agreements to the private sector.

UNDP-funded Integrated Strategic Environmental Assessment (2009): This was an environmental assessment project carried out by the CEA to prepare zoning plans for development of the under-developed areas including the Northern region after the end of the 30-year internal conflict. The assessment has been completed for Hambantota and Trincomalee Districts. The project had substantive impacts on the AFOLU sectors of the selected areas.

Section 2:  Project Governance and Operational Arrangements

## Stakeholder Engagement

Various stakeholders—including governmental agencies, academic and research institutions, international organizations, and CSOs/ NGOs—have been extensively consulted during this project’s development.  FAO consultants have conducted numerous one to one meeting with the highest government profiles to develop the concept, agree on implementation arrangements, and the specific output relevant to Sri Lanka. The final design of this project was also validated at a workshop with multi stakeholders in February 21st, 2019 . Annex 4 presents the summary report for the workshop conducted. Annex 5 provides the participant list and agenda for that workshop.  As noted below (see Section 2.2.2), various stakeholders will be extensively involved in the delivery of this project via execution partnerships, co-financed activities, representation on the project’s steering committee, Stakeholder Engagement knowledge-sharing, project workshops, etc.

## Project Governance

### Operational mode

Project Management Unit (PMU). The Project Management Unit (PMU) will coordinate the daily execution of the project’s activities. The PMU will be co-located with Climate Unit of Climate Change Secretariat (CCS) under the Ministry of Mahaweli Development and Environment at the National Level and operate through the relevant government departments at the district level Based on delegation from the BH, the PMU will be led by a National Project Manager (NPM)  and will be supported by an Administrative Officer, and a Finance Officer. These three staff will be the core staff within the PMU. The NPM will work closely with the governmental counterpart, the National Project Director (NPD), who will be designated by the government to manage the government’s side of the project’s daily operations.  It is anticipated that the NPD will be a member of CCS.  The National Project Manager (NPM) will facilitate a decision-driven approach to the project’s outcomes, including mitigation-related MRV, adaptation-related M&R, and project-related M&E. The NPM will help to ensure that capacities and systems are developed to produce action-oriented information that efficiently enables stakeholders to achieve national and local climate-related goals, especially those of the NDC.  . During the project inception phase and ongoing implementation, the NPM will identify the specific technical assistance required for the project implementation and strengthen the quality inputs to guide the project towards the intended outcomes.  It is expected that the PMU’s  National Project Manager will split his/ her 20% of time between the PMU’s and FAO’s offices in order to coordinate FAO’s administrative support of the PMU’s operational arrangements. Appendix 6 contains abbreviated, provisional ToRs for members of the PMU.

The PMU will arrange for execution through various forms of agreements (e.g., MOUs, LOAs, contracts, procurement, and coordinated activities) with appropriate stakeholders. The PMU will endeavor, as appropriate and practical, to execute the project’s activities through the stakeholders who will be expected to continue those activities after the project has ended—the post-project responsible stakeholder (PPRS). If the PPRS does not currently have the capacity to deliver the required activities, the PMU will coordinate with the PPRS to establish a transitional plan that enables the project’s activities to be completed while building the capacities of the PPRS. The aim is to ensure that, by the end of the project, the PPRS is fully capacitated to conduct its post-project responsibilities. Ideally, the PPRS will take over those responsibilities prior to the end of the project and any transition of responsibilities will be gradual or phased.

PPRSs will be identified by the PMU in collaboration with the CCS and are anticipated to be primarily governmental agencies (e.g., ministerial subsidiaries) or public institutions (e.g., public universities, public research institutions).  Particularly in cases where the mandates of governmental agencies or public institutions clearly delineate a relevant area of responsibility for the project’s activities, the PMU (or its assignee, as stipulated through an LOA) may propose an execution partner. The PMU will abide by FAO’s guidelines for project execution.  FAO Manual Section 507 (MS507) will govern the PMU’s decisions regarding LOAs.

For activities that do not have a relatively clear PPRS, the PMU will follow a process of competitive bidding, whereby the primary selection factor is value for money both during and after the project and sustainability which entails a consideration of the effective transition of responsibilities to the eventual PPRS. In some cases, project-relevant activities are arranged by governmental agencies, but technically supported through other partners (via governmentally issued contracts or LOAs), such as NGOs or private companies.  In such cases, the PMU will consult with the NPD, Project Steering Committee (PSC) and with FAO in its implementing role to determine the best option by taking into consideration of the risks, policies, and controls of the potential PPRS intermediary.

The PMU will seek to strengthen governmental engagement with relevant CSOs where necessary by engaging with them for execution activities during and after the project when practicable and appropriate.  However, specific CSOs, NGOs, and private companies cannot be identified as PPRSs. Such PPRS functions must be designated as a class of stakeholders for which any agreements are competitive.

The PMU will be supervised technically by FAO Lead Technical Officer (LTO) and operationally by Budget Holder (BH).  The PMU will also be technically supported by the three Technical Working Group (TWG) and will be operationally advised by the National Mitigation Advisory Committee and National Adaptation Advisory Committee through the preparation of the work plan and operational matters.

Technical Working Group: This project will form and work with Technical Working Groups ( which comprises the government agencies, private sector, academic/ researchers, NGOs and CSOs as appropriate. The project will strengthen their capacity to collect quality data, improve the quality of data analysis and reporting towards the NDCs.

Project Steering Committee (PSC).  This project document establishes the project’s intended and default execution arrangements, including work-plan and budget. However, it is anticipated that national circumstances and stakeholders’ priorities will evolve during the course of the project, requiring some degree of adaptability and flexibility. Flexibility in the project’s approach (including work-plan and budget) is ensured via the Project’s Steering Committee (PSC). The PSC will oversee and coordinate strategic aspects of the project’s execution.  PSC members act as the project’s focal points in their respective institutions. The PMU keeps the NDA informed of the project’s progress via the PSC and as part of normal business operations. Appendix 4 presents the terms of reference (ToR) and provisional membership of the PSC. The PSC will meet biannually (twice a year) and as needed.

GEF Agency.  FAO will act as a trustee of GEF resources, applying a fiduciary standard to ensure efficient delivery of global environmental benefits. FAO will disburse funds and provide technical, operational, and financial oversight throughout the project cycle, and will fulfil annual reporting obligations to GEF Secretariat on the project’s status.

Project Support Services.  FAO’s country office will assist the PMU in providing six-monthly financial reports including a statement of project expenditures to the Project Steering Committee (PSC).  FAO will also assist the PMU in the preparation of budget revisions and in tracking the project’s finances via FAO’s financial management system.

### Institutional framework

Figure 14 depicts an overview of the project’s institutional arrangements. Appendix 4 presents the terms of reference and provisional membership of the PSC. Appendix 5 presents the terms of reference and proposed membership of the TWG.  Appendix 6 presents the abbreviated terms of reference for the members of the PMU.

- Figure 14.  Overview of the Project’s Institutional Arrangements

National Expert Committee

↓ Execution

↑ Implementation

Project Steering Committee

GEF Secretariat

FAO

Ministry of Mahaweli Development and Environment

Project Management Unit

(Climate Chance Secretariat)

Gov. Agencies

Academic & Rsch. Inst.

CSOs

Others

flow of funding

flow of reporting

Technical Working Groups

### FAO’s comparative advantages

This project focuses primarily on the AFOLU sector. The GEF Council has formally recognized FAO’s comparative advantages in matters relating to fisheries, forestry, agriculture, and land management. Among other areas, FAO has extensive expertise and experience in technical areas that are highly relevant to this project, including: climate-change mitigation in agriculture and forestry, climate-change adaptation for agriculture, integrated production systems, grasslands production and maintenance, pastoral management of rangelands, integrated ecosystem management, sustainable land use and land management, land degradation, land degradation assessment in drylands (LADA), indigenous agricultural heritage systems, agricultural policies and practices, conservation agriculture, soil fertility, integrated land and water management, watershed management, global forest resources assessment, wild fire management and control, and sustainable forest management.

FAO has developed and maintains the FAOSTAT database, a global inventory of GHG emissions from the AFOLU sector. FAOSTAT provides Tier 1 default estimates in accordance with IPCC’s 2006 Guidelines using data from the Global Forest Resource Assessment (FRA) and countries’ official reports on agriculture and land-use changes. Additionally, as a technical agency, FAO has specific expertise, tools, and training materials for CCM MRV and GHG-I, such as:

- the suite of tools available through FAO’s program on Mitigation of Climate Change in Agriculture (MICCA) ;

- FAO’s Estimating Greenhouse Gas Emissions in Agriculture:  A Manual to Address Data Requirements for Developing Countries (2015);

- the OpenForis suite of free and open-source software tools that facilitate flexible and efficient data collection, analysis, and reporting;

- OpenForis’s CollectEarth tool, developed initially in the context of REDD+ and adapted through experience under the UN-REDD Programme for application in wider land-use contexts;

- the system for earth observations, data access, processing, and analysis for land-monitoring (SEPAL), which allows users to access powerful cloud-computing resources to query, access, and process satellite data quickly and efficiently for advanced analyses without heavy investment in information technology infrastructure;

- “Building a sustainable national greenhouse gas inventory for Agriculture, Forestry and Other Land Use”, which is FAO’s new e-learning series to guide users in estimating AFOLU emissions following IPCC’s 2006 Guidelines using Tier 1 methods, with practical exercises to apply the acquired knowledge and information in order to transition from the 1996 to the 2006 IPCC Guidelines; and

- FAO’s Ex-Ante Carbon-balance Tool (Ex-ACT), which is an appraisal system that provides estimates of the impact of AFOLU projects, programs, and policies on the carbon-balance.

FAO’s overall capacity in this area is globally recognized, for example, as a service provider through the World Bank’s Forest Carbon Partnership Facility (FCPF). Technical contributions from the NFM/ REDD+ team within FAO will therefore comprise an important part of the implementation approach of this project not only to maintain consistency with progress made on Forest/REDD+ MRV, but also to expand that progress to a wider land-use context.

Importantly, the FAO representation in Sri Lanka is well equipped to:

- fulfil its fiduciary obligations in the financial, administrative, and operational aspects of the project’s implementation and execution;

- act as a neutral platform and honest knowledge broker for national partners to share, discuss, and evaluate viewpoints, helping to find common ground based on evidence, common goals, and shared principles; and

- deploy its networking capacity within FAO, the executive partners, and other stakeholders nationally and locally in order to ensure the project’s success and sustainability.

### Priorities for the inception phase

During the inception phase of the project (i.e., the first six months after the project has become operationally active) the PMU will focus on the following operational activities.

- Recruit the PMU staff.

- Establish the PSC.

- Establish the TWG, including the PSC’s formal endorsement of the TWG’s ToR and membership.

- Review and, as needed, refine the stakeholder-coordination mapping and the MRV assessments from the PPG phase.

- Review of the project’s logical framework and results matrix (e.g., baselines) and draft any refinements for the PSC’s review and endorsement in order to reflect any circumstantial changes since the GEF CEO’s endorsement.

- Draft  Year1 annual work-plan and budget for PTF clearance and further  approval  by the PSC.

- Consolidate activities for the first proposed batch of LOAs and contracts

- Conduct an inception workshop.

- Hold the first PSC meeting.

- In particular, indicators (and related baseline and targets) will be finalized;

- Refine the M&E plan as needed to reflect specific requirements for each indicator (e.g., data collection methods, frequency, responsibilities for data collection and analysis and budget).  Any missing baseline data will also be collected during this time.

- Prepare an inception report and submit its outcome to the PSC (which includes the FAOR).

### Grievance mechanism

FAO facilitates the resolution of concerns of beneficiaries/stakeholders of FAO projects and programmes regarding alleged or potential violations of FAO’s social and environmental commitments and safeguards. For this purpose, concerns may be communicated in accordance with the eligibility criteria, which apply to all FAO programmes and projects. Furthermore, these programmes and projects are required to publicise the mechanism for the receipt and handling of grievances at the local level.

### Disclosure

The disclosure of relevant project information helps stakeholders participate effectively and ensures transparency, which enables the project to remain responsive and relevant.  FAO will disclose information in a timely manner, before appraisal formally begins. The information disclosed will be accessible and culturally appropriate, placing due attention to the specific needs of community groups that may be affected by project implementation, such as literacy, gender, differences in language, and accessibility of technical information or connectivity.

An inception workshop for the project’s design phase was held on 21st Feb 2019 in Colombo Governmental and non-governmental representatives contributed extensively to the project’s design, including via the inception workshops and one to one meetings.  Throughout the project’s design phase, the project’s formulation team consulted extensively with potentially relevant stakeholders.

### Planning and financial management

The total cost of the project is USD 2,659,242 of which USD 863,242 will be financed with a grant from the GEF.

### Financial plan (by components, outcome and co-financiers)

Error! Reference source not found.9 presents the cost per component, outcomes and source of funding based on the confirmed co-financing. All co-financing letters are found in Appendix 7. FAO, as a GEF agency, will be responsible only for the execution of GEF resources and FAO co-financing.

Table 9.  Financial Plan by Component, Outcome, and Co-financier

| Institution | FAO Sri Lanka | Government of Sri Lanka Co-Financing | Total Co-financing | GEF | Total Project financing |
| --- | --- | --- | --- | --- | --- |
| Component 1: | 75,000 | 625,000 | 700,000 | 309,428 | 1,009,428 |
| Component 2: | 70,000 | 440,000 | 510,000 | 232,598 | 742,598 |
| Component 3: | 55,000 | 531,000 | 586,000 | 242,739 | 828,739 |
| Project Management Cost | 0 | 0 | 0 | 78,477 | 78,477 |
| Total Project | 200,000 | 1,596,000 | 1,796,000 | 863,242 | 2,659,242 |

### GEF Contribution

The GEF contribution will support the following: i) hiring full time and part-time consultants that will form part of the PMU; ii) transfers of resources that will be made through Letters of Agreements (LoAs) and/or service contracting; iii) procurements, iv) communications; v) training; vi) travel and vii) activities related to project monitoring and evaluation.

### Government Contribution

The Government’s financial contribution will be in kind and will consist of the following: i) government officials’ time assigned to the CBIT project; ii) office space, meeting services and supplies; and iii) vehicle and general office expenses.

### FAO Contribution

FAO will provide in kind contributions amounting to USD 200,000 will consists of office space and other project support related costs that are not covered by the fees.

### Financial management of and reporting on GEF resources

All financial management and reporting in relation to the GEF resources will be carried out in accordance with FAO’s rules and procedures for the implementation of projects under FAO’s direct execution.

Financial Records: FAO shall maintain a separate account in USD for the Project’s GEF resources showing all income and expenditures. Expenditures incurred in a currency other than US$ shall be converted into US$ at the United Nations operational rate of exchange on the date of the transaction. FAO shall administer the Project in accordance with its regulations, rules, and directives.

Financial Reports: The BH shall prepare six-monthly project expenditure accounts, six monthly finance variation report and final accounts for the Project, showing amount budgeted for the year, amount expended since the beginning of the year, and separately, the un-liquidated obligations as follows:

- Annually: Details of project expenditures on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the Project document, as at 30 June and 31 December each year.

- Final report: Final accounts on completion of the Project on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the Project document.

- A final statement of account in line with FAO Oracle Project budget codes, reflecting actual final expenditures under the Project, when all obligations have been liquidated.

Financial reports for submission to the donor (GEF) will be prepared in accordance with the provisions in the GEF Financial Procedures Agreement and submitted by the FAO Finance Division

Budget Revisions: Budget revisions will be prepared by the BH in accordance with FAO standard guidelines and procedures. The budget revision will take into consideration the status of the implementation of the Project activities towards achieving specific outputs and outcomes. The budget revision will be submitted by BH through FPMIS. The budget revision should be prepared based on field needs and the agreed AWP. The NTC normally prepares the draft budget revision in consultation with the National Project Director and LTO for their reviews and submits to BH, and then BH will submit the budget revision to FAO/GEF Coordination Unit for approval. Budgets are the costed equivalent of the work plan in that they foresee the transformation of inputs into activities and activities into outputs. Budget management, monitoring, and revision are the responsibility of the BH and constitute a substantive, integral, and essential component of project management. The BH is required to carry out at least two budget revisions per year in full consultation with the PTF: (i) in March following the corporate equalization process (explained in the following paragraph), and (ii) in September/October to support work-planning for the following year, to ensure that expenditures that have occurred in the year are adequately covered by the corresponding budget.

Responsibility for Cost Overruns: The BH is authorized to enter into commitments or incur expenditures up to a maximum of 20 percent over and above the annual amount foreseen in the project budget under any budget sub-line provided the total cost of the annual budget is not exceeded.

Any cost overrun (expenditure in excess of the budgeted amount) on a specific budget sub-line over and above the 20 percent flexibility should be discussed with the FAO/GEF Coordination Unit with a view to ascertaining whether it will involve a major change in project scope or design. If it is deemed a minor change, the BH shall prepare a budget revision in accordance with FAO standard procedures. If it involves a major change in the project’s objectives or scope, a budget revision and justification should be prepared by the BH for discussion with the GEF Secretariat.

Savings in one budget sub-line may not be applied to overruns of more than 20 percent in other sub-lines even if the total cost remains unchanged, unless this is specifically authorized by the GEF Coordination Unit upon presentation of the request. In such a case, a revision to the Project document amending the budget will be prepared by the BH. Under no circumstances can expenditures exceed the approved total Project’s budget or be approved beyond the NTE date of the project. Any over-expenditure is the responsibility of the BH.

Audit: The Project shall be subject to the internal and external auditing procedures provided for in FAO financial regulations, rules, and directives and in keeping with the Financial Procedures Agreement between the GEF Trustee and FAO. The audit regime at FAO consists of an external audit provided by the Auditor-General (or persons exercising an equivalent function) of a member nation appointed by the Governing Bodies of the Organization and reporting directly to them, and an internal audit function headed by the FAO Inspector-General who reports directly to the Director-General. This function operates as an integral part of the Organization under policies established by senior management, and furthermore has a reporting line to the governing bodies. Both functions are required under the Basic Texts of FAO, which establish a framework for the terms of reference of each. Internal audits of accounts, records, bank reconciliation, and asset verification take place at FAO field and liaison offices on a cyclical basis.

## Procurement

Careful procurement planning is necessary for securing goods, services and works in a timely manner, on a “Best Value for Money” basis. It requires analysis of needs and constraints, including forecast of the reasonable timeframe required to execute the procurement process. Procurement and delivery of inputs in technical cooperation projects will follow FAO’s rules and regulations for the procurement of supplies, equipment, and services (i.e. Manual Sections 502 and 507). Manual Section 502: “Procurement of Goods, Works and Services” establishes the principles and procedures that apply to procurement of all goods, works and services on behalf of the Organization, in all offices and in all locations, with the exception of the procurement actions described in Procurement Not Governed by Manual Section 502. Manual Section 507 establishes the principles and rules that govern the use of Letters of Agreement by FAO for the timely acquisition of services from eligible entities in a transparent and impartial manner, taking into consideration economy and efficiency to achieve an optimum combination of expected whole life costs and benefits.

As per the guidance in FAO’s Project Cycle Guide, the BH will draw up an annual procurement plan for major items, in collaboration with PMU, which will be the basis of requests for procurement actions during implementation. The first procurement plan will be prepared at the time of project start-up, if not sooner, in close consultation with the NPD and the LTO. The plan will include a description of the goods, works, or services to be procured, estimated budget and source of funding, schedule of procurement activities and proposed method of procurement. In situations where exact information is not yet available, the procurement plan should at least contain reasonable projections that will be corrected as information becomes available.

The PMU shall draft the 12-month procurement plan each year and will submit it to the BH and LTO for clearance prior to submitting to the PSC for review and endorsement together with the AWP/ B and annual financial statement of expenditures report for the next instalment of funds.  The procurement plan is reviewed and updated (if necessary) every six months.

With the approved procurement plan and the work plan, FAO will procure equipment and services in accordance with FAO’s rules and regulations and with the assistance of FAO’s country office.

Letters of Agreement (LoAs) will be signed between FAO and service providers for the implementation of proposed project activities. The Terms of References for LoAs will be prepared by the PMU in consultation with NPD. The PMU, together with the LTO, will be responsible for setting up all necessary LoAs to be defined at the inception phase of project implementation. The LoAs will be administratively managed by the BH. The funds received by the service providers will be used to carry out proposed project activities ensuring alignment and conforming to the rules and procedures of FAO.

## Monitoring and Evaluation (M&E)

As the GEF implementing agency, FAO is responsible for oversight of the project, including efficient delivery that abides by GEF’s and FAO’s guidelines.  Effective monitoring and evaluation (M&E) of the project will be accomplished through (i) regular monitoring and reporting (ii) planned midterm review (MTR) and (iii) planned terminal evaluation. Data collection tools will be developed with the inception phase and be ready to test upon the project implementation commenced.

### Monitoring and reporting

FAO’s GEF Coordination Unit will provide annual Project Implementation Reviews (PIRs) to the GEF Secretariat.  The PIRs update the GEF Secretariat on the project’s progress according to the results matrix, log frame, work-plan, and budget.  PIRs also explain adjustments that have been made to the project’s approach or budget in order to accommodate emerging circumstances.  PIRs are informed by the PTF, technical and operational back-stopping missions, and biannual Project Progress Reports (PPRs), which the PMU provides to the PSC.

FAO achieves layered oversight of the project via the FAOR, PTF, RAP, FAO’s GEF Coordination Unit, FAO’s Legal Department, and FAO’s Office of Evaluation (OED).  Oversight will ensure that the project accomplishes its objective and achieves its targeted benefits through the efficient delivery of the projects agreed outputs, while abiding by GEF’s and FAO’s guidelines.  Oversight also ensures that risks are proactively identified and mitigated, and that the project identifies and capitalizes on opportunities for greater efficacy.

The project’s performance will be assessed based on the delivery of outputs and achievement of the project’s outcomes and objective as defined in the results matrix. The inception report, biannual PPRs, annual PIRs, and the terminal report will be the main reports used by the PTF to monitor and evaluate the project.

The reports to be prepared for the project are:

- Project Inception Report

- Annual work-plans and budgets (AWPs/Bs)

- Biannual Project Progress Reports (PPRs) for FAO

- Annual Project Implementation Reviews (PIRs) for GEF

- Technical reports

- Co-financing reports

- Terminal Report

Project Inception Report.  After both the government and FAO sign the GCP Agreement, an inception workshop should be held as soon as possible.  The PMU will draft the Project Inception Report on the basis of the outcome of inception workshop.  The report will contain important information for stakeholders to discuss during the project’s inception workshop.  In consultation with the PTF, the PMU will finalize the inception report to reflect discussions from the inception workshop and, as needed, further decisions made during the first meeting of the PSC.  The report will re-confirm and elucidate the roles and responsibilities of the project’s main partners, describe progress to date, and describe any changed external conditions that may affect the project’s implementation.  The report will also include a detailed first-year AWP/B and a detailed project monitoring plan. The draft inception report will be cleared by the PTF before it is circulated to the PSC members and submitted to FAO GEF unit. .  The report should be finalized, no later than one month after the project’s inception workshop.  The PMU will upload the final report to FAO’s Field Project Management Information System (FPMIS).

Annual work-plans and budgets (AWPs/Bs).  Each year, the PMU will submit updated AWPs/Bs to the PSC and, thereby, to the BH.  The AWP/B will list the activities as well as corresponding budgets and targets for the up-coming year.  It will also describe any planned activities for monitoring and supervision.  The PMU will draft the AWP/B in consultation with the NPD, PTF, and other relevant stakeholders.  The PMU will draft the first AWP/B and submit it to the inception workshop for discussion, then present it to PSC for review and approval.  Once approved by the PSC approval the AWP/B will be circulated to the  PTF and uploaded to the  FPMIS.

Project Progress Reports (PPRs).  The PMU will prepare six-month PPRs based on the project’s results framework, using FAO PPR template. The purpose of the PPR is to provide regular updates on the project’s progress, including implementation of the project’s risk-mitigation plan.  The PPR identifies and anticipates factors that will impede the project’s efficient implementation, and proposes appropriate remedial, mitigative, or pre-emptive actions. The PMU submits the draft PPR to the BH and LTO for clearance. The FLO sitting in FAO’s GEF Coordination Unit will review and endorse the report and upload it into the FPMIS.

Project Implementation Reviews (PIRs).  The PMU will prepare annual PIRs covering the period from 1 July (the previous year) through 30 June (current year) and submit them for review and clearance by the LTO, BH, and FLO by mid-July.  FAO’s GEF Coordination Unit will submit the PIR to the GEF Secretariat and GEF Evaluation Office as part of the Annual Monitoring Review report of the FAO-GEF portfolio.  FAO’s GEF Coordination Unit will upload PIRs to FAO’s FPMIS.

Key milestones for the PIR process include:

- 30 June:  LTO provides an initial draft of PIR to the PTF and initiates consultations for clearances from BH and FLO.

- Mid-July:  LTO or BH sends final PIR draft to FLO (FAO’s GEF Coordination Unit) for review/endorsement and further submission to the GEF-Secretariat.

- Early August:  FAO’s GEF Coordination Unit prepares and finalizes the FAO Summary Tables and submits to the GEF Secretariat by the date communicated each year by the GEF Secretariat.

- September/ October: FAO’s GEF Coordination Unit coordinates with LTOs to finalize and clear PIR.

- Mid-November: FAO’s GEF Coordination Unit submits the final PIR to the GEF Secretariat and GEF’s Independent Evaluation Office.

Technical reports.  In coordination with the TWG, the PMU will ensure preparation of relevant technical reports as indicated by the project’s results matrix GEF’s CBIT tracking tool.  All technical reports released by the PMU must be cleared by the BH and LTO.  The PSC may also require technical reports to be reviewed or cleared by the PSC or TWG.  The LTO will be responsible for ensuring appropriate technical review and clearance of technical content in reports.  The BH will upload the final cleared reports to FAO’s FPMIS.  The PMU will ensure accessibility of technical reports to relevant stakeholders, including FAO’s PTF and the PSC.

Co-financing reports.  The PMU will support the BH in reporting on co-financing as required by FAO and GEF.  The PMU will compile the information received from co-financiers for expenditures and activities from 1 July to 30 June and transmit it to the BH by mid-July of each project year.  The BH will ensure that the co-financing report is incorporated into the PIR by end-July each project year.  The format and tables to report on co-financing are included in the PIR.

GEF Tracking Tool.  The PMU will update the relevant indicators of the CBIT Tracking Tool in consultation with relevant stakeholders, particularly the PTF, PSC, and chair of the TWG.  The PMU will update the CBIT Tracking Tool at the project’s mid-point and in preparation for the project’s terminal evaluation or final completion report.  The FLO will upload the submitted CBIT Tracking Tool to FAO’s FPMIS.  The LTO will ensure the technical accuracy of the submission.

Terminal Report.  The main purpose of the Terminal Report is to reflect the findings of the Terminal Evaluation, give guidance on the policy decisions required for the follow-up of the project, and to provide the donor with information on how the funds were utilized.  The report is accordingly a concise account of the main products, results, conclusions, and recommendations of the project, without unnecessary background, narrative, or technical details.  The target audience consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and steps to ensure sustainability of the project’s results.

The PMU will prepare the Terminal Report.  The PMU will submit a drafted Terminal Report to the PTF three months before the project’s end date (NTE) and prior to the completion of the Terminal Evaluation (TE) exercise.  The PMU will revise the Terminal Report based on the findings of the Terminal Evaluation and feedback from PTF.  Upon approval of the LTO and BH, the BH will submit the Terminal Report to FAO’s GEF-Coordination Unit.

### Evaluation

Independent Midterm review (MTR) of the CBIT project will be undertaken in the middle point of the project implementation phase. It is expected that the MTR will fall in the first quarter of 2nd year of the project.   The MTR will review progress and effectiveness of implementation in terms of achieving the project objectives, outcomes and outputs. Findings and recommendations of this review will be instrumental in bringing improvement into the overall project design and execution strategy for the remaining period of the project’s implementation and management.

Based on the recommendation of the MTR, Results matrix, log frame, work-plan, and budget will also be revised to better align the project towards its intended outcomes. M&E tools will also be updated as and when required to ensure quality and consistency in data collection, data analysis and reporting.

A Final Evaluation will be initiated six months prior to the actual completion date (NTE) of the project.  FAO Office of Evaluation, in consultation with project stakeholders, will be responsible for launching, organizing and backstopping the Final Evaluation, including: finalizing the ToR, selecting and backstopping the team and Quality Assurance of the final report.

The evaluation will be implemented in Sri Lanka and may be clustered with the regional evaluation of CBIT interventions in Asia / South Asia. A rigorous monitoring system will be developed during the project start-up phase to facilitate the measurement and assessment of project performance during implementation and at final evaluation stage, as well as comparison of results achieved across CBIT interventions.. The evaluation will be conducted through an inclusive process and in coordination with all relevant stakeholders, such as the national counterpart, the Project Steering Committee, the FAO-GEF Coordination Unit and the national GEF focal points

The final evaluation will focus on the achievement of outcomes and their sustainability, as well as on the potential impacts of the intervention, in line with GEF Guidelines and FAO/UNEG Evaluation Standards and Policy. The Project's effects on gender equality and women's empowerment, human rights, capacity development, and environmental sustainability will also be explored.

Findings and recommendations of this evaluation will be instrumental for bringing improvement in the overall project design and execution strategy for similar future interventions. FAO will arrange for the evaluation in consultation with the project partners. The evaluation will, inter alia:

- review the relevance, effectiveness, efficiency and sustainability of project results; and

- highlight results and lessons learned derived from project design, implementation, and management.

Separate analysis, reporting ratings and co-funding tables will be produced for each project.

### Summary of M&E Arrangements

Table 10.  Summary of M&E Arrangements

| M&E activity | Responsible party(ies) | Schedule or Deadline | Budget |
| --- | --- | --- | --- |
| Inception Workshop & Report | PMU in consultation with the PTF and PSC | Within one month following project start-up | USD 5,000 |
| Results-based Annual Work Plan and Budget (AWP/B) | PMU in consultation with the LTO | Within one month of project start-up and on an annual basis thereafter covering the July to June reporting period | USD 2,500 |
| Updated baseline information | PMU, LTO | Inception and end of each project year | USD 7,500 (PMU staff time) |
| Supervision visits | PMU, LTO, FLO | Annual | FAO visits via GEF Agency fees (others via project’s travel budget as needed) |
| Project Progress Reports (PPRs) | PMU, LTO, BH | No later than one month after each biannual reporting period (Jan-Jun and Jul-Dec) | USD 15,000 (PMU staff time) |
| Project Implementation Review (PIR) | Drafted by the NPD, with the supervision of the LTO and BH. Approved and submitted to GEF by the FAO-GEF Coordination Unit | 1 August of each reporting year | GEF Agency fees |
| Independent Midterm Review (MTR) | FAO | End of first year |  |
| Co-financing Reports | PMU | Annual together with PIR | USD 7,500 (PMU staff time) |
| GEF Tracking Tools | LTO | Mid-point and end-of-project | GEF Agency fees |
| Technical Reports | PMU (staff or LOAs); reviewed by LTO, TWGs | As appropriate | PMU staff time and corresponding LOAs USD 20,000 |
| Final workshop | PMU, BH, LTO, FLO | At the end of the project | USD 5,000 |
| Independent Terminal Evaluation (TE) | BH | Six months prior to the actual project completion date | USD 20,000 |
| Processing of Terminal Report | PMU, BH, LTO, GEF Coordination Unit, TCS Report Group | At the end of project implementation | USD 6,600 |
| Total Project Budget for M&E |  |  | USD 89,100 |

### Communication

In coordination with the activities under Output 1.2, a communication and knowledge-sharing plan will be developed early in the project.  A work-plan will be designed and enacted to share the results of the project and the lessons learned over the three years of project’s implementation.  Best practices, lessons learned, and relevant case studies will be documented and disseminated to representatives of the project’s stakeholders as well as to counterparts in other sectors and other countries, largely via the global CBIT projects.  The communication plan will align with the global CBIT project’s communication and knowledge-sharing framework to disseminate the project’s results, achievements, and lessons learned in line with the global reporting and communication requirements.

The communication plan will be developed jointly with key stakeholders.  Diverse communication and visibility tools and approaches (e.g., website, radio, press releases, leaflets/ pamphlets, training materials) will be employed throughout the project’s implementation to raise awareness of the project's key messages and support scaling-up of the results.  During the final workshop, consolidated information will be disseminated, including the project’s results, best practices, and lessons learned.

## Risk Management

### Incorporation of lessons learned

Table 11.  Incorporation of Lessons Learned from Relevant Prior Projects

| Project Title (Agency; Document; Date) | Relevant Recommendation | Incorporation |
| --- | --- | --- |
| UNJP/SRL/064/UNJ Under the Reducing Emissions from Deforestation and Degradation (UN-REDD) Sri Lanka National Programme (2013-2017) | There is high interest in technically specific capacity development, especially for relevant application at local level | - Project specifically strengthens relevant decentralized technological and human capacities |
|  | National Forest Reference Emissions Level (FREL) and National Forest Monitoring System (NFMS) has been developed and available for adaptation | - This CBIT project will build upon REDD+ capacity needs assessments at national and regional levels and expand to other land-use types with a particular focus on agriculture |
|  | Stakeholders capacity increased towards working on MRV in Agriculture sector. | - Experiences accumulated by FAO and partners in developing REDD+ MRV systems including Forest Reference Emission Levels (FREL) will be used as the basis for designing and implementing MRV systems for agriculture activities identified in Sri Lanka’s NDC. |
|  | The understanding on importance of collaboration among the government stakeholders improved. | The proposed CBIT will ensure coordination to ensure contributing to enhance transparency-related processes; and building upon the existing capacity available through this programme. The horizon of GHG inventory will be expended to agriculture, livestock and other relevant sectors to enable Sri Lanka to report in its National Communications. |
| GCP/SRL/063/GFF, Rehabilitation of degraded agricultural lands in Kandy, Badulla and Nuwara Eliya Districts in the Central Highlands (2015 to 2019) | Local communities gain awareness agro-ecosystem and reducing pressure on natural resources and adopted environment friendly vegetable cultivation in Central Province | CBIT project will improve the capacity of stakeholders to report on the GHG emission in agriculture taking into account of the positive contribution of organic vegetable cultivation in central province |
|  | Number of technical best practices can be acknowledged, such as seed and crop selection, agronomic practices such as improving soil quality, crop-livestock integration, land management, water harvesting and improving kitchen gardens were successfully undertaken through the project. These have enhanced the knowledge of marginalized farmers mainly on resilient agriculture and water management. | Agriculture sector improve its contribution toward reporting NDCs and better use the support of CBIT project to build on the reporting structure and tools. |
| GCP/SRL/048/GEF, Promoting Sustainable Biomass Production and the Modern Bio-Energy Technologies, (2014 to 2017). | Biomass energy generation and adaptation of bio-mass based energy technologies improved | - The proposed CBIT will help in transfer of knowledge for GHG inventory to set baseline for future monitoring and reporting purposes |
|  | Link with other project and initiatives to ensure post-project sustainability | - The project also seeks to address the underlying issue of financial sustainability by facilitating alternative funding (e.g., greater access to international environmental off-set markets via strengthened MRV; clearer substantiation of funding via linkages to governmental revenues based on strengthened MRV) and reducing costs (e.g., efficiencies of reducing redundancies; use of proxy measures; strengthening existing operational arrangements). |
| GCP/SRL/069/CAN, Agro-Economic Development Project, (2015 to 2017). | Community based- sustainable agro-economic livelihood development opportunities improved in Northern Province in Sri Lanka | Sustainable agro-economic model will play a vital role in reducing pressure on forestry sector leading to reduced GHG emission and enhanced sequestration. Through CBIT better accountability of emission reduction targets can be set by technology transfer (Example EX-ACT). |
|  | Community resilient sustainable agriculture opportunities contributes for the effective land management best practices in the Norther Province | Stakeholders have been proactively engaged in the design phase and are included in the PSC and TWG |
|  | Use of ICT is effective and cost-efficient | Project seeks to increase cost-efficiency through ICT for decentralized measurements (reducing costs, errors, and delays associated with transcription) and proxy measures (e.g., feedback from land users via mobile devices; remote-sensing) |
|  | Need adaptability to national evolving national circumstances | The project has been designed to allow operational and budgetary flexibility to adjust to evolving circumstances, given that (i) the project will need to respond to the clarification of priorities and targets (especially true for CCA), (ii) several stakeholders are pursuing related initiatives, and (iii) the project will need to respond to feedback from improved measures. - The project’s PSC is explicitly tasked with ensuring that the project’s design, budgeting, and execution adapts to evolving circumstances and priorities. |

### Risks and risk-mitigation measures

- Table 12.  Risks and Risk-mitigation Measures

| No. | Description of Risk | Type of Risk | Probability and Impact (1-5) | Measures to Mitigate the Risk |
| --- | --- | --- | --- | --- |
| 1 | Lack of coordination among concerned ministries and local government authorities | Institutional | P = 4 I = 3 | - To address risks associated with coordination the project will work through existing coordination mechanisms established under the UN-REDD Programme. That will help in ensuring smooth functioning of activities. - Project will work largely through LOAs with the PPRSs, so that such tasks are institutionalized and related capacities are strengthened. - Project will pilot approaches in order to identify and rectify operational challenges. |
| 2 | Limited cooperation on data and information sharing among stakeholders | Institutional | P = 3 I = 5 | - To address risks associated with data management consultation and data system assessments will be crucial elements of activities under Outputs 2.1.2 and 3.1.3. The project will also build on existing systems where possible developed for REDD+ with respect to mitigation and for NAP. Clear data sharing agreement of the stakeholders to collect and hand over required data and information. - Engagement with National Advisory Committees - incorporation of relevant duties into job descriptions and performance standards - full estimation of initial and on-going resource requirements - cost-efficiency approaches (e.g., reduced redundancy; proxy measures) - capacity-development for relevant stakeholders (including technology and training) - established QC and QA protocols |
| 3 | Inability for the government to fund the ETF related activities beyond the project cycle | Financial | P = 4 I = 1 | - The proposed CBIT project will include measures to mainstream ETF activities into government budgetary and extra-budgetary processes. It will be proposed that ETF reporting be incorporated into current and future CPAP processes. - working through LOAs helps ensure near-term continuity - formalizing ETF-related institutional arrangements supports long-term continuity |
| 4 | Gender mainstreaming hindered by resistance from local and national stakeholders | Cultural | P=3 I=3 | - Clear initial communication on gender equality as one of the key monitoring element for tracking progress of the project – particularly with respect to adaptation monitoring and reporting and co-benefits. |
| 5 | Transparency related work loses momentum as the Paris Agreement is not adopted | Political | P = 1 I = 4 | - To address this issue CBIT project activities will focus on the potential positive externalities associated with improved data collection, monitoring and reporting of agriculture and land-use sector mitigation and adaptation activities. These could include more effective targeting of initiatives to improve farm and land-use efficiency and strengthen rural resilience. This ‘no-regrets’ approach will aim to highlight the need for and benefits of this transparency work that will go beyond the lifetime of the Paris Agreement. |

# Section 3:  Innovation, Potential for Scaling-up, and Sustainability

## Innovation

The proposed CBIT project will facilitate scientific innovation through investment in infrastructure and systems to update and modernize the measurement and monitoring capacities of Government and local technical and research institutions. The project will facilitate investment and technology transfer for new and updated equipment at local universities and labs to measure and monitor emissions from a wide range of agriculture and land-use activities. The project will also facilitate investment in dedicated knowledge management information systems and IT hardware for the more effective management and reporting of data and information related to transparency of both mitigation and adaptation actions. Field monitoring systems will be overhauled under the project through the upgrading of data collection processes with the wider application of mobile telecommunications, app-based data collection platforms and cloud-based data storage and transfer services where appropriate.

These systems will be designed to benefit from recent advances and tools for estimating GHG emissions from the crops, livestock and forestry sectors. FAO, with partners, has developed or is currently developing a suite of tools for standardizing emissions monitoring and reporting at Tier 2 levels. For example, the Global Livestock Environment Assessment Model (GLEAM) establishes baselines and assesses the impacts of different mitigation and adaptation scenarios at local and national scale. Based on IPCC Tier 2 methodology and GIS based modeling of livestock distribution, GLEAM allows the assessments of all major GHG emissions from livestock and the impacts of all actions to reduce emissions from the sector. Similar tools are under development for field crops based on projects including a global program on Mitigating Agricultural Greenhouse Gases (MAGHG) and support for countries in Southeast Asia to prepare Nationally Appropriate Mitigation Actions for different field crops.

With the application of GHG estimation tools such as GLEAM and those developed under MAGHG, national institutions will have enhanced capacity to measure progress toward NDC priorities in agriculture and land-use sectors. At global level, evidence tested and compiled in Sri Lanka will facilitate the improvement of scientific knowledge of GHG emissions reduction potential from AFOLU sectors, consequently improving our knowledge to estimate global environmental benefits. These systems once implemented and operational will support the potential for improved understanding of mitigation and adaptation potentials and the possibility for increased levels of ambition and quantification of support required in future iterations of Sri Lanka’s NDC in the lead up to and during the commitment period of the Paris Agreement.

In addition, the project adopts an innovative approach that integrates extensive stakeholder consultations and assessments of capacity needs and baseline activities for monitoring the progress. The project interventions have been formulated by taking into account the need to enhance national capacity in monitoring mitigation and adaptation actions for AFOLU and relevant sectors as a whole emerging from the representatives of line ministries in Sri Lanka.

Additionally, this project’s design phase has made use of newly innovated tools for assessments of capacities, gaps, and stakeholders’ decision processes.  These tools have also been designed to provide on-going value by helping to guide ETF-related decisions and efforts during and after the project.

The project is expected to strengthen the capacity of CCS to develop a Provincial Data Collection mechanism namely “Provincial Cells”. These Provincial Cells will collect the data from the various stakeholders and departments at the ground level for compilation and analysis at the Provincial level. It is also expected that the capacity of these Provincial Cells would be enhanced through critical engagement of 3rd national report preparation process.

## Potential for Scaling-up

The project specifically embeds opportunities to scale-out and scale-up the measures implemented. The information management systems and infrastructure for monitoring and reporting mitigation and adaptation actions in the agriculture and land-use sectors established under the project will be designed in way to allow for easy replication and adoption by other sectors.

Hardware, capacity building and training provided to national and local level stakeholders will be developed as modules that they can be adapted to improve data collection methods and analysis across all sectors. By working through and strengthening the institutional mechanisms in place for transparency of climate change actions the project will be able to better facilitate this process of scaling out project-developed systems and processes. The enhanced capacity provided by the project will enable regular national reporting of actions to address climate change drivers and impacts as envisioned under Paris Agreement Article 13.

Outcome 1 of the project will also facilitate Sri Lanka’s engagement in international transparency-related processes under the UNFCCC. With the enhanced institutional capacity and engagement with international process, the government of Sri Lanka will be capacitated to identify potential partners to further develop scaling-up actions and investment opportunities for further improving transparency over time, as well as to benefit other countries in the region to develop more transparent, accurate, complete, consistent and comparable monitoring and reporting systems.

The government will use a combination of national budget, and planned international support for fulfilling its reporting requirements to the Convention and ensure continued application and sustainability of the transparency systems and infrastructure for the other sectors.

It is envisaged that the government mechanism for quality data collection and reporting on NDC towards ETF will be improved overtime and adopted completely in AFOLU sector.

## Sustainability

The primary driver of the project’s sustainability is its relevance.  Climate change is a national priority with direct relevance to livelihoods and well-being, particularly in the AFOLU sector.  Institutional stakeholders have strong incentives to gain and act upon accurate climate-related information.  This CBIT project directly addresses that need.

In addition to the project’s direct relevance to stakeholders’ needs, the project also enables institutional stakeholders to demonstrate results through improved data, such as on the effectiveness of various interventions.  This improved transparency is foundational to good governance, because it provides a basis for responsiveness and accountability.

Financial uncertainties pose the largest challenge to post-project sustainability.  The central government’s current plans for future financing of ETF-related activities rely heavily on international, project-based funding, which is not conducive to staff continuity (thereby under-cutting technical capacity development), operation and maintenance costs, institutional accountability, and strategic planning.  Therefore, the design of this project has incorporated several approaches to address this challenge.

First, the project seeks to minimize ETF-related costs by:

        - building on extant institutional and operational arrangements when possible,

        - augmenting the capacities of relevant extra-governmental stakeholders (e.g., academic and research institutions, CSOs/ NGOs) when appropriate to enhance their abilities to support ETF-related activities (rather than expensively reproducing redundant capacities or technologies within a governmental institution that might rarely use them),

        - reducing redundancies and inter-institutional friction by clarifying ETF-related mandates, accountabilities, and boundaries,

        - maximizing the proportion of the project’s resources directed to capacity development within the institutions that will be responsible for delivering ETF-related outputs after the project has completed (i.e., the post-project responsible stakeholders—PPRSs—e.g., via technical training, non-expendable procurement of technologies necessary for post-project activities),

        - identifying, validating, and establishing the use of cost-efficient proxy measures,

        - using technology to reduce operational costs (e.g., gathering field data with tablets that auto-synch and auto-upload when connected to the internet, thereby reducing costs and errors associated with transcription), and

        - identifying opportunities to work with extra-governmental partners (e.g., academia, research institutions, CSOs/ NGOs, private sector, local communities) for the conduct of activities for which those partners provide cost-efficiency or other value (e.g., established networks of local engagement; relevant operational technologies or efficiencies).

Second, the project seeks to provide a foundation for transitioning to additional sources of financial support for ETF-related activities by:

  - strengthening the evidentiary basis for greater political and budgetary support,

  - increasing the capacity to conduct sufficiently rigorous MRV to transition to access to global environmental off-set markets (e.g., carbon markets),

  - building the capacity to form an evidentiary (MRV) basis for enforcement-based revenues,

  - building the capacity to form an evidentiary (MRV) justification or rationalization of linkages to value-capture from natural resources (e.g., funding from the capture of economic rents on the extraction of public natural resources, such as from taxes on logging and mining), and

  - in coordination with private-sector lenders, identifying practical criteria for evaluating opportunities for financial support to environmentally beneficial investments (e.g., preferential lending terms, risk-based products).

### Capacity development

FAO’s guidelines for formulating GEF projects emphasize the need for effective, robust and system-wide capacity development (CD) approaches in order to enhance the impact, sustainability, and scale of GEF project results through deepening country ownership, commitment, and leadership of the developmental process.  Capacity-development is the primary means by which this project will achieve its aim of improving the quality of information regarding climate change in Sri Lanka’s agricultural and land-use sub-sectors.  To do so, the project will strengthen the enabling environment and build the capacities of organizations and individuals.

The project addresses the enabling environment—primarily via activities under Component 1—by (i) strengthening stakeholder coordination and (ii) supporting the development of strategy documents that clarify ETF-related organizational responsibilities and guide capacity-development decisions for organizations and individuals.

The project addresses organizational capacities—via activities under each of the project’s components—by (i) helping identify and develop pathways to improved financial sustainability, (ii) engaging a broad range of relevant stakeholders, which supports the retention of relevant expertise throughout the network of national stakeholders, (iii) providing technological equipment and associated training to enable delivery of critical ETF-related activities, and (iv) strengthening stakeholders’ abilities to retain and access relevant knowledge (despite inevitable turnover).

The project also builds individual capacities, particularly for ETF-related technical skills.  The project budget supports extensive training, training of trainers, quality-control training, and sharing of best practices with relevant other stakeholders, sectors, and countries.

Additionally, the project provides tools and procedures to continue to assist stakeholders in identifying future opportunities for continuous learning and improvement.  The project will avail of FAO’s extensive tools, experience, and expertise for developing the capacities of diverse stakeholder groups in the AFOLU sector.  For example, the project will benefit from the substantial relevant expertise in FAO’s NFM/REDD+ team and MICCA team in HQ and RAP.

The project will continue to apply the CD principles of joint stakeholder assessment, design, identification, and tracking of CD to deepen country-ownership.  The PMU also includes a Decision-support Specialist, who will ensure that the project’s interventions efficiently contribute to strengthened ETF-related decision-making.  Thus, the Decision-support Specialist will help identify relevant capacity gaps and effective means of addressing them.  Because the project is being executed largely through PPRSs, the related tools, approaches, and practices will be transferred to relevant stakeholders during the project, thereby increasing the likelihood of post-project sustainability.

### Decent rural employment

This project is not expected to affect people’s livelihoods and employment status directly. Indirectly, the project is expected to contribute overall socio-economic benefits by supporting the effective and efficient management of natural resources as well as publicly funded initiates to steward those resources.  Given that the national and local economies are so intimately reliant on environmental resources, this project’s benefits for the quality, transparency, and accessibility of related information will greatly benefit all citizens, especially those directly engaged in the AFOLU sector and vulnerable to climate change.

### Environmental sustainability

This project directly contributes to local, national, and global environmental sustainability.  This project will build stakeholders’ capacities to improve the quality of information regarding climate change, including its impacts and efforts to mitigate and adapt to it.  Therefore, the project improves related decision-making processes, such as regarding the relative effectiveness and cost-efficiencies of different initiatives.  In fact, projects such as this—which improve the quality and transparency of climate-related information—are necessary for enabling stakeholders to assess sustainability and its antecedents.

### Gender equity

The PMU will advise the TWG to consider gender-related issues in the formulation of the NCCMF and other project-related technical issues.  For example, the TWG will be asked to consider gender among the issues that might be associated with differential climate-related impacts or vulnerabilities, and how such issues might be reflected in adaptation-related M&R.  The PMU will also request that the TWG consider the ways in which gender-related issues should potentially be reflected in the NDC.  Additionally, the project will provide gender-disaggregated reporting for capacity-development activities, such as trainings.  The project will report on gender-related issues as prescribed for PPRs, PIRs, and other project-related documentation.

The project itself has benefited to date from extensive engagement from various stakeholders, including substantial representation by women.  The proposed memberships of the TWG and PSC both expected to include substantial representation by women.  In cooperation with governmental partners, the project’s intervention will align with GEF’s Gender Equality Action Plan.  FAO, the PSC, and the PMU will ensure that the project addresses any gender-specific needs, that women have equal access to the project’s governance and activities, and that women benefit equitably from the project.

### Indigenous groups and people

The project sites do not hold any population of indigenous people as these are commonly defined.  The project’s activities will have indirect effects on the management of natural resources, which are closely associated with the traditional lifestyles of various communities.

# List of Appendices and Annexes

Appendix 1.  Results Matrix

Appendix 2.  Work-plan

Appendix 3.  Budget

Appendix 4.  Project Steering Committee’s Terms of Reference and Provisional Membership

Appendix 5.  Technical Working Group’s Terms of Reference and Proposed Membership

Appendix 6.  Abbreviated Terms of Reference for Members of the Project Management Unit

Appendix 7. Co-financing Letters - Ministry of Mahaweli Development and Environment

Appendix 8.  Co-financing Letters – FAO

# Appendix 1:  Results Matrix

| Result | Indicator | Baseline | Mid-term Target | Final Target | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: By 2020, Sri Lanka is preparing reports to the UNFCCC under the Paris Agreement Enhanced Transparency Framework (ETF) covering all components identified in Sri Lanka’s Nationally-Determined Contribution (NDC), including strengthened agriculture and land use sector components, inventories of emissions sources and sinks and information necessary to track progress against priority actions in the NDC. |  |  |  |  |  |  |
| Component 1: Institutional arrangements to coordinate preparation of ETF reports for agriculture, land-use and other relevant sectors enhanced |  |  |  |  |  |  |
| Outcome 1.1: Institutional arrangements coordinating information and data collection from the agriculture and land use sectors into ETF processes and reports enhanced. | A: Coordinated sharing of data, information, and analyses from agricultural and land-use sub-sectors in a manner that facilitates ETF processes and reports | Data, information, and analyses from the majority of agricultural and land-use sub-sectors are not being produced and shared in a timely and coordinated manner; no agreed protocols for such data-sharing | Data-provision/ data-sharing protocols established; Primary opportunities and mechanisms identified and being strengthened for improved sharing of data, information, and analyses for key categories in the agricultural and land-use sub-sectors. | ETF-relevant data, information, and analyses within the agricultural and land-use sub-sectors are shared in accordance with adopted and enacted protocols for data-sharing/ data-provision. | Status of the National Climate-change Monitoring Framework (NCCMF); ETF reporting | Sufficient political support to enact reporting guidance from the NCCMF |
|  | B: CBIT Tracking Tool Indicator 5: Qualitative assessment of institutional capacity for transparency-related activities (Scale: 1 – 4) | 2: Designated transparency institution exists, but with limited staff and capacity to support and coordinate implementation of transparency activities under Article 13 of Paris Agreement. Institution lacks authority or mandate to coordinate transparency activities under Article 13. | 2: Designated transparency institution exists, but with limited staff and capacity to support and coordinate implementation of transparency activities under Article 13 of Paris Agreement. Institution lacks authority or mandate to coordinate transparency activities under Article 13. | 3: Designated transparency institution has an organizational unit with standing staff with some capacity to coordinate and implement transparency activities under Article 13 of the Paris Agreement. Institution has authority or mandate to coordinate transparency activities under Article 13. Activities are not integrated into national planning or budgeting activities. | Status of the National Climate-change Monitoring Framework (NCCMF) | Sufficient political support to enact reporting guidance from the NCCMF |
|  | C: ETF readiness in terms of institutional and human capacities | Low level of readiness as per section A of AFOLU readiness assessment and expected ETF requirements | Updated AFOLU readiness assessment and finalized ETF requirements | Measurable increases in readiness level (Note: Quantitative targets to be defined based on updated AFOLU readiness assessment and finalized ETF requirements) | AFOLU readiness assessment (final report) | Capacities are maintained and attrition is kept to a minimum |
| Outcome 1.2: Best practices on ETF reporting processes, information gathering, system infrastructure, methodologies in the agriculture and land-use sectors disseminated to relevant priority sectors (e.g. energy, industry/trade, transportation). | D: Level of engagement of agricultural and land-use sub-sectors with ETF processes | Very limited engagement of agricultural and land-use sub-sector stakeholders, including government, CSOs, and private-sector | Sub-sector coordination mechanisms established (e.g., NCCMF, TWG, MRV portal) | Broad engagement of stakeholders from agricultural and land-use sub-sectors via established coordination mechanisms | Engagement via TWG (e.g., attendance), MRV portal (e.g., active links), and mechanisms indicated in the NCCMF | Stakeholders have sufficient intrinsic and extrinsic motivations to engage |
|  | E: Degree of engagement with other sectors | Agricultural and land-use sub-sectors not contributing to ETF capacities of other sectors | Increased engagement with inter-sectoral coordination mechanisms | Agricultural and land-use sub-sectors engaging with, benefitting from, and contributing to ETF capacities in other sectors | Project reporting; attendance records; presentations/ reports submitted, disaggregated by sex. |  |
|  | F: Degree of engagement with regional and global ETF counterparts | Agricultural and land-use sub-sectors minimally contributing to ETF capacities of regional and global counterparts | Increased engagement with regional and global ETF coordination mechanisms | Agricultural and land-use sub-sectors engaging with, benefitting from, and contributing to ETF capacities of regional and global counterparts; at least 1 formal document of best practices and lessons learned shared; at least 2 specific summaries/ case studies of lessons learned circulated; regular engagement with established coordination mechanisms | Project reporting; attendance records; presentations/ reports submitted, disaggregated by sex. | Global CBIT projects facilitate engagement with regional and global counterparts |
| Component 2: Capacity to assess and report emissions and removals from agriculture and land-use sectors and to design and monitor related emission reduction activities strengthened |  |  |  |  |  |  |
| Outcome 2.1: Reporting on inventories of emissions sources and sinks and mitigation activities from agriculture and land-use sectors strengthened | G: AFOLU CCM component of CBIT Tracking Tool Indicator 3: Quality of MRV systems (Scale: 1 – 10) | 3: AFOLU CCM measurement systems are in place for a few activities, improved data quality and methodologies, but not cost or time efficient; wider access to reporting is still limited and information is partial; verification is rudimentary/ non-standardized | 3: AFOLU CCM measurement systems are in place for a few activities, improved data quality and methodologies, but not cost or time efficient; wider access to reporting is still limited and information is partial; verification is rudimentary/ non-standardized | 6: AFOLU CCM measurement systems are strong and cover a greater percentage of activities – feedback loops exist even if they are not fully functioning; reporting is available through multiple pathways and formats but may not be complete/ transparent; verification is done through standard methodologies but only partially (i.e. not all data are verifiable) [Verification is expected to be the constraint at this stage.] | IPCC MRV assessment tool (see Annex 3); MRV portal functionality (see Activity 1.1.2.6) |  |
|  | H: Availability of formal, adopted metadata parameters and QC protocols for agricultural and land-use sub-sectors | None | Drafted by TWG | Endorsed and adopted by relevant stakeholders | NCCMF; publication of protocols; formal endorsements of relevant stakeholders | Stakeholders assured of sufficient, reliable support for their obligations under the protocols |
|  | I: Sufficiency of technical and human capacities to enact CCM-related QC protocols for agricultural and land-use sub-sectors | Very low, particularly for decentralized locations | Technological needs determined based on drafted protocols; materials developed for human needs | High for all stakeholders with direct relevance to the NCCMF protocols | Training records; procurement records; outcomes of pilots, disaggregated by sex. | Staff turnover will not undercut capacity development; post-project funding will support operation and maintenance |
| Component 3: Capacity to implement, monitor and report adaptation activities and actions in agriculture and land-use sectors strengthened |  |  |  |  |  |  |
| Outcome 3.1: Strengthened measurement of climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors. | J: Availability of formal, adopted metadata parameters and QC protocols for CCA in the agricultural and land-use sub-sectors | None | Drafted by TWG | Endorsed and adopted by relevant stakeholders | NCCMF; publication of protocols; formal endorsements of relevant stakeholders | Stakeholders assured of sufficient, reliable support for their obligations under the protocols |
|  | K: Sufficiency of technical and human capacities to enact CCA-related QC protocols for agricultural and land-use sub-sectors | Very low, particularly for decentralized locations | Technological needs determined based on drafted protocols; materials developed for human needs | High for all stakeholders with direct relevance to the NCCMF protocols | Training records; procurement records; outcomes of pilots, disaggregated by sex. | Staff turnover will not undercut capacity development; post-project funding will support operation and maintenance |

# Appendix 2:  Work-plan

| Outcome | Output | Budgeted Work Plan "Strengthening capacity in the agricultural and land-use sectors for enhanced transparency in implementation and monitoring of Sri Lanka’s Nationally Determined Contribution (NDC)" |  | Year 1 |  |  |  | Year 2 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Activity | Mode | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1.1. Institutional arrangements coordinating information and data collection from the agriculture and land use sectors into ETF processes and reports enhanced. |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1. Coordination mechanism established/strengthened integrating relevant authorities from the agriculture and land use sector into national UNFCCC reporting processes. |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.1.1. Conduct a stakeholder/coordination mapping for AFOLU sectors. | CCS |  |  |  |  |  |  |  |  |
|  |  | 1.1.1.2. Create an AFOLU MRV technical working group (TWG)s and link TWGs to the advisory responsibilities for NCs. | PMU, ALL STAKEHOLDERS |  |  |  |  |  |  |  |  |
|  |  | 1.1.1.3. Build a framework for CCS to obtain TWG support for ETF transition and management. | PMU, ALL STAKEHOLDERS |  |  |  |  |  |  |  |  |
|  |  | 1.1.1.4. Create multi-party Internal arrangements (agreements/circulars/memo) for relevant data-sharing. | PMU, ALL STAKEHOLDERS |  |  |  |  |  |  |  |  |
|  |  | 1.1.1.5. Create an online portal for ETF-related information on CCS with mobile uploading capability. | LOA |  |  |  |  |  |  |  |  |
|  | 1.1.2. Assessment prepared to assess institutional, data collection, analysis and reporting capacity gaps and needs for meeting ETF requirements with specific focus on the priority NDC actions for the agriculture, forestry and land-use sectors. |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.2.1. Develop a AFOLU MRV assessment framework. | PMU, CCS LOA |  |  |  |  |  |  |  |  |
|  | 1.1.3. National ETF monitoring and reporting roadmap for the AFOLU sectors prepared and adopted |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.3.1. Produce an ETF-compliant MRV protocol for the agricultural and land-use sectors. | PMU, FAO, STAKEHOLDERS |  |  |  |  |  |  |  |  |
|  | 1.1.4. Capacity developed to clarify measurement and reporting of key NDC information (baselines, Business-As-Usual targets) and support provided for ETF reporting in AFOLU sectors |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.4.1. Provide training and necessary capacity for CCS to liaise with AFOLU stakeholders: to train stakeholders to generate data necessary for UNFCCC reporting. | PMU through FAO and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 1.1.4.2. Create national ETF-complaint reports covering mitigation and adaptation-related activities in accordance with NDC commitments for the AFOLU sector. | PMU through FAO and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  | 1.1.5. Sri Lanka's engagement strengthened in the AFOLU sectors with international transparency-related processes under the UNFCCC. |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.5.1. Publish a peer-reviewed AFOLU sector ETF-compliant MRV document concurrently with National Communications. | LOA: CCS |  |  |  |  |  |  |  |  |
| 1.2. Best practices on ETF reporting processes, information gathering, system infrastructure, methodologies in the agriculture and land-use sectors disseminated to relevant priority sectors (e.g. energy, industry/trade, transportation). |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.1. Multi-sectoral coordination mechanism strengthened integrating relevant authorities into national UNFCCC reporting processes. |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2.1.1. Identify opportunities for inter-sectoral efficiencies and reduce redundancies in measurement and primary data storage. | LOA: CCS |  |  |  |  |  |  |  |  |
|  |  | 1.2.1.2. Ensure that AFOLU data-sharing processes are integrated with broader inter-sectoral and national coordination for data-sharing. | LOA: CCS |  |  |  |  |  |  |  |  |
|  |  | 1.2.1.3. Establish QC protocols for collecting, managing, and archiving data | PMU through FAO and CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  | 1.2.2 ETF lessons learned from AFOLU sectors monitored, captured, scaled up and shared to enhance wider national reporting. |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2.2.1. Conduct bi-annual Stakeholder feedback sessions. | LOA: CCS |  |  |  |  |  |  |  |  |
|  |  | 1.2.2.2. Compile AFOLU MRV best practices with relation to similar practices in other NDC sectors. | LOA: CCS |  |  |  |  |  |  |  |  |
|  |  | 1.2.2.3. Contribute to efforts via the CBIT global projects to share and up-scale relevant AFOLU MRV best practices and lessons learned. | LOA: CCS |  |  |  |  |  |  |  |  |
|  | 1.2.3. Peer exchange program on transparency activities established for relevant priority sectors |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.2.3.1. Create a capacity building and conferencing platform for transparency improving modifications of MRV across sectors | LOA: CCS |  |  |  |  |  |  |  |  |
| 2.1. Strengthened capacity to measure GHG emissions, removals, and emission-reduction activities from agricultural , forestry and land-use sectors.. |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1. Quality-control (QC) protocols established for regular, systematic estimates of emissions, removals, and emission-reduction activities in the agricultural and land-use sectors. |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.1.1. Establish data entry templates and specifiy updating frequency for partner agencies to match with national GHG inventory/ reporting cycles. | PMU through FAO and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 2.1.1.2. Estimate resource requirements and sources for initial and sustained support (e.g., technology, personnel, funding, etc.). | LOAs: CCS. |  |  |  |  |  |  |  |  |
|  |  | 2.1.1.3. Draft AFOLU ETF data-provision guidelines. (related to Output 1.1.3.) | PMU through FAO and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  | 2.1.2. Information technology systems upgraded to integrate, analyze, and archive diverse data types. |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.2.1. Develop a dedicated ICT infrastructure for parallel updating by stakeholder and partner institutions with appropriate security clearances | PMU through FAO, CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  | 2.1.3. Capacity and technology upgraded in relevant institutions to strengthen mitigation-related MRV, including country-specific emissions factors, activity data, and Tier 2 reporting for key sub-categories in the agriculture, forestry and land-use sectors. (Coordinates with 3.1.3.) |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.3.1. Update forest cover maps, develop allometric equations for updated estimates of emission from source and removals from sinks in forestry sector | LOA: FD |  |  |  |  |  |  |  |  |
|  |  | 2.1.3.2. Capacity development for three priority key categories | LOA: CCS |  |  |  |  |  |  |  |  |
|  |  | 2.1.3.3. Provide relevant stakeholders with the equipment and software necessary for decentralized data collection, storage, and uploading in line with data-provision guidelines | PMU through FAO, CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 2.1.3.4. Produce training materials, including materials for training of trainers, for associated technologies and QC protocols. | PMU through FAO, CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 2.1.3.5. Conduct training of relevant stakeholders, including training of trainers, to enable measurements in line with data-provision guidelines. |  |  |  |  |  |  |  |  |  |
|  | 2.1.4. Relevant measures validated and piloted for key mitigation sub-categories in the agriculture, forestry and other land-use sectors. |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.4.1. Commission meta-analysis studies to review relevant research literature to determine provisional Tier 2 estimates where possible and, as needed, uncertainty assessments for estimates in key sub-categories. | PMU through FAO, CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 2.1.4.2. Conduct pilot tests of measurement protocols and revise protocols as needed. | PMU through FAO, CCS and LOA with National Consultants |  |  |  |  |  |  |  |  |
|  |  | 2.1.4.3. Conduct validation pilot studies of proxy measures and introduce an updating frequency for proxy measures. | Contracts |  |  |  |  |  |  |  |  |
|  |  | 2.1.4.4. Conduct preliminary validations of proxy measures. | LOAs: contracts with academic and research bodies |  |  |  |  |  |  |  |  |
| 3.1. Strengthened capacity to measure climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.1. Measurement framework developed for climate-change impacts, vulnerabilities, and adaptation-related activities prioritized in the NDC for the agriculture, forestry and land-use sectors. |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.1. Generate a typology of adaptation processes in AFOLU sectors using expertise in adaptation-related sciences and multi-disciplinary expertise. | LOA: AFOLU experts |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.2. Develop an analytical framework to assess adaptation challenges and opportunities in AFOLU sector through a stakeholder consultation. | LOAs: CCS, FAO |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.3. Capacity building for development of land use policy and regulations to reduce land and environmental degradation |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.4. Development of Good Practice Guidelines for land use planning |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.5. Conduct an assessment of vulnerability based on a revalidation of agroecological zoning | LOA: AFOLU, MoA |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.6. Estimate resource requirements and sources for initial and sustained support (e.g., technology, personnel, funding, etc.) for MRV of adaptation activities in AFOLU sectors. | LOA: AFOLU experts, CCS |  |  |  |  |  |  |  |  |
|  |  | 3.1.1.7. Prepare knowledge-management plan, products and demonstrate for adaptation activities. | LOA: CC adaptation experts |  |  |  |  |  |  |  |  |
|  | 3.1.2. Information technology systems upgraded to integrate and analyze adaptation-related data.. |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.2.1. Develop an information system onCC adaptation priorities at national and local levels by development initiatives as a preliminary adaptation safeguards check for development projects | LOA: CC adaptation experts, CCS |  |  |  |  |  |  |  |  |
|  | 3.1.3. Capacity and technology upgraded in relevant institutions to strengthen M&R for adaptation priorities identified in the NDC for the agricultural and land-use sectors. (Coordinates with 2.1.3.) |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.3.1. Provide relevant stakeholders with the equipment and software necessary for decentralized data collection, storage, and uploading in line with data-provision guidelines | CCS, PMO |  |  |  |  |  |  |  |  |
|  |  | 3.1.3.2. Produce training materials, including materials for training of trainers, for QC and associated technologies. | LOA: AFOLU agencies, CCS |  |  |  |  |  |  |  |  |
|  |  | 3.1.3.3. Conduct training of relevant stakeholders, including training of trainers, to enable measurements in line with data-provision guidelines. | PMU; LOAs: CCS |  |  |  |  |  |  |  |  |
|  | 3.1.4. Relevant measures validated and piloted for adaptation priorities identified in the NDC for the agricultural and land-use sectors. |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.4.1. Review relevant research literature to determine provisional estimates where possible and conduct uncertainty assessments for estimates for key indicators | LOA: AFOLU and CC adaptation experts |  |  |  |  |  |  |  |  |
|  |  | 3.1.4.2. Conduct pilot tests of measurement protocols and revise protocols as needed. | Contracts |  |  |  |  |  |  |  |  |
|  |  | 3.1.4.3. Conduct preliminary validations of proxy measures | LOAs: Contracts |  |  |  |  |  |  |  |  |

# Appendix 3:  Budget

| Enhancing and bridging knowledge gaps in Sri Lanka's NDC implementation of AFOLU sector for Enhanced Transparency Framework (ETF) | BUDGET (USD) |  |  |  |  |  |  |  |  | BUDGET BY YEAR (USD) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Unit | Qty | Unit cost | Outcome 1.1 | Outcome 1.2 | Outcome 2.1 | Outcome 3.1 | PMC | Total GEF | Year 1 | Year 2 |
| 5300 & 5500 Salaries |  |  |  |  |  |  |  |  |  |  |  |
| Administration Associate | mo | 24 | 1,450 | - | - | - | - | 34,800 | 34,800 | 17,400 | 17,400 |
| Finance / Procurement Associate | mo | 24 | 1,819.9 | - | - | - | - | 43,677 | 43,677 | 21,838.5 | 21,838.5 |
| 5300 Sub-total - Salaries, Professionals |  |  |  | - | - | - | - | 78,477 | 78,477 | 39,239 | 39,239 |
| 5570 Consultants |  |  |  |  |  |  |  |  |  |  |  |
| # International Consultants |  |  |  |  |  |  |  |  |  |  |  |
| # 1 Livestock MRV Specialist | # day | # 40 | # 450 | # 4,800 | # 1,200 | # 6,000 | # 6,000 |  | # 18,000 | # 13,500 | # 4,500 |
| # Sub-total - International Consultants |  |  |  | # 4,800 | # 1,200 | # 6,000 | # 6,000 | # - | # 18,000 | # 13,500 | # 4,500 |
| National Consultants |  |  |  |  |  |  |  |  |  |  |  |
| 1 National Project Manager | mo | 24 | 1,160 | 20,000 | 5,000 | - | 2,840 | - | 27,840 | 13,920 | 13,920 |
| 1 Technical Assistant | mo | 24 | 900 | 10,800 | 2,700 | 7,000 | 1,100 | - | 21,600 | 10,800 | 10,800 |
| 1 Decision-support Specialist | mo | 24 | 900 | 15,800 | 2,400 | 2,000 | 1,400 | - | 21,600 | 10,800 | 10,800 |
| National Consultant - Climate Change Mitigation | mo | 24 | 1,160 | 1,000 | 5,340 | 19,000 | 2,500 | - | 27,840 | 13,920 | 13,920 |
| National Consultant - Climate Change Adaptation | mo | 24 | 1,160 | 1,000 | 5,340 | 2,500 | 19,000 | - | 27,840 | 13,920 | 13,920 |
| Sub-total - National Consultants |  |  |  | 48,600 | 20,780 | 30,500 | 26,840 | - | 126,720 | 63,360 | 63,360 |
| 5570 Sub-total - Consultants |  |  |  | 53,400 | 21,980 | 36,500 | 32,840 | - | 144,720 | 76,860 | 67,860 |
| 5650 LOAs and Contracts |  |  |  |  |  |  |  |  |  |  |  |
| LOAs and Contracts with executing partners and service providers | sum | 1 | 274,280 | 77,800 | 9,200 | 85,280 | 102,000 | - | 274,280 | 137,140 | 137,140 |
| Coordination meetings/ workshops (e.g., TWGs) (Comp1) | sum | 1 | 6,000 | 4,800 | 1,200 | - | - | - | 6,000 | 3,000 | 3,000 |
| Inception workshop (incl. report) | sum | 1 | 5,000 | 1,334 | 333 | 1,667 | 1,666 | - | 5,000 | 5,000 | - |
| Final workshop | sum | 1 | 5,000 | 1,334 | 333 | 1,667 | 1,666 | - | 5,000 | - | 5,000 |
| Final/ Terminal evaluation | each | 1 | 20,000 | 5,334 | 1,333 | 6,667 | 6,666 | - | 20,000 | - | 20,000 |
| Processing of final report | each | 1 | 6,600 | 1,760 | 440 | 2,200 | 2,200 | - | 6,600 | - | 6,600 |
| 5650 Sub-total - LOAs and Contracts |  |  |  | 92,362 | 12,839 | 97,481 | 114,198 | - | 316,880 | 145,140 | 171,740 |
| 5900 Travel |  |  |  |  |  |  |  |  |  |  |  |
| International travel | sum | 1 | 40,000 | 10,666 | 2,667 | 13,333 | 13,334 | - | 40,000 | 20,000 | 20,000 |
| Domestic travel | sum | 1 | 40,000 | 10,666 | 2,667 | 13,333 | 13,334 | - | 40,000 | 20,000 | 20,000 |
| 5900 Sub-total - Travel |  |  |  | 21,332 | 5,334 | 26,666 | 26,668 | - | 80,000 | 40,000 | 40,000 |
| 5920 Training |  |  |  |  |  |  |  |  |  |  |  |
| Technical capacity development | sum | 1 | 33,500 | 33,500 | - | - | - | - | 33,500 | 27,000 | 6,500 |
| Training for national and regional focal points | sum | 1 | 17,000 | 17,000 | - | - | - | - | 17,000 | 14,000 | 3,000 |
| Training of trainers re: MRV for data-provision guidelines | sum | 1 | 8,000 | - | - | 4,000 | 4,000 | - | 8,000 | - | 8,000 |
| 5920 Sub-total - Training |  |  |  | 50,500 | - | 4,000 | 4,000 | - | 58,500 | 41,000 | 17,500 |
| 6100 Non-expendable Procurement |  |  |  |  |  |  |  |  |  |  |  |
| Equipment for national and regional AFOLU MRV focal points | sum | 1 | 16,500 | 16,500 | - | - | - | - | 16,500 | 6,600 | 9,900 |
| ICT systems upgraded for stakeholder departments | sum | 1 | 9,000 | - | - | 4,500 | 4,500 | - | 9,000 | 3,000 | 6,000 |
| Equipment and software for data-collection and -management | sum | 1 | 107,000 | - | - | 56,000 | 51,000 | - | 107,000 | - | 107,000 |
| PMU furniture, common equipment, and renovation | sum | 1 | 4,000 | 1,066 | 267 | 1,333 | 1,334 | - | 4,000 | 3,200 | 800 |
| PMU computer equipment, electronics, power generation, security, etc. | sum | 1 | 5,003 | 1,334 | 334 | 1,668 | 1,667 | - | 5,003 | 4,000 | 1,003 |
| 6100 Sub-total - Non-expendable Procurement |  |  |  | 18,900 | 601 | 63,501 | 58,501 | - | 141,503 | 16,800 | 124,703 |
| 6300 General Operating Expenses (GOE; ≤ 5%) |  |  |  |  |  |  |  |  |  |  |  |
| Vehicle rental (incl. cars, boats, drivers, fuel, related operating costs, etc.) | day | 504 | 40 | 7,600 | 7,120 | 1,720 | 3,720 | - | 20,160 | 10,080 | 10,080 |
| Communication | mo. | 24 | 30 | 180 | 180 | 180 | 180 | - | 720 | 360 | 360 |
| Utilities | mo. | 24 | 50 | 300 | 300 | 300 | 300 | - | 1,200 | 600 | 600 |
| Stationery and Consumables | sum | 1 | 1,000 | 250 | 250 | 250 | 250 | - | 1,000 | 500 | 500 |
| Miscellaneous including contingencies | sum | 1 | 20,082 | 8,000 | 8,000 | 2,000 | 2,082 | - | 20,082 | 10,041 | 10,041 |
| 6300 Sub-total - GOE |  |  |  | 16,330 | 15,850 | 4,450 | 6,532 | - | 43,162 | 21,581 | 21,581 |
| TOTAL |  |  |  | 252,824 | 56,604 | 232,598 | 242,739 | 78,477 | 863,242 | 380,620 | 482,623 |

# Appendix 4.  Project Steering Committee’s Terms of Reference and Provisional Membership

Purpose and Duties

The PSC will provide guidance and decision-making to ensure that the project’s execution leads efficiently to the project’s objective, and that the project continually accords with national policies.  The PSC will oversee the project’s execution and ensure that all activities are executed in accordance with the project document, inception report, and updates or amendments approved by the PSC.  The PSC will:

- Provide institutional and political support for the project’s goals and activities;

- Provide overall guidance to the Project Management Unit (PMU) in the implementation of the project;

- Ensure all project outputs accord with the project document, inception report, and updates or amendments approved by the PSC;

- Review, amend (if appropriate), and clear the project’s drafted annual work-plan and budget for submission to FAO;

- Proactively identify and discuss related initiatives and policies, and their potential implications for the project;

- Provide inputs to project reviews and the terminal evaluation, review findings, and provide comments for the response;

- Facilitate relevant inter-ministerial discussion and knowledge-sharing;

- Ensure dissemination of information, best practices, and lessons learned from the project; and

- Identify, propose, and support efforts to strengthen post-project sustainability.

Membership

PSC membership is held ex officio (i.e., by office or official capacity), such that turnover does not affect membership.  The PSC’s chair and members will be confirmed during the project’s inception phase.

Nomination and Removal of Members

Nominated members may decline membership in the PSC and active members may renounce their membership at any time with notice to the chair and the PSC secretariat (PMU).  The PSC may add new members (ex officio) in accordance with the voting rules of the PSC.  However, the PSC shall aim to balance the needs for relevant representation against the needs for practical functionality of the PSC.  It is suggested that the number of voting members of the PSC not exceed 15.  Members may be removed by consensus of the chair of the PSC, the FAO Representative (as in-country representative of the GEF implementing agency), and the national GEF Operational Focal Point.

Duties of the Chairperson

The Chairperson shall exercise the functions conferred on him/ her as indicated in this document, and in particular shall:

- Declare the opening and closing of each PSC meeting;

- Direct the discussions at such meetings and ensure observance of these rules, equitably accord the privilege to speak, put questions to the members, and announce decisions;

- Rule on points of order;

- Control the proceedings of the PSC in accord with these rules;

- Ensure that the PSC’s membership continues to represent relevant stakeholder groups;

- Appoint such ad hoc committees as the PSC may direct;

- Ensure circulation of all relevant documents by the secretariat to PSC members;

- Agree with annual work-plans and budgets and any subsequently proposed amendments submitted to FAO;

- Enforce recusal for the purposes of discussion or voting for any members with a potential conflict of interest on a matter before the PSC for which the member(s) have not recused himself/ herself/ themselves;

- At his/ her discretion, in consultation with the PMU, request that the chairperson of the Technical Working Group (TWG) or his/ her designee(s) present to or advise the PSC on relevant technical matters;

- At his/ her discretion and with at least 3 business days’ advance notice to the PSC’s secretariat and members, invite relevant observers or advisors to attend PSC meetings in a non-voting capacity; and

- In consultation with the PSC’s secretariat (PMU), determine the date, location, and agenda of the PSC meetings, the chairing of such meetings as well as nomination of Chairperson and members for PSC and TWG.

Secretariat

The PMU (The National Project Manager (NPM)) will act as secretariat to the PSC and be responsible for providing PSC members with all required documents in advance of PSC meetings, including agendas, drafted annual work-plan and budget, and any documents to be discussed during the meeting.  The secretariat will ensure timely and appropriate logistical arrangements for meetings, including translation services as requested.  The secretariat will prepare a written report summarizing the main points of discussion, guidance, and decisions of the PSC, as well as any issues directed to FAO in its role as GEF Agency.   The secretariat will circulate minutes to the PSC members for review and clarification prior to finalization, and will archive the PSC’s minutes.  The secretariat will ensure that all matters necessary for the efficient operational conduct of the project and required administrative processes are raised to the PSC.

Potential Conflicts of Interest

PSC members represent the agencies, constituents, and considerations of their respective official positions (ex officio) rather than their personal interests.  PSC members must notify the PSC chair regarding any potential personal or professional conflicts of interest, and must recuse themselves from discussions or voting accordingly.

PSC members should represent agencies that are unlikely to sign LOAs or contracts related to execution of the project.  If such cases arise, those members should notify the chairperson and recuse themselves from associated discussions and voting.

Meetings of the PSC

The PSC will convene its first meeting at or around the time of the inception workshop to operationalize the project.  Among other agenda items the PSC might address in its first meeting, the PSC will:

- Revise, as needed, and confirm the membership and roles of the PSC, including the chairperson and secretariat;

- Accept the PSC’s rules and terms of reference or propose amendments to FAO in its role as GEF Agency;

- Determine the primary language for the PSC’s oral discussions (as noted below);

- Review, revise (as needed), and approve the annual work-plan and budget, including any requested amendments or changes, for submission by the PMU to FAO;

- Review, revise (as needed), and approve the initial membership and terms of reference of the Technical Working Group (TWG); and

- Set an approximate date and location for the next PSC meeting.

The PSC will meet biannually (twice per year) and on an ad-hoc basis as needed.  No more than nine months may elapse between PSC meetings.  PSC members may attend meetings virtually (e.g., video-conference) at the discretion of the chair and with adequate advance notice to the secretariat for making such arrangements.

Invitations to regular PSC meetings shall be issued at least 45 calendar days before the meeting.  Invitations to special or ad-hoc meetings shall be issued at least 20 calendar days before the meeting.  PSC members shall update their contact information with PSC secretariat if it changes.

Agenda

The secretariat will solicit requested agenda items from PSC members at least 40 days prior to regularly scheduled meetings, and as early as possible for ad-hoc meetings.  The secretariat will draft agendas and submit them for the chairperson’s review and approval.  The secretariat will send agendas to PSC members and scheduled observers at least 15 calendar days prior to regularly scheduled meetings and as early as possible for ad-hoc meetings.

The agenda of each regular meeting shall include:

- Adoption of the agenda;

- Resolution of any outstanding issues from the prior meeting;

- A report from the PMU on project-related activities during the inter-sessional period;

- A report and recommendations from the PMU on the proposed annual work-plan and budget for the ensuing period;

- Reports that require PSC consideration;

- Review of alignment and harmonization between relevant projects;

- Matters to be resolved before the next meeting;

- Consideration of the time and location of the next meeting;

- Any other matters approved by the chairperson.

The agenda of a special or ad-hoc meeting shall consist only of items relating to the purpose for which the meeting was called, unless otherwise directed by the chairperson.

Quorum

A quorum comprises at least 60% of members who have not explicitly abstained (including recusal) and must include the chair or his/ her designated representative.  Members who are unable to attend may appoint a representative on their behalf.  If at least half (50%) of members are in attendance, a quorum may also be met at the chair’s discretion if the requisite proportion of members (60%) concurs at a later date with the minutes and decisions of a meeting.

Decision-making

The PSC will endeavor to achieve consensus in all decisions.  When consensus is not possible or practicable, approval requires at least 80% support, including the support of the chair and the FAO Representative (in his/ her capacity as representative of the implementing agency).

Reports and Recommendations

At each meeting, the PSC shall agree with the report text that embodies its views, recommendations, and decisions, including a statement of minority views upon request from those members.

The secretariat will circulate a drafted PSC meeting report to the PSC’s members as soon as possible after the meeting for comments.  Comments shall be accepted over a period of 7 calendar days.  Following the chairperson approval, the final meeting report will be distributed to the PSC’s members and archived.

Official Language

Spoken:  The primary spoken language for discussions in the PSC meetings is English, however it will be decided in the first meeting whether to include Sinhala and Tamil also the language to be used for discussion. In case of agreement to use the local languages for the meeting, the PMU, as PSC Secretariat, shall arrange for simultaneous translation services as needed.

Written:  Because all official versions of the project’s documents are in English, the official written language for PSC documentation shall be English.  The PMU, as PSC Secretariat, shall arrange for translation services for written documents upon request.

# Appendix 5.  Technical Working Group’s Terms of Reference and Proposed Membership

Purpose and Duties

The purpose of the Technical Working Group (TWG) is to facilitate national initiatives to fulfill Sriu Lanka’s AFOLU-related commitments under (i) the Enhanced Transparency Framework (ETF) of the Paris Agreement and (ii) Sri Lanka’s Nationally Determined Contribution.  The TWG provides a basis for technical and operational coordination between stakeholders for climate-related measurement, reporting, and verification in the AFOLU sector.  The main duties of the TWG are described in the project document and include, inter alia:

- Draft the National Climate-change Monitoring Framework;

- Draft metadata parameters for measurement of phenomena and conditions associated with climate-change mitigation and adaptation;

- Draft related Quality Control (QC) guidelines;

- Estimate technical and budgetary requirements;

- Advise on piloting of QC protocols and remediation of operational and technical difficulties;

- Upon request of the PMU, review technical materials related to the project, such as training materials;

- Advise the Project Management Unit (PMU) and Project Steering Committee (PSC) on technical matters related to climate change in the agricultural and land-use sub-sectors;

- Anticipate technical and operational challenges during and after the project, and propose options to (i) improve the project’s efficient achievement of its objective and (ii) ensure post-project sustainability; and

- Communicate the TWG’s decisions and recommendations within members’ respective organizations.

At the discretion of the PSC, the TWG may be constituted independently or may expand the functionality of an existing technical coordination group.

Membership

The membership of the TWG comprises technical experts representing diverse fields and stakeholders relevant to climate change in Sri Llanka’s agricultural and land-use subsectors.  Members are nominated and serve in an ex-officio capacity, representing their official positions, agencies, and constituents rather than their personal interests or views.  Membership in the TWG is completely voluntary and does not affect or prejudice decisions regarding awards of contracts or LOAs to members’ respective organizations.

The chairperson of the TWG will be nominated by the PSC.  The initial nominees for membership in the TWG will be approved by the PSC.  Subsequently, the chair of the TWG may add members to the TWG with concurrence of the PMU.  Decisions of the PSC supersede those of the chair of the TWG.

The proposed initial membership of the TWG, to be considered in the PSC’s first meeting, is presented at the end of these terms of reference.

Duties of the Chairperson

The chairperson shall exercise the functions conferred on him/ her as indicated in this document, and in particular shall:

- Declare the opening and closing of each TWG meeting;

- Direct the discussions at such meetings and ensure observance of these rules, equitably accord the privilege to speak, put questions to the members, and announce decisions;

- Rule on points of order;

- Control the proceedings of the TWG in accord with these rules;

- Ensure that the TWG’s membership continues to represent relevant technical areas;

- Appoint and direct committees or sub-committees as appropriate or as the PMU or PSC may direct;

- At his/ her discretion, direct the establishment of a roster or rosters of technical experts upon whom the TWG, PMU, or PSC may wish to call;

- Ensure circulation of all relevant documents by the secretariat to TWG members;

- Review and endorse all publications of the TWG or recommendations to the PMU and PSC;

- Enforce recusal for the purposes of discussion or voting for any members with a potential conflict of interest on a matter before the TWG for which the member(s) have not recused him-/ herself/ themselves;

- Present to or advise the PMU and PSC on relevant technical matters;

- At his/ her discretion and with at least 3 business days’ advance notice to the PSC’s secretariat and members, invite relevant observers or advisors to attend PSC meetings in a non-voting capacity; and

- In consultation with the PSC’s secretariat (PMU), determine the date, location, and agenda of the PSC meetings, the chairing of such meetings as well as nomination of Chairperson and members for PSC and TWG.

Secretariat

The PMU will act as secretariat to the TWG and be responsible for providing TWG members with all required documents in advance of TWG meetings, including agendas and any documents to be discussed during the meeting.  The secretariat will ensure timely and appropriate logistical arrangements for meetings, including translation services as requested.  The secretariat will prepare a written report summarizing the main points of discussion, guidance, and decisions of the TWG, as well as any issues directed to the PMU or PSC.   The secretariat will circulate minutes to the TWG members for review and clarification prior to finalization, and will archive the TWG’s minutes.  The secretariat will ensure that all matters necessary for the efficient operational conduct of the project and required administrative processes are raised to the TWG.  The secretariat will facilitate the relevant inter-sessional collaboration of TWG members.  The PMU provides financial support to the TWG in accordance with the project’s approved work-plan and budget.

Meetings of the TWG

The TWG will meet quarterly (four times per year) and on an ad-hoc basis as needed.  TWG members may attend meetings virtually (e.g., video-conference) at the discretion of the chair and with adequate advance notice to the secretariat for making such arrangements.

Invitations to regular TWG meetings shall be issued at least 20 calendar days before the meeting.  Invitations to special or ad-hoc meetings shall be issued at least 14 calendar days before the meeting.  TWG members shall update their contact information with TWG secretariat if it changes.

The TWG will convene its first meeting as soon as practicable after approval of the PSC.  Among other agenda items the TWG might address in its first meeting, the TWG will:

- Suggest any changes in the membership and roles of the TWG for consideration by the chair, the PMU, and the PSC;

- Endorse the TWG’s rules and terms of reference or propose amendments for the PSC’s consideration;

- Determine the primary language for the TWG’s oral discussions (as noted below); and

- Set an approximate date and location for the next TWG meeting.

Agenda

The secretariat will solicit requested agenda items from TWG members at least 30 days prior to regularly scheduled meetings, and as early as possible for ad-hoc meetings.  The secretariat will draft agendas and submit them for the chairperson’s review and approval.  The secretariat will send agendas to PSC members and scheduled observers at least 10 calendar days prior to regularly scheduled meetings and as early as possible for ad-hoc meetings.

The agenda of each regular meeting shall include:

- Adoption of the agenda;

- Resolution of any outstanding issues from the prior meeting;

- A report from the PMU on progress toward deadlines relevant to the TWG;

- Documents that require TWG consideration;

- Matters to be resolved before the next meeting;

- Consideration of the time and location of the next meeting;

- Any other matters approved by the chairperson.

The agenda of a special or ad-hoc meeting shall consist only of items relating to the purpose for which the meeting was called, unless otherwise directed by the chairperson.

Quorum

A quorum comprises at least half (50%) of members who have not explicitly abstained (including recusal) and must include the chair or his/ her designated representative.  Members who are unable to attend may appoint a representative on their behalf.  If at least 30% of members are in attendance, a quorum may also be met at the chair’s discretion if the requisite proportion of members (50%) concurs at a later date with the minutes and decisions of a meeting.

Decision-making

Plenary decisions.  The PSC will endeavor to achieve consensus in all plenary decisions.  When consensus is not possible or practicable, approval requires at least 80% support, including the support of the chair and the FAO Representative (in his/ her capacity as representative of the implementing agency).

Specialized decisions.  The chairperson may designate a subset of relevant members to make decisions regarding a specialized technical area.  In such cases, chair will establish the threshold for decision-making.

Official Language

Spoken:  The primary spoken language for discussions in the PSC meetings is English, however it will be decided in the first meeting whether to include Sinhala and Tamil also the language to be used for discussion. In case of agreement to use the local languages for the meeting, the PMU, as PSC Secretariat, shall arrange for simultaneous translation services as needed.

Written:  At the discretion of the chair, publications of the TWG may be drafted and adopted in (a) English (b) Sinhala and (c) Tamil.  The PMU, as TWG Secretariat, shall arrange for translation services for written documents.  The TWG will ensure the accuracy/ fidelity of any translations.

# Appendix 6.  Abbreviated Terms of Reference for Members of the Project Staff

National Project Manager

The National Project Manager (NPM) will be stationed primarily in PMU which will be co-located with Climate Unit of Climate Change Secretariat (CCS) under the Ministry of Mahaweli Development and Environment and will be responsible for coordinating the project’s execution and daily operations.  The NPM reports to the Budget Holder (BH; in his/ her role as the in-country representative of the executing agency) and works in close cooperation with the National Project Director (NPD).

Inter alia, the NPM will:

- Coordinate technical inputs into the project;

- Coordinate and deliver the project’s activities in accordance with the project document and approved annual work-plan and budget;

- Work closely with LTO and timely obtain technical clearances for field activities as envisaged.

- Manage the project’s daily operations;

- Monitor project fund use and conduct financial control

- Propose budget revision as per the actual field needs and the approved work plan.

- Draft project procurement and submit it to FAO for technical clearance and PSC for endorsement.

- Coordinate with stakeholders and related initiatives;

- Ensure collaboration between the participating institutions and organizations;

- Ensure fulfillment of the PMU’s obligations as secretariat for the PSC and TWG;

- Implement and manage the project’s monitoring and evaluation (M&E) plan and its communication plan;

- Collect data of co-financing from various project stakeholders

- Prepare the PPRs;

- Organize annual project workshops and meetings to monitor project progress and prepare the AWP/B;

- Submit PPRs and AWP/B to PSC and FAO for approval; and

- Support the preparation of PIRs, joint supervision missions, and final evaluation.

Roles and Responsibilities

- Support the day-to-day operation of the Project activities;

- Establish and organize project task forces and ensure timely provision of suitable inputs (personnel, training, equipment and supplies) including preparing initial and regular budget revisions and providing overall administrative and operational support to the Project;

- Liaise with donors and government authorities as required;

- Ensure timely submission of regular project progress and implementation reports including identification of project follow up requirements and project closure including reporting;

- Ensure timely and complete information data entry into the field programme management information system (FPMIS) throughout the whole project cycle;

- Monitor the Project in close collaboration with other units at headquarters and at country level;

- Monitor delivery estimates and contribute to regular reports at the request of the budget holder and NPC;

- Carry out financial management and supervision of Project budgets on behalf of the budget holder;

- Lead, in collaboration with the NPM, the preparation of the preparation of annual work plans and budget;

- Appraisal and operational clearance of Project documents, preparation of budgets and active participation in project discussions;

- Prepare detailed budgets for cash transfer requests based on the annual work plans and budgets and Project account cash balance;

- Maintain the Project’s disbursement ledger and journal;

- Keep the financial records and regular review of the Project account;

- Review the receipts and financial reports submitted by service providers;

- Prepare six-monthly financial statement of expenditures and other project financial reports as required;

- Prepare relevant documents for internal and external financial audits.

Administration Associate

Roles and Responsibilities

- Support the day-to-day operation of the Project activities;

- Establish and organize project task forces and ensure timely provision of suitable inputs (personnel, training, equipment and supplies) including preparing initial and regular budget revisions and providing overall administrative and operational support to the Project;

- Liaise with donors and government authorities as required;

- Monitor the Project in close collaboration with other units at headquarters and at country level;

- Monitor delivery estimates and contribute to regular reports at the request of the budget holder and NPC;

- Carry out financial management and supervision of Project budgets on behalf of the budget holder;

- Lead, in collaboration with the NPM, the preparation of the preparation of budget;

- Appraisal and operational clearance of Project documents, preparation of budgets and active participation in project discussions;

- Prepare detailed budgets for cash transfer requests based on the annual work plans and budgets and Project account cash balance;

- Maintain the Project’s disbursement ledger and journal;

- Keep the financial records and regular review of the Project account;

- Review the receipts and financial reports submitted by service providers;

- Prepare six-monthly financial statement of expenditures and other project financial reports as required;

- Prepare relevant documents for internal and external financial audits.

Background/qualifications

- University degree in finance, business administration or a related field

- A minimum of 5 years’ experience working in one of the above fields

- Experience managing the administration and finances of large projects

- Excellent communication skills

- Excellent planning and organizing skills, accurate with attention to detail

- Able to work as part of a multi-national team

- Working knowledge of English and local languages

- Experience in the UN system is an asset

Finance / Procurement Associate

Roles and Responsibilities

            - Implementing all procurement management processes in an appropriate manner and in accordance with FAO rules, liaising with national counterparts about procurement issues and customs formalities including all procedures for importing goods into Cambodia and coordination with project partner companies involved with procurement management;

            - Monitoring cash availability and alignment with purchases made under project procurement plans;

            - Ensuring accurate records of all relevant data for operational and financial supervision of all project-related purchases;

            - Ensuring that relevant reports relating to purchase-related expenditure, forecasts and progress regarding project plans and closure are prepared and submitted in accordance with FAO and GEF procedures and according to the given formats, submission schedules and notifying reports, as necessary;

            - Implementing specific and timely actions regarding all operational requirements associated with the procurement process, including equipment, material and disbursements in the field;

            - Participating in partnership meetings with project partners and the Steering Committee, as necessary;

            - Undertaking oversight missions to monitor the results-based budget and resolve outstanding operational issues relating to procurement, as appropriate.

Background/qualifications

- University degree in economics, finance, business administration or a related field

- A minimum of 5 years’ experience working in one of the above fields

- Experience managing the procurement of large projects

- Excellent communication skills

- Excellent planning and organising skills, accurate with attention to detail

- Able to work as part of a multi-national team

- Working knowledge of English and local languages

- Experience in the UN system is an asset

Technical Assistant

The Technical Assistant will be stationed with the PMU.  The Technical Assistant will report to the National Programme Manager (NPM) and will support the NPM in coordinating the project’s execution and daily operations. The Technical Assistant works in close cooperation with other PMU staff.

Inter alia, the Technical Assistant will support:

- The coordination of technical inputs into the project;

- The monitoring of the project’s activities in accordance with the project document and approved annual work-plan and budget;

- The project’s daily operations;

- The coordination with stakeholders and related initiatives;

- Communication between the participating institutions and organizations;

- Fulfilment of the PMU’s obligations as secretariat for the PSC and TWG;

- Implementation of the project’s monitoring and evaluation (M&E) plan and its communication plan;

- The preparation of the PPRs;

- The organization of annual project workshops and meetings to monitor project progress and prepare the AWP/B;

- The submission of PPRs and AWP/B to PSC and FAO for approval; and

- The preparation of PIRs, joint supervision missions, and final evaluation.

Decision-support Specialist

The Decision-support Specialist will be stationed with the PMU.  The Decision-support Specialist will report to the National Programme Manager and will provide expertise to facilitate a decision-driven approach to the project’s outcomes, including mitigation-related MRV, adaptation-related M&R, and project-related M&E.  The Decision-support Specialist will help to ensure that capacities and systems are developed to produce action-oriented information that efficiently enables stakeholders to achieve national and local climate-related goals, especially those of the NDC.

The Decision-support Specialist will contribute directly to:

- Relevant work of the TWG and associated analyses;

- Identification of pragmatic and cost-efficient options for measurement and data-provision, especially for proxy measures;

- Drafting relevant requirements of LOAs and contracts;

- Structuring the online data-sharing portal;

- Drafting of technical reports;

- Engaging with stakeholders to understand and define relevant decisions and informational needs, especially related to informational constraints to taking relevant actions;

- Proposing options for analyses and data visualizations efficiently tailored to stakeholders’ needs; and

- Facilitating the dissemination and broader use of the project’s best practices and lessons learned.

National Consultant (NC)– Climate Change Mitigation

Under the overall supervision of National Programme Director, Lead Technical Officer of FAO, FAO Representative and National Programme Manager the consultant will closely work on capacity development for MRV activities of emissions and removals from AFOLU sector. He or She will also ensure implementation of all climate change mitigation related activities in this project. Apart from implementing regular project activities the NC will also provide extensive support and coordination to FAO HQ and FAORAP technical experts engaged in providing technical advice for project implementation.

The Details of activities are given below:

    - Support hiring of consultants and technical experts; ensure that consultants are guided and supported to deliver project documents on time; and provide substantive inputs to various drafts – till finalization; and seek timely input from consultants as well as FAO Technical Advisers. Meet all the deadlines of project cycle.

    - Undertake and manage the necessary due diligence, risk analysis and mitigation in the structuring and implementation of project activities.

    - Provide substantial advice to executing agencies on project preparation and processing for implementation of project activities

    - Prepare and Monitor LOAs and contracts for various project activities to be implemented by stakeholder organization and individual consultants.

    - Facilitate active relationships all stakeholders including Civil Society Organization, Non-Governmental Organizations and Private sector in the country and beyond.

    - Development of partnerships with the other UN Agencies, government institutions, private sector, civil society in the specific thematic areas, country needs and donors’ priorities.

    - Analysis and prepare plans for active contribution to the overall office effort in resource mobilization.

    - Maintain and share knowledge on lessons learned from public and private sector operations and emerging best practices in areas of expertise.

    - Participate in and contribute to activities for advocacy, dissemination and knowledge building relating to FAO’s relevant policies and strategies to promote green growth.

    - Support or contribute to the planning and implementation of capacity development activities, workshops, meetings and conferences on CBIT for AFOLU sector;

    - Regular and systematic documentation and archiving process established to ensure accuracy and sustainability of the inventory, including quality assurance and quality control, for all project activities completion.

    - GHG Information Management System (IMS) and infrastructure for agriculture and land-use sectors upgraded

    - Capacity and system hardware developed for relevant institutions at different levels to adopt and mainstream latest tools and methodologies to develop country-specific emission factors (EFs), improve activity data (AD) and better quantify the impact of mitigation policy measures in the agriculture and land-use sectors

    - National/sectoral reports prepared and submitted on inventory of emissions sources and sinks and emissions reduction activities from agriculture and land-use sectors consistent with latest UNFCCC guidance

The Consultant will do the background research; coordinate internal and external stakeholders; build partnership with government and private sector actors; and oversee the technical work of other consultants engaged in development of project documents of the pipeline projects. The consultant will deliver an inception report documenting all planned work, which must be approved by the supervisor.

National Consultant – Climate Change Adaptation

Under the overall supervision of National Programme Director, Lead Technical Officer of FAO, FAO Representative and National Programme Manager the consultant will closely work on capacity development for to strengthen capacity to measure climate-change impacts, vulnerabilities, and adaptation-related activities in the agricultural and land-use sectors.He or She will also ensure implementation of all climate change adaptation related activities in this project. Apart from implementing regular project activities the NC will also provide extensive support and coordination to FAO HQ and FAORAP technical experts engaged in providing technical advice for project implementation.

The Details of activities are given below:

    - Support hiring of consultants and technical experts; ensure that consultants are guided and supported to deliver project documents on time; and provide substantive inputs to various drafts – till finalization; and seek timely input from consultants as well as FAO Technical Advisers. Meet all the deadlines of project cycle.

    - Undertake and manage the necessary due diligence, risk analysis and mitigation in the structuring and implementation of project activities.

    - Provide substantial advice to executing agencies on project preparation and processing for implementation of project activities

    - Prepare and Monitor LOAs and contracts for various project activities to be implemented by stakeholder organization and individual consultants.

    - Facilitate active relationships all stakeholders including Civil Society Organization, Non-Governmental Organizations and Private sector in the country and beyond.

    - Development of partnerships with the other UN Agencies, government institutions, private sector, civil society in the specific thematic areas, country needs and donors’ priorities.

    - Analysis and prepare plans for active contribution to the overall office effort in resource mobilization.

    - Maintain and share knowledge on lessons learned from public and private sector operations and emerging best practices in areas of expertise.

    - Participate in and contribute to activities for advocacy, dissemination and knowledge building relating to FAO’s relevant climate change adaptation policies and strategies to promote green growth.

    - Support or contribute to the planning and implementation of capacity development activities, workshops, meetings and conferences on CBIT for AFOLU sector;

    - Measurement framework developed for climate-change impacts, vulnerabilities, and adaptation-related activities prioritized in the NDC for the agriculture, forestry and land-use sectors.

    - Information technology systems upgraded to integrate and analyze adaptation-related data.

    - Capacity and technology upgraded in relevant institutions to strengthen M&R for adaptation priorities identified in the NDC for the agricultural and land-use sectors.

    - Relevant measures validated and piloted for adaptation priorities identified in the NDC for the agricultural and land-use sectors.

The Consultant will do the background research; coordinate internal and external stakeholders; build partnership with government and private sector actors; and oversee the technical work of other consultants engaged in project activities implementation. The consultant will deliver an inception report documenting all planned work, which must be approved by the supervisor.

# Appendix 7.  Co-financing Letter - Ministry of Mahaweli Development and Environment

# Appendix 8.  Co-financing Letter - FAO

E.g., NDCs for the 5-year period from 1 January 2026 to 31 December 2030 must be submitted by 31 December 2020.

as of Dec 2018 (COP24) Modalities, Procedures, and Guidelines (MPGs) for the transparency framework for actions and support referred to in Article 13 of the Paris Agreement have been adopted. The MPG also sets out further work by the Subsidiary Body for Scientific and Technological Advice (SBSTA) to develop common reporting tables and outlines of the biennial transparency report (BTR), national inventory document and technical expert review report pursuant to MPGs, for consideration and adoption by the Conference of the Parties by November 2020. Parties shall submit their first biennial transparency report and national inventory report, if submitted as a stand-alone report, in accordance with the modalities, procedures and guidelines, at the latest by 31 December 2024.

Verification can be done domestically, but the term is omitted here to avoid the insinuation of international verification processes for adaptation-related measurements and reports.

Non-Annex I parties are also encouraged to conduct MRV relevant to climate-change adaptation as it pertains to (i) climate change impacts and vulnerabilities, and (ii) progress on adaptive priorities established in a country’s NDC.  Adaptation-related MRV is more country-specific than is mitigation-related MRV, and is therefore less amenable to international aggregation.

Modalities, Procedures, and Guidelines (MPGs) for the transparency framework for actions and support referred to in Article 13 of the Paris Agreement adopted at the 24th COP, December 2018

Reproduction of Figure 1.4 in Volume 4, Chapter 1 of the IPCC’s Guidelines for National Greenhouse Gas Inventories (2006).  https://www.ipcc-nggip.iges.or.jp/public/2006gl/pdf/4_Volume4/V4_01_Ch1_Introduction.pdf

IPCC’s Guidelines (2006) provide guidance on the identification of key categories.

E.g., a country’s forests might be a key category because they sequester a significant amount of GHGs.

E.g., emissions from dairy cattle might be minor, but rapidly increasing.

Calculations of GHG fluxes are quite sensitive to certain parameters and estimates.  Therefore, uncertainties in those influential factors can justify the special attention given to key categories.  E.g., calculations of GHGs from enteric fermentation are sensitive to estimates of the digestibility of livestock feed.

QC refers to efforts, typically ex ante, to ensure the rigor of measurement and analyses undertaken by entities and individuals directly involved in the measurement or inventory process—e.g., establishing standard operating procedures (SOPs) for data collection, calibrating measurement equipment, training field staff, etc.

QA refers to efforts, typically ex post, to check the accuracy of obtained measures by entities and individuals not directly involved in the measurement or inventory process—e.g., in-depth spot checks, data audits, etc.

http://unfccc.int/tools_xml/country_LK.html.

Adapted from Second National Communication to UNFCCC, Year 2012.

CB (2011 and 2016). Central Bank of Sri Lanka, Annual Report.

FAO & New Zealand Agricultural Greenhouse Gas Research Centre. 2017. Options for low-emission development in the Sri Lanka dairy sector – reducing enteric methane for food security and livelihoods. Rome. 38 pp.

Forest Department unpublished provisional data from the recent forest cover mapping exercise.

GOSL (2008). Nomination of the Central Highlands of Sri Lanka: its cultural and natural heritage for inscription in the world heritage list. Submitted to UNESCO by the Government of the Democratic Socialist Republic of Sri Lanka.

Mittermeier RA, Valladares-Pádua CB, Rylands AB, Eudey AA, Butynski TM, Ganzhorn J , Kormos, R , Aguiar, J , Walker, S. 2006.  Most     Endangered Primates 2004-2006. Conservation International 20:1-28.

FAO. (2017). Tracking adaptation in agricultural sectors:  Climate change adaptation indicators.

SL REDD program

Page-40, Technology Needs Assessment and Technology Action Plans for Climate Change Adaptation 2011.

Sri Lanka’s National Capacity Needs Self-assessment (2007).

In order to address the cross sectoral nature of major environmental challenges caused by climate change, and to fulfil the commitments under the United Nations Framework Convention on Climate Change (UNFCCC) & Kyoto Protocol, the Ministry of Mahaweli Development and Environment, which is the National Focal Point for the UNFCCC and Kyoto Protocol has taken the initiative to establish a Climate Change Secretariat under its preview. The Climate Change Secretariat, which is headed by the Director of the Climate Change Division, adopts a comprehensive national approach to address climate change challenges that as these concerns categorize as an environmental concern, which is also a development issue of Sri Lanka.

Third National Communication is in a process of finalization by Climate Change Secretariat, Ministry of Mahaweli Development and Environment.

https://www4.unfccc.int/sites/NAPC/Documents%20NAP/National%20Reports/National%20Adaptation%20Plan%20of%20Sri%20Lanka.pdf

Sustainable financing could take the form of (i) revenues from enforcement or value-recovery from resource extraction (e.g., mining-related royalties), (ii) international markets, such as carbon markets, or (iii) an endowed trust.  (Regular funding from the state budget is plausible, but would require a supportive funding source, such as those described here.)  Whatever the funding source, effective MRV will be required and is often a prerequisite.

which can also comprise internal QA

and potential domestic verification at some point in the future

Available via:  http://www.fao.org/3/a-i4260e.pdf

See:  http://www.fao.org/in-action/micca/resources/tools/en/

Available via:  http://www.fao.org/3/a-i8145e.pdf

“Verification” is often omitted from adaptation-related tracking protocols in order to avoid the insinuation of international verification processes or requirements, though domestic verification is possible.

E.g., “Results-based management (RBM) at the GEF is designed to focus M&E of projects and programs towards portfolio-level objectives and goals.  The RBM framework for the LDCF/SCCF supports the GEF Secretariat in monitoring and reporting and it guides GEF Agencies in project design.”  Similarly, AMAT “provides concrete means for [GEF] Agencies and GEFSEC to track progress towards portfolio-level objectives, outcomes and outputs.”  Biagini, B. (June 2011).  Monitoring and evaluation for adaptation:  The GEF experience. Presentation at UNFCCC Climate Talks:  Bonn, Germany.

Table adapted and expanded from FAO. (2017). Tracking adaptation in agricultural sectors:  Climate change adaptation indicators.

Indicator 3 applies to all outcomes under the CCM focal area.

The BH for execution funds is typically the FAOR, who is typically also the BH for the portion of agency fees allocated by FAO for national-level implementation.

E.g., FAO. (2012). Guide to the Project Cycle.  Available via:  www.fao.org/docrep/016/ap105e/ap105e.pdf

GEF Council (2006).  Roles and comparative advantages of the GEF agencies.  GEF/C.30/9.

See:  http://www.fao.org/in-action/micca/resources/tools/en/

Available via:  http://www.fao.org/3/a-i4260e.pdf

Available via:  http://www.fao.org/tc/exact/ex-act-home/en/

See FAO Corporate Strategy; available via:  http://www.fao.org/capacity-development/en/

Indicator refers to the institutional arrangements for data-sharing and data-provision, not the production of data/ information (i.e., measurement), which is covered under Components 2 and 3.

Versus his/ her capacity as representative of the executing agency

Versus his/ her capacity as representative of the executing agency