UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  | GEF ID.:5775 | Umoja no:P1-33GFL-000812 |  |
| --- | --- | --- | --- | --- |
| Project Number + Project Title |  | Building the Foundation for Forest Landscape Restoration at Scale |  |  |
| Duration months | Planned | 36 months |  |  |
|  | Extension(s) | 17 April 2019 ¦ 3 months added; new completion date: 31 July 2019 |  |  |
| Division(s) Implementing the project |  | GEF Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Executing Agency(ies) |  | World Resources Institute (WRI) |  |  |
| Names of Other Project Partners |  | WRI India |  |  |
|  |  | WRI Indonesia |  |  |
|  |  | Peatland Restoration Agency (BRG) ¦ Indonesia |  |  |
|  |  | Environment, Forest and Climate Change Commission ¦ Ethiopia |  |  |
|  |  | Kenya Forest Service ¦ Kenya |  |  |
|  |  | Kenya Water Towers Agency ¦ Kenya |  |  |
|  |  | Government of Makueni County ¦ Kenya |  |  |
|  |  | Ministry of Environment – Forest Service (Eaux et Foret) ¦ Niger |  |  |
|  |  | Ministry of Environment – Monitoring and Evaluation Center (CNEDD) ¦ Niger |  |  |
|  |  | Regional Center for Specialized Learning in Agriculture (CRESA) ¦ Niger |  |  |
|  |  | University of Niamey (Agronomy faculty) ¦ Niger |  |  |
|  |  | National Agroforestry Institute (INRAN) ¦ Niger |  |  |
| Project Type |  | Medium Size Project |  |  |
| Project Scope |  | Global + Ethiopia, Kenya, Niger, India, and Indonesia |  |  |
| Names of Beneficiary Countries |  | Ethiopia, Kenya, Niger, India, and Indonesia |  |  |
| Programme of Work |  | PoW 2018-2019, subprogramme 3 on healthy and productive ecosystems; accomplishment a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels |  |  |
| GEF Focal Area(s) |  | Land Degradation – 3 |  |  |
| UNDAF linkages |  | Ethiopia ¦ UNDAF (2016-2020). https://www.undp.org/content/dam/undp/documents/undaf/Ethiopia%20-%202016-2020.pdf. Project is aligned with Outcomes 1, 2 3, 5, 13, for example: Selected federal and regional institutions have improved competencies to deliver agricultural related services and natural resources management |  |  |
|  |  | Kenya ¦ UNDAF (2014-2018). https://www.unicef.org/about/execboard/files/DPDCPKEN2_UNDAF.pdf Project is aligned with Outcome 4: Environmental sustainability, land management and human security: By 2030 Kenya is prosperous, underpinned by efficient management of natural resources and equitable access of Kenyans to development assets including land, water and other renewable resources, and achievement and sustainability of national cohesion and resilience that guarantees long term peace and prosperity |  |  |
|  |  | Niger ¦ UNDAF (2014-2018). https://www.un.org/en/development/desa/population/migration/events/other/workshop/2015/docs/Workshop2015_UNDAF_Niger.pdf Project is aligned with Outcomes highlighted under 1: Resilience: food and nutritional security, environmental management, prevention and risk management and disaster reduction |  |  |
|  |  | India ¦ UNDAF (2013-2017). https://www.unicef.org/about/execboard/files/IND_FINAL_UNDAF_DOC_2013-2017.pdf Project is aligned with Outcome 6: Government, industry and other relevant stakeholders actively promote more environmentally sustainable development, and resilience of communities is enhanced in the face of challenges of Climate Change, Disaster Risk and natural resource depletion |  |  |
|  |  | Indonesia ¦ UNDAF (2016-2020). https://www.unicef.org/about/execboard/files/Indonesia-UNPDF_2016_-_2020_final.pdf Project is aligned with Outcome 3: Environmental sustainability and enhanced resilience to shocks which aims for: By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  | 2.4.1 - Proportion of agricultural area under productive and sustainable agriculture 6.3.2 - Proportion of bodies of water with good ambient water quality 15.1.1 - Forest area as a proportion of total land area 15.2.1 - Progress towards sustainable forest management 15.3.1 - Proportion of land that is degraded over total land area 15.9.1 - Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011-2020 |  |  |
| GEF financing amount |  | $1,900,000 |  |  |
| Co-financing amount |  | $6,250,000 |  |  |
| Date of CEO Endorsement |  | 31 August 2015 |  |  |
| Start of Implementation |  | 17 November 2015 |  |  |
| Date of first disbursement |  | 8 March 2016 |  |  |
| Total disbursement as of 30 June |  | USD $ 1,075,324 |  |  |
| Total expenditure as of 30 June |  | USD $1,819,384 |  |  |
| Expected Mid-Term Date |  | N/A |  |  |
| Completion Date |  | Planned |  | April 2019 |
|  |  | Revised |  | 31 January 2020 |
| Expected Terminal Evaluation Date |  | 30 September 2019 |  |  |
| Expected Financial Closure Date |  | March 30 2020 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) PoW 2018-2019, subprogramme 3 on healthy and productive ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) Accomplishment a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels. Achievement (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems Achievement (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services |
| --- | --- |
| The approved objective of this project is to contribute to the wider sustainable landscape goal and its interaction with the complementary strategies of avoided deforestation and climate smart agriculture. In other words, the project will help to achieve large-scale landscape restoration and the revitalization of degraded lands and forests. To date, the project has had tremendous success in achieving this objective by building an enabling environment that allows the countries to scale their FLR initiatives. ROAM assessments were carried out at national and subnational levels, informing FLR commitments to the Bonn Challenge and AFR100, as well as helping to prioritize areas to focus limited time and resources on. Restoration Diagnostic assessments identified key enabling factors that were both missing and in place, serving as the basis for FLR strategies and action plans. Multi-stakeholder working groups have been established that enable a diverse group of actors who do not typically engage with one another to collaborate on FLR planning and priority setting. Accelerators have been run regionally (Africa) and nationally (Niger) that build the capacities and skills of FLR entrepreneurs who aim to address land degradation and climate change through business opportunities. Monitoring frameworks and systems are now in place to allow countries to track their progress towards locally relevant goals and objectives to ensure FLR meets both environmental and socioeconomic targets. FLR is now solidly on the development agenda in all of these countries when at the beginning of the project it was nearly non-existent. The foundation for scaling locally appropriate FLR strategies has been set and many countries are now building on this success and moving towards implementation on the ground based on well-founded analysis and stakeholder consultation. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
| N/A GEF 5 Project | Indicative expected Results |

| Planned linkages with UNDAF | Ethiopia: - Outcome 1: By working with the agricultural sector to plan for and monitor trees as well as clearly articulating the benefits from trees and identifying (partially) missing enabling conditions for successful long-term agroforestry systems, the project has contributed to more productive, sustainable and diversified agriculture systems. - Outcome 2: By working with restoration entrepreneurs, the project has contributed to building a thriving forest industry, which has the potential to create hundreds of thousands of jobs. - Outcome 3: By mapping potential for new natural forests and developing a tool to monitor them, the project has laid the ground to greater provision of ecosystem services, and indirectly a decrease in the incidence of some natural disasters. - Outcomes 5: By publishing the potential maps for tree-based landscape restoration on-line and developing the tools to monitor tree cover and distribution inside and outside forests, the project has helped Ethiopia take a great stride towards better planning and monitoring their trees, a crucial mitigation and adaptation measure to climate change. - Outcome 13: Through the adaptation and implementation of new tools and the capacity built within key institutions in Ethiopia, the project has contributed to increasing the consideration of data in decision-making. Kenya: In Kenya, the project helped contribute towards the UNDAF by: - Identifying opportunities for landscape restoration; - Mobilizing and inspiring a national and sub-national (Makueni County) restoration movement; - Supporting the establishment of the first cross-sector landscape restoration working group to guide and coordinate restoration efforts; - Setting a national restoration target to catalyze restoration and better coordination of landscape restoration. - The Water Towers monitoring framework will directly contribute to efficient and effective management of the water towers ensuring sustainable supply of resources for communities into the future. Niger: In Niger, the project helped contribute towards Outcomes 3, 4 and 5 under the UNDAF by: - Assisting the government of Niger in 1) identifying degraded areas; 2) mapping priority landscapes and 3) proposing low-cost solutions for greater management of scare resources and fragile ecosystems. - Proposing land restoration options (including Assisted Natural Regeneration and agroforestry) and mobilizing local restoration champions to improve resilience to climate change and food security. - Conducting research on the socioeconomic benefits of land restoration at the subnational level (in the Maradi Region) to understand the economical dimension of FLR, thus allowing food insecure populations to have more resilient livelihoods and sustainable food systems. - Supporting Niger in the development of a National Strategy on Sustainable Land Management and adopting a decree allowing legal tree tenure to farmers, which contributed to establishing the legal/political environment for improved food security and social protection. - Strengthening the technical and financial capacity to tackle environmental management by providing trainings on monitoring and reporting systems and by supporting the country’s efforts to access private sector funding. India: In India, the project helped contribute towards Outcome 6 under the UNDAF by: - Publishing a national level restoration opportunities atlas that supports building national and state-level restoration pathways for achieving India’s climate and sustainable development commitments including the nationally determined contribution to the Paris Climate Agreement, Sustainable Development Goals, Bonn Challenge, Aichi biodiversity targets and land degradation neutrality target. - Adapting the Restoration Opportunity Assessment Methodology (ROAM) to the Sidhi district and Indian context, enabling the assessment of landscape restoration potential at landscape level for enhanced flow of ecosystem services, increased resilience to climate change, creation of green jobs – particularly for women, persons belonging to Scheduled Caste/Scheduled Tribe and other marginalized groups – and strengthened management of natural resources. - Developing a resource suite of tools and methods that can be utilized by government, industry and other relevant stakeholders to promote sustainable development using a landscape approach, that supports monitoring and planning landscape restoration to meet environmental goals and developmental priorities. - Conducting capacity building workshops on the assessment of restoration opportunities for officials from NABARD, forest department, state governments, civil society and private sector. Indonesia: In Indonesia, the project helped contribute towards the UNDAF by: - Supporting the sub-national government in mapping degraded land and restoration potential, including in peatlands, where Indonesia is focusing its emission reduction target. - Recommending restoration interventions consisting of natural regeneration, agroforestry, and rehabilitation. - Enhancing technical capacity of government through collating best practices for restoration in protected areas and knowledge sharing. - Assisting the government to achieve its restoration target through developing a platform to monitor peatland restoration and the state of peatlands nationally. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | 2.4.1 - Proportion of agricultural area under productive and sustainable agriculture: The restoration potential mapping done through this project has given countries a clear understanding of where and to what extent agroforestry and climate smart agriculture can be implemented. The action plans that have been developed or are under development by the technical working groups have a strong focus on expanding the inclusion of trees into agricultural landscapes to enhance ecosystem services and aid with climate change adaptation. 6.3.2 - Proportion of bodies of water with good ambient water quality: In many of the countries, water is one of the main drivers of restoration. In Kenya specifically, the proejct is working with the Kenya Water Towers Agency, whose mandate is to conserve and restore the forested water catchments to provide a number of ecosystem service, clean water being one of the most important. Kenya’s water towers are the sources of nearly all of Kenya’s surface water and play a key role in filtering this water for downstream uses. 15.1.1 - Forest area as a proportion of total land area: Through this project, WRI and its partners were able to help secure restoration targets in all of the target countries totaling 44.6 million ha. Additionally, other countries in Africa have made commitments to the AFR100 during the life of this project, inspired by the steps taken by Niger, Kenya, and Ethiopia. This area includes both naturally forested areas, commercial plantations, and agroforests. Through the resto of the activities carried out on mapping, planning, policy development, and so on, the countries are in a better position to fulfill these commitments, adding nearly 50 million ha of additional forest land to the world. 15.2.1 - Progress towards sustainable forest management: The restoration strategies and plans developed through this project and based on the results from the ROAM process, highlight the importance of managing current forest cover sustainably while taking steps towards expanding these forests through restoration. The Technical Working Groups established in the countries are well positioned to continue providing guidance on best practices for sustainable forest management and restoration. 15.3.1 - Proportion of land that is degraded over total land area: The 44.6 million ha committed to being restored by the target countries will target degraded land, bring it back into productivity. By restoring these areas, the countries are not only increasing forest and tree cover but are recuperating degraded ecosystem services that will benefit many communities, both natural and human. 15.9.1 - Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011-2020: In many of the target countries, biodiversity was also a strong driver of restoration. The provision of important wildlife habitat was a key factor in many of the ROAM processes undertaken. In Indonesia, the target restoration of critical peatlands will have massive positive impacts for local wildlife. In Kenya and Ethiopia, wildlife corridors and water body buffers emerged as important areas to target for restoration. |
| --- | --- |

| Implementation Status | FY 2017 | FY 2018 | FY 2019 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | Final PIR |  |  |

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Global: The World Resources Institute and partners have achieved the target outcomes for this reporting period. The high-level achievements in each target country have positioned each of them to be able to build on this foundation and meet their ambitious targets set forth in the first years of the project. The project team has completed all final activities in this final reporting period. Globally relevant highlights of the project team’s progress include: - The World Resources Institute continues to develop and test new tools and methods across the world to support FLR planning and implementation. In the last reporting period, WRI published a new guide, Mapping Social Landscapes, which for the first time details the process for identifying and mapping the diverse set of actors present within a specified geographic space (e.g. country, district, landscape) and how they are connected. This analysis helps identify key areas for intervention (e.g. which actors serve as bridges to other groups or sectors that are currently not being reached; which actors are bottle necks or gate keepers of information). The team has also further developed and refined the WRI-FAO restoration monitoring framework into a step-by-step guide which will be officially launched in October in Rome. The monitoring guide has now been used in 5 countries to assist in identifying key indicators and metrics for monitoring progress towards FLR goals within countries or sub-national administrations. Finally, the team continues to explore and test new tools for monitoring restoration progress by using Collect Earth Online for assessments in a selection of landscapes. The online version of the FAO-developed tool Collect Earth allows for greater detailed analysis and collaboration across geographies, opening the possibilities for collaborative monitoring efforts with teams from around the globe. WRI will be publishing a detailed user guide for using Collect Earth for monitoring FLR by the end of 2019. - Country-level commitments to FLR continue to be made across the globe. During the reporting period, three additional countries in Africa have officially joined the AFR100, bringing the total number of hectares committed to the initiative to 113 million ha across 28 countries. - Burkina Faso: 5 million ha - Tanzania: 5.2 million ha - Zimbabwe: 2 million ha In Latin America, the Initiative 20x20 has surpassed its commitment goal by more than double, with 50 million ha now committed to being restored across the region. The initiative is on track to meet the 20 million ha target by 2020, with the additional 30 million extending through to 2030. - High-level commitments to accelerate and scale up FLR continue to emerge as more countries see the connection between ecosystem restoration and meeting development goals. First proposed in March by El Salvador’s Ministry of Environment and then endorsed by meeting participants at the 3rd annual AFR100 partners’ meeting (including the 28 member countries), the United Nations Decade of Ecosystem Restoration (2021 – 2030) has been approved by the UN General Assembly (UNGA). If successful, “restoration could remove up to 26 gigatons of greenhouse gases from the atmosphere” according to UN Environment. WRI continues to explore new ways to finance FLR both in the target countries and beyond. In November 2018, WRI and Fledge launched the first ever Land Accelerator for restoration entrepreneurs across Africa. The accelerator was a success, attracting hundreds of applicants from across the continent. 12 businesses were selected to participate in the program, culminating in a demonstration day in front of private investors. Building on the success of the first Land Accelerator, a second accelerator was hosted in September 2019. The entrepreneurs not only receive a week-long intensive training on both business/planning/presentation/and restoration skills, but also receive mentorship for the months following the accelerator. WRI is now scaling this program to include accelerators in Latin America and India in the coming years. WRI is also developing a digital platform that will connect financiers with landscape restoration implementers in need of funding. This restoration marketplace will serve as a vetted matchmaking platform between the two parties in an effort to reduce the time spent looking for viable projects and funding as well as level the playing field and provide additional transparency to the process for project developers. A minimum viable product of the platform is planned to be beta tested in early 2020, initially focusing on philanthropic funding sources. The team sees enormous potential to grow the platform to include private sector investment in restoration businesses. Over the last year the team has manually matched nearly $2 million with projects on the ground across the world, including Kenya and Ethiopia. - As more countries use the WRI-FAO monitoring framework guide to identify key indicators and metrics for tracking progress against FLR goals, WRI has continued to refine its suite of tools to provide easy-to-use platforms for implementing these systems. WRI’s Forest Atlas and Map Builder platforms, originally developed for easily implemented forest monitoring platforms to fight against deforestation, are now being tested as platforms for tracking restoration progress. Ethiopia, Kenya, and India are now using this platform for FLR. The ease of use and replicability of the platform makes it an ideal tool for replicating nationally-relevant monitoring systems around the world. WRI has also begun testing the use of multiple datasets to better detect trees outside of the forest and regrowth of trees. The first analysis of this new data was conducted for the Mekong region and presented in a detailed report at the New York Declaration on Forests in New York in September. This analysis will continue to be refined in an effort to produce a global layer for tree cover regrowth similar to the global layer for tree cover loss found on the Global Forest Watch platform. Kenya: A national FLR restoration coordination platform was established through the support of this project that brought together stakeholders from forest, agriculture, water, livestock, climate, among others, for the first time to collaboratively share, learn and plan FLR goals together. This platform led to a national Forest and landscape restoration movement in Kenya. In September 2016 the Ministry of Environment and Natural Resources officially launched the national landscape restoration potential opportunities maps, web atlas, and AFR100 and Bonn Challenge restoration commitment of 5.1 million ha. Many sectors outside the environment and natural resources disciplines were in attendance. The broad attendance and ownership by all stakeholders of the mapping process and the national pledge is one of the major achievements of the event. Many media outlets were also present and helped get the landscape restoration message out to the Kenyan public, resulting in many visits to the Kenya restoration web atlas. WRI has now been working at the county level in Makueni County, which lies 70km southeast of Nairobi. The progressive governor, Kivutha Kibwana, and his team have been very open to addressing major environmental and social challenges in the county through the application of landscape restoration. The county-level restoration mapping and application of ROAM have been key in outlining the first county landscape restoration action plan in Kenya. Lastly, the Kenya Water Towers Agency (KWTA) has made large strides in developing a national landscape restoration monitoring framework. A KWTA-led cross-sector monitoring technical working group recently released a national monitoring framework report for landscape restoration detailing the indicators and metrics that will need to be monitored to track progress against national restoration goals, as well as the key actors who will need to be involved in providing data. A national monitoring platform is now being developed based on the WRI Forest Atlas platform, which will allow KWTA to combine national datasets with datasets available on the Global Forest Watch platform in order to better manage the water towers and track restoration progress. Ethiopia: The project has empowered restoration actors to make more sciences-based decisions. For the first time, they have access to national restoration potential maps and data on http://eth.restorationatlas.org. The project also developed a method tailored to Ethiopia to map restoration potential and prioritize implementation at national and woreda levels. The project helped the Ethiopian Government have a better understanding and provided tools regarding the increase of financial flows to restoration. It helped increase investors’ interest in Ethiopian restoration businesses and supported the first foray of 2 local NGOs in crowdsourcing. It also was instrumental in successfully moving Ethiopia’s $22.5M-FOLUR IP proposal from Expression of Interest to Concept Note. The project also provided the Ethiopian Government with tools to monitor tree cover and distribution across all sectors. It identified 35 indicators to track progress towards targets and inform implementation; it created the Tree Assessment Survey to collect data on tree cover and distribution from very-high-resolution imagery; and it put forward a roadmap regarding how to scale up the use of the Tree Assessment Survey. Niger: In Niger, the project was announced a few months after the country had announced its commitment to the Bonn Challenge and the AFR100 Initiative. Consequently, the first two years of the project were aimed at operationalizing the country’s commitment, which included compiling success factors and barrier; and prioritizing key regions for an accelerated achievement of the 3.2 million of restored land, pledged by the government by 2030. In September 2017, the project team contributed to the 2nd Annual AFR100 Partners meeting, held in Niamey, by organizing a site visit, with over 150 participants, in Tillabery to showcase successfully restored landscapes and innovative water retention techniques. Following the enthusiasm built by the AFR100 Annual meeting in Niamey, the project team organized a national workshop, convened in May 2018, by the Director of the Forest Service of the Ministry of Environment, with more than 50 participants including senior staff of the Ministry of Planning and Ministry of Agriculture, technical partners engaged in FLR, local NGOs, religious groups, and representatives of WRI. During the workshop, a national task force on FMNR was created along with a proposed road map to regreening Niger at low cost, that was shared with His Excellency Mr. Almoustapha Garba, Ministry of Environment. Afterwards, in June 2018, the Ministry of Environment released a National Strategy on Land Management with a strong emphasis on FMNR. During that workshop, WRI also proposed the concept of a “week of restauration in Niger” – a week dedicated to various discussions on restoration. The concept was welcomed and adopted as a yearly event in the Ministry of Environment’s workplan which underlines the country’s political will and cross sectoral support to FLR. To further promote the use of FMNR in local communities, the Ministry of Environment, in collaboration with WRI, organized a radio broadcast in May 2018, featuring two restoration champions from the Dan Saga Commune to share their experiences in assisted natural regeneration (ANR) and encourage their other farmers from the Maradi region to regreen their lands. The radio event was successful in targeting different communities and deepened the interest of the Forest Services to use tools such as radios to promote restoration in other regions. A second radio event was organized in December 2018, featuring two restoration champions, who have transformed the Simiri communes in the Tillabery Region with water retention techniques including banquettes and half-moons. Both radio broadcasts were recorded and continuously replayed across the countries on local radio stations, by the Department of Forestry. Other tools, such the Tree Cover Mapper, were tested and applied to support FLR monitoring and progress report, and thus empowering decision making processed for better scaling up approaches. During Q4 2018, the team focused on seeking approval on a law decree that supports FMNR and supporting farmers to own the tree on their farmlands. WRI developed recommendations on a decree on agroforestry that adequately consider the rights of farmers. A work plan was sent to the Ministry of Planning and other partners engaged in FLR for their review in September 2018 and, two experts on national resources policy and ecosystems policies were selected, in October 2018, to develop a draft of a decree on agroforestry. The drafted decree from the consultants was first revised and commented by WRI, the Department of Forestry, and the Ministry of Agriculture, before being shared with a larger audience of FMNR agents in Niger during a national forum on agroforestry in December 2018. The forum took place in the Dosso region and welcomed over 50 representatives from the government, international and national NGOs, commune leaders, civil society groups, forest rangers and farmers. The proposed decree was thoroughly discussed, and several points of improvements were identified including procedures in case of illegal cutting and the role of the treasury in all financial transactions. A final document, incorporating recommendations from the forum, was prepared by the Department of Forestry with the plan of submitting it to the Prime Minister office for an internal review, and official adoption of the decree. The team also focused on increasing financial flows for restauration activities in the country. WRI supported the Ministry of Environment in the development of GEF7 funds by identifying national consultants to assist in the development of concept notes and GEF’s Expression of Interest. Furthermore, December 19, 2018, WRI hosted a business workshop in Niamey to support local restoration entrepreneurs who want to raise capital to grow their enterprises. The business workshop provided some investment readiness training as well as the opportunity for the enterprises and entrepreneurs to identify common challenges and opportunities for growth. A follow-up event was organized in March 2019, using another donor’s grant, but building on the foundation laid by this GEF5 project. India: In India, the project focused on: - building evidence and tools to develop pathways to achieve India’s international commitments and domestic targets related to landscape restoration; - assessing the potential for landscape restoration to provide climate and livelihood benefits; - engaging with multiple stakeholders and disseminating findings to scale landscape restoration. The Restoration Opportunities Atlas for India was launched in September 2018 at a roundtable dialogue chaired by Mr. Jamshyd Godrej, with prominent participants from government, civil society and private sector. The atlas supports decision-makers to develop national and state-level pathways for achieving India’s forestry target under the nationally determined contribution (NDC) of sequestering additional 2.5 to 3 billion tons of CO2 equivalent through increased forest and tree cover by 2030, the Bonn Challenge commitment to restore 21 Mha of degraded and deforested land and targets under the Sustainable Development Goals. Results from the Atlas have enabled building a foundation for planning for landscape restoration in India. For instance, WRI India used results from the atlas for a policy brief submitted to India’s Fifteenth National Finance Commission to make a case for fiscal transfers in the forestry sector to support positive climate and social development goals. Additionally, civil society organizations are using the atlas for research on conservation and protection of forests and landscapes in India. The Ashoka Trust for Research in Ecology and the Environment (ATREE) is using data and analysis from the atlas to study climate friendly agrobiodiversity around tiger reserves and protected areas. The State forest departments in India are using the atlas to develop working plans (statutory requirements for managing forests in India) in accordance to the National Working Plan Code 2014 - the Himachal Pradesh state forest department is using analysis from the atlas to identify forest management activities and prepare a working plan for the Ani forest division. WRI India adapted and implemented the Restoration Opportunities Assessment Methodology (ROAM) for India, specifically Sidhi district of Madhya Pradesh. As part of the assessment, WRI India conducted the first Collect Earth based participatory mapathon that paired farmers and youth from the district with GIS experts to interpret and collect data from high-resolution satellite images. The assessment has catalyzed interest and commitment to landscape restoration in the district. The results from the assessment were shared at a ‘way forward’ workshop held in February 2018 with over 200 participants including officials from the state and district administration, state rural livelihoods mission, state bamboo mission, NABARD, private sector, media, farmer producer companies and local population. The workshop was chaired by the State Election Commissioner and there was unanimous support for landscape restoration. A high-level expert consultative group was set up at the state level to plan and guide implementation of Sidhi’s opportunity assessment. The findings were validated by the three technical working groups, as well as WRI’s science and research process. The final report is being designed and the executive summary was launched at the UNCCD COP in September 2019. Overall, the GEF5 project has supported in developing the foundation for scaling restoration in India, with innovative participatory tools, methods and approaches that have been developed that can be adapted to implement and scale restoration. A key focus of our influence strategy has been on engaging with multiple stakeholders on salience of landscape restoration and landscape approaches for achieving India’s climate and development goals. WRI India established three Technical Working Groups at the national level consisting of experts from over 40 environment and development organizations. Results from this work, and other associated WRI tools, have been presented at several multi-stakeholder consultations and one-to-one high-level meetings. Most recently, we showcased the tools and approaches developed as part of this GEF5 project at the UNCCD CoP14 as part of the technology fair. The restoration opportunities atlas and the Sidhi assessment were also discussed at the two side events that WRI India organized at the CoP, and the findings were well received and widely disseminated. WRI India is equipping decision-makers and restoration practitioners in planning landscape restoration at scale with multiple benefits through capacity building workshops. WRI India has secured additional funds and co-financing through Good Energies and the complementary institutional funding from WRI to strengthen its work and build a foundation for restoration at scale in India. Indonesia: In Indonesia, the project has helped accelerate the adoption and implementation of restoration by improving the capacity of the Ministry of Environment and Forestry on restoration in protected areas and peatlands. Several seminars and capacity building events were held, and a book on the success stories of restoration in conservation areas has been published and launched at the 2018 National Conservation Day commemoration The project team has also mainstreamed blue carbon into national development planning through development recommendations on mangrove restoration. |  |  |  |  |  |

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Global: The World Resources Institute and partners have completed all remaining outputs and activities for the project in this final reporting period. Globally relevant highlights of the project team’s progress include: - WRI continues to play a major role in convening restoration actors to increase the rate of FLR implementation on the ground and provide a platform for groups to connect with each other. WRI hosted the 3rd Annual AFR100 Partners meeting in Nairobi, Kenya in August which brought together more than 170 delegates from around the world, who represented Management Team Partners (NEPAD, WRI, IUCN, BMZ, GIZ, and WB), countries (28 member countries), financial partners, technical partners, NGOs and civil society groups. These events continue to provide a space for countries to announce FLR commitments, directly make requests to technical partners on required assistance, and call for global action. WRI also hosted the annual Initiative 20x20 annual meeting in Argentina, where member countries have now committed more than double the initial target (50 million ha.) - The Restoration Opportunity Assessment Methodology (ROAM) is being applied at the national and subnational levels in more than 25 countries, including and beyond the priority countries. ROAM includes opportunity mapping, spatial prioritization, economic analyses, and application of the Restoration Diagnostic, all measured by outcome indicators of this project. Applications of ROAM and the Restoration Diagnostic have led to significant policy changes in the priority countries and beyond. In Indonesia, the results led to South Sumatra’s Green Growth Plan and 400,000 hectares restoration target. - Establishment of baseline and monitoring systems is a significant priority for restoration countries moving from ambition to implementation. This grant has been critical in the continuing development of Collect Earth as an effective tool to monitor regrowth of trees inside and outside forests. Baselines have been established at the national level or in priority landscapes in Ethiopia, Kenya and India, and other countries beyond those of this grant. Train-the-trainer workshops were held in to build the capacity of stakeholders in-country. The application of the Forest Atlas platform for the use in restoration monitoring was made possible through this project, with 3 of the 5 target countries now hosting or developing a restoration atlas. Kenya: In Kenya, the first integrated water tower monitoring framework was developed and officially launched through a multi-stakeholder collaborative process which lead to full ownership by all stakeholders and Kenya Water Towers Agency (KWTA). This framework will serve as the roadmap for developing the national monitoring system and will detail the role each organization will play. KWTA with support from WRI, have started developing a pilot system that builds on the national monitoring framework and uses the WRI Forest Atlas platform to bring together local and global data sets to provide dynamic ways to display and analyze data on land use change. The proejct team also advanced its work with Makueni County, carrying out the first sub-national restoration diagnostic assessment and mobilizing a sub-national FLR multi stakeholder working group to collaboratively plan and coordinate FLR in the county. This work has set the stage for a sub-national restoration movement that is based in scientific data and is inclusive of multiple sectors and stakeholders. Makueni County’s Governor Kivutha Kibwana and his team clearly see the opportunities for FLR to help address major environmental and social challenges in the county. Their leadership, enthusiasm, and drive for inclusion have built a strong foundation for this sub-national movement to grow from. Ethiopia: All deliverables are now complete except for two that are in the final stages of the review process. In October 2018, the Ministry of Environment, Forest and Climate Change was changed into the Environment, Forest and Climate Change Commission (EFCCC), under the Prime Minister’s Office. While the Commission’s responsibilities are greater (they now also include wildlife conservation), the Commissioner does not have the rank of Minister. This change in status makes the project more indispensable in providing knowledge and tools to make the case for, implement and monitor restoration. The national potential maps, associated technical report, and data were successfully launched in the presence of 180 guests in October 2018. They are now available at http://eth.restorationatlas.org At woreda level, after a national validation workshop in December, both the Cost-Benefit Analysis (CBA) and the Restoration Diagnostic were finalized. The CBA discusses seven restoration transitions in both Sodo and Meket. The Restoration Diagnostic, which also includes a capacity assessment, identified two dozen (partially) missing enabling conditions in each woreda. Thanks to the project’s production of local land use-land cover and percent tree cover maps, tree-based landscape restoration potential maps were produced for both Sodo and Meket woredas. With a second Mapathon conducted for each of the woredas, 2015 data were collected with a revised version of Ethiopia’s survey to assess tree cover and distribution, which allowed for the assessment of change for 35 indicators over the first period of Ethiopia’s Growth and Transformation Plan (2010-2015), as well as informing adaptive implementation. The project has actively engaged in increasing financial flows towards restoration. Ethiopia’s Government dedicated about $15M of its star allocation to the GEF7 Food Systems, Land Use and Restoration Impact Program. The project has successfully supported EFCCC and its partners in submitting the Expression of Interest in January 2019 and the Concept Note in March 2020. The team is now supporting the PPG phase. This project will provide about $22.5M for integrated land use management and restoration across sectors. In addition to public financing, the project contributed and benefited from a business accelerator targeting restoration businesses and investors. The accelerator built on the scoping of Ethiopia-relevant restoration businesses and investors conducted earlier in the project. Finally, the project supported two local NGOs to crowdsource online for the first time ever. Niger: In Niger, the project implementation has contributed to: - Establishing a national restoration baseline – The project has supported a stocktaking exercise aimed at assessing the available information (quantitative and qualitative) regarding restoration efforts in Niger. The baseline information that was collected was organized in maps and table which were presented and validated during a ROAM Workshop, organized by TerrAfrica, in February 2018. The baseline was also used as a resource by the Ministry of Environment in the development of their national land management plan that was published in August 2018. Additionally, WRI collaborated with the Economics of Land Degradation Initiative (ELD), between June and December 2018, to develop capacity for socio-economic assessments in the Maradi region. The assessments began with case studies in the pastoral lands of the Maradi region, followed by a summary report highlighting baselines and key statistics. The research also included over a month of socio-economic data collection on the value added of restored lands on the land, biodiversity, people and revenues. A first complete draft of the economic assessment was developed by WRI in collaboration with a consultant in December 2018. - Supporting a national strategy and political momentum – WRI, in collaboration with the Forest Services of the Ministry of Environment has proposed an action plan to accelerate restoration efforts at a low cost and by including local communities. WRI’s recommendations were utilized by the Ministry of Environment while developing a national strategy on sustainable land management. Additionally, the project team supported the country’s political momentum by proposing FLR-themes for the National Tree Day – A day dedicated to a national awareness on tree related topics. WRI proposed themes were: Land Restoration in 2016; Landscape approach for sustainable management in 2017; and FMRN in 2018. The latter allowed more visibilities on the various aspects and opportunities of land restoration. Finally, WRI has also support the development of a national decree allowing farmers to have the right of their trees on their agricultural lands. The decree was a cross sectoral efforts to create the appropriate enabling condition for greater restoration efforts at the local level. - Coordination of partner across sectors – Through various workshop and training, WRI in collaboration with the Forest Services have created a Restoration Task Force in all 8 regions of the country. That allowed each region to be equipped with a group of experts and resources person to support local restoration efforts. The project team has also assisted in the Week of Restoration – a unique event that allowed key stakeholders from various sectors to discuss on ways for better collaboration and implementation of efforts on the ground. Through the project, Niger is now equipped with 1) a Restauration Task Force and 2) a Yearly event aimed at emphasizing the cross-sectoral approach to FLR. - Placing the communities in the driver’s seat – This GEF5 project has allowed the project team to position local communities ( including farmers and women leaders) in a what where they can 1) contribute to national discussion and decision making processes ( WRI support the presence of farmers/women groups at the AFR100, the Agroforestry forum and the week of restoration); 2) inspire their fellow community member to join the restoration movement ( during radio broadcasts and community discussions) and 3) by sharing with technical partner and research groups successful options for restoration at scale ( through exchange visits between villages and across institutions). - Advocating for more funds for FLR– In December 2018, WRI, in collaboration with the Chamber of Commerce and an incubator Center organized a business roundtable for a discussion around the involvement of the private sector in restauration efforts, providing the ~25 businesses/entrepreneurs that participated, with information about relevant ways they can contribute and play a role in the country’s restoration movement. The project team has also assisted the country in securing GEF7 funding by assisting them with technical and financial resources during the EOI and the PIF phases. - Support innovative information sharing – The project team, in collaboration with the Ministry of Environment and research centered has contributed to increasing awareness on 1) the restoration success stories in Niger; 2) the countries potential for FLR at scale and 3) the restoration champion such as Sakina Mati and Malam Ali showcasing that restoration can be done with success in the most challenging environments; using different avenues including national newsletters; AFR100 country profile; Blogs and other communication materials. India: In India, the first two years of the project focused on getting the evidence and tools ready and engaging with multiple stakeholders on landscape restoration as a strategy to meet various international commitments and domestic targets on restoration. In the final year, the team focused on disseminating the results from this work and rolling out an influence strategy that can enable planning for landscape restoration at scale. To support India to achieve its NDC and SDGs, WRI India developed the Restoration Opportunities Atlas which brings together fragmented data and rigorous analysis to create India’s first-of-its kind web-based platform. The Atlas shows that India has more than 140 million ha of opportunity for forest protection and landscape restoration. Realizing India’s forest protection and landscape restoration potential can sequester 3 to 4.3 billion tons of above-ground carbon by 2040, while also providing other critical ecosystem services such as biodiversity conservation, water recharge and provisioning of food, fuelwood, fodder and minor forest produce. The Atlas includes a layer on past and on-going restoration initiatives across India that captures over 300 examples of the country’s extensive and varied experience of initiatives for improving forest and tree cover. The Atlas presents information on key enabling conditions under three sections – threats; secure tenure and resource rights; and restoration finance. Our analysis shows that in the period 2011-2016, the Government of India allocated upwards of USD 13 billion to protecting and improving forests as well as extending tree cover. WRI India adapted the ROAM to suit the Indian context by focusing on the flow of multiple ecosystem services, livelihoods assessment for identifying benefits to local population, role of institutions and networks and integrating concerns around land tenure, governance, gender and social inclusion. The adapted ROAM was implemented in Sidhi through extensive consultation with local communities, field work, data collection and analysis. The Sidhi assessment identifies over 360,000 ha of land with potential for landscape restoration that can support biodiversity conservation, erosion control, carbon sequestration and improve provisioning of food, fuelwood, fodder and minor forest produce for local communities. Further, implementing landscape restoration can generate 3.75 million person days of employment and USD 9.8 million in wage income through nursery development. Establishing value chains around only six key native species, can generate 30,000 new jobs, particularly for women, youth and landless in the district. The assessment shows that landscape restoration can contribute not only to the NDC, Bonn Challenge and SDGs but also several domestic targets including National Mission for Green India, national agroforestry policy and doubling of farmer income by 2022. The social landscape guidebook was launched in September 2018. The guidebook takes a new approach to environmental governance by focusing on identifying the social capital of actors within the landscapes. It centers on two main approaches: 1) mapping actors’ resource flows and 2) mapping actors’ priorities and values. Co-written by WRI international offices, this methodology has been tested in Brazil, India, Indonesia, Kenya, Mexico, and Rwanda. By using this guidebook, environmental practitioners can be more efficient with resources, collaboration, and outreach, and better anticipate potential conflicts and bottlenecks. The findings from the guidebook which is a collaborative effort by WRI is being widely disseminated throughout India. As part of the influence strategy, WRI India shared findings from the Restoration Opportunities Atlas, adapted ROAM and Sidhi findings at various conferences, meetings and workshops including the; India Land and Development Conference 2017, 2018, 2019; Geospatial conference, 2018; conference on best practices for implementing forest landscape restoration in South Asia, 2018; World Bank’s Land and Poverty Conference 2019; Asia Pacific Forestry Week 2019; UNCCD CoP 14 and so on. The Sidhi’s findings have also been presented through one-on-one meetings with United Nations Development Programme, Food and Agriculture Organization (FAO), National Bank for Agriculture and Rural Development (NABARD) and in the state of Madhya Pradesh to provide inputs into the planning process. Indonesia: In Indonesia, the project team improved the capacity of the Ministry of Environment and Forestry on restoration in protected areas through knowledge sharing and collaboration with major national CSOs. A major capacity building activity held was a 10-day conservation traveling seminar in November 2018, attended by middle-to-senior level staff members of the Ministry of Environment and Forestry. The traveling seminar was co-organized by WRI Indonesia with major CSOs such as WWF, TNC, CI, WCS, Wetlands International, etc. to improve the leadership skills of the attendees and expose them to the latest science and development in many conservation issues. A significant portion of the traveling seminar was dedicated toward discussing restoration in protected areas. As part of the seminar, attendees visited a mangrove nature reserve in West Java, a restoration site in a national park in Sumatra, and a social forestry site at the border of a national park. These sites are also where many of the CSOs are co-organizing work to support the Ministry of Environment and Forestry. The project also developed a suite of recommendations on mangrove restoration for the Indonesia Blue Carbon Strategy Framework which will be a reference for mainstreaming blue carbon into country’s development planning. A capacity building event and a national workshop on community-based mangrove restoration were held in October 2018. The workshop produced a suite of recommendation for the Indonesia Blue Carbon Strategy Framework. The workshop, attended by more than 50 mangrove experts and practitioners, focused on identifying key success factors and innovative financing options to achieve effective community-based mangrove restoration. The results of this workshop were presented at the blue carbon side event at the 2018 Our Ocean Conference. |  |  |  |  |  |

| Risk Rating | FY 2017 | FY 2018 | FY 2019 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | L | L | L |  |  |
| The project team has now completed all planned activities for this project and has not experienced any of the risks laid during CEO endorsement. The proejct team acknowledges that there are some risks of sustainability and continuity after the completion of this project due to climate and political factors, but we feel confident that through the implementation of this proejct, we have positioned the target countries such that these impacts have been minimized or that local actors feel they have the tools needed to address them. The project team has assigned a rating of “Low” for this reporting period. |  |  |  |  |  |

| Stakeholder engagement | Throughout the life of this project, the proejct teams in each country have organized and supported many stakeholder engagement forums to ensure that all activities are informed by multiple points of view and circumstances. While the project team tried its best to ensure all impacted stakeholder groups were represented during these workshops and meetings, in some cases, the team was limited by local partner constraints or logistics. The project was very successful in bringing together groups of stakeholders who do not typically coordinate or work together. The emphasis on multi-stakeholder, multi-sector collaboration carried through to all opportunities for engagement. |
| --- | --- |

| Gender mainstreaming | While gender mainstreaming is widely accepted within the target countries, entrenched gender biases continue to be an issue and will take time before full gender integration can be achieved. While some instances were outside of the project team’s control, where possible, the proejct team ensured that participation in workshops, technical working groups, and policy working groups had significant gender inclusion. With a number of women now in high-level roles in government positions in a few of the target countries, the project team expects that gender mainstreaming will continue to improve in the future. |
| --- | --- |

| Knowledge activities and products | A number of knowledge products were published during this reporting period, and a few more will be published before the end of the year. These include: - Mapping Social Landscapes – a guide for identifying key actors who influence landscape restoration within a given geographical context and mapping how these actors interact with one another to both positively and negatively affect FLR. - WRI-FAO Guide to Identifying Priorities and Indicators for Monitoring FLR – Building on the initial WRI-FAO monitoring framework that was tested and applied in Kenya as well as other non-project countries, the guide provides step-by-step instructions for stakeholders to follow in order to develop well-rounded, locally appropriate monitoring systems. The guide will be published in October 2019. - Application of Collect Earth for FLR User Guide – A forth-coming guide based in part on the application of Collect Earth through this proejct for the use of monitoring restoration progress. The guide will provide detailed instructions on all steps of Collect Earth, including survey development, running a mapathon, and analyzing the results. The guide is tentatively set to be published by the end of 2019. - The Adapted ROAM process to suit the Indian context – The adapted ROAM focuses on the flow of multiple ecosystem services, livelihoods assessment for identifying benefits to local population, the role of institutions and networks and integrating concerns around land tenure, governance, gender and social inclusion. The adapted ROAM was implemented through this project in Sidhi through extensive consultation with local communities, field work, data collection and analysis. This adapted ROAM can now be applied to other landscapes within India and produce more locally-relevant results. - The India Restoration Opportunities Atlas – This atlas supports decision-makers to develop national and state-level pathways for achieving India’s forestry target under the nationally determined contribution (NDC). Results from the Atlas have enabled building a foundation for planning for landscape restoration in India. - The Ethiopian Restoration Opportunities Atlas – This atlas hosts the national restoration potential maps, the associated technical report, and links to datasets. This is the first atlas of its kind in Ethiopia and will serve as a central point of contact for landscape restoration planning in the country. |
| --- | --- |

| Stories to be shared | The project final report will compile the project’s stories, blogs and media content |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Compelling analyses for improved decision making to support restoration is developed for each of the focus countries, including the number of hectares and expected benefits | # of compelling analysis presentations to decision-makers including the different roles that gender plays in restoration activities | 0 | Decision makers cited ROAM data, findings or recommendations at least once in each country | Decision makers cited ROAM data, findings or recommendations at least twice in each country | Kenya, Ethiopia, India, and Indonesia have produced landscape restoration atlases. India and Niger have produced landscape baseline assessments and/or stocktaking that aid decision making. Kenya’s Makueni County has used ROAM data in their county-level ROAM assessment and action plan. ROAM Data was also used by the national restoration working group in the development of a national FLR action plan. | HS |
| Outcome 2: Restoration commitments drafted and announced in target countries contributing to the Bonn Challenge goal of 150 million hectares in the process of being restored by 2020 | Area of hectares of restoration committed to international platforms on restoration goal by each country | Ethiopia: 15M ha Kenya: committed without ha target Niger: 120,000 ha annually India: 0 M ha Indonesia: 0 M ha | Ethiopia: 15M ha Kenya: committed without ha target Niger: 120,000 ha annually India: 0 M ha Indonesia: 0 M ha | Ethiopia: 15M ha Kenya: 10M ha Niger: 3.2M ha India: 13 M ha Indonesia: 10 M ha | Ethiopia: 15M ha Kenya: 5.1 M ha Niger: 3.2 M ha India: 21 M ha Indonesia: 0.3 M ha While Ethiopia and Niger made commitments that are in line with the end of project target, and India surpassed this amount, Kenya and Indonesia ended up making final commitments that were lower than expected at the beginning of the project. However, the actual number of hectares committed totaled 44.6 million ha, while the target total number of hectares was 51.2 million. | S |
| Outcome 3: High-level political commitment and cross-sectoral support for implementation of forest and landscape restoration actions in the target countries and emerging globally | # of decisions that reflect the needs and priorities of populations affected by forest landscape restoration proposed by the working group that are adopted by target country governments *adopted means that a relevant government official or agency with decision making authority has officially codified or enacted decisions in their national legal, regulatory, or policy system. | There is interest from key stakeholders to adopt enabling conditions. See baseline narrative for more details. | There is interest from key stakeholders to adopt enabling conditions. See baseline narrative for more details. | Decision that reflects the needs and priorities of populations affected by forest landscape restoration, is proposed by the Working Group in each country, and is adopted by target country governments | Working groups have been created and are actively working to make decisions on forest and landscape restoration implementation in all five focus countries. In Kenya, the working group is drafting a National FLR Action Plan that will detail where, how, and with who FLR should be carried out to achieve Kenya’s restoration target and achieve its related outcomes. In Niger, WRI supported the government in the concretization of amendments of the forest law to ensure farmers’ rights on trees on their farms and agroforestry parks. An implementation decree, 2000-040 of June 8th, 2004 was adopted in March 2018 with focus on restoration and farmland management. The decree supports FMNR in its practice but fails to provide relevant details on farmers’ rights. WRI assisted further work to implement a new decree that supports FMNR and considers the rights of farmers In Ethiopia, discussions were started on establishing an inter-ministerial platform on restoration but changes in government have slowed down progress. | S |
| Outcome 4: Tools developed, tested and applied at scale to support forest landscape restoration planning and implementation. Countries and institutions have easy access to these tools. Decision makers empowered | # of institutions systematically using ROAM findings, strategies and recommendations as part of their forest landscape restoration planning or implementation | 0 | Curriculum developed for trainings in each country. | At least 10 executing partner agencies used ROAM findings to develop final plans | India has completed restoration opportunity mapping at the national level and at the landscape level in Sidhi district. Indonesia has completed ROAM analyses for the two priority landscapes, with results disseminated to the public. Indonesia also launched an alpha version of a restoration stocktaking platform that compiles restoration activities conducted by non-state entities, and this platform has now been included in a platform dedicated to peat restoration (see http://www.pantaugambut.id), as well as a ROAM video in Bahasa Indonesia. Kenya has carried out ROAM at the national level through a technical FLR working group comprised of more than 12 different institutions. ROAM has also been carried out at the county level in Makueni County with key stakeholders. WRI, with FAO, will soon be launching a global guide to developing a monitoring framework which will guide users to identify the indicators to monitor based on their specific goals of restoration activities. | HS |
| Outcome 5: Increased capacity of key actors and institutions to assess the potential for and implement forest and landscape restoration actions at scale | % of participants increase their knowledge as a result of tailored training curriculum. Disaggregated by gender | 0 | Curriculum developed for trainings in each country | 80% of participants increase their knowledge as a result of training curriculum | Workshops in all the priority countries have continued to provide the forum for training and increased capacity of actors and organizations to implement forest and landscape restoration actions. In Indonesia an alpha version of a restoration stocktaking platform was launched that compiles restoration activities conducted by non-state entities, and this platform has now been included in a platform dedicated to peat restoration (see http://www.pantaugambut.id), as well as a ROAM video in Bahasa Indonesia. These tools have allowed for a much broader uptake of restoration planning tools. In India, the project team adapted the ROAM to suit the Indian context by focusing on the flow of multiple ecosystem services, livelihoods assessment for identifying benefits to local population, role of institutions and networks and integrating concerns around land tenure, governance, gender and social inclusion. | S |
| Outcome 6: Financial flows to accelerate the pace of forest and landscape restoration actions at scale identified in each country | Amount of $ committed to forest landscape restoration benefiting 5 targeted countries unlocked by WRI engagement | Various sources of funding for restoration exist but there's lack of strategy to implement restoration throughout landscapes | Emerging commitments unlocked by WRI engagement | $10 million pledged. | Globally, more than $3 billion have been earmarked by impact investors for restoration activities, with $481 M of that committed under AFR100 and $2.6 billion committed under Initiative 20x20 for restoration projects in Africa and Latin America, respectively. Additionally, WRI has been working with multiple philanthropic funding organizations, helping match projects with funding opportunities. To date nearly $2 M have been matched to projects with activities already taking place on the ground. WRI, in partnership with Fledge, has hosted the world’s first land use-focused business accelerator program in November 2018, and a the second in September 2019. The accelerators brought together 26 African restoration entrepreneurs to develop important business planning and entrepreneurial skills, culminating in a demo day where the businesses made pitches to private investors. in India, the National Bank for Agriculture and Rural Development (NABARD) - the apex development bank in India, is part of the project team's expert consultative group for implementing landscape restoration in Sidhi. The group will be activated once the team can secure funds for implementing Sidhi's opportunity assessment. | HS |
| Outcome 7: Restoration monitoring system designed to provide transparency in the verification and reporting on forest landscape restoration progress globally | # of best practice methods used to scale up restoration monitoring nationally | No restoration monitoring and evaluation framework in any country | WRI-developed method completed in 3 countries | 5 restoration monitoring methods adopted and in the process of national scale up in 5 target countries | In Ethiopia, change assessments were conducted in 2 landscapes, looking at the years 2010 and 2015. These entailed 4 individual mapathon exercises, the results of which are now being published in an official government report. Baseline assessments have been carried out in 2 landscapes in India and 1 landscape in Kenya. Additionally, in Kenya, the Kenya Water Towers Agency adopted the WRI-FAO monitoring framework and used it to develop a national monitoring framework for the water towers. The framework has been officially accepted and a digital platform is now being developed to support long-term monitoring efforts. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| Satisfactory (S) | Satisfactory (S) | The project has completed all planned activities and delivered all of its targets, many of which beyond expectation. Therefore, the overall progress toward meeting the intended results is verging onto highly satisfactory (3 out of 7 outcomes). |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | N/A |  |
| on stakeholder engagement | N/A |  |
| on gender actions | While gender mainstreaming is widely accepted within the target countries, entrenched gender biases continue to be an issue and will take time before full gender integration can achieved. | While some instances were outside of the project team’s control, where possible, the proejct team ensured that participation in workshops, technical working groups, and policy working groups had significant gender inclusion. |
| on safeguards | N/A |  |
| on delivering GEF Core Indicators | N/A |  |
| on delivering of PoW EA | N/A |  |
| on sustainability of results | N/A |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected completion date | Implementation status as of 30 June 2018 (%) | Implementation status as of 30 June 2019 (%) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: Restoration Opportunity Mapping that quantifies the area of opportunity in each country, based on the best local knowledge and science develop, tested and applied in the Output 1: Output 1: Restoration Opportunity Mapping that quantifies the area of opportunity in each country, based on the best local knowledge and science develop, tested and applied in the candidate countries. |  |  |  |  | S S S S S S S S S S S S S |
| Global: | December 2018 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Kenya: Activity 1 Develop National restoration priority map Activity 2 Develop restoration potential for priority landscape Activity 3 Stocktaking and document success Activity 4 Establish restoration website | September 2016 October 2018 October 2018 September 2016 | 100% 90% 90% 100% | 100% 100% 100% 100% | Complete. See previous PIR for full details. Complete: First draft restoration maps for Bungoma and Trans-Nzoia Counties were completed in 2017 and shared with stakeholders. Restoration opportunity and prioritization mapping done in Makueni County with input from local stakeholders and government officials. These maps have been shared with the County Government to inform the sub-national restoration commitment towards the national target as well as restoration implementation on the ground. These maps and data were also shared with the County climate change board that manages the county climate change fund to guide climate change resilience and mitigation efforts. Complete: Several stakeholder consultation meetings were carried out in the Bungoma and Trans-Nzoia counties to document successful restoration strategies, identify causes, pinpoint locations of degradation, and propose action items for national and sub-national institutions. Additionally, as part of the national process to develop a landscape restoration roadmap, a detailed national stocktaking exercise was conducted, which looks at successful interventions around the country, focusing on the three major land uses: forests, cropland, and rangeland/grazing lands. This report has been shared with the Government and is currently being used to inform the national strategy. Complete. See previous PIR for full details. |  |
| Ethiopia: Activity 1 Assess land degradation for priority landscapes Activity 2 Stocktaking and document success Activity 3 Establish land use plan for priority landscape | December 2018 September 2018 December 2018 | 50% 90% 75% | 100% 100% 95% | Completed. The project team requested, through EFCCC, access to the EthioSIS data for Sodo and Meket Woredas to the Agricultural Transformation Agency (ATA) but ATA’s web portal is being built, preventing the Agency to share any data in a timely fashion for them to be included in the analysis. Low percent tree cover was used as a proxy. The percent tree cover map was produced based on a cloud-based classification in Google Earth Engine, based on data collected in Collect Earth for 2016-2017. Completed. The stock-take of restoration activities in Sodo and Meket Woredas was conducted as part of the Restoration Diagnostic. The land use and percent tree cover maps produced through cloud-based classification in Google Earth Engine were finalized for both Meket and Sodo. These maps served as the basis for the mapping of 5 tree-based landscape restoration interventions in Sodo (establishment of secondary forests, agri-silviculture, woodlots/plantations, enrichment planting in shrubland, bamboo) and 6 in Meket (establishment of secondary forests, agroforestry, woodlots/plantations, frankincense, shrubland enrichment, buffer to waterbody). A technical report for each Woreda was written to ensure that the local experts understand what has been done and how to replicate it. This report also includes a section presenting the results from running InVEST to assess the minimum area and best location of secondary forests in Sodo and Meket to control waterbody sedimentation. The reports are in the final stages of the review process. |  |
| Indonesia: Activity 1 Stocktaking and document success Activity 2 Establish land use plan for priority landscape Activity 3 Establish restoration website | September 2017 September 2017 September 2017 | 100% 100% 100% | 100% 100% 100% | Complete. ROAM analyses have been completed for two priority landscapes (Musi in South Sumatra Province and Batanghari in Jambi Province). WRI Indonesia also supported the Peat Restoration Agency to produce an indicative map for peat restoration and in the process of assisting the Agency with land use planning for certain peat landscapes. WRI Indonesia launched an alpha version of a restoration stocktaking platform that compiles restoration activities conducted by non-state entities, and this platform has now been included in a platform dedicated to peat restoration (see http://www.pantaugambut.id). WRI Indonesia was involved in a publication entitled “Forest Ecosystem Recovery in Indonesia” by Indufor that reviews restoration policy in Indonesia. Together with the Ministry of Environment and Forestry, WRI Indonesia also produced a book documenting success stories from restoration in protected/conservation areas. |  |
| Niger: Activity 1 Develop regional restoration priority map | December 2017 | 100% | 100% | Complete. A team of field experts from the Forestry Department (Direction des Eaux et Forets), conducted two field visits in the country in August-September 2018. The first visit aimed at collecting georeferenced information from all the projects across the nation that had a restoration or sustainable land management component. A table of all the projects was created and completed with information gathered with the Ministry of planning. The table revealed that although there were over 20 large projects on restoration, very few of them had georeferenced data that we could use. The second field visit focused on the area with the most data, partners and technical support: the Maradi region. The team focused on collecting GPS coordinates and shapefiles of existing successfully restored farmlands. That data was used to create a comprehensive map showing restored land (using FMNR) in Maradi. The maps and table produced by the experts were presented and validated during a National Workshop, organized by TerrAfrica, in February 2018. They were also used as a resource by the Ministry of Environment in the development of their national land management plan that was published in August 2018. |  |
| India: Activity 1 Develop National restoration priority map | September 2017 | 100% | 100% | Complete. The national map of restoration opportunities has been developed and reviewed by an expert technical working group on mapping and monitoring at the national level. It is estimated that 150 million ha of forest and agricultural lands offer opportunities for wide scale restoration (49 million ha) and mosaic restoration (101 million ha) in India. The map and findings have been widely shared with government agencies, private sector organizations, funders, NABARD and civil society organizations. The maps have been disseminated widely through the Restoration Opportunities Atlas for India (https://india.restorationatlas.org/) that was launched in September 2018 at a roundtable dialogue. A technical note detailing the methodology underpinning the development of different spatial layers on the Restoration Opportunities Atlas was published in September 2018. The atlas has state level statistics available through state level reports. A podcast on the atlas is available here. The map of restoration opportunities and the priority interventions for Sidhi is complete. It was validated by community representatives in Sidhi and has been widely shared with different central ministries, state departments, NABARD and civil society organizations. The final map of restoration opportunities in Sidhi shows more than 350,000 ha of land has potential for landscape restoration. |  |
| Output 2: Quantification of potential net economic benefits in the countries developed by analyzing the economic costs and benefits of the relevant restoration interventions in each country. |  |  |  |  | S S S S S S S S |
| Global: | N/A | N/A | N/A | N/A: output applies at the country level only. |  |
| Kenya: Activity 5 Assess cost and benefits at national level and build business case | October 2018 | 75% | 100% | Completed: WRI's New Restoration Economy (NRE) project published two reports (Roots of Prosperity, and The Business of Planting Trees) in late 2017 and early 2018 respectively. The first takes an in-depth analysis of the global economic potential for landscape restoration, and the other profiles successful restoration enterprises, including some from Kenya, like F3 Life and Komaza. In addition to this, as part of a study that will inform the development of the national landscape restoration roadmap, detailed cost and benefit analyses was conducted in partnership with IUCN for the major restoration intervention types used across Kenya (as identified in the ROAM analysis). In addition, WRI mobilized additional support from our partner organization (CIFOR) to carry out gender analysis for restoration |  |
| Ethiopia: Activity 4 Build business case for landscape restoration in priority landscapes based on costs and benefits to individuals and society. | September 2018 | 90% | 100% | Completed. After a national validation workshop (see Internal Report and PPT), the cost-benefit analysis (CBA), conducted for seven restoration transitions in both Sodo and Meket, was finalized. The CBA is being summarized to be published as a fact sheet. This is part of a co-funded project with IUCN and will be published after the end of this GEF project. |  |
| Indonesia: Activity 4 Quantify carbon benefits Activity 5 Develop briefs on use of restoration for mitigating carbon emissions Activity 6 Develop cost and benefits analysis for restoration planning | January 2018 January 2018 January 2018 | 100% 100% 100% | 100% 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Niger: Activity 2 Stocktaking and document success | December 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| India: Activity 2 Identify and document a sample of past and ongoing experiences of restoration through governmental programmes in different sectors, private sector and civil society initiatives. Activity 3 Assess cost and benefits in priority landscape and build business case | December 2018 December 2018 | 70% 100% | 100% 100% | Complete. A database of past and on-going restoration interventions in India has been developed. The database captures information such as geographic location, model of restoration intervention (natural regeneration, plantation, agroforestry system), key actors involved, funding agency, benefits accrued (both regulatory and provisioning services) and associated business models. A report based on the framework for stocktaking to document learning from past experiences of restoration in India has been developed. The framework aids in identifying key factors that can enable scaling site level interventions through select case studies. Complete. See previous PIR for full details. |  |
| Output 3: Pledged contributions drafted to the Bonn Challenge (hectares) |  |  |  |  | S S S S S S S S S |
| Global: | December 2018 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Kenya: Activity 6 Quantify the area that can be committed to restoration | September 2016 | 100% | 100% | Complete. See previous PIR for full details. After consultations with Makueni County government officials, it was decided that action plans at the sub-county level would be the most valuable for scaling up restoration implementation on the ground, and so 3 sub-counties were selected. These action plans were completed in early 2019 |  |
| Ethiopia: Activity 5 Inform national strategy and road map for achieving 15 million ha with landscape restoration work at national and priority landscape levels | September 2018 | 98% | 100% | Completed. The maps, technical report, and data were launched on 08 October 2018, along with the National Forest Sector Development Program. All are available at http://eth.restoration-atlas.org. The maps were presented to an audience of 180 people, including the Minister of Environment, Forest and Climate Change, the Ambassadors of Norway and Sweden, and the Head of UNDP country office. A leaflet was distributed and a blog published on AFR100 website. |  |
| Indonesia: Activity 7 Translate existing national strategy in executable activities in watersheds Activity 8 Organize workshop with conservation concessions | March 2017 March 2017 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Niger: Activity 3 Develop strategy to scale up farmer managed Natural Regeneration (FMNR) Activity 4 Develop strategy and road map to achieve national pledge | June 2018 August 2018 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| India: Activity 4 Translate national commitments into area that can be committed to restoration Activity 5 Identify specific interventions that support restoration policies | September 2017 September 2017 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Output 4: Presidential decrees, parliamentary actions and/or inter-ministerial working groups drafted and structured in support of forest landscape restoration |  |  |  |  | S S S S S S S S S |
| Global: | December 2018 | 75% | 100% | Complete. The GLF hosted an Africa-specific forum in Nairobi in August, just after the 3rd Annual Partners meeting of AFR100. The partners meeting brought together more than 170 delegates from around the world, who represented Management Team Partners (NEPAD, WRI, IUCN, BMZ, GIZ, and WB), countries, financial partners, technical partners, NGOs and civil society groups. The Government of Burkina Faso announced that it would sign onto AFR100, committing 5 million ha and bringing the initiative to 27 partner countries. Overall, country representatives emphasized the importance of moving beyond pledges to focus on implementation. Specifically, they highlighted the need to: spotlight successes and replicate what’s working; engage communities; access finance, Monitor FLR progress and impacts. Meeting participants also endorsed the motion to have the United Nations General Assembly (UNGA) declare a “Decade of Action on Ecosystem Restoration,” first proposed in March by El Salvador’s Ministry of Environment. This motion has since been approved by the UNGA in March. |  |
| Kenya: Activity 7 Establish national steering/technical working committee Activity 8 Establish District Steering committee Activity 9 Establish technical district working group | June 2016 February 2018 February 2018 | 100% 100% 100% | 100% 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Ethiopia: Activity 6 Organize multi-sector technical Working Group to coordinate the implementation of landscape restoration activities in priority landscapes | Continuous, but first engagement was in February 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Indonesia: Activity 9 Prepare policy briefs on restoration and support outreach Activity 10 Establish District Steering committee/Technical working group on watershed level | October 2018 October 2018 | 90% 90% | 100% 100% | Complete. WRI Indonesia’s work at the subnational level has been conducted in close coordination with the watershed management forum in each of the watersheds. Some popular publications in the form of booklets, maps, and op-eds have been produced and disseminated. In terms of outreach, WRI Indonesia has also produced various blog posts/op-eds, brochures, and a ROAM video in Bahasa Indonesia. In late 2018, WRI Indonesia also published a booklet containing key takeaways and recommendations from a national mangrove restoration workshop that it organized. |  |
| Niger: Activity 5 Seek approval of forest law that supports FMNR Activity 6 Establish national steering/technical working committee | November 2018 | 80% 100% | 100% 100% | Complete. After the National Workshop in March 2017, and the validation of the study on the legislative status of ANR in Niger, WRI continued supporting Niger in the concretization of amendments of the forest law to ensure farmers’ rights on trees on their farms and agroforestry parks. An implementation decree, 2000-040 of June 8th, 2004 was adopted in March 2018 with focus on restoration and farmland management. The decree supports FMNR in its practice but fails to provide relevant details on farmers’ rights. WRI assisted further work to implement a new decree that supports FMNR and considers the rights of farmers. For that, two Niger-based consultants were hired, in October 2018, to support the Department of Forestry in the drafting and adoption of a decree on agroforestry parkland management. Two documents were produced by the consultants: a draft decree proposing new rules and procedures supporting more rights for farmers; and a summary document of all supporting legal references coupled with a letter explaining the methodology that was used in the development of the proposed decree. These two documents were presented and vividly discussed during a national agroforestry forum in December 2018. The forum, organized in the Dosso region, welcomed over 50 key intuitions in land restauration and management- including farmers unions and traditional chiefs. The proposed decree was edited after the forum to incorporate participants’ comments and suggestions. The Department of Forestry in now finalizing the proposed decree and plan to submit it to the Prime Minister’s office for their internal review and official adoption. Complete. See previous PIR for full details. |  |
| India: Activity 6 Provide input into the national action planning process in the context of the INDCs, to highlight the opportunity for restoration as a strategy for climate change mitigation and adaptation. | December 2017. | 100% | 100% | Complete. See previous PIR for full details. |  |
| Output 5: Rapid Restoration Diagnostic applied to assess the enabling conditions for restoration in each country, including custodial rights of local people, gender equity, poverty-forests linkages, and application of FPIC and social and environmental safeguards systems. Result is a detailed report to identify the gaps in the enabling conditions as well as strategic recommendations to address these gaps. |  |  |  |  | S S S S S S S S S |
| Global: | N/A | N/A | N/A | N/A: output applies at the country level only. |  |
| Kenya: Activity 10 Conduct the restoration diagnostic at national scale Activity 11 Conduct the restoration diagnostic at priority landscape scale | March 2016 October 2018 | 100% 25% | 100% 100% | Complete. See previous PIR for full details. Complete: County level restoration diagnostic exercises was conducted with the Makueni County restoration technical working group and other county level stakeholders. The findings are currently being used to inform FLR programs in Makueni County by the County Government and Partners. |  |
| Ethiopia: Activity 7 Conduct the Restoration Diagnostic to review economic, social and political contexts in priority landscapes | September 2018 | 90% | 100% | Complete. After a national validation workshop (see Internal Report and PPT), the Restoration Diagnostic report, which identified two dozen (partially) missing enabling conditions in each woreda, was finalized. The report is being designed to be published. |  |
| Indonesia: Activity 11 Conduct the restoration diagnostic at national scale Activity 12 Conduct the restoration diagnostic at priority landscape scale | September 2018 September 2018 | 90% 90% | 100% 100% | Restoration diagnostics at priority landscape scale and at site level have been conducted in South Sumatra and Jambi. The results are included in the various booklets that have been produced. A mobile-based app that helped the restoration diagnostic analysis at the priority landscapes was also developed by WRI Indonesia’s partner, ICRAF. The analysis at the national scale is being conducted as part of a book chapter currently being co-written by WRI Indonesia’s FLR Manager with researchers from CIFOR and Tropenbos. WRI has contributed to the book chapter. While the book is still being finalized. |  |
| Niger: Activity 7 Planning of Restoration activities Activity 8 Training workshops on scaling strategies | March 2018 March 2017 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. Training on FMNR is underway by partners and steps are being taken to improve coordination of partners supporting the widespread adoption of ANR. Communication materials and radio interventions are planned for March 2018, to shine the light on existing success and allow farmers to share their experiences. A ROAM training week is being organized in February 2018, to introduce the methodologies and identify scaling strategies. A training on how to develop pitch decks were organized during a business roundtable aimed at encouraging the private sector’s involvement in scaling land restauration in Niger in late 2018. |  |
| India: Activity 7 Conduct the restoration diagnostic at priority landscape scale Activity 8 Support the application/testing of WRI's tools and assets related to restoration (ROAM), forest governance (GFI Indicator framework) and the Global Forest Watch to identify their potential for scaling up restoration. | December 2017 December 2017 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Output 6: Strategies in Forests, Environment, Agriculture and/or Finance adopted to address the gaps identified by the Rapid Restoration Diagnostic |  |  |  |  | S S S S S S S S |
| Global: | N/A | N/A | N/A | N/A: output applies at the country level only. |  |
| Kenya: Activity 12 Recommendations on governance improvements for restoration Activity 13 Develop strategy paper on restoration governance at county level Activity 14 Develop restoration master plan for district level | December 2018 September 2018 September 2018 | 60% 60% 75% | 100% 100% 100% | The restoration diagnostic was conducted at the national-level to identify key barriers to restoration, including governance aspects. The national landscape restoration technical working group also conducted a national policy analysis, assessing all the laws that deal with natural resource management and their applicability to landscape restoration. Findings and recommended next steps have been presented in a draft document to the Government of Kenya for incorporation in the National Restoration action plan. The results from the above assessments are now being included in the national restoration roadmap/action plan. This document will be cross-sectoral, including sections specific to forests, rangelands, and croplands, and will also include sections on cost benefit analysis, gender impacts of restoration interventions, and stocktaking of successful restoration strategies across the country. The national working group has established sectoral task forces (forest, cropland, rangeland) that are each developing guidance on how to conduct restoration in these areas. A landscape governance framework strategy paper at county level was done with Makueni county restoration working group and the county restoration stakeholders. Final document has been shared with the County Government to guide the integration of FLR in the well-established County-level public participation. Makueni County developed a restoration roadmap that will guide where and how restoration should be implemented with a focus on Nzaui landscape. WRI worked with the Makueni restoration working group and stakeholders to develop key components of the master plan (mapping efforts and stocktaking). |  |
| Ethiopia: Activity 8 Plan how to address policy and legal gaps identified by Rapid Restoration Diagnostic to achieve landscape restoration targets in priority landscapes | December 2018 | 90% | 100% | Complete. How to address the gaps identified in the Restoration Diagnostic are included in the Recommendations of the report (see Activity 7). |  |
| Indonesia: Activity 13 Develop a paper with recommendations on governance improvements for restoration Activity 14 Develop a paper for restoration master plan for district level/watershed | October 2018 October 2018 | 85% 100% | 100% 100% | The analysis at the national scale has been conducted as part of a book chapter co-written by WRI Indonesia’s FLR Manager with researchers from CIFOR and Tropenbos. The paper/book chapter includes recommendations from the well-documented workshops and focus group discussions that WRI Indonesia organized. In South Sumatra, restoration strategies for the whole Musi Watershed have been included in the Province’s Green Growth Plan document and have been mainstreamed into a Provincial Regulations. Booklets on restoration plans in several forest management units have also been completed. We have also produced a booklet containing recommendations to accelerate mangrove restoration in Indonesia. |  |
| Niger: Activity 9 Reinforce rules and community practices on FMNR Activity 10 Support involvement of FMNR farmer champions in national strategy | May 2018 December 2018 | 100% 100% | 100% 100% | Complete. On 1 May 2018, WRI in collaboration with the Department of Forestry organized a radio broadcast which featured two restoration champions, Sakina Mati and Ali Malam, who shared their experiences with FMNR and encouraged neighboring communities to adopt FMNR practices. On 2 May 2018, during the Week of Restoration, WRI led a session on the role of farmers in scaling up restoration strategies. The case of Dan Saga, a village in the Maradi region was presented. The Dan Saga community successfully implemented village bylaws to protect their trees and ensure sustainable management of common farmlands. This model was discussed, and participants suggested the promotion of model village bylaws for managing trees as well as grazing lands. After the discussion, WRI presented a summary of the discussion to the Department of Forestry and recommended in a one-pager the creation of model village bylaws by the Ministry of Environment, which can then be adapted by each village to its specific conditions. The bylaws used by the village of Dan Saga could be used as a template and source of inspiration. The objective will be to accelerate the rate of restoration while promoting a set of proven techniques, and while creating or strengthening village institutions which can manage re-capitalized resources. WRI published a blog post on this success story in August 2018. On December 21st, 2018, a second radio broadcast was organized by the Department of Forestry in collaboration with WRI, in the Tillabery region, with two farmers, Kimba and Ide. The later have successfully supported their community in restoring degraded plateau using land retention techniques ( Banquettes). Both radio events were recorded and are frequently being replayed across the nation’s radio stations. Complete. For this output, WRI began by first identifying groups of FMNR champions across the country. The Department of Forestry, with WRI support, identified ANR and landscape restauration as themes for the National Tree Day (August 3rd) for FY 2017 and 2018; on those day, a contest among farmer took place to select the restauration champion for 2017. Ali Neimo from the Dan Saga region was selected as the 2018 National Restauration Champion. As a result, Ali was invited in March, September and December 2018, to attend national forums and workshops on land restauration and agroforestry parkland management. During those events, Ali represented the farmers and played an important role in developing strategies and activities that benefits farmers and local communities. |  |
| India: Activity 9 Dissemination of findings from the RRD along with recommendations for strategies in forest, environment, agriculture and/or finance to leverage strengths and address gaps. | December 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Output 7: Policy-makers, thought-leaders and/or journalists participating in exchanges and training programs, with representation from across the forest, REDD+, climate smart agriculture sectors. |  |  |  |  | S S S S S S S |
| Global: | December 2018 | 100% | 100% | Complete. The GLF hosted an Africa-specific forum in Nairobi in August, just after the 3rd Annual Partners meeting of AFR100. The partners meeting brought together more than 170 delegates from around the world, who represented Management Team Partners (NEPAD, WRI, IUCN, BMZ, GIZ, and WB), countries, financial partners, technical partners, NGOs and civil society groups. The Government of Burkina Faso announced that it would sign onto AFR100, committing 5 million ha and bringing the initiative to 27 partner countries. Overall, country representatives emphasized the importance of moving beyond pledges to focus on implementation. Specifically, they highlighted the need to: spotlight successes and replicate what’s working; engage communities; access finance, Monitor FLR progress and impacts. Meeting participants also endorsed the motion to have the United Nations General Assembly (UNGA) declare a “Decade of Ecosystem Restoration,” first proposed in March by El Salvador’s Ministry of Environment. This motion has since been approved by the UNGA in March. In May, WRI participated in the first AFR100 Technical Partners meeting in Ghana. The main takeaway from the meeting was that the technical partners needed to be coordinating with each other more effectively and sharing lessons among themselves. It was acknowledged that the initiative needed to better match the needs from countries with the capacities and expertise among the technical partners. WRI also hosted the first Global Forest Watch user summit in Washington, DC in June 2019. Nearly 400 people attended, traveling from over 30 countries like Peru, Colombia, Mexico, Indonesia, China, Cameroon and Kenya to participate. In addition to focusing on reducing deforestation, Restoration specific sessions were held on innovative monitoring approaches, many of which have been field tested through this project. Later this year members of the proejct team will convene in New York at the UN Climate week to present the findings of a monitoring pilot for the Mekong region on restoration progress since the launch of the NY Declaration on Forests. |  |
| Kenya: Activity 15 Hold a best practice and experience sharing forum | October 2018 | 80% | 100% | Complete: As part of the national restoration roadmap development process, a national level stocktaking exercise was conducted. The stocktaking looked at best practices for restoration across the country and by sector (forest, cropland, rangeland). This technical working group also formed three task forces that focus on each of these sectors, with a primary aim of providing best practices and experience to the stocktaking team. The resulting report has been a key input into the national roadmap/action plan that is currently being developed by the Government and will be shared with stakeholders at both national and county level. |  |
| Ethiopia: Activity 9 Facilitate a forum for regional and national stakeholders on landscape restoration where information on landscape restoration activities and opportunities is shared or disseminated | Dec 2018 | 80% | 100% | Complete. During the PPG phase, exchange visits were carried out between the Environment, Forest and Climate Change Commission in Ethiopia and the Kenya Forest Service to see ongoing restoration work taking place in the countries and learn from each other’s experiences. Following this visit was an exchange visit between two rural communities from both countries currently carrying out different types of restoration interventions. Each community visited the other to see what they were doing and learn from their experience. In addition, the Environment, Forest and Climate Change Commission requested an exchange visit to be organized in Kenya in December for 10 national and regional experts as a way to exchange experiences. The trip had been arranged with support from the Greenbelt Movement, but the Commission had to cancel the trip at the last minute for logistic reasons. |  |
| Indonesia: Activity 15 Hold a best practice and experience sharing forum | June 2018 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Niger: Activity 11 Organize study visits inside Niger Activity 12 Develop communication material on scaling up | March 2018 May 2018 | 100% 100% | 100% 100% | Complete. During the 2nd Annual Partners’ AFR100 meeting, in September 2017 held in Niger, the Department of Forestry and WRI organized a field visit to the Tillabery Region to share Niger’s success in the restoration degraded lands. Another visit to the Dan Saga community in Maradi and the Batodi Village in Tahoua was organized in April 2018 with WRI and representatives from the Ministry of Environment to assess the techniques used by these communities in land restoration (FMNR and water retention technics such as Tassa were observed). A third field study visit took place in July-August 2018, with the objective of assessing the extent and possible solutions for insect infestation of Gao trees in and around the three departments of Loga, Doutchi and Tibiri and other affected areas in Niger. Three Niger-based consultants were selected for this work and a full mission report and experts’ recommendations was submitted in August 2018 to the Department of Forestry and WRI. The report described the spread of the Gao tree disease and proposed solutions for community members, research centers and the Ministries of Agriculture and Environment. Some of their recommendations were implemented by the National Institute on Agriculture Research- INRAN in their new project (ANR at Scale) funded by the EU. Some of the expert recommendations were also presented to the Department of the Forestry during a briefing meeting, with the Under-Secretary General of the Ministry of Environment. Complete. In May 2018, WRI in collaboration with the Regional Director of Environment of the Maradi region organized a radio event with two restoration champions (Sakina and Ali). Both Sakina and Ali mastered FMNR techniques and have become great champions and teachers for their communities. The radio event took place on May 1st, 2018 in the district of Aiguee. Over 500 posters announcing the radio event were distributed two weeks in advance, to the villages in the Maradi Region. Announcements about the event, were also made on the national radio and other local radios, in local languages, to maximize the audience. After a successful radio event with many listeners from all around the country, a WRI representative was interviewed by the National TV (Tele Sahel News) about the importance of FMNR and the government efforts in land restoration. The recording of the radio event was shared with government officials and partners such as NEPAD Agency and the African Development Bank. Niger’s success was also recently shared on the AFR100 newsletter. Videos of the transformational regreening efforts in the 3M triangle in Zinder was planned to be created but given the recent security concern by that board, the activity was cancelled. Instead, pictures and videos of the restored plateau of the Ileila Valley were captured, with the assistance of the Tahoua Regional Environmental Director. |  |
| India: Activity 10 Multi-stakeholder meetings, workshops and trainings to create awareness about and increase capacities to implement assets and tools developed by WRI. | December 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Output 8: Technical exchanges between countries and at the sub-national level |  |  |  |  | S S S S S S |
| Global: | N/A | N/A | N/A | N/A: output applies at the country level only. |  |
| Kenya: Activity 16 Facilitate exchange program to successful landscape restoration sites in Kenya and in countries that have successfully implemented landscape restoration at scale. | December 2018 | 75% | 100% | Complete. During the PPG phase, exchange visits were carried out between Kenya Forest Service officials and Ministry of Environment, Forest and Climate Change in Ethiopia to see ongoing restoration work. Following this visit was an exchange visit between two rural communities in both countries currently carrying out different types of restoration interventions. Each community visited the other to see what they were doing and learn from their experience. An additional exchange visit was carried out between Makueni County stakeholders and those in to the Tigray region of Ethiopia where they learned various techniques and best practices for dryland restoration. |  |
| Ethiopia: Activity 10 Assess priority needs for capacity building to implement landscape restoration activities, and develop a capacity building strategy and plan for priority landscapes Activity 11 Build capacity about landscape restoration in priority landscapes | September 2018 December 2018 | 90% 75% | 100% 100% | Complete. The identification and prioritization of capacity needs in priority landscapes was carried out as part of the restoration diagnostic (see Activity 7). The outcomes of the prioritization exercise were used as inputs for the restoration diagnostic report. Approaches to overcome identified capacity gaps are incorporated in the Restoration Diagnostic recommendations. Complete. As part of the Mapathons conducted in December 2018 (see activity 17) 37 national, regional and woreda experts were trained for 2 days in image interpretation. Most (32/37) of these experts had attended the 2010 Mapathon, which helped solidify the knowledge acquired in 2017 in Collect, Collect Earth and Saiku and allowed them to actively support the use of the tool by their colleagues during the 2015 Mapathon. Out of a pool of 250 applicants, 2 Ethiopian businesses were selected to participate in the world’s first Land Accelerator, held in Nairobi in December 2018. These businesses benefitted from four days of technical training, mentorship, and business development support (see blog). They were connected with private investors and had the opportunity to pitch their businesses in an effort to attract financing. |  |
| Indonesia: Activity 16 Assess priority needs for capacity building to implement landscape restoration activities, and develop a capacity building strategy and plan for priority watersheds | June 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Niger: Activity 13 Assess priority needs for capacity building to implement landscape restoration activities, and develop a capacity building strategy and plan for at least one priority landscape | February 2018 | 100% | 100% | Complete. See previous PIR for full details. |  |
| India: Activity 11 Regional and sub-national exchanges | December 2017 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Output 9: Restoration Opportunity Fund(s) designed (national and broader in scope potentially). |  |  |  |  | S S S S S S S S |
| Global: | December 2018 | 100% | 100% | Complete. See previous PIR for full details. |  |
| Kenya: Activity 17 Identify and assess funds that could support restoration | November 2018 | 75% | 100% | Complete. In November 2018, the project team, in partnership with Fledge, hosted the world’s first land use-focused business accelerator program, which brought together 12 African restoration entrepreneurs and relevant financiers. The ultimate goal was to support projects and businesses that are not yet investment ready to become investment ready in the near term, and to expose projects that are investment-ready to investors, thereby matchmaking and solidifying private finance deals for restoration projects. On the final day of the 4-day program, approximately 15 investors convened in Nairobi to hear the entrepreneurs deliver their business pitches. |  |
| Ethiopia: Activity 12 Convene international finance dialogues targeting restoration/carbon finance sector and the traditional private sector finance Activity 13 Initiate restoration financial assessment system in Ethiopia | December 2018 December 2018 | 80% 80% | 100% 100% | Complete. In November 2018, the project team, in partnership with Fledge, hosted the world’s first land use-focused business accelerator program, which brought together 12 African restoration entrepreneurs, among which two Ethiopian (SA Bamboo Works and Edenfield Agri-Seed Enterprise), and relevant financiers. The ultimate goal was to support projects and businesses that are not yet investment ready to become investment ready in the near term, and to expose projects that are investment-ready to investors, thereby matchmaking and solidifying private finance deals for restoration projects. On the final day of the 4-day program, approximately 15 investors convened in Nairobi to hear the entrepreneurs deliver their business pitches. Complete. The potential financial sources for investment in restoration in the priority landscapes are included in the CBA report (see Activity 4). In addition, thanks to complementary funding from BMZ and the US Department of State, the project team has performed desk research and phone interviews to assess impact investors’ investment criteria and strategies as they related to Ethiopia’s restoration sector. Financier profiles, which outline average investment size, expected returns and payback period, are compiled in the Investor Spotlight report, which is currently under review. |  |
| Indonesia: Activity 17 Develop local capacity in order for local stakeholders to develop restoration plans including financing Activity 18 Build business case for restoration | September 2017 September 2017 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| Niger: Activity 14 Support stakeholders to mobilize funds Activity 15 Advocate for more funds for international processes | May 2018 August 2018 | 100% 30% | 100% 100% | Complete. See previous PIR for full details. A meeting between the Department of Forestry and the Green Climate Fund National Designated Authority (CNDD), took place mid-July 2018, to discuss Niger’s priority regarding adaptation and their support for a potential proposal on the link between FLR and climate resilience. The discussion identified a project topic including the restoration of the degraded giraffe zones, the degraded plateau of Tillabery and Tahoua. In December 2018, WRI, in collaboration with the Chamber of Commerce and an incubator organized a business roundtable for a discussion around the involvement of the private sector in restauration efforts. Niger’s Forestry Department and Chamber of Commerce opened the event, providing the ~25 businesses/entrepreneurs that participated, with information about relevant government-sponsored resources for businessowners. We then dived into group activities focused on understanding the entrepreneurs’ shared challenges in raising money for and running their enterprises. The second half of the day focused on investor pitch deck training, with the goal of preparing the entrepreneurs to present their business models to impact investors in March. The latter will be funded by another donor however it will build on the foundations created by this GEF5 project. In November-December 2018, WRI supported the Ministry of Environment in the development of a GEF7 concept note and letter of interest. The letter proposed a $13 million project to restore over 400,000 ha of degraded lands in the Dallol Bosso. |  |
| India: Activity 12 Partner with financial institutions like the National Bank for Agriculture and Rural Development to explore potential for leveraging climate finance for restoration. | December 2018 | 70% | 100% | Complete. Dialogue and collaboration with NABARD will continue throughout the project. The restoration opportunity assessment findings for Sidhi district were presented to NABARD’s regional office in Bhopal on 21 December 2017. The findings were also shared with the District Development Manager of Rewa on 15 January 2018. The findings were also shared with the Chief General Manager (CGM), Farm Sector Policy Department, NABARD on 28 August 2018. The CGM advised on few next steps for getting Sidhi’s opportunity assessment to implementation. The CGM advised that one district may not be feasible to get to implementation and that we may have to focus on proof of concept with multiple districts. NABARD is also part of a voluntary Expert Consultative Group (ECG) that was set up after the February 3 workshop under the guidance of Madhya Pradesh Election Commissioner to identify pathways to operationalize Sidhi’s restoration potential. The first meeting of the group was held on 5 March 2018 and mapped out a framework for implementing restoration in Sidhi. The second meeting was convened on 14 August 2018 in Bhopal. The ECG advised that implementation of landscape restoration in Sidhi requires the presence of strong NGOs on the ground. The paucity of such NGOs is a drawback and WRI India could play a role in bringing interested NGO partners together. Based on the findings from Sidhi, WRI India can identify interventions that have synergies with activities of NABARD such as Farmer Producer Companies (FPOs) and WADI. NABARD can then look into implementation of these activities. The ECG advised on cluster approach for getting to implementation. A cluster approach with focusing on either forestry or agroforestry interventions has also been advised by CGM NABARD. We have been in discussions with Indian Council for Agricultural Research (ICAR) who is interested in partnering on working on a clustered approach to develop a proposal for funding. The ECG also advised on developing a concept note that details the findings from the restoration opportunities assessment emphasizing livelihood opportunities and return on investment. We are now in process of finding funding for this concept note. WRI India designed and administered a two-day training on ROAM for participants from NABARD, and civil society organizations from 12-13 April 2018 at the Bankers Institute for Rural Development (BIRD) at Lucknow to scope out project pipelines under climate finance. 30 people participated in the training. |  |
| Output 10: Restoration Finance Assessment conducted in each country to identify opportunities to align existing and new financing to restoration opportunities and to clearly highlight the positive and negative incentives for restoration. |  |  |  |  | S S S S S S S S S |
| Global: | N/A | N/A | N/A | N/A: output applies at the country level only. |  |
| Kenya: Activity 18 Strengthen existing funds for landscape restoration Activity 19 Convene investment forum at priority landscape | December 2018 November 2018 | 25% 25% | 100% 100% | Complete. The landscape restoration opportunity maps and stocktaking report done for Makueni county were also shared with the County Climate Change Board that manages the county Climate Change Fund. These will guide climate change resilience and mitigation efforts, helping identify where to prioritize investment as well as what types of interventions lend themselves to scaling up based on past experiences. Complete. The first Land Accelerator was held in Nairobi in November 2018. In addition to brought together 12 restoration entrepreneurs from across Africa, including Kenya, the accelerator also convened investors who joined for a full-day forum. The entrepreneurs gave their pitches to the investors, highlighting how their businesses help restore the landscape, and the investors provided concrete feedback and expressed interest in some of the businesses. |  |
| Ethiopia: Activity 14 Develop typology of investment and business models for restoration for restoration based on experience in priority landscape(s) Activity 15 Engage relevant financial public and private institutions and put in place the financing mechanisms to provide seed funding in priority landscapes | December 2018 Continuous | 70% 80% | 100% 100% | The criteria of the typology have been identified and an interface facilitating matching business and investor profiles were developed based on the Investor Spotlight report (see Activity 13). Complete. The project team has kept helping increase public investment in restoration with its support to the development of a $13.5M GEF-7 proposal on food systems, land use and restoration by the EFCCC and its partners. WRI’s inaugural Land Accelerator (see Activity 12) acted as a pilot finance mechanism for restoration entrepreneurs, which included two Ethiopian enterprises who had the opportunity to pitch their high-impact restoration business models to relevant investors (see their pitch here and here). The visibility of the entrepreneurs has already benefitted from attending the Land Accelerator (see blog) and their pitches will be socialized through WRI’s partnership with the Global Impact Investment Network (GIIN), through the AFR100 financial partner network, and on an online Restoration Marketplace. Building on this pilot project, the team has begun discussing the next iteration of the Land Accelerator, which will include a Special Purpose Vehicle (SPV) that provides upfront equity investments/seed funding to participating entrepreneurs. |  |
| Indonesia: Activity 19 Convene international finance forum | December 2018 | 80% | 100% | Complete. WRI Indonesia has started to compile a list of potential restoration financing schemes in Indonesia. As a follow up to the finance and resourcing analyses within ROAM, a forum on this topic was held in late 2017 with the Ministry of Environment and Forestry, focusing on how to finance restoration in conservation areas. Representatives from the embassies of donor countries and multinational companies were invited. WRI Indonesia has also been conducting research on the innovative financing for peatland restoration. We also conducted a regional workshop on mangrove restoration in October 2018, whereby innovative financing was a key topic. |  |
| Niger: Activity 16 Facilitate collaboration between funding sources Activity 17 Convene civil society leaders to further the idea of investment in restoration | April 2018 June 2018 | 100% 100% | 100% 100% | Complete. See previous PIR for full details. Complete. See previous PIR for full details. |  |
| India: Activity 13 Conduct an assessment of funds and identify opportunities and barriers for funds that could support restoration Activity 14 Develop framework for incentives | June 2018 December 2018 | 100% 70% | 100% 100% | Complete. See previous PIR for full details. Complete. The database of past and on-going restoration interventions has been developed that captures details of restoration projects. This database is developed as a report. The report also captures factors that support scaling, methodology for the factors and detailed case studies. The database and report have been developed through extensive literature review and consultation with the national level technical working groups to develop a list of factors that support scaling of landscape restoration in India. These factors include tenure, policies, finance, capacities, market, business models, monitoring and evaluation, benefits, flow of information, institution and stakeholders, reconciling boundaries, and technology. Using this framework, two detailed case studies were developed for NABARD's Wadi programme that is being implemented across India and a KfW funded project in the state of Tripura. |  |
| Output 11: Method for establishing baselines and monitoring changes in biomass established |  |  |  |  | S S S S S S S S S S S S S S |
| Global: | December 2018 | 90% | 100% | In cooperation with FAO as part of the global restoration monitoring group, WRI has developed a restoration monitoring framework. This framework guides users (e.g. national and sub-national government officials) through the process of making choices on what to monitor for each restoration goal that the country has set, and what metrics to apply to ensure monitoring costs are minimal but still give accurate information on progress of monitoring. This framework has now been refined and published as an official WRI report that will be launched in early October in Rome with FAO. With complementary funding from FAO the project team has also developed a prototype of a decision-based app (currently called LandTrack) which is based on the monitoring framework publication, that will allow users in the field to use it to design monitoring frameworks. Additionally, a user guidebook on how to use “Collect Earth” and run mapathons as tools to support monitoring has been drafted by the proejct team and is currently in review with WRI’s Science and Research team. The guide will tentatively be published before the end of the year. |  |
| Kenya: Activity 20 Establish county level baseline Activity 21 Develop restoration monitoring and evaluation framework Activity 22 Establish biomass baseline for priority landscape | September 2018 December 2018 December 2018 | 30% 85% 50% | 100% 100% 50% | A Collect Earth mapathon was conducted in Kenya, which established a current baseline for Makueni County. The baseline looked at tree cover, tree count, and land cover. This baseline will allow Makueni County to measure its progress towards restoring degraded land. Complete. WRI supported the Kenya Water Tower Agency (KWTA) to develop a landscape restoration monitoring framework which would guide the development of a monitoring system. KWTA formed a multi-sectoral monitoring working group which met on a monthly basis in 2018. The working group identified the goals and most important indicators that need to be measured, as well as mapping out which organizations already collect this data and at what interval and resolution. The monitoring frame work is now being used by the KWTA and stakeholders to guide implementation of an integrated monitoring system for the water towers. A biomass baseline for the year 2000 was established for Makueni County using data available on the Global Forest Watch – Climate platform. This data has been shared with the Makueni County restoration working group and will be used to measure progress on restoration. |  |
| Ethiopia: Activity 16 Develop multiscale, integrated restoration monitoring and evaluation system of environmental, social and economic costs and benefits that can be operationalized country wide Activity 17 Establish baseline information for priority landscapes from existing sources if possible Activity 18 Monitor gains through the established system for priority landscapes | September 2017 November 2018 December 2018 | 100% 60% 25% | 100% 100% 95% | Complete. See previous PIR for full details. In addition, a poster on the monitoring framework was exhibited during the launch of the national potential maps. Version 1.0 of Ethiopia’s Tree Assessment Survey was improved based on the feedback received after the 2010 Mapathons held in December 2017 (see post-Mapathon survey for Sodo and Meket). Feedback on version 1.1 was elicited from experts (see 2015 post-mapathon survey). Complete. The baseline/2010 statistics for both Sodo and Meket were produced for 20+ indicators (see Sodo and Meket PPTs). Baseline data include 2010 percent tree cover by land use-land cover and total, on treated land, and in gullies; 2010 tree spatial pattern in cropland, grassland, rural compound and settlement; 2010 percent of linear features (i.e., waterbody banks, bunds/terraces, boundaries, roads, gully banks) with tree canopy. In the Fall of 2018, 19 experts from Sodo and SNNP Region, and 18 experts from Meket and Amhara Region attended a 6-day Mapathon to collect data for 2015 using version 1.1 of Ethiopia’s Tree Monitoring Survey. Data were collected for 2,452 and 2,533 plots for Sodo and Meket, respectively. The data were cleaned, analyzed, and included in a report assessing change in tree cover and distribution between 2010 and 2015 and informing implementation for both woredas. The reports are in the final stages of the review process. |  |
| Indonesia: Activity 20 Test the use of high resolution imagery to test baseline Activity 21 Develop multiscale restoration and monitoring on biomass Activity 22 Develop multiscale restoration and monitoring on socio-economic cost/benefits | March 2019 March 2019 January 2019 | 80% 80% 80% | 100% 100% 100% | Complete. WRI Indonesia in coordination with the Peatland Restoration Agency and other partners have completed LiDAR mapping for 5 landscape areas that will serve as a baseline for peat restoration works. This work is also part of a project that is funded by the Norwegian Government. WRI Indonesia and multiple partners have been developing a crowdsourcing platform through mobile application and website to map degraded land and potential restoration options in two provinces. This is part of an international project called RESTORE+ involving many partners, which kicked off in April 2017. The restoration monitoring platform for peatland restoration called PRIMS has been set up and developed by WRI Indonesia for the Peatland Restoration Agency, co-funded primarily by the Norwegian Government. The platform has been used actively by the government to monitor the restoration progress and state of peatlands. |  |
| Niger: Activity 18 Support the establish a national restoration baseline including socio-economic factors Activity 19 Support information sharing and communication around restoration achievements | December 2018 March 2018 | 80% 100% | 95% 100% | Primary baseline assessments have been conducted and described in previous reports, with assessments including stocktaking of existing success, priority mapping and identification of major challenges and opportunity to scale up restoration. WRI collaborated with the Economics of Land Degradation Initiative (ELD), between June and December 2018, to develop capacity for socio-economic assessments in the Maradi region. The assessments began with case studies in the pastoral lands of the Maradi region, followed by a summary report highlighting baselines and key statistics. The research also included over a month of socio-economic data collection on the value added of restored lands on the land, biodiversity, people and revenues. The research adopted a wider angle for socio-economic assessment than "farmer-managed natural regeneration" (of trees) and includes other land management investments and a variety of ecosystem services. A first complete draft of the economic assessment was developed by WRI in collaboration with a consultant in December 2018. The data collected have been used by ELD and GIZ in a country level analysis on the economy of land degradation which will be published in 2020. Complete. See previous PIR for full details. |  |
| India: Activity 15 Analyze existing forest monitoring mechanisms to identify their strengths and weaknesses for restoration monitoring Activity 16 Develop methodologies for establishing restoration baselines from ecological, social and economic perspectives. | December 2018 April 2018 | 70% 100% | 100% 100% | Complete. The database on restoration interventions identifies practices and mechanisms in place for monitoring restoration has been developed. The framework on factor for scaling restoration includes monitoring as a key criteria and the in-depth case studies analyze existing monitoring mechanisms in detail. A database of over 350 past and on-going restoration interventions in India. These interventions have been implemented by government, civil society, local communities and private sector. Based on the database, short case studies were developed for the interventions and compiled into a report. This report is hosted on the Restoration Opportunities Atlas. Complete. See previous PIR for full details. Additionally, a methodology for creating a baseline of existing institutions in the area and their relationships has been created using social network analysis through deep dive analysis in Sidhi district of eastern Madhya Pradesh. The social landscape guidebook was launched in September 2018 and takes a new approach to environmental governance by focusing on identifying the social capital of actors within the landscapes. It centers on two main approaches: 1) mapping actors’ resource flows and 2) mapping actors’ priorities and values. Co-written by WRI international offices, this methodology has been tested in Brazil, India, Indonesia, Kenya, Mexico, and Rwanda. By using this guidebook, environmental practitioners can be more efficient with resources, collaboration, and outreach, and better anticipate potential conflicts and bottlenecks. Podcast on the social landscape guidebook is available here. The podcast features the two case studies of Lake Toba in Indonesia and the Sidhi district in India. Webinar is available here which features an overview of the guide and the methodology, as well as a deep dive from WRI India’s work in Madhya Pradesh. |  |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The outputs achieved through this project have been instrumental in moving FLR along in the target countries. In many cases, the analysis and engagement carried out through this proejct directly resulted in either high-level political commitments and policy changes (Kenya, Indonesia, Niger), or significant progress towards restoration implementation and monitoring (all target countries). The project teams worked tirelessly to ensure deep engagement from local partners and stakeholders, resulting in strong ownership by national actors. These activities came at a very strategic time when more interest and pressure globally on FLR is driving the target countries to take action. Though this was a medium sized project, the proejct team was able to leverage support from many different partners and funders to have significant impact on the progress of FLR implementation in the target countries and globally. Many of the methodologies and tools piloted in this project have now been proven on the ground and are now publicly available and being used in other regions outside of the target countries to advance FLR adoption and implementation. These include Social Landscape Mapping for FLR, the WRI-FAO Restoration Monitoring Framework, the use of Collect Earth as a low-cost restoration monitoring tool, the Restoration Opportunities Assessment Methodology (ROAM), and the Restoration Diagnostic. The project has also helped spark sub-national interest and leadership in FLR, where prior to the proejct much of the focus world-wide was with national level commitments. The enthusiasm and adoption of FLR as a way to meat development goals and adapt to and mitigate climate change was unexpected and resulted in significant outcomes in all of the target countries. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| N/A | N/A | N/A | N/A |

3.3. Risk Rating.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Lack of available data and information to conduct trusted analyses (geospatial data, economic data, sectoral strategies and plans, etc.) | In cases where key data or information is not available from traditional secondary sources, the project team will convene key informant interviews, focus groups and/or workshops to obtain the best available in-country knowledge on the topic. | At implementation, the project team followed the mitigation strategy detailed at CEO approval. In every country, the project team ran into cases where key data were not available but were able to overcome these by using either best available regional or global data sets, or convening experts in-country and gathering this data through workshops. In some cases, baseline data collected through Collect Earth mapathons was also used to fill gaps in land use/land cover data. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Inability to engage beyond one ministry and sector | Align restoration as a strategy to achieve existing priorities in key sectors outside of environment, with focus on agriculture as the dominant land use in all the priority countries. Build the capacity of the team to include agricultural expertise and experience, while leveraging the growing capacities of WRI’s growing portfolio of programmatic work on food and the World Resources Report. | In all of the target countries the project team engaged with multiple ministries and sectors throughout the project, namely the agriculture and water sectors. They were engaged at the national level during ROAM mapping and national planning, and especially at the sub-national level where sector silos are less prevalent, and more integration is already taking place. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Lack of willingness to revise land use planning to prioritize forest restoration | Land use planning is usually a long process that involves different ministries horizontal and vertical that can take years | While the proejct activities did not aim to develop official land us plans, the restoration action plans and strategies developed do propose ways to adjust current approaches to land use and layout strategies for incorporating more trees into different land uses. The multi-ministerial working groups at both national and sub-national levels are well convinced of the importance and potential benefits of incorporating restoration into land use planning and are well positioned to continue moving this conversation forward past the end of the project. Many of the following projects being implemented by WRI after the completion of this GEF5 project will continue to build on this progress and sure restoration plays a key role in future land use decisions. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Social inequalities exacerbate | Project activities will be inclusive and planned to involve wide participation of all community members | All project workshops, at both national and sub-national level, included a wide range of stakeholders to ensure all points of view were included in discussion. At national level, this included multiple ministries, Civil Society organizations, academia, and NGOs. At sub-national level, this included many of the same stakeholder groups mentioned above but at sub-national level, as well as members from local community associations. Social inequality was also one of the focuses of the ROAM discussions carried out by the proejct teams. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Over the project period, countries likely continue to experience weather variability, that may have deleterious impacts on ecosystem services over which land users have no control | Ongoing assessments will measure and take into account changing climate conditions, and project activities such as community land management planning and training in land management will be adapted based on these assessments. | At the sub-national level especially, the project team worked directly with stakeholders who have a deep knowledge of local climate context. These insights were included in planning and assessments. At national level, technical working groups were well aware of changing weather patterns, and this was reflected in discussion and final products that were produced. This risk will continue to affect the target countries well past the end of the project. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| The increase rate of population, which is challenging in terms of demand of productions against economic growth rate | It is notable that this growth rate, need to be matched with equal opportunities to reduce destructive activities such as charcoal burning. Investments or promotion of livelihood activities as forms of financing restoration activities such as nature-based enterprise provide a window, which could be utilized by this project | Population growth in the target countries continues to be a risk to sustainable land use practices, including restoration. During the mapping assessments, current population and project population growth was taken into account to identify restoration potential. A strong focus on restoration within current cropland areas which tend to be the areas experiencing the most population growth, aimed to identify options for increasing tree cover in order to meet livelihood needs. At the sub-national level, the project team built on efforts already being taken by local stakeholders to provide livelihood opportunities (e.g. in Makueni County, Kenya, mango growing is a growing business, and the county has secured a long-term contract with the EU to sell mangoes and mango pulp.) Population growth pressure will continue past the end of this project, but the restoration plans, if implemented, should help ameliorate this pressure on natural systems. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
|  | L | Based on the risk rating and mitigation strategies listed in the above table, the project team feels that there is low risk to the project. Since the completion of project activities earlier this reporting period, none of the above risk have either materialized or impacted the delivery of project deliverables and achievement of outputs. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  | X |  |  |  |  | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Improved monitoring opportunities fall in line with availability of high-resolution satellite imagery. However, integrating these into national monitoring frameworks requires technical capacity development at national level |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  | X |  |  |  |  | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Choices for and prioritization of topics and areas remain politically driven. However, they did not overly affect project-internal decisions |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: TM: While stakeholders at national and local levels have an immense knowledge about and awareness of changing climatic conditions and are able to set their adaptation strategies accordingly, it is undeniable that climate change has negative impacts on restoration efforts in the longer term. |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | Overall the project team believes that this project earns a low risk rating because most of the factors noted above are low risk. The project team has completed all proejct activities to date and none of the above risks pose any threat to the project. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation, please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.