Project Implementation Report (PIR)

01/07/2024–30/06/2025

Strengthening forest management for improved biodiversity conservation and climate resilience in the Southern Rangelands of Kenya

Table of Contents

A.	Project Overview	2

B.	Overall Ratings (Final – Validated by Regional Portfolio Manager)	4

C.	Ratings and Overall Assessments	5

D.	Outcomes achievements and outputs delivery	9

E.	Challenges: Information on challenges of project implementation activities	13

F.	Adjustments	57

G.	Implementation Progress	59

H.	Critical Risk Management	60

I.	Gender	64

J.	Implementing the Stakeholder Engagement Plan	65

K.	Environmental and Social Safeguards	67

L.	Knowledge Management	73

Annex - Ratings definitions	78

# Project Overview

| Project Information |  |
| --- | --- |
| IUCN Project ID | P03162 |
| GEF ID | GEF ID:10292 |
| Title | Strengthening forest management for improved biodiversity conservation and climate resilience in the Southern Rangelands of Kenya |
| Country(ies) | Kenya |
| Regional Programme | GEF-7 Sustainable Forest Management Impact Program on Dryland Sustainable Landscapes (SFM DSL-IP) |
| Global Thematic Programme/Regional Thematic Programme (if relevant) | Dryland Sustainable Landscapes Impact Program (DSL-IP) |
| Joint Agency (if relevant) | FAO (Food and Agriculture Organization of the United Nations) |
| Executing Agency(ies) | National Environment and Management Authority (NEMA-Kenya) |
| Project Type | Full-Sized Project (FSP) |

Project Description

The GEF-7 project "Strengthening Forest Management for Improved Biodiversity Conservation and Climate Resilience in the Southern Rangelands of Kenya", aims to foster a resilient dryland forest landscape supporting sustainable economic and food production through integrated natural resource management. Spanning 13,250 km² across Kajiado and Narok Counties in Southern Kenya, inhabited predominantly by Maasai pastoral and agro-pastoralists, the project addresses severe land degradation. This degradation is driven by increased human and livestock populations, leading to unsustainable exploitation of resources like forests for charcoal and timber, high dependency on biomass energy, widespread poverty, and lack of alternative livelihood opportunities. The region also faces exacerbating challenges from adverse weather and climate change impacts and the spread of invasive species like Prosopis juliflora. Weak management, implementation, and enforcement of natural resource policies further contribute to problems like soil erosion, siltation of Lake Magadi, declining wildlife, and increased human-wildlife conflicts. With the International Union for Conservation of Nature (IUCN) as the Implementing Agency and the National Environment Management Authority of Kenya (NEMA) as the Executing Agency, the project employs a holistic approach to link income-generating activities with sustainable environmental management, focusing on strengthening governance and community capacity, scaling up restoration and integrated land-use, increasing sustainable investments in resilient livelihoods, and coordinating knowledge management at local, county, and national levels. Objectives - Develop community enterprises and livelihood value chains based on sustainable natural resource use. - Strengthen governance of land resources through empowered community organizations and government institutions. - Support communities and local authorities in implementing resource management and restoration plans. - Coordinate management through an integrated dryland landscapes knowledge exchange and platform. Outcomes and Outputs Outcome 1.1: Governance institutions, and community capacity for sustainable land management are strengthened. - Output 1.1.1: Strengthened, gender-sensitive community organizations (CFAs, Conservancies, River Users Associations) to implement land/resource plans. - Output 1.1.2: Enhanced capacity of County Environment Committees in Narok and Kajiado to implement restoration plans in Loita, Namanga, Suswa, and Olkiramatian/Shompole forests. - Output 1.1.3: Increased financial resource allocation at local levels for sustainable land management. Outcome 2.1: Restoration and sustainable land use actions are implemented. - Output 2.1.1: Rangeland restoration sites identified through gender-responsive opportunity mapping. - Output 2.1.2: Participatory restoration investment action plans developed. - Output 2.1.3: Rangeland rehabilitation and management techniques applied. - Output 2.1.4: Improved water access for communities and livestock. - Output 2.1.5: Human–wildlife conflicts mitigated. Outcome 2.2: Sustainable investments in resilient livelihood actions are increased - Output 2.2.1: Sustainable offtake mechanisms with private processors and export markets established. - Output 2.2.2: Gender-sensitive clean energy investments reduce reliance on biomass. - Output 2.2.3: Market-based climate insurance and risk transfer schemes developed. - Output 2.2.4: Community–private sector ecotourism investment partnerships signed. - Output 2.2.5: Impact investment funds promoted for viable forestry and agroforestry practices. Outcome 3.1: Sustainable landscape management actions are informed, coordinated, and mainstreamed. - Output 3.1.1: Functional landscape-level information system established for dryland planning - Output 3.1.2: Gender-responsive localized tools for climate, biodiversity, and health assessments developed - Output 3.1.3: Lessons captured, evaluated, and shared nationally and regionally. - Output 3.1.4: National and Eastern Africa policy dialogue on dryland restoration promoted through evidence-based briefs and recommendations.

| Project Contacts |  |
| --- | --- |
| Task Manager (Implementing Agency) | Benjamin Mutua |
| Global/Regional Thematic Lead (Implementing Agency) | Dr. Olivier Habimana |
| Regional Portfolio Manager (GEF/GCF) | Ms. Debasmita Boral Rolland |
| Project Manager (Executing Agency) | Dr. Leonard Tampushi |
| Project Monitoring and Evaluation Officer (Executing Agency) | Ms Iqra Osman |
| Project Safeguards Officer (Executing Agency) | Mr Newton Osoro |
| Project Communication Officer (Executing Agency) | Ms Judith Otieno |
| GEF Operational Focal Point | Principal Secretary |

# Overall Ratings (Final – Validated by Regional Portfolio Manager)

| Overall Development Outcomes Rating | Moderately Satisfactory |
| --- | --- |
| Overall Implementation Rating | Moderately Satisfactory |
| Overall Risk Rating | Moderate Risk |
| Safeguards Risk Rating | Moderate Risk |

# Ratings and Overall Assessments

| Role | YEAR Development Objective Progress Rating | YEAR Implementation Progress Rating | YEAR Project Risk Rating |
| --- | --- | --- | --- |
| Project Management Unit (PMU) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) |
|  | The project made strong progress towards its objectives in Reporting period, with most annual milestones fully achieved or surpassed. Governance & Institutions: 5 community institutions (2 WRUAs, 2 CFAs, 1 Grazing Committee) were strengthened against the annual target of 5, achieving 100%. A total of 327 members (156 women, 171 men) participated in the capacity-building sessions, ensuring inclusivity. County Environment Committees (CECs): 2 CEC trainings were completed (Narok and Kajiado), meeting the endline target in the first year. Sustainable Financing (PES): 1 PES scheme was identified and negotiations initiated, pending MoU signing, meeting the Year 1 target. Restoration & Resource Management: ROAM mapping covered 552,000 ha (vs. 62,000 ha planned nearly 9 times higher). Restoration action plans were developed, and initial works included 65.4 ha under restoration activities, establishment of 4 tree nurseries established, producing 600,000 indigenous seedlings, planting of 6 agroforestry gardens, and training of 300 community members. Water access was improved through the construction of five 50 m³ school rainwater tanks, directly benefiting over 2,000 pupils and indirectly adjacent communities. Knowledge Management & Policy: A functional MEL system was established and is operational. Lessons from 3 baseline studies were captured and shared through a national policy forum, 1 project magazine, and 3 media publications, contributing to national and regional policy dialogue. Overall, the project has achieved its Year 1 targets in governance, restoration planning, PES groundwork, and knowledge management, thereby laying a strong foundation for subsequent years. | Year 1 implementation was timely, efficient, and aligned with annual work plans, with concrete delivery across all planned outputs. Institutions Strengthened: 5 institutions (100% of annual target) supported and trained. CEC Trainings: 2 county CECs trained (Narok & Kajiado), achieving the full endline target earlier than expected. PES: 1 PES scheme initiated and under negotiation, pending MoU signing (70% of Year 1 target). Restoration: ROAM mapping identified 552,000 ha for restoration (surpassing target of 62,000 ha). Restoration action plans developed, 65.4 ha restored, 600,000 indigenous tree seedlings raised, and 6 agroforestry gardens established with 300 beneficiaries trained. (ROAM across 13 wards mapped 592,911 ha (target 62,000 ha in the Result Framework), establishing the baseline of degraded areas disaggregated by type. This nine-fold overachievement provides a strong evidence base to guide the project’s 1,750 ha restoration target) Water Access: 5 school rainwater harvesting tanks (50 m³ each) constructed, directly benefiting 2,000+ pupils and indirectly local community members. Knowledge Sharing: MEL system operationalized; 3 baseline studies completed; lessons disseminated through 1 national policy forum, 1 magazine, and 3 media publications. Although the hectares restored (65.4 ha vs. 300 ha target) were below the set milestone, this is mitigated by the strong preparatory groundwork (seedling establishment, agroforestry, nurseries) which positions the project to scale up restoration in Year 2. | During the first reporting year, the project effectively identified, monitored, and mitigated key High and Medium risks. The major risks addressed included: External – Climate Variability: Classified as High risk due to minimal rains affecting restoration. Mitigation included introducing drought-resistant tree species, tree site-matching, and adjusting restoration pans and designs based on weather forecast. Despite rainfall challenges, initial restoration activities proceeded with 552,000 ha mapped and 600,000 indigenous tree seedlings established, showing effective adaptation. Financial – Disbursement Delays: Rated High risk. A consultative meeting between the Implementing Entity, Executing Agency, and National Treasury will be held to align financial cycles. Funds are still being processed at 50-50% policy, but mitigation like spreading half year budget across the full implementation targets still affects the annual progress targets and achievements. Operational – Delayed Inception & Launch: The project launch was delayed by 12 months (launched 7th June 2024). Fast-tracking of activities has reduced the backlog; with Year 1 milestones substantially achieved despite the late start. Operational – Stakeholder Management: Rated Medium risk. Continuous community and county engagement improved understanding of project roles, reducing the likelihood of grievances and disputes. Stakeholder expectations are now better aligned with project objectives. Overall, mitigation measures were timely and effective, with no escalation of risks and no new High risks identified during the reporting period. |
| IUCN Regional/Global Thematic Lead (as relevant) | Overall Assessment | Overall Assessment | Overall Assessment |
|  | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory |
|  | Please provide justification for overall assessment | Please provide justification for overall assessment | Please provide justification for overall assessment |
|  | Project did not achieve most of its major relevant annual targets due to delays in start-up and steepy partners’ learning curve on the project key methodological aspects. | Not all components have kicked off and/or are delivered as per the initial plan. Next year, the PMU will have to accelerate implementation for all project partners across all components/activities. | Most of the project assumptions still hold. However, there are structural issues that can contribute to operational and financial risk of the project delivery, if not quickly resolved. |
| IUCN Regional/Global Portfolio Manager | Overall Assessment | Overall Assessment | Overall Assessment |
|  | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |
|  | Please provide justification for overall assessment | Please provide justification for overall assessment | Please provide justification for overall assessment |
|  | During the reporting period, the project achieved encouraging progress in laying institutional and technical foundations, but tangible outcomes on the ground remain limited. Governance and capacity-building efforts were broadly on track: five institutions were strengthened against the annual target, gender-sensitive training reached 185 members, and ROAM mapping exceeded expectations, producing a robust evidence base for restoration planning. However, the translation of this groundwork into measurable environmental and livelihood results has been slow. Only 65 ha were restored against a 300-ha annual target, the PES scheme has not moved beyond negotiation, and several planned outputs – such as climate insurance, ecotourism partnerships, and impact-investment funds – did not start. There is little evidence so far that training, mapping, or initial livelihood demonstrations are delivering biodiversity or socio-economic gains, leaving the project at a preparatory stage with limited field impact, which has to be rectified by fasttracking implementation in the remaining years. | Implementation progress has been constrained by structural and operational challenges, as well as prolonged inception phase that witnessed debates and iterative exchanges around the project’s targets and scope. A delayed financing agreement and budget approvals postponed launch by almost a year, while subsidiary agreements, account-opening hurdles, and a 50/50 disbursement rule slowed fund flow and absorption. Although the team adopted sensible mitigation measures – including early engagement with the Treasury, linking nurseries to markets, and prioritising activities – these have not yet addressed the underlying causes of delay. Restoration, PES, and livelihood activities therefore lag behind schedule, and delivery will need to accelerate sharply to recover lost time. | Project risks remain substantial. The financial architecture, particularly the disbursement cap, poses a continuing threat to timely implementation and may undermine confidence among partners. Market viability for nurseries and PES remains untested, risking community disengagement, while policy shifts introduce uncertainty for alignment and co-financing. Restoration targets are highly ambitious compared with the current rate of progress, requiring a clear strategy for scaling up. Amending the financing agreement to allow full annual disbursement and streamlining approval processes are essential steps to reduce these risks. |

# Outcomes achievements and outputs delivery

Outcomes Achievements and Outputs Delivery Outcome 1.1: Governance, institutions and community capacity for sustainable land management is strengthened During the reporting period, the project made significant strides in strengthening governance and institutional capacity for sustainable land management. Out of the 20 institutions targeted for strengthening over the life of the project, 5 were reached in the first year, representing 100% achievement of the annual target. These included 2 Water Resource Users Associations (WRUAs), 2 Community Forest Associations (CFAs), and 1 Grazing Committee. Capacity-building sessions reached a total of 165 participants, including women and youth, demonstrating inclusivity in project delivery. While the results are highly encouraging, follow-up in subsequent years will be essential to measure how the skills gained are being applied and sustained. Output 1.1.1 – Gender-sensitive local community organizational capacity strengthened Organizations were supported during the reporting year: Meeyu Milk Cooperative (100% women), a Grass Bank (40 women trained), and Oldonyorok Youth Group (35 men, 15 women). A total of 185 members were trained (100 women, 35 men, and 50 youth). Against the annual target of training 150 members, this represents strong delivery on organizational support, though member training numbers were lower than expected. The achievement reflects steady progress in building institutional capacity with strong gender inclusion, while highlighting the need to scale up training in future reporting periods. Output 1.1.2 – Capacity of County Environment Committees (CECs) strengthened Both Kajiado and Narok CECs were trained, meeting the annual target fully and even securing the endline target earlier than anticipated. In Kajiado, the training supported the development of a County Environment Action Plan, while Narok will require refresher training for new committee members appointed post-election. Overall, the target was achieved with strong delivery, reflecting timely implementation and follow-up in subsequent years will be essential to measure how the skills gained are being applied and sustained. Output 1.1.3 – Financial resource allocation through PES schemes A PES baseline assessment was completed, identifying opportunities in water regulation, biodiversity conservation, carbon sequestration, and soil erosion control. From this, 1 PES scheme on water regulation was selected for negotiation and is under implementation. This partially meets the Year 1 target of establishing one PES scheme. MoU signing is pending; the groundwork provides a solid foundation for sustainable financing mechanisms. Outcome 2.1: Restoration and sustainable integrated land use management actions are implemented During the reporting period, the project made significant strides in laying the groundwork for restoration and sustainable land management across the target landscapes. A total of 592,911 ha was identified for restoration, with 65.4 ha already under active restoration, complemented by water and livelihood interventions engaging 385 community members (39% women). The Project Management Unit (PMU) recognizes that the endline target for the ROAM assessment was 62,000 ha, while the overall restoration target for the project is 600,000 ha. To achieve this goal, it was necessary to first establish a baseline on the extent, area coverage, and type of degradation. The project therefore employed the Restoration Opportunities Assessment Methodology (ROAM) across 13 wards in the two counties (Narok and Kajiado), identifying both the level and type of degradation. By leveraging ROAM, the project has overachieved the 62,000-ha assessment target by far, mapping nearly nine times more restoration opportunities than planned, thereby creating a robust evidence base to guide large-scale restoration towards the 600,000-ha target. Output 2.1.1 – Rangeland restoration sites identified 552,911 ha were mapped through ROAM, against an annual target of 62,000 ha. This represents a significant overachievement and provides the evidence base for restoration planning. Output 2.1.2 – Restoration action plans developed 4 participatory and gender-responsive action plans were developed, covering 21.6 ha (13.6 ha communal, 8 ha pasture). The planning process engaged 385 community members (39% women) and included training for 85 farmers (67 women, 18 men). This achievement demonstrates inclusive and technically sound restoration planning. Output 2.1.3 – Rangeland rehabilitation and management implemented Implementation began with 65.4 ha restored, supported by 600,000 seedlings, six agroforestry gardens (37 ha), four nurseries, and training of 300 members (85 women, 215 men). In addition, 100 Langstroth beehives were distributed to support alternative livelihoods. While the hectares restored are below the annual target of 300 ha, the substantial preparatory work positions the project to accelerate delivery in subsequent years. Output 2.1.4 – Improved water access Five (5), 50 m³ school rainwater harvesting tanks were constructed, benefiting over 2,000 pupils and surrounding communities. Two degraded wetlands were also identified for protection. This fully met the Year 1 target. Output 2.1.5 – Human-Wildlife Conflict mitigation The project recruited 30 community scouts across Shompole, Mosiro, Musenke, and Olorte. the recruitment and training of scouts established a foundation for future reduction of HCW. Outcome 2.2: Sustainable investments in resilient livelihood actions are increased The reporting period focused on mobilization, awareness, and demonstration activities to lay the groundwork for resilient livelihoods. Direct employment opportunities are planned for future reporting periods, but achievements demonstrate strong community interest and gender inclusivity. Output 2.2.1 – Sustainable offtake mechanisms Not planned for this reporting period. Output 2.2.2 – Gender-sensitive clean energy investments A clean energy exhibition in Kajiado showcased nine local innovators, including women-led groups such as Lamaratak Self-Help Group (briquettes) and Enkakenya Sidai Women Initiative (energy-saving stoves, beekeeping, beadwork). Three demonstration sites were identified, with 120 community members sensitized and 150 mobilized (107 women, 43 men). These activities demonstrate early adoption of clean energy practices and strong gender inclusion. Output 2.2.3 – Climate insurance schemes A baseline study was initiated to assess Index-Based Livestock Insurance (IBLI) options. This preparatory work will guide rollout of insurance packages in the next period. So not planned for this reporting period. Outputs 2.2.4 & 2.2.5 – Ecotourism partnerships and impact investment funds Not planned for this reporting period but consultations conducted in preparation for future implementation Objective 4: To coordinate the management of an integrated dryland landscapes knowledge exchange and management platform Outcome 3.1: Sustainable landscape management actions are informed, coordinated, and mainstreamed at county and national level During the reporting period, the project made notable progress in strengthening coordination, monitoring, and knowledge-sharing systems for dryland restoration. Output 3.1.1: Functional landscape-level information system for improved planning and management of dryland resources established A key milestone was the development and operationalization of a Monitoring, Evaluation, and Learning (MEL) system at the project and its partners.. This system now allows real-time tracking of restoration activities, water access, and rangeland management, consolidating data in a central platform. The achievement fully met the annual target, significantly enhancing evidence-based decision-making and planning capacity across institutions. Output 3.1.2: Gender-responsive localized drylands health, climate, and biodiversity assessment tools developed and utilized The development of these assessment tools was not scheduled for this reporting period and will be implemented in the coming year. Once developed, they will be critical for generating localized data to guide restoration and biodiversity management, ensuring that interventions remain gender-responsive and scientifically sound. Output 3.1.3: Project lessons are captured, evaluated, and shared nationally and across countries and regions The project achieved its annual target of two publications, producing the Rangelands Rising Magazine and the Communication & Knowledge Management (CKM) Assessment Report. Beyond publications. Output 3.1.4: National and Eastern Africa policy dialogue on dryland restoration promoted through evidence-based policy briefs and recommendations The project convened the National GEF-7 SFM Forum, which brought together stakeholders to deliberate on dryland restoration priorities and produced actionable recommendations. To complement this, communication products such as brochures and case study drafts were developed, while visibility was boosted through posters, online platforms, and media features. The first project magazine was finalized, and audiovisual materials documenting community innovations were produced. These actions laid the groundwork for stronger policy engagement, though formal policy briefs will be finalized in the next reporting period.

# Challenges: Information on challenges of project implementation activities

Challenges Encountered Since the Project Started Delayed project launch by appx 12 months hindered timely commencement of activities. The financing agreement was signed in April 2023, towards the end of FY 2022/23. Consequently, the project budget could not be included in the FY 2023/24 estimates, as the budgeting process had already been concluded by the National Treasury. NEMA requested the Treasury to allow utilization of funds pending budget regularization, but was advised that funds could only be accessed through a supplementary budget process. This was finalized in December 2023, enabling NEMA to receive the first disbursement in January 2024. Further delays occurred as NEMA initiated negotiation for the subsidiary agreements with Sub-executing Agencies (SEAs) (KALRO, ACC, NETFUND, and SORALO), which was concluded in April 2024. The subsidiary agreements were required to open dedicated project bank accounts before NEMA could disburse fund to SEA’s. Some SEAs faced delays in account opening due to administrative procedures, such as approval by the Boards of Management which only convene once a quarter. Policy and administrative changes slowed implementation. Shifts in government administration and the introduction of new policy priorities, including the 15 billion Trees by 2032 program and the national government’s Bottom-Up Transformation Agenda (BETA), contributed to delays in project launch and implementation. Market challenges undermined community sustainability. Lack of reliable markets for seedlings produced by the strengthened community organizations, particularly in areas such as Eramatare community cooperative, limited the viability of community-based nursery operations, conic benefits and over maturity of seedlings beyond planting age. Protracted fund disbursement processes affected absorption. Lengthy disbursement procedures involving both the IE and the Treasury, combined with capped annual budgetary allocations, further delayed implementation. Under the IUCN–National Treasury agreement, disbursements were restricted to a 50/50 arrangement. While 50% of funds were released in the first year, the Treasury capped the same amount as the project’s annual budget. These delays constrained the timely execution of activities and slowed overall fund absorption. The project applied several measures to address and mitigate these challenges - Enhanced coordination across components: Regular joint planning meetings and continuous communication among, Sub-executing agencies, and NEMA helped reduce bottlenecks and improve alignment of activities across components. - Delayed project launch and budget allocation: NEMA engaged the National Treasury early to secure project funds through a supplementary budget process. In parallel, NEMA initiated subsidiary agreements with SEAs (KALRO, ACC, NETFUND, and SORALO) and provided technical support to expedite the opening of project accounts, ensuring that subsequent disbursements would not be delayed. - Policy and administrative changes: The project aligned its implementation strategy with new government priorities, particularly the 15 billion Trees by 2032 initiative and the Bottom-Up Transformation Agenda (BETA). This ensured relevance to national priorities and created opportunities for synergies with ongoing government programs. - Market challenges for seedlings: Community-based nurseries were linked with government-led restoration programs, private sector actors, and county governments to create reliable seedling markets. The project also encouraged diversification of products (e.g., agroforestry seedlings, fruit trees, fodder species) to enhance market demand and sustainability. - Protracted fund disbursement and capped allocations: NEMA strengthened financial planning and prioritization of activities within available funds to avoid disruptions. Regular consultations with the National Treasury and IUCN were held to fast-track disbursement processes. In addition, capacity-building was provided to SEAs and community groups to enhance timely utilization and reporting of funds, improving absorption rates. Recommendation. The financing agreement should be amended to remove 50/50% disbursement clause for the project to receive 100% annual disbursement from IUCN. This will facilitate enhanced project implementation and time recovery.

Results Framework

| OUTCOME 1.1: Governance, institutions and community capacity for sustainable land management is strengthened |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes (Copy and paste outcomes from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Progress rating (HS, S,MS,MU,U,SU) |
| Outcome 1.1: Governance, institutions and community capacity for sustainable land management is strengthened | Number of county and community level structures/institutions with improvements in governance of land and resources as demonstrated by improvements in participatory land use planning, enforcement of regulations related to natural resource use, etc. | 0 | 2 WRUAs 3 CFAs 4 Grazing Committees | 5 WRUAs 6 CFAs 9 grazing Committees | Four (4) Community groups capacity strengthened i. Namanga CFA ii. Enoosupukia CFA (41 participants), iii. WRUA in Kajiado (124 participants) Iv. Kitikini WRUA | 2 WRUA 2 CFAs 1 Grass bank committee Identification of the remaining groups have been done | HS (Highly Satisfactory) This is because the target was to strengthen 20 institutions over the project period, and five institutions were achieved within the first year. This represents 100% achievement of the planned annual milestone, demonstrating strong early performance and effective delivery. However, follow-up after the trainings has not yet been undertaken to assess how the institutions are applying the new skills and knowledge. Measuring the impact of these capacity-building efforts will be important in subsequent years to validate sustainability and effectiveness. 100% |
| Outputs (Copy and paste outputs from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Implementation status (%) |
| Output 1.1.1 : Gender-sensitive local community organizational capacity strengthened (Community Forest Associations, Conservancies, River Users Associations) to implement land and resources management plans | Number of organizations strengthened Number of organization/group members (at least 35% female) given knowledge or skills in areas related to Sustainable Land and Natural Resources Management and governance (disaggregated by Type of Organizations). | 0 | 5 institutions 1000(700M, 350 W) | 10 2,000 (1,400m, 700f) | 3 organizations strengthened i. Meeyu Milk Cooperative (45 members. Women 100%) ii. 1 Grass bank. 40 community members trained (100% women) iii. Oldonyorok Youth group (45 members. 35 males, 15 female) iv Ewangan Baptist Women group (40 members) v Oldonyo orok Youth Self Help group (50) But no segregated into gender | 3 organizations strengthened 100 Women trained 35 Men trained 50 youth trained | Moderately Satisfactory (MS), 69%. Organizations strengthened: 100% (Satisfactory). Target fully achieved, showing strong progress in institutional strengthening and gender-responsive engagement. Members trained: 185/500 = 37% Moderately Unsatisfactory Training reached fewer than half of the intended participants for the year. |
| Output 1.1.2: The capacity of County Environment Committees (CECs) in Narok and Kajiado strengthened to implement sub-county restoration plans for natural resources including high conservation value forest (HCVF) areas particularly Loita, Namanga 1, suswa and Olkiramatian/Shompole forest. | Number of County Environment Committees (CECs) strengthened to for implementation County or Cub- County restoration plans | 2 | 1 | 2 | 2 CECs trained Narok county government CEC term in office expired and a new CEC was appointed which will be trained this financial year | 2 CEC Trained. | Highly Satisfactory 100% Exceeded the reporting period target and met endline early. Both counties were trained, however, Narok has new CEC members who still require training to sustain institutional capacity. The training supported the Kajiado County Executive Committee (CEC) in developing the County Environment Action Plan, The PMU is planning to have a follow up meeting subsequent year so as to measure the impact of that training on the members. |
| Output 1.1.3: Financial resource allocation increased at the Local level to support sustainable land management | Number of Payment for ecosystem Services (PES) financing MoU implemented at community level | Baseline assessment was conducted to identify viable PES schemes, focusing on water regulation, biodiversity conservation, carbon sequestration, and soil erosion control | 2 | 3 | The PES baseline was completed, and one scheme on water regulation has been identified for negotiation and subsequent MoU signing. | One PES scheme has been identified and is currently under implementation | Moderately Satisfactory (MS) 50% The project successfully identified a PES scheme and completed negotiations, demonstrating solid progress in laying the foundation for PES as a financing mechanism. However, the MoU has not yet been signed, meaning the scheme is not fully operational. This partial delivery reflects the time intensive nature of stakeholder engagement and negotiation. |
| Narrative Report Objective 2: To improve effective governance of land resources through strengthening of community level organizations, National and County governments Outcome 1.1: Governance, institutions and community capacity for sustainable land management is strengthened During the reporting period (01/07/2024 – 30/06/2025), the project made significant strides in strengthening governance and institutional capacity for sustainable land management. Out of the 20 institutions targeted for strengthening over the life of the project, five were reached in the first year. This achievement represents 100% of the annual milestone, reflecting strong delivery and highly satisfactory progress. The institutions supported included two Water Resource Users Associations (WRUAs), two Community Forest Associations (CFAs), and one Grazing Committee. Capacity-building sessions reached a total of 165 participants across these groups, with active involvement of both men and women. While these results are highly encouraging, follow-up assessments on how the groups are applying the acquired skills are yet to be conducted. Such follow-ups will be essential in subsequent years to measure the sustainability and impact of the interventions. Output 1.1.1: Gender-sensitive local community organizational capacity strengthened The project supported the strengthening of three organizations during the reporting year: Meeyu Milk Cooperative (composed entirely of women members), a Grass Bank (40 women trained), and Oldonyorok Youth Group (with 35 male and 15 female participants). In total, 100 women, 35 men, and 50 youth were trained in sustainable land and natural resource management practices. Output 1.1.2: Capacity of County Environment Committees (CECs) strengthened Both County Environment Committees (CECs) in Kajiado and Narok were trained during the reporting year, surpassing the annual target and achieving the endline target earlier than planned. In Kajiado, the training directly supported the development of the County Environment Action Plan, enhancing the county’s ability to implement restoration and conservation initiatives. In Narok, while the CEC was successfully trained, a new committee was later appointed following the expiry of the previous term. The new members are scheduled to undergo training in the next financial year to sustain institutional capacity. This output is rated Highly Satisfactory (100%), since the project not only exceeded its annual target but also met the end-of-project target early, demonstrating efficient and timely delivery. Output 1.1.3: Financial resource allocation through Payment for Ecosystem Services (PES) schemes The project successfully identified a PES scheme and completed negotiations, demonstrating solid progress in laying the foundation for PES as a financing mechanism. However, the MoU has not yet been signed, meaning the scheme is not fully operational. This partial delivery reflects the time intensive nature of stakeholder engagement and negotiation |  |  |  |  |  |  |  |

| Outcome 2.1: Restoration and sustainable integrated land use management actions are implemented |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes (Copy and paste outcomes from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Progress rating (HS, S,MS,MU,U,SU) |
| Outcome 2.1: Restoration and sustainable integrated land use management actions are implemented | Area (Ha) under restoration and sustainable management in the target landscapes • Increase in number of households with improved access to water | 600,000 Ha | 300,000 Ha | 600,000 Ha | 592,911 ha identified for restoration; 65.4 ha under actual restoration, water and livelihood interventions implemented,385 community members engaged | The cumulative result to date aligns with the periodic result, as restoration activities under this output were only initiated in January 2025 by KARLO | Satisfactory (S) 43.6% Even though the percentage is very small, this is expected in the first year as activities focused on mapping, site identification, and piloting restoration interventions. The groundwork lays a strong foundation for scaling up in the following years. (The % is calculated as 65.4 ha(Achievement so far) divide by 150 ha(Target for the R.period) the multiply by 100= 43.6% |
| Outputs (Copy and paste outputs from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Implementation status (%) |
| Output 2.1.1: Rangeland restoration sites identified through detailed gender-responsive landscape restoration opportunity assessment mapping | Coverage (Ha) of sites/areas identified for restoration activities | 62,000 Ha | 62,000 Ha | 62,000 Ha | 552, 911 Ha have been identified (ROAM across 13 wards mapped 592,911 ha (target 62,000 ha in the Result Framework), establishing the baseline on extent and type of degradation. This nine-fold overachievement provides a strong evidence base to guide the project’s 600,000 ha restoration target) | 592,911 ha Restoration sites identified (ROAM) | HS (Highly Satisfactory) 100% The identification of 552,911 ha, well above the planned 62,000 ha, demonstrates strong early performance and establishes a robust foundation for actual restoration activities in the coming years. |
| Output 2.1.2: Participatory and gender-responsive forest and rangeland landscape restoration investment action plans developed | Percentage (%) of women actively involved in the development of landscape restoration planning Process | 0 | 20% | 40% | During the reporting period a total of 387 community members participated in restoration planning process Total 387 M=207 (53%) F=180(47%) Three (3) gender-responsive actions on Grass hay and seed production: - Naboisho Women Tikoshi in Kajiado Central with 28 members comprising 22 (79%) female and 6 (21%) men - Emurua Women Oldaraja in Kajiado Central comprising 24 all-female members - Nailepu SHG in Narok East with 33members comprising 21 (64%) females and 12 (36%) males Total F = 47, M = 12 Overall: 79% female, 21% male - Kona Maziwa (8 M / 3 F) - Namanga (6 M / 0 F) - Oldonyo Orok Youth Office (4 M / 2 F) - County Env. Offices (1 M / 3 F) - Kimelok (6 M / 7 F) - Narosura (7 M / 2 F) - Loita (10 M / 2 F) - Suswa (8 M / 4 F) - Noonchuta Women Group (5 M / 7 F) - Namanga CFA (12 M / 8 F) - Oldonyo Orok WRUA (14 M / 5 F) - Oldonyo Orok Youth Group (11M/ 5 F) - Enkakenya Sidai (6 M / 4 F) - Ramat SHG (6 M / 5 F) - Olonkishu Women Group (12 F) - Olkiramatian Community Land (6 M / 4 F) - Entasopia WRUA (6M / 4 F) - Empaash Conservancy (5 M / 4 F) - Shompole Conservancy (7 M/ 3F) - Olkeri Community Land (9M / 2F) - Nasila Women Group (1 M / 20 F) - Pakase WRUA (5M / 2F) - Kwenia Conservancy (7M 3F) - LoNaMo CBO (0M / 5F) - Eramatare SHG (4M / 2F) - Kitilikini WRUA (8M / 1 F) - Mosiro CBO (10 M / 9 F) - Narosura WRUA (4 M / 5 F) - Entashata CBO (2 M / 0 F) - Siyapei WRUA (-) - Loita CBO (8M / 10F) Total 319 (186 Male / 133 Female) | During the reporting period a total of 387 community members participated in restoration planning process Total 387 M = 207 (53%) F = 180 (47%) | Satisfactory (S) – 80% The project exceeded its targets on the number of restorations plans and women’s participation, demonstrating strong inclusivity and planning achievements. While the area restored is minimal compared to the target, critical foundations were laid through training, community mobilization, and consolidation of restoration technologies. These actions provide a solid base for larger-scale implementation in subsequent years. Total = 387 M = 207 (53%) F = 180 (47%) Four restoration action plans developed through a participatory and gender responsive process with restoration activities initiated in 65.4 Ha During the reporting period, the project has established grazing plans/systems and traditional land use practices in 5 different sites 1. Nooganayio – 899 Ha 2. Maparasha – 809 ha 3.loita Olosidan – 161.9 Ha 4. Entashata – 647.7 Ha Total 2,427.6 Ha against a target of 5000 Ha |
|  | Number of restoration action plans developed through a participatory and gender responsive | 0 | 3 restoration action plans | 5 restoration action plans | 4 restoration action plans developed. 85 farmers including 67 females and 18 males were trained on pasture establishment 65.4 Ha were for pasture and seed production. | 4 restoration plans 65.4 Ha on pasture development 85 farmers including 67 females and 18 males were trained on pasture establishment 385 direct beneficiaries - Female 152 Male - 233) 39% women |  |
|  | Area under communal natural resources management/restoration plans | 0 | 10,000 Ha | 20,000 Ha | During the reporting period, the project has established grazing management plans/systems and traditional land use practices in 5 different sites 1. Nooganayio – 899 Ha 2. Maparasha – 809 ha 3.loita Olosidan – 161.9 Ha 4. Entashata – 647.7 Ha Total 2,427.6 Ha | During the reporting period, the project has established grazing plans/systems and traditional land use practices in 5 different sites 1. Nooganayio – 899 Ha 2. Maparasha – 809 ha 3.loita Olosidan – 161.9 Ha 4. Entashata – 647.7 Ha Total 2,427.6 Ha |  |
| Output 2.1.3: Rangeland rehabilitation and management techniques/actions implemented | Area under restoration and conservation management activities (disaggregated by ‘’Type of Activity e.g. grass/pasture, gully restoration, removal of invasive species, tree planting, improved grazing plan) • Area of communal rangeland under improved livestock management regime Number of people trained in rangeland rehabilitation and management techniques disaggregated by Gender Number of gender-sensitive irrigation and water management schemes for crop and fodder production and dry season grazing developed | 0 0 0 0 | 300,00 Ha 60,000 Ha under improved communal livestock management 1000 (People (at least 20% female) 2 schemes | 600,000 Ha 120,000 Ha 2,000 People (at least 40% female) 5 schemes | 600,000 tree seedlings established 5.6 hectares of land were planted with African fox tail, bush rye, Horse tail and Maasai love grass varieties (3.6 in Kajiado & 2 in Narok). - Two (2) grazing management plans for Kajiado county done, drafting of 2 more in Narok County commenced. - 300 community members including 85 females and 215 males directly benefiting from the activity Agroforestry gardens Six (6) agro-forestry gardens successfully established with1,570 and 6,140 seedlings including fruit and fodder covering 37 hectares have been planted in Kajiado and Narok, respectively. Survival rate of the seedlings in the - gardens averages 85%/ Six (6) initial trainings i.e. one for each agroforestry group covering the planting and care for the seedlings were conducted Grass seeds(Types) banks A 10 hectares field planted and weeding done in Ole Serian village, Mile 46, Kajiado West, Kajiado County. In Narok county, 2.4 hectares planted in Olepolos village, Oloshaiki location, Naroosura, Narok South Trees planting In the two counties, a total of 8,900 seedlings were distributed and planted expected to cover about 16 hectares. A survival rate of 70% was realized owing to early cessation of the rains resulting in death of some of the seedlings especially in Kajiado County Eramarate Cooperative raised 300,000 tree seedlings, with 190,000 tubes potted and over 170,000 pricked out by 43 members (27 women). In Kajiado. Three more community groups Noonchuta Women Group, Olteyani Conservation CBO, and Oldonyo Orok Youth SHG for alternative livelihoods, including tree nurseries and beekeeping. 100 Langstroth beehives supplied to one community cooperative The activity was not planned for this reporting period. It will be done in the next reporting period. The activity was not planned for this reporting period. It will be done in the next reporting period The activity was not planned for this reporting period. It will be done in the next reporting period | Four (4) tree nurseries established ansu plied with materials and equipment’s 600,000 seedlings established 65.4 Ha under restoration and conservation management 100 Langstroth Beehives Delivered - - - | Moderately Unsatisfactory (MU), 21.8% Achieved 65.4 ha against the annual target of 300 ha, with strong groundwork in training, nursery establishment, and seedling planting, laying a solid foundation for scaling up restoration activities. So even though the numeric % of land restored is low, the quality and breadth of activities justify a Satisfactory rating for the first year of implementation, as these early steps are critical for long-term success. - - - |
| Output 2.1.4: Water access for communities and livestock is improved | Increase in the number of natural swaps restored, water pans in right locations and water harvesting structures | 0 | 25% increase in water harvesting structures | 50% increase in water harvesting structures | Baseline study to identify areas for community water projects and schools was completed Assessment to identify degraded natural wetlands/swamps was completed and 2 selected for protection. Rain water harvesting technologies established in 5 Schools each receiving a 50M3 water tank constructed and completed The tanks will support over 2000 pupils and communities | Baseline done Areas for establishing water harvesting technologies for community and livestock done Assessment and identification of wetlands for protection | Satisfactory (S), 100% Baseline studies and site assessments were completed, two degraded wetlands identified for protection, and rainwater harvesting structures installed in five schools (50 m³ tanks each), benefiting over 2,000 pupils and surrounding communities. |
| Output 2.1.5: Human / Wildlife conflicts are mitigated | Decrease in the number of elephant infestation reports/conflict cases reported to the conservancy or KWS • Decrease in the number of livestock killed by big cats | 0 | 22.5% | 45% decrease in HWC | 30 officers were recruited in Shompole (14), Mosiro (6), Musenke (3), Olorte (5) | 30 community scouts recruited, stablishing the operational capacity to monitor and respond to HWC at community level. This is an important structural achievement that enables future reductions in conflict. | Moderately Satisfactory (MS) 30 community scouts were recruited across Shompole (14), Mosiro (6), Musenke (3), and Olorte. |
| Narrative Report: Objective 3: Implementation of local resource management and restoration plans by community units and local authorities Outcome 2.1: Restoration and sustainable integrated land use management actions are implemented In the first reporting year, the project focused on establishing the evidence base and piloting restoration. A total of 592,911 ha was identified for restoration through ROAM, far surpassing the 62,000-ha target, thus providing a comprehensive baseline for guiding the 600,000-ha project goal. Out of this, 65.4 ha were restored through pasture reseeding, agroforestry gardens, tree planting, and grass seed banks. Restoration was closely linked to livelihoods, with 385 community members engaged and 2,000 pupils and surrounding communities benefitting from improved water access. While the proportion of land restored is still small, this was expected in Year 1 as activities focused on mapping, planning, and piloting. Output 2.1.1: ROAM identified 592,911 ha against a target of 62,000 ha, a nine-fold overachievement that established a solid evidence base for scaling restoration. Output 2.1.2: Four restoration action plans were developed against three planned, with 39% women participation and 8 ha piloted for pasture production. The process was inclusive and technically sound, laying strong groundwork for expansion. Output 2.1.3: Restoration was initiated on 65.4 ha, supported by 600,000 seedlings, four nurseries, six agroforestry gardens (37 ha), and 100 beehives for alternative livelihoods. Although the area restored is below the 100-ha target, the breadth of activities demonstrates significant groundwork. Output 2.1.4: A baseline study identified priority sites for water, with two wetlands selected for protection and five schools equipped with 50 m³ rainwater tanks, benefiting over 2,000 pupils and communities Output 2.1.5: 30 community scouts were recruited and trained to monitor and respond to human–wildlife conflict. While reductions in conflict are yet to be measured, the structures for long-term mitigation are now in place. |  |  |  |  |  |  |  |

| Outcome2.2: Sustainable investments in resilient livelihood actions are increased |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes | Indicators | Baseline | Midterm Target | End of project Target |  | Periodic Results (01/07/2024-30/06/2025) | Result to Date (from project start) | Progress rating (HS, S,MS,MU,U,SU) |
| 2.2 | % Increase of no. of men and women employed in livestock tourism and energy sector in the project area. | 0 | 1000 | 45% (20% men and 25% women) |  | The activity was not planned for this reporting period. It will be done in the next reporting period. | - | - |
| Outputs | Indicators | Baseline | Midterm Target | End of project Target |  | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Implementation status (%) |
| 1.Output 2.2.1: Mechanism on sustainable offtake with private processors and export off-takers markets established | Number of mechanisms established and functioning (disaggregated by “Type of Mechanism”e.g community enterprises, producer groups, IGAs, Milk processing units, revolving/Net funds, grass seed banks, grazing plans etc.) • Number of farmers/pastoralists accessing project supported extension services disaggregated bygender • Number of conservation agreements signed | 0 | 2 | 5 Mechanisms 40,000 households (at least 40% female) 13 (1 for each group ranch) |  | The activity was not planned for this reporting period. It will be done in the next reporting period. | - | - |
| 2.Output 2.2.2: Gender sensitive investments in clean energy that reduces households’ dependency on biomass energy is made | Number of clean energy demonstration centres established Number of community members trained on clean energy technologies through the demonstration centres promoted by the project. | 0 | 5 Demonstration centres established 500 people trained |  | 10 centres 1000 (70% female) | 3 sites identified for establishment of clean energy centres Enkakenya Sidai showcased traditional energy-saving jikos, beadworks done by the women and beekeeping products (honey) The project organized for a clean energy exhibition in Kajiado county. A total of 9 exhibitors showcased different local innovations on green energy. Notably two (2) women community groups showcased the promotion of clean energy solutions through innovative local briquette production (Lamaratak Self-help Group) community groups showcased the promotion of clean energy solutions through innovative local briquette production (Lamaratak Self-help Group) At least 120 people were sensitized comprising of representation from the County Government, Community Members, University students, Exhibitors and NEMA staff. | 3 sites identified in Kajiado as clean energy demonstration 120 community members trained on clean energy technologies 150 community members engaged for establishment of a demonstration centre (43 men and 107 women) | Satisfactory (S) – 70% 3sites identified in Kajiado for clean energy demonstration centers (exceeding target of 2 sites identified, though not yet equipped). 1 clean energy exhibition in Kajiado County with 9 exhibitors, including 2 women-led groups (Lamaratak Self-help Group – briquettes; Enkakenya Sidai Women Initiative – energy-saving stoves, beadwork, honey). 120 people trained/sensitized on clean energy technologies (48% of target). 150 people mobilized for future demonstration centres (71% women: 107 women, 43 men). |
| 3.Output 2.2.3: Market-based climate insurance and risk transfer schemes developed to scale up disaster risk and exposure reduction mechanisms for livestock and agriculture production | Number of households with increased resilience to drought disaster on crops and livestock • Increase in the number of farmers with insurance for their livestock or crops (disaggregated by gender) • Numbers of pastoralists signed up for IBLI | 0 | 25% increase in (15% men and 20% women) | 45% increase (20% increase for men and 25% increase for women) |  | The activity was not planned for this reporting period. It will be done in the next reporting period | - | - |
| 4.Output 2.2.4: Community-private sector ecotourism investment partnerships are developed and signed | Number of partnerships established and effectively promoting ecotourism investment in the target area • Number of Community-Private sector ecotourism investments developed | 0 | 2 Partnerships 5 Community- Private sector ecotourism investments | 3 Partnerships 10 Community- Private sector ecotourism investments |  | The activity was not planned for this reporting period. It will be done in the next reporting period | - | - |
| 5.. Output 2.2.5: Impact investment funds are developed to promote commercially viable forestry and agroforestry practices | Number of revolving funds established | 0 | 1 revolving fund | 1 revolving fund |  | The activity was not planned for this reporting period. It will be done in the next reporting period | - | - |
| Narrative Report for Objective 1: To develop community enterprises and livelihood value chains based on sustainable use of natural resources in the drylands During the reporting period (01/07/2024 – 30/06/2025), progress under Objective 1 focused on laying the foundation for resilient community enterprises and livelihood value chains, with notable achievements in awareness creation, stakeholder engagement, and early-stage implementation of clean energy and insurance interventions. While some activities were not planned for this reporting period. It will be done in the next reporting period, important groundwork has been established, particularly around gender-sensitive clean energy investments and preparatory activities for climate insurance schemes. Outcome2.2: Sustainable investments in resilient livelihood actions are increased At outcome level, employment opportunities in livestock, tourism, and clean energy sectors were yet to be realized during the reporting period. Activities directly contributing to job creation are planned for the subsequent financial year. Nonetheless, community-level mobilization, sensitization, and demonstration activities have raised awareness and built interest among targeted beneficiaries, setting the stage for effective implementation and achievement of midterm targets. Output 2.2.1: Mechanism on sustainable offtake with private processors and export off-takers markets established The output has not been planned for this reporting period; it will be done in the next reporting period. However, consultations held with county governments and producer groups during broader project activities indicate readiness and willingness of pastoralist groups to participate in structured market offtake mechanisms. This points to strong potential for uptake once mechanisms are developed. Output 2.2.2: Gender-sensitive investments in clean energy that reduce household dependency on biomass energy are made This output achieved tangible progress during the reporting period. A major milestone was the clean energy exhibition organized in Kajiado County, where nine exhibitors showcased diverse local innovations on green energy. Notably, women-led groups such as the Lamaratak Self-Help Group demonstrated briquette production using locally available materials, while the Enkakenya Sidai Women Initiative (comprising 300 groups) showcased energy-saving stoves, beadwork, and beekeeping products. These activities highlighted both the entrepreneurial potential of women in the clean energy value chain and the multiple co-benefits for household livelihoods. In addition, three sites were identified for establishment of clean energy demonstration centres, with 120 community members sensitized on clean energy technologies, including county government officials, students, and community groups. Furthermore, 150 community members (43 men and 107 women) were mobilized towards the establishment of demonstration centres, reflecting strong gender inclusivity and community ownership. Overall, these efforts have enhanced community awareness of alternative energy solutions, created linkages between innovators and users, and demonstrated early behavioral shifts towards reduced reliance on biomass fuels. Output 2.2.3: Market-based climate insurance and risk transfer schemes developed to scale up disaster risk and exposure reduction mechanisms The output has not been planned for this reporting period; it will be done in the next reporting period. Output 2.2.4: Community-private sector ecotourism investment partnerships are developed and signed The output has not been planned for this reporting period; it will be done in the next reporting period. Output 2.2.5: Impact investment funds are developed to promote commercially viable forestry and agroforestry practices The output has not been planned for this reporting period; it will be done in the next reporting period. |  |  |  |  |  |  |  |  |

| Outcome 3.1: Sustainable landscape management actions are informed, coordinated and mainstreamed at county and national level |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes (Copy and paste outcomes from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Progress rating (HS, S,MS,MU,U,SU) |
| Outcome 3.1: Sustainable landscape management actions are informed, coordinated and mainstreamed at county and national level | Number of project management, coordination and (e.g. project management team, steering committee, implementing partners, PCU etc.) implementation mechanisms established and functioning effectively to deliver the project |  | 5 | 4 | 5 PSC- Project steering Committee PMU- Project Management unit PMT- Project Management Team TC- Project technical Committee SEAs- Sub-executing Agencies | 5 | Satisfactory 100% |
| Outputs (Copy and paste outputs from Result Framework) | Indicators | Baseline | Midterm Target | End of project Target | Periodic Result (01/07/2024-30/06/2025) | Result to Date (from project start) | Implementation status (%) |
| Output 3.1.1: Functional landscape-level information system for improved planning and management of dryland resources established | Monitoring, Evaluation, Learning and Reporting systems developed and operationalized at project, county and community levels. | 1 | 1 | 1 | 1 M&S System developed | 1 M&S System developed | Satisfactory 100% |
| Output 3.1.2: Gender responsive localized drylands health, climate and biodiversity assessment tools developed and utilized | Number drylands health, climate and biodiversity assessment tools developed and. applied | 0 | 15 drylands health, climate and biodiversity assessment tools developed and applied | 30 drylands health, climate and biodiversity assessment tools developed and applied | The activity was not planned for this reporting period. It will be done in the next reporting period | - | - |
| Output 3.1.3: Project lessons are captured, evaluated and shared nationally and across countries and regions | Number of knowledge generation research studied carried out and disseminated. | 0 | 7 publications 2 Baselines | 15 publications 3 Baselines | 2 Publications 3 Baselines | Publications & Reports: -Rangelands Rising Magazine (special edition, July 2025 National Stakeholder Forum). -Communication & Knowledge Management (CKM) Assessment tools & National Rangeland Stakeholders Forum Recommendations Report (2025). 3 baselines (ROAM assessment, Institutional and governance and PES) | Highly Satisfactory 100% The target during this reporting period was develop 2 publications and 3 Baselines namely: ROAM, Assessment of PES Frameworks and Institutional Governance which have been achieved. |
| Output 3.1.4: National and Eastern Africa policy dialogue on dryland restoration promoted through generation of evidence-based policy briefs and recommendations. | National and Eastern Africa policy dialogue on dryland restoration promoted through generation of evidence-based policy briefs and recommendations. | 3 policy papers 15 Number of knowledge or communication products/outputs developed and shared through various channels/means | 2 Policy papers 6 Number of knowledge or communication products | 3 Policy papers 15 Number of knowledge or communication products | Held 1 National GEF 7 SFM forum. Knowledge Products -CRC and Green Points posters and brochures. -Case studies on water harvesting, tree nurseries, and community grazing frameworks to be compiled and disseminated -Knowledge management tools/log books purchased shared with communities and members trained on how to capture knowledge Digital & Online Platforms -Social media: Twitter/X (#GEF7Kenya, #RangelandForum2025). -Online presence: Project materials featured on IUCN, NEMA, and ACC websites. -Digital repository: Google Drive/SharePoint hub for storing and sharing project resources. Audio-Visual Materials -Short documentaries on community impact (water harvesting, hay making were produced. Green -Local FM radio talk shows on biodiversity and forest management. Media Coverage -National newspaper coverage of the July 2025 National Stakeholder Forum. -Feature stories on women-led nurseries and youth-led grazing management practices. | 1 National GEF 7 SFM forum. 3 Knowledge Products, 3 Digital & Online Platforms, 2 Audio-Visual Materials, 2 Media Coverage,1 Magazine. |  |
| Narrative report Objective 4: To coordinate the management of an integrated dryland landscapes knowledge exchange and management platform Outcome 3.1: Sustainable landscape management actions are informed, coordinated, and mainstreamed at county and national level During the reporting period, the project made notable progress in strengthening coordination, monitoring, and knowledge-sharing systems for dryland restoration. Output 3.1.1: Functional landscape-level information system for improved planning and management of dryland resources established A key milestone was the development and operationalization of a Monitoring, Evaluation, and Learning (MEL) system at the project, county, and community levels. This system now allows real-time tracking of restoration activities, water access, and rangeland management, consolidating data in a central platform. The achievement fully met the annual target, significantly enhancing evidence-based decision-making and planning capacity across institutions. Output 3.1.2: Gender-responsive localized drylands health, climate, and biodiversity assessment tools developed and utilized The development of these assessment tools was not scheduled for this reporting period and will be implemented in the coming year. Once developed, they will be critical for generating localized data to guide restoration and biodiversity management, ensuring that interventions remain gender-responsive and scientifically sound. Output 3.1.3: Project lessons are captured, evaluated, and shared nationally and across countries and regions The project achieved its annual target of two publications, producing the Rangelands Rising Magazine and the Communication & Knowledge Management (CKM) Assessment Report. Beyond publications. Output 3.1.4: National and Eastern Africa policy dialogue on dryland restoration promoted through evidence-based policy briefs and recommendations The project convened the National GEF-7 SFM Forum, which brought together stakeholders to deliberate on dryland restoration priorities and produced actionable recommendations. To complement this, communication products such as brochures and case study drafts were developed, while visibility was boosted through posters, online platforms, and media features. The first project magazine was finalized, and audiovisual materials documenting community innovations were produced. These actions laid the groundwork for stronger policy engagement, though formal policy briefs will be finalized in the next reporting period. |  |  |  |  |  |  |  |

GEF Core Indicators

Please report on GEF core indicators that are relevant to your project using guidance provided by GEF on the implementation of the GEF-8 results measurement framework

Table 1. Eleven GEF Core Program Indicators

| Indicator # As per GEF portal | Indicator | Baseline | Project Target | Progress to date (from project start) | Means of Verification |
| --- | --- | --- | --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management This indicator will be reported as the aggregate total of the following Sub-Indicators. - Terrestrial protected areas newly created - Terrestrial protected areas under improved management effectiveness | 502,911 Ha (Overall degraded land cover in conservancies, ranches, forests e.g., Empaash) | 600,000 Ha (50,000 Forest Land, 550,000 Grass Land Management) | ROAM Baseline assessment done through gender responsive (80% completed 502, 911 Ha of degraded areas identified Assessment of Instructional and Governance issues at community level done Procured restoration materials/tools. For communities Natural resource baseline ongoing (80% done) | Field surveys, ROAM Assessment, Procurement records |
| 2 | Marine protected areas created or under improved management This indicator will be reported as the aggregate total of the following Sub-Indicators. - Marine protected areas newly created - Marine protected areas under improved management effectiveness | 0 | 0 | 0 | 0 |
| 3 | Area of land and ecosystems under restoration This indicator will be reported as the aggregate total of the following Sub-Indicators. - Area of degraded agricultural lands under restoration - Area of forest and forest land under restoration - Area of natural grass and woodlands under restoration - Area of wetlands (including estuaries and mangroves) under restoration | ROAM baseline done and 502,911 Ha Overall Degraded Land Cover | 600,000 Ha for restoration. | Baseline assessments done 502,911 Ha identified as degraded for restoration The degraded areas are to be aggregated using Geomaps | Field Survey and Biodiversity Survey, Geospatial mapping |
| 4 | Area of landscapes under improved practices (excluding protected areas) This indicator will be reported as the aggregate total of the following Sub-Indicators. - Area of landscapes under improved management to benefit biodiversity - Area of landscapes under third-party certification incorporating biodiversity considerations - Area of landscapes under sustainable land management in production systems - Area of High Conservation Value or other forest loss avoided - Terrestrial OECMs supported | 600,000 Ha | 600,000 Ha | ROAM baseline complete, 65.4 Ha under restoration/conservation, 6 agroforestry gardens established | Field surveys, ROAM assessment, project reports |
| 5 | Area of marine habitat under improved practices to benefit biodiversity This indicator will be reported as the aggregate total of the following Sub-Indicators. - Fisheries under third-party certification incorporating biodiversity considerations - Large Marine Ecosystems with reduced pollution and hypoxia - Marine OECMs supported | N/A |  |  |  |
| 6 | Greenhouse gas emissions mitigated This indicator will be reported through the following Sub-Indicators - Greenhouse gas emission mitigated in the AFOLU sector - Greenhouse gas emission mitigated outside of the AFOLU sector - Carbon sequestered or emissions avoided in the AFOLU sector (Direct) - Carbon sequestered or emissions avoided in the AFOLU sector (Indirect) - Emissions avoided outside AFOLU sector (Direct) - Emissions avoided outside AFOLU sector (Indirect) - Energy saved - Increase in installed renewable energy capacity per technology | N/A | To be determined. | Tree planting, agroforestry, clean energy demos started, carbon sequestration not yet quantified. Partial contribution through tree planting (600,000 seedlings), establishment of agroforestry gardens, clean energy demonstrations (briquettes, energy-saving jikos), but full carbon sequestration calculation pending | Field surveys, community records, energy project records |
| 7 | Shared water ecosystems under new or improved cooperative management This indicator will be reported through the following Sub-Indicators - Level of Regional Legal Agreements and Regional Management Institutions to support its implementation - Level of Transboundary Diagnostic Analysis and Strategic Action Program (TDA/SAP) formulation and implementation - Level of National/Local reforms and active participation of Inter-Ministerial Committees - Level of engagement in IW:LEARN through participation and delivery of key products | N/A |  |  |  |
| 8 | Globally over-exploited fisheries moved to more sustainable levels | N/A |  |  |  |
| 9 | Chemicals of global concern and their waste reduced This indicator will be reported through the following Sub-Indicators - Solid and liquid Persistent Organic Pollutants (POPs) removed or disposed (POPs type) - Quantity of mercury reduced - Hydrochlorofluorocarbons reduced/phased out - Countries with legislation and policy implemented to control chemicals and waste - Low-chemical/non-chemical systems implemented, particularly in food production, manufacturing and cities - POPs/Mercury containing materials and products directly avoided - Highly Hazardous Pesticides eliminated - Avoided residual plastic waste | N/A |  |  |  |
| 10 | Persistent organic pollutants to air reduced This indicator will be reported through the following Sub-Indicators - Countries with legislation and policy implemented to control emissions of POPs to air - Emission c ontrol technologies/practices implemented | N/A |  |  |  |
| 11 | People benefiting from GEF-financed investments This indicator will be reported as the aggregate total of the following Sub-Indicators. - Female - Male | 200,000 |  | 30,000 (based on direct engagement in clean energy, agroforestry, rangeland restoration, water harvesting, and community capacity-building activities) | Household surveys, community engagement reports |
| Key Achievements and Progress – Midterm Review (GEF Core Indicators) - Indicator 1 & 3: Substantial progress has been made in identifying degraded areas (ROAM assessment). Restoration activities have started with tree nurseries, agroforestry gardens, and rangeland rehabilitation, though actual restored area is still below target. - Indicator 4: Area under improved practices is growing, with agroforestry gardens and community-based land management plans being implemented. - Indicator 6: GHG mitigation is indirectly supported through afforestation, clean energy interventions, and reduced reliance on biomass, but quantification of emissions avoided is pending. - Indicator 11: 30,000 people have directly and indirectly benefited from project interventions (community trainings, restoration activities, clean energy demonstrations). Full target yet to be reached. |  |  |  |  |  |

# Adjustments

Please provide comments on delays during this reporting period in achieving any of the following key project milestones: inception workshop, mid-term review, terminal evaluation and/or project closure.

Delayed project launch by appx 12 months hindered timely commencement of activities. The financing agreement was signed in April 2023, towards the end of FY 2022/23. Consequently, the project budget could not be included in the FY 2023/24 estimates, as the budgeting process had already been concluded by the National Treasury. NEMA requested the Treasury to allow utilization of funds pending budget regularization, but was advised that funds could only be accessed through a supplementary budget process. This was finalized in December 2023, enabling NEMA to receive the first disbursement in January 2024. Further delays occurred as NEMA initiated negotiation for the subsidiary agreements with SEAs (KALRO, ACC, NETFUND, and SORALO), who were required to open dedicated project bank accounts before receiving funds. Some SEAs faced delays in account opening due to administrative procedures, such as Boards of Management sitting only once a quarter to approve financial decisions.

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines.

Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of the change that occurred in the textbox. You may attach supporting documents as appropriate within this PIR submission.

|  | Results framework |
| --- | --- |
|  | Components and cost |
| / | Institutional and implementation arrangements |
|  | Financial management |
| / | Implementation schedule |
|  | Executing Entity |
|  | Executing Entity Category |
|  | Minor project objective change |
|  | Safeguards |
|  | Risk analysis |
|  | Increase of GEF project financing up to 5% |
|  | Co-financing |
|  | Location of project activity |
|  | Other |

| Minor amendments | Change description |
| --- | --- |
| Results framework | No change |
| Components and cost | No change |
| Institutional and implementation arrangements | During the first year of implementation, adjustments were made to the Project Management Unit (PMU) following the exit of the Project Coordinator. A new Project Coordinator was appointed and officially assumed duties on June 2024 In addition, some project partners were dropped for various reasons. Meat Naturally was dropped due to the lack of a physical presence in Kenya, which was a requirement for partnership. ILRI withdrew after requesting a minimum budgetary allocation for specific activities, which the Executing Agency (EA) was unable to accommodate. The Nature Conservancy voluntarily withdrew before the project commenced. Notably, no subsidiary agreements had been signed with the institutions that exited. |
| Implementation schedule | Due to the challenges experienced during the first year of implementation, the project faced a delay of 12 months. While the original start date was scheduled for August 2023, aligned with the first disbursement of funds to the National Treasury, NEMA only received its first disbursement in January 2024. The project launch subsequently took place in June 2024, following the challenges already outlined. As a result, the original closure date of August 2027 based on the initial disbursement timeline may need to be revised to August 2028. This extension would allow the project to recover the lost time and ensure that all objectives are achieved successfully. |
| Executing entity | No change |
| Executing entity category | No change |
| Minor project objectives | No change |
| Safeguards | No change |
| Risks | During the implementation of this activity, the project engaged communities in areas affected by human–wildlife conflict (HWC), particularly predation by big cats such as lions. The communities expressed a preference for engaging community youth helpers (Ilaretok) instead of installing solar deterrent lights. They highlighted several reasons for this choice: Fixed and limited coverage: solar lights are static and only protect a small area. Energy concerns: prolonged use may lead to unnecessary power wastage. Social inequality: only families who can afford the lights benefit, leaving vulnerable households at greater risk of attack. Seasonal predation patterns: predator activity varies, making mobile and responsive strategies more effective than static lights. Wildlife conservation: trained youth can track and monitor lions, giving early warnings that reduce retaliatory killings of wildlife. The community emphasized that engaging Ilaretok youth is more sustainable, reliable, effective, and efficient in mitigating conflicts with big cats. Their role includes: - Monitoring wildlife movements. - Conducting patrols in the morning and evening. - Providing reliable feedback on predator locations. - Setting up mobile camps to enhance vigilance. - Sharing safety information with community members. - Timely reporting of incidents. - Supporting participatory rangeland resource management. This approach strengthens both human safety and lion conservation, while fostering community ownership in managing rangeland resources. |
| Increased GEF financing up to 5% | No change |
| Co-financing | No change |
| Location of project activity | No change |
| Other | None |

# Implementation Progress

Please insert graph below showing cumulative disbursements on quarterly and yearly basis since project launch

| Cumulative Disbursements |  |
| --- | --- |
| Cumulative general ledger delivery against total approved amount (in Project Document) - % | 25% |
| Cumulative general ledger delivery against expected delivery as of this year - % | 88% |
| Cumulative disbursement as of 30 June 2025 (note: amount to be updated in later August) | USD 878,188 |

| Key Financing Amounts |  |
| --- | --- |
| PPG Amount | USD 150,000 |
| GEF Grant Amount | USD 5,354,588 |
| Planned Co-Financing Co-Financing to date | USD 2,071,320 1,533,056 |

| Key Project Dates |  |
| --- | --- |
| PIF Approval Date | 23rd October 2019 |
| CEO Endorsement Date | 11th June 2021 |
| Project Document Signature Date (Project start date) | 23rd June 2023 |
| Date of Inception workshop date | 20th FEB 2024 |
| Project launch date | 7th June 2024 |
| Expected date of mid-term review | August 2026 |
| Actual date of mid-term review | TBD |
| Expected date of Terminal Evaluation | January 2027 |
| Original planned closing date | June 2027 |
| Revised Planned closing date | June 2029 |

Dates of Project Steering Committee / Board Meetings during reporting period (June to July)

13th August 2024

13th August 2024

12TH March, 2025

21st May 2025

# Critical Risk Management

Please complete the table below (Only risk with High or Medium rating / level should be recorded) by using the information in the Project Risk register (excel file provided with PIR templates). If a project risk register has already been completed for the project, please provide any updates for High or Medium risk from this reporting period – e.g. changing in risk rating, risk owners or additional risk identified etc. in the table below.

| Risk Category | Risk description | Rating / Level (H, M) | Mitigation measures undertaken in this reporting period | Risk Owner | Updates / Changes |
| --- | --- | --- | --- | --- | --- |
| External | Climate variability (Short and minimal rain to sustain tree planting) | H | Measures put in place to establish drought-resistant tree species with site matching Use of other restoration approaches by considering climate change in project implementation designs | All | Measures put in place to establish drought-resistant tree species with site matching Use of other restoration approaches by considering climate change in project implementation designs |
| Financial | Inconsistency in financial disbursement with national government budgeting cycle The full annual allocation should be transferred in a single lumpsum to the National Treasury to reduce the processing cycle. Currently the project receives 50% of the annual budgets from the IA which is affecting implementations This amount is what the National Treasury allocates to the project as an annual budget. | H | A consultative meeting between the IE, EA & NT to be convene to address the risk and align the financial budgeting cycles The annual disbursement should be made in once to facilitate tangible outcomes on critical activities, such as restoration activities. | IE/AE | No change |
|  | Inconsistent and lengthy funds processing time from the IE to NT, Ministry of Environment then finally to AE | M | Fund disbursement to be fast-tracked once requested by AE | IE & EA | No change A consultative engagement between IE/AE/NT to be invoked |
| Operational | Delayed inception of and launch of the project | H | The project inception and launch were delayed due to the reasons cited above. I addition, new government administrative changes and also leadership changes in some of our SEA’s delayed opening of project accounts The project was launched on 7th June 2024 | The project is fast-tracking implementation of activities to try to recover the lost duration | Minimal change since the project is time based hence. The project has since delayed for a period of 12 months |
| Governance/Institutional | Stakeholder management | M | Manage expectations of various stakeholders (community and county governments) Continuous engagement at and consultation with communities and counties | EA | Significant change in managing expectations since the communities has well understood the project objectives and responsibilities of all players. The county government being part of the project leadership structures also have so far appreciated the project objectives and purpose |

Project overall risk rating (Low, Moderate, Substantial or High). Please see Annex – Ratings definition for guidance.

| 2023 rating (H, S, M, L) | 2024 rating (H, S, M, L) | Comments/reasons for the rating for 2023 and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| M | M | The project implementation is currently stable with substantial progress in actual activities and financial absorption highly improved as compared to 2023. However the risk identified under table C may affect the overall project risk rating at Moderate. |

# Gender

Progress in advancing Gender equality and women’s empowerment

Please note that all projects approved since GEF 6 are required to carry out a gender analysis and provide gender-responsive and where possible gender transformative measures to address differences, identified impacts and risks, and opportunities through a Gender Action Plan (GAP) or equivalent.

Does this project specifically target woman or girls as direct beneficiaries?

The project developed a Gender Action Plan, which is currently under implementation. Women and girls are directly targeted and actively involved in all project activities. A baseline assessment on Institutional and Governance was conducted, through which community groups were mapped and identified for participation in project implementation. Of the groups identified, 25% are women-only groups, while the remaining 75% all include women representation. In addition, the project has directly implemented restoration activities that strengthen women’s participation and benefits. These include seed and pasture development action plans for women-only groups, as well as capacity building and value chain enhancement in honey production. Women’s groups have been supported with the necessary tools, equipment, and technical expertise to improve their productivity and incomes. The project also adheres to the National Government’s two-thirds gender inclusion policy in all recognized committees, including the County Environment Committees, Water Resource User Associations, and Community Forest Associations

In case a gender analysis was not undertaken during project preparation (PPG), has it been carried out in this reporting period? If yes, what were the main findings? If an analysis during project design had been undertaken, but further updates have been carried out during the reporting period, please indicate this below. Please also report on additional site level gender analyses if they were undertaken during this reporting period.

A gender analysis was conducted during the project preparation phase (PPG), through which gender-related issues were assessed to enable their integration into project implementation. Building on this, the project finalized a Gender Action Plan (GAP) to guide the promotion of gender equality and equity across all project interventions. Although the gender analysis has not yet been updated, most of the issues identified during the PPG remain relevant and are currently being addressed through site-level implementation.

Please describe progress in implementing the Gender Action Plan (GAP); you could also add the GAP in form of a GAP progress report as annex. Please also specify results achieved during this reporting period through implementing gender-responsive measures. Results reported can include site level results working with local communities and municipal/ regional organizations as well as work to integrate gender considerations into national policies, strategies and planning. Please explain how the results reported addressed the different needs of men or women, improved norms, values and power structures, and/or contributed to transforming or challenging gender inequalities and discrimination.

- At the site level implementation, men, women and youth are actively involved and share equal opportunities and benefits derived from the project. - The project has identified community groups to work with at the site level in which 25% of the groups selected are women only membership. The 75% consist of both men, women and youth. - Key livelihood activities, such as pasture production and agroforestry, are being led and implemented by these women. - Additionally, the project has ensured meaningful participation of women even in mixed-gender groups, strengthening their leadership and engagement in restoration work. - Efforts have also been made to ensure that women in mixed-gender groups are not only present but actively involved in decision-making and implementation processes. - The project empowered women through alternative livelihood opportunities like tree nursery establishment and beekeeping, while also addressing climate vulnerabilities and nature-based solutions - The capacity building of these CBOs comprises of at least 35% % women - On integration of gender actions into policies measures, the project has actively considered national government policies such as the affirmative action on ⅔ gender rule - The deliberate gender actions taken and implemented has led to more inclusive and equitable decision-making processes for the community groups - Women empowerment has been realized since both women and men participate in leadership and responsibilities hence minimizing inequalities and discrimination - Gender consideration in the project has also demonstrated inclusive governance of resources and division of roles

Please report on gender-responsive indicators and gender-disaggregated targets as established in the results framework of the project

Please refer to the GAP in the Annexes

# Implementing the Stakeholder Engagement Plan

The GEF Stakeholder Engagement Policy Guidelines require that Agencies prepare a Stakeholder Engagement Plan to describe how Stakeholders will be engaged in the project specifying means of engagement throughout the project/program cycle. Agencies should include information on progress, challenges and outcomes of stakeholder engagement in the annual PIR.

Please either provide the Stakeholder Engagement Plan and its respective progress report as annex or complete the below table by specifying the engagement strategies and achievements for the most important stakeholder groups. This can include demonstrating how different stakeholders were engaged in decisions on project governance (e.g. as member of the steering group), in the management or monitoring of the project or in specific programmatic activities. Forms of engagement include direct consultation or exchange, or the obtaining of consent prior to carrying out activities, as well as indirect forms such as through media or other communication channels. Where relevant, explain whether further stakeholder mapping and analysis has been carried out. Please also specify how the engagement is documented to provide evidence of such activities.

Please note that the data may be used for reporting to the GEF or IUCN web site, and for other internal and external knowledge and learning efforts. It is critical that the SEP and documentation complies with the IUCN Data Protection Policy

All projects must complete this section. Please enter N/A in cells that are not applicable to your project.

Information on stakeholder engagement strategies, progress, outcomes and challenges

Local governments

The County governments of Kajiado and Narok are members of the National Steering Committee The county governments officers are members of the technical committee and are involved in all field activities Technical officers from the county governments are directly involved in project implementation at community level

Civil society organisations

The Sub-executing agencies (SEAs) are directly involved in project implementation Continuous consultations Signed Subsidiary agreements

Local communities (disaggregate where relevant)

Meeyu Milk Cooperative – 45 members, 100% women Grass Bank – 40 community members trained, 100% women Oldonyorok Youth Group – 45 members, 35 males and 15 females Ewangan Baptist Women Group – 40 members, all women Oldonyo Orok Youth Self Help Group – 50 members (Gender breakdown not provided) Eramarate Cooperative – 43 members, 27 women and 16 men Noonchuta Women Group – 36 members, women-only Olteyani Conservation CBO – 18 members, mixed membership, 12 women and 6 men Lamaratak Self-help Group – women-led, showcased briquettes at energy exhibition Enkakenya Sidai Women Initiative – women-led, promoted energy-saving stoves, beadwork, honey Kajiado WRUA (Water Resource Users Association) – 124 participants (gender not broken down) Kitikini WRUA – membership not disaggregated Total - 25% of all identified groups are women-only - 75% are mixed groups (men, women, youth)

Indigenous Peoples

Direct involvement in project implementation at community and national levels Community engagement meetings for decision making during activity planning at community level Involvement at county and national forums

Private sector

Participation in meetings such county and national forums Engagement on specific project activities

Other relevant stakeholders as identified in the projects’ stakeholder mapping and analysis

Media: involvement in project publicity at county and national levels Involvement in county and national forums

# Environmental and Social Safeguards

This section of the PIR describes the progress made towards implementing the Environmental and Social Management Plans or other safeguard tools, when appropriate. Note that this section only applies to projects classified as moderate or high risk, not to low-risk projects.

For reporting progress on the implementation of ESMS plans or tools, please either provide the ESMP Monitoring Table as annex (see ESMP guidance note and template) or complete the below table.

| Progress of implementing the Environmental and Social Management Plan (ESMP) or other safeguard tools |  |  |  |  |
| --- | --- | --- | --- | --- |
| Environmental and Social Risks | Risks identified by ESMS Screening or during any update of ESMP since project start | Actions taken during this FY; explain how you engaged with groups affected by the identified risks and the outcomes achieved |  | Are the measures considered sufficient? Are there any outstanding issues relevant for next FY? |
| Adverse gender-related impacts | No significant risk identified | The community groups selection followed the criteria stipulated in the ProDoc which provides a threshold for selection. Similarly, participatory assessment and community engagement to ensure vulnerable groups such as women and youths are strongly involved. The project also used the affirmative action’s measures enshrined in the Constitution of Kenya and institutional frameworks to prevent such risk from arising. |  | The control measures employed by the project to mitigate potential risks were highly effective. There are no outstanding issues As the project deep dive into implementation of restoration sub-projects, screening will be done to ensure compliance to all relevant regulations. |
| Risks of affecting vulnerable groups | No significant risk identified | To ensure that vulnerable groups are well represented, participatory assessment were used to guarantee that vulnerable groups are actively participating. In order to mitigate this risk, the project also made advantage of institutional structures and affirmative action policies established in the Kenyan Constitution. |  | The measures were effective and there are no outstanding issues or anticipated risk in this financial year |
| Risk of undermining human rights | No significant risk identified | The project did not experience and neither anticipate such risk to occur |  | The project shall observe and prevent any of such risks from occurring through the relevant |
| Community health, safety and security risks | No significant risk identified | There were no activities with major health and safety risk during the period |  | The project shall observe and prevent any of such risks from occurring through the relevant including undertaking screening and EIA for specific sub-projects in accordance with the provision of NEMA’s EIA regulations and other ESMS tools |
| Labour and working conditions | No significant risk identified | The project has continuously paid attention to the needs of various groups |  | There are no outstanding |
| Resource efficiency, pollution, wastes, chemicals | No significant risk identified | Even though there were no adverse risk experienced during the period under reporting, the project is being implemented in compliance with the provision of relevant national environmental policies such Environmental Management and Coordination Act, 1999. |  | There are no outstanding |
| New risks emerged | No new risk emerged |  |  |  |
| ESMS Standards | Required management measures/plans (when standard triggered) | Actions taken during this FY – for each safeguard plan, please indicate if actions are on schedule; explain how you engaged with groups affected by the identified risks and the outcomes achieved |  | Are the measures considered sufficient? Are there any outstanding issues relevant for next FY? |
| Involuntary Resettlement & Access Restrictions ☐ yes ☐ no ☐ TBD | ☐ Resettlement Action Plan ☐ Resettlement Policy Framework ☐ Action Plan to Mitigate Impacts Access Restriction ☐ Access Restrictions Mitigation Process Framework ☐ Other: | No risk identified hence no standard triggered during the reporting Observation of the existing national policies will be activated in case such risk are identified. |  | No adverse risk No outstanding issues |
| Indigenous Peoples ☐ yes ☐ no ☐ TBD | ☐ Indigenous Peoples Plan ☐ Indigenous Peoples Planning Framework ☐ Other: | No risk identified hence no standard triggered during the reporting |  | No adverse risk |
| Cultural Heritage ☐ yes ☐ no ☐ TBD | ☐ Chance Find Procedures ☐ Other: | No risk identified hence no standard triggered during the reporting |  | No adverse risk |
| Biodiversity & Sustainable Use Natural Resources ☐ yes ☐ no ☐ TBD | ☐ Pest Management Plan ☐ Other: | There was no any adverse risk identified. However, the Pest Control Products Act CAP 346, regulates the use of herbicides in the control and management of invasive species in case of any risk triggered Pest Management plan will also develop if there would be solid belief that there would be pest. |  | It is anticipated that the interventions funded by the project will improve biodiversity. The national laws regulate the risks associated with invasive species. As a precaution, the project will enlist professionals with the know-how or relevant connections to offer the required direction when carrying out associated activities. |
| ESMS Risk Category (as per ESMS Screening) |  |  | ☐ Low Risk ☐ Moderate Risk ☐ High Risk |  |
| Have findings during implementation triggered any changes to the ESMS Risk Category? If yes, explain the issues and justification for the new rating. |  |  | No |  |
| List all risk issues that are now rated as high risk (if any) |  |  | None |  |
| Has a list of relevant host country regulations on environmental and social matters been established? What is the status of the project’s compliance with the applicable laws and regulations? |  |  | Kenya has a comprehensive law on ESMS, Kenya’s Environmental and Social Management System (ESMS) is anchored in the Environmental Management and Coordination Act (EMCA, 1999, revised 2015), together with subsidiary regulations such as the Environmental (Impact Assessment and Audit) Regulations (2003) and the Environmental (Strategic Assessment, Integrated Impact Assessment and Audit) Regulations (2020) The project complies with these regulations in the event of any triggered risk during the project implementation |  |
| In case any changes of regulations have occurred since project design, have these changes been reflected in project implementation? |  |  | None |  |

Please indicate whether any grievances as per IUCN ESMS and GEF ESS policies have been received during this reporting period. If yes, please complete the below table. Also include grievances that had been received in earlier reporting periods which have not yet been closed. Note that anonymity and compliance with the IUCN Data Protection Policy (see footnote above) needs to be ensured.

| Grievance | Date of receipt | Action taken during this reporting period; has the grievance been addressed (closed)? | If grievance hasn’t been closed: describe actions planned for next FY | Has the grievance led to changes / improvement of project design / activities? |
| --- | --- | --- | --- | --- |
| Delayed payment of community | November 2024 | Payment was done after the EA received all supportive documents | Closed | No |

# Knowledge Management

Knowledge activities / products (when applicable), as outlined in Knowledge Management Approach approved at CEO Endorsement / Approval during this reporting period.

Does the project have a knowledge management strategy? How does the project collect, document and share good practices? Please list relevant good practices from this year that can be learned and shared from the project.

# Yes, the project has developed a Knowledge Management (KM) strategy, informed by the Communication & Knowledge Management (CKM) Assessment and complemented by the Communication and Visibility Plan. The KM approach emphasizes structured documentation, centralized repositories, and participatory knowledge-sharing mechanisms to strengthen forest management and climate resilience in the Southern Rangelands. # Knowledge Collection & Documentation Recommendations # Recommended Digital Repositories: Shared drives (Google Drive, OneDrive) to be widely used to store reports, presentations, and meeting notes. A centralized Knowledge Hub to be developed through SharePoint/Google Workspace for systematic archiving of research outputs, field reports, and lessons learned. # Recommended Monitoring and Data Systems: Tools such as Kobo Toolbox are to be identified for piloting for surveys and community-level data collection. ArcGIS and Google Earth Engine are recommended for use for real-time spatial monitoring of forest and rangeland cover. # Collaborative Platforms: Platforms such as Zoom, Microsoft Teams, WhatsApp groups, and physical workshops were recommended to enable timely exchange of lessons and facilitated engagement between field teams, counties, and national actors. # Recommend Knowledge Sharing & Good Practices # Storytelling approaches and multilingual WhatsApp broadcasts were successfully used to include grassroots actors, ensuring knowledge reached diverse audiences across the counties. # Integration of spatial data tools (ArcGIS, Earth Engine) enhanced decision-making and provided strong evidence for county-level restoration planning. # Quarterly training workshops were conducted, building stakeholder proficiency in CKM tools and fostering a stronger information-sharing culture. # Community water harvesting and tree nursery initiatives were documented and shared as practical models for scaling across other counties.

Does the project have a communication strategy? Please provide a brief overview of the communications successes and challenges this year.

# Yes, the project has a Communication Plan and Visibility Plan as part of the communication strategy that complements the KM framework. The primary goal is to raise awareness, educate communities, and encourage active participation in Green Points and Community Resource Centres (CRCs). # Specifically, the strategy seeks to: # Improve access to CRCs as hubs for knowledge exchange and resource accessibility. # Increase awareness of sustainable forest management, biodiversity conservation, and # climate resilience. - Strengthen stakeholder engagement across government, NGOs, private sector, and community partners. - Encourage community participation in restoration and rangeland governance # activities. # Communication Successes this Year: # Green Points and CRCs visibility campaigns: Posters, infographics, and radio messages have been drafted and they will encourage community use of CRCs for learning and resource access. # Community education drives: Newsletters, workshops, and reports have been recommended to promote awareness of forest conservation and biodiversity. # Stakeholder engagement platforms: National and county forums fostered dialogue and collaboration, particularly the July 2025 National Stakeholder Forum in Nairobi. # Social media outreach: were actively used, supported by consistent hashtags (#GEF7Kenya, #RangelandForum2025). # Media coverage: Print and broadcast coverage of the National Stakeholder Forum amplified project visibility. # Challenges: # Uneven reach of communication channels, with rural communities facing barriers in accessing online content. # Limited multilingual communication, with English-only outputs excluding some grassroots groups. # Bureaucratic delays affecting timely sharing of project updates. # Underutilization of newsletters and dashboards due to lack of training and incentives. # Limited budget for continuous media engagement. # The project is addressing these by developing multilingual materials, rolling out structured communication protocols, training partners on digital tools (Hootsuite, Mailchimp, Trello), and expanding impact measurement through Power BI/Tableau dashboards.

Communication material

Please provide a list of publications, project website, project page on the IUCN website, any other facebook, twitter, flickr or youtube account related to the project, as well as hyperlinks to any media coverage of the project, for example stories written by an outside source. Please upload any supporting files, including photos, videos, stories, and other documents.

- Publications & Reports - Rangelands Rising Magazine (special edition, July 2025 National Stakeholder Forum). - Communication & Knowledge Management (CKM) Assessment & Recommendations Report (2025). - Knowledge Products - CRC and Green Points posters and brochures. - Case studies on water harvesting, tree nurseries, and community grazing frameworks to be compiled and disseminated - Knowledge management tools/log books purchased shared with communities and members trained on how to capture knowledge - Digital & Online Platforms - Social Media: Twitter/X (#GEF7Kenya, #RangelandForum2025). - Online presence: Project materials featured on IUCN, NEMA, and ACC websites. - Digital repository: Google Drive/SharePoint hub for storing and sharing project resources. - Audio-Visual Materials - Short documentaries on community impact (water harvesting, hay making were produced.Green - Local FM radio talk shows on biodiversity and forest management. - Media Coverage - National newspaper coverage of the July 2025 National Stakeholder Forum. - Feature stories on women-led nurseries and youth-led grazing management practices. Link to stories - https://youtu.be/FclefAl7FFU?si=TfTPXJdsIwLZ6466 - https://youtu.be/WKhWLxiaR_E?si=zPKneyyaOl62ThRk - https://kenyatopstories.co.ke/index.php/2025/07/28/kenya-commits-to-reverse-land-degradation-amid-climate-change/ - https://www.fao.org/in-action/dryland-sustainable-landscapes/news-and-events/news-detail/news-from-kenya/en Social media posts on NEMA social media handle - https://www.facebook.com/share/p/176ZePhCVW/ - https://x.com/NemaKenya/status/1949812181337309227 - https://x.com/NemaKenya/status/1949767659936977206 - https://x.com/NemaKenya/status/1933551301607968768 - https://x.com/NemaKenya/status/1923361832233840944 - https://x.com/NemaKenya/status/1923362372565057716 - https://x.com/NemaKenya/status/1923362919921717745

Lessons learned

Please share any particular lessons learnt in the context of project implementation (e.g. successfully tested tools, unexpected positive or negative impacts) and/or lessons learnt regarding one of your key outcomes

Community mobilization requires stronger ownership campaigns – While communities are mobilized and willing to participate, sustained engagement demands more intensive awareness and sensitization efforts to strengthen ownership. Digital tools enhance reach but not inclusivity – Platforms such as Zoom and Microsoft Teams proved effective in connecting stakeholders,however, rural communities without internet access were excluded. This highlighted the importance of complementing digital platforms with accessible channels such as radio broadcasts and local-language communication. Standardized communication protocols improve efficiency – The introduction of structured reporting templates and shared repositories minimized duplication, streamlined information flow, and improved timeliness in reporting. Capacity gaps limit the impact of tools – Tools such as newsletters, dashboards, and M&E systems remain underutilized without adequate training. Regular quarterly training is essential to strengthen stakeholder capacity and ensure effective use. Youth and women drive sustainability – Youth innovations (e-marketing, drones, mobile apps) and women’s indigenous knowledge (seed banking, water management) are critical enablers of long-term resilience and sustainability. Community engagement drives outcomes – Communities show high willingness to participate in restoration when properly sensitized. For example, involving women in seedling production and engaging community groups in nursery operations has significantly contributed to Kenya’s 15 billion Trees Program while also improving local livelihoods. Early communication on statutory requirements such as SHAs helps build trust and ensures smoother participation. Climate-smart restoration practices are effective – The use of native grass species, coupled with a blend of traditional land management and modern reseeding practices, supports sustainable restoration outcomes. Integrating grass reseeding with soil and water conservation techniques strengthens resilience to climate shocks such as drought. Youth participation and strong governance enhance outcomes – Active involvement of youth and women improves restoration impact, while effective governance within community groups ensures smooth implementation and accountability.

Communicating impact

Tell us the story of how the project has helped to improve people’s lives and biodiversity and how it contributed to the target(s) pledged through internal conventions (UNCCD LDN, UNFCCC NDCs, CBD NBSAPs, SDGs, etc) and/or national policies (The text will be used for IUCN Corporate Communications, the IUCN-GEF web-site, and/or other internal and external knowledge and learning efforts) Please also note you can share your success story and solution on the IUCN PANORAMA web platform. This will allow for knowledge retention and dissemination of project outcomes and success factors.

Communicating Impact The Southern Rangelands of Kenya are undergoing a remarkable transformation through the project’s interventions. Once fragile and degraded, these landscapes are now showing tangible signs of recovery, offering renewed hope for both people and nature. Restoring Biodiversity and Ecosystems Communities have taken the lead in reversing rangeland degradation by establishing tree nurseries, developing grass banks, and constructing gabions to control erosion. These restoration efforts directly advance Kenya’s commitments under the Convention on Biological Diversity (CBD) National Biodiversity Strategy and Action Plan (NBSAP), the UNCCD Land Degradation Neutrality (LDN) targets, and the Sustainable Development Goals (SDGs), particularly SDG 13 (Climate Action) and SDG 15 (Life on Land). Building Resilient Livelihoods The project has created new economic opportunities through diversified, nature-based enterprises. Beekeeping, eco-tourism, fodder banks, and agroforestry have emerged as viable income sources for households previously vulnerable to climate shocks. With NETFUND and ICIPE pledging to pilot three additional enterprises in 2025/26, communities are now better equipped to adapt to changing climatic conditions advancing Kenya’s Nationally Determined Contributions (NDCs) on climate adaptation. Strengthening Policy and Governance In July 2025, the National Stakeholder Forum marked a turning point in rangeland governance. The county governments of Narok and Kajiado committed to reviewing rangeland policies, paving the way for harmonized management frameworks. Furthermore, the establishment of a National Technical Working Group to draft a National Rangeland Framework by December 2025 signals a shift from fragmented interventions to a coordinated national approach, aligned with global environmental agreements. Promoting Social Inclusion and Equity The project has also advanced equity and inclusion. At the Forum, 42% of participants were women and 30% were youth, ensuring that decision-making was representative and inclusive. Women’s vital roles in seed banking, water management, and indigenous knowledge were formally recognized, while youth showcased cutting-edge innovations, from drones for monitoring to mobile apps and e-marketing platforms. This intergenerational collaboration has strengthened social cohesion and created a shared vision for sustainable rangeland management. Institutional Legacy By institutionalizing the National Stakeholder Forum as an annual platform, the project has secured a lasting mechanism for accountability, knowledge exchange, and innovation. This ensures that impact will continue to grow beyond the project’s lifetime. A Model for Global and Local Action Through bridging science, policy, and grassroots innovation, the project has improved livelihoods and restored biodiversity in Kenya’s Southern Rangelands. It has delivered resilient ecosystems, diversified community enterprises, and strengthened governance and inclusion. Importantly, these outcomes contribute directly to Kenya’s obligations under the CBD NBSAP, UNCCD LDN targets, UNFCCC NDCs, and the SDGs, while reinforcing national rangeland and climate policies. The legacy is a powerful demonstration of how local action can drive global commitments leaving behind stronger communities and healthier ecosystems.

What is the most significant change that has resulted from the project during this reporting period?

The most significant change during this reporting period has been the transition from fragmented rangeland governance to inclusive, county and community-led ownership reinforced by concrete policy commitments. Counties such as Narok and Kajiado pledged to initiate rangeland policy reviews within six months, while a National Technical Working Group was established to develop a National Rangeland Management Framework by December 2025. This marks a pivotal shift, aligning community-driven practices with county policies and national and global obligations under the UNCCD LDN targets, CBD NBSAPs, and the SDGs. Equally transformative has been the shift in community roles from passive beneficiaries to active custodians of biodiversity. Women’s indigenous knowledge and youth-led innovations in technology were not only showcased but formally integrated into governance processes, strengthening inclusivity and intergenerational collaboration. The institutionalization of the National Stakeholder Forum as an annual event has further consolidated this transformation. It guarantees continuity, co-ownership, and accountability, ensuring that inclusive dialogue and coordinated action on rangeland resilience will extend well beyond the project’s lifetime.

# Annex - Ratings definitions

Implementation Progress Ratings

Highly Satisfactory (HS): Implementation of all components is in substantial compliance

with the original/formally revised implementation plan for the project. The project can be presented as “good practice”.

Satisfactory (S): Implementation of most components is in substantial compliance with the original/formally revised plan except for only a few that are subject to remedial action.

Moderately Satisfactory (MS): Implementation of some components is in substantial compliance with the original/formally revised plan with some components requiring remedial action.

Moderately Unsatisfactory (MU): Implementation of some components is not in substantial compliance with the original/formally revised plan with most components requiring remedial action.

Unsatisfactory (U): Implementation of most components is not in substantial compliance with the original/formally revised plan.

Highly Unsatisfactory (HU): Implementation of none of the components is in substantial compliance with the original/formally revised plan.

Global Environment Objective/Development Objective Ratings

Highly Satisfactory (HS): Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice”.

Satisfactory (S): Project is expected to achieve most of its major global environmental objectives, and yield satisfactory global environmental benefits, with only minor shortcomings.

Moderately Satisfactory (MS): Project is expected to achieve most of its major relevant objectives, but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environment benefits.

Moderately Unsatisfactory (MU): Project is expected to achieve its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives.

Unsatisfactory (U): Project is expected not to achieve most of its major global environment objectives or to yield any satisfactory global environmental benefits

Highly Unsatisfactory (HU): The project has failed to achieve, and is not expected to achieve, any of its major global environment objectives with no worthwhile benefits.

Development/Adaptation Objective Ratings (For LDCF/SCCF/GCF Adaptation)

Highly Satisfactory (HS): Project is expected to achieve or exceed all its major development/adaptation objectives, and yield substantial adaptation benefits, without major shortcomings. The project can be presented as “good practice”.

Satisfactory (S): Project is expected to achieve most of its major development/adaptation objectives, and yield satisfactory adaptation benefits, with only minor shortcomings.

Marginally Satisfactory (MS): Project is expected to achieve most of its major relevant development/adaptation objectives, but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major development objectives or yield some of the expected adaptation benefits.

Marginally Unsatisfactory (MU): Project is expected to achieve its major development/adaptation objectives with major shortcomings or is expected to achieve only some of its major adaptation objectives.

Unsatisfactory (U): Project is expected not to achieve most of its major development/adaptation objectives or to yield any satisfactory adaptation benefits.

Highly Unsatisfactory (HU): The project has failed to achieve, and is not expected to achieve, any of its major development/adaptation objectives with no worthwhile adaptation benefits.

Risk ratings

Risk ratings will assess the overall risk of factors internal or external to the project that may affect implementation or prospects for achieving project objectives. Risks of projects should be rated on the following scale:

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

| The table below illustrates how the risk categories used by GEF and IUCN align with one another. |  |
| --- | --- |
| GEF risk categories | IUCN risk categories |
| Climate | External |
| Environment & Social | Part of Environmental and Social Safeguards |
| Political and Governance | External |
| Macro-economic | External |
| Strategies and policies | Strategic |
| Technical design of project or program | Operational |
| Institutional capacity for implementation and sustainability | Operational |
| Fiduciary: financial management and procurement | Finance |
| Stakeholder engagement | Part of ESMS risk assessment |
| Other | People management; Legal / Compliance; Information systems |
| Financial risks for NGI projects | N/A |

| The table below illustrates how the risk rating/level used by GEF and IUCN align with one another. |  |
| --- | --- |
| GEF risk rating / level | IUCN risk rating / level |
| High | High |
| Substantial | High |
| Moderate | Medium |
| Low | Low |

Safeguard risk ratings (also referred to as ESMS risk category)

The ESMS risk category determines the significance of environmental and/or social (E&S) risks or impacts. The significance is established for each identified E&S risks by combining likelihood and expected impact as demonstrated in table 2. The project ESMS risk category is then that of the highest risk rating. The ESMS Guidance Note on Assessment and Management of Environmental and Social Risks provides further details (including factors influencing the likelihood and impact).

Rating significance of a risk event

| Impact | Likelihood of occurrence |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Very unlikely to occur (1) | Low likelihood (2) | Likely – could occur (3) | Known to occur - almost certain (4) | Common occurrence (5) |
| Severe (5) | Moderate | Moderate | High | High | High |
| Major (4) | Low | Moderate | Moderate | High | High |
| Medium (3) | Low | Low | Moderate | Moderate | Moderate |
| Minor (2) | Low | Low | Low | Moderate | Moderate |
| Negligible (1) | Low | Low | Low | Low | Low |

This section will use the scale used by the GEF and outlined in Annex L of this document: 1) Highly satisfactory, 2) Satisfactory, 3) Moderately Satisfactory, 4) Moderately Unsatisfactory, 5) Unsatisfactory, 6) Highly Unsatisfactory

Idem

This section will use the scale used by the GEF and outlined in the Annex of this document: 1) High Risk, 2) Substantial Risk, 3) Moderate Risk, 4) Low Risk

Using the methodology established by the IUCN Environmental and Social Management System (ESMS) - see Annex

This section will use the scale used by the GEF and outlined in Annex of this document: 1) Highly satisfactory, 2) Satisfactory, 3) Moderately Satisfactory, 4) Moderately Unsatisfactory, 5) Unsatisfactory, 6) Highly Unsatisfactory

Idem

Abbreviations are explained in the Annex

IUCN risk categories: Strategic, Financial, People management, Operational, Legal/Compliance, Information systems, External

Stakeholder Engagement Policy Guidelines (SD/GN/01), December 20, 2018

Available at: https://iucn.org/sites/default/files/2022-05/iucn-data-protection-policy_0.pdf.

https://www.iucn.org/sites/dev/files/esms_esmp_guidance_note_and_template.docx

Add n/a if the respective risk issues has neither been identified during the ESMS screening nor in any update of the ESMP.

Please check the respective box to indicate the decision at Screening stage: whether a standards has been triggered or not, or the decision was deferred to the implementation phase. If the latter, please explain the status of this decision.

Please describe the grievance in an anonymized way, e.g type (e.g. gender, participation, violence etc)

Available et: https://iucn.org/sites/default/files/2022-09/iucn_esms_gn-risk-management-clean-22.pdf