UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 4847 | Umoja no.: GFL/11207-14AC0003-4E34 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Pine Islands – Forest/Mangrove Innovation and Integration (Grand Bahamas, New Providence, Abaco and Andros) |  |  |
| Duration months | Planned |  | November 2015 – November 2019 (48 months) |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | GEF Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Name of co-implementing Agency |  |  | N/A |  |  |
| Executing Agency(ies) |  |  | The Bahamas Environment, Science and Technology (BEST) Commission |  |  |
| Names of Other Project Partners |  |  | Bahamas Agriculture and Industrial Corporation (BAIC), Bahamas National G.I.S Centre (BNGIS), Bahamas National Trust (BNT), Department of Lands and Surveys (DLS), Forestry Unit, Department of Physical Planning (DPP) and Town Planning Committee (TPC) |  |  |
| Project Type |  |  | Full Size Project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Latin America and Caribbean |  |  |
| Names of Beneficiary Countries |  |  | The Bahamas |  |  |
| Programme of Work |  |  | Biennia: 2016-17; 2018-19 Sub-programme 3: Healthy and productive ecosystems |  |  |
| GEF Focal Area(s) |  |  | Biodiversity and Land Degradation |  |  |
| UNDAF linkages |  |  | N/A |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG Goal 13 Climate action – - Strengthen resilience and adaptive capacity to climate related hazards and natural disasters in all countries - 13.2 Integrate climate change measures into national policies, strategies and planning - Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning SDG 15 Life on Land - By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands. - Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed - Enhance global support for efforts …..by increasing the capacity of local communities to pursue sustainable livelihood opportunities |  |  |
| GEF financing amount |  |  | 2,853,425 |  |  |
| Co-financing amount |  |  | 7,695,258 |  |  |
| Date of CEO Endorsement |  |  | 8 September 2015 |  |  |
| Start of Implementation |  |  | 17 November 2015 |  |  |
| Date of first disbursement |  |  | 23 February 2016 |  |  |
| Total disbursement as of 30 June |  |  | USD 416,332 |  |  |
| Total expenditure as of 30 June |  |  | USD 396,591.16 |  |  |
| Expected Mid-Term Date |  |  | N/A |  |  |
| Completion Date |  | Planned | November 2019 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  | N/A |  |  |
| Expected Financial Closure Date |  |  | 31 December 2020 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Insert the Subprogramme(s) and biennia of the PoW to which the project contributes Sub-programme 3: Healthy and productive ecosystems Biennia: 2016-17; 2018-19 | Specify the relevant Expected Accomplishment(s) & Indicator(s) Insert the Subprogramme’s Expected Accomplishment(s) and Indicator(s) to which the project contributes EA 3 (b) Policymakers in the public and private sectors test the inclusion of the health and productivity of ecosystems in economic decision-making Indicator: (i) Increase the in number of public sector institutions that test the incorporation of the health and productivity of marine and terrestrial ecosystems in economic decision-making |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] There has been relatively little movement in project activity given the protracted period over which the project had not received a subsequent cash advance due to reporting non-compliance. This issue was rectified in the first part of 2019 that allowed for a disbursement in March 2019. The BEST Commission also took the needed measure to recruit a dedicated project manager to address wider issues related to the project reporting challenges and ensuring that implementation gets back on schedule. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] It should be noted that a specific UNDAF for the Bahamas is not available, however the UNDAF for the Caribbean region termed the ‘United Nations Multi-Country Sustainable Development Framework in the Caribbean’ cites Priority Area 4 ‘A Sustainable and Resilient Caribbean’ as relevant to the objectives under this project. Under this priority area the UN system will support coherent efforts to strengthen the resilience of the Caribbean and its peoples by mitigating the effects of climate change, disasters and environmental degradation on: sustainable development, livelihoods, and the economies. The anticipated relevant outcome is ‘Inclusive and sustainable solutions adopted for the conservation, restoration and use of ecosystems and natural resources’. Refer to: https://www.unicef.org/about/execboard/files/UNDAF-MSDF-Caribbean.pdf |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes [section to be shared with SDG unit] SDG Goal 13 Climate action – - 13.1 Strengthen resilience and adaptive capacity to climate related hazards and natural disasters in all countries - 13.2 Integrate climate change measures into national policies, strategies and planning - 13.3 Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning SDG 15 Life on Land - 15.1 By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands. - 15.6 Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed - 15.C Enhance global support for efforts by increasing the capacity of local communities to pursue sustainable livelihood opportunities |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MU | U | U |  |  |
| Progress made towards achieving the project results are consistent with previous years. There is continual advancements being made towards outcome deliverables. The project has had relatively little movement over the last review period. This was mainly as a result of non-compliance with technical and financial reporting which continued until March 2019. After March all the outstanding financial issues were finally addressed and new cash disbursements were made to some project partners. Each component of the project suffered some level of delay most notably component #1 under the Department of Physical Planning (DPP). Since inception DPP has been unable to provide the manpower and resources necessary to undertake activities under the project. This was due primarily as a result of a Supreme Court Order in which the Department was required to undertake certain activities that were legally mandated under provisions of the Planning and Subdivision Act. The Order was issued with a specific timeline that conflicted with the project’s schedule. This Order significantly impacted the project as the Department had no alternative but to focus all available human resources to address the court-specified actions. The DPP has confirmed that with the recent contracted engagement of an urban planner and an assistant, they are now able to provide the necessary assistance to complete their obligations under the project. Additionally, delays occurred with component 3 due to significant administrative and technical personnel changes in BAIC. The new staff were faced with no institutional knowledge regarding the project and thus were unable to get up to speed in time to make progress during the reporting period. However, after the second disbursement was made there have been more than 5 steering committee meetings within BAIC with a focus on project implementation and continued development. The recruitment of a new project coordinator to join the project in July 2019 will allow improved focused project management moving forward. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | U | U | U |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. Component 1: Development of Land-Use Plans for 2 islands which integrates biodiversity, ecosystem services and forestry the landscape level - The DPP has engaged a consultant who will be working on the project full-time as co-financing contribution by the Government of The Bahamas. The consultant is an ex-employee of the Department of Physical Planning. The consultant has reviewed and provided input into the updated work plan and is preparing the first steps to begin mobilization to meet project deliverables. Component 2: National Forest Estate: Develop Assessment and monitoring system - Legislation review was undertaken. The Forestry Act 2014 is being repealed and replaced with the Forestry Act 2019 that would facilitate the following; establishment of a Forestry Department and empowering the Minister responsible for the Environment to establish the National Forest Estate. The final draft has been forwarded to the Department of Legal Affairs for final vetting and advancement. The Forestry (amendment) Regulations, 2018 Second Schedule, was approved by Cabinet, and forwarded to the Cabinet Office for gazettement. - Town Meetings were held on Andros and New Providence for the promotion of the National Forest Estate. - Monitoring activities have been carried out within Conservation Forest areas in Abaco and Andros. - The National Forest Inventory (NFI) methodology was finalized and sample design was completed (reference manual as deliverable. - NFI Certifications and Re-certifications of 5 staff has been accomplished working with the International Conservation Corps (ICC) and the United States Forest Service (USFS) (Note: The Forestry Unit is awaiting the final payment due to EPI of $50,000 to receive the deliverables of the inventory grid and methodology of the NFI plots on the various islands) - Partnerships: The Forestry Unit has a partnership coming on stream with the Royal Botanic Gardens, called the Global Tree Seed Project. Chief among the many opportunities a project such as this affords The Bahamas is the establishment of the first seed bank of the Bahamas with 32 plant species to be stored at the University of the Bahamas. Main activities included: - Seed collection workshop with partners - Drafting of a plant species list - Establishment of partnerships on family islands - Ground truthing of plant species with GPS coordinates - National Management Plan: - ICCF: pre-workshop meeting in October 2018 - ICCF: workshop with assigned team November 2018 - Strategic Development workshop January 2019 - Davis Creek Mangrove Restoration and Rehabilitation: - Partnership with University of Wisconsin – River Falls: May 2018 – June 2018 - Partnership with ForFar Research Station & Hocking College – November 2018 and February 2019 Component 3: There has been strong interest from the Ministry of Agriculture & Marine Resources in this component, to this effect there has been two sub committees set up during the reporting period., The subcommittee is primarily focused on activities 3.2.1: : Resource assessment of cascarilla on Acklins, Crooked Island, Samana Cay and Plana Cays, Activity 3.2.2: Promotion of Sustainable harvesting of cascarilla, Activity 3.2.4: Establish a formalized plantation, Activity 3.2.5: Develop Marketing Plan for Promotion of Cascarilla products (bark and oil). A steering committee has been established by BAIC for the implication of this project component with a diverse body of stakeholders. This steering committee also has three sub committees which are focused on ensuring the success of the project relative to the following: - GEF Project Implementation (Monitoring, Reporting, Financing Requests etc.) - GEF Work Plan and Time Table (Design, Monitoring, Reporting, etc.) - Cascarilla Industrialization Work Breakdown Structure (WBS) Sub-Committee (Design, Monitoring, Reporting, etc.) The Ministry of the environment of Housing (Forestry Unit) has entered into a MOU with Creative Nassau, this allows creative Nassau to be brought onto the project and will be assisting BAIC with activities; Activity 3.1.2: Develop Industry Education awareness for Palm Cultivation, Activity 3.1.3: Promotion of Sustainable harvesting of silver top & cabbage palms, Activity 3.1.4: Promotion of Indigenous Craft trade (using harvested Palm tops), Activity 3.1.5: Establish a formalized plantation of palms for ornamental landscape market. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | N/A | L | M-S |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 Key changes include: - Hiring of new full-time dedicated Project Manager, to come on board in July 2019 - Setting up of ad hoc committee for Component 3 sustainable livelihoods - Set up new internal structure to ensure reporting is completed on time. (Gantt Chart) - Funding made available to pay consultants involved in Component 1. 1.1.4 |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] Some Challenges the project has faced during stakeholder engagements include: - Scheduling: It has proven to be a challenging at times getting all the relevant stake holders to attend meetings due to scheduling conflicts and other commitments. - Changes in Staff: There has been a number of changes to staff members which has affected continuity on project deliverables, when some individuals depart, they sometimes leave with a lot of institutional knowledge which can have a negative impact on the project. - Weather: due to the nature of the project, when there has been adverse weather (heavy rain, hurricanes etc.) it has had a delay on project implementation as it is unsafe to be in the field during those adverse conditions. - Lack of project reporting: partners have failed to submit reports on time due to personnel changes in two of the steering committee agencies which has resulted in delays from the Executing agency delivering reports on time. Lack of Project Disbursement: The project has only received two cash disbursements from project inception. However, multiple factors have attributed to the lack of disbursement, but principally lack of reporting mainly among partners due to various/unforeseen circumstances. This has greatly affected the projects ability to execute its deliverables on time. Outstanding payment have resulted in one contract payment being outstanding for more than 18 months However, the project has seen some progress which includes: - All members of the project steering committee have been reengaged - BAIC - the Minister of Agriculture and Marine Resources has expressed interest in the project which seems to have galvanized the key stakeholders in Component 3, this has resulted in the formation of 3 subcommittee’ looking to meet project deliverables. - Signing of MOU- the Ministry of Environment and Housing (Forestry Unit) has entered into a MOU with Creative Nassau {An NGO who specializes in thatch cultivation and production) to assist with Component 3 section 1. Native palm cultivation to support Indigenous Craft Industry on Andros and Grand Bahama - Dedicated Project Coordinator: - In July 2019 the BEST Commission initiated recruitment for a full time NPC. The prospective hire is to commence duties in July This will enable more accurate and detailed oversight if project implementation. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] Component 3 Sustainable Livelihoods: This component seeks to empower individuals who go out to source raw materials. This activity of the project is still in the implementation stages. Because this activity is dependent on other working being completed there has been no progress during the reporting period. |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval [section will be uploaded into the GEF Portal] Due to unforeseen circumstances such as personnel changes and lack of funding there has been limited progress during this reporting period; therefore nothing be assessed. |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/ GEF communication] Due to unforeseen circumstances such as personnel changes and lack of funding there has been limited progress during this reporting period; therefore nothing be assessed. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective | Integrate Biodiversity Considerations & Ecosystem Services into Forest Management and Land Use Planning (4 Pine Islands: Grand Bahamas, New Providence, Abaco and Andros) | N/A | N/A | N/A | N/A | N/A |
|  | 2. |  |  |  |  |  |
|  | 3. |  |  |  |  |  |
| OUTCOME 1.1 Enhanced enabling environment in support of Sustainable Land Management (SLM) and Sustainable Forest Management (SFM) with integration of Biodiversity into land use planning | 2 sub national plans integrate BD and SFM | Implementation of Pine Islands land use plans does not integrate of sustainable land use, forest ecosystem services, and biodiversity values. | Draft of the 2 sub-national land use plans that integrate BD and SFM | Town Planning Committee implementation of Land Use Plans integrates sustainable land use, forest ecosystem services considerations, and biodiversity values. | No progress was made on this activity during the reporting period. Due to a court order the responsible agency was mandated to prioritize other works. | MU |
|  | Establishment of Carbon and Forestry monitoring systems | Consolidated BD-1 Tracking Tool Score: 140 SFM Tracking Tool Score: 4 LD-3 Tracking Tools Score: 5 No open access to forestry, biodiversity or ecosystem services resources data. No established monitoring systems. | Consolidated BD-1 Tracking Tool Score: SFM Tracking Tool Score: LD-3 Tracking Tools Score: | Consolidated BD-1 Tracking Tool Score:259 SFM Tracking Tool Score:6 LD-3 Tracking Tools Score: 8 | There has been no progress in terms of deliverables for this reporting period. Due to a court order the responsible agency was mandated to prioritize other works. Activities are earmarked to start in August 2019 | U |
|  |  |  | Available data collected, consolidated and collated. Draft framework available for review. Conducted Remote Sensing to determine carbon values | Open source framework accessible to all agencies of forest resources which integrates ecosystem services and biodiversity data. Developed GIS datasets using Remote Sensing analysis | Data has been acquired from BNGIS; however, some data was corrupted. Data gathering continues. Additionally, external data is also being sought to address project needs. | MU |
| Outcome 1.2 Increased targeted public awareness of the importance and benefits of sustainably managing forest & mangrove biodiversity, ecosystems services and sustainable land management | An Integrated GIS framework for all agencies in regards to Forestry Resources Sub national land-use plans for Andros and New Providence Enhance capacity | No Forestry in existing GIS framework No comprehensive land-use plans that incorporate biodiversity and conservation areas exist for Andros or New Providence Limited technical capacity | Data collection completed Draft of the 2 sub-national land use plans that integrate BD and SFM Capacity needs assessment carried out | Developed an open-source framework for all agencies to have access to Forestry data and Land-Use plans Town Planning Committee implementation of Land Use Plans integrates sustainable land use, forest ecosystem services considerations, and biodiversity values. 75% of the Town Planning Committee and Family Island Administrators received training | Progress has been made for this activity. Boundaries have been demarked and identified. Awaiting approval by Department of Land and Surveys | MS |
|  | Public Awareness | Community awareness of basis decision making limited | Tools and training modules developed Baseline awareness Surveys completed | Public awareness activities Local Island Administrators on Andros and Abaco increased by 50% over baseline. | Forestry Awareness Week was carried out. The initiative is undertaken twice a year and focuses on bringing awareness to all forestry projects, including the BPI project. Some PR vehicles used include: newspaper adds, radio adds, and posters earth. | MU |
|  | Tools and Training for capacity enhancement in the areas of sustainable land use, forest ecosystem services, and biodiversity values. | No tools or training modules in the areas of sustainable land use, forest ecosystem services, and biodiversity values | Capacity needs assessment conducted Developed training modules workshop With Planning Consultant/DPP, FU, BEST BNGIS, and DLS | Public awareness activities Local Island Administrators on Andros and Abaco increased by 50% over baseline. | The Forestry Unit is in the process of setting up a workshop to address works outlined in the activity. Lack of disbursements lead to subcontracted consultants not being brought in country during the reporting period. Workshops will commence in August 2019. | U |
|  | Awareness built of benefits of sustainable land use, forest ecosystem services and biodiversity values. | Low awareness and no communication strategy | Conduct baseline surveys within communities Development of communication strategy and action plan | 30% Increased Awareness in Targeted Communities based on Surveys | The Forestry Unit utilized “Forestry Week” which took place in June and March 2019 to promote public awareness. Some PR vehicles used include: newspaper adds, radio adds, flyers, school visits /competitions, and posters benefits. | U |
| COMPONENT 2. Expansion and improved management of forest/mangrove sector |  |  |  |  |  |  |
| OUTCOME 2 Improved management effectiveness of existing and new forest reserves | BD-Tracking Tool SFM Tracking Tool | Consolidated BD-1 Tracking Tool Score: 140 SFM Tracking Tool Score: 4 | Consolidated BD-1 Tracking Tool Score SFM Tracking Tool Score | Consolidated BD-1Tracking Tool Score:259 SFM Tracking Tool Score:6 | The SFM is in the development stages and will be produced as a part of the National Forestry Plan under the Forestry Unit. There has been little progress in terms of deliverables, due to the situation relating to DPP. Activities are earmarked to start September 2019 now that funding has been received. | U |
|  | Establishment of National Forestry Estate inclusive of Conservation & Protected Forests | The Forestry Act 2010 speaks to these designations. Cabinet conclusion directing Forest Department to gazette national forestry estate | Draft boundaries for estimated total of 283,750.2 ha (Conservation Forests = 149396.99 ha (52.65% of forestry Estate ) & Protected Forests= 37810.58 ha ) (13.33%) for Forestry Estate | Gazettal of National Forestry Estate (GEF supports Conservation & Protected Forests and GOB supports Forest Reserves) Vesting of Forestry lands into Ministry of Environment and Housing | The Forestry Unit is in the process of setting up a workshop to address works outlined in the activity. Pending reviews from the Department of Land and Servery are forthcoming. | S |
|  | Management Plans developed and implemented taking into account balanced gender roles and opportunities | No Community management plans Baseline COeq | Gazettal of target Forest areas (Blue Hole Conservation Abaco and Maiden Hair, Andros) & community consultations underway EXACT figure CO2eq in 2 yrs | Forest Conservation Plans signed, adopted and implemented by Communities. EXACT figure CO2eq in 4yrs | No progress made due to lack of disbursement to subcontracted consultant. There are workshops scheduled for Aug. 2019 to solidify workplans in order to meet deliverables. | U |
|  | The area and condition of mangrove forests | Degraded mangrove system, limited ecosystem services provisioning Baseline CO2eq | Culverts cleaned out. Invasive species removed. Establishment of nursery EXACT fig CO2eq in 2 yrs | 50 hectares of degraded mangrove restored. Carbon stock increase of up to 14,563 tCO2 eq. EXACT fig CO2eq in 4yrs | No progress made due to lack of disbursement to subcontracted consultant. There are workshops scheduled for Aug. 2019 to solidify workplans in order to meet deliverables | U |
| COMPONENT 3. Models for SFM Sustainable livelihoods, agriculture, forestry & sustainable land management in coastal communities of the Pine Islands, and additional Family Islands in Central and SE Bahamas |  |  |  |  |  |  |
| Outcome 3. Effective provisioning of forest ecosystems underpinned by strengthened livelihoods people dependent on use of forest resources - increased use of sustainable land, agroforestry and forestry management practices among coastal communities. | Integrated landscape management practices adopted by local communities taking into account balanced gender roles and opportunities. | Unsustainable and uninformed harvesting of non timber forest products (NTFPs). | Data and guidelines for sustainable models of NTFPs developed | Sustainable practices adopted in 2 Pine Island communities | Major personnel turn over resulted in lack of progress during the reporting period. BAIC has held multiple subcommittee implementation meetings in order to address deliverables. | HU |
|  | Application of sustainable practices in forest communities of the Pine Islands taking into account balanced gender roles and opportunities. | Unsustainable harvesting of palm hearts is damaging productivity | Sustainable model of harvesting developed on the basis on gathered data. Gender disaggregated socio-economic survey for surrounding communities | Joint community/forestry unit monitoring of 40.5 ha in Andros and 40.5 ha in Grand Bahama 35% Increase in persons engaged in NTFPs and community level income (gender disaggregated) | BAIC has held multiple subcommittee implementation meetings in order to address deliverables There are townhall meetings scheduled for Sep. 2019 to engage local communities on Andros. | HU |
|  | Application of sustainable practices in forest communities of the Pine Islands taking into account balanced gender roles and opportunities. 10 ha in Acklins and 10 ha in Crooked Island | Unsustainable harvesting of cascarilla bark prohibits regeneration and limiting productivity. No baseline data. | Sustainable model of harvesting developed on the basis on gathered data. Gender disaggregated socio-economic survey for surrounding communities | Joint community/forestry unit monitoring of 20 ha in Acklins and 20 ha in Crooked Island 35% Increase in persons engaged in NTFPs and community level income (gender disaggregated) | BAIC is working in partnership with several entities including the Forestry Unit, CARDI, and BDB in order to meet project deliverables. A sub steering committee has been formed and a work plan is in development. | HU |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| U | U | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. This information provides the rationale for the Development Objective Rating in Section 2. The project faced major delays largely due to halting of further cash disbursements linked to non-reporting/non compliancy in financial and technical reporting. The status had not changed for most this PIR cycle, until the BEST Commission was able to bring report to compliance and the second cash disbursement of US$464,038 to the project was made in March 2019. The timing of the disbursement however has not permitted realization of significant movement in implementation. The project has not been convening regular meetings of the steering committee and as such has hindered collaboration and coordination among the stakeholders and the project management team in the BEST Commission. This has led to loss of continuity and stakeholder mobilization. This was indeed affected to some degree by the lack of funding to the project. It is noteworthy that the BEST Commission has a new Director who assumed office at the start of 2019 who has committed to ensure that the project implementation is hastened and importantly ensure that the management capacity of the BEST Commission is strengthened. In this regard an important step made is the recruitment of a dedicated project manager who will be in place by July 2019. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - Changes in Staff: There has been a number of changes to staff members which has affected continuity on project deliverables, when some individuals depart them can sometimes leave with a lot of institutional knowledge which can have a negative impact on the project. - Capacity limitation with the BEST Commission: A key staff issue was that for an extended period over the project, it was managed by a staff member whose time was not solely dedicated to the management of the project and compromised responsiveness to the project needs. - Lack of cash Disbursement: The project has only received 2 cash disbursements from project inception, this has greatly affected the projects ability to execute its deliverables on time. This however was linked to challenges in technical and financial reporting to UNEP upon which cash advances to the project depended. Note point below. | Request clear handover notes to minimize the impact of staff departures. Personnel within the BEST Commission must provide all support for continuity and management must put the needed systems in place for transition processes. Ensure that the incoming project manager is adequately oriented by the management of the BEST Commission (particularly by the staff member who previously held the role of PM). There needs to be an orientation to the reporting requirements (Anubis) by the UNEP’s team support in Panama and the Task Manager. A specific session (by skype) will be organized with the possibility for further in-country support. Step up efforts ensure that partners submit clear, concise and quantifiable periodic progress reports in good time to facilitate compilation for submission to UNEP. The incoming project manager will need to provide necessary support to the project partners in this regard. |
| on stakeholder engagement | - Lack of/timeliness project reporting: partners have failed to submit reporting on time which has resulted in delays from the Executing agency in delivering reports on time to UNEP to facilitate acceptance and continuity in making funding available. This presented challenges to the BEST Commission in maintaining coordination and appropriately reacting with needed measures and interventions to support implementation. - Scheduling: It has proven to be challenging at times getting all the relevant stake holders to attend meetings due to scheduling conflicts and other commitments. | The project management team will need to develop a roster of meetings for the project steering committee and ensure to the extent possible, full participation. There is a realistic issue in that fact that the project is being implemented across multiple islands which presents challenges to bring all to one meeting space. Alternative means such as engagement via telecon or making decision by round-robin email consensus should be agreed on in the decision-making process. In any case meetings should be planned further in advance, providing as much detail/information as needed. Designed backup representatives from all agencies involved in the project should be identified. |
| on gender actions | N/A | N/A |
| on safeguards | N/A | N/A |
| on delivering GEF Core Indicators | N/A | N/A |
| on delivering of PoW EA | N/A | N/A |
| on sustainability of results | N/A | N/A |
| others | N/A | N/A |

3.2	Rating of progress implementation towards delivery of outputs

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| Outputs | Expected completion date | Implementation status as of 30 June 2018 (%) | Implementation status as of 30 June 2019 (%) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Assessment and monitoring system (GIS); database of forestry lands with biodiversity overlay, inc mangroves. |  | 50% | 50% | GIS data received however unable to use data as file is ‘corrupted’, received quotation from the nature conservancy (TNC) for a total value of US$100,000+ for the same data in question, needs to be revisited. | U |
| Activity 1.1.1.1: Development of work plan and acquirement of geospatial data for proceeding activities for entire project | 30/06/2019 | 50% | 100% | Workplan developed; Acquired all available geospatial data from local source | HU |
| Activity 1.1.1.2: Identification and demarcation of boundaries through field assessments, GPS coordinates and utilizing GIS to update 1986 forestry maps to create maps of the forest estate (demarcation will require legal action and gazetting of the proposed boundaries). | 30/06/2019 | 50% | 100% | Completed boundaries for proposed National Forest | U |
| Activity 1.1.1.3: Conduct remote sensing analysis to determine true Carbon sequestration values and sensing analysis of forestry lands | 30/06/2019 | 40% | 40% | EPI delayed due to lack of financing; Pending geospatial datasets: upcoming call in August 2019 to plan way forward and revised timelines. | U |
| Activity 1.1.1.4: Develop Forestry Maintenance Plan for Forestry dataset | 30/03/2019 | 0% | 25% | Draft outline has been developed. Forestry Unit working with ICCF to complete. ICCF delayed due to lack of funding. | U |
| Activity 1.1.1.5: Develop Forestry Monitoring system within the established Forestry Estate | 30/06/2019 | 15% | 25% | Draft outline has been developed. Forestry Unit working with ICCF to complete. ICCF delayed due to lack of funding. | U |
| Activity 1.1.1.6: Develop and implement open source framework accessible to all agencies, using data developed in previous activities | 31/12/2019 | 0% | 0% | No activity in 2018 -2019. Progress is dependent on other deliverables being completed. | N/A |
| Output 1.1. 2: Development of Land-Use Plans for 2 islands which integrates biodiversity, ecosystem services and forestry at the landscape level |  | 45% | 45% | Land Use plan for Andros has been produced, however needs to be further modified, currently being undertaken for new providence island. | U |
| Activity 1.1.2.1: Review of the National Planning and Development Policies including in depth reviews on Andros and Town Planning Committee on New Providence | 30/06/2019 | 90% | 90% | Limited progress - ongoing | S |
| Activity 1.1.2.2: Collate and update selected species and ecosystems baseline for incorporation into the tools | 30/06/2019 | 25% | 25% | The responsible agency has not reported progress on this activity for the reporting period. | MU |
| Activity 1.1.2.3: Development of 2 sub-national plans for Andros and New Providence | 31/12/2019 | 45% | 45% | Limited progress - ongoing | MU |
| Activity 1.1.2.4: Public consultations/review process of the proposed land-use plans for Andros and New Providence | 30/06/2019 | 0% | 0% | Due to legal actions taken against partner agency; local courts have advised said agency to prioritize other works during the reporting period hence no progress | U |
| Activity 1.1.2.5: Approval of the Land-use plans | 31/03/2019 | 0% | 0% | Depending on the results of the reviews from 1.1.2.1, 1.1.2.3 and 1.1.2.4 it may need to be brought forward. | MU |
| Output 1.2.1: Tailored tools, methodologies, and training for integration of biodiversity into forest management/ land use management |  | 45% | 45% | Land use management plan is currently being produced, consultant has been hired to work with the Forestry Unit to further integrate biodiversity and forest management into land management. | U |
| Activity 1.2.1.1: Identification of tools, methodologies and training programs to be used for the integration of BD into SLM/SFM at DPP/TPC, FU, DLS and Local Government levels | 30/06/2019 | 5% | 5% | A consultant has been identified to establish TORs. Due to legal actions taken against the partner agency (unrelated to this project); local courts have advised the agency to prioritize and address the litigation over other matters hence the lack of implementation | U |
| Activity 1.2.1.2: Review and Selection of appropriate tools, methodologies and training programs at meeting with Stakeholders | 31/03/2019 | 25% | 25% | Discussed and identified, but due to major personnel changes in key stakeholder had to be postponed for the time being. | MU |
| Activity 1.2.1.3: Development of integrated Land Use Planning Materials | 30/03/2019 | 5% | 5% | Activities awaiting commencement depending on the completion of other deliverables. | MU |
| Activity 1.2.1.4: Feedback on developed tools from agencies | 30/06/2019 | 0% | 0% | Not applicable in this reporting period. | N/A |
| Activity 1.2.1.5: Integration into policy framework and follow-up of tools with stakeholders and Local Administrators | 31/12/2019 | 0% | 0% | Not applicable in this reporting period. | N/A |
| Output 1.2.2: Awareness building modules - benefits of sustainable land use and forest management. |  | 25% | 25% | Forestry Unit carries out Forestry awareness week on an annual basis as part of co finance to raise awareness, project will also soon be seeking an awareness expert to advertise to the wider public. | MU |
| Activity 1.2.2.1: Development of Awareness and Communication strategies | 31/12/2019 | 30% | 30% | ‘Forestry awareness week’ was used as an awareness tool. This even happened in March and June of 2019. | MS |
| Activity 1.2.2.2: Develop action plan, including training programme, to build capacity and awareness of strategy and policy options and mainstreaming tools and disseminate relevant information widely | 31/12/2019 | 0% | 0% | No progress made during reporting period. | U |
| Activity 1.2.2.3: Strengthen public awareness, learning and sharing experiences at local, regional and national levels using appropriate multi-media methods | 31/12/2019 | 15% | 20% | No progress made during reporting period. Activity is dependent on other deliverables. A comprehensive plan is required to address the needs of all components. | MU |
| Output 2.1: Establishment of National Forestry Estate inclusive of Conservation & Protected Forests |  | 50% | 50% | GIS data sets have been obtained however the file is unusable, need to resolve the data issue. Forested areas have been identified and need to be gazetted. | MS |
| Activity 2.1.1.1: Obtain GIS dataset layers developed in Activity 1.1.1.2 | 30/06/2019 | 25% | 80% | Workplan developed; Acquired all available geospatial data from local sources | MS |
| Activity 2.1.1.2: Collaborative efforts over the finalization of boundaries with Forestry Unit, DPP, Town Planning Committee, Depts. Of Lands & Surveys, and BNGIS Centre | 30/06/2019 | 75% | 75% | The DPP has been re-engaged during the reporting period. The Forestry Unit has collaborated with all relevant agencies . | MU |
| Activity 2.1.1.3: Collaboration with DPP for insight and cooperation in the land classification designations | 30/09/2019 | 25% | 45% | July 2018: Forestry Unit met with DPP to discuss progress of the NFE boundaries on the Pine Islands; Follow-up meeting to be done to present authenticated boundaries approved from Department of Lands & Surveys | MU |
| Activity 2.1.1.4: Submit boundaries to Parliament and proceed through the approval processes (Public Consultations, Cabinet approvals) for the Gazettal of the National Forestry Estate | 31/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.1.1.2 | U |
| Activity 2.2.1: Obtain GIS dataset layers developed in Activity 1.1.1.2 | 30/09/2019 | 0% | 100% | Workplan developed; Acquired all available geospatial data from local sources. | S |
| Output 2.2 - Community co-management of 2 Conservation forests (representing 15% of Conservation Forests) |  | 60% | 60% | An internal forestry plan has been produced, in discussions with the Office of the Attorney General and Minister of Environment and Housing to prepare to table the bill in Parliament. | U |
| Activity 2.2.2: Develop a National Forest Plan as per Forestry Act 2010 Part II 5: (1) (a) – (e) | 31/12/2019 | 15% | 25% | Subcontractor engaged. ICCF awaiting payment to move forward with activity. | U |
| Activity 2.2.3: Submit the national forest plan for review to the Minister of Environment & Housing, and Public Consultation as per Forestry Act 2010 Part II 5: (2) | 30/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.2.2 | N/A |
| Activity 2.2.4: as per Forestry Act 2010 Part II 5: (3) after the Minister has approved a national forest plan, the plan shall be tabled in Parliament and subsequently Gazetted | 30/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.2.3 | N/A |
| Activity 2.2.5: Develop a Forest Management Plan for 2 Conservation Forest areas as per Forestry Regulations, 2014 Part V- (19) (1) (a) – (e) | 30/12/2019 | 0% | 15% | Advancing as described; upcoming workshop in August 2019 to produce draft v2 of document | N/A |
| Activity 2.2.6: Collaborative efforts over the finalization of boundaries with Forestry Unit, DPP, Town Planning Committee, Depts. Of Lands & Surveys, and BNGIS Centre; In addition to developing partnerships with community based associations for the management of Forest Areas | 30/12/2019 | 15% | 15% | No activity during reporting period. | MU |
| Activity 2.2.7: Conduct Public Consultation of the Proposed Management for Conservation Forest areas | 30/12/2019 | 50% | 50% | No activity during reporting period. | S |
| Activity 2.2.8: Develop a Sustainable Financial Plan for the 2 Conservation Forest Areas in Abaco and Andros | 31/12/2019 | 0% | 0% | No activity in during reporting period; To be addressed in upcoming workshop August 2019 with ICCF | HU |
| Activity 2.2.9: After consultation, the Minster shall grant formal approval of the 2 Conservation Forest Areas in Abaco and Andros | 30/12/2019 | 0% | 0% | No activity in during reporting period; contingent on Activity 2.2.5 | U |
| Activity 2.2.10: Implementation of Conservation Forest Areas in Abaco and Andros | 31/12/2019 | 5% | 5% | Implementation plan contingent on the national forest plan and the management plan | U |
| Activity 2.2.11: Monitoring of activities within Conservation Forest areas | 31/12/2019 | 0% | 20% | Routine patrolling in place. Upcoming August 2019 workshop will address the plan for the Permanent Sample Plots to be established throughout the National Forest Estate | U |
| Activity 2.2.12: Strengthen public awareness, learning and sharing experiences at local, regional and national levels using appropriate multi-media methods (ref. to activity 1.2.2.3) | 31/12/2019 | 0% | 45% | Ongoing Efforts from the Forestry Unit to promote Sustainable Forestry Management of the GEF Pine Island Project (Forestry Week promotion) | U |
| Output 2.3: Restoration of Andros Davis Creek Mangrove system (50 ha) with CO2 savings up to 14,563 tCO2 eq |  | 15% | 15% | Received a tentative offer from the Bahamas National Trust, was in negotiations but stalled, due to lack of funding. A cash disbursement has officially been received, will restart negations shortly. | U |
| Activity 2.3.1: Conduct specific site assessment and determine baseline analysis | 30/06/2019 | 25% | 45% | Interim Preliminary site assessments completed. Various partners and stakeholders engaged on low-scale restoration activities. Negotiations with contractor (BNT) collapsed due to budget and logistical challenges. | HU |
| Activity 2.3.2: Develop and commence implementation of Participatory based Site Specific Management Plans based on the SFM principles for restoring/rehabilitating degraded mangrove | 31/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.3.1 | U |
| Activity 2.3.3: Develop and implement a community based monitoring of the rehabilitated mangrove site | 31/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.3.2 | U |
| Activity 2.3.4: Research and Monitoring programme established for indicator species | 31/12/2019 | 0% | 0% | No activity during reporting period. Dependent on Activity 2.3.3 | U |
| Output 3.1 Pilot Model Sustainable Cultivation of Native Palms |  | 200% | 20% | Strong interest from the Minister of Agriculture has kick-started the whole component again, a preliminary field visit was conducted in May, with further visits and a huge mobilization being planned. | U |
| Activity 3.1.1: Resource assessment of silver top and cabbage palms | 30/06/2019 | 5% | 5% | Due to major personnel changes the responsible agency was unable to get up to speed on project activities during the reporting period. | HU |
| Activity 3.1.2: Develop Industry Education awareness for Palm Cultivation | 31/12/2019 | 5% | 5% | Due to major personnel changes the responsible agency was unable to get up to speed on project activities during the reporting period. | U |
| Activity 3.1.3: Promotion of Sustainable harvesting of silver top & cabbage palms | 31/12/2019 | 0% | 5% | Due to major personnel changes the responsible agency was unable to get up to speed on project activities during the reporting period. | U |
| Activity 3.1.4: Promotion of Indigenous Craft trade ( using harvested Palm tops) | 31/12/2019 | 0% | 0% | Activities awaiting commencement depending on the completion of other deliverables. | U |
| Activity 3.1.5: Establish a formalized plantation of palms for ornamental landscape market | 31/12/2019 | 0% | 0% | Activities awaiting commencement depending on the completion of other deliverables. | U |
| Activity 3.1.6: Develop Marketing Promotion Strategy of Indigenous Craft trade (using harvested palm tops) | 31/12/2019 | 0% | 0% | Due to major personnel changes the responsible agency was unable to get up to speed on project activities during the reporting period. | U |
| Activity 3.1.7: Establish formalized plantation of palms for ornamental landscape market | 31/12/2019 | 0% | 0% | Awaiting further activities and consultations before the activity can begin. | U |
| Output 3.2 Pilot Model Sustainable Cascarilla Cultivation and Processing |  | 25% | 15% Revised from previous PIR assessment | Strong interest from the Bahamas Development Bank has kick-started the whole component again with a push for mobilization being planned | U |
| Activity 3.2.1: Resource assessment of cascarilla on Acklins, Crooked Island, Samana Cay and Plana Cays | 30/06/2019 | 5% | 20% | Based on the preliminary assessment, recommendations to revise the scope of the project as implementation especially on the Samana and Plana Cays exceeds the budget and logistical capacity; A working group created from the BAIC, IICA and Ministry of Agriculture was formed to reformulate the workplan. | U |
| Activity 3.2.2 Promotion of Sustainable harvesting of cascarilla | 31/12/2019 | 0% | 0% | Activities awaiting commencement depending on the completion of other deliverables. | U |
| Activity 3.2.3: Develop Industry Education system to build capacity | 31/12/2019 | 0% | 0% | Activities awaiting commencement depending on the completion of other deliverables. | U |
| Activity 3.2.4: Establish a formalized plantation | 31/12/2019 | 0% | 0% | Activities awaiting commencement depending on the completion of other deliverables. | U |
| Activity 3.2.5: Develop Marketing Plan for Promotion of Cascarilla products (bark and oil) | 31/12/2019 | 0% | 0% | Due to major personnel changes the responsible agency was unable to get up to speed on project activities during the reporting period. | U |
| Output 4.1: Monitoring & Evaluation |  |  |  |  |  |
| Activity 4.1.1: Finalize and disseminate project Monitoring and Evaluation Framework | 31/12/2019 | 0% | 50% | Quarterly and half year reports were submitted. | MS |
| Activity 4.1.2: Implement participatory Monitoring and Evaluation plan, tools, and methods with targeted communities, including necessary training | 31/12/2019 | 0% | 0% | No progress during this monitoring period. | HU |
| Activity 4.1.3: Establish reporting plan and requirements, templates | 30/06/2019 | 75% | 75% | Reporting plan and requirements, templates discussed during individual steering committee meetings | MS |
| Activity 4.1.4: Submit project and financial reports to GEF | 31/12/2019 | 0% | 50% |  | MS |
| Activity 4.1.5: Organise and implement project Mid-Term Evaluation | 30/06/2019 | 0% | 0% | Not applicable in this reporting period | N/A |
| Activity 4.1.6: Organise and implement project Final Evaluation | 31/12/2019 | 0% | 0% | Not applicable in this reporting period | N/A |
| Outcome 5.1: Project Management |  |  |  |  |  |
| Activity 5.1.2 Selection and appointment of NPC | 30/09/2016 | 100% | 100% | Full time NPC recruited at the end of the reporting period | MS |
| Activity 5.1.3.1: Plan and undertake a full project inception meeting to address capacity building related to relevant project methodologies, approaches and general technical guidance as well as project management and administration | 30/09/2016 | 100% | 100% | Inception workshop held in February of 2016. | S |
| Activity 5.1.3.2: Establish and operate project budgeting and accounting system | 31/12/2016 | 100% | 100% | Anubis and internal finance officer in place. | S |
| Activity 5.1.3.3: Review and refine annual work plan with national project coordinator and national partners based on better understanding of local context in pilot sites and in-depth baseline | 31/12/2019 | 0% | 25% | Individual steering committee meeting were held during this reporting period. | MS |
| Activity 5.1.3.4: Establish project National Steering Committees and conduct regular meetings | 31/12/2019 | 25% | 30% | Individual steering committee meeting were held during this reporting period. | S |
| Activity 5.1.3.5: Establish other relevant committees including Site Committees and other committees, working groups identified for other project outputs | 31/12/2019 | 0% | 25% | Individual steering committee meeting were held during this reporting period. BAIC formed subcommittees for aspects of components. | MS |
| Activity 5.1.3.6: Finalize and disseminate project Communication Strategy | 30/06/2019 | 0% | 100% | Communication Strategy resolved. | MS |
| Activity 5.1.3.7: Establish overall project Capacity Building Plan, including essential project management process-related training such as developing effective partnerships | 30/06/2019 | 50% | 100% | Capacity building plan identified. Effective partnerships have been arranged, Equipment has been donated and works have been carried out by various project partners | MS |
| Activity 5.1.4 Selection of subject matter specialists, experts, and consultants | 30/06/2019 | 25% | 75% | Subject specialists have been identified; they include ICCF, USGS, EPI, TNC, Creative Nassau and Consultant Bryan Manco as well as other Governmental organizations. Works have been carried out with the various organization and individuals. DPP (Component 1 has consultant identified.) | MS |

| FY2018 rating [previous] | FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- | --- |
| U | U | U | The rating of progress in the delivery of outputs should be assessed in terms of both quantity and quality. The assessment must consider ownership by, and usefulness to, intended beneficiaries and the timeliness of their delivery. Use the comments column to explain the reasons behind the success or shortcomings of the project in delivering its programmed outputs and meeting expected quality standards. The rating remains relatively unchanged on account of the fact that the project was essentially stalled due to lack of cash disbursements for the greater part of the PIR cycle. Toward the start of 2019 the BEST Commission was able to bring outstanding reporting up to date which allowed for the release of the second cash advance to the project. BAIC the agency responsible for component three are engaged several expert organizations to form subcommittees to further project works. The Forestry Unit the agency responsible for component two has schedule consultants to advise on the many activities associated with component two. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Changes in Staff: There has been a number of changes to staff members which has affected continuity on project deliverables, when some individuals depart, they can sometimes leave with a lot of institutional knowledge which can have a negative impact on the project. | Vacating personnel should leave clear and concise handover notes for use by the incoming project managers. All historical project documents should be centralized and organized for easy handover. | BEST Commission | July 2019 |
| Capacity limitation with the BEST Commission: A key staff issue was that for an extended period over the project, it was managed by a staff member whose time was not solely dedicated to the management of the project and compromised responsiveness to the project needs. | Orient the incoming project manager by the management of the BEST Commission (particularly by the staff member who previously held the role of PM). There needs to be an orientation to the reporting requirements (Anubis) by the UNEP’s team support in Panama and the Task Manager. A specific session (by skype) to be organized with the possibility for further in-country support. | BEST Commission; UNEP | PM to be installed by mid-July. Convene orientation activity for PM by early August |
| Lack of cash Disbursement: The project has only received 2 cash disbursements from project inception, this has greatly affected the projects ability to execute its deliverables on time. This however was linked to challenges in technical and financial reporting to UNEP upon which cash advances to the project depended. Note point below. | BEST Commission (PM) to send a letter to all partners advising of the ‘re-start’ of the project, particularly those partners waiting on cash inflow to recommence activities. Advise/remind all partners on the periodic reporting requirements and provide needed templates for all reporting PM to prepare a budget revision and workplan for 2019 in consultation with partners for submission to UNEP. PM to ensure that all quarterly expense reporting is completed within 2 weeks of the end of the period in Anubis. | BEST Commission | July 2019 July 2019 July 2019 for Q2 reporting; follow-on |
| Scheduling: It has proven to be challenging at times getting all the relevant stake holders to attend meetings due to scheduling conflicts and other commitments. | Prepare a roster of meetings for 2019 for the project steering committee and circulate to all PSC members. Convene a PSC meeting early into Q3; key focus must be on the activity schedule and budget rephasal. Ensure full participation to link others remotely where not possible to attend in person. PM to request that partner agencies on the PSC designate backup representatives | BEST Commission and Project partners | mid-July 2019 Late July to early August 2019 Mid-August 2019 |
| Interdepartmental communication: response times from stakeholders can vary, depending on their priorities, which can affect project delivery. | Agree upon final dates for deliverables, as tasks are set out. Reporting deadlines are to be clearly communicated during ever steering committee meeting. Stakeholders to be informed that meeting reporting deadlines does affect disbursement frequency. | BEST Commission and Project Partners BEST Commission and Project Partners | Moving Forward Moving Forward |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Key Project partners, communities, farmers and hunters are not prepared to fully participate in the process, exchange information or materials; | Increased communication with all stakeholder levels throughout the project phases thus promoting trust, and sharing of information should follow; using open source software would assist in accessibility to data. Component 3 focused on alternative livelihoods designed to engender participation and support. | Limited measures applied although the project has done some level of awareness-raising to avert this risk. All three agencies responsible their individual components are aware of the public awareness complainant of the project. While finalizing their work plans each agency will outline plans to raise public awareness. | CEO: H TM: H PM:H |
| Adoption of land-use planning strategies may lead to resistance from Local Government island Administrators which will lead to continued fragmented landscapes because of competing land-uses | Mitigate temp. zoning requirements if a conflicting development occurs with a conservation zone; Using the participatory and interactive approach with island communities therefore reducing prejudice that all decisions are top-down approach; By integrating their needs and recommendations, this will increase ownership and acceptance of the process. New legislation for 2010 Subdivision Act encompasses substantive procedural consultative agreement processes. | Through the public awareness initiative and the integration of numerous agencies all parties involved with be informed of the prosses and will produce cohesiveness between said agencies. | CEO: M TM: M PM: M |
| Long-term monitoring system developed and implemented | Training to Town Planning Committees and Family Island Administrators to be provided under project and responsibilities clarified. | During the project implementation phase training of Family Island Administrators was discussed. This integration is essential in the long-term plan for success of the project. | CEO: M TM: M PM: M |
| Land ownership and access within coastal communities | Increased communication with all stakeholder levels throughout the project phases thus promoting trust, and sharing of information should follow; using open source software would assist in accessibility to data. Component 3 focused on alternative livelihoods designed to engender participation and support. | The majority of land that will be affect under this project is crown (government owned) land. Varies government departments are well aware of the works preceding as a part of the project and have not shown objections. |  |
| Sustainable Livelihoods | Implementing a scientific review; conducting research to establish baseline values integration of gender and youth into livelihoods component; outreach and branding strategy; reducing the middle men; processing locally; adding value. | Due to the rural area in which component three takes place self-sustainability is essential. The nature of the project lends to the reduction in the middle men; local processing; and adding value to the community. | CEO: M TM: M PM: M |
| Forest fires | Mitigate with prescribed burns; increasing community training about how to mitigate burns and protect pilot sites through development of prescribed burn plans. | The Forestry Unit is in consultation with ICCF which has members with over 50 years of forestry management experience combined. This source of knowledge combined with their own standards and practices should allow for proper Forestry management. | CEO: M TM: M PM: M |
| Other risks identified during implementation |  |  |  |
| Data collection risk, in terms of non-validated reports or other data that could be incorrect or misstated. | A focus of this project will be the development of new partners and new data sources beyond the project itself, moving toward a scenario with multiple data sources, some of which will be sources that can be used to validate other claims of progress or results. Example: the partnership with National Bureau of Statistics in Nigeria. | Quality control and quality assurance measures to be identified and implemented to ensure data accuracy and validity | CEO: N/A |
|  |  |  | TM: H |
|  |  |  | PM: H |
| Partners, having made implementation commitments and set goals, back away from or abandon their goals as deadlines approach. | Broadly speaking, the project serves to support the partners and help them maintain progress on reaching their goals by providing a beneficial non-partisan political exposure, which partners will gain through their participation. The project will closely track partners’ implementation to ensure that they deliver on their commitments. Specific webinars and one-on-one sessions will be organized with those partners which achieve commitments to share their success stories and best practices. | Partners are still committed to the fulfilment and success of the project. All responsible agencies and steering committee members are still fully engaged. Monthly meetings and continued communication is utilized to keep activities on schedule and keep members engaged. | CEO: N/A |
|  |  |  | TM: M |
|  |  |  | PM: H |
| Drafted and proposed legislation is not passed into law | Project activities tap the right expertise through GLOBE’s extensive partnerships to inform and justify needed policy changes. Chapter and/or executive‐level engagement activities create the necessary political will, momentum, and leadership for change. Legislation is the ideal to which the project will aspire, but where immediately feasible, regulatory responses may be sought in the interim. The project-proposed legislation changes will be explained comprehensively and put in an international context in order to increase cross-party ownership and support. | Several government agencies including Minister of Agriculture have expressed strong interest in components of the projects. Several government departments are the responsible agencies for varies component activities, the integral nature of the varies departments relationship to the project lends to legislation being proposed to further the project. | CEO: N/A |
|  |  |  | TM: M |
|  |  |  | PM: M |
| ESERN [add cells as appropriate to capture all Medium and High Risks] |  |  |  |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2017 rating [previous] | FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- | --- |
| Missing | S | M-S | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below The risk rating has not changed significantly from the last PIR assessment in that the problems for the project in respect to inability to provide required technical and financial reporting and the consequent hold on disbursement prevailed over most of the review period. However, the BEST Commission was able to comply with the outstanding reporting by the start of 2019 that triggered the second disbursement, and combined with the recruitment of a dedicated project manager has demonstrated tangible movement toward reducing the implementation risk. The risk of non-engagement of the key partner in Component 3, the Bahamas Agricultural and Industrial Corporation (BAIC) remans a concern and the project must take proactive steps to ensure there is progress; the same applies to all stakeholders. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM : There has been a change in operational Focal point (Director of BEST Commission) and a new dedicated NPC for the Project is being recruited to assume duties by mid- July 2019. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The recruitment of a dedicated PM with full-time responsibility expected to accelerate implementation |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | x |  |  |  |  |  | PM : The BEST Commission has designated individuals from each agency, and often meets with them, the issue arises in trying to schedule all the partners to be in one place at the same time. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: There must be a more concerted effort to bring the project partners to oversee and participate in implementation |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM Frequent meetings are held at the BEST commission among staff members. Constant communication. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  |  |  | x |  |  | PM: Major delays or changes in work plan or method of implementation in regards to possible extension of project time line. |  |  |  | X |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The delays will force a change in the implementation plan with possible budget implications. This needs to be addressed soonest |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | x |  |  |  |  | PM: Co-financing for the project is secured but payments are slow and bureaucratic |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Most of the co-financing is to be in-kind. The project management has to ensure that there is adequate capture of reporting by partners |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | x |  |  |  |  | PM: Minor budget reallocation needed; some budget items were severely underestimated during initial design. Additionally, the tax rate has increased in the Bahamas. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: There was minimal reported expenditure due to halt in disbursements. The budget needs to be rephased to facilitate resumption of activities |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  |  | x |  |  |  | PM: Only 2 cash disbursements have been issued on the project, with the second disbursement taking much longer than anticipated due to the bank rejecting the payment |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This has been a major issue during this period. Indeed the disbursement was delayed due to issues with the bank transfer that had to be rectified with UN Treasury |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  |  | x |  |  |  | PM: Reports have been delayed in the past which has resulted in lack of cash disbursements and consultants have refused to release reports pending payments. A new dedicated NPC will be brought on to the project in July. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This issue was at the core of the project delays that triggered the cash flow issues in the project. This challenge has been worked out. It is anticipated that with a full-time manager this issue will be addressed moving forward. |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  |  | x |  |  |  | PM: There has been some engagement from stakeholders, however there is a lack of interest from some partners on how delayed timeline can affect other aspects of project components. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This constitutes a significant risk to the project and the PMU must address this now that the project has received funds, with a new PM coming on board |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | x |  |  |  |  | PM There have been bi weekly meetings with some project partners, however there needs to be joint meetings between all agencies with higher frequency. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed. It is of highest priority to institute regular PMC meetings and ensure where not feasible to bring all to the rook to cater so that there can be remote participation |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  | x |  |  |  |  | PM: The project is resolving the issues as they are brought forward. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | x |  |  |  |  |  | PM: Project based on sound science and well-established technologies | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | x |  |  |  |  |  | PM: Project decisions and choices are not particularly politically driven | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed that is not a significant issue, but the project should not entirely lose sight. There should be some level of high policy level championship |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | x |  |  |  |  |  | PM: Political context is stable and safe | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  |  |  | x |  |  | PM: Project area has very harsh environmental conditions (Hurricane and other adverse weather) |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  |  | x |  |  |  | PM: Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | x |  |  |  |  | PM: Weaknesses exist but have been identified and actions is taken to build the necessary capacity |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This has been a critical issue. It is expected that this will change when the new project manager is brought on board. |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| 1 | Administrative changes | There has been some changes to the Political focal point and signatories on the project accounts which has resulted in administrative changes. | Very little could be done to mitigate against the departmental changes. It is suggested that the project discuss in a steering committee meeting possible risk mitigation measures such as informative talks for new authorities and or changes in strategies for execution. | The Implementation agency ‘The BEST Commission’ was affected by the departmental change. | On-rolling basis. |
| 12 | Weather | If a severe enough weather phenomenon passes through the area (E.g., Hurricane) the damage could be so destructive that it sends the project back to the beginning stages and may require all ground work to be re-done. | Not much action can be taken against a hurricane, all that can be done is to monitor the storms and make sure everyone is aware of the situation on the ground, with all the equipment being kept in a secure and dry place to minimize losses. All work done on the ground will be at risk of being damaged or lost. | The Project Manager is to keep everyone informed via the Implementation agency, in this instance ‘The BEST Commission’ | On-rolling basis. |
| 3 | New tax introduced/ Fiscal Changes. | The administration has reviewed all current financial obligations and as a result they created a new budget for the fiscal year, and in order to meet the co-finance requirements it was vital the project partners understand the whole process of co finance. | Explain the importance of the project and the importance of the co-financing to the new administration so it can be added into the new fiscal year budget. | The implementing Agency ‘The BEST Commission’. | On-rolling basis. |
| 4 | Lack of Funds Disbursed | As a result in the lack of funds on the project all activities have been put on hold, holding up the project until the funds have been received | Provide all the background and background information required to receive funding. Quickly address all points raised, | The Executing Agency ‘UNEP’ BEST to submit reports on time | On rolling basis. |
| 5 | Lack of reporting | As a result in the lack of funds on the project all activities have been put on hold, holding up the project until the funds have been received | Provide all the background and background information required to receive funding. Quickly address all points raised, | BEST to submit reports on time | On rolling basis. |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2016 rating | FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- | --- |
| N/A | Missing | Substantial | M-S | The capacity limitations in terms of dedicated project management was a main challenge that plagued the project in the previous reporting period that essentially caused a halt on disbursements due to non-compliance in reporting. The BEST Commission has addressed this situation by recruitment of a dedicated project manager, and it is anticipated that this situation will improve. The project stakeholder engagement process has to be re-initiated moving forward, with a high level of emphasis to ensure commitment. Ensuring that project steering committee meetings are convened regularly and supporting the partners as needed, must be given a close level of attention. |
|  |  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |
|  |  |  |  | A risk management plan under the previous period was generally put into operation that resulted in firstly the update of the outstanding reporting that permitted the disbursement of new funding, and the process toward recruitment of a dedicated project manager. |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

To be provided by the UNEP Task Manager

Only for Substantial to High risk.