PROJECT IMPLEMENTATION REPORT (PIR)

for the project:

GEF-7 INCLUSIVE CONSERVATION INITIATIVE (ICI)

FY26

July 1, 2025 – June 30, 2026

Executing Partners

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Title: | Inclusive Conservation Initiative |  |  |
| Country(ies): | Global | GEF ID: | 10404 |
| GEF Agency(ies): | Conservation International, IUCN | Duration In Months: | 68 months |
| Executing Agency(ies): | CI’s Center for Communities and Conservation, IUCN Human rights in Conservation Team, Sotz’il, FENAMAD, Observatorio Ciudadano, Fundación Ambiente y Recursos Naturales, ANAPAC, Ujamaa Community Resource Team, IMPACT, Indigenous Peoples’ Foundation for Education and Environment, Nepal Federation of Indigenous Nationalities, House of Ariki, Bose Vanua o Lau, -CI-Fiji | Actual Implementation Start Date: | February 15, 2022 |
| GEF Focal Area(s): | Biodiversity | Expected Project Completion Date: | October 31, 2027 |
| GEF Grant Amount: | USD 22,535,780 | Expected Financial Closure Date: | April 30, 2028 |
| Expected Co-financing: | USD 90,384,856 | Date of Last Steering Committee Meeting: | ICI GSC meeting (Virtual) – Session – The SC meeting was held on June 17, 2026. |
| Co-financing Realized as of June 30, 2026: | USD $22,312,040 (CI) USD $10,242,972 (IUCN) | Mid-Term Review-Planned Date: | January 2025 |
| Date of First Disbursement: | April 17, 2024 | Mid-Term Review-Actual Date: | August 2025 |
| Cumulative disbursement as of June 30, 2026: | USD 7,968,516 (CI) USD 5,800,036 (IUCN) | Terminal Evaluation-Planned Date: | July 2027 |
| PIR Prepared by: | PMU | Terminal Evaluation-Actual Date: | TBD |
| IUCN-GEF and CI-GEF Project Managers: | Joshua Schneck, Free de Koning | CI-GEF Finance Lead: IUCN-GEF finance lead: | Shannon Wiecks Sakdiset Phlasrirojn |

The CI-GEF Project Agency Project Implementation Report (PIR) is composed of seven sections:

Section I:    General Project Status Summary: provides a brief summary of the project as well as a table summarizing the trend on implementation progress rating, development objective rating, and overall project risk rating;

Section II:   Project Performance: describes the progress made towards (a) achieving the project objective and outcomes since the start of the project and (b) delivery of outputs and implementation of activities as well as recommendations to improve the project performance, when needed;

Section III:  Key Risks Status and Rating describes the progress made towards managing and mitigating project risks, the project risks mitigation rating reassessment as needed, as well as recommendations to improve the management of project risks;

Section IV:  Project Environmental and Social Safeguards Implementation Status and Rating: describes the progress made

towards complying with the Environmental & Social Safeguards and the Plans prepared during the PPG phase, the

safeguard plans implementation rating, as well as recommendations to improve the project safeguards;

Section V:  Project Implementation Experiences and Lessons Learned: describes the experiences learned by the project managers and the lessons learned through the process of implementing the project; and

Section VI: Project Geocoding: documents the precise and specific geographic location(s) of activities supported by GEF

Investments based on information available in Project Document.

Section VII: Minor Amendment: describes the changes to the project design or implementation that do not have significant impact 	    on the project objectives or scope, or an increase of the GEF project financing up to 5%

SECTION I: GENERAL PROGRESS STATUS SUMMARY

SUMMARY OF RATINGS AND TRENDS

| PROJECT PART | PRIOR FY25 PROGRESS RATING | CURRENT FY26 PROGRESS RATING | RATING TREND |
| --- | --- | --- | --- |
| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | S | S | Unchanged |
| IMPLEMENTATION PROGRESS (OUTPUTS AND ACTIVITIES) RATING | S | S | Unchanged |
| OVERALL PROJECT RISK RATING | M | M | Unchanged |

# SECTION II: PROJECT PERFORMANCE

This section describes the progress made since the start of the project towards achieving the project objective and outcomes, the implementation progress rating of the project, as well as recommendations to improve the project performance. This section is composed four parts:

a. Progress towards Achieving Project Expected Objective: this section measures the likelihood of achieving the objective of the project

b. Progress towards Achieving Project Expected Outcomes (by project component)

c. Overall Project Results Progress Rating, and

d. Recommendations for improvement

## a. Progress towards Achieving Project Objective and Outcomes (Development Objective):

This section of the report assesses the progress in achieving the objective of the project.

| PROJECT OBJECTIVE: | The objective of this project is to enhance Indigenous Peoples’ and Local Communities’ (IPs and LCs) efforts to steward land, waters and natural resources to deliver global environmental benefits. |
| --- | --- |

| OBJECTIVE INDICATORS | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- |
| - B. IPLC Terrestrial protected areas created or under improved management for conservation and sustainable use (Hectares) (Target: 4,551,701 ha) | 5,337,522 ha | IS | All 10 ICI subprojects continued implementing priority actions as per their impact strategies to improve protected areas management. As of June 2026, the project cumulatively reported 5,337,522 ha under improved management through activities supporting ICCA registration, territorial and biocultural mapping, the development of management plans and co-management agreements, territorial monitoring and strengthened collaboration with local and national governments to advance participatory governance and long-term conservation. Management effectiveness was measured using the ManGo tool. |
| 1.1. Terrestrial protected areas newly created (ha) (Target: 783,000 ha) | 0 ha |  |  |
| 1.2 Terrestrial protected areas under improved management effectiveness (ha) (Target: 3,768,701 ha) | 5,337,522 ha |  |  |
| 3.C Area of land restored (Hectares) (Target: 14,314 ha) | 523,764 ha | IS | As of June 30, 2026, the project cumulatively reported 523,764 ha of restored land within project territories through activities including reforestation and the restoration of areas degraded by mining. Of this, 507,736 ha specifically represents the restoration of natural grasslands and shrublands in Tanzania, supported through a holistic rangeland management approach implemented by UCRT Tanzania. The practice combines Indigenous and traditional knowledge with planned rotational grazing and the establishment of grazing blocks. This approach helps regulate grazing pressure, allows degraded areas sufficient time to recover, and supports the regeneration of native grasses and shrubs. |
| 3.1. Area of degraded agricultural lands restored (ha) (Target: 5,000 ha) | 7,916 ha |  |  |
| 3.2. Area of forest and forest land restored (ha) (Target: 9,314 ha) | 8,112 ha |  |  |
| 3.3. Area of natural grass and shrublands restored (ha) (Target: 0 ha) | 507,736 ha |  |  |
| 3.4. Area of wetlands (including estuaries and mangroves) restored (ha) |  |  |  |
| 4. Area of landscapes under improved practices (excluding protected areas) (Hectares) (Target: 2,883,851 ha) | 3,616,273 ha | IS | All 10 ICI subprojects continued implementing priority actions under their Impact Strategies to improve the management and sustainable use of landscapes outside protected areas. As of June 30, 2026, the project cumulatively reported 3,616,273 ha under improved landscape management through activities including strengthening IPLC traditional governance, biocultural and territorial mapping, the development of Life Plans, Biocultural Protocols, and Community Management Plans, community livelihood initiatives, community monitoring, environmental education, traditional knowledge programs, and land registration. |
| 4.1. Area of landscapes under improved management to benefit biodiversity (qualitative assessment, noncertified) (ha) (Target: 1,541,302 ha) | 2,835,279 ha |  |  |
| 4.2. Area of landscapes that meet national or international third-party certification and that incorporates biodiversity considerations (ha) |  |  |  |
| 4.3. Area of landscapes under sustainable land management in production systems (ha) (Target: 1,342,549 ha) | 780,994 ha |  |  |
| 4.4. Area of High Conservation Value Forest loss avoided (ha) |  |  |  |
| 5. Area of marine habitat under improved practices (excluding protected areas) (Hectares) (Target: 165,200 ha) | 232,482 ha | IS | As of June 2026, the project has contributed to improved management of 232,482 ha of marine habitat across the Pacific and Guna Yala in Panama through marine mapping, traditional governance, and community-led management of customary fishing grounds and LMMAs. These efforts have strengthened community decision-making and governance, supported adaptive management through citizen science and fisheries data, and promoted the sustainable use of coastal and marine resources. Complementary activities such as mangrove conservation, the development of coastal and marine management strategies, restoration of traditional knowledge and measures to address lionfish and marine debris have further strengthened locally led marine conservation and governance. |
| 5.1. Number of fisheries that meet national or international third-party certification that incorporates biodiversity considerations (Contextual Sub-Indicator) |  |  |  |
| 5.2. Number of Large Marine Ecosystems with reduced pollution and hypoxia (Contextual Sub-Indicator) |  |  |  |
| 5.3. Amount of Marine Litter Avoided (Contextual Sub-Indicator) |  |  |  |
| 6. Greenhouse Gas Emissions Mitigated (metric tons of CO2e) (Target: 20,862,368 mt) | 67,117,739 mt | IS | A preliminary portfolio-wide assessment using the FAO Ex-Ante Carbon-balance Tool (EX-ACT) estimates a mitigation potential of 67,117,739 ￼ of CO₂e across all 10 subprojects over the 20-year accounting period, equivalent to approximately 322% of the approved target of 20,862,368 metric tons of CO₂e. The estimate is reported under Sub-Indicator 6.1, as the quantified benefits arise primarily from Agriculture, Forestry and Other Land Use (AFOLU) interventions. The figure is provisional and based on project data, EX-ACT Tier 1 default factors and, where necessary, proxy assumptions. It should therefore be interpreted as an estimated mitigation potential rather than a fully verified achievement and will be further refined in FY27 as additional site-specific data become available. |
| 6.1. Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry and Other Land Use (MtCO2e) | 67,117,739 mt |  |  |
| 6.2. Emissions avoided (through interventions in sectors other than the Agriculture, Forestry, and Other Land Use sector) (MtCO2e) |  |  |  |
| 6.3. Energy saved (megajoules) (Contextual Sub-Indicator) |  |  |  |
| 6.4. Increase in installed renewable energy capacity per technology (megawatts) (Contextual Sub-Indicator) |  |  |  |
| 11. Number of direct [beneficiaries] disaggregated by gender as co-benefit of GEF investment (Target: 142,514), (50% m, 50% w)) Disaggregation: Subprojects (Component 1), Target: 141,174 Global (Components 2-4), Target: 1,340 Total Direct Beneficiaries Target: (142,514) | Cumulative Total: 128,362, Men 65,164 (51%) and Women 63,198 (49%) | IS | As of June 2026, the project had reached 128,362 direct beneficiaries across all components through direct support and engagement. Of these, 65,164 (51%) were men and 63,198 (49%) were women. Disaggregation: The breakdown of direct beneficiaries and partners by component is provided below. Component; Men; Women; Total. Component - 1; 63,536; 61,211; 124,747. Component - 2; 1,437; 1,781; 3,218. Component - 3; 115; 126; 241. Component - 4; 38; 45; 83. Component - 5; 38; 35; 73. Total; 65,164; 63,198; 128,362. Percentage; 50.77%; 49.23%. |

This part of the report assesses the progress towards achieving the outcomes of the project.

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING9 | COMMENTS /JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 1: Local IPLC Action to Deliver Global Environmental Benefits (GEB): Established on-the ground projects led by IPLC organizations. |  |  |  |  |  |
| OUTCOME 1.1: Inclusive Conservation Initiative (ICI) Subprojects are led by IPLC organizations. | Outcome Indicator 1.1.A: Number of direct beneficiaries disaggregated by gender. | Outcome Indicator Target 1.1.A: 141,174 direct beneficiaries disaggregated by gender | Total individuals as IPLC partners engaged: Cumulative Total: 124,747, Men 63,536 (50.93%) and Women 61,211 (49.06%) | IS | Indicator 1.1.A is under implementation. All 10 ICI subprojects have been implementing their priority actions as outlined in their annual workplans and Impact Strategies to contribute to this outcome. |
|  | Outcome Indicator 1.1.B: Percentage of beneficiaries of ICI subprojects that report increased livelihood benefits to the communities. (Gender disaggregated) | Outcome Indicator Target 1.1.B: ≥50 % of beneficiaries of ICI projects report increased livelihood benefits (50% of those beneficiaries will be women). | 91.1% of surveyed beneficiaries reported increased livelihood benefits (286 of 314 verified respondents). This included 90.4% of women (151 of 167) and 91.8% of men (135 of 147). Women represented 52.8% of all respondents reporting increased livelihood benefits (151 of 286). | IS | The ICI Mid-Term Livelihood Benefits Survey was conducted across the 10-subproject portfolio to assess progress against Outcome Indicator 1.1.B. Following data verification and quality assurance, 314 responses were received from verified beneficiaries, including 167 women (53.2%) and 147 men (46.8%). Overall, 286 respondents (91.1%) reported that ICI support had contributed to increased livelihood benefits for themselves, their households, or their communities. This included 151 women (90.4% of female respondents) and 135 men (91.8% of male respondents). Women represented 52.8% of all beneficiaries reporting increased livelihood benefits. The main benefits reported included improved skills, knowledge, and technical capacities (55.2%), strengthened traditional livelihoods and cultural practices (54.5%), and improved women’s economic participation (43.4%). The mid-term result therefore exceeds the indicator target of at least 50%, including the requirement that women constitute at least 50% of beneficiaries reporting increased livelihood benefits. These findings will serve as a benchmark for comparison with the endline survey. |
|  | Outcome Indicator 1.1.C: Percentage of ICI subprojects integrating Gender Responsive strategies. | Outcome Indicator Target 1.1.C: 100% of ICI projects integrating Gender Responsive strategies | 100% 10 out of 10 subprojects have incorporated gender action plans into their Impact Strategies | CA | Indicator 1.1.C has been achieved. All subprojects finalized their Impact Strategies, with 100% integrating gender-responsive approaches through Gender Action Plans. These actions have been incorporated into annual workplans to support implementation and monitoring. |
|  | Outcome Indicator 1.1.D: Number of subprojects that have secured additional funding through Impact Strategy activities implemented to support economic and financial sustainability | Outcome Indicator Target 1.1.D: 10 subprojects have secured additional funding (in addition to GEF allocation) | 10 Subprojects. Overall ICI reported a cumulative total of USD 5,486,975 of co-financing | IS | Indicator 1.1.D is under Implementation. Co-finance contributions will continue and are expected to increase as all 10 ICI subprojects continue implementing their project activities on the ground. |
| OUTCOME 1.2: Project implementation capacity of IPLC partner organizations in subproject geographies substantially increased. | Outcome Indicator 1.2.A: Number of ICI subproject lead organizations showing improvement against organizational capacity assessment baselines | Outcome Indicator Target 1.2.A: At least 10 ICI partner organizations show at least a 20% improvement in organizational capacity assessments. | All ICI 10 subprojects are actively implementing capacity-building activities and training outlined in their impact strategy and annual workplan. | IS | Indicator 1.2.A is under implementation. Organizational capacity-building plans across the 10 subprojects are at varying stages of development, informed by organizational capacity assessments covering five key areas: human resources, financial resources, management systems, strategic planning and programme delivery. In several subprojects, capacity-building priorities identified through these assessments have already been integrated into ongoing project implementation and are being advanced. For the remaining subprojects, organizational capacity-building plans are currently being finalized and are expected to be implemented beginning in Q1FY27. |
|  | Outcome Indicator 1.2.B.: Number of ICI subprojects that incorporate youth in project designs. | Outcome Indicator Target 1.2.B.: At least two youths (one male, one female) involved in execution team in each subproject. | 10 subprojects have reported a Total of 57 (Male – 23(40%) and Female 34 (60%)) youth involved in their project execution team during this reporting period. Disaggregation: 1. NEIFN Nepal, (T- 15, F – 11, M – 4) 2. IPF Thailand, (T- 5, F – 3, M – 2) 3. UCRT Tanzania, (T- 2, F –1, M – 1) 4. Sotz’il Guatemala, (T- 2, F- 1, M- 1) 5. ANAPAC DRC, (T- 5, F – 2, M – 3) 6. IMPACT Kenya, (T- 8, F – 6, M – 2) 7. FENAMAD Peru, (T- 4, F – 1, M – 3) 8. Futa Mawiza Chile, (T- 5, F – 2, M – 3) 9. Fiji & Cook Island, (T- 4, F – 3, M – 1) 10. Argentina, (T- 7, F – 4, M – 3) | IS | Indicator 1.2.B is under implementation as scheduled. All subprojects have incorporated youth involvement in execution providing opportunities for intergenerational transfer of traditional knowledge and youth leadership. |

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING9 | COMMENTS/ JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 2: Global IPLC Capacity Building: IPLC capacity strengthened to improve management of lands, territories, waters and natural resources and increase access to public and long-term sustainable financing mechanisms. |  |  |  |  |  |
| OUTCOME 2.1: IPLC capacity substantially strengthened within and beyond ICI subproject geographies. | Outcome Indicator 2.1.A: Number and percentage of IPLC trainees who successfully complete ICI Learning Academy training modules (disaggregated by gender, person-hours of capacity building, affiliation, country, theme). | Outcome Indicator Target 2.1.A: At least 400 IPLC trainees successfully complete ICI Learning Academy training modules. At least 50% are women, and at least 25% are from outside the subproject geographies. | A cumulative total of 1,082 trainees completed the self-paced ICI Learning Academy course on Indigenous Peoples and Local Communities, Gender and Biodiversity Linkages, exceeding the target of 400, including 476 participants who self-identified as Indigenous Peoples. women represented approximately 43.2% of completers . In the latest cohort, 589 of 721 completers (81.7%) were from countries outside the ICI subproject geographies, exceeding the 25% target. | IS | Indicator 2.1.A remains under implementation. The overall course completion target has been substantially exceeded; however, women’s participation remains below the target of at least 50%. Continued targeted outreach and learner-engagement measures will support increased course completion among women. |
|  | Outcome Indicator 2.1.B: Capacity building modules developed with support of GEF Inclusive Conservation Learning Academy, including sections on gender. | Outcome Indicator Target 2.1.B.: At least 6 capacity building modules are developed with support from GEF Inclusive Conservation Learning Academy, including sections on gender. | 1 of 6 ICI learning modules, IPLCs, Gender and Biodiversity Linkages, has been successfully developed and launched and remains publicly accessible on the UNDP Learning for Nature platform. | IS | Indicator 2.1.B is under implementation. The PMU is developing five additional learning modules to support IPLC leadership in conservation. |
| OUTCOME 2.2: Cross-regional IPLC organization partnerships and networks strengthened through ICI Learning Exchanges. | Outcome Indicator 2.2.A: Number of new cross-regional collaborations documented. | Outcome Indicator Target 2.2.A: ≥4 cross-regional collaborations [*At least 4 cross-regional collaborations documented to strengthen collaboration outside subproject geographies and build linkages with the ICI Community of Practice] | 7 ICI Learning Exchanges (4 – Regional Learning Exchanges: 1. Asia, 2. Africa, 3. Latin America and 4. Pacific) and 3 – Global Learning Exchanges: 1. Global Learning Exchange during UNCBD, COP16 in Cali Colombia, 2. IUCN WCC Abu Dhabi and 3. GEF Assembly, Canada) | IS | Outcome Indicator 2.2.A remains under implementation. Cumulatively, seven ICI Learning Exchanges have been successfully conducted. The Global Steering Committee has also agreed to explore the possibility of organizing an eighth Learning Exchange alongside the project close-out and final GSC meeting, tentatively planned for February or March 2027. The format and location will be determined based on the remaining Learning Exchange budget and any additional co-financing secured. |
|  | Outcome Indicator 2.2.B: Percentage of IPLC organizations that report greater capacity to advance IPLC-led conservation after participating at Learning Exchanges (disaggregated by gender, affiliation, country, theme). | Outcome Indicator Target 2.2.B.: ≥75% IPLC organizations reporting greater capacity [At least 75% of IPLC Organizations report greater capacity to advance IPLC-led conservation after participating in Learning Exchanges (disaggregated by gender, affiliation, country, theme). | Cumulative Progress 7 learning exchanges against target: 100% of IPLC organizations reported greater capacity to advance IP- and LC-led conservation after participating in the ICI Learning Exchanges, exceeding the target of at least 75%. IPLC organizations: A cumulative total of 52 unique IPLC organizations reported increased capacity. Survey respondents: The finding is supported by 79 respondents, comprising 43 men (54.4%) and 36 women (45.6%). Geographic coverage: Respondents represented 24 countries across the seven ICI Learning Exchanges. | IS | Indicator 2.2.B remains under implementation. Cumulatively, seven ICI Learning Exchanges have been conducted, comprising four Regional Learning Exchanges in Asia, Africa, Latin America, and the Pacific, and three Global Learning Exchanges held in Canada; Cali, Colombia; and Abu Dhabi. Post-Exchange feedback indicates that 100% of the 52 unique responding IPLC organizations reported greater capacity to advance IP- and LC-led conservation. Respondents highlighted strengthened knowledge and practical capacity in Indigenous governance, conservation management, policy engagement, gender equality, climate resilience, sustainable finance, and organizational networking. The indicator result is based on the six post-Exchange surveys that included a comparable question on increased capacity. Feedback from the IUCN World Conservation Congress was reviewed but excluded from the percentage calculation because its survey did not contain the same question. |
| OUTCOME 2.3: IPLC organizational capacity increased to formulate sustainable financing strategies. | Outcome Indicator 2.3.A: Number of ICI subproject lead organizations that have a fully developed sustainable financing strategy. | Outcome Indicator Target 2.3.A: 10 ICI subproject lead organizations [At least 10 ICI subproject lead organizations have a fully developed sustainable financing strategy] | 0 of 10 ICI subproject lead organizations had completed a fully developed sustainable financing strategy | IS | Outcome Indicator 2.3.A remains under implementation. Following the October 2024 GSC decision, Output 2.3.1 was adjusted to provide practical support for resource mobilization through Catalytic Grants. All 10 initiatives began sustainable financing activities and submitted a total of 11 Catalytic Grant proposals (Fiji and Cooks were submitted separately). Grant agreements were completed for all participating organizations, with each organization eligible to access up to USD 10,000 to pursue funding opportunities and strengthen long-term financial sustainability. The grants are supporting organizations to prepare funding proposals, develop fundraising strategies, identify and engage potential donors, diversify partnerships, and position their priorities for future financing opportunities, including the GEF-9 replenishment cycle. Progress also advanced on the Finance Mapping Study, which will identify relevant funding opportunities and barriers affecting IPLC access to conservation finance. These activities are expected to inform the development and finalization of sustainable financing strategies for all 11 ICI organizations receiving catalytic funds. |
|  | Outcome Indicator 2.3.B: Percentage of ICI subproject lead organizations that report greater capacity in proposal development, fundraising and implementation of sustainable financing strategies. | Outcome Indicator Target 2.3.B: ≥60% ICI subproject lead organizations [At least 60% of ICI subproject lead organizations report greater capacity in proposal development, fundraising and implementation of sustainable financing strategies.] | 0% | IS | Outcome Indicator 2.3.B remains under implementation and is closely linked to progress under Indicator 2.3.A. During the reporting period, all 10 ICI subproject lead organizations engaged in practical sustainable-financing activities through the preparation and submission of 11 Catalytic Grant proposals. These activities are supporting organizations to strengthen proposal development, identify funding opportunities, engage potential donors, and diversify their financing sources. The planned virtual training series, adapted from the IPFAF Capacity-Building Module, has been rescheduled to Q1–Q2 FY27 to align with subproject workloads. As the training and grant activities are still being implemented, the percentage of organizations reporting increased capacity has not yet been formally assessed and will be measured through a follow-up capacity assessment. |

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 3: IPLC Leadership in International Environmental Policy: Building the pathway from local action to global impact through targeted engagement in international environmental policy and relevant international platforms. |  |  |  |  |  |
| OUTCOME 3.1: Strengthened influence of IPLC in relevant regional and international decision-making processes. | Outcome Indicator 3.1.A: Number of IPLC leaders with greater opportunity to influence international environmental policy with support of ICI (disaggregated by gender, affiliation, IPLC status, county, convention, and accreditation). | Outcome Indicator Target 3.1.A.: ≥400 IPLC leaders; 50% women. [At least 400 IPLC leaders, 50% of whom are women, report greater opportunity to influence international environmental policy with support of ICI.] | Cumulative Total IP and LC leaders: 105 (Men: 65 (61.9%) and Women: 40 (38.1%) Disaggregation Policy Level Events FY26: - New York Climate Week, September 2025: From Pledge to Practice: Transforming Climate and Biodiversity Finance through Indigenous-Led Action Men – 3, Women – 3: - COP 6- Minamata Convention on Mercury held in Geneva, Switzerland: Men – 0 (0%) and Women – 2 (100%)) - 8th GEF Assembly held in Samarkand, Uzbekistan, RoundTable on Leaving No One Behind, Panel on Territorial Management and Community Leadership/ ICI Event on Indigenous Leadership Delivering Global Biodiversity Benefits: Men-6/Women 6 - ICI Global Learning Exchange - IUCN WCC held in Abu Dhabi: Total 20, Men – 12 (60%) and Women – 8(40%) | IS | Indicator 3.1.A is under implementation. During this reporting period, the PMU supported 105 IP and LC leaders to engage in high level policy events, including COP 6- Minamata Convention on Mercury – Geneva, New York Climate Week, 8th GEF Assembly - Samarkand, Uzbekistan and the ICI Global Learning Exchange IUCN WCC- Abu Dhabi. |
|  | Outcome Indicator 3.1.B: Number of ICI partners engaging with and providing technical support to national delegations at international policy meetings (disaggregated by gender, affiliation, country, convention). | Outcome Indicator Target 3.1.B.: 40 ICI delegates (of whom 50% are women) engaging with and providing technical support to national delegations at international policy meetings (disaggregated by gender, affiliation, country, convention).] | Cumulative Total IP and LC leaders: 105 (Men: 65 (61.9%) and Women: 40 (38.1%),provided with technical support to their constituencies and actively engaging with national delegations at international policy meetings particularly COP 6- Minamata Convention on Mercury, Geneva, Switzerland, 8th GEF Assembly - Samarkand, Uzbekistan and ICI Global Learning Exchange IUCN WCC - Abu Dhabi. | IS | Indicator 3.1.B is under implementation. The PMU is implementing the Strategic Policy Engagement Calendar focused on major climate and biodiversity events in FY27, including UNCCD COP17 - Mongolia, NY Climate Week – New York, UNCBD COP 17 – Armenia, UNCBD SB – Kenya and UNFCCC COP31 - Turkey. In addition, the PMU has been providing targeted technical support to the IIPFCC under the UNFCCC and the IIFB under the CBD. ICI also supported IPLC participation in the COP 6 Minamata Convention, where the Indigenous Caucus was formally established and the International Indigenous Peoples Forum on Mercury (IIPFM) achieved formal recognition. |

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 4: ICI Knowledge to Action: Transforming Inclusive Conservation Knowledge and Lessons Learned into demonstration models that expand support and advance field of IPLC-led conservation. |  |  |  |  |  |
| OUTCOME 4.1: The field of IPLC-led conservation advanced with improved knowledge management. | Outcome Indicator 4.1.A: Number of ICI publications, reports, communication materials or tools that advance the global field of knowledge regarding IPLC-led conservation. | Outcome Indicator Target 4.1.A.: ≥7 lessons learned and flagship reports [At least 7 lessons learned, and flagship reports prepared to advance the global field of knowledge regarding IPLC-led conservation.] *[5 Lessons Learned reports and 2 flagship reports, .] | 3 Lessons Learned Reports have been produced and published on the ICI Knowledge Platform. - Phase I Lessons Learned Report - Phase II Lessons Learned Report - Phase III Lessons Learned Report | IS | Indicator 4.1.A remains under implementation. During the reporting period, the PMU launched the Phase III Lessons Learned report on August 7th, 2025, and advanced the preparation of the fourth ICI Annual Report, which is scheduled for launch in August 2026, in conjunction with the International Day of the World’s Indigenous Peoples, with the French and Spanish editions expected to follow in October 2026 to be launched during the UNCBD COP17. The ICI Knowledge Platform was fully revamped to provide a more engaging and user-friendly hub for sharing evidence, lessons, and results on IP- and LC-led conservation. Its expanded library includes Regional Learning Exchange outcomes, web stories, podcasts, subproject blogs, policy updates, videos, newsletters, and multilingual communication materials. During the reporting period, ICI content generated more than 21,000 views and reached 2,397 followers across digital channels, further strengthening the visibility and accessibility of the initiative’s knowledge products. Several knowledge products were also developed and published in collaboration with Indigenous Peoples and local community organizations. These included the multilingual ICI Phase Three Report; blogs by ICI Fellows highlighting their experiences and case studies; a podcast series showcasing how Indigenous women are redefining science through ancestral knowledge, lived experience, and community leadership; and videos featuring Indigenous leaders from Chile and Argentina sharing perspectives on protecting nature, sustaining culture, and defending their territories of life. Additional content highlighted the IUCN World Conservation Congress and other global Indigenous events. |
|  | Outcome Indicator 4.1.B: Number of new multiregional partnerships established to strengthen collaboration outside subproject geographies and build linkages with the ICI Community of Practice. | Outcome Indicator Target 4.1.B.: ≥2 new partnerships [At least 2 multiregional partnerships established to strengthen collaboration outside subproject geographies and build linkages among the ICI Community of Practice.] | 02 – Partnerships developed (1 - UNDP for hosting ICI Learning Academy and 1- IIFB) | CA | Indicator 4.1.B has been completed. ICI is strengthening its partnership with UNDP to host ICI learning modules on the UNDP Learning for Nature platform. At the same time, ICI is enhancing collaboration with IIFB to advance the GBF, ensuring the roles, rights, and contributions of IPLCs are recognized and upheld. |
|  | Outcome Indicator 4.1.C: Percentage of IPLC organizations that report greater collaboration after participating in ICI Community of Practice (disaggregated by gender, affiliation, country, theme). | Outcome Indicator Target 4.1.C.: ≥75% IPLC organizations [At least 75% of IPLC Organizations report greater collaboration after participating in Community of Practice (disaggregated by gender, affiliation, country, theme).] | 0 | IS | During FY26, the ICI Community of Practice moved into full implementation and provided regular opportunities for peer learning, knowledge exchange, and collaboration among Indigenous Peoples and local community organizations, ICI Fellows, and project partners. Virtual exchanges, Fellows’ sessions, and in-person engagements strengthened connections across countries and subprojects and supported the exchange of experiences, challenges, and practical approaches. However, the percentage of participating IPLC organizations reporting greater collaboration has not yet been formally measured. Therefore, achievement against the target of at least 75% cannot yet be confirmed. A follow-up assessment will be conducted to determine the percentage of organizations reporting for increased collaboration, with results disaggregated by gender, affiliation, country, and thematic area. |
| OUTCOME 4.2: Expanded audience engaged in IPLC-led conservation. | Number of average monthly visits to the ICI Knowledge Platform. | Outcome Indicator Target 4.2.A.: ~500 average monthly visits [At least 500 average monthly visits to ICI Knowledge Platform. | During the reporting period, there have been over 13,440 views to ICI Knowledge platform, which averages 1,120 Visits per month. | IS | During FY26, the Indicator 4.2 is under implementation. The PMU has actively used the ICI website and social media platforms—including Instagram posts and stories—to share updates, stories, and learning materials. This includes the publication of the ICI Phase III Report in Spanish, English, and French, as well as featured blogs such as: - Connecting Local Challenges to Global Learning: Reflections from Mabula Village - How has long-term fellowship redefined my leadership? - Learning, Leading, and Giving Back: My Journey as an ICI Fellow - Living with Change: Community Adaptation and Climate Learning in Northern Thailand - Turning Traditional Knowledge into Resilience: Through My Fellowship - When Support Arrives On Time: Caring For Life From The Territory The ICI Knowledge Platform continues to serve as a central hub for learning and visibility. Website metrics show steady growth since July 2024, with spikes during key IPLC events such as Indigenous Peoples Day. During this reporting period, the platform received 13,440 views, averaging 1,120 average visits per month. |
|  | Outcome Indicator 4.2.B: Number of members of ICI Community of Practice (disaggregated by gender, IPLC status, county, field of expertise). | Outcome Indicator Target 4.2.B.: ≥500 members (50 participants in bilateral and learning exchanges, 450 participants in virtual events) | 45 (Men 19 (42.22%) and women 26 (57.77%)) participated in the Virtual Technical Exchange: "Ancestral Knowledge, Territory, and Communication" | IS | The ICI Community of Practice (CoP) has moved into full implementation in FY26, continuing to evolve as a collaborative platform for peer learning, knowledge exchange, and inclusive conservation. Structured around a four-phase Design Thinking model—Inspiration, Ideation, Co-development, and Outcomes—the CoP has advanced significantly through a combination of virtual and in-person engagement. Virtual exchanges and Fellows virtual sessions are now being held on an ongoing basis, providing regular touchpoints for peer learning and cross-project dialogue between ICI Fellows and partners. |
|  | Outcome Indicator 4.2.C: Percent increase in project communications index (index to be developed as part of ICI communications strategy including inter alia trends in social media followers, listserv members, website visits) | Outcome Indicator Target 4.2.C.: 10% annual increase in project communications index. | ICI Listserv 32% increase in subscribers Total subscribers 1,208 (Growth of 292 since November 2025) ICI Instagram 29% increase in followers Total Followers 1,488 (growth of 336 followers since November 2025) ICI Knowledge Platform Total visits 13,440 (Average 1,120 visits/month) | IS | Indicator 4.2.C is under implementation. During the reporting period of July 2025 to June 2026, the ICI Knowledge Platform recorded 13,440 total visits, averaging 1,120 visits per month. The ICI Instagram account also showed positive engagement, reaching 1,488 followers with a net increase of 29% since November 2025. The ICI Listserv also grew steadily, reaching 1,208 total subscribers, a 32% increase (292 new subscribers) since November 2025. Steady engagement, supported by event-driven content and visual storytelling, strengthened the project’s digital presence and contributed to the overall improvement of the ICI communications index for the reporting period. |

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATOR | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 5: Monitoring and Evaluation |  |  |  |  |  |
| OUTCOME 5.1: Monitoring and evaluation conducted to verify effective project execution. | Outcome Indicator 5.1.A: Number of satisfactory Project progress reports | Outcome Indicator Target 5.1: 20 satisfactory quarterly Project progress reports produced | 18 ICI Reports (16 quarterly and 2 semiannual reports) | IS | Indicator 5.1.A is under implementation. During the July 2025–June 2026 reporting period, the PMU submitted two semi-annual progress reports to the CI and IUCN GEF Agencies in accordance with the agreed streamlined ICI reporting process. A total of 18 ICI progress reports have bene submitted. |

| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | JUSTIFICATION |
| --- | --- |
| S | All core indicator targets have already been achieved at the aggregate level, except for the number of beneficiaries. At the sub-indicator level, some sub-indicator targets have been overachieved, some are in progress, and for one no results are reported yet (terrestrial protected areas newly created). Good progress has been made at the outcome level, where several targets have already been achieved or overachieved. Targets that have not been achieved yet, including development of capacity building modules; development of sustainable financing strategies; capacity increase in proposal development; fundraising and implementation of sustainable financing strategies; participation in community of practice, are expected to be achieved by the end of the project. The ManGo tool is successfully being applied to track management effectiveness. |

## b. Progress towards Implementation Progress (Delivery of Outputs and Implementation of Activities)

This part of the report assesses the progress towards delivery of outputs and implementation of activities planned for the year.

## Progress: Information on progress outcomes of project implementation activities

During the reporting period, the ICI continued to make steady progress across all five components, advancing Indigenous-led conservation, strengthening IPLC governance and capacity, expanding participation in international environmental policy processes, and enhancing knowledge sharing and learning. Key achievements included the continued implementation of all ten IPLC-led subprojects, two major learning exchanges, the launch and operationalization of catalytic grants, expansion of the ICI Fellowship Program, increased Indigenous engagement in global policy forums, and continued improvements to communications, monitoring, evaluation, and adaptive management systems. Overall, implementation remained on track and contributed to strengthening Indigenous leadership and delivering conservation outcomes at local, national, and global levels. Component 1: Established on-the-ground projects led by IPLCs organizations All ten ICI subprojects remained under active implementation throughout the reporting period, advancing priority actions to strengthen IPs and LCs' rights, governance systems, and stewardship of natural and cultural resources. Subprojects continued implementing activities that address environmental degradation of drivers, strengthen territorial governance, and promote sustainable livelihood and financing opportunities. Across the reporting year, Component 1 activities reached more than 40,000 direct beneficiaries and partners with near gender parity, reflecting continued engagement and participation across project landscapes. The PMU provided ongoing technical support to subprojects through site visits, capacity-building activities, reporting and monitoring support, and guidance on safeguards, gender integration, financial sustainability, and resource mobilization. Site visits conducted in Kenya, Chile, Peru, Guatemala, Argentina, and the Cook Islands strengthened implementation oversight, facilitated adaptive management, and supported subprojects in addressing emerging challenges and opportunities. Component 2: Global IPLC Capacity Building Component 2 focused on strengthening IPLC capacity, peer learning, and access to sustainable financing opportunities. A major milestone was the Third ICI Global Learning Exchange, held alongside the IUCN World Conservation Congress and Indigenous Peoples Summit in Abu Dhabi, which brought together 132 Indigenous leaders from 44 countries, including 23 ICI Indigenous leaders (57% men and 43% women). Survey results demonstrated clear improvements in participant knowledge across Indigenous leadership, equity and inclusion, access to finance, and integration of Indigenous knowledge, while 100% of participating organizations reported establishing new partnerships or collaborations, directly contributing to stronger cross-regional networks and partnerships. Building on this momentum, the Pacific Inclusive Conservation Learning Exchange was convened in the Cook Islands in June/July 2026, bringing together traditional leaders, women, youth, conservation practitioners, and ICI Fellows from nine countries to strengthen regional collaboration on customary governance, climate resilience, and Indigenous-led conservation. Capacity-building efforts were further strengthened through continued development of the Makanisi Learning Academy and expanded support for sustainable financing. The Indigenous Negotiations, Governance, Project Management, and International Environmental Policy modules are advancing development, while a multilingual Training-of-Trainers package was finalized to increase accessibility. In addition, Catalytic Grants for Sustainable Financing were operationalized, with organizations able to access up to USD 10,000 each to pursue new funding opportunities and strengthen long-term sustainability. During the reporting period, grant agreements were completed for all participating organizations to commence implementation. Progress also advanced on a Finance Mapping Study designed to identify funding opportunities and barriers affecting Indigenous Peoples' and Local Communities' access to conservation finance. Component 3: Indigenous Peoples and Local Communities Leadership in International Environmental Policy ICI continued to strengthen Indigenous participation and leadership in international environmental policy processes through its Fellowship Programme and support for engagement in major global forums. During the reporting period, four Fellows from the 2025-2026 cohort participated directly in international environmental policy processes, including the IUCN World Conservation Congress and COP-6 of the Minamata Convention, where they presented case studies and shared Indigenous perspectives on conservation, governance, and environmental challenges. In addition, five Indigenous leaders from Kenya, Tanzania, Thailand, Peru, and the Democratic Republic of the Congo represented ICI at the Eighth GEF Assembly, where ICI leaders contributed to high-level discussions on Indigenous-led conservation, direct access to finance, and the future of Indigenous Peoples' engagement within the GEF. The initiative's experience was highlighted during Assembly discussions as a leading example of Indigenous-led conservation finance and informed conversations around the proposed Indigenous Peoples funding initiative under GEF-9. Building on these achievements, ICI expanded its Fellowship Program by selecting a new cohort of five International Policy Fellows for 2026-2027, exceeding the original target of three fellows through the mobilization of additional resources. The new cohort will focus on sustainable finance, Indigenous and traditional territories, and Indigenous knowledge and governance, while participating in international policy processes and developing policy-relevant case studies. Capacity-building efforts were also advanced through three thematic webinars delivered to Fellows during the reporting period and continued development of the International Environmental Policy Negotiations course focused on the Minamata Convention, with two of three planned modules completed and preparations underway for launch in English, Spanish, and French Component 4: Knowledge to Action ICI expanded its communications and knowledge-sharing efforts to increase the visibility, accessibility, and influence of Indigenous-led conservation. The ICI Knowledge Platform continued to grow its reach, with digital analytics showing 2,397 followers across channels and more than 21,000 content views during the reporting period, including over 17,000 social media views. Knowledge products developed and disseminated during the year included blogs, videos, policy products, newsletters, social media content, and the annual report Walking the Talk: How Inclusive Conservation Is Delivering Results, which was published in English, Spanish, and French to broaden accessibility and outreach. Communications capacity across the portfolio was further strengthened through the development of a new global communications strategy, implementation of a communications training series for subproject teams, and the launch of communications mini-grants supporting locally led storytelling and outreach campaigns. In addition, ICI released a policy brief on direct financing for Indigenous Peoples and Local Communities and launched the Redefining Science podcast series to elevate Indigenous voices and share lessons from the initiative with wider audiences. Regular updates to the ICI website, combined with preparations for a comprehensive website redesign, further strengthened the initiative's role as a platform for knowledge exchange, learning, and policy dialogue across the global ICI network Component 5: Monitoring and Evaluation The project continued strengthening its monitoring, evaluation, and learning system through implementation of Mid-Term Review recommendations, enhanced reporting processes, and expanded technical support to subprojects. Revised reporting tools, semiannual indicator reviews, safeguards monitoring, and technical guidance improved the quality, consistency, and comparability of results reported across the portfolio, while also strengthening gender-responsive monitoring and reporting. Key achievements included the adaptation and piloting of the Indigenous-centered Management and Governance (ManGo) Tool, advancement of Global Environmental Benefits reporting through ICCA and FAO EX-ACT methodologies, and establishment of the ICI Subprojects Core M&E Working Group. Additional learning and evidence-generation efforts included beneficiary livelihood surveys, pre- and post-learning exchange surveys, and field-based monitoring visits, all of which strengthened adaptive management and informed decision-making across the initiative. Progress Toward GEF Global Environmental Benefit As of June 2026, the ICI project is performing strongly against its GEF Global Environmental Benefit targets, with most indicators already meeting or exceeding targets. These results reflect the contributions of all 10 subprojects through strengthened IPLC governance, territorial planning, conservation management, restoration, and sustainable resource use. The project has exceeded its target for terrestrial protected areas under improved management, reaching 5.34 million hectares against a target of 4.55 million hectares. Progress has been driven by territorial and biocultural mapping across most subprojects, the development of management plans and co-management agreements, community monitoring, and stronger collaboration with government partners. While no new protected areas have been formally established, the project has significantly strengthened management effectiveness across existing conservation areas and IPLC territories. For landscapes under improved practices outside protected areas, the project has reached 3.62 million hectares, exceeding the target of 2.88 million hectares. Key activities include biocultural mapping alongside the development of biocultural protocols, the development of Life Plans and Community Management Plans, and sustainable livelihood initiatives such as agroforestry, tourism, and handicrafts. Additional contributions have come from environmental education and traditional knowledge programs that support the revitalization of local knowledge, cultural values, and practices that promote harmony between communities and their territories, as well as community-based monitoring and land registration efforts. The project has also greatly surpassed its land restoration target, reporting 523,764 hectares restored compared to a target of 14,314 hectares. Restoration results have been achieved through reforestation, rehabilitation of mining-degraded lands, and ecosystem restoration efforts led by Indigenous Peoples and local communities, particularly in natural grasslands and shrublands through holistic rangeland management approaches. Results for marine habitats under improved practices have also exceeded expectations, achieving 232,482 hectares against a target of 165,200 hectares across the Pacific and in Panama. Achievements have been driven by marine mapping, traditional governance systems, community management of customary fishing grounds and locally managed marine areas, citizen science, fisheries monitoring, as well as mangrove conservation. The project's estimated greenhouse gas mitigation potential is 67.1 million tCO₂e, more than three times the approved target of 20.9 million tCO₂e. These preliminary estimates are based on EX-ACT analysis and largely reflect the contribution of conservation, restoration, and sustainable land-use interventions. While highly promising, the estimates remain provisional and will be refined as additional field data become available. Finally, the project has reached 128,362 direct beneficiaries, representing approximately 90% of the target of 142,514, with near gender parity (51% men and 49% women). This demonstrates strong progress toward delivering environmental benefits alongside equitable social outcomes for Indigenous Peoples and local communities. Overall, the project is on track to meet or exceed most GEF targets, with particularly strong performance in protected area management, ecosystem restoration, landscape and marine conservation, and projected climate mitigation benefits. A key challenge remains the development and adaptation of monitoring tools that can quantitatively measure improvements in management effectiveness and governance systems that are rooted in Indigenous and local knowledge and practices, while also integrating scientific approaches and data. Strengthening these methodologies will be important to more fully capture the conservation outcomes generated through IPLC-led management and stewardship.

Challenges: Information on challenges of project implementation activities

Learning Module Delays: Delivery of Component 2 learning modules, including the development and launch of several courses, was delayed partly because of reduced staffing capacity on the partner platform originally supporting module development. As a corrective action, the PMU is working with two platforms. The remaining modules will be hosted on an alternative platform with new instructional design support, with launch targeted by Q2 FY27. Site Visit Access Constraints (DRC & Tanzania): During Jan–June 2026, active health risks and regional travel advisories linked to the Ebola outbreak prevented planned monitoring and implementation site visits to ANAPAC (DRC) and UCRT (Tanzania). To maintain project oversight ahead of closure, these visits have been rescheduled to FY27. Futa Mawiza Argentina Operating Context: Subproject implementation continued to navigate a complex and evolving institutional, policy, and environmental context throughout both reporting periods, including shifting territorial governance frameworks, increased extractive industry activity in the region, water scarcity, and reduced availability of national climate-related support. Forest fires were an added strain during this reporting period. Land Use and Consultation Pressures in Peru: Subproject implementation continued to be shaped by competing land-use priorities in the region, particularly those driven by external stakeholders such as local governments and private industries, where extractive activities such as mining and logging are often prioritized over conservation. Ongoing infrastructure development in Indigenous territories led by external actors has also underscored the importance of stronger community engagement in decision-making processes affecting these areas. Operational Constraints in Guatemala and Tanzania: In Guatemala, elevated security conditions in parts of the western highlands led to increased movement restrictions, affecting planned field travel and site visits. In Tanzania, a period of political transition brought increased security measures and periodic restrictions on movement, which limited stakeholder engagement and required adjustments to planned timelines and travel. Regulatory Delays in Thailand: Progress on Subdistrict Ordinances and some Special Cultural Zone declarations was delayed due to legal uncertainties and pending implementation guidance under newly enacted national legislation.

| IMPLEMENTATION PROGRESS (DELIVERY OF OUTPUTS AND IMPLEMENTATION OF ACTIVITIES) RATING | JUSTIFICATION |
| --- | --- |
| S | Good progress was made this fiscal year with the implementation of activities and delivery of outputs. Implementation of all ten IPLC-led subprojects has continued, learning exchanges were organized, and catalytic grants for developing fundraising strategies were delivered. The ICI Fellowship Program was expanded, and communications, monitoring & evaluation, and adaptive management activities were delivered. Some challenges were encountered, such as complex political context, pressure on indigenous territories, and situations affecting field visits including security issues and disease outbreak. |

## c. Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| Ensure that all activities and outputs are on track for completion by the end of the project. Continue to implement the MTR response matrix. | PMU | Ongoing |

# SECTION III: PROJECT RISKS STATUS AND RATING

## a. Progress towards Implementing the Project Risk Mitigation Plan

This section describes the activities implemented to manage and reduce high, substantial, modest, and low risks of the project. This section has three parts:

a. Ratings for the progress towards implementing measures to mitigate project risks and a project risks annual reassessment

b. Recommendations for improving project risks management

Progress towards Implementing the Project Risk Mitigation and Plan Project Risks Annual Reassessment

| PROJECT RISKS | PRODOC RISK DEFINITION AND MITIGATION MEASURE | MITIGATION MEASURES IMPLEMENTATION PROGRESS | PRODOC RISK RATING | CURRENT FY26 RISK RATING |
| --- | --- | --- | --- | --- |
| CONTEXT |  |  |  |  |
| Climate Change: | Risk: Natural disasters (potentially intensified by climate change) delays implementation. Climate risk screening was conducted as part of project safeguards screening. Measures include adaptive management training, supporting community tools, capacity, and information to adapt to change. | This risk is assessed as a Substantial Risk (S). All ICI 10 Subproject safeguard plans are under implementation. The activities have been updated, planned, and budgeted as part of the FY workplan. These activities include safety and security practices in case of natural disasters and other climate irregularities. Throughout the process, the PMU has provided technical targeted support on safeguards virtually and in-person during the site visits in FY26. | Substantial (S) | Substantial (S) |
| Environmental and Social | Risk: Pandemic prevents travel, meetings and fieldwork, delaying implementation. | The risk is currently assessed as Low (L). The project continues to follow CI and IUCN institutional protocols for travel, meetings and fieldwork, informed by security assessments, WHO guidance and relevant national health authority requirements. Adaptive management and flexible activity sequencing are applied as needed to minimize potential implementation delays. Global activities are implemented in accordance with the ICI Environmental and Social Management Plan, including measure C2-4 and the relevant provisions of ESS8, with particular attention to the heightened risks that pandemics may pose to Indigenous Peoples and Local Communities. The risk will continue to be monitored, and mitigation measures will be adjusted if changes in public health conditions affect project implementation. | Moderate (M) (Note: while COVID-19 has posed a significant risk to some populations, the risk is rated M with respect to ability to achieve project results over the course of the project timeline; as efforts to control the pandemic and protect people continue to gain ground, challenges to implementation are expected to diminish) | Low (L) |
| Political and Governance | Risk: Local-level governments conflict with national level governments Subproject selection criteria; guidance from knowledgeable advisors; engagement strategy; grievance mechanism | The risk is assessed as Moderate (M). The PMU engaged Operational Focal Points during site visits to review project progress and obtain feedback. Subprojects also continued to engage local and national authorities to promote alignment, address emerging issues, and reduce the potential for institutional conflict. Subprojects participated in national climate and biodiversity planning processes to demonstrate ICI’s contribution to the implementation of National Biodiversity Strategies and Action Plans and Nationally Determined Contributions. The ICI Accountability and Grievance Mechanism remains operational and is designed to provide an independent, transparent, and accessible process while minimizing the risk of retaliation against complainants. The PMU continued to encourage all 10 subprojects to raise stakeholder awareness of the mechanism and document progress on its dissemination. | Low (L) | Moderate (M) |
|  | Risk: Local social tensions Government and civil instability Conflicts between government and IPLC organizations Subproject selection criteria; guidance from knowledgeable advisors; engagement strategy; grievance mechanism | This risk is assessed as Moderate (M). The PMU has continued to hold periodic follow-up meetings with subproject leads to monitor changes in national and local contexts, assess emerging tensions, and provide guidance on appropriate mitigation measures. The project has also supported the participation of Indigenous Peoples and Local Communities’ representatives in high-level policy forums and global learning exchanges, helping to ensure that their perspectives and priorities are reflected in relevant decision-making processes. No specific grievance cases or conflict-related incidents were reported under this risk during the reporting period. However, the Accountability and Grievance Mechanism remains operational across all 10 ICI subprojects to identify, document, address and monitor grievances, conflicts or social tensions should they arise. Subprojects continue to communicate information on the mechanism to communities and stakeholders within their respective project areas. | Moderate (M) | Moderate (M) |
|  | Risk: Government resistance to IPLC participation ICI training for IPLC participants to include effective engagement of government counterparts | This risk is assessed as a Substantial Risk (S). All ICI 10 subprojects have included engagement of OFPs and key Government agencies in their Stakeholder Engagement Plans (SEPs) and implementation of their Impact Strategies. During site visits, the PMU engaged OFPs to discuss project progress and is also coordinating with the GEF Secretariat and GEF Agencies as needed to provide updates to the OFP regarding the project. Engagement between IPLC with governments will be ongoing throughout the life of ICI. | Moderate (M) | Substantial (S) |
| INNOVATION |  |  |  |  |
| Institutional and Policy | Risk: Weak institutional capacity for planning, management and governance in targeted areas Subproject selection criteria Assessments against GEF Minimum Fiduciary Standard Requirements Training and capacity-building | This risk is assessed as a Moderate Risk (M). The PMU has provided targeted technical support to all subprojects virtually and in-person during their site visits to continue strengthening their capacity for project management, including safeguards and monitoring and evaluation | Moderate (M) | Moderate (M) |
| Technological: N/A |  |  |  |  |
| Financial and Business Model | Risk: Sustainable financing strategies are limited or require a longer timeframe than the project. Potential private sector partners or investors do not wish to engage Targeted capacity building in sustainable finance planning Private sector engagement plans; due diligence screening of potential private sector partners Targeted capacity building in sustainable finance planning | The risk is assessed as Substantial (S). To address this risk, CI developed the Terms of Reference for a consultancy to prepare and deliver a sustainable finance strategies course. The assignment is expected to commence in August 2026 and be completed by January 2027. In parallel, IUCN finalized the Terms of Reference and recruited a consultant to undertake a funding-mapping study. The assignment commenced in June 2026 and is expected to be completed by October 2026. These complementary activities are intended to strengthen the capacity of ICI partners to develop sustainable financing strategies, identify relevant funding opportunities and improve engagement with prospective donors, private-sector partners and investors beyond the project period. | Moderate (M) | Substantial (S) |
| EXECUTION |  |  |  |  |
| Capacity for implementation | Risk: Local level partners are slow to participate or decline to participate in training and capacity building activities Impact Strategies for subprojects to include capacity-building strategy ICI support for communications efforts to convey value of participation Risk: Coordination of many partners becomes unmanageable Coordination built into Results Framework Dedicated coordination capacity to be installed in ICI | The risk is assessed as Low (L). All 10 ICI subprojects have incorporated capacity-building activities into their Impact Strategies, informed by the findings of their Organizational Capacity Assessments. Subprojects are implementing priority actions identified in their annual workplans and addressing stakeholder engagement needs within their respective territories. Cumulatively, engagement has expanded to 137 stakeholder groups, reflecting continued participation and strengthened partnerships since project inception. Communication and outreach activities are ongoing to demonstrate the value of participation, promote project achievements, and encourage stakeholder involvement. ICI’s social media channels continue to support this outreach and will remain active throughout the project lifecycle. | Low (L) | Low (L) |
| Fiduciary | Risk: Fiduciary capacity of subproject recipients is low Subproject selection criteria Assessments against GEF Minimum Fiduciary Standard Requirements Training and capacity-building | This risk is assessed as a Moderate Risk (M). All ICI 10 subprojects have incorporated capacity building training to strengthen organizational capacities and GEF fiduciary requirements as part of finalization of their impact strategies. Moreover, financial due diligence of subproject completed planning grants. IUCN and CI Grants and Contracts teams are providing targeted support and training during site visits | Substantial (S) | Moderate (M) |
| Stakeholder | Risk: IPLC organizations face high stakeholder expectations Lack of transparency Lack of financial sustainability Lack of leadership continuity Communications strategy; application of FPIC; transparency requirements stipulated in sub-grant agreements; grievance mechanism; targeted training on skills and organizational capacity; design training programs to reach a critical mass of current and potential future leaders | The risk is assessed as Substantial (S). All 10 ICI subprojects continue to engage Indigenous Peoples’ and Local Communities’ leaders in target communities and territories and apply Free, Prior and Informed Consent throughout project implementation. To strengthen transparency and accountability, the ICI Accountability and Grievance Mechanism has been published on the ICI website and communicated to stakeholders. The Global Steering Committee’s Grievance Sub-Committee supports the mechanism by facilitating the transparent and timely review of grievances. Although no capacity-building activities specifically addressing this risk were reported during the period, organizational development remains integrated into subproject implementation. Targeted activities are planned to strengthen governance, leadership continuity, financial sustainability and stakeholder management within participating Indigenous Peoples’ and Local Communities’ organizations. | Substantial (S) | Moderate (M) |
|  | Risk: Limited uptake of ICI knowledge products Creation of a dynamic knowledge management system; communications strategy | The risk is assessed as Low (L). The PMU established a Community of Practice listserv to support the dissemination of ICI knowledge products and facilitate knowledge exchange among project stakeholders. The PMU also strengthened coordination with communications staff and social media managers from ICI Indigenous Peoples’ and Local Communities’ organizations, as well as with environmental organizations, funding agencies and other relevant partners, to expand outreach and promote the uptake of finalized knowledge products. In addition, collaboration with the GEF Secretariat’s communications team and partner communications teams continued to support the strategic dissemination, visibility and accessibility of ICI knowledge products among wider audiences. | Low (L) | Low (L) |
|  | Risk: ICI outreach efforts fail to connect with audience Evolving and adapting communications strategy and outreach | This risk is assessed as low (L). During this reporting period, the ICI Communications Strategy has been in execution. | Low (L) | Low (L) |
| Other (e.g. NGI) |  |  |  |  |

| OVERALL RISK RATING | JUSTIFICATION | RISK RATING TREND |
| --- | --- | --- |
| M | Although the overall risk level remains moderate, some risks have increased, such as those related to political context and sustainable financing. The project is implementing mitigation measures appropriately. | Unchanged |

## Recommendations

| MITIGATION AND CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| The adaptive management described above is considered appropriate. |  |  |

SECTION IV: PROJECT ENVIRONMENTAL AND SOCIAL MANAGEMENT IMPLEMENTATION STATUS AND RATING

This section of the PIR describes the progress made towards complying with the approved ESMF plans, as well as recommendations to improve the implementation of the ESMF plans when needed. This section is divided into six parts:

a. Progress towards complying with the CI-GEF Project Agency’s ESMF

b. Information on Progress, challenges and outcomes on stakeholder engagement

c. Information on the progress towards achieving gender sensitive measures/targets

d. Lessons learned and Knowledge Management products developed and disseminated

e. Overall Project ESMF Implementation Rating

f. Recommendations

  - Progress towards complying with the CI-GEF Project Agency’s ESMF

| MINIMUM ESMF INDICATORS | PROJECT TARGET | END OF YEAR STATUS | CUMULATIVE STATUS | PROGRESS RATING17 | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| ACCOUNTABILITY AND GRIEVANCE MECHANISM Number of conflict and complaint cases reported to the project’s Accountability and Grievance Mechanism | The number of complaints per subproject geography is low and decreases rather than increases over time. | 1 | 1 | IS | This indicator is currently being implemented, with one issue reported during this reporting period FY26 (July 25-June 26) in the Pacific Region, which was addressed and resolved locally. ICI Accountability Grievance Mechanism (AGM) has been communicated to stakeholders under different platforms and multiple languages. The project has been tracking the progress of dissemination of the AGM at the global and sub-project level. It was observed that subprojects of governance and local protocols for conflict resolution have been instrumental in addressing concerns at local levels. In addition, the PMU has recommended all 10 ICI subprojects to raise awareness about the ICI AGM among project stakeholders and track the progress on its dissemination. Additionally, the PMU recommended all subprojects update their records concerning the dissemination of messages related to the grievance mechanism within their project areas. |
| Percentage of conflict and complaint cases reported to the project’s Accountability and Grievance Mechanism that have been resolved. | 100% of complaints were concluded satisfactorily | 100% | 100% | IS | One grievance was raised in the Pacific, but it was addressed and resolved at the regional level, considering local protocols for conflict resolution. |
| GENDER MAINSTREAMING GM C1.1: Number and percentage of women/men who are ICI direct beneficiaries | 50% of women 50% of Men | Total: 49,659 Men - 24341 (49.0%) and Women – 25,318 (51.0%). | Cumulative Total Direct Beneficiaries: 123,836, Men 63,062 (51%) and Women 60,774 (49%) | IS | This indicator is currently under implementation. All 10 ICI subprojects are actively carrying out priority actions and activities as outlined in their respective Annual Workplans and Impact Strategies. As of the reporting date, total of 49.659 direct beneficiaries has been reached under Component I—comprising Men - 24341 (49.0%) and Women – 25,318 (51.0%). These individuals were engaged through various community and stakeholder activities, including meetings and workshops, implemented across all subprojects during the reporting period. Subprojects; Ex- Agency /Organized; Men; Women; Total. NEFIN; IUCN; 577; 595; 1,172. UCRT; IUCN; 1,856; 1,693; 3,549. IPF Thailand; IUCN; 6,985; 7,139; 14,124. Guatemala; IUCN; 1,769; 1,917; 3,686. ANAPAC; IUCN; 4,342; 4,816; 9,158. IMPACT; CI; 5,322; 5,435; 10,757. Chile; CI; 341; 511; 852. Argentina; CI; 884; 1,274; 2,158. Fiji and Cook; CI; 723; 480; 1,203. FENAMAD; CI; 1542; 1,458; 3,000. Total; 24,341; 25,318; 49,659. %; 49.0; 51.0. |
| GM C1.2: Proportion of decision-making spaces held by women/men in the ICI, including the 10 subprojects. | 50 % of women 50% of Men | Total 9: Women - (33.3%) Men - (66.6%)/ *Primary GSC Member Composition | Total: 31 Women - 9 (29%) Men – 22 (71%) | IS | During the reporting period (July 25 – June 26), an average of 9 representative (03 Women (33.3%)) and 06Men (66.6%) engaged in decision making spaces through ICI three GSC Meetings. |
| GM C1.3: Percentage of women/men of ICI subprojects that report increased. livelihood benefits to the communities | 50% of women 50% of Men | 91.1% of surveyed beneficiaries reported increased livelihood benefits (Women: 90.4%; Men: 91.8%). Women constituted 52.8% of all beneficiaries reporting increased livelihood benefits. 0 | 91.1% of surveyed beneficiaries reported increased livelihood benefits (Women: 90.4%; Men: 91.8%). Women constituted 52.8% of all beneficiaries reporting increased livelihood benefits. | IS | The ICI Mid-Term Livelihood Benefits Survey was conducted as a beneficiary perception-based assessment across the 10-subproject portfolio to assess progress against Outcome Indicator 1.1.B. Following data verification and quality assurance, 314 valid responses from verified direct beneficiaries across nine subprojects were included in the consolidated analysis, including 167 women (53.2%) and 147 men (46.8%). Overall, 286 respondents (91.1%) perceived that ICI activities and support had contributed to increased livelihood benefits for themselves, their households, or their communities. This included 151 women (90.4% of female respondents) and 135 men (91.8% of male respondents). Women represented 52.8% of all beneficiaries reporting increased livelihood benefits. The main perceived livelihood benefits reported by respondents included improved skills, knowledge, and technical capacities (55.2%), strengthened traditional livelihoods and cultural practices (54.5%), and improved women’s economic participation (43.4%). Respondents indicated that these benefits were experienced primarily at the whole-community level, while ICI’s contribution to the reported livelihood changes was assessed predominantly as moderate. As the survey captures beneficiaries’ self-reported perceptions and experiences of livelihood benefits, the findings represent perceived livelihood improvements and ICI’s perceived contribution rather than an objective measurement of changes in household income or other economic conditions. These findings establish the project’s mid-term benchmark for comparison with the endline survey. The mid-term result of 91.1% therefore exceeds the indicator target of at least 50%, including the requirement that women constitute at least 50% of beneficiaries reporting increased livelihood benefits. These findings will serve as a benchmark for comparison with the endline survey. |
| GM C1.4: Percentage of ICI subprojects that have developed a GMP. | 100% | 100% | 100% | CA | This indicator has been completed. |
| GM C1.5: Percentage of benefits and services (e.g., income -generation opportunities, credit, technology, training, etc.) that target to women. | At least 50% of ICI subproject services (e.g. income-generation opportunities, credit, technology, training, etc.) target women. | 25,318 (50.98%) Women Benefited through different services under component 1 is. training, workshop activities. | Cumulative Total 123,636, Men 62946 (50.91%) and Women 60,690 (49.08%) Women Benefited through different services under component 1 is. training, workshop Activities. | IS | This indicator is currently being implemented. All 10 ICI subprojects have been implementing project activities on the ground. During this reporting period 25,318 women (50.98%) benefited through different services under component 1 including trainings and workshops. These services are already generating impacts: in Tanzania, women have increased access to land rights and credit; In Nepal women had access to technical training and in DRC and Thailand access to finance by women groups has been promoted and across projects women’s leadership has expanded, with greater participation in governance and decision-making structures. In addition, more progress will become more visible in the next fiscal year, FY27. |
| GM C1.6: Percentage of additional funding raised in ICPGs that have mainstreamed gender in their project formulation. | 100% | 2,233,925 USD | Cumulative co-finance Total: USD 32,555,012 | IS | This indicator is currently being implemented. During this reporting period, USD 2,233,,925 additional funding has been raised in ICPGs that have mainstreamed gender, benefiting the project formulation. |
| GM C2.1: Percentage of improvement in terms of knowledge and skills on gender Issues | At least 25% of improvement in terms of gender knowledge and skills. | 43.13% of women participation in the ICI Learning Module on Gender and Biodiversity Linkages 24% improvement in participants’ self-reported knowledge and understanding of gender issues, based on 657 post-course survey responses. | 43.13% of women participation in the ICI Learning Module on Gender and Biodiversity Linkages 24% improvement in participants’ self-reported knowledge and understanding of gender issues, based on 657 post-course survey responses. | IS | A cumulative 1,082 participants completed the gender-related ICI Learning Module, of whom approximately 467 (43.2%) were women. The 43.2% represents the proportion of women among course completers and should not be interpreted as an improvement in gender-related knowledge and skills. To assess learning outcomes, a post-course feedback survey was administered following completion of the self-paced e-learning course, including retrospective pre- and post-course self-assessments of participants’ knowledge across three key gender-related learning areas. Based on 657 survey responses, the average self-assessed knowledge score increased from 4.16 before the course to 5.15 after the course on a six-point scale, representing an approximately 24% improvement in self-reported knowledge. This demonstrates substantial progress toward the indicator target of at least 25% improvement in knowledge and skills on gender issues. |
| GM C2.2: Number of ICI staff professionals (women and men) involved in the capacity building strategy have gender expertise | At least 50% staff involved in drafting the capacity building strategy have gender expertise. | 100% staff involved in drafting the capacity building Strategy has gender expertise. | 100% staff involved in drafting the capacity building | IS | The Makanisi academy’s curricula have been developed based on the ICI organizational needs assessments conducted with IPLC organizations, as well as inputs from IPLC capacity-building partners and initiatives. Six topics were selected and approved by ICI’s Global Steering Committee to be developed into self-paced learning modules. The first course on IPLC, gender and biodiversity linkages, has been developed by the ICI gender specialist and specialist from the Indigenous Women Biodiversity Network (IWBN). The second course on indigenous governance also include the support of a gender expertise and the third one on indigenous negotiations also include gender specialist in the development of the content. |
| GM C2.3: Percentage of IPLC organizations in mapping study with expertise in gender and indigenous peoples within and beyond the ICI subproject geographies | Mapping of IPLC organizations documents and shares information on IPLC organizations with expertise in gender and indigenous peoples | 100% – Mapping Completed | 100% – Mapping Completed | CA | During the elaboration of the subprojects impact strategy, executing partners did a mapping exercise and at the elaboration of the stakeholder engagement plan to identify organizations with expertise in gender, youth, IP and other topics relevant to the subproject context. The sharing of information with organizations beyond ICI has been promoted during the second global exchange as well as at the regional exchanges in Tanzania, Nepal, Latin America and Oceania. |
| GM C2.4: Percentage of IPLC women and men participating in the Inclusive Conservation Learning Exchanges | 50% of IPLC who participate in the Inclusive Conservation Learning Exchanges are women. | Total 275 IP and LC (Men-125 (45.45%) and Women 150 (54.54%)) participated in the Inclusive Conservation global learning exchange i.e. Pacific and IUNC WCC | Total cumulative 514 IP and LC (Men - 249 (48%) and Women - 265 (51.6%)) participated in the 7 ICI Global and Regional Learning Exchanges | IS | During this reporting period, two ICI Learning Exchanges were conducted: one Global Learning Exchange held in Abu Dhabi in conjunction with the IUCN World Conservation Congress (WCC), and one Pacific Regional Learning Exchange held in the Cook Islands. Across the two exchanges, a total of 275 Indigenous Peoples and local community (IP and LC) participants participated, comprising 125 men (45.45%) and 150 women (54.55%). |
| GM C3.1: Number of political/policy dialogues between IPLC partners that raise gender equality issues. | At least 1/3 political/policy dialogues between IPLC partners have focused on gender issues. | All 7 events mainstreamed gender | All 13 events are mainstreamed gender | IS | PMU supported the following seven side events at the IUCN World Conservation Congress (WCC) in Abu Dhabi from 9–15 October 2025. The events highlighted Indigenous leadership, inclusive conservation, Indigenous knowledge, youth engagement, territorial governance, and access to climate and biodiversity finance. Gender equity was an important topic that was mainstreamed in all these dialogue events. - Transforming Climate and Biodiversity Finance: Lessons Learned from Indigenous-Led Initiatives – Forum Event. - Walking the Talk: ICI’s 2025 Report on Advancing Equity through Indigenous-Led Conservation – GEF Pavilion. - Walking the Talk: Mapping and Governing Territories for Inclusive Conservation – Nature Positive Pavilion. - Walking the Talk: Inclusive Conservation in Action Across the Americas – Americas Pavilion. - Voices of Indigenous Youth: Community Leadership and Ancestral Knowledge for Nature and Culture – Youth Pavilion. - Stewarding the Earth: Session 1 and Session 2 – Indigenous Peoples Pavilion. - Beyond Passion: The Realities Youth Face in Conservation – Youth Pavilion. |
| GM C3.2: Percentage of IPLC women and men of the ICI who are meaningfully participating in the Rio Conventions and other international conventions and Platforms | 50% of IPLC who participate in the Rio Conventions and other international conventions and platforms, including the Policy Coordination Mechanisms, are Women | 27 IP and LC leaders (Men – 14 (51.85%) and Women – 13 (48.15%)) participated in the Rio Conventions and other international conventions and Platforms | Cumulative Total: 104 IP and LC participants: Men: 64 (61.54%) Women: 40 (38.46%) | IS | 27 IP and LC leaders (Men – 14 (51.85%) and Women – 13 (48.15%)) participated in international policy and advocacy events, strengthening Indigenous Peoples’ and local communities’ engagement and representation in global environmental and conservation processes. Disaggregation: - IUCN World Conservation Congress (WCC), Abu Dhabi: 20 IP and LC leaders — Men: 12 (60%) and Women: 8 (40%). - COP6 – Minamata Convention on Mercury, Geneva: 2 IP and LC leaders — Men: 0 (0%) and Women: 2 (100%). - 8th GEF Assembly, Samarkand: 4 IP and LC leaders — Men: 2 (50%) and Women: 2 (50%). - New York Climate Week (NYCW): 1 IP and LC leader — Woman: 1 (100%). Important for FY26 reporting: New York Climate Week is dated 21–28 September 2026, so it falls outside FY26 (July 2025–June 2026). If this is specifically for the FY26 PIR, the correct FY26 total would be 26 leaders: 14 men (53.85%) and 12 women (46.15%). |
| GM C4.1: Number of findings of the final and mid-term independent evaluation of ICI that are related to gender equality and women’s empowerment | At least 1 section of the final and mid-term independent evaluation is focused on gender equality and women’s empowerment | 1 | 1 | IS | The ICI Mid-Term Review (MTR) was done by consultants, and the MTR report had a gender section with findings and recommendations. PMU presented the responses for gender recommendations and next steps. It is expected that the final evaluation will also have a gender section. |
| the GM C4.2: Number of good practices on gender equality and women’s empowerment highlighted in the PIR or APR | At least 1 section of the PIR or APR highlights gender equality good practices | 1 gender section on ICI SAR 2025 and in the ICI report phase 3 with 10 gender equality good practices | 20 good practices on gender equality and women’s empowerment | IS | Several good practices on promoting gender equality are reported in the 2nd PMU semi-annual technical progress report. For example, - the PMU level, efforts to include gender responsive activities include support offered to women so they can either bring their children to international events, such as the COP6 Minamata Convention, or for child-care services in their communities. The PMU also recognizes that women fellows may need additional support for childcare services to complete fellowship activities. - At the subproject level, teams aim to schedule events around times when women are most able to participate, welcome women to bring their children to workshops and in some cases provide childcare support - They also conduct separate women’s working groups to ensure women’s priorities are included in community decision making and workshops. - Projects has sensitized men leaders about the importance of supporting women participation in capacity building session - and training session are done in the community which allow more women to participate. - In the learning exchanges there is always an effort to bring women to participate but also the gender topic must be considered in the agenda del event and the emphasis of what gender aspect will be highlighted will depend on or what the indigenous women request. Besides the ICI Report ¦ Inclusive Conservation Initiative Phase 3 Report – Walking the Talk: How Inclusive Conservation is Delivering Results has a section on gender equality and women’s empowerment where report 4 good practices and that aall current initiatives are implementing GAPs complemented by 9 WRLFs advocating for women’s land rights in Tanzania. More than 1,800 Indigenous women have been supported through economic empowerment initiatives in the DRC, Guatemala, and Tanzania. Protocols to prevent and respond to GBV are now in place in Peru, Chile, Argentina and the DRC. These diverse efforts are not only shifting institutional norms, but they are also driving broader cultural and generational transformation - where both Indigenous women and men are actively engaged and empowered, recognizing the importance of their equal participation and complementary roles in conserving biodiversity in their territories. |
| GM C4.3: Percentage of ICI staff who believe that gender has been adequately mainstreamed into the ICI | 100% of ICI staff believe that gender has been adequately mainstreamed into the ICI | 100% | 100% | CA | This indicator has been completed, as 100% of ICI staff are highly committed and sensitized to prioritizing gender considerations. |
| GM C4.4: Number of genders -specific communication activities within the ICI Communication program | At least 20% of gender-specific communication activities within the ICI Communication program | 100% of communication activities include gender content | 100% of communication activities include gender content | IS | This indicator is under implementation. During this reporting period, ICI advanced the following below gender specific communication activities within the ICI Communication Program. 12 blog posts, 3 videos, and a 4-part podcast series were published on gender/Indigenous-leadership themes in FY26 (see KM Products section for full list). |
| STAKEHOLDER ENGAGEMENT Number of government agencies, civil society organizations, private sector, indigenous peoples, and other stakeholder groups that have been involved in the project implementation phase on an annual basis. | 10 ICI Subprojects Stakeholder Engagement Plans developed as part of finalization of Impact Strategies. | 303 stakeholder groups were engaged across five ICI regions: 30 government/public authorities, 255 IP/LC orgs, CSOs/CBOs and private/community partners, 4 intl. conservation/development orgs, and 14 research, academic, governance and other bodies. | Cumulatively, 495 stakeholder groups were engaged, including 71 government/public authorities, 378 IP/LC orgs, CSOs/CBOs and private/community partners, 6 international conservation/development orgs, 12 OFPs, 14 research/academic/governance bodies, and 14 other stakeholder groups. | IS | This indicator remains under implementation. During FY26, all ten ICI subprojects actively engaged a diverse range of government agencies, Indigenous Peoples and local community (IP/LC) organizations, civil society organizations (CSOs), community-based organizations (CBOs), private/community partners, and other stakeholders in project implementation. Across the five ICI regions, 303 stakeholder groups were engaged, including 30 government/public authorities, 255 IP/LC organizations, CSOs/CBOs and private/community partners, 4 international conservation/development organizations, and 14 research, academic, governance and other stakeholder bodies. The following key high level Stakeholder engagement was tailored to local contexts and project priorities: Africa — Kenya, Tanzania, DRC - Territorial and community land governance - Indigenous governance, rights and policy advocacy - Women/youth livelihoods and economic empowerment - Indigenous knowledge, conservation and community learning Asia — Nepal, Thailand - FPIC, community consultation and natural resource governance - Indigenous knowledge, education and cultural revitalization - Government/policy engagement and Indigenous advocacy - Community livelihood and organizational capacity strengthening Latin — Peru, Guatemala - Indigenous governance, rights and organizational strengthening - Territorial protection and ecosystem management - Indigenous knowledge, youth and cultural engagement - Sustainable livelihoods and climate-resilient production Pacific — Cook Islands & Fiji - Traditional governance and Indigenous leadership strengthening. - Stakeholder consultation, coordination, and policy engagement. - Regional learning exchanges, experiential learning, and knowledge sharing. - Community livelihoods, microgrants and marine/environmental citizen science. Southern Cone — Argentina, Chile - Biocultural mapping, territorial knowledge, and community validation. - Mapuche/Indigenous knowledge, education, cultural revitalization and traditional skills. - Indigenous governance, women’s leadership and organizational strengthening. - Policy advocacy, institutional dialogue, community conservation and local livelihood initiatives The engagement of diverse stakeholder groups has helped strengthen local ownership, inclusive governance, and collaboration across sectors, while supporting culturally appropriate implementation consistent with ESS4 safeguards. Since project inception, cumulative engagement has reached 495 stakeholder groups, demonstrated the continued expansion and strengthened of partnerships across the ICI portfolio. |
| Number persons (sex disaggregated) that have been involved in project implementation phase (on an annual basis) | 10 ICI Subprojects Stakeholder Engagement Plans developed as part of finalization of Impact Strategies. | 49,659 (Men 24,341(49.0%) and Women 25,318 (51.0%)) | Cumulative Total Direct Beneficiaries: 123,636, Men 62,946 (50.91%) and Women 60,690 (49.09%) | IS | This indicator is under implementation. ICI Subprojects have reached a total of 49,659 (Men 24,341(49.0%) and Women 25,318 (51.0%)) during this reporting period (July 25 – June 26) under component 1. The partners were engaged through various activities reported during this period by All ICI 10 subprojects. These activities included community mapping activities, stakeholder engagement activities, trainings, workshops, trainings, development of biocultural land maps, registry of ICCAs, etc. |
| Number of engagement (e.g., meeting, workshops, consultations) with stakeholders during the project implementation phase (on an annual basis) | 10 ICI Subprojects Stakeholder Engagement Plans developed as part of finalization of Impact Strategies. | Total 563 Engagement in FY26 at both PMU and ICI subprojects level PMU Level Status 37 PMU-led stakeholder engagements in FY25 Disaggregation: 5 Learning Exchanges, GSC & Peer-Learning Events 27 Technical Workshops & Capacity-Building 3 Policy & Global Advocacy Engagements 2 PMU-Led Field Missions ICI 10 Subprojects level 526 documented stakeholder engagements across 10 ICI subprojects Disaggregation: 45 Community & FPIC Consultations 97 Participatory Planning, Mapping & Territorial Management Sessions 127 Capacity-Building, Training & Livelihood Support Events 94 Cultural, Knowledge Exchange & Leadership Events 96 Policy Dialogue & Local Governance Meetings 67 Project Coordination, Technical Monitoring & Other Stakeholder Engagements | Cumulatively, 989 stakeholder engagements were recorded at both PMU and ICI subproject levels. | IS | This indicator remains under implementation. During FY26, the ICI project recorded 563 stakeholder engagements, including 37 PMU-led engagements at global and regional levels and 526 subproject-level engagements across the five ICI regions. These engagements supported project delivery through community consultations, participatory planning and mapping, capacity building, policy dialogue, learning exchanges, technical support, and field-based engagement, while strengthening Indigenous Peoples and local communities’ participation, territorial governance, knowledge exchange, and inclusive conservation decision-making. PMU-Level Engagements (37): PMU (CI/IUCN) engagement focused on global learning, technical capacity building, policy engagement, project governance, and implementation support: - Learning Exchanges, GSC & Peer-Learning Events (5): Pacific Regional Learning Exchange, Global Learning Exchange at IUCN WCC, 2 FY26 GSC virtual meetings, and the virtual technical exchange on Ancestral Knowledge, Territory and Communication. - Technical Workshops & Capacity-Building (27): 4 ICCA Registry trainings, 11 ManGo training/update sessions, the ICI gender and biodiversity Learning Module, launch of the third Fellows cohort, 4 communications training sessions, and 6 M&E/EX-ACT/livelihood survey technical sessions. - Policy & Global Advocacy Engagements (3): IUCN World Conservation Congress policy-level engagement, COP6 of the Minamata Convention, and participation in the 8th GEF Assembly. - PMU-Led Field Missions (2): Technical/site missions to FENAMAD Peru and Sotz’il Guatemala. ICI Subproject-Level Engagements (526): 10 of 10 ICI subprojects actively engaged Indigenous Peoples and local communities, government authorities, CSOs, traditional institutions and other partners throughout FY26 to support inclusive project implementation, strengthen local ownership and advance community-led conservation. - 45 Community & FPIC Consultations: Community consultations, FPIC processes, community assemblies, validation meetings, stakeholder consultations and local dialogues. - 97 Participatory Planning, Mapping & Territorial Management Sessions: Biocultural and territorial mapping, GPS/georeferencing, land-use and grazing planning, CCRO processes, Life Plans, conservation planning, resource-management plans and community monitoring. - 127 Capacity-Building, Training & Livelihood Support Events: Technical training, advocacy and rights training, vocational skills, agroforestry, entrepreneurship, livelihood development, community funds, microgrants and organizational capacity building. 94 Cultural, Knowledge Exchange & Leadership Events: Indigenous knowledge exchanges, intergenerational learning, cultural revitalization, Indigenous education, women and youth leadership, traditional practices and learning exchanges. - 96 Policy Dialogue & Local Governance Meetings: Engagement with government agencies, local authorities, traditional governance bodies, councils and committees on rights, policy, regulations, conservation governance and institutional coordination. - 67 Project Coordination, Technical Monitoring & Other Engagements: Project review and coordination meetings, partner engagement, M&E, safeguards, technical monitoring, donor engagement and implementation follow-up. |
| ESS 1: Environmental and Social Impact Assessment | I1.1: Number of ESIA or similar developed including ESMP according to the scope of each site-specific activity | All ICI 10 subprojects are fully implementing their ESMPs, with field monitoring and safeguard compliance ongoing. | 10 ESMPs are fully under implementation with ongoing field monitoring and safeguard compliance in FY26. | IS | During FY26, environmental and social safeguards monitoring continued across all ICI subprojects through routine progress reporting, indicator reviews, safeguards oversight, and field-based verification. The PMU systematically reviewed subproject reports, supporting documentation, implementation updates, and field-level evidence to assess environmental and social risks, verify the implementation of agreed mitigation measures, and monitor compliance with approved Environmental and Social Management Plans (ESMPs). Technical site visits were conducted to IMPACT Kenya (8–18 August 2025), Observatorio Ciudadano Chile (6–12 December 2025), the Cook Islands (22 February–5 March 2026), Futa Mawiza Argentina (8–13 March 2026), FENAMAD Peru (23–29 March 2026), and Sotz’il Guatemala (12–15 May 2026). These missions enabled direct engagement with subproject teams, community leaders, implementing partners, and other stakeholders to review safeguards implementation, verify reported progress, identify capacity and reporting gaps, and provide targeted technical support. Where gaps or inconsistencies were identified, the PMU provided follow-up guidance to strengthen risk documentation, evidence of mitigation measures, and safeguards of reporting. The establishment of the ICI Subprojects Core M&E Working Group also provided a regular platform for technical assistance, peer learning, and the resolution of reporting and safeguards-related issues. Collectively, these efforts strengthened safeguards oversight, improved the completeness and consistency of reporting, and supported evidence-based adaptive management and decision-making across the portfolio. |
|  | 1.2: Number of organizational structures related to ESS risk management activities in Place. | All 10 ICI subprojects have functional organizational structures actively implementing ESS risk management activities. | 10 organizational structures are fully operational in FY26, actively implementing ESS risk management activities. | IS | During FY26, organizational structures for environmental and social risk management remained functional across all 10 ICI subprojects, supporting continued implementation and oversight of approved safeguards requirements. Subproject teams maintain responsibility for monitoring environmental and social risks, implementing agreed mitigation measures, and reporting progress through established project management and reporting arrangements. At the portfolio level, the PMU continued to provide centralized safeguards oversight by reviewing progress reports, supporting evidence, implementation updates, and field-based information. The establishment of the ICI Subprojects Core M&E Working Group further strengthened coordination between subproject teams and the central MEL function by providing a regular platform for technical assistance, peer learning, follow-up on identified gaps, and resolution of safeguards-related reporting issues. These structures supported systematic risk management, improved accountability, and strengthened the quality and consistency of safeguards implementation across the portfolio. |
| ESS 2: Protection of Natural Habitats and Biodiversity Conservation Hectares of natural and/or critical natural habitats are lost or degraded. | I2.1: Number of BMP developed. | I2.1: 03 of 10 ICI Subproject's Biodiversity Management Plans (BMP) developed; all 10 subprojects implementing | I2.1: 10 of 10 ICI Subproject's Biodiversity Management Plans (BMP) developed and implementing | IS | ICI subprojects continued implementing site-specific Environmental and Social Management Plan (ESMP) measures under ESS2, with a focus on biodiversity conservation, habitat protection, invasive alien species management, and forest-fire risk reduction. These measures remained integrated into subproject workplans and were considered throughout the implementation of field activities. No invasive alien species (IAS) outbreaks were reported during the reporting period, indicating that ongoing monitoring, prevention, and community-based surveillance measures remained effective. IAS management actions continued to be incorporated into subproject operational plans, while communities applied lessons from previous training to identify biodiversity threats, distinguish invasive species from native species, and support early detection and preventive action. Fire-prevention and preparedness measures also remained embedded in relevant subproject plans. Futa Mawiza Argentina received support to implement the mini-grant initiative, “Development of Technical and Financial Guidelines to Address the Growing Impacts of Wildfires on Mapuche Communities of the Mapuche Confederation of Neuquén within the Futa Mawiza Territory, Argentina,” with additional financial support from Conservation International. The initiative is strengthening community preparedness and developing practical technical and financial guidance for wildfire prevention, mitigation, and response. Collectively, these measures supported the protection of natural habitats and community assets, strengthened local capacity to respond to biodiversity and wildfire risks, and contributed to the continued implementation of ESS2 safeguards across the ICI portfolio. |
|  | I2.2: Number of workshops per sites about suitable options for new economic enterprises, in line with traditional knowledge, including reports recording local knowledge. | 0 | 0 | IS | Subprojects continued engaging Indigenous Peoples and Local Communities to identify sustainable livelihood and enterprise options aligned with traditional knowledge, local priorities, and available natural resources. Community consultations and capacity-building activities supported discussions on nature-based livelihoods, sustainable production, and culturally appropriate value chains. Relevant subprojects also documented local knowledge and practices to inform the design and implementation of these initiatives. Further details on the number of workshops, participants, and reports will be added once consolidated data is available. |
|  | I2.3: Number of trainings about IASs and native species differentiation. | 0 | 0 | IS | Community awareness and capacity to identify invasive alien species and distinguish them from native species continued to be strengthened across relevant subprojects. Although consolidated training figures are still being verified, communities applied knowledge from previous capacity-building activities through biodiversity monitoring, early detection, and prevention measures. No invasive alien species outbreaks were reported during the period. The number of trainings, participants, and locations will be updated following data validation. |
|  | I2.4: Number of trainings about forest fires Prevention. | 0 | 0 | IS | Forest-fire prevention, preparedness, and community-based risk-reduction measures remained integrated into the operational plans of relevant subprojects. Communities continued to participate in awareness, monitoring, and mitigation activities. Futa Mawiza Argentina also advanced implementation of its wildfire-related mini-grant to develop technical and financial guidance and strengthen preparedness among Mapuche communities. Consolidated information on the number of trainings, participants, and locations will be added once confirmed. |
| ESS 4: Indigenous Peoples Percentage of indigenous/local communities where FPIC have been followed and documented. The percentage of communities where project benefit sharing has been agreed upon through the appropriate community governance mechanisms and documented. | I4.1.1: Number of ESIA developed that incorporate FPIC process. | I4.1.1: 10 of 10 ICI Subprojects developed ESIA with integration of FPIC. | I4.1.1: 10 of 10 ICI Subprojects developed ESIA with integration of FPIC | IS | All 10 ICI subprojects continued implementing activities in accordance with established Free, Prior, and Informed Consent (FPIC) processes, Indigenous Peoples Plans, and culturally appropriate community-governance mechanisms. FPIC remained integrated into community consultations, participatory planning, implementation of priority activities, and stakeholder engagement across project territories. Subprojects also continued promoting equitable benefit-sharing arrangements through relevant Indigenous Peoples and Local Community governance structures. All 10 ICI subprojects continued applying the FPIC provisions incorporated into their Environmental and Social Impact Assessment and Environmental and Social Management Plan processes. FPIC was implemented through community assemblies, consultations with traditional leaders, participatory planning sessions, and other culturally appropriate decision-making mechanisms. Field visits and routine reporting reviews enabled the PMU to verify stakeholder participation and provide technical guidance where improvements in FPIC documentation were required. |
|  | I4.1.2.1: Number of grievance redress mechanisms which include specific mechanism culturally appropriate and accessible to affected indigenous peoples. | I4.1.2.1: All 10 ICI subprojects have developed culturally appropriate grievance redress mechanisms as part of their Impact strategies. These mechanisms are now operational and accessible to affected Indigenous People. | I4.1.2.1: All 10 of 10 ICI subprojects have developed culturally appropriate grievance redress mechanisms as part of their impact strategies. These mechanisms are now operational and accessible to affected Indigenous people | IS | Accountability and Grievance Mechanisms remained operational across all 10 ICI subprojects. During the reporting period, the PMU recommended that subprojects further strengthen awareness of the ICI Accountability and Grievance Mechanism among project stakeholders and systematically document its dissemination through community meetings, awareness sessions, locally appropriate communication channels, and grievance-tracking records. Follow-up guidance was provided to support the accessibility and cultural appropriateness of these mechanisms. |
|  | I4.1.2.2: Number of grievances raised in the context of indigenous people engagement and participation process. | I4.1.2.2: 1 – One grievance raised during the reporting period. | I4.1.2.2: 1– One grievance raised during the reporting period. | IS | One grievance was reported in the Pacific region during Q3 FY26. The grievance was reviewed and addressed by the relevant subproject team through the established accountability and grievance process. No unresolved grievances were reported across the portfolio at the end of the reporting period. The PMU continues to encourage all subprojects to maintain updated grievance records and report concerns and their resolution in a timely manner. |
|  | I4.1.3: Number of stakeholders (Disaggregated by gender) participating in capacity building activities that were communicated and held using a culturally appropriate and gender sensitive approach, in line with traditional knowledge, including reports recording local knowledge. | Total 49,659 (Men – 24,341 49(%) and Women – 25,318 (51%) | Total 119,380 (Men – 60,935 (51%) and Women – 58,445 (49%) | IS | During the reporting period, the PMU and ICI subprojects continued engaging Indigenous Peoples, Local Communities, traditional leaders, women, youth, implementing partners, and other stakeholders through culturally appropriate and gender-sensitive capacity-building and consultation activities. Relevant activities included: - Implementation of subproject priority actions and community capacity-building activities; - Community consultations, participatory planning, and FPIC-related engagement; - Technical site visits to the Cook Islands, Futa Mawiza Argentina, FENAMAD Peru, and Sotz’il Guatemala; - Community-level monitoring and verification of project activities and safeguards; - Awareness-raising on the ICI Accountability and Grievance Mechanism; - Learning, knowledge-sharing, and Indigenous governance activities; and - Capacity-building related to biodiversity conservation, livelihoods, gender integration, project management, and sustainability. |
|  | I4.2.1: Number of IPP developed. | 10 of 10 ICI subprojects are implementing their IPPs as part of their Impact Strategies. | 10 of 10 ICI subprojects are implementing their IPPs as part of their Impact Strategies. | IS | Indigenous Peoples Plans remained operational across all 10 ICI subprojects and continued to be implemented as part of their approved Environmental and Social Management Plans. The plans guided culturally appropriate stakeholder engagement, FPIC implementation, benefit-sharing, Indigenous governance, traditional knowledge activities, women’s and youth participation, and the implementation of locally identified priorities. The PMU continued monitoring their implementation through progress-report reviews, supporting documentation, field visits, and targeted technical follow-up. |
| ESS 5: Resource Efficiency and Pollution Prevention Number of hectares where pest management is applied. Percentage of pest management area where Integrated Pest Management or Integrated Vector Management is applied. Percentage of pesticide applications that comply with the International Code of Conduct on the Distribution and Use of Pesticides. | I5.1: Number of Resource Efficiency and Pollution Prevention Plans developed. | 10/10 subprojects developed and implementing Resource Efficiency and Pollution Prevention Plans | 10/10 subprojects developed and implementing Resource Efficiency and Pollution Prevention Plan | IS | During FY26, all 10 ICI subprojects continued implementing Resource Efficiency and Pollution Prevention measures through their approved ESMPs. Monitoring remained integrated into field implementation to track compliance with ESS5 requirements, including the responsible use of natural resources and prevention of pollution. No chemical inputs, pesticide-related issues, or pollution incidents were reported across the portfolio during the reporting period. |
|  | I5.2: Number of trainings about Resource Efficiency and Pollution Prevention. | 10 trainings on Resource Efficiency and Pollution Prevention conducted | 10 trainings on Resource Efficiency and Pollution Prevention conducted | IS | No new standalone trainings on Resource Efficiency and Pollution Prevention were specifically reported during the year. However, subprojects continued applying resource-efficiency and pollution-prevention practices through ongoing field activities, community engagement, and implementation of their ESMP workplans. Updated information on relevant training and participants will be included once consolidated and verified. |
| ESS 6: Cultural Heritage Number of physical cultural resources found in the project area. | I6.1: Number of CHMP developed. | All 10 ICI subprojects have developed Cultural Heritage Management Plans (CHMPs) and are currently implementing them | All 10 ICI subprojects have developed Cultural Heritage Management Plans (CHMPs) and are currently implementing them | IS | During FY26, all 10 ICI subprojects continued implementing their Cultural Heritage Management Plans, embedded within their approved ESMPs and Impact Strategies. These plans guided the protection of tangible and intangible cultural heritage and supported the continued application of Indigenous knowledge, customary practices, and traditional natural-resource management throughout project implementation. |
|  | I6.2: Percentage of green enterprises making use of traditional knowledge in creating new market products, were documentation exists about how the Intellectual Property Law was adhered to and benefits shared. | 0 | 0 | IS | Subprojects continued supporting livelihood and enterprise activities informed by traditional knowledge and local cultural practices. However, the percentage of green enterprises with complete documentation demonstrating compliance with intellectual property requirements and agreed benefit-sharing arrangements has not yet been consolidated. The PMU will continue working with subprojects to verify relevant enterprises and strengthen documentation on traditional knowledge use, intellectual property protection, FPIC, and benefit-sharing. |
| ESS 7: Labour and Working Conditions (ESIA, EMP, IPP, PMP, V-RAP, Process Framework, etc.) | I7.1: Number of ESMPs that include Occupational Health and Safety (OHS). | All 10 ICI subprojects are implementing Occupational Health and Safety (OHS) measures as outlined in their ESMPs, with safe labor practices and field monitoring in Place. | 10 of 10 subprojects have Occupational Health and Safety (OHS) fully integrated and under implementation | IS | During FY26, all 10 ICI subprojects continued implementing Occupational Health and Safety measures through their approved ESMPs and operational arrangements. OHS requirements were reinforced through ESS7-related training and incorporated into subcontractor agreements. Field verification in Peru, Argentina, the Cook Islands, and Guatemala confirmed compliance with applicable safeguards requirements. No labour-related incidents were reported during the period. |
|  | I7.2: Number of ESMPs that articulate with Gender Mainstreaming Plan. | All 10 ICI subprojects are actively implementing their Gender Mainstreaming Plans, integrating gender-sensitive actions into ESMPs, community trainings, and governance Activities. | 10 of 10 subprojects have gender plans fully developed and under implementation. | IS | All 10 subprojects continued implementing gender-sensitive labour provisions aligned with the ICI Gender Mainstreaming Plan. Gender considerations were integrated into contractual arrangements, capacity-building activities, and local employment opportunities. Women and men were engaged as community facilitators, paralegals, youth trainees, and other local personnel, supporting equitable participation and reducing the risk of discrimination in project activities. |
|  | I7.3. Number of ESMPs that include a workplace harassment protocol | All 10 ICI subprojects are implementing workplace harassment protocols, ensuring awareness among staff and community facilitators and integrating them into operational Practice | 10 of 10 subprojects have workplace harassment protocols developed and fully under implementation | IS | All 10 subproject ESMPs continued to include and apply workplace harassment protocols covering physical, psychological, and sexual harassment, intimidation, exploitation, discrimination, and child labour. These measures were reinforced through ESS7 training and day-to-day project management and contractual arrangements, supporting a safe, respectful, and inclusive working environment across the portfolio. |
| ESS 8: Community Health, Safety and Security (ESIA, EMP, IPP, PMP, V-RAP, Process Framework, etc.) | 8.1: Number of ESMPs that have included a health, safety and security assessment in the subproject execution strategy. | All 10 ICI subprojects continued implementing health, safety, and security measures during FY26, including safe field operations, context-specific risk assessments, and conflict-sensitive engagement, particularly in Peru and Argentina. | 10 of 10 ICI subprojects have fully integrated health, safety, and security assessments into their ESMPs and are under continuous implementation | IS | During FY26, all 10 ICI subprojects continued integrating health, safety, and security considerations into the implementation of their Environmental and Social Management Plans (ESMPs). Risk assessments were applied in areas affected by security concerns, health hazards, environmental risks, or heightened tensions to support the safe participation and travel of Indigenous Peoples and Local Communities. Context-specific measures were applied in particularly sensitive locations. In Peru, safeguards addressed risks related to mercury exposure and activities near territories of Indigenous Peoples in Isolation and Initial Contact (PIACI). In Argentina, access to and dissemination of biocultural maps were limited to community and educational purposes to avoid increasing risks in an increasingly hostile environment for Indigenous communities. Post-pandemic health and safety measures also continued to support inclusive participation in meetings and training activities while reducing potential health risks during gatherings. |
|  | I8.2.1: Number of subproject-specific AGM which considers tracking grievances related to tensions between stakeholders and other situations of conflict. | All 10 ICI subprojects maintained fully functional AGMs during FY25, ensuring accessibility to Indigenous Peoples and Local Communities (IPLCs) and reinforcing early conflict prevention | 10 of 10 ICI subprojects have established AGMs that remain operational and accessible |  | All 10 subproject-specific Accountability and Grievance Mechanisms remained operational and accessible during the reporting period. The mechanisms continued to provide culturally appropriate channels for identifying, documenting, and addressing concerns related to stakeholder tensions, conflict, gender-based violence, sexual exploitation, abuse and harassment, and community health and safety. Their continued operation supported transparency, early identification of potential risks, and trust between subproject teams and participating communities. |
|  | I.8.2.2: Number of grievances raised in the context of tension. | No grievances were reported in FY26; proactive engagement and awareness measures prevented escalation of community Concerns | 0 grievances reported to date; AGMs remain active and functional | IS | No grievances related to stakeholder tensions, community health, safety, or security were reported during FY26. Subprojects continued monitoring potential concerns through their Accountability and Grievance Mechanisms and community engagement processes. The absence of reported grievances reflects the continued application of preventive safeguards and conflict-sensitive stakeholder engagement. |
|  | I.8.3: Number of ESMPs with codes of ethics developed in alignment with CI’s Code of Ethics and IUCN policies for staff and participants |  |  |  | All 10 subproject ESMPs continued to apply ethical and professional standards aligned with CI’s Code of Ethics and relevant IUCN policies. These requirements guided the conduct of project staff, implementing partners, community facilitators, consultants, and participants and supported safe, respectful, inclusive, and culturally appropriate engagement. Compliance with these standards remained integrated into project implementation, field activities, training, and stakeholder-engagement processes across the portfolio. |
| ESS 10: Climate Risk and Related Disasters (ESIA, EMP, IPP, PMP, V-RAP, Process Framework, etc.) | I.10.1: Number of ESMPs that have included a climate risk assessment in the subproject execution strategy. | All 10 ICI subprojects are actively implementing the climate risk measures embedded in their ESMPs, including seasonal planning, rotational grazing, watershed and forest restoration, and contingency protocols to manage droughts, floods, and cyclones | 10 of 10 ICI subprojects have climate risk assessments fully integrated into ESMPs and under active implementation | IS | During FY26, climate-risk considerations continued to be integrated into ESMP implementation and subproject execution strategies. Climate-change scenarios, exposure assessments, and differentiated impacts on women and men informed activity planning across relevant subprojects. In Tanzania and Thailand, rotational grazing and watershed-restoration measures strengthened resilience to droughts and floods. In Sotz’il, Fiji, and Peru, mangrove, forest, and agroforestry restoration helped reduce exposure to storms, erosion, and other climate-related risks. In Kenya and Argentina, cultural calendars and traditional knowledge supported community-led disaster preparedness and locally appropriate adaptation planning. |
|  | I.10.2: Number of contingency plans that consider measures to mitigate climate risks. | 0 –No contingency plans developed yet | 0 –No contingency plans developed yet | IS | Climate-responsive contingency planning continued during FY26 to reduce disruptions caused by extreme weather and seasonal variability. In Nepal and Fiji, flexible scheduling and seasonal planning were applied to adjust implementation timelines and execution modalities when required. Engagement patterns and climate conditions were monitored to support timely operational adjustments. Across relevant subprojects, contingency measures included ecosystem-based restoration, drought and flood resilience measures, culturally informed preparedness, and flexible work planning, strengthening local capacity to respond to climate-related hazards and maintain implementation continuity. |

## b. Information on Progress, challenges and outcomes regarding engagement of stakeholders in the project based on the description included in the Stakeholders Engagement Plan

Stakeholder engagement remained a core element of project implementation across all ten ICI subprojects, in accordance with the Stakeholder Engagement Plan approved at CEO Endorsement. Throughout the reporting period, subprojects continued to engage Indigenous Peoples, local communities, government agencies, civil society organizations, and other key stakeholders through inclusive and participatory processes. These included territorial governance meetings, community consultations, multi-stakeholder workshops, regional exchanges, and national and international forums that supported collaborative decision-making, strengthened recognition of Indigenous knowledge and governance, and fostered alignment with national and international conservation, biodiversity and climate priorities. Challenges included shifting government policies, political changes, and declining public investment in conservation and climate, which created a more challenging operating environment in some countries. In response, the project strengthened engagement in national and international policy forums, expanded partnerships with trusted private-sector and civil society stakeholders, and continued to support Indigenous leaders through defender protocols and targeted capacity-building efforts.

## c. Information on the progress towards achieving gender sensitive measures/targets and any intermediate gender result areas as documented at CEO Endorsement/Approval including gender-sensitive indicators contained in the project results framework or gender action plan

Describe the progress towards achieving gender sensitive measures or targets as documented at CEO endorsement/approval in the gender action plan or equivalent. Please reply to the following questions in your description: - Are all activities anticipated by the GMP implemented? Yes/No Why? All 10 ICI subprojects are actively implementing their annual Gender Action Plans (GAPs), which contribute to the advancement of the ICI Gender Mainstreaming Plan (GMP). The PMU has provided targeted technical support through in-person field visits and monthly virtual working sessions to assist with the implementation of gender-related actions. During these technical support meetings, gender focal points have received guidance on improving gender reporting and have been given access to online training courses on gender issues, as well as participatory methodologies. In addition, the inclusion of gender issues in component 2, 3, and 4 of the projects has been done according to the activities anticipated in the GMP. One new activity included was the development of the male engagement strategies by the implementing partners organizations as a recommendation from the midterm evaluation. To support the development of these strategies, the gender focal points had technical sessions, and some organizations contracted experts on the topic to develop the document. PMU has also been planning a webinar for ICI partners on the topic of GBV and male engagement strategies in July to increase their capacity in relation to these two topics. - Did the project face any challenges to implementing GMP as initially proposed? Please describe the challenges in case there are any. The main challenge has been the UNDP Learning platform not been able to upload the “Gender, ILPC and Biodiversity Linkages” course in Spanish and French. The solution has been to move this module to the IUCN Academy however; the translations of this module will not be available until January 2027. Delaying subprojects ability to enroll in and complete the course. - As compared to the original GMP, was any adaptive management applied to promote meaningful participation of women and advance towards other gender sensitive targets? To promote the meaningful participation of women, the PMU supported the attendance of an Indigenous fellow at the sixth meeting of the Conference of the Parties to the Minamata Convention (COP-6) in Geneva by covering travel expenses for both the fellow and her young son. This support enabled her participation in the conference, which would otherwise not have been possible due to caregiving responsibilities, and reflects the project's commitment to removing barriers to women's full and effective participation in international policy processes. For exchanges and global policy engagement, it has been recommended that organizers adopt an affirmative action approach by aiming for at least 50% participation by women and ensuring that gender considerations are included as a dedicated topic in the event agenda. This helps promote gender equity and encourages the integration of gender perspectives into knowledge-sharing and decision-making processes. - Did the project team/stakeholders observe any unintended outcomes (positive or negative) related to gender equality, that are difficult to capture in a quantitative way during this period of time? For example, women are more active in decision-making processes in the project, or public servants are more interested and open to advance gender outcomes, men or women are more reluctant to participate in the project activities, or other similar situations. In relation to the “Gender, ILPC and Biodiversity Linkages” course, more people have enrolled than initially expected. For the last year among enrolled participants, 56.42% identified as female, 42.11% as male. Among participants who completed the course, 43.41% identified as female, 55.75% as male, - Considering all the above, what are the recommendations for the next FY to continue advancing towards gender-sensitive targets? Looking ahead to FY27, subprojects will focus on completing the remaining activities under their Gender Action Plans. Organizations developing male engagement strategies will also share their experiences and lessons learned with other ICI initiatives. In addition, the final year presents an opportunity to document and synthesize how each subproject advanced a gender-responsive approach, including through a potential publication showcasing lessons learned, good practices, and experiences across the ICI portfolio.

## d. Lessons learned on the Environmental and Social Management Implementation

One important lesson in relation to the management of the GBV risk has been the development of male engagement strategies that were not considered as part of the activities in the gender action plan. Having the male engagement strategy document will provide a roadmap to the organization of how to work with Indigenous men so they can become gender champions and support the advance of gender equality.

Experience across ICI continues to demonstrate that environmental and social safeguards are most effective when integrated into Indigenous governance systems, customary decision-making processes, and community-led conservation approaches rather than implemented as standalone compliance requirements. Subprojects reported that embedding safeguards into project design, stakeholder engagement, participatory planning, documentation processes, and knowledge management activities strengthened community ownership, trust, and participation while supporting culturally appropriate implementation. Early and continuous engagement with communities and relevant stakeholders also proved critical for identifying and addressing potential risks before activities commenced, contributing to the absence of significant environmental or social safeguard incidents during the reporting period. A key lesson relates to the importance of protecting Indigenous knowledge, cultural heritage, and sensitive community information through robust consent processes and community-led protocols for information management and dissemination. These approaches not only helped reduce potential social and cultural risks, but also strengthened community ownership, reinforced cultural identity, and supported the intergenerational transfer of Indigenous knowledge.

## e. Overall Project ESMF Implementation Progress Rating

| SUMMARY: PROJECT ESMF IMPLEMENTATION RATING BY TYPE OF PLAN |  |  |
| --- | --- | --- |
| ESMF PLAN REQUIRED BY THE PROJECT (delete those not applicable) | CURRENT FY25 IMPLEMENTATION RATING | RATING TREND |
| Accountability and Grievance Mechanism (AGM) | S | Increasing |
| Gender Mainstreaming Plan (GMP) | S | Increasing |
| Stakeholder Engagement Plan (SEP) | S | Unchanged |
| ESS 1: Full/limited ESIA and Environmental & Social Management Plan (ESMP) | S | Increasing |
| ESS 2: Plan for Natural Habitat Protection and Biodiversity Conservation | S | Increasing |
| ESS 4: Indigenous Peoples Plan | S | Unchanged |
| ESS 5: Resource Efficiency and Pollution Prevention Plan | S | Unchanged |
| ESS 6: Cultural Heritage Management Plan | S | Unchanged |
| ESS 7: Labour Management Procedures | S | Unchanged |
| ESS 8: Community Health, Safety and Security Management Plan | S | Unchanged |
| ESS 10: Climate and Related Disasters Risk Management Plan | S | Unchanged |

| OVERALL PROJECT ESMF IMPLEMENTATION RATING |  |  |
| --- | --- | --- |
| RATING | JUSTIFICATION | RATING TREND |
| S | Overall, the project has continued to deliver and advance towards achieving the ESMF-related targets. On the AGM, the project received and resolved its first grievance, demonstrating that the increase in dissemination efforts is paying off, by improving awareness on the existence of the AGM. On the GMP, women’s participation is significant both as beneficiaries but also in decision-making spaces. The virtual course on Gender and IPs has had successful implementation and feedback so far. On the SEP, the project has engaged key stakeholders, both at the local and global levels. The project has continued to track all other ESS risks at the initiatives level, together with any required mitigation measures. |  |

## f. Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| The project has had a significant learning curve in implementing safeguards and gender requirements for Indigenous Peoples’ organizations, the project should document the lessons and recommendations that emerged from this process. The project should continue to oversee that the initiatives are disseminating their AGMs and adequately reporting and document grievances received. | PMU PMU | By June 2027 Ongoing |

SECTION V: PROJECT IMPLEMENTATION EXPERIENCES, KNOWLEDGE MANAGEMENT AND LESSONS LEARNED

## a. Progress on the implementation of the project’s KM approach approved at CEO Endorsement/Approval

Report on the progress on the implementation of the project’s KM approach and its key deliverables. List KM products developed by the project and how/where/when they were distributed and to whom. Indicate the type of product (e.g. brochure, newsletter/newspaper article, web post, radio announcement, and any special measures (e.g. KM translated into local languages, catered to marginalized/vulnerable groups) taken to ensure that the product is accessible to stakeholders. 11. ICI Knowledge products at PMU level developed during this reporting period FY26 (July 25 – June 26). Sr. No.; Categories Knowledge Products; List of Knowledge Products. 1; Lesson Learned Report; ICI Phase – III Report 2025 (English): The ICI Phase III Report 2025 “Walking the Talk: How Inclusive Conservation is Delivering Results”, was launched on August 7th 2025, to coincide with the International Day of the World’s Indigenous Peoples (English, Spanish, and French). 2; Blog/ Article; Earth Day Blog: Territories of Life in Resilience and Resolve: https://www.inclusiveconservationinitiative.org/posts/territories-of-life-in-resilience-and-resolve. 3; Phase 3 Report Blog: Walking the Talk: Indigenous Leadership Advances Inclusive Conservation Worldwide: https://inclusiveconservationinitiative.org/walking-the-talk-indigenous-leadership-advances-inclusive-conservation-worldwide/. 4; Blog: My First Journey Beyond the Mountains: The Voice of an Indigenous Fellow on the Global Stage: https://inclusiveconservationinitiative.org/my-first-journey-beyond-the-mountains-the-voice-of-an-indigenous-fellow-on-the-global-stage/. 5; International Women’s Day Podcast Series - Indigenous Women Redefining Science: https://www.instagram.com/reel/DUnsS-Lkggm/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==. 6; GEF Assembly Video: Instagram. 7; Learning Exchange Video Documentaries; ICI Presents: When the River Speaks - https://www.youtube.com/watch?v=te2kc1ESglc. 8; Earth Day Video - Territories of Life in Resilience and Resolve video featuring Futa Mawiza Argentina and Chile: https://www.instagram.com/reel/DT2xPR_jCie/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==. 9; International Education Day Video on Fellows (English, Spanish, and French): https://www.instagram.com/reel/DT2xPR_jCie/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==. 10; ICI Video: Lighting the Path with Indigenous Knowledge: ICI Video ¦ Lighting the Path with Indigenous Knowledge — Inclusive Conservation Initiative. ICI Knowledge products at the subproject level developed during this reporting period FY26 (July 25 – June 26). Sr. No.; Categories Knowledge Products; List of Knowledge Products. Social Media Pages; Updates on subproject achievements, news stories, and implementation progress are regularly shared via their social media channels, available at the following pages: • FENAMAD: https://www.instagram.com/fenamad/ ; https://www.facebook.com/FENAMAD • Futa Mawiza Chile: https://www.instagram.com/futamawiza/ ; https://www.youtube.com/@F%C3%BCtaMawizaGulumapu • Futa Mawiza Argentina: https://www.instagram.com/fvtamawiza.puelmapu/ ; https://www.youtube.com/@FvtaMawiza • IMPACT Kenya: https://www.instagram.com/impacttrustkenya/ ; https://www.facebook.com/IMPACTKENYA2002 • UCRT Tanzania: https://www.instagram.com/ujamaa_crt/. Web Sites; Many subprojects also maintain organizational websites that provide information about their broader work, highlight ICI-supported activities alongside other initiatives, and share news, resources, and project achievements: • NEFIN - https://www.nefin.org.np/ • ANAPAC RDC - https://anapacrdc.org/ • Sotz'il - https://sotzil-guatemaya.org/en/ • Futa Mawiza Argentina - https://confederacionmapuche.org/futa-mawiza/ • Futa Mawiza Chile - https://futamawiza.org/ • FENAMAD - https://fenamad.com.pe/ • IMPACT Kenya - https://impactkenya.org/ • IPF Foundation - https://www.ipfinfo.org/ • UANKA - https://uankacookislands.com/. Sub-Projects Knowledge Products; Video Year 2025 Implementation FENAMAD Community Bulletin 4 Futa Mawiza Chile Women´s Exchange Summary Futa Mawiza Chile Fiji Traditional Governance Manual IMPACT Kenya ICI Research Programme https://www.cookislandsnews.com/internal/national/local/outer-islands/new-community-led-education-and-citizen-science-initiative-launched-in-mauke/.

b. Additional optional topics (please choose two)

Interpretation and application of GEF guidelines: The Management Effectiveness Tracking Tool (METT) is the GEF's standard instrument for measuring management effectiveness in protected areas. However, METT was designed specifically for state-managed protected areas and does not adequately capture the governance structures, customary land management practices, or holistic relationship to land and resources that characterize IP and LC territories.

To address this gap, ICI adopted the Management and Governance Tool (ManGo) as an alternative to METT, adapting both the tool and its variables to fit the specific context of each subproject and using subproject means of verification to assess variables and develop scores. ManGo was co-designed in 2022 by CI with Indigenous Peoples, and is structured to align with IP and LC governance systems and their integrated view of land, resources, and territorial management, rather than imposing a protected-area management framework built for a different context.

During this reporting period, the tool was applied across all 10 ICI initiatives, generating baseline, MTR, and PIR data that better reflects how Indigenous and local governance actually functions and improves over time. This reinterpretation of the GEF's monitoring guidance demonstrates ICI's commitment to metrics that are both scientifically robust and culturally appropriate, a distinction that matters for accurately tracking long-term management effectiveness outcomes in IPLC-led contexts.

In addition, in FY26, ICI provided ManGo trainings across the initiative portfolio through 9 total regional trainings, reaching 64 participants.

Factors that improve likelihood of long-term sustainability of project impacts: In FY26, ICI launched a call for Catalytic Grant applications open to all ICI initiatives, dedicating $100,000 in total funding ($10,000 per initiative) to support the sustainability of project impacts beyond the life of GEF-7 ICI funding. Initiatives were asked to design proposals outlining how they would use the grant to secure follow-up funding and scale or elevate the work advanced through ICI.

Initiatives are applying the funds toward strategies tailored to their respective fundraising needs and capacities, including participation in donor and funding network events, hiring proposal development specialists, and developing fundraising strategies. The objective across initiatives is to build capacity to design and submit competitive funding proposals, positioning them to secure independent, longer-term financing. By investing directly in initiatives' fundraising capacity, the Catalytic Grants address one of the central risks to long-term sustainability: that impact achieved under ICI stalls once the project's direct funding ends. This approach reflects a deliberate strategy to strengthen the financial self-sufficiency and continuity of IP and LC-led initiatives.

MTR Management Response: The MTR, conducted by Earth Empower between March and August 2025, resulted in 23 recommendations across nine thematic areas. CI-GEF and IUCN-GEF, in coordination with the PMU, prepared a formal Management Response and have tracked implementation progress since September 2025. As of this reporting period, 5 recommendations are complete, 14 are in progress, and 4 were assessed as most relevant to the design of future IPLC-led projects rather than requiring fitting into the current ICI design. A thematic summary of progress is provided below.gg

| MTR THEMATIC AREA | # RECS | STATUS | KEY FY26 PROGRESS HIGHLIGHTS |
| --- | --- | --- | --- |
| Project Design, Appraisal & Planning | 4 | 1 In Progress; 3 N/A to ICI | Adaptive management milestones remain embedded in quarterly reporting, workplan updates, and annual PIR recalibration. The CI–IUCN MOU has been reviewed and updated as a living document defining team roles and responsibilities (Completed). Recommendations on a dedicated “Year Zero,” global-level Theory of Change framing, and single-lead institutional models were assessed as most relevant to the design of future multi-institutional IPLC projects. |
| Project Management | 3 | 1 Completed; 2 N/A to ICI | Component 4 management was transferred from IUCN to CI to address staffing constraints and delivery delays (Completed). Recommendations on dedicated travel budgets for finance/grants capacity-building and single-institution leadership were noted as most applicable to future project design. |
| Capacity Building | 1 | In Progress | The Makanisi Learning Academy continues to expand its capacity development offerings. Six online courses are currently under development, and nine virtual training topics have been identified, with translation and accessible delivery underway. |
| Gender | 3 | 1 Completed; 2 In Progress | Gender-responsive actions and budgets were mainstreamed into all FY26 subproject workplans (Completed). Bi-monthly dialogues among gender focal points, the GSC, and the PMU continue, and subproject-level masculinities strategies are being developed with organizations. |
| Knowledge, Collaboration & Learning | 2 | 1 Completed; 1 In Progress | Informal WhatsApp-based exchange groups are active and effective across the GSC, communications, fellows, and regional networks (Completed). Virtual knowledge-exchange sessions (ManGo, ICCA registration, gender, communications) are ongoing. |
| Communication & Outreach | 1 | In Progress | Multi-channel communication loops (email, WhatsApp, direct technical follow-up) are maintained with all IPLC-led subprojects; regional exchange blogs and videos continue to be co-created and authored directly by IPLC partners under informed-consent protocols. |
| Sustainability | 2 | In Progress | IPLC leaders continue to engage in global climate finance spaces (e.g., UNFCCC COPs) and connect with climate finance actors; targeted trainings on sustainable finance are in development. Support for land titling, tenure security, and legal recognition of IPLC governance continues with national governments and legal partners. |
| Risk Management | 3 | In Progress | Subproject Safeguard Plans have been revised to reflect protections for high-risk areas and environmental defenders. ESS and risk-management frameworks were co-developed directly with subproject partners through the Impact Strategy design process. The ICI Community of Practice is being strengthened as a cross-subproject space for sharing risk-mitigation experience. |
| Monitoring & Evaluation | 3 | 1 Completed; 2 In Progress | The ICI M&E Reform streamlined subproject reporting to two sections in Q1–Q3, with full reporting in Q4 (Completed). The Global M&E Operational Plan is already in place and provides standardized, gender and IPLC-sensitive qualitative indicators rolled out with targeted training for subproject M&E staff. |

The full Management Response Matrix including detailed responses, responsible parties, timelines, and evidence is maintained by the PMU and reviewed regularly as part of ICI’s adaptive management.

SECTION VI: PROJECT GEOCODING

This section of the PIR documents the precise and specific geographic location(s) of activities supported by GEF investments based on information provided in the Project Document.  The following information should be contained in this section:

  - Geo Location Information of Project Location(s) for the current fiscal year

  - Project Map and Coordinates from Project Document

Geo Locations Information of Project Location(s) for the current fiscal year FY26 (July 25 – June 26)

The Geolocation Information of Project Locations (s) for the current fiscal year is compiled in this excel sheet.

| INITIATIVE NAME Name of Inclusive Conservation Initiative Location. | CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included at CEO Endorsement/ Approval or not. Please add more columns for projects with more than 3 locations. Note: Provide justification if the location is a new site in this line | GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org | LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. |
| --- | --- | --- | --- | --- | --- |
| Annapurna Conservation Area “NEFIN-Nepal” | excel sheet. |  |  |  |  |
| DR Congo ANAPAC/ Dem. Republic of Congo |
| Ewaso Ng’iro River Basin IMPACT Kenya | excel sheet. |  |  |  |  |
| Futa Mawiza Biocultural Territory Argentina FARN/Argentina | excel sheet. |  |  |  |  |
| Futa Mawiza Biocultural Territory – Observatorio Ciudadano /Chile | excel sheet. |  |  |  |  |
| Thailand/IPF Thailand | excel sheet. |  |  |  |  |
| Northern Tanzania UCRT/Tanzania | excel sheet. |  |  |  |  |
| Ru K'ux Abya Yala Guatemala, Panama/ Sotzil | excel sheet. |  |  |  |  |
| Southwest Amazon “FENAMAD /Peru” | excel sheet. |  |  |  |  |
| Lau Seascape Cook Islands Fiji/Cook Island | excel sheet. |  |  |  |  |

Please provide a justification regarding changes in location during implementation. Justifications should also be provided in the event the geographic 	location of key project activities cannot be provided at CEO Endorsement/Approval stage.

(Geo Name ID: Location Name) Justification:

Project Map and Coordinates

Please provide geo-referenced information and an image map where the project interventions took place. If available, please provide

attachments as 	appropriate such as in the case of locations presented along geometric shapes in popular formats like shapefiles, KML

and GeoJSON.

Map: AMERICAS REGION: ARGENTINA Subproject Region: Southern Cone Indigenous groups : Mapuche Geographic scope (ha) : 454,409 EA: Fundación Ambiente y Recursos Naturales – Argentina Please access the link for Google Map: FARN, Argentina Georeferenced Intervention Map Please access the link for KML File: Link for KML File CHILE: Subproject Region: Southern Cone Indigenous groups: Mapuche Geographic scope (ha): 491,792 EA: El Observatorio Ciudadano – Chile Please access the link for Google Map: Futa Mawiza Chile Georeferenced Intervention Map Please access the link for KML File: Link for KML File PERU: Subproject Region: Southwest of the Amazon in Peru Indigenous groups: Ese Eja Nation, Harakbut Nation, Yine Nation, Matsigenka communities of the Manu National Park Geographic scope (ha): 7,497,911 EA: FENAMAD-Perú Please access the link for Google Map: FENAMAD, Peru Georeferenced Intervention Map Please access the link for KML File: Link for KML File GUATEMALA-PANAMA: Subproject Region: Mesoamerica – Guatemala, Panama Indigenous groups: Maya, Kaqchikel, Q’eqchi, k’iche and Garifuna (Guatemala), and Guna (Panamá) Peoples. Geographic scope (ha): 854,604 ha EA: Asociación Sotz’il-Guatemala Please access the link for Google Map: Sotzil, Guatemala-Panama Georeferenced Intervention Map Please access the link for KML File: Link for KML File ASIA REGION: NEPAL: Subproject Region: Himalayas, Anapurna conservation area Indigenous groups: Gurung, Magar, Thakali, Manange, Baragungle and Tingaule Thakali Indigenous Peoples Geographic scope (ha): 787,900 EA: Nepal Federation of Indigenous Nationalities (NEFIN) Nepal Please access the link for Google Map: NEFIN, Nepal Georeferenced Intervention Map Please access the link for KML File: Link for KML File THAILAND: Subproject Region: Mainland Southeast Asia-Thailand Indigenous groups: Karen, Hmong, Lisu, Lahu, Iu Mien, Akha, and Mani. Geographic scope (ha): 139,743 EA: Indigenous Peoples’ Foundation for Education and Environment (Thailand) Please access the link for Google Map: IPF Thailand Georeferenced Intervention Map Please access the link for KML File: Link for KML File AFRICA REGION: KENYA Subproject Region: The Ewaso Ng’iro River Basin- East Africa Drylands Indigenous groups: Borana; Gabra; Maasai; Rendille; Samburu; Somali; Turkana; Pokot Geographic scope (ha): 3,468,488 EA: Indigenous Movement for Peace, Advancement & Conflict Transformation (IMPACT) Kenya Please access the link for Google Map: IMPACT, Kenya Georeferenced Intervention Map Please access the link for KML File: Link for KML File TANZANIA: Subproject Region: Northern Tanzania- East Africa Drylands rangelands. The project area extends across critical areas of rangeland connectivity south and east of the greater Serengeti – Ngorongoro and makes up the northern and southern most extents of the Tarangire – Manyara ecosystems. Indigenous groups: Hadzabe, Akie, Maasai, Datoga, and Iraqw Geographic scope (ha): 940,000 EA: Ujamaa Community Resource Team (Tanzania) Please access the link for Google Map: UCRT, Tanzania Georeferenced Intervention Map Please access the link for KML File: Link for KML File RÉPUBLIQUE DÉMOCRATIQUE DU CONGO Subproject Region: Congo basin Indigenous groups : Bambuti- Babuluko; Batwa; Bacwa Geographic scope (ha) : 661,931 EA : Alliance Nationale d'Appui et de Promotion des Aires et territoires conservés par les Peuples autochtones et communautés locales en République démocratique du Congo (ANAPAC-RDCONGO) Please access the link for Google Map: ANAPAC-RDCONGO Georeferenced Intervention Map Please access the link for KML File: Link for KML File PACIFIC REGION: FIJI & COOK ISLANDS Subproject Region: Pacific-Lau Seascape and Cook Islands Indigenous groups: Lauan, Atiu, Pukapuka Geographic scope (ha): 483,104 EA: House of Ariki/Lau execution support through CI Fiji Please access the link for Google Map: FIJI & COOK ISLANDS Georeferenced Intervention Map Please access the link for KML File: Link for KML File

Section VII: Minor Amendments

This section of the PIR captures the changes to the project design or implementation that do not have a significant impact on the project objectives or scope as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Select any minor amendment that happened to the project during the latest fiscal year and provide a description of the minor amendment in a narrative format (max 100 words) as appropriate in the related textbox. You may provide supporting documents as attachment to this PIR.

| Minor Amendment Categories | Minor Amendment Justification |
| --- | --- |
| Results framework | Any change in outcomes and outputs, including targets from approved Project Document |
| Components and cost | Change in GEF grant amount allocated to the components of more than 10% |
| Institutional and implementation arrangements | The GEF approved the C4 funds transfer from IUCN to CI in October 2025. |
| Financial management | Change in financial management or financial flows from what was described in the Project Document |
| Implementation schedule | Change in implementation period from approved Project Document |
| Executing Entity | Change in Executing Agency from approved Project Document |
| Executing Entity Category | Change in Executing Agency category (e.g., CSO, government, private sector) from approved Project Document |
| Minor project objective change | A decrease in 10% of Objective Indicator targets from approved Project Document |
| Safeguards | Change in ESS Standards (e.g., new ones triggered, existing ones escalated/de-escalated) |
| Risk analysis | An inclusion of a new risk |
| Increase of GEF project financing up to 5% | Any request in GEF funding up to 5% of approved amount. Note that this is not typical for GEF projects |
| Co-financing | For final PIRs only, a decrease in 10% or more of co-financing from amount in approved Project Document |
| Location of project activity | Change in location of project activities from approved Project Document |
| Other | Any other change not captured above |

MINOR AMENDMENT RESPONSE FROM CI-GEF

APPENDIX I: PROJECT ANNUAL IMPLEMENTATION PROGRESS RATING

| Rating |  | Overdue (O) | Delayed (D) | Not started on schedule (NS) | Under implementation on schedule (IS) | Completed/Achieved (CA) |
| --- | --- | --- | --- | --- | --- | --- |
| Highly Satisfactory (HS) | HS | 0% |  | 100% |  |  |
| Satisfactory (S) | S | 20% |  | 80% |  |  |
| Moderately Satisfactory (MS) | MS | 40% |  | 60% |  |  |
| Moderately Unsatisfactory (MU) | MU | 60% |  | 40% |  |  |
| Unsatisfactory (U) | U | 80% |  | 20% |  |  |
| Highly Unsatisfactory (HU) | HU | 100% |  | 0% |  |  |

- Highly Satisfactory: 100% of the indicators:  a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Annual Workplan for the project. The project can be presented as an example of “good practice” project,

- Satisfactory: 80% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; except for only 20% that are delayed and/or overdue and need remedial action,

- Moderately Satisfactory: 60% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 40% are delayed and/or overdue and need remedial action,

- Moderately Unsatisfactory: 40% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 60% are delayed and/or overdue and need remedial action,

- Unsatisfactory: only 20% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 80% are delayed and/or overdue and need remedial action, and

- Highly Unsatisfactory: 100% of the indicators: a) are overdue, and/or b) delayed in their implementation, according to the approved/revised Project Annual Workplan for the project.

# APPENDIX II: RISK RATINGS

| Rating |  |
| --- | --- |
| Low (L) | L |
| Moderate (M) | M |
| Substantial (S) | S |
| High (H) | H |

- Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold, and/or the project may face substantial risks.

- High Risk: There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

# APPENDIX III: PROGRESS TOWARDS ACHIEVING PROJECT EXPECTED OUTPUTS

| # INDICATORS | # PROJECT TARGET | # END OF YEAR INDICATOR STATUS | # PROGRESS RATING | # COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- |
| # Outcome 1.1 Inclusive Conservation Initiative (ICI) Subprojects are led by IPLC organizations |  |  |  |  |
| # Output Indicator 1.1.1.: Number of IPLC organizations contracted in ICI Subproject Geographies | # 10 lead-contracting organizations | Completed! 10 of 10 IPLC organizations contracted in ICI Subproject Geographies. | CA | All 10 ICI lead IPLC organizations have finalized their impact strategies by signing the implementing ICI Planning Grants. Each organization now serves as an IPLC Executing Agency. |
| # Output Indicator 1.1.2.: Number of subproject Impact Strategies | # 10 Impact Strategies | Completed! All 10 ICI Subprojects have completed their impact strategies. | CA | All 10 ICI subprojects completed their Impact Strategies and advanced towards implementation phase. Moreover, all ICI subprojects have identified priority actions which will contribute to GEF global targets. |
| # Output Indicator 1.1.3.: Number of ICI subprojects that have implemented activities for enhancing IPLC rights and governance | # 10 subprojects | All 10 ICI subprojects have been implementing their project activities outlined in the Subproject's FY26 Annual Workplan, particularly focusing on enabling and enhancing the rights and governance of IPLC. | IS | All 10 subprojects are implementing FY26 Workplans, with a strong focus on advancing IPLC rights and governance. Highlights include Fiji’s Traditional Leadership and Governance Manual (94% of chiefly titles registered, now piloted in 19 villages), UCRT’s completion of village land-use planning across 175,709 ha and UCRT also kept strengthening Women’s Rights and Leadership Forums (WRLFs), to among others to d guide women on appropriate reporting and referral pathways for rights violations within their communities., IMPACT Kenya’s boundary-harmonization work and new rights-based conservation course, ANAPAC’s ICCA mapping and legal working group top keep supporting the requested assistance in demarcating Indigenous living territories; , and continued policy engagement by FENAMAD, NEFIN, and Sotz’il, especially with a strong incidence at local but also global spaces and articulation of women shaped messages. Monitoring continues through subprojects’ quarterly and semi-annual reporting. |
| # Output Indicator 1.1.4.: Number of ICI subprojects that have implemented activities for improving management of natural and cultural resources | # 10 subprojects | All 10 ICI subprojects have been implementing their project activities outlined in the Subproject's FY26 Annual Workplan, particularly focusing on improving management of natural and cultural resources. | IS | All 10 subprojects are implementing FY26 activities to address drivers of environmental degradation, including FENAMAD's national policy engagement (30x30 Target), Futa Mawiza's co-governance agreements and Environmental Monitoring Committee work, IMPACT's pastoralist forums and animal-health monitoring, Fiji's iKatch fisheries-monitoring app launch, and Sotz'il's reforestation and firebreak maintenance. Monitoring continues through subprojects' quarterly and semi-annual reporting, i.e. ANAPAC with their local cartographers trained by the project had carried out monitoring activities on their community boundaries and the degradation of biodiversity. . It is also important to highlight Sotz’il’s work with implementing partners operating in conflict-affected areas, where communities strengthened their knowledge and capacity to manage collective rights and resolve conflicts. |
| # Output Indicator 1.1.5.: Number of ICI subprojects that have implemented activities for addressing the drivers of environmental degradation | # 10 subprojects | All 10 ICI subprojects have been implementing their project activities outlined in the Subproject's FY26 Annual Workplan, particularly focusing on addressing the drivers of environmental degradation. | IS | All 10 subprojects are implementing FY26 activities to address drivers of environmental degradation, including FENAMAD's national policy engagement (30x30 Target), Futa Mawiza's co-governance agreements and Environmental Monitoring Committee work, IMPACT's pastoralist forums and animal-health monitoring, Fiji's iKatch fisheries-monitoring app launch, and Sotz'il's reforestation and firebreak maintenance. Monitoring continues through subprojects' quarterly and semi-annual reporting, i.e. ANAPAC with their local cartographers trained by the project had carried out monitoring activities on their community boundaries and the degradation of biodiversity. It is also important to highlight Sotz’il’s work with implementing partners operating in conflict-affected areas, where communities strengthened their knowledge and capacity to manage collective rights and resolve conflicts. |
| # Output Indicator 1.1.6.: Number of ICI subprojects that have implemented activities to support economic and financial sustainability | # 10 subproject | All 10 ICI subprojects have been implementing their project activities outlined in the Subproject's FY26 Annual Workplan, particularly focusing on supporting economic and financial sustainability. | IS | All 10 subprojects advanced income-generating and enterprise activities, including IPF's Community Fund (benefiting 4,700+ people), Sotz'il's "Nuestras Raíces" brand, UCRT's VICOBA training and USD 718,500 in conservation revenue, ANAPAC's micro-grants to women's and youth groups, and new livelihood initiatives in Fiji/Cook Islands and Futa Mawiza; and NEFIN keeps providing financial support to start-up initiatives, with women comprising at least 50% of beneficiaries and Indigenous women-led enterprises representing at least 50% of those supported. Monitoring continues through subprojects' quarterly and semi-annual reporting. |
| # Output Indicator 1.1.7 Number of ICI subprojects with designated IPLC-led governance structures | # 10 subproject | All 10 ICI subprojects have representation in the Global Steering Committee (ICI governance). | IS | The PMU facilitated three virtual GSC meetings across FY26. Key decisions included launching the Catalytic Grants (Output 2.3.1), transitioning Component 4 oversight to CI, renominating GSC co-chairs Vivian Silole and Jorge Nawel through project close-out, expanding the third Fellows cohort to five, and holding the final Global Learning Exchange jointly with project close-out (Feb/Mar 2027). |
| # OUTCOME 1.2: Project implementation capacity of IPLC partner organizations in subproject geographies substantially increased. |  |  |  |  |
| # Output Indicator 1.2.1.: Number of capacity assessments and plans | # 10 assessments and plans | All ICI 10 subprojects are actively implementing capacity-building activities and training. | # IS | Organizational capacity-building plans for the five IUCN subprojects are currently at an advanced stage of development and are being finalized based on the findings of organizational capacity assessments covering five key areas: human resources, financial resources, management systems, strategic planning and programme delivery. The finalized plans will be implemented in Q1 FY27. For the CI-managed subprojects, organizational capacity-building priorities have already been incorporated into their respective Impact Strategies and are currently being implemented. |
| # Output Indicator 1.2.2.: Number of people trained in project management and implementation capacities identified in capacity plans | # 90 people trained (10 per subproject) | Cumulative Total 188 Men 97 (51.59%) and 91 Women (48.40%) across 10 subprojects | # IS | All 10 ICI initiatives have participated in targeted training. During FY26, the PMU strengthened the implementation and project management capacities of ICI subproject partners through training, technical assistance, and field support. Training focused on reporting, monitoring and evaluation, GEB tracking, communications, safeguards, gender mainstreaming, project management, Management and Governance tool effectiveness, and ICCA registration, with these priorities integrated into subproject Impact Strategies. A key achievement was the development and piloting of the ManGo Tool as an alternative to the Management Effectiveness Tracking Tool. Following the pilot, nine regional workshops trained 64 participants from subproject technical teams, enhancing their ability to assess management effectiveness, support territorial planning, and report on GEF Core Indicators. In parallel, UNEP-WCMC delivered four regional workshops on ICCAs and the ICCA registration process, reaching 34 participants. Additional capacity-building support was provided through field visits to subprojects in Kenya, Chile, the Cook Islands, Argentina, Peru, and Guatemala, which helped review implementation progress, verify results, identify challenges and lessons learned, and discuss long-term sustainability beyond the ICI project period. In total, the ManGo and ICCA workshops reached 98 participants during FY26. To build capacity on external communications, the PMU also held four communications training sessions, reaching 41 individual learners; all 10 ICI Initiatives participated in targeted training. The series — four of five planned modules delivered to date — equipped communications focal points with practical tools to plan, develop, and evaluate communications products, moving subproject reporting beyond activity-based updates toward narratives that demonstrate meaningful change and Indigenous leadership. |
| # OUTCOME 2.1: IPLC capacity substantially strengthened within and beyond ICI subproject geographies. |  |  |  |  |
| # Output Indicator 2.1.1.: Number of Curricula designed | # 1 Curriculum designed | 1 curriculum designed https://www.learningfornature.org/en/courses/gender-and-biodiversity-decision-making/ | # CA | The indicator target has been surpassed. One ICI learning curriculum, “IPLCs, Gender and Biodiversity Linkages”, has been successfully developed and launched, and reaching 3,564 participants cumulative. In addition, four other curricula are under development or in the final stages of review, translation, and rollout, bringing the total number of launched and in-development curricula to five. During FY27, translated versions of the launched module will be published through the IUCN Learning Academy and UNDP Learning for Nature Platform, while the associated Training-of-Trainers manual undergoes editorial review. The Indigenous Negotiations, Indigenous Governance Systems and Institutional Strengthening, Global and Regional Frameworks for Indigenous Peoples’ Rights Protection and Promotion, Project Cycle and Results-Based Management Frameworks, and Sustainable Financing Principles and Strategies modules are expected to be finalized and rolled out during FY27, further expanding the Makanisi Learning Academy and increasing access to culturally relevant learning opportunities for Indigenous Peoples and Local Communities. |
| # Output Indicator 2.1.2.: Number of Learning Academies established | # 1 Learning Academy established | # 1 Learning Academy established | # CA | The ICI Makanisi Learning Academy was successfully established and operationalized during FY26 through its presence on the ICI website and partnerships with UNDP’s Learning for Nature platform and the IUCN Learning Academy. Makanisi serves as a culturally appropriate virtual platform offering access to knowledge materials, tools, training modules, and curated resources developed by IPLC organizations. It ensures that learning remains grounded in Indigenous perspectives while promoting collaboration and shared learning. Makanisi also anchors a growing community of practice that connects IPLC leaders across regions to exchange experiences, build solidarity, and co-create approaches to inclusive conservation. The animation video for the Makanisi Academy has also been finalised and will be used for promotional purposes. The Academy’s first learning module, IPLCs, Gender and Biodiversity Linkages, remained publicly available throughout the year, enrolling 2,334 participants and demonstrating strong demand for Indigenous Peoples and Local Communities (IPLC)-focused learning resources. Additional foundational elements were completed, including multilingual branding and promotional materials and the development of a Training-of-Trainers manual. Progress also continued expanding the Academy’s learning offer. By the end of FY26, one module had been completed, four additional modules were under development, and preparations were underway for the Sustainable Financing Principles and Strategies training series. English, French, and Spanish versions of key courses were finalized, while publication, translation, and rollout activities will continue during FY27. As the remaining modules are launched and resources are progressively consolidated on the IUCN Learning Academy, the Makanisi Learning Academy will continue to grow as a centralized platform for culturally relevant capacity-building resources, improving accessibility, visibility, user management, and monitoring of learning outcomes. |
| # Output Indicator 2.1.3.: Number of organizations supported | # 10 ICI subproject lead organizations, at least 20 additional organizations | 52 IP and LC additional organizations supported | IS | The output remains under implementation; however, substantial progress was made during FY26 in providing organizational development and capacity-building support through the ICI Makanisi Learning Academy. Learning content, virtual trainings, partnerships with Indigenous networks (IIFB, Indigenous Women Biodiversity Network, and Network of Indigenous Women on Biodiversity from Latin America and the Caribbean), and a finance-mapping exercise were advanced to inform future training and support. In parallel, all 10 ICI initiatives participated in virtual capacity-building and technical support activities on topics including strategic communications, ICCA registration, and financial management through the ManGo programme. Several ICI partners also completed the IPLCs, Gender and Biodiversity Linkages course, which remained publicly accessible and attracted more than 2,300 participants from both ICI and non-ICI organizations. IUCN further strengthened outreach, networking, and knowledge exchange by connecting Indigenous Peoples' and Local Communities' organizations with regional and global initiatives and learning opportunities. During FY27, the rollout of additional learning modules, Training-of-Trainers resources, and findings from the Finance Mapping Study will support the delivery of more structured organizational development and capacity-building support through the Makanisi Learning Academy. |
| # Output Indicator 2.1.4.: Number of evaluations completed | # 1 evaluation | 0 out of 1 planned evaluation completed. | IS | The indicator remains under implementation. During FY26, preparatory work advanced for the future evaluation of the ICI Makanisi Learning Academy through the collection and review of enrolment, completion, and gender-disaggregated participation data for the IPLCs, Gender and Biodiversity Linkages module. The course remained publicly accessible through UNDP's Learning for Nature platform and enrolled 2,334 participants, of whom 721 completed the course, providing an initial evidence base for assessing uptake, accessibility, and performance. Arrangements were also initiated to regularly consolidate and analyze learning data from UNDP's Learning for Nature platform, the IUCN Learning Academy, and other delivery mechanisms. A comprehensive evaluation of the Academy's learning offer will be undertaken in FY27, once the remaining five modules have been finalized and launched, enabling a broader assessment of the relevance, accessibility, participation, completion rates, and overall effectiveness of the full suite of six ICI learning modules. |
| # OUTCOME 2.2: Cross-regional IPLC organization of partnerships and networks strengthened through ICI Learning Exchanges. |  |  |  |  |
| Adapted Output Indicator 2.2.1.: Number of IPLC funding mapping reports # Output Indicator 2.2.1.: Number of stakeholder mapping reports (**ICI ProDoc, Original) | # 1 mapping report, incorporating subproject/regional information and global scan of additional organizations | 1 mapping report under development | IS | The indicator remains under implementation because the finance-mapping exercise and its associated deliverables had not been completed by the end of FY26. A consultant was contracted in Q4FY26, with the mapping of funding report expected by September 2026 for launch at UNCBD COP17. The consultancy will produce three main outputs: Finance Mapping Study Report; Map of Funding Opportunities; and One-page summary of the key findings and recommendations. An Indigenous Miskita finance expert has been engaged to lead the Finance Mapping study to map key conservation and climate finance opportunities for Indigenous Peoples and local communities, assess their accessibility, and identify the main requirements and barriers to direct finance. The study will be finalized for presentation at the Nature and Culture Summit, jointly organized by the COP17 Presidency, UNESCO, IUCN and partners. Its findings will be featured in a dedicated panel on inclusive and direct finance during the UN Biodiversity Conference, CBD COP17, taking place in Yerevan, Armenia, in October 2026. |
| # Output Indicator 2.2.2.: Number of learning exchanges | # 8 learning exchanges with gender mainstreaming throughout, and a gender focus in at least one (5 regional, 3 global) | 7 learning exchanges completed (3 global and 4 regional) | IS | Indicator 2.2.2 remains under implementation because the final global ICI event has not yet been delivered. Since the start of the project, seven ICI Exchanges have been completed (three global and four regional), two occurred in FY26 creating important opportunities for peer learning, collaboration, and knowledge exchange among Indigenous Peoples and Local Communities (IPLCs), ICI partners, and external stakeholders. During FY26, consultations with GSC members and subproject teams helped refine the thematic focus and delivery of the exchanges, prioritizing communications and storytelling, traditional knowledge, co-governance of protected areas, and territorial and land-use planning. The Third Global Learning Exchange, held in Abu Dhabi in October 2025 alongside the IUCN World Conservation Congress, enabled ICI partners and Indigenous leaders to participate in the first-ever World Summit of Indigenous Peoples and Nature, a landmark gathering that brought together Indigenous leaders from around the world to advance Indigenous rights, knowledge, and leadership within the global conservation agenda. Participant feedback from the exchange demonstrated increased knowledge and skills across areas including Indigenous leadership, equity and inclusion, access to finance, traditional knowledge, policy engagement, communications, and partnership building, with all participating organizations reporting new partnerships or collaborations. This momentum continued through the Pacific Inclusive Conservation Learning Exchange, held in the Cook Islands in June-July 2026, which brought together Indigenous chiefs, traditional leaders, knowledge holders, women, and youth from across the Pacific and beyond to exchange experiences on Indigenous governance, ocean stewardship, sustainable livelihoods, conservation finance, and intergenerational knowledge transfer. Together, these exchanges have strengthened regional and global networks, fostered collaboration, and supported IPLC participation in conservation decision-making, with a final project-wide learning and close-out event planned for FY27 to consolidate lessons and results across the initiative. |
| # OUTCOME 2.3: IPLC organizational capacity increased to formulate sustainable financing strategies. |  |  |  |  |
| Adapted Output Indicator 2.3.1: No. of small grants awarded to ICI subprojects to support prospect funding efforts (target: 2 rounds of $5,000 per project). # Output Indicator 2.3.1.: Number of Financial Opportunity analyses completed (**ICI ProDoc, Original) | Adapted Output Indicator Target 2.3.1. (5k/project x 2 rounds) # Output Indicator Target 2.3.1.: 10 Financial Opportunity analyses completed. (**ICI ProDoc, Original) # ) | USD 10,000/project (USD 100,000 total) approved in a single round, in lieu of the planned 2-round/$5k structure; no additional rounds will be planned. USD 32,000 disbursed to date. | IS | The Catalytic Grants initiative was launched in October 2025 to provide grants to ICI subprojects to help secure prospective funding and strengthen resource-mobilization efforts. By June 30, 2026, all 11 proposals from the 10 ICI initiatives had been received, with Fiji and the Cook Islands submitting separate proposals. During the reporting period, nine proposals received a total of USD 32,000 in catalytic grant funding. Monitoring, reporting, and documentation of grant implementation and results are ongoing. Results will be consolidated and circulated as the supported initiatives begin implementing their proposed activities and reporting on the use of the funds. Most of the grants received focus on preparing project documents for potential submission under the GEF-9 replenishment cycle. Others, such as UCRT, have identified specific opportunities and venues to showcase their work and present their priorities directly to potential donors. Sotz’il’s strategy has focused on expanding and diversifying its portfolio of partners to strengthen future collaboration and resource mobilization. |
| # Output Indicator 2.3.2.: Number of ICI subproject lead organizations trained | # 10 organizations trained. | TOR and course outline developed for rollout in FY27 | IS/D | The indicator remains under implementation, as the course outline was developed and TOR developed, but rollout of the training had not been completed by the end of FY26. |
| # OUTCOME 3.1: Strengthened influence of IPLC in relevant regional and international decision-making processes. |  |  |  |  |
| # Output Indicator 3.1.1.: Number of mechanisms strengthened | # 2 mechanisms strengthened (IIFB-IIPFCC) | 100% and in progress | # IS | ICI partners continued engagement with the International Indigenous Forum on Biodiversity (IIFB) throughout FY26, including at the IUCN World Conservation Congress. In Q3–Q4, support expanded to the UNCCD IP Caucus, alongside continued engagement ahead of UNCBD COP17 and UNFCCC COP31. In Q2, ICI also engaged with Indigenous leaders at the COP6 Minamata Convention. |
| # Output Indicator 3.1.2.: Number of curricula developed and delivered | # 1 curriculum | 1 curriculum under development | # IS | Synergies across ICI programs—including the ICI Fellowship, Regional and Global Exchanges, and support for IPLC leaders’ participation in the UNCBD and UNFCCC processes—are contributing to stronger engagement in global policy discussions. During the IUCN World Conservation Congress (WCC) in Abu Dhabi, IPO IUCN members together with IUCN facilitated virtual sessions to brief participants on WCC engagement. ICI Fellows and Global Steering Committee members actively participated in these preparatory discussions. In parallel, engagement has also continued with the Minamata Convention, ICI project and IP partners, with a dedicated curriculum currently in development related to the Minamata Convention. This curriculum will be launched through the Makanisi Learning Academy as part of ICI’s broader policy learning agenda in FY27. In addition, coordination has begun to support UNCCD IP Caucus for formal establishment. |
| # Output Indicator 3.1.3.: Number of fellows supported | # 15 fellows (5 per year in years 2-4 of project, at least 50% women) | 17 fellows supported (59% women) | # IS | The ICI Fellows Program supports emerging Indigenous leaders by linking their community-based conservation efforts with global environmental policy processes. The second cohort of seven fellows participated in a transformative journey that included leadership training, applied case studies, and direct engagement at IUCN WCC, Pacific Regional Exchange, and Minamata Convention. A third cohort of five fellows was also selected in this reporting period. Fellows are also engaged in peer learning and strategic partnerships, including diploma programs and cross-cohort exchanges, strengthening their role as agents of change in both territorial and international arenas. |
| # Output Indicator 3.1.4.: Number of high-level events organized | # 5 events (at least 1 event to include focus on gender issues/topic) | Cumulative Total IP and LC leaders: 105 (Men: 65 (61.9%) and Women: 40 (38.1%) | # IS | In FY26, ICI organized a total of 9 events including: 7 events at the IUCN World Conservation Congress in October 2025, 1 event at the Minamata COP6 in November 2025, and 1 event at the GEF Assembly in May 2026. Gender issues were integrated across all the below listed events, with IPLC women directly sharing their experiences and perspective. The event at Minamata COP6 — Indigenous Peoples in the Arctic and the Amazon: Monitoring experiences and the implementation and effectiveness evaluation of the Minamata Convention — specifically addressed the impacts of mercury contamination on women and children. IUCN World Conservation Congress (October 2025): - Transforming Climate and Biodiversity Finance: Lessons Learned from Indigenous-Led Initiatives. (Forum Event) - Walking the Talk: ICI’s 2025 Report on Advancing Equity through Indigenous-Led Conservation (GEF Pavillion) - Walking the Talk: Mapping and Governing Territories for Inclusive Conservation (Nature Positive Pavillion) - Walking the Talk: Inclusive Conservation in Action Across the Americas (America's Pavillion) - Voices of Indigenous Youth – Community Leadership and Ancestral Knowledge for Nature and Culture (Youth Pavilion) - Stewarding the Earth: Session 1 and Session 2 (Indigenous Pavilion) - Beyond Passion: The Realities Youth Face in Conservation (Youth Pavilion) Minamata Convention COP6 (November 2025): - Indigenous Peoples in the Arctic and the Amazon: Monitoring experiences and the implementation and effectiveness evaluation of the Minamata Convention. GEF Assembly Samarkand (May 2026): - Indigenous Leadership Delivering Global Environmental Benefits: Scaling Impact Through GEF-7 and GEF-8 — Pathways to GEF-9 |
| # OUTCOME 4.1: The field of IPLC-led conservation advanced with improved knowledge management. |  |  |  |  |
| # Output Indicator 4.1.1.: Number of KM platforms established | # 1 KM platform established | 1 KM platform established | # CA | The ICI Knowledge Platform underwent a full revamp to better showcase the initiative's results and the efforts of its subprojects. The updated site features a more visually engaging, user-friendly design and an expanded library of knowledge products including regional learning exchange outcomes, web stories, podcasts, blog posts from ICI subprojects, and policy engagement updates. Together, these enhancements strengthen the platform's role as the central hub for sharing knowledge and learning across the initiative. |
| # Output Indicator 4.1.2.: Number of Knowledge products developed | # 07 products (reflecting gender-inclusivity) | 03 of 07 knowledge products i.e. Lessons Learned Reports have been produced and published on the ICI Knowledge Platform. - Phase I Lessons Learned Report - Phase II Lessons Learned Report - Phase III Lessons Learned Report | # IS | During this reporting period, several key knowledge products were developed and published in collaboration with IPLC organizations. These include the ICI Phase Three Report (available in English, Spanish, and French), a series of blogs authored by ICI fellows sharing how the fellowship has impacted them and their case studies, a podcast series honoring International Women's Day exploring how Indigenous women are reshaping the meaning of science through ancestral knowledge, lived experience, and community leadership. As well as videos including a video on Earth Day that featured the voices of Indigenous leaders in Chile and Argentina sharing what it means to protect nature, sustain culture, and defend their territories of life. |
| # Output Indicator 4.1.3.: Number of communities of practice established | # 1 community of practice | 1 community of practice | CA | The ICI Community of Practice (CoP) has been established as a collaborative platform for peer learning, knowledge exchange, and inclusive conservation. Structured around a four-phase Design Thinking model—Inspiration, Ideation, Co-development, and Outcomes—the CoP has advanced significantly through a combination of virtual and in-person engagement. Virtual exchanges and Fellows virtual sessions are now being held on an ongoing basis, providing regular touchpoints for peer learning and cross-project dialogue between ICI Fellows and partners. |
| # OUTCOME 4.2: Expanded audience engaged in IPLC-led conservation. |  |  |  |  |
| # Output Indicator 4.2.1.: Number of communications strategies developed | # 1 communications strategy (reflecting gender mainstreaming) | 1 communication strategy (reflecting gender mainstreaming) | CA | Following the shift of Component 4 responsibility to CI in FY26, the updated ICI Communications Strategy for FY25–FY27 is now under implementation. Developed from a communications needs assessment, the strategy aims to elevate IPLC-led conservation efforts, expand outreach to key audiences including donors, governments, and partners, and strengthen storytelling and visibility through the Community of Practice. With responsibility for Component 4 now under CI, execution has resumed and is progressing toward elevating the reach of ICI communications products and expanding audience engagement. |
| # Output Indicator 4.2.2.: Number of Communications Programs executed | # 1 program | 1 program under implementation | # IS | # The ICI Communications Program is now in full implementation, following an updating process undertaken in FY26 to strengthen delivery and coordination. Key deliverables are advancing, including the launch of the Makanisi page, creation of a Policy Fellows subpage, updates to geographic pages and impact trackers, and the reintegration of stories across the website. |
| # Output Indicator 4.2.3.: Number of people trained | # 90 people trained (10 per geography) | # A total of 83 people were trained in communications, comprising 38 men (45.8%) and 45 women (54.2%). | IS | Following completion of the communications needs assessment with all 10 ICI project partners, the resulting training program was launched in FY26, with three of five planned trainings delivered to date. The trainings incorporate gender-responsive strategies and are designed to strengthen partners' capacity for visibility, storytelling, and engagement. The remaining two trainings are planned for completion in Q1FY27. |
| OUTCOME 5.1: Monitoring and evaluation conducted to verify effective project execution. |  |  |  |  |
| # Output Indicator 5.1.1: Number of Project M&E systems operational | # One Project M&E system | 100% achieved – system operational across all 10 ICI subprojects | # CA | # Although the indicator has been achieved, implementation of follow-up and quality assurance will continue during FY27 to consolidate results and complete outstanding monitoring processes. The PMU will continue reviewing subproject progress reports, Indicator Performance Tracking Tables, beneficiary data, and means of verification, providing targeted technical guidance on remaining data-quality issues, reporting gaps and inconsistencies. This will be complemented by semi-annual indicator reviews and ongoing safeguards monitoring. Technical review and validation of the FAO EX-ACT calculations will also continue, to ensure consistency in assumptions and methodologies and to produce a consolidated portfolio-level estimate of greenhouse gas emissions mitigated through ICI interventions. # Data collection, follow-up and analysis for the ICI Subprojects Mid-Term Survey on Livelihood Benefits to Communities will be completed during FY27, helping ensure adequate beneficiary coverage, balanced representation of women and men, and reliable evidence for assessing progress against Outcome 1.1 and Indicator 1.1.B. The ICI Subprojects Core M&E Working Group will continue to provide a platform for technical assistance, peer learning, adaptive management and resolution of reporting issues — supporting evidence of quality and final project reporting through FY27. |

Progress (IP) Rating: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). For more details about IP rating, please see the Appendix I of this report

Rating trend: Improving, Unchanged, or Decreasing

Risk Rating: Low (L), Moderate (M), Substantial (S), High (H)

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

The reported mitigation amount of 67,117,739 tCO₂e corresponds to an EX-ACT net carbon balance of –67,117,739 tCO₂e. In EX-ACT, a negative carbon balance represents a net sink or reduction in emissions relative to the without-project scenario.

In the context of ICI, this GEF common indicator includes IPLC as partners and expands the project's perspective beyond conventional characterization of beneficiaries.

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

Rating trend: Increasing, Unchanged or Decreasing

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved