## GEF Core Indicators FY23-FY26
GEF7 CORE INDICATORS
CONTRIBUTIONS TO THE GENERATION OF GLOBAL ENVIRONMENTAL BENEFITS
Indicator & Component Sub-indicator |  | Contextual Sub-indicator
|  |  | Target | Achieved | Achieved | Achieved | Achieved | % of completion
|  |  | CEO Endorsement | FY23 (Jan 22 - June 23) | FY24 (July 23 - June 24) | FY25 (July 24 - June 25) | FY26 (July 25 - June 26)
1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (ha) |  | 4551701 | 0 | 0 | 1898967 | 5337522 | 158.9843
1.1 | Terrestrial protected areas newly created (ha)
1.2 | Terrestrial protected areas under improved management effectiveness (ha) |  |  |  |  | 1898967 | 5337522
2 | Marine protected areas created or under improved management for conservation and sustainable use (ha) |  | 0 ha | 0 | 0
2.1 | Marine protected areas newly created (ha)
2.2 | Marine protected areas under improved management effectiveness (ha)
3 | Area of land restored (ha) |  | 14314 | 0 | 0 | 10280 | 523764 | 3730.9208
3.1 | Area of degraded agricultural lands restored (ha) |  |  |  |  | 5108 | 7916
3.2 | Area of forest and forest land restored (ha) |  |  |  |  | 5172 | 8112
3.3 | Area of natural grass and shrublands restored (ha) |  |  |  |  | 0 | 507736
3.4 | Area of wetlands (including estuaries and mangroves) restored (ha) |  |  |  |  | 0
4 | Area of landscapes under improved practices (excluding protected areas) (ha) |  | 2883851 | 0 | 0 | 2141321.63 | 3616273 | 199.6495
4.1 | Area of landscapes under improved management to benefit biodiversity (qualitative assessment, noncertified) (ha) |  |  |  |  | 1265137.63 | 2835279
4.2 | Area of landscapes that meet national or international third-party certification and that incorporates biodiversity considerations (ha)
4.3 | Area of landscapes under sustainable land management in production systems (ha) |  |  |  |  | 826184 | 780994
4.4 | Area of High Conservation Value forest loss avoided (ha) |  |  |  |  | 50000
5 | Area of marine habitat under improved practices to benefit biodiversity (excluding protected areas) (ha) |  | 165200 | 0 | 0 | 119 | 232482 | 140.7996
5.1 | Number of fisheries that meet national or international third-party certification that incorporates biodiversity considerations |  |  |  |  | 119 | 232482
5.2 | Number of Large Marine Ecosystems with reduced pollution and hypoxia
5.3 | Amount of Marine Litter Avoided
| Total area under improved management (ha) (sum of indicators 1 through 5) |  | 7615066 | 0 | 0 | 4050687.63 | 9710041 | 180.704
6 | Greenhouse gas emissions mitigated (MtCO2e) |  | 20862368 | 0 | 0 |  | 67117739 | 321.7168
6.1 | Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry and Other Land Use (MtCO2e) | [5 empty] | 67117739
6.2 | Emissions avoided (through interventions in sectors other than the Agriculture, Forestry, and Other Land Use sector)(MtCO2e)
6.3 | Energy saved (megajoules)
6.4 | Increase in installed renewable energy capacity per technology (megawatts)
7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management (number)
7.1 |  | Level of Transboundary Diagnostic Analysis and Strategic Action Program formulation and implementation
7.2 |  | Level of regional legal agreements and regional management institution(s) to support its implementation
7.3 |  | Level of national/local reforms and active participation of Inter-Ministerial Committees
7.4 |  | Level of engagement in IW:LEARN through participation and delivery of key products
8 | Globally over-exploited fisheries moved to more sustainable levels (metric tons)
9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials, and products (metric tons of toxic chemicals reduced)
9.1 | Solid and liquid Persistent Organic Pollutants (POPs) removed or disposed (POPs type) (Metric tons)
9.2 | Quantity of mercury reduced (metric tons)
9.3 | Hydrochlorofluorocarbons reduced/phased out (metric tons)
9.4 |  | Number of countries with legislation and policy implemented to control chemicals and waste (number)
9.5 |  | Number of low-chemical/non-chemical systems implemented, particularly in food production, manufacturing, and cities (number)
9.6 |  | Quantity of products/materials containing POPs/Mercury directly avoided
10 | Reduction, avoidance of emissions of POPS to air from point and non-point sources (grams of toxic equivalent gTEQ)
10.1 |  | Number of countries with legislation and policies implemented to control emissions of POPs to air (number)
10.2 |  | Number of emission control technologies/practices implemented (number)
11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment (number) |  | 142514 | 6000 | 17123 | 52598 | 52641 | 90.0697
11.1 | Women |  | (Men - 50% and Women - 50%) | (Men – 2,917 (49%), Women – 3,083 (51%)) | (Men – 8,332 (49%) and Women – 8,791 (51%) | (Men 28,262(54%)- and Women -24,336(46%)) | (Men 25,653 (48.73%)- and Women- 26,988(51.27%))
11.2 | Men
.

## Analysis Indicator (hidden)
Outcome Level Indicators:
|  | EXPECTED OUTCOMES INDICATORS | PROJECT BASELINE | NOTES: [TOTAL END OF PROJECT TARGET] | TOTAL END OF PROJECT TARGET | Progress Indicator |  | Analysis Progress
PROJECT KEY COMPONENT | EXPECTED OUTCOMES/RESULTS |  |  |  |  | TOTAL ACHIEVEMENT FY2022 - FY2023 (JAN 2022- JUNE 2023) | TOTAL ACHIEVEMENT FY2023 - FY2024 (JULY 2023- JUNE 2024) | Balance/ Variance | % of Achievement | Rating
COMPONENT 1 Local IPLC Action to Deliver Global Environmental Benefits (GEB): Established on-the-ground projects led by IPLC organizations. | OUTCOME 1.1: Inclusive Conservation Initiative (ICI) Subprojects are led by IPLC organizations. | Indicator 1.1.A: Number of direct beneficiaries disaggregated by gender. | No direct beneficiaries | Target 1.1.A: 141,174 direct beneficiaries disaggregated by gender | 141174 |  | 17123 | 124051 | 12.129 | IS
|  | Indicator 1.1.B: Percentage of beneficiaries of ICI subprojects that report increased livelihood benefits to the communities. (gender disaggregated) | No beneficiaries | Target 1.1.B: ≥50 % of beneficiaries of ICI projects report increased livelihood benefits (50% of those beneficiaries will be women). | ≥50 % of beneficiaries |  | 0 | 0 | 0 | IS
|  | Indicator 1.1.C: Percentage of ICI subprojects integrating Gender Responsive strategies | No sub-projects | Target 1.1.C: 100% of ICI projects integrating Gender Responsive strategies | 100% of ICI projects integrating Gender Responsive strategies |  | 100% | 0% | 100% | CA
|  | Indicator 1.1.D: Number of subprojects that have secured additional funding through Impact Strategy activities implemented to support economic and financial sustainability | No sub-projects | Target 1.1.D: 10 subprojects have secured additional funding (in addition to GEF allocation) | 10 |  | 563672.15 USD |  |  | IS
| OUTCOME 1.2: Project implementation capacity of IPLC partner organizations in subproject geographies substantially increased. | Indicator 1.2.A: Number of ICI subproject lead organizations showing improvement against organizational capacity assessment baselines | No organizations | Target 1.2.A: At least 10 ICI partner organizations show at least 20% improvement in organizational capacity assessments. | 10 |  | 0 | 0 | 0 | IS
|  | Indicator 1.2.B.: Number of ICI subprojects that incorporate youth in project designs | No subprojects | Target 1.2.B.: At least two youths (one male, one female) involved in execution team in each subproject. | 20 |  | 55 | 0 | 100% | CA
COMPONENT 2: Global IPLC Capacity Building: IPLC capacity strengthened to improve management of lands, territories, waters and natural resources and increase access to public and long-term sustainable financing mechanisms. | OUTCOME 2.1: IPLC capacity substantially strengthened within and beyond ICI subproject geographies. | Indicator 2.1.A: Number and percentage of IPLC trainees who successfully complete ICI Learning Academy training modules (disaggregated by gender, person-hours of capacity building, affiliation, country, theme). | No trainees | Target 2.1.A: At least 400 IPLC trainees successfully complete ICI Learning Academy training modules. At least 50% are women, and at least 25% are from outside the subproject geographies | 400 |  | 0 | 400 | 0% | IS
|  | Indicator 2.1.B: Capacity building modules developed with support of GEF Inclusive Conservation Learning Academy, including sections on gender. | No modules | Target 2.1.B.: At least 8 capacity building modules are developed with support of GEF Inclusive Conservation Learning Academy, including sections on gender | 8 |  | 0 | 8 | 0% | IS
| OUTCOME 2.2: Cross-regional IPLC organization partnerships and networks strengthened through ICI Learning Exchanges. | Indicator 2.2.A: Number of new cross-regional collaborations documented. | No cross-regional collaborations | Target 2.2.A: ≥4 cross-regional collaborations [At least 4 cross-regional collaborations documented to strengthen collaboration outside subproject geographies and build linkages with the ICI Community of Practice] | 4 |  | 1 | 3 | 75 | IS
|  | Indicator 2.2.B: Percentage of IPLC organizations that report greater capacity to advance IPLC-led conservation after participating at Learning Exchanges (disaggregated by gender, affiliation, country, theme). | No organizations | Target 2.2.B.: ≥75% IPLC organizations reporting greater capacity [At least 75% of IPLC Organizations report greater capacity to advance IPLC-led conservation after participating in Learning Exchanges (disaggregated by gender, affiliation, country, theme).] | ≥75% IPLC organizations |  | 0 | ≥75% | 0% | IS
| OUTCOME 2.3: IPLC organizational capacity increased to formulate sustainable financing strategies. | Indicator 2.3.A: Number of ICI subproject lead organizations that have a fully developed sustainable financing strategy. | No organizations | Target 2.3.A: 10 ICI subproject lead organizations [At least 10 ICI subproject lead organizations have a fully developed sustainable financing strategy] | 10 |  | 0 | 10 | 0% | NS
|  | Indicator 2.3.B: Percentage of ICI subproject lead organizations that report greater capacity in proposal development, fundraising and implementation of sustainable financing strategies. | No organizations | Target 2.3.B: ≥60% ICI subproject lead organizations [At least 60% of ICI subproject lead organizations report greater capacity in proposal development, fundraising and implementation of sustainable financing strategies.] | ≥60% ICI subproject lead organizations |  | 0 | ≥60% | 0% | IS
COMPONENT 3 IPLC Leadership in International Environmental Policy: Building the pathway from local action to global impact through targeted engagement in international environmental policy and relevant international platforms. | OUTCOME 3.1: Strengthened influence of IPLCs in relevant regional and international decision-making processes. | Indicator 3.1.A: Number of IPLC leaders with greater opportunity to influence international environmental policy with support of ICI (disaggregated by gender, affiliation, IPLC status, county, convention, and accreditation). | No people supported by ICI | Target 3.1.A.: ≥400 IPLC leaders; 50% women. [At least 400 IPLC leaders, 50% of whom are women, report greater opportunity to influence international environmental policy with support of ICI.] | 400 |  | 20 | 380 | 5 | IS
|  | Indicator 3.1.B: Number of ICI partners engaging with and providing technical support to national delegations at international policy meetings (disaggregated by gender, affiliation, country, convention). | No ICI delegates | Target 3.1.B.: 40 ICI delegates (of whom 50% are women) [40 ICI delegates (of whom 50% are women) engaging with and providing technical support to national delegations at international policy meetings (disaggregated by gender, affiliation, country, convention).] | 40 |  | 20 | 20 | 50 | IS
COMPONENT 4 ICI Knowledge to Action: Transforming Inclusive Conservation Knowledge and Lessons Learned into demonstration models that expand support and advance field of IPLC-led conservation. | OUTCOME 4.1: The field of IPLC-led conservation advanced with improved knowledge management. | Indicator 4.1.A: Number of ICI publications, reports, communication materials or tools that advance the global field of knowledge regarding IPLC-led conservation. | No ICI publications, reports, communication materials or tools | Target 4.1.A.: ≥7 lessons learned and flagship reports [At least 7 lessons learned and flagship reports prepared to advance the global field of knowledge regarding IPLC-led conservation.] | 7 |  | 1 | 6 | 14.2857 | IS
|  | Indicator 4.1.B: Number of new multiregional partnerships established73 to strengthen collaboration outside subproject geographies and build linkages with the ICI Community of Practice. | No partnerships | Target 4.1.B.: ≥2 new partnerships [At least 2 multiregional partnerships established to strengthen collaboration outside subproject geographies and build linkages among the ICI Community of Practice.] | 2 |  | 2 | 0 | 100% | IS
|  | Indicator 4.1.C: Percentage of IPLC organizations that report greater collaboration after participating in ICI Community of Practice (disaggregated by gender, affiliation, country, theme). | No organizations | Target 4.1.C.: ≥75% IPLC organizations [At least 75% of IPLC Organizations report greater collaboration after participating in Community of Practice (disaggregated by gender, affiliation, country, theme).] | ≥75% IPLC organizations |  | 0 | ≥75% | 0% | D
| OUTCOME 4.2: Expanded audience engaged in IPLC-led conservation. | Indicator 4.2.A: Number of average monthly visits to ICI Knowledge Platform. | No visits | Target 4.2.A.: ~500 average monthly visits [At least 500 average monthly visits to ICI Knowledge Platform]. | 500 |  | 884 average visits per month. | 0 | 100% | IS
|  | Indicator 4.2.B: Number of members of ICI Community of Practice (disaggregated by gender, IPLC status, county, field of expertise). | No members | Target 4.2.B.: ≥500 members (50 participants in bilateral and learning exchanges, 450 participants in virtual events) [At least 500 members of ICI Community of Practice (disaggregated by gender, IPLC status, county, field of expertise)]. | 500 |  | 0 | 500 | 0% | D
|  | Indicator 4.2.C: Percent increase in project communications index (index to be developed as part of ICI communications strategy including inter alia trends in social media followers, listserv members, website visits) | No increase | Target 4.2.C.: 10% annual increase in project communications index [10% annual increase in project communications index [At least a 10% annual increase in project communications index]. | 10% annual increase |  | Percentage changes in ICI social media (Twitter and Instagram) from FY22-23 to FY23-24: Twitter: Engagement: 8.8 % Increased Mentions: 38.9% Increased Followers: 56.12% decreased Impressions: 29.3% decreased Instagram: Posts: 14.3 Decreased Followers: 18.8 Decreased 24 - ICI Knowledge products supported/developed delivered during this reporting period. |  |  | D
COMPONENT 5 Monitoring and Evaluation. | OUTCOME 5.1: Monitoring and evaluation conducted to verify effective project execution. | Indicator 5.1.A: Number of satisfactory Project progress reports | No satisfactory Project progress reports | Target 5.1: 20 satisfactory quarterly Project progress reports produced | 20 |  | 3 | 17 | 15 | IS
PROJECT KEY COMPONENT | EXPECTED OUTPUS | EXPECTED OUTPUT INDICATORS | PROJECT BASELINE | "NOTES: [TOTAL END OF PROJECT TARGET]" | TOTAL END OF PROJECT TARGET | Progress Indicator |  | Analysis Progress
[6 empty] | TOTAL ACHIEVEMENT FY2022 - FY2023 (JAN 2022- JUNE 2023) | TOTAL ACHIEVEMENT FY2023 - FY2024 (JULY 2023- JUNE 2024) | Balance/ Variance | % of Achievement | Rating
COMPONENT 1 Local IPLC Action to Deliver Global Environmental Benefits (GEB): Established on-the-ground projects led by IPLC organizations. | Output 1.1.1: IPLC organizations in ICI Subproject Geographies contracted to lead subprojects. | Indicator 1.1.1.: Number of IPLC organizations contracted in ICI Subproject Geographies |  | Target 1.1.1.: 10 lead-contracting organizations | 10 |  | 10 | 0 | 100 | CA
| Output 1.1.2: Subproject Impact Strategies finalized to guide project implementation. | Indicator 1.1.2.: Number of subproject Impact Strategies |  | Target 1.1.2.: 10 Impact Strategies | 10 |  | 10 | 0 | 100 | CA
| Output 1.1.3: Activities implemented for enhancing IPLC rights and governance of natural resources. | Indicator 1.1.3.: Number of ICI subprojects that have implemented activities for enhancing IPLC rights and governance |  | Target 1.1.3.: 10 subprojects | 10 |  | 10 | 0 | 100 | IS
| Output 1.1.4: Activities implemented for improving management of natural and cultural resources in IPLC Lands and Territories. | Indicator 1.1.4.: Number of ICI subprojects that have implemented activities for improving management of natural and cultural resources |  | Target 1.1.4.: 10 subprojects | 10 |  | 10 | 0 | 100 | IS
| Output 1.1.5: Activities implemented for addressing the drivers of environmental degradation affecting IPLC sustainable development. | Indicator 1.1.5.: Number of ICI subprojects that have 97 implemented activities for addressing the drivers of environmental degradation |  | Target 1.1.5.: 10 subprojects | 10 |  | 10 | 0 | 100 | IS
| Output 1.1.6: Activities implemented to support the economic and financial sustainability of IPLC-led conservation. | Indicator 1.1.6.: Number of ICI subprojects that have implemented activities to support economic and financial sustainability |  | Target 1.1.6.: 10 subprojects | 10 |  | 10 | 0 | 100 | IS
| Output 1.1.7: ICI subproject governance structures designated and supported. | Indicator 1.1.7.: Number of ICI subprojects with designated IPLC-led governance structures |  | Target 1.1.7.: 10 subprojects | 10 |  | 10 | 0 | 100 | IS
| Output 1.2.1: Capacity assessments and capacity building plans of ICI subproject lead organizations in subproject geographies prepared. | Indicator 1.2.1.: Number of capacity assessments and plans |  | Target 1.2.1.: 10 assessments and plans | 10 |  | 10 | 0 | 100 | IS
| Output 1.2.2: Capacity-building activities delivered to ICI subproject lead organizations in subproject geographies. | Indicator 1.2.2.: Number of people trained in project management and implementation capacities identified in capacity plans |  | Target 1.2.2.: 90 people trained (10 per subproject) | 90 |  | 0 | 90 | 0% | IS
COMPONENT 2: Global IPLC Capacity Building: IPLC capacity strengthened to improve management of lands, territories, waters and natural resources and increase access to public and long-term sustainable financing mechanisms. | Output 2.1.1: ICI Learning Academy Curricula designed. | Indicator 2.1.1.: Number of Curricula designed |  | Target 2.1.1.: 1 Curriculum designed | 1 |  | 0 | 1 | 0 | IS
| Output 2.1.2: IPLC Inclusive Conservation Learning Academy established. | Indicator 2.1.2.: Number of Learning Academies established |  | Target 2.1.2.: 1 Learning Academy established | 1 |  | 0 | 1 | 0 | IS
| Output 2.1.3: Organizational Development and Capacity Building of IPLC organizations delivered through the ICLA. | Indicator 2.1.3.: Number of organizations supported |  | Target 2.1.3.: 10 ICI subproject lead organizations, at least 20 additional organizations | 10 |  | 0 | 10 | 0 | IS
| Output 2.1.4: Learning Evaluation completed of IPLC Inclusive Conservation Learning Academy. | Indicator 2.1.4.: Number of evaluations completed |  | Target 2.1.4.: 1 evaluation | 1 |  | 0 | 1 | 0 | NS
| Output 2.2.1: IPLC organizations mapped to strengthen collaboration within and beyond subproject geographies. | Indicator 2.2.1.: Number of stakeholder mapping reports |  | Target 2.2.1.: 1 mapping report, incorporating subproject/regional information and global scan of additional organizations | 1 |  | 0 | 1 | 0 | IS
| Output 2.2.2: Inclusive Conservation Learning Exchanges delivered. | Indicator 2.2.2.: Number of learning exchangesz |  | Target 2.2.2.: 8 learning exchanges with gender mainstreaming throughout, and a gender focus in at least one (5 regional, 3 global) | 8 |  | 1 | 7 | 12.5 | IS
| Output 2.3.1: Financial Opportunity Analysis completed. | Indicator 2.3.1.: Number of Financial Opportunity analyses completed |  | Target 2.3.1.: 10 Financial Opportunity analyses completed | 10 |  | 0 | 10 | 0 | IS
| Output 2.3.2: Capacity Building in Sustainable Financing delivered. | Indicator 2.3.2.: Number of ICI subproject lead organizations trained |  | Target 2.3.2.: 10 organizations trained | 10 |  | 0 | 10 | 0 | IS
COMPONENT 3 IPLC Leadership in International Environmental Policy: Building the pathway from local action to global impact through targeted engagement in international environmental policy and relevant international platforms. | Output 3.1.1: ICI Policy Coordination Mechanisms developed to support IPLC engagement across Rio Conventions and other fora. | Indicator 3.1.1.: Number of mechanisms strengthened |  | Target 3.1.1.: 2 mechanisms strengthened (IIFB-IIPFCC) | 2 |  | 2 | 0 | 100% | IS
| Output 3.1.2: ICI International Environmental Policy Negotiations Curriculum developed and delivered. | Indicator 3.1.2.: Number of curricula developed and delivered |  | Target 3.1.2.: 1 curriculum | 1 |  | 0 | 1 |  | IS
| Output 3.1.3: ICI International Environmental Policy Fellows Program established and supported. | Indicator 3.1.3.: Number of fellows supported |  | Target 3.1.3.: Target 3.1.3.: 15 fellows (5 per year in years 2-4 of project, at least 50% women) | 15 |  | 5 | 10 | 33.3333 | IS
| Output 3.1.4: IPLC representation and recognition increased at the Rio Conventions and other relevant international conventions and platforms. | Indicator 3.1.4.: Number of high-level events organized |  | Target 3.1.4.: 5 events (at least 1 event to include focus on gender issues/topic) | 5 |  | 2 | 3 | 60 | IS
COMPONENT 4 ICI Knowledge to Action: Transforming Inclusive Conservation Knowledge and Lessons Learned into demonstration models that expand support and advance field of IPLC-led conservation. | Output 4.1.1: ICI Knowledge Management Platform established. | Indicator 4.1.1.: Number of KM platforms established |  | Target 4.1.1.: 1 KM platform established | 1 |  | 1 | 0 | 100% | IS
| Output 4.1.2: ICI Knowledge Products developed with IPLC organizations. | Indicator 4.1.2.: Number of Knowledge products developed |  | Target 4.1.2.: 7 products (reflecting gender-inclusivity) | 7 |  | 26 | -19 | 100% | IS
| Output 4.1.3: ICI Community of Practice established and supported. | Indicator 4.1.3.: Number of communities of practice established |  | Target 4.1.3.: 1 community of practice | 1 |  | 0 | 1 | 0 | D
| Output 4.2.1: ICI communications strategy developed based on needs assessment. | Indicator 4.2.1.: Number of communications strategies developed |  | Target 4.2.1.: 1 communications strategy (reflecting gender mainstreaming) | 1 |  | 1 | 0 | 100% | D
| Output 4.2.2: ICI Communications Program executed. | Indicator 4.2.2.: Number of Communications Programs executed |  | Target 4.2.2.: 1 program | 1 |  | 0 | 1 | 100% | D
| Output 4.2.3: ICI communications training provided to project partners, reflecting gender mainstreaming. | Indicator 4.2.3.: Number of people trained |  | Target 4.2.3.: 90 people trained (10 per geography) | 90 |  | 0 | 90 | 0 | D
COMPONENT 5 Monitoring and Evaluation. | Output 5.1.1: A gender-sensitive M&E system developed to collect, analyze, and synthesize data and information generated during project implementation | Indicator 5.1.1: Number of Project M&E systems operational |  | Target 5.1.1: One Project M&E system | 1 |  | 1 | 0 | 100% | IS