ANNEX G

PIR FORMAT – PROJECT IMPLEMENTATION REVIEW

CAF-GEF PIR for Fiscal Year:  (Period: July 1, 2024  to June 30, 2025)

PART A – Project Implementation Progress & Risk Management

# PROJECT GENERAL INFORMATION

| Project Title: | “BE-CLME+”: Promoting National Blue Economy Priorities Through Marine Spatial Planning in the Caribbean Large Marine Ecosystem Plus |
| --- | --- |
| Implementing Agency: | Development Bank of Latin America and the Caribbean (CAF) and Food and Agriculture Organization (FAO) |
| Executing Agency: | Caribbean Regional Fisheries Mechanism (CRFM) |
| Project Partners: |  |
| Geographical Scope: | Latin America and Caribbean |
| Participating Countries: | Barbados, Belize, Guyana, Jamaica, Panama and Saint Lucia. |

| GEF Project ID: | 10211 | CAF Project ID: | CAF-GEF 011 |
| --- | --- | --- | --- |
| Participating Countries: | Barbados, Belize, Guyana, Jamaica, Panama and Saint Lucia. |  |  |
| Focal Area (s): | International Waters, Biodiversity | GEF OP#: |  |
| GEF Strategic Priority/ Objective: | IW-1-1: Strengthen blue economy opportunities through sustainable healthy coastal and marine ecosystems BD-1.1: Mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors IW-1-2: Strengthen blue economy opportunities through catalysing sustainable fisheries management BD- 2.7: Address direct drivers to protect habitats and species | GEF approval date*: | 18 November 2022 |
| CAF approval date: | 17 April 2024 | Date of first disbursement*: | October 20, 2023 (FAO) October 17, 2024 (CAF) |
| Actual start date2: | 1 July 2024 | Planned duration: | 4 years |
| Intended completion date*: | 30 June 2028 | Actual or Expected completion date: |  |
| Project Type: |  | GEF Allocation*: |  |
| PPG GEF cost*: |  | PPG co-financing*: |  |
| Expected MSP/FSP Co-financing*: |  | Total Cost*: |  |
| Mid-term review/eval. (planned date): | Date to be determined | Terminal Evaluation (actual date): | Date to be determined |
| Mid-term review/eval. (actual date): | Date to be determined | No. of revisions*: |  |
| Date of last Steering Committee meeting: | February 26-27, 2025 | Date of last Revision*: |  |
| Disbursement as of June 30, 2025 | $315,760.10 (CAF) $500, 777 (FAO) | Date of financial closure*: |  |
| Date of Completion: |  | Actual expenditures reported as of 30 June 2025: | US$467,864 (FAO) US$85,287 (CAF) US$553,151 (TOTAL) |
| Total co-financing realized as of 30 June 2025 | 911,989 | Actual expenditures to date: | US$467,864 (FAO) US$85,287 (CAF) US$553,151 (TOTAL) |
| Leveraged financing: | None |  |  |

| Project Summary3 |  |
| --- | --- |
| To promote blue economy development in the CLME+ through marine spatial planning and marine protected areas (MPAs), ecosystem approach to fisheries (EAF), and sustainable seafood value chains. Project Component 1 focuses on investments into national and regional marine spatial planning efforts that inform development and implementation of national blue economy strategies. These national-level efforts leverage multiple sources of valuable existing information, including from CLME SAPs/NAPs, relevant marine spatial planning efforts from the GEF-World Bank Caribbean Regional Oceanscape Project and other initiatives, national sustainable development priorities, and country-specific information from key economic sectors. Since each participating country has its own unique challenges and opportunities, this component is focused on assessing each national situation through a lens of marine spatial planning tools and latest experiences in development of national blue economy planning. Component 1 is designed with two complementary outcomes that focus on national strategy development via MSP and BE combined with strategic use of MPAs to promote ecosystem-based fisheries management. Project Component 2 focuses on establishing inclusive sustainable seafood value chains that take into account building resilience to climate change and capacity to deal with external shocks like COVID 19. The value chain stretches from the harvest activity to final consumption. Often, value chains in fisheries are complicated and entwined, so it is more accurate to talk about ‘value nets’ rather than value chains. To do a meaningful analysis some simplifications are always necessary. The simplification process is a balancing act, as the most important specificities or characteristics must not be thrown out during the process while at the same time the granularity must not be too small to make the analysis intractable. Improving value chains in fisheries is important, as it not only increases economic efficiency and value creation, but also because it is an important factor in securing sustainability of the fishery. Sustainability and long-term economic improvements go hand in hand. Improving the value chains is a necessary ingredient of sustainable fisheries management, which is an important part of the GEF-7 Focal Area Strategy, by enforcing ecosystem integrity and linking long-term resource management with efficient resource use; it helps in eliminating hunger through securing raw material supply, promotes health through better fishing and handling technologies and better traceability, and reduce poverty by increasing the value of catches, labour and capital. For fisheries value chains to be effective, they must be appropriately defined. Sub-optimal definition can lead to ineffective project interventions which may counteract the overall blue economy goals of the project itself. Therefore, it is necessary to launch an information campaign early in the project implementation to ensure the necessary buy-in for successful value chain definition and effective project intervention. In order to determine how to distribute the limited resources available towards the most promising case studies or projects to be developed further by the appropriate agencies and stakeholders, a ranking procedure will be developed to assist in identifying and prioritizing value chains for analysis. Such a ranking procedure can be designed in many ways but should reflect realistic economic, social and environmental goals set by each country or region, while building on existing policy frameworks, especially the ones related to BE and MSP strategies. Successful fisheries value chains require strong institutional frameworks and capacity, and as such, it will be necessary to map the institutional requirements and capacity needs necessary to implement strategies towards inclusive and sustainable value chains. Project Component 3 supports the first two project components through knowledge management and project monitoring and evaluation, based on knowledge and experiences from the project as well as taking advantage of knowledge and experiences with the blue economy from other regions and other GEF International Waters projects in partnership with IW:LEARN as well as the experiences and lessons from the CLME and CLME+Project. Collectively the three outcomes under Component 3 will bolster regional capacity and engagement in blue economy opportunities, from regional and national organizations, to private sector partners and on down to targeted trainings for fisherfolk. Specifically, the component will focus on advancing lessons learned on marine spatial planning and the role of marine protected areas for ecosystem-based fisheries management, promotion of sustainable fisheries value chains and value of marine ecosystem goods and services within the context of blue economy. This component will also promote cooperation through the establishment of a knowledge management platform that will facilitate partnership building, knowledge exchange and collaboration, and promoting participation in technical meetings for regional knowledge sharing and targeted training for beneficiary institutions and associations, including actively engaging in IW:LEARN activities. Finally, to ensure successful project execution, the project will be supported by robust project monitoring and evaluation systems to inform timely adaptive project management, including meeting project reporting requirements and third-party mid- term and terminal evaluations. |  |
| Project Status FY 2023-244 |  |
| The project was activated with the Inception Meeting in Panama City, September 2023. RSC and TAC Meetings were held at the end of Q1 of the FY during the Inception Meeting and formulated the AWP 2023-24. The Operational Agreements were put in place during this year, however disbursement for CAF was not received until 2024-25. Recruitment of the PMU Staff was significantly delayed with challenges finding suitable candidates for all 3 roles. At the end of the 2023-24 FY, the SVC Specialist and the MSP Specialist were on-board, with the RPC still yet to be engaged. However, despite these challenges, the CRFM continued with start-up activities, especially under Component 1 as the FAO funds were active. |  |
| Project Status FY 2024-255 |  |
| This project year realized significant improvement of project activities across all Components. The RPC was also engaged effective July 1, 2024, and now completed the PMU team. First disbursement of funds from CAF was received in October 2024, and the first consultant engaged in December 2024. The RSC and TAC Meetings in September 2024 were convened virtually, and approved the 2024-25 Workplan and Budget. The RSC and TAC were convened in-person in Jamaica in February 2025 and approved the realigned 2025 Workplan and Budget. Five (5) consultancies were completed during this FY with several others commenced. Engagement with GEF IW:LEARN significantly improved in this FY with 4 major engagements. The engagement of participating countries has been enhanced, and with the exception of Guyana, all countries are active under the project especially with facilitating consultants in-country. The project is expected to continue the momentum into the subsequent periods. The major challenge was the pace of procurement of qualified consultants due to the low response rate. Additionally, the participation of Guyana needs to improve. |  |
| Planned contributions to strategic priorities/targets 6: |  |
| IW-1-1: Strengthen blue economy opportunities through sustainable healthy coastal and marine ecosystems: Tools, strategies and cooperation frameworks developed and informing policy formulation, adoption and investment processes towards long term sustainability of coastal marine resources. IW-1-2: Strengthen blue economy opportunities through catalysing sustainable fisheries management: Policy reforms and strengthened frameworks developed and implemented at the regional and national levels, in support of sustainable fishing practices, market mechanisms to support sustainable fisheries value chains, and the expansion of opportunities for private sector engagement. BD-1.1: Mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors: Loss, fragmentation, and degradation of significant natural habitats, and associated extinction debt, is reduced, halted or reversed, and conservation status of known threatened species is improved and sustained, including through monitoring, spatial planning, incentives, restoration, and strategic establishment of protected areas and other measures. BD- 2.7: Address direct drivers to protect habitats and species: The area of protected areas under effective and equitable management is significantly increased, including development of sustainable financing. The ecological representativeness of protected area systems, and their coverage of protected areas, and other effective area-based conservation measures, of particular importance for biodiversity is increased, especially habitats for threatened species. |  |

2 Only if different from first disbursement date, e.g., in cases where a long time elapsed between first disbursement and recruitment of project manager.

# PROJECT OBJECTIVE

State the global environmental objective(s) of the project7

To promote blue economy development in the CLME+ through marine spatial planning and marine protected areas (MPAs), ecosystem approach to fisheries (EAF), and sustainable seafood value chains.

Please provide a narrative of progress made towards meeting the project objective(s). Describe any significant environmental or other changes (results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes (not more than 300 words)

Preliminary activities are underway to develop comprehensive MSPs. Data Gaps and Needs Assessment completed for 4 of 6 countries with a 5th to be complete in July 2025 and regional MSP Protocol development is underway. These will guide national MSPs. Barbados has developed a BE Roadmap- Strategy and Implementation Plan and conducted national stakeholder validation workshops. Work is underway for Panama and Saint Lucia while Jamaica and Belize are expected to begin in September 2025. Development of MPA management training materials is underway and will be used for planned MPA management training activities. Both activities are expected to contribute to the overall output which includes the enhancement of management effectiveness of MPAs. This was also complemented with the joint MPA Training in November 2024 in which the project co-organized and co-instructed. Capacity Building for Mainstreaming the SSF Guidelines into Value Chains was completed producing trainers and a training package covering 15 topics. Description and Analysis of Existing Value Chains and Identification of Opportunities have shown significant progress. Draft Analysis of 13 Existing Value Chains completed. Final reports expected by October 2025. Seafood Value Chain Carbon Footprint Analysis in Belize (large scale – lobster) and Panama (small scale mariculture) is underway and expected to be completed in December 2025. Assessment of Bottlenecks to Value Chain Added-Value Opportunities and Identification of Optimal Value Chains will commence in September 2025 along with the Identification of Value Chain Capacity Needs and Gaps. The development and implementation of the Knowledge Management Platform is expected to commence in September 2025 with the engagement of a suitable consultant. The engagement with GEF IW:LEARN increased significantly with 3 major engagements and 1 planned for November 2025. ESS tools have been developed and operationalized: - The Stakeholder Engagement Plan. - Indigenous Peoples Plan - Accountability and Grievance Mechanism

Please provide a narrative of progress towards the stated GEF Strategic Priorities and Targets if identified in project document 8(not more than 200 words)

GEF-7 Relevant Strategic Priorities: IW-1-1: Strengthen blue economy opportunities through sustainable healthy coastal and marine ecosystems: Component 1 focuses on the development of MSPs for participating countries which will guide the enhancement and expansion of marine protected areas. The Project has completed 5 of 6 national data gaps assessments, which informs the current development of the MSP Regional Framework. These 2 major activities will guide the development of national MSPs including protected areas, and comprehensive BE Strategies. BD-1.1: Mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors The project has also co-organized and delivered regional MPA Training for participating countries with the main objective to strengthen the management of MPAs. Engagement of governments in expansion of MPA system is ongoing, with support for this coming through the MSP activities which enhances the scientific approach to MPAs. IW-1-2: Strengthen blue economy opportunities through catalysing sustainable fisheries management BD- 2.7: Address direct drivers to protect habitats and species Consultancy activities for the national blue economy roadmap Implementation Plan for the Fisheries Sector for Barbados are completed. Description and Analysis of Existing Value Chains which highlights the importance of taking a broad and holistic approach to fisheries management to ensure sustainable use of marine resources and assessed 13 seafood value chains, exceeding the target of at least nine. The assessment of the carbon footprint of 1 large and 1 small fisheries in the participating countries has commenced and is expected to be completed in the 3rd Quarter of this year. This will guide the improvement of GHG emissions in the fisheries sector, covering all 3 Scopes (I, II and III), thereby taking a holistic approach to addressing the issue.

3 As in project document

4 Please add additional lines to keep prior year implementation status (if any)

5 Progress made during current reporting period (one paragraph stating key changes since previous reporting period)

6 For Full Size Projects this information is found in the front page of the project Executive Summary; for Medium-Sized Projects the information appears in the MSP brief cover page.

7 Or immediate project objective

8 Projects that did not include these in original design are encouraged to the extent possible to retrofit specific targets.

# RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the CAF Task Manager9 will make an overall assessment and provide ratings of:

- Progress towards achieving the project objective(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The CAF Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - Progress towards achieving the project objective (s)

| Project objective and Outcomes | Description of indicator10 | Baseline level11 | Mid-term target12 | End-of-project target | Level at 30 June | Progress rating 13 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective14 To promote blue economy development in the CLME+ through marine spatial planning and marine protected areas (MPAs), ecosystem approach to fisheries (EAF), and sustainable seafood value chains. |  |  |  |  |  |  |
| Outcome 1.1: Governments and key stakeholders enabled to support the sustainable use of fisheries and key marine habitats | # of countries with comprehensive MSPs | 0 | 2 countries with comprehensive MSPs | 5 countries with comprehensive MSPs | 36% Complete Comprehensive MSPs have not been developed for participating countries under this project. Before this can commence, the following preliminary activities are currently being undertaken. These activities ( identified below) will establish the baseline and agreed approach for the development of MSPs. Activity 1.1.1.1: Preliminary consultancy activities under this output- Data Gaps and Needs Assessment to inform MSP are completed for four (4) of the six (6) Countries- Barbados, Belize, Jamaica and Saint Lucia. During this reporting period findings and recommendations for Panama were presented and validated by stakeholders during a hybrid session held in May 2025. The feedback from stakeholders were considered in the development of the final data gaps and needs assessment report (Product 3) which is currently under review. Activity 1.1.1.2 Development of a project-wide MSP protocol that takes into account national data assessments. Consultancy activities kicked off with an inception meeting with participating countries and members of the TAC. The development of the protocol will take into consideration the current data gaps identified (Activity 1.1.1.1) and make recommendations to add value and facilitate further MSP planning and implementation at the national level. The MSP step by step guide will be prescriptive about the requirements of each step, identify common and distinct challenges associated with each step and provide recommendations for those challenges of particular relevance to the Caribbean. Consideration will also be given to other member states to ensure that the MSP guidelines and protocol are inclusive and facilitate regional cooperation to support the implementation of the protocol. |  |
|  | # of countries with new and updated National Blue Economy Strategies # of National decision-support systems developed and implemented for sustainable fisheries management. | 2 Draft National Blue Economy Strategies (Barbados and Belize) 0 | 4 countries with national blue economy strategies in place and/or updated 2 National decision-support systems developed and implemented | 6 countries with national blue economy strategies in place and/or updated 6 National decision-support systems developed and implemented for sustainable fisheries management | 17% Complete Activity 1.1.2.2: Hold national BE Strategy validation workshop. The abovementioned activity is one of three activities contributing to output 1.1.2. Activity 1.1.2.2 is preceded by activity 1.1.2.1 (FAO funded) 1 national BE strategy validation workshop was completed for Barbados in august 2024, after the completion of a BE Roadmap Implementation Plan for the Fisheries Sector for Barbados (Activity 1.1.2.1-Conduct national BE assessments and draft BE strategies -FAO funded). A wide cross section of stakeholders including academia, shipping and transport sectors, coast guard, and civil society were present at the validation meeting (11 participants with 64% being females) During the reporting period consultancies were ongoing for Panama and Saint Lucia for Activity 1.1.2.1 which is a precursor to Activity 1.1.2.2 and 1.1.2.3). Following its completion, national validation workshops are expected during September to October 2025. Based on recommendations from TAC and PSC during the preparation of the 2023 to 2024 workplan and budget, Activity 1.1.2.1 and consequently Activity 1.1.2.2 was suspended for all the participating countries except Barbados. This was to allow for the completion of data gaps and needs assessment to inform MSP (Activity 1.1.1.1). While this may have resulted in delay in the commencement of the precursor activity 1.1.2.1, the results and findings from Activity 1.1.1.1 informed and guided the scope of Activity 1.1.2.1 developed for the other 5 participating countries. Activities for Guyana are pending due to delays in the completion of evaluations of the EOIs by the national focal point. 0% Complete No activities planned for the reporting period. |  |
|  | Tonnes of exploited fisheries moved to more sustainable levels | 0 | 20,000 | 45,000 mt of exploited fisheries moved to more sustainable levels | 0% complete No activities/ audits/reports produced for this reporting period |  |
| Outcome 1.2: The protection of critical fish habitats has been established/expanded, and informed by national marine spatial planning (MSP). | % increase in METT Score among project countries* *Average METT score of MPAs being expanded or with management enhancement as a consequence of the project’s support | TBD* Barbados: Belize: Guyana: 0.0 Jamaica: Panama: St. Lucia: *Baseline refer to METT score only for MPAs being expanded or with management enhancement as a consequence of the project’s support | Baseline + 10% | Baseline + 30% | 20% Complete No activities have been implemented to improve the capacity and management effectiveness of MPA, under this specific output. The activity presented below (1.2.2.1) will establish a baseline for capacity needs and training, and inform the development of training materials to address those gaps. The deliverables from activity 1.2.2.1 will be used in the implementation of future planned MPA management training activities (Activity 1.2.2.2). Activity 1.2.2.1: Develop project wide MPA management training materials Following the evaluation of proposals, consultancy services form the University of the West Indies- Centre for Resource Management and Environmental Studies (UWI- CERMES) were secured to assess the training needs and develop MPA management training materials that prioritizes MSP,BE and EbFM. An inception meeting was convened with the consultant, the CFRM/PMU, participating countries and members of the TAC (6 participants, 67% females). Feedback from the inception will guide the preparation of the inception report which detailed the approach and methodology for undertaking the assignment, as well as the workplan and schedule. The Inception report has been submitted. It should be noted that a related activity (3.1.1.2) was completed in November 2024 where 20 MPA managers from the English speaking Caribbean including the participating countries were trained in MPA and Ecosystem-based Fisheries Management. |  |
|  | Area of MPAs created or Expanded in project countries (Ha) | 0* *Baseline is zero since the indicator measures new or expanded, not current # Ha of MPAs | + 96,746 | 540,774Ha of MPAs created or expanded *Actual total area subject to outcome of public consultations and support during project implementation | 0% No activities planned for the reporting period under this outcome. |  |
| Outcome 2.1: New and strengthened national and regional seafood value chains supporting realization of blue economy opportunities and sustainable development goals | # of seafood value chains assessed and incorporated into national blue economy strategies and marine spatial planning efforts | 0 | 5 | At least 9 seafood value chains assessed and incorporated into national blue economy strategies and marine spatial planning efforts | 30% Activity 2.1.1.1 + 2.1.1.2 - Analysis of Existing Value Chains The TOR was developed in the interim while waiting for CAF funding to be processed and received. The CAF agreement was signed on 17 April 2024, and the funds were received in October 2024. The TOR for this activity was finalized and subsequently advertised, with a submission deadline of 19 July 2024. A total of 9 proposals were received, and the technical and financial evaluations were completed between July and August 2024. This evaluation package included the completed evaluations, the summarized scores and the procurement report which was signed by each panel member. The evaluation package was forwarded to the Finance department for review, approval and contracting. The consulting firm Nexus Coastal Resource Management Limited was selected to execute the consultancy. The contract date is 1 December 2024 to 29 August 2025. The CRFM/PMU convened the Inception meeting with the consultant and their team on 6 December 2024. The inception report was submitted on 11 December 2024 and subsequently shared with the TAC and RSC members for their comments and approval as well as the CRFM/PMU. The report was returned to the consultant on 20 December 2024, together with feedback from the project countries. The consultant then resubmitted the revised report on 20 December 2024, incorporating all received comments. On 24 December 2024, the report was accepted as Product 1 (the Inception Report). During Q1YR2, the consultant progressed with the activities outlined in the work plan such as desktop research, development of stakeholder mapping, design and launch of online survey and planning of in-country field visits. The stakeholder mapping was developed and shared with project country countries for updating and augmenting on 28 January 2025. On 3 March the online survey was launched with over 160 stakeholders across the six project countries. The in-country-visits for data collection were conducted during the period 17 February to 8 March 2025. During these in-country visits, the consultant held key meetings with actors along the entire value chain in all six countries as well as government agencies to comprehensively assess the value chains. In total, the consultant engaged 101 persons of which 25% were female. These visits were followed by an Information Request on 18 March 2025 to all six countries requesting supplemental fisheries data for the analysis. The consultant noted that some countries have not yet provided the requested data, which presents challenges and potential delays in the analysis. The PMU recalled at the Inception Meeting to allow sufficient time for requests from NFPs and communicate any challenges such as to the PMU. Also, it was the understanding that the data request should have preceded the in-country-visits allowing the focal points sufficient time to gather information from various sources. This feedback was documented by letter dated 1 April 2025 to the consultant and was supported by the project countries during our quality control checks. A follow-up visit to Panama was scheduled for 29 April to 8 May 2025 to visit the Bocas del Toro Indigenous-led fishery as this was not covered in the initial in-country visit due to coordination limitations. During the Bocas del Toro visit a total of 27 persons in the value chain were interviewed of which 6 were female (29%) and 12 persons were identified as Indigenous (44%). The consultant submitted the first draft report on the analysis for the existing chains on 23 May 2025 which was initially extended due to allow additional time to augment the report with the fisheries data and the data collected on the Indigenous-led fishery to ensure an adequate first draft. This report was circulated to project country’s PSC and TAC members for review and comments. On Friday 23 May 2025 the first draft report Product 2 – Description and analysis of value chains was submitted as per revised timeline. The English and Spanish versions were shared with project countries TAC + PSC members for review with a deadline of 9 June 2025. Due to a slow response rate the deadline was further extended to 13 June 2025. Prior to the compilation of the comments from project countries, a letter dated 18 June 2025 detailing key revisions required for the first draft report, as it was considered inadequate. On 23 June 23, the collated comments were sent to Nexus, and a meeting was held on 24 June to review the letter and provide clarification on the necessary revisions. and they were guided to revise the report to address the identified gaps in the value chain analysis and other key missing elements. We anticipate the submission of the revised report by June 30, 2025, which marks the end of the current reporting period. |  |
|  |  |  |  |  | 0% Activity 2.1.1.3 - Mapping of the certification and quality control requirements in potential export markets and identifying gaps. There were no planned activities for the reporting period. |  |
|  |  |  |  |  | 0% Activity 2.1.1.4 - Linking value chains to BE strategies and MPA planning (Workshop) There were no planned activities for the reporting period. |  |
| Output 2.1.2 Seafood value chain added- value opportunities identified, and market and economic feasibility assessed, including testing innovative post- harvest processing methods and reduction of post-harvest loss and improved/creation of new seafood products to reduce waste | # of Seafood value chain added- value opportunities identified, and market and economic feasibility assessed | 0 | 2 | At least 6 Seafood value chains added- value opportunities identified, and market and economic feasibility assessed | 15% Activity 2.1.2.1 + 2.1.2.2 - Assessment of Bottlenecks to Value Chain Added-Value Opportunities and Identification of Optimal Value Chains Activity 2.1.2.1 + 2.1.2.2 was recommended and agreed to be merged at the first TAC meeting held during 4-6 September 2024. It was agreed to merge the activities due to Activity 2.1.2.1 being precursor in nature to inform the selection of optimal value chains as well as to benefit from cost savings and enhance the attractiveness of the consultancy. This approach hopefully will address the low response rates being experienced by the project. The final draft TOR was presented at the second TAC meeting held on 5 December 2024 with a deadline for final comments by 9 December 2024. The TOR received comments from the FAO in January 2025 and during Q1 2025 the TOR was revised and received clearance/no objection from FAO on 24 March 2025. CAF was asked to provide no objection by 28 March 2025 and is yet to be received. This consultancy will focus on assessing the main challenges in the value chain referred to as “bottlenecks”. This assessment coupled with the outputs of Activity 2.1.1.1 + 2.1.1.2 will compare the baselines cases and inform the selection of the value chains that are most promising and should be pursued for optimization in Caribbean fisheries through the development of country-specific case studies and guided by analysis and best practices of case studies and lessons learnt at the international and regional levels. During the reporting period, the TOR was reviewed internally and inclusion made for a technical final report as part of procurement requirements before forwarding to the Finance department to begin the procurement process. It is anticipated that the procurement process would be completed in the next reporting period. Noting, this activity will be guided by the outcome of the precursor activity 2.1.1.1 + 2.1.1.2 - Analysis of Existing Value Chains and Identify Opportunities for New Value Chains which is expected to be completed at the end of the next reporting period. |  |
| Output 2.1.3 National policy recommendations developed promoting an enabling environment for strengthening of seafood value chains and markets, including empowerment of women, indigenous peoples, and ethnic minorities. | # of national policy recommendations developed promoting enabling environment for strengthening of seafood value chains and markets | 0 | 2 | At least 1 regional and 6 national policy recommendations developed promoting enabling environment for strengthening of seafood value chains and markets, including the empowerment of women, indigenous peoples, and ethnic minorities | 0% Activity 2.1.3.1 - Preparing national policy recommendations (National Workshops + 1 Regional Workshop) There were no planned activities for the reporting period. |  |
|  |  |  |  |  | 100% Activity 2.1.3.2 - Capacity Building for Mainstreaming FAO’s Small-Scale Fisheries Guidelines into value chains This activity has been successfully completed. While there was a slight delay in the final reports, a no-cost extension was approved from the initial deadline date of 18 February to 31 March 2025, due to medical reasons. All prior deliverables for this activity were received and satisfactorily completed according to the project timeline. |  |
|  |  |  |  |  | 0% Activity 2.1.3.3 - Value Chain Policy Awareness and Understanding There were no planned activities for the reporting period. This will be started once the KM and Communications Consultant is engaged by August 2025 |  |
|  |  |  |  |  | 20% Activity 2.1.3.4 - Seafood Carbon Footprint Analysis The approved TOR was advertised with an initial deadline of 8 July 2024. During this period a total of 2 proposals were received. This was inadequate and did not meet procurement requirements and the bid was reopened with a new deadline of 30 August 2024. Subsequently, a total of 5 proposals were received consisting of 3 firms, 1 individual and 1 team. During YR1Q4 the technical and financial evaluations were completed on 10 December 2024 which included the procurement report and summarized scores. This evaluation package was forwarded to Finance for review and approval. No further progress was made during the quarter due to end of year office closures and annual leave schedules. On 29 January 2025 approval was received, and the consultant Green Initiative was selected to execute the consultancy.The contract date is 3 February 2025 to 5 September 2025. On 13 February the inception meeting was convened, and Green Initiative presented the work plan schedule and selection criteria. On 14 February selection criteria. This included the interview guide, quick assessment survey and scoring guide for selection of fisheries and scoring guide submitted for review and comments by project countries. Follow-up meetings were held with project countries to review the methodology and selection criteria on 6 March with Panama (10 participants, 30% female) and on 11 March with Belize, Guyana, and Saint Lucia (9 participants, 22% female). In April, the countries progressed with completing the quick assessment survey that evaluated the fishery entities based on the following criteria: Technical criteria (30%), Stakeholder readiness (30%), Strategic value (20%), and Environmental and social impact (20%). Then based on the scores the consultant would use a ranking method to evaluate and select the fisheries with the highest score for both large-scale and small-scale fisheries. During April, Belize, Panama, and Saint Lucia made submissions, while Barbados and Jamaica opted out due to data availability constraints. Guyana is yet to submit. Based on the scoring the consultant then used a ranking method to evaluate and select the fisheries with the highest score which resulted in the selection of Belize's Spiny Lobster Fishery (large-scale) and Panama's Marine Aquaculture operation (small-scale) for the analysis. During May, the consultant announced the outcome of the selection process following the evaluation. The NFPs for each selected country were asked to confirm the entity that would undergo the assessment. For the Caribbean Spiny Lobster, the entity selected is Northern Fishermen Cooperative (NFC) and for the Marine Aquaculture the entity is Dyer Aquaculture LLC. Subsequently, the Directors of these entities were contacted to inform them of the next steps and the project timeline. An introductory meeting was held with Dyer Aqua on the 20 May with three participants (no female in attendance) and with the NFC on 23 May with 4 participants (no female in attendance). On 26 May NFC and Dyer Aqua were sent a Request for Information to formalize the request for information necessary to conduct an assessment. This entailed defining Scope 1 (Direct Emissions), Scope 2 (Indirect Emissions from Energy) and Scope 3 (Other Indirect Emissions) We are now in the data collection and analysis phase of the consultancy, which we expect to be completed by Q3. On 20 May 2025 introductory meeting was held with Alcibiades Arauz of Dyer Aqua, Panama (Focal point) and on 23 May 2025 with Robert Usher, NFC to convene the introductory meeting. The approach, methodology and calculation book were presented and the operational limits established. The data collection will begin from the following week and a virtual meeting for data collection scheduled for every Wednesday. Following the introductory meeting, on 21 May and 26 May the consultant sent a Request for Information for the Carbon Footprint Assessment to Dyer Aqua and NFC. This was followed up via email on 27 May and then 5 June with both entities. There has been some challenge in obtaining the necessary data from the entities which may cause a delay in the overall analysis and could impact the subsequent delivery of subsequent outputs. We anticipate completing the consultancy by the next reporting period, assuming an extension is not required. Dyer Aqua, Panama has made significant progress, providing approximately 85% of the required data. NFC, Belize has not yet been able to submit any data. This is primarily due to competing priorities within the NFC which is involved in other projects. Additionally, the data collection and analysis phase coincided with the reopening of the lobster season in Belize on 1 July 2025, further limiting their availability. |  |
| Output 2.1.4 Regional and national fisheries authorities and other relevant regulatory agencies trained in seafood value chain analysis and development within the context of the blue economy. | # of regional and national fisheries authorities and other relevant regulatory agencies trained | 0 | 8 | At least 18 regional and national fisheries authorities and other relevant regulatory agencies trained | 20% Activity 2.1.4.1 - Identification of Value Chain capacity Needs and Gaps Activity 2.1.4.1 was presented at the second TAC meeting held on 5 December 2024 with a deadline for final comments by 12 December 2024. The TOR received comments from the FAO in January 2025 and during Q1 2025 the TOR was revised and received clearance/no objection from FAO on 24 March 2025. CAF is yet to provide feedback. The consultancy will focus on mapping the capacity needs and gaps in each project country and at the regional level for the stakeholders identified in Output 2.1.3., inclusive of public, private and fisherfolk organizations. The findings will be ranked and prioritized to inform the design of training materials/programmes and delivery under Activity 2.1.4.2 - Training courses for relevant stakeholders. This Activity is also directly linked to Activity 2.1.1.2 – Identification of Opportunities for New Value Chains and will address the gap in capacity needs of stakeholders in benefiting from new opportunities in the value chain within Blue Economy context. In June, the TOR was reviewed internally and inclusion made for a technical final report as part of procurement requirements before forwarding to the Finance department to begin the procurement process. It is anticipated that the procurement process would be completed in the next reporting period. |  |
|  |  |  |  |  | 0% Activity 2.1.4.2 - Training courses for relevant stakeholders (Consultancy) There were no planned activities for the reporting period. |  |
| Outcome 3.2: Project implementation according to result- based management and lessons learned systematized and disseminated | # project monitoring & evaluation systems in place | 0 | 1 | 1 project monitoring & evaluation system in place | Activity 3.2.1.1: Develop Project Annual Work Plans and detailed Project Monitoring & Evaluation System. 80% AWP 2025 developed, reviewed and approved at RSC Meeting (February 2025); being refined as the progress occurs throughout the year with adaptive management principles; TAC and RSC meetings conducted as well as Coordination Meetings to monitor progress. Quarterly progress reports and Quarterly Financials Reports submitted. However, more effort must be made to ensure that these are done in a more timely manner |  |
|  | # of mid-term evaluation conducted | 1 | 1 | 1 mid-term evaluation conducted | No activity planned for this reporting period |  |
|  | # of terminal evaluation conducted | 0 | 0 | 1 terminal evaluation conducted | No activity planned for this reporting period |  |
| Outcome 3.3: Knowledge shared between Caribbean countries and organizations, and GEF IW projects in partnership with IW:LEARN | # of knowledge management & information platform established | 0 | 1 | 1 | Activity 3.3.2.1: Design and implement structure and operational protocols for knowledge management & information platform 10% Case studies of KM Platforms compiled to be used to inform the development. TORs completed and advertised, with engagement of consultant(s) expected in August 2025. Documents and other digital assets compiled since project start date, to be uploaded to platform once it is established. |  |
|  |  |  |  |  | Activity 3.3.2.2: Develop and implement technical meetings and targeted training for beneficiary institutions 0% No activity planned for this reporting period. |  |
|  |  |  |  |  | ESS Guidelines 3 ESS activities started: 1. Stakeholder Engagement plan is in second draft for review and approval & Stakeholder Survey developed and link dispatched to consultants to create database of stakeholders for the overall project 2. Indigenous Peoples Plan is in second draft for final review and approval 3. Accountability and Grievance Mechanism has preliminary guidelines which are to be further developed as part of a wider GRM for CRFM overall. A Grievance Log has been developed, online access to the public is to be finalized and manual modalities are to be discussed and agreed with implementation partners. - Meetings held with consultants to sensitize on the ESS requirements in their contracts and all deliverables reviewed to ensure ESS in mainstreamed in the deliverables. |  |
|  | # of learning engagements | 0 | At least 2 | At least 4 | - GEF IW:LEARN: 100% 4 significant engagements done for reporting period 1: The RPC participated in the GEF IW Large Marine Ecosystems Meeting in Athens, Greece in May 2025 and presented on the project implementation, and participated in the discussions leading into UNOC3. 2: After several discussions with IW:LEARN, the proposal to twin the BE-CLME+ Project with the Micronesia Challenge under the IW Twinning Program was accepted, and the activity is scheduled to be completed in November, 2025. This would involve joint expeditions to Palau and Jamaica with 3 persons from each region, covering aspects of marine protected areas, ecosystem-based fisheries management, governance and management effectiveness. 3: The Project co-organized and partnered with other regional projects and organizations, led by IOC IW:LEARN to host a regional MSP Training and Forum in Panama City in February 2025. The project supported participation of the PMU Staff (x2) and participating countries (x6), joining the group of 80 participants at the event. 4: IWC10 (Uruguay, Sep 2024): The PMU (2 staff) and a country representative from Belize (MSP Officer) attended and participated, including making presentations at IWC10. This also included the 2-day pre-conference training workshops. |  |

9 For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

10 Add rows if your project has more that 3 key indicators per objective or outcome.

11 Depending on selected indicator, quantitative or qualitative baseline levels and targets could be used.

12 Many projects did not identify Mid-term targets at the design stage therefore this column should only be filled if relevant.

13 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

14 Add rows if your project has more than 4 objective-level indicators. Same applies for the number of outcome-level indicators.

Overall rating of project progress towards meeting project objective(s) (To be provided by CAF-GEF Task Manager. Please add columns to reflect all prior year ratings)

| FY rating | FY rating | Comments/narrative justifying the current FY rating and explaining reasons for change (positive or negative) since previous reporting periods |
| --- | --- | --- |

Action plan to address MS, MU, U and HU rating (To be completed by CAF GEF Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |

This section should be completed if project progress towards meeting objectives was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| Low participation from Guyana | Leveraging existing coordinating and cross-cutting intergovernmental mechanisms to ensure that Guyana improves their participation in the project | CRFM with support from FAO-Guyana and FAO Sub-regional Office | Ongoing (commenced November 2024) |
| Delayed first disbursement from CAF | Banking arrangements finalized | CRFM and CAF | September 2024 (first disbursement received Oct 17, 2024 |
| Delayed engagement of Consultants | Improved outreach for RfPs | CRFM | September 2024 and ongoing |

15 Add rows if your project has more than 5 Outcomes.

  - (a) Project implementation progress

| Outputs 16 | Expected completion date 17 | Implementation status as of June 30, 2024 (%) | Implementation status as of June 30, 2025 (%) | Comments if variance18. Describe any problems in delivering outputs | Progress rating19 |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: National MSP conducted in project countries, with a participatory, climate- and gender-sensitive approach (To inform national blue economy strategy and opportunities) |  |  |  |  |  |
| Activity 1.1.1.1 Data Gaps and needs assessment to inform MSP | TBD | 8% | 80% | Consultancy activities for Barbados, Belize, Jamaica and Saint Lucia commenced in April 2024, with inception meetings and reports completed by the end of June 2024. As at June 30 2025, 4 out of the 6 participating countries- Barbados, Belize, Jamaica and Saint Lucia- have completed activity 1.1.1.1, with consultancy activities for Panama to be completed by July 2025. The expected completion date for this activity by all participating countries is TBD pending the completion of EOI evaluations by Guyana. The results and recommendation from this consultancy will establish a baseline to inform subsequent project activities such as the development of MSP Guidelines and Protocol (Activity 1.1.1.2) and conducting a national stakeholder driven MSP (Activity 1.1.1.3). |  |
| Activity 1.1.1.2 Development of a project-wide MSP protocol that takes into account national data assessments | December 2025 | 0% | 6% | Following the inception meeting with the consultant, CRFM/PMU, and participating countries, the consulting firm- Howell Marine Consulting- submitted the inception report detailing the approach and methodology for undertaking the assignment, workplan and budget. In addition to the six participating countries, the status of MSP and the application of the MSP Guidelines and Protocol by other CRFM Member States will be considered during this consultancy. The MSP Guide and protocol will include MSP steps and principles for the Caribbean Region with the MSP guide offering prescriptive requirements for each step of the MSP process and recommending solutions for challenges of particular relevance to the Caribbean. The Regional MSP Protocol will include voluntary requirements to ensure transboundary cooperation for data alignment, stakeholder engagement,etc. |  |
| Activity 1.1.1.3 Conduct national stakeholder-driven MSP following project MSP protocol and in support of nationally relevant priorities. | TBD | 0% | 0% | The draft TOR is completed, however the commencement of this activity is contingent on the completion of the abovementioned preliminary activities 1.1.1.1 and 1.1.1.2 which will further define the scope of activities for each participating country. As such the completion date can not be determined at this time. However, it is anticipated that the commencement of this activity will commence during the next reporting period. |  |
| Output 1.1.2: National BE strategies designed, validated and deployed in project countries (with key marine economic sectors). |  |  |  |  |  |
| Activity 1.1.2.1:Conduct national BE assessments and draft BE strategies, including specific focus on national BE sustainable financing options and seafood value chain opportunities | TBD | 4% | 21% | Consultancy activities commenced for Barbados in April 2024. By the end of June 30 2024, the inception meeting was convened with the Consultant, CRFM/PMU and national agencies from Barbados, and submitted the inception report detailing the approach and methodology as well as the workplan and schedule. As at June 30, 2025,one out of the six participating countries completed activity 1.1.2.1. The Barbados Blue Economy Roadmap was enhanced through the development of a National BE Roadmap Strategy and Implementation Plan for the Fisheries Sector under this activity. Sustainable financing options for the implementation of BE activities were also identified. Following the recommendations from TAC and PSC, activity 1.1.2.1 was suspended for all the participating countries except Barbados. This was to allow for the completion of data gaps and needs assessment to inform MSP (Activity 1.1.1.1). While this may have resulted in delay in the commencement of the activity 1.1.2.1, the results and findings from activity 1.1.1.1 informed and guided the scope of Activity 1.1.2.1 developed for the other 5 participating countries During the reporting period, activities commenced for Panama and Saint Lucia (April 2025) with the completion of inception meetings and the submission of the inception report. The TORs for Belize and Jamaica were also finalised, with procurement expected to commence in July 2025. There continues to be a delay in the commencement of activities for Guyana under this output notwithstanding several attempts by the CRFM/PMU to solicit and encourage the evaluation of proposals by the national technical focal point. Evaluation of proposals by the national technical focal point is required for selection of the most suitable consultant to undertake the consultancy. |  |
| Activity 1.1.2.2:Hold national BE strategy validation workshops (Workshop) |  | 0% | 17% | As at June 30, 2025, one of the six participating countries completed activity 1.1.2.2. National validation has been completed for Barbados following the completion of the BE assessment and development of BE Roadmap Implementation Plan for the Fisheries Sector (Activity 1.1.2.1- FAO funded). Progress on this activity for the other participating countries is contingent on the completion of the final deliverable under Activity 1.1.2.1 (National BE Strategy), that is ongoing for Saint Lucia and Panama. Procurement of consultancy services for Belize and Jamaica will commence in July 2025. Activities for Guyana are pending due to delays in the completion of evaluations of the EOIs by the national focal point. |  |
| Activity 1.1.2.3:Implement at least one BE strategy recommendation as part of long-term BE strategy (Government sub-grant) |  | 0% | 0% | No activity planned for this reporting period. Progress on this activity is contingent on the completion of Activity 1.1.2.1(FAO funded) and activity 1.1.2.2 (CAF Funded). The design of the BE strategies will guide and inform the support to be provided to implement at least one BE recommendation. |  |
| Output 1.2.1: Newly created marine protected areas or Effective Area-Based Conservation Measures (OECM) in targeted countries. |  |  |  |  |  |
| Activity 1.2.1.1: Conduct a data-driven assessment utilizing national project MSPs to develop recommendations that identify areas for newly created marine protected areas (MPAs) or Other Effective Area-Based Conservation Measure (OECM) (Government-led or Consultancy) that promote an ecosystem-based approach to fisheries management | TBD | 0% | 0% | No activities planned for this reporting period |  |
| Activity 1.2.1.2: Hold a stakeholder workshop to discuss MPA/OECM recommendations and draft national project specific MPA strategies that map out nationally relevant path for timely MPA/OECM creation/expansion (Workshop) | TBD | 0% | 0% | No activities planned for this reporting period |  |
| Activity 1.2.1.3: Implement national project specific MPA strategies for timely MPA creation/expansion | TBD | 0% | 0% | No activity planned for this reporting period |  |
| Output 1.2.2: Enhanced marine protected areas management capacity in select countries. |  |  |  |  |  |
| Activity 1.2.2.1: Develop project-wide MPA management training materials (online and in-person) that prioritize MSP, BE, and ecosystem-based fisheries management | October 2025 | 0% | 20% | Following the evaluation of proposals, consultancy services form the University of the West Indies- Centre for Resource Management and Environmental Studies (UWI- CERMES) were secured to assess the training needs and develop MPA management training materials that prioritizes MSP,BE and EbFM. An inception meeting was convened with the consultant, the CFRM/PMU, participating countries and members of the TAC (6 participants, 67% females). Feedback from the inception will guide the preparation of the inception report which detailed the approach and methodology for undertaking the assignment, as well as the workplan and schedule. The deliverables from this consultancy will be used in the implementation of future planned MPA management training activities (Activity 1.2.2.2). Both activities (1.2.2.1 and 1.2.2.2) are expected to contribute to the overall output. 1.2.2 which include enhancement of management effectiveness of MPAs |  |
| Activity 1.2.2.2: Hold a project-wide workshop for MPA managers from participating countries to implement MPA management training materials (Activity 1.2.2.1). | TBD | 0% | 0% | No activities planned for this period. Implementation of this activity is contingent on the completion of Activity 1.2.2.1 (Develop project-wide MPA management training materials (online and in-person) that prioritize MSP, BE, and ecosystem-based fisheries management- FAO Funded) which is currently ongoing and expected to be completed by December 2025. |  |
| Output 2.1: |  |  |  |  |  |
| Activity 2.1.1: Key seafood value chains assessed and incorporated into national blue economy strategies and marine spatial planning efforts, including identification of future value chains and end market requirements. |  |  |  |  |  |
| Activity 2.1.1.1 - Analysis of Existing Value Chains Activity 2.1.1.2 - Identify New Opportunities | YR2Q4 YR2Q4 | 0% 0% | 30% 0% | Due to quality control concerns of the first draft report and subsequent reports due to the additional time required by the consultant to gather and integrate data and insights, as well as conduct a follow-up visit to Bocas del Toro Panama. It was suggested that the delivery date of the first draft report be rescheduled to 23 May 2025. The first draft report Product 2 - Analysis of Existing Value Chains was submitted on 23 May and after review by the PMU and all the project countries it was concluded that key sections for the analysis and inconsistencies were present throughout the report which led to the report being considered as inadequate. This was communicated to the consultant via letter dated 18 June and a monitoring meeting was convened on 24 June with the consultant to discuss the outcome of the review and they were guided to revise the report to address the identified gaps in the value chain analysis and other key missing elements. The revised report is expected to be submitted in the next reporting period (July). Due to the delay in Product 2, the submission date for Product 3 will be affected. The additional time needed for Product 2 will compromise the original timeline for Product 3 (20 June 2025 to 22 August 2025). |  |
| Activity 2.1.1.3: Mapping of the certification and quality control requirements in potential export markets and identify gaps. (Consultancy) | YR2Q4 | 0% | 0% Not planned for this reporting period | TOR Development on-going and it is expected to have a first draft by August 2025. |  |
| Activity 2.1.1.4: Linking value chains to BE strategies and MPA planning (Workshop) | YR2Q4 | 0% | 0% Not planned for this reporting period | Not planned for this reporting period |  |
| Activity 2.1.2: Seafood value chain added- value opportunities identified, and market and economic feasibility assessed, including testing innovative post- harvest processing methods and reduction of post-harvest loss and improved/creation of new seafood products to reduce waste. |  |  |  |  |  |
| Activity 2.1.2.1 and Activity 2.1.2.2 Assessment of Bottleneck to Value Chain Added-Value Opportunities and Identification of Optimal Value Chains in Caribbean Fisheries | YR3Q2 | 0% | 15% | This activity has been merged with Activity 2.1.2.2 and is guided by the outcome of the precursor Activity 2.1.1.1 & 2.1.1.2. The TOR is approved by project countries and FAO. It was reviewed internally and a technical final report was included as part of procurement requirements before forwarding to the Finance department to begin the procurement process. It is expected that the procurement process would be completed in the next reporting period. |  |
| Activity 2.1.3: National policy recommendations developed promoting an enabling environment for strengthening of seafood value chains and markets, including empowerment of women, indigenous peoples, and ethnic minorities. |  |  |  |  |  |
| Activity 2.1.3.1: Preparing national policy recommendations (National Workshops + 1 Regional Workshop) | YR4Q1 | 0% | 0% Not planned for this reporting period | Not planned for this reporting period |  |
| Activity 2.1.3.2: Capacity Building for Mainstreaming FAO’s Small-Scale Fisheries Guidelines into value chains | YR2Q1 | 0% | 100% | The workshop has been completed, however, there was a minor delay in the finalization of the final products and reporting. This was due to a medical situation experienced by the lead consultant with UWI Cermes. |  |
| Activity 2.1.3.3: Value Chain Policy Awareness and Understanding | YR3Q1 | 0% | 0% Not planned for this reporting period | Not planned for this reporting period |  |
| Activity 2.1.3.4 Seafood Value Chain Carbon Footprint Analysis | YR2Q3 | 20% | 30% | There was a delay in the submission of the quick assessment survey by project countries which led to a delay in the evaluation and selection of fisheries for the analysis. Also, the data collection process is experiencing a delayed timeline due to competing priorities of the selected fishery entities, time and availability mainly Northern Fishermen Coop. as the data collection time coincided with their preparation and reopening of the lobster season on 1 July 2025. |  |
| Activity 2.1.4: Regional and national fisheries authorities and other relevant regulatory agencies trained in seafood value chain analysis and development within the context of the blue economy. |  |  |  |  |  |
| Activity 2.1.4.1 Identification of Value Chain Capacity Needs and Gaps | YR3Q2 | 0% | 15% | The TOR is in the procurement stage as of 23 June and it is expected to be advertised and active in the next reporting period. |  |
| Activity 2.1.4.2: Training courses for relevant stakeholders (Consultancy) | YR3Q3 | 0% | 0% Not planned for this reporting period. | Not planned for this reporting period |  |
| Output 3.1: Output 3.1.1: Assessment and compilation of existing MSP planning efforts in the CLME+ to inform regional ecosystem- based management of key fisheries (building on MSP plans from GEF-6 Caribbean Regional Oceanscape Project) |  |  |  |  |  |
| Activity 3.1.1: Develop and implement training on Marine Spatial Planning and the Blue Economy | YR3Q2 | 5% | 25% Regional MSP Training completed in partnership with IOC in February 2025. Development of the Regional MSP Framework and Protocols has commenced and this will inform national-level training on development of MSPs | Slow project start-up, including staffing and funds disbursement during first year resulted in delays. However, with the team in place since July 2024, this has resulted in improvement of rate of output for this activity. |  |
| Activity 3.1.1.2:Develop and implement training on MPAs and Ecosystem-Based Fisheries Management | YR 3 Q3 | 0% | 25% Regional MPA Training developed and delivered in partnership with UNEP, FAO and other regional partners in November 2024. UWI-CERMES has been engaged to identify training needs and develop MPA management training materials that prioritizes MSP,BE and EbFM. This is expected to be completed in early 2026, which will guide the implementation of the training | Delays in procurement and engagement of consultants to produce the training materials were experienced. However, this has now been addressed. |  |
| Output 3.1.3: New national and regional partnerships to foster cooperation on ecosystem- based fisheries management and the development of seafood value chains | YRQ4 | 10% | 30% Regional partnerships has increased significantly, mainly through joint activities including MPA Training, MSP Training and SF Value chains | The partnership-building will be ongoing. This includes new and existing partnerships. |  |
|  | YR4Q3 | 0% Discussions to engage IW:LEARN held | 40% GEF IW:LEARN: The RPC participated in the GEF IW Large Marine Ecosystems Meeting in Athens, Greece in May 2025 and presented on the project implementation, and participated in the discussions leading into UNOC3. The proposal to twin the BE-CLME+ Project with the Micronesia Challenge under the IW Twinning Program was accepted, and the activity is scheduled to be completed in November, 2025. This would involve joint expeditions to Palau and Jamaica with 3 persons from each region, covering aspects of marine protected areas, ecosystem-based fisheries management, governance and management effectiveness. | Engagement with IW:LEARN enhanced since July 2024 as full PMU Team convened. This has resulted in increased engagement with IW:LEARN |  |

16 Outputs and activities as described in the project logframe or in any updated project revision.

17 As per latest workplan (latest project revision)

18 Variance refers to the difference between the expected and actual progress at the time of reporting.

19 To be provided by the CAF Task Manager

| Outputs 16 | Expected completion date 17 | Implement- ation status as of June 30, 2024 (%) | Implement-ation status as of June 30, 2025 (%) | Comments if variance18. Describe any problems in delivering outputs | Progress rating19 |
| --- | --- | --- | --- | --- | --- |
| Output 3.2.1: Project monitoring and evaluation plan and system, in place |  |  |  |  |  |
| Activity 3.2.1.1: Develop Project Annual Work Plans and detailed Project Monitoring & Evaluation System. | YR4Q4 | 70% Project Monitoring System in place and active | 80% Coordination Meetings, TAC Meetings and RSC Meetings held to monitor progress of the project | NFPs were tasked to confirm the RSC Representatives and then approve the TAC Members. This was completed in Sep 2024. |  |
|  | YR4 Q4 | ESS (0%) ESS Officer not engaged at this stage | 30% (overall project - ESS)) 3 ESS Plans Drafted: - Stakeholder engagement Plan - Indigenous Peoples Plan - Grievance Redress Mechanism (70% each) The delays are due to the protracted engagement of the ESS Officer. No ESS post was initially included in the project, approval had to be sought from the Project Steering Committee. Subsequent to the engagement of a new Officer, the Officer resigned in May 2025. A new ESS Officer was engaged mid June 2025. | Delayed recruitment of PMU Staff |  |
| Activity 3.2.2.1: Conduct Project Mid-Term Evaluation (MTE) | TBD | not planned for this period | Not planned for this period |  |  |
| Activity 3.2.2.2: Conduct Project Terminal Evaluation | TBD | not planned for this period | Not planned for this period |  |  |
| Output 3.3.1: Technical manuals on ecosystem-based management of fisheries informed by MSP, developed and disseminated within the region |  |  |  |  |  |
| Activity 3.3.1.1: Develop and disseminate Ecosystem-Based Fisheries Management Manuals |  | 0% | 0% Not planned for this period as precursor activity is being done | N/A |  |
| Activity 3.3.1.2: Develop and implement training at the regional level in the use of Ecosystem-Based Fisheries Management Manuals |  | 0% | 0% Not planned for this period as precursor activity is being done | N/A |  |
| Output 3.3.2: One knowledge management & information platform established (focused on project lessons learned from MSP, seafood value chain, and national blue economy |  |  |  |  |  |
| Activity 3.3.2.1: Design and implement structure and operational protocols for knowledge management & information platform | YR 2 Q4 | 0% | 10% Consultancy being advertised; digital assets from previous activities collected to be used in KR Platform once developed | Delayed approval of TORs |  |
| Activity 3.3.2.2: Develop and implement technical meetings and targeted training for beneficiary institutions | YR3 Q3 | 0% | 0% Not planned for this period as precursor activity is being done |  |  |

Overall project implementation progress 20 (To be completed by CAF- GEF Task Manager. Please add columns to reflect prior years’ ratings):

| FY 2023-24 rating | FY2024-25 rating | Comments/narrative justifying the rating for this FY and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |

Action plan to address MS, MU, U and HU rating. (To be completed by CAF Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |

20 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

This section should be completed if project progress was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| Delay in first disbursement; this delayed the engagement of consultants for activities | Increased communication with CAF Task Manager and banking contacts | CRFM and CAF | August 2024 (first disbursement received October 17, 2024) |
| Inadequate reports from consultants | Formal letter sent to consultants outlining areas for improved performance, planning or outputs | RPC and ED | Ongoing |
| Poor response rate from project countries | Follow-up emails, whatsapp messages and whatsapp calls to NFPs | PMU | Ongoing |
| Competing priorities and limited availability | Dialogue with NFPs and technical staff in-country to combine related activities and stakeholder groups to reduce time commitment by staff | PMU with Country NFPs | Ongoing |
| Low participation from Guyana | Leverage existing coordinating and cross-cutting intergovernmental mechanisms to ensure that Guyana continues to participate in the project | CRFM with involvement of FAO and CAF | Already started in November 2024 and periodically since; will continue with different strategies until there is an improvement in Guyana’s involvement. |
| Extended procurement process cycle | Improve pace of procurement by using targeted advertisement through list servers and consultants’ databases, engagement with recruiters | CRFM | Already started in January 2025 and will continue throughout project |

3.3.	Risk

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what

measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the CAF Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The CAF Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems |  | X |  |  |  |  | PM : Changes in project organization management structure being done to maximize efficiency. Once this is complete, the risk would be reduced as there will be stability and clarity of roles and responsibilities |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : TAC and RSC was appropriately convened and meetings have been conducted regularly |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal com- munications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Communications are transparent and timely |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow | Project progressing | Some changes in project work plan | Major delays or changes in work |  | X |  |  |  |  | PM: Delays with Consultancies, especially with in-country activities has resulted in extensions being granted to the Consultants. Though these are not very long extensions, for precursor activities, this would have an impact on subsequent activities |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | according to work plan | but without major effect on overall timetable | plan or method of implementation |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co- financing may not materialize |  | X |  |  |  |  | PM: Owing to late start up, co-financing reported is relatively low but already showing increased contributions as activities have increased. |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: There will be some adjustments in the budget between line items, mainly on consultancies, however these should not exceed 30% of the original budget. Overall budget is not expected to be affected |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: Funds appropriately managed and accounted for |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete | Reports are complete and accurate but often delayed or lack critical | Serious concerns about quality and timeliness of project reporting |  | X |  |  |  |  | PM: Reports were behind but have since been brought up to date. Measures have been put in place to ensure that delays in reporting are not experienced in the subsequent periods |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | and accurate with a good analysis of project progress and implementation issues | analysis of progress and implementation issues |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: With the ESS measures in place, and involvement of the NFPs for each country in the consultancies, stakeholder involvement has been ensured.Other critical groups such as women’s organization and indigenous organizations are identified and engaged for all activities which also strengthens the inclusivity. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External com- munications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstand- ings concerning objectives and activities evident |  | X |  |  |  |  | PM: There is adequate communications of the project to external stakeholders, however, this will improve with the implementation of the KM Platform and Communications Strategy in the next reporting period |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: There is clarity among the project executing agency including the PMU of the linkage with the short-term precursor activities and the subsequent activities and how these align to the long-term goals of the project. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: The consultancy activities are guided by significant scientific input from TAC, RSC, CRFM, CAF and FAO. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: There is no negative political impact on project decisions. Decisions have been taken based on national policy priorities to ensure relevance in the work under the project. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: Normal democratic elections have occurred in the participating countries during the project. This will also continue for the rest of the project life. This causes delays in-country with government staff may be involved with other activities during election periods, however, the PMU has been working with the NFPs to ensure that the project is not affected. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: One major storm, Hurricane Beryl in 2024, affected activities in the participating countries, most notably in Barbados. As these project activities are not infrastructural, there was no negative damage to the project outputs. However, this led to delays with some workshops and stakeholder consultations, as well as involvement of key staff in the country. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: There was a minor disruption in June 2025 in Bocas del Toro that affected the timelines on one in-country activity. However, the workplan of the consultant was adjusted, and there should not be any major impact. Further the partnership with NFP and other stakeholder groups strengthens project communication to aid early warnings of any potential issue so that appropriate corrective actions or responses can be taken. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: The main issue in the partner institutions is the added burden on this project along with an increasing work portfolio of key staff. Though there is always a need to improve technical capacity of the personnel in these agencies, the need is for time allocation for this project. The PMU constantly aims to coordinate among the various consultant activities to more efficient and cognizant of staff time in country |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement21 |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY rating | FY rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| N/A | LOW |  |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

21 Only for Substantial to High risk.

# RATING MONITORING AND EVALUATION

Based on the answers provided to the questions in 4.1, 4.2 and 4.3 below, the CAF Task Manager

will provide ratings for the following aspects of project monitoring and evaluation:

- Overall quality of the Monitoring & Evaluation plan

- Performance in the implementation of the M&E plan

  - Does the project M&E plan contain the following:

    - Baseline information for each outcome-level indicator	Yes □	No □

    - SMART indicators to track project outcomes	Yes □	No □

    - A clear distribution of responsibilities for monitoring project progress.	Yes □	No □

  - Has the project budgeted for the following M&E activities:

| - Mid-term review/evaluation | Yes □ | No □ |
| --- | --- | --- |
| - Terminal evaluation | Yes □ | No □ |
| - Any costs associated with collecting and analysing indicators’ |  |  |
| related information | Yes □ | No □ |

Please rate the quality of the project M&E plan (use HS, S, MS, MU, U, HU):

4.3 Has the project:

| - Utilized the indicators identified in the M&E plan to track progress |  |  |
| --- | --- | --- |
| in meeting the project objectives; Yes □ |  | No □ |
| - Fulfilled the specified reporting requirements (financial, including |  |  |
| on co-financing and auditing, and substantive reports) Yes □ |  | No □ |
| - Completed any scheduled MTR or MTE before or at project |  |  |
| implementation mid-point; Yes □ |  | No □ |
| - Applied adaptive management in response to M&E activities Yes □ |  | No □ |
| - Implemented any existing risk mitigation plan (see previous section) | Yes □ | No □ |

Please rate the performance in implementing the M&E plan (use HS, S, MS, MU, U, HU):

  - Please describe activities for monitoring and evaluation carried out during the reporting period22

  - Provide information on the quality of baseline information and any effects (positive or negative) on the selection of indicators and the design of other project monitoring activities

  - Provide comments on the usefulness and relevance of selected indicators and experiences in the application of the same.

  - Describe any challenges in obtaining data relevant to the selected indicators; has the project experienced problems to cover costs associated with the tracking of indicators?

  - Describe any changes in the indicators or in the project intervention logic, including an explanation of whether key assumptions23 are still valid

  - Describe how potential social or environmental negative effects are monitored

22 Do not include routine project reporting. Examples of M&E activities include stakeholder surveys, field

surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, etc.

23 Assumptions refer to elements of the “theory of change” or “intervention logic” (i.e, the problem is a result of A, therefore, if we change B, this will lead to C) and not to pre-conditions for project implementation. It is a common mistake to include statements such as “political will” as an assumption. This is rather a necessary condition to implement the project.

  - Please provide any other experiences or lessons relevant to the design and implementation of project monitoring and evaluation plans.

# PROJECT IMPLEMENTATION EXPERIENCES AND LESSONS

  - Please summarize any experiences and/or lessons related to project design. Please select relevant areas from the list below:

- Conditions necessary to achieve global environmental benefits such as (i) institutional, social and financial sustainability; (ii) country ownership; and (iii) stakeholder involvement, including gender issues.

Given the nature of the project and the wide range of stakeholders to be engaged, having the NFP as the only focal point can cause delays with activities. Other agencies/ ministries

(e.g. Gender) would be useful to have on board at  the onset of the project to help mobilize

key groups such as women/ indigenous groups to ensure holistic and impactful engagement

is achieved.

- Institutional arrangements, including project governance

Since ESS is a cross cutting theme and is to be monitored  throughout the project, the ESS Officer should have been considered a key role as part of the project team structure from the onset. This would have aided early recruitment and ensured the ESS is operationalized from the onset of project activities.

    - Engagement of the private sector

      - Efforts were made to engage the private sector during the development of the BE Strategy Implementation Plan for Barbados, however, greater participation was seen among the regulatory/ management agencies. Notwithstanding, the strategy considered and defined the role of the private sector in the implementation of the strategy in Barbados. As a lesson learnt from the level of participation of private sector in Barbados, consultants for the ongoing activities (1.1.2.1) in Panama, Saint Lucia, Belize and Jamaica are required to demonstrate deliberate and active engagement of stakeholders in the private sector during their in- country stakeholder consultations and in the development of national BE strategies. The national focal point agencies have also provided support in identifying the key private sector stakeholders.

    - Capacity building;

      - Through a joint collaborative effort with UNEP-CEP, IUCN- BIOPAMA and UWI CERMES, a regional training on MPA and Ecosystem- Based Fisheries Management (Activity 3.1.1.2) was held from November 11- 21 2024 in Barbados. The training took the form of a Training of Trainers through the 14th CaMPAM Training of Trainers Course in MPA Management. This joint activity brought together 20 participants across the English speaking Caribbean including technical officers from project beneficiary countries. This created an opportunity for participants to learn and share their MPA experiences and to network.  Topics covered during the training included, inter alia, data and information for decision making, marine habitat assessments and monitoring, MPA enforcement, ecosystem approach to fisheries, MSP and stakeholder engagement. A follow-up activity to this training includes the implementation of an initiative based on the training received and a need to improve MPA management in each of the participating countries. However it was identified that further mentoring and funding is required to ensure the successful implementation of national initiatives  A similar co-design and co-implementation approach was taken  for the Regional MSP Training and Forum through the IW: Learn partnership held in Panama City from February 18-21, 2025. This regional training on MSP (Activity 3.1.1.1) brought together 80 participants from across Latin America and the Caribbean to participate in training on MSP and the Blue Economy and a forum where countries and experts share best practices and experiences. The BE-CLME+ Project supported the attendance of participants from the 6 participating project countries and members of the PMU, as well as in the panel discussions and breakout group facilitation.  These collaborative approaches have led to greater effectiveness of funding and allowed for reaching a wider stakeholders beyond those from the beneficiary countries. The project will continue to work in seeing partnerships particularly in areas of capacity building and knowledge sharing.

Financial management and co-financing.

The Execution Agreement between CAF and the CRFM was signed on 17 April 2024, and the first advance of funds was received on 17 October 2024. Although the request for the initial disbursement had been submitted early, receipt of the funds was delayed due to external banking challenges unrelated to CAF. Specifically, the transfer was repeatedly rejected by intermediary banks due to U.S. sanctions affecting transactions originating from Venezuela. The CRFM Secretariat, in close coordination with its banking partners, explored multiple alternative channels to receive the funds, all of which proved unsuccessful until the transaction was finally completed in October. As a result of the uncertainty surrounding the timing for the receipt of the fund transfer, the CRFM Secretariat was compelled to delay the commencement of CAF-funded activities until the October–December 2024 quarter. During this period, procurement processes and consultant engagements were undertaken, with full project implementation and disbursement of related payments beginning in January 2025.

The Operational Partner Agreement between FAO and the CRFM was signed on 28 June 2023.  The first tranche of funds was received on 20 October 2023.  Implementation of the FAO-funded activities have been ongoing and funds are available for payments to consultants.

Co-financing during this reporting period has been primarily in-kind contributions received through Member States and regional organizations participation in project implementation activities.  The CRFM Secretariat also made in-cash contributions towards purchasing office equipment, furniture and assets for the project staff.

Component 2

The completion of the SSF Guidelines ToT Workshop, was the first of the many capacity building activities built into the project. This workshop in design was gender-sensitive and inclusive resulting in the participation of 50% females and the engagement of the private sector in the value chain in the area of fish processing and retail and chartered fishing and tours services. Additionally, the on-going value chain consultancy (Activity 2.1.1.1 + 2.1.1.2) has engaged 104 people in total, inclusive of the private sector mainly in fish processing and fishing services. The Seafood Carbon Footprint Analysis (Activity 2.1.3.4) engaged two private sector entities in two project countries and aims to develop action plans and recommendations for reducing GHG emissions in fisheries as well as capacity building strengthening technical, institutional, and human resources to understand, measure, and address carbon footprints. Lastly, the recently advertised consultancy assessment of bottlenecks and identification of optimal seafood value chains (Activities 2.1.2.1 + 2.1.2.2) will examine barriers or hindrances in the improvements in the value chain which will require active private sector engagement and will highlight the most promising opportunities for upscaling the value chain through case-study analysis.

  - Please highlight a few major achievements resulting so far from the project implementation, including but not limited to:

    - Concrete results, both on-the-ground and normative

      - Data gaps and needs assessment to inform MSP has been completed for 4 out of the 6 countries. The reports provided information and made recommendations on the bio-physical and socio-economic data availability and gaps, as well as the institutional and human capacity needed to inform the MSP process. The results and findings were also validated during stakeholder workshops. These hybrid workshops facilitated stakeholder feedback which were incorporated in the finalisation of the consultancy products. The results and recommendation from this consultancy established a baseline to inform subsequent project activities such as the development of national BE Strategies (Activity 1.1.2.1) and the Regional MSP Guideline and Protocol (Activity 1.1.1.2).

      - Consultancy service for conducting national BE assessments and draft BE Strategies (Activity 1.1.2.1) was completed for Barbados. This activity focused on assessing the ongoing BE Program and Policy for Barbados but more specifically the implementation of Fisheries Sector priorities set out in Barbados BE Roadmap. The products under this consultancy included;

        - Stakeholder Map and List Report

        - National BE Roadmap implementation plan for the Fisheries Sector with BE sustainable financing options.

        - National workshop report

A stakeholder validation workshop was held to obtain feedback and recommendations on the results of the abovementioned products.

      - MPA Management Training of Trainers: Twenty (20) participants completed the Training of Trainers Course in MPA management (Activity 3.1.1.2). Training topics were delivered by experts from across the Caribbean who delivered on areas relevant to MPA management in the Caribbean and SIDS context. Topics included, inter alia, Data and information for decision making, marine habitat assessments and monitoring, MPA enforcement, ecosystem approach to fisheries, MSP, and stakeholder engagement.

      - Regional Training and Forum of MSP and BE: Through the IW:LEARN platform led by UNESCO-IOC (MSPGlobal) and co-organised with other GEF supported initiatives within Latin America and the Caribbean, eight (80) participants were trained and participated in forum discussions on BE and MSP. The Training and forum sessions covered topics on MSP& Biodiversity and Climate Change; MSP and Sustainable Blue Economy; Hands-on exercises with MSP challenge and Blue Planning in Practice approaches; as well as sharing of experiences and lessons across the Caribbean and Latin America.

      - The Training of Trainers workshop for integrating the SSF Guidelines into Value Chains was conducted with 10 participants representing 6 countries. The main outputs included the creation of a training package, consisting of a training curriculum, training manual, and supporting materials. Following the completion of this package, efforts will shift to focus on mainstreaming the guidelines in partnership with CNFO and national fisheries authorities from the project countries.

      - The ongoing value chain analysis has submitted the first report on the Analysis of Existing Value Chains and is under review. This report draws upon extensive data collection, including desktop research, in-country visits to all 6 countries including the Indigenous-led fishery of Bocas del Toro, Panama and analysis of inputs from national fisheries authorities.

    - Gender:

- Consultants have been sensitized and have adapted an intersectionality lens where gender, age, disability etc continue to guide them in implementing project activities. Stakeholder engagement is intentional to ensure all groups are represented , barriers to participation are considered and corrective measures explored. With the progress made in the GRM, the Grievance Log is established which facilitates reports to the focal points so beneficiaries have an avenue to seek recourse for complaints. A wider GRM is being developed for the CRFM at large and will also facilitate online, walk in and other modalities to receive complaints. From an M&E standpoint, Indicator 11 ‘Number of Direct beneficiaries disaggregated by Gender as a co-benefit of GEF investment’ the project has maintained engagement of at least 40% of women across all activities which is in alignment with the targets set in the results framework. As part of the wider gender lens engagement of youth in the fisheries sector has also been very consistent. Consultants are advised to be intentional in ensuring stakeholders that are disabled are also captured. We have deployed a stakeholder engagement survey and as it continues to be populated a more detailed breakdown by gender, age disability will be available.

    - Indigenous peoples

- With the preparation of the Indigenous People Plan, consultants have begun engaging the respective groups using  Free Prior & Informed Consent. Despite location or language barriers Indigenous People have been able to fully participate in the relevant activities to date as consultants use interpreters or hire team members that speak the language and online engagement is used when face to face is not possible.

    - Private Sector, Sustainability and Innovation

Following the completion of the SSF Guidelines ToT Workshop, female participation was 50% and private sector participation was 20%. The on-going value chain consultancy (Activity 2.1.1.1 + 2.1.1.2) has engaged 104 people, with 24% female and 12% Indigenous engagement. Additionally, the private sector was engaged along the entire value chain. The Seafood Carbon Footprint Analysis (Activity 2.1.3.4) engaged two private sector entities in two countries and aims to develop action plans and recommendations for reducing GHG emissions in fisheries. This addresses the sustainability of the fishing sector identifying emission points and its environmental impact. Also, with fossil fuels as the main fuel source contributing to GHG emissions and fish processing consumption of electricity. This analysis also promotes innovation in the fisheries sector as a driver towards sustainability practices and climate-smart strategies. Lastly, the recently advertised consultancy assessment of bottlenecks and identification of optimal seafood value chains (Activities 2.1.2.1 + 2.1.2.2) will examine barriers or hindrances in the improvements in the value chain which will require active private sector engagement and will highlight the most promising opportunities for upscaling the value chain through case-study analysis.

Based on the approved Project Document, Output 1.1.3: Sustainable financing strategies for national BE, designed and validated, highlighting marine based economic opportunities was combined with activities under Output 1.1.2 more specifically Activity 1.1.2.1.

Activity 1.1.3.1 was combined with Activity 1.1.2.1 (as per project  document)

Antigua and Barbuda, Belize, The Bahamas, Dominica, Guyana, Grenada, Jamaica, St. Kitts and Nevis, Saint Lucia, Trinidad and Tobago, Barbados.