UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5195 | Umoja no.: SB-006773.01 |
| --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | 5195: Building National and Regional Capacity to Implement Multilateral Environment Agreements (MEA) by Strengthening Planning and State of Environment Assessment and Reporting in the Pacific |  |
| Duration months | Planned |  | 48 months |  |
|  | Extension(s) |  | 31st December 2021 & 12 months added |  |
| Division(s) Implementing the project |  |  | Science Division (Formerly DEWA), Climate Services & Capacity Building Unit, Capacity Development & Innovations Branch. |  |
| Executing Agency(ies) |  |  | Secretariat of the Pacific Regional Environment Programme (SPREP) |  |
| Names of Other Project Partners |  |  | International Union for Conservation of Nature (IUCN) |  |
|  |  |  | European Union - African, Caribbean and Pacific (ACP) region |  |
| Project Type |  |  | Full Size Project (FSP) |  |
| Project Scope |  |  | Regional |  |
| Region (delete as appropriate) |  |  | Asia Pacific |  |
| Names of Beneficiary Countries |  |  | Cook Islands, Federated States of Micronesia (FSM), Fiji, Kiribati, Republic of the Marshall Islands (RMI), Nauru, Niue, Palau, Papua New Guinea (PNG), Samoa, Solomon Islands, Tonga, Tuvalu, and Vanuatu |  |
| Programme of Work |  |  | POW 7.1 |  |
| GEF Focal Area(s) |  |  | Multi Focal Area |  |
| UNDAF linkages |  |  | The Inform project contributes to the United Nations Pacific Strategy 2018 – 2022 strategic priority area 1; climate change, disaster resilience, and environmental protection. It also contributes to outcome 5 on governance and community engagement. |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Although this GEF CCCD project has been designed to create enabling environment and enhance the implementation, monitoring and reporting of all SDGs with an environmental dimension, majority of the project interventions primarily contribute to the following SDGs, targets and indicators: SDG 13 (13.2.1, 13.3.1, 13.3.2, 13.b.1); SDG 15 (15.1.1, 15.1.2, 15.2.1, 15.3.1, 15.4.1/2, 15.9.1); SDG 16 (16.10.2); and SDG 17 (17.14.1; 17.16.1; 17.18.1) This project also links to SDG 14 (14.1, 14.2, 14.3, 14.5, 14.a, 14.c) |  |
| GEF financing amount |  |  | USD 4,319,635 |  |
| Co-financing amount |  |  | USD 6,476,276 |  |
| Date of CEO Endorsement |  |  | 15 September 2016 |  |
| Start of Implementation |  |  | 21 December 2016 |  |
| Date of first disbursement |  |  | 16th January 2017 |  |
| Total disbursement as of 30 June |  |  | USD 1,557,926 |  |
| Total expenditure as of 30 June |  |  | USD 1,405,906 |  |
| Expected Mid-Term Date |  |  | 31 October 2019 |  |
| Completion Date |  | Planned | 31 December 2021 |  |
|  |  | Revised | NA |  |
| Expected Terminal Evaluation Date |  |  | 30 June 2022 |  |
| Expected Financial Closure Date |  |  | 31 December 2022 |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Insert the Subprogramme(s) and biennia of the PoW to which the project contributes 2018-2019 UNEP SP7 EA(a)(ii) | Specify the relevant Expected Accomplishment(s) & Indicator(s) Insert the Subprogramme’s Expected Accomplishment(s) and Indicator(s) to which the project contributes SP7 EA(a): Governments and other stakeholders use quality open environmental data, analyses and participatory processes that strengthen the science-policy interface to generate evidence-based environmental assessments, identify emerging issues and foster policy action SP7 EA(a)(ii): Increase in the number of countries reporting on the environmental dimension of sustainable development through shared environmental information systems with country-level data made discoverable through UNEP |
| --- | --- |
| The GEF-funded “Inform” project directly contributes to the PoW EA and indicators through the establishment of environmental data portals and reporting tools for 14 Pacific Island Countries. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
| NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. Not applicable, this being a GEF5 project |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Inform project contributes to the United Nations Pacific Strategy 2018 – 2022 strategic priority area 1; climate change, disaster resilience, and environmental protection. It also contributes to outcome 5; governance and community engagement. For Outcome 1, the project improves the tracking and environmental condition and the datasets and information that informs decision making on the topics of climate change, climate variability and environmental protection. For Outcome 5, the project provides mechanisms, processes and capacity building to increase transparency in the decision-making process in all levels of government. Project also provides a mechanism for government data and information to be easily shared with the citizens. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The Inform Project assists Pacific Island countries better manage and use environmental datasets for national, multilateral environment agreements and SDG Reporting. The environmental databases and indicators developed in the project focused on the waste biodiversity and climate change cluster of MEA’s. As a result of this information and indicators have been collated and developed which pertain in part or directly to SDG 13, 14, 15 and targets of 12, 11, 16, 6 and 17. The project outputs bring together datasets and information from related sectors so that interactions between the datasets can be documented in SDG tracking and reporting. The Pacific data portal and national portals along with the regional partnership the project has developed worked directly to provide transparency and decision making, government and public access to data and policy coherence within and between sectors. Due to the nature of the data and reporting being supported by this project multiple stakeholders now have free unfettered access to data. Capacity building is taking place within the environment sector and their key government partners including Statistics to ensure administrative environmental data can be used by the National Bureaus of Statistics. The project is supporting country data collection which will inform the tracking of progress toward achieving the following SDGs: 11.6, 12.4.1, 12.4.2, 13.1, 13.B, 14.1, 14.2, 14.3, 14.5, 14.A, 14.C, 15.1, 15.2, 15.3, 15.4, 15.5, 15.6, 15.8, 15.9, 15.A, 15.B, 16.10, 17.14, 17.16, 17.18 |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2018 | FY 2019 | FY 202 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR |  |  |  |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2018 | FY 2019 | FY 2020 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S |  |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. For the first year of the Inform project, an internalization process took place that saw the project manager hired in September 2017. The Inception workshop was held in Apia, Samoa in November 2017 and was attended by 13 participating member countries. During the Inception workshop, the Steering Committee was established and first official meeting convened, the Terms of Reference for the Steering Committee approved, Membership selected from Nauru, Papua New Guinea and Tonga representing the three sub-regions: Melanesia, Micronesia and Polynesia. The Inception Meeting was supported by SPREP Environmental Monitoring and Governance Programme staff and key staff of SPREP. UN Environment was represented by the UNEP GEF Task Manager, Finance Officer and Developers of IRIS. As of June 2018, this project was well underway with coordination, communication across the 14 governments working well to enhance access to environmental data for decision makers. Main project outputs and results completed included: national level inception workshops completed in 10 of the 14 countries. National data portals (repositories) installed and in use. A prototype indicator reporting tool was tested in 1 the Cook Islands. Capacity building activities were conducted in 10 of the 14 PICs. Considering the complex data portal hosting modalities, the project team and country focal points have agreed on a simplified, cloud-based hosting solution for all of the participating countries. The 2nd year of the Inform project’s actual implementation following the Inception Workshop has seen the development and deployment of a network of 14 nationals data portals and a regional data portal. Some global data sources have been integrated into the national portals and the project has developed a partnership with the Secretariat of the Pacific Community’s Pacific Data Hub. The result of the network of data portals and integration to the SPREP’s data management workflow has resulted in over 5,000 datasets being collated at the regional level. The reporting tool developed in 2018 was tested and trialled with Cook Islands in country and all countries during regional consultations; based on country feedback the tool has been redeveloped for more intuitive workflow. The improved reporting tool will be launched in the 3rd quarter 2019. A joint Regional inform & ACPMEA 2 workshop was held the week of September 19th,2018 and was attended by 12 project countries. The second Steering Committee meeting was held during the regional meeting chaired by Tonga and attended by Nauru and Papua New Guinea including UN Environment GEF Task Manager and SPREP EMG Director. The Inform Project Manager presented the 2019 workplan which was subsequently approved by the Steering Committee. Given that Membership of the Steering Committee is based on a 12-month rotational basis, three new members were therefore selected. Capacity building has been carried out for all Inform project countries during regional workshops including in-country capacity building in 11 countries: RMI, FSM, Palau, Nauru, Kiribati, PNG, Solomon Islands, Samoa, Niue, Tonga, and Cook Islands. Over 100 national officers and participants have been exposed to and trained in the use of the national data portals and over 60 government officers have been trained in the State of the Environment report process. The State of Environment (SoE) reporting process is a national requirement and a mechanism within the Inform project to access, interpret and immediately use national datasets for decision making as well as linked reporting. Indicators within the SoE have been developed with national reporting in mind as well as MEA requirement and SDG tracking. Awareness and outreached also took place through electronic media, including email blasts that reach over 160 people, press releases and data stories. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | HS |  |  |  |
| - Since project inception, a small open data community has formed around the national data portals in the majority of project countries. These are national officers who are contributing to open data at the sector level are also working toward transparency in decision making. While only PNG belongs to the open data charter, many of the other Pacific island nations are contributing to its goals through this project. More awareness and visibility on this issue will be built over the 2nd half of the project. - An Environmental data policy was developed and adopted to meet national needs of PNG and a similar policy was also developed and adopted to meet regional needs at SPREP. - The Inform project has contributed to the development of a Pacific data community amongst the Pacific countries by engaging with SPC and the Pacific Data Hub as well as SPREP projects and other Council of Regional Organizations of the Pacific agencies. This community further supports enhanced data availability for Pacific Island countries. - A project implementation challenge identified includes a small user-base for the reporting tool identified during this phase of the project. The project has attempted to mitigate this issue by re-designing a more intuitive interface. - Another challenge identified is the legacy of prior UNDP CCCD project implementation in four countries; Samoa, PNG, Vanuatu & Kiribati. These project outputs partially addressed the database component of the Inform project and significant time has been spent trying to reconcile various systems including the perceived competition between the systems. In the case of PNG the database was theoretical and that it was recommended but not established anywhere. In the case of Kiribati and Vanuatu a DEV info installation was installed however neither system was populated with data and only one officer per country could access the system. In the case of Samoa, a system called DKIF was purchased. This system is currently offline and has substantial ongoing software maintenance cost which approved to be a burden to the ministry. The key changes since June 2018 include a ten-fold increase in the number of available datasets for the Pacific islands to use for reporting and planning. The complete redevelopment of the reporting tool integrating the need for clear guidance on the tool and intuitive interface and additional output options. In addition, there has been an increased awareness of the Inform project and its related tools and processes within departments and ministries of environment including within SPREP. In addition, the project has undertaken a visibility and awareness campaign through press releases, online stories and social media to raise the profile of the project. Increased capacity has been built among key government staff and SPREP officers working on data collection in their relevant sectors. A key partnership has been established between SPREP and the Secretariat of the Pacific Community (SPC). |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L |  |  |  |
| The project continues to reduce risk by maintaining frequent communication with each participating country, providing value in all capacity building exercises and products and adapting to country needs. Small and under resourced departments are backstopped by the Inform team where possible. |  |  |  |  |  |

| Stakeholder engagement | The inform project has engaged all 14 countries project countries at the operational level and several countries at the ministerial level. Overall stakeholder engagement has been high, with enthusiastic up take in PNG and FSM. Fiji has been slow to engage for a variety of reasons, mostly due to human capacity. A number of efforts have been made to work with Fiji and improved communication has taken place in 2nd quarter 2019. |
| --- | --- |

| Gender mainstreaming | The project is focused on Environmental data for decision making so gender is most relevant to who is using the data and has access to it. The project is delivered by a gender balanced team to fairly gender balanced country counterpart, a notable achievement in the IT sector |
| --- | --- |

| Knowledge activities and products | CD 2: Generating, Accessing, and Using Information and Knowledge. Current status is: - Institutions and stakeholders have built skills and knowledge to research, acquire and apply information for collective actions in 10 countries. - Country and regional information is being generated and kept in a coordinated and structured manner which meets all declared environmental monitoring and reporting needs and standards (at national and regional levels) with this information readily available to countries and relevant institutions on demand and on a regular basis, institutional and legal arrangements are being put in place to support this. CD 5: Enhancing Capacities to Monitor and Evaluate Environmental Impacts and Trends. Current status is: - Skills enhancement is taking place through the SoE process so that, national institutions are able to monitor environmental changes. - The data portals have been developed as a means to make monitoring and analytical processes and procedures institutionalised permanently within countries. Such processes include feedback mechanisms so lessons learnt can be shared within each country and across the region/world. |
| --- | --- |

| Stories to be shared | - Inform project webpage with project video and updates: https://www.sprep.org/inform - Data stories posted on the Pacific Environment Portal https://pacific-data.sprep.org/stories - Help-dashboard on the Pacific Environment Portal: https://pacific-data.sprep.org/help-support - The Federated States of Micronesia posted stories on their national data portal on the training sessions they conducted in the different FSM states: https://fsm-data.sprep.org/story/pohnpei-state-data-portals-training - NEMS guidelines available online: https://www.sprep.org/publications/national-environmental-management-strategy-for-pacific-island-countries-and-territories - Mobile Data Collection - Interviews with Pacific islanders: https://www.youtube.com/watch?v=YQFDPG8g6HY&feature=youtu.be - News releases posted to SPREP website: 1. Palau Inform data portal training https://www.sprep.org/news/keeping-environmentally-informed-in-palau-with-the-inform-project 2. FSM develops key environment documents https://www.sprep.org/news/fsm-develops-key-environment-planning-documents 3. Pacific Islands discuss open data https://www.sprep.org/news/pacific-islands-discuss-open-data-for-environment-information 4. South-South Knowledge Exchange https://www.sprep.org/news/south-south-knowledge-exchange-on-open-data-for-the-environment 5.PNG launches 2 environment products https://www.sprep.org/news/png-launches-data-portal-and-data-sharing-policy-for-the-environment 6. Pacific Learning Partnership Established https://www.sprep.org/news/the-pacific-learning-partnership-for-environmental-and-social-sustainability-established 7.EIA important tool for building resilience https://www.sprep.org/news/environmental-impact-assessment-an-important-tool-for-building-resilience-and-achieving-sustainable-development-in-the-pacific-island-region-highlighted-at-iaia19-conference 8. Solomon Islands Waste Management Strategy important tool to address SDG’s and MEAs. https://www.sprep.org/news/solomon-islands-waste-management-strategy-helps-address-sdgs-and-multi-lateral-environment-agreements-meas-solomon-islands-has-a-rich-environment-with-diverse-marine-and-terrestrial-biodiversity-which-is-increasingly-threatened-by-human-induced 9. Pacific islands towards a better community of practice https://www.sprep.org/news/pacific-island-countries-towards-a-better-community-of-practice-in-environment-and-social-impact-assessment 10. Solomon Islands finalize SoE and NEMS https://www.sprep.org/news/solomon-islands-finalise-state-of-environment-report-and-national-environment-management-strategy 11. BIOPAMA-Inform project partnership for Pacific island protected areas https://www.sprep.org/news/biopama-and-inform-project-a-partnership-for-improved-reporting-on-pacific-protected-and-conserved-areas 12.Nauru introduced to Inform project, https://www.sprep.org/news/resilient-environment-through-enhanced-decision-making-nauru 13. Solomon’s Islands new environment portal https://www.sprep.org/news/solomon-islands-new-environment-portal 14. Niue receives draft SoE and NEMS documents https://www.sprep.org/news/niue-track-its-environmental-reporting-and-planning-process 15. Cook Islands national environment portal https://www.sprep.org/news/environmental-data-portal-and-national-reporting-tool-released-cook-islands 16. Tonga begin development of SoE and NEMS https://www.sprep.org/news/stakeholders-meet-develop-state-environment-report-and-national-environment-management 17. PNG gains portal access https://www.sprep.org/news/papua-new-guinea-gains-portal-ease-data-sharing-and-access 18. SPREP establish set of core environment indicators https://www.sprep.org/news/sprep-begins-process-have-set-core-environmental-indicators 19. Tonga gather data for SoE https://www.sprep.org/news/a-good-policy-is-based-on-good-data 20. FSM develops key documents https://www.sprep.org/news/federated-states-of-micronesia-develops-key-environmental-documents 21. PNG hosts improved data portal https://www.sprep.org/news/papua-new-guinea-conservation-and-environmental-protection-authority-hosts-improved-environmental-data-portal |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target/Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1. Design national and regional databases & network to facilitate monitoring the state of the Pacific’s environment. | 1. Data portals accessible online with evidence of use, measured by number of hits per month. | Environment national and regional databases largely non-existent and un-networked where present. | Environmental data portals developed, hosting arrangement confirmed, and capacity building begun. | Environmental data portals in use in at least 8 of the 14 countries. And information from portals being used to inform environmental reporting. | Databases for all 14 PIC’s have been established and deployed on AWS servers in Sydney and Tokyo. Systems administration is currently supported 100% by project staff in Apia. The sustainability and hosting cost of the cloud- based hosting option was identified as the lowest cost most sustainable option available. Evidence of use is clear in 13 of the 14 countries, Fiji has been slow to engage, and the number of unique visits have increased from 405 in Nov 2018 to 980 users in June 2019. Outreach and engagement are taking place in the remaining 4 countries - Kiribati, Vanuatu, Fiji and Samoa. The regional database is now dubbed the “Pacific Environment Portal” or PEP, for ease of communication. First phase of capacity building and user support conducted in 13 PIC’s, with one more to be completed in 2019. | HS |
| 2. Environmental data are efficiently and effectively used for environmental planning and reporting at all levels by strengthening national and regional legal, policy and planning frameworks. | 2. National SoE and NEMS developed and linked to regional and global MEAs and SDGs evidence by the use of SoE indicators in MEAs and SDGs reporting. | Few current SoE and NEMS at the national level. Existing environmental indicators often only used once, with no formal links to MEAs and SDGs. | 8 SoE and NEMS developed with explicit links to MEA and SDG reporting requirements for relevant indicators. | All countries have up to date SoE and NEMS and links between indicators and regional and global reporting requirements are clear. | The SoE and NEMS process is being jointly implemented by the ACPMEA2 and Inform projects. The ACPMEA 2 project provides co-financing to Inform. Inform is adding value to these outputs through better environmental data management through the environment portal as well as the use and development of the reporting tool. The project supports the analysis of national data and interpretation of data for use in indicator-based reporting. SOE reports from Niue, Tonga and FSM include explicit links to SDG and MEA reporting. The state of environment report from RMI served as a foundation for RMI’s fifth national report to the CBD. SoE and NEMS process stage: - finalized and approved in RMI, Palau. - finalized and submitted to the national government in Cook Islands, Niue. - in progress in PNG, Solomon Islands, Tonga and FSM. Reports expected to be completed in 2019 - 2020. - in initial planning stage in Kiribati, Fiji, Vanuatu, Samoa. Regional SoE process has started, with support by The Nature Conservancy. | S |
| 3. Capacity development to support the technical facility | 3. National environment officers actively using the technical facility. Measured by improved reporting rate to MEAs. | In most cases, the technical facility does not exist, thus, capacity is limited in the area of environmental data management. | Training provided to all 14 countries in the use of the technical facility. Evidence of use measured by number of data sets in data portal and number of completed indicators in the reporting tool. | National environment officers make regular contributions and draw from technical facility required environmental data. | Training provided to national environment officers and national stakeholders, on the use of national data portal hosting of data, retrieval and distribution for Cook Islands, Federated States of Micronesia, Republic of Marshall Islands, Nauru, Niue, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu and Palau. National officers in Cook Islands, FSM, Nauru, Niue, PNG, Tonga and Solomon Islands are making regular use of the technical facility (data portal). To date, over 100 officers in the above-mentioned countries have been exposed and trained on the use of the national data portals. The number of datasets has increase since the last reporting period from 500 to over 5000. | HS |
| 4. Project Management and Evaluation | 4. Project is effectively managed with rigorous financial tracking and regular reporting. Measured by on time narrative and financial reports accepted by the Task Manager. | Project and financial tracking began January 01, 2017. | 2019 PIR and Financial Report submitted to Task Manager. Mid Term Review begun and fully supported by Inform PMU. | Terminal Report, Final PIR and financial report submitted and accepted. Terminal Review supported. | Narrative and Financial Reports submitted and accepted in accordance with PCA and respecting UNEP deadlines. Engagement with the mid-term review consultant has begun and planning for country interviews and feedbacks are well underway. A plan has been developed for post project sustainability. | HS |
| Outcome 1: Systematic assessments of existing technical capacity in country using recent documentation and surveys of 14 PICs and regional institutions including SPREP, SPC- /SOPAC, USP, and consultations to facilitate endorsement by the SPREP Meeting of regional environmental targets & indicators. | 1. Completed National and regional baseline assessments Endorsed environmental indicators | Existing Regional and National Sustainable Development Documents. MEA reporting requirements and national reports National MDG Report. NCSA Reports: Stocktake Reports, Thematic Assessments, Prioritization and Planning Reports, and NCSA Action Plans and Strategies. SoE reports for Fiji, Cooks Islands, Republic of the Marshall Islands and Samoa. Pacific Environment and Climate Change Outlook Report. State of Conservation in Oceania. | Completed National and regional baseline Assessments Recommended environmental indicators endorsed by the SPREP Meeting | Endorsed environmental indicators incorporated into design of environment databases | Technical Assessment of Country Data Needs and Gaps, including indicators has been completed for all of the countries, for use in indicator-based reporting. In-country technical assessment took place in Kiribati (March 2019) and Vanuatu (June 2019), the current EMISs status were evaluated and compared to the national environment portal. The way-forward is under-development. A formal working relationship has been established with the Pacific Data Hub (SPC) and the Inform Project (SPREP). Core National and Regional indicators finalized and adopted by SPREP Senior Management Team. Countries now use these core indicators in the national SoE/NEMS processes. Initial trials are ongoing in PNG, Tuvalu, the Regional SoE and the Reporting Tool. | S |
| Design national and regional databases and network to facilitate monitoring the state of the Pacific’s environment. Assess the UNEP National Indicator Reporting Information System (IRIS) as the data collection, sharing and SoE reporting tool. | 2. National and regional database design available for use by 14 PICs | UNEP Live National Reporting Toolkit MEA Reporting Templates National Reporting Requirements | Work completed with UNEP to adapt national indicator reporting information system for regional applications. | National and regional databases active and networked. | Final configuration was presented, reviewed and formally endorsed during the Steering Committee Meeting in September 2018. IRIS assessed as incompatible with country needs and alternative reporting tool developed. Based on country input, the Inform project has developed a more user-friendly interface for the revamped Reporting Tool which will be launched and trialled by all country representatives during the Inform regional meeting August 2019. The indicator reporting tool was fully developed by the Inform project team and the final code library will be made available and open source on Github. This software will be tested in the Pacific and it may be useful to any other country with indicator base reporting including SDG reporting. | S |
| Guidance on data management and sharing protocols at national and regional levels (including data ownership & sharing, compatibility with existing national & regional systems.). | 3. National protocols for environmental data management and sharing agreed within each of the 14 PICs. Regional data sharing protocols agreed by SPREP Meeting. | No overarching national protocols exist National Protocols exist for some sectors. National Protocols developed but not used. Some regional Protocols developed within existing regional institutional (CROP agency) arrangements. | Draft National Protocols prepared. Conceptual diagram of national to/from regional data / database prepared. Regional Framework and Protocols recommended for SPREP Meeting endorsement. | Guidance on data management and sharing protocols available for use in 14 PICs. Regional data management and sharing protocols endorsed and in use. | Gaps identified. Legal consultancy on data ownership and sharing requirements finalized. Outputs: Access License Agreements, Definition of License Types, Policies on Data Sharing, MoU templates (Ministry to Ministry, SPREP to Country), User Guide on Data Licenses. PNG has tailored the data policy for national use and is using the MoU template for inter-agency data sharing. This model will be promoted to other PICs. In addition, SPREP has adopted its first organization wide data sharing policy based on the Inform project’s outputs. SPREP has shared its approved data policy with other Council of Regional Organisations in the Pacific (CROP) agencies for their information use. | S |
| Outcome 2: Assess, strengthen and monitor existing legislation, protocols, policies, and procedures that govern data collection & management for MEA reporting in PICs | 1. National assessment reports published with recommendations for strengthening legislation, protocols, policies, and procedures for data collection & management. | Some countries have specific data reporting requirements in their legislation but majority have no specific requirements and framework for data collection and management. | National assessment reports on legislation, protocols, policies, and procedures for data collection and management completed. | Recommendations from national assessment reports addressed through the project. | The project has provided in-country advisory training on data cleaning, sharing and analysis protocols and procedures. Inform has also provided a workflow guidance from field data collection through validation and use. In addition, the project has built capacity in mobile data collection to support standardized field data collection and management. The project has supported the development of a regional data sharing policy (SPREP data policy) and the PNG environment data sharing policy. The data portal enforces data sharing permissions based on the developed licences. The Inform project has built awareness around the need for data sharing as well as made available draft policies, MoUs and an open data discussion paper. | S |
| Establish and strengthen the institutional network of environmental data management agencies & organisations at the national and regional levels. | 2. Number of assessment report recommendations addressed (from output 2.1.1). Number of national agencies and organizations engaged with national and regional networks | None of the countries has an established network of environmental data management agencies and organisations. Current condition to be verified by output 2.1.1 | National Planning and Statistical Offices fully engaged and leading the implementation of the project. At least 5 countries have a functioning national network for environmental data management. | Replication in remaining 9 countries. All 14 PICs contributing to regional environmental data management. | The Inform project has introduced and promoted the use of its data sharing policies to ensure environmental data is available and accessible to relevant government ministries. Include progress in engaging Statistics and national planning offices There are over 100 registered data providers in the network of national portals. However only about a quarter are regularly active, primarily from environment departments. 12 of the 14 countries have varying levels of activity in their national network for environment data management. | S |
| Monitoring guidelines developed and agreed for the capture of data for all national & regional environ-mental indicators. | 3. Number of environmental indicators with monitoring guidelines | Most have no national guidelines but use inter-national guidelines or those of developed countries. Limited sectoral guidelines exist in various forms and conditions from country to country. | Priority environmental indicators identified, and monitoring guidelines drafted and piloted for use in the region. | Monitoring guidelines for data acquisition for all priority environmental indicators developed and available for national adoption. | A core set of 33 regionally endorsed national indicators has been developed including indicators for the waste cluster, biodiversity cluster and the climate change. Guidelines in the form of methodologies have been developed and are currently being utilized and refined. Indicators are in use in both the regional SOE and the PNG SOE as well as all proposed SOES for a later 2019/2020. | HS |
| Develop tools & approaches to assist countries to implement and monitor & report to MEAs, RIO +20 outcomes (the future we want), SAMOA pathway and SDGs including through a web-based system & offline options. | 4. Tools and methods to monitor& report on MEAs, RIO +20, SAMOA Pathway and SDGs. Web based reporting system available. | Countries reporting on MEAs to Conventions’ secretariats | Tools developed to monitor progress for MEAs, RIO +20, SAMOA Pathway, and SDGs including a web based system. | Tools and web-based system used in all 14 PICs for reporting. | A new more user-friendly version of the Reporting tool finalized in June 2019. Launch and first trial by stakeholders planned during Regional Meeting (August 2019). The indicators in the reporting tool are mapped against national reporting requirements, regional reporting requirements, MEA reporting requirements and SDGs. | S |
| Identify equipment, software and hardware needs for each country and purchased to enable establishment of national environment database and network of data providers. | 5. Number of PICs for which national equipment, software & hardware needs have been addressed and resolved. | NCSA Reports. Lessons learned from national SoE reports for Samoa, Fiji and the Cook Islands and Republic of the Marshall Islands. | Equipment, software and hardware needs identified, and necessary purchases made. | All 14 PICs have functioning national environment databases and networks. | Hardware equipment and software needs assessed; procurement process finalized. Inform workstations procured for the 14 countries: 11 countries have received a workstation; all countries expected to receive workstation in 2019. Data portal and reporting tool hosting procured and managed for all countries. One server procured for Samoa based on national needs. | S |
| Train relevant Government staff to use the indicator reporting information system and web-based templates for integrating SoE and NEMS with national MEA commitments drawing from national environ-mental reporting (including SAMOA Pathway, Rio + 20 outcomes, and SDGs). | 6. Staff trained on the use of the indicator reporting information system and web-based templates for MEA reporting. | Countries are not using web-based templates. Countries reporting in PDF format, often through consultancies. | Web-based templates developed for trial. Government and other stakeholder staff trained in template use and have provided feedback on functionality. | Web-based templates used for national and MEA reporting requirements. | National regional state of environment reporting template developed and available for use. Tonga, FSM, PNG and Solomon Islands are currently using the national SOE template and a regional SOE is being developed with the regional template. In 3rd quarter 2019, a new, more user-friendly version of the Reporting tool will be launched. This will be the online standardized template for future use. | S |
| Develop & provide training for collection of national environment statistics and SoE Reporting templates for each country. | 7. SOE reporting template developed for each PIC (including SAMOA pathway, Rio + 20 outcomes and sustainable development goals). | SoE templates exist for 3 countries (Samoa, Fiji and the Cook Islands and Republic of the Marshall Islands). | SoE report formulation and template training provided for all 14 PICs. | SoE reports available for all 14 PICs. | SoE template developed by the ACPMEA 2 project and its use and refinement will be further supported by the Inform Project. Indicator based reporting including environmental statistics underway in, Federated States of Micronesia, PNG, Solomon Islands, Tonga and at the regional level. | S |
| Develop and provide training for NEMS which integrate national MEA commitments and draw from national environ-mental reporting. | 8. NEMS developed integrating national MEA commitments (including SAMOA pathway, Rio + 20 outcomes and sustainable development goals) and drawing on national SoE reports. | NEMS drafted for 2 PICs. | NEMS drafted for 7 PICs. | NEMS drafted and endorsed for all 14 PICs. | Similar to the SoE, NEMS training and capacity building were initiated under the ACPMEA2 project and the Inform Project built on it for Solomon Islands, FSM, PNG and Tonga. NEMS status: Complete and awaiting approval for Niue. In process and awaiting completion: Tonga, Solomon Islands, FSM, | S |
| Develop and provide training on EIA protocols and procedures based on regional Environment Impact Assessment (EIA) guidelines as well as EIA monitoring protocols that may contribute data that could be integrated into national environmental databases. | 9. EIA protocols in use and producing data for national environmental monitoring. | EIA protocols exist in some PICs, with various level of use, but don’t include guidance on collecting reliable data to contribute to environmental monitoring. | EIA monitoring protocols developed and trialled in 4 PICs. | EIA monitoring protocols in use and contributing to environ-mental monitoring in all 14 PICs. | National enforcement capacity building through the EIA process is a core function of SPREP. EIA training and support being implemented across the region, specific support in Nauru, and Vanuatu, Tuvalu, Solomon Islands, FSM, Kiribati. | S |
| Effective management and delivery of project, meeting agreed measurable output and outcome indicators. | 10. Approval inception report, annual workplan and budget, and the annual progress reports. Establishment of PMU. | SPREP’s strategic plan. SPREP annual workplan. | Inception report. Quarterly progress and financial reports. Steering committee report(s). | Terminal evaluation report. Audit report. Lessons learned and best practice report. | All reporting, both narrative and financial, are up to date. Project indicators are being tracked and are on pace for successful delivery. Capacity building is being tracked using the GEF capacity building scorecard. Progress against all metrics shows a positive trend. Notable indicators include establishment of national data portals, development of reporting tool, in-country engagement and capacity building. | HS |
| Project monitoring and evaluation methodology designed to align with GEF project & operating standards, including regular project audits. | 11. Inception Workshop completed. Evaluation Reports (Mid-Term and/or Terminal Evaluation). Project reports to Project Board. Asset Register. Site inspection by UNEP. | No project in place | Inception workshop report, Mid-Term Evaluation Report Up to date Asset Register. | Audit Report Terminal Evaluation Report. | Project Monitoring and Evaluation undertaken at regular intervals. Mid-term Review (MTR) consultant engaged and fully supported by the Inform project. National evaluation conducted on a regular basis and input used to improve future delivery. | S |
| Develop communication & visibility materials for education and awareness. | 12. Public awareness raised through educational campaigns and communication | Public knowledge of individual MEAs made possible through previous and existing GEF projects. | First round of communication materials produced and distributed. | Communication materials and public awareness campaign fully implemented. | Engagement with major audiences on all levels is an integrated part of the project, (including ministerial level, technical officer level, donors and public). Project Communication strategy developed. Notable outputs: brochures, briefs, graphics, videos, email blasts, webpage, online data stories, social media, banners, promotional material, stakeholder surveys. At least two informed communication products have been picked up and re-published on the IISD, SDG knowledge hub. | HS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating | FY2019 rating | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | In the second year of implementation since the Inception Workshop, the Inform project gained momentum in the Pacific region through the deployment of 14 national data portals and a consolidated regional portal managed by the EA (SPREP). The project has rolled out an active communication strategy through diverse products, which has enhanced visibility. Therefore, it is on track to deliver the overall results in a satisfactory manner provided that ownership by countries and longer-term sustainability are adequately addressed in the second half of the project. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Project implementation is well underway |  |
| on stakeholder engagement | The risk of low stakeholder engagement has been reduced through active engagement by the inform project team activities that result in high level support for the project. This includes ministerial briefings and the use of multiple communication channels including formal and informal medians including social media. National champions have been identified who serve to motivate their national colleagues as well as project counterparts in other countries during south-south exchanges. |  |
| on sustainability of results | A sustainability plan has been developed and will be submitted to the steering committee for approval and input |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implementation as of 30 June 2018 | Implementation as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| (copy & paste from approved Results Framework) [activities may be included for reference, but the rating should focus on output delivery] |  |  |  |  |  |
| Output 1.1.1: Systematic assessments of existing technical capacity in-country using recent documentation and surveys of 14 PICs and regional institutions including SPREP, SPC/SOPAC, USP, and consultations to facilitate endorsement by the SPREP Meeting of regional environmental targets and indicators. | 2019 | 80% | 100% | National capacity assessed and delivery modality agreed upon by member countries. SPREP meeting 2018 endorsed the data portals and indicators. | HS |
| Output 1.1.2: Design national and regional databases and network to facilitate monitoring the state of the Pacific’s environment. | 2020 | 60% | 80% | National data portals developed and deployed. National data portals networked at the regional level inside the Pacific environment portal. In-country Capacity building is ongoing. Monitoring and reporting on the state of environment is completed in Fiji, Samoa, Niue, Cooks, RMI and Palau. Underway in 5 countries FSM, Tonga, Solomon Islands, Tuvalu and PNG. National indicator reporting tool developed and refined, implementation planned for 4th quarter 2019,2020. | HS |
| Output 1.1.3: Regional SoE assessment indicators selected and agreed for use in national and regional databases. Baseline information for agreed variables established for each PIC and the region. | 2021 | 25% | 70% | Regional indicators agreed upon and endorsed by SPREP members, including all participating countries. Indicators built in to reporting tool and in use in current SOEs. Baseline data collected and stored in data portals for 6 countries with the additional 8 underway. | S |
| Output 1.1.4: Country consultations lead to agreement on a framework and protocols on how the databases will work at national and regional levels (including data ownership and sharing, compatibility with existing national and regional systems, and other issues that may arise). | 2021 | 40% | 60% | A suite of legal and policy documents has been developed and provided to countries. This includes a template MOU for sharing between ministries, three license agreements that have been tailored for the pacific context, a template environment data policy and a discussion paper on national freedom of information acts. An organisational data policy has been established at SPREP, which governs data management on behalf of countries. Individual consultations underway. Integration with existing national and regional systems underway. Regional data sharing established between SPREP and SPC. | S |
| Output 1.1.5: Databases validate through iterative trialling, and quality control initially in 4 pilot countries before replicating in the remaining target countries, and at regional level. | 2019 | 90% | 100% | Databases and quality control process tested in 4 countries. Validation and quality control methodology rolled out to all participating countries. | S |
| Output 2.1.1: Rapid assessment of existing legislation, protocols, policies, and procedures that govern data collection and management for MEA reporting in PICs. | 2018 | 100% | 100% | Rapid assessment of existing legislation and protocols conducted. For Pacific island countries have freedom of information or open data acts or policies. | S |
| Output 2.1.2: Strengthen legislation, policies and procedures for planning and reporting at the national and regional levels. | 2021 | 40% | 60% | Draft data sharing agreements, data license agreements and data policies have been developed and provided to members. Tailoring of these products is underway. Behaviour change in data sharing is undertaken during the SOE process and is also underway. | S |
| Output 2.1.3: Monitoring guidelines developed and agreed for the capture of data for all national and regional environmental indicators. | 2020 | 25% | 75% | Monitoring guidelines developed as part of each indicator. Guidelines and indicators agreed upon at SPREP meeting in 2018. | S |
| Output 2.1.4: Establish data collection guidelines and data sharing protocols to facilitate effective use of data for planning and decision making and ensure these processes generate relevant information. | 2021 | 25% | 50% | Data sharing protocols and communication products to support decision making have been developed and are being applied during national reporting activities. There is evidence of use of relevant information in both funding applications and national prioritisation of relevant issues. | S |
| Output 2.1.5: Develop tools and approaches to assist countries to implement and monitor RIO +20 outcomes (the future we want) and SAMOA pathway and SDGs. | 2021 | 40% | 60% | Environmental data portals, indicators and the indicator reporting tool have all been tailored to support tracking the RIO +20 outcomes, Samoa pathway and relevant SDG’s. | S |
| Output 3.1.1: Identify national capacities for indicator development and managing national data through a web-based system and offline alternative options. | 2019 | 80% | 100% | National capacity for indicator development and managing national data assessed. Web based data hosting identified as the preferred option for the Pacific region. | HS |
| Output 3.1.2: National and regional training and capacity building carried out to address: - Data collection - Data capture - Database management, including ongoing maintenance - Data analysis and reporting - End-user interpretation, including SoE formulation and reviews Train relevant staff on the use of the web-based tools including national minimum environment indicators interface. | 2021 | 25% | 60% | National and regional capacity building underway with all participating countries. Progress is occurring at a faster rate with countries who are developing SOEs currently. Capacity building is a central component of the project and will continue through the project’s completion. There is evidence of increased competence in data management throughout the region, however much work remains to be done to ensure sustainability. | S |
| Output 3.2.1: Train relevant Government staff to use the web-based templates for national and regional levels and for individual PIC MEA reporting needs | 2021 | 10% | 25% | The web-based indicator reporting tool has been designed and modified to suit user requirements. Testing in one pacific Island country, Cook Islands took place in 2018. The results of the testing led to the redesign. Implementation of the indicator reporting tool plan for 4th quarter 2019. | S |
| Output 3.3.1: Relevant staff trained on the methodology for analysing the required information which meet the necessary national and regional reporting, forecasting and planning requirements. | 2021 | 25% | 60% | National officers trained and involved in the data analysis process for national and regional reporting to be used in planning processes at the national level. This is an ongoing activity; capacity building will take place throughout the life of the project. | S |
| Output 3.3.2: Develop and provide training for SoE Reporting templates for each country and establish links SoE links to MEA reporting, national planning and policy development (Including reporting on SAMOA pathway, Rio + 20 outcomes and sustainable | 2021 | 25% | 75% | SoE Reporting template developed, published and capacity building in the use of the templates underway. Indicators used for the SoE have been mapped to all relevant reporting requirements including MEA’s and SDG’s. | HS |
| Output 3.3.3: Develop and provide training for NEMS which integrate national MEA commitments and draw from national environmental reporting and EIAs (including SAMOA pathway, Rio + 20 outcomes and sustainable development goals). | 2021 | 25% | 60% | The process to integrate national environmental reporting into NEMS has been developed. A training modality for this integration has been rolled out and with the state of environment reporting process. | S |
| Output 3.3.4: Develop and provide training on EIA protocols and procedures based on regional EIA guidelines as well as EIA monitoring protocols which feed into national Environmental database | 2021 | 10% | 25% | EIA protocols and procedures developed, capacity building underway. The Solomon Island instance provides the best evidence of use. In the Solomon Islands EIA documents are stored and shared with the public for public consultation through the national data portal. | MS |
| Output 3.4.1: Facilitate PICs in meeting their national and MEA reporting requirements by providing training on the use of databases to generate reports. | 2021 | 20% | 40% | Indicator based reporting for national and MEA requirements established. Capacity building is underway and integrated with the state of environment reporting process. | S |
| Output 3.4.2: Improved data management and availability of data for MEA planning, monitoring and reporting | 2021 | 50% | 75% | Data management at the national and regional level has been improved and improvements will continue throughout the life of the project. Explicit links to MEAs and SDGs are being established to relevant datasets. Over 5,000 datasets and documents that were previously undiscoverable or hard to find are now online and available for national use. | HS |
| Output 4.1.1: Project monitoring and evaluation methodology designed to align with GEF project and operating standards, including regular project audits. | 2021 | 25% | 50% | Project monitoring evaluation underway and aligned to GEF project standards. Audits conducted on an annual basis. Audits so far have been unqualified. | S |
| Output 4.1.2: Mechanisms in place to enable regular synchronization and rationalization of systems and personnel involved at national and regional levels based on a well-designed M&E system. | 2021 | 25% | 50% | National project focal point and relevant staff are well integrated into project delivery and a two-way flow of communication has been established. Project steering committee, TOR developed and improved. Steering committee meetings held on an annual basis. Workplan and budget approved by Steering committee. | HS |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating | FY2019 rating | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | HS | In the second year of implementation since the Inception Workshop, the Inform project gained momentum in the Pacific region through the deployment of 14 national data portals and a consolidated regional portal managed by the EA (SPREP). The project has rolled out an active communication strategy through diverse products, which has enhanced visibility. The project management team has done an excellent job in accelerating implementation progress of outputs and reporting back to the IA in a timely and responsive manner. The delivery of outputs has been commendable especially in view of the complex nature of the project with 14 participating countries. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc.).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Data portal sustainability. The current condition is no standardised data management culture or tools. The risk is that without a shift in culture and process, the tools may be under-utilized and therefore, unsustainable. Low use and low demand may result in lack of support for continuation. | Work continuously with all identified stakeholders and their partners to make full use of the tools provided for their intended purposes and other associated processes and outputs. 2019 update - Regular country contact, capacity building, demonstrated use has taken place to reduce this risk. A sustainability plan is underdevelopment. | Inform Project Team, SPREP staff, National focal points | 2020 |
| Political support for data sharing and data use, particularly inter-agency, varies between countries. Where support is not explicit, or strong, this poses a risk to access to data and comprehensive datasets needed for environmental reporting. In some cases, there may be gaps in data that are reflective of a political or institutional blockage and not an actual data gap. | Work continuously with decision makers to raise awareness and promote the benefits of the collaborative approach and tools being produced by the Inform project. 2019 update – PNG has adopted an interagency MOU as a mechanism to formally open data flow processes and this modality will be promoted in other PICs. | Inform Project team, SPREP EMG, National focal points | 2021 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Lack of cross-sectoral communication and coordination between agencies | The project uses existing coordination mechanisms at national and regional level. These mechanisms have been there for some time and are linked to national legislation or national priority programmes. Where coordination is weak, the project will strengthen it. | The project has taken an advantage of existing environment sector coordination bodies such as CMAC in RMI which includes all relevant agencies to coordinate multi sector inputs. In countries that do not have existing coordination mechanisms the state of environment process has served to pull together relevant stakeholders. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Changing policies, laws, and regulations may be difficult or time-consuming | Awareness campaigns and information generated during this project and pro-actively fed back to the countries via the existing EA country networks plus the projects should enable better understanding of the issues and need for adoption of proposed policy and law changes | Many of the project countries have data sharing practices that are functioning but not formalised while for the countries, Palau, FSM, Vanuatu and PNG, have formal open data policies. The project has taken an ad hoc approach to developing new policies and has met with limited challenges thus far. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Small environment departments with multi responsibility and high staff turnover | Set up a national data management network that is part of national planning and national statistics framework incorporating non-government and academic stakeholders. Ultimately facilitate collection and management of national environmental statistics by national statistics offices. | Implementation of the project has taken a collaborative and supportive approach particularly with smaller departments and has insured that the time savings aspect of the project has been highlighted. Explicit links to program and other project delivery have been made. For example, the R2R project required an environmental database to be developed and the informed projects national data portals were able to be used as this database in some cases, Nauru. | CEO: H |
|  |  |  | TM: H |
|  |  |  | PM: M |
| Key personnel lost from key institutions and stakeholder groups | Three Sub-regional co-coordinators, funded by the project will oversee the project requirements for hardware, software, data collection, and training for an assigned group of 3-5 PICs. Robust, well-documented management systems will be established. | The Inform Project implementation has taken a decentralised approach to data use and data management; a number of staff within each ministry of environment have been trained to use the data portal and the indicators for the environmental reporting. Thereby reducing the risk of a single key staff leaving the department. Both the tools and the processes put in place by the project have low barriers to entry and are intuitive to use. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: L |
| Unforeseen financial pressure due to current economic climate | All financing has been agreed and committed with all partners. However, the value of local co- financing relative to GEF funding will be unavoidably affected by exchange rate fluctuations. Strengthened financial safeguards in SPREP. | SPREP financial safeguards have been strengthened additional resourcing has been identified and allocated to project outputs, for example UNDP CCCD project 150k. Currently expenditures and deliverables are on track for successful delivery. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | Overall the project is a low risk, mainly due to strong government support, close working relationships with national officers, the regionally perceived need for this project and the well-functioning project management unit at the EA. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Project Implementation was delayed by approximately one year with the Inception meeting being held November 2018 while the formal project start was January 2017.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

SPREP Data Policy link: https://www.dropbox.com/sh/0hprf69s60pindm/AADstmd-J1ix4pL56kUZ31wxa?dl=0

Indicators link: https://www.dropbox.com/sh/kuwj7vbexmogmkg/AADDZ-NpIjXB4VxMO-uZxxqHa?dl=0

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)