UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5197 | Umoja no.: SB-000689.07 |
| --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | 5197: Increase St. Lucia's capacity to monitor MEA implementation and sustainable development |  |
| Duration months | Planned |  | 48 months |  |
|  | Extension(s) |  | 30 June 2021 & 18 months added |  |
| Division(s) Implementing the project |  |  | Science Division (Formerly DEWA), Climate Services & Capacity Building Unit, Capacity Development & Innovations Branch. |  |
| Executing Agency(ies) |  |  | Govt. of St. Lucia: Ministry of Sustainable Development, Energy, Science and Technology - Sustainable Development and Environment Division |  |
| Project Type |  |  | Medium Size Project |  |
| Project Scope |  |  | National |  |
| Region (delete as appropriate) |  |  | Latin America and Caribbean |  |
| Names of Beneficiary Countries |  |  | St. Lucia |  |
| Programme of Work |  |  | 2018-2019; UNEP SP7 EA(a)(ii) |  |
| GEF Focal Area(s) |  |  | Multi Focal Area |  |
| UNDAF linkages |  |  | Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes. This project contributes to the first and second outcome of the fourth priority area of the 2017-2021 United Nations Multi-Country Sustainable Development Framework (UN MSDF) in the Caribbean: 2017-2021 Caribbean UN MSDF, Priority 4: A Sustainable and Resilient Caribbean Outcome 1: Policies and programmes for climate change adaptation, disaster risk reduction, and universal access to clean and sustainable energy in place Outcome 2: Inclusive and sustainable solutions adopted for the conservation, restoration, and use of ecosystems and natural resources |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Although this GEF CCCD project has been designed to create enabling environment and enhance the implementation, monitoring and reporting of all SDGs with an environmental dimension, majority of the project interventions primarily contribute to the following SDGs, targets and indicators: SDG 13 (13.b.1); SDG 15 (15.3.1,15.9.1); SDG 16 (16.10.2); and SDG 17 (17.16.1; 17.18.1) |  |
| GEF financing amount |  |  | USD 1,000,000 |  |
| Co-financing amount |  |  | USD 1,080,000 |  |
| Date of CEO Endorsement |  |  | 7 January 2015 |  |
| Start of Implementation |  |  | 30 September 2015 |  |
| Date of first disbursement |  |  | 28 December 2015 |  |
| Total disbursement as of 30 June |  |  | USD 725,353.50 |  |
| Total expenditure as of 30 June |  |  | USD 509,077.00 |  |
| Expected Mid-Term Evaluation Date |  |  | MTR completed in November 2018 |  |
| Completion Date |  | Planned | 31 December 2019 |  |
|  |  | Revised | 30 June 2021 |  |
| Expected Terminal Evaluation Date |  |  | 31 December 2021 |  |
| Expected Financial Closure Date |  |  | 30 June 2022 |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Insert the Subprogramme(s) and biennia of the PoW to which the project contributes 2018-2019 UNEP SP7 EA(a) (ii | Specify the relevant Expected Accomplishment(s) & Indicator(s) Insert the Sub-programme’s Expected Accomplishment(s) and Indicator(s) to which the project contributes SP7 EA(a): Governments and other stakeholders use quality open environmental data, analyses and participatory processes that strengthen the science-policy interface to generate evidence-based environmental assessments, identify emerging issues and foster policy action SP7 EA(a)(ii): Increase in the number of countries reporting on the environmental dimension of sustainable development through shared environmental information systems with country-level data made discoverable through UNEP |
| --- | --- |
| The project is contributing to the increase in the number of countries reporting on the environmental dimension of sustainable development in the Caribbean region and has been instrumental to consolidate partnerships and collaboration among key stakeholders, including UN agencies and programs active in the country. In addition, the project is contributing to the adoption of an integrated approach to implement the 2030 Agenda for Sustainable Development and has accelerated the endorsement of governance arrangements to enhance data sharing and coordination. The National Environmental Information System (NEIS) was launched in 2018 by the Minister for Education, Innovation, Gender Relations and Sustainable Development. The NEIS includes a Common Data Storage Facility (CDSF), which serves seventeen (17) public and private agencies who have agreed, through the signing of a Memorandum of Understanding (MoU) to collaborate and co-ordinate institutional agreements for sharing environmental information and data in Saint Lucia. The CDSF serves as a supporting and foundational tool for reporting on MEAs and the translation of data into useful and actionable information. Relevant data and information now available for use by MEA Focal Points and other users for policy and decision-making. The NEIS was specifically developed for Saint Lucia and is designed to provide MEA Focal Point Ministries and other users with data and information for reporting on the state of the environment under the United Nations Convention on Biological Diversity (UNCBD), United Nations Framework Convention on Climate Change (UNFCCC) and United Nations Convention to combat desertification (UNCCD). The achievement of the goals and objectives related to the MEAs’ indicators will be based upon data and information managed through the NEIS. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
| NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] This project contributes to the first and second outcome of the fourth priority area of the 2017-2021 United Nations Multi-Country Sustainable Development Framework (UN MSDF) in the Caribbean: 2017-2021 Caribbean UN MSDF, Priority 4: A Sustainable and Resilient Caribbean Outcome 1: Policies and programmes for climate change adaptation, disaster risk reduction, and universal access to clean and sustainable energy in place Outcome 2: Inclusive and sustainable solutions adopted for the conservation, restoration, and use of ecosystems and natural resources Operationalizing sustainable development and resilience strategies for Saint Lucia requires managing and evaluating complex interrelationships between environmental, social, and economic objectives. One of the Project’s output (National Environmental Information System) NEIS, greatest strengths is to function as an effective mechanism for information exchange to help inform Saint Lucia decision making pertaining to strategy design and implementation. Developing the necessary national and sub-national strategies for meeting MEA goals are being coordinated through participatory and iterative processes encompassing situation analysis, formulation of action plans, supporting the development of policies and legislations, implementation, monitoring and follow-up evaluation. The NEIS can be strategic for clearly communicating relationships of data on established benchmarks of key national and/or local parameters necessary for helping planners identify problem areas, establish objectives, set priorities, review strategy options, and assist with carrying out simulations. The NEIS can be used to compare benchmark data and scenario results against future monitoring and evaluation of actual processes, outcomes and impacts of implemented strategies. The status and findings of strategies and local phenomenon can then be used to feed into MEA indicator reporting. This information can be shared across the region as multi-agency partnerships are at the core of the Project’s strategies and mode of operations, and it therefore establishes and maintains a number of collaborative arrangements that are critical to the performance of the project’s objectives and the delivery of outcomes |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | SDG 13 (13.b.1); SDG 15 (15.3.1,15.9.1); SDG 16 (16.10.2); and SDG 17 (17.16.1; 17.18.1) SDG 13 13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities 13.b.1 Number of least developed countries and small island developing States that are receiving specialized support, and amount of support, including finance, technology and capacity-building, for mechanisms for raising capacities for effective climate change-related planning and management, including focusing on women, youth and local and marginalized communities Operationalizing sustainable development and resilience strategies for Saint Lucia will require managing and evaluating complex interrelationships between environmental, social, and economic objectives. One of the National Environmental Information System (NEIS) greatest strengths is to function as an effective mechanism for information exchange to help inform Saint Lucia decision making pertaining to strategy design and implementation. Developing the necessary national and sub-national strategies for meeting MEA goals will be a coordinated, participatory and iterative process encompassing situation analysis, formulation of policies and action plans, implementation, monitoring and follow-up evaluation. The NEIS would be strategic for clearly communicating relationships of data on established benchmarks of key national and/or local parameters necessary for helping planners identify problem areas, establish objectives, set priorities, review strategy options, and assist with carrying out simulations. The NEIS could then be used to compare benchmark data and scenario results against future monitoring and evaluation of actual processes, outcomes and impacts of implemented strategies. The status and findings of strategies and local phenomenon could then be used to feed into MEA indicator reporting. Achieving the full use of the EIS would require the national and sub-national government authorities of Saint Lucia to implement institutional policies and frameworks for encouraging all necessary agency and department stakeholders participate in the use of the NEIS. SDG 15 15.3 By 2030, combat desertification, restore degraded land and soil, including land affected by desertification, drought and floods, and strive to achieve a land degradation neutral world 15.3.1 Proportion of land that is degraded over total land area Presently, the NEIS contains data on coverage of protected areas and forest land cover information. However, there is more relevant information the NEIS could house. The NEIS could become a tool for monitoring the health of dryland forests and track specific attributes regarding land cover quantity and quality trends over time. The tropical dry forest of Saint Lucia is largely comprised of scrub forest characterized by a short canopy and a large number of small-diameter trees. The similarity of soil properties between short-stature scrub forest and relatively undisturbed dry forest suggest that repeated disturbance, rather than edaphic properties, is a major influence on forest composition and structure within the dry forest zone of Saint Lucia. Information on these types of characteristics could be tracked in the NEIS. Furthermore, Saint Lucia’s coastal dry forests, especially in the North East Coast, are increasingly destroyed for tourism development, with exact rates that could also be measured and disseminated via the NEIS. Saint Lucia’s dry forests provide ecosystem services which provide inputs into the production of key sectors in the Saint Lucian economy. Such ecosystem services include water, soil fertility, pollination, pest control, growth and reproduction of food species, storm mitigation, climate regulation, biological waste assimilation The NEIS could also help planners engage with private property owners for the purpose of having them adopt afforestation and forest conservation measures. A key challenge right now for Saint Lucia is that over 40% of forests are located on private lands, limiting the Government’s ability to address deforestation, which is more of an issue in private land holdings. Through local government technician observation and data input into the NEIS, government administrators could target properties and engage with owners on the impacts related to deforestation and encourage them to participate in conservation programs; raising owner awareness about impacts to drinking and recreational water quality, loss of biodiversity and threats to nearshore fisheries. From a public sector perspective, conflicting goals may arise, for example between economic development and environmental protection. The country’s dry season and coastal area low water regimes coincide during prime tourist season. Where the maintenance of planted green spaces for tourist attraction (e.g. forest conservation) require heavy water consumption, at such a critical time this may contribute to water scarcity and aridification (potentially exacerbated by climate change).13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities 15.9 By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts 15.9.1 Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011–2020 Data and information collected by the project were utilized to develop Saint Lucia’s 6th National Review for production of the UNCBD NBSAP report SDG 16. 16.10.2 Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements Saint Lucia’s Environmental Management Bill (Draft 2018) incorporates legislation for the sustainability and use of the National Environmental Information System. The Department shall - (a) oversee the creation and maintenance of a National Environmental Information System as part of a Government Information Service or as an independent service, (b) facilitate the collection, collation and analysis of environmental data and information as is necessary to achieve the purposes of subsection (2). (c) train and equip public and private sector and civil society representatives in the use of Saint Lucia’s National Environmental Information System to facilitate data collection, sharing and indicator-based reporting on International Environmental Agreements. (2) The National Environmental Information System must: - ensure the right of access to environmental information; - ensure that, as a matter of course, environmental information is progressively made available and disseminated to the public; - improve environmental management and inform environmental decision-making; - facilitate the evaluation, monitoring and reporting of environmental compliance; - improve the collection, exchange and use of environmental data; and - support environmental research and development. - be available online to the greatest extent practicable. Moreover, under the continued support of this GEF and other donor funded environmental projects in St. Lucia, MoE spearheaded the development and adoption of the Country’s Open Data Policy, which provides a framework for advancing open data services and thus encouraging accountability in the provision of government services. State actors and all environmental partners are now encouraged and able to access, download, analyses and share/ publish multi-sectoral data and information products through the St. Lucia’s government Open Data Portal, specifically developed to operationalize this policy. SDG 17.16.1 17.16 Enhance the Global Partnership for Sustainable Development, complemented by multi-stakeholder partnerships that mobilize and share knowledge, expertise, technology and financial resources, to support the achievement of the Sustainable Development Goals in all countries, in particular developing countries 17.16.1 Number of countries reporting progress in multi-stakeholder development effectiveness monitoring frameworks that support the achievement of the Sustainable Development Goals The project has been working to strengthen the coordination between different institutions to mobilize and share knowledge, expertise and data to support the achievement of the Sustainable Development Goals. SDG 17.18.1 17.18 By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts 17.18.1 Proportion of sustainable development indicators produced at the national level with full disaggregation when relevant to the target, in accordance with the Fundamental Principles of Official Statistics The NEIS is a coordinated and collaborative effort to enhance reporting capacity of the Country. NEIS will be instrumental for the co-produce indicators that will be co-produced by across different entities in St. Lucia. This capacity will increase data coordination and quality with all the necessary characteristics and disaggregation. Different capacities have been strengthened to collect, produce and disseminate environmental information. Serve as a one-stop-shop and searchable portable for high quality information to efficiently complete compliance reports on MEA implementation. In this regard as well, the NEIS can be used by Civil Society Organizations (CSOs) to track indicators of their interests and collaborate with technical officers in Government to come up with strategies to reverse negative trends. The establishment of the NEIS is a stepping-stone towards the achievement of the Department of Sustainable Development’s long-term outcome — “Enhanced application of Science, Technology and Innovation for National Socio-economic Development and Environmental Management across all sectors”. The NEIS was launched by the Minister for Education, Innovation, Gender Relations and Sustainable Development in an official ceremony on 7th August 2018. The NEIS includes a Common Data Storage Facility (CDSF), which serves seventeen (17) public and private agencies who have agreed, through the signing of a Memorandum of Understanding, to collaborate and co-ordinate institutional agreements for sharing environmental information and data in Saint Lucia. The CDSF serves as a supporting and foundational tool for reporting on MEAs and the translation of data into useful and actionable information. Relevant data and information now available for use by MEA Focal Points and other users for policy and decision-making. The NEIS was specifically developed for Saint Lucia and is designed to provide MEA Focal Point Ministries and other users with data and information for reporting on the state of the environment under the United Nations Convention on Biological Diversity (UNCBD), United Nations Framework Convention on Climate Change (UNFCCC) and United Nations Convention to combat desertification (UNCCD). The achievement of the goals and objectives related to the MEAs’ indicators will be based upon data and information managed through the NEIS |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR |  |  |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | HS |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. Increasing capacity to monitor and report on Saint Lucia's MEA objectives required initiatives helmed by multiple Ministries, Departments, and Agencies; all providing multiple intersecting datasets. A key factor was the alignment of data with GEF indicators related to the objectives of the UNCBD, UNFCCC and UNCCD. Training workshops have been held for targeted agencies focused on the three (3) environmental conventions listed covering how information needs, and challenges in access to information influence environmental conventions agreements; in negotiating such agreements and monitoring the implementation of the same Currently, which the NEIS and the CDSF are operational, their uses are being streamlined across Ministries and Agencies in Saint Lucia. A consultancy firm has been retained by the Government of Saint Lucia to help mainstream the use of the Better appreciation of the link between planning for, collection of and use of data in development planning and implementation monitoring This was one of the most observable accomplishments from the project. A series of data management presentations and repetitive application of these skills during working sessions has led to significant skills improvement. Officers/workshop participants were able to recite and apply the steps to manage and upload data to the CDSF. They were also able to see the need to collaborate in building relational data bases between various departments in the Ministries. Working in teams across sectors to formulate and map indicators at the national and sub-national levels As stated before, low data quality affected the formulation of complex indicators in the workshop. Because of this there was no dataset integration between departments to formulate indicators. Persons in their teams, however, were able to see how they can use each other’s data to improve their own data quality and analysis of complex environmental issues in their sectors. This applied to data at both the national and sub-national levels in the country. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. Key progress to 2018: The project achieved better coordination of environmental information management and reporting on 3 MEAs. The Common Data Storage Facility and Environmental Information System has had a significant progress and it is in final stages. The Information Management Training was conducted, and reports are now available. The project completed the Mid Term Review (MTR) in2018 Key progress to 2019: Significant contributions have been produced as a result of the gap assessments. There has been a significant progress on national policy assessments and recommendations and institutional arrangements are part of current negotiations. Through the coordination with different stakeholders and institutions a clear attribution of responsibilities per organization on data collection and management has been identified and the common data storage facility is being updated. Negotiation simulation exercises were also hands-on experiences on the need to prepare well for negotiations on environmental issues, and significant alliances have been developed. The consultancy being done is also aimed at the application of the NEIS in the areas of sustainable development at the national level and the development of State of the Environment Scenarios with data (not limited) from the CDSF and reports from the NEIS. It is evident that stakeholders continue to be genuinely committed and engaged in environmental monitoring within their agencies. It should also be acknowledged that the persons who attend workshops were suitable and at the required levels of responsibilities to contribute to the process of reporting on the obligations of the MEAs. Notwithstanding, the knowledge gap between participants was substantial. While some individuals had previous experience and familiarity with the subject areas and concepts, others did not have any previous exposure or background knowledge of the topics. This was particularly evident in the workshops on GIS, Environmental Indicator Development, and Vulnerability and Adaptation Assessments. Until now, priority environmental data gaps are identified, and plans developed to address them. The only activity missing is the development of plans to address institutional needs which is still in progress and is expected to be finalized by 2020. In the case of the online platform for sharing and presenting available information on SD and MEA indicators, data collection strategies are being undertaken across relevant agencies. In the case of M&E the project has been conducting continuous activities and identifying necessary adjustments. Progress reports, evaluations reports and consultancies reports will be prepared following completion of these M&E activities. A number of outreach campaigns have been conducted during 2019 and a final Communication strategy is being developed during this year. There were two notable changes to the participation rate at capacity building trainings compared to that during the Phase I training. Participation rate by Agencies/ Departments was over 90%. Over twenty (20) persons more attended the workshops than had originally indicated intention to do so. The second difference is that the general gender split of participants across all workshops was on average 37% male to 63% female compared to 22% male to 78% female during the Phase I training. This is an improvement the Department will continue to encourage. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L-M | L-M | L-M |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 Improved understanding of the layout and use of the CDSF and NEIS The layout and potential uses of the Common Data Storage Facility (CDSF) and the National Environmental Information System (NEIS) were discussed during a number of presentation sessions in targeted stakeholder workshops. The system layout was explained which set the foundation for working with the platforms. By the end of the workshops, participants better appreciated how the data from multiple Departments could help improve planning at all country levels. Importantly as well, workshop participants saw how the NEIS could be used to show their own departments achievements in their areas of environmental management in the country. Improved ability to formulate indicators and upload suitably structured data on the CDSF and visualize it on the NEIS Presentations on the formulation of indicators were done in the areas of: Land Degradation, Social Development, Biodiversity and Climate Change. At the beginning some officers were looking at their datasets not knowing how to transform them into meaningful trends related to these themes. By working with these persons, eventually everyone began seeing ways to transform their data into simple trends to which their data related. Because of the low quality of the data more complex indicators could not be developed. Data was uploaded then visualized. Data formatted by agencies were visualized. The Project’s Webmaster/Administrator for the CDSF and NEIS is oriented on monitoring the implementation of the plan developed to populate the CDSF and NEIS, thereby increasing the value of the platforms as a tool for development planning in Saint Lucia. The Webmaster/Administrator had a firsthand introduction to the CDSF and NEIS during sectoral testing and training workshops; the promise and limitations of the platforms and technical challenges moving forward. A number of software and website design issues will be resolved before the data uploading plans could be implemented. |  |  |  |  |  |

| Stakeholder engagement | The PMU has utilized many opportunities to present and display the NEIS in various media, meetings of various agencies and workshops. The following represents a list of public awareness and education activities conducted during this period: - Project Overview and NEIS/CDSF Presentation at National Biodiversity Strategy and Action Plan (NBSAP) Consultancy Meeting (July 13, 2018) - Participation in stakeholder consultations for information gathering sessions for Saint Lucia’s Sixth National Report (6NR) to the Convention on Biological Diversity (October 16, 2018) - Community Engagement Presentations on the NEIS and relevance for Saint Lucia becoming signatory to the Regional Agreement on Access to Information, Public Participation & Access to Justice on Environmental Matters – ESCAZU Agreement (August to September 2018) - Booth Display and Presentations to General Public during GEF- SGP People’s Knowledge Fair (December 10 & 11 2018) - Presentation on NEIS at Decade of Research and Innovation Consultation Meeting (December 12, 2018) - Booth Display and Presentations to Schools at OECS Climate Change Exhibition during Regional Nationally Determined Contributions Forum held in Saint Lucia (October 8-12) - Contributions to stakeholder meeting for the Review of SAMOA Pathway Mid-term Report (November 13) - Presentation at Private Sector Engagement Meeting on Climate Change (November 20, 2018) - Contributions to Environmental Management Bill for Saint Lucia – NEIS given consideration as part of Legislation for Climate Change and Environmental Management Bill (September 26 & 27 2018) - Primary and Secondary Schools Sargassum Awareness Campaign (May 2019) - Sharing good practices for the implementation of MEAs at Regional Workshop on progress and challenges in the implementation of the Escazu Agreement in LAC: towards an early entry into force, ECLAC, Chile (April 2019) - Established a partnership with the Mona Geoinformatics Institute from the University of the West Indies - who designed the current St. Lucia’s NEIS system and even featured the NEIS in one of their transformative stories titled ’Sargassum to Systems – Environmental Reporting Gets a Boost in Saint Lucia’ - Continued engagement with the ‘The Civil Society Organizations Coalition for Sustainable Development in Saint Lucia. The organization also published a story about the NEIS on their website: Making Saint Lucia’s National Environmental Information System (NEIS) work for you [section will be uploaded into the GEF Portal] |
| --- | --- |

| Gender mains-streaming | The remaining activities particularly the Information Management Training Phase 2 and NEIS Mainstreaming workshops paid closer attention to facilitate a greater gender balance in participants selected. However, the final nominations for participants are of the purview of each Agency and not the project. The gender gap in Stakeholders’ participation has greatly improved from Phase 1 of Information Management Training where 78% of participants were female and 22% Male to Phase 2 now having 56% female and 42% Male participation. 2% of participants chose to not be Gender classified. Mainstreaming of NEIS workshop also showed improved gender balance with 43% Male participation and 57% Female participation (see Fig. 1 below). Moreover, the project undertook the Mid-Term Review (MTR) in November 2018, which also reviewed the project interventions towards the promotion and actualization of human rights and gender equity measures in the country. Page 23 of the MTR report summarizes these measures as below. “4.7.4 Responsiveness to Human Rights and Gender Equity: There are no Human Rights, Gender or Youth related results in the project. However, the project supports reporting on the UNCBD and thereby Saint Lucia’s NBSAP implementation, which has a focus on gender, particularly women, and youth and vulnerable groups and will therefore need to collect the respective disaggregated data (see chapter 4.2 “Strategic Relevance”). A core indicator identified for the UNCCD is “Status and changes of Poverty and Inequality Levels” which relates to SDGs 5 “Achieve gender equality and empower all women and girls”. Component 3, through the Communication Strategy, also plans to engage women, girls and boys and vulnerable groups (and will therefore need to develop the respective indicators and targets). The project team consists of female staff only (the majority of DSD staff are female). A good gender balance is kept among contractors/ consultants and the PSC membership. The collection of gender disaggregated data and the monitoring of these wherever appropriate is mentioned in the ToRs of the project team. Training targets in the Logical Framework are capturing gender dimensions. The first Information Management training attracted more female than male participants. Recommendations on how to achieve better gender balance during the second training phase have been received from the training consultant”. [section will be uploaded into the GEF Portal] |
| --- | --- |

| Knowledge activities and products | Administrative, operational and management staff levels were made more aware of the importance of collecting data relating to the environment. Training workshops were targeted specifically at addressing capacity limitations at the systemic, institutional and individual levels to achieve effective implementation of MEAs and environmental management initiatives. This was aligned to the Government’s efforts to allow decision makers to have access to environmental information based on valid data, in order to inform decision-making. Through this effort, over 150 persons from sixty-two (62) agencies, inclusive of the public, private sectors and civil society organizations have received certified training at the basic, intermediate and advance levels in data analysis, monitoring and evaluation, understanding convention methodologies, communicating environmental information and risks, information management, conducting vulnerability assessments and development of environmental indicators. As a result of these interventions, institutions are showing a willingness to cooperate and share their data. This is as a result of the establishment of systematic groups, where we have established train the trainer’s networks so that trained personnel take back information to their local agencies and offer internal agency training and support. List of training manuals created during the considered reporting period - NEIS General User Manual - NEIS Administrator Manual - Common Data Storage Facility User Manual - Environmental Information Training Manual (Module 1: Geographic Information Systems; Module 2: Research Methods and Techniques; Module 3: Environmental Indicators Development; Module 4: Conducting Vulnerability and Adaptation Assessments; Module 5: Metadata and Statistical Analysis - Demonstrating the Use of the EIS in Saint Lucia Training Manual The Information Management Training (IMT) Workshops Phase 2 involved hands-on exercises on the topics covered. This approach led to the intended reinforcing of the workshop content through review and discussions on actual projects in the workshop participant's portfolio rather that the workshops being set in a theoretical abstraction. Originally, an estimated sixty (60) persons were scheduled to be trained in total across all the workshops. There were changes to this plan with persons applying to attend the classes late in the process and responding late to the invitation to attend. In the end, eighty-one (81) persons attended the training sessions. Briefs on the proceedings of each workshop are as follows: 3.1 Module 1. Introduction to Geographic Information Systems (GIS): This workshop lasted three (3) days and transferred GIS skills to twenty-one participants from fourteen (14) agencies. Some participants had previous GIS training/ work experience, but most of the participants had never been trained in GIS. Because of this, the course curriculum, in terms of the application of GIS, was ambitious for the group as a whole and adjustment had to be made as the course proceeded, and as the participants’ grasp of the material was observed. Strong aspects of the method of the workshop were repetition of the previous day’s concepts, individual hands-on work, end-of-day assignments for all participants, and a constant focus on making them aware of key practical points and thinking about a workflow of data input – processing – map making in a GIS. The training objective was to introduce participants to the fundamental concepts of GIS. And to familiarize participants with GIS (open) software (QGIS) by hands-on experience and help them develop basic skills related to data input into GIS, coordinate systems, map projections, database management, and spatial data models and operations. 3.2 Module 2. Research Methods and Techniques: This 2-day workshop covered the basic concepts of research methods. The first day focused on defining a research topic, reviewing the literature on the research topic and defining/refining the research question. Workshop participants were encouraged to choose a topic that was relevant to the work, department or project. Throughout the first day, participants refined their research topic iteratively by reflecting on existing literature and discussing with their peers. At the end of day one, six discussion groups had formed and produced a set of 27 possible research questions. The workshop facilitator provided feedback on the research questions over the evening, and the questions were further refined in Day 2. 3.3 Module 3. Environmental Indicators Development: This 2-day workshop consisted of brief lectures followed by group-based exercises. The first exercise probed participants to think about their understanding of indicators and the use of indicators in Saint Lucia. Following the first exercise, participants were divided into six working groups, water, climate change, waste management, ecosystem services and natural resources. Working groups developed a Communication Strategy for communicating the relevance and value of Environmental Indicators. Through a brief lecture, participants were introduced to the composite indicators and used the Global Footprint website. Through an exercise, participants calculated their own footprint. The participants also found data from the database on Saint Lucia’s biocapacity and footprint and compared it to other countries in the world. This practice exercise got participants thinking about access to data and how to use an unknown database for the first time. Furthermore, participants learned about the DPSIR framework and applied the framework to their case study trying to find indicators that measure these components. In the second day, participants were presented with information about global sustainability institutions including the three MEAs that are the focus of the project. Following a review of critical information about MEA Indicators, the participants returned to the previous days exercise of identifying indicators relevant for the DPSIR framing of their case study. Participants then applied the EEA Typology to understand their indicators gaps. The primary output for the workshop was groups were able to produce a preliminary Indicator Framework which included a set of indicators for both DPSIR elements and linkages, identification of gaps based on the EEA typology and identification data sources to develop the indicators. The Indicator Frameworks were presented to the larger group. Groups identified several challenges with the Indicator Framework. Challenges included the complexity and challenges of identifying suitable indicators, availability of data or lack of data, outdated data and lack of a centralized location of data. Overall, only one group of participants identified data from the Open Data platform, while two groups were using recently established NEIS database in Saint Lucia. It was evident from the workshop that both platforms have limited data to date and need additional data to support indicator development and use in Saint Lucia. 3.4 Module 4. Conducting Vulnerability and Adaptation Assessments: This 2days workshop covered the basic concepts and practical steps for gathering data to conduct vulnerability assessments, evaluating its accuracy and relevancy, and applying it for adaptation planning and resource management. On the first day, the workshop focused on establishing a conceptual framework and a clear understanding of the topics since a significant number of participants did not have previous knowledge on this particular area. In that sense, they learnt the definitions of key concepts including, for example, “Risk,” “Resilience,” “Adaptive Capacity,” “Adaptation Planning,” amongst others. They were also exposed to common internationally recognized practices and methodologies to conduct vulnerability and adaptation assessments. The day closed with a discussion on vulnerability and adaptation metrics and identifying practical strategies to deal with uncertainty and pitfalls. On the second day, a number of international case studies on vulnerability assessments and adaptation planning were explored. A scenario simulation exercise was used as a strategy to engage participants in developing a vulnerability assessment for Saint Lucia in which they had the opportunity to practice computational skills, to recognize the complexities and challenges that are inherent to the process (e.g. lack of certainty, lack of data, stakeholder engagement, etc.), to balance cost and benefits, and to share knowledge and experiences. A number of case studies were used in the classroom as vehicle to demonstrate the usefulness of MS Excel, Power Query, Pivot Tables, and Visual Basic as alternative, low cost tools to conduct vulnerability assessments. Following this discussion, participants were invited to form small groups and create their own case study for vulnerability assessment scenario simulation. As part of this exercise, they defined a scenario, set multicriteria for evaluation, estimated the scenario with different data inputs, and presented the result of their simulation to the rest of the class by using data mining techniques and probabilistic inference. After completing this workshop, all participants have significantly improved their ability to critically analyze vulnerability assessments and to effectively identify the most appropriate measures, policies, and strategies that can be implemented to minimize the negative impacts of a phenomenon. 3.5 Module 5. Metadata and Statistical Analysis: This training workshop took place over the course of two (2) days of intense workload. In the first day, basic concepts and definitions related to metadata were presented to participants. Some of the areas discussed include metadata standards, types of metadata (descriptive, structural, and administrative), methodologies for standardizing metadata, and best practices. Participants learnt and put into practice a number of strategies and methodologies to deal with metadata creation, metadata distribution, and data discovery in the semantic web. Procedures for geo-data online dissemination were also explored. At the end of the lecture, the focus changed into identifying and analyzing some of the main metadata problems and limitations that are visible to online users. Other topics touched upon by the workshop included statistics in ecology and conservation, uncertainty in science and implications for decision-making, modeling processes and techniques, study and sampling design, ethics and diversity in metadata, big data management, and statistical analysis. A first exercise required participants to analyze real data sets with the software tools introduced to them in order to prepare them to understand and develop a brief technical report on metadata and information management. 3.6 Selected Persons for Knowledge Sharing: One of the objectives of the training workshops was to identify persons with the aptitude for and grasp of the concepts presented such that they could assist with guiding other staff if called upon to provide guidance. These persons could therefore serve in the capacity of trainers of junior staff to continue capacity building in the area of monitoring MEAs in Saint Lucia. In working with the groups in the various workshops, interacting with the participants and observing the group dynamics in the in-class exercises, persons were identified by the workshop facilitators who could perform these roles. These persons were selected based on their levels of engagement in the classes, contribution to group work, demonstration of leadership, prior knowledge in the subject areas, levels of interest in the subject matter and willingness to share their knowledge with others. In each case separate discussions were held with the persons identified and their agreement solicited, in so far that, if called upon by the Department of Sustainable Development, they could join working sessions to contribute to the monitoring of MEAs in the country. [section will be uploaded into the GEF Portal] |
| --- | --- |

| Stories to be shared | A culture of information management and use is being created. Inter-agency agreements facilitate formal collaborations and public and private sector access and interest in data for use in development planning breaks the silos that have characterized the public service system. The open sharing of critical environmental data, accessibility to the NEIS, Saint Lucia’s Open Data platform and other platforms by the general public are elements that will take information sharing to a new level in Saint Lucia. Posting on Saint Lucia’s EIS by Coalition of Civil Society Organization: http://saintluciacsocoalition.org/uncategorized/making-saint-lucias-national-environmental-information-system-neis-work-for-you/ Posting on Saint Lucia’s EIS on International Open Data Day online showcase: https://data.govt.lc/showcase News article published on both UNEP and GEF websites titled ‘Paradise found: Saint Lucia preserving beauty through data and policy action’: (a) UNEP https://www.unenvironment.org/news-and-stories/story/paradise-found-saint-lucia-preserving-beauty-through-data-and-policy-action (b) GEF https://www.thegef.org/news/paradise-found-saint-lucia-preserving-beauty-through-data-and-policy-action Above story featured on the UNEP’s 2018 Annual Report: https://www.unenvironment.org/annualreport/2018/chapter-07-environment-under-review.php?fbclid=IwAR2_-xxLyUi182-hnXGj_M34jOuwWjbWp3qTMnC1EgsLwwqW80Q1noTKSD0 Ecosystem based and other news articles published by the Mona GeoInformatics Institute (MGI) and the Blue Coastal Dynamics Modelling Laboratory at the University of the West Indies: - Mona Geoinformatics Institute (MGI) Revolutionises Environmental Reporting for Saint Lucia: http://www2.monagis.com/content/mgi-revolutionises-environmental-reporting-for-saint-lucia - Sargassum to Systems – Environmental Reporting Gets a Boost in Saint Lucia: http://blue.monagis.com/sargassum-to-systems-environmental-reporting-gets-a-boost-in-saint-lucia/ Various online articles by the St Lucia Ministry of Sustainable Development - National Environmental Information System (NEIS) portal: https://www.neis.govt.lc/#/ - Saint Lucia launches National Environmental Information System (NEIS): https://www.stlucianewsonline.com/saint-lucia-launches-national-environmental-information-system-neis/ - Strengthening environmental management in Saint Lucia: http://www.govt.lc/news/strengthening-environmental-management-in-saint-lucia - Saint Lucia launches its Open Data website: https://data.govt.lc/story/saint-lucia-launches-its-open-data-website Online blog posting and news reports by the VP (The Voice) and ST online News portals of St. Lucia: - https://thevoiceslu.com/2018/08/saint-lucia-launches-national-environmental-information-system/, - https://www.stlucianewsonline.com/department-of-sustainable-development-formally-engages-agencies-for-cooperation-on-environmental-information-management-in-saint-lucia/ , - https://www.stlucianewsonline.com/17-agencies-to-sign-memorandum-of-understanding-for-cooperation-on-environmental-information-management-in-saint-lucia/ \ [section to be shared with communication division/ GEF communication] |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress ratings |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1.1: Coordination of environmental information management is agreed and piloted in MEA reporting | 1. Coordinated MEA reporting in place for at least the Rio Conventions | 0 | Enhanced inter-agency coordination system leads to common approach for MEA reporting | MEA reporting system in place (at least for the Rio conventions) | Project documentation and reporting for UNCBD, UNCCD and UNFCCC. Where there is increased sectoral overlapping agencies share existing information and increased coordination/inclusion in all meetings/workshops/discussions on data collection among relevant agencies | HS |
| Outcome 1.1.1: Inter-agency agreement on information management are concluded, involving at least 7 agencies and/or research institutions | Number of agencies involved in inter-agency agreement | No formal arrangement in existence | 3 agencies formalize agreements | At least 7 agencies conclude agreements | Memorandum of Understanding signed between 17 agencies | HS |
| Outcome 1.1.2: Reporting system for MEA implementation is applying above agreements and is being used for reporting to at least 3 MEAs | At least 7 organizations contribute to reporting, at least for the Rio Conventions, through the EIS | 0 | MEA reporting system is agreed upon by the different agencies | MEA reporting system is functional as a part of the EIS | Project report highlights existing data gaps for MEAs reporting and responsible agencies for data collection processes. MEA focal point agencies (7) are contacted regularly to provide indicator-based data to upload to current common data storage facility to be utilized by EIS | MS |
| Outcome 1.2: Environmental Information System and online platform operation | 1. EIS established, incorporating the coordinated MEA reporting system | 0 | Project documentation highlights process of selection of key technology and design decisions made based on a review of different alternative approaches. System specifications and selections made by Technical Sub-committee of technical experts from the agencies representing the Project Steering Committee | EIS tested and online platform operational as of August 7th 2018 | The NEIS is fully operational and accessible to the 17 agencies as it provides a common data storage facility for data and information sharing. | HS |
| Outcome 1.2.1: Set of core sustainable development and environmental indicators for the national level is developed, where appropriate coherent with relevant regional and global indicators | 1. Set of core SD and environmental indicators is established, in line with international guidance and standards | Uncoordinated data collection, analysis and reporting | Set of Indicators developed | Indicator framework agreed by relevant stakeholders in Saint Lucia | Core Sustainable Development and Environmental Indicators Report developed for Saint Lucia with feedback and approval by Inter-agency Working Group of Cabinet approved SDGs Coordinating Committee. This provides a more coordinated approach to SDGs reporting for Saint Lucia that was utilized to assist with Saint Lucia’s Voluntary National Review for SDGs Implementation and SDGs Audit Report | HS |
| Outcome 1.2.2: National and regional information sources are mapped relating to priority D and MEA indicators | Plan of existing national data and information sources for priority SD and MEA indicators | No consistent overview of data availability and locations | Mapping exercise concluded |  | Mapping of National and Regional Environmental Indicators to Information Sources Report developed providing linkages to existing and new sources of data & information for MEAs reporting | S |
| Outcome 1.2.3: Priority environmental data gaps are identified, and plans developed to address them | Gap assessment completed | 0 | Gap assessment | Plans developed on how to fill the gaps | Data Gap Assessments with recommendations on how to fill gaps technical report developed. MEA focal points for UNCCCD & UNCDB has consulted reports to provide useful guidance in reporting | HS |
| Outcome 1.2.4: Online platform established, for sharing and presenting available information related to SD and MEA indicators | Online platform for EIS operational and prepared for long-term maintenance | 0 | Online platform developed | Platform operational | Public and private access available for online platform at www.neis.govt.lc and the governments Open Data portal. Data available for analysis and download | HS |
| Outcome 1.3: National stakeholders are able to use environmental information for planning, project development and environmental management | 1. Number of agencies and organizations contributing to environmental information management; | 0 | > 5 organizations | ≥ 10 organizations | To date all agencies signed onto MOU have contributed data and continue to develop capacity to understand importance of reporting by indicators. | MS |
|  | 2. Number of agencies that use EIS information for planning | 0 | > 5 organizations | ≥ 10 organizations | This will be surveyed after the scenario processes being facilitated in September 2019 | MS |
| Outcome 1.3.1: Different stakeholder groups trained to utilize information in planning and project development, and at least 3 initiatives prepared to test the information system in different sectors | Number of individuals trained Number of different stakeholder groups trained | 0 | Training tools developed | 10 different entities and 100 persons trained 3 sectoral EIS tests prepared | Training manuals developed 150 persons from 47 agencies and organizations trained to date 3 sectoral tests: climate change, biodiversity, and land use conducted | HS |
| Outcome 1.3.2: M&E system for environmental management developed | Results-based M&E system operational | 0 | M&E system developed | Recommendations developed on integrating M&E system into existing management procedures | Evaluation surveys and reports presented to Project Steering Committee Members. M&E system recommended for incorporation into Department’s Strategic Plan | S |
| Outcome 1.3.3: Project monitoring system operating, providing systematic information on progress in achieving project outcome and output targets | Project M&E system operational |  | Project M&E system established | Reporting on track; output and outcome achievements are captured | Consistent quarterly progress reports to Project Steering Committee includes M&E reports | HS |
| Outcome 2.1: Increased human and institutional capacity to use environmental science and information to guide development planning | 1. Measurable increase in the use of environmental assessment tools for planning and decision-making |  | > 2 assessment tools referenced in planning processes | ≥ 5 assessment tools referenced in planning processes | Impact, Risk and Vulnerability Assessment Report developed for 3 sectors (climate change, biodiversity and land desertification) | S |
| Outcome 2.1.1: Measurable increase in the capacities of govt agencies to conduct impact, risk and vulnerability assessments, using tools, methodologies and data available on various data platforms | Number of officers from different agencies trained in assessment tools |  | Training developed and 20 officials trained | At least 50 officials from different agencies trained | Post training evaluation report highlights 38 officials trained from 14 agencies | S |
| Outcome 2.1.2: A range of relevant stakeholders trained in the use of assessment finds for policy development and land use planning, and at least 3 initiatives prepared to test the information system in different sectors | Number of different stakeholders and groups trained |  | Training modules developed and 5 organizations/30 persons trained | At least 10 organizations/60 persons trained At least 3 sectoral initatives prepared | Training manual developed 38 persons from 14 agencies trained 3 sectoral initiatives prepared: climate change, biodiversity, land degradation | HS |
| Outcome 2.1.3: National, participatory scenario process conducted focusing on priority environmental issues and integrating environmental, social and economic information | National scenario exercise completed |  | Scenario development tools disseminated and related workshop held | Scenario (s) developed based on national priority issues and EIS data | Scenarios currently being developed, and related workshop scheduled for September 17-20 2019 | MS |
| Outcome 3.1: Public knowledge of and participation in the collection and use of environmental information increased | 1. Measurable increase of public contribution to the environmental information system |  | Public participation opportunities developed | Members of the public are contributing information on ≥ 1 priority environmental theme(s) | Strategies currently being developed with communications plan to be completed by August 22, 2019 | MS |
| Outcome 3.1.1: Stakeholders (incl. CSOs, CBOs, NGOs and govt agencies) trained in the use of the IES and at least 3 initiatives prepared to test the system in different geographic areas | EIS trainings conducted and tested |  | Training content developed | At least 200 persons from a range of different stakeholder groups trained At least 3 tests initiated | To date 150 persons have received training. Additional sessions scheduled for September and November 2019 | HS |
| Outcome 3.1.2: An initiative developed for public provision or validation of environmental information on priority indicators | Public engagement initiative in place, covering both online and direct involvement |  | Development of public engagement strategy with govt agencies and public leaders | Initiative launched and tested; information access points established | Consultancy to developed public engagement strategy in initial stages (Contract signed on July 1, 2019 for 5 months). Stakeholder engagement workshop including public leaders scheduled for September 23 – 26 2019 | MS |
| 3.1.3: Public awareness programme conducted on the NEIS | Communications and outreach strategy in place and media campaign conducted |  | Outreach strategy in place | Different channels utilized to communicate EIS to public inclusive of print, electronic media, town hall meetings etc | Consultancy to developed public engagement strategy in initial stages (Contract signed on July 1, 2019 for 5 months). NEIS publicized in various media | S |
| 3.1.4: An initiative where regional CCCD projects can share experiences and lessons learnt |  |  |  | Lessons learnt report | New initiative planned implementation date of December 2019 | MS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | HS | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. Overall, the project has achieved most of the expected results. A vast majority of Targets set for the end of the project seem to be easily achievable as a result of an effective management of the project by the PMU. Most of the activities have been considered between satisfactory and highly satisfactory based on the main results described for each component. In some cases, activities evaluated as marginally satisfactory have faced administrative delays, which have been addressed by the TM and the PMU. This information provides the rationale for the Development Objective Rating in Section 2. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - Change of coding and template for financial reporting caused delays in submission of reports and risk of needed funds being late therefore stalling project planned activities and procurement - Original budget for procurement of consultants insufficient | - “Learning as we go” approach with assistance from UNEP representatives on correct coding and classifications, - Revision of budget to accommodate cost of consultants. - UNEP to organize a financial and administrative training for the PMU |
| on stakeholder engagement | - Challenges in obtaining pertinent information (data & feedback on stakeholder activities) in timely manner from focal points - Stakeholders report time allocated for trainings are insufficient - Gap was discovered between farmers who may be illiterate and ability to rely on/navigate NEIS | - More face to face meetings and onsite visits to personally collect necessary data and information to offset email response waiting period - PMU recommends more sharing of training and skills obtained with colleagues within organization. PMU also remains available to facilitate additional one on one trainings upon request - Communications Strategy workshops in efforts to bridge gap at grassroots’ level |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results | Continuation of data uploading and system maintenance beyond project life | - Efforts have been made to have system uploads be done by assigned officers within agencies - Training and regular group sessions being arranged for data contributors and curators - NEIS link included on open data portal which directs all users to the source of environmental data - Inclusion of environmental monitoring an EIS in Environmental Management Legislation and Department’s Strategic Plan |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implementation status as of 30 June 2018 | Implementation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.) | Progress rating |  |
| --- | --- | --- | --- | --- | --- | --- |
| Output 1: (1.1.1) Inter-agency agreements on information management are concluded, involving at least 7 agencies and/or research institutes (key agencies to be specified during inception). |  |  |  |  | HS |  |
| Activity 1: Initiate assessments on data gaps and needs with regard to data per agency | June 2017 | 100% | 100% |  | HS |  |
| Activity 2: Develop recommendations on contributions of different agencies to the system based on their mandates and responsibilities | June 2017 | 100% | 100% |  | HS |  |
| Activity 3: Adopt/sign national policy, institutional arrangements and/or MoUs for cooperation on environmental information management | March 2018 | 100% | 100% |  | HS |  |
| Output 2: (1.1.2) Reporting system for MEA implementation is applying the above agreements (see 1.1.1) and is being used for reporting to at least 3 MEAs | November 2017 | 100% | 100% |  | HS |  |
| Activity 4: Conduct assessment of currently reported information against reporting requirements of at least the Rio Conventions (in close coordination with the assessment under Activity 1) | December 2017 | 100% | 100% |  | HS |  |
| Activity 5: Develop reporting system with clear attribution of responsibilities per organization on data collection and management | August 2017 | 100% | 100% |  | HS |  |
| Activity 6: Establish common data storage facility and decide on access and sharing modalities | December 2017 | 95% | 100% |  | S |  |
| Output 3: (1.2.1) Set of core sustainable development and environmental indicators for the national level is developed, where appropriate coherent with relevant regional and global indicators |  |  |  |  | HS |  |
| Activity 7: Establish Inter-Agency Working Group for joint indicator development | November 2017 | 100% | 100% |  | HS |  |
| Activity 8: Establish indicator framework (including list of indicators and methodological sheets) in line with national and, where appropriate, regional and global frameworks and building on past results and exercises | August 2017 | 100% | 100% |  | HS |  |
| Activity 9: Disseminate indicator framework amongst relevant stakeholder groups for feedback | November 2017 | 100% | 100% |  | HS |  |
| Output 4: (1.2.2) National and regional information sources are mapped relating to priority SD and MEA indicators |  |  |  |  |  |  |
| Activity 10: Undertake mapping of existing information sources (including govt., academia, non-govt.) | December 2017 | 100% | 100% |  | HS |  |
| Activity 11: Link additional and potential new sources with existing landscape (local, national, regional) | December 2017 | 100% | 100% |  | HS |  |
| Activity 12: Develop recommendations on how best to include these further sources into the indicator framework | December 2017 | 100% | 100% |  | HS |  |
| Output 5: (1.2.3) Priority environmental data gaps are identified and plans developed to address them |  |  | 100% |  |  |  |
| Activity 13: Undertake environmental data needs assessment | June 2017 | 100% | 100% |  | HS |  |
| Activity 14: Develop recommendations on addressing data gaps | June 2017 | 100% | 100% |  | HS |  |
| Activity 15: Develop plans to address institutional needs | June 2017 | 100% | 100% |  | HS |  |
| Output 6: (1.2.4) Online platform established, for sharing and presenting available information on SD and MEA indicators | May 2018 | 95% | 100% |  | HS |  |
| Activity 16: Compile data in an accessible and easy-to-use format by the relevant agencies | April 2018 | 30% | 50% | Data collection strategies being undertaken across relevant agencies | MS |  |
| Activity 17: Provide database management training for the contributing agencies and organizations | May 2018 | 80% | 100% |  | HS |  |
| Activity 18: Establish online EIS platform, including clear protocols for data provision, platform maintenance and access and sharing modalities | May 2018 | 90% | 100% |  | S |  |
| Output 7: (1.3.1) Different stakeholder groups (govt. agencies, NGO, local communities) trained to utilize information in planning and project development, and at least 3 initiatives prepared to test the information system in different sectors | April 2018 | 60% | 100% |  | S |  |
| Activity 19: Develop training modules on how to utilize EIS data for analysis and planning | April 2018 | 90% | 100% |  | S |  |
| Activity 20: Organize awareness raising sessions on the importance of environmental information management for decision makers in relevant sectoral ministries and in contributing agencies | June 2018 | 60% | 70% | Mainstreaming consultancy currently being undertaken activities scheduled for November 2019 | MS |  |
| Activity 21: Prepare initiatives to test the usefulness of the EIS for planning purposes in at least 3 different sectors | December 2018 | 60% | 100% |  | S |  |
| Output 8: (1.3.2) M&E system for environmental management developed |  |  |  |  | HS |  |
| Activity 22: Agree on a hosting agency and the potential changes to existing mandates. | December 2016 | 100% | 100% |  | HS |  |
| Activity 23: Define specific targets for environmental management in St. Lucia | December 2016 | 100% | 100% |  | HS |  |
| Activity 24: Establish a results-based monitoring and reporting framework for the targets defined under 22 (1.3.2.1) | March 2017 | 100% | 100% |  | HS |  |
| Activity 25: Agree upon reporting responsibilities, intervals and lines for monitoring achievements against established targets | September 2017 | 100% | 100% |  | HS |  |
| Output 9: (1.3.3) Project monitoring system operating, providing systematic information on progress in achieving project outcome and output targets |  |  |  |  | S |  |
| Activity 26: Refine and confirm project targets and indicators during inception phase (months 1-3) | November 2017 | 100% | 100% |  | HS |  |
| Activity 27: Establish results-based monitoring framework during project inception phase (months 1-3) | March 2018 | 100% | 100% |  | HS |  |
| Activity 28: Ensure continuous monitoring and reporting on project achievements at national and decentralized levels | December 2019 | 70% | 80% | M&E is a continuous activity. Progress reports, evaluations reports and consultancies report prepared following completion of activities | S |  |
| Output 10: (2.1.1) Measurable increase in the capacities of govt. agencies to conduct impact, risk and vulnerability assessments, using tools, methodologies and data available on various data platforms | August 2018 |  |  |  | S |  |
| Activity 29: Identify opportunities where EIS data and information can provide input to risk and vulnerability assessments and planning processes | December 2018 | 50% | 100% |  | S |  |
| Activity 30: Assess data and training needs | December2018 | 50% | 100% | Sectoral training needs and assessment done during Mainstreaming Consultancy and completed June 2019 | S |  |
| Activity 31: Agree on data sharing modalities and protocols | June 2018 | 100% | 100% |  | HS |  |
| Activity 32: Compile lessons learned on the usefulness of the EIS | December 2019 | 50% | 100% | Sectoral training needs and assessment done during Mainstreaming Consultancy and completed June 2019 | HS |  |
| Output 11: (2.1.2) A range of relevant stakeholders trained in the use of assessment findings for policy, development and land use planning, and at least 3 initiatives prepared to test the information system in different sectors |  |  |  |  | S |  |
| Activity 33: Identify stakeholder groups and training needs and opportunities | December 2017 | 100% | 100% |  | HS |  |
| Activity 34: Develop modules or modify existing training tools for the identified stakeholder needs | March 2019 | 60% | 100% | Sectoral training needs and assessment done during Mainstreaming Consultancy and completed June 2019 | HS |  |
| Activity 35: Conduct trainings, where appropriate jointly or in groups of relevant stakeholders | August 2019 | 60% | 70% | Mainstreaming Consultancy currently being undertaken. Additionally, training sessions scheduled for September and November 2019 | S |  |
| Activity 36: 3 Initiatives carried out to test the system by trained groups and relevant stakeholders | October 2019 | 50% | 100% | Sectoral training needs and assessment done during Mainstreaming Consultancy and completed June 2019 | S |  |
| Output 12: (2.1.3) National, participatory scenario process conducted focusing on priority environmental issues and integrating environmental, social and economic information |  |  |  |  |  |  |
| Activity 37: Convene workshop on scenario development tools, planning and delivery | Sept 2019 | 50% | 60% | Task 3 of Mainstreaming Consultancy currently being undertaken | MS |  |
| Activity 38: Define priority issues and information to feed into scenario development | December 2019 | 60% | 60% | Task 3 of Mainstreaming Consultancy currently being undertaken | MS |  |
| Activity 39: Develop scenario(s) | October 2019 | 50% | 60% | Task 3 of Mainstreaming Consultancy currently being undertaken | MS |  |
| Activity 40: Compile a State of the Environment Report based on EIS data and information and the scenario(s) | March 2019 |  |  | a State of the Environment Report was completed in 2015. It has been recommended that one done for Saint Lucia every 5 years. |  |  |
| Activity 41: Conduct outreach campaign with feedback opportunities, e.g. through town halls or community gatherings | December 2019 | 20% | 50% | Task 4 of Mainstreaming Consultancy currently being undertaken | MS |  |
| Activity 42: Decide on access and sharing opportunities for the scenarios to maintain relevance | August 2019 | 50% | 70%% | Task 4 of Mainstreaming Consultancy currently being undertaken. Scheduled for September 2019 with completion by December 2019 | S |  |
| Output 13: (3.1.1) Stakeholders (incl. CSOs, CBOs, NGOs and govt. agencies) trained in the use of the EIS and at least 3 initiatives prepared to test the system in different geographic areas |  |  |  |  |  |  |
| Activity 43: Establish training needs and opportunity assessment | March 2019 | 50% | 100% | Task 2 completed under Mainstreaming Consultancy June 2019 | S |  |
| Activity 44: Develop training modules and materials, where required specific to the targeted audience | May 2019 | 50% | 100% | Task 2 completed under Mainstreaming Consultancy June 2019 | HS |  |
| Activity 45: Conduct EIS trainings for different stakeholder groups | August 2019 | 50% | 100% | Task 2 completed under Mainstreaming Consultancy June 2019 | S |  |
| Activity 46: Define three different EIS usage areas and prepare testing its usefulness and appreciation by the respective target group | May 2019 | 50% | 100% | Mainstreaming Consultancy Task 2 completed June 2019 | S |  |
| Output 14: (3.1.2) An initiative developed for public provision or validation of environmental information on priority indicators |  |  |  |  | MS |  |
| Activity 47: Select one or more priority environmental themes with strong public interest | December 2019 | 60% | 60% | Communication Consultancy currently being undertaken | MS |  |
| Activity 48: Design a platform (online if possible) allowing the public to provide or validate information on these themes | December 2019 | 50% | 50% | Communications Consultancy currently being undertaken | MS |  |
| Activity 49: Train representatives of and multiplicators for the public on using the information platform | October 2019 | 50% | 60% | Task 2 to be undertaken September 2019 of Communications Consultancy | MS |  |
| Activity 50: Monitor the extent to which the platform is used | December 2019 | 50% | 50% | Task to be completed in December 2019 of Communications Strategy and Action Plan | MS |  |
| Output 15: (3.1.3) Public awareness programme conducted on the national environmental information system |  |  |  |  | S |  |
| Activity 51: Develop communication strategy | November 2018 | 70% | 90% | Stakeholder Consultation held for validation of strategy. Final Action Plan to be submitted August 2019 | S |  |
| Activity 52: Conduct outreach and awareness campaign on the EIS (through print- and electronic media, town hall meetings, community gatherings etc.) | December 2019 | 60% | 70% | A number of outreach campaigns being conducted along with different Government and CSO organisations | HS |  |
| Activity 53: Survey public awareness and opinion and adapt communication strategy where required | December 2019 | 50% | 50% | Currently planned as part of Communications Strategy and Action plan to be implemented December 2019 | S |  |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating | FY2019 rating | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Overall, the project implementation is moving on a fast pace. The execution of most of the activities included in the work plan is on track and consistent with the adopted timeline. Nevertheless, the relatively slow start of the project, due to changes to UN Environment financial processes (adoption of UMOJA) and changes in government administration and change of Ministry to Department of Sustainable Development, had produced a significant delay in the commencement of the activities, which eventually had forced the PMU to request an extension of the project duration through end of June 2021. Some challenges experienced by the PMU with the revision of the Budget and Work Plan and the submission of expenditure reports along with the relatively slow procedures to contract consultants have produced some slight delays in the execution of some activities. Over the last fiscal year, the TM has been addressing these issues, with frequent interactions with the PMU, which included thorough revision of financial reporting and revision of technical documents, in a common effort to expedite the execution (including reporting) of the project and accelerate spending rate. Some concerns remain around the quantity and quality of data being shared by key stakeholders through the NEIS. The TM is monitoring the situation and consulting with the PMU to identify and implement viable measures to stimulate and sustain data sharing using the NEIS. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc.).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Improve ability to formulate indicators and upload suitably structured data on the CDSF and visualize it on the NEIS | Further capacity building required in understanding environmental indicators | PMU | December 2019 |
| Data standardization | Work in teams across sectors to formulate and map indicators at the national and sub-national levels | PMU | September 2019 |
| Improve current system layouts and understandings of the limitations of the platforms. | Explore avenues for enhanced use and visualization of geospatial data through the NEIS. | PMU, Webmaster | August 2019 |
| Data collection from key agencies | Development of a plan to populate the CDSF and NEIS, thereby increasing the value of the platforms as a tool for development planning in Saint Lucia. | Webmaster | September 2019 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Lack of interest of relevant stakeholder groups | Awareness raising will provide all stakeholder groups with the necessary knowledge on issues and opportunities that lie within their active engagement in environmental management at all levels. Close engagement of non-governmental stakeholder groups (including local resource users and beneficiaries) will provide them with means to contribute to data gathering and assessment and to contribute to the development of environmental information management. The major incentive will be additional knowledge and skills to contribute to a better understanding of the environmental parameters that underpin their livelihoods. | Project updates and NEIS demonstrations are currently being undertaken at National Climate Change Committee Meetings, regional forums presentations and coordinated efforts for data management along with country efforts for ratification of the ESCAZU agreement. Additionally, project education and awareness being undertaken during inter-agency collaborations during World Biodiversity Day Awareness, GEF SGP Knowledge Fair and World Forest or Water Data activities being undertaken by agencies such as Forestry, Fisheries, and Sustainable Development Departments A regional forum for CCCD projects discussions in planning phase for December 2019 | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Lack of accord on data collection needs, format and methodology to collect, collate, and analyse data | Consensus-based development of data portal, information system and indicators. | Data training sessions planned for data curators and collectors in separate sessions. Plans to coordinate data challenges along with Central Statistics Office and the Public Service who both manages data web portals. Currently, a link across platforms with the open data portal exist where the public access to environmental data leads directly to the NEIS portal. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: M |
| CC-induced severe weather events delay or impede project completion. | The project will ensure that appropriate measures are taken to prevent and mitigate the possible impacts of extreme weather events on project implementation. The project will also link with ongoing disaster risk management initiatives to ensure that it provides additional information on ensuring that recovery and reconstruction programmes are undertaken in a sustainable and adapted way. |  | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating by the Project Manager |  |  | L/M |
| Overall Risk Rating by the Task Manager |  |  | L/M |

| FY2018 rating | FY2019 rating | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L/M | L | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below. The risk rating of the project decreased to Low. All Medium risks identified at CEO endorsement have been successfully addressed and mitigated by the project. Main stakeholders are actively involved in the project implementation and development of NEIS and indicators have been endorsed by an Inter-Agency Working Group. Risk related to Climate Change seems to be marginal to the remaining activities of the project implementation. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks

Gonzalez, Otto J., and Donald R. Zak. 1996. “Tropical Dry Forests of Saint Lucia, West Indies: Vegetation and Soil Properties.” Biotropica 28 (4): 618–26. https://doi.org/10.2307/2389048.

Ibid.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)