UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 5662 |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Defining and Demonstrating Best Practises for Exchange of Information on Chemicals in the Textile Products |  |  |
| Duration months | Planned |  | January, 2015 to June, 2017 |  |  |
|  | Extension(s) |  | 31st May, 2019 |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste Unit |  |  |
| Name of co-implementing Agency |  |  | N/A |  |  |
| Executing Agency(ies) |  |  | MEP-FECO: Foreign Economic Cooperation Office-Ministry of Environmental Protection of China |  |  |
| Names of Other Project Partners |  |  | UNEP Science and Knowledge Unit |  |  |
| Project Type |  |  | MSP |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | N/A |  |  |
| Names of Beneficiary Countries |  |  | China |  |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |  |
| GEF Focal Area(s) |  |  | POPs |  |  |
| UNDAF linkages |  |  | Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Where appropriate, insert the most relevant SDG target(s) and indicator(s) to which the project contributes |  |  |
| GEF financing amount |  |  | US$1,000,000 |  |  |
| Co-financing amount |  |  | 4,395,205 |  |  |
| Date of CEO Endorsement |  |  | 6th October,2014 |  |  |
| Start of Implementation |  |  | 31st December 2014 |  |  |
| Date of first disbursement |  |  | 31st December 2014 |  |  |
| Total disbursement as of 30 June |  |  | US $925,000 |  |  |
| Total expenditure as of 30 June |  |  | US $897,509.73 |  |  |
| Expected Mid-Term Date |  |  | N/A |  |  |
| Completion Date |  | Planned | June, 2017 |  |  |
|  |  | Revised | 31st May, 2019 |  |  |
| Expected Terminal Evaluation Date |  |  | January 2020 |  |  |
| Expected Financial Closure Date |  |  | December 2019 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Chemicals and Health Subprogramme | Specify the relevant Expected Accomplishment(s) & Indicator(s) |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] "a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM. |  |

For all GEF 6 and later projects: N/A

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | This project will identify and demonstrate practices which facilitate access to information on chemicals contained in textile products. The international community of chemicals policymakers and stakeholders has through UN ENVIRONMENT’s Strategic Approach to International Chemicals Management (SAICM) identified access to information on chemicals contained in products as a priority issue. The governing body of SAICM , the International Conference on Chemicals Management (ICCM) mandated UN ENVIRONMENT to develop a Chemicals in Products (CiP) programme that will facilitate the exchange of CiP information throughout product life cycles and for all major stakeholder groups. UN ENVIRONMENT is developing the CiP programme, which is generic to all product sectors: this project will pilot the CiP programme in the textiles sector. The project will strengthen and complement existing efforts promoting exchange of information on chemicals in products. The outcomes of this project will allow the textile industry to practice sound chemicals management and to take the appropriate measures to reduce the use of less desirable chemicals in their products. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | This project will leverage significant recent efforts by a number of leading apparel, footwear and outdoor-clothing brands to increase access to CiP information throughout their supply chains. The Executing Agency, the Ministry of Environmental Protection of China, will work closely with the national production base for the textiles industry – a sector with which they already have extensive cooperation on chemicals issues. MEP will as well coordinate with the Chinese Academy of Inspection and Quarantine (CAIQ), a government institute supporting China’s oversight of exports. In this regard the UN ENVIRONMENT CiP programme pilot will coordinate with government activities and industry initiatives of the textiles industry (e.g. the Chemicals Management Framework) in a supportive manner, ensuring coordination and efficiency in promoting shared goals. The project will engage with textile supply chains in China, and with other stakeholder representatives globally, to pilot this information exchange. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2016_ | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | Final PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2016_ | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS | MS | MS |  |
| During the period from July 2018 to May 2019, the main focus was on organization of training activities, feedback collection and report writing During the use of tool kits, total of 516 accounts have registered, including 321 accounts of chemical suppliers, 157 accounts of chemical users. According to statistics on log-in of accounts, the vast majority of users logging in the system and reporting data were chemical users (textile enterprises), most chemical suppliers have never logged in mainly because the majority of chemicals are not fully willing to report data and will not actively log in the system to report data. The final conclusion of the project is that the toolkit could be carried out for information exchange, however there are still need to be developed in the future. Read the project final report for more details. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2016_ | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS | MS | MS |  |
| During the period from July to December in 2018 the implementation work mainly focused on component 3 activities and preparation for the further implementation of this project. All these works can be summarized as follows: After UNEP has developed the training kit, pilot activities of the project were successfully held in Shishi city of Fujian province, Foshan city of Guangdong province, Shaoxing city of Zhejiang province, Zibo city of Shandong province and Changzhou city of Jiangsu province where the industrial clusters are concentrated and the textile industry was mature from July to September. The whole training activity involved more than 400 people and more than 300 enterprises. After the completion of training activities, a questionnaire on the motivation of tool kits was circulated and an exercise conducted. In order to complete the project, a closing meeting was also held. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2016_ | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | M | L | L |  |
| The project was low risk because implementation was delayed but project was completed. |  |  |  |  |  |

| Stakeholder engagement | According to statistics about the distribution of users of the platform after the CiP project training, a total of 516 accounts have registered, including 321 chemical suppliers, chemical 157 chemical users and 38 brand purchasers. All kinds of stakeholders are fully mobilized to participate in the initiative. |
| --- | --- |

| Gender mainstreaming | More than half of project execution teams were women. There is also a fairly balanced representation of men and women in toolkit training. |
| --- | --- |

| Knowledge activities and products | Tool kit developed |
| --- | --- |

| Stories to be shared | N/A |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To define principles and stakeholder roles and responsibilities and to demonstrate best practices for chemicals information exchange in textile products |  |  |  |  |  |  |
| Outcome 1: Information needs identified and baseline strengthened | 1. Multi-stakeholder project coordination team in place and work-plan and budget agreed. | 1) Project team not in place (2) Work plan outline is available; project budget needs to be refined to reflect activities after a multi stakeholder consultation |  |  |  |  |
|  |  |  | 1) Project team in place. (2) Endorsed work plan and budget (at inception workshop). | Project team is in place. Work plan and budget have been endorsed. | Though there were some changes in the project team personnel during the course of the project contributing to delays, eventually a team was established and met the objectives of the project. | S |
|  | 2. Existing information on chemicals in products in the textile sector collated and assessed in relation to the CiP programme and textile sector stakeholder needs | State of play of CiP information exchange in the textiles sector with respect to stakeholder needs is incomplete or uncoordinated | (1)Review and assessment completed (2)Guidance materials researched and assessed. Appropriate guidance materials identified | (1)Review and Assessment completed (2)Appropriate guidance materials identified | The targets were met satisfactorily. | HS |
| Outcome 2: Best practices for product chemical content information exchange are developed and endorsed in the textiles sector. | 1. Matrix of roles and responsibilities for CiP information exchange among textile industry stakeholders is established | No roles and responsibilities matrix exists. | Roles and responsibilities matrix has been drafted, reviewed and adopted by a multi stakeholder community. | Roles and responsibilities matrix established. | The targets were met satisfactorily. | HS |
|  | 2. Chemicals information to be exchanged throughout the production process and among stakeholders is defined and endorsed | No sector-wide agreement on what CiP information to exchange among stakeholders. | What CiP information to exchange among stakeholders has been drafted. | What CiP information to exchange among stakeholders has been endorsed. | The targets were met satisfactorily. | HS |
|  | 3. Best practices for CiP information exchange in the textiles sector are established. | Best practices in chemicals in textile products information exchange do not exist. Sector practices vary widely among the different stakeholders and groups. | Current practices in the sector have been compared to principles for CiP information exchange and draft best practices are available for testing. | Best practices are finalized for the sector | The targets were met satisfactorily. | HS |
| Outcome 3: Stakeholders adopt best practices in chemical content information exchange for textile products manufactured in China | 1.Number of textile sector brands or retailers who apply (pilot) best practices in CiP information exchange | 0 textile sector brands or retailers applying best practices | 5 textile sector brands or retailers have agreed to apply the best practices | 5 textile sector brands or retailers apply the best practices | The targets were met satisfactorily. | HS |
|  | 2.Number of supply chain production facilities where best practices in information exchange are applied | 0 facilities | 5 facilities | 10 facilities | The targets were met satisfactorily. | HS |
|  | 3.Number of product lines where best practices in information exchange are applied to multiple life-cycle phases (e.g. business-to-business, business-to-consumer, business-to-government) | 0 product lines | 10 product lines | 20 product lines | The targets were met satisfactorily. | HS |
| Outcome 4: Lessons learned from demonstrating CiP information exchange in the textiles sector promote replication | 1. Lessons learned and best practices are disseminated to textile stakeholders outside of this project. | 0 stakeholders | 5 stakeholders | 25 stakeholders | The targets were met satisfactorily. | HS |
|  | 2.Number of non-textile sector stakeholders participating in the development of a dissemination and engagement strategy for promoting best practices in CiP information exchange in other sector(s) | 0 stakeholders | 2 stakeholders | 5 stakeholders | The targets were met satisfactorily. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Summarize the annual progress towards meeting project results. This project could have had a higher rating but was rated as MS because of the change in personnel on the executing agency side which caused a delay in execution of the project but once a team was established, especially in the past year of the project, the project progressed and completed well. This information provides the rationale for the Development Objective Rating in Section 2. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | No Risk | No Risk |
| on stakeholder engagement | No Risk | No Risk |
| on gender actions | No Risk | No Risk |
| on safeguards | No Risk | No Risk |
| on delivering GEF Core Indicators | No Risk | No Risk |
| on delivering of PoW EA | No Risk | No Risk |
| on sustainability of results | No Risk | No Risk |
| others | No Risk | No Risk |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: Project workplan and budget endorsed and published and baseline materials identified and available. | 2015.5 | 100% | 100% | Once the project dates were revised the outputs were met successfully. | S |
| Output 2: Published assessment of existing information on chemicals in products in the textile sector | 2016.4 | 100% | 100% | Once the project dates were revised the outputs were met successfully. | MS |
| Output 3: The roles and responsibilities of stakeholders in the textiles sector in exchanging chemicals in products information are identified, defined and analysed in an assessment report. | 2017.5 | 100% | 100% | Once the project dates were revised the outputs were met successfully. | S |
| Output 4: What chemicals information should be exchanged between stakeholders in the textiles sector is defined. | 2016.8 | 100% | 100% | Once the project dates were revised the outputs were met successfully. | S |
| Output 5: A set of best practices for chemical in products information exchange for the textiles sector is established and available | 2018.8 | 50% | 100% | Once the project dates were revised the outputs were met successfully. | S |
| Output 6: Project report detailing experiences and lessons learned from the application of best practices for CiP information exchange in the textiles sector. | 2019.1 | 33% | 100% | Once the project dates were revised the outputs were met successfully. | MS |
| Output 7: A synthesis report of findings from the project available (including a synthesis of the activities to engage others sectors) available | 2019.6 | 0% | 100% | Once the project dates were revised the outputs were met successfully. | S |
| Output 8: Monitoring and evaluation plan fully implemented . | 2020.1 |  | 75% | Once the project dates were revised the outputs were met successfully. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS |  |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Considering that there is no solid policy to support the project activities for the time being, the enthusiasm of enterprises to fill toolkits is not that strong, and the scope of filling toolkits is limited | Telephone communication and door-to-door visits have be done with enterprises participating who accepted the training to persuade them to fill out the toolkit | CAIQ | September 2018 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Data collection risk, in terms of non-validated reports or other data that could be incorrect or misstated. | A focus of this project will be the development of new partners and new data sources beyond the project itself, moving toward a scenario with multiple data sources, some of which will be sources that can be used to validate other claims of progress or results. Example: the partnership with National Bureau of Statistics in Nigeria. |  | CEO: M |
|  |  |  | TM:L |
|  |  |  | PM:L |
| Partners, having made implementation commitments and set goals, back away from or abandon their goals as deadlines approach. | Broadly speaking, the project serves to support the partners and help them maintain progress on reaching their goals by providing a beneficial non-partisan political exposure, which partners will gain through their participation. The project will closely track partners’ implementation and will leverage in a diplomatic fashion on its soft power to ensure that they deliver on their commitments. Specific webinars and one-on-one sessions will be organized with those partners which achieve commitments to share their success stories and best practices. |  | CEO: M |
|  |  |  | TM:L |
|  |  |  | PM:L |
| Drafted and proposed legislation is not passed into law | Project activities tap the right expertise through GLOBE’s extensive partnerships to inform and justify needed policy changes. Chapter and/or executive‐level engagement activities create the necessary political will, momentum, and leadership for change. Legislation is the ideal to which the project will aspire, but where immediately feasible, regulatory responses may be sought in the interim. The the project-proposed legislation changes will be explained comprehensively and put in an international context in order to increase cross-party ownership and support. |  | CEO: M |
|  |  |  | TM:L |
|  |  |  | PM:L |
| ESERN [add cells as appropriate to capture all Medium and High Risks] |  |  |  |
|  |  |  | L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L |  |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | L |  |  |  |  |  | PM :L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | L |  |  |  |  |  | PM :L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary | N/A |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | L |  |  |  |  |  | PM:L |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:L |  |  |  |  |  |  |
| Others, please N/A | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

N/A

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L |  |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.