United Nations Development Programme

Project Document

| Project title: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country(ies): Global | Implementing Partner (GEF Executing Entity): UNDP |  |  |  | Execution Modality: DIM |
| Contributing Outcome (UNDAF/CPD, RPD, GPD): RPD OUTCOME 1 - Accelerating structural transformations through more effective governance systems |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Low Risk |  |  | UNDP Gender Marker: GEN 2 |  |  |
| Atlas Award ID: 00122005 |  |  | Atlas Project/Output ID: 00117767 |  |  |
| UNDP-GEF PIMS ID number: 6277 |  |  | GEF Project ID number: 10128 |  |  |
| LPAC meeting date: 15 -22 April 2020 |  |  |  |  |  |
| Latest possible date to submit to GEF: October 31, 2019 |  |  |  |  |  |
| Planned start date: July 1st, 2020 |  |  | Planned end date: June 30th, 2023 |  |  |
| Expected date of posting of Mid-Term Review to ERC: N/A |  |  | Expected date of posting Terminal evaluation report to ERC: November 30, 2022 |  |  |
| Brief project description: The overall objective of the project is to provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. Component 1 of the project will focus on streamlined knowledge development and delivery in support of Article 13. It will design and build a streamlined platform for climate change reporting and transparency information; maintain content and features for the platform; and develop knowledge products, including their associated training modules, for dissemination through the platform and through other events. Component 2 of the project will support global stakeholder outreach and dissemination of best practices. It will conduct an annual stocktaking of transparency activities; organize COP side events and other meetings to disseminate good practice; facilitate communication among donors; and support countries with integrating the UNFCCC gender action plan into their transparency policies, measures, and management. UNDP will implement Component 2 of the project as described (with the exception of Activity 2.2.4). |  |  |  |  |  |
| - FINANCING PLAN - UNDP |  |  |  |  |  |
| GEF Trust Fund |  |  | $1,015,000 |  |  |
| UNDP TRAC resources |  |  | $0 |  |  |
| Confirmed cash co-financing to be administered by UNDP |  |  | $0 |  |  |
| - Total Budget administered by UNDP |  |  | $1,015,000 |  |  |
| - FINANCING PLAN AND PARALLEL CONFIRMED CO-FINANCING – UNEP |  |  |  |  |  |
| GEF Trust Fund (implemented by UNEP) |  |  | $985,000 |  |  |
| Co-financing in kind to be provided and administered by UNEP DTU Partnership (UDP) |  |  | $400,000 |  |  |
| - Total confirmed co-financing |  |  | $0 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | $2,400,000 |  |  |
| Signatures |  |  |  |  |  |
| Signature: Ms. Agi Veres Deputy Regional Director and Deputy Assistant Administrator Regional Bureau for Europe and the CIS (RBEC) United Nations Development Programme (UNDP) |  | Agreed by UNDP |  | Date/Month/Year: within 25 days of GEF CEO endorsement |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	6

III.	Strategy	8

IV.	Results and Partnerships	10

V.	Project Results Framework	22

VI.	Monitoring and Evaluation (M&E) Plan	24

VII.	Governance and Management Arrangements	28

VIII.	Financial Planning and Management	33

IX.	Total Budget and Work Plan	35

X.	Legal Context	37

XI.	Risk Management	38

XII.	Mandatory Annexes	41

Annex 1:  Project map and Geospatial Coordinates of project sites	42

Annex 2: Multi-Year Work Plan	43

Annex 3: Monitoring Plan:	45

Annex 4:  Stakeholder Engagement Plan	48

Annex 5: UNDP Risk Log	51

Annex 6:  Overview of Technical Consultancies	52

Annex 7: Terms of References	53

Annex 8: Social and Environmental Screening Procedure (SESP)	58

Annex 9: Initial Gender Analysis and Gender Action Plan	59

Annex 10: Procurement Plan	63

Annex 11: Theory of Change	68

Annex 12:  GEF Core indicators	69

Annex 13: GEF 7 Taxonomy	70

Annex 14: Aggregated Total Budget and Work Plan (UNDP and UNEP)	71

List of Acronyms and Abbreviations

AFOLU			Agriculture Forestry and Other Land Use

BPPS			(UNDP) Bureau for Policy and Programme Support

BTR			Biennial Transparency Report

BUR			Biennial Update Report
CBIT 			Capacity-building Initiative for Transparency

CCMRVH		Caribbean Cooperative MRV Hub

CGE 			Consultative Group of Experts
CI			Conservation International

COP 			Conference of the Parties
CSO			Civil Society Organization

DIM			Direct Implementation

DPC			Direct Program Costs

EIGE			European Institute for Gender Equality

ETF			Enhanced Transparency Framework

EMG			Executive Management Group

FAO			United Nations Food and Agriculture Organization

GCP			Global Coordination Platform
GDI			Gender and Development Index

GEF 			Global Environment Facility
GHG 			Greenhouse Gas
GOE			General Operating Expenses

GSP 			Global Support Programme
IA			Implementing Agency

ICAT 			Initiative for Climate Action Transparency
IGES			Institute for Global Environmental Strategies

IPCC 			Intergovernmental Panel on Climate Change
IRH			Istanbul Regional Hub

LAC 			Latin America and Caribbean

LDC			Least Developed Country

LAC 			Latin America and Caribbean

M&E			Monitoring and Evaluation

MPGs			Modalities, Procedures, and Guidelines

MRV 			Measurement, Reporting, and Verification
NAP			National Adaptation Plan

NC 			National Communications
NCSA			National Capacity Self-Assessment

NCSP			National Communications Support Programme

NDC 			Nationally Determined Contribution
PaSTI			Partnership to Strengthen Transparency for co-Innovation

PATPA			Partnership on Transparency in the Paris Agreement

PCCB			Paris Committee on Capacity Building

PIMS			Project Information Management System

PIR			Project Implementation Report

PMU			Project Management Unit

POPP			Programme and Operations Policies and Procedures

PSC			Project Steering Committee

RedINGEI		Latin American GHG Inventories Network (Red Latinoamericana de Inventarios

Nacionales de Gases de Efecto Invernadero)

ROAR			Results Oriented Annual Reporting

SDGs			Sustainable Development Goals

SIDS			Small Island Developing States

SB			Subsidiary Body

SBSTA 			Subsidiary Body for Scientific and Technological Advice

TNA			Technology Needs Assessment

TE			Terminal Evaluation

UNDP 			United Nations Development Programme

UNDP-GEF		UNDP Global Environmental Finance Unit
UNEP 			United Nations Environment Programme
UNFCCC 		United Nations Framework Convention on Climate Change

WEDO			Women Economic Development Outreach

# Development Challenge

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way. This approach can reduce the time burden and financial burden on developing countries.

In addition to reporting commitments under Articles 4.1 and 12.1 of the United Nations Framework Convention on Climate Change (UNFCCC), the Durban Outcomes (1/CP.16) and Cancun Agreements (2.CP17), and Article 13 of the Paris Agreement, countries are to submit revised Nationally Determined Contributions (NDCs) in 2020, followed by a subsequent revised NDC in 2025. It should be noted that progress in reporting under these agreements varies widely among developing countries. There are countries that have produced several national communications (NCs) and several biennial update reports (BURs), while other countries have yet to produce a BUR.  All of these countries now face additional reporting under Article 13. The Conference of Parties (COP) 24, held in December 2018 in Katowice, Poland reached a series of important decisions regarding transparency under Article 13, known collectively as the Paris Rulebook.  The decisions outlined key commitments for all parties to the agreement and their timing during the 2020-2024 “Preparatory Phase” for reporting. Specifically, Parties are to submit a Biennial Transparency Report (BTR) by the end of 2024, which should include, among other items, a GHG inventory based upon the Intergovernmental Panel for Climate Change (IPCC) 2006 guidelines, which are themselves subject to recent refinement; projections of GHG emissions and removals for a period of at 15 years beyond the next year ending in zero or five; and reporting on progress towards achieving NDCs.

It is important to note that even countries that have not yet submitted a BUR must submit a BTR by December 31, 2024. Likewise, National Communications are still part of the UNFCCC reporting process and will continue to require support.  In addition, there is an even greater need to avoid overlap with other reporting exercises, such as monitoring Sustainable Development Goals (SDGs), and to centralize the data collection and analysis for National Communications, BURs, BTRs, and NDCs.  At present, these multiple commitments represent a serious challenge to developing country Parties. While developing countries have an increasing number of methodological and informational resources at their disposal, many of them face persistent challenges in their capacity to monitor and report on climate change, such as the barriers described in Table 1.

### Table 1: Barriers to Compliance with Enhanced Transparency Framework Requirements

| Barrier | Type of Barrier | Description |
| --- | --- | --- |
| Limited or non-existent country-level institutional frameworks for reporting on mitigation, adaptation, and financial resources needed and received | Institutional | Many developing countries have some information systems that contribute to reporting in their NCs and BURs; however, these systems are often incomplete and unconnected. Countries often lack the legislative and regulatory mandates to obtain data from sectoral ministries or from the private sector on an ongoing basis, and the data received may not be properly formatted or vetted for quality. |
| Limited or weak technical capacities to prepare solid quality reports | Organizational / individual | Government agencies that are currently responsible for reporting and transparency are understaffed, and frequent turnover and administrative reorganization cause disruptions in the continuity of employees working on the reports. When staff are available, they may lack particular methodologies that would allow them to undertake impact assessments of mitigation and adaptation measures and vulnerability to climate change. In other cases, staff are fully occupied with current reporting obligations and lack the time and resources to interpret new developments related to Article 13. These barriers are often symptomatic of an underlying problem: insufficient funding in governments to support staff who carry out transparency-related activities. |
| Absence of data and/ or difficulties in accessing data | Organizational/Procedural | Lack of activity data and/or data quality continue to be the biggest barriers to robust inventory compilation. New methodologies and reporting platforms being developed in many countries are limited in their effectiveness by an underlying lack of good-quality data. While data gaps and uncertainties have improved in the past few years in many countries, they continue to be a very important barrier to the quality and comprehensiveness of the NC reports, and the sustainability of the NC and BUR processes. |
| Limited stakeholder consultation processes | Institutional / Organizational/ Cultural | Many countries lack the tools for broad consultative processes that include a wide variety of sectoral agencies and civil society, including the private sector and disadvantaged groups. A consultative approach is seldom part of the organizational culture of institutions leading those processes. |
| Lack of integration of gender considerations | Organizational/procedural | Although gender is mentioned in a number of NDCs, evidence in the form of national reports suggests that developing countries’ capacity to support gender mainstreaming or to integrate gender-related climate change findings into sectoral policies needs to be strengthened. |

Although countries face serious barriers to effective transparency activities, the introduction of enhanced transparency frameworks presents an opportunity to streamline MRV activities by approaching the common elements of transparency activities in a holistic way. This approach can reduce the time burden and financial burden on developing country Parties. Furthermore, there is an opportunity to share experiences and good practice across Parties, avoiding the need to devote valuable time and scarce expertise and funding to elaborate unique structures and approaches for each developing country Party.

This CBIT Phase II project is consistent with the Paris Agreement and national priorities, such as national communications, BURs, and NDCs tracking, as it will support countries in obtaining the necessary additional capacities and tools to track the progress in climate change mitigation and adaptation and, more specifically, the enhanced transparency framework's modalities procedures and guidelines (MPGs).

Also, this project is in line and will contribute to the UNDP Climate Promise, which aims to help ensure countries’ new climate action pledges better align their national sustainable development priorities through a wide range of thematic technical support. It will be instrumental in particular to the Climate Promise Service Line 5 “Monitor Progress and Strengthen Transparency”, since it will support for capacity strengthening related to monitoring and tracking progress on key climate-related indicators.  At the same time, it will also support data collection and analysis that can in turn inform other policy exercises, such as Technology Needs Assessments (TNAs), National Adaptation Plans (NAPs), National Capacity Self Assessments (NCSAs), and others.

This project will also contribute to Sustainable Development Goals (SDGs) 13 and 17. The platform will serve as an underlying mechanism for tracking progress towards the Paris Agreement on Climate Change (SDG 13) and the specific target of 13.3 'Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning' and its indicator 13.3.2 'Number of countries that have communicated the strengthening of institutional, systemic and individual capacity-building to implement adaptation, mitigation and technology transfer, and development actions'.  At the same time, it will provide a forum encouraging partnerships among relevant actors (SDG 17) and the specific target of  17.9 ‘Enhance international support for implementing effective and targeted capacity-building in developing countries to support national plans to implement all the sustainable development goals, including through North-South, South-South and triangular cooperation’ and its indicator 17.9.1 ‘Dollar value of financial and technical assistance (including through North-South, South-South and triangular cooperation) committed to developing countries.’

# Strategy

The CBIT Global Coordination Platform (GEF ID 9675) will be provided targeted report on transparency issues until approximately March 2020. The Global Support Programme (GSP) will continue to provide support for sub-regional networks and for reporting under NCs and BURs until December 2020, when it will also end.  However, the need for country support will not end; on the contrary, developing country Parties will be grappling with new regulations under the Paris rulebook as Article 13 is operationalized, through the implementation of the MPGs.  Therefore, there is an acute need to ensure sustainability and combined implementation of the CBIT Global Coordination Platform and the Global Support Programme beyond 2019 and 2020, respectively. This need is clearly stated under Paragraph 14 of Article 13 itself, which states that “Support shall also be provided for the building of transparency-related capacity of developing country Parties on a continuous basis.” At the same time, UNEP and UNDP are aware that continuation of both the GSP and Global CBIT Support Platform as separate initiatives under the Paris Agreement is likely to create a duplication of effort.  GSP was launched under the UNFCCC Convention, whereas the Global CBIT Support Platform was launched under the Paris Agreement. This fact is acknowledged in the Paris Agreement, whereby Paragraph 74(a) of the Paris Agreement clearly states that part of the 2016-2020 work plan should assess how to increase synergies through cooperation and avoid duplication among existing bodies [or initiatives] established under the Convention. Countries will be best able to address reporting requirements through unified tracking systems, and as they move towards unified frameworks, they will best be supported by a unified web platform.

The proposed approach consists of two sequential projects: this proposed CBIT Phase II MSP (IIA) and a subsequent Full-Sized Project (IIB), both of which will be jointly implemented with UNEP.  Originally designed as a single Phase II project, the project was divided into two parts in order to ensure the allocation of funding that was available through the CBIT set-aside under GEF-6. Phase IIA therefore focuses on a streamlined platform for knowledge delivery, support for knowledge products, and global stocktaking and dissemination of best practices—all elements that require funding early in the subsequent phase of the project.   Phase IIB will continue support for the integrated web platform, but it will also provide targeted technical support and training for developing country parties and south-south sub-regional networks and learning.  Phase IIA presents an opportunity to pilot certain approaches and materials prior to the finalization of Phase IIB, particularly in the area of south-south peer learning networks.  Details regarding the approach and activities under Phase IIB are currently under discussion and will incorporate lessons learned and consultations with developing country Parties, the GEF, and support providers, including GEF IAs.

CBIT Phase II, comprised of the Phase IIA and IIB projects, will use three main strategies in its approach. First, it will build on the successful foundation of ongoing delivery models and leverage long-standing South-South networks and relationships with developing countries.  Its activities will draw upon successful approaches that have been identified and refined over time through feedback from consultations and external evaluations. Second, CBIT Phase II will use an agile approach to address new issues related to Article 13 as they arise.  As with CBIT Phase I, it will maintain flexibility to be responsive to, and integrate, evolving COP guidance related to the Modalities, Procedures and Guidelines (MPGs) for the Enhanced Transparency Framework under the Paris Agreement. Because the project emphasizes stakeholder participation, it will be able to mobilize experts and respond to changes in the climate policy landscape as they emerge. It is assumed that guidance regarding the MPGs will continue to develop, and the global program will be well positioned to disseminate information and provide support in complying with additional guidance from the COP.

Third, CBIT Phase II will utilize a partnership model for delivery. The integration of the GSP and CBIT support to countries will utilize the combined expertise and country networks of UNEP and UNDP under a common initiative that will simplify country participation. The project will also continue to provide facilitation support for the delivery of the UNFCCC Secretariat work programmes and the work of the Consultative Group of Experts (CGE).

Figure 1 provides an overview of the envisaged integration of the provision of information and technical assistance currently being carried out by CBIT Phase I and the GSP into the unified global coordination platform.  The integration is designed to provide continuous support for countries through the end of 2025 while avoiding overlap in activities.  It should be noted that the website maintenance and support activities in IIA and IIB will be sequential; i.e., IIB will begin to support these activities following the closure of IIA.

### Figure 1: Proposed Timeline of Project Coordination

This proposed approach will be increasingly important as the size of the GEF portfolio of CBIT-funded projects grows.  In addition to the CBIT projects that have already been approved, $164 million is earmarked for CBIT projects and enabling activities under GEF 7.  However, many more developing countries will not have a CBIT project but will nonetheless be required to submit a BTR in 2024. Phase II outputs and outreach strategies will be designed to maximize outreach and support to all developing country Parties.

This project will ultimately contribute to enhanced ambitions in reducing GHG emissions. Improved coordination will generate synergies and avoid duplication across support initiatives and efforts, freeing resources for additional efforts in the global aim to keep global warming below 2 degrees Celsius. Similarly, the enhanced availability of knowledge through a centralized coordination platform will help countries increase their transparency capacity and, as a result, their capacity to report progress on their NDCs and long-term policy planning, providing for increased ambition.  A theory of change diagram for the project is provided as Annex 10 of this document.

The project is primarily aligned with GEF Focal Area CCM-3-8, “Foster enabling conditions for mainstreaming mitigation concerns into sustainable development strategies through capacity building initiative for transparency.”  However, it will also play an important role in advancing progress in GEF Focal Area CCM-EA, “Foster enabling conditions for mainstreaming mitigation concerns into sustainable development strategies through enabling activities,” through the integrated web platform. In addition, the knowledge products developed, global stakeholder outreach, and dissemination of best practices will directly support CCA-2, “Strengthen institutional and technical capacities for effective climate change Adaptation,” as many developing countries have included an adaptation component in their NDCs and in GEF-funded CBIT projects.

# Results and Partnerships

Expected Results:

The overall objective of the project is to provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. The outcomes of the project are as follows: 1) Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements; and 2) Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming.

The project is composed of two components: 1) Streamlined knowledge development and delivery in support of Article 13; and 2) Global stakeholder outreach and dissemination of best practices.

Note: UNDP will implement Component 2 of the project as described (with the exception of Activity 2.2.4), while UNEP will implement the remainder of the project.

Component 1: Streamlined development and delivery of knowledge in support of Article 13

Component 1 will be implemented by UNEP and executed by the UNEP DTU Partnership

Component 1 seeks to provide developing countries with a holistic source of information and knowledge related to transparency and a web platform for online peer learning.  It focuses on merging two existing web platforms related to transparency—CBIT and GSP—and maintaining the core services provided under those web platforms while expanding the resources and learning materials available through the development of new guidance publications and training modules. In this way, the new transparency web platform will become a “one-stop shop” for information related to Article 13 and transparency more broadly.

The requirements in the “Paris Rulebook,” or the detailed rules and procedures that will govern the implementation of the Paris Agreement, will continue to evolve over time, providing guidance to countries on how to report on their efforts related to climate change and the commitments that they have made in the form of Nationally Determined Contributions. In addition, the release of the rules provides an opportunity to structure country-level transparency frameworks in such a way as to optimize reporting under other UNFCCC commitments. However, in both cases, developing countries will require additional support and guidance on interpreting the rulebook and implementing it with the least additional time and expense possible. The structure of BTRs, the introduction of the IPCC 2006 guidelines for national GHG inventories (or their modification according to the 2019 refinement), and reporting on progress towards NDCs necessitate new guidance and knowledge for all Parties. Under this project component, the web platform will accommodate resources related to the Paris rulebook through a designated knowledge base area as they become available and will develop its own knowledge products, including the associated training modules, and best practice case studies as necessary.

Finally, specific activities will also support women’s active participation in knowledge generation and active use of the integrated platform.

Output 1.1	Existing CBIT and GSP platforms merged and redesigned into an integrated web platform

UNDP and UNEP currently provide transparency-related information to developing countries and other stakeholders through two internet websites.  The first, the Global Support Programme website (www.un-gsp.org), provides information and resources designed to strengthen capacity related to the preparation of NCs and BURs. The second website, the CBIT Global Coordination Platform (cbitplatform.org) through the UNEP DTU Partnership, focuses explicitly on strengthening capacity to undertake transparency arrangements under Article 13 of the Paris Agreement and provides information on and support to countries that are implementing projects under the GEF CBIT funding mechanism.

The integrated web platform will initially contain five modules:

- Information on ongoing and upcoming in-country, regional and global transparency initiatives through a project database, mailing list, events forum, analytics, and a global snapshot with certain periodicity;

- Country profiles with information on progress on NCs and BURs, self-assessed needs, and CBIT national projects;

- A library of practices, methodologies, and guidance, including guidance materials on the Consultative Group of Experts (CGE) and the Paris Rulebook and archived materials from the previous websites;

- Information exchange and on-line tools for peer learning, including a feature that will allow the platform to serve as a point of coordination for regional MRV and transparency networks; and

- A “one-stop shop” for requesting assistance with country-level reports and transparency issues.

In subsequent phases, these modules can be expanded, institutionalizing the platform as the go-to destination for transparency practitioners as an all-encompassing information source. However, key features of each site will remain, for example, the self-assessment tool and self-progress reporting for CBIT participant countries will remain in place based on the roadmap for platform developed under CBIT Phase I or the audiovisual resources developed under the GSP.

MRV experts in developing countries are often involved both in reports to the UNFCCC and in current discussions on Article 13.  Therefore, the merger of the websites will simplify their searches for information and resources on transparency issues. In cases where users are familiar with only one of the websites, the merger will increase the resources that they access. In summary, an integrated platform will establish a unified virtual space for all national and international stakeholders interested in gathering information on MRV and the enhanced transparency framework and in following the implementation status of NCs, BURs, BTRs, and CBIT projects and practices.

Activities under this output include the following:

1.1.1	Conduct requirements elicitation, including focus groups or surveys with different user groups and analyze usage patterns (disaggregated by gender)

1.1.2	Review and analyze existing, relevant climate change information portals and user traffic on the two current websites and propose a re-branding strategy, including a new logo, for the unified website

1.1.3	Design integrated website, evolving the existing features and the additional features, and conduct a usability study and beta testing at the prototype stage

1.1.4	Program the integrated platform, including search engine optimization

1.1.5	Conduct functional, performance, and integration tests on the integrated platform

1.1.6 	Develop and implement a website maintenance plan, including continuous software updates, data privacy and data security issues, regular backups, code repository and software version controls

1.1.7	Develop and implement a communications/re-branding strategy to inform users and potential users about the merge and publicize the launch of the integrated website

1.1.8	Survey users periodically after the website becomes operational and incorporate their feedback into the site design and features

Deliverables under Output 1.1 consist of the operational integrated platform and corresponding reports on website analytics every six months following the launch of the platform; a maintenance plan for the platform; a branding strategy and vision for the integrated platform; a website area for on-line regional transparency initiatives and corresponding reports on its use every six months; and a “one-stop shop” interface for requesting assistance with country-level reports and transparency issues, including reports on its usage every six months.

Output 1.2 	Platform content and features maintained and updated regularly

Both existing websites contain content and features that are directly relevant to users seeking information and resources related to transparency.  At present, the GSP website contains information by topic, and it also provides recent topical documents, resources such as infographics and video clips, good practice country reports, materials and information from past training and networking events, and country information pages.  In addition, the website maintains a roster of experts on various aspects of NCs and BURs who can provide support to countries. Finally, the GSP produces a newsletter that circulates to interested countries and to other stakeholders. The CBIT website maintains a project database of CBIT projects, and it provides news and interviews on transparency issues.  It also contains a library for information and materials from global and regional meetings.

Good knowledge management of the integrated web platform created under Output 1.1 will ensure that it is a valuable resource for countries seeking information and support. There will be a need to edit and curate content, and to draft case studies and project summaries when necessary.  Content development will be managed by the global level of the web platform, which will allow it to disseminate results from countries without adding to the time burden of country experts related to writing up results and sharing information.  Other content will be developed by countries within the framework of their GEF CBIT projects.

The coordination and capacity-generating efforts of the integrated website will be made easily digestible for all practitioners through a regular output: the "transparency snapshot." This knowledge will be disseminated through a factsheet, providing a regular summary of needs and gaps in line with information available in the platform's database. The website will also facilitate peer-to-peer discussions among developing country parties with common interests through a platform moderated by project experts.

Finally, the management of the platform will also take steps to encourage active engagement by women users: e.g., support articles and content written by women; encourage women’s participation in peer learning exchanges and events such as webinars. It will also track platform engagement by gender where possible.

Activities under this output include the following:

1.2.1	Develop a knowledge management workplan for regular content creation, maintenance, and curation on the integrated platform, including the progress reporting tool for participating CBIT countries

1.2.2 	Maintain and update the technical content of the website, including search engine optimization

1.2.3	Track and analyze country queries, downloads, etc. in order to inform future content.

1.2.4 	Facilitate expert-moderated online peer learning / knowledge sharing through the regional network coordination feature

1.2.5	Track platform engagement by gender where possible

Deliverables under Output 1.2 consist of a knowledge management plan for updating content on the integrated website and content that is maintained and updated over the course of the project.

Output 1.3	Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, best practice case studies, updated, developed, and customized

With the decisions undertaken at COP 24 in December 2018 on reporting under the Paris Agreement, countries must align their current climate change related MRV systems with the requirements of the Enhanced Transparency Framework envisioned under Article 13.  The advent of new requirements represents a serious time and resource burden for developing countries, particularly in smaller countries or least developed countries, which are already stretched thin in their efforts to comply with existing reporting under the UNFCCC and other COP decisions. However, because the rulebook is new to all parties, there is an opportunity to align enhanced transparency frameworks and to benefit from the structures and approaches that will be identified by developed country and “first mover” developing country parties for their reporting. It is expected that knowledge products developed under this output will be particularly valuable for developing countries in the preparation of BTRs, including countries that do not have a GEF CBIT project as reported monthly in the CBIT Platform.  As a part of BTR guidance, it will be necessary to support various aspects of the BTR. These include inventories, for which countries must use the IPCC 2006 guidelines, take into account the 2019 modification, and report consistent annual time series from 1990 with the latest reporting year no more than two years prior to the BTR.  They also include NDC tracking and projections of GHG sources and sinks at least 15 years into the future.  In addition, the “preparatory” phase for BTRs, which will take place during the implementation of the Phase II project, will allow countries that are interested to begin to incorporate BTR elements into their BUR reporting. Most countries with GEF CBIT projects have requested support for inventory improvements and inventory tools (73% and 70%, respectively); however, only 18% have requested support for scenario modeling, indicating that there may be an increased need for support from the global program in this area.

Knowledge products will be coordinated closely with stakeholders in the donor community (see Section II.2) in order to avoid overlap.  The selection of topics will also be influenced by demand as expressed in feedback from CBIT project countries, other developing country Parties, and the pilot peer-to-peer learning network, and they may include different areas of reporting, such as systematic reporting on needs and gaps or financial resources received.

Activities under this output include the following:

1.3.1	Survey existing awareness-raising and training materials related to the Paris Rulebook to identify needs

1.3.2	Develop a work plan for producing new reports and training modules on emerging issues (enhanced transparency frameworks and the Paris rulebook, gender mainstreaming) and updates of existing handbooks and associated training modules on climate change MRV, including a plan for translation of all guidance into key participant languages as needed

1.3.3	Refine the CBIT Phase I self-assessment tool

1.3.4	Integrate good-practice templates and successful approaches to reporting issues from participating countries into training materials and other knowledge products (webinars, audio briefings, web content, etc.)

Deliverables under Output 1.3 consist of at least three guidance documents on climate transparency, a report on the updated results from self-assessment questionnaires, reports from at least three annual webinars, and at least three good practice briefs.

Component 2: Global stakeholder outreach and dissemination of best practices

Component 2 will be implemented and executed by UNDP with the exception of Activity 2.2.4, which will be implemented by UNEP and executed by the UNEP DTU Partnership

In the framework of the Global CBIT Support Platform, three global meetings have been organized so far (see description under Output 2.1). Future events will serve several purposes. First, they will allow the project to present a real-time “transparency snapshot” of how countries are progressing in establishing transparency frameworks.  Second, they will provide a forum for disseminating good practice in MRV systems and transparency to donors and to countries. Third, they will provide an opportunity for south-to-south peers, mentors, and staff of twinned projects to spend time meeting face to face to discuss key issues of mutual interest. Finally, they will increase donor coordination, which will allow the project to leverage other resource and reach the maximum number of stakeholders possible while avoiding duplication of effort.

Output 2.1: Annual stocktaking of progress, capacity needs, and support to all non-Annex I countries conducted

This output will build on the CBIT Phase I project annual technical meetings, which have been held three times: in 2017 in Copenhagen; in April 2018 in Berlin; and in May 2019 in Rome.  The most recent workshop was the largest to date: it involved 100 attendees from 7 donor countries, 36 program countries, international organizations, and CSOs engaged in supporting transparency frameworks.

Annual global stocktaking meetings under this component will be aimed at strengthening national transparency capacities by presenting objectives and results from national CBIT projects, by identifying common approaches to existing challenges to transparency, and by presenting opportunities for actors from different initiatives to meet and coordinate their work. In addition, meetings may organize some outreach efforts by baseline country capacity; i.e., countries with experience with the IPCC 2006 guidelines could discuss common challenges, while countries that are just starting to create MRV frameworks and consider the 2006 guidelines could receive targeted information. In other cases, experienced countries can mentor neighboring countries that need more capacity support. Ideally, these meetings should provide participants with information that can strengthen their reporting efforts.

Activities under this output include the following:

2.1.1	Organize three annual global stocktaking meetings, including the selection of topics and participants and encouraging representation and active involvement by women participants

2.1.2	Disseminate findings and materials shared at the meetings and workshops through various communication channels, including the integrated web platform

Deliverables under Output 2.1 consist of three annual global stocktaking meetings and at least three meeting summaries and stocktaking briefs.

Output 2.2: COP side events and outreach efforts organized to enhance and disseminate results

This output will maintain the practice developed under the GSP and the CBIT global platform of presenting results from selected countries and regions at UNFCCC events in order to reach the widest possible audience of climate change decision-makers from both developed and developing countries.  These events will support information exchange among developed and developing country Parties and will contribute to increased donor coordination. They may include events that are organized in conjunction with another meeting (e.g. a regional climate weeks) in order to minimize time and travel burdens for participants.  This output will support a pilot regional collaboration effort among different complimentary initiatives on transparency in Latin America and Caribbean (LAC), including CBIT work, PATPA, RedINGEI, and CCMRVH. It will foster south-south peer exchanges with the aim of enhancing country transparency practices, supporting the sharing of good practices and lessons learned, and supporting countries to identify cooperative actions to increase ambition on transparency and climate goals.

Activities under this output include the following:

2.2.1	Organize at least three side events for upcoming COPs and subsidiary body (SB) meetings (likely to be COP25, COP26, and COP27, and SB50, SB52, and SB54) and/or regional climate weeks, including the selection of topics and participants and encouraging representation and active involvement by women participants,

2.2.2	Provide logistical support for the side events,

2.2.3	Disseminate meeting summaries through various communication channels, including the integrated web platform,

2.2.4	Pilot the fostering of south-south peer exchanges on climate transparency actions in the LAC region.

Deliverables under Output 2.2 consist of meeting summaries on at least three side events at COPs, SB meetings, and/or regional climate weeks; and reports every six months on the activities of the pilot regional collaboration network for climate transparency in the LAC region and supporting activities following the launch of the network.

Output 2.3: Coordination among support providers facilitated

This output will focus on maintaining and expanding the communication among support providers with the purpose of improving the effectiveness and timeliness of provision of technical and financial support to developing countries, by making coordination among interested stakeholders easier. Significant efforts  have been developed through the GSP and CBIT Phase I, such as the May 2019 “Enhancing Coordination on Climate Transparency” meeting, which was held in tandem with the GEF Technical workshop in Rome. approximately 45 participants of that meeting included representatives of Parties that contributed to the CBIT Trust Fund, international organizations, and other institutions involved in providing support to enhanced transparency frameworks.

The project will communicate regularly with support providers (a broadly-defined group that includes any entity providing support, such as government donors, UN agencies, developing country governments where applicable, think tanks, and formal and informal groups of providers) to exchange information regarding activities.  This output will also focus on continuous improvement in the quality of technical backstopping provided to recipient countries.  This output is designed to complement activities under Component 1 that will collect training materials and transparency-related information, including program descriptions, for the CBIT global platform, making these materials available to countries through the integrated website.

Activities under this output include the following:

2.3.1	Organize at least one coordination meeting per year for support providers to map current activities and to identify regions and sub-regions that are in need of assistance and potential areas for combined service delivery,

2.3.2	Conduct a dialogue with support providers to determine ways to leverage their activities for the regional climate transparency networks that have been supported under the GSP to date.

Deliverables under Output 2.3 consist of reports from three coordination meetings with support providers.

Output 2.4: Assistance provided to countries with integrating the UNFCCC Gender Action Plan into enhanced transparency frameworks

While the Paris Agreement has highlighted gender equality and women’s empowerment as a guiding principle, countries will require assistance to operationalize these principles in their transparency activities. Therefore, this output focuses on supporting countries with integrating the UNFCCC Gender Action Plan (GAP) and associated decisions such as Decision 21/CP.22, which extends the Lima work plan on gender to COP25 in 2019, into transparency activities. The UNFCCC process continues to move to integrate gender-sensitive education and increase participation by women in UNFCCC processes and decisions, most recently with a draft gender action plan commissioned by COP22.  This action plan is designed to address gender sensitivity in all mitigation and adaptation activities, including the NDCs and low-term low greenhouse gas emission development strategies.  In addition to materials that focus explicitly on gender in MRV and Article 13, CBIT Phase IIA training and supporting knowledge products will incorporate the areas of the UNFCCC gender action plan that are targeted for attention: A) Capacity-building, knowledge sharing and communication; B) Gender Balance in Participation, and Women’s Leadership; C) Coherence across UNFCCC bodies and other UN entities; D) Gender-responsive Implementation and Means of Implementation; and E) Monitoring and Reporting on gender-related mandates under the UNFCCC.

While the UNFCCC provided training at COP24 in conjunction with WEDO and UN Women for UNFCCC Gender Focal Points, it will be important for focal points and project teams to continue to receive information and guidance, particularly in the priority area of monitoring and reporting. While all project components will take gender equality issues and women’s participation into consideration (e.g. women’s active participation in the integrated platform under Component 1), this output focuses on integrating the GAP into enhanced transparency frameworks at the country level with a special emphasis on national reports. It also represents an opportunity to disseminate results under the GSP, which has supported two regional workshops on supporting the integration of gender considerations into MRV/transparency processes in the Western Balkan countries and Lebanon. These GSP activities, however, will conclude in February 2020.

Activities under this output will also support the exchange of information on gender considerations related to NDC tracking. Finally, it will provide support for the update and expansion of the gender-responsive national communications toolkit used by many countries to include recommendations on integrating gender equality considerations into BTRs and ETFs more generally.

Activities under this output include the following:

2.4.1	Provide and coordinate reviews of national reports and supporting documentation by gender experts in response to country requests,

2.4.2	Provide an updated toolkit on integrating the UNFCCC Gender Action Plan into national transparency frameworks that will build upon the current GSP toolkit (Gender Responsive National Communications and BURs),

2.4.3	Conduct at least four regional workshops (at least one workshop in each of four regions) on integrating gender analysis and the UNFCCC Gender Action Plan into national reporting and transparency. Workshops will be scheduled in conjunction with other CBIT-related meetings and workshops where possible to use resources efficiently.

2.4.4	Collect and analyze country reporting with regards to gender mainstreaming and integration of the Gender Action Plan in support of the annual stocktaking under Output 2.1.

Deliverables under Output 2.4 consist of on-demand gender reviews of national reports, an updated gender toolkit, and workshop reports from four regional workshops.

Partnerships:

There are three types of partnerships that are central to this project: 1) GEF-funded global projects on national reporting and transparency, 2) CBIT projects at the country and global level; and 3) donor-funded country and regional projects that are funded by sources other than GEF.

GEF-funded global projects on national reporting and transparency

The Global Support Programme (GSP), which is jointly implemented by UNEP and UNDP, was initiated with the objective of providing support to non-Annex I Parties in their preparations of National Communications and Biennial Update Reports. Since 2015, GSP has been providing technical support to all developing countries, complementing the work of other supporting bodies such as the Consultative Group of Experts on National Communications from Parties not included in Annex I to the Convention. In the framework of the GSP, UNEP and UNDP have conducted national and regional training workshops and dialogues on issues of NCs, BURs and their components. Guidance documents were prepared and published, including translation of existing guidelines into other United Nations languages. To date, thirteen regional workshops (with 87 countries participating), 14 national workshops (in 12 countries), and six webinars have been organized, co-organized and/or co-funded by the GSP. The GSP has also assisted 32 countries in reviewing 25 GHG inventories, 10 NCs, and two BURs. Three regional networks have been established, and 16 countries have received request-based support, where GSP has reviewed technical terms of reference for experts. In addition to a high level of activity, the GSP has had a truly global reach: it has engaged 113 non-Annex I parties, and 73% of all non-Annex I parties, 74% of all least developed countries (LDCs), and 71% of all small island developing states (SIDS) have participated in GSP activities. It has also been able to respond to all country requests to date. In the course of the mid-term evaluation of the GSP, “Stakeholders interviewed uniformly expressed an appreciation of GSP support in terms of relevance, quality, and utility.” With the advent of the Paris Agreement, the UNEP DTU Partnership and the GSP provided support to 32 countries compiling their Intended Nationally Determined Contributions (INDCs) from 2015 to 2017.  That initiative included the development of an INDC portal, which served as a helpdesk for developing country Parties.

Collaboration between UNEP and UNDP in providing technical support to developing countries was further enhanced with the approval of the CBIT Global Coordination Platform (GCP) (GEF ID 9675) and its launch in 2017. The CBIT was established "to support developing country Parties, upon request, in meeting enhanced transparency requirements as defined in Article 13 of the Agreement." The primary problem it was designed to address was the lack of a global coordination platform for information sharing and knowledge management on the enhanced transparency framework, as defined by the article 13 of the Paris Agreement. In the framework of the Global CBIT Support Platform, three global meetings have been organized so far in Copenhagen (April 2016), Berlin (April 2017), and Rome (May 2019) on the implementation of ETFs by countries with GEF-funded CBIT projects. Participants have included numerous developing countries along with a number of donors, developed country parties, and civil society organizations (CSOs). At the same time, both UNEP and UNDP have begun to assist countries in the implementation of national CBIT projects.

At the 2018 Berlin meeting, the global CBIT project launched the CBIT Global Coordination Platform (https://www.cbitplatform.org/).  This web-based platform was established to promote peer learning among countries receiving CBIT support. Of these, the 42 national CBIT projects in the GEF pipeline have country profiles including key information about the projects, implementation progress, and the status of CBIT project activities and other transparency support initiatives. In addition, all 42 country-level projects have completed transparency self-assessments and have identified a CBIT focal point. Countries designing CBIT projects can use this assessment to guide the project design process and countries implementing projects can use it to track progress in building capacity and to inform design of additional transparency projects. The platform is also issuing bi-monthly status updates on the CBIT though the Transparency Snapshot.

As of March 2019, only 4 countries had initiated the implementation of CBIT projects, and so the CBIT platform was primarily being used by potential CBIT applicant countries to design projects, rather than for sharing lessons learned. Initial activities on the platform included a series of articles interviewing country focal points. In addition, several webinars have been held to facilitate peer learning at the design stage. As of June 2019, 13 countries have started the implementation phase of their CBIT projects, and so peer learning activities will be designed that fit their needs.

GEF-funded CBIT projects at the country level

As of May 2019, there were 42 country-level CBIT projects with approved concepts and, of those, 15 with approved CEO Endorsement Requests.  41 projects were approved during the GEF-6 funding cycle, 14 were Least Developed Countries (LDCs), and 7 were small island developing states (SIDS).  Overall, 31% of Non-Annex I countries, which in turn represent 22% of global GHG emissions, have a PIF or CEO Endorsement Request.

In addition to these country-level projects, there are two global GEF-funded CBIT projects implemented by the Food and Agriculture Organization of the UN (FAO): CBIT-Forestry (GEF ID 10071) and CBIT-AFOLU (GEF ID 9864). The CBIT-AFOLU project is expected to produce methodologies and tools for tracking progress towards NDCs in the AFOLU sector, and knowledge products developed under that project will be relevant to many developing country Parties.

Other donor-supported initiatives

A 2019 analysis by the MRV Group of Friends identified 475 MRV / transparency activities undertaken by 21 donors.  Several bilateral donors have initiatives to support MRV in climate change, such as the “Information Matters” project for ambitious climate reporting that has been managed by GIZ (2013-2019).

In addition to bilateral donors, several multilateral coalitions have emerged to support transparency. For example, the Initiative for Climate Action Transparency (ICAT) is currently developing an integrated suite of 10 guidance documents on various aspects of transparency, ranging from sectoral guidance in renewable energy and forestry to reporting on non-state action and Sustainable development and transformational impact assessment. ICAT also provides Capacity-Building for MRV systems for transparency in 35 Partner Countries, working very closely with developing countries to strengthen their capacity to assess climate actions and report their progress in line with the Paris Agreement, based on individual country needs. Furthermore, the Partnership on Transparency in the Paris Agreement (PATPA), which describes itself as a semi-formal forum, has had more than 100 countries participate in its activities, which include regional technical workshops and knowledge sharing. The Paris Committee on Capacity Building (PCCB), although not an implementing body, focuses on capacity gaps and needs. The PCCB relies on volunteers, and its activities have included support for NDC implementation and cross-cutting issues, including gender equality. They have undertaken a six-country pilot exercise, and they a have a web-based capacity-building portal. The Partnership to Strengthen Transparency for co-Innovation (PaSTI) was established in 2017 at COP23 as an initiative of the Ministry of the Environment of Japan (MOEJ) in collaboration with the World Resources Institute (WRI). PaSTI is designed to provide value-added activities to existing initiatives on transparency, and it promotes engagement of the private sector and local government by identifying incentive mechanisms and developing critical tools. PaSTI has held several webinars on topics such as enhancing MRV in the private sector, and it held a side event at COP24. The EU-funded EU4Climate project implemented in the Eastern Partnership countries (Armenia, Azerbaijan, Belarus, Georgia, Republic of Moldova, and Ukraine) and supporting above all enhanced MRV systems and NDC implementation in the beneficiary countries. EU4Climate supports the development and implementation of climate-related policies which contribute to their low emission and climate resilient development and their commitments to the Paris Agreement on Climate Change. It identifies key actions and results in line with the Paris Agreement, the "20 Deliverables for 2020”, and the key global policy goals set by the UN 2030 Agenda for Sustainable Development.

Furthermore, country cooperation has taken place at the regional level. For example, in Latin America and the Caribbean (LAC), country-level CBIT projects, facilitated by UNEP and UNDP, ICAT, PATPA activities, and the Latin American Network for GHG Inventories (RedINGEI) have all supported regional exchanges of knowledge and experience. Information on how these baseline projects and initiatives will be involved in project implementation is provided in Annex 4 of this document and in the description of activities under Output 2.3, which is explicitly designed to enhance the coordination of support providers.

Risks:

The following table provides an overview of project-related risks and how they will be addressed.

### Table 2: Project Risks and Risk Mitigation

| Risk | Level of Risk | Approach to Risk Mitigation |
| --- | --- | --- |
| The integrated platform is not perceived as relevant by users and fails to attract traffic | Low | The number of internet platforms dedicated to climate change transparency are still limited. The GSP and CBIT-GCP platforms already have a specific/dedicated audience, and the integrated platform will continue to provide enhanced content that is not available elsewhere. The project will also undertake specific activities to drive traffic to the new website, including continuous communication with other platforms. |
| Stocktaking workshops and side events fail to attract sufficiently high-level decision-makers and practitioners | Low | Experience with these events to date has indicated that high-level decision-makers and practitioners will attend when the topics are relevant and emerge from ongoing dialogue. The project will communicate with other support providers to avoid scheduling conflicts and to schedule back-to-back workshops when possible, reducing the need for participants to travel. |
| High turnover of participants due to high turnover of political appointees and civil servants in participating countries | Moderate | 1) The availability of strong documentation and codification of knowledge in regional languages under the project will ease the transition between experts and decision-makers. 2) Stocktaking meetings and side events will be scheduled throughout the project implementation period, exposing new participants to resources and contacts without a long waiting period. 3) Knowledge products that support country-level MRV systems will encourage countries to centralize and archive data, which will preserve institutional memory and minimize disruption from staff turnover. |

Stakeholder engagement plan:

Annex 4 provides an overview of the proposed roles for relevant stakeholders in the project and a plan for their engagement.

The GEF categorization of the role of CSOs in the project is “Other: Information exchange; training provision; consultation; work planning, participation in meetings and workshops.” Several CSOs (with equal participation by women and men) were consulted in August 2018 specifically regarding the design of the CBIT Phase II project.  These consultations affirmed the proposed project activities and provided information on current donor and CSO activities. No objections to any proposed activities or approaches were raised.  Subsequently, the GEF Technical Workshop and accompanying donor coordination forum (Rome, May 2019) and the accompanying meeting on enhancing donor coordination in transparency provided an additional opportunity to solicit feedback from representatives of CSOs.  General themes in consultations included a high interest in information exchange.

Civil society will be involved in the project in several ways.  First, the integrated platform will share best practices from CBIT national projects on how to integrate CSOs into national transparency activities.  In addition, international NGOs (INGOs) such as the World Resources Institute, have participated in CBIT technical workshops to contribute expertise and serve as a resource for country participants. The project intends to encourage the continued participation of relevant INGOs in technical workshops, COP side events, and other project-related meetings. Finally, the project will support the two-way exchange of information with regional and international CSOs that support gender equality and women’s participation, such as the European Institute for Gender Equality, to inform the deliverables under Output 2.4.

Gender equality and Women’s Empowerment:

This project addresses gender equality issues across its components and in a dedicated output designed to support countries in mainstreaming gender equality into transparency activities. The current project will draw on existing resources and networks to support capacity strengthening related to gender equality and climate change.  For example, the Gender Responsive National Communications Toolkit  developed under the GSP will serve as a foundation for the development of gender mainstreaming in transparency activities. This toolkit makes the process of reporting more transparent in terms of who is involved, whose views are represented, gender-differentiated risks, and the types of support men and women need to influence climate adaptation, mitigation, policymaking and reporting. It can also be used to build capacity for gender analysis of key climate change issues that are reported on in NCs.

Several CBIT country projects to be financed under GEF-6 include targeted outputs related to gender mainstreaming.  In addition, the project will build upon gender-mainstreaming activities undertaken through GSP support for regional networks, such as the “Supporting the integration of gender considerations into MRV/transparency processes in the Western Balkan Countries” sub-regional workshops, which took place since December 2017.  This project will draw from their experiences and allow the dissemination of good practices. As well as, promoting women as role models in climate action in the professional areas where there are underrepresented, or eventually engage and showcase feminist climate change specialist, leaders, thinkers in the activities where women tend to be understated. This will be promoted via the CBIT web platform, peer learning activities and workshops.

Activities under Output 2.4 of the proposed project focus directly on gender mainstreaming in Article 13. In addition, activities in each component include explicit language on supporting women’s meaningful participation in project activities.  Content and materials that are developed under this output will be made available to a broad audience in several ways. First, they will be disseminated through the annual stocktaking meetings conducted under Component 2. Second, they will be available on the integrated web platform established under Component 1.1. Finally, they may be shared through the pilot south-south learning network for Latin American countries that is established under Output 2.2. Several activities also support the collection of gender-disaggregated data and knowledge that includes gender considerations.

In the area of project management, gender equality and balance will be promoted during all project’s recruitment of personnel/consultants and related activities. All advertised positions will be equally opened to both genders and the text on term of references will be carefully checked to avoid any gender stereotypes. M&E activities will request gender dis-aggregated data and will consider whether project activities and/or benefits have had differentiated results by gender. Furthermore, gender sensitive/responsive indicators will be monitored at the objective level as part of the monitoring of GEF streamlined indicators and also as part of the stocktaking exercise so that this can inform the design follow up interventions.

Finally, the project will adopt guidance resulting from the recommendations that was prepared for consideration by UNFCCC Conference of the Parties at its 25th session (November 2019) on the basis of the synthesis report to be prepared by the UNFCCC Secretariat for the Subsidiary Body for Implementation “on the implementation of the gender action plan, identifying areas of progress, areas for improvement and further work to be undertaken in subsequent action plans.” An initial gender analysis and gender action plan are included as Annex 9 of this project document.

South-South and Triangular Cooperation (SSTrC):

Component 1 of the project (Streamlined knowledge development and delivery in support of Article 13) will focus on generating knowledge products and maintaining a web platform to allow knowledge sharing and dissemination for south-south learning. The streamlined platform is also consistent with the recommendation of the 2015 GEF Scientific and Technical Advisory Panel (STAP) interim report on knowledge management in the GEF to provide enhanced support for South-South exchanges. Component 2 explicitly supports learning from other relevant initiatives through the stocktaking in 2.1, information dissemination through a pilot regional coordination initiative in 2.2, and coordination with support providers in 2.3.

Additional learning opportunities and technology transfer from peer countries will be further explored during project implementation. To present opportunities for replication in other countries, the project will codify good practices and facilitate dissemination through global ongoing South-South and global platforms, such as Africa Solutions Platform, the UN South-South Galaxy knowledge sharing platform and PANORAMA.

Innovativeness, Sustainability and Potential for Scaling Up:

Innovativeness

The proposed Phase II project presents an innovative approach to support to developing country parties through its unified structure that combines support for multiple Convention-related commitments in a single “one-stop shop.” The organization of the integrated web platform and supporting knowledge products will also allow the project to be flexible and address issues related to Article 13 as they arise. Early phase support for BTR preparation and for integrating gender considerations into ETFs is also highly innovative, as is the approach of working with countries on request to incorporate elements of the BTRs into their current reporting.

In addition, the project is innovative in its use of south-south learning.  The pilot regional network for GHG inventories in LAC will allow countries to exchange relevant tools and experiences and also allow for some mentoring by developing country Parties with more experience in national reporting on climate change.  The regional network will also feed good practice upstream to the global platform, where it can be shared with developing country Parties and support providers in other regions.

Indeed, this project has a unique multi-level approach. At the global level, it provides information and knowledge to all interested developing country Parties.  At the same time, it also fosters regional exchanges and support to specific CBIT project countries.  It then uses the knowledge gained from these interactions to contribute to the global platform. Finally, it encourages individual countries to share transparency-related knowledge and experience with their peers directly through the platform.

Sustainability

The focus of project support is a sustainable approach to transparency activities by supporting capacity strengthening in CBIT project countries and other developing country Parties to the Paris Agreement.  One key element of the streamlined platform established in this project is the preservation of the platform under the proposed Phase IIB, which will extend its life through the 2019-2024 “preparatory phase” for Article 13 reporting. This arrangement will maintain continuity and allow countries access to valuable transparency-related information beyond the conclusion of this project.

Furthermore, it directly encourages countries to enhance and embed enhanced transparency frameworks into their institutional frameworks, which will put procedures into place that will last long after this Phase IIA project finishes.  This project also engages other stakeholders in fulfilling the provisions of the Paris Agreement, including senior policy-makers and CSOs. Ideally, this CBIT project will increase the ownership role that national institutions play in MRV and transparency activities, which increases the likelihood that countries will support continuous MRV systems and will move towards the utilization of the information they generate for national policy-making purposes.

The project approach also emphasizes sustainability by capturing transparency-related knowledge and experience that is generated by experts both globally and in individual countries and regions and sharing it through long-term information platform. The pilot regional peer-to-peer learning network on GHG inventories will build formal and informal ties among countries in the LAC region, which should provide benefits that extend beyond this project

Potential for Scaling up

The project itself represents the scaling up of activities implemented under the GSP and CBIT global platform projects, but it also has strong potential to expand.  For example, the number of sub-regional networks can increase as additional countries identify areas for cooperation. It will also address other Convention-related requirements or initiatives as they arise. Finally, the knowledge products and support for CBIT program countries will be highly relevant to the many developing country Parties who will not receive CBIT funding from GEF, but who will still need to meet reporting requirements under the Paris Agreement.  There will be a significant demand for the tools and methodologies developed under the national projects, the global project, and other global CBIT projects, such as the FAO-GEF global project on AFOLU and the Conservation International (CI)-GEF project on forestry. Knowledge products from all of these projects will be shared through the new streamlined platform, creating synergies and optimizing available resources.

# Project Results Framework

This project will contribute to the following Sustainable Development Goal (s): SDG 13: Take urgent action to combat climate change and its impacts

This project will be linked to the following output of the UNDP Strategic Plan (2018-2021): Output 1.4: Scaled up action on climate change adaptation and mitigation cross sectors which is funded and implemented.

This project will contribute to the following country outcome (UNDAF/CPD, RPD, GPD): N/A

|  | Objective and Outcome Indicators | Baseline | End of Project Target | Sources of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. | Mandatory GEF Indicator 1: # of project beneficiaries disaggregated by gender (individual people) | 150 people | At least 300 people will utilize support for transparency and reporting from project outputs and activities, and at least 150 of them will be women. | Reporting by CBIT Project Countries and project documentation that includes registration lists for webinars, trainings, and other in-person or on-line gatherings or discussion | Participating countries will continue to use the tracking tool indicator. |
|  | Indicator 2: % of the users surveyed who consider the platform (website, its features, and knowledge products) very useful or useful for their purposes | 0 (platform has not yet been merged) | 70% of users surveyed consider the platform to be very useful or useful for their purposes (measured as a score of 4 or 5 on a 5-point satisfaction scale) | Pop-up survey conducted on the streamlined website. | Partners will have sufficient time and interest to utilize the project’s resources. |
| Project component 1 | Streamlined knowledge development and delivery in support of Article 13 |  |  |  |  |
| Project Outcome 1 Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements | Indicator 3: Knowledge demand / uptake: i.e., number of countries and practitioners using the platform’s services and knowledge products every quarter (on average) | At least 40 countries and practitioners use the CBIT Global platform’s services and knowledge products every quarter (on average) | At least 60 stakeholders use the platform’s services every quarter (on average) | Website analytics. Country and practitioner feedback collected in the course of the Terminal Evaluation by the evaluator(s). | The unified website will simplify requests and searches for users and increase user interest. |
| Outputs to achieve Outcome 1 | 1.1 Existing Global Support Program (GSP) and CBIT platforms merged and redesigned into an integrated web platform 1.2 Platform content and features maintained and updated regularly 1.3 Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, updated, developed, and customized |  |  |  |  |
| Project component 2 | Global stakeholder outreach and dissemination of best practices |  |  |  |  |
| Outcome 2 Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming. | Indicator 4: Number of developing countries with beneficiaries who have shared their lessons (progress, support needed and received, and/or good practice) through project activities. | Experiences from more than 40 countries have been documented by developing country beneficiaries through annual self-reporting exercises, such as questionnaires in advance of technical workshops and implementation reports and / or through workshops supported by CBIT Phase I. | Experiences from more than 60 developing country beneficiaries have been documented through annual self-reporting exercises, such as questionnaires in advance of technical workshops and implementation reports and / or through workshops and regional meetings supported by this project. | Lists of countries participating in regional and global workshops based on registration data; information from questionnaires collected in advance of technical workshops and other content on the streamlined platform; and Project Implementation Reports for country-level CBIT projects. Structured interviews conducted in the course of the terminal evaluation by the evaluator(s). | New CBIT program countries will see value added in contributing information to the platform. |
|  | Indicator 5: Number of developing countries sharing good practice in gender mainstreaming on the streamlined CBIT web platform | None | Good practice in gender mainstreaming from at least 15 developing countries is shared on the streamlined platform. | Review of project documentation and platform content in the course of the Terminal Evaluation by the evaluator(s). | Developing country experts will have time and interest in participating in gender mainstreaming training. |
| Outputs to achieve Outcome 2 | 2.1 Annual stocktaking of progress, capacity needs, and support to all non-Annex I countries conducted 2.2 COP side events and outreach efforts organized to enhance and disseminate results 2.3 Coordination among support providers facilitated 2.4 Assistance provided to countries with integrating the UNFCCC Gender Action Plan into enhanced transparency frameworks |  |  |  |  |

# Monitoring and Evaluation (M&E) Plan

The project results, corresponding indicators and mid-term and end-of-project targets in the project results framework will be monitored annually and evaluated periodically during project implementation. If baseline data for some of the results indicators is not yet available, it will be collected during the first year of project implementation. The Monitoring Plan included in Annex details the roles, responsibilities, frequency of monitoring project results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Istanbul Regional Hub is responsible for ensuring full compliance with all UNDP project monitoring, quality assurance, risk management, and evaluation requirements.

Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The costed M&E plan included below, and the Monitoring plan in Annex, will guide the GEF-specific M&E activities to be undertaken by this project.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report: A project inception workshop will be held within 60 days of project CEO endorsement, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Steering Committee meetings and finalize the first-year annual work plan.

- Formally launch the Project.

GEF Project Implementation Report (PIR):

GEF Project Implementation Report (PIR): UNDP will assume overall responsibility for, and the Project Coordinator and the EMG will provide objective input to, the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR. The PIR submitted to the GEF will be shared with the Project Steering Committee.

Knowledge management:

The project team will ensure extraction and dissemination of lessons learned and good practices to enable adaptive management and upscaling or replication at local and global scales. Results will be disseminated to targeted audiences through relevant information sharing fora and networks. The project will contribute to scientific, policy-based and/or any other networks as appropriate (e.g. by providing content, and/or enabling participation of stakeholders/beneficiaries)

GEF Core Indicators:

The relevant GEF Core indicator, GEF-7 Streamlined Indicator 11, is used as Indicator 1 in the Project Results Framework. This indicator will be used to monitor global environmental benefits and will be updated for reporting to the GEF prior to the Terminal Evaluation (TE). Note that the project team is responsible for updating the indicator status. The updated monitoring data should be shared with TE consultant(s) prior to the required evaluation mission, so it can be used for subsequent “ground-truthing.” The methodologies to be used in data collection have been defined by the GEF and are available on the GEF website.

Terminal Evaluation (TE):

An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities, to be funded and in equal parts by UNDP and UNEP, and to be implemented by UNDP. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center.

The evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired by UNDP evaluation specialists to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the consultants should not be in a position where there may be the possibility of future contracts regarding the project being evaluated.

In agreement with UNEP, the part of the funds for TE under UNEP authorization ($15,000) will be directly transferred to UNDP by GEF once the CEO endorsement is approved. The terminal evaluation process will begin six months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the Evaluation Offices of UNEP and UNDP. The draft Terminal Evaluation report will be sent by the UNDP Evaluation Office to project stakeholders for comments. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six-point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the report is finalized and further reviewed by the GEF Independent Evaluation Office upon submission. The evaluation report will be publicly disclosed and may be followed by a recommendation compliance process. The management response and the evaluation will be uploaded to the GEF, UNEP, and UNDP corporate systems, which include the Project Information Management System (PIMS) and the UNDP Evaluation Office Evaluation Resource Centre in the case of UNDP.

The CBIT program country teams and other stakeholders will be actively involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate.

The final TE report and TE TOR will be publicly available in English and posted on the UNDP ERC by November 30, 2022.  A management response to the TE recommendations will be posted to the ERC within six weeks of the TE report’s completion.

Final Report:

The project’s terminal GEF PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Steering Committee during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

| Monitoring and Evaluation Plan and Budget: |  |  |  |
| --- | --- | --- | --- |
| GEF M&E requirements | Responsible Parties | Indicative costs (US$) | Time frame |
| Inception Workshop | Project Coordinator (UNDP) Project Manager (UNEP DTU) | 31,000 | Within 60 days of CEO endorsement of this project. Cannot be charged to GEF Fee. |
| Inception Report | Project Coordinator (UNDP) With the support of Project Manager (UNEP DTU) | None | Within 90 days of CEO endorsement of this project. |
| Monitoring of indicators in project results framework | Project Coordinator will oversee national institutions/agencies charged with collecting results data. | None | Annually prior to GEF PIR. This will include GEF core indicators. |
| GEF Project Implementation Report (PIR) | Project Coordinator (UNDP) | None | Annually typically between June-August |
| Monitoring all risks (Atlas risk log) | Project Coordinator | None | On-going. |
| Monitoring of stakeholder engagement plan | Project Stakeholder Engagement Officer | None | On-going. |
| Monitoring of gender action plan | Project Gender Officer | None | On-going. |
| Project Steering Committee Meetings | GEF IAs Project Coordinator | None | Annually. |
| Reports of Project Steering Committee Meetings | GEF IAs Project Coordinator | None | Annually. |
| Lessons learned and knowledge generation | Project Coordinator | None | Annually. |
| Oversight missions | UNDP-GEF Directorate | None | Troubleshooting as needed |
| Terminal GEF Core indicators | UNDP in conjunction with UNEP and UNEP DTU Partnership | None | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) and management response | UNDP Evaluation Specialists and independent evaluation consultants (UNDP with financial and technical support from UNEP) | 30,000 | Q4 2023 |
| TOTAL indicative COST |  | 61,000 |  |

# Governance and Management Arrangements

Institutional Coordination

Note on Implementation Arrangements: UNDP and UNEP will be the GEF Implementing Agencies (IAs) for the CBIT Phase IIA project and are responsible to the GEF for the use of project resources as written in the project document, or any amendments agreed. UNDP will serve as the implementing partner and will appoint a Project Coordinator as the primary point of contact. UNEP will be the responsible party for Component 1 and for Activity 2.2.4. In outputs where UNEP is a responsible party, it will either implement the outputs directly or it will delegate implementation of the outputs to its collaboration center, the UNEP DTU Partnership.  UNDP and its implementing partners will be responsible for day-to-day management of the project, including financial management and project reporting. Project administration will follow the procedures of UNDP and its implementing partners, including those related to procurement, contracting, and recruitment.

Note on Project Management: The Project Coordinator will report to the executive management group (EMG), which will be composed of representatives from UNEP (consisting of the project UNEP liaison officer and task manager), UNDP (the project coordinator and task manager), and the UNEP DTU Partnership (the project manager). The EMG will oversee the implementation of the project through monthly meetings. Its main functions will be to approve management decisions, including workplan and budget revisions, and ensure timely delivery of quality outputs. The main purpose of the EMG is to establish a very close coordination between UNEP and UNDP in order to ensure the execution of the activities of the four components as one single project.

Note on Project Oversight: The project will utilize a project steering committee (PSC), which will be composed of representatives from the following organizations: UNEP, UNDP, the UNEP DTU Partnership, the UNFCCC, the GEF Secretariat, one developed country; and one developing country. The committee will be responsible for reviewing project progress and providing strategic guidance to the EMG. The PSC will meet annually, unless one of the committee members calls for ad hoc interim meeting. Developing country representation on the PSC will provide a voice for project beneficiaries. The PSC meetings will be scheduled concurrently with other workshops or side events organized by the project to minimize and travel costs.

Roles and responsibilities of the project’s governance mechanism applied to component 2 with the exception of Activity 2.2.4:

Implementing Partner: The Implementing Partner for this project is UNDP IRH.

The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

Project stakeholders and target groups:  The proposed project is designed to prevent a gap in support to developing countries on transparency issues.  Project activities are therefore scheduled to transition from the CBIT Phase I project and the GSP into a unified Phase II support program. Figure 1 in this document provides an overview of the timing of this process.  The proposed project will also liaise with the planned CBIT projects to maintain an overview of the work being done in the sector.  Furthermore, the project will maintain contact with country-level projects under the CBIT funding window and country-level climate change enabling activities due to their focus on GHG inventories and reporting. Further, national experts working on CBIT country level projects will be actively engaged in the decision-making process of this initiative, by providing in person and written suggestions and ideas at the annual CBIT meetings. A stakeholder engagement plan is outlined in Annex 4 of this document.

UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is responsible for the Project Assurance role of the Project Steering Committee.  A strict firewall will be maintained between project oversight costs and personnel (called implementation by the GEF) and implementation of the project costs and personnel (called execution by the GEF).

Project organisation structure

Project Coordinator (UNDP IRH)

PMU (Project coordinator and project manager)

Project Steering Committee

Project Executive

UNDP

Istanbul Regional Hub Manager

Beneficiary Representatives

Beneficiary Country Representatives

Development Partners

UNDP, UNEP, UNEP DTU Partnership

Project Assurance

Regional Programme Specialist, UNDP IRH

Climate Mitigation Manager, UNDP

Task Manager, UNEP

Project Organisation Structure

UNEP DTU Partnership (Component 1 and

Activity 2.2.4)

UNDP (Component 2 with the exception of Activity 2.2.4)

Project Steering Committee:  The Project Steering Committee is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Steering Committee decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

In case consensus cannot be reached within the Board, the UNDP Istanbul Regional Hub for Europe and CIS (IRH) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

Specific responsibilities of the Project Steering Committee include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project manager’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

The composition of the Project Steering Committee must include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Steering Committee.

- Beneficiary Representative(s): Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. A Beneficiary representative will be appointed from among developing country Parties that have a GEF-funded CBIT project.

- Development Partner(s): Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partner(s) is/are: UNDP, UNEP and UNEP DTU Partnership.

- Project Assurance: UNDP performs the quality assurance role and supports the Project Steering Committee and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Steering Committee cannot delegate any of its quality assurance responsibilities to the Project Manager. UNDP provides multi – tier oversight services involving the UNDP Istanbul Regional Hub and UNDP Headquarters. Project assurance is totally independent of the Project Management function.

Project Coordinator: The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Project Steering Committee. The Implementing Partner appoints the Project Coordinator who must be different from the Implementing Partner’s representative in the Project Steering Committee.

The Project Coordinator’s primary responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Coordinator will inform the Project Steering Committee and the Project Assurance roles of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Project Coordinator will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed.

Specific responsibilities include:

- Manage the overall conduct of the project.

- Plan the activities of the project and monitor progress against the approved workplan.

- Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work.

- Monitor events as determined in the project monitoring plan, and update the plan as required.

- Provide support for completion of assessments required by UNDP, spot checks and audits.

- Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form.

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports.

- Monitor progress, watch for plan deviations and make course corrections when needed within project Steering Committee-agreed tolerances to achieve results.

- Ensure that changes are controlled and problems addressed.

- Perform regular progress reporting to the Project Steering Committee as agreed with the board, including measures to address challenges and opportunities.

- Prepare and submit financial reports to UNDP on a quarterly basis.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Steering Committee for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation.

- Prepare revisions to the multi-year workplan, as needed, as well as annual and quarterly plans if required.

- Prepare the inception report no later than one month after the inception workshop.

- Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Compile the GEF PIR;

- Assess major and minor amendments to the project within the parameters set by UNDP-GEF;

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans;

- Monitor and track progress against the GEF Core indicators.

- Support the Terminal Evaluation process.

# Financial Planning and Management

The total cost of the project is $2,400,000. This is financed through a GEF grant of $1,015,000 to UNDP, a GEF grant of $985,000 to UNEP, and $400,000 in other co-financing.  UNDP, as a GEF Implementing Agency, is responsible for the oversight of the GEF resources and the cash co-financing transferred to UNDP’s bank account only.

Confirmed Co-financing: The actual realization of project co-financing will be monitored during the terminal evaluation process and will be reported to the GEF. Co-financing will be used for the following project activities/outputs:

| Co-financing source | Co-financing type | Co-financing amount | Planned Co-financing Activities/Outputs |
| --- | --- | --- | --- |
| UNEP DTU Partnership | In kind | USD 50,000 | Content and features of the streamlined GSP/CBIT web platform maintained and updated |
|  | In kind | USD 350,000 | Knowledge products on the Paris Rulebook developed |

UNDP to provide direct project support services UNDP IRH will provide support services in the amount of $20,000 for the full duration of the project. To ensure the strict independence required by the GEF and in accordance with the UNDP Internal Control Framework, these execution services should be delivered independent from the GEF-specific oversight and quality assurance services (i.e. not done by same person to avoid conflict of interest).

Budget Revision and Tolerance: As per UNDP requirements outlined in the UNDP POPP, the Project Steering Committee will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project coordinator to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Steering Committee. Should the following deviations occur, the Project Coordinator and the UNDP Istanbul Regional Hub will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop.

Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, and if there is no increase of the project budget, one extension of the operational closure date beyond the initial duration of the project may be approved by the UNDP-GEF Directorate. However, all costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Steering Committee during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Steering Committee meeting. Operational closure must happen with 3 months of posting the TE report to the UNDP ERC. The Implementing Partner through a Project Steering Committee decision will notify the UNDP Istanbul Regional Hub when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the Project Steering Committee following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project management Unit (team) complete their assignments.

Financial completion (closure):  The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

The project will be financially completed within 6 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Istanbul Regional Hub will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Istanbul Regional Hub.

Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Directorate in New York. No action is required at the regional level on the actual refund from UNDP project to the GEF Trustee.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Award ID: | 00122005 | Atlas Output Project ID: | 00117767 |
| Atlas Proposal or Award Title: | CBIT II Phase A:Unif |  |  |
| Atlas Business Unit | SVK10 |  |  |
| Atlas Primary Output Project Title | Global CBIT II Phase A:Unified Support Platform-Paris Ag |  |  |
| UNDP-GEF PIMS No. | 6277 |  |  |
| Implementing Partner | UNDP |  |  |

| GEF Component/Atlas Activity | Responsible Party (Atlas Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | Description | Year 1 | Year 2 | Year 3 | Total | Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 2: Global stakeholder outreach and dissemination of best practice (with the exception of Activity 2.2.4, which will be implemented by UNEP and executed by the UNEP DTU Partnership) | UNDP | 62000 | CBIT/ GEF |  |  |  |  |  |  |  |
|  |  |  |  | 61300 | Salary & Post Adj Cst – IP Staff | 30,000 | 35,000 | 35,000 | 100,000 | L |
|  |  |  |  | 71200 | International Consultants | 43,000 | 74,000 | 70,000 | 187,000 | M |
|  |  |  |  | 71600 | Travel for workshops and international meetings | 10,000 | 10,000 | 10,000 | 30,000 | O |
|  |  |  |  | 75700 | Training, workshops and conferences | 179,000 | 186,000 | 177,000 | 542,000 | P |
|  |  |  |  | 74200 | Audio-visual and print production costs | 0 | 2,000 | 1,000 | 3,000 | Q |
|  |  |  |  | 74500 | Miscellaneous | 0 | 591 | 500 | 1,091 | R |
|  | Total of Component 2 |  |  |  |  | 262,000 | 307,591 | 293,500 | 863,091 |  |
| MONITORING AND EVALUATION | UNDP | 62000 | CBIT/ GEF | 71200 | International Consultant -- Terminal Evaluation | 0 | 0 | 30,000 | 30,000 | S |
|  |  |  |  | 75700 | Training, workshops, and conferences | 31,000 | 0 | 0 | 31,000 | T |
|  | Total of Monitoring and Evaluation |  |  |  |  | 31,000 | 0 | 30,000 | 61,000 |  |
| PROJECT MANAGEMENT COSTS (PMC) | UNDP | 62000 | CBIT/ GEF | 61200 | Salaries Cost -- GS Staff | 12,000 | 14,000 | 14,000 | 40,000 | U |
|  |  |  |  | 61300 | Salary & Post Adj Cost – IP Staff | 7,000 | 7,000 | 7,000 | 21,000 | U |
|  |  |  |  | 74100 | Professional Services -- Audit | 3,000 | 3,000 | 3,000 | 9,000 | V |
|  |  |  |  | 74500 | Miscellaneous | 909 | 0 | 0 | 909 | W |
|  |  |  |  | 74596 | Direct Project Costs - General Operating Expenses (GOE) | 6,000 | 7,000 | 7,000 | 20,000 | X |
|  | Total for Project Management Costs |  |  |  |  | 28,909 | 31,000 | 31,000 | 90,909 |  |
|  | GRAND TOTAL |  |  |  |  | 321,909 | 338,591 | 354,500 | 1,015,000 |  |
|  | Budget Notes | Description |  |  |  |  |  |
|  | L | Cost-shared salary of Project Coordinator for technical support to all activities under Component 2 with the exception of 2.2.4 |  |  |  |  |  |
|  | M | IC / Transparency Expert in support of Outputs 2.1, 2.2., 2.3, and 2.4 |  |  |  |  |  |
|  | O | Travel Expenses for UNDP project team in support of Outputs 2.1, 2.2, 2.3, and 2.4 |  |  |  |  |  |
|  | P | Workshops and meetings costs to be held under outputs 2.1 and 2.4 (annual stocktaking and gender workshops) |  |  |  |  |  |
|  | Q | Production costs for knowledge materials in support of all outputs under Component 2 |  |  |  |  |  |
|  | R | Miscellaneous expenses for workshops under Outputs 2.1 and 2.4 |  |  |  |  |  |
|  | S | IC for Terminal Evaluation (In agreement with UNEP, the part of the funds for TE under UNEP authorization ($15,000) will be directly transferred to UNDP by GEF once the CEO endorsement is approved.) |  |  |  |  |  |
|  | T | Inception Workshop for Project |  |  |  |  |  |
|  | U | Cost-shared salary of Project Coordinator and Project Associate for coordination-managerial support to the project |  |  |  |  |  |
|  | V | Annual audit of project (@ $3,000 / year) as per UNDP audit policies |  |  |  |  |  |
|  | W | Miscellaneous expenses for project management unit |  |  |  |  |  |
|  | X | Direct Project Services to project - GOE for IRH: support services to be provided by UNDP IRH (estimated $20,000 for total project) |  |  |  |  |  |

Summary of Funds:

|  | $321,909 | $338,591 | $354,500 | $1,015,000 |
| --- | --- | --- | --- | --- |
| GEF (Implemented by UNEP) | $415,856 | $371,000 | $198,144 | $985,000 |
| UNEP DTU Partnership (In Kind) | $130,000 | $135,000 | $135,000 | $400,000 |
| TOTAL | $867,765 | $844,591 | $687,644 | $2,400,000 |

# Legal Context

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures, only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The designations employed do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations or UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - In the performance of the activities under this Project, UNDP as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or address SEA and SH.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# Mandatory Annexes

- Project Map and geospatial coordinates of the project area

- Multiyear Workplan

- Monitoring Plan

- Stakeholder Engagement Plan

- UNDP Atlas Risk Log

- Overview of technical consultancies/subcontracts

- Terms of Reference for Technical services to be provided by UNDP, the Project Steering Committee, Project Manager, Chief Technical Advisor and other positions as appropriate

- SESP (as a separate document)

- Gender Analysis and Gender Action Plan

- Procurement Plan – for first year of implementation especially

- Theory of Change

- GEF Core indicators

- GEF Taxonomy

## Annex 1: Project map and Geospatial Coordinates of project sites

N/A: global project.

## Annex 2: Multi-Year Work Plan

Note: Shaded areas represent outputs and activities that will be undertaken by UNEP under its role as a joint implementing agency for the project.

## Annex 3: Monitoring Plan:

This Monitoring Plan and the M&E Plan and Budget in Section VI of this project document will both guide monitoring and evaluation at the project level for the duration of project implementation.

| Monitoring | Indicators | Targets | Description of indicators and targets | Data source/Collection Methods | Frequency | Responsible for data collection | Means of verification | Risks/Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project objective from the results framework: To provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. | Indicator 1 # of project beneficiaries disaggregated by gender (individual people) | By the end of the project, at least 300 people will utilize support for transparency and reporting from project outputs and activities, and at least 150 of them will be women. | The indicator is a mandatory GEF indicator; the target was derived using GEF methodology and extrapolating from experience with CBIT Phase I activities. | The baseline figure of 150 beneficiaries reflects data collected during CBIT Phase I activities according to GEF guidance. Data will continue to be collected on project beneficiaries according to GEF and any relevant supplementary UNDP and UNEP guidance. | Annually Reported in DO tab of the GEF PIR | UNDP Project Coordinator | Reporting by CBIT Project Countries and project documentation that includes registration lists for webinars, trainings, and other in-person or on-line gatherings or discussion. | Risks: The risk that the reach of the project will not expand is minimal. Assumptions: The assumptions that the number of stakeholders will increase is consistent with an increase in applications for country-level CBIT project support from the GEF. |
|  | Indicator 2: % of the users surveyed who consider the platform (website, its features, and knowledge products) very useful or useful for their purposes | By the end of the project, 70% of users surveyed consider the platform to be very useful or useful for their purposes (measured as a score of 4 or 5 on a 5-point satisfaction scale) | The indicator was selected because of its focus on user satisfaction (as this is a project designed to provide support) and due to the potential for comparison with the CBIT Phase I project. | As the integrated platform does not yet exist, there is not a baseline figure for this indicator. User surveys will be administered directly to website users and also during the stocktaking workshops under Output 2.1. | Annually Reported to the Project Steering Committee (PSC) and in the terminal evaluation (TE) | UNEP DTU | Pop-up survey conducted on the streamlined website. | Risks: Specific elements of satisfaction will be difficult to assess. This risk will be mitigated by qualitative follow-up questions in surveys. Assumptions: The project assumes that stakeholders will be open and forthcoming in their ratings. |
| Project Outcome 1 Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements | Indicator 3: Knowledge demand / uptake: i.e., number of countries and practitioners using the platform’s services and knowledge products every quarter (on average) | By the end of the project, at least 60 stakeholders use the platform’s services every quarter (on average) | This indicator was selected on the basis of capturing the utility of support provided and due to the possibility to compare with data collected under CBIT Phase I. | The baseline figure of at least 40 countries and practitioners was derived from surveys conducted under Phase I. A similar approach will be used under Phase II so that the data are comparable. | Quarterly Reported annually to the PSC. Reported in the TE. | UNEP DTU | Website analytics. Country and practitioner feedback collected in the course of the Terminal Evaluation by the evaluator(s). | Risks: Beneficiaries will not have sufficient time or interest to use the platform (this risk is low, as platform reporting is an integral part of the work of the country projects). Assumptions: Countries and other transparency practitioners will continue to utilize the platform. |
| Project Outcome 2 Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming. | Indicator 4 Number of developing countries with beneficiaries who have shared their lessons (progress, support needed and received, and/or good practice) through project activities. | Experiences from more than 60 developing country beneficiaries have been documented through annual self-reporting exercises, such as question-naires in advance of technical workshops and implementation reports and / or through workshops and regional meetings supported by this project. | This indicator was selected in order to capture the element of south-south knowledge exchange and due to comparability with data collected under CBIT Phase I. | The baseline figure of project beneficiaries from more than 40 countries was gathered under Phase I. A similar approach will be used under Phase II so that the data are comparable. | Quarterly. Reported annually to the PSC. Reported in the TE. | UNEP DTU Project Manager (for Activity 2.2.4) and UNDP Project Coordinator (for all other project elements) | Lists of countries participating in regional and global workshops based on registration data; information from questionnaires collected in advance of technical workshops and other content on the streamlined platform; and Project Implementation Reports for country-level CBIT projects. Structured interviews conducted in the course of the terminal evaluation by the evaluator | Risks: Beneficiaries will not have sufficient time or interest to participate in project activities. Assumptions: Countries and other transparency practitioners will continue to participate actively in CBIT-related activities. |
|  | Indicator 5 Number of developing countries sharing good practice in gender mainstreaming on the streamlined CBIT web platform | By the end of the project, good practice in gender mainstreaming from at least 15 developing countries is shared on the streamlined platform. | This indicator was selected in order to capture the element of south-south knowledge exchange related to gender equality and transparency quickly. | As the platform will be new, there is not a baseline figure for participation. Content will be reviewed on the website to determine the presence of good practice related to gender equality. | Quarterly. Reported annually to the PSC. Reported in the TE. | UNDP Project Coordi-nator | Review of project documentation and platform content in the course of the Terminal Evaluation by the evaluator(s). | Risks: Beneficiaries will not have sufficient time or interest to participate in gender equality-related project activities (this risk is low, as these activities form an integral part of many country-level CBIT projects). Assumptions: Countries and other transparency practitioners will utilize the materials on the platform. |

## Annex 4: Stakeholder Engagement Plan

The following table presents an overview of relevant stakeholders and their proposed role in the project.

| Name of Institution | Type of Stakeholder | Role in the Project |
| --- | --- | --- |
| UNEP | Joint GEF Implementing Agency | UNEP is a GEF implementing agency that will also serve as the implementing agency for Component 1 of the project and for Activity 2.2.4. It will play a key role in facilitating coordination and knowledge sharing among the national CBIT projects in its portfolio. |
| UNEP DTU Partnership | Executing Agency for the project | The UNEP DTU Partnership will serve as an executing agency for selected project outputs implemented by UNEP. The UNEP DTU Partnership will also provide in-kind co-financing for capacity building and analytical support related to transparency, particularly in the area of adaptation and for project management. |
| Food and Agriculture Organization of the United Nations (FAO), Conservation International (CI), and others | Other GEF implement-ing agencies | Other GEF implementing agencies will share materials developed through other global CBIT projects and will coordinate on training. The CBIT Phase II project will serve as a means of disseminating information resources, guidance, and good practice from the FAO-GEF project on agriculture, forestry, and other land use (AFOLU) following that project’s scheduled conclusion and will include a dedicated space where pilot countries can interact. Finally, the project will provide a broader means of distribution for training materials developed under country-level CBIT project implemented by other agencies (i.e. CI) and will involve those project managers and experts in global platform meetings and activities. |
| Initiative for Climate Action Transparency (ICAT), Partnership on Transparency in the Paris Agreement (PATPA), International Partnership on Mitigation and MRV, Paris Committee on Capacity Building (PCCB), Partnership to Strengthen Transparency for co-Innovation (PaSTI) | Other transparency support initiatives | The information available through the library and other sections of the integrated web platform and the development and content of training modules will be coordinated with a network of existing transparency support initiatives. The integrated web platform will contain links to the platforms, databases, and on-line tools that have been developed through these partnerships. For example, ICAT will share its series of guidance documents on transparency with the project beneficiaries. The CBIT integrated web platform and newsletter will also provide information on learning events sponsored by these initiatives, such as PCCB capacity building forums and PaSTI webinars. |
| Countries with GEF-funded CBIT projects | National governments | Participating countries will provide information regarding their national CBIT project, participate in knowledge exchange, collaborate in the creation of content for the platform. |
| Development Partners | International Organisations and developed country governments | These partners will coordinate existing and upcoming support to develop national capacity globally to support countries meeting the Paris Agreement Article 13 requirements. |
| Civil Society Organizations (CSOs) | NGOs (national, sub-regional, regional, and international) and research institutes | International NGOs such as the World Resources Institute (WRI) participated in CBIT technical workshops under Phase I, contributing their expertise, and they are expected to continue to do so. In addition, the project will exchange information with CSO partners; e.g. the BUR database to be maintained by the Institute for Global Environmental Strategies (IGES). The project will also exchange information with regional and sub-regional CSOs; e.g., with Fundacion Bariloche for the Latin America and Caribbean region. Non-governmental actors at the country level are expected to benefit through the increased availability and quality of climate change information and through more robust NDCs. In addition, the project will support the two-way exchange of information with regional and international CSOs that support gender equality and women’s participation, such as the European Institute of Gender Equality, to inform the deliverables under Output 2.4. |
| UNFCCC | International organization | The UNFCCC and its secretariat will play three important roles in project implementation. First, the secretariat will serve as a provider for capacity building related to the UNFCCC. Second, the Secretariat, which houses the 24-member Consultative Group of Experts (CGE) and its e-Network, will exchange information with the project. Third, it will play a facilitating role in the implementation of the Convention. |
| UNFCCC Parties | All countries | All parties to the UNFCCC are expected to provide information and participate in discussions and information exchanges. A representative of one developing and one developed country government will serve on the Project Steering Committee (see Section II.6). |

## Annex 5: UNDP Risk Log

| # |  | Description | Date Identified | Risk Category | Impact & Probability | Risk Treatment / Management Measures | Risk Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | The integrated platform is not perceived as relevant by users and fails to attract traffic |  | Operational | The ability of the platform to disseminate information would be limited by low usage. P = 2 I = 3 | New and unique content will be available on the platform; countries will report to the platform. | Project Coordinator |  |
| 2 |  | Stocktaking workshops and side events fail to attract sufficiently high-level decision-makers and practitioners |  | Organizational | Dissemination of information would be limited; policy-maker capacity would not be strengthened to as great an extent P = 2 I = 3 | Workshop organizers will focus on timely topics and schedule workshops in conjunction with high-level events. | Project Coordinator |  |
| 3 |  | High turnover of participants due to high turnover of political appointees and civil servants in participating countries |  | Political | Capacity strengthening and training activities will have a limited benefit. P = 3 I = 4 | ‘Stream’ training to incorporate newcomers; document and archive procedures to improve continuity. | Project Coordinator |  |

## Annex 6: Overview of Technical Consultancies

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management / Monitoring & Evaluation |  |  |
| International / Regional and global contracting |  |  |
| Company contract for Terminal Evaluation (lump sum) | Q12 of the project | See the full TOR below for details. |
| For Technical Assistance |  |  |
| Outcome 2 |  |  |
| International / Regional and global contracting |  |  |
| IC / Facilitator Rate: USD 500/day plus travel | 20 days/year, over 3 years | - For Output 2.1, the consultant will provide support to global stocktaking meetings organized by the project. Full TOR is provided below in Annex 7. |
| IC /Gender Rate: USD 300/day | 100 days/year over 3 years | For Output 2.4, the consultant will carry out the following tasks: - Provide reviews of national reports and supporting documentation in response to country requests - Provide the primary inputs for an updated toolkit on integrating the UNFCCC Gender Action Plan into national transparency frameworks that will build upon the current GSP toolkit (Gender Responsive National Communications and BURs). - Provide preparatory support for at least four regional workshops on integrating gender analysis and the UNFCCC Gender Action Plan into national reporting and transparency - Collect and analyse country reporting with regards to gender mainstreaming and integration of the Gender Action Plan in support of the annual stocktaking under Output 2.1 Full TOR is provided below in Annex 7. |

## Annex 7: Terms of References

Terms of Reference for Key Project Staff

Project Coordinator

Background

The Project Coordinator (PC) will work under overall supervision of the UNDP IRH Manager. The coordinator will implement both coordination-management tasks as well as technical tasks, with an estimated distribution of labor of 83% technical support and 17% coordination-management tasks.

Duties and Responsibilities

Coordination-management tasks

- In cooperation with EMG, supervises and ensures the timely implementation of the project relevant activities as scheduled in the working plan

- Prepares a detailed work plan for the project and draft terms of reference for the subcontracts (in consultation with the EMG and PSC);

- Identifies and hires/subcontracts experts and institutions as needed for project activities;

- In cooperation with the EMG, supervises project support staff and consultants who are recruited to provide technical assistance as needed;

- Organizes and supervises the workshops and training needed during the project;

- Liaises with the developing country Parties, support providers, and NGOs in order to gather and disseminate information relevant to the project;

- Manages and monitors the project risks initially identified and submits new risks to the EMG and PSC for consideration and decision on possible actions if required; updates the status of these risks by maintaining the project risks log.

- Ensures timely submission of the Inception Report, Project Implementation Report, Technical reports, quarterly financial reports, and other reports as may be required by UNEP, UNDP, GEF and other oversight agencies.

- Controls the expenditures and otherwise ensure adequate management of the resources provided for the project;

- In cooperation with the EMG, summarizes and synthesizes the results of the project;

- Identifies follow-up activities and mobilizes other resources at the extent possible;

- Identifies and ensures synergy of the projects’ activities with other relevant ongoing / new projects.

- Collaborates with all relevant stakeholders and the Project Steering Committee and other partners to ensure their involvement in project activities.

Technical tasks

- Ensures that project activities are in the line with guidance provided by the CoP of the UNFCCC and contributes to the improvement of the UNFCCC reporting process and decisions relevant to Article 13 of the Paris Agreement.

- Engage directly with developing countries representatives and provide them with sound technical backstopping on all different topics covered by CBIT, including not limited to, elaboration of greenhouse gas inventories, development of emission mitigation scenarios, establishment of MRV systems, support to NDC tracking, establishment of monitoring and evaluation frameworks for adaptation.

- Provide sound advice and implement work to support countries in integrating gender equality considerations into the enhanced transparency framework, as established under 2.4

- Follows the process of international negotiations in the UNFCCC and respective decisions related to reporting of non-Annex 1 Parties and particularly in relation to the Paris Rulebook.

Required skills and expertise

- A university degree (MSc or PhD) in a subject related to natural resource management or environmental sciences.

- At least 5 years of demonstrable project/programme management experience.

- At least 5 years of experience working with ministries, national or provincial institutions that are concerned with natural resource and/or environmental management.

Competencies

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise multiple Project Implementation Units in their implementation of technical activities in partnership with a variety of subnational stakeholder groups, including community and government.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, especially in timely and accurate responses to emails.

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet search.

- Strong knowledge about the political and socio-economic context related to the Indonesian protected area system, biodiversity conservation and law enforcement at national and subnational levels.

- Excellent command of English and local languages.

Project Associate

Under the guidance and supervision of the Project Coordinator, the Project Associate will carry out the following tasks:

Duties and Responsibilities

- Manage the day to day operations of the Project Management Unit, particularly with respect to the provision of technical services and support .

- Assist the Project Coordinator in the implementation of technical and operational activities for the preparation of the outputs under the project.

- Review technical and support information on climate change studies, projects and initiatives that may contribute to the project activities.

- Support the preparation of detailed terms of reference for the international and local consultants and experts to be hired for the implementation of the project as needed.

- Assist the Project Coordinator in the selection process of the consultants, including the consultant(s) for the Terminal Evaluation, to be hired by the Project according to the rules and procedures established by UNDP.

- Participate in the planning, organization and execution of Project activities.

- Support the organization and coordination of seminars, training activities, workshops, and other exchange and facilitation events for project stakeholders.

- Organize and coordinate information exchanges internationally and between participating institutions as necessary.

- Compile and/or prepare the documentation necessary for the procurement of services, good and supplies under the project

- Prepare administrative, technical and financial reports.

- Perform the procurement of services, good and supplies authorized by the Project Coordinator.

- Prepare requests for the payment as authorized by the Project Coordinator

- Assist the Coordinator in monitoring disbursements in accordance with the Project Budget and Disbursement Plan.

- Maintain the Project’s files and supporting documentation for payments.

- Undertake other administrative/ financial duties as requested by the Project Coordinator

- Other duties which may be required

Required skills and expertise

- A Bachelors degree or an equivalent qualification;

- At least five years of work experience preferably in a project involving biodiversity conservation, natural resource management and/or sustainable livelihoods. Previous experience with UN project will be a definite asset;

- Very good inter-personal skills;

- Proficiency in the use of computer software applications especially MS Word and MS Excel.

- Excellent language skills in English (writing, speaking and reading) and in local languages

IC / Terminal Evaluator

Under the guidance and supervision of the Project Coordinator, the contractor for the terminal evaluation will carry out the following tasks:

- Lead the mid-term and/or the final evaluations (these evaluations will be contracted separately and may involve two different consultants).

- Work with the project team in order to assess the project progress, achievement of results and impacts.

- Disaggregate findings by gender, to the extent possible, and include quantitative and qualitative data regarding the project activities

- Develop and present a draft evaluation report, discuss it with the project team, government and UNDP, and submit a final report.

- Contribute on an as-needed basis in discussions to extract lessons for UNDP and GEF.

IC / Transparency Expert

The consultant will closely work to support the GSP- CBIT platform in the development and facilitation of the following Transparency workshops both in the part regarding the coordination meeting as well as the technical workshop.

The consultant’s tasks will be the following:

- To provide support for the implementation of all activities under Component 2 of the project with the exception of Activity 2.2.4.

- To support the GSP in the design and implementation of the workshops. In this phase, virtual meetings will be held in order to identify key elements and construct the guide for the facilitation process of the meeting, based on lessons learnt from previous events and on UNDP capacity development principles;

- To facilitate the coordination meeting and the technical workshop by using participatory methodologies following the guide for the facilitation process. The facilitator will facilitate in English. The consultant will need to have background knowledge on MRV, ensure full implementation of the agenda, facilitate the transition from one resource person to another, ensure participants’ active engagement in the discussions, coordinate Question and Answers sessions and facilitate the practical exercises during the event;

- To prepare two short reports describing the results from both the coordination meeting and the technical workshops. The format of the report will be provided by the GSP, upon suggestions by the consultant, and will include a synthesis of the event, identified lessons relevant for GSP’s work as well as recommendations for future activities of The CBIT platform.

Required Skills and Experience

Education:

- A minimum of a Master’s degree or equivalent in sustainable development, economics, engineering or a related field.

Experience:

- At least 8 years of professional experience facilitating workshops, retreats and other interventions is required;

- At least 4 proven assignments on leading and facilitating trainings, workshops and capacity building activities in the field of international development, climate change and or UNFCCC intergovernmental process is required;

- Preferable to have experience in environment, climate change and greenhouse gas emissions in the developing countries;

- Preferable hands-on experience in the design and facilitation of multi-stakeholder meetings involving large international organizations (such as UN), with an experience in facilitating participation in team work in such settings;

- Preferable experience working with the United Nations system/UNDP/similar organisations, their expertise, practices, and procedures; particularly in conflict-affected and fragile areas;

Language:

Excellent writing, editing, and oral communication skills in English is required.

IC/ Consultant on Gender and Climate Change

The consultant will closely work to support the GSP- CBIT platform in all activities related to gender and climate change mainstreaming. His/her responsibilities will be: - Provide technical assistance to each Network (Latin American and Balkan) to help them elaborate, refine and finalize their substantive gender/climate transparency work plans – as part of the work nationally implemented under NCs/BURs/CBIT - Assist in the implementation of the “Gender responsive National Communications Toolkit” in the Western Balkan + Lebanon and other regions (e.g. providing input to the national teams in drafting ToRs or providing peer review of relevant documents prepared by other consultants) - Update the Gender Responsive National Communications toolkit in light of new COP requirements and lessons learnt; - Support developing Countries in increasing the nomination of UNFCCC gender focal points; - Support the constructive collaboration among the member countries, including leading workshops, dialogue meetings, webinars and virtual interactions (e.g. emails and web). - Provide technical inputs to and facilitate the identification, design and roll-out of substantial initiatives at the regional and national levels, including but not limited to raise awareness and to enhance institutional collaboration between institutions and other relevant actors (ex. Ministries dealing with gender issues). - Design the agenda and facilitate the Network workshop on gender responsiveness to climate change actions if any. - Provide technical inputs for elaborating training materials and carry on in-country trainings on gender responsiveness on climate change actions. - Assist the GSP coordinator in providing inputs for terms of reference, concept notes, webinars, translate documents and elaborate technical documents - Support tasks related to the needs of the Network

##### Required Skills and Experience

Academic Qualifications/Education:

- Master’s degree or equivalent in sustainable development, economics, public administration, social sciences, gender studies or a related field

Experience:

- At least 3 years of substantive professional experience in design, monitoring or evaluation of gender projects.

- At least 2 years of working experience in the design, analysis, evaluation of climate change mitigation or adaptation projects/initiatives

- Demonstrated experience on gender mainstreaming in climate change/environment/sustainable development

- Preferable experience working on policy and programmatic issues with national and local governments and civil society organizations including community organizations

- On-the-ground work experience in the Western Balkan region or Latin America on gender or climate change/environment/sustainable development is an asset

- Desirable experience working with international organizations related to climate change or gender

Language skills:

- Fluency in written and spoken of English, other UN language is an asset.

## Annex 8: Social and Environmental Screening Procedure (SESP)

This annex is sent as a separate document and included as Annex O in CEO Endorsement.

## Annex 9: Initial Gender Analysis and Gender Action Plan

Initial Gender Analysis

Developing country parties of the UNFCCC and the Paris Agreement vary in terms of gender equality and women’s empowerment. According to the Gender Development Index (GDI) data for 2017, the global GDI value is 0.941, while the average value for least developed countries is 0.868. It should be noted some countries with national CBIT projects have GDI values higher than the global average, while others have values that are lower.

According to the Global Gender Gap Report 2018, the global gender gap score, another measure of parity, is currently 68%. The 2018 report notes that “Across the four sub-indexes, on average, the largest gender disparity is on Political Empowerment, which today maintains a gap of 77.1%. The Economic Participation and Opportunity gap is the second-largest at 41.9%....”  Again, developing country Parties vary widely in their scores and in some cases have achieved high levels of parity by global standards; for example, Nicaragua and Rwanda are fifth and sixth in the global rankings, respectively.

Developing country Parties that have signed the 2015 UN Sustainable Development Goals (SDGs) have committed to progress under SDG 5: “Achieve gender equality and empower all women and girls.” Under this goal, countries are to achieve nine specific targets that include the following relevant targets for this project: “Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision making in political, economic and public life;” and “Enhance the use of enabling technology, in particular information and communications technology, to promote the empowerment of women.” Countries also commit to monitor progress towards the targets that have been established.

As the introduction to the 2017 UN Women guidebook Leveraging Co-Benefits between Gender Equality and Climate Action notes, “Gender mainstreaming is not simply about adding a ‘women’s component.’ Gender mainstreaming is about thinking differently, modifying climate and development interventions so that they will benefit men and women equally. It is about transforming social, economic and institutional structures towards gender equality and women’s empowerment in climate action and resilience building. The impacts of climate change, including on access to productive and natural resources, amplify existing gender inequalities. Climate change affects women’s and men’s assets and well-being differently in terms of agricultural production, food security, health, water and energy resources, climate-induced migration and conflict, and climate-related natural disasters. At the same time, women are powerful change agents to address climate change at scale. They are key actors in building community resilience and responding to climate-related disasters. Women tend to make decisions about resource use and investments in the interest and welfare of their children, families, and communities.”

The UNFCCC Gender Action Plan was established under UNFCCC 3/CP.23 Section E of the Action Plan specifically focuses on monitoring and reporting, and it states that “The GAP seeks to improve tracking in relation to the implementation of and reporting on gender-related mandates under the UNFCCC.” The Paris Agreement has highlighted gender equality and women’s empowerment as a guiding principle and called for adaptation and capacity-building actions to be implemented in a gender-responsive manner.

In 2016, 40% of the (I)NDCs mentioned women and/or gender in the context of their national priorities and ambitions for reducing emissions. However, developing countries will require support in monitoring progress regarding these ambitions. In the area of reporting, a number of developing countries do not mention gender equality issues / priorities in their National Communications and BURs. Revised NDCs and the advent of BTRs will necessitate capacity strengthening in developing countries related to gender equality and women’s empowerment as they relate to reporting and transparency.  At the same time, a number of developing country Parties have experience in improving gender parity in climate change decision-making at a national level that is relevant to others.

Gender Action Plan

| Objective | Action | Indicator | Responsible Institution |
| --- | --- | --- | --- |
| Component 1: Streamlined development and delivery of knowledge in support of Article 13 |  |  |  |
| Promote women’s representation and active participation in capacity strengthening activities and in the platform for online peer learning. | Monitor women participation in the website- platform: conduct surveys with different website users’ groups and analyze usage patterns (disaggregated by gender) Monitor representation in training activities (peer learning exchanges, webinars) related to CBIT Ensure knowledge products on the Paris Rulebook and other reporting under UNFCCC mainstream gender | % of women representatives in the CBIT platform % of women participating in training activities under Component 1 Presence of documented analysis that mainstreams gender considerations | UNEP, Project Manager |
| Component 2: Global stakeholder outreach and dissemination of best practices |  |  |  |
| Ensure gender equality dimension are addressed in the annual global stocktaking meetings, and all dialogues related to UNFCCC activities | Encourage and monitor representation in the three annual global stocktaking meetings, COPs side events, and regional workshops Ensure climate national reports are mainstreaming gender Ensure the UNFCCC Gender Action Plan will support the updated of the GSP toolkit (Gender Responsive National Communications and BURs) Increase number of UNFCCC gender focal points Conduct capacity building on gender mainstreaming in climate change activities Ensure data collection and analysis on gender mainstreaming in climate transparency (i.e. NCs, BURs and CBIT projects) | Number of the professional trained on gender equality issues / on gender mainstreaming (disaggregated by gender) under Component 2 Number of documents analysis that mainstreams gender considerations (as of total) Presence of UNFCCC gender considerations in the updated toolkit Number of UNFCCC gender focal points Four regional workshops done on integrating gender in UNFCCC activities At least five best practices of gender mainstreaming on NCs and BURs developed based on the analysis done | UNDP, Project Coordinator |
| Monitoring and Evaluation / Project Management |  |  |  |
| Increase understanding of how project benefits may vary by gender | Include gender issues in the scope of work for the Mid-Term and Terminal Evaluation of the project. | At the mid-point and the end of the project, gender-disaggregated findings, including quantitative and qualitative data, are available regarding the project approach and activities. | UNEP and UNDP |
| Raise awareness regarding gender mainstreaming in transparency frameworks | Consult both men and women in the development of promotional materials Assess the most appropriate communication channels for disseminating information about project activities, keeping in mind that they may be different for girls and women as opposed to boys and men. | Increase in awareness levels regarding climate change issues among both men and women The project communication strategy utilizes men’s and women’s communication channels | UNEP and UNDP |

## Annex 10: Procurement Plan

The procurement plan will cover a 12 months’ period. UNDP shall update the procurement plan throughout the duration of the project at least annually by including contracts previously awarded. All procurement plans, their updates or modifications shall be published on the website of UNDP.

General Information

| Project Name: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase II A: Unified Support Platform and Program for Article 13 of the Paris Agreement |  |
| --- | --- |
| Country: Global | Executing Agency: UNDP |
| GEF Grant Amount: US$ 1,015,000 |  |
| Date of First Procurement Plan: Quarter 1/Year 1 | Date of this Procurement Plan: September 2019 |

- Process Thresholds, Review and 12 Month Procurement Plan

  - Project Procurement Thresholds

- The following UNDP procurement thresholds shall apply to procurement of goods and works:

| Procurement method | Contract value | Type of requirement | Method of solicitation | Type of completion |
| --- | --- | --- | --- | --- |
| Micro purchasing | Below $ 10,000 | Goods & Works | Canvassing (by phone, internet, shopping, etc.) | Limited international or national |
| Request for quotation | $10,000 to $149,999 | Goods & Works | Written request for quotation | Limited international or national |
| Invitation to bid | 150,000 and above | Goods & Works | Advertisement in international media | Open international |
| Desk review | 150,000 and above | Consulting Services | Competitive sourcing | Open international |
| Advertisement | $150,000 an above | Consulting Services/ Staff/ UN volunteers | Advertisement in international/national media | Open international/national |

  - Prior or Post Review

- The following UNDP prior or post review requirements apply to the various procurement and consultant recruitment methods used for the project.

Please see below for UNDP Policy on Prior and Post Review.

  - Goods and Works Contracts Estimated : 184,000 US$

- The following table lists goods and works contracts for which procurement activity is expected to commence within the first 12 months.

| General Description | Contract Value (US$) | Procurement Method | Prequalification of Bidders (y/n) | Advertisement Date (quarter/year) |
| --- | --- | --- | --- | --- |
| Provision of conference and catering services for annual global stocktaking meeting | 20,000 | Request for quotation | No | Q2 / Y1 |
| Provision of transportation services for the participants of annual global stocktaking meeting | 80,000 | Request for Quotation | In line with LTA prequalification | Q2 / Y1 |
| Provision of conference and catering services for side events for upcoming COPs and subsidiary body (SB) meetings | 10,000 | Micro purchasing | No | Q3 / Y1 |
| Provision of transportation services for the participants of annual side events for upcoming COPs and subsidiary body (SB) meetings | 15,000 | Request for Quotation | In line with LTA prequalification | Q3 / Y1 |
| Provision of conference and catering services for the coordination meeting | 10,000 | Micro purchasing | No | Q4 / Y1 |
| Provision of transportation services for the participants of the coordination meeting | 10,000 | Request for Quotation | In line with LTA prequalification | Q4 / Y1 |
| Provision of conference and catering services for annual regional gender workshop | 10,000 | Micro purchasing | No | Q3 / Y1 |
| Provision of transportation services for the participants of annual regional gender workshop | 25,000 | Request for Quotation | In line with LTA prequalification | Q3 / Y1 |
| Procurement of Office Supplies (Miscellaneous Expenses) | 3,000 | Micro purchasing | No | Q1 / Y1 |
| Communication, Printing and production of documents | 1,000 | Micro purchasing | No | Q2 / Y1 |

  - Consulting Services Contracts Estimated: 70,000 US$

- The following table lists consulting services contracts for which procurement activity is either ongoing or expected to commence within the first 12 months.

| General Description | Contract Value (US$) | Recruitment Method1 | Advertisement Date (quarter/year) | International or National Assignment |
| --- | --- | --- | --- | --- |
| Individual Consultant to assist in organization and facilitate global stocktaking meetings organized by the project | 10,000 | Advertisement | Q2 / Y1 | International |
| Individual Consultant to assist in integration of the UNFCCC Gender Action Plan into enhanced transparency frameworks | 30,000 | Advertisement | Q2 / Y1 | International/National |
| Consultancy Firm or Individual Consultant for Terminal Evaluation | 30,000 | Request for Proposal or Advertisement | Q4 / Y3 | International/National |

- Indicative List of Packages Required Under the Project

- The following table provides an indicative list of all procurement (goods, works and consulting services) over the life of the project.

PROCUREMENT METHOD 1: GOODS

| General Description | Estimated Value (cumulative) | Estimated Number of Contracts | Procurement Method 1 | Comments |
| --- | --- | --- | --- | --- |
| Audio Visual & Print Prod Costs | 9,000 | 3 | Micro purchasing | Goods |
| Supplies- Miscellaneous Expenses | 3,000 | 3 | Micro purchasing | Goods |

PROCUREMENT METHOD 2: GOODS & SERVICES

| General Description | Estimated Value (cumulative) | Estimated Number of Contracts | Procurement Method 2 | Comments |
| --- | --- | --- | --- | --- |
| Training, Workshops, Conferences | 150,000 | 10 | Request for quotation | Goods and services |
| Travel (Participants) | 390,000 | 1 | Request for quotation (LTA) | Goods and services |
| Travel | 30,000 | 1 | Request for quotation (LTA) | Goods and services |

RECRUITMENT METHOD 1: CONSULTANCIES

| General Description | Estimated Value (cumulative) | Estimated Number of Contracts | Recruitment Method 1 | Comments |
| --- | --- | --- | --- | --- |
| Contractual Services - Companies / Int-Serv (IC Terminal Evaluator) | 30,000 | 1 | International Advert | Services |
| Contractual Services – Individ (Gender Consultant) | 30,000 | 1 | International Advert | Services |

RECRUITMENT METHOD 2: CONSULTANCIES

| General Description | Estimated Value (cumulative) | Estimated Number of Contracts | Recruitment Method 2 | Comments |
| --- | --- | --- | --- | --- |
| Contractual Services - Individ | 90,800 | 3 | Desk review | Services |

- UNDP Policy on Prior and Post Review

|  | Level 1 (Country Level): Contracts, Assets and Procurement Committee | Level 2 (Regional): Regional Advisory Committee on Procurement (country offices only) | Level 3 (HQ): Advisory Committee on Procurement |
| --- | --- | --- | --- |
| Competitive procurement process |  |  |  |
| Any contract or series of contracts including amendments to be awarded to a vendor in a calendar year that in aggregate has a cumulative value: | Above US $50,000 (above US $100,000 for Individual Contracts) and up to the standard delegated procurement authority – Direct Review by CAP Chairperson Above the standard delegated procurement authority and up to any increased delegated procurement authority – by CAP Committee | Above the delegated procurement authority and up to US $2 million (applies per year for Long-Term Agreements) | Country offices: above US $2 million (applies per year for Long-Term Agreements) |
| Direct contracting |  |  |  |
| Any contract or series of contracts, including amendments to be awarded to a vendor in a calendar year that in aggregate has a cumulative value: | Above US $50,000 and up to 50 percent of the standard delegated procurement authority – Direct Review by CAP Chairperson Above 50 percent of the standard delegated procurement authority and up to 50 percent of any increased delegated procurement authority – by CAP Committee | Above 50 percent of the delegated procurement authority and up to US $2 million (applies per year for long-term agreements) | Headquarters units: above 50 percent of the delegated procurement authority Country offices: above US $2 million (applies per year for long-term agreements) |
| Amendment of all contracts |  |  |  |
| Any amendment or series of amendments to a contract which, in aggregate, increases the contract value by 20 percent or the delegated procurement authority, whichever is less: | Above US $50,000 and up to the standard delegated procurement authority – Direct Review by CAP Chairperson. Above the standard delegated procurement authority and up to the increased delegated procurement authority - by CAP Committee | Above the delegated procurement authority and up to US $2 million (applies per year for long-term agreements) | Country offices: above US $2 million (applies per year for long-term agreements) |
| Ex ante review |  |  |  |
| Ex ante review refers to the review of the procurement strategy roadmap prior to commencement of the procurement process for complex procurement actions with a value: | N/A | Above US $1 million and up to US $2 million (applies per year for long-term agreements) | Above US $2 million (applies per year for long- term agreements) |
| Notes: | - The procurement support unit shall participate when requested in the committee review of ex ante submissions. - An ex ante review is not required if: - The business unit has had a previous successful experience in the procurement of similar goods/services/works that was already subject to an ex ante review; or - There is sufficient specific corporate guidance and templates on the procurement of the said goods/services. - Irrespective of the above, the procurement authority may submit the cases for ex ante review if significant risks are perceived. |  |  |

## Annex 11: Theory of Change

## Annex 12: GEF Core indicators

This annex is submitted separately as Annex E of the accompanying CEO Endorsement Request.

## Annex 13: GEF 7 Taxonomy

This annex is included as Annex F of the accompanying CEO Endorsement Request.

## Annex 14: Aggregated Total Budget and Work Plan (UNDP and UNEP)

|  | Project Title: Global CBIT Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Project Number: GEF ID 10128 |  |  |  |  |
|  | Project Implementing Agency: UNDP, UNEP |  |  |  |  |
|  | Project Executing Agency: UNDP, UNEP, UNEP DTU Partnership |  |  |  |  |
|  | Project implementation period: | From: | 03/2020 | To: | 02/2023 |

| UNDP Budget Code | UN Env Class |  | Description | Year 1 | Year 2 | Year 3 | Total | Lead |  | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1 |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |
|  | C1-0101 |  | Programming support to merge GSP/CBIT platform (UDP staff) | 35,000 | 35,000 | 19,273 | 89,273 | UNEP DTU |  | A |
|  | C1-0102 |  | Maintain and update content on the GSP/CBIT platform (UDP staff) | 115,901 | 115,000 | 38,217 | 269,118 | UNEP DTU |  | B |
|  | C1-0103 |  | Knowledge dissemination and communication (UDP staff) | 41,000 | 41,000 | 14,700 | 96,700 | UNEP DTU |  | C |
|  | C1-0104 |  | Graphic designer | 10,000 | 10,000 | 5,000 | 25,000 | UNEP DTU |  | D |
|  | C1-0105 |  | Software programmer | 100,000 | 72,000 | 30,000 | 202,000 | UNEP DTU |  | E |
|  | C1-0106 |  | Climate transparency expert | 20,000 | 10,000 | 10,000 | 40,000 | UNEP DTU |  | F |
|  | C1-0107 |  | Communication expert | 12,000 |  |  | 12,000 | UNEP DTU |  | G |
|  |  |  | Subtotal | 333,901 | 283,000 | 117,190 | 734,091 |  |  |  |
|  | 120 |  | Contract Services |  |  |  |  |  |  |  |
|  | C1-1202 |  | Meetings and workshops (UDP) | 3,000 | 3,000 | 3,000 | 9,000 | UNEP DTU |  | H |
|  | C1-1203 |  | Translation | 5,000 | 5,000 | 5,000 | 15,000 | UNEP DTU |  | I |
|  |  |  | Subtotal | 8,000 | 8,000 | 8,000 | 24,000 |  |  |  |
|  | 125 |  | Operating & Other Costs |  |  |  |  |  |  |  |
|  | C1-1251 |  | Domain host | 2,000 | 2,000 | 2,000 | 6,000 | UNEP DTU |  | J |
|  |  |  | Subtotal | 2,000 | 2,000 | 2,000 | 6,000 |  |  |  |
|  | 130 |  | Supplies, Commodities and Materials |  |  |  |  |  |  |  |
|  |  |  | Subtotal | - | - | - | - |  |  |  |
|  | 135 |  | Equipment |  |  |  |  |  |  |  |
|  |  |  | Subtotal | - | - | - | - |  |  |  |
|  | 160 |  | Travel |  |  |  |  |  |  |  |
|  | C1-1601 |  | Travel for workshops and international meetings | 10,000 | 10,000 | 10,000 | 30,000 | UNEP DTU |  | K |
|  |  |  | Subtotal | 10,000 | 10,000 | 10,000 | 30,000 |  |  |  |
| COMPONENT 2 |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |
| 61300 |  |  | Salary & Post Adjustment Cost – IP Staff | 30,000 | 35,000 | 35,000 | 100,000 | UNDP |  | L |
| 71200 |  |  | International Consultants | 43,000 | 74,000 | 70,000 | 187,000 | UNDP |  | L |
|  | C2-0104 |  | Peer exchange and capacity building in the LAC region | 30,000 | 35,000 | 35,000 | 100,000 | UNEP DTU |  | M |
|  |  |  | Subtotal | 103,000 | 142,000 | 142,000 | 387,000 |  |  |  |
|  | 160 |  | Travel |  |  |  |  |  |  |  |
| 71600 |  |  | Travel for workshops and international meetings | 10,000 | 10,000 | 10,000 | 30,000 | UNDP |  | N |
|  |  |  | Subtotal | 10,000 | 10,000 | 10,000 | 30,000 |  |  |  |
|  | 120 |  | Contract Services |  |  |  |  |  |  |  |
| 75700 |  |  | Training, workshops and conferences | 179,000 | 186,000 | 177,000 | 542,000 | UNDP |  | O |
| 74200 |  |  | Audio-visual and print production costs | - | 2,000 | 1,000 | 3,000 | UNDP |  | P |
|  |  |  | Subtotal | 179,000 | 188,000 | 178,000 | 545,000 |  |  |  |
| 74500 |  |  | Miscellaneous | - | 591 | 500 | 1,091 | UNDP |  | Q |
|  |  |  | Subtotal | - | 591 | 500 | 1,091 |  |  |  |
| MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |
| 71200 |  |  | International Consultant -- Terminal Evaluation | - | - | 30,000 | 30,000 | UNDP |  | R |
| 75700 |  |  | Training, workshops, and conferences | 31,000 | 0 | 0 | 31,000 | UNDP |  | S |
|  |  |  | Subtotal | 31,000 |  | 30,000 | 61,000 |  |  |  |
|  |  |  | Subtotal for M&E | 31,000 |  | 30,000 | 61,000 |  |  |  |
| PROJECT MANAGEMENT COSTS (PMC) |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |
|  | PM-0101 |  | Project manager of Component 1 | 35,000 | 35,000 | 20,909 | 90,909 | UNEP DTU |  | T |
| 61200 |  |  | Salaries Cost -- GS Staff | 12,000 | 14,000 | 14,000 | 40,000 | UNDP |  | U |
| 61300 |  |  | Salary & Post Adj Cost – IP Staff | 7,000 | 7,000 | 7,000 | 21,000 | UNDP |  | U |
|  |  |  | Subtotal | 54,000 | 56,000 | 41,909 | 151,909 |  |  |  |
| 74100 |  |  | Professional Services -- Audit | 3,000 | 3,000 | 3,000 | 9,000 | UNDP |  | V |
| 74500 |  |  | Miscellaneous | 909 | 0 | 0,000 | 909 | UNDP |  |  |
| 74596 |  |  | Direct Project Costs - General Operating Expenses (GOE) | 6,000 | 7,000 | 7,000 | 20,000 | UNDP |  |  |
|  |  |  | Subtotal | 9,909 | 10,000 | 10,000 | 29,909 |  |  |  |
|  |  |  | Subtotal for Project Management Costs | 63,909 | 66,000 | 51,909 | 181,818 |  |  |  |
|  | GRAND TOTAL |  |  | 740,810 | 711,591 | 547,599 | 2,000,000 |  |  |  |
| Budget Notes |  | Description |  |  |  |  |  |  |
| A |  | Support to Activities 1.1.1, 1.1.2, 1.1.3 |  |  |  |  |  |  |
| B |  | Support to Activities 1.2.1, 1.2.2, 1.2.3, 1.2.3, 1.2.4, 1.2.5 |  |  |  |  |  |  |
| C |  | Support to Activities 1.3.1, 1.3.2, 1.3.3, 1.3.4 |  |  |  |  |  |  |
| D |  | Support to Activity 1.1.3 |  |  |  |  |  |  |
| E |  | Support to Activity 1.1.4, 1.1.5, 1.1.6, 1.1.8, 1.3.3 |  |  |  |  |  |  |
| F |  | Support to Activity 1.3.1, 1.3.4 |  |  |  |  |  |  |
| G |  | Support to Activity 1.1.2, 1.1.7 |  |  |  |  |  |  |
| H |  | Support to Activity 2.2.4 |  |  |  |  |  |  |
| I |  | Translation of regional materials for platform under Output 1.2 |  |  |  |  |  |  |
| J |  | Domain hosting in support of Output 1.2 |  |  |  |  |  |  |
| K |  | Travel for Project Management (PM-0101) in support of activities under Component 1 and Activity 2.2.4 |  |  |  |  |  |  |
| L |  | Technical support of the Project Coordinator and the IC / Transparency Expert to all outputs under Component 2 with the exception of 2.2.4 |  |  |  |  |  |  |
| M |  | Consultant for support to Activity 2.2.4 |  |  |  |  |  |  |
| N |  | Travel for Project Coordinator and UNDP in support of Outputs 2.1, 2.2, 2.3, and 2.4 |  |  |  |  |  |  |
| O |  | Workshops to be held under outputs 2.1 and 2.4 (annual stocktaking and gender workshops) |  |  |  |  |  |  |
| P |  | Print production costs for knowledge materials in support of all outputs under Component 2 |  |  |  |  |  |  |
| Q |  | Sundry expenses for workshops under Outputs 2.1 and 2.4 |  |  |  |  |  |  |
| R |  | IC for Terminal Evaluation |  |  |  |  |  |  |
| S |  | Inception Workshop for Project |  |  |  |  |  |  |
| T |  | Salary of Project Manager for Component 1 and Activity 2.2.4 |  |  |  |  |  |  |
| U |  | Cost-shared salary of Project Coordinator and Project Associate for support to all activities under Component 2 with the exception of 2.2.4 and for general coordination and monitoring duties |  |  |  |  |  |  |
| V |  | Annual audit of project (@ $3,000 / year) |  |  |  |  |  |  |

Summary of Funds:

| GEF (Implemented by UNDP) | $321,909 | $338,591 | $354,500 | $1,015,000 |
| --- | --- | --- | --- | --- |
| GEF (Implemented by UNEP) | $415,856 | $371,000 | $198,144 | $985,000 |
| UNEP DTU Partnership (In Kind) | $130,000 | $135,000 | $135,000 | $400,000 |
| TOTAL | $867,765 | $844,591 | $687,644 | $2,400,000 |

IPCC (2019). 2019 Refinement to the 2006 Guidelines for National Greenhouse Gas Inventories.

However, there is some flexibility in these requirements for developing countries that need it.

GEF (2018). Progress Report on the Capacity Building Initiative for Transparency. GEF/C.55/Inf.12: 5.

GEF ID 5141.

Prasada Rao (2018) Mid-Term Review.

The Gender Responsive National Communications Toolkit is accessible through this link: http://www.un- gsp.org/sites/default/files/documentos/undp_gender_responsive_national_communications_toolkit.pdf

FCCC/SBI/2017/L.29, paragraph 5.

GEF/STAP/C.48/Inf.03/Rev.01 (2015): 7.

https://panorama.solutions/en

See https://www.thegef.org/gef/policies_guidelines

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Data collection methods should outline specific tools used to collect data and additional information as necessary to support monitoring. The PIR cannot be used as a source of verification.

The GDI is a measure that is based on the sex-disaggregated Human Development Index, which is defined as a ratio of the female to the male HDI. As such, the GDI is meant to identify gender inequalities in three basic dimensions of human development: health (measured by female and male life expectancy at birth), education (measured by female and male expected years of schooling for children and mean years for adults aged 25 years and older); and command over economic resources (measured by female and male estimated GNI per capita). Data available at: http://hdr.undp.org/en/composite/GDI

The Global Gender Gap Index (GGGI) of the World Economic Forum examines the gap between men and women in four categories: economic participation and opportunity, educational attainment, health and survival; and political empowerment. Available at: http://www3.weforum.org/docs/WEF_GGGR_2018.pdf

World Economic Forum (2018) The Global Gender Gap Report 2018: vii.

Ibid.: 7.

http://www.undp.org/content/undp/en/home/sustainable-development-goals/goal-5-gender-equality/targets.html

UN Women (2017). “New Guidebook Launched to Boost Gender Mainstreaming.” https://unfccc.int/news/new-guidebook-launched-to-boost-gender-mainstreaming.

UNFCCC (2018). FCCC/CP/2017/11/Add.1: 16.

International Union for Conservation of Nature and United States Agency for International Development (2016)