GEF-7 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type: Medium-sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

# PART I: PROJECT INFORMATION

| Project Title: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Global | GEF Project ID: |  | 10128 |
| GEF Agency(ies): | UNDP UNEP | GEF Agency Project ID: |  | UNDP 6277 |
| Other Executing Partner(s): | UNEP DTU Partnership | Submission Date: |  | Sep. 27, 2019 |
| GEF Focal Area (s): | Climate Change | Project Duration (Months) |  | 36 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program |  | Agency Fee ($) |  | 190,000 |

- Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| CCM-3-8 | Foster enabling conditions for mainstreaming mitigation concerns into sustainable development strategies through capacity building initiative for transparency | GEF TF | 2,000,000 | 400,000 |
| Total project costs |  |  | 2,000,000 | 400,000 |

- Project description summary

| ### Project Objective: To provide global streamlined support, capacity building and coordination to help developing countries meet enhanced transparency requirements under Article 13 of the Paris Agreement. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| 1. Streamlined knowledge development and delivery in support of Article 13 | Technical Assistance | Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements | 1.1 Existing Global Support Program (GSP) and CBIT platforms merged and redesigned into an integrated web platform 1.2 Platform content and features maintained and updated regularly 1.3 Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, updated, developed, and customized | GEF TF | 794,091 | 350,000 |
| 2. Global stakeholder outreach and dissemination of best practices | Technical Assistance | Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming. | 2.1 Annual stocktaking of progress, capacity needs, and support to all non-Annex I countries conducted 2.2 COP side events and outreach efforts organized to disseminate results 2.3 Coordination among support providers facilitated 2.4 Assistance provided to countries with integrating the UNFCCC Gender Action Plan into enhanced transparency frameworks | GEF TF | 963,091 | 0 |
| 3. Knowledge Management and Monitoring and Evaluation (M&E) | Technical Assistance |  |  |  | 61,000 |  |
| Subtotal |  |  |  |  | 1,818,182 | 350,000 |
| Project Management Cost (PMC) |  |  |  | GEF TF | 181,818 | 50,000 |
| Total project costs |  |  |  |  | 2,000,000 | 400,000 |

- confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| Other | UNEP DTU partnership | In-kind | 400,000 |
| Total Co-financing |  |  | 400,000 |

- Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
| UNDP | CBIT | Global | Climate Change | CBIT | 1,015,000 | 96,425 | 1,111,425 |
| UNEP | CBIT | Global | Climate Change | CBIT | 985,000 | 93,575 | 1,078,575 |
| Total Grant Resources |  |  |  |  | 2,000,000 | 190,000 | 2,190,000 |

a ) Refer to the Fee Policy for GEF Partner Agencies

- Project’s Target Contributions to GEF 6 Core Indicators

Update the relevant sub-indicator values for this project using the methodologies indicated in the Core Indicator Worksheet (as used in GEF 7 Endorsement template – Annex E) and aggregating them in the table below. Progress in programming against these targets is updated at mid-term evaluation and at terminal evaluation. Achieved targets will be aggregated and reported any time during the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and SCCCF.

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (Hectares) |  |
| 2 | Marine protected areas created or under improved management for conservation and sustainable use (Hectares) |  |
| 3 | Area of land restored (Hectares) |  |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) |  |
| 5 | Area of marine habitat under improved practices (excluding protected areas) (Hectares) |  |
|  | Total area under improved management (Hectares) |  |
| 6 | Greenhouse Gas Emissions Mitigated (metric tons of CO2e) |  |
| 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management |  |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric tons) |  |
| 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (metric tons of toxic chemicals reduced) |  |
| 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent gTEQ) |  |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 300 direct beneficiaries, of whom 150 are women |

Provide additional explanation on targets, other methodologies used, and other focal area specifics (i.e., Aichi targets in BD) including justification where core indicator targets are not provided.

- Project Taxonomy

Please update the table below for the taxonomic information provided at PIF stage. Use the GEF Taxonomy Worksheet provided in Annex F to find the most relevant keywords/topics/themes that best describe the project.

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing Models | Strengthen institutional capacity and decision-making |  |  |
| Stakeholders | Type of Engagement | Information Dissemination Partnership |  |
| Capacity, Knowledge and Research | Enabling Activities Capacity Development Knowledge Generation and Exchange Knowledge and Learning | Knowledge Management Capacity Development |  |
| Gender Equality | Gender Mainstreaming Gender Results Areas | Gender-Sensitive Indicators Capacity Development Knowledge Generation |  |
| Focal Area/Theme | Climate Change | United Nations Framework Convention on Climate Change | Capacity Building Initiative for Transparency |
| Rio Markers | Climate Change Mitigation 2 Climate Change Adaptation 1 |  |  |

# PART II:  PROJECT JUSTIFICATION

A. describe any changes in alignment with the project design with the original pif

The project is still aligned with the project design proposed in PIF.  Changes in the approach and activities can be summarized as follows:  1) Activities and deliverables have been modified to reflect decisions taken at COP 24 influencing the reporting requirements of developing country parties.  For example, this project will provide methodologies and tools in support of the requirement to submit a BTR by December 31, 2024.  2) Some wording has been modified to reflect the need for the project to provide comprehensive support for transparency for countries that may go beyond Article 13 requirements to elements of other climate change reporting, such as National Communications and BURs; 3) In addition to creating a feature on the integrated platform to support regional peer-to-peer learning, the project will pilot a coordination initiative for climate-related networks in Latin America and the Caribbean (LAC).

While the overall budget requested for the project remains the same, the distribution has changed slightly. As a result of discussions with country beneficiaries, UNEP, and the GEF Secretariat, USD 100,000 has been shifted from Component 1 to Component 2 in order to pilot regional collaboration among complementary transparency initiatives under Output 2.2. Finally, as UNDP will conduct the terminal evaluation, the totals for agency project financing and fee requested have been changed to reflect this change.

The following table summarizes changes that have been made in the wording of outcomes and outputs.

| PIF stage | Proposal | Justification |
| --- | --- | --- |
| Outcome 1. Developing countries increasingly access information and knowledge in support of Article 13 of the Paris Agreement Budget: USD 909,091 | Outcome 1. Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements Budget: 794,091 | Wording updated, as the project will provide support for existing reporting requirements (e.g. National Communications) along with new reporting (e.g. Biennial Transparency Reports) The budget change resulted from the re-allocation of USD 100,000 to Component 2 to cover the activity “2.2.4 Pilot the fostering of south-south peer exchange in climate transparency actions in the LAC region” as a pilot regional coordination initiative and reallocation of USD 15,000 to the the M&E budget under Component 3 (see below). |
| Output 1.1 Existing CBIT and Global Support Program (GSP) web platforms merged and redesigned into an integrated platform | Output 1.1 Existing Global Support Program (GSP) and CBIT platforms merged and redesigned into an integrated web platform | Wording updated to reflect broad nature of platforms and for consistency. |
| Output 1.3 Paris Rulebook knowledge products including training modules updated, developed, and customized | Output 1.3 Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, updated, developed, and customized | Wording updated, as the project will provide support for existing reporting requirements (e.g. National Communications) along with new reporting (e.g. Biennial Transparency Reports). “Associated” is added to specify that the training modules would support the knowledge products rather than focusing on additional topics. |
| Component 3: Knowledge Management and Monitoring and Evaluation (M&E) |  | A stand-alone component to support knowledge management and M&E activities has been created and funding for these activities has been allocated from the amounts budgeted for Components 1 and 2 in the PIF. |
| Project Management |  | Co-financing in the amount of USD 50,000 has now been allocated to project management activities from the total co-financing amount in the PIF. |

A.1. Project Description. Elaborate on: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF,  and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovativeness, sustainability and potential for scaling up.

## Project Context

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way. This approach can reduce the time burden and financial burden on developing countries. Figure 1 below provides an overview of current reporting requirements for Parties to the United Nations Framework Convention on Climate Change (UNFCCC) and the Paris Agreement.  The figure highlights two elements: 1) The multiple sets of requirements; and 2) The common elements across these requirements.

Figure 1: Overview of Climate Change Reporting Requirements

In addition to these reporting commitments, countries are to submit a revised Nationally Determined Contributions (NDCs) in 2020, followed by a subsequent revised NDC in 2025. It should be noted that progress in reporting under the UNFCCC and the Durban Outcomes and Cancun Agreements varies widely among developing countries. There are countries that have produced several national communications (NCs) and several biennial update reports (BURs), while other countries have yet to produce a BUR.  All of these countries now face additional reporting under Article 13.

In the time since this PIF was submitted to the GEF Secretariat, requirements for developing countries have emerged The Conference of Parties (COP) 24 held in December 2018 in Katowice, Poland reached a series of important decisions regarding transparency under Article 13, known collectively as the Paris Rulebook.  The decisions outlined key commitments for all parties to the agreement and their timing during the 2020-2024 “Preparatory Phase” for reporting. Specifically, Parties are to submit a Biennial Transparency Report (BTR) by the end of 2024, which should include, among other items:

- A GHG inventory based upon the Intergovernmental Panel for Climate Change (IPCC) 2006 guidelines, which are themselves subject to recent refinement;

- Projections of GHG emissions and removals for a period of at 15 years beyond the next year ending in zero or five; and

- Reporting on progress towards achieving NDCs.

It is important to note that even countries that have not yet submitted a BUR must submit a BTR by December 31, 2024; therefore, the early phase of BTR compilation should be a key focus for technical support.  Likewise, National Communications are still part of the UNFCCC reporting process and will continue to require support.  In addition, there is an even greater need to avoid overlap with other reporting exercises, such as Sustainable Development Goals (SDGs)  monitoring, and to centralize the data collection and analysis for National Communications, BURs, BTRs, and NDCs.

At present, these multiple commitments represent a serious challenge to developing country Parties. While developing countries have an increasing number of methodological and informational resources at their disposal, many of them face persistent challenges in their capacity to monitor and report on climate change: a lack of data, staff shortages and turnover, a lack of individual capacity to conduct certain transparency-related activities, and others (see Table 1).

Table 1: Barriers to Compliance with Enhanced Transparency Framework Requirements

| Barrier | Type of Barrier | Description |
| --- | --- | --- |
| Limited or non-existent country-level institutional frameworks for reporting on mitigation, adaptation, and financial resources needed and received | Institutional | Many developing countries have some information systems that contribute to reporting in their National Communications (NCs) and Biennial Update Reports (BURs); however, these systems are often incomplete and unconnected. Countries often lack the legislative and regulatory mandates to obtain data from sectoral ministries or from the private sector on an ongoing basis, and the data received may not be properly formatted or vetted for quality. |
| Limited or weak technical capacities to prepare solid quality reports | Organizational / Individual | Government agencies that are currently responsible for reporting and transparency are understaffed, and frequent turnover and administrative reorganization cause disruptions in the continuity of employees working on the reports. When staff are available, they may lack particular methodologies that would allow them to undertake impact assessments of mitigation and adaptation measures and vulnerability to climate change. In other cases, staff are fully occupied with current reporting obligations and lack the time and resources to interpret new developments related to Article 13. Furthermore, training materials may not be available in a format or language that is accessible to staff. Finally, some countries rely on external consultants for their inventories, leading in some cases to “implementation without internalization.” In all of these cases, reports may then fail to address previous gaps, much less build upon previous results. These barriers are often symptomatic of an underlying problem: insufficient funding in governments to support staff who carry out transparency-related activities. |
| Absence of data and/ or difficulties in accessing data | Organizational /Procedural | Lack of activity data and/or data quality continue to be the biggest barriers to robust inventory compilation. New methodologies and reporting platforms being developed in many countries are limited in their effectiveness by an underlying lack of good-quality data. While data gaps and uncertainties have improved in the past few years in many countries, they continue to be a very important barrier to the quality and comprehensiveness of the NC reports, and the sustainability of the NC and BUR processes. These gaps will also hinder the robustness of NDCs. This barrier is closely related to the lack of harmonized institutional frameworks, as in some cases data are available but are not consistently shared, as described above. |
| Limited stakeholder consultation processes | Institutional / Organizational/ Cultural | Many countries lack the tools for broad consultative processes that include a wide variety of sectoral agencies and civil society, including the private sector and disadvantaged groups. A consultative approach is seldom part of the organizational culture of institutions leading those processes. |
| Lack of integration of gender considerations | Organizational/Procedural | Although gender is mentioned in a number of NDCs, evidence in the form of national reports suggests that developing countries’ capacity to support gender mainstreaming or to integrate gender-related climate change findings into sectoral policies needs to be strengthened. |

Although countries face serious barriers to effective transparency activities, the introduction of enhanced transparency frameworks presents an opportunity to streamline MRV activities by approaching the common elements of transparency activities in a holistic way. This approach can reduce the time burden and financial burden on developing country Parties. Furthermore, there is an opportunity to share experiences and good practice across Parties, avoiding the need to devote valuable time and scarce expertise and funding to elaborate unique structures and approaches for each developing country Party.

## 2) the baseline scenario and any associated baseline projects;

Associated Baseline Support for MRV Activities

Developing country Parties have forged networks and relationships to support their MRV work that flow from the original UNFCCC reporting requirements. The National Communications Support Programme (NCSP), a UNDP-GEF project that was launched in 1997 to support non-Annex countries in the preparation of their Initial National Communications to the UNFCCC, piloted a number of activities—regional workshops, expert rosters, networking among country teams and thematic experts, and peer assistance—that are still considered good practices.  In the area of developing country reporting, UNDP and UNEP have served and continue to serve as GEF Implementing Agencies for Enabling Activity projects that have supported numerous National Communications and – following the Durban Outcomes and Cancun Agreements – Biennial Update Reports.

The Global Support Programme (GSP), which is jointly implemented by UNEP and UNDP, was initiated with the objective of providing support to non-Annex I Parties in their preparations of National Communications and Biennial Update Reports. Since 2015, GSP has been providing technical support to all developing countries, complementing the work of other supporting bodies such as the Consultative Group of Experts on National Communications from Parties not included in Annex I to the Convention. In the framework of the GSP, UNEP and UNDP have conducted national and regional training workshops and dialogues on issues of NCs, BURs and their components. Guidance documents were prepared and published, including translation of existing guidelines into other United Nations languages. To date, thirteen regional workshops (with 87 countries participating), 14 national workshops (in 12 countries), and six webinars have been organized, co-organized and/or co-funded by the GSP. The GSP has also assisted 32 countries in reviewing 25 GHG inventories, 10 NCs, and two BURs. Three regional networks have been established, and 16 countries have received request-based support, where GSP has reviewed technical terms of reference for experts.

In addition to a high level of activity, the GSP has had a truly global reach: it has engaged 113 non-Annex I parties, and 73% of all non-Annex I parties, 74% of all least developed countries (LDCs), and 71% of all small island developing states (SIDS) have participated in GSP activities. It has also been able to respond to all country requests to date.

In the course of the mid-term evaluation of the GSP, “Stakeholders interviewed uniformly expressed an appreciation of GSP support in terms of relevance, quality, and utility.” With the advent of the Paris Agreement, the UNEP DTU Partnership and the GSP provided support to 32 countries compiling their Intended Nationally Determined Contributions (INDCs) from 2015 to 2017.  That initiative included the development of an INDC portal, which served as a helpdesk for developing country Parties.

Collaboration between UNEP and UNDP in providing technical support to developing countries was further enhanced with the approval of the CBIT Global Coordination Platform (GCP) (GEF ID 9675) and its launch in 2017. The CBIT was established "to support developing country Parties, upon request, in meeting enhanced transparency requirements as defined in Article 13 of the Agreement." The primary problem it was designed to address was the lack of a global coordination platform for information sharing and knowledge management on the enhanced transparency framework, as defined by the article 13 of the Paris Agreement. In the framework of the Global CBIT Support Platform, three global meetings have been organized so far in Copenhagen (April 2016), Berlin (April 2017), and Rome (May 2019) on the implementation of ETFs by countries with GEF-funded CBIT projects. Participants have included numerous developing countries along with a number of donors, developed country parties, and civil society organizations (CSOs). At the same time, both UNEP and UNDP have begun to assist countries in the implementation of national CBIT projects.

At the 2018 Berlin meeting, the global CBIT project launched the CBIT Global Coordination Platform (https://www.cbitplatform.org/).  This web-based platform was established to promote peer learning among countries receiving CBIT support. CBIT projects in the GEF pipeline have country profiles on the platform, including key information about the projects, implementation progress, and the status of CBIT project activities and other transparency support initiatives. In addition, CBIT country-level projects have completed transparency self-assessments and have identified a CBIT focal point. Countries designing CBIT projects can use this assessment to guide the project design process and countries implementing projects can use it to track progress in building capacity and to inform design of additional transparency projects. The platform is also issuing bi-monthly status updates on the CBIT though the Transparency Snapshot.

As of March 2019, only 4 countries had initiated the implementation of CBIT projects, and so the CBIT platform was primarily being used by potential CBIT applicant countries to design projects, rather than for sharing lessons learned. Initial activities on the platform included a series of articles interviewing country focal points. In addition, several webinars have been held to facilitate peer learning at the design stage. Peer learning activities will be designed to fit the needs of countries that have started the implementation phase of their CBIT projects.

Other Baseline Projects

Two types of baseline projects: GEF-funded CBIT projects at the country and global level; and donor-funded country and regional projects that are funded by sources other than GEF.

GEF-Funded Projects: More than 40 CBIT projects were approved during the GEF-6 funding cycle, including more than 10 projects from Least Developed Countries (LDCs) and more than five from Small Island Developing States (SIDS).  A GEF progress report released in May 2019 on the CBIT initiative found that the most common project activities in country-level projects fell into eleven groups:

- Enhancement and/or establishment of new institutional arrangements;

- Use of NDC transparency activities to inform policy design;

- Accounting and measurement, review and verification (MRV) methodologies for mitigation actions;

- Accounting and MRV methodologies for adaptation actions;

- Economic and greenhouse gas (GHG) emissions scenario modelling;

- GHG inventory data collection and management tools;

- Enhancement and/or establishment of new MRV systems;

- GHG inventory improvements including development of country-specific emission factors and activity data;

- Capacity building, training, and knowledge sharing;

- Tracking climate finance, and;

- Agriculture, Forestry and other Land Use (AFOLU) focused activities.

In addition to these country-level projects, there are two global GEF-funded CBIT projects implemented by the Food and Agriculture Organization of the UN (FAO): CBIT-Forestry (GEF ID 10071) and CBIT-AFOLU (GEF ID 9864). The CBIT-AFOLU project is expected to produce methodologies and tools for tracking progress towards NDCs in the AFOLU sector, and knowledge products developed under that project will be relevant to many developing country Parties.

Other donor-supported initiatives: A 2019 analysis by the MRV Group of Friends identified 475 MRV / transparency activities undertaken by 21 donors.  Several bilateral donors have initiatives to support MRV in climate change, such as the “Information Matters” project for ambitious climate reporting that has been managed by GIZ (2013-2019).

In addition to bilateral donors, several multilateral coalitions have emerged to support transparency. For example, the Initiative for Climate Action Transparency (ICAT) is currently developing an integrated suite of 10 guidance documents on various aspects of transparency, ranging from sectoral guidance in renewable energy and forestry to reporting on non-state action and sustainable development and transformational impact assessment. ICAT also provides capacity building for MRV systems for transparency in 35 partner countries, working very closely with developing countries to strengthen their capacity to assess climate actions and report their progress in line with the Paris Agreement, based on individual country needs. Furthermore, the Partnership on Transparency in the Paris Agreement (PATPA), which describes itself as a semi-formal forum, has had more than 100 countries participate in its activities, which include regional technical workshops and knowledge sharing. The Paris Committee on Capacity Building (PCCB), although not an implementing body, focuses on capacity gaps and needs. The PCCB relies on volunteers, and its activities have included support for NDC implementation and cross-cutting issues, including gender equality. They have undertaken a six-country pilot exercise, and they a have a web-based capacity-building portal. The Partnership to Strengthen Transparency for co-Innovation (PaSTI) was established in 2017 at COP23 as an initiative of the Ministry of the Environment of Japan (MOEJ) in collaboration with the World Resources Institute (WRI). PaSTI is designed to provide value-added activities to existing initiatives on transparency, and it promotes engagement of the private sector and local government by identifying incentive mechanisms and developing critical tools. PaSTI has held several webinars on topics such as enhancing MRV in the private sector, and it held a side event at COP24. The EU-funded EU4Climate project implemented in the Eastern Partnership countries (Armenia, Azerbaijan, Belarus, Georgia, Republic of Moldova, and Ukraine) and supporting above all enhanced MRV systems and NDC implementation in the beneficiary countries. EU4Climate supports the development and implementation of climate-related policies which contribute to their low emission and climate resilient development and their commitments to the Paris Agreement on Climate Change. It identifies key actions and results in line with the Paris Agreement, the "20 Deliverables for 2020”, and the key global policy goals set by the UN 2030 Agenda for Sustainable Development.

Furthermore, country cooperation has taken place at the regional level. For example, in Latin America and the Caribbean (LAC), country-level CBIT projects facilitated by UNEP and UNDP, PATPA activities, and the Latin American Network for GHG Inventories (RedINGEI), and the Caribbean Cooperative MRV Hub (CCMRVH) have all supported regional exchanges of knowledge and experience.

Information on how these baseline projects and initiatives will be involved in project implementation is provided in Table 2 of this document and in the description of activities under Output 2.3, which is explicitly designed to enhance the coordination of support providers.

Baseline Scenario

Under the baseline scenario, the CBIT Global Coordination Platform (GEF ID 9675) will provide targeted report on transparency issues until approximately December 2019, when it will end. The GSP will continue to provide support for sub-regional networks and for reporting under NCs and BURs until December 2020, when it will also end.  However, the need for country support will not end; on the contrary, developing country Parties will be grappling with new regulations under the Paris rulebook as Article 13 is operationalized through the implementation of the modalities, procedures, and guidelines (MPGs).

As the GSP mid-term review found, “The global functions carried out by GSP as well as consolidation and sustainability of the regional networks beyond 2020 depends on further funding, e.g. from the GEF. There is a potential risk of a gap which could threaten the networks and partnerships established, since GSP is scheduled for completion in 2020….” The GSP mid-term review also made several strategic recommendations for the development of GSP activities over the medium term; i.e., a subsequent phase that would depend upon additional funding.  They include establishing one or more regional networks in Asia and providing staffing support within Asia to strengthen engagement; and strengthening the voice of developing countries in project oversight by including a representative on the Project Steering Committee. These elements are all included in proposed Phase II activities, but in the absence of funding support for Phase II, they will not be realized. In summary, there is an acute need to ensure sustainability and combined implementation of the CBIT Global Coordination Platform and the Global Support Programme beyond 2019 and 2020, respectively. This need is clearly stated under Paragraph 14 of Article 13 itself, which states that “Support shall also be provided for the building of transparency-related capacity of developing country Parties on a continuous basis.”

At the same time, UNEP and UNDP are aware that continuation of both the GSP and Global CBIT Support Platform as separate initiatives under the Paris Agreement is likely to create a duplication of effort.  GSP was launched under the UNFCCC Convention, whereas the Global CBIT Support Platform was launched under the Paris Agreement. This fact is acknowledged in the Paris Agreement, whereby Paragraph 74(a) of the Paris Agreement clearly states that part of the 2016-2020 work plan should assess how to increase synergies through cooperation and avoid duplication among existing bodies [or initiatives] established under the Convention. Countries will be best able to address reporting requirements through unified tracking systems, and as they move towards unified frameworks, they will best be supported by a unified web platform.

## 3) the proposed alternative scenario with a brief description of expected outcomes and components of the project;

Proposed Alternative Scenario

The proposed approach consists of two sequential projects:  this proposed CBIT Phase II MSP (IIA) and a subsequent Full-Sized Project (IIB).  Originally designed as a single Phase II project, the project was divided into two parts in order to ensure the allocation of funding that was available through the CBIT set-aside under GEF-6. Phase IIA therefore focuses on a streamlined platform for knowledge delivery, support for knowledge products, and global stocktaking and dissemination of best practices—all elements that require funding early in the subsequent phase of the project. Phase IIB will continue support for the integrated web platform, but it will also provide targeted technical support and training for developing country parties and south-south sub-regional networks and learning.

CBIT Phase II, comprised of the Phase IIA and IIB projects, will use three main strategies in its approach. First, it will build on the successful foundation of ongoing delivery models and leverage long-standing South-South networks and relationships with developing countries.  Its activities will draw upon successful approaches that have been identified and refined over time through feedback from consultations and external evaluations.

Second, CBIT Phase II will use an agile approach to address new issues related to Article 13 as they arise.  As with Phase I, it will maintain flexibility to be responsive to, and integrate, evolving COP guidance related to the Modalities, Procedures and Guidelines (MPGs) for the Enhanced Transparency Framework under the Paris Agreement. Because the project emphasizes stakeholder participation, it will be able to mobilize experts and respond to changes in the climate policy landscape as they emerge. It is assumed that guidance regarding the MPGs will continue to develop, and the global program will be well positioned to disseminate information and provide support in complying with additional guidance from the COP.

Third, CBIT Phase II will utilize a partnership model for delivery. The integration of the GSP and CBIT support to countries will utilize the combined expertise and country networks of UNEP and UNDP under a common initiative that will simplify country participation. The project will also continue to provide facilitation support for the delivery of the UNFCCC Secretariat work programmes and the work of the Consultative Group of Experts (CGE).

The CBIT Global Coordination Platform project (Phase I) is currently implementing its remaining activities:  (i.e. the addition of website content, including self-assessment reports as countries join the pool of national CBIT project participants, and the baseline assessment of global gaps related to the enhanced transparency framework).

Figure 2 provides an overview of the envisaged integration of the provision of information and technical assistance currently being carried out by CBIT Phase I and the GSP into the unified global coordination platform.  The integration is designed to provide continuous support for countries through the end of 2025 while avoiding overlap in activities.  It should be noted that the website maintenance and support activities in IIA and IIB will be sequential; i.e., IIB will begin to support these activities following the closure of IIA.

Figure 2: Proposed Timeline of Project Coordination

This proposed approach will be increasingly important as the size of the GEF portfolio of CBIT-funded projects grows.  In addition to the CBIT projects that have already been approved, USD 164 million is earmarked for CBIT projects and enabling activities under GEF 7.  However, many more developing countries will not have a CBIT project but will nonetheless be required to submit a BTR in 2024. Phase II outputs and outreach strategies will be designed to maximize outreach and support to all developing country Parties.

Project Strategy

The overall objective of the project is to provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. The outcomes of the project are as follows: 1) Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements; and 2) Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming.

The project is composed of two components: 1) Streamlined knowledge development and delivery in support of Article 13; and 2) Global stakeholder outreach and dissemination of best practices.

Component 1: Streamlined development and delivery of knowledge in support of Article 13

Component 1 will be executed by the UNEP DTU Partnership

Component 1 seeks to provide developing countries with a holistic source of information and knowledge related to transparency and a web platform for online peer learning.  It focuses on merging two existing web platforms related to transparency—CBIT and GSP—and maintaining the core services provided under those web platforms while expanding the resources and learning materials available through the development of new guidance publications and training modules. In this way, the new transparency web platform will become a “one-stop shop” for information related to Article 13 and transparency more broadly.

The requirements in the “Paris Rulebook,” or the detailed rules and procedures that will govern the implementation of the Paris Agreement, will continue to evolve over time, providing guidance to countries on how to report on their efforts related to climate change and the commitments that they have made in the form of Nationally Determined Contributions. In addition, the release of the rules provides an opportunity to structure country-level transparency frameworks in such a way as to optimize reporting under other UNFCCC commitments.  However, in both cases, developing countries will require additional support and guidance on interpreting the rulebook and implementing it with the least additional time and expense possible. The structure of BTRs, the introduction of the IPCC 2006 guidelines for national GHG inventories (or their modification according to the 2019 refinement), and reporting on progress towards NDCs necessitate new guidance and knowledge for all Parties. Under this project component, the web platform will accommodate resources related to the Paris rulebook through a designated knowledge base area as they become available and will develop its own knowledge products, including the associated training modules and best practice case studies, as necessary.

Finally, specific activities will also support women’s active participation in knowledge generation and active use of the integrated platform.

Output 1.1	Existing CBIT and GSP platforms merged and redesigned into an integrated web platform

UNDP and UNEP currently provide transparency-related information to developing countries and other stakeholders through two internet websites.  The first, the Global Support Programme website (www.un-gsp.org), provides information and resources designed to strengthen capacity related to the preparation of NCs and BURs. The second website, the CBIT Global Coordination Platform (cbitplatform.org) through the UNEP DTU Partnership, focuses explicitly on strengthening capacity to undertake transparency arrangements under Article 13 of the Paris Agreement and provides information on and support to countries that are implementing projects under the GEF CBIT funding mechanism.

The integrated web platform will initially contain five modules:

- Information on ongoing and upcoming in-country, regional and global transparency initiatives through a project database, mailing list, events forum, analytics, and a global snapshot with certain periodicity;

- Country profiles with information on progress on NCs and BURs, self-assessed needs, and CBIT national projects;

- A library of practices, methodologies, and guidance, including guidance materials on the Consultative Group of Experts (CGE) and the Paris Rulebook and archived materials from the previous websites;

- Information exchange and on-line tools for peer learning, including a feature that will allow the platform to serve as a point of coordination for regional MRV and transparency networks; and

- A “one-stop shop” for requesting assistance with country-level reports and transparency issues.

In subsequent phases, these modules can be expanded, institutionalizing the platform as the go-to destination for transparency practitioners as an all-encompassing information source. However, key features of each site will remain: for example, the self-assessment tool and self-progress reporting for CBIT participant countries will remain in place based on the roadmap for platform developed under CBIT Phase I or the audiovisual resources developed under the GSP.

MRV experts in developing countries are often involved both in reports to the UNFCCC and in current discussions on Article 13.  Therefore, the merger of the websites will simplify their searches for information and resources on transparency issues. In cases where users are familiar with only one of the websites, the merger will increase the resources that they access. In summary, an integrated platform will establish a unified virtual space for all national and international stakeholders interested in gathering information on MRV and the enhanced transparency framework and in following the implementation status of NCs, BURs, BTRs, and CBIT projects and practices.

Activities under this output will include the following:

1.1.1	Conduct requirements elicitation, including focus groups or surveys with different user groups and analyze usage patterns (disaggregated by gender)

1.1.2	Review and analyze existing, relevant climate change information portals and user traffic on the two current websites and propose a re-branding strategy, including a new logo, for the unified website

1.1.3	Design integrated website, evolving the existing features and the additional features, and conduct a usability study and beta testing at the prototype stage

1.1.4	Program the integrated platform, including search engine optimization

1.1.5	Conduct functional, performance, and integration tests on the integrated platform

1.1.6 	Develop and implement a website maintenance plan, including continuous software updates, data privacy and data security issues, regular backups, code repository and software version controls

1.1.7	Develop and implement a communications/re-branding strategy to inform users and potential users about the merge and publicize the launch of the integrated website

1.1.8	Survey users periodically after the website becomes operational and incorporate their feedback into the site design and features

Deliverables under Output 1.1 consist of the operational integrated platform and corresponding reports on website analytics every six months following the launch of the platform; a maintenance plan for the platform; a branding strategy and vision for the integrated platform; a website area for on-line regional transparency initiatives and corresponding reports on its use every six months; and a “one-stop shop” interface for requesting assistance with country-level reports and transparency issues, including reports on its usage every six months.

Output 1.2 	Platform content and features maintained and updated regularly

Both existing websites contain content and features that are directly relevant to users seeking information and resources related to transparency.  At present, the GSP website contains information by topic, and it also provides recent topical documents, resources such as infographics and video clips, good practice country reports, materials and information from past training and networking events, and country information pages.  In addition, the website maintains a roster of experts on various aspects of NCs and BURs who can provide support to countries. Finally, the GSP produces a newsletter that circulates to interested countries and to other stakeholders. The CBIT website maintains a project database of CBIT projects, and it provides news and interviews on transparency issues.  It also contains a library for information and materials from global and regional meetings.

Good knowledge management of the integrated web platform created under Output 1.1 will ensure that it is a valuable resource for countries seeking information and support. There will be a need to edit and curate content, and to draft case studies and project summaries when necessary.  Content development will be managed by the global level of the web platform, which will allow it to disseminate results from countries without adding to the time burden of country experts related to writing up results and sharing information.  Other content will be developed by countries within the framework of their GEF CBIT projects.

The coordination and capacity-generating efforts of the integrated website will be made easily digestible for all practitioners through a regular output: the "transparency snapshot." This knowledge will be disseminated through a factsheet, providing a regular summary of needs and gaps in line with information available in the platform's database. The website will also facilitate peer-to-peer discussions among developing country parties with common interests through a platform moderated by project experts.

Finally, the management of the platform will also take steps to encourage active engagement by women users: e.g., support articles and content written by women; encourage women’s participation in peer learning exchanges and events such as webinars. It will also track platform engagement by gender where possible.

Activities under this output will include the following:

1.2.1	Develop a knowledge management workplan for regular content creation, maintenance, and curation on the integrated platform, including the progress reporting tool for participating CBIT countries

1.2.2 	Maintain and update the technical content of the website, including search engine optimization

1.2.3	Track and analyze country queries, downloads, etc. in order to inform future content.

1.2.4 	Facilitate expert-moderated online peer learning / knowledge sharing through the regional network coordination feature

1.2.5	Track platform engagement by gender where possible

Deliverables under Output 1.2 consist of a knowledge management plan for updating content on the integrated website and content that is maintained and updated over the course of the project.

Output 1.3	Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules and best practice case studies, updated, developed, and customized

With the decisions undertaken at COP 24 in December 2018 on reporting under the Paris Agreement, countries must align their current climate change-related MRV systems with the requirements of the Enhanced Transparency Framework envisioned under Article 13.  The advent of new requirements represents a serious time and resource burden for developing countries, particularly in smaller countries or least developed countries, which are already stretched thin in their efforts to comply with existing reporting under the UNFCCC and other COP decisions. However, because the rulebook is new to all parties, there is an opportunity to align enhanced transparency frameworks and to benefit from the structures and approaches that will be identified by developed country and “first mover” developing country parties for their reporting. It is expected that knowledge products developed under this output will be particularly valuable for developing countries in the preparation of BTRs, including countries that do not have a GEF CBIT project.  As a part of BTR guidance, it will be necessary to support various aspects of the BTR. These include inventories, for which countries must use the IPCC 2006 guidelines, take into account the 2019 modification, and report consistent annual time series from 1990 with the latest reporting year no more than two years prior to the BTR.  They also include NDC tracking and projections of GHG sources and sinks at least 15 years into the future.  In addition, the “preparatory” phase for BTRs, which will take place during the implementation of the Phase II project, will allow countries that are interested to begin to incorporate BTR elements into their BUR reporting. Most countries with GEF CBIT projects have requested support for inventory improvements and inventory tools (73% and 70%, respectively); however, only 18% have requested support for scenario modeling, indicating that there may be an increased need for support from the global program in this area.

Knowledge products will be coordinated closely with stakeholders in the donor community (see Section II.2) in order to avoid overlap.  The selection of topics will also be influenced by demand as expressed in feedback from CBIT project countries, other developing country Parties, and the pilot peer-to-peer learning network, and they may include different areas of reporting, such as systematic reporting on needs and gaps or financial resources received.

Activities under this output will include the following:

1.3.1	Survey existing awareness-raising and training materials related to the Paris Rulebook to identify needs

1.3.2	Develop a work plan for producing new reports and training modules on emerging issues (enhanced transparency frameworks and the Paris rulebook, gender mainstreaming) and updates of existing handbooks and associated training modules on climate change MRV, including a plan for translation of all guidance into key participant languages as needed

1.3.3	Refine the CBIT Phase I self-assessment tool

1.3.4	Integrate good-practice templates and successful approaches to reporting issues from participating countries into training materials and other knowledge products (webinars, audio briefings, web content, etc.)

Deliverables under Output 1.3 consist of at least three guidance documents on climate transparency, a report on the updated results from self-assessment questionnaires, reports from at least three annual webinars, and at least three good practice briefs.

Component 2: Global stakeholder outreach and dissemination of best practices

Component 2 will be implemented by UNDP

In the framework of the Global CBIT Support Platform, three global meetings have been organized so far (see description under Output 2.1). Future events will serve several purposes. First, they will allow the project to present a real-time “transparency snapshot” of how countries are progressing in establishing transparency frameworks.  Second, they will provide a forum for disseminating good practice in MRV systems and transparency to donors and to countries. Third, they will provide an opportunity for south-to-south peers, mentors, and staff of twinned projects to spend time meeting face to face to discuss key issues of mutual interest. Finally, they will increase donor coordination, which will allow the project to leverage other resource and reach the maximum number of stakeholders possible while avoiding duplication of effort.

Output 2.1: Annual stocktaking of progress, capacity needs, and support to all non-Annex I countries conducted

This output will build on the CBIT Phase I project annual technical meetings, which have been held three times: in 2017 in Copenhagen; in April 2018 in Berlin; and in May 2019 in Rome.  The most recent workshop was the largest to date: it involved 100 attendees from 7 donor countries, 36 program countries, international organizations, and CSOs engaged in supporting transparency frameworks.

Annual global stocktaking meetings under this component will be aimed at strengthening national transparency capacities by presenting objectives and results from national CBIT projects, by identifying common approaches to existing challenges to transparency, and by presenting opportunities for actors from different initiatives to meet and coordinate their work. In addition, meetings may organize some outreach efforts by baseline country capacity; i.e., countries with experience with the IPCC 2006 guidelines could discuss common challenges, while countries that are just starting to create MRV frameworks and consider the 2006 guidelines could receive targeted information. In other cases, experienced countries can mentor neighboring countries that need more capacity support. Ideally, these meetings should provide participants with information that can strengthen their reporting efforts.

Activities under this output may include the following:

2.1.1	Organize three annual global stocktaking meetings, including the selection of topics and participants and encouraging representation and active involvement by women participants

2.1.2	Disseminate findings and materials shared at the meetings and workshops through various communication channels, including the integrated web platform

Deliverables under Output 2.1 consist of three annual global stocktaking meetings and at least three meeting summaries and stocktaking briefs.

Output 2.2: COP side events and outreach efforts organized to disseminate results

This output will maintain the practice developed under the GSP and the CBIT global platform of presenting results from selected countries and regions at UNFCCC events in order to reach the widest possible audience of climate change decision-makers from both developed and developing countries.  These events will support information exchange among developed and developing country Parties and will contribute to increased donor coordination. They may include events that are organized in conjunction with another meeting (e.g. a regional climate week) in order to minimize time and travel burdens for participants.  This output will support a pilot regional collaboration effort among different complimentary initiatives on transparency in LAC, including CBIT work, PATPA, RedINGEI, and CCMRVH. It will foster south-south peer exchanges with the aim of enhancing country transparency practices, supporting the sharing of good practices and lessons learned, and supporting countries to identify cooperative actions to increase ambition on transparency and climate goals.

Activities under this output may include the following:

2.2.1	Organize at least three side events for upcoming COPs and subsidiary body (SB) meetings (likely to be COP25, COP26, and COP27, and SB50, SB52, and SB54) and/or regional climate weeks, including the selection of topics and participants and encouraging representation and active involvement by women participants

2.2.2	Provide logistical support for the side events

2.2.3	Disseminate meeting summaries through various communication channels, including the integrated web platform

2.2.4	Pilot the fostering of south-south peer exchange in climate transparency actions in the LAC region

Deliverables under Output 2.2 consist of meeting summaries on at least three side events at COPs, SB meetings, and/or regional climate weeks; and reports every six months on the activities of the pilot regional collaboration network for climate transparency in the LAC region and supporting activities following the launch of the network.

Output 2.3: Coordination among support providers facilitated

This output will focus on maintaining and expanding the communication among support providers that has been developed through the GSP and CBIT Phase I, such as the May 2019 “Enhancing Coordination on Climate Transparency” meeting, which was held in tandem with the GEF Technical workshop in Rome. The approximately 45 participants of that meeting included representatives of Parties that contributed to the CBIT Trust Fund, international organizations, and other institutions involved in providing support to enhanced transparency frameworks.

The project will communicate regularly with support providers (a broadly-defined group that includes any entity providing support, such as government donors, UN agencies, developing country governments where applicable, think tanks, and formal and informal groups of providers) to exchange information regarding activities.  This output will also focus on continuous improvement in the quality of technical backstopping provided to recipient countries.  This output is designed to complement activities under Component 1 that will collect training materials and transparency-related information, including program descriptions, for the CBIT global platform, making these materials available to countries through the integrated website.

Activities under this output may include the following:

2.3.1	Organize at least one coordination meeting per year for support providers to map current activities and to identify regions and sub-regions that are in need of assistance and potential areas for combined service delivery.

2.3.2	Conduct a dialogue with support providers to determine ways to leverage their activities for the regional climate transparency networks that have been supported under the GSP to date.

Deliverables under Output 2.3 consist of reports from three coordination meetings with support providers.

Output 2.4: Assistance provided to countries with integrating the UNFCCC Gender Action Plan into enhanced transparency frameworks

While the Paris Agreement has highlighted gender equality and women’s empowerment as a guiding principle, countries will require assistance to operationalize these principles in their transparency activities. Therefore, this output focuses on supporting countries with integrating the UNFCCC Gender Action Plan (GAP) and associated decisions such as Decision 21/CP.22, which extends the Lima work plan on gender to COP25 in 2019, into transparency activities. The UNFCCC process continues to move to integrate gender-sensitive education and increase participation by women in UNFCCC processes and decisions, most recently with a draft gender action plan commissioned by COP22.  This action plan is designed to address gender sensitivity in all mitigation and adaptation activities, including the NDCs and low-term low greenhouse gas emission development strategies.  In addition to materials that focus explicitly on gender in MRV and Article 13, CBIT Phase IIA training and supporting knowledge products will incorporate the areas of the UNFCCC gender action plan that are targeted for attention: A) Capacity-building, knowledge sharing and communication; B) Gender Balance in Participation, and Women’s Leadership; C) Coherence across UNFCCC bodies and other UN entities; D) Gender-responsive Implementation and Means of Implementation; and E) Monitoring and Reporting on gender-related mandates under the UNFCCC.

While the UNFCCC provided training at COP24 in conjunction with WEDO and UN Women for UNFCCC Gender Focal Points, it will be important for focal points and project teams to continue to receive information and guidance, particularly in the priority area of monitoring and reporting. While all project components will take gender  equality issues and women’s participation into consideration (e.g. women’s active participation in the integrated platform under Component 1), this output focuses on integrating the GAP into enhanced transparency frameworks at the country level with a special emphasis on national reports. It also represents an opportunity to disseminate results under the GSP, which has supported two regional workshops on supporting the integration of gender considerations into MRV/transparency processes in the Western Balkan countries and Lebanon. These GSP activities, however, will conclude in February 2020.

Activities under this output will also support the exchange of information on gender considerations related to NDC tracking. Finally, it will provide support for the update and expansion of the gender-responsive national communications toolkit used by many countries to include recommendations on integrating gender considerations into BTRs and ETFs more generally.

Activities under this output may include the following:

2.4.1	Provide and coordinate reviews of national reports and supporting documentation by gender experts in response to country requests

2.4.2	Provide an updated toolkit on integrating the UNFCCC Gender Action Plan into national transparency frameworks that will build upon the current GSP toolkit (Gender Responsive National Communications and BURs).

2.4.3	Conduct at least four regional workshops (at least one workshop in each of four regions) on integrating gender analysis and the UNFCCC Gender Action Plan into national reporting and transparency. Workshops will be scheduled in conjunction with other CBIT-related meetings and workshops where possible to use resources efficiently.

2.4.4	Collect and analyse country reporting with regards to gender mainstreaming and integration of the Gender Action Plan in support of the annual stocktaking under Output 2.1

Deliverables under Output 2.4 consist of on-demand gender reviews of national reports, an updated gender toolkit, and workshop reports from four regional workshops.

## 4) alignment with GEF focal area and/or Impact Program strategies;

The project is primarily aligned with GEF Focal Area CCM-3-8, “Foster enabling conditions for mainstreaming mitigation concerns into sustainable development strategies through capacity building initiative for transparency.”  However, it will also play an important role in advancing progress in GEF Focal Area CCM-EA, “Foster enabling conditions for mainstreaming mitigation concerns into sustainable development strategies through enabling activities,” through the integrated web platform. In addition, the knowledge products developed, global stakeholder outreach, and dissemination of best practices will directly support CCA-2, “Strengthen institutional and technical capacities for effective climate change Adaptation,” as many developing countries have included an adaptation component in their NDCs and in GEF-funded CBIT projects.

## 5) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, and co-financing;

The underlying incremental reasoning for a global CBIT platform has not changed from the design of the CBIT Phase I program. The CBIT Phase II proposal maintains the same focus of the Phase I project: the generation of global public goods in form of coordination, knowledge generation, and the creation of a public knowledge repository, which by definition is free of access but still associated with a cost for the goods. In absence of CBIT funding, it is highly likely that no funding will be made available for these global public goods despite the imminent need for them. Moreover, donor initiatives and country-level projects are generating useful, albeit dispersed, capacities. By emphasizing coordination, this proposal will be able to leverage individual ongoing and future initiatives by centralizing knowledge and making it broadly available. Consequently, this proposal provides an incremental value to a wide-ranging number of initiatives and efforts.

In the absence of the Phase II project, most developing countries would lack a single, reliable source of information on transparency issues. At the same, their reporting and transparency obligations would increase. Selected countries would receive support through the GEF CBIT window, and others might benefit from bilateral donors or CSOs, but this support would target national transparency initiatives, and expertise and good practice developed through these projects would not be shared at the global level. As a result, many developing countries would be slow to receive this information, and they might lack the support to apply it.  Overall, developing countries would have fewer resources with which to address increasing transparency demands and could consume them in an effort to essentially “reinvent the wheel” with transparency activities, consuming valuable expertise and financial support that could be dedicated to furthering in-country mitigation and adaptation efforts.

The CBIT programme is designed to improve mandatory reporting of signatories of the UNFCCC. As such, this project is financed on full agreed cost basis. In the case of this programme, eligible activities have been described in the GEF document Programming directions for the Capacity Building Initiative for Transparency (GEF/C.50/06). The activities of this project are consistent with the scope of the programming directions. Co-financing is not a necessary requirement for this project; however, a total in-kind contribution of USD 400,000 has been leveraged.

## 6) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF);

Global environmental benefits

This project will ultimately contribute to enhanced ambitions in reducing GHG emissions. Improved coordination will generate synergies and avoid duplication across support initiatives and efforts, freeing resources for additional efforts in the global aim to keep global warming below 2 degrees Celsius. Similarly, the enhanced availability of knowledge through a centralized coordination platform will help countries increase their transparency capacity and, as a result, their capacity to report progress on their NDCs and long-term policy planning, providing for increased ambition.

In the area of climate change, the project will increase climate-related knowledge through improved GHG inventories and transparency frameworks and will disseminate good practice to developing countries, which will in turn allow them to undertake more robust mitigation activities. Furthermore, capacity improvements related to climate change adaptation and guidance on including robust adaptation goals in NDCs will generate adaptation-related benefits, but they may also generate benefits in other global environmental areas, such as biodiversity and land degradation through improved REDD+ capacity.

## 7) innovation, sustainability and potential for scaling up;

Innovation

The proposed Phase II project presents an innovative approach to support to developing country parties through its unified structure that combines support for multiple Convention-related commitments in a single “one-stop shop.” The organization of the integrated web platform and supporting knowledge products will also allow the project to be flexible and address issues related to Article 13 as they arise. Early phase support for BTR preparation and for integrating gender equality considerations into ETFs is also highly innovative, as is the approach of working with countries on request to incorporate elements of the BTRs into their current reporting.

In addition, the project is innovative in its use of south-south learning.  The pilot regional network for GHG inventories in LAC will allow countries to exchange relevant tools and experiences and also allow for some mentoring by developing country Parties with more experience in national reporting on climate change.  The regional network will also feed good practice upstream to the global platform, where it can be shared with developing country Parties and support providers in other regions.

Indeed, this project has a unique multi-level approach. At the global level, it provides information and knowledge to all interested developing country Parties.  At the same time, it also fosters regional exchanges and support to specific CBIT project countries.  It then uses the knowledge gained from these interactions to contribute to the global platform. Finally, it encourages individual countries to share transparency-related knowledge and experience with their peers directly through the platform.

Sustainability

The focus of project support is a sustainable approach to transparency activities by supporting capacity strengthening in CBIT countries and other developing country Parties to the Paris Agreement.  One key element of the streamlined platform established in this project is the preservation of the platform under the proposed Phase IIB, which will extend its life through the 2019-2024 “prepatory phase” for Article 13 reporting. This arrangement will maintain continuity and allow countries access to valuable transparency-related information beyond the conclusion of this project.

Furthermore, it directly encourages countries to enhance and embed enhanced transparency frameworks into their institutional frameworks, which will put procedures into place that will last long after this Phase IIA project finishes.  This project also engages other stakeholders in fulfilling the provisions of the Paris Agreement, including senior policy-makers and CSOs. Ideally, this CBIT project will increase the ownership role that national institutions play in MRV and transparency activities, which increases the likelihood that countries will support continuous MRV systems and will move towards the utilization of the information they generate for national policy-making purposes.

The project approach also emphasizes sustainability by capturing transparency-related knowledge and experience that is generated by experts both globally and in individual countries and regions and sharing it through long-term information platform. The pilot regional peer-to-peer learning network on GHG inventories will build formal and informal ties among countries in the LAC region, which should provide benefits that extend beyond this project.

Potential for Scaling up

The project itself represents the scaling up of activities implemented under the GSP and CBIT global platform projects, but it also has strong potential to expand.  For example, the number of sub-regional networks can increase as additional countries identify areas for cooperation. It will also address other Convention-related requirements or initiatives as they arise. Finally, the knowledge products and support for CBIT program countries will be highly relevant to the many developing country Parties who will not receive CBIT funding from GEF but who will still need to meet reporting requirements under the Paris Agreement.  There will be a significant demand for the tools and methodologies developed under the national projects, the global project, and other global CBIT projects, such as the FAO-GEF global project on AFOLU and the Conservation International (CI)-GEF project on forestry. Knowledge products from all of these projects will be shared through the new streamlined platform, creating synergies and optimizing available resources.

1b. Project Map and Geo-Coordinates. Please provide geo-referenced information and map where the project interventions will take place.

The proposed project is a global project, and it will involve the participation of developing countries around the globe.

# A.2. Child Project?  If this is a child project under a program, describe how the components contribute to the overall program impact.

# Not applicable.

A.3.  Stakeholders. Please provide the Stakeholder Engagement Plan or equivalent assessment.  In addition, provide a summary on how stakeholders will be consulted in project execution, the means and timing of engagement, how information will be disseminated, and an explanation of any resource requirements throughout the project/program cycle to ensure proper and meaningful stakeholder engagement.

Select what role civil society will play in the project:

Consulted only;

Member of Advisory Body; contractor;

Co-financier;

Member of project steering committee or equivalent decision-making body;

Executor or co-executor;

Other (Please explain). Information exchange; training provision; consultation; work planning, participation in meetings and workshops.

Civil society will be involved in the project in several ways.  First, the integrated platform will share best practices from CBIT national projects on how to integrate CSOs into national transparency activities.  In addition, international NGOs (INGOs) such as the World Resources Institute, have participated in CBIT technical workshops to contribute expertise and serve as a resource for country participants. The project intends to encourage the continued participation of relevant INGOs in technical workshops, COP side events,  and other project-related meetings. Finally, the project will support the two-way exchange of information with regional and international CSOs that support gender equality and women’s participation, such as the European Institute for Gender Equality, to inform the deliverables under Output 2.4.

Avoiding duplication with other initiatives will be key to using project resources efficiently. Meetings and workshops conducted over the course of the CBIT Phase I project have provided ample opportunity to consult with project stakeholders regarding Phase II of the project.  In addition, two other GEF Implementing Agencies and several CSOs (with equal participation by women and men) were consulted in August 2018 specifically regarding the design of the Phase II project.  These consultations affirmed the proposed project activities and provided information on current donor and CSO activities. No objections to any proposed activities or approaches were raised.

The GEF Technical Workshop and accompanying donor coordination forum (Rome, May 2019) and the accompanying meeting on enhancing donor coordination in transparency provided an additional opportunity to solicit feedback from CBIT project countries, donors, and representatives of CSOs.  General themes in consultations included a high interest in information exchange both among donors and participating developing countries.  Other indications of country interests and priorities were gathered from the GEF 2018 analysis of CBIT country projects, in which 100% of participating countries sought support for capacity building and training, 88% for transparency policy design, and 80% for MRV systems.  These priorities will be taken into consideration during the development of work plans for knowledge products, including the associated training modules, under Output 1.3.

Table 2 provides an overview of the anticipated project stakeholders and their envisioned role in the project.

Table 2: Key Stakeholders

| Name of Institution | Type of Stakeholder | Role in the Project |
| --- | --- | --- |
| UNDP | Implementing and Executing Agency for the project | UNDP is a GEF implementing agency that will also serve as the lead implementing agency for this project and an executing agency for Component 2 of the project (with the exception of Activity 2.2.4). It will be responsible for appointing a project coordinator. UNDP will also play a key role in facilitating coordination and knowledge sharing among the national CBIT projects in its GEF portfolio. |
| UNEP | Implementing Agency for the project | UNEP is a GEF implementing agency that will also serve as the implementing agency for Component 1 of the project and for Activity 2.2.4. It will play a key role in facilitating coordination and knowledge sharing among the national CBIT projects in its portfolio. |
| UNEP DTU Partnership | Executing Agency for the project | The UNEP DTU Partnership will serve as an executing agency for selected project outputs implemented by UNEP. The UNEP DTU Partnership will also provide co-financing for capacity building and analytical support related to transparency, particularly in the area of adaptation, and for project management. |
| Food and Agriculture Organization of the United Nations (FAO), Conservation International (CI), and others | Other GEF implementing agencies | Other GEF implementing agencies will share materials developed through other global CBIT projects and will coordinate on training. The CBIT Phase II project will serve as a means of disseminating information resources, guidance, and good practice from the FAO-GEF project on agriculture, forestry, and other land use (AFOLU) following that project’s scheduled conclusion and will include a dedicated space where pilot countries can interact. Finally, the project will provide a broader means of distribution for training materials developed under country-level CBIT project implemented by other agencies (i.e. CI) and will involve those project managers and experts in global platform meetings and activities. |
| Initiative for Cliamte Action Transparency (ICAT), Partnership on Transparency in the Paris Agreement (PATPA), International Partnership on Mitigation and MRV, Paris Committee on Capacity Building (PCCB), Partnership to Strengthen Transparency for co-Innovation (PaSTI) | Other transparency support initiatives | The information available through the library and other sections of the integrated web platform and the development and content of training modules will be coordinated with a network of existing transparency support initiatives. The integrated web platform will contain links to the platforms, databases, and on-line tools that have been developed through these partnerships. For example, ICAT will share its series of guidance documents on transparency with the project beneficiaries.The CBIT integrated web platform and newsletter will also provide information on learning events sponsored by these initiatives, such as PCCB capacity building forums and PaSTI webinars. |
| Countries with GEF-funded CBIT projects | National governments | Participating countries will provide information regarding their national CBIT project, participate in knowledge exchange, collaborate in the creation of content for the platform. |
| Development Partners | International Organisations and developed country governments | These partners will coordinate existing and upcoming support to develop national capacity globally to support countries meeting the Paris Agreement Article 13 requirements. |
| Civil Society Organizations (CSOs) | NGOs (national, sub-regional, regional, and international) and research institutes | International NGOs such as the World Resources Institute (WRI) participated in CBIT technical workshops under Phase I, contributing their expertise, and they are expected to continue to do so. In addition, the project will exchange information with CSO partners; e.g. the BUR database to be maintained by the Institute for Global Environmental Strategies (IGES). The project will also exchange information with regional and sub-regional CSOs; e.g., with Fundacion Bariloche for the Latin America and Caribbean region. Non-governmental actors at the country level are expected to benefit through the increased availability and quality of climate change information and through more robust NDCs. In addition, the project will support the two-way exchange of information with regional and international CSOs that support gender equality and women’s participation, such as the European Institute of Gender Equality, to inform the deliverables under Output 2.4. |
| UNFCCC | International organization | The UNFCCC and its secretariat will play three important roles in project implementation. First, the secretariat will serve as a provider for capacity building related to the UNFCCC. Second, the Secretariat, which houses the 24-member Consultative Group of Experts (CGE) and its e-Network, will exchange information with the project. Third, it will play a facilitating role in the implementation of the Convention. |
| UNFCCC Parties | All countries | All parties to the UNFCCC are expected to provide information and participate in discussions and information exchanges. A representative of one developing and one developed country government will serve on the Project Steering Committee (see Section II.6). |

Private Sector Engagement: As the project is focused on improving the capacity of governments to undertake transparency obligations, the private sector will not be directly engaged in the project. However, indirect engagement of the private sector will take place in three ways:  1) knowledge sharing from GEF-CBIT project countries related to activities they undertake to involve the private sector in mitigation activities;  2) the dissemination of methodologies and tools for engaging the private sector; e.g., in ETFs and in national GHG inventories using IPCC 2006 guidelines (industry surveys for activity data, etc.); and 3) the identification investment priorities for private sector climate change actions and green portfolios.

A.4. Gender Equality and Women's Empowerment. Provide the gender analysis or equivalent socio-economic assessment.

Developing country parties of the UNFCCC and the Paris Agreement vary in terms of gender equality and women’s empowerment. According to the Gender Development Index (GDI) data for 2017, the global GDI value is 0.941, while the average value for least developed countries is 0.868. It should be noted some countries with national CBIT projects have GDI values higher than the global average, while others have have values that are lower.

According to the Global Gender Gap Report 2018, the global gender gap score, another measure of parity, is currently 68%. The 2018 report notes that “Across the four subindexes, on average, the largest gender disparity is on Political Empowerment, which today maintains a gap of 77.1%. The Economic Participation and Opportunity gap is the second-largest at 41.9%....”  Again, developing country Parties vary widely in their scores and in some cases have achieved high levels of parity by global standards; for example, Nicaragua and Rwanda are fifth and sixth in the global rankings, respectively.

Developing country Parties that have signed the 2015 UN Sustainable Development Goals (SDGs) have committed to progress under SDG 5: “Achieve gender equality and empower all women and girls.” Under this goal, countries are to achieve nine specific targets that include the following relevant targets for this project: “Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision making in political, economic and public life;” and “Enhance the use of enabling technology, in particular information and communications technology, to promote the empowerment of women.” Countries also commit to monitor progress towards the targets that have been established.

As the introduction to the 2017 UN Women guidebook Leveraging Co-Benefits between Gender Equality and Climate Action notes, “Gender mainstreaming is not simply about adding a ‘women’s component.’ Gender mainstreaming is about thinking differently, modifying climate and development interventions so that they will benefit men and women equally. It is about transforming social, economic and institutional structures towards gender equality and women’s empowerment in climate action and resilience building. The impacts of climate change, including on access to productive and natural resources, amplify existing gender inequalities. Climate change affects women’s and men’s assets and well-being differently in terms of agricultural production, food security, health, water and energy resources, climate-induced migration and conflict, and climate-related natural disasters. At the same time, women are powerful change agents to address climate change at scale. They are key actors in building community resilience and responding to climate-related disasters. Women tend to make decisions about resource use and investments in the interest and welfare of their children, families, and communities.”

The UNFCCC Gender Action Plan was established under UNFCCC 3/CP.23 Section E of the Action Plan specifically focuses on monitoring and reporting, and it states that “The GAP seeks to improve tracking in relation to the implementation of and reporting on gender-related mandates under the UNFCCC.” The Paris Agreement has highlighted gender equality and women’s empowerment as a guiding principle and called for adaptation and capacity-building actions to be implemented in a gender-responsive manner.

In 2016, 40% of the (I)NDCs mentioned women and/or gender in the context of their national priorities and ambitions for reducing emissions. However, developing countries will require support in monitoring progress regarding these ambitions. In the area of reporting, a number of developing countries do not mention gender equality issues/ priorities in their National Communications and BURs. Revised NDCs and the advent of BTRs will necessitate capacity strengthing in developing countries related to gender equality and women’s empowerment as they relate to reporting and transparency.  At the same time, a number of developing country Parties have experience in improving gender parity at a national level that is relevant to others.

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes  /no) If yes, please upload gender action plan or equivalent here.

If possible, indicate in which results area(s)  the project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision making; and or

generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes /no)

The proposed project incorporates these elements and addresses gender  equality issues across its components and in a dedicated output designed to support countries in mainstreaming gender equality into transparency activities. The current project will be able to draw on existing resources and networks to support capacity strengthening related to gender equality and climate change.  For example, the Gender Responsive National Communications Toolkit  developed under the GSP could serve as a foundation for the development of gender mainstreaming in transparency activities. This toolkit makes the process of reporting more transparent in terms of whose involved, whose views are represented, gender-differentiated risks, and the types of support men and women need to influence climate adaptation, mitigation, policymaking and reporting. It can also be used to build capacity for gender analysis of key climate change issues that are reported on in NCs.

Several CBIT country projects to be financed under GEF-6 include targeted outputs related to gender mainstreaming.  In addition, the project will build upon gender-mainstreaming activities undertaken through GSP support for regional networks, such as the “Supporting the integration of gender considerations into MRV/transparency processes in the Western Balkan Countries” sub-regional workshops, which took place since December 2017.  This project will draw from their experiences and allow the dissemination of good practices. As well as, promoting women as role models in climate action in the professional areas where there are underrepresented, or eventually engage and showcase feminist climate change specialist, leaders, thinkers in the activities where women tend to be understated. This will be promoted via the CBIT web platform, peer learning activities and workshops.

Activities under Output 2.4 of the proposed project focus directly on gender mainstreaming in Article 13. In addition, activities in each component include explicit language on supporting women’s meaningful participation in project activities.  Content and materials that are developed under this output will be made available to a broad audience in several ways. First they will be disseminated through the annual stocktaking meetings conducted under Component 2. They will be available on the integrated web platform established under Component 1.1. Finally, they may be shared through the pilot south-south learning network for Latin American countries that is established under Output 2.2. Several activities also support the collection of gender-disaggregated data and knowledge that includes gender considerations.

In the area of project management, gender equality and balance will be promoted during all project’s recruitment of personnel/consultants and related activities. All advertised positions will be equally opened to both genders and the text on term of references will be carefully checked to avoid any gender stereotypes. M&E activities will request gender dis-aggregated data and will consider whether project activities and/or benefits have had differentiated results by gender. Furthermore, gender sensitive/responsive indicators will be monitored at the objective level as part of the monitoring of GEF streamlined indicators and also as part of the stocktaking exercise so that this can inform the design follow up interventions.

Finally, the project will adopt guidance resulting from the recommendations that will be prepared for consideration by UNFCCC Conference of the Parties at its 25th session (November 2019) on the basis of the synthesis report to be prepared by the UNFCCC Secretariat for the Subsidiary Body for Implementation “on the implementation of the gender action plan, identifying areas of progress, areas for improvement and further work to be undertaken in subsequent action plans.”

A.5 Risk. Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation.(table format acceptable):

The following table provides an overview project-related risks and how they will be addressed.

# Table 3: Project Risks and Risk Mitigation

| Risk | Level of Risk | Approach to Risk Mitigation |
| --- | --- | --- |
| The integrated platform is not perceived as relevant by users and fails to attract traffic | Low/Moderate | The number of internet platforms dedicated to climate change transparency continues to increase. The GSP and CBIT-GCP platforms already have a specific audience, and the integrated platform will continue to provide content (e.g. the expert roster) that is not available elsewhere. The project will also undertake specific activities to drive traffic to the new website, including continuous communication with other platforms. |
| Stocktaking workshops and side events fail to attract sufficiently high-level decision-makers and practitioners | Low | Experience with these events to date has indicated that high-level decision-makers and practitioners will attend when the topics are relevant and emerge from ongoing dialogue. The project will communicate with other support providers to avoid scheduling conflicts and to schedule back-to-back workshops when possible, reducing the need for participants to travel. |
| High turnover of participants due to high turnover of political appointees and civil servants in participating countries | Moderate | 1) The availability of strong documentation and codification of knowledge in regional languages under the project. will ease the transition between experts and decision-makers. 2) Stocktaking meetings and side events will be scheduled throughout the project implementation period, exposing new participants to resources and contacts without a long waiting period. 3) Knowledge products that support country-level MRV systems will encourage countries to centralize and archive data, which will preserve institutional memory and minimize disruption from staff turnover. |

A.6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

# Implementing and Executing Arrangements: UNDP and UNEP will be the GEF Implementing Agencies (IAs) for this initiative and are responsible to the GEF for the use of project resources as written in the project document, or any amendments agreed. UNDP will serve as the lead agency for the project as a whole and will appoint a Project Coordinator as the primary point of contact. UNEP will have the IA role for Component 1 and for Activity 2.2.4, and UNDP will have the IA role for Component 2, with the exception of Activity 2.2.4. UNDP will be responsible for executing project outputs where it serves as an IA. In outputs where UNEP has an IA role, it will either execute the outputs directly or it will delegate the execution of the outputs to its collaboration centre, the UNEP DTU Partnership.  The Executing Agencies will be responsible for day-to-day management of the project, including financial management and project reporting. Project administration will follow the procedures of the respective Executing Agencies, including those related to procurement, contracting, and recruitment.

Project Management: The Project Coordinator will function within an executive management group (EMG), which will be composed of representatives from UNEP (consisting of the UNEP liaison officer and task manager), UNDP (the project coordinator and task manager), and the UNEP DTU Partnership (the project manager). The EMG will oversee the implementation of the project through monthly meetings. Its main functions will be to approve management decisions and ensure timely delivery of quality outputs. The main purpose of the EMG is to establish a very close coordination between UNEP and UNDP in order to ensure the execution of the activities of the four components as one single project.

Project Oversight: The project will utilize a project steering committee (PSC), which will be composed of representatives from the following organizations: UNEP, UNDP, the UNEP DTU Partnership, the UNFCCC, the GEF Secretariat, one developed country; and one developing country. The committee will be responsible for reviewing project progress, approving annual work plans, budget and providing strategic guidance to the EMG. The PSC will meet annually, unless one of the committee members calls for ad hoc interim meeting. Developing country representation on the PSC will provide a voice for project beneficiaries. The PSC meetings will be scheduled concurrently with other workshops or side events organized by the project to minimize and travel costs.

Monitoring and Evaluation (M&E) Coordination: Project‐level monitoring and evaluation will be undertaken in the framework of the United Nations Evaluation Group 2016 Norms and Standards and, within that framework, UNDP requirements as outlined in the UNDP Program and Operations Policies and Procedures (POPP) and UNEP requirements for project monitoring and evaluation. Additional mandatory, GEF‐specific M&E requirements will be undertaken in accordance with GEF M&E policy and other relevant GEF policies.

Coordination with other GEF-funded projects that focus on transparency: The proposed project is designed to prevent a gap in support to developing countries on transparency issues. Project activities are therefore scheduled to transition from the CBIT Phase I project and the GSP into a unified Phase II support program. Figure 2 in Section II.1.a provides an overview of the timing of this process.  The proposed project will also liaise with the planned CBIT projects to maintain an overview of the work being done in the sector.  Furthermore, the project will maintain contact with country-level projects under the CBIT funding window and country-level climate change enabling activities due to their focus on GHG inventories and reporting.

# Coordination with other stakeholders is outlined in Table 2.

# Additional Information not well elaborated at PIF Stage:

A.7 Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF)?

The socioeconomic benefits of improved MRV in the area of climate change are—while indirect—potentially significant. As an International Energy Agency (IEA) report on the socioeconomic issues related to the low-carbon transition states, “It is a multifaceted challenge in which the actors are inter-dependent and for whom the solutions have immediate local benefit (e.g. improved quality of life, employment, investments) as well as long-term global benefits, such as reduction of CO2. For the transition to be a success, a variety of stakeholders representing socio-economic sectors will need to actively participate: policy makers, energy planners, the research community, academia, businesses and industry, and individuals.”

Under Outcome 1 of the project, “Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements,” the unified website will provide information and tools will support streamlined transparency activities, which will result in a more efficient use of public funds in the countries that utilize them.  In addition, support for aligning policies and measures with action to address climate change will lead to efficiencies and increased uptake of policies with low-carbon benefits.  The same IEA report states that “A virtual knowledge centre where theory, practice, case studies and experiences can be shared across various cultures and programmes was found to be particularly effective.”

Under Outcome 2 of the project, “Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming,” countries will gather the information necessary to set more robust and meaningful targets. Current research shows the need for improved MRV in key sectors such as agriculture that would allow countries to align their policies and measures with commitments under their NDCs.  Strong transparency frameworks will allow countries to identify cost-effective means of mitigation and adaptation and to understand the co-benefits, including socio-economic benefits, of action to address climate change.

Finally, a stronger transparency framework would provide countries with the information necessary to undertake more ambitious targets, which would contribute at the global level to meaningful action against climate change.

A.8 Knowledge Management. Elaborate on the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives (e.g. participate in trainings, conferences, stakeholder exchanges, virtual networks, project twinning) and  plans for the project to assess and document in a user-friendly form (e.g. lessons learned briefs, engaging websites, guidebooks based on experience) and share these experiences and expertise (e.g. participate in communities of practice, organize seminars, trainings and conferences) with relevant stakeholders.

As in the ongoing CBIT project, knowledge management is at the core of the proposed CBIT Phase II. Special attention has been given in CBIT Phase II to knowledge accessibility in all project components. Steps to increase accessibility will include distributing information from sub-regional workshops and networks to other regions, identifying low-bandwidth and off-line approaches to knowledge sharing for the many parts of the world that face connectivity issues, translating relevant materials guidance into multiple languages so that more experts can use them easily, and encouraging countries to utilize open-source solutions to data management. Knowledge generated under both Phase II projects will be distributed free of charge.

All components involve capturing knowledge and disseminating it in such a way as to reach the largest global audience. The project will also capture and share knowledge from country-level projects and from other transparency-related initiatives, and it will develop a long-term data management plan in order to ensure that information and knowledge gathered during the project will continue to be accessible to those who need it.

Component 1 of the project (Streamlined knowledge development and delivery in support of Article 13) will focus on generating knowledge products and maintaining a web platform to allow knowledge sharing and dissemination. The streamlined platform is also consistent with the recommendation of the 2015 GEF Scientific and Technical Advisory Panel (STAP) interim report on knowledge management in the GEF to provide enhanced support for South-South exchanges. Component 2 explicitly supports learning from other relevant initiatives through the stocktaking in 2.1, information dissemination through a pilot regional coordination initiative in 2.2, and coordination with support providers in 2.3.

Table 4 provides an overview of the knowledge management approach for Phase IIA.

Table 4: Knowledge Management Approach for CBIT Phase IIA

|  | Key Deliverables | Timeline |
| --- | --- | --- |
| Project Component 1 | - Unified project website - Data management plan - Webinars, audio briefings, articles - Survey of website users - KM plan for information from individual country CBIT projects and the self-assessment tool - Facilitated peer learning / knowledge sharing through website - At least two knowledge products (website content, webinar, etc.) from emerging good practice in participating CBIT countries. - Knowledge inventory of guidance documents and training modules with a view to updating and/or replacing them - Handbook for countries on sustainable data management - Training modules - Fact sheets on emerging issues related to the the Paris Rulebook and COP24, particularly BTRs | Website: Y1 Website Maintenance: Ongoing KM Plan: Y1 Knowledge Inventory: Y1 Fact sheets: Ad hoc Knowledge products: Ongoing |
| Project Component 2 | - Global stocktaking reports and dissemination of findings from country-level annual self-assessments - COP side event summaries - Guidance on integrating gender into reporting and transparency | Reports and summaries: Annually Gender guidance: Y1-2 |
| Project Management | - Project brochure - Final Report, summary of achievements | Brochure: Y1 Report/summary:Y3 |
| Project M&E and Learning | - Inception report, terminal evaluation - Reports on training participation by gender and gender mainstreaming in other activities, including website usage - Lessons learned note(s) | M&E reports: see Section 9 and Annex I LLN: ad hoc |

# B. DESCRIPTION OF THE CONSISTENCY OF THE PROJECT WITH NATIONAL PRIORITIES

B.1 Consistency with National Priorities. Describe the consistency of the project with national strategies and plans or reports and assessements under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.:

This CBIT Phase II project is consistent with the Paris Agreement and national priorities, such as national communications, BURs, and NDCs tracking, as it will support countries in obtaining the necessary additional capacities and tools to track the progress in climate change mitigation and adaptation and, more specifically, the enhanced transparency framework's modalities procedures and guidelines (MPGs). Also, this project is in line and will contribute to the UNDP Climate Promise, which aims to help ensure countries’ new climate action pledges better align their national sustainable development priorities through a wide range of thematic technical support. It will be instrumental in particular to the Climate Promise Service Line 5 “Monitor Progress and Strengthen Transparency”, since it will support for capacity strengthening related to monitoring and tracking progress on key climate-related indicators.  At the same time, it will also support data collection and analysis that can in turn inform other policy exercises, such as Technology Needs Assessments (TNAs), National Adaptation Plans (NAPs), National Capacity Self Assessments (NCSAs), and others.

This project will also contribute to Sustainable Development Goals (SDGs) 13 and 17. The platform will serve as an underlying mechanism for tracking progress towards the Paris Agreement on Climate Change (SDG 13) and the specific target of 13.3 'Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning' and its indicator 13.3.2 'Number of countries that have communicated the strengthening of institutional, systemic and individual capacity-building to implement adaptation, mitigation and technology transfer, and development actions'.  At the same time, it will provide a forum encouraging partnerships among relevant actors (SDG 17) and the specific target of  17.9 ‘Enhance international support for implementing effective and targeted capacity-building in developing countries to support national plans to implement all the sustainable development goals, including through North-South, South-South and triangular cooperation’ and its indicator 17.9.1 ‘Dollar value of financial and technical assistance (including through North-South, South-South and triangular cooperation) committed to developing countries.’

# C.  DESCRIBE THE BUDGETED M &E PLAN

The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project‐level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP (Programme and Operations Policies and Procedures (POPP) and UNDP Evaluation Policy. While these UNDP requirements are not outlined in this project document, the UNDP Istanbul Regional Hub will work with the relevant project stakeholders to ensure UNDP monitoring and evaluation (M&E) requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF‐specific M&E requirements will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project‐level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities.

M&E Oversight and monitoring responsibilities:

Project Coordinator: The Project Coordinator is responsible for day‐to‐day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Coordinator will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Coordinator will inform the EMG and the Project Board of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

The Project Coordinator will develop annual work plans based on a multi‐year work plan, including annual output targets to support the efficient implementation of the project. The Project Coordinator will ensure that the standard GEF IA and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence‐based reporting in the GEF Project Implementation Report (PIR), and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender strategy, KM strategy, etc.) occur on a regular basis.

Project Steering Committee: The Project Steering Committee will take corrective action as needed to ensure the project achieves the desired results. The Project Steering Committee will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Steering Committee will hold an end‐of‐project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

Project Implementing Partners: The lead agency (UNDP) is equally/coordinately responsible with UNEP for providing any and all required information and data necessary for timely, comprehensive and evidence‐based project reporting, including results and financial data, as necessary and appropriate.

The UNDP Istanbul Regional Hub is responsible for complying with all UNDP project‐level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the Atlas risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and UNDP Results-Oriented Annual Reporting (ROAR). Any quality concerns flagged during these M&E activities (e.g. the annual GEF PIR quality assessment ratings) must be addressed by the Project Coordinator and the EMG.

The UNDP Istanbul Regional Hub will retain all M&E records for this project for up to seven years after project financial closure to support ex‐post evaluations undertaken by the UNDP Independent Evaluation Office and/or the GEF Independent Evaluation Office.

UNDP‐GEF Unit: Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP‐GEF Directorate as needed.

Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on projects using Direct Implementation (DIM).

Additional GEF monitoring and reporting requirements:

Kick-off Meeting and Inception Report: A project kick off meeting will be held immediately as the project is approved. The Project Coordinator will prepare the inception report no later than 60 days after the inception workshop. The inception report will be cleared by the EMG and will be approved by the Project Board.

GEF Project Implementation Report (PIR): UNDP will assume overall responsibility for, and the Project Coordinator and the EMG will provide objective input to, the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR. The PIR submitted to the GEF will be shared with the Project Steering Committee.

Lessons learned and knowledge generation: Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy‐based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

GEF Focal Area Core Indicators: The following GEF core indicator will be used to monitor global environmental benefit results: number of beneficiaries, and of that, number of women. This indicator will be monitored by the Project Coordinator/Team and shared with the consultant(s) conducting the terminal evaluation before the required evaluation mission takes place. The core indicator numbers will be submitted to the GEF along with the completed Terminal Evaluation report.

Terminal Evaluation (TE): An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities, to be funded and in equal parts by UNDP and UNEP and to be implemented by UNDP. In agreement with UNEP, the part of the funds for the TE under the UNEP authorization will be directly transferred to UNDP by GEF once the CEO endorsement is approved.

The terminal evaluation process will begin six months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by UNEP Evaluation Office and UNDP. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The draft TE report will be sent by the UNEP Evaluation Office to project stakeholders for comments. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the report is finalized and further reviewed by the GEF Independent Evaluation Office upon submission. The evaluation report will be publicly disclosed and may be followed by a recommendation compliance process. The management response and the evaluation will be uploaded to the GEF, UNEP, and UNDP corporate systems, which include the Project Information Management System (PIMS) and the UNDP Evaluation Office Evaluation Resource Centre in the case of UNDP.

Final Report: The Final Report will be a comprehensive report summarizing all activities, achievements, lessons learned, objectives met or not achieved structures and systems implemented, etc. It will make recommendations for any further steps that may need to be taken to ensure the sustainability and replication of project activities. It is to be completed not more than three months following the technical closure of the project. This report, along with the project’s terminal PIR, the terminal evaluation (TE) report, and the corresponding management response will comprise the final project report package. The final project report package shall be discussed with the Project Steering Committee during an end‐of‐project review meeting to discuss lessons learned and opportunities for scaling up.

A summary of M&E activities envisaged is provided in Annex I.  When relevant, M&E activities will assess gender mainstreaming. The GEF contribution for M&E activities is USD 61,000.

# PART III:  CERTIFICATION BY GEF PARTNER AGENCY(IES)

- GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Pradeep Kurukulasuriya, Executive Coordinator and Director, Global Environmental Finance UNDP |  |  | Damiano Borgogno | +90-850-2882-206 | damiano.borgogno @undp.org |
| Kelly West, Senior Programme Manager and GEF Coordinator, Corporate Services Division, UNEP |  |  | Geordie Colville | +254206723257 | geordie.colville @unep.org |

- GEF_CEOENDR_60

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

|  | Objective and Outcome Indicators | Baseline | End of Project Target | Sources of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. | Mandatory GEF Indicator 1: # of project beneficiaries disaggregated by gender (individual people) | 150 people | At least 300 people will utilize support for transparency and reporting from project outputs and activities, and at least 150 of them will be women. | Reporting by CBIT Project Countries and project documentation that includes registration lists for webinars, trainings, and other in-person or on-line gatherings or discussion | Participating countries will continue to use the tracking tool indicator. |
|  | Indicator 2: % of the users surveyed who consider the platform (website, its features, and knowledge products) very useful or useful for their purposes | 0 (platform has not yet been merged) | 70% of users surveyed consider the platform to be very useful or useful for their purposes (measured as a score of 4 or 5 on a 5-point satisfaction scale) | Pop-up survey conducted on the streamlined website. | Partners will have sufficient time and interest to utilize the project’s resources. |
| Project component 1 | Streamlined knowledge development and delivery in support of Article 13 |  |  |  |  |
| Project Outcome 1 Developing countries and practitioners increasingly access and use information and knowledge on new and existing reporting requirements | Indicator 3: Knowledge demand / uptake: i.e., number of countries and practitioners using the platform’s services and knowledge products every quarter (on average) | At least 40 countries and practitioners use the CBIT Global platform’s services and knowledge products every quarter (on average) | At least 60 stakeholders use the platform’s services every quarter (on average) | Website analytics. Country and practitioner feedback collected in the course of the Terminal Evaluation by the evaluator(s). | The unified website will simplify requests and searches for users and increase user interest. |
| Outputs to achieve Outcome 1 | 1.1 Existing Global Support Program (GSP) and CBIT platforms merged and redesigned into an integrated web platform 1.2 Platform content and features maintained and updated regularly 1.3 Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, updated, developed, and customized |  |  |  |  |
| Project component 2 | Global stakeholder outreach and dissemination of best practices |  |  |  |  |
| Outcome 2 Developing countries can document and share progress, support needed and received, and good practice on Article 13 implementation, including gender mainstreaming. | Indicator 4: Number of developing countries with beneficiaries who have shared their lessons (progress, support needed and received, and/or good practice) through project activities. | Experiences from more than 40 countries have been documented by developing country beneficiaries through annual self-reporting exercises, such as questionnaires in advance of technical workshops and implementation reports and / or through workshops supported by CBIT Phase I. | Experiences from more than 60 developing country beneficiaries have been documented through annual self-reporting exercises, such as questionnaires in advance of technical workshops and implementation reports and / or through workshops and regional meetings supported by this project. | Lists of countries participating in regional and global workshops based on registration data; information from questionnaires collected in advance of technical workshops and other content on the streamlined platform; and Project Implementation Reports for country-level CBIT projects. Structured interviews conducted in the course of the terminal evaluation by the evaluator(s). | New CBIT program countries will see value added in contributing information to the platform. |
|  | Indicator 5: Number of developing countries sharing good practice in gender mainstreaming on the streamlined CBIT web platform | None | Good practice in gender mainstreaming from at least 15 developing countries is shared on the streamlined platform. | Review of project documentation and platform content in the course of the Terminal Evaluation by the evaluator(s). | Developing country experts will have time and interest in participating in gender mainstreaming training. |
| Outputs to achieve Outcome 2 | 2.1 Annual stocktaking of progress, capacity needs, and support to all non-Annex I countries conducted 2.2 COP side events and outreach efforts organized to enhance and disseminate results 2.3 Coordination among support providers facilitated 2.4 Assistance provided to countries with integrating the UNFCCC Gender Action Plan into enhanced transparency frameworks |  |  |  |  |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

| Secretariat Comment at PIF/Work Program Inclusion | IA Response |
| --- | --- |
| “Not at this time. After a call with the agencies, it was decided that the proposal would be broken up into two projects, an MSP that would request resources from the CBIT Trust Fund and an FSP that would request resources from the GEF Trust Fund. This will allow the CBIT Trust Fund resources to be programmed before the Council deadline of October 31, 2018 and ensure the continued support to the CBIT Global Coordination Platform, of which Phase I will end by June 2019.” | Project has been divided into two projects, and the MSP submitted here requests funds from the CBIT Trust Fund as per the decision taken. |

ANNEX C:  STATUS OF IMPLEMENTATION OF PROJECT PREPARATION ACTIVITIES AND THE USE OF FUNDS

A.  Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: USD 50,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| ## Component A: Preparatory Technical Studies & Reviews | 20,000 | 17,150 | 2,850 |
| ## Component B: Formulation of the UNDP-GEF Project Document, CEO Endorsement Request, and Mandatory and Project Specific Annexes | 10,500 | 3,251 | 7,249 |
| Component C: Validation Workshop and Report | 19,500 | 3,249 | 16,251 |
| Total | 50,000 | 23,640 | 26,360 |

ANNEX D:  CALENDAR  OF EXPECTED REFLOWS (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up)

Not applicable.

# ANNEX E: GEF 7 CORE INDICATOR WORKSHEET

Use this Worksheet to compute those indicator values as required in Part I, Table E to the extent applicable to your proposed project.  Progress in programming against these targets for the program will be aggregated and reported at any time during the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and SCCF.

| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  | (Number) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target |  | Number Achieved |  |
|  |  |  |  | CEO Endorsement | MTR | TE |
|  |  |  | Female | 150 | Not applicable |  |
|  |  |  | Male | 150 | Not applicable |  |
|  |  |  | Total | 300 | Not applicable |  |

# ANNEX F: GEF PROJECT TAXONOMY WORKSHEET

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| X Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | X Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| X Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | X Type of Engagement |  |  |
|  |  | X Information Dissemination |  |
|  |  | X Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| X Capacity, Knowledge and Research |  |  |  |
|  | X Enabling Activities |  |  |
|  | X Capacity Development |  |  |
|  | X Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | X Knowledge and Learning |  |  |
|  |  | X Knowledge Management |  |
|  |  | Innovation |  |
|  |  | X Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| X Gender Equality |  |  |  |
|  | X Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | X Gender-sensitive indicators |  |
|  | X Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | X Capacity development |  |
|  |  | Awareness raising |  |
|  |  | X Knowledge generation |  |
| X Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | X Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | X United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution X Capacity Building Initiative for Transparency |
|  |  | X Rio Markers | X Climate Change Mitigation 2 X Climate Change Adaptation 1 |

# ANNEX G: TERMS OF REFERENCE OF PROJECT STAFF AND CONSULTANTS TO BE HIRED

KEY PERSONNEL: Project Coordinator (UNDP 61300)

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Project coordinator – staff (UNDP)

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Istanbul

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: The Project Coordinator will report to the Climate Mitigation Manager at UNDP.

Job tasks: The coordinator will implement both coordination-management tasks as well as technical tasks, with an estimated distribution of labor of 83% technical support and 17% coordination-management tasks.

Coordination-management tasks

- In cooperation with EMG, supervises and ensures the timely implementation of the project relevant activities as scheduled in the working plan

- Prepares a detailed work plan for the project and draft terms of reference for the subcontracts (in consultation with the EMG and PSC);

- Identifies and hires/subcontracts experts and institutions as needed for project activities;

- In cooperation with the EMG, supervises project support staff and consultants who are recruited to provide technical assistance as needed;

- Organizes and supervises the workshops and training needed during the project;

- Liaises with the developing country Parties, support providers, and NGOs in order to gather and disseminate information relevant to the project;

- Manages and monitors the project risks initially identified and submits new risks to the EMG and PSC for consideration and decision on possible actions if required; updates the status of these risks by maintaining the project risks log.

- Ensures timely submission of the Inception Report, Project Implementation Report, Technical reports, quarterly financial reports, and other reports as may be required by UNEP, UNDP, GEF and other oversight agencies.

- Controls the expenditures and otherwise ensure adequate management of the resources provided for the project;

- In cooperation with the EMG, summarizes and synthesizes the results of the project;

- Identifies follow-up activities and mobilizes other resources at the extent possible;

- Identifies and ensures synergy of the projects’ activities with other relevant ongoing / new projects.

- Collaborates with all relevant stakeholders and the Project Steering Committee and other partners to ensure their involvement in project activities.

Technical tasks

- Ensures that project activities are in the line with guidance provided by the CoP of the UNFCCC and contributes to the improvement of the UNFCCC reporting process and decisions relevant to Article 13 of the Paris Agreement.

- Engages directly with developing countries representatives and provide them with sound technical backstopping on all different topics covered by CBIT, including not limited to, elaboration of greenhouse gas inventories, development of emission mitigation scenarios, establishment of MRV systems, support to NDC tracking, establishment of monitoring and evaluation frameworks for adaptation.

- Provides sound advice and implement work to support countries in integrating gender equality considerations into the enhanced transparency framework, as established under 2.4

- Follows the process of international negotiations in the UNFCCC and respective decisions related to reporting of non-Annex 1 Parties and particularly in relation to the Paris Rulebook.

KEY PERSONNEL: Project Associate (UNDP 61200)

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Project Associate – staff (UNDP)

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Istanbul

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: The Project Associate will report to the Project Coordinator.

Job tasks:

The Project Associate will provide assistance to project implementation in the mobilization of inputs, the organization of events and other activities, and financial management and reporting. These activities will be undertaken in support of all project activities under Component 2 (with the exception of Activity 2.2.4), M&E activities, and project management activities. Specific duties include the following:

- Manage the day to day operations of the Project Management Unit, particularly with respect to the provision of technical services and support .

- Assist the Project Coordinator in the implementation of technical and operational activities for the preparation of the outputs under the project.

- Review technical and support information on climate change studies, projects and initiatives that may contribute to the project activities.

- Support the preparation of detailed terms of reference for the international and local consultants and experts to be hired for the implementation of the project as needed.

- Assist the Project Coordinator in the selection process of the consultants, including the consultant(s) for the Terminal Evaluation, to be hired by the Project according to the rules and procedures established by UNDP.

- Participate in the planning, organization and execution of Project activities.

- Support the organization and coordination of seminars, training activities, workshops, and other exchange and facilitation events for project stakeholders.

- Organize and coordinate information exchanges internationally and between participating institutions as necessary.

- Compile and/or prepare the documentation necessary for the procurement of services, good and supplies under the project

- Prepare administrative, technical and financial reports.

- Perform the procurement of services, good and supplies authorized by the Project Coordinator.

- Prepare requests for the payment as authorized by the Project Coordinator

- Assist the Coordinator in monitoring disbursements in accordance with the Project Budget and Disbursement Plan.

- Maintain the Project’s files and supporting documentation for payments.

- Undertake other administrative/ financial duties as requested by the Project Coordinator

- Other duties which may be required

KEY PERSONNEL # PM-0101

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Project management - staff

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Copenhagen

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP Task Manager and the Project Coordinator.

Detailed consultancy activities:

Manage and coordinate the day-to-day activities in Component 1that fall under the UNEP DTU Partnership scope

Provide technical input to the implementation of activities under Outputs 1.1, 1.2, and 1.3

Participate in the preparation of TORs for consultants and participate in the selection process

Prepare Project Steering Committee meetings

Prepare progress reports and a report on the streamlined platform under Output 1.1.

Ensure coordination with relevant partners to ensure that project activities are fully complementary to other on-going initiatives

KEY PERSONNEL # C1-0101

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Programming support to merge GSP/CBIT platform - staff

Duration: three years (part time)

Date Required: Jan 2020

Duty station: Copenhagen

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

Provide inputs on Activities 1.1.1, 1.1.2, and 1.1.3, including a report on the streamlined platform

Conduct requirements elicitation, including focus groups or surveys on user preferences and usage patterns (disaggregated by gender), both before and after the integrated platform becomes operational

Review and analyse existing, relevant climate change information portals and user traffic on the two current websites and propose a re-branding strategy, including a new logo, for the integrated platform with the support of the branding and communication expert and the graphic designer.

KEY PERSONNEL # C1-0102

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Maintain and update content on the GSP/CBIT platform - staff

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Copenhagen

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

Deliver inputs under Activities 1.2.1, 1.2.2, and 1.2.3, 1.2.4, and 1.2.5

Facilitate online peer learning through existing features and knowledge sharing through the regional network coordination feature (Activity 1.2.4)

KEY PERSONNEL # C1-0103

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Knowledge dissemination and communication - staff

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Copenhagen

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

- Under Output 1.3, develop and implement work plan for producing guidance documents and training modules on emerging issues (enhanced transparency frameworks and the Paris rulebook, gender mainstreaming)

- Under Activity 1.3.4, produce good-practice cases and successful approaches to reporting issues from participating countries documented and disseminated in the form of at least 3 good practice briefs and at least 3 webinars.

- Under Activities 1.3.1, 1.3.2, and 1.3.3, work with the Transparency Expert (C1-0106) to provide inputs to at least 3 knowledge products on emerging issues related to transparency and reporting.

KEY PERSONNEL # C1-0104

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Graphic designer (part time)

Duration: Three years

Date Required: Jan 2020

Duty station: Copenhagen/home-based

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

- Under Activity 1.1.3, design the integrated website, evolving the existing features and the additional features, and conduct a usability study and beta testing at the prototype stage

KEY PERSONNEL # C1-0105

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Software programmer

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Copenhagen

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

- Work with staff programming support (C1-0101) program the integrated platform and new features (planned and ad hoc), including search engine optimization (Activities 1.1.4, 1.1.5, 1.1.6, 1.1.8)

- Refine and update the self-assessment questionnaire under Activity 1.3.3 jointly with knowledge and dissemination staff to respond to new reporting requirements and user feedback

KEY PERSONNEL # C1-0106

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Climate transparency expert

Duration: Three years (part time)

Date Required: Jan 2020

Duty station: Home-based

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure: This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

Develop and implement work plan for producing guidance documents and training modules on emerging issues related to enhanced transparency frameworks and the Paris rulebook (Activities 1.3.1 and 1.3.4)

KEY PERSONNEL # C1-0107

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: Branding & communication expert

Duration: 3 years (part time)

Date Required: Jan 2020

Duty station: Home based

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Detailed consultancy activities:

Under Activity 1.1.2, review and analyse existing, relevant climate change information portals and user traffic on the two current websites, and under Activity 1.1.7 propose a re-branding strategy, including a new logo, for the integrated platform

KEY PERSONNEL # C2-0104

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Post title: LAC Regional Network Expert

Duration: 3 years (part-time)

Date Required: Jan 2020

Duty station: Panama City, Panama

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

Reporting Structure:   This position will report to the UNEP DTU Project Manager

Detailed consultancy activities:

- Identify and track countries’ demand for south-south support based on an initial survey and continuous interaction with countries.

- Ensure coherence and complementarity between CBIT initiatives in the LAC region and other ongoing and planned activities under other transparency initiatives (e.g. PATPA, ICAT, CBIT, RedINGEI, CCMRVH), including those supporting the mandate of the Latin American Forum of Environmental Ministers (Activity 2.2.4).

- Analyze and review national and subnational transparency activities, outputs and outcomes in the LAC region in order to identify complementarities and economies of scale that can be achieved through the promotion of south-south cooperation and sharing of good-practices, ultimately supporting countries to increase climate ambition and enhance the effectiveness of transparency actions. (Activity 2.2.4).

- Facilitate exchanges between LAC countries to enhance the design, uptake, and implementation of policies, regulations, and economic instruments tailored to the specific regional and national contexts of LAC to implement the enhanced transparency framework and the NDCs (Activity 2.2.4).

Contract (UNDP M&E: 71200): Terminal Evaluation (TE)

Project: Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement

Duration: Three months (part time)

Date Required: November 2022

Duty station: Home-based with travel as needed

Background:

The Paris Agreement signified an important turning point in the climate change negotiations as the global community recognized the urgency in facing climate change and agreed on a goal of "holding the increase in the global average temperature to well below 2 degrees Celsius above pre-industrial levels and pursuing significant efforts to limit the temperature increase to 1.5 degrees Celsius above pre-industrial levels” (Article 2). Article 13 of the Paris Agreement is critical to implementation, as it provides the outline for an enhanced transparency framework (ETF) for countries through which they can report on the actions they take related to climate change and the support that they provide and receive. From 2020 onward, all Parties to the Paris Agreement, both developed and developing, will be expected to begin to comply with Article 13. The advent of enhanced transparency frameworks presents an opportunity to streamline measurement, reporting, and verification (MRV) activities related to climate change by approaching the common elements of transparency activities in a holistic way.

The TE will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The TE will also review the project’s strategy, its risks to sustainability.The TE will be carried out by company with experience of evaluative projects and programs evaluation. The TE will assess the following four aspects of project progress: 1) Project strategy; 2) Progress towards results; 3) Project implementation and adaptive management; and 4) Sustainability.

- Reporting Structure: The contractor will report to the Project Coordinator.

Detailed contract activities:

The TE must provide evidence-based information that is credible, reliable and useful. The TE will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Environmental & Social Safeguard Policy, the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, lesson learned reports, strategic documents, knowledge products, and any other materials that the team considers useful for this evidence-based review). The TE will review the baseline GEF focal area Tracking Tool submitted to the GEF at CEO endorsement.

While the TE needs to employ various types of data as well as data collection tools, the TE is highly encouraged to use as much quantitative data as possible to make the analysis more objective and evidence-based. Qualitative approaches, including document reviews and structured or open-ended interviews, are also required for this TE.

The TE is expected to follow a collaborative and participatory approach ensuring close engagement with project personnel, participants from developing country Parties, staff from UNDP, UNEP, and the UNEP DTU Partnership, and other key stakeholders.

Engagement of stakeholders is vital to a successful TE. Stakeholder involvement should include interviews with stakeholders who have contributed or received information and/or support from the project.

Deliverables:

An inception report based on a desk review of project materials and documentation

Stakeholder interviews, either by phone or in person (a mission may be proposed as necessary)

A draft Terminal Evaluation Report, including updated GEF Tracking Tool figures

An accompanying summary presentation of the report’s findings

A final Terminal Evaluation Report that incorporates feedback from project stakeholders

Contract (UNDP 71200): IC / Transparency Expert

The consultant will closely work to support the GSP- CBIT platform in the development and facilitation of the following Transparency workshops both in the part regarding the coordination meeting as well as the technical workshop.

The consultant’s tasks will be the following:

- Provide support for the implementation of all activities under Component 2 of the project with the exception of Activity 2.2.4.

- Support the GSP in the design and implementation of the workshops. In this phase, virtual meetings will be held in order to identify key elements and construct the guide for the facilitation process of the meeting, based on lessons learnt from previous events and on UNDP capacity development principles

- Facilitate the coordination meeting and the technical workshop by using participatory methodologies following the guide for the facilitation process. The facilitator will facilitate in English. The consultant will need to have background knowledge on MRV, ensure full implementation of the agenda, facilitate the transition from one resource person to another, ensure participants’ active engagement in the discussions, coordinate Question and Answers sessions and facilitate the practical exercises during the event;

- Prepare two short reports describing the results from both the coordination meeting and the technical workshops. The format of the report will be provided by the GSP, upon suggestions by the consultant, and will include a synthesis of the event, identified lessons relevant for GSP’s work as well as recommendations for future activities of The CBIT platform.

Contract (UNDP 71200): IC / Gender and Climate Change

The consultant will closely work to support the GSP- CBIT platform in all activities related to gender and climate change mainstreaming. His/her responsibilities will be: - Provide technical assistance to each Network (Latin American and Balkan) to help them elaborate, refine and finalize their substantive gender/climate transparency work plans – as part of the work nationally implemented under NCs/BURs/CBIT - Assist in the implementation of the “Gender responsive National Communications Toolkit” in the Western Balkan + Lebanon and other regions (e.g. providing input to the national teams in drafting ToRs or providing peer review of relevant documents prepared by other consultants) - Update the Gender Responsive National Communications toolkit in light of new COP requirements and lessons learnt; - Support developing Countries in increasing the nomination of UNFCCC gender focal points; - Support the constructive collaboration among the member countries, including leading workshops, dialogue meetings, webinars and virtual interactions (e.g. emails and web). - Provide technical inputs to and facilitate the identification, design and roll-out of substantial initiatives at the regional and national levels, including but not limited to raise awareness and to enhance institutional collaboration between institutions and other relevant actors (ex. Ministries dealing with gender issues). - Design the agenda and facilitate the Network workshop on gender responsiveness to climate change actions if any. - Provide technical inputs for elaborating training materials and carry on in-country trainings on gender responsiveness on climate change actions. - Assist the GSP coordinator in providing inputs for terms of reference, concept notes, webinars, translate documents and elaborate technical documents - Support tasks related to the needs of the Network

# ANNEX H-1: DETAILED GEF BUDGET

|  | Project Title: Global CBIT Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Project Number: GEF ID 10128 |  |  |  |  |
|  | Project Implementing Agency: UNDP, UNEP |  |  |  |  |
|  | Project Executing Agency: UNDP, UNEP, UNEP DTU Partnership |  |  |  |  |
|  | Project implementation period: | From: | 03/2020 | To: | 02/2023 |

| UNDP Budget Code | UN Env Class |  | Description | Year 1 | Year 2 | Year 3 | Total | Lead |  | Budget Note |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1 |  |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |  |
|  | C1-0101 |  | Programming support to merge GSP/CBIT platform (UDP staff) | 35,000 | 35,000 | 19,273 | 89,273 | UNEP DTU |  | A |  |
|  | C1-0102 |  | Maintain and update content on the GSP/CBIT platform (UDP staff) | 115,901 | 115,000 | 38,217 | 269,118 | UNEP DTU |  | B |  |
|  | C1-0103 |  | Knowledge dissemination and communication (UDP staff) | 41,000 | 41,000 | 14,700 | 96,700 | UNEP DTU |  | C |  |
|  | C1-0104 |  | Graphic designer | 10,000 | 10,000 | 5,000 | 25,000 | UNEP DTU |  | D |  |
|  | C1-0105 |  | Software programmer | 100,000 | 72,000 | 30,000 | 202,000 | UNEP DTU |  | E |  |
|  | C1-0106 |  | Climate transparency expert | 20,000 | 10,000 | 10,000 | 40,000 | UNEP DTU |  | F |  |
|  | C1-0107 |  | Communication expert | 12,000 |  |  | 12,000 | UNEP DTU |  | G |  |
|  |  |  | Subtotal | 333,901 | 283,000 | 117,190 | 734,091 |  |  |  |  |
|  | 120 |  | Contract Services |  |  |  |  |  |  |  |  |
|  | C1-1202 |  | Meetings and workshops (UDP) | 3,000 | 3,000 | 3,000 | 9,000 | UNEP DTU |  | H |  |
|  | C1-1203 |  | Translation | 5,000 | 5,000 | 5,000 | 15,000 | UNEP DTU |  | I |  |
|  |  |  | Subtotal | 8,000 | 8,000 | 8,000 | 24,000 |  |  |  |  |
|  | 125 |  | Operating & Other Costs |  |  |  |  |  |  |  |  |
|  | C1-1251 |  | Domain host | 2,000 | 2,000 | 2,000 | 6,000 | UNEP DTU |  | J |  |
|  |  |  | Subtotal | 2,000 | 2,000 | 2,000 | 6,000 |  |  |  |  |
|  | 130 |  | Supplies, Commodities and Materials |  |  |  |  |  |  |  |  |
|  |  |  | Subtotal | - | - | - | - |  |  |  |  |
|  | 135 |  | Equipment |  |  |  |  |  |  |  |  |
|  |  |  | Subtotal | - | - | - | - |  |  |  |  |
|  | 160 |  | Travel |  |  |  |  |  |  |  |  |
|  | C1-1601 |  | Travel for workshops and international meetings | 10,000 | 10,000 | 10,000 | 30,000 | UNEP DTU |  | K |  |
|  |  |  | Subtotal | 10,000 | 10,000 | 10,000 | 30,000 |  |  |  |  |
| COMPONENT 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |  |
| 61300 |  |  | Salary & Post Adjustment Cost – IP Staff | 30,000 | 35,000 | 35,000 | 100,000 | UNDP |  | L |  |
| 71200 |  |  | International Consultants | 43,000 | 74,000 | 70,000 | 187,000 | UNDP |  | L |  |
|  | C2-0104 |  | Peer exchange and capacity building in the LAC region | 30,000 | 35,000 | 35,000 | 100,000 | UNEP DTU |  | M |  |
|  |  |  | Subtotal | 103,000 | 142,000 | 142,000 | 387,000 |  |  |  |  |
|  | 160 |  | Travel |  |  |  |  |  |  |  |  |
| 71600 |  |  | Travel for workshops and international meetings | 10,000 | 10,000 | 10,000 | 30,000 | UNDP |  | N |  |
|  |  |  | Subtotal | 10,000 | 10,000 | 10,000 | 30,000 |  |  |  |  |
|  | 120 |  | Contract Services |  |  |  |  |  |  |  |  |
| 75700 |  |  | Training, workshops and conferences | 179,000 | 186,000 | 177,000 | 542,000 | UNDP |  | O |  |
| 74200 |  |  | Audio-visual and print production costs | - | 2,000 | 1,000 | 3,000 | UNDP |  | P |  |
|  |  |  | Subtotal | 179,000 | 188,000 | 178,000 | 545,000 |  |  |  |  |
| 74500 |  |  | Miscellaneous | - | 591 | 500 | 1,091 | UNDP |  | Q |  |
|  |  |  | Subtotal | - | 591 | 500 | 1,091 |  |  |  |  |
| MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |
| 71200 |  |  | International Consultant -- Terminal Evaluation | - | - | 30,000 | 30,000 | UNDP |  | R |  |
| 75700 |  |  | Training, workshops, and conferences | 31,000 | 0 | 0 | 31,000 | UNDP |  | S |  |
|  |  |  | Subtotal | 31,000 |  | 30,000 | 61,000 |  |  |  |  |
|  |  |  | Subtotal for M&E | 31,000 |  | 30,000 | 61,000 |  |  |  |  |
| PROJECT MANAGEMENT COSTS (PMC) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 010 |  | Staff & Personnel (Including Consultants) |  |  |  |  |  |  |  |  |
|  | PM-0101 |  | Project manager of Component 1 | 35,000 | 35,000 | 20,909 | 90,909 | UNEP DTU |  | T |  |
| 61200 |  |  | Salaries Cost -- GS Staff | 12,000 | 14,000 | 14,000 | 40,000 | UNDP |  | U |  |
| 61300 |  |  | Salary & Post Adj Cst – IP Staff | 7,000 | 7,000 | 7,000 | 21,000 | UNDP |  | U |  |
|  |  |  | Subtotal | 54,000 | 56,000 | 41,909 | 151,909 |  |  |  |  |
| 74100 |  |  | Professional Services -- Audit | 3,000 | 3,000 | 3,000 | 9,000 | UNDP |  | V |  |
| 74500 |  |  | Miscellaneous | 909 | 0 | 0,000 | 909 | UNDP |  |  |  |
| 74596 |  |  | Direct Project Costs - General Operating Expenses (GOE) | 6,000 | 7,000 | 7,000 | 20,000 | UNDP |  |  |  |
|  |  |  | Subtotal | 9,909 | 10,000 | 10,000 | 29,909 |  |  |  |  |
|  |  |  | Subtotal for Project Management Costs | 63,909 | 66,000 | 51,909 | 181,818 |  |  |  |  |
|  | GRAND TOTAL |  |  | 740,810 | 711,591 | 547,599 | 2,000,000 |  |  |  |  |
| Budget Notes |  |  | Description |  |  |  |  |  |  |
| A |  |  | Support to Activities 1.1.1, 1.1.2, 1.1.3 |  |  |  |  |  |  |
| B |  |  | Support to Activities 1.2.1, 1.2.2, 1.2.3, 1.2.3, 1.2.4, 1.2.5 |  |  |  |  |  |  |
| C |  |  | Support to Activities 1.3.1, 1.3.2, 1.3.3, 1.3.4 |  |  |  |  |  |  |
| D |  |  | Support to Activity 1.1.3 |  |  |  |  |  |  |
| E |  |  | Support to Activity 1.1.4, 1.1.5, 1.1.6, 1.1.8, 1.3.3 |  |  |  |  |  |  |
| F |  |  | Support to Activity 1.3.1, 1.3.4 |  |  |  |  |  |  |
| G |  |  | Support to Activity 1.1.2, 1.1.7 |  |  |  |  |  |  |
| H |  |  | Support to Activity 2.2.4 |  |  |  |  |  |  |
| I |  |  | Translation of regional materials for platform under Output 1.2 |  |  |  |  |  |  |
| J |  |  | Domain hosting in support of Output 1.2 |  |  |  |  |  |  |
| K |  |  | Travel for Project Management (PM-0101) in support of activities under Component 1 and Activity 2.2.4 |  |  |  |  |  |  |
| L |  |  | Technical support of the Project Coordinator and the IC / Transparency Expert to all outputs under Component 2 with the exception of 2.2.4 |  |  |  |  |  |  |
| M |  |  | Consultant for support to Activity 2.2.4 |  |  |  |  |  |  |
| N |  |  | Travel for Project Coordinator and UNDP in support of Outputs 2.1, 2.2, 2.3, and 2.4 |  |  |  |  |  |  |
| O |  |  | Workshops to be held under outputs 2.1 and 2.4 (annual stocktaking and gender workshops) |  |  |  |  |  |  |
| P |  |  | Print production costs for knowledge materials in support of all outputs under Component 2 |  |  |  |  |  |  |
| Q |  |  | Sundry expenses for workshops under Outputs 2.1 and 2.4 |  |  |  |  |  |  |
| R |  |  | IC for Terminal Evaluation |  |  |  |  |  |  |
| S |  |  | Inception Workshop for Project |  |  |  |  |  |  |
| T |  |  | Salary of Project Manager for Component 1 and Activity 2.2.4 |  |  |  |  |  |  |
| U |  |  | Cost-shared salary of Project Coordinator and Project Associate for support to all activities under Component 2 with the exception of 2.2.4 and for general coordination and monitoring duties |  |  |  |  |  |  |
| V |  |  | Annual audit of project (@ USD 3,000 / year) |  |  |  |  |  |  |

# ANNEX H-2: DETAILED CO-FINANCING BUDGET

| Co-finance contributor: UNEP DTU Partnership |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Outputs | In-kind co-finance (USD) |  |  |  |
|  | Y1 | Y2 | Y3 | TOTAL |
| 1.1 Existing CBIT and GSP web platforms merged and redesigned into an integrated platform | 20,000 | 15,000 | 15,000 | 50,000 |
| 1.2 Platform content and features maintained and updated regularly | 10,000 | 20,000 | 20,000 | 50,000 |
| 1.3 Knowledge products on the Paris Rulebook and other reporting under the UNFCCC, including associated training modules, updated, developed, and customized Project Management | 100,000 | 100,000 | 100,000 | 300,000 |
| Total | 130,000 | 135,000 | 135,000 | 400,000 |

# ANNEX I: M&E BUDGET AND WORK PLAN

Table I.1: Mandatory GEF M&E Requirements and M&E Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co‐ financing |  |
| Kick off meeting | UNDP & UNEP | 31,000 | None | Within two months of project document signature |
| Kickoff and technical workshop report | Project Coordinator | None | None | Within two weeks of first workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Istanbul Regional Hub | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework and revision of indicators and targets as necessary | Project Coordinator | None | None | Annually |
| GEF PIR | Project Coordinator and UNDP | None | None | Annually (to be submitted by end of July, covering July-June period) |
| Lessons learned and knowledge generation | Project Coordinator | None | None | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Coordinator | None | None | On‐going |
| Addressing environmental and social grievances | Project Coordinator UNDP Bureau for Policy and Programme Support and/or UNEP Safeguards Advisor as needed | None | None | Annually |
| Project Steering Committee meetings | Project Steering Committee Members Project Coordinator | None | None | At minimum annually |
| Oversight missions | UNDP‐GEF team UNEP Task Manager | None | None | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | Project Coordinator and relevant executing agency staff/representatives | None | None | To be determined. |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP with financial and technical support from UNEP | 30,000 | None | At least three months before operational closure. |
| Final Report | Executive Management Group | None | None | No later than three months after the technical closure of the project |
| TOTAL INDICATIVE COST Excluding project team staff time, and UNDP and UNEP staff and travel expenses |  | USD 61,000 |  |  |

# ANNEX J: PROJECT IMPLEMENTATION ARRANGEMENTS

As part of the Paris Agreement, Parties to the United Nations Framework Convention on Climate Change (UNFCCC) have agreed to establish a Capacity-building Initiative for Transparency (CBIT). The CBIT will aim to strengthen the institutional and technical capacities of developing countries to meet the enhanced transparency requirements in the Paris Agreement. The Paris Agreement requested that the GEF support the establishment of the CBIT through voluntary contributions during GEF-6 and future replenishment cycles.

UNDP and UNEP will be the GEF Implementing Agencies (IAs) for this initiative and are responsible to the GEF for the use of project resources as written in the project document, or any amendments agreed.

UNDP will serve as the lead agency for the project as a whole and will appoint a Project Coordinator as the primary point of contact. UNEP will have the IA role for Component 1, led by a Task Manager, and UNDP will have the IA role for Component 2, which will be led by the Project Coordinator. UNDP will be responsible for executing project outputs where it serves as an IA. In outputs where UNEP has an IA role, it will either execute the outputs directly or it will delegate the execution of the outputs to its collaboration centre, the UNEP DTU Partnership. A UNEP DTU Partnership Project Manager will be responsible for outputs where UNEP serves as the executing agency, a UNEP liaison officer will also be designated (at no cost to the project). The executing agencies will be responsible for day-to-day management of the project, including financial management and project reporting. Project administration will follow the procedures of the respective executing agencies, including those related to procurement, contracting, and recruitment.

The Project Management Cost budget – USD 181,818 - will be used to cover a part-time salary for the Project Coordinator and a Project Associate as well as direct project costs (DPC). UNDP Istanbul Regional Hub (IRH) will also provide administrative, operative and QA/QC support during the implementation of the program

The scope of the work is divided in such a way that UNEP is responsible for the on-line transparency platform, supporting knowledge products, and the regional network coordination intiative, while UNDP is responsible for the coordination of stocktaking, global/regional workshops, coordination of support providers, and guidance to developing country Parties on gender equality and women’s participation.

Project Management Unit

The Project Management Unit (PMU) will consist of two people: the UNDP Project Coordinator and a UNEP DTU Partnerhsip Project Manager. The PMU will be responsible for day to day management of the project. The PMU will be responsible for execution of the respective project components under the CBIT project. The PMU will also be expected to identify critical links and synergies between the components of the project through biweekly meetings.

Executive Management Group

The executive management group (EMG) will comprise representatives from:

UNEP (a Task Manager and a UNEP liaison officer),

UNDP (the Project Coordinator, who will also manage the UNDP-executed Component 2),

UNEP DTU Partnership (a Project Manager)

The EMG will oversee the implementation of the project through monthly meetings. Its main functions will be to approve management decisions, annual work plans and budget revisions, and ensure timely delivery of quality outputs. The main purpose of the EMG is to maintain very close coordination between UNEP and UNDP in order to ensure the execution of the activities of the two components as a single project.

Project Steering Committee

The Project Steering Committee (PSC) will comprise representatives from:

UNEP

UNDP

UNEP DTU partnership

UNFCCC representative

GEF Secretariat representative

1 Annex I country representative

1 non-Annex I country representative

The Committee will be responsible for reviewing project progress and providing strategic guidance to the EMG. The PSC will meet annually, unless one of the committee members calls for an ad hoc interim meeting. It will allow users as well as the key donor and the UNFCCC to participate in the decision-making process. The PSC meetings will be organized back to back with some of the other workshops or side events organized by the project.

Implementing Agencies (UNEP and UNDP)

Ensure timely disbursement/sub-allotment to executing partner (UNEP DTU partnership), based on agreed legal document and in accordance with UNEP and GEF fiduciary standards

Follow-up with Executing partner for progress, equipment, financial and audit reports

Provide consistent and regular oversight on project execution and conduct project supervisory missions as per Supervision Plans and in doing so ensures that all UNEP, UNDP and GEF criteria, rules and regulations are adhered to by project partners;

Technically assess and oversee quality of project outputs, products and deliverables – including formal publications

Provide no-objection to main ToRs and subcontracts issued by the project, including selection of project manager or equivalent

Attend and facilitate inception workshops, field visits where relevant, and selected steering committee meetings

Assess project risks, and monitor and enforce a risk management plan

Regularly monitor project progress and performance and rates progress towards meeting project objectives, project execution progress, quality of project monitoring and evaluation, and risk;

Monitor reporting by project executing partners and provides prompt feedback on the contents of the report;

Promptly inform management of any significant risks or project problems and takes action and follows up on decisions made;

Apply adaptive management principles to the supervision of the project;

Review reporting, checking for consistency between execution activities and expenditures, ensuring that they follow GEF rules and regulations;

Provide clearance of cash requests, and authorization of disbursements once reporting found to be complete

Approve budget revision, certifies availability of funds, and transfers funds

Ensure that GEF, UNEP and UNDP quality standards are applied consistently to all projects, including branding and safeguards

Certify project operational completion

Link the project partners to any events organised by GEF, UNEP and UNDP to disseminate information on project results and lessons

Manage relations with GEF

Executing Agencies (UNEP DTU Partnership and UNDP)

Proper achievement of the objectives of the Project;

Monitoring and evaluation of the project outputs and outcomes;

Effective use of resources allocated to it;

Timely availability of financing to support project implementation;

Proper coordination among all project stakeholders; in particular coordination between both executing agencies

Timely submission of all project reports, including work plans and financial reports.

# ANNEX K: PROJECT WORKPLAN AND DELIVERABLES

# ANNEX L: CBIT-GEF TRACKING TOOL

# ANNEX M: OFP ENDORSEMENT LETTER

Not applicable.

# ANNEX N: CO-FINANCING LETTER

# Annex O: ENVIRONMENTAL, SOCIAL AND ECONOMIC REVIEW NOTE (ESERN)

- Project Overview

| Identification | GEF ID 10128 |
| --- | --- |
| Project Title | Global Capacity Building Initiative for Transparency (CBIT) Platform Phase IIA: Unified Support Platform and Program for Article 13 of the Paris Agreement |
| Managing Division | Economy Division |
| Type/Location | Global |
| Region |  |
| List Countries |  |
| Project Description | The overall objective of the project is to provide streamlined support and capacity building at the country, regional, and global level to improve reporting capacity of countries and enhanced transparency frameworks to allow developing countries to meet commitments under Article 13 of the Paris Agreement. Component 1 of the project will focus on streamlined knowledge development and delivery in support of Article 13. It will design and build a streamlined platform for climate change reporting and transparency information; maintain content and features for the platform; and develop knowledge products, including their associated training modules, for dissemination through the platform and through other events. Component 2 of the project will support global stakeholder outreach and dissemination of best practices. It will conduct an annual stocktaking of transparency activities; organize COP side events and other meetings to disseminate good practice; facilitate coordination among donors; and support countries with integrating the UNFCCC gender action plan into their transparency policies, measures, and management. |
| Estimated duration of project: | 36 months |
| Estimated cost of the project: | USD 2,400,000, out of which USD 2,000,000 are GEF grant |

A. Summary of the Safeguard Risks Triggered Safeguard Standard Triggered by the Project; Impact of Risk (1-5); Probability of Risk (1-5); Significance of Risk (L, M, H). SS 1: Biodiversity, natural habitat and Sustainable Management of Living Resources; 1; 1; L. SS 2: Resource Efficiency, Pollution Prevention and Management of Chemicals and Wastes; 1; 1; L. SS 3: Safety of Dams; 1; 1; L. SS 4: Involuntary resettlement; 1; 1; L. SS 5: Indigenous peoples; 1; 1; L. SS 6: Labor and working conditions; 1; 1; L. SS 7: Cultural Heritage; 1; 1; L. SS 8: Gender equity; 1; 1; L. SS 9: Economic Sustainability; 1; 1; L. Additional Safeguard questions for projects seeking GCF-funding (Section IV). B. ESE Screening Decision (Refer to the UNEP ESES Framework (Chapter 2) and the UNEP’s ESES Guidelines.) Low risk X Moderate risk High risk Additional information required C. Development of ESE Review Note and Screening Decision: Prepared by: Name: _Susan Legro (UNDP consultant)__ Date: 2nd of July 2019_ Safeguard Advisor: Name: Yunae Yi Date: 1st of August 2019 Task Manager: Name: _Suzanne Lekoyiet__________ Date: 2nd of August 2019

D. Recommended further action from the Safeguard Advisor: This is a low safeguard risk project.

# ANNEX P: ACRONYMS AND ABBREVIATIONS

AFOLU		Agriculture Forestry and Other Land Use

BTR			Biennial Transparency Report

BUR			Biennial Update Report
CBIT 			Capacity-building Initiative for Transparency

CCMRVH		Caribbean Cooperative MRV Hub

CGE 			Consultative Group of Experts
CI			Conservation International

COP 			Conference of the Parties
CSO			Civil Society Organization

DIM			Direct Implementation

DPC			Direct Program Costs

EIGE			European Institute for Gender Equality

ETF			Enhanced Transparency Framework

EMG			Executive Management Group

FAO			United Nations Food and Agriculture Organization

GCP			Global Coordination Platform
GDI			Gender and Development Index

GEF 			Global Environment Facility
GHG 			Greenhouse Gas
GOE			General Operating Expenses

GSP 			Global Support Programme
IA			Implementing Agency

ICAT 			Initiative for Climate Action Transparency
IGES			Institute for Global Environmental Strategies

IPCC 			Intergovernmental Panel on Climate Change
IRH			Istanbul Regional Hub

LDC			Least Developed Country

M&E			Monitoring and Evaluation

MPGs			Modalities, Procedures, and Guidelines

MRV 			Measurement, Reporting, and Verification
NAP			National Adaptation Plan

NC 			National Communications
NCSA			Natonal Capacity Self Assessment

NCSP			National Communications Support Programme

NDC 			Nationally Determined Contribution
PaSTI			Partnership to Strengthen Transparency for co-Innovation

PATPA		Partnership on Transparency in the Paris Agreement

PCCB			Paris Committee on Capacity Building

PIMS			Project Information Management System

PIR			Project Implementation Report

PMU			Project Management Unit

POPP			Programme and Operations Policies and Procedures

PSC			Project Steering Committee

RedINGEI		Latin American GHG Inventories Network (Red Latinoamericana de Inventarios

Nacionales de Gases de Efecto Invernadero)

ROAR			Results Oriented Annual Reporting

SDGs			Sustainable Development Goals

SIDS			Small Island Developing States

SB			Subsidiary Body

SBSTA 		Subsidiary Body for Scientific and Technological Advice

TNA			Technology Needs Assessment

TE			Terminal Evaluation

UNDP 			United Nations Development Programme
UNEP 			United Nations Environment Programme
UNFCCC 		United Nations Framework Convention on Climate Change

WEDO			Women Economic Development Outreach

Annex Q: Table of Contents

PART I: PROJECT INFORMATION	1

PART II:  PROJECT JUSTIFICATION	4

Project Context	6

2) the baseline scenario and any associated baseline projects;	9

3) the proposed alternative scenario with a brief description of expected outcomes and components of the project;	13

4) alignment with GEF focal area and/or Impact Program strategies;	21

5) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, and co-financing;	22

6) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF);	22

7) innovation, sustainability and potential for scaling up;	23

A.3.  Stakeholders	24

A.4. Gender Equality and Women's Empowerment.	27

A.5 Risk.	30

A.6. Institutional Arrangement and Coordination	30

A.7 Benefits	32

A.8 Knowledge Management	32

B. DESCRIPTION OF THE CONSISTENCY OF THE PROJECT WITH NATIONAL PRIORITIES	34

C.  DESCRIBE THE BUDGETED M &E PLAN	34

PART III:  CERTIFICATION BY GEF PARTNER AGENCY(IES)	38

ANNEX A:  PROJECT RESULTS FRAMEWORK	39

ANNEX B:  RESPONSES TO PROJECT REVIEWS	42

ANNEX C:  STATUS OF IMPLEMENTATION OF PROJECT PREPARATION ACTIVITIES	43

ANNEX D:  CALENDAR  OF EXPECTED REFLOWS	44

ANNEX E: GEF 7 CORE INDICATOR WORKSHEET	45

ANNEX F: GEF PROJECT TAXONOMY WORKSHEET	46

ANNEX G: TERMS OF REFERENCE OF PROJECT STAFF AND CONSULTANTS TO BE HIRED	52

ANNEX H-1: DETAILED GEF BUDGET	66

ANNEX H-2: DETAILED CO-FINANCING BUDGET	70

ANNEX I: M&E BUDGET AND WORK PLAN	71

ANNEX J: PROJECT IMPLEMENTATION ARRANGEMENTS	73

ANNEX K: PROJECT WORKPLAN AND DELIVERABLES	76

ANNEX L: CBIT-GEF TRACKING TOOL	78

ANNEX M: OFP ENDORSEMENT LETTER	79

ANNEX N: CO-FINANCING LETTER	80

Annex O: ENVIRONMENTAL, SOCIAL AND ECONOMIC REVIEW NOTE (ESERN)	81

ANNEX P: ACRONYMS AND ABBREVIATIONS	84

ANNEX Q: TABLE OF CONTENTS	86

Project ID number remains the same as the assigned PIF number.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives 
   and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving..

IPCC (2019). 2019 Refinement to the 2006 Guidelines for National Greenhouse Gas Inventories.

However, there is some flexibility in these requirements for developing countries that need it.

GEF ID 5141.

Prasada Rao (2018) Mid-Term Review.

GEF (2019). Progress Report on the Capacity Building Initiative for Transparency. GEF/C.56/Inf.06. Results as of April 2019.

Ibid.

Ibid.

GEF (2018). Progress Report on the Capacity Building Initiative for Transparency. GEF/C.55/Inf.12: 5.

GEF (2018): 5.

The GDI is a measure that is based on the sex-disaggregated Human Development Index, which is defined as a ratio of the female to the male HDI. As such, the GDI is meant to identify gender inequalities in three basic dimensions of human development: health (measured by female and male life expectancy at birth), education (measured by female and male expected years of schooling for children and mean years for adults aged 25 years and older); and command over economic resources (measured by female and male estimated GNI per capita). Data available at: http://hdr.undp.org/en/composite/GDI

The Global Gender Gap Index (GGGI) of the World Economic Forum examines the gap between men and women in four categories: economic participation and opportunity, educational attainment, health and survival; and political empowerment. Available at: http://www3.weforum.org/docs/WEF_GGGR_2018.pdf

World Economic Forum (2018) The Global Gender Gap Report 2018: vii.

Ibid.: 7.

http://www.undp.org/content/undp/en/home/sustainable-development-goals/goal-5-gender-equality/targets.html

UN Women (2017). “New Guidebook Launched to Boost Gender Mainstreaming.” https://unfccc.int/news/new-guidebook-launched-to-boost-gender-mainstreaming.

UNFCCC (2018). FCCC/CP/2017/11/Add.1: 16.

International Union for Conservation of Nature and United States Agency for International Development (2016)

The Gender Responsive National Communications Toolkit is accessible through this link: http://www.un- gsp.org/sites/default/files/documentos/undp_gender_responsive_national_communications_toolkit.pdf

FCCC/SBI/2017/L.29, paragraph 5.

http://unevaluation.org/document/detail/1914

IEA Experts’ Group on R&D Priority-Setting and Evaluation (2011). Summary Report: The Transition to a Low-Carbon Economy: Socio-Economic Considerations. Baden, Austria: IEA, 24-25 May 2011: 7.

Ibid.: 5.

“Climate change mitigation strategies for agriculture: an analysis of nationally determined contributions, biennial reports and biennial update reports.” In Climate Policy. Vol. 19, No. 6 (July 3, 2019): 688.

GEF/STAP/C.48/Inf.03/Rev.01 (2015): 7.

See https://www.thegef.org/gef/policies_guidelines

See guidance here: https://info.undp.org/global/popp/frm/pages/financial‐management‐and‐execution‐modalities.aspx

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF

https://gefportal.worldbank.org/App/#/gefsecreview/agency/reviewsheet/e888add2-d7c7-e811-813e-3863bb2e1360/edit. GEF Sec Decision Recommendation.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.

Excluding project team staff time and UNDP staff time and travel expenses.

Refer to UNEP Environment, Social and Economic Sustainability (ESES): Implementation Guidance Note to assign values to the Impact of Risk and the Probability of Risk to determine the overall significance of Risk (Low, Moderate or High).

Low risk:  Negative impacts negligible: no further study or impact management required.

Moderate risk: Potential negative impacts, but less significant; few if any impacts irreversible; impact amenable to management using standard mitigation measures; limited environmental or social analysis may be required to develop a ESEMP.  Straightforward application of good practice may be sufficient without additional study.

High risk: Potential for significant negative impacts, possibly irreversible, ESEA including a full impact assessment may be required, followed by an effective safeguard management plan.