Ghana (GEF ID 4368): PROVACCA

GEF Terminal Evaluation (TER)

Audit trail on specific comments

(Reviewer: Mark Keating, IOE)

| IFAD IOE comment | Response |
| --- | --- |
| Para 2. IOE was not sure that the PROVACCA project was extended because of the delays in implementation. | Not having the official project extension justification to hand and after having reviewed the supervision mission reports again, the MTR does state that the extension was due to slow project implementation (paragraph 14) and that the project has ‘done very poorly in the complex procurement’(paragraph 65). It also gives the justification of the short project duration of 30 months as not being sufficient for “a proper development of capacity and analysis of impact” of the gasification plant and related investments even if they had they been implemented as originally scheduled (paragraph 58a). This has been reflected in the TER paragraph 2. |
| Paragraph 26. IOE requests more clarity with regards to whether the GPS was borrowed or not from RTIMP. | The TER makes reference to GPS equipment that was borrowed and GIS equipment that was procured. These are two different types of equipment. An adjustment has been made to clarify that the GPS were actually borrowed from RTIMP. |
| Paragraph 26. IOE requests if the delays in signing the MOU were caused by the university of Ghana. | The word ‘latter’ has been replaced by the University of Ghana. |
| Paragraph 26. IOE asks whether the TER comment that supervision missions had not raised the issue of two-year delay for the MOU with the university of Ghana, is a reference to IFAD supervision missions. | This is correct. The TER has been adjusted to clarify this point. |
| Paragraph 35. IOE wants to know who’s authority was not granted to allow the international travel for component 2.1. | This information was not specified in the written reports provided by the project. |
| Paragraph 37. IOE asks why the AWS was abandoned at the last minute. | The TER has been updated with a summary of the detailed explanation in paragraph 29 by stating that it was due to under budgeting and sustainability concerns. A footnote has been added to point the reader to paragraph 29 where this has been explained in greater detail. |
| Paragraph 43. IOE reports an awkward sentence. | This has been revised. |
| Paragraph 54. IOE suggests to make a reference to a description of the biogas and gasification technology in para 42. | This has been done in the form of a footnote. |
| Paragraph 87. IOE observation on results rather than conclusions being mixed. | This has been altered. |