GEF - PROJECT IMPLEMENTATION REPORT (PIR)

Document Generated by: CCA TM

At: 2024-07-31 10:15:46

# Table of contents

1 PROJECT IDENTIFICATION	3

1.1 Project Details	3

1.2 Project Description	3

1.3 Project Contacts	4

2 Overview of Project Status	5

2.1 UNEP PoW & UN	5

2.2. GEF Core and Sub Indicators	6

2.3. Implementation Status and Risks	6

2.4 Co Finance	14

2.5. Stakeholder	15

2.6. Gender	17

2.7. ESSM	18

2.8. KM/Learning	19

2.9. Stories	20

3 Performance	21

3.1 Rating of progress towards achieving the project outcomes	21

3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)	34

4 Risks	46

4.1 Table A. Project management Risk	46

4.2 Table B. Risk-log	46

4.3 Table C. Outstanding Moderate, Significant, and High risks	50

5 Amendment - GeoSpatial	51

5.1 Table A: Listing of all Minor Amendment (TM)	51

5.2 Table B: History of project revisions and/or extensions (TM)	51

UNEP GEF PIR Fiscal Year 2024

Reporting from 1 July 2024 to 30 June 2025

# 1 PROJECT IDENTIFICATION

## 1.1 Project Details

| GEF ID: 5203 | Umoja WBS:SB-008696 |
| --- | --- |
| SMA IPMR ID:35104 | Grant ID:S1-32LDL-000045 |
| Project Short Title: EbA II |  |
| Project Title: Catalyzing Ecosystem Restoration for Climate Resilient Natural Capital and Rural Livelihoods in Degraded Forests and Rangelands of Nepal. |  |
| Duration months planned: | 48 |
| Duration months age: | 51 |
| Project Type: | Full Sized Project (FSP) |
| Parent Programme if child project: | N/A |
| Project Scope: | National |
| Region: | Asia Pacific |
| Countries: | Nepal |
| GEF Focal Area(s): | Climate Change Adaptation |
| GEF financing amount: | 5,246,475.00 |
| Co-financing amount: | 22,365,714 |
| Date of CEO Endorsement/Approval: | 2015-08-11 |
| UNEP Project Approval Date: | 2018-04-04 |
| Start of Implementation (PCA entering into force): | 2018-05-25 |
| Date of Inception Workshop, if available: | 2019-03-11 |
| Date of First Disbursement: | 2019-02-01 |
| Total disbursement as of 30 June 2025: | $ 4,216,995.87 |
| Total expenditure as of 30 June 2025: | $ 3,853,445.62 (as of Dec 31, 2024, will be incorporated once final report done) |
| Midterm undertaken?: | Yes |
| Actual Mid-Term Date, if taken: | 2022-09-19 |
| Expected Mid-Term Date, if not taken: |  |
| Completion Date Planned - Original PCA: | 2024-12-31 |
| Completion Date Revised - Current PCA: | 2025-06-30 |
| Expected Terminal Evaluation Date: | 2025-12-15 |
| Expected Financial Closure Date: | 2025-06-30 |

## 1.2 Project Description

Background and scope of the project

Nepal is ranked one of the most vulnerable countries in the world to natural disasters and is exposed to climate hazards such as flood, landslides, glacial lake outburst floods, thunderstorms, cold waves and droughts. The country is, therefore, experiencing consistent rising trends in annual mean temperature, extreme rainfall events, and other climate risks. In view of the above, efforts are being made to explore options in which nature can provide solutions to the development challenges, enabling local communities and societies at large to adapt and cope with the effects of climate change on the long run. This project intends to build, consolidate and value add to the good practices and lessons learned from earlier flagship EbA and EbA south projects and other similar practices conducted by the government and development partners.

Project implementation modality

The project is being implemented by MoFE as the lead executing agency and UNEP as the implementing agency. Department of Livestock and Department of Agriculture under the Ministry of Agriculture and Livestock Development (MoALD) are the collaborating partners. At the local level, the project works closely with the four municipalities and six rural municipalities and three Division Forest Offices to implement field level activities.

The project covers two distinct physiographic regions; midhills -Achham and Salyan districts and high mountain-Dolakha district. A total of ten local municipalities (four Municipalities and six Rural municipalities) come under the project jurisdiction. Achham district has three municipalities: Sanfebagar municipality, Ramaroshan and Mellekh Rural Municipality. Salyan district has Bangad-Kupinde Municipality and Kumakh-Malika Rural Municipality. Similarly, Dolakha district has Bhimeshwor and Jiri Municipality and Gaurishankar, Kalinchowk and Shailung Rural Municipality. A total of 18 wards of the ten Municipalities are under the project working areas.  Each one of the project districts has six working wards.  Achham district has six wards (Babla, Bhatakatiya, Ramaroshan, Rishidaha 1, Rishidaha 2, and Sodasha), six wards fall under Salyan district (Devasthal, Ganjaripipal 6, Ghanjaripipal 7, Mulkhola 4, Mulkhola 5, and Suikot 2) and Dolakha district has six wards (Khare 8, Lakuridanda 9, Lapilang 5, Lapilang 6, Magapauwa 4 and Jiri 5). A total of 11,453 households with a population of 56,170 will benefit from EbA interventions.

The Project has three outcomes:

Outcome 1: Increased capacity of Government officials and local user groups to implement EbA through enhanced institutional arrangements, inter-sectoral collaboration and research

Outcome2: National Policies and strategies strengthened to promote EbA implementation

Outcome 3: EbA implemented and monitored by User groups to restore forests and rangelands in the mid-hills of Accham and Salyan and high mountains of Dolakha to decrease the sensitivity of local communities to climate change

## 1.3 Project Contacts

| Division(s) Implementing the project | Ecosystems Division |
| --- | --- |
| Name of co-implementing Agency | N/A |
| Executing Agency (ies) | Ministry of Forests and Environment (MoFE) |
| names of Other Project Partners | Ministry of Agriculture and Livestock Development (MoALD) |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Moon Shrestha |
| UNEP Budget/Finance Officer | Bwiza Wameyo Odemba |
| UNEP Support Assistants | N/A |
| Manager/Representative | Dr. Maheshwar Dhakal |
| Project Manager | Top B. Khatri |
| Finance Manager | Shreedhar P Adhikari |
| Communications Lead, if relevant | Kumar Gurung |

# 2 Overview of Project Status

## 2.1 UNEP PoW & UN

| UNEP Current Subprogramme(s): | Thematic: Climate action subprogramme, Thematic: Nature action subprogramme |
| --- | --- |
| UNEP previous Subprogramme(s): | 1. Climate Stability2. Living in harmony with nature |
| PoW Indicator(s): | - Climate: (i) Number of national, subnational and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support. - Climate: (ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support. - Climate: (iv) Positive shift in public opinion, attitudes and actions in support of climate action as a result of UNEP action - Nature: (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring and sustainably managing biodiversity. - Nature: (iii) Number of countries and national, regional and subnational authorities and entities that incorporate, with UNEP support, biodiversity and ecosystem-based approaches into development and sectoral plans, policies and processes for the sustainable management and/or restoration of terrestrial, freshwater and marine areas - Nature: (iv) Increase in territory of land- and seascapes that is under improved ecosystem conservation and restoration |
| UNSDCF/UNDAF linkages | Aligned with priority thematic area 3 "Resilience, disaster risk reduction and climate change" |
| Link to relevant SDG Goals | - Goal 13: Take urgent action to combat climate change and its impacts - Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss |
| Link to relevant SDG Targets: | - 13.1 Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries - 13.2 Integrate climate change measures into national policies, strategies and planning - 13.3 Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning - 13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth, and local and marginalized communities - 15.1 By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements - 15.2 By 2020, promote the implementation of sustainable management of all types of forests, halt deforestation, restore degraded forests and substantially increase afforestation and reforestation globally - 15.5 Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species |

## 2.2. GEF Core and Sub Indicators

GEF core or sub indicators targeted by the project as defined at CEO Endorsement/Approval, as well as results

|  | Targets - Expected Value |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Mid-term | End-of-project | Total Target | Materialized to date |

Implementation Status 2024: 7th PIR

## 2.3. Implementation Status and Risks

|  | PIR# | Rating towards outcomes (section 3.1) | Rating towards outputs (section 3.2) | Risk rating (section 4.2) |
| --- | --- | --- | --- | --- |
| FY 2025 | 7th PIR | S | S | L |
| FY 2024 | 6th PIR | S | S | L |
| FY 2023 | 5th PIR | S | S | L |
| FY 2022 | 4th PIR | S | S | L |
| FY 2021 | 3rd PIR | S | S | L |
| FY 2020 | 2nd PIR | MS | MS | L |
| FY 2019 | 1st PIR | S | S | M |
| FY 2018 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2017 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2016 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2015 | --Select-- | --Select-- | --Select-- | --Select-- |

Summary of status

Progress

During this reporting period, the project has undertaken various activities under the three outcomes. Detailed progress is presented hereunder.

Outcome 1: Increased capacity of national and local government institutions in Nepal to adapt to climate change by implementing EbA in degraded forests and rangelands in mid-hill and high mountain areas

During this reporting period, capacity was built among central level government officials through a 5-Day training on identifying, prioritizing, implementing, monitoring and evaluating EbA interventions held 16-20 December 2024. The training was led by Mr. Keshav Khanal (NCASEE) with support from the National Public Education Expert (NPEE). A total 23 officials attended the training programme, among which 30% were female. This training program focused on strengthening the capacity of officials at the Forest Research and Training Centre (FRTC) and academic institutions to include and deliver training packages that incorporate effective planning, implementation, and monitoring & evaluation of EbA programs. The program also reinforced advocacy for the effective prioritization and integration of EbA into the government’s regular programs. Participants built their capacity to apply the Adaptation, Livelihoods and Ecosystems Planning (ALiVE) tool designed to help organize and analyze information to plan effective EbA interventions. The training report can be found in the link:

https://drive.google.com/file/d/1tZ4MYKRoDREZRvCgB29lhKyPhOf67oQM/view?usp=sharing

In addition, a 3 Day training was organized on Gender Equality Disability and Social Inclusion (GEDSI) integration in EbA programming from 10 to 12 March 2025. This GEDSI integration training was organized as a follow-up and advanced program for government officials to leverage their learning to plan and design EbA programming through the lens of GEDSI. The training, facilitated by GEDSI consultants Dibya Devi Gurung and Sindhu Prasad Dhungana (former NPD), brought together 21 government officials from 17 institutions, including forest, agriculture, and livestock sectors. Key sessions covered GEDSI concepts, their relevance to climate resilience, and the integration of GEDSI into the EbA planning cycle. Participants conducted situation analyses, identified key barriers, developed transformative outcomes, and crafted GEDSI-responsive action and M&E plans through tools such as problem tree analysis and privilege walk exercises. National and global frameworks, such as the COP 29 outcomes and feminist institutional approaches, were discussed to contextualize Nepal's commitments to inclusive climate action. The training fostered deep awareness and equipped government partners with tools to drive more equitable, inclusive, and climate-resilient programming. The training report can be found in the link:

https://drive.google.com/file/d/1jrVHJHHcbRwwrJM6oT2QM5dS5_F3Onhq/view?usp=sharing

In addition to EbA practitioners, and government officials, training for central level media personnel was organized on 16-17 February 2025 in Dhulikhel, Kavre.  The training aimed to strengthen journalists' understanding and reporting skills on climate and environmental issues, enabling them to more effectively communicate nature-based solutions, including within Nepal’s NAP and NDC 3.0. Eighteen participants (including 4 women) from major national print, online, radio, and television outlets attended. Pre- and post-training assessments showed a 4% improvement in knowledge. The training report can be found in the link:
https://drive.google.com/file/d/1mS4tA68k1EQrSm7NLkJir1s3HV9gA2Mo/view?usp=sharing

Recognizing the importance of education and academic institutions, the project in collaboration with the Curriculum Development Centre (CDC) expanded the delivery of EbA curriculum for grade 6-8. The project also held (1) a 3 Day workshop between 13-15 December 2024 for 31 teachers and resource persons from CDC and, (2) in May 2025, an advanced follow-up workshop to finalize the curriculum contents that were developed as an outcome of the first workshop. The workshop helped to enhance teachers’ understanding of climate change awareness, adaptation capabilities and reduction of vulnerabilities to climate-related disasters and their skills in transferring the knowledge to students. The report on first workshop can be found in the link below:

https://drive.google.com/file/d/1Sb3ZuggWyyz9UjIGhtpXFVB_-FLkY947/view?usp=sharing

Supporting curriculum development and delivery, thematic papers have been produced and disseminated on 1) Impact of EbA Curricula in generating awareness on CC & EbA in Bhimeshwor Municipality, Dolakha; 2) Assessment of increased water yield as a result of EbA interventions in three districts and 3) Climate change mitigation benefit. https://www.amazon.com/Forests-Climate-Change-Biological-Perspectives/dp/9819739047/ref=monarch_sidesheet https://forestaction.org/wp-content/uploads/2025/07/4_JFL_25_1_Khanal-et-al.pdf

https://drive.google.com/drive/folders/1u9OZVUSAqxO1NRZxcv5QNk_FLacKfXY6?usp=sharing

Furthermore, the media fellowship programme concluded in this reporting period with results including stories and reports on EbA disseminated through different media channels. As part of the programme, 22 print media articles, 10 radio broadcasts and 5 TV news reports have been published and broadcast. These products mainly covered topics on the impact of conservation ponds, filtering dams, improved terraces, plantation, livelihood enhancement, community’s role in actions against climate change and adaptation initiatives etc. A few examples of published articles are as below:

•	https://www.hamroupdate.com/31/07/2024/166134/

•	https://madhyanhadaily.com/post/1659

•	https://butwaltoday.com/?p=66963

•	https://salyantoday.com/2024/08/08/12797.

More detailed can be found in the report: https://drive.google.com/file/d/1v2IT1O3_9j6EFmYPdNOtcZ3w2YU8zLLN/view?usp=sharing

To document and disseminate the impacts of the project, Nepal Forum of Environmental Journalists (NEFEJ) produced a 35-minute comprehensive documentary and a 10-minute short version, highlighting major interventions such as forest restoration, climate-resilient agriculture, eco-tourism, and community-based conservation, eco-club initiatives in schools, and women's involvement in natural resource management.  The documentary was produced in Nepali with English subtitles and broadcast through the Aankhijhyal video magazine on 15 national and regional TV channels. The video links are as below:

- https://www.youtube.com/watch?v=BpF3gx28dEg

- https://www.youtube.com/watch?v=IiyYx6WIwP0

In addition, two short videos on climate change and adaptation were showcased during side event in COP29 at Baku, Azerbaijan. Links for videos are as below:

- https://youtu.be/V1sXm2P1njk

- https://youtu.be/pb-Kd5UmKHc

Finally, the project distributed the following educational and awareness materials: Protocol for Planning and Implementing Ecosystem based Adaptation (EbA) Interventions, EbA Capacity building training for Government officials, Guideline for implementing Ecosystem based Adaptation (EbA) Interventions, Community level training manual on EbA, District level training manual on EbA, EbA II brochures, EbA Posters and educational toolkit “Green School Resource Handbook”.

In addition to training solely carried out under the project, contributions to ongoing national capacity building initiatives enhanced the achievement of Outcome 1. During this reporting period, the project supported the mainstreaming of EbA within the Sagarmatha Sambaad held between May 16-18, 2025, in Kathmandu on the theme “Climate Change, Mountains and the Future of Humanity.” Sagarmatha Sambaad is a biennial, multi-stakeholder dialogue forum initiated by the Government of Nepal to address pressing global, regional, and national issues.

The project also convened, a thematic session on the impact of sanitation nutrition and climate change in infectious disease, occupational and environmental health under the main theme of “Health Beyond Health”, at the National Health Summit 2024 organized by Nepal Medical Association (NMA) on 13-14 December 2024.

As of the end of the project period, the project has provided training to 776 participants (30% female) on EbA planning and implementation with the representation from the federal and district level government officials, community leaders and ward officials.

Outcome 2: National Policies and strategies strengthened to promote EbA implementation.

Under this outcome, three draft policy briefs aimed at influencing the policy arena were finalized during the reporting period: (1) Rangeland restoration, 2) Integration of EbA into community-based forest management and (3) Restoration and enhancement of agroecosystems through plantations and agroforestry on private lands.

The project developed an EbA upscaling strategy and financing plan that is targeted to local, provincial, and federal governments and stakeholders to integrate EbA into forestry, biodiversity, wetland and watershed sector policies and regulatory and operational instruments. The upscaling strategy can be found in the link: https://drive.google.com/file/d/189Ym5nKvnr4UxpoqQWnGh-imyi6U6z2F/view?usp=sharing

To support the implementation of the upscaling strategy, 12 best practices and critical lessons learned were documented and disseminated., These practices span seven thematic areas: policy integration, planning and upscaling, media engagement, research collaboration, capacity-building, water conservation, and livelihood improvement. The document can be found in the link: https://drive.google.com/file/d/1GKjQl_Huorg6qiw8Yx6h5OVkEjvFFYDu/view?usp=sharing

Finally, to further support mainstreaming EbA into national policies, the project provided support for the inclusion of the newly published Nepal Disaster Report 2024 prepared by the Ministry of Home Affairs as part of its commitment to the UNDRR and the Sendai Framework. This is the first time that the report highlights climate-induced disasters and loss and damage and focuses on building resilience through EbA. Nepal presented the report at the Asia Pacific Ministerial Conference on Disaster Risk Reduction in Manila from October 14-18, 2024. The disaster report can be found in the link: https://drive.google.com/file/d/1PsIebzVHRz5cnH6taOhNMouSTxEjxMkt/view?usp=sharing

Outcome 3: EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change.

Under this outcome, the project has undertaken restoration works and community livelihood options to build community resilience. During the reporting period, 106 hectares of degraded rangelands have been restored, with a total cumulative restoration of 425 hectares (94% of overall rangeland restoration target 450) and 35 hectares of terraces have been improved/constructed for a cumulative improvement of 638 hectares of terraces.

Furthermore, during the reporting period, 42 sheds for livestock were constructed, additional support was provided to the nursery established in the DFO Achham premises, a filtering dam has been constructed with a cumulative total of 222 to date and a water conservation pond has been constructed with a cumulative total of 100 water conservation ponds constructed/rehabilitated so far.

With regards to reducing sensitivity through local planning and development, 3 Community Forestry Operational Management Plans (CFMP) have been updated to include EbA criteria bringing the project total to 141 CFMP updated against 100 targeted. Furthermore, in Dolakha district, seven Community Livelihood Improvement Plans (CLIPs) activities related to EbA were implemented, and in Salyan district, 23 EbA related CLIP activities were implemented. Overall, during the project period, 20 CLIPs have been developed, and 113 activities have been implemented improving communities’ livelihood opportunities and increased income generation.

Finally, Local Adaptation Plans for Action (LAPA) were planned for eight working municipalities (Bangad Kupinde, Sanfebagar, Mellekh, Ramaroshan, Bhimeshwor, Kalinchowk, Shailung and Jiri). So far, three LAPAs have been developed in Sanfebagar Municipality, Ramaroshan Rural municipality and Kalinchowk Rural Municipality with the remaining 5 LAPAs are expected to be developed by August 2025.

Challenges

The project only faced one notable challenge during the reporting period, during the LAPA development process. Since rural municipalities have limited knowledge and technical expertise on development of LAPA, they took some time in fully understanding the process. This delayed the timely initiation of development process. However, the project was able to address and overcome this challenge by providing technical support on steps to follow in the LAPA development process. With additional technical support, all LAPAs were on track for completion in August 2025.

Rating:

The overall rating of the project is satisfactory. The project completed most of the planned activities and achieved the overall target.

## 2.4 Co Finance

| Planned Co-finance: | USD 22,365,714 |
| --- | --- |
| Actual to date: | USD 21,483,109 (96%) |
| Progress | Justify progress in terms of materialization of expected co-finance. State any relevant challenges: - Total co-finance reported: USD 21,483,109 (96%) - Co-finance in this reporting period: USD 72,732 - Co-finance reported in previous PIR: USD 1,663,328 In this reporting period, USD 72,732 was reported as in-kind co-finance from MoFE for administrative support mostly in the form of office space, staffing and office supplies. MoFE is hosting the PMU as well as government officials supporting the projects, especially NPD and NPC. The space and time of these personnel are reported as in-kind contributions. In this reporting period, there is no report of co-finance from MoALD. In the last reporting period, USD 1,605,466 was reported. The other co-financers e.g. Adaptation for Smallholders in Hilly Areas, (ASHA), National Adaptation Plan (NAP), Nepal Climate Change Support Programme (NCCSP2) and Adapting to Climate-Induced Threats to Food Production & Food Security in Karnali Region of Nepal (CAF-Karnali) have phased out and thus no co-finance was reported from them. Overall, co-financing expenditures by partners have contributed largely to building the technical capacity of national and local stakeholders and enhancing the resilience of vulnerable communities. In addition, rangeland ecosystem enhancement has been achieved through investment in livestock productivity (LDSEP) through appropriate management of ecosystems. Besides the co-finance planned, the project has been able to leverage funding from local government. For example, a conservation pond was jointly renovated by EbA II and Bangad Kupinde Municipality of Salyan district. Similarly, in Kalinchowk-6 of Dolakha district, the project and the rural municipality jointly funded Allo (Himalyan Giant Nettle) processing training for community members under CLIPs activity. The municipalities contributed 20% of the total cost. The detailed co-finance report can be found in the link: https://docs.google.com/spreadsheets/d/1bN71yhQ2TWKFxtnZnY5ebM66D-KFnLYq/edit?usp=sharing&ouid=117834138242423528371&rtpof=true&sd=true |

## 2.5. Stakeholder

| Date of project steering committee meeting | 2024-09-01, 2024-12-02 |
| --- | --- |
| Stakeholder engagement (will be uploaded to GEF Portal) | In addition to the PSC meeting, the following activities and meetings were conducted with project stakeholders: - OAG Audit field visit, 8 - 13 July 2024 - Monitoring visit by DPC Salyan, 26-30 January 2025 - CCMD monitoring field visit, 10 – 14 January 2025 Meeting minutes or field visit reports can be found in the link: https://drive.google.com/drive/folders/1F6Wc1mBi8ferFVqSPKIv1X0QnmfeCl-Q?usp=sharing The project has been operationalizing its Stakeholder Engagement Plan (SEP) to ensure stakeholder engagement, avoid negative impacts, and enhance stakeholder ownership. The project has meaningfully engaged a wide range of stakeholders and experts providing them with opportunities to be involved at various stages, along with a grievances redress mechanism (GRM). The project actively engages central-level stakeholders through PSC meetings, providing updates on the plan, work progress, and implementation issues. PSC members from various ministries and departments are involved in decision-making processes. The 10th and 11th PSC meeting were platforms where the revised annual workplan for 2024 and project extension was approved, and directions were provided to project for timely completion of remaining activities and initiate project exiting approaches. At the subnational and local levels, municipalities, wards, and local user groups play a direct role in planning, implementing, and monitoring project interventions. Project DPCs regularly coordinate and communicate with municipal leaders and ward chairs on the identification of intervention sites, implementation and monitoring of the project activities. To further foster coordination, all DPCs are stationed in division forest offices of each working district. Proposals for activities are prepared by the ward offices and presented to the municipality for endorsement and approval. Field level activities are implemented through local user group committees While CAO, Municipal heads and technical personnel monitor the works after completion and approve the budgets and expenditures upon public hearing. Ward officials, including ward members regularly monitor ongoing project activities and provide suggestions and feedback based on observation to the user groups responsible for carrying out the activity. While local government undertakes routine monitoring of project activities, the project further includes them in field visits made by the project team, especially from PMU. This helps to not only foster the partnership between the project and local government but also create a sense of accountability for joint undertaking of project and the outcomes it generates. In Achham, a separate EbA implementation committee is in operation that is responsible for the overall planning and execution of activities. In addition, a technical official from each municipality is designated as EbA focal person who oversees implementation in each ward in consultation with the implementation committee. Likewise, an all-political party mechanism has been constituted and is operational in Ramaroshan Achham to provide guidance, monitor and resolve local issues if any. In Babla, local beneficiaries are made to sign a commitment letter to ensure local stewardship of the interventions undertaken. Participants for central level capacity building training are selected in consultation with MoFE and MoALD ensuring appropriate categories of officials are capacitated. In this reporting period, participants represented institutions/departments like FRTC, DoFSC, MoALD, Department of Livestock Services, Department of Agriculture, MoFE, CCMD (MoFE), Planning (MoFE), AFU and DNPWC. The project seeks contribution, support and approval from local and district-level line agencies for development and implementation of training materials, guidelines, and toolkits. For example, in this reporting period, EbA Education Toolkit titled “Green Resource Book” has been developed and printed in consultation with local stakeholders. Teachers and students participate through the teacher-student network for educational toolkit design. The overarching CEPA strategy and dissemination framework serve as key tools for engaging the public, including national awareness campaigns on EbA. Likewise, the project engages media personnel from all three working districts for EbA awareness raising and quality news reporting. For media engagement, the project liaises with federation of Nepali Journalist (FNJ). For example, 18 media personnel selected by respective FNJs from working districts have been brought on board and oriented under the media fellowship programme for wider dissemination of EbA key messages and awareness. To ensure transparency, participation, learning and accountability, the project has put in place grievance redress mechanism (GRM). DPCs have been oriented on the mechanism and the significance of its functioning. As part of the project implementation, all activities include dissemination of information on GRM among all project beneficiaries giving them the opportunity to share their grievances and suggestions if any. In addition, during field visits, M&EO verifies the functioning of the mechanism through interaction with beneficiaries and government stakeholders. In recent field visits, a few beneficiaries reported not knowing the technical name of the mechanism (i.e., GRM) but having awareness of who and where to go if they have complaints. This shows that stakeholders are aware of GRM and can reach out to project whenever they need to. |

## 2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming (will be uploaded to GEF Portal): | During this reporting period, the project has undertaken activities in line with the Gender Action Plan (GAP). Training modules and session plans were developed to enhance gender mainstreaming while, when conducting central and field level training activities have been put into practice to encourage the full and effective participation of the women. Despite project efforts, there is 30% women representation in the capacity building trainings for national, district, local government officials and community members. At community level training, project has achieved 35% women representation. Furthermore, development of the Community Livelihood Improvement Plan (CLIPs) ensures the inclusion of at least 30% women in Income Generating Activity (IGA) groups. Special attention is given to developing climate-resilient livelihood options for single women and female-headed households. Furthermore, in this reporting period, to reinforce gender inclusion, GEDSI integration training has been conducted to encourage and advocate for GEDSI mainstreaming in EbA programming. The project has also ensured that equality is maintained for payment for work. In all labour work related activities (skilled/unskilled), men and women are equally paid (E.g., NPR. 800 and 1000 for unskilled and skilled work respectively). Not only in field level activities, but the project has also ensured gender inclusion in all key aspects of its programming. For example, 58% of the research grantees who are currently undertaking research on EbA related issues/topics are female and 31% government officials trained on EbA are female. As already reported, MoFE has its own gender mainstreaming strategy and action plan along with gender focal person. Since EbA II is executed by MoFE, following the implementation of the gender action plan under the project, the follow up actions including monitoring will be continued by gender focal person from the MoFE.CC and GESI strategy, MOFE (2020-2027)https://www.mofe.gov.np/uploads/documents/gesiclimate-chng-repnepali1625885588pdf-9628-989-1657876169.pdf The project places significant emphasis on gender and social inclusion. The project, at its initial stage, developed a policy review action plan aligned with GAP. This report informs the integration of gender and social inclusion (GESI) issues and action plans at all project levels, including capacity building training. In capacity building training for government officials and community members, 31% women's participation was ensured. In the mid-mountain areas, where men often migrate for work, women's involvement in project interventions is significantly increasing. On average, approximately 51% of women have been engaged in various project interventions: 52% in rangeland restoration, 51% in forest restoration, 54% in terrace improvement, 50% in bio-engineering measures, 50% in filtering dam construction, 49% in conservation/recharge pond construction, and 51% in CLIPs. These interventions also provide opportunities for seasonal employment and cash income for women. The project has been successful in generating employment opportunity to the women. The involvement of women in implementation of recharge pond construction and operationalization are very high compared to other activities. This also provides an opportunity for seasonal employment and cash income for women. Disaggregated information about training participants can be found in the link https://docs.google.com/spreadsheets/d/15iEGz-DJl4Xtrn4X7atPdsuk4ZmLGWjf/edit?usp=sharing&ouid=117834138242423528371&rtpof=true&sd=true |

## 2.7. ESSM

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk CEO Endorsement/Approval Stage? No If yes, what specific safeguard risks were identified in the SRIF/ESERN? |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No If yes, describe the new risks or changes? |
| Complaints and grievances related to social and/or environmental impacts | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No If yes, please describe the complaint(s) or grievance(s) in detail, including the status, significance, who was involved and what actions were taken? |
| Environmental and social safeguards management | The project Safeguard Risk Identification framework (SRIF) categorized activities from this reporting period as having low risk and no new risks have surfaced and identified during this reporting period. Below is a summary of the project's Safeguards Risk Summary. |

## 2.8. KM/Learning

| Knowledge activities and products | The project has created various knowledge products in this reporting period. Knowledge products: - Documentation of Best Practices and Lessons Learned - EbA Upscaling Plan - Project Completion Report The project also distributed the following educational and awareness materials: Protocol for Planning and Implementing Ecosystem based Adaptation (EbA) Interventions, EbA Capacity building training for Government officials, Guideline for implementing Ecosystem based Adaptation (EbA) Interventions, Community level training manual on EbA, District level training manual on EbA, EbA II brochures, EbA Posters and educational toolkit “Green School Resource Handbook”. List of media coverage during this reporting period: - https://butwaltoday.com/?p=71416 - https://gurashonline.com/2024/09/22/4752 - https://newsofnepal.com/2024/06/30/653078/?fbclid=IwZXh0bgNhZWOCMTEAAR2RI7XSvSfq1aeSo- - https://www.onlinekhabar.com/2024/08/1522014 - https://gorkhapatraonline.com/news/119646 - https://www.onlinekhabar.com/2024/12/1595317/a-glimpse-of-the-lost - https://www.karobardaily.com/news/267715 - https://www.onlinekhabar.com/2024/10/1552748/happiness-safe-in-mothers-pouch - https://www.karobardaily.com/news/266389 - https://www.youtube.com/watch?v=MPpHcgpgKbA |
| --- | --- |
| Main learning during the period | Throughout the implementation, the project has continued to ensure that learning is collected time and again to gain valuable insights and inform decision-making for adaptive programming and stock taking. Some of these key learnings include: - Build the capacity of community groups through training on business planning, income generation, and infrastructure maintenance. Clear communication of roles and responsibilities fosters ownership and sustainability. - Continue technical, financial, and institutional support beyond project timelines. Strengthen monitoring systems and reactivate local-level staff to maintain momentum and oversight. - Embed EbA and LAPA approaches into local and municipal planning. Enhance coordination among federal, provincial, and local governments for aligned implementation and policy coherence. - Provide additional technical support for local communities / rural municipalities who lack experience in LAPA development. - Install signage at project sites and use communication tools like documentaries and success stories to raise awareness and inspire replication. - Scale up successful interventions such as terrace improvements, bioengineering, and conservation ponds in similar ecological regions to maximize impact. - Shift from isolated site interventions to integrated, landscape-level planning to ensure ecological connectivity and resilience. |

## 2.9. Stories

| Stories to be shared | In this reporting period, additional impact stories have been developed, they are: - Supporting locally led adaptation through engaged communities - Supporting locally led adaptation through engaged communities - Small enterprise: Big hopes for women entrepreneurs |
| --- | --- |

# 3 Performance

## 3.1 Rating of progress towards achieving the project outcomes

| Project Objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Progress as of current period (numeric, percentage, or binary entry only) | Summary by the EA of attainment of the indicator & target as of 30 June | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Increased capacity of national and local government institutions in Nepal to adapt to climate change by implementing EbA in degraded forests and rangelands in mid-hill and high mountain areas | 1. The degree to which capacity of targeted government institutions is strengthened at national and sub-national levels to identify, prioritize, implement, and assess the effectiveness of EbA interventions | Government Institutions at federal and provincial levels are in the process of identifying climate change risks. However, they are not acquainted with the EbA interventions to address climate related risks. As a result, management systems are not in place to implement EbA, and this approach is not included in budget allocations. | Approximately 200 beneficiaries will directly benefit from the project interventions | The increase of at least 3 in the capacity score of each institution (max 10, Min 0) | 100% | Complete information to measure this indicator remains to be gathered which will be done by the end of the project period as the status of institutions on the capacity criteria is yet to be verified. However, below is information that contributes to efforts made so far. By the end of the reporting period, 776 government officials and academicians (272) and community leaders (504) have been capacitated on EbA prioritization, planning, implementation, monitoring and evaluation. Most specifically, capacities of 10 working r/municipalities and 3 Division Forest Offices have been enhanced by demonstrating effective EbA implementation through forest and rangelands restoration. On account of these experiences and knowledge, r/municipalities have started prioritizing and investing in EbA initiatives and there is commitment to continue EbA as local plan priorities. In addition, Community Forest User Groups engaged with the project now have better knowledge about EbA and experience of implementing EbA initiatives enhancing their capacity to implement EbA projects in future on their own. At national level, Nepal government recently published 16th five-year Periodic Plan which identifies climate change and need of locally led adaptation initiatives as top priorities for period 2024-2028. Under the chapter 13 of the plan, Government of Nepal sets a transformative strategy to increase the capacity of local level government and communities against adverse impact of climate change by leveraging traditional knowledge and local resources, EbA initiatives, innovative techniques and technologies. Similarly, Forest Research and Training Centre (FRTC), a government body under the MoFE responsible for forestry research and survey activities at the national level, have started mainstreaming climate change and EbA into their regular in-service training programs. In particular, they have allocated a separate session on climate change and EbA in their training program. Likewise, research institution, Nepal Academy of Science and Technology (NAST) has also been trained on EbA and through them, 40 research grants (5 PhD, 15 Masters and 20 Bachelors) have been provided which will contribute to evidence generation on EbA for informed programming and learning. Furthermore, EbA curriculum development and roll out (in 29 community schools) has led to municipality (Bhimeshwor Municipality – Dolakha district) being able to introduce climate change and EbA from school level. In addition, for all capacity building training conducted, a pre and post training evaluation system has been introduced to measure the changes in the level of understanding of the participants. For instance, results from pre and post-test evaluation of central level government officials who participated in 5 Day training on EbA planning, implementation, monitoring and evaluation, suggest that there is a 22.4% increase in understanding among participants on topics covered during the training. Whereas in the case of district level government officials, the change in their understanding is 61%. | S |
|  | 2. A number of beneficiaries benefitting from project interventions disaggregated by gender. | Zero | Approximately 200 beneficiaries will directly benefit from the project interventions | Over 1220 beneficiaries will be directly benefitted from project interventions | 3,275 % | During the reporting period, a cumulative total of 39,958 (71% of the total population) beneficiaries engaged and directly benefitted by the project interventions through 9,527 (83%) households. Among them, 51% women are direct beneficiaries, and the ethnic composition comprises of Dalit, Janajati are others represented by 16.3%, 28.2% and 55.5% respectively. To ensure gender equality, a Gender Action Plan has been implemented guiding the implementation of gender-responsive activities. It is noteworthy that, on average, approximately 51% of women have actively participated in various project interventions as follows: i) Rangeland restoration - 51%; ii) Forests restoration - 51%; iii) Terrace improvement - 54%; iv) Bio-engineering measures - 50%; v) Filtering dam construction - 50%; vi) Conservation/Recharge Pond construction - 49%; vii) Community-led Initiatives and Practices (CLIPs) - 51%. The baseline report mentions that 11,453 HH are the beneficiaries of the project. Of the total population, 51% comprise of women. The ethnic composition comprises of Dalit, Janjati are others represented by 13%, 28% and 58% respectively. In line with this, the Gender Action Plan has been prepared based on which gender responsive activities are under implementation. During the activities implementations till the reporting period, a total of 17,435 women are directly engaged in project interventions. | HS |
| Increased capacity of government officials and local user groups to implement EbA through enhanced institutional arrangements, inter-sectoral collaboration and research. | 1. A technical working group with a mandate to identify, prioritize and monitor EbA established within IMCCCC | The technical working group does not exist. | An EbA Technical Working Group (TWG) has been formed and at least two meetings held. | At least 5 TWG meetings held to influence policy arenas through IMCCCC. | 100% | The third Technical Working Group meeting was held on 23 July 2024. Eba Upscaling strategy and financing plan were presented and reviewed during the meeting. As no further meeting was required, three meetings were deemed sufficient for the project. Thus, the achievement is 100%. | S |
|  | 2. Number of the national, district and local officers and community members with the capacity to identify, prioritize and implement EbA | Zero | During the mid-term, at least 75 government officials from three tiers of government are trained, of which 15% are women | By project end-point, at least 150 officials are trained, of which 30% are women. | 181% | In this reporting period, two sets of training were organized targeting central level government officials who are responsible for conservation, environment and climate change. The first training was on EbA planning, implementation, monitoring and evaluation and other one was on GEDSI integration in EbA Programming. In total 44 government officials participated in the training which improved their knowledge and skills on EbA and GEDSI mainstreaming in EbA programming. As of now, a total of 272 (22% female) Officials has been trained by organizing 12 events. Thus, the target of 150 has already been achieved by organizing 36 events or trainings for national, district, local officials and community leaders. The training report can be found here: https://drive.google.com/drive/folders/1tGTj8saF202fOxRcMn9vy8Mr55jA5vxL?usp=sharing For further information on the participants of the training, please follow the link: https://docs.google.com/spreadsheets/d/15iEGz-DJl4Xtrn4X7atPdsuk4ZmLGWjf/edit?usp=sharing&ouid=117834138242423528371&rtpof=true&sd=true | HS |
|  | 3. Number of national campaigns implemented by the project to increase public awareness on EbA. | Zero | At least one national awareness campaign held. | At least two national awareness campaigns organized. | 100% | Two national level campaigns were already implemented in the previous reporting period. | S |
| Increased capacity of government officials and local user groups to implement EbA through enhanced institutional arrangements, inter-sectoral collaboration and research. | 4. Number of educational tools including research findings developed by a project that is being used by government institutions to integrate EbA in the educational programmes and national planning. | Zero | Four tools developed. | Four tools developed. | 100% | EbA curricula for grades 6-8 and EbA educational toolkit titled “Green School Resource book” has been developed to deliver EbA related topics in their education programmes. The toolkit can be found in link: https://drive.google.com/drive/folders/1iFyRhfAPV6j0jJhmWcRxtZPs7mO5IA4e?usp=sharing In addition, with project commissioned grants, 40 academic research projects (Bachelors - 20, Masters - 15 and PhD - 5) are currently undergoing on topics related to Climate change, environment and EbA. Few examples of research topics are Soil characteristics and soil respiration in different, Forest types of Phulchoki, Central Nepal, Management of geosmin contamination of fish food from the eutrophic environment, Geospatial analysis of wetland dynamics and vulnerability assessment of major wetlands of Pokhara Valley, Nepal, and Ecosystem management and climate change adaptation options in the community managed forest of Nepal. Nepal Academy of Science and Technology (NAST) plans to organize a national level seminar and develop compendium as per their final deliverables. In addition, a comprehensive documentary was produced in Nepali with English subtitles and broadcast through the Aankhijhyal video magazine on 15 national and regional TV channels. It aimed to inform policy stakeholders, promote replication of EbA practices, and raise awareness on nature-based solutions for climate change adaptation. | S |
| National Policies and strategies strengthened to promote EbA implementation. | 1. Number of policy briefs to guide the revision of the policies/ strategies to integrate EbA. | Strategy/policy are inadequate to integration of EbA as part of an adaptation strategy in Nepal. |  | At least one policy brief is developed that has guided the revision of national policy/strategy | 100% | The project has developed three final draft policy briefs on: - Restoration of Degraded Private Land through Plantations, Natural Regenerations and Agroforestry - Mainstreaming Ecosystem-based Adaptation into Community-Based Forestry Management. - Rangelands Restoration and Management | S |
| National Policies and strategies strengthened to promote EbA implementation. | 2. Up scaling strategy for EbA in forests and rangelands developed. | No EbA up scaling strategy developed to date in Nepal. | EbA up scaling strategy developed. | Up-scaling strategy developed. | 100% | The project has developed EbA Upscaling Strategy and Action Plan. The project has also developed, published and disseminated EbA Upscaling plan. | S |
| National Policies and strategies strengthened to promote EbA implementation. | 3. Financing plans developed for EbA, including proposed budget allocations. | No financing plans for EbA exist to date in Nepal. | Draft financing plan developed. | Financing plan developed. | 100% | The project has developed EbA Upscaling Strategy and Action Plan which includes a financing plan. | S |
| EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change. | 1. A number of ha of forests restored by the project in selected wards using EbA | Baseline report has identified a total of 2,937 ha of degraded forests. | 400 ha of forests restored using EbA. | 1000 ha of forests restored using EbA. | 75% | No activities were conducted in this reporting period. In the previous reporting period (2022-2023), 138 ha of forests land was restored with cumulative total of 274 ha. Likewise, a total of 475-hectares of degraded forests have been restored during the reporting period. A total cumulative 750 hectares of degraded forests have been restored till date. A total of 184,968 seedlings/rhizomes of various species are planted. Notable among them are soft walnut, Timur (pepper), dale grass, Amriso, Cardomom, Texas (Loth salla), Nigalo (Himalayan bamboo), Bamboo, Chiuri, Ritha, Tooni, Khair, Tanki, Koiralo and Ipil. Bamboo. CFUG members have directly benefited from the engagement in nursery related work, bedding, pitting, plantation and restoration work. S. N District Restored (ha) during reporting period Cumulative till date Achham 158.342 Dolakha 215.713 Salyan 376 Total 750.05 Until the reporting date, 86% of the cumulative forest restoration target of for year 2024 (870 ha) and 75% of overall forest restoration target (1000 ha) has been achieved. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 69.4 ha 2021-2022: 67.1 ha 2022-2023: 138 ha 2023-2024: 475 ha 2024-2025: 0 ha Total: 750 ha (75%) | S |
| EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change. | 2. A number of ha of rangelands reseeded by the project in selected wards using EbA | As per Baseline report, local demand for restoration of 703 ha rangelands across 3 districts. | 200 ha of rangelands restored using EbA options. | At least 450 ha of rangelands restored using EbA. | 94% | In the previous reporting period (2023-2024), 102 ha of rangeland was restored with cumulative total of 319 ha. 106 hectares of degraded rangelands have been restored during this reporting period. In addition, 42 sheds for livestock have been constructed out of which 15 are Yak sheds, 16 are goat sheds, 9 are buffalo sheds and 2 are sheep sheds. A total cumulative 425 hectares of degraded rangelands have been restored during the project tenure. CFUG members have directly benefited from this intervention in clearing and fencing, plantation, seeding and other related work. Under this activity, the project has been able to achieve 94% against the project target of 450 ha. Restoration works are still ongoing in the field and there will be more progress in the coming days. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 93.4 ha 2021-2022: 53.7 ha 2022-2023: 70 ha 2023-2024: 102 ha 2024-2025: 106 Total: 425 ha (94%) | S |
| EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change. | 3. A number of operational management plans updated to include EbA interventions as part of VDC adaptation strategies. | Zero | 80 operational management plans updated. | 100 operational management plans updated | 141% | A total of 141 Community Forestry Operational Management Plans (CFMP) has been updated with the integration of EbA criteria with 3 additional in this reporting period. In this regard, 138% progress has been achieved against the project target of updating 100 CFMP. | HS |
| EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change. | 4. Number of techniques introduced in selected wards to conserve topsoil and water. | Zero | 60 ha of improved terraces, 18 filtering dams, 18 water conservation ponds and 12 community rainwater harvesting devices constructed in selected Wards | 720 ha of improved terraces, 36 filtering dams, 36 water conservation ponds and 24 community rainwater harvesting devices constructed in selected Wards | 89% | In the previous reporting period (2022-2023), 113 ha of terraces were improved with cumulative total of 603 ha. A total of 35 ha terrace has been improved during this reporting period. A cumulative 638-hectare of terraces has been improved to conserve agriculture land and control torrents/runoff till date. The progress on improved terraces is 89% against the target of 720 hectares. This has been one of the most sought-after activities under the project. Terrace. At the time of reporting, terrace improvement works in many sites were nearing completion and thus, more progress is certain in coming days. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 101.4 ha 2021-2022: 271.6 ha 2022-2023: 117 ha 2023-2024: 113.4 ha 2024-2025: 35 ha Total: 638 ha (89%) Likewise, a filtering dam has been constructed during the reporting period. A total cumulative of 222 filtering dams have been completed. The intervention would slow runoff, reduce water erosion, retain sediment, and promote water filtration. The progress on filtering dams is 617% against the target of 36. Similarly, a water conservation pond was constructed during the reporting period. A cumulative 100 water conservation ponds have been constructed to date, 278% progress against the project target of 36 nos. In addition, the conservation ponds are reported to benefit, through irrigation facilities. Furthermore, these ponds will also provide a source of drinking water for livestock and wildlife from the immediate neighborhoods. In Dolakha, six spurs (loose stone wall/gabion wall with bamboo and Amriso plantation) were constructed near the right and left bank of the streams. Six sites located at (Jhingane in Bhimeshor-9, ghattekhola in Shailung-4, GodungKhola in Lapilang-6, Ghattekhola in Lapilang-5, Dhunge Khola in Jiri- 5, Tatopani in Gaurishankar-8) have completed with bio-engineering measures. | S |
| EbA implemented and monitored by user groups to restore forests and rangelands in the mid-hills of Achham and Salyan and high mountains of Dolakha to decrease sensitivity of local communities to climate change. | 5. Number Community Livelihood Improvement Plans (CLIPs) developed from forests, rangelands and agro-ecosystems of and implemented in selected wards . | Zero | 2 CLIPS developed and implemented. | 10 CLIPS developed for forests, rangelands and agro-ecosystems and implemented in selected wards. | 200% | Overall, during the project period, 20 CLIPs have been developed, and 113 activities have been implemented improving communities’ livelihood opportunities and increased income generation. Few examples of IG options are Potato chips processing unit, cadmium processing unit, turmeric processing unit and milk cooling center, Allo processing unit (Training and Truss House), mushroom farming training and constructed, mushroom farming tunnel, Timur farming, orange farming and bamboo handicraft training; seasonal tunnel vegetable farming; and bamboo handicraft training, Beekeeping training and hive distribution, Sisno (stinging nettle) powder processing training, Potato chips production and marketing support, Ginger cultivation and peanut cultivation, solar dry house, compost processing machines etc. | HS |

## 3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Component No | Output/Activity | Expected completion date | Implementation status as of previous reporting period (%) | Implementation status as of current reporting period (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Output 1.1: Technical working group on EbA established within the IMCCCC | 2024-07-30 | 95% | 100% | Two TWG meetings have already been held in the last report. In this reporting period, the third and last TWG meeting was held to present and review the EbA upscaling strategy and action plan. | S |
| 1 | Output 1.2 Training provided for national, district and local stakeholders on identifying, prioritizing, implementing, monitoring and evaluating EbA interventions. | 2024-06-30 | 152% | 181% | A total of 44 central government officials has been trained on EbA, during this reporting period of which 15 were female (34%). With this training, all training events planned under the project have been completed. The project has already achieved the target of 150, exceeding 122 (i.e., 272). | HS |
| 1 | Output 1.3: National campaigns implemented, and district level collaboration facilitated on EbA approaches and benefits, including lessons learned in Component 3. | 2024-06-30 | 95% | 100% | Two national awareness campaigns have already been completed in last reporting periods. No campaigns were organized in this reporting period. However, a comprehensive documentary was produced in Nepali with English subtitles and broadcast through the Aankhijhyal video magazine on 15 national and regional TV channels. It aimed to inform policy stakeholders, promote replication of EbA practices, and raise awareness on nature-based solutions for climate change adaptation. | S |
| 1 | Output 1.4: Primary, secondary and tertiary educational programmes developed on EbA best practices. | 2024-09-30 | 100% | 100% | EbA curricula for grades 6-8 and EbA educational toolkit titled “Green School Resource book” has been developed to deliver EbA related topics in their education programmes. The toolkit can be found in link: https://drive.google.com/drive/folders/1iFyRhfAPV6j0jJhmWcRxtZPs7mO5IA4e?usp=sharing | S |
| 2 | Output 2.1: Number of policy brief to guide the revision of the policies/strategies to integrated EbA | 2024-09-30 | 95% | 100% | The project has developed three final draft policy briefs on: - Restoration of Degraded Private Land through Plantations, Natural Regenerations and Agroforestry - Mainstreaming Ecosystem-based Adaptation into Community-Based Forestry Management. - Rangelands Restoration and Management | S |
| 2 | Output 2.2: Upscaling strategy for EbA in forests and rangelands developed. | 2024-09-30 | 95% | 100% | The project has developed an EbA Upscaling Strategy and Action Plan. | S |
| 2 | Output 2.3: Financing plans developed for EbA, including proposed budget allocations | 2024-09-30 | 95% | 100% | The project EbA Upscaling Strategy and Action Plan includes a financing plan. | S |
| 3 | Output 3.1: A number of ha of forests restored by the project in selected wards using EbA. | 2024-12-30 | 75% | 75% | The forest restoration activities were completed in the last reporting period. Thus, no more achievements were recorded in this reporting period. In the previous reporting period (2022-2023), 476 ha of forests land was restored with cumulative total of 750 ha. Thus, a total cumulative 750 hectares of degraded forests could be achieved during project tenure. The total percentage of restoration progress is 86% against the cumulative target of year 2024 (870 ha) and 75% against the project target of 1000 ha. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 69.4 ha 2021-2022: 67.1 ha 2022-2023: 138 ha 2023-2024: 475 ha 2024-2025: 0 ha Total: 750 ha (75%) Delay in resolution of issue on wrong budget heading in Achham district resulted in forest restoration no meeting 100% i.e. 1,000 ha. The project team explored all avenues and continuously followed up with ministries (MoFE and MoF) to expedite the resolution process. Finally, when the issue was resolved, it was too late, according to DFO Achham, for restoration works to be carried out. The project will look to explore other avenues to initiate the forest restoration works in Achham but there remains a possibility of underachievement of overall target of 1000 ha. | S |
| 3 | Output 3.2: Number of ha of rangelands reseeded by the project in selected wards using EbA. | 2024-09-30 | 71% | 94% | In the previous reporting period (2023-2024), 102 ha of rangeland was restored with cumulative total of 319 ha. 106 hectares of degraded rangelands have been restored during this reporting period. In addition, 42 sheds for livestock have been constructed out of which 15 are Yak sheds, 16 are goat sheds, 9 are buffalo sheds and 2 are sheep sheds. A total cumulative 425 hectares of degraded rangelands have been restored during the project tenure. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 93.4 ha 2021-2022: 53.7 ha 2022-2023: 70 ha 2023-2024: 102 ha 2024-2025: 106 ha Total: 425 ha (94%) | S |
| 3 | Outputs 3.3 A number of operational management plans updated to include EbA interventions as part of VDC adaptation strategies | 2024-06-30 | 138% | 141% | A total of 3 Community Forestry Operation Management Plan (CFOMP) has been updated during this reporting period. 6 Community Forestry Operation plan was reported in the previous year. A total of 141 CFOP have been updated with the integration of EbA criteria. In this regard, 1141% of progress has been achieved against the project target of updating 100 CFOMP. Integration of EbA in CFOMP support in mainstreaming EbA in community forestry of the country. The rating of HS is given because the internal target was 100. There were demands from additional Community Forestry User Groups for updating their operational management plans. Budget allocated for 100 plans was enough to update additional plans. | HS |
| 3 | Output 3.4: Number of techniques introduced in selected wards to conserve top soils and water | 2024-09-30 | 84% 614% 275% | 100% 617% 278% | In the previous reporting period (2022-2023), 113 ha of terraces were improved with cumulative total of 603 ha. A total of 35 ha terrace has been improved during this reporting period. A cumulative 638-hectare of terraces has been improved to conserve agriculture land and control torrents/runoff till date. The progress on improved terraces is 89% against the target of 720 hectares. This has been one of the most sought-after activities under the project. Terrace. At the time of reporting, terrace improvement works in many sites were nearing completion and thus, more progress is certain in coming days. Distinct achievement as per reporting period is as below: 2019-2020: 0 ha 2020-2021: 101.4 ha 2021-2022: 271.6 ha 2022-2023: 117 ha 2023-2024: 113.4 ha 2024-2025: 35 ha Total: 638 ha (89%) Likewise, a filtering dam has been constructed during the reporting period. A total cumulative of 222 filtering dams have been completed. The intervention would slow runoff, reduce water erosion, retain sediment, and promote water filtration. The progress on filtering dams is 617% against the target of 36. Similarly, a water conservation pond was constructed during the reporting period. A cumulative 100 water conservation ponds have been constructed to date, 278% progress against the project target of 36 nos. In addition, the conservation ponds are reported to benefit, through irrigation facilities. Furthermore, these ponds will also provide a source of drinking water for livestock and wildlife from the immediate neighborhoods. In Dolakha, six spurs (loose stone wall/gabion wall with bamboo and Amriso plantation) were constructed near the right and left bank of the streams. Six sites located at (Jhingane in Bhimeshor-9, ghattekhola in Shailung-4, GodungKhola in Lapilang-6, Ghattekhola in Lapilang-5, Dhunge Khola in Jiri- 5, Tatopani in Gaurishankar-8) have completed with bio-engineering measures. | HSS |
| 3 | Output 3.5: Community Livelihood Improvement Plans (CLIPs) produced from forests, rangelands and agro ecosystems and implemented with local communities. | 2024-09-30 | 60% | 200% | Overall, during the project period, 20 CLIPs have been developed, and 113 activities have been implemented improving communities’ livelihood opportunities and increased income generation. Few examples of IG options are Potato chips processing unit, cadmium processing unit, turmeric processing unit and milk cooling center, Allo processing unit (Training and Truss House), mushroom farming training and constructed, mushroom farming tunnel, Timur farming, orange farming and bamboo handicraft training; seasonal tunnel vegetable farming; and bamboo handicraft training, Beekeeping training and hive distribution, Sisno (stinging nettle) powder processing training, Potato chips production and marketing support, Ginger cultivation and peanut cultivation, solar dry house, compost processing machines etc. | HS |

The Task Manager will decide on the relevant level of disaggregation (i.e. at either the output or activity level).

# 4 Risks

## 4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating

| Risk Factor | EA Rating | TM Rating |
| --- | --- | --- |
| 1 Management structure - Roles and responsibilities | Low | Low |
| 2 Governance structure - Oversight | Low | Low |
| 3 Implementation schedule | Low | Low |
| 4 Budget | Low | Low |
| 5 Financial Management | Low | Low |
| 6 Reporting | Low | Low |
| 7 Capacity to deliver | Low | Low |

If any of the risk factors is rated a Moderate or higher, please include it in Table B below

## 4.2 Table B. Risk-log

Implementation Status (Current PIR)

Insert ALL the risks identified either at CEO endorsement (inc. safeguards screening), previous/current PIRs, and MTRs. Use the last line to propose a suggested consolidated rating.

| Risks | Risk affecting: Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 | PIR 6 | PIR 7 | Δ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Information gaps |  | L | L | L | L | L | L | L |  |  | The information gaps of GAP. SRIF SEP has been generated and developed. Regarding SRIF and SEP. PMU will conduct periodic monitoring and address the issues accordingly. This issue has been resolved for now. |
| Financial Management |  |  | H | H | L | L | L | L |  |  | The high probability of fund diversion on the early part of the project was partly attributed to the new approach for municipal executives. Prior to EbA II. none of the municipal bodies had experience of using external fund (conditional grants) for a set of specific EbA activities. PMU realised this and provided various orientation and technical training including preparation of EbA implementation guidelines and working procedures to guide them. As a result, the possibility of fund diversion has been completely ruled out now. |
| Lengthy procurement process. Public Procurement Act (PPA) of the Government is lengthy and often time consuming and therefore. procurement delays have been realized from the very start resulting in the delivery of outputs and targets of the project. Procurement DPCs has to go through this process. A normal procurement process will take at least 17 weeks to materialize. |  |  | M | M |  | L | L | L |  |  | It is obligatory to follow the government procedures. CCMD/PMU team will have to be proactive and more vigilant to ensure that paper works are prepared on time and processed for timely execution. As of now. most of the recruitment and procurement has been completed and this issue will no longer be relevant. |
| Procedural delays: With the change in the governance structures. Project has been facing procedural delays for the channelization of project funds owing to various tiers of government from federal. provincial and local and subsequent reporting. |  |  |  | M | L | L | L | L |  |  | The procedural delays will be inherent and will continue to exist. as the project needs to follow Government rules and procedures. |
| Disagreement among stakeholders on the allocation of roles in the project |  |  |  | M | L | L | L | L |  |  | As the project undertook central and field level inception workshops during which the stakeholders were informed about their role and responsibilities. PMU also prepares the working procedures for project implementation on the ground. Likewise, a stakeholder's engagement plan (SEP) has been developed to engage them at every level of project implementation. |
| The limited capacity of institutions to undertake scientifically rigorous research. |  |  |  |  | M | L | L | L |  |  | The project has implemented a series of capacity building measures for wide range of stakeholders. Including AliVE tool training. EbA identification. planning. prioritization. implementation & monitoring. Likewise. project has developed technical guidelines. Protocols, manuals, implementation guidelines for building their capacity on EbA. Similarly. an MoU with NAST has been signed to undertake research on EbA |
| Lack of inter-institutional data sharing or collaboration. |  |  |  |  |  | L | L | L |  |  | The project coordinates with relevant partners in sharing relevant data information through the TWG meetings. |
| Lack of political will to implement project activities. |  |  |  |  |  | L | L | L |  |  | The PMU has maintained regular good coordination with Ministry and collaborative partners both at the centre and field. |
| High turnover of staff members in implementing agencies |  |  |  |  |  | L | L | L |  |  | The project has not faced the issue currently. However. the project has prepared “working procedures” of the project and got it endorsed by Ministry. Thus. even with the changes. the modality will guide the system. |
| Limited acceptance of EbA by local communities |  |  |  |  |  | L | L | L |  |  | Inspection workshop held, working procedure developed and implemented. field implementation plan rolled out. orientation on EbA held. GAP developed and CLIPs rolled out. |
| Disagreement over the allocation of land for the implementation of project activities. |  |  |  |  |  | L | L | L |  |  | The project has not encountered this issue yet and if there are any issues. It will be resolved with stakeholder consultation. |
| Extreme climatic events and climate variability. |  |  |  |  |  | L | L | L |  |  | None as of now. |
| Limited local technical capacity hinders project interventions. |  |  |  |  |  | L | L | L |  |  | TA and thematic expert are providing technical know-how and expertise for building capacity on EbA measures to ensure long-term sustainability of interventions undertaken. The project has collaborated with NAST to undertake research EbA. |
| Limited commitment/buy-in from local communities. |  |  |  |  |  | L | L | L |  |  | The stakeholder engagement plan has ensured that there is community buying and also the GAP and GESI has been rolled out as part of the community engagement. |
| Unsustainable land and natural resource use. |  |  |  |  |  | L | L | L |  |  | Restoration work related to forest and rangelands will contribute towards the conservation and sustainable use of lands. CLIPS will also ensure the protection and sustainable use of forest resources. |
| Limited understanding of the difference between “business-as-usual” reforestation/restoration of rangelands and EbA by indigenous and local communities |  |  |  |  |  | L | L | L |  |  | The project has imparted capacity building training and awareness raising campaigns to enhance the knowledge and understanding on the importance of EbA measures. |
| Insufficient surface water and groundwater availability at intervention sites. |  |  |  |  |  | L | L | L |  |  | Water conservation measures such as conservation ponds. recharge ponds. water augmentation measures including infrastructures such as rainwater harvesting techniques have been undertaken for the conservation and sustainable use of water and wetlands. |
| Risk k |  |  |  |  |  | L | L | L |  |  |  |
|  |  |  |  |  |  | L |  |  |  |  |  |

## 4.3 Table C. Outstanding Moderate, Significant, and High risks

Additional mitigation measures for the next periods

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken this reporting period | What | When | By Whom |
| --- | --- | --- | --- | --- | --- |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. Significant Risk (S): There is a probability of     between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may     fail to hold or materialize, and/or the project may face only modest risks. Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may     face only modest risks.

# 5 Amendment - GeoSpatial

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to         5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of         the change that occurred in the textbox. You may attach supporting document as appropriate

## 5.1 Table A: Listing of all Minor Amendment (TM)

| Minor Amendments | Changes |
| --- | --- |
| Results Framework: |  |
| Components and Cost: |  |
| Institutional and implementation arrangements: |  |
| Financial Management: | Yes |
| Implementation Schedule: |  |
| Executing Entity: |  |
| Executing Entity Category: |  |
| Minor project objective change: |  |
| Safeguards: |  |
| Risk analysis: |  |
| Increase of GEF financing up to 5%: |  |
| Location of project activity: |  |
| Other: | Yes |

Minor amendments

The Project has undergone a No Cost Extension period as mandated by the PSC and endorsed by MoF until the end of December 2024. Accordingly, the PCA has been amended and recorded by both parties.

Some activities such as rainwater harvesting devices have been dropped and the resources are allocated for construction of recharge ponds. Likewise, AWS (automatic weather stations and long-term research monitoring has been dropped. Similarly, as recommended by the Baseline survey report, yak sheds have been constructed to address critical climate induced risk.  All the above activities were adequately discussed and agreed during the MTR mission.

## 5.2 Table B: History of project revisions and/or extensions (TM)

| Version | Type | Signed/Approved by UNEP | Entry Into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
| Original legal instrument | Extension | 05/25/2018 | 05/25/2018 | 05/31/2023 |  |
| Extension 1 | Extension | 01/23/2013 |  | 06/30/2025 |  |

GEO Location Information:

Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as         appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please         see the Geocoding User Guide by clicking here

| Location Name | Latitude | Longitude | GEO Name ID | Location Description | Activity Description |
| --- | --- | --- | --- | --- | --- |
| Khare.8 | 27.7771 | 86.2217 |  | Project working sites in Dolakha district |  |
| LakuriDanda.9 | 28.1420 | 82.5610 |  | Project working sites in Dolakha district |  |
| Lapilang 5 | 27.7450 | 86.1086 |  | Project working sites in Dolakha district |  |
| Lapilang 6 | 27.7377 | 86.0877 |  | Project working sites in Dolakha district |  |
| Magapauwa 4 | 27.6551 | 85.9867 |  | Project working sites in Dolakha district |  |
| Jiri 5 | 27.6674 | 86.2728 |  | Project working sites in Dolakha district |  |
| Devasthal | 28.5140 | 82.0282 |  | Project working sites in Salyan district |  |
| Ganjaripipal 6 | 29.2511 | 81.0771 |  | Project working sites in Salyan district |  |
| Ganjaripipal 7 | 29.3021 | 81.1021 |  | Project working sites in Salyan district |  |
| Mulkhola 4 | 28.5398 | 82.1110 |  | Project working sites in Salyan district |  |
| Mulkhola 5 | 28.6490 | 82.3121 |  | Project working sites in Salyan district |  |
| Suikot 2 | 28.5729 | 82.1534 |  | Project working sites in Salyan district |  |
| Babla | 29.3215 | 81.2486 |  | Project working sites in Achham district |  |
| Bhatakatiya | 29.2316 | 81.4039 |  | Project working sites in Achham district |  |
| Ramaroshan | 29.2018 | 81.4135 |  | Project working sites in Achham district |  |
| Rishidaha 1 | 29.0396 | 81.2518 |  | Project working sites in Achham district |  |
| Rishidaha 2 | 29.1207 | 81.3197 |  | Project working sites in Achham district |  |
| Sodasha | 29.0664 | 81.2934 |  | Project working sites in Achham district |  |

Please provide any further geo-referenced information and map where the project interventions is taking place as appropriate. *

[Annex any linked geospatial file]

Additional Supporting Documents:

| Filename | File Uploaded By | File Uploaded At |  |
| --- | --- | --- | --- |