UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5681 | Umoja no.: 32CCL-14AC0001-S1-32CCL-000012-SB-006743 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Building climate resilience of urban systems through Ecosystem-based Adaptation (EbA) in Latin America and the Caribbean |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | Ecosystems Division, Climate Change Adaptation Unit, Freshwater, Land and Climate Branch |  |  |
| Executing Agency(ies) |  |  | UNEP-ROLAC, MARN, MWLECC and SEMARNAT |  |  |
| Names of Other Project Partners |  |  | Mexico: Fondo Golfo de México AC (FGM) Jamaica: Jamaica Social Investment Fund (JSIF); Jamaica 4H Clubs El Salvador: FUNDASAL; PROCOMES |  |  |
| Project Type |  |  | Full Size Project |  |  |
| Project Scope |  |  | Regional |  |  |
| Region (delete as appropriate) |  |  | Latin America and the Caribbean |  |  |
| Names of Beneficiary Countries |  |  | El Salvador, Jamaica and Mexico |  |  |
| Programme of Work |  |  | Programmes of Work 2018-2019 and 2020-2021, Climate Change Subprogramme |  |  |
| GEF Focal Area(s) |  |  | Climate Change Adaptation |  |  |
| UNDAF linkages |  |  | Mexico UNDAF 2014-2019 – Outcome 3: Environmental sustainability and green economy - Direct effect 6: the three orders of government, the private sector, academia and civil society will have strengthened their capacities to reverse environmental degradation and take sustainable and equitable use of natural resources through the mainstreaming of environmental sustainability, low emission development and green economy in legislation, programming and decision-making processes. Jamaica UN-MSDF for the Caribbean 2017-2021 – Priority area 4: A Sustainable and Resilient Caribbean - Outcome 1: Policies and programmes for climate change adaptation, disaster risk reduction and universal access to clean and sustainable energy in place El Salvador: UNDAF 2016-2020 – Priority 4: Move towards an economy and society environmentally sustainable and resilient to the effects of climate change - Effect 4: The population and those who are most vulnerable and excluded have increased their resilient capacities to face disasters, environmental degradation and the negative effects of climate change. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Goal 13: Take urgent action to combat climate change and its impacts Targets 13.1, 13.2 and 13.3 Indicators 13.2.1 and 13.3.2 Goal 11: Make cities inclusive, safe, resilient and sustainable Targets 11.A and 11.B Indicator 11.A.1Indicator 11.A.1 |  |  |
| GEF financing amount |  |  | 6,000,000 USD |  |  |
| Co-financing amount |  |  | 29,734,000 USD |  |  |
| Date of CEO Endorsement |  |  | October 21, 2016 |  |  |
| Start of Implementation |  |  | April 14, 2017 |  |  |
| Date of first disbursement |  |  | N/A (internally executed project) |  |  |
| Total disbursement as of 30 June |  |  | N/A (internally executed project) |  |  |
| Total expenditure as of 30 June |  |  | 587,477.20 |  |  |
| Expected Mid-Term Date |  |  | January 2020 |  |  |
| Completion Date |  | Planned | October 2021 |  |  |
|  |  | Revised | N/A |  |  |
| Expected Terminal Evaluation Date |  |  | April 2022 |  |  |
| Expected Financial Closure Date |  |  | October 2022 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Climate Change Subprogramme PoW 2018-2019 | Specify the relevant Expected Accomplishment(s) & Indicator(s) Expected Accomplishment (a): Countries increasingly advance their national adaptation plans which integrate ecosystem-based adaptation Indicator (ii): Increase in the number of countries that have technical capacity to integrate ecosystem-based management into national adaptation plans |
| --- | --- |
| In the reporting period, awareness and understanding of Ecosystem-based Adaptation (EbA) approaches has been enhanced in the three project target cities through capacity building and participatory vulnerability assessment processes. Capacity for analyzing climate change impacts and vulnerabilities and for identifying adaptation options has been strengthened, paving the way for their integration in urban policy-making and planning processes. The demonstration of EbA approaches was also initiated in each of the three cities. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
| N/A (GEF 5 project) | N/A (GEF 5 project) |

| Planned linkages with UNDAF | The project is linked to the UNDAF 2014-2019 in Mexico, UNDAF 2016-2020 in El Salvador and to the Caribbean UN-MSDF 2017-2021 for Jamaica. The project’s interventions contribute towards increasing the resilience of populations to the impacts of climate change and towards environmental sustainability, and as such contribute directly to the Mexican UNDAF outcome 3 “Environmental sustainability and green economy”, the Caribbean’s UN-MSDF Priority area 4 “A Sustainable and Resilient Caribbean” and El Salvador’s UNDAF outcome 4 “Move towards an economy and society environmentally sustainable and resilient to the effects of climate change”. In particular, the project is linked to Mexico’s Direct effect 6 (under outcome 4), as the project is building technical and institutional capacity for integrating adaptation in planning processes, thus strengthening key stakeholders’ “capacities to reverse environmental degradation”. Moreover, the demonstration of Ecosystem-based Adaptation (EbA) approaches reported this year will facilitate the “mainstreaming of environmental sustainability” as indicated. Concerning the Caribbean UN-MSDF priority area 4, the project is contributing to the development of “policies and programmes for climate change adaptation” stated in its 1st outcome, through capacity building with government stakeholders to integrate EbA approaches into planning, policies and regulations. In this reporting period, vulnerabilities and adaptation options have also been identified in the three target cities, thus contributing directly to the previously stated UNDAF, as well as to the 4th effect of El Salvador’s UNDAF outcome 4, seeking to increase “resilient capacities to face disasters, environmental degradation and the negative effects of climate change”. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project is building the capacity of vulnerable communities and various stakeholders in the three target cities to build their resilience to the impacts of climate change. This is done through technical capacity building, identification of vulnerabilities and adaptation options, the demonstration of Ecosystem-based Adaptation (EbA approaches), and the building of a knowledge base on urban EbA. This will contribute towards the achievement of SDG target 13.3 and indicator 13.3.2. The project is also specifically building the technical capacity of government stakeholders to integrate EbA approaches into planning, policies and regulations of the three cities, and will eventually make specific recommendations to this end. This will contribute towards SDG targets 13.2 and 11.A, and indicators 13.2.1 and 11.A.1. |
| --- | --- |

| Implementation Status | FY 2018 | FY 2019 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR |  |  |  |

| Development Objective Rating FY | FY 2018 | FY 2019 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS |  |  |  |
| Despite some administrative setbacks in the process of formalizing cooperation agreements, the project has made substantive progress towards the development objective in this last reporting period. Progress has been very different in the three countries, as a result of the differentiated capacity levels. Mexico and El Salvador have made significant progress in the development of vulnerability assessments, and there is a high level of engagement from key stakeholders that have participated in a number of consultations and capacity building activities. In the case of Jamaica, progress with the vulnerability assessment is not as advanced as a result of the limited cooperation among public agencies and availability of data, and also as a result of the lack of clarity in terms of responsibilities in city planning and development mandates. The development of these vulnerability assessments has provided a very good opportunity to build institutional capacities and institutional coordination in all three project cities. It is clear from the consultation and validation workshops that there is very limited integration of adaptation issues into city planning processes. However, there is an increasing need to consider risk projections and climate change scenarios for the design of infrastructure and new urban areas. Finally, the process of developing the vulnerability assessments has also created an opportunity to start the discussion on potential upscaling needs, strategies and locations. Results from the vulnerability assessments are already being adopted by some stakeholders in their decision-making process. For example, the Environment Department of the municipality of Tlalnelhuayocan, in Mexico, is already using the risk maps developed for the municipality in their environmental impact assessment process for new building projects. Capacity building has been undertaken mainly through the consultation and validation workshops for the vulnerability assessments, where more than 400 people have participated. Regarding the implementation of Ecosystem-based Adaptation (EbA) measures, Mexico and Jamaica have already started with the implementation of rainwater harvesting systems (2 systems each so far), with a twofold objective of: a) decreasing the amount of water that is lost through runoff (reducing flooding risk); and b) ensuring water supply during dry periods in key sites like schools. The capacity to collect water with these types of systems is very relevant for those municipalities with low level of water supply and sanitation systems. El Salvador and Jamaica have also progressed with the reforestation and rehabilitation activities. El Salvador started with the establishment of almost 15,000 lineal meters of vegetated infiltration ditches in 32 hectares of coffee plantations which increases vegetation cover in key areas for water and soil retention and is, at the same time, a key source of income for rural population in the area. With the objective of watershed protection, Jamaica started activities for the reforestation of 7 Hectares of the Hope watershed in April 2019 involving the eventual planting of some 4,200 Caribbean Pine trees and El Salvador constructed 14,117 lineal meters of vegetated infiltration ditches (as part of the 400Ha of slope stabilization with agroforestry) in the upstream areas of the two cities. One key component of this project are the school and urban gardens that also have multiple objectives, including to: a) serve as capacity building centers for students and families on climate change, adaptation and ecosystem-based adaptation, b) serve as a source of food for schools and vulnerable populations in the city; and c) promote alternative resilient livelihoods for vulnerable urban population. School gardens have already been established in 5 schools in El Salvador and 2 in Jamaica where more than 250 students have participated in the set up and related capacity building activities. They will be used as teaching tools for garden construction and maintenance as part of the schools’ agricultural curriculum focusing on the use of Ecosystem-based Adaptation, in Jamaica particularly, which could reach at least 200 students per year. The third component of the project relates to the long-term research strategies that would be key to develop with the objective to generate more scientific knowledge and evidence about ecosystem-based adaptation strategies in urban areas. Research partnerships have already been established both in Mexico and El Salvador including on: a) use of the i-tree platform in an urban park in San Salvador to determine ecosystem services at the individual tree level; b) an assessment of urban trees on sidewalks and streets of San Salvador, with a preparation of a list of suitable trees and their corresponding environmental services; c) economic and social analysis of the production of edible mushrooms as an EbA strategy in Mexico: Case of “Manos Mágicas” women group; and d) Economic valuation of the Gutierrez Barrios urban watershed ecosystem services in Xalapa, Mexico. In Jamaica, portfolios are being prepared for distribution to three universities for them to consider engaging in the long-term research program on EbA. |  |  |  |  |  |

| Implementation Progress Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS |  |  |  |
| The overall management of the project is organized through regular contact between the regional coordinator, national coordinators and project partners. Technical orientations regarding the reporting methodologies or the language of communication (English in Jamaica and Spanish in El Salvador and Mexico) were needed at first, but the learning process on the overall project coordination has led to positive outcomes. The exchange of information between the coordinators and the local project partners can be challenging though, as the complexity of the project (multi-country, multi-faceted) leads to difficult internalization in each city. Continuous dialogue and support from the regional office are provided to address this general issue. As for national progress monitoring and follow up, each country has set up a technical advisory committee that includes the relevant institutions and stakeholders to ensure appropriate guidance and integration with ongoing initiatives and strategies. This has already led to very interesting synergies created in Mexico with the technical team of the municipality and the Technical Institute in Xalapa, and in El Salvador with the University of San Salvador and the municipalities of San Salvador and Antigua Cuscatlan. There has been substantive progress in the project’s implementation process, despite the delays in disbursement and administrative setbacks previously mentioned. These delays led to some adjustments in the calendar of implementation and corresponding budget (mainly for activities in the 2nd component), but these were minor changes that shouldn’t affect project results. The changes in the work plan are scheduled to be regularized in the upcoming year. On another note, political changes in El Salvador resulted in a stable and safe transition, and no other external risks of political nature have been experienced or are expected in the short term in any of the three cities. During this reporting period, consultation processes were conducted in all three cities for validation of the baseline and vulnerability assessments (Jamaica is still pending for the validation workshop). The consultations allowed first to identify the most vulnerable communities and their risk perception, and this analysis then validated the justification of the EbA interventions planned for the project. The results of the vulnerability assessment were shared with decision-makers, resulting in their early integration into the urban planning process in Mexico in particular. The consultations involved numerous stakeholders and revealed that, despite the institutional capacity of most stakeholders, some trainings are required for capacity building on EbA mainstreaming. Some substantive efforts were thus made in terms of dialogue and capacity building in Xalapa especially. There, stakeholders from community management centers, decision-makers of critical urban areas and from the state government were trained in the identification of needs and EbA solutions. Also, a local team of 15 technicians in critical areas was trained on climate vulnerability assessment by using geographic information systems. More capacity building has been identified as necessary in terms of planning instruments (integrated landscape management, urban planning, environmental regulations, etc.). Regarding EbA interventions in Mexico, some changes are currently under study: after some site changes in 2018, EbA interventions planned in a natural protected area called “Molinos de San Roque” are also going to be reconsidered due to a lack of legal permission from the Xalapa municipality. New options and strategies are thus under consideration and should be ready by next year. |  |  |  |  |  |

| Risk Rating | FY 2018 | FY 2019 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | M | M |  |  |  |
| Despite the substantive positive difference from June 2018 in the level of coordination among institutions, data sharing and understanding of the concept of EbA for urban areas, there is still a risk that the overarching project objectives are not fully understood or internalized by national stakeholders because of the project’s multi-faceted, multi-country nature. There are also differences in the capacity and engagement between the three countries, which is already reflected in different levels of progress, and is likely to result in different levels of target achievement and quality. For example, there is a risk to fall short in the results from the vulnerability assessment and in the consultative process to build capacity of stakeholders in Jamaica. Continued capacity building, dialogue and exchanges are being provided by the regional project coordination to minimize the potential impact of these risks on the achievement of project target and overall objectives. The regional team is providing continuous technical support for the development of the vulnerability assessments and supporting the national technical teams to access data from international data sources to carry out the assessments. Through the several consultation and validation workshops that included the participation of the national coordinators, the team is building a strong regional learning process. The information shared between the cities is expected to support overcoming the challenges encountered, through knowledge exchange and learning from other countries’ experiences that could be beneficial in other cities. |  |  |  |  |  |

| Stakeholder engagement | The process for stakeholder consultations and engagement during the implementation phase has included to date: i) initial meetings with national and sub-national government authorities – the MARN, MWLECC and SEMARNAT – and communal authorities during the inception workshops that took place in 2018; ii) consultations with the coordinators of the baseline and partner projects to update baselines and strengthen coordination among the interventions. In some cases, like San Salvador and Xalapa, the baseline projects were already close to completion; iii) consultations with a wide range of stakeholders identified as key for the implementation of the project; iv) consultations with NGOs, local associations and cooperatives through the workshops for design and validation of the vulnerability assessments; and v) consultations with community-based organisations to validate baselines of the project as well as implementation plans and community engagement into the project. MoUs are under way with some of these stakeholders such as the Instituto Tecnológico de Xalapa. It has been challenging to engage stakeholders into the discussions of this project due to the complex and integrated approach it entails. Working with local organizations as partners for execution still requires a significant amount of capacity building efforts on the meaning and implications of ecosystem-based adaptation, ecosystem services and the concept of urban planning with a wider focus than the constructed limits of the cities. The project is being implemented with the support of national organizations as a means to ensure sustainability of results and ownership of the process. The situation is different depending on the country and the existing capacities: Fondo Golfo de Mexico is a very solid organization with years of experience on environmental and climate change projects in the region. It is also linked to a larger national organization, Fondo Mexicano para la Conservación de la Naturaleza, that will serve as a platform to disseminate results of the project at the national and international level. In El Salvador, the project is engaging two national organizations. FUNDASAL has expertise in rural and urban housing, neighborhood improvement, and risk mitigation in urban and rural neighborhoods. The institutional methodological basis methodological basis of FUNDASAL is on community-focused learning-by-doing and mutual aid. They also have presence in various departments of El Salvador. PROCOMES, on the other hand, has experience in urban communities in the metropolitan area of San Salvador. They have also developed projects with the participation of civil society in topics such as risk reduction, food and nutrition security, basic sanitation and environment. One of their main lines of work is to improve the productive value chains, specifically coffee and urban agriculture. In Jamaica, the partner organization is the 4H club that promotes agriculture training among young population as a mean to maintain the link between citizens and the rural environment. With more than 100,000 members at the national level, it is interesting to build the capacity of this organization on climate change adaptation so this approach can be incorporated into their activities and disseminated at the national level. The 4H club is an international organization, which also provides an opportunity to disseminate results from the project at a much wider level. |
| --- | --- |

| Gender mainstreaming | A partnership has been established between UNEP and UN Women to incorporate gender mainstreaming throughout the project implementation cycle, including the development and implementation of a Gender Action Plan and gendered results frameworks in El Salvador and Mexico. The approach is challenging, given that it implies incorporating and validating gender-based elements to the existing project work plan and its corresponding allocated funds. As per the agreement, UN Women is engaged in an ongoing three-step process that is focused on conducting a desk review and developing an initial gender action plan for each country (Mexico and El Salvador), undertaking a field mission to each country, and lastly finalizing and implementing national gender action plans for each country. Under the agreement, the following steps were conducted and finalized during the reporting period: As part of phase 1, an initial draft of the gender action plan was prepared for El Salvador and Mexico based on data and information gathering from the countries, including a comprehensive review of the documentation provided by UN Women and UN Environment as well as stakeholder analysis documentation. As part of phase 2, in order to further expand on the information gathered from the desk review, field missions were sent to the respective countries in March/April 2019, where key stakeholders were consulted in order to refine and specify the project proposal by addressing critical issues raised by the stakeholders. A key component of phase 2 was ensuring the stakeholders were comprehensively consulted comprehensively consulted through dialogues, interviews and feedback sessions for the preparation of the Gender Action Plan for El Salvador and Mexico. |
| --- | --- |

| Knowledge activities and products | Formal knowledge products are under development, although not publicly available yet. Some of these products include: publications of the three vulnerability assessments, and drafts of the protocols for some of the EbA measures. Mexico has drafted factsheets for 3 EbA interventions (green corridors in Xalapa, promotion of production of Macadamia nuts, and implementation of biodigesters). https://www.dropbox.com/sh/ph9e4piy9gxc2zz/AAAtqiiEIV5U3ZJAKDqAk_Mma?dl=0 The UNEP GEF Communications team has supported the team in Mexico to develop a video showcasing the project and its interventions in Xalapa. |
| --- | --- |

| Stories to be shared | El Salvador: The change in practices that we have started with the coffee growers required first to demonstrate the benefits of these practices. The coffee growers used to make holes of 30x30x30 cm next to the coffee plant (called “encajuelado”), whose only benefit is to maintain the humidity of the plant. When they were shown the vegetated infiltration ditches, they did not see the difference compared with the old practice, so they had to be trained by doing several in practice. These are made with dimensions of 30 cm of base by 40 cm of depth by 50 cm of surface with lengths that border the coffee farms. 6 months after starting the construction of ditches, coffee growers see the following benefits, among others: soil moisture retention, nutrient retention, erosion regulation, soil formation. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: To reduce the vulnerability of communities living in three medium-sized Latin American and Caribbean cities to the effects of climate change through the integration of Ecosystem-based Adaptation (EbA) into urban planning in the medium- to long-term. | 1. Total number of direct beneficiaries from the project and % of which are women. | Zero | N/A | At least 194,090 people benefitting from the project (of which at least 50% are women). México: 36,590 people in the Carneros watershed, of which 53% women. Jamaica: - 8,000 residents (2,500 households, of which ~60% are headed by women) in Greenwich Town. - 6,000 students at 4 schools, of which ~55% are women. - 28,000 people in Petersfield district, of which ~60% women. El Salvador: 115,500 people in the Arenal-Monserrat watershed, of which~53% are women. | Mexico: More than 100 people from local government institutions and local organizations have participated in the consultation and validation processes of the vulnerability assessments for the city of Xalapa and the identification of EbA measures. These people have enhanced access to information about climate change vulnerability and the capacity to use and apply that information to decision making process. 810 citizens are benefitting from the installation of rainwater harvesting systems, including 300 students and their families at home. An additional rainwater harvesting system has been installed in the municipal slaughterhouse with an indirect impact on 90,000 people in the municipality. Jamaica: Consultations have gathered over 30 stakeholders; the municipal authority was informed of the projects through a meeting with the Climate Change Division and the Kingston and St. Andrew Municipal Corporation, meetings were held with the Principals of the two schools selected for EbA interventions during this period, and a site visit was done to the Greenwich Fishing Village and sections of Greenwich Town. These three national consultations were undertaken for validation of the baseline and vulnerability assessments to determine the most vulnerable areas in the city of Kingston and included a total of around 90 people who now have a better understanding of the project and EbA interventions. Two rainwater harvesting systems and one urban garden were installed, having the potential to reach at least 200 students per year. The reforestation of 7 Hectares of the Hope Watershed commenced, benefitting a total of 7,000 people with more secure water supply. El Salvador: The implementation of EbA interventions on coffee plantations involved 162 coffee farmers (~23% women) trained on the construction of infiltration ditches. Members of the coffee cooperatives Acoboquerón (68 people) and El Espino (around 500 families) would benefit from these measures. In addition, 5 school gardens in 5 schools within the city were implemented, and 188 students (~50% women) were trained on the construction of school gardens. The total number of students in these 5 schools that can benefit from these gardens exceeds 2,200. Finally, around 5,093 people from different communities of the watersheds of El Triunfo (Cantón El Carmen), Arenal Monserrat (Colonia IVU), La Mascota (CDI - Comunidad Asunción) and San Felipe (Lomas de San Francisco) are benefiting from the EbA interventions on infiltration ditches and sustainable agricultural practices. | MS |
| Outcome 1: Technical capacity of government stakeholders from urban development and natural resource management ministries to integrate EbA into planning, policies and regulations strengthened | 1. Number of relevant government staff within each targeted national and local institution with improved technical capacity to identify, prioritise, plan and implement urban EbA (disaggregated by gender). | Zero | N/A | By project end-point, at least 190 relevant government staff (of which at least 50% are women) within targeted institutions have increased technical capacity to identify, prioritize, plan and implement urban EbA. México: At least 50 people are trained, of which 50% are women. Jamaica: At least 100 people are trained, of which ~50% are women. El Salvador: At least 40 people are trained, of which ~40% are women. | Mexico: At this time, 40 people from 13 community management centers have participated in the process of the vulnerability assessment. 10 decision makers of key areas in the municipalities of Xalapa and Tlalnelhuayocan have been trained in the identification of adaptation needs and EbA solutions. A team of technicians in key areas of the Xalapa and Tlalnelhuayocan municipalities, composed of 15 people, is being trained in climate vulnerability analysis using geographic information systems. At a regional level, a 30-person group of the Veracruz state government were trained in the same topic. Jamaica: Scheduled to start in the next reporting period. El Salvador: 1st EbA workshop composed of a capacity training to understand the interventions and concepts before validating them: 36 people (~42% were women) | S |
|  | 2. Number of technical guidelines developed on urban EbA. | Zero | N/A | At least three sets technical guidelines developed for each city to plan, implement and monitor urban EbA (nine in total). | The vulnerability assessments for EbA in urban areas have been drafted in all three countries, and will form the basis for the technical guidelines. In El Salvador, a proposal has been developed for the technical guidelines. The technical guidelines are a continuous process and draft content has already been produced through the development of the vulnerability assessments. The project will develop these guidelines as a web-based tool that will be updated constantly along the project. All three countries have held consultation and validation workshops (Jamaica still pending validation workshop) to develop the vulnerability assessments. More than 100 people mainly from government agencies have participated in this process. | MS |
|  | 3. Number of policy briefs developed with relevant government stakeholders outlining recommendations for revisions to policies/strategies/plans to integrate EbA | Zero | N/A | At least one set of policy briefs, developed with relevant government stakeholders, produced for each country to guide revision of national and city policies, strategies and plans (in total). | Draft policy briefs have already been developed reflecting the progress on the selection and implementation of EbA measures, and the vulnerability assessment process. These are still not publicly released. Draft documents on barriers and opportunities for integrating EbA into policy and regulatory instruments have been developed in each country (pending completion in Jamaica). | MS |
|  | 4. Number of draft upscaling strategies developed for urban EbA | Zero | N/A | One urban EbA upscaling strategy developed in each country (three in total). | Upscaling strategies to be developed in the last two years of project implementation. Some upscaling opportunities have already been identified through the vulnerability assessments in Mexico and El Salvador. | S |
| Outcome 2: Demonstration of EbA in San Salvador, Kingston and Xalapa to increase the capacity of urban and peri-urban communities to adapt to the effects of climate change. | 1. Number of hectares and kilometres restored by the project using EbA interventions | Zero | N/A | México: - 3.6 km of riparian corridor restored. - 2.8 km of infiltration ditches and 1.67 km of berms built. - 0.20 km connectivity corridor between EbA action gardens built. - 2 km of linear park. - 2 km of concentric circuits, one for cycling and one for walking. Jamaica: - 4,200 trees planted across 44,000 ha to contribute to restoration in the Hope watershed. - 500 meters of dykes. - 2 hectares of the wetland in Greenwich town rehabilitated. - 2,500 meters of permeable pavements and walkways. - 2.3 hectares in May Pen Park, in Kingston, including 400 fruit trees and 1,000 forest trees planted. El Salvador: - 1,000 hectares of sustainable agriculture in the Arenal- Monserrat watershed, which includes the vegetated infiltration ditches on the slope of the San Salvador volcano. - 16 kilometres of riparian forest restored along 4 ravines (4 kilometres each). - 150 hectares of critical ecosystems restored. | Mexico: Activities for the riparian restoration and infiltration ditches and berms will start in 2020, taking advantage on the vulnerability assessment to select the best sites for implementation. Jamaica: Activities for the reforestation of 7 Hectares of the Hope watershed began in April 2019, other activities will start in 2020. There is a contradiction in the project document regarding this activity and the target figure needs to be revised once the vulnerability assessment has been finalized. El Salvador: Sustainable agriculture: 32 hectares of restoration in the coffee plantation area of the basin with coffee plants. This is part of the 600 Ha of coffee plantations to be recovered. Also 14,117 lineal meters of vegetated infiltration ditches have been constructed as part of the 400Ha of slope stabilization with agroforestry. | MS |
|  | 2. Number of protocols developed to guide implementation of EbA in San Salvador, Kingston and Xalapa | Zero | N/A | At least one set of EbA protocols developed for each pilot city (three in total) | México: A rainwater harvesting protocol with EbA integrated was developed using the experience of the academia and the CDMX experience with “Isla Urbana”. A brief protocol was developed to offer alternative livelihoods in the periurban zone of Xalapa, taking into account the ecosystem services reported on the vulnerability assessment. https://www.dropbox.com/sh/cbn6u4jwn0ms49m/AAB8Bk7SZ0FOvD7JxnCPWxuwa?dl=0 El Salvador: 4 protocols developed considering related risks, ecosystems where these interventions will be implemented, descriptions and methodologies, environmental and social benefits, co-benefits, costs, impact measurements and reporting indicators: - Vegetated infiltration ditches - Urban food gardens - Fruit tree harvesting - Riparian forest restoration https://drive.google.com/open?id=1vG5khlnnjFo_FkbcaiCgP6sZ_4TJg3kD Jamaica: A rainwater harvesting protocol with EbA integrated is under development using the draft rainwater harvesting protocol of the Government of Jamaica. Protocols for urban container gardens and beekeeping have also been developed, and are to be revised to include EbA. | S |
|  | 3. Number of water storage and management systems established through the project | Zero | N/A | México: - 1 artificial wetland at the Telesecundaria School Rafael Hernández Ochoa. - 10 rainwater harvesting systems on the roof tops of 8 schools and 2 public buildings Jamaica: - 3 detention ponds. - 4 rainwater harvesting systems installed at schools. El Salvador: - 30 water storage points h=1 meter. - 10 rainwater harvesting systems for selected schools. - 1 rainwater harvesting system for 1 selected community. | Mexico: 2 rainwater harvesting systems have been installed in one school and one public building within the most vulnerable areas in Xalapa. It is foreseen that a set of 3 additional rainwater systems will be installed at the end of 2019. Jamaica: 2 rainwater harvesting systems installed in September 2019 in St Andrews Technical High School and Kingston Technical High School. 1 additional rainwater harvesting system will be installed by November 2019 in Camperdown High School and the final one in 2020. El Salvador: Activity scheduled for next reporting period. At the end of 2019, rainwater harvesting systems will be designed, and 10 schools and 2 communities selected for their implementation. | S |
|  | 4. Number of waste management systems implemented in El Salvador. | El Salvador: Zero | N/A | El Salvador: 2 ecological sanitation systems at 2 schools to improve management of grey water and sewage. | El Salvador: Activity scheduled for next reporting period. At the end of 2019, the ecological sanitation systems will be designed and 2 schools selected for their implementation. | MS |
|  | 5. Number of climate resilient alternative livelihoods demonstrated at intervention sites through providing equipment, training and technical support. | Zero | N/A | México: - At least 10 food gardens to demonstrate potential climate-resilient livelihoods. - 20 demonstration plots for commercial mushroom production - 8 agricultural start-up kits at 8 schools Jamaica: - 1 urban garden per school for 2 schools and 1 community garden. - 400 fruit trees per school at 2 schools. - 1 beekeeping unit in the community garden. El Salvador: - 10 urban gardens in 10 schools. - 10 agricultural start-up kits at 10 schools in the Arenal Monserrat area. | Mexico: 5 best practices on agroforestry and 5 edible mushroom demonstration modules currently underway (10 different sites).The mushroom production will be located in the peri-urban area, which used to be agricultural areas; this area plays an important role to prevent the expansion of the urban area. Jamaica: One urban garden established in 2019; Two urban gardens will be established at 1 school and 1 community location in 2020. El Salvador: 5 urban gardens established in 5 schools 5 agricultural start-up kits at 5 schools in the Arenal Monserrat area. | S |
|  | 6. Number of people trained on implementing and maintaining the EbA interventions and climate resilient livelihoods. | Zero | N/A | Mexico: At least 50 students (of which at least 50% women) per school from 10 schools will be trained on using agricultural start-up kits as well as development and maintenance of the urban gardens Jamaica: At least 50 students (of which at least 50% women) per school from 4 schools will be trained on the development and maintenance of the urban gardens. At least 40 people are trained on bee-keeping. El Salvador: Al least 50 students (of which 50% women) per school for 10 schools will be trained on using agricultural start-up kits as well as development and maintenance of the urban gardens. | Mexico: Together with the local government agroecology department, best practices in urban food gardens, benefits and co-benefits were identified. The students’ training will start in 2020. Jamaica: Scheduled to start in next reporting period. El Salvador: 188 students at 5 schools of which ~50% are women were trained on implementing urban gardens | MS |
| Outcome 3 Knowledge and awareness of urban EbA interventions strengthened in El Salvador, Jamaica and Mexico, and throughout the LAC region | 1. Number of communication strategies for urban EbA developed. | El Salvador: Zero Jamaica: One (national) Mexico: Zero | N/A | One communication strategy developed for each city (three in total) with specific guidelines for targeting different groups. | A regional strategy is under development, with the participation of the three countries, and the development of the local strategies is running at the same time. Jamaica: A national climate change communication strategy was developed to improve public awareness and public education with funds from the European Union Global Climate Change Alliance, (EUGCCA). This strategy will be reviewed and updated to include EbA as the main focus. | S |
|  | 2. Number of communication tools developed and implemented – with specific focus on different groups (e.g. men, women, the youth, the elderly, persons with disabilities) – to increase awareness of government staff and urban communities on the benefits of EbA. | Zero | N/A | At least 15 tools developed in total. Mexico: At least 12 tools developed (including flyers, better practices manuals, short film signage, etc.), at least 1 of which focused specially on women. Jamaica: At least 4 tools developed, at least 1 of which is focused specifically on women. El Salvador: At least 3 tools developed, at least 1 of which is focused specifically on women. | Mexico: A short documentary on the project is currently under development Jamaica: Activities to start in next reporting period. El Salvador: One brochure about Urban EbA project in San Salvador, 3 banners about urban gardens, ecosystem services and EbA project and workshop notebooks | MS |
|  | 3. Number of MSc research reports developed on the benefits of urban EbA with a particular focus on gender. | Zero | N/A | At least 6 reports, 3 of which include specific reference to gender-specific aspects of urban EbA México: 2 reports Jamaica: 2 reports El Salvador 2 reports | Mexico: The two research reports are underway. Report 1: Economic and social analysis of the production of edible mushrooms as an EbA strategy: Case of “Manos Mágicas”, women group. Report 2: Economic valuation of the Gutierrez Barrios urban watershed ecosystem services. Xalapa, Veracruz, Mexico Jamaica: Scheduled to start in next reporting period El Salvador: Two topics have been selected with pre-grade students from National University of El Salvador –– UES: 1. Use of the i-tree platform in an urban park emphasizing ecosystem services; and 2. An assessment of urban trees on sidewalks and streets of San Salvador, with a preparation of a list of suitable trees and their corresponding environmental services. | S |
|  | 4.- Number of educational toolkits – for primary and secondary schools – developed on best EbA practices. | Zero | N/A | At least 7 educational toolkits developed in total. México: 4 toolkits developed Jamaica: 2 toolkits developed El Salvador: 1 toolkit developed | Mexico: 1 educational toolkit focused on rainwater harvesting is underway and will be developed by the end of 2019. Jamaica: Scheduled to start in next reporting period El Salvador: A toolkit on urban garden and waste management will be finished at the end of 2019. | MS |
|  | 5.- Number of knowledge- sharing products/events supported by the project to share lessons learned using existing regional and global networks. | Zero | N/A | At least three knowledge- sharing reports/events to share lessons learned through implementing EbA disseminated through regional networks (including REGATTA). | This activity is planned for the next years for all three countries. | MS |

Overall rating of project progress towards meeting project Result(s)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The project has made considerable progress towards the project results in this last reporting period, in particular in terms of the strengthening of technical capacity to integrate EbA in planning processes (Outcome 1). The vulnerability assessment processes undertaken in each of the three cities (under Component 2) have provided an excellent platform for raising awareness and understanding of the concept of EbA in an urban context. They have also succeeded in convening relevant stakeholders and planning institutions, and in building capacity for the identification of climate change challenges and possible adaptation solutions in the cities, as well as for institutional coordination. At the same time, there are significant differences between the three cities in progress, which are related to different levels of capacity and engagement. Furthermore, the integration of EbA approaches into policies and planning processes and the demonstration of EbA approaches (Outcome 2) are still in early stages, and somewhat lagging behind planned progress at this stage. Main reasons for these challenges relate to the fact that the project is very ambitious in its anticipated results, considering the multifaceted nature of its interventions and the regional (multi-country) approach, which require extensive coordination both within the three cities and between the three project countries. There have also been some challenges during the development of the vulnerability assessments and validation of the interventions specified in the CEO Endorsement due to the complexity of the topic the project is dealing with. It has been necessary to build the capacities of the technical teams through discussion tables, workshops to develop participatory vulnerability assessments, and the mapping of actors. |

Risks to the delivery of results

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Steering Committee and/or other project bodies do not meet frequently enough to provide effective direction/inputs at the national level. | The technical advisory committees defined at the national level will meet at least three times per year to ensure adequate guidance to the project. |
|  | Some lack of clarity in terms of administrative processes and modalities of engagement for national partners have created some delays on overall timetable. | Clear modalities and processes have been established and timelines for administrative processes have been clarified. |
|  | Consultation and participation processes seem strong but are missing some groups or relevant partners in each country. | The map of actors for the project is being strengthened in each country to ensure participation of all key partners and stakeholders. |
|  | There are large variations in capacity and engagement between the three countries, which is already reflected in different levels of progress, and is likely to result in different levels of target achievement and quality. | The project Regional Coordinator will identify any major delays or issues in the delivery of results, and corrective actions (e.g. additional support needed) will be identified in consultation with the country teams and the Task Manager. |
|  | The project scope and targets are very ambitious, considering the funding and timeframe available. As such, some departures from the original workplan are necessary, in order to make most efficient use of resources. For example, the delivery of some outputs has been combined under a single process. However, there is also a need to ensure that the originally-planned targets are still on track to be met, or that revisions to targets are identified and agreed on if necessary. | The project Mid-Term Review (MTR) is planned for early 2020. This will be an opportunity to revisit the targets and the project approach, and to identify and discuss any possible revisions that may be needed. |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 (%) | Implement-ation status as of 30 June 2019 (%) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Technical capacity of government stakeholders from urban development and natural resource management ministries to integrate EbA into planning, policies and regulations strengthened. |  |  |  |  |  |

| Output 1.1: Policy briefs developed to outline recommendations for revisions to policies, strategies and plans – including budget allocations – to integrate EbA into urban planning and management of natural resources | Q4 2018 | Mexico: 0 Jamaica: 0 El Salvador: 30 |  | Mexico: 40 Jamaica: 30 El Salvador: 30 | Mexico: A draft document on barriers and opportunities for integrating EbA into policy and regulatory instruments has been developed. A map of actors for the mainstreaming of EbA into urban planning has been drafted. Jamaica: Draft policy brief is being elaborated as well. El Salvador: A draft document on barriers and opportunities for integrating EbA into policy and regulatory instruments has been developed. | MS |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1.2: Technical guidelines on planning and implementing EbA in urban areas developed for relevant government stakeholders, private sector and targeted communities | Q4 2019 | Mexico: 0 Jamaica: 0 El Salvador: 0 |  | Mexico: 30 Jamaica: 0 El Salvador: 30 | Mexico: The vulnerability assessments for EbA in urban areas have been drafted and will form the basis for the technical guidelines. Jamaica: Scheduled to be drafted by next reporting period. El Salvador: An initial draft of technical guidelines for urban EbA interventions has been developed based on the description of the consultative process undertaken for the development of the vulnerability assessment. | MS |  |
| Output 1.3: Training provided to local government authorities and relevant private sector stakeholders in San Salvador, Kingston and Xalapa on implementing urban EbA. | Q1 2021 | 0 |  | Mexico: 10 Jamaica: 0 El Salvador: 0 | Mexico: 40 people from 13 community management centers and 10 decision makers of key areas in the municipalities of Xalapa and Tlalnelhuayocan have been trained in the identification of adaptation needs and EbA solutions. A team of technicians in key areas of the Xalapa and Tlalnelhuayocan municipalities, composed of 15 people, is being trained in climate vulnerability analysis using geographic information systems (Qgis). At a regional level, a 30-persons group of the Veracruz state government were trained in the same topic. Jamaica: Scheduled to start in next reporting period El Salvador: Training on urban EbA scheduled for the end of 2019 for local government authorities. | S |  |
| Output 1.4: Strategies developed to upscale and sustain EbA interventions in El Salvador, Jamaica and Mexico | Q2 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 |  | Mexico: 0 Jamaica: 0 El Salvador: 0 | Upscaling strategies to be developed in the two last years of project implementation. El Salvador: A water quality profile of a principal ravine of Arenal Monserrat watershed has been done in dry season. This activity contributes to the National Drainage Plan Drainage Plan to ensure there is baseline information on water quality for their future climate change projections. | S |  |
| Outcome 2: Demonstration of urban EbA interventions in selected cities to enhance climate-resilience |  |  |  |  |  |  |  |
| Output 2.1: Assessments of climate change hazards, adaptation needs, and scenario maps of resource availability produced for each pilot city. |  | Q3 2018 | Mexico: 10 Jamaica: 5 El Salvador: 5 | Mexico: 80 Jamaica: 50 El Salvador: 95 |  | The activity was implemented as a collaboration between an international partner (WERN) and national partners and experts in each of the three countries. The exercise of vulnerability assessments has become a very interesting tool to enhance the discussion among stakeholders and it will continue to be strengthened along the duration of the project. Mexico: The vulnerability assessments and maps have been developed, and are currently under validation process with stakeholders. Jamaica: Initial results for the vulnerability assessment have been produced with a group of national experts and presented to stakeholders in an initial workshop. It is currently under review for validation in a second national workshop. El Salvador: Vulnerability assessment and maps have been produced, and will be finalized and validated by July. | S |
| Output 2.2: Protocols for city-specific EbA interventions developed |  | Q2 2018 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 3030 Jamaica: 20 El Salvador: 40 |  | Mexico: Protocols for rainwater harvesting systems, edible mushrooms and agro-silvo-pastoral activities are already developed. Jamaica: Protocol for rainwater harvesting systems, urban container gardens and beekeeping developed, and to be revised to include EbA. El Salvador: 4 protocols developed: vegetated infiltration ditches, food urban gardens, fruit trees harvest and riparian forest restauration. Project includes 6 more modules still to be developed: rainwater harvesting system in schools and communities, coffee planting restauration, ecological sanitation system in school, infiltration dills and critical ecosystem restoration. | S |
| Output 2.3: Relevant urban EbA interventions demonstrated in San Salvador, Kingston and Xalapa at the household, urban landscape and urban catchment scale using the developed EbA protocols |  | Q3 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 1515 Jamaica: 1515 El Salvador: 10 |  | México: 2 rainwater harvesting systems currently in implementation stage. Jamaica: 2 rainwater harvesting systems currently in implementation stage. Activities for the reforestation of 7 ha of the Hope watershed began in April 2019. El Salvador: 32 hectares of restoration within a coffee plantation has been implemented, as well as 14,117 lineal meters of vegetated infiltration ditches. Areas where riparian vegetation restoration will be implemented in July have been identified. | MS |
| Output 2.4: Additional climate-resilient livelihoods from EbA promoted through training and demonstration in community spaces |  | Q3 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 3030 Jamaica: 10 El Salvador: 3030 |  | Mexico: 5 best practices on agroforestry and 5 edible mushroom demonstration modules currently under way and will end in 2019 Jamaica: One urban garden established in 2019 in Kingston High School; Two urban gardens will be established at 1 school and 1 community location in 2020. El Salvador: 5 urban gardens in 5 schools have been established. Also, areas for planting fruit trees in the watershed of Arenal Monserrat have been identified. 5 agricultural start-up kits at 5 schools in the Arenal Monserrat area. |  |

| Outcome 3: Knowledge of urban EbA interventions strengthened in El Salvador, Jamaica and Mexico as well as throughout the LAC region |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output 3.1: Communication strategies developed to collate and disseminate knowledge on urban EbA | Q1 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico:15 Jamaica: 15 El Salvador: 15 | A communication expert is already part of the team and communication strategies are under development at the regional and national levels | S |
| Output 3.2: Public awareness communication materials developed and shared with decision-makers, community members and identified stakeholders | Q1 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 10 Jamaica: 0 El Salvador: 15 | Mexico: A short documentary on the project is currently under development El Salvador: The project has produced some communication materials like a brochure, banners and workshop notebooks. | S |

| Output 3.3: A long-term research program established on the benefits and cost-effectiveness of urban EbA interventions in the three pilot cities | Q3 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 15 Jamaica: 10 El Salvador: 15 | Mexico: Two research reports are underway. Report 1: Economic and social analysis of the production of edible mushrooms as an EbA strategy: Case of “Manos Mágicas”, women group. Report 2: Economic valuation of the Gutierrez Barrios urban watershed ecosystem services. Xalapa, Veracruz, Mexico An agreement is under development with the Instituto Tecnológico de Xalapa to develop the policy briefs for the project and to install some of the EbA measures in their campus as there is an interesting opportunity for training and dissemination of results. The project is also providing advice for the development of a sustainability MSc course. Jamaica: There are 3 portfolios under development for the University of West Indies, University of Technology and Northern Caribbean University El Salvador: Two topics for research reports have been selected with pre-grade students from the National University of El Salvador (UES). A Memorandum of Understanding between UES, UN Environment and FUNDASAL is pending | S |
| --- | --- | --- | --- | --- | --- |
| Output 3.4: Educational toolkits detailing lessons learned and good EbA practices developed and shared with local, sub-national, national and regional authorities | Q4 2020 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 10 Jamaica: 0 El Salvador: 0 | Mexico: 1 educational toolkit focused on rainwater harvesting underway, to be finalized by the end of 2019. Jamaica: Scheduled to start in the next reporting period El Salvador: A toolkit about urban garden and waste management will be finished at the end of 2019 | MS |
| Output 3.5: Knowledge generated by the SCCF-financed project – including lessons learned – shared through web-based portals within the Global Adaptation network, including REGATTA | Q3 2021 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Mexico: 0 Jamaica: 0 El Salvador: 0 | Activities not yet started. | MS |

Overall project implementation progress :

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Most of the administrative delays (legal agreements and payments to partners) and coordination challenges that resulted in a prolonged inception period have been successfully addressed. The overall management of the project is organized through regular contact between the regional coordinator, national coordinators and project partners. The exchange of information between coordinators and local project partners can be challenging, as many stakeholders at the national level have a limited overview of the overarching project objectives because of the project’s multi-faceted, multi-country nature. Continuous dialogue and support from the regional office are provided to address this general issue. As for national progress monitoring and follow up, each country has set up a technical advisory committee that includes the relevant institutions and stakeholders to ensure appropriate guidance and integration with ongoing initiatives and strategies. The past administrative delays led to some adjustments in the calendar of implementation and corresponding budget (mainly for activities in component 2), but these were relatively minor changes that shouldn’t affect project results. The project has made considerable progress in implementation in this reporting period. In particular, the vulnerability assessments undertaken through consultative processes in the three cities (under Component 2) have provided an overarching approach that has, in addition to paving the way for the demonstration of EbA approaches, also enabled progress to be made in activities under Component 1 (in particular the development of technical guidelines and the provision of training and capacity building). The timeliness and quality of the vulnerability assessment processes have, however, varied between the cities, due to differences in capacity and engagement. Some of the other project activities are also somewhat delayed in their level of implementation, for example the development of policy briefs with recommendations for revisions to policies, strategies and plans. |

Risks in implementation

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| National Coordinators and stakeholders at the national level have a limited overview of the overarching project objectives because of the project’s multi-faceted, multi-country nature. | The development of technical capacities will be strengthened through exchanges with other initiatives, organization of webinars and development of training materials. | National project coordinators | Capacity building sessions and trainings for stakeholders planned for 2020. |
| Delay in the process of the vulnerability assessments in Jamaica due to the limited coordination among technical experts and limited understanding of the concept of Ecosystem based Adaptation | The validation workshop for the vulnerability assessment will need to be delayed in order to give some additional time to develop this assessment in a more solid manner. The coordinator in Jamaica will be participating in the validation workshop in Mexico to gain understanding of the consultative process and applications of the results. | National coordinator, national technical advisory committee | Participation in consultation in Mexico (August 2019). Continuation with the further development of the vulnerability assessment (Aug – Dec 2019). |
| Administrative delays with legal agreements and payments to partners | The timeframe considered to formalize new legal agreements needs to increase and the new agreements with the national partners that will start from January 2020 will be drafted between August and October 2019. | Regional coordinator/Regional office/National coordinators | August – December 2019 |
| Issues with permissions to intervene in some areas identified in the project document (Santuario de las Garzas in Mexico, Arenal Monserrat in El Salvador, Hope Watershed in Jamaica) | Arranging permissions with the relevant institutions (National authorities in Mexico and El Salvador, and Forestry department in Jamaica) | National coordinators | End of 2019 |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| National Coordinators and stakeholders at the national level have a limited overview of the overarching project objectives because of the project’s multi-faceted, multi-country nature. | A detailed plan and clear description of roles and responsibilities will be developed to ensure that all stakeholders are well appraised of the project across all three countries. | Further than the clear definition of roles and responsibilities, the development of technical capacities will be strengthened through exchanges with other initiatives, organization of webinars and development of training materials. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Poor coordination among project stakeholders because of language and geographical barriers. | The National Coordinator within each NCU will be responsible for ensuring appropriate coordination among project partners – particularly with the regional coordinator at ROLAC – and that GEF standards are met. Formal and informal communication and reporting functions between national and regional committees will be undertaken in both English and Spanish. | Participation of national coordinators in the national consultations of the other countries will be ensured as long as the budget allows, to ensure cross learning and coordination among the three countries. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Limited inter-sectoral data sharing. | The existing cross-sectoral committees and mainstreaming mechanisms in each country will be used to promote communication and information sharing between sectors. Information technologies and telecommunication systems selected will be those suited to the local context and which do not restrict the transfer and communication of information. | The use of open data will be maximized to minimize problems with data sharing. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | Despite the substantive positive difference from June 2018 in the level of coordination among institutions, data sharing and understanding of the concept of EbA for urban areas, there is still a risk that the overarching project objectives are not fully understood or internalized by national stakeholders because of the project’s multi-faceted, multi-country nature. There are also differences in the capacity and engagement between the three countries, which is already reflected in different levels of progress, and is likely to result in different levels of target achievement and quality. For example, there is a risk to fall short in the results from the vulnerability assessment and in the consultative process to build capacity of stakeholders in Jamaica. Continued capacity building, dialogue and exchanges are being provided by the project coordination to minimize the potential impact of these risks on the achievement of project target and overall objectives. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| e | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM: Roles and responsibilities were well defined and understood in the first initial meeting – it has been evolving positively with activities being implemented. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The management structure, including roles and responsibilities, have been well established. |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | x |  |  |  |  |  | PM: There´s regular contact with regional coordinator and project partners. There’s however a wish for the technical project committee to meet more to improve the governance of the project in Mexico. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The Project Steering Committee has not had an active role in project oversight or guidance. The national technical committees have potential for strengthening country-level governance of the project, as well as for facilitating stakeholder engagement and synergies. |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM: Communication is fluid with regular meetings (through conference calls, emails, telephone, face to face with local partners). Language is sometimes a barrier (Spanish in El Salvador and Mexico, English in Jamaica) but efforts are done regularly to mitigate this. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: There seems to be regular and largely fluid communication within the project team. |  |  |  |  |  |  |
| Workflow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | x |  |  |  |  | PM: Delays in disbursements’ receipt to IPs were experienced in the 3 countries. This led to some delays or changes in activities / work plan. Despite this, a regularization in the project results is expected in the upcoming year. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Administrative delays with recruitments, legal instruments and funds transfers have resulted in some delays. |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | x |  |  |  |  |  | PM: Co-financing is being monitored by the National Coordinators. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The overall status of co-financing realized to date needs to be updated. |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | x |  |  |  |  | PM: Some adjustments in the budget are being done, mainly for activities in the 2nd component (due to issues with CEO endorsement for the riparian vegetation restauration in San Salvador, and above-mentioned delays in budget disbursement to IPs). Budget reallocation should lead do minor changes. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Minor budget reallocations will need to be processed. |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | x |  |  |  |  |  | PM: Funds are correctly managed and transparently accounted for with the IPs in each country. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Financial management is transparent. There have been some delays with financial reporting. |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | x |  |  |  |  |  | PM: First reports (technical and financial) needed the support of National and Regional Coordinator and administrative specialist of UNEP/ROLAC, as there was no prior example to base them on. The quality of the analysis and implementation issues is thus progressing. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Substantive reports have been of timely and adequate, although the inputs received from different countries have been of varying quality. |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | x |  |  |  |  |  | PM: There is a good participation process with stakeholders in all 3 cities, with some difficulty encountered in Jamaica due to time limits and methodology issues. New partnerships are being developed: national coordinators are preparing MoUs with some institutional actors. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Stakeholder engagement has been clear in e.g. the vulnerability assessment processes. There is a need to build on this to further strengthen and broaden stakeholder engagement in all cities, as it’s a critical factor in project success. |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | x |  |  |  |  | PM: Communication strategies are being developed and stakeholders are strongly interested. However, the project’s objectives, activities and results should be transmitted to more than stakeholders, and as the concepts is rather new, there is a need for a more comprehensive communication strategy to maintain the momentum of the project in media, stakeholders and other audiences. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Considering the multi-faceted nature of the project and the lack of familiarity with the concepts around ecosystem-based adaptation, communication activities need to be strengthened, |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long-term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  |  |  |  |  | x | PM: The project includes an upscaling strategy, but there needs to be more time to detail it. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The longer-term vision and upscaling strategy are still to be developed. They are of crucial importance considering the pilot / demonstration nature of the project. |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | x |  |  |  |  |  | PM: EbA interventions are based on well-established technologies. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Project interventions are based on well-established EbA approaches, although it is testing them in a less conventional (i.e urban) context |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | x |  |  |  |  |  | PM: No political involvement nor political interference to be reported. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: No comment |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | x |  |  |  |  |  | PM: Even though there were some political changes (in El Salvador), political context is stable and safe, and no political issues are expected in the short term. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Despite some political changes, the political context has been stable and safe to date |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | x |  |  |  |  | PM: Some environmental conditions were identified in all countries as presenting potential risks to some activities, but they are known and understood |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: There is some risk of environmental and climate conditions affecting project implementation |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | x |  |  |  |  | PM: Due to uncontrolled urban development, some sites were changed in 2018. However, new options and strategies are planned. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Land-use, zoning and development pressures have necessitated the reconsideration of certain project interventions and sites. |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | x |  |  |  |  | PM: Despite the institutional capacity of most stakeholders, some trainings will be required for capacity building on EbA mainstreaming, especially regarding planning instruments (integrated landscape management, urban planning, environmental regulations, etc.) |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Some further training and capacity building is needed to improve capacity for EbA mainstreaming |  |  |  |  |  |  |
| Others, please specify: Lack of permissions for EbA intervention in Mexico |  |  |  |  | x |  |  |  |  | PM: Regarding the activity “2.3.3. Implement appropriate EbA interventions in Fernando Barrio Guttierez in Xalapa” there is an activity in a natural protected area called “Molinos de San Roque” that is Subnational government property and the Xalapa Municipality has no permission to implement the EbA intervention. See risk mitigation plan for more details. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: As above. |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| Medium | Mexico: Regarding the activity “2.3.3. Implement appropriate EbA interventions in Fernando Barrio Guttierez in Xalapa” there is an activity in a natural protected area called “Molinos de San Roque” that is Subnational government property and the Xalapa Municipality has no permission to implement the EbA intervention. | The EbA intervention can’t be implemented at that site | Alternative site to implement the intervention must be identified by using the results of the Vulnerability Assessment, with special attention to the main intention of the original EbA intervention. | The national coordinator, together with the local authorities and guidance from regional coordinator | 1st quarter of 2020 |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| Medium | Medium |  |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.