UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1. PROJECT IDENTIFICATION

# 1.1. Project detail1. IDENTIFICATION

| Identification Table |  |  | GEF ID.: 9145 | UNEP Umoja no.: SB-009921 |
| --- | --- | --- | --- | --- |
|  |  |  | UNEP SMA IPMR ID: 37070 | UNEP Grant ID: S1-32GFL-000616 |
|  |  |  | Project Short Title: SC South Africa |  |
| Project Title |  |  | Building a resilient and resource-efficient Johannesburg: Increased access to urban services and improved quality of life. |  |
| Duration months | Planned |  | 60 months |  |
|  | Age |  | 72 months |  |
| Project Type |  |  | Full Size Project / Child Project |  |
| Parent Programme if child project |  |  | Sustainable Cities Integral Approach Pilot (GEF-6) |  |
| Project Scope |  |  | National |  |
| Region |  |  | Africa |  |
| Countries |  |  | South Africa |  |
| GEF Focal Area(s) |  |  | Climate Change Mitigation |  |
| GEF financing amount |  |  | US$ 8,093,171 - UNEP: US$ 3,999,296 - DBSA: US$ 4,093,875 |  |
| Co-financing amount |  |  | US$ 124,439,330 |  |
| Date of CEO Endorsement/Approval |  |  | 8 May 2017 |  |
| UNEP Project Approval Date (on Decision Sheet) |  |  | 23 November 2017 |  |
| Start of Implementation (PCA entering into force) |  |  | - UNEP: 12 March 2018 - DBSA: 12 March 2017 |  |
| Date of Inception Workshop, if available |  |  | 13 May 2019 |  |
| Date of first disbursement |  |  | - UNEP: 7 June 2018 - DBSA: 30 June 2021 |  |
| Total disbursement as of 30 June 2025 |  |  | - UNEP: US$ 2,640,116 - DBSA: US$ 1,567,394.73 |  |
| Total expenditure as of 30 June 2025 |  |  | - UNEP: US$ 2,336,307 - DBSA: US$ 435,657.35 |  |
| Midterm undertaken? |  |  | Yes |  |
| Actual Mid-Term Date, if taken |  |  | 31 July 2023 |  |
| Expected Mid-Term Review Date |  |  | 31 March 2023 |  |
| Completion Date |  | Planned-Original PCA | 31 August 2022 |  |
|  |  | Revised-Current PCA | UNEP: 30 June 2026 (PCA amendment 3) |  |
| Expected Terminal Evaluation Date |  |  | 31 December 2026 |  |
| Expected Financial Closure Date |  |  | 30 June 2027 |  |

# 1.2. Project description

Project Objective: The project will foster city level resilience, resource efficiency, emission reductions and other co-benefits through area-based pilot demonstrations, systems analysis (food) and improved integrated planning. The project is organized around the following 5 expected outcomes: - Outcome 1 - Eco Districts: CoJ test eco-district prototypes to set improved environmental standards for Corridors of Freedom (led by UNEP) - Outcome 2 - Social Housing: CoJ adopts gender sensitive and resource efficiency guidelines for improved sustainability of social housing (led by UNEP) - Outcome 3 - Food resilience: Emerging urban farmers increasingly implement more environmentally sustainable food security solutions (led by UNEP) - Outcome 4 - Biodegradable Waste: CoJ adopts an integrated biodegradable waste management strategy and has pre-investment documents to mobilise finance to implement the strategy (led by DBSA) - Outcome 5 - Evidence based planning: Enhanced capability of CoJ in evidence-based policy and strategy making (led by UNEP) Executing Agency: City of Johannesburg

# 1.3. Project Contacts

| Division(s) Implementing the project | Climate Change Division, Mitigation Branch, GEF Climate Mitigation unit, UNEP |
| --- | --- |
| Name of Lead implementing Agency | Development Bank of South Africa (DBSA) |
| Name of co-implementing Agency | United Nations Environment Programme (UNEP) |
| Executing Agency(ies) | City of Johannesburg |
| Names of Other Project Partners | JOSHCO |
|  | JDA (Johannesburg Development Agency) |
|  | EnergiDrop (DBSA Oversight partner) |
|  | University of Johannesburg |
|  | South African Cities Network (SACN) |
|  | South African Local Government Association (SALGA) |
|  | City Power |
|  | Social Housing Regulatory Authority |
|  | South African Organic Sector Organization |
|  | Environmental & Infrastructure Service Department |
|  | Provincial Department of Agriculture and Rural Development |
|  | National Department of Agriculture, Land Reform and Rural Development |
|  | Johannesburg Fresh Produce Market |
|  | Johannesburg City Parks and Zoo |
|  | Metrobus |
|  | Pikitup |
| DBSA Portfolio Manager(s) | Muhammed Sayed |
| DBSA Task Manager(s) | Mookho Mathaba |
| DBSA Budget/Finance Officer | Aubrey Maredi |
| DBSA Support/Assistants | Lesedi Letlhogile and Deepesh Govan |
| UNEP Portfolio Manager(s) | Asher Lessels |
| UNEP Task Manager(s) | Julien Lheureux |
| UNEP Budget/Finance Officer | Fatma Twahir |
| UNEP Support/Assistants | Kerubo Moseti |
| EA Manager/Representative (Project Lead, COJ) | Eric Raboshakga |
| EA Project Manager | Thandeka Mlaza-Lloyd |
| EA Finance Manager | Bennie van der Merwe |
| EA Communications Lead, if relevant | N/A |

# 2. OVERVIEW OF PROJECT STATUS

2.1 UNEP PoW and UN

| UNEP Current Subprogramme(s) | Climate stability: Countries increasingly transition to low-emission economic development pathways and enhance their adaptation and resilience to climate change |
| --- | --- |
| PoW Indicator(s) | Indicator (i) Number of national, subnational and private sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support. Indicator (ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support. |
| UNEP previous Subprogramme(s) | N/A |
| UNSDCF / UNDAF linkages | The project is aligned with Strategic Priority No. 4 (Climate resilience and sustainably managed natural resources) of South Africa’s UNSDCF 2020-2025 |
| Link to relevant SDG Goal(s) | SDG-11. Make cities and human settlements inclusive, safe, resilient and sustainable. SDG-13. Take urgent action to combat climate change and its impacts |
| Link to relevant SDG Target(s) | 11.2 By 2030, provide access to safe, affordable, accessible and sustainable transport systems for all, improving road safety, notably by expanding public transport, with special attention to the needs of those in vulnerable situations, women, children, persons with disabilities and older persons. 13.2 Integrate climate change measures into national policies, strategies and planning. |

2.2. GEF Core Indicators:

| Indicators | Targets – Expected Value |  |  | Materialized to date |
| --- | --- | --- | --- | --- |
|  | Mid-term | End-of-project | Total target |  |
| Core Indicator 6.2 - Emissions avoided Outside AFOLU | N/A | Direct: 3,291,577 tCO2eq Indirect: 1,113,658 tCO2eq (20 years post project) | Direct: 3,291,577 tCO2eq Indirect: 1,113,658 tCO2eq (20 years post project) | Given the nature of the project’s interventions, the project team will only be able to make projections on the estimated GHG emission reductions at the time of the project’s technical completion. These estimations will be communicated in the GEF Tracking Tool, along with the project’s Terminal Evaluation report. |

2.3. Implementation Status and Risk

|  | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PIR # | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | Final |
| Rating towards outcomes (section 3.1) | S | S | S | S | S | S | S |  |
| Rating towards outputs (section 3.2) | S | MS | S | S | S | S | S |  |
| Risk rating (section 3.3) | L | L | M | M | M | M | M |  |

Summary on Progress towards outcomes Outcome 1 (Eco-Districts): The outputs contributing to this outcome have been completed. CoJ has approved its Green Building Policy with new standards for all new buildings and is demonstrating its application in the design of 5 clinics, in accordance with the new standards. Of the 5 clinics, 4 are currently under construction. Institutionalization of the body of work has been on-going and will continue. This has been done through the inclusion of carbon emissions modelling introduced into workflows of the online Spatial Plan Management System (SPMS) and content requirements for new spatial plans. Resource efficiency guidelines have been included into several different documents, including the City’s draft Urban Design Guidelines. In addition, a climate change resilience and spatial data theme on the Integrated Spatial Data Portal (ISDP) has been included. The Carbon Emissions Model was finalised and tested by the City of Johannesburg’s development planning team. A User/training Manual for the model was completed, which will be used to further internal and external capacitation. The case study of the methodology of Orange Grove as an EcoDistrict has been documented, demonstrating environmental indicators informed by the City’s Climate Action Plan for local eco-districts. New communication products have been finalised, including two marketing and information toolkits for private developers and citizens. Outcome 2 (Social housing): The outputs contributing to this outcome have mostly been completed. The Guidelines and Manuals are starting to find expression within City processes as JOSCHO has included elements emanating from learnings informing the Guidelines and Manual into the Entity’s Business Plan for the 2025/2026 financial year. JOSHCO continues to measure the cost and building performance of the retrofitted units in the Tshedzani3 Roodepoort social housing project for purposes of comparing them with the cost and building performance of the conventional units in the City Deep social housing project. The findings are captured and communicated via a Building Performance Report. Building on this progress, a tender process has been initiated for the implementation of additional energy efficiency interventions at Tshedzani Phase 3, including the installation of the waste management roof and gate, a smart metering and monitoring system, and solar electronics. The JOSHCO Board has been appointed, with permanent placements made for the Chief Operating Officer (COO) and Chief Financial Officer (CFO). Additionally, the recruitment process for the Chief Executive Officer (CEO) has commenced, with the position advertised during this reporting period, which is expected to facilitate the formal adoption and signing of the Green Building Guidelines and Operational Manuals. In addition, AIA has been appointed to assist in the development of the gender sensitivity and responsiveness output, the JOSHCO design briefs, tenant manuals, and key lessons learnt document, all works are progressing and currently underway. Outcome 3 (Food resilience): Conversion of Agri-Resource Centres from in-organic farming into semi-organic farming has been done, in additional to the traditional ‘farm area’. This is done to improve access to the specific target groups, noting that the Agri-resource areas include the conversion of existing community spaces, located within accessible areas for the lower income groups. The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment. The parallel certification process that entails the procurement of a service provider to certify the organic farms following the infrastructure being installed in the farms is also underway. Certification documents were submitted to the CoJ City Manager’s office for approval, which have subsequently been granted. The tender procurement process is currently being undertaken. AIA has completed the packaging of User Guides as information/training tool and certification guidelines and conducted on gender inclusivity and mainstreaming in urban farming and food resilience. Despite overall project progress, challenges related to project management at the JDA have been experienced. The Programme Coordination Office is actively addressing these issues to prevent delays in programme completion. Outcome 4 (Biodegradable waste): The service provider for sub-components 4.1, 4.2 and 4.4 has been appointed and has started work on the various sub-components. The city has proposed two pilot sites for Separation at Source (S@S): the Johannesburg Fresh Produce Market and selected Dailies in Region F. A detailed plan and resource list have been submitted for approval. The pilot will require waste collection services for separated waste, with the city to decide whether to use Pikitup or appoint a private provider. Procurement methods for resources are also under review, and the pilot is awaiting final decisions on service provision and procurement. For sub-component 4.3, An EPC contractor has been appointed for the biogas plant, with the contract signed and design work set to begin by the end of July 2025. Construction is scheduled to start in November 2025. A separate contractor has been appointed for the building works, expected to begin by the end of August 2025. Both construction activities will run concurrently. Outcome 5 (Evidence-based planning): The Website development has been completed. Configuration of CoJ environment has been completed and both the ISDP and SPMS has been migrated from development environment to production environment for Beta deployment of the online portal (Integrated Spatial Data Portal and Spatial Plan Management/Sharing System). User manuals (technical user guides) for both the ISDP and SPMS were developed. A summary presentation (Pitch Deck) for events, including launch and knowledge sharing sessions, have been completed. Based on the above, the project overall progress towards achieving the expected outcomes is rated as Satisfactory. Rating towards outputs Component 1 (Eco-districts): Testing of the carbon emissions model was conducted in Quarter 1 of 2025. Internal staff members received training for the carbon emissions model. A User/training carbon emissions manual was finalised and uploaded onto the new SPMS on-line system (accessible to public). Two marketing and information documents were finalised: A Citizen’s and a Developer’s Guideline to Eco-districts in Johannesburg. A document, summarising lessons learned from the project, in addition to the one completed by the service providers, have been completed. All deliverables have been finalised. Component 2 (Social housing): A permanent Chief Operations Officer (COO) has been appointed at JOSHCO and has been appraised on the Green Building Guidelines and Operations Manuals. Official adoption and sign-off are anticipated by September 2025. The tender process for the installation of the waste management roof and gate, smart metering and monitoring system, and solar electronics has been initiated. The contract has been advertised for a three-month duration, with acceleration efforts to be employed where possible. UNEP and CoJ have submitted an amendment to the Project Cooperation Agreement (PCA) to extend the GEF-funded project to 2026. This extension will support the achievement of this component’s outcomes if the appointed service provider is unable to complete the work within the projected three months. AIA has been appointed to develop the Knowledge Management, Communication and Marketing Strategy for the project. An accelerated programme has been adopted, with most project outcomes already completed. The remaining deliverables, including focus groups on the green regulatory environment (value chain mapping), the pitch deck, and the Lessons Learnt report on the green building value chain, are expected to be finalised by the end of Quarter 3, 2025. Component 3 (Food resilience): The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed through the City implementing agent JDA. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment in quarter 2 of 2025. The JDA has been requested to facilitate an accelerated workplan to ensure the project is completed within the five-month project duration. UNEP and CoJ have submitted an amendment to the Project Cooperation Agreement (PCA) to extend the GEF-funded project to 2026. This extension will support the achievement of this component’s outcomes if the appointed service provider is unable to complete the work within the projected five months from appointment. The food mapping tender has experienced delays due to the non-vetting of the bid specification and bid evaluation members. A request to nominate new vetted members as per CoJ supply chain policy and process is being explored with department head of Social Development. The certification tender has received approval from the City Manager office and the procurement process is currently being undertaken to appoint the relevant service providers. AIA is currently finalising additional knowledge products as per project outcome including articles, case study and testimonial videos which are expected to be completed by the end of Quarter 3, 2025. Component 4 (Biodegradable waste): The Service Level Agreement (SLA) between DBSA and Energidrop for the implementation of sub-components 4.1, 4.2, and 4.4 was concluded on 31 July 2024. The waste management strategy has been divided into several work packages; each developed as a standalone document. The final integrated strategy will consolidate these and include findings from the upcoming Separation at Source (S@S) pilots. Similarly, the investment feasibility studies are dependent on the outcomes of the S@S pilots and the assessment of treatment technologies for biodegradable waste. Completion of both the strategy and feasibility studies is therefore pending the results of these ongoing activities. The EPC contractor for the biogas plant has been appointed and the contract signed. Design activities are expected to begin by the end of July 2025, with construction scheduled to start in November 2025. A separate contractor for building works has also been appointed, with construction anticipated to commence by the end of August 2025. Both construction streams will proceed concurrently Component 5 (Evidence-based planning): ESRI (Environmental Systems Research Institute, Inc) has upgraded the IT environment to enable the Workflow manager to be accessible on the City’s IT Environment. All licenses have been provisioned and configured. The completion of the portal configuration was finalised and Beta deployment achieved. System testing has been completed by the project team, which resulted in some system amendments. User testing is planned for mid-August 2025. Skills training and transfer will commence in Quarter 3 of 2025 and the ISDP portal will be launched for public use. Based on the above, the project overall progress towards delivering the outputs is rated as Satisfactory. Overall risk rating: The overall programme is advancing fairly well, with a variation of concluded activities and those nearing conclusion. Nonetheless, the following risks have been identified in the 2025 PIR: - Cross cutting: The co-signing of the Amendment No 3 of the Project Cooperation Agreement (PCA) between CoJ and UNEP to permit the extension of the project implementation period beyond September 2025 has been delayed due to ongoing turnover in the City of Johannesburg’s administrative leadership. Despite that the initial request to co-sign the PCA amendment was sent in May 2025, the change in acting arrangements necessitated the re-submission in July 2025. The delays in finalizing the documents required for the extension presents potential risks of time limitations to complete the remaining activities. Continuous efforts are underway to urgently resolve the matter and minimise any adverse impact on project implementation. - Component 3: There are some details noted with respect to on-going procurement process that may result in delays to the completion of project activities related to the certification and food mapping tenders. Adjustment to the timelines for completion of activities have been included in the proposed workplan and budget Revision 5 which is contingent upon the co-signing of the Amendment No 3 of the Project Cooperation Agreement (PCA). - Component 4: No new risk identified during the reporting period. - Component 5: No residual risk. - Financial: Risk of COJ underspending GEF funding available for UNEP-led components due to project timelines requiring extension.

2.4. Co-financing

| Planned Co-finance Total: US$ 124,439,330 Actual to date: US$ 185 053 345 (≈ 149%) | Component 1: US$ 5,678,806 from the CoJ between July 2024 - June 2025 leading to a total of US$ 171,996,947 since project start (out of the expected US$ 46,113,333) Component 2: US$ 3,200,084 from the COJ between July 2024 - June 2025 leading to a total of US$ 9,272,475 since project start (out of the expected US$ 64,304,200) Component 3: US$ 149,831 from the CoJ between July 2024 - June 2025 leading to a total of US$ 1,390,596 since project start (out of the expected US$ 8,084,867) Component 4:160,905.03 from DBSA between July 2024 – June 2025 leading to a total of US$ 1,085,495 since project start (out of expected US$ 4,220,00) Component 5: US$ 7,945 from the CoJ between July 2024 - June 2025 leading to a total of US$ 1,307,832 since project start (out of the expected US$ 1,091,735) |
| --- | --- |
| Progress | The different co-finance contributions consist in the following: - Component 1: The CoJ has invested capital budget in the defined TOD Corridors and precincts during the 2024/25 financial year. The projects included investment in social facilities (clinic, multipurpose community centres), infrastructure (stormwater, water and sanitation and road infrastructure), as well as public transport infrastructure. Further in-kind contributions include staff salaries. Component 2: the CoJ has invested capital budget in the new greenfield development (Riverside View social housing) and in-kind contributions in staff salaries. Installed smart meter in all 172 units at Tshedzani Phase 3 Social housing. Component 3: the CoJ has invested in purchasing seeds that were used for organic farms and replicates. Further in-kind contributions include staff salaries. Component 4: the DBSA and the CoJ has invested financial and in-kind contributions in the form of staff salaries. Component 5: the CoJ has invested in-kind contributions in the form of staff salaries. |

2.5. Stakeholder engagement

| Date of project steering committee meeting | 5 December 2024 |
| --- | --- |
| Stakeholder engagement | Component 1 (Eco Districts): Attended Green Building Convention, hosted by the Green Building Council of South Africa in Cape Town, South Africa from the 05-07 November 2024. This is an annual Convention aimed at supporting green building initiatives in the continent. The 2024 theme of the Convention: Net Zero Today, Climate Positive Tomorrow, with an estimated 300 delegates in attendance. There were further informal engagements with other city colleagues from the City of Cape Town and the City of Tshwane to collaborate in 2025 under the sustainable/resilient/low carbon emission precinct development agenda. Component 2 (Social Housing): From 24 to 28 February 2025, attended the City of Johannesburg & Copenhagen workshop hosted by Johannesburg City Power and the Danish Embassy. As part of the programme, we hosted the delegation at the Tshedzani GEF Retrofitting Project site, providing an overview of the work undertaken to improve water and electricity efficiency. This workshop formed part of a collaboration on the Energy Monitoring and Building Management Systems Proof of Concept. On 1 April 2025, presented the GEF project to C40 Cities representatives and various Johannesburg entities during the Bloomberg Cities Idea Exchange: Renovation and Retrofitting Social Housing workshop. From 8 to 10 April 2025, participated in the Promoting Sustainable Urbanization that Contributes to Global Environmental Goals workshop hosted by UNEP and the World Bank. On 8 April, joined the session online where the Tshedzani Retrofitting Project was featured under the topic Decarbonization and Resilient Built Environment: Low-Carbon & Resource-Efficient Eco-Districts in Johannesburg, South Africa. Component 3 (Food resilience): Collaborated with Joburg Market to host a Farmer’s Day in October 2024. The Farmers’ Day entailed the capacitation of a wide range of Farmers on opportunities offered by the City and its partners (partners for the Event: Standard Bank, Gauteng Department of Agriculture and the Land Bank). The aim was to capacitate emerging, small- and large-scale farmers on how to participate in farming initiatives, detail of trainings available, how to access relevant markets, partnerships with the city and other entities in the space). The Farmers’ Day also entailed an exhibition of a wide range of produce and products from local farmers supported by the City. The Food Resilience Team formed part of the exhibitions and show-cased seedlings and products to support seedling production. The Farmer’s Day was attended by approximately 1000 people. The Farmer’s Day has been followed by several conversations with Joburg Market Executives to determine future collaborations to support the work of Component 3. Component 3 further took part in a Site Visit from 24 – 28th February 2025 co-hosted by the Department of Rural Development and Agriculture to various organic farms across the Bohlabela District. The purpose of the site visit was to allow the sharing of new practices and techniques of organic farming. Component 4 (Biodegradable Waste): As part of ongoing stakeholder engagement efforts, Ms Lesedi Letlhogile attended a Sustainable Cities Workshop in Kenya, where the GEF-6 project was referenced in discussions on urban sustainability. The project also aligns with the upcoming GEF-8 Sustainable Cities initiative currently under development. In addition, the GEF hosted an Expanded Constituency Workshop (ECW), which included a site visit to a similar biogas plant to facilitate knowledge exchange. Participants also visited the Johannesburg Fresh Produce Market, one of the identified waste sources for the project. These engagements have reinforced the strategic relevance of the project within the broader GEF Sustainable Cities portfolio. Component 5 (Evidence based planning): No stakeholder engagements were conducted in the reporting period. Overall project: The project organized the 5th PSC meeting in December 2024, with the participation of DBSA, UNEP and all component leads from the COJ. |

2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming | A Gender Action Plan has been developed. Further improvements on the impact of the plan is being explored. The Knowledge Management, Communications and Marketing Team has been briefed about this activity and their Gender Specialist has started interrogating the previously developed Gender Action Plan to ensure that beyond the identified indicators, further measures are included that will enable both component and overall project vetting in response to transforming the gender space in City processes. Component 2: Focus groups on gender mainstreaming in social housing were conducted for component 2 on the 17 May 2025. The inputs received at these sessions were used to inform the lessons learnt and pitch deck content which were finalised on the 30th of June 2025. Component 3: Focus groups on gender inclusivity and mainstreaming in urban farming and food resilience were also conducted at administrative region A, C, D, E, G as well as Component focus group. The inputs received at these sessions were used to inform the lessons learnt and pitch deck content which were finalised on the 30th of June 2025. Component 4: Gender mainstreaming efforts have been strengthened through the engagement of consultants tasked with enhancing the gender components of the waste management strategy and the broader Component 4 deliverables. The consultants have developed a Gender Action Plan to guide implementation and ensure inclusivity. As part of this process, a gender workshop was scheduled to take place at the DBSA on 15 July 2025, providing a platform for dialogue and capacity building on gender-responsive approaches within the project. |

2.7. Environmental and social safeguards management

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk CEO Endorsement/Approval Stage? No If yes, what specific safeguard risks were identified in the SRIF/ESERN? N/A |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? Component 3: Following an environmental and regulatory review by the City of Joburg’s Environment and Infrastructure Services Department (EISD), the Innes Free Park site (one of the five originally identified for infrastructure installation) has been deemed unfeasible due to the site being non-compliant with key environmental and land use regulations (largely due to the presence of a river in close proximity to the site, necessitating an application for a water use license which was anticipated to take over 12 months for an approval). As such, the project at this site has been halted. To mitigate the impact, the associated beneficiaries have been consulted and have agreed to relocate to the Northern Farms site. The existing and planned infrastructure originally intended for the Innes Free Park site will now be relocated and consolidated at the Northern Farms site to support the continued participation of the beneficiaries in the project. |
| Complaints and grievances related to social and/or environmental impacts (to be filled in by TM and EA) | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No. |
| Environmental and social safeguards management | Component 1 (Eco Districts): Low-carbon emission development is promoted through the component. The completion of the City’s Green Building Policy was institutionalized through training of CoJ building and plans examiners and including new operational requirements into the building plan submission to start monitoring responsiveness to the new policy. Resilience and sustainability aspects have been included in the draft Urban Design Policy of the City, which will be finalised once more consultation is done. Through capacitation and knowledge sharing processes, several built environment professionals including developers have been sensitised to a pathway of low carbon development. Practical interventions have been identified and demonstrated. Application of improved knowledge has led to appropriate scoping of renewable energy technical interventions in the design of new facilities (demonstrated by the clinics), resulting in cost savings and greater efficiencies. The sub-metering project introduced as part of the baseline data collection process, has raised awareness with the participating residents around their energy consumption patterns and ways to improve it. It has also improved operational aspects in the CoJ clinic where operations were monitored. Furthermore, the carbon emissions model and the precinct scale guidelines that have been developed will assist in identifying high-emission activities early, enabling proactive mitigation measures, and guiding low-carbon infrastructure planning that reduces environmental harm while promoting equitable access to cleaner, healthier urban spaces. These tools will also help ensure compliance with environmental standards and supports inclusive decision-making by quantifying impacts on vulnerable communities. Component 2 (Social Housing): In the 172 units retrofitted at Roodepoort Tshedzani Phase 3, the component team has been able to raise the tenants’ awareness and change their behavioural patterns towards energy and water saving, and waste management. Over and above this social and behavioural change, the retrofit project has been able to provide an environmentally friendly source of energy and waste management. Environmental Management is addressed through JOSHCOs Waste Management Guidelines as well Design Guidelines which are in line with SANS10400 Town planning and Landscaping minimum targets. Socio-economic safeguards are managed through JOSHCOs Social Facilitation processes of engagement with the stakeholders involved as outlined in the Standard Operational Procedures. JOSHCO is currently developing Riverside Phase 4, and the development is being developed with green building initiatives integrated into the project’s design specifications. These include energy-efficient technologies, water conservation systems, and sustainable waste management solutions which will continue to minimise the ecological impact and ensure healthier, more inclusive living environments for future residents. Component 3 (Food resilience): The component seeks to address environmental challenges such as soil degradation, pollution and erosion. As well as social challenges such as food insecurity. This project continues to advance positive environmental and social safeguard measures through the procurement of organic fertilisers, pesticides, herbicides, fungicides and seeds. Additional provision has been made, which is production input aimed at improving soil fertility and dealing with problems related to pests as a result of climate change. Further to this, engagements have been had to source compost from the City entities such as Pikitup and City Parks and Zoo to boost soil fertility. Part of the advisory services offered by the component to the farmers was to use contour planting to avoid soil erosion. The component addresses food insecurity by providing organic vegetables that contain less chemical residue. This will address environmental challenges simultaneously with food security. Component 4 (Biodegradable Waste): N/A Component 5 (Evidence based planning): N/A |

2.8. Knowledge management

| Knowledge activities and products | Africa International Advisors (AIA) have been appointed (November 2024) to develop the Knowledge management, Communication and Marketing Strategy for all five components. The following deliverables were submitted in the reporting period: - Component 1 (Eco Districts): Guidelines and Toolkits - Private Developers’ Guidelines to Eco-Districts –30 June 2025. - Citizen’s Guidelines to Eco-Districts –30 June 2025. - SPMS Web Page Design Inputs concluded (included into final SPMS layout by 30 June 2025) – all final GEF knowledge products to be uploaded during July-August 2025, before SPMS goes live. Articles and Media - What can we learn from Global Practices Article –26 May 2025 Focus Groups/Workshops - SPMS Web design requirements and expectations - Guidelines Objectives, Expectations and Arranged Site Visits to capture content Component 2 (Social Housing): Guidelines and Manuals - Greenfield and Brownfield Building Specification Guidelines – Submitted 30 April 2025 - Packaging of Tenant Training Manuals - 16 May 2025 - Lessons Learnt on Tenant Conflict Management – 30 June 2025 - Lessons Learnt on Gender Mainstreaming in Social Housing – 30 June 2025 Articles and Media - Tenant testimonials – 30 June 2025 - A ‘how to’ infographic on the SolarMan Smart App – 30 June 2025 Focus Groups/Workshops - Focus groups on gender mainstreaming – 17 May 2025 The outstanding deliverable are the focus groups on Green regulatory environment -mapping of the value chain, the pitch deck and Lessons Learnt on the green building value chain, which are anticipated to be completed by September 2025. Component 3 (Food resilience): Guidelines and Manuals - User Guide/Training Materials for farmers – 30 June 2025 Focus Groups/Workshops - Focus groups on gender inclusivity and mainstreaming in urban farming and food resilience. The outstanding deliverable are additional knowledge products such as case study and testimonial videos which are expected to be completed by the end of Quarter 3, 2025. Component 4 (Biodegradable Waste): Articles and Media - Turning Trash into Jobs: Unlocking South Africa’s Waste Economy - Waste Management: A Key Lever to Improving the Liveability and Sustainability of South African Cities In addition, the DBSA published an article on its official website and social media platforms highlighting the project's contribution to sustainable urban development. The article is titled DBSA Drives Sustainable Urban Development Through GEF-Funded Initiative. These knowledge products aim to raise awareness, share insights, and promote the project’s impact across broader audiences. Component 5 (Evidence based planning): Guidelines and Manuals - Technical User guides for ISDP and SPMS - 30 June 2025 - ISDP Lessons Learnt- 30 June 2025 - Pitch Deck – summary presentation The outstanding deliverables are the close out article and the ISDP Launch Event (online), planned for end of August 2025. The close out article needs to include reflections from the event. Knowledge Management, Communication and Marketing Strategy The Knowledge Management Framework (finalised on 27 June 2025) and the Marketing and Communication Strategy (finalised on 25 April 2025) have both been developed, with extensive stakeholder engagements conducted across internal departments and component leads to inform and strengthen the respective deliverables. In addition, the Stakeholder Engagement Framework was completed, with the final plan submitted on 25 April 2025. |
| --- | --- |
| Main learning during the period | Component 2: AIA conducted focus groups to explore the key lessons that can emerge from tenant conflict management in the context of social housing. As such, the findings reveal that most conflicts during the retrofitting of green infrastructure were not rooted in resistance to change, but rather in communication breakdowns, exclusion from decision-making, and unclear roles around maintenance and accountability. Knowledge management challenges such as, siloed information, inconsistent engagement, and the lack of structured feedback systems further exacerbated tensions. The key takeaway is that effective conflict prevention hinges on early and meaningful tenant involvement, recognition of legitimate tenant committees, clear user education, and responsive systems. Ultimately, the retrofitting process must be as focused on building trust, transparency, and shared ownership as it is on delivering technical upgrades. |

2.9. Stories to be shared

| Stories to be shared | As part of the programme's knowledge sharing and impact communication efforts, the following multimedia stories have been developed to highlight community benefits and project outcomes: Tshedzani Phase 3 Testimonial Video: This video features personal testimonials from beneficiaries of the Tshedzani Phase 3 social housing project. Residents share their experiences regarding improved living conditions, energy-efficient infrastructure, and the positive impact of green building interventions on their quality of life. Testimonial video.Vf.mp4 Food Resilience Story: This segment documents the programme’s contribution to urban agriculture and food security. It highlights how local communities are building resilience through sustainable food systems, supported by infrastructure upgrades, training, and cooperative models. Food Resilience.mp4 Social Housing Story: This video showcases the broader impact of the programme’s social housing initiatives, focusing on equitable access to housing, integration of green building principles, and the promotion of inclusive urban development across multiple sites. Social Housing.Mp4 |
| --- | --- |

# 3. PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

3.1	Rating of progress towards achieving the project outcomes (Development Objectives)

| Project objective and Outcomes | Indicator | Baseline level | Mid-term target | End-of-project target | Progress as of current period | Summary of progress to achieve indicator targets as of 30 June 2025 | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The project will foster city level resilience, resource efficiency, emission reductions and other co-benefits through area-based pilot demonstrations, systems analysis (food), and institutionalisation of evidence-based decision-making through integrated planning | Lessons from the project are reflected in the budget for city housing, waste management, food security, and area-based planning | 0 | - | 5 investments in the budget are influenced by the lessons from the project | 5 | Eco-District: Eco-District: Development Planning Department budgeted to construct the Turffontein Clinic; the first pilot project underway informed by the new guidelines for resource-efficiency. 5 new clinic designs have been informed by these guidelines. 3 of these clinics have been allocated capital budgets in the CoJ’s approved Medium term budget (2023/24-2025/26) to be constructed -Hkinsele Clinic,Naledi Clinic and Protea South Clinic. Naledi clinic was completed and opened in March 2025. Food resilience: Following the budget provisions being made as influenced by the preliminary outcomes of the Project, City of Joburg funding is being continuously utilized to support the farming projects. For the current reporting period (July 2024 – June 2025); seeds, to the value of USD$ 27,420 have been bought. This is starting to indicate a shift in processes as the outcomes of the project are starting to have effect on the City and structures that run processes. | S |
| Outcome 1: CoJ test eco-district prototypes to set improved environmental standards for City of Johannesburg | Number of eco-districts modelled for optimised resilience and sustainability and number of new developments informing eco-district criteria completed or under construction. | None | - | 1 eco-district modelled and 4 new developments informing eco-district design criteria modelled and under construction | 1 eco-district modelled & 5 developments modelled and 3 under construction | 1.Eco-district has been modelled and an emissions reduction pathway with interventions has been defined for two development scenarios. Goals, targets and Indicators, as well as strategies were developed for Orange Grove to demonstrate application of the EcoDistrict methodology. Guidelines (towards achieving NZC targets) were codeveloped for specific building categories, including new city facilities (clinics and multipurpose community halls) as well as social housing. Capacitation and knowledge sharing sessions were done with public and private sector stakeholders. The design of 5 new clinics were informed by the new guidelines, with 3 clinics currently under construction (Turffontein, Hkinsele, Protea South Clinics) and 1 clinic completed (Naledi). Turffontein and Hkisnele clinics are more than 50% completed, whereas the construction of Protea South clinic has progressed beyond 20%. | S |
|  | The eco-district targets are recommended as the standard for the TOD Corridors | Not yet | - | Yes | Yes | Guidelines and standards have been documented based on the Eco-district modelling. New environmental guidelines were included into other City documents, including the new draft Urban Design Guideline for CoJ. The approved Green Building Policy: new buildings will be applicable to the TOD corridors (and city-wide). | S |
| Outcome 2: CoJ adopts gender sensitive and resource efficiency guidelines for improved sustainability of social housing | Adoption by JOSCHO of revised guidelines that include improved sustainability criteria | Current JOSCHO guidelines are not revised to include improved sustainability aspects or social housing are not constructed as planned | Guidelines in draft form | JOSCHO adopts and implements the revised guidelines for new social housing development and retrofits | Guidelines in (final) draft form. All input work completed, awaiting the endorsement from the Executives and Board. | Riverside View Development, comprising of 80 units with the green building initiatives incorporated into the design and building specifications (that is, its design and tender specifications informed by the new guidelines) has been completed. Tenants have been allocated and monitoring is underway. Following the completion of the brownfield’s retrofits and some installation of the smart meters in Roodepoort Tshedzani 3 social housing (172 housing units), off-site monitoring is occurring, and baseline data is continuously being generated. The App is used to enable continuous monitoring and tweaking of the system to respond to challenges experienced. The tender for additional smart metering & monitoring system, and solar electronics is currently underway which will enable more effective and accurate data being generated. Noting that the Guidelines continue to get in principle endorsement by the EXCO. The final adoption (signoff) by the COO, EXCO and Board Members is still pending. In Quarter 2 of 2025 a permanent COO was appointed and they were consulted. The official adoption and signoff is anticipated to be finalised by September 2025. The documents have been presented at the JOSCHO Strategic Session where they were endorsed to form part of the Entity’s Business Plan for 2025/2026 financial year. | S |
| Outcome 3: Emerging urban farmers increasingly implement more environmentally sustainable food security solutions | # m2 of community gardens converted to certified organic production methods. | 0 m2 | 5,700 m2 under organic production methods | 5,700 m2 under organic production methods and certified | 17,000 m2 converted to organic farming, pending certification | Approximately 17,000 m2 of City land has been converted to organic farming area, certification of said space has not yet occurred as the overall certification will be done once the infrastructure installation workstream has been finalised. The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment. The parallel certification process that entails the procurement of a service provider to certify the organic farms following the infrastructure being installed in the farms is also underway. Certification documents were submitted to the CoJ City Manager’s office for approval, which have subsequently been granted. The tender procurement process is currently being undertaken. | S |
|  | Number of men and women emerging farmers and CoJ officials trained in and using sustainable and/or organic farming methods; | None | 200 | 400 (Values disaggregated by gender) | Total number trained to date 3,387 people. | Organic awareness training and focus groups for 95 people took place in June 2025. The cumulative total number of individuals trained since project start has increased to 3,387 people. Number of women trained: 1,779 Number of men trained: 1,545 Preferred not to state gender: 63 | HS |
| Outcome 4: CoJ adopts an integrated biodegradable waste management strategy and has pre-investment documents to mobilise finance to implement the strategy | Strategy for biodegradable component of CoJ’s municipal waste | None | Preliminary strategy completed | Strategy is formally adopted by CoJ. | Strategy drafted | The development of the strategy is under way and due to be completed by September 2025. However, it is dependent on the completion of the S@S pilots. There has been delays in implementing those pilots due to procurement delays of the city. | MS |
|  | Weight of biodegradable waste diverted from landfill sites (by all means, including separation at source) | 0 tons | - | 20,000 tons | 0 | The biogas plant has not started construction and the pilots have not yet commenced. | MS |
| Outcome 5: Enhanced capability of CoJ in evidence-based policy and strategy making. | Number of online users of the platform per quarter | 0 | GIS platform is operational | 100 users per quarter | GIS platform is operational | ESRI (Environmental Systems Research Institute, Inc) has upgraded the IT environment to enable the Workflow manager to be accessible on the City’s IT environment. All licenses have been provisioned and configured. Completion of the portal configuration and Beta deployment achieved. Launch of portal is planned for end of August 2025 for internal and public users. | S |
|  | Number of departments/entities keeping the data in the GIS integrated platform up to date. | 0 | GIS platform has data from the ‘pilot’ departments / entities | All departments and entities have their spatial data integrated into the platform | GIS platform has data from the ‘pilot’ departments / entities | Available datasets from departments/entities were identified during the Audit and subsequent discussions. Data from one department was uploaded by 30 June 2025. The dataset inventory from identified departments and entities is being finalised for data upload by 15 August 2025. | S |

3.2	Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Outputs/Activities | Expected completion date | Implementation status as of 30 June 2024 (%) | Implementation status as of 30 June 2025 (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress rating |
| --- | --- | --- | --- | --- | --- |
| OUTCOME 1: COJ test eco-district prototypes to set improved environmental standards for City of Johannesburg |  |  |  |  |  |
| Output 1.1: One Eco-District (at neighbourhood, precinct, block and site scale) modelled for optimized resilience and sustainability | 30 Nov 2022 | 100% | 100% | The ISDP is being updated to include requirements that speak to the below: Model and Baseline Assessment completed (activity 1.1.2). Emissions Interventions Modelling completed for two development scenarios (activity 1.1.3). Activities 1.1.4 (goals for Eco-districts based on pre-modelling), 1.1.5 (emission reduction pathways for Eco-districts) and 1.1.6 (environmental indicators) have all been completed with the emission reduction pathway demonstrated against interventions and target (NZC). Activity 1.1.7 was completed – a user-friendly model interface was developed and the model is hosted on on-line platform. | S |
| Output 1.2: Knowledge-share and information transfer products developed for private and public green construction sector | 31 Dec 2022 | 100% | 100% | Activity 1.2.1 was completed, with cost modelling and financial implications of the emission reduction interventions included into the report. Activity 1.2.2 completed – guidelines were developed for incorporating green elements into new city facilities and social housing. Activity 1.2.4 completed – capacitation sessions with city professionals, developers and private sector professionals were held on 23 November 2022. More communication products will be developed once the knowledge management service providers have been appointed. Activity 1.2.3 is completed – lessons learned are captured in the stakeholder and standard development process reports. Activity 1.2.4 is completed –Training has been provided by Solid green consultants to key stakeholders within the City. | S |
| Output 1.3: Evidence-based green policies and guidelines adopted by the CoJ | 30 Sep 2025 | 85% | 100% | Activities 1.3.2 and 1.3.3 have been completed - new standards and guidelines documented and Green Building Policy completed. Processes to operationalise and mainstream Green Building Policy implementation is underway – an implementation plan was formulated through an internal task team and the first phase completed. Activity 1.3.4 Document process of standard setting and lessons learned (including demonstrations of emissions interventions) – Standard setting process linked to emission reductions and interventions were completed, and lessons learned included into pathway documents, carbon emissions model user manual and summary document on Orange Grove. A Lessons Learnt summary document was completed June 2025. Activity 1.3.5 (Include modelling and resource efficiency guideline into requirements for spatial plans and precinct scale developments) – a link to the model as “toolkit” was included in the new Spatial Plan Management System (component 5). This will allow users to access the model using a link to test/use the model to calculate carbon emissions. Activity 1.3.7: A Carbon emission model User Manual was developed – this is adequate for training purposes. Activity 1.3.8 has been completed. For Marketing and information purposes, two guidelines were developed: A Citizen’s and a Developer’s Guideline to Eco-districts.. The packaging of the data/information into Toolkits and Products has been finalized by the incoming Knowledge Management, Marketing and Communications Strategy Consultant: Africa International Advisors (AIA) and final documents submitted on 30 June 2025. | S |
| OUTCOME 2: COJ adopts gender sensitive and resource efficiency guidelines for improved sustainability of social housing |  |  |  |  |  |
| Output 2.1: Revised sustainable, affordable and gender sensitive social housing retrofit guidelines are adopted by JOSHCO | 31 Mar 2026 | 98% | 98% | 2.1.1 to 2.1.4 These activities have reached Close Out stage and their implementation needs to continuously be monitored in line with JOSHCOs Maintenance Plan through the housing site manager. Noting that the retrofitting has been completed, data collection has primary been done via manual reading and logging of information from Units. Smart metering to allow for the digital monitoring of tenant use continues to be critical as inefficiencies are sometimes experienced with the manual collection of data. Smart Meter installation is still in process. The full installation of Smart Meters will enable the digital sourcing of data from all the Units into the SMART APP. 2.1.5 to 2.1.6 Despite both the Guideline and Manuals being completed, challenges still exist in getting them formally adopted by JOSCHO. The final adoption (signoff) by the COO, EXCO and Board Members is still pending. In Quarter 2 of 2025 a permeant COO was appointed, and they have been consulted regarding the documents. The official adoption and signoff are anticipated to be finalised by September 2025. The documents have been presented at the JOSCHO Strategic Session where they were endorsed to form part of the Entity’s Business Plan for 2025/2026 financial year. | S |
| Output 2.2: JOSCHCO processes are revised to ensure constructed social housing conforms with design brief | 31 Mar 2026 | 98% | 98% | 2.2.4 Findings report are being shared at wokshop/seminars, ongoing proccess. Final findings will be shared at the programme close-out seminar/conference. 2.2.4 to 2.2.5 Despite both the Guideline and Manuals being completed, challenges still exist in getting them formally adopted by JOSCHO. The final adoption (signoff) by the COO, EXCO and Board Members is still pending. In Quarter 2 of 2025 a permeant COO was appointed, and they have been consulted regarding the documents. The official adoption and signoff are anticipated to be finalised by September 2025. The documents have been presented at the JOSCHO Strategic Session where they were endorsed to form part of the Entity’s Business Plan for 2025/2026 financial year Noting that in principle endorsement has been attained, the learnings contained in the Guidelines and Manuals is however being institutionalized. In addition, further refining is continuously being done as data continues to be available. | S |
| Output 2.3: Revised sustainable, affordable and gender sensitive social housing retrofit + greenfields guidelines are adopted by JOSHCO | 31 Mar 2026 | 98% | 98% | Activity 2.3.1 to 2.3.5 The activities under this output have reached Close Out stage. Activity 2.3.7 to 2.3.8 A Gender Action Plan has been developed. Further improvements on the impact of the plan is being explored. The Knowledge Management, Communications and Marketing Team has been briefed about this activity and their Gender Specialist has started interrogating the previously developed Gender Action Plan to ensure that beyond the identified indicators, further measures are included that will enable both component and overall project vetting in response to transforming the gender space in City processes. Component 2: Focus groups on gender mainstreaming in social housing were conducted for component 2 on the 17 May 2025. The inputs received at these sessions were used to inform the lessons learnt and pitch deck content which were finalised on the 30th of June 2025. Activity 2.3.6 The sharing of findings in various sessions is a continuous activity. | S |
| Output 2.4: All revised guidelines and processes are shared with other social housing development agencies for uptake | 31 Dec 2025 | 98% | 98% | This output has reached Close Out stage as the draft Guidelines have been produced and have received in-principle approvals via the consultations with the various Senior Executives of JOSHCO. Notwithstanding the outstanding final signatures on the actual Guidelines and Manuals, the learnings from the Project as contained in the draft Manuals and Guidelines will be implemented as they have been endorsed in the JOSHCO Strategic Session where they were further endorsed to from part of the JOSHCO Business Plan for 2025/2026 FY which begins in July 2025. The draft Manuals and Guidelines have not officially been shared with other Agencies as they first need to receive the official signoff from JOSHCO Executives. However, sharing of the contents is an ongoing exercise with as sister agencies and partners as such sharing builds capacity and contributes toward improving the Product.. The final signature on the Manuals and Guidelines is anticipated in September 2025. Upon the final signature being attained then official sharing all stakeholders will occur. | S |
| OUTCOME 3: Emerging urban farmers increasingly implement more environmentally sustainable food security solutions |  |  |  |  |  |
| Output 3.1: Ways of urban farming production are piloted to improve food quality, affordability, financial and environmental sustainability and gender equality | 31 Mar 2026 | 75% | 80% | A Gender Action Plan has been developed. Further improvements on the impact of the plan is being explored. The Knowledge Management, Communications and Marketing Team has been briefed about this activity and their Gender Specialist has started interrogating the previously developed Gender Action Plan to ensure that beyond the identified indicators, further measures are included that will enable both component and overall project vetting in response to transforming the gender space in City processes. Focus groups on gender inclusivity and mainstreaming in urban farming and food resilience were also conducted at administrative region A, C, D, E, G as well as Component focus group. The inputs received at these sessions were used to inform the lessons learnt and pitch deck content which were finalised on the 30th of June 2025 The establishment/conversion of organic farming land is progressing as the actual farming space to date is sitting at a collective 17,000sqm. The said land requires the installation of infrastructure and later organic certification. The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed through the City implementing agent JDA. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment in quarter 2 of 2025. The process to permit the Certification of the farmland is also being initiated. Certification documents were submitted to the CoJ City Manager’s office for approval, which have subsequently been granted. The tender procurement process is currently being undertaken, | S |
| Output 3.2: Policies and recommendations for increased food resilience in CoJ are drafted and adopted | 31 Mar 2026 | 20% | 25% | The Tender for the consultant to undertake the activities under this output has been advertised. The closing date for the Tender was in November 2024. The food mapping tender has experienced delays due to the non-vetting of the bid specification and bid evaluation members. A request to nominate new vetted members as per Co supply chain policy and process is being explored with department head of Social Development | MS |
| Output 3.3: A plan is prepared and agreed with CoJ to replicate successful pilots | 31 Mar 2026 | 70% | 70% | Criteria to deem/disqualify ‘project success’ is being produced and this is informed by the ongoing learnings and data generated from the operations and trainings since project inception. This Criteria will then be formally endorsed as a standard and pilot to guide and replicate future like farming projects. The initial data is available and will be supplemented by the deliverables from Output 3.1 and 3.2. Progress remains the same as the Service Provider will undertake this work on appointment. | S |
| OUTCOME 4: CoJ adopts an integrated biodegradable waste management strategy and has pre-investment documents to mobilise finance to implement the strategy |  |  |  |  |  |
| Output 4.1: Waste to biogas pilot is constructed and operational | June 2026 | 45% | 50% | EPC contractor for the biogas plant appointed. Contract has been signed, with design activities expected to start by end of July 2025. Construction expected to start November 2025. A separate contractor for building works has also been appointed with expectation to commence with construction by end of August 2025. Both the building works and construction of the biogas plant will take place concurrently. | S |
| Output 4.2: Waste separation at source is piloted | September 2025 | 50% | 55% | Two options for separation at source (S@S) were selected by the City: implementation at the Johannesburg Fresh Produce Market (JFPM) and selected "Dailies" in Region F. A detailed pilot plan, along with a list of required resources, has been submitted to the City for approval. The pilots will require waste management services, including the collection of separated waste from participating waste generators. The City will determine the most viable option for service provision, either appointing a private service provider or utilising Pikitup, the municipal-owned entity. The City will also decide on the preferred procurement method for the necessary resources (e.g., public tender). The pilot is currently awaiting decisions on both the service provider and the procurement process. | MS |
| Output 4.3: A COJ integrated bio-degradable waste management strategy is developed that is gender sensitive | September 2025 | 10% | 80% | The strategy has been structured into multiple focused work packages, with each sub-deliverable developed as an individual document. The final integrated strategy will consolidate these outputs and incorporate insights from the separation at source (S@S) pilot initiatives. And therefore, the last component of the strategy will be finalised with input from the S@S pilot, which is awaiting commencement. | S |
| Output 4.4: Investment feasibility studies are completed for the implementation of COJ’s biodegradable waste management strategy | September 2025 | 10% | 10% | The investment feasibility studies depend on several key inputs, including the outcomes of the separation at source (S@S) pilots and the viability of the treatment technologies currently under investigation for biodegradable waste. These studies will assess these factors in detail to determine the most practical and sustainable investment options. Therefore, the completion of this output is pending the results of the S@S pilots and the finalisation of ongoing technical assessments. | MU |
| OUTCOME 5: Enhanced capability of CoJ in evidence-based policy and strategy making |  |  |  |  |  |
| Output 5.1: Indicator selection and data collection for evidenced based policy and strategy making | 29 Feb 2024 | 100% | 100% | The service provider has undertaken all activities and this has informed the development of the System. 5.1.5 The ISDP Data Sharing Protocols document have been finalized and are ready for inputting on the System at handover. System handover is anticipated to be in Quarter 3 of 2025 | S |
| Output 5.2: GIS layers & analysis for evidenced based planning | 31 Aug 2025 | 60% | 90% | All licenses have been provisioned and configured. Completion of the portal configuration and Beta deployment. Project team testing of the system completed and amendments underway. User testing and internal training planned for 14 August 2025, before launch of platform at the end of August 2025. External training opportunities will be made available after the launch. | S |
| Output 5.3: Lessons and knowledge from the project are shared for replication | 30 Sep 2025 | 60% | 80% | The Service Provider was appointed late December 2024 (Africa International Advisers). An amended work schedule was produced that permitted the completion deliverables. The draft knowledge management, marketing and communication frameworks have been produced. | S |

# 4. Risk Rating

4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating.

| Risk Factor | EA’s Rating | TM’s Rating |
| --- | --- | --- |
| 1. Management structure – Roles and responsibilities | M | M |
| 2. Governance structure – Oversight | M | M |
| 3. Implementation schedule | L | L |
| 4. Budget | M | L |
| 5. Financial Management | M | M |
| 6. Reporting | M | L |
| 7. Capacity to deliver | L | M |

If any of the risk factors is rated a Moderate or higher, please include it in table B below.

4.2 Table B. Risk-Log

| Risk | Risk affecting: | Risk Rating |  |  |  |  |  |  |  | Variation respect to last rating |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 | PIR 6 | PIR 7 | Δ | Justification |
| Risks identified at CEO Endorsement |  |  |  |  |  |  |  |  |  |  |  |
| Economic changes such as large depreciation of local currency; rising inflation and interest rates; increasing prices of inputs, labour. Project implementation hindered / collapsed by increased costs, negatively affecting financial viability of planned work. (esp. biogas plant – imported equipment) | All | N/A | L | M | M | M | M | M | M | = | The country’s economic growth path is declining, with rising inflation and interest rates and a depreciation of local currency. These trends have had an impact on component 1 (the initial intent of the project being able to attract a developer in the eco-district) and 4 (cost of the biogas plant). It has influenced costs - infrastructure and operating costs (component 3), which means less can be done with budgets allocated. |
| Biogas – Regulatory environment: Environmental authorizations and compliance. Delay in implementation due to environmental authorisations, licensing and permitting | Outcome 4 | N/A | L | L | L | L | L | L | L | = | The risk remains low as the project team is working closely with regulatory authorities, prioritising clear communication and coordination to expedite approvals and ensure compliance for timely project implementation. |
| Biogas - Waste stream not contractually secure. Project progress hindered by a break in the chain for supply of biogas. | Outcome 4 | N/A | L | L | L | L | / | L | L | = | The City is engaging with private organic waste generators, through its owner's engineers, to secure waste off-take agreements, and ensure feedstock security |
| Biogas - Ownership Risks: Uncertainty over who will continue to operate and own the waste facility after the initial 12-month period. Project collapse. | Outcome 4 | N/A | L | L | M | M | / | M | M | = | The City and UJ are currently finalizing an MOU. |
| There is no viable business model for biogas production from city waste streams The operation of the pilot biogas plant stops and there is no replication | Outcome 4 | N/A | L | L | L | L | / | L | L | = | The City through DBSA has appointed the Owner’s Engineer to do a prefeasibility study and develop a term of reference for the appointment of the Transactional Advisory Team to undertake a bankable feasibility for the upscaling of the 50ton pilot plant to 350 000tons biogas plant. Terms of Reference (Vol 3) completed and submitted |
| Funding risk: funding withdrawn or depleted or funding for future continuation not secured. Project collapse due to lack of funding. | All | N/A | L | M | L | L | L | L | L | = | The City continues to make budget available in its budgeting process to co-fund the project. The GEF grant has also been utilized as funding. City personnel to be capacitated during implementation and operation processes to ensure the City participate in future operations and maintenance. |
| In Outcome 3, Participants do not engage in project activities There may be no uptake by farmers resulting in underperformance of the project | Outcome 3 | N/A | L | L | L | L | L | L | L | = | Lengthy procurement processes from the City still prove to be a discouraging to farmers, albeit contracts being signed to ensure commitment and participation. The City is continuously improving by pursuing legally sound avenues to fast-track the procurement processes |
| Procurement and supply chain management delays Delays in equipment procurement and hiring of requisite personnel | All | N/A | L | S | M | L | L | L | L | = | Component 2 has utlised internal JOSCHO panel for the appointment of service providers which has reduced timelines in procurement process. Component 3 and 5 have partnered with the JDA to facilitates procurement processes where possible and personnel make themselves available to engage farmers in all developments in order to maintain their commitment to the project. |
| Changes in political leadership at city level. Project might see a change in internal support from the municipality | All | N/A | L | M | M | L | L | L | L | = | The project is not linked to political heads and is linked to the administrative offices of the City. It is well aligned with political priorities (food security, social housing, smart city initiatives). |
| The project is not able to attract a developer in the eco-district. The innovative planning approach cannot be tested and therefore would not be replicated along the Corridors of Freedom. | Outcome 1 | N/A | L | L | S | L | L | L | L | = | The risk is rated low because the focus has shifted away from trying to attract private sector developers towards capacitation of private sector professionals through public sector projects. This new focus is reflected in the workplan and budget revision 4 and currently 5 templates presented at the 4th PSC meeting convened on 24 November 2023. |
| The project is not able to recommend improvements on JOSHCO social housing commissioning process JOSHCO designs do not translate to the construction stage | Outcome 2 | N/A | L | L | L | L | L | L | L | = | JOSHCOs improved design case and technical specifications for the retrofits and greenfield developments will be monitored during the construction stage and be assessed and monitored afterwards to establish improvements between the base case and improved case using the EDGE Tool as a standard measure. |
| The project is not able to identify energy saving technical solutions for the retrofit or new buildings that are cost effectiveness. The JOSHCO pilots would not become standard design specifications for JOSHCO. | Outcome 2 | N/A | L | L | L | L | L | L | L | = | Design Guideline Specifications and Energy and Water savings have been clearly defined and the performance is being tested on the current Retrofitted Project, and this will influence the Technical Specification to be adopted. The monitoring to date identifies cost and energy savings with the technical solutions implemented. It has been incorporated into the proposed standards. Furthermore smart metering and monitoring systems are being procured to ensure more effective data generation which will lead to increased energy savings. |
| Municipal departments do not keep the GIS data updated. The GIS is not an up to date and reliable planning tool. | Outcome 5 | N/A | L | L | L | L | L | L | L | = | Consultation and data audit have been completed. Departments will continue to be consulted in the process throughout the development of the system to ensure their buy-in. Potential external partners have been identified to link data portal to existing systems and networks. |
| Farmers do not see the benefits of the pilots. No broader uptake of pilots within the CoJ food security programme. | Outcome 3 | N/A | L | L | L | L | L | L | L | = | The farmers have entered into contracts with the city to ensure their commitment and participation. |
| There is no demand for food products from project interventions Pilots will not be replicated | Outcome 3 | N/A | L | L | L | L | L | L | L | = | The declining economic growth and rising unemployment is increasing the demand on social support programmes, including food security and food production. |
| Risks identified in the Environmental and Social Safeguards screening |  |  |  |  |  |  |  |  |  |  |  |
| Non-compliance with environmental and land use regulations, such as the proximity to protected watercourses, may render identified sites unfeasible for infrastructure installation, leading to project delays and the need for relocation, as experienced at Innes Free Park. |  | N/A |  |  |  |  |  |  | L | = | The risk is rated low, as beneficiaries have agreed to relocate to the Northern Farms site, where existing and planned infrastructure from Innes Free Park will be consolidated to ensure continued participation. Additionally, screening and compliance have been initiated and assessments are ongoing at the remaining four sites to prevent similar regulatory issues. |
| Risks identified in the 2020 PIR |  |  |  |  |  |  |  |  |  |  |  |
| August 2021 Local government elections. A new municipal government may reduce department’s budgets which may have an impact on the ability to contribute towards the co-finance | All |  |  | M | M | M | L | L | L | = | Local government elections took place on 01 November 2022. Disruptive coalition politics, but budgets still get approved. |
| Procurement and supply chain management delays | All |  |  | S | M | L | L | L | L | = | An alternative procurement process has been determined through a partnership with the JDA, and procurements have been undertaken through the entity. Confirmation from the JDA has been received that the project has been added to the entity’s annual performance plan and annual |
| Risks identified in the 2021 PIR |  |  |  |  |  |  |  |  |  |  |  |
| City operational and capital budgets decrease as a result of severe revenue under collection due to Covid-19 | All |  |  |  | M | M | M | M | M | = | The enduring impact of a shrinking economy and the potential change of focus by the new administration could contribute to the future decrease of operational and capital budgets. The component teams have and will continuously lobby for budget provision in the city and look for opportunities to partner or attract resources from external stakeholders in order to fulfil the co-finance commitment. |
| Risks identified in the 2022 PIR |  |  |  |  |  |  |  |  |  |  |  |
| No risks identified in the 2022 PIR |  |  |  |  |  |  |  |  |  |  |  |
| Risks identified in the 2023 PIR |  |  |  |  |  |  |  |  |  |  |  |
| Absence of a dedicated Project Manager since September 2022 affects project coordination and oversight | All |  |  |  |  |  | S | L | L | = | CoJ had appointed an interim Project Manager to support project coordination and management over the course of year 2023 and 1st half of 2024. A new dedicated Project Manager was recruited in July 2024 |
| Risks identified in the 2024 PIR |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 (UNEP): Recent changes in the political leadership of the City, which in turn delay the appointment of the JOSHCO’s board may further delay the formal endorsement of the revised guidelines for new social housing development and retrofits | Outcome 2 |  |  |  |  |  |  | M | L | ↓ | The JOSHCO Board has been appointed, with permanent placements made for the Chief Operating Officer (COO) and Chief Financial Officer (CFO). Additionally, the recruitment process for the CEO has commenced, with the position advertised during this reporting period, which is expected to facilitate the formal adoption and signing of the Green Building Guidelines and Operational Manuals |
| Component 3 (UNEP): the new SCM panels via JDA could potentially cause further delays in remaining procurement activities related to urban farming component | Outcome 3 |  |  |  |  |  |  | M | L | ↓ | The procurement process for the urban farming infrastructure tender has been finalised, and service providers have been appointed. However, the CoJ will continue to closely coordinate with the JDA to ensure effective project management and timely implementation. |
| Component 4 (DBSA): Absence of a dedicated Component Lead for DBSA and onboarding process that may delay project continuity | Outcome 4 |  |  |  |  |  |  | M | M | = | No variation from the last reporting period. DBSA has not yet appointed a project manager to lead Component 4; however, interim oversight arrangements have been put in place to maintain progress and ensure continuity. |
| Cross cutting: the recommendations to improve project delivery and impact suggested during the Mid-Term Evaluation may not be fully implemented by the project team | All |  |  |  |  |  |  | M | L | ↓ | The project’s Mid-Term Evaluation exercise was completed and the MTE report included a number of recommendations to maximize the project’s impact or overcome some of the shortcomings identified. . Cross-cutting and component-based interventions, in-line with the Recommnenations, have been implemented to improve project delivery. |
| Financial: risk of COJ underspending GEF funding available for UNEP-led components. | N/A |  |  |  |  |  |  | L | S | = | In comparison to the past financial year spending has improved and is expected to climb, noting pending invoices. The processing of the pended Invoices, which is affected by internal administration issues is having an impact on the steps made to reduce underspending thus far. This risk is rated significant as pended invoices are having an impact on further activities being initiated as consultants/constructors will not proceed with work pending payment. Time constraints to complete outstanding activities are noted. |
| New risks identified in the current 2025 PIR |  |  |  |  |  |  |  |  |  |  |  |
| The City still does not have a permanent appointment in the Office of the City Manager | All |  |  |  |  |  |  |  | S |  | This is rated as a significant risk, as the absence of a permanently appointed City Manager continues to delay key project outcomes and implementation targets, potentially impacting overall project completion timelines and related budget spending. |
| JDA is slow in processing invoices for completed work which impacts the rate of expenditures reported by CoJ to UNEP | Outcome 3 and 5 |  |  |  |  |  |  |  | M |  | This risk has been rated as moderate, the Development Planning Executive Office has escalated the matter to JDA's executive management and COO. Interim measures have been implemented to ensure the timely processing of invoices for Component 3 and 5. The department will continue to closely monitor the situation to mitigate any further delays which may negatively impact project timelines. |
| The delayed countersignature by the COJ of PCA amendment 3 (between UNEP and COJ) could have a detrimental impact on project implementation | All UNEP led outcomes |  |  |  |  |  |  |  | S |  | This risk is rated significant, as this presents potential risks to have project activities frozen from 1st October 2025 onward, limiting the City’s ability to deliver on all the key component outcomes, thus affecting project impact. Continuous efforts are underway to urgently resolve the matter (before 30 September 2025 latest) and minimise any adverse impact on project implementation. |
| The City of Johannesburg’s supply chain processes may result in delays to the completion of project activities related to the certification and food mapping tenders under project component 3. | Outcome 3 |  |  |  |  |  |  |  | M |  | The certification and food mapping tenders are being procured through the CoJ supply chain processes. Given the typically longer timelines associated with these procedures, there is a potential risk that the certification process may not be completed by 30 June 2026. |
| Component 5: Complexity of the City of Johannesburg’s IT processes | Outcome 5 |  |  |  |  |  |  |  | L |  | This risk is rated low, as the project is nearing completion however this risk may pose challenges to ongoing the project implementation and maintenance. |
| Consolidated project risk |  | n.a |  | L | M | M | M | M | M |  | This section focuses on the variation. The overall rating is discussed in section 2.3. |

Table B. Outstanding Moderate, Significant, and High risks

| Risk | Actions decided during the previous reporting instance (2024 PIR) | Actions effectively undertaken this reporting period | Additional mitigation measures for the next period |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | What | When | By whom |
| Risks from the 2022 PIR |  |  |  |  |  |
| Outcome 3 – Food resilience [UNEP] |  |  |  |  |  |
| Procurement and supply chain management delays | UNEP Action 1 [2024]: TORs reconfigured to speak to rescoping. When: 30 June 2024 Advertisement of tender. When: Between July- September 2024 | Action cleared. The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed through the City implementing agent JDA in quarter 1 of 2025. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment in quarter 2 of 2025. | N/A | N/A | N/A |
| Outcome 4 – Biodegradable Waste [DBSA] |  |  |  |  |  |
| Economic changes such as large depreciation of local currency; rising inflation and interest rates; increasing prices of inputs, labour. Project implementation hindered / collapsed by increased costs, negatively affecting financial viability of planned work. (esp. biogas plant – imported equipment) | DBSA Action 1 [2024]: Scope reconfiguration | Action cleared. The project scope remains unchanged, as the City has successfully secured additional resources to close the funding gap. | N/A | N/A | N/A |
| Biogas - Ownership Risks: Uncertainty over who will continue to operate and own the waste facility after the initial 12-month period. Project collapse. | DBSA Action 2 [2023]: At Knowledge transfer for continued operational sustainability When: 2024 | Conducted high-level discussions with the City and stakeholders to clarify potential ownership and operational models. | DBSA Action 1 (2025): Facilitate institutionalisation of ownership and operational arrangements, building on the 2023 knowledge transfer initiative. This includes finalising governance structures, embedding operations within the City’s waste management framework, and securing long-term service agreements to ensure financial and operational sustainability. | 31 December 2025 – June 2026. | DBSA/CoJ |
| Risks from the 2024 PIR |  |  |  |  |  |
| Component 2 (UNEP): Recent changes in the political leadership of the City, which in turn delay the appointment of the JOSHCO’s board may further delay the formal endorsement of the revised guidelines for new social housing development and retrofits. | UNEP Action 2 [2024]: The COJ PM and component 2 lead shall organize a meeting with JOSHCO’s new leadership to present the project and the importance of ensuring the revised guidelines are endorsed. A report on the outcomes of the meeting shall be prepared and shared with UNEP before end of November 2024. When: 30 November 2024 | The ongoing briefing of Executives in acting capacities to ensure that traction is not lost despite formal appointments being made that will enable adoption of Deliverables. Meetings have been facilitated by the Component Lead and Programme Manager on different occasions: 24 October 2024, 11 and 22 November 2024. Subsequently, the JOSHCO Board has been appointed, with permanent placements made for the Chief Operating Officer (COO) and Chief Financial Officer (CFO). Additionally, the recruitment process for the Chief Executive Officer (CEO) has commenced, with the position advertised during this reporting period. | UNEP Action 1 [2025] Once the JOSHCO board is in place, organize a meeting with the board members to facilitate the official adoption and sign off of the revised guidelines for new social housing development and retrofits. | By 30 September 2025, latest | Programme Manager/CoJ |
| Component 3 (UNEP): the new SCM panels via JDA could potentially cause further delays in remaining procurement activities related to urban farming component | UNEP Action 3 [2024] JDA SCM panels’ process should be monitored by COJ. The COJ shall update UNEP on a monthly basis on the progress made with procurement. When: Monthly until procurement is completed | Action cleared. The infrastructure tender has been finalised and a main contractor (KPA Civils) has been appointed through the City implementing agent JDA in quarter 1 of 2025. Project inception has been completed which included finalising appointment documentation, conducting stakeholder and community engagements and initial site verification and site establishment in quarter 2 of 2025. | N/A | N/A | N/A |
| Component 4 (DBSA): Absence of a dedicated Component Lead for DBSA and onboarding process that may delay project continuity | DBSA Action 3 [2024]: DBSA is in the process of reconciling budgets and from there on, budget availability will determine viability of appointing a ‘new’ project lead When: 31 December 2024 | While a permanent lead has not yet been onboarded; DBSA has put in place interim oversight arrangements to maintain progress. | DBSA will continue with interim oversight arrangements while assessing budget availability for the appointment of a permanent Component 4 Lead. | Ongoing | DBSA |
| Cross cutting: the recommendations to improve project delivery and impact suggested during the Mid-Term Evaluation may not be fully implemented by the project team | DBSA Action 4 [2024] The status of implementation of MTE recommendations will be discussed between COJ, DBSA and UNEP during the next quarterly check in meeting in September 2024. When: 30 September 2024 | The status of implementation of the MTE recommendations was reviewed jointly by CoJ, DBSA, and UNEP during the quarterly check-in meeting. | N/A | N/A | N/A |
|  | DBSA Action 4 [2024]: The COJ PM will follow up with component leads on the implementation of MTE recommendations and update DBSA and UNEP on a quarterly basis, until project completion. When: Quarterly, until project completion | This remains an ongoing process, with quarterly follow-ups continuing to ensure implementation of the MTE recommendations. The emphasis has become increasingly important in 2025 as the project prepares for the Terminal Evaluation, where progress on these actions will be a key focus | Quarterly follow-ups will remain ongoing, with added emphasis on preparing for the Terminal Evaluation. Additional measures include consolidating evidence of progress, addressing any gaps ahead of the TE, and ensuring alignment with CoJ and UNEP | On-going (quarterly basis until Project completion) | DBSA |
| Financial: risk of COJ underspending GEF funding available for UNEP-led components. | UNEP Action 5 [2024] COJ shall identify potential supplementary activities that could be entertained under components 1, 2, 3 or 5 before 30 September 2025 with unspent budget – not entailing lengthy procurement process. A proposal of supplementary activities should be presented to UNEP by end of November 2024. When: 30 November 2024 | Action cleared. A financial assessment has been done for Components 1-3 and 5. This has revealed that there will be a shortfall for Component 3 for the infrastructure due to the time it has taken at procurement stage. All surplus funding will be directed to Component 2 and 3. UNEP shared a budget 5 revision template with the COJ. The COJ team prepared a draft of the budget revision to reflect the expected adjustments and shared with UNEP in quarter 2 of 2025. | N/A | N/A | N/A |
| New risks identified in the 2025 PIR |  |  |  |  |  |
| Cross cutting: The City still does not have a permanent appointment in the Office of the City Manager | N/A | N/A | UNEP Action 2 [2025] The COJ’s GFE project team will continue to engage with the Acting City Manager and senior leadership to ensure continuity in decision-making and project oversight. The COJ GEF project team will maintain a clear escalation protocol to support continued efforts to resolve GEF programme related bottlenecks without undue delays | On a monthly basis, through the remaining duration of the project | Programme Manager/CoJ |
| JDA is slow in processing invoices for completed work, which impacts the rate of expenditures reported by CoJ to UNEP | N/A | N/A | UNEP Action 3 [2025] The CoJ Programme Manager will attend the established JDA-DP Programme implementation committee on a monthly basis to ensure progress is tracked and feedback on milestones are provided in a regular basis, for timely issuance of invoices related to the GEF project. | Monthly, from July 2025 | Programme Manager/CoJ |
| The delayed countersignature by the COJ of PCA amendment 3 (between UNEP and COJ) could have a detrimental impact on project implementation | N/A | N/A | UNEP Action 4 [2025] The COJ GEF project team will continue engaging with the Acting City Manager on a weekly basis to resolve this matter. A virtual meeting shall be organized between the COJ (GEF project team, City Manager team, legal group) and UNEP to discuss and resolve the matter. | By 5 September 2025, latest. | Programme Manager/CoJ UNEP |
| The City of Johannesburg’s supply chain processes may result in delays to the completion of project activities related to the certification and food mapping tenders under project component 3. | N/A | N/A | UNEP Action 5 [2025] Bid Specification and Bid Evaluation Members have been identified. The Bid Spec Committee to consider approved ToRs by the end of August 2025.Appointment of service providers is anticipated to be completed by 30 November 2025. | 30 November 2025 | Programme Manager/CoJ |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Significant Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

# 5. Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines.

Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of the change that occurred in the textbox. You may attach supporting document as appropriate.

5.1 Table A: Listing of all Minor Amendment

| X | Results framework |
| --- | --- |
| X | Components and cost |
|  | Institutional and implementation arrangements |
|  | Financial management |
| X | Implementation schedule |
|  | Executing Entity |
|  | Executing Entity Category |
|  | Minor project objective change |
|  | Safeguards |
|  | Risk analysis |
|  | Increase of GEF project financing up to 5% |
|  | Co-financing |
| X | Location of project activity |
|  | Other |

| Minor amendments | Results framework: as part of project revision 3 (UNEP) that occurred in 2022, a minor adjustment had been made to the outcome 1 statement. The outcome had been changed from “CoJ test eco-district prototypes to set improved environmental standards for TOD Corridors” to “CoJ test eco-district prototypes to set improved environmental standards for City of Johannesburg”. Components and cost: as part of the project revision 5 (UNEP), budgetary reallocations have been made, including shifting funds between components 1 and 5 to meet emerging needs. These changes are not foreseen to affect the project’s ability to meet the expected outcomes 1 and 5. As part of revision 4 -Component 4.3 of the project was restructured to divide the biogas construction task into separate activities. This change allowed for the flexibility to implement multiple activities simultaneously and enables various qualified consultants to undertake the work, rather than having one large task that no one in the market could qualify for. Implementation schedule: as part of project revision 5 (UNEP), the timeline of a few activities under components 1, 2, 3 and 5 has been revised. The project’s technical completion is now 30 June 2026. Location of project activity: Following the EISD recommendation to halt the Innes Free Park project site, the project site will no longer be utilised and the beneficiaries and existing and planned urban farming infrastructure have been relocated to Northerns Farms. |
| --- | --- |

5.2 Table B: History of project revisions and/or extensions

| Version | Type | Signed / Approved by UNEP | Entry into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
| Original legal instrument |  |  | 12 March 2018 | 31 August 2022 | N/A |
| Amendment 1 / Extension 1 | Revision 1 | 18 September 2019 | 17 October 2019 | 31 October 2025 | Extension of the project’s technical completion date to 30 June 2024 to factor in the CoJ’s delays in setting up the Project Management Unit and hiring the Project Manager. |
| N/A | Revision 2 | 23 April 2021 | N/A | 31 October 2025 | Reorganization of the project’s budget and workplan to factor in the delays related to lengthy procurement processes and the Covid-19 related restrictions. Technical completion date remains the same as in Rev1. |
| Amendment 2 / Extension 2 | Revision 3 | 28 June 2022 | 27 July 2022 | 30 September 2026 | Revision of the project’s budget and workplan to factor in the delays related to the CoJ’s lengthy procurement processes, the Covid-19 related restrictions and the greenfield social housing construction works. New technical completion date: 30 September 2025 |
| N/A | Revision 4 | 11 November 2023 | N/A | 30 September 2026 | Revision of the Project Budget and workplan to factor in delays related to the CoJ’s lengthy procurement processes. Technical completion date remains 30 September 2025. |
| Amendment 3/ Extension 3 | Revision 5 | 15 May 2025 | (awaiting CoJ counter-signature) | 30 June 2027 | Extension of the project’s technical completion date to enable completion of all project activities. This also includes a revision to the timelines of project activities and outputs in the workplan to factor in the delays in implementation of pending activities and to reflect actual expenditures as reported by CoJ. Ne w technical completion date: to 30 June 2026, |

# 6. GEO Location Information

The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please see the Geocoding User Guide by clicking here

| Location Name Required field | Latitude Required field | Longitude Required field | Geo Name ID | Location Description Optional text field | Activity Description Optional text field |
| --- | --- | --- | --- | --- | --- |
| Component 1: Orange Grove | -26.16184 | 28.09011 |  | Neighbourhood and Special Development Zone as identified in City Policy (Louis Botha Strategic Area Framework) | Emissions Modelling, Baseline, Pathways and interventions design at site, block, precinct and neighbourhood levels. |
| Component 2: Tshedzani 3. Olivier St, Roodepoort, Johannesburg | -26.1642017 | 27.8697771 |  | Existing Residential Complex corner Olivier Street and Dumat Street. | Solar photovoltaics and Solar geysers installed on Roof tops for micro energy generation stored in lithium ion batteries. |
| Component 3: Siyakhana Project | -26.183816 | 28.092409 |  | Located within Bezuidenhout park | Organic farming practice |
| Component 3: Danny Van Zyl | -26.176557 | 27.960783 |  | Danny Van Zyl Community Hall | Organic farming practice |
| Component 3: Braamfischer Project | -26.210822 | 27.849376 |  | Braamfisherville area | Organic farming practice |
| Component 3: Gold Soil/Kopanong project | -26.218342 | 27.884791 |  | Meadowlands community wall property next to the meadowland clinic. | Organic farming practice |
| Component 3: Slovoville Project | -26.213465 | 27.776819 |  | Slovoville primary school | Organic farming practice |
| Component 3: Eikenhof projects (Northern Farms) -Molobanyane -Ndimo -NFS -Shapathupa / Modiyanyebo | -26.338826 | 28.011793 |  | Eikenhof farm opposite red farmers property | Organic farming practice |
| Component :4 Robinson Deep Landfill site | - 26.231353020087067 | 28.042627862561705 |  |  | Biodigester Site; Landfill Gas |
| Component 5: City of Johannesburg Metropolitan Municipality | -26.191163 | 28.039907 |  | Head Office of the City of Johannesburg Metropolitan Municipality | Evidence based planning, including developing a spatial data portal and spatial plan management system for the City of Johannesburg |

Please provide any further geo-referenced information and map where the project interventions are taking place as appropriate. *

N/A

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Numeric, percentage, or binary entry only

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

This outcome statement has been updated in line with the Results Framework revision No. 2

Outputs and activities (or deliverables) as described in the project logframe and as per UNEP workplan revision 5.

The completion dates should be as per latest UNEP workplan revision 5.

To be provided by the DBSA / UNEP Task Manager