## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 4
5

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Africa (RAF)
Country(ies): | Benin
Project Title: | Strengthening capacity in the energy, agriculture, forestry and other land-use sectors for enhanced transparency in the implementation and monitoring of Benin's Nationally Determined Contribution
FAO Project Symbol: | GCP /BEN/060/GFF
GEF ID: | 10156
Type of Trust Fund(s): | CBIT, GFF
GEF Focal Area(s): | Climate Change Mitigation
Project Executing Partners: | Ministère du Cadre de Vie et des Transports, chargé du développement durable (MCVT) of the Republic of Benin
Initial project duration (years): | 3
Project Dates
GEF CEO Endorsement Date: | 2021-03-31
Actual Agency Approval Date | 2021-11-16
Project Implementation Start Date/EOD: | 2022-02-01
First Disbursement Date | 2022-10-31
Planned Project End Date/NTE1: | 2025-02-01
Revised project implementation End date (if approved)2: | 31/12/2025
Actual Completion Date: | n/a
Expected Financial Closure Date: | 31/122026
Funding
GEF Grant Amount (USD): | 1319863
Total GEF grant delivery (as of June 30, 2025 (USD): | 980029.72
Total Co-financing amount (USD)3: | 460000
Total estimated co-financing materialized as of June 30, 20254: | 460000
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 2025-05-07
Expected Mid-term Review date5: | n/a
Actual Mid-term review date (if already completed): | n/a
Expected Terminal Evaluation Date6: | ongoing
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Moderately Satisfactory (MS)
Overall implementation progess rating: | Satisfactory (S)
Overall risk rating: | Low
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 3rd PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Akpovo, Edgard Romaric (MCVT) National Project Coordinator CBIT-BENIN |  | akpovoromaric@gmail.com
Budget Holder (BH) | AngueObama, Isaias (FAOBJ) FAO REPRESENTATIVE |  | isaias.angueobama@fao.org
GEF Operational Focal Point (GEF OFP) | Boni Yalla, Memanton (MCVT) Director of Planning, Administration and Finances |  | mboniyalla@gouv.bj
Lead Technical Officer (LTO) | Bouda, Zoewinde (FAOSFW) FORESTRY OFFICERA Alternate: w, Mohamadou (NFOU) PROGRAMME OFFICER |  | zoewinde.bouda@fao.org / mohamadou.aw@fao.org
GEF Technical Officer (GTO) | Ogunkua, Nifesimi (FAONG) Climate Change and GEF Portfolio Support Expert |  | nifesimi.ogunkua@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
Coordonnateur National | Yes | 08 AUG 2022 AKPOVO Kocou Edgard Romaric akpovoromaric@gmail.com |  | National Consultant
Assistant Technique MRV | Yes | 08 AUG 2022 AMOU Martial martial.amou@yahoo.com |  | National Consultant
Responsible en suivi-evaluation | Yes | 08 AUG 2022 KEKE Djidjoho Diane djidjohodiane@gmail.com |  | National Consultant
Assistant administratif et financier | Yes | 08 AUG 2022 HOUEGNON Sèdéton Euloge sedetoneulogeh@gmail.com |  | National Consultant
Specialiste en communication et gestion des connaissances | Yes | 08 AUG 2022 AYOLA Olayemi Lydia ayolalydia@gmail.com |  | National Consultant
Specialiste Genre | Yes | 31 MAR 2023 SEGBEMON Ahignongbé Christiane Malvina segbemonmalvina@gmail.com |  | National Consultant
Specialiste gestion des infrastructures de données | Yes | 01 SEP 2023 DOTONOU Agossou Tétédé Cosme cosme.dotonou@gmail.com |  | National Consultant

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
Strengthening capacity in the energy, agriculture, forestry and other land-use sectors for enhanced transparency in the implementation and monitoring of Benin's Nationally Determined Contribution | Outcome 1.1: Institutional arrangements enhanced for coordinating information and data from the energy and AFOLU sectors into ETF processes and reports | Number of institutions with ability to respond to the requirements of the ETF in a coordinated way | 0 | At least 1 | At least 2 | 10 | 100% | Highly Satisfactory (HS)
| Output 1.1.1: Assessment prepared regarding institutional arrangements, data collection, analysis and reporting capacity gaps and needs for meeting ETF requirements with specific focus on the priority NDC actions for the energy and AFOLU sectors | Number of staff in relevant positions who are interviewed for the assessment | 0 | 10 | At least 20 | 20 | 100% | Highly Satisfactory (HS)
| Output 1.1.2: Awareness raised amongst the energy and AFOLU sectors policy makers and practitioners on mainstreaming institutional arrangements in the ETF processes | Number of staff in relevant positions who participated in awareness raising events delivered by the project | 0 | At least 50% of the core staff at MCVDD, MAEP and ME designated to be part of the inventory team participating in at least one capacity development event | At least 75% of the core staff at MCVDD, MAEP and ME designated to be part of the inventory team participating in at least one capacity development event | 60.57% | 60.57% | Moderately Satisfactory (MS)
| Output 1.1.3: A roadmap for achieving the ETF institutional arrangements for the energy and AFOLU sectors prepared and adopted | Number of roadmap completed | 0 | 1 | 1 | 1 | 70.66% | Moderately Satisfactory (MS)
| Output 1.1.4: A sustainable multi-sectoral coordination mechanism strengthened integrating relevant institutions/ stakeholders into national UNFCCC reporting processes. | Number of relevant institutions involved | 0 | 2 | At least 3 | 10 | 100% | Highly Satisfactory (HS)
| Outcome 1.2: Data and information collection, QA/QC processes and system infrastructure enhanced | Degree of improved institutional capacity and infrastructure in data processing and archiving | 0 | 1 | 1 | 1 | 75% | Satisfactory (S)
| Output 1.2.1: Best practices on data and information acquisition and system infrastructure in the energy and AFOLU sectors collected and shared with other relevant priority sectors | Number of best practices identified and shared | 0 | 3 | At least 5 | 4 | 80% | Satisfactory (S)
| Output 1.2.2: Regular and systematic documentation and archiving procedures as well as quality assurance and quality control processes improved to ensure accuracy and sustainability of MRV and M&E systems in the energy and AFOLU sectors | Number of improved procedures/processes | 0 | 1 | At least 2 (common documentation and archiving procedure and improved QA/QC plan taking into account all components of the climate change report - inventory, monitoring of mitigation and adaptation measures and support received) | 2 | 85% | Satisfactory (S)
| Output 1.2.3: Information management system and infrastructure for the energy and AFOLU sectors upgraded | Number of improved systems | 0 | 2 | At least 3 | 1.5 | 50% | Moderately Satisfactory (MS)
| Outcome 2.1: Monitoring of NDC mitigation activities and reporting on inventories of greenhouse gases from the energy and AFOLU sectors strengthened | Degree of increased institutional capacity on the enhanced transparency framework | 0 | 1 | At least 1 national/ sectoral report prepared integrating tracking of progress in the implementation of NDC mitigation activities | 1 | 85% | Satisfactory (S)
| Output 2.1.1: Technical capacity enhanced for relevant institutions to adopt and mainstream ETF-enhanced MRV Global Products and other international tools for monitoring, reporting and verifying the implementation of priority NDC mitigation activities from the energy and AFOLU sectors | Number of beneficiaries from capacity building activities developed by the project (disaggregated by gender) | 0 | At least 30% of the core staff at MCVDD, MAEP and ME designated to be part of the inventory team participated in at least one capacity development event | At least 75% of the core staff at MCVDD, MAEP and ME designated to be part of the inventory team participated in at least one capacity development event | 80% | 80% | Satisfactory (S)
| Output 2.1.2: Knowledge of methodologies to collect activity data increased and country-specific emission factors developed in the energy and AFOLU sectors | Number of staff with demonstrated increased capacity | 0 | At least 10 | At least 20 | 17 | 85% | Satisfactory (S)
|  | Number of emission factors developed | 0 | At least 1 | At least 1 | 0 | 90% | Moderately Satisfactory (MS)
| Output 2.1.3: National/sectoral reports prepared and submitted on inventory of greenhouse gases from the energy and AFOLU sectors consistent with latest UNFCCC reporting guidelines. | Number of sectoral reports produced | 0 | 1 | At least 2 | 3 | 96.15% | Satisfactory (S)
| Outcome 3.1: Monitoring and evaluation of NDC priority adaptation actions in the energy and AFOLU sectors strengthened sectors | Number of national/ sectoral reports integrating the M&E framework | 0 | 0 | At least 1 | 1 | 50% | Moderately Satisfactory (MS)
| Output 3.1.1: Technical capacity enhanced in relevant institutions to adopt and mainstream ETF-enhanced M&E Global Products and other international tools for monitoring and evaluating NDC priority adaptation actions in the energy and AFOLU sectors | Number of beneficiaries from capacity building activities delivered by the project (disaggregated by gender) | 0 | At least 30% of core staff at MCVDD, MAEP and ME designated to the GHG inventory team and NDC research team have participated in at least one capacity-building event. | At least 75% of core staff at MCVDD, MAEP and ME designated to the NC, BUR and NDC research teams have participated in at least one capacity-building event. | 67,16% | 67.16% | Moderately Satisfactory (MS)
| Output 3.1.2: National/sectoral appropriate indicators and monitoring and evaluation framework developed for NDC priority adaptation actions in the energy and AFOLU sectors | Number of M&E indicators developed/selected | 0 | 2 | At least 5 | 3 | 60% | Moderately Satisfactory (MS)
|  | Number of staff trained on M&E framework | 0 | 10 | At least 20 | 8 | 40% | Moderately Unsatisfactory (MU)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
76.36% | 120.6% | 74.25%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Satisfactory (S) | Moderately Satisfactory (MS) | Moderately Unsatisfactory (MU) | Satisfactory (S) | Moderately Unsatisfactory (MU)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The PMU is satisfied with the project results despite concerns about recurring delays in the availibility of funds transferred by FAO. This situation is due to the procedures of the national Treasury Department where the project bank account is held. The project team is working to implement adaptation measures to address this critical challenge and move the project forward. | The project was subjected to a 12-month no-cost extension and progress toward logframe's indicators seems not on tracked despite the PMU's optimism. Some doubts about the achievement of all targets by the new NTE. | The measure put in place for funds transaction in the country has slowed down the access on time of the project funds by the implementing agency. | No comments | The project has delivered significantly on its outcomes, it is expected that the remaining outcomes will be achieved within the project’s no-cost extension period
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
All outcomes |  | Find an arrangement with the government for ease the projects implementation |  | FAOR in contact with RC and other UN agencies |  | ASAP
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.1: Institutional arrangements enhanced for coordinating information and data from the energy and AFOLU sectors into ETF processes and reports
Output.1.1.1: Assessment prepared regarding institutional arrangements, data collection, analysis and reporting capacity gaps and needs for meeting ETF requirements with specific focus on the priority NDC actions for the energy and AFOLU sectors | Number of staff in relevant positions who are knowledgeable about ETF and related institutional responsibilities, ETF, data collection, analysis and reporting requirements | 8 |  |  | N/A
Output 1.1.2: Awareness raised amongst the energy and AFOLU sectors policy makers and practitioners on mainstreaming institutional arrangements in the ETF processes | Number of staff in relevant positions who participated in awareness raising events delivered by the project | 12 |  |  | N/A
Output 1.1.3: A roadmap for achieving the ETF institutional arrangements for the energy and AFOLU sectors prepared and adopted | Availability of legal or other type of provisions defining ETF-compliant institutional arrangements | In progress |  |  | N/A
Output 1.1.4: A sustainable multi-sectoral coordination mechanism strengthened integrating relevant institutions/ stakeholders into national UNFCCC reporting processes. | Number of relevant institutions involved | 10 |  |  | N/A
Outcome 1.2: Data and information collection, QA/QC processes and system infrastructure enhanced
Output 1.2.1: Best practices on data and information acquisition and system infrastructure in the energy and AFOLU sectors collected and shared with other relevant priority sectors | Number of best practices identified and shared | 4 |  |  | N/A
Output 1.2.2: Regular and systematic documentation and archiving procedures as well as quality assurance and quality control processes improved to ensure accuracy and sustainability of MRV and M&E systems in the energy and AFOLU sectors | Number of improved procedures/processes | 2 |  |  | N/A
Output 1.2.3: Information management system and infrastructure for the energy and AFOLU sectors upgraded | Number of interconnected nodes | In progress |  |  | N/A
Outcome 2.1: Monitoring of NDC mitigation activities and reporting on inventories of greenhouse gases from the energy and AFOLU sectors strengthened
Output 2.1.1: Technical capacity enhanced for relevant institutions to adopt and mainstream ETF-enhanced MRV Global Products and other international tools for monitoring, reporting and verifying the implementation of priority NDC mitigation activities from the energy and AFOLU sectors | Number of beneficiaries from capacity building activities developed by the project (disaggregated by gender) | 12 |  |  | N/A
Output 2.1.2: Knowledge of methodologies to collect activity data increased and country-specific emission factors developed in the energy and AFOLU sectors | Number of staff with demonstrated increased capacity | 5 |  |  | N/A
| Number of emission factors developed | In progress |  |  | Here, the focus will no longer be on developing emission factors, but rather on developing the methodology for developing emission factors; selecting and encouraging institutions capable of doing so. (methodologies currently being finalized)
Output 2.1.3: National/ sectoral reports prepared and submitted on inventory of greenhouse gases from the energy and AFOLU sectors consistent with latest UNFCCC reporting guidelines. | Number of sectoral reports produced | 3 sectorial reports (agriculture, forestry, energy) |  |  | N/A
Outcome 3.1: Monitoring and evaluation of NDC priority adaptation actions in the energy and AFOLU sectors strengthened
Output 3.1.1: Technical capacity enhanced in relevant institutions to adopt and mainstream ETF-enhanced M&E Global Products and other international tools for monitoring and evaluating NDC priority adaptation actions in the energy and AFOLU sectors | Number of beneficiaries from capacity building activities developed by the project (disaggregated by gender) | 4 |  |  | N/A
Output 3.1.2: National/sectoral appropriate indicators and monitoring and evaluation framework developed for NDC priority adaptation actions in the energy and AFOLU sectors | Number of M&E indicators developed/selected | 3 |  |  | N/A
| Number of staff trained on M&E framework | 0 (training not yet started as of June 30, 2025) |  |  | N/A
Output 3.1.3: National reports prepared on priority adaptation activities in the energy and AFOLU sectors consistent with the latest ETF available guidance. | Number of sectoral reports integrating ETF principles developed | 2 reports in progress (biennial transparency report, 4th national communication) |  |  | N/A
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Moderately Satisfactory (MS) | Moderately Unsatisfactory (MU) | Satisfactory (S) | Moderately Satisfactory (MS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The PMU is satisfied with the project results despite concerns about recurring delays in the availibility of funds transferred by FAO. This situation is due to the procedures of the national Treasury Department where the project bank account is held. The project team is working to implement adaptation measures to address this critical challenge and move the project forward. | The project was subjected to a 12-month no-cost extension and progress toward logframe's indicators seems not on tracked despite the PMU's optimism. Some doubts about the achievement of all targets by the new NTE. | The measure put in place for funds transaction in the country has slowed down the access on time of the project funds by the implementing agency. | No Comments | Despite some initial delays in accessing funds, the project has made significant progress. Nonetheless, the PMU team will need to further expedite implementation to ensure activities are completed within the no-cost extension period
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The progress made in the implementation of the project during the period under review is as follows: The implementation of the Capacity Building Initiative for Transparency (CBIT) in Benin has made significant progress: 42 of the 51 planned activities have been fully implemented to date and important milestones have been achieved. Improvement of institutional arrangements Following the inconclusive validation workshop (validation not pronounced) of the proposals for improvement in terms of institutional arrangements (institutional arrangements, multisectoral coordination mechanisms, implementation roadmaps, capacity building plan, etc.), the consultant has integrated the observations and suggestions and the final validation is expected soon. At the same time, regulatory acts (orders, decrees, partnership agreements) are being drafted and are benefiting from consultations with the parties involved. Implementation of an MRV information management system After the design of the system (functional architecture, activity diagram, user case diagram, model), the list of material and equipment needs expressed by the sectors and validated by the Ministry's Department of Information Systems (DSI/MCVT) was sent to FAO for acquisition. The latter has just launched the procurement process. Capacity building on MRV emissions - mitigation The draft report on the proposed improvements (methodological guide, procedures manual, QA/QC protocol, archiving and documentation protocol, capacity-building plan and materials, etc.) has been tabled and is awaiting validation. Following the training of the AFOLU and Energy sectoral groups on the requirements of the ETF and GHG inventory tools and methodologies, the sectors benefited from continuous support in the preparation of the national GHG inventory as part of the development of the BTR1 (improvement of spreadsheets, readjustment of time series, disaggregation of certain data, etc.). AFOLU sectors have also received training on MRV mitigation, BTR requirements and tools such as NEXT and the NDC tracking tool. Capacity building on ES adaptation The draft report on the proposed improvements (updating of indicators, proposal for a monitoring and evaluation system) has been submitted and is awaiting validation.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The major challenge in the implementation of this project remains the management and quarterly fundraising mode which amplifies the consequences of late transfers on implementation.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it.
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results?

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low
New environmental and social risks. | None
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | Due to its thematic and institutional nature, the initiative is inherently consistent with environmental and social standards. Activities focused on capacity-building and improved transparency systems contribute positively to the achievement of environmental and social objectives. Continued compliance with the principles of the ESMP is ensured through regular monitoring and integration of environmental and social considerations into all phases of the initiative's implementation.
Grievance Redress Mechanism (GRM) | None

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Political |  | Low | Yes | Lack of political will to support the project activities due to change government
2 | Institutional |  | Substantial | Yes | Lack of coordination among concerned ministries and local government authorities
3 | Institutional |  | Moderate | Yes | Limited cooperation on data and information sharing among stakeholders
4 | Political |  | Moderate | Yes | Inability for the government to fund the ETF related activities beyond the project cycle
5 | Social |  | Moderate | Yes | Gender mainstreaming hindered by resistance from local and national stakeholders
6 | Environmental |  | Moderate | Yes | Transparency related work loses momentum as the Paris Agreement is not adopted
7 | Environmental |  | Low | Yes | Climate
8 | Social |  | Low | Yes | COVID and other pandemics
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Low | Low | There are no major dangers that could constitute an obstacle to this project. Nevertheless, constant vigilance is required to maintain the positive trajectory of the project
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework
Components and cost
Institutional and implementation arrangements
Financial management
Implementation schedule
Executing Entity
Executing Entity Category
Minor project objective change
Safeguards
Risk analysis
Increase of GEF project financing up to 5%
Co-financing
Location of project activity
Other minor project amendment (define)
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Ministère du Cadre de Vie et des Transports, en charge du développement durable (MCVT) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Ministère de l'Agriculture, de l'Élevage et de la Pêche (MAEP) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Ministère de l'Énergie (ME) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Ministère des Affaires Sociales et de la Microfinance (MASMF) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Comité National sur les Changements Climatiques (CNCC) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Ministère de l'Enseignement Supérieur et de la Recherche Scientifique (MESRS) | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Government Institutions | Ministère de la Décentralisation et de la Gouvernance Locale (MDGL) /ANCB | Direct Beneficiary (Government Institution/Agency) | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
NGOs | ONG UPE | Collaboration | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
NGOs | ONG PRO ENVIRONNEMENT | Collaboration | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Private Sector entities | Chambre de Commerce et de l'Industrie du Bénin (CCIB) | Collaboration | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation
Others | Contact persons | Collaboration | Presence as a member of the PSC and the Technical Committee. Strategic direction and technical support of the project. Participation in the implementation of corrective actions identified during the diagnostic evaluation

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | Integration of parity and equitable access to resources criteria into the proposed MRV institutional arrangements. Development of gender-disaggregated indicators and data in data collection sheets and methodologies and monitoring procedures.
b. Improving women's participation and decision making | Yes | Organization of capacity-building workshops with moderate gender balance among sectoral participants. Proposal for quotas for women's representation in committees and decision-making bodies.
c. generating socio-economic benefits or services for women | Yes | Development of consultation protocols and indicators systematically including women's groups in the evaluation of climate actions
Any other good practices on gender | Yes | Training of sectoral teams on gender analysis applied to MRV. Revision of methodological guides to include gender sensitivity checklists in all proposed MRV procedures.

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | Not Applicable
If NO, how does the project identify, collect and document good practices? | Related elements were incorporated into the communication strategy developed and validated. It is planned to collect, structure, archive, share and update best practices
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | In terms of project management, several good practices have been put in place for the success of the project: Knowledge Management, Collaboration and Communication: • Creation of a SharePoint space for data sharing and archiving of finalized media • Setting up a Google Drive for document sharing to facilitate collaboration • Organize WhatsApp forums and exchange meetings via Teams or Google Meet for smooth and seamless communication • Collective management of difficulties with the assurance that all media use a predefined chain and a mainly thematic initiative • Setting up an internal hard drive to back up project resources • Developed and shared summaries and key messages in the form of flyers and brochures Technical innovations: • Introduction and training on new tools (NEXT, NDC Tracking Tool, etc.) to members of the national reporting clusters • Provision of the FAO self-learning platform on the NEXT tool • Development of the national MRV platform currently underway • Cloud archiving and free access to the tools and materials of the various training sessions • Continuous online support of the AFOLU and Energy sectoral groups in the preparation of the first biennial transparency report and the Fourth National Communication • Updating and development of the procedures manual on inventories and mitigation assessment (pending validation) • Development of a Monitoring and Evaluation system for adaptation actions (pending validation) Institutional innovations: • Proposal for a new institutional arrangement (pending validation) • Drafting of legal and regulatory acts on MRV (awaiting signature)
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | During the period under review, we worked hard to strengthen the visibility and notoriety of the initiative, in particular through: - strong media coverage organized around the various activities; - the involvement of media focal points for a greater effect of media coverage; - an awareness and popularization campaign initiated and currently being deployed; - the various social media accounts of the initiative regularly updated and used to make useful information available and mark a real presence of the initiative via the web, - a video element in progress to retrace the journey of the initiative and highlight the achievements; - communication and awareness-raising materials to be used for the upcoming wave of capacity-building, currently being designed, - the production of a radio-based thematic programme. The main communication challenges this year are as follows: - ensure permanent cohesion within the management unit; - Successfully finalize the production of the video element in progress; - ensure greater visibility of the initiative's actions and interventions; - Establish a reliable system for the sustainability of achievements; - Ensure the effective implementation of as many of the residual activities of the Communications Strategy as possible before the end date of the Initiative.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | None (As the project is essentially thematic, none of the technical activities implemented to date has allowed us to have a direct impact on the living conditions of the populations).
Please provide links to related website, social media account | https://www.facebook.com/share/v/1FzMuvrgyC/ https://www.facebook.com/share/p/1Rx8ymUpz4/ https://www.facebook.com/share/p/1E5AFpTd3V/ https://reportermediasmonde.com/pour-une-meilleure-coordination-des-donnees-sur-les-emissions-de-gaz-a-effet-de-serre/ Système Mrv/Transparence climatique: La Cbit renforce les capacités des institutions nationales https://www.facebook.com/lanationbenin?mibextid=ZbWKwL https://youtu.be/rhDPA6xtA6k?si=d8F_O0rygcssfh9x https://www.youtube.com/live/LPHttr5EwQY?si=pjgF9pd6mGjNs0rx https://lepotentiel.bj/2025/04/16/pour-repondre-aux-exigences-du-cadre-de-transparence-renforcee-de-laccord-de-paris-les-experts-nationaux-des-structures-techniques-a-lecole-du-mrv-a-lokossa/ https://www.facebook.com/share/p/1Z2paEmwuh/ https://www.facebook.com/share/p/16kCHZ9vGW/ https://www.facebook.com/share/p/16awCpLxUh/ https://www.facebook.com/share/p/19K8b11Sce/ https://www.facebook.com/share/p/15of5sNHak/ https://lanation.bj/actualites/systeme-mrv-et-transparence-les-avancees-de-linitiative-cbit-presentees-aux-cadres-sectoriels?fbclid=IwY2xjawJ406RleHRuA2FlbQIxMQABHomiP2IHXDPmOOKBqBUrbr5t--_mnqSbmBnP1sj7U57399V5T9pmwtayYabq_aem_5T_PO2Iiy-fyJTH88tJCuw&sfnsn=wa Dr Martial Amou au sujet de la transparence climatique: « Elle est essentielle pour la gouvernance des changements climatiques » https://youtu.be/FRmjeVu9QSI?si=SHVZMTh5gcvSoS3w https://lepotentiel.bj/2025/04/26/systeme-mrv-et-transparence-climatique-la-maquette-et-larchitecture-du-futur-systeme-national-de-gestion-informatique-des-donnees-climatiques-exposee/
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any.
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Mrs. AYOLA Olayèmi Lydia Communication and Knowledge Management Specialist of the CBIT-Benin Project E-mail: ayolalydia@gmail.com / cbit.benin@gmail.com Phone: +229 01 97 14 17 51 / +229 01 95 23 74 73

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. The project works closely with local communities, who are an integral part of the steering and technical committees. They are represented by the Association of Municipalities of Benin and actively participate in the project's activities.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | Ministère du Cadre de Vie et des Transports, in charge of sustainable development (MCVT) | In-kind | 10000 | 10000
GEF agency | FAO | In-kind | 250000 | 250000
GEF agency | FAO | Grant | 200000 | 200000
Total |  | Total | 460000 | 460000
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report?
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*
Direction Générale de l'Environnement et du Climat, Ministère du Cadre de Vie et des Transports, en charge du développement durable (MCVT) | 63539739 | 24313757 |  | Headquarters of the Project Management Unit in Cotonou, Benin

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.