The Federation of Malaysia

Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM)

# Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM)

Mid-term Review Report

| Type of mission | Mid-term Review (MTR) |
| --- | --- |
| Project Name | Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM) |
| Country | The Federation of Malaysia |
| Executing Agency | Ministry of Natural Resources and Environmental Sustainability (NRES) Implemented by Forestry Department of Peninsular Malaysia |
| Name of Project Director | Dato’ Hj. Roslan bin Rani |
| Name of Project Manager | Dr. Ahmad Ainuddin bin Nuruddin |
| Date of mission (month/year) | 19-30 August 2024 |
| Project Area: | Selangor, Pahang, Sarawak, Sabah State |
| Days in the field | 6 days (19 – 25 August 2024) |
| Field sites visited | Selangor (Northern Selangor Landscape), Pahang (Pekan landscape), Sarawak (Maludam Landscape), Sabah (Klias Peninsula Landscape) |
| Mission composition | Independent consultant: Mr. Peter Situ and Mr. Praise Uke IFAD: Ms. Yumi Sakata, Program Officer, IFAD Indonesia ICO, Mr. Gadzi Murad Abdulvadudov, IFAD Financial Management Specialist, APR, Mr. Muhammed Iskandar, Country Programme Analyst/ Procurement reviewer, IFAD Indonesia ICO, Ms. Chiara Merola, Programme Analyst/ Junior Professional Officer, IFAD Indonesia ICO, Mr. Dudy Nugroho, Natural Resources Specialist, IFAD Indonesia ICO. The PCU team members: Project Coordinator, Project Manager, Financial Officer, Project Assistant and Technical Officer (PATO), Knowledge and Communication Officer, State Technical Officer joined the MTR mission. |

Asia and the Pacific Division

Department of Country Operations

## List of acronyms

| ATFP | ASEAN Task Force on Peatlands |
| --- | --- |
| AWPB | Annual Work Plan and Budget |
| BMP | Best Management Practices |
| BOMBA | Malaysian Fire and Rescue Department |
| DOA | Department of Agriculture |
| EA | Executing Agency |
| FA | Financial Agreement |
| FDPM | Forestry Department Peninsular Malaysia |
| FDRS | Fire Danger Rating System |
| FRIM | Forestry Research Institute of Malaysia |
| FM | Financial Management |
| GEF | Global Environment Facility |
| GHG | Greenhouse gas |
| EA | Executing Agency |
| IA | Implementing Agency |
| IFAD | International Fund for Agricultural Development |
| IFR | Interim Financial Report |
| IAC | Initial Attack Crew |
| IMP | Integrated Management Plan |
| IP | Indigenous People |
| KM | Knowledge Management |
| M&E | Monitoring and Evaluation |
| MyBIS | Malaysia Biodiversity Information System |
| MyGAP | Malaysia Good Agricultural Practices |
| MPOB | Malaysia Palm Oil Board |
| NAPP | National Action Plan for Peatlands |
| NGO | Non-Governmental Organisation |
| NPMO | National Project Management Officer |
| NPSC | National Peatland Steering Committee |
| NREB | Natural Resources and Environment Board (Sarawak) |
| NRES | Natural Resources and Environmental Sustainability |
| NRO | Natural Resource Office |
| NSPSF | North Selangor Peat Swamp Forest |
| OFP | Operational Focal Point |
| PDR | Project Design Report |
| PMO | Project Management Office |
| PIR | Project Implementation Report |
| PPP | Public-Private Partnership |
| SAPP | State Action Plan for Peatlands |
| SEPPL | Southeast Pahang Peatland Landscape |
| SMPEM | Sustainable Management of Peatland Ecosystems in Malaysia |
| SPMO | State Project Management Office |
| SPSC | State Peatland Steering Committee |
| SSPL | South Selangor Peatland Landscape |
| TWG | Technical Working Group |

## Mission Objectives and Key Conclusions

### Background and main objectives of the mission

The Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM) was endorsed by GEF CEO on 28 January 2018 and it was approved by the IFAD Executive Board and became effective on 6 February 2018 with a four-year implementation life. The total cost for the SMPEM was estimated at USD 62.14 million. GEF financing is USD 9.43 million. Anticipated co-financing of approximately USD 52.71 million is expected to come from various sources, including Federal and State governments, the private sector, IFAD and Civil Society Organisations (CSOs). The Project Goal is to sustainably manage peatlands in Malaysia in an integrated manner to conserve resources, prevent degradation and fires, and generate benefits for current and future generations; the development objective is to strengthen national policy and institutional capacity for implementing peatland-related strategies and plans and to enhance integrated peatland management in targeted landscapes. The project consists of three technical components, namely: (1) Enhanced policy dialogue and improved institutional capacity for development and implementation of peatland related strategies and plans; (2) Enhanced Management framework and practices for sustainable management of peatlands in Pahang, Sabah, Sarawak and Selangor; and (3) Development and implementation of Integrated Management Plans (IMPs) for targeted, peatland landscapes, supported by project management offices at both national and state levels. The project completion date is 31 December 2024 and its closing date is 30 June 2025, with an 18-month no-cost extension being proposed and under consideration. The implementation was recorded as starting on 17 December 2020 and the inception workshop was conducted in July 2022. Two annual supervisions were conducted respectively in May 2022 and in April 2023, supplemented by a latest IFAD implementation support mission in 1-2 August 2024, resulted in producing the project 3rd GEF project implementation report (PIR) for the Fiscal Year 2024 (01 July 2023 - 30 June 2024).

The mid-term review mission to SMPEM was conducted during 19 – 30 August 2024 in Malaysia. The overall objectives of the MTR are to (i) review the progress of the implementation of GEF6 SMPEM in accordance with the project’s logical framework; (ii) identify challenges, good practices and lessons learned, and (iii) provide implementation support with emphasis on accelerating the implementation to achieve the project targets. Its specific objectives focus on: a) overall project management and institutional arrangement, b) financial management (FM), procurement and compliance with legal covenants, and c) Monitoring & Evaluation (M&E) and knowledge management (KM). Based on these reviews, the mission provides recommendations and implementation support for further improvements in line with the project strategy and objectives. The mission kick off was conducted on 19 August 2024 in Putrajaya led by Puan Norsham Binti Abdul Latip (Deputy Secretary General (Natural Resources) – Ministry of Natural Resources and Environmental Sustainability (NRES)), followed by field visits by two teams respectively in 1) Pahang and Selangor, and 2) Sabah and Sarawak during 19 – 25 August 2024. In close collaboration with and supported by the national project management office (NPMO), the mission undertook consultations and exchanges with the representatives of State governments, State Ministries, State Economic Planning Units, Federal and States agencies, state project management offices (SPMOs), NGOs, and other stakeholders including representatives and beneficiaries of communities visited. The mission provided technical advice to the project stakeholders where applicable, especially regarding the implementation of the annual work plan and budget (AWPB) and procurement plan, and financial management. A pre-wrap up meeting was held on 29 August with the NPMO, followed by an official wrap-up on 30 August chaired by Mr. Siva Kumar a/l Solay Rajah, Under Secretary (Biodiversity and Forestry Management Division), with representatives from Forestry Department Peninsular Malaysia (FDPM), NMPO, PMO from Selangor State, PMO from Pahang State, PMO from Sabah State, PMO from Sarawak, the independent consultant team, and the IFAD team.

### Mission methodology

The evaluation of the project was conducted using a comprehensive and systematic methodology designed to assess the project’s performance, outputs, and outcomes against its objectives. The approach employed a mix of qualitative and quantitative methods to ensure a balanced and holistic understanding of the project's achievements and challenges. This section outlines the key methodological steps and tools used in the evaluation.

##### Desk Review of Project Documentation

The evaluation began with an in-depth review of key project documents, including:

  - The Project Design Report (PDR), which provided a baseline framework and initial project objectives.

  - Annual Work Plans and Budgets (AWPBs) from 2022, 2023, and 2024, which outlined planned activities, targets, and financial allocations.

  - Project Implementation Reports (PIRs) from 2022 to 2024, which detailed the progress, challenges, and adjustments made during implementation.

  - Audit reports, monitoring and evaluation (M&E) data, and knowledge products developed during the project.

- This desk review offered insights into the project’s design, implementation trajectory, and performance across its three components.

##### Stakeholder Consultations

Extensive consultations were conducted with a range of stakeholders to gather diverse perspectives on the project’s implementation and impact. These stakeholders included:

  - National-Level Actors: Representatives from the Ministry of Natural Resources and Environmental Sustainability (NRES), the Malaysian Palm Oil Board (MPOB), and the Department of Environment provided insights into policy-level initiatives and institutional challenges.

  - State-Level Authorities: Representatives from state forestry departments in Selangor, Pahang, Sabah, and Sarawak shared their experiences in developing the State Action Plan for Peatlands (SAPP) and implementing Integrated Management Plans (IMPs), as well as coordinating fire prevention strategies.

  - Local Communities: Discussions with Indigenous Peoples (IPs), women’s and youth groups, and smallholder farmers illuminated the social and economic impacts of the project at the community level.

  - Private Sector Partners: Feedback from plantation companies involved in Public-Private Partnerships (PPPs) highlighted the effectiveness of collaborative approaches to fire prevention and sustainable agriculture.

- These consultations were conducted through structured interviews, focus group discussions, and participatory workshops. The data collected was used to validate findings from the desk review and to provide context-specific insights.

##### Field Visits and Observations

Field visits were conducted to selected project sites across the four targeted landscapes: (i) North Selangor Peat Swamp Forest (Selangor State), (ii) Southeast Pahang Peat Swamp Forest (Pahang State), (iii) Maludam National Park in Sarawak (Sarawak State), (iv) Klias Peninsula in Sabah (Sabah State). These visits included direct observations of project activities such as community-based fire patrols, sustainable agriculture initiatives, and ongoing rehabilitation efforts. Field visits allowed for first-hand assessment of the physical progress of interventions, such as reforestation and hydrological restoration; community engagement and participation in project activities; and the integration of traditional knowledge into sustainable peatland management practices. The field visits also facilitated informal discussions with beneficiaries and local implementers, enriching the qualitative dataset with anecdotal evidence.

### Key mission agreements and Conclusions

- Main findings and conclusion.

The project experienced initial implementation delays due to extreme weather events, flooding, and the impacts of the COVID-19 pandemic. However, progress has steadily improved over time, with each successive Project Implementation Report (PIR) up to June 2024 reflecting stronger results across all components. Despite these gains, overall financial and physical achievements remain moderate at this stage. The cumulative financial disbursement was reported for a total of USD 12.798 million all financiers combined, or 20.6% as of 30 June 2024. GEF grant progress registered a total of USD 1.127 million, accounting for 11.95% of the total available allocation; Government counterpart funding was estimated for a total of USD 9.018 million or 18.5% of its total allocation. Overall disbursement remains chronically low; analysis of GEF grant indicated high disbursements of spending in expenditures categories of Operating cost and Salaries and allowances, respectively at 92% and 58%, while other categories remain below 15%. This hints off a high management cost and limited remaining balances while expenditures related to investments are low, meaning the Government may need to increase its contribution in operating costs in the remaining period of project life.

Implementation of activities has rolled out in all the components with improved and speed-up momentum. Effects have become observable in project support to the national consultation platform of multi-sectors and stakeholders, leading to increased multi-sector or multi-agency actions in sustainable peatland ecosystems management at state and community levels. Overall physical progress remains moderate, hindered by delays in procurement and other administrative processes. Activities such as training sessions, workshops, knowledge management, and communications have been conducted, but operations requiring goods and services faced delays due to protracted procurement procedures.

Overall, the SMPEM project has made uneven but meaningful progress across its three components, with varying degrees of implementation pace.

Component 1 has seen the establishment of multi-stakeholder policy platforms at both national and state levels, including the State Peatland Technical Working Groups and the National Peatland Working Group Committee. These platforms have improved coordination and policy dialogue on peatland management and facilitated Malaysia’s active engagement in regional and international forums. However, actual policy updates, such as the National Action Plan for Peatlands (NAPP) and State Action Plans (SAPPs), remain in progress.

Component 2 has achieved notable early progress, laying critical groundwork for sustainable peatland management practices despite limited financial disbursement (15% of its GEF allocation). Efforts to develop SAPPs have advanced in several states, with Sabah demonstrating particularly strong multi-stakeholder commitment. The project has introduced Best Management Practices (BMPs) for agriculture, fire prevention, and water management, alongside training programs that have strengthened community capacities. Noteworthy achievements include the rollout of MyGAP certification in Sabah, establishment of fire prevention teams, and deployment of innovative tools like Selangor’s IoT-based groundwater monitoring system. While progress in scaling these practices at landscape level has been slower than planned, foundations for future expansion are in place.

Under Component 3, important preparatory work has been undertaken to review, update, and initiate Integrated Management Plans (IMPs) for priority peatland landscapes. These activities include stakeholder consultations, data compilation, and initial awareness and capacity-building efforts in Selangor, Pahang, Sabah, and Sarawak. Although tangible outputs are still limited, these initiatives have helped foster multi-stakeholder collaboration and laid the groundwork for integrated, landscape-level peatland management.

A significant challenge lies in the protracted approval process for the Annual Work Plan and Budget (AWPB), compounded by issues in procurement. The delays in these areas can be attributed to the project’s top-down design, which relies heavily on achieving key outputs such as the review and update of the National Action Plan for Peatland (NAPP) under Component 1. While this framework ensures alignment with national policy objectives, it creates bottlenecks that impede timely state-level implementation. Opportunities exist to enhance mutual leverage between national and state levels, fostering two-way engagement to accelerate progress. Despite these challenges, the project has achieved commendable results in outreach efforts. It has directly served 4,006 beneficiaries, of which 48% are women and 46% belong to Indigenous Peoples (IP) groups. Activities directed to communities or at beneficiary level, such as the introduction of agricultural best management practices, groundwater monitoring and early detection and fire control for peatland conservation, directly benefited 1538 people (736 female and 1161 IPs). These figures surpass the originally approved mid-term target of 300 households, equivalent to 1200 beneficiaries. Additionally, the project benefited 2468 people (1079 female and 580 IPs) for capacity building activities at agency or staff level on sustainable management of peatlands. The project has demonstrated strong collaboration with Indigenous Peoples, and this focus should be maintained through enhanced monitoring and evaluation (M&E) systems to systematically document and analyse this coverage.

The AWPB 2024 of the project amounts to a total of 4.5 million as GEF grant financing, or 48% of the total available allocation (USD 9.4 million). Annual financial progress was estimated at approximately 6% against the AWPB 2024 and 45% against funds received as of 30 June 2024, indicating the continued pressure on need of effective execution of AWPBs since the project start-up.

The project experienced issues related to implementation delay, slow progress and low disbursement. Slow fund disbursement is likely due to lengthy administrative hurdles, which led to delayed implementation; the mission notes the disbursement is particularly slow. The complexity of coordinating across multiple levels of government has slowed decision-making processes, due to the multiple layers of clearance and approval, such as the need for trust deeds at both the national and state levels, hindering progress on policy enhancement and capacity building.

Against this backdrop, improved management efficiency will be key to bring up the project progress and performance to a satisfactory level, especially in the areas of securing PMO staffing and key functions, improving AWPB and procurement effectiveness, and improving vertical and horizontal coordination along the management structure and with multi-sector stakeholders.

Key mission agreements are highlighted below. The mission recommends a series of follow-up actions:

- Build capacity of the project management office (PMO) early next year while the project extension should be granted;

- Revisit needs and identify priority activities in line with designed project outputs and expenditure categories, ensure further accelerated implementation and improved responsiveness;

- Systemize project KM and produce KM products in line with good practices generated and success stories of replicable and innovative potential. This effort will contribute to the project's lessons learned and enhance its sustainability;

- Enhance the M&E system to systematically track outputs and outcomes, conduct outcome analyses, and ensure compliance with GEF6 core indicators. Efforts should include filling gaps in baseline data to better quantify progress;

- Expedite the execution of the AWPB 2024, leveraging funds in state project accounts to achieve a higher disbursement rate. Simplifying procurement processes and reducing approval timelines are key to enhancing efficiency;

- Increase implementation under components 2 and 3 and apply good management practices and success stories in support of national policy engagement under component 1 (bottom up as compared to top-down).

The mission recommended to maintain the Moderately Satisfactory (MS) for the overall project implementation performance, subject to IFAD and GEF management review.

## Overview and Project Progress

- Component 1 – Enhanced policy dialogue and improved institutional capacity for development and implementation of peatland related strategies and plans

The component focuses on strengthening national frameworks and capacities for the sustainable management of peatlands and peatland ecosystems in Malaysia, with an emphasis on multi-sectoral aspects of peatland management and rationalization of resource use. This component emphasizes on strengthening the capacity for implementing the National Action Plan on Peatlands and other policy and plans up to 2030. The component has a total allocation of USD 3.03 million all financiers combined (5% of total project allocation), and GEF grant USD 1.875 million (20% of total GEF grant). As of 30 June 2024, the project reported a financial achievement of USD 397,297 under component 1, of which GEF financing USD 137,676 (13% of total component funding all financiers combined, and 7.34% of GEF component financing).

Output 1.1 - Policies, guidelines, institutional arrangements, and capacity for sustainable peatland management enhanced

Mechanisms for policy consultations and dialogues have been established, including the formation and meetings of the State Peatland Technical Working Group and the National Peatland Working Group Committee. These groups have facilitated consultative meetings to advance policymaking related to peatlands. The project has also supported active involvement in policy discussions at the ASEAN and international levels, including the country’s participation in annual ASEAN Task Force on Peatlands (ATFP) meetings and the Wetlands COP in Geneva, Switzerland. Since the project's inception, SMPEM has coordinated efforts among multiple stakeholders.

The project supports the National Peatland Steering Committee (NPSC), and Technical Working Group (TWG) led by NRES at the Federal level. The project also supports the mainstreaming of the scheme at the state level and established the State Steering Committee (SSC) and State Technical Working Group (STWG) which include key governmental agencies. In Pahang the steering committee is led by BPEN, the steering committee in Selangor is led by UPEN, the steering committee in Sabah is led by the natural resources office (NRO), and the steering committee in Sarawak is led by the economic and planning unit (EPU). It is indicated that the project has strong ownership by the government to ensure that the program will be continued after project completion.

Support to NAPP, SAPP and IMP have been initiated with the appointment of consultants for updating the National Action Plan for Peatland. It is expected that the updated NAPP will be completed by January 2025 and provide an overall guiding framework for the exercise of reviewing and completing SAPP and IMP guidelines.

Significant stakeholder involvement was observed in policy dialogue and capacity building. The project has facilitated workshops and consultations aimed at enhancing policy frameworks, such as the National Action Plan on Peatlands (NAPP) and associated guidelines. In Sabah, the government has shown strong support for the project by actively involving multi-stakeholder forums in the adoption and development of key documents like the State Action Plan for Peatlands (SAPP) and Integrated Management Plans (IMP).

The Enhanced Multi-Stakeholder Approach to sustainable peatland management has significantly improved collaboration among governmental agencies, institutions, and community groups, resulting in numerous well-coordinated actions. This project has facilitated multi-level forums at both the federal/national and state levels, with technical working and steering committee meetings taking place at least twice annually. At the federal/national level, the Ministry of Natural Resources & Environmental Sustainability (NRES), as the executing agency of SMPEM, leads the steering committee and collaborates with other key agencies: Malaysia Palm Oil Board (MPOB), Forest Research Institute Malaysia (FRIM), Department of Agriculture (DOA), Department of Environment (DOE), Fire and Rescue Department (BOMBA), Malaysia Space Agency (MySA), and Department of Meteorology (MET-Malaysia). These entities have joined forces to reinforce conservation efforts and integrate sustainable development.

At the state level, coordinated planning has improved across ministries, state agencies, including UPEN/BPEN and MUDeNR, and district authorities, ensuring effective implementation of sustainable peatland management (SPM) policies. Additionally, the Department of Agriculture has promoted sustainable practices in peatland farming under the Malaysia Good Agriculture Practices (MyGAP) initiative, while comprehensive site management and public awareness campaigns have bolstered peatland fire prevention through partnerships with the DOE, the Meteorological Department, MYSA, Fire and Rescue Department, and local organizations such as the GEC. Water management has also been strengthened through collaboration among DOA, DID, and JMG, and sustainable oil palm cultivation in peatlands is supported by the coordinated efforts of MPOB, Malaysia Sustainability Palm Oil - MSPO, private plantation operators, and smallholders. Moreover, this approach fosters innovation by exploring potential carbon trading initiatives with Enggang Holdings Sdn Bhd (private sector) in Pahang and engaging with international projects like GIZ SUPA and the IFAD regional project MAHFSA programme to extend its impact globally.

Output 1.2 - Investment framework for NAPP 2021 – 2030 developed and adopted is expected to start after the MTR, once the NAPP update has been fully completed.

The SMPEM project has started the process of updating the National Action Plan on Peatland (NAPP) for Malaysia, commencing on 9th August 2023. The workshop was attended by representatives from the NRES, FDPM, and representative from the state governments. Following deliberation, the NRES has agreed to proceed with the NAPP update, and UPM Consultancy & Services Sdn Bhd has been appointed for a 7-month consultation period, anticipated to work in close collaboration with key federal and national partners to achieve finalization by January 2025. It is imperative that the NAPP undergoes updating in 2024, as the Malaysian government needs to provide parallel support in integrating the ASEAN Peatland Management Strategy (APMS) and aligning it with the NAPP and IMPs.

Output 1.3: Knowledge management and exchange enhanced to support scaling-up of sustainable peatland management

Drafting of KM plan is still ongoing, as recommended by previous missions, and the project should complete the KM Strategy and Action Plan (2024–2026). The project reported activities in presenting and promoting SMPEM in relationship with sustainable forestry management (XV World Forestry Congress at Seoul, 2 – 6 May 2022) and sustainable peatland ecosystems management in Peninsular Malaysia (Dahalan, M.P.; Yong, H.; Nuruddin, A. A., 2022). In addition to the inception workshops in the project states, the project regularly participated in events related to the project objectives, mainly in areas of sustainable peatland ecosystems management, fire control training, and hosting international delegations in their visits to peatland areas in Malaysia.

The Project conducted the CEPA (Communication, Education, and Public Awareness) Program involving 289 participants, with 41% (118) males and 59% (171) females in Sarawak, and a total of 164 participants with 50% females in Sabah.

The project has produced various KM/communication products, including videos, posters, buntings, and pamphlets related to sustainable peatland management. It has also maintained public communication through national mass media and social media platforms, including Facebook (facebook.com/smpem_malaysia), LinkedIn (Linkedin.com/smpem-malaysia), and Instagram (@smpem_malaysia).

The project was mentioned by the Honourable Mr. Nik Nazmi Nik Ahmad (Minister of Natural Resources and Environmental Sustainability) in a press statement, which was picked up by mainstream online newspapers such as Berita Harian, Free Malaysia Today (FMT), and TV3 News Bulletin on 14 February 2024. The statement elaborated on the SMPEM project’s initial success in reducing peatland fire incidents, particularly in Peninsular Malaysia, Selangor, and Pahang. Key activities include updating the National Action Plan for Peatlands (NAPP), fire prevention measures with the Fire and Rescue Department, training, equipment procurement, awareness campaigns, restoration, and water level monitoring.

- Preliminary indications of enhanced policy dialogue have been reported in Sabah, where stakeholder collaboration has led to the faster adoption of important strategies, thanks to strengthened multi-stakeholder forums and a plan to utilize available data in the development of Integrated Management Plans – IMPs in the peatland ecosystems. Selangor has completed developing the IMPS for two landscapes with a total area is 91,045.40 Ha, as accumulation from the North Selangor Peat Swamp Forest:  81,530.96 Ha, and South Selangor Peatland Landscape:  9,514.42 Ha. The project successfully conducted the National Biological Diversity Conference 2023 – Peatland Ecosystem Management and Conservation Seminar, co-organized by the Ministry of Natural Resources, Environment, and Climate Change (NRECC), which shared technical and policy arrangements to support peatland management.

- Component 2 – Enhanced Management Framework and Practices for Sustainable Management of Peatlands in Pahang, Sabah, Sarawak, and Selangor

Component 2 aims to improve the sustainable management of peatlands in target states, with a focus on implementing best management practices (BMPs) in agriculture, fire prevention, and water management. The component has a total allocation of USD 30,999,000 from combined financiers, representing 50% of the total project allocation, with a GEF grant of USD 2,724,000, which accounts for 29% of the total GEF grant. As of 30 June 2024, the project reported a financial achievement of USD 6,631,863 under Component 2, of which GEF financing amounted to USD 411,363, representing 21% of total component financing and 15.10% of GEF component financing.

Output 2.1 - State Action Plan for Peatlands (SAPP) Developed and Adopted by Pahang, Sabah, Sarawak, and Selangor

Progress has been made in developing the State Action Plans for Peatlands (SAPP) across the target states. In Sabah, the government has shown strong commitment by actively involving multi-stakeholder forums to accelerate the development of SAPPs. Consultations and workshops are on the way to gather input from relevant stakeholders, ensuring that the SAPPs reflect local conditions and priorities. This collaborative approach has led to the rapid development and planned adoption of SAPPs in line with national and international guidelines.

- Output 2.2 - Best Management Practices Introduced in Agriculture and Plantation Sectors

The project has successfully introduced Best Management Practices (BMPs) in agriculture and the plantation sectors across Pahang, Sabah, Sarawak, and Selangor. These practices focus on sustainable land use, particularly in oil palm plantations on peatlands. In Sabah, the promotion of MyGAP certification has been particularly successful, with 12 households already certified and 18 more in progress. The project has also conducted training programs to enhance the capacity of farmers and plantation workers, focusing on reducing environmental impacts and improving land management practices. In Pahang, collaboration with the Department of Agriculture has focused on promoting the sustainable peatland management. Key activities included a seminar to raise awareness, a land use mapping workshop to identify agriculture-destined peatland areas, and a community engagement session providing advisory services. Additionally, a workshop was held to educate farmers on soil suitability and sustainable agricultural practices on peatland.

Output 2.3 - Best Management Practices for Peatland Fire Prevention and Control for Reducing GHG Emissions in Four States

The Project has conducted a workshop and a training through BOMBA on fire mitigation. The mission witnessed the trained BOMBA Community and patrollers working effectiveness with acquired skills and knowledge.

Significant progress has been made in implementing BMPs for peatland fire prevention and control, a critical component for reducing GHG emissions. The project has established fire prevention teams at the state and district levels, particularly in Pahang and Sabah. These teams are supported by Fire Danger Rating Systems (FDRS), public awareness campaigns, and the procurement of fire monitoring equipment such as drones and thermal imagers. Training programs for local communities and forest rangers have also been conducted, significantly improving fire prevention efforts and reducing the incidence of peatland fires. In Selangor, the Internet of Things (IoT) system was developed at Kuala Langat South Forest Reserve for detecting real-time ground water levels in peat swap forest. This innovation assists the management in its decision making and subsequent actions to prevent forest fire, conserve resources and avoid the degradation of peat swap forest. The IoT system can also be used to profile the Fire Danger Rating System (FDRS). Selangor is also working closely with different agencies, NGOs, and local community in fire monitoring. For example, Friends of North Selangor Peat Swamp Forest (SHGSU) and the Malaysian Volunteer Corps Department are involved in monitoring and forest fire prevention on a daily basis during dry seasons. Selangor has organised the peat swamp forest fire prevention and control training course to strengthen local capacities.  In Pahang, BOMBA Komuniti Enggang plays an important role in fire prevention in Pekan, Peat Forest and serves as an example of public-private partnership. In Sarawak, Natural Resources and Environment Board (NREB) in collaboration with BOMBA conducted a refresher course on peat fire suppression and updated progress on SOP for peat fire prevention and suppression by landowners. Additionally, the NP rangers and group community in Maludam have conducted regular patrolling activities for biodiversity and fire monitoring. In Sabah, the project supported the Sabah Forestry Department to conduct the fire prevention and control training for the Initial Attack Crew (IAC). The mission witnessed and commended the strengthened capacity building at both state and community levels, thanks to engagement efforts starting from the national level, particularly in fire prevention and land management.

Outcomes and Challenges. The project has seen considerable success in enhancing the management framework and practices for sustainable peatland management. In Sabah, the rapid development and adoption of SAPPs, combined with effective stakeholder engagement, have set a strong foundation for sustainable peatland management. The introduction of BMPs has led to improved agricultural practices and reduced environmental impacts, particularly in oil palm plantations.

However, the project has faced challenges in slow fund disbursement due to lengthy administrative procedures which delayed the implementation of key activities. This has hindered the timely adoption of SAPPs and the rollout of BMPs in some areas. Additionally, the complexity of coordinating across multiple levels of government has slowed decision-making processes, impacting overall progress.

- Component 3 – Development and Implementation of Integrated Management Plans (IMPs) for Targeted Peatland Landscapes

Component 3 focuses on the development and implementation of Integrated Management Plans (IMPs) for five key peatland landscapes across Malaysia. The objective is to ensure comprehensive and sustainable management of these landscapes by integrating environmental, social, and economic considerations. The component has a total allocation of USD 26,491,000 from combined financiers, representing 43% of the total project allocation, with a GEF grant of USD 4,385,000, which accounts for 46% of the total GEF grant. As of 30 June 2024, the project reported a financial achievement of USD 4,480,163 under Component 3, of which GEF financing amounted to USD 320,463, representing 17% of total component financing and 7.31% of GEF component financing.

Output 3.1 - Review, Update, and Implement Existing Integrated Management Plan (IMP) for North Selangor Peat Swamp Forest (NSPSF), and Develop a New IMP for South Selangor Peatland Landscape

Significant progress has been made in completing the Integrated Management Plan (IMP) for the North Selangor Peat Swamp Forest (NSPSF). The project has engaged stakeholders, including government agencies, local communities, and NGOs, in consultative meetings to gather input and ensure that the revised IMP addresses the current challenges and opportunities in the area. The development of a new IMP for the South Selangor Peatland Landscape is also underway, with a focus on integrating sustainable land use practices, water management, and biodiversity conservation.

- Output 3.2 - Review Existing Integrated Management Plans (IMP) for Southeast Pahang Peat Swamp Forest, and Update and Expand the Scope to Cover the Southeast Pahang Peatland Landscape

In Pahang, the project has initiated the review and expansion of the IMP for the Southeast Pahang Peat Swamp Forest to encompass the broader Southeast Pahang Peatland Landscape. Stakeholder consultations and workshops have been conducted to gather insights and ensure that the updated IMP reflects the ecological and socio-economic realities of the region. The project is in the process of recruiting consulting services to assist in the hydrological analysis and land use mapping, which are critical components of the updated IMP. It is also planned that the IMP will be synchronized with the State Policy regarding carbon trade and will work closely with Enggang Holdings Sdn Bhd.

- Output 3.3 - Develop and Implement a New Landscape-Level IMP for Klias Peninsula Peatland Landscape in Sabah

The development of a new landscape-level IMP for the Klias Peninsula Peatland Landscape in Sabah has been marked by strong collaboration with stakeholders. The Sabah government has been particularly supportive, facilitating multi-stakeholder forums to ensure that the IMP aligns with both state and national priorities. The project has conducted public awareness campaigns and capacity-building workshops to involve local communities in the IMP development process, ensuring that their needs and knowledge are incorporated into the management plan. The Technical Working Group (TWG) has collected existing data and information from previous and ongoing activities.

- Output 3.4 - Develop and Implement a Landscape-Level IMP in the Maludam Peninsula, Sarawak

The project has initiated consultations with key stakeholders, including the Forest Department Sarawak and local communities, to gather inputs for the IMP. Equipment have been procured to support biodiversity management in Maludam National Park, and the project has emphasized the importance of integrating sustainable water management and land use practices into the IMP. In early 2024, the Technical Working Group compiled data on forest and biodiversity, community and socio-economic factors, hydrology and drainage, and peat mapping.

Outcomes and Challenges. Component 3 has made significant strides in developing and implementing IMPs across the targeted peatland landscapes. The progress in Selangor, Sabah and Sarawak demonstrate the effectiveness of a multi-stakeholder approach and the importance of integrating local knowledge and priorities into landscape management plans. In Selangor, the updating of the NSPSF IMP and the development of a new IMP for the South Selangor Peatland Landscape are on track, supported by stakeholder engagement and technical expertise. In Pahang, efforts to establish Komuniti BOMBA have faced challenges due to the economic demand on the Orang Asli (Indigenous people) community in Pekan, which limit their availability for community activities. Additionally, difficulties in securing voluntary participation have raised concerns about the sustainability of the initiative, particularly regarding funding after the project’s completion.  Overall, the development of a landscape-level IMP for all landscapes has progressed, albeit with challenges due to slow fund disbursement.

## Project implementation

- Effectiveness and Development Focus

## Development effectiveness (rating: Moderately Satisfactory)

The project continues to address the complex challenge of sustainable peatland management (SPM) that requires coordinated and complementary actions in several key thematic areas at multiple geographic levels, and systematic monitoring over time. All the three technical components have initiated their respective key activities with different operational effectiveness but supporting the multi-sectoral policy dialogues at both national and state levels, benefiting the communities living and engaging the private sector in the project areas at both landscape and thematic levels. While disbursement remains low and outcome-level achievements are yet to be systematically assessed, the project has started to show improved implementation effectiveness of its AWPB 2024; further improvements are expected if agreed actions and recommendations of the MTR will be followed up timely.

- Targeting and outreach (rating: Moderately Satisfactory).

The project was designed with a well-defined geographic targeting at state level, working in Pahang, Sabah, Sarawak and Selangor, and at the five peatland conservation sites specified. The design included a national-level component that aims to enhance policy framework and institutional capacity building. The mission’s findings indicated that activities were carried on under the three technical components, at national, state and local levels as per design; most of the stakeholder agencies participated and contributed to the achievement of implemented activities in support of related outputs, and in Pahang, Sabah Sarawak and Selangor, including the five peatland conservation sites.

Overall, the project has reached 4,006 beneficiaries, combining both capacity-building participants and direct beneficiaries. The project reported a total 2,468 participants mostly through the capacity building support such as training and workshops. 1,079 of them are female (44%) and 580 belong to the IP communities (24%). The project has directly served 1,538 rural beneficiary individuals of which 736 are female (48%) and 1,161 IPs (76%).  The mission recommends the project to regularly update the logframe to reflect the achievements in the outreach targets.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Outreach target and achievement consolidation Continue to record and report project achievements in targeting and outreach. | PMOs and all participating agencies | Continuously | Agreed |

- Gender equality & women’s participation (rating: Satisfactory).

The SMPEM project has established Technical Working Groups (TWG) and Steering Committees at both federal and state levels to support the decision support system for sustainable peatland management. The composition of these groups includes at least 20% women representatives, ensuring that women are actively involved in peatland management governance structures. By promoting women’s participation in technical, policy, and operational processes, the project has increased women’s visibility in decision-making spaces. This approach is supported by robust stakeholder engagement mechanisms, gender-disaggregated monitoring, and the prioritization of women’s participation in capacity-building initiatives. The project’s gender-responsive actions are aligned with national policy frameworks such as the National Action Plan for Peatland (NAPP 2026–2035) and follow GEF procedures and guidelines for gender inclusion across project activities.

The SMPEM project has consistently monitored women’s participation in the development of key policy and management documents. Notably, in the preparation of the National Action Plan for Peatland (NAPP) at the federal level and the Integrated Management Plans (IMPs) for North and South Selangor Landscapes in Selangor State, women’s participation has been maintained at a minimum of 30% in every meeting and consultation process. The NAPP 2026–2035, while not explicitly naming women in every action point, aligns with SDG 5 on gender equality by embedding community empowerment and inclusive participation principles. Its inclusive strategies acknowledge that women’s active involvement is crucial to achieving sustainable peatland conservation and socio-economic resilience in Malaysia.

At the field implementation level, SMPEM has demonstrated tangible outcomes in promoting women’s roles through the Malaysia Good Agricultural Practices (MyGAP) certification initiative in Takuli Village, Beaufort, Sabah. Through collaboration with the Department of Agriculture Sabah, SMPEM has supported local farmers, particularly women, in adopting sustainable and environmentally friendly agricultural practices on peatland areas. Programs such as MyGAP Seminars, Workshops, and Composting Workshops were specifically designed to be inclusive, ensuring a welcoming environment for women participants. As a result, women’s participation in these agricultural activities reached 40%, involving women from diverse backgrounds including women working alongside spouses and female heads of households. This inclusive approach has been instrumental in addressing traditional barriers to women’s economic participation in agriculture. By August 2024, 12 out of 44 households in Takuli Village secured MyGAP certification for their pineapple plantations, supported by women’s leadership in field management and decision-making on farm practices.

The SMPEM project has maintained systematic gender-disaggregated monitoring of direct beneficiaries across all activities. As of June 2024, a total of 4,006 individuals had directly benefited from the project, with 45% women and 43% Indigenous Peoples (IP) among participants. Specifically, 2,468 participants took part in capacity-building activities such as trainings and workshops, with women making up 44% of attendees and IP communities 24%. In rural beneficiary-focused initiatives, the project directly served 1,538 individuals, of whom 48% were women and 76% belonged to IP communities. These figures demonstrate the project’s progress in reaching gender equality targets in participation and inclusion, although continued efforts are needed to formalize mechanisms ensuring equitable access to project benefits and to track outcomes on women’s leadership and influence at community and household levels.

While SMPEM has made notable progress in promoting gender-responsive actions, several challenges remain. A key limitation is the absence of a dedicated, formalized gender strategy, which limits the ability to systematically track and strengthen gender equality outcomes. Although gender-disaggregated participation data is being collected, the project is still developing the mechanisms to monitor changes in women’s participation in decision-making roles over time, nor to assess how project benefits are equitably distributed at the household level. Furthermore, while gender considerations have been integrated into national and state-level peatland management frameworks, many of these policy documents do not explicitly articulate gender-specific targets or actions. Ensuring sustainable gender outcomes will require continued efforts to formalize monitoring systems, strengthen leadership opportunities for women, and address persistent barriers to equitable access to project resources, decision-making spaces, and economic benefits within peatland-dependent communities.

- Adaptation to Climate Change (rating: Moderately Satisfactory).

The SMPEM project significantly contributes to global environmental benefits by promoting sustainable peatland management across Malaysia. The project targets key areas such as peatland forest conservation, reducing greenhouse gas (GHG) emissions, and enhancing biodiversity. Through activities like restoring degraded peatlands, preventing fires, and supporting sustainable agriculture, the project helps sequester carbon and reduce GHG emissions linked to land degradation and fires. It also promotes biodiversity by restoring peat swamp forests and creating wildlife corridors to protect habitats.

Efforts to reduce emissions include fire prevention measures, such as Fire Danger Rating Systems (FDRS), public awareness campaigns, and community training, which have led to a decline in peatland fires. Restoring peatland hydrology through canal blocking and check dam maintenance has also helped reduce carbon emissions by preventing peat oxidation. Furthermore, sustainable agriculture practices, such as the MyGAP certification, have minimized environmental impacts, helping maintain peatland integrity. Sabah State is also supporting the improvements of its integrated early warning system, expected to foster greater integration among agencies to enhance awareness and mitigate disasters that could impact economic development. This approach can serve as a pilot model and be replicated in other states

- Sustainability and Scaling-up

- Institutions and Policy Engagement (rating: Satisfactory)

The project supports the National Peatland Steering Committee (NPSC), and Technical Working Group (TWG) led by NRES at the Federal level. The project facilitated the integration of the scheme at the state level and established the State Steering Committee (SSC) and State Technical Working Group (STWG) with the involvement of key agencies. In Pahang, the steering committee is led by BPEN; in Selangor, it is led by UPEN; in Sabah, it is led by NRO; and in Sarawak, it is led by EPU. It is noted that the government exhibits strong ownership of the project to ensure the program's continuation after its completion.

The support for NAPP, SAPP, and IMP has commenced with the appointment of consultants tasked with updating the National Action Plan for Peatland. The updated NAPP is anticipated to be finalized by January 2025 and will serve as a comprehensive framework for the review and completion of the SAPP and IMP guidelines.

Stakeholders have actively participated in policy dialogue and capacity building. The project has organized workshops to enhance frameworks like the National Action Plan on Peatlands (NAPP) and associated guidelines. In Sabah, the government has supported the project by involving multi-stakeholder fora in developing key documents such as the State Action Plan for Peatlands (SAPP) and Integrated Management Plans (IMP).

- Partnership building (rating: Satisfactory)

Partnership building is a strong element of the SMPEM project, evident through the establishment of the State Steering Committee (SSC) and State Technical Working Group (STWG)—both composed of multiple agencies—to drive coordinated actions in peatland management. This multi-stakeholder approach has fostered collaboration among government institutions (FDPS, SabahFD, SarawakFD, FRIM, DOA, DOE, Met, MYSA, F&RD, MPOB, MSPO, DID, JMG), local communities, and private sector entities, ensuring more effective planning, water management, site conservation, fire prevention, and sustainable agricultural practices in peatlands.

The project also supports public-private partnerships (PPP) that create tangible economic and social benefits for Indigenous Peoples (IP), such as village-based rural tourism and community-run fire patrols in Selangor. In Pahang, the BOMBA Komuniti Enggang initiative further reinforces PPP for fire management, while ongoing engagement with international programs (GIZ SUPA, MAHFSA) and new opportunities for carbon trading (Enggang Holdings Sdn Bhd) illustrate how the project drives broad-based, inclusive collaboration to achieve lasting peat swamp forest conservation and resilience.

- Environment and Natural Resources Management (rating: Satisfactory)

The SMPEM project significantly contributes to environment and natural resources management in Malaysia through a comprehensive, multi-level approach focused on sustainable peatland ecosystems. By enhancing institutional capacity and updating key national and state-level policy frameworks, SMPEM ensures long-term governance and coordination across sectors. The establishment of steering and technical working groups at both federal and state levels promotes inclusive, multi-stakeholder dialogue, aligning local, national, and regional strategies such as the ASEAN Peatland Management Strategy (APMS).

On the ground, the project introduces best management practices in agriculture, fire prevention, and water management, reducing environmental degradation and greenhouse gas emissions while protecting biodiversity-rich peat swamp forests. Community engagement, public education, and the development of knowledge management strategies further support the scaling-up of sustainable practices. SMPEM also explores innovative financing mechanisms, including carbon trading, and fosters strong partnerships with both public and private sectors.

The project is supporting two significant national systems: the Malaysia Good Agricultural Practices (MyGAP) and the Malaysia Biodiversity Information System (MyBIS). Targeted communities, such as those visited by the mission in the pineapple and sago peatland areas, have received assistance in obtaining MyGAP certification in compliance with government regulations, thereby mitigating negative impacts on the environment and the peatland ecosystem. SMPEM is furthermore collaborating with NRES to develop a submodule within the MyBIS platform focused on peatland ecosystems, with the objective of enhancing the monitoring of biodiversity in peatland landscapes.

- Potential for Scaling-up (rating: Moderately Satisfactory)

Multi-sector stakeholder platforms and approaches established under Components 1 and 2 have fostered inclusive collaboration among government agencies, NGOs, private sector entities, and local communities. This collaboration has accelerated policy dialogue and capacity building, with diverse stakeholders coming together to share best practices, align priorities, and coordinate on sustainable peatland management efforts. Although the National Action Plan for Peatlands (NAPP), State Action Plans (SAPPs), and Integrated Management Plans (IMPs) are still being updated, these collaborative efforts lay a strong foundation for developing comprehensive frameworks and driving future investments at the landscape level. SMPEM project has completed the Integrated Management Plans (IMP) for two landscapes with a total area is 91,045.40 Ha, as accumulation from the North Selangor Peat Swamp Forest:  81,530.96 Ha, and South Selangor Peatland Landscape:  9,514.42 Ha.

The project has initiated the review and expansion of the IMP in the targeted landscapes. It is also planned that the IMP will be synchronized with the State Policy regarding carbon trade and will work closely with Enggang Holdings Sdn Bhd, thus tapping into the potential for carbon trading in Malaysia.

In addition, the SMPEM project has reported effective public-private partnerships that actively engage rural communities. These partnerships have led to the implementation of practical interventions, such as sustainable agricultural practices on peatlands and fire prevention measures, which have been witnessed firsthand by the project mission. The positive outcomes from these collaborations underline the project's ability to mobilize community participation and leverage private sector expertise, laying a solid foundation for further focused investments at the landscape level.

- Project Management

- Quality of Project Management (rating: Moderately Satisfactory)

Essential duties fulfilled. The project has maintained a stable management structure as per design. NPSC meetings were conducted once a year to provide overall guidance on the project implementation, and relevant policy and strategic issues. State-level PSCs held semi-annual meetings to provide guidance and endorsement on AWPBs and implementation progress and reporting. The Technical Working Groups (TWGs) were established with senior professional and technical staff from the line agencies to ensure the quality of technical procedures and models in application and to assist with operational decision-making at the state level.

The PMOs maintained their continued capacity building in areas relevant to project management and sustainable management of peatland, holding regular management meetings in all states. Overall, the PMOs at all levels complied with the preparation and submission of AWPBs, and semi-annual progress reports were generally of good quality. PMO staff participated in the learning and sharing events organized by IFAD. All the PMOs maintained essential functional reporting in project coordination, financial management, monitoring and evaluation, and knowledge management despite the high turnover rate of staff.

High staff turnover and reduced capacities of PMOs were observed at both national and state levels. This caused a substantial loss of built capacities in project management and coordination. At the same time, IFAD’s management tools have evolved, especially in digital platforms and systems of FM and procurement. While the key PMO staff attended the regular technical training conducted by IFAD in these technical fields, there is a need of revisiting the project overall operational framework with updated knowledge and skills to help pursuing the movements towards the achievements of the project’s theory of change. The mission suggested conducting updated training for PMO staff and key focal points of line agencies, facilitated by IFAD's technical assistance in essential areas such as FM, M&E, KM, SECAP/ESS, and multi-level and sector operational coordination. Otherwise, the mission reiterated the importance of committing stable, sufficient and qualified staff to NPMO and SPMOs to ensure the key functions of FM, M&E and KM, procurement coordination, and inter-agency coordination in implementing good management practices in both peatland ecosystems, and sustainable agriculture and oil palm plantation. The mission recommended to the NPMO and SPMOs to identify and include other support staff in the Forestry Departments or other line agencies, engaging them as part-time support members of the PMOs in the core technical functions such as M&E, KM, procurement, FM, SECAP/ESS to help strengthen the PMOs’ required capacities in project management and coordination.

PMO staff incentive.	To address PMOs' ongoing loss of capacity affecting project progress, the mission suggested a competitive incentive package for PMO staff at national and state levels. The NPMO should lead in preparing a proposal with SPMOs' support and submit it to IFAD for approval. The incentives could be funded by the GEF grant under Salaries and Allowances, which currently has a remaining balance of 50%.

As a GEF-funded project dedicated to the sustainable management of peatland ecosystems in the country, the NPMO should have a focal point in environment and climate change to assist the technical decision making and track GEF’s core indicators related to sustainable peatland management. The mission recommends the recruitment of national consultant specialised in the relevant fields.

Extension consideration.	A request for non-cost extension was submitted to IFAD by the Government; it is expected that IFAD will process the request within the next two months. Assuming a confirmation for a no-cost extension of 18 months, the preparation of the next AWPB 2025 will be critical for achieving increased progress and improved performance.

| Actions Project management | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Increased staffing and capacities of PMOs Identify and include other support staff in the Forestry Departments or other line agencies, engaging them as part-time support members of the PMOs in the core technical functions such as M&E, KM, procurement, FM, and SECAP/ESS | Senior management of Forestry Departments, NPMO and PMOs, line agencies | 11/2024 | Agreed |
| Recruitment of environment and climate change focal point, to be included in the AWPB and procurement plan of 2025 | NPMO | 03/2025 | Agreed |
| PMO staff incentives Submit a proposal on staff incentives to IFAD for No-Objection before their application | NPMO and SPMOs | 10/2024 | Agreed |
| Management refreshing training A refreshing training for PMO staff and key focal points of line agencies, to be conducted by IFAD focus technical assistance mainly in the key areas of FM, M&E and KM, SECAP/ESS, and multi-level and sector operational coordination | IFAD, NPMO, SPMOs, participating line agencies | 02/2025 | Agreed |
| No-cost extension request for 18 months Process the request and inform the Government on the result. | IFAD | 10/2024 | Agreed |

- Knowledge Management (rating: Moderately Satisfactory)

Knowledge Management (KM) related activities were conducted and included in the AWPB mostly under component 1 as output 1.3, though the KM plan is still under drafting. The mission was provided with several documented stories of successful cases, ranging from community engagement fire prevention and control, empowerment of IPs, and engagement of private sector and CSO, which presented good potential for further knowledge sharing and management. The mission also took note of the intra-project knowledge sharing among the project states through exchanges and various thematic training conducted by the project management.

The Project has been active in the organisation of knowledge sharing events, such as workshops and seminars both at the national and State level, and awareness programmes involving schools and farmer groups. During the implementation period July 2023 – June 2024, SMPEM hosted 11 national events and 86 State-level events and produced 14 knowledge products (KP). The Project has moreover been employing social media for the dissemination of information regarding SMPEM activities and objectives.

The mission sampled some project’s KPs and they are informative and present a good design for distribution. The project reported that KPs have been disseminated to a wide range of audiences, including government officials, professionals in the forestry sector, researchers and academics, and reaching the broader public by means of a national TV interview and dedicated SMPEM social media channels.

SMPEM is in the process of recruiting the consultants to support the drafting of its KM Strategy and KM Plan. The Project expects to finalise both the KM Strategy and Plan by June 2025. The project recommended an earlier completion of the KM plan in order to ensuring its effective use during the remaining but limited project life.

The Project is currently in the process of adding a module to the Malaysia Biodiversity Information System (MyBIS), which is managed by the Ministry of Natural Resources and Environmental Sustainability (NRES), and to the Malaysia Good Agricultural Practices (MyGAP) platform, which falls under the jurisdiction of the Ministry of Agriculture. These platforms will be utilized to implement sustainable management practices and business models for peatland ecosystems as developed through the project implementation.

The mission notes that the project will contribute to updating the Hazard, Exposure and Vulnerability (HEVA) profile for Malaysia, particularly concerning natural resources management. The project has supported fire mitigation during the El Niño event in 2023, which can be used to update the existing document (https://nidm.gov.in/easindia2014/err/pdf/country_profile/Malaysia.pdf).

The mission underscored the significance of Knowledge Management (KM) planning for documenting lessons learned and best practices to facilitate potential replication and scaling-up efforts in the future, particularly during the remaining period of the project under a well-defined strategy. Furthermore, the mission recommends establishing a project website to broadly disseminate the project's activities, best practices, and KM products. The website will also serve as a repository for all KM products and events accomplished.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| - KM Plan Develop a knowledge management plan and implement it accordingly. | NPMO and SPMOs | Feb 2025 | Agreed |
| - Integrate the Project's Website Page into MyBIS | NPMO | Dec 2024 | Agreed |

- Coherence btw. AWPB and implementation (rating: Unsatisfactory).

In 2023, 14% of the approved AWPB 2023 was utilized, totalling USD 535,613 out of USD 3,699,834. By 30 June 2024, 6% of the approved AWPB 2024 was used, amounting to USD 285,228 out of USD 4,526,927.

Given the expected extension of the project duration and insights from previous AWPB performances, preparations for the 2025-AWPB should start early in 2024, ensuring that the approved AWPB 2025 will be available 60 days before January 1, 2025.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| - Preparation and endorsement/approval of AWPB Joint exercise of all states and NPMO to prepare AWPB, combine and conduct review and endorsement meetings of TWPs and PSCs at relevant levels to shorten the processing time. Proceed to AWPB 2025 preparation from September 2024 | PSCs and TWGs at all levels, NPMO and SPMOs | To be completed for IFAD No-Objection before the start of financial year under new AWPB | Agreed |

- Performance of the M&E System (rating: Moderately Satisfactory).

The Project updates the semi-annual progress reports (SAPR) and project implementation reports (PIR) in a timely manner. The AWPBs are prepared based on the SAPR and PIR reports. The project M&E system has been in place and generally functional in capturing the results of implementation of activities under different outputs, although reporting has mostly followed a qualitative approach. Financial and physical progress reports have been produced to reflect periodic achievements. The mission noticed the absence of a baseline survey, and no-application of the GEF Tracking Tool on core indicators. This put the mission in a difficult position of genuinely appreciating the project achievements at outcome level, despite some data was provided by the SPMOs during the mission. The project M&E system needs to be revisited to:

Timely record and report on AWPB progress in incremental and cumulative manner,

Periodically update the logframe as required,

Track the financiers’ contributions as compared to the approved allocations, especially the government contributions,

Systematically monitor the progress of i) Project’s Target Contributions to Global Environmental Benefits, ii) Estimated emission reduction linked to project activities, iii) Risk Mitigations and iv) other GEF6-related as required in the GEF CEO endorsement note.

The mission commended the PMOs’ immediate action in addressing the challenges outlined above, by organizing and conducting an M&E workshop in September 2024, participated by NPMO and SPMO officers. The workshop will also be a good opportunity for preparing a M&E plan understanding the purposes and methods of data collection and data coherence among the different national and state offices.

The M&E system should be improved to capture both output and outcome level achievements in line with the Project objectives in a quantitative and systematic manner, which will contribute to strengthening the logframe and KM activities.

M&E duties have been fulfilled but M&E officers have not been assigned. The mission recommends this key position to be filled in all the PMOs, at both national and state levels.

The Project is currently in the procurement process to have the consulting services to conduct the baseline study. The MTR survey, including the baseline for both the control and treatment groups, should be conducted upon the completion of the procurement process.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Revisit project M&E system Project M&E system needs to be upgraded to capture the key elements of M&E functions as required for GEF6. Service consultancy should be included in the next PP. | NPMO and SPMOs | Mar 2025 | Agreed |
| - Finalize the M&E Strategy & Plan. | NPMO | Sep 2024 | Agreed |
| Ensure that the logframe is regularly updated in a quantitative and systematic way to adequately reflect project progress and achievements and to guide evidence-based decision making | NPMO | Ongoing | Agreed |
| - Complete the recruitment of M&E officers. | NPMO and SPMOs | Dec 2024 | Agreed |
| - Carry out an outcome analysis/study. | NPMO | Jun 2025 | Agreed |

- Requirements of SECAP (rating: Moderately Satisfactory).

SECAP/ESS-related review, risks and mitigations. The project is fully aligned with the GEF Environmental Safeguard Standards and several key IFAD policies, including the IFAD Strategic Framework 2016-2025, Environmental Natural Resource Management (ENRM) Policy, and Climate Change Strategy. It also adheres to IFAD's policies on Gender Equality, Indigenous Peoples, Land Access and Tenure, and Knowledge Management.

The project has undergone a thorough review in line with IFAD’s Social, Environmental, and Climate Assessment Procedures (SECAP), which classified the project as Category B, indicating moderate potential for social and environmental impact.

Mitigation measures have been implemented to address these risks, with a focus on climate change-related vulnerabilities, such as increased flooding and droughts that could disrupt peatland hydrology and exacerbate fire risks .

The SMPEM project significantly contributes to global environmental benefits by promoting sustainable peatland management across Malaysia. The project targets key areas such as peatland forest conservation, reducing greenhouse gas (GHG) emissions, and enhancing biodiversity. Through activities like restoring degraded peatlands, preventing fires, and supporting sustainable agriculture, the project helps sequester carbon and reduce GHG emissions linked to land degradation and fires. It also promotes biodiversity by restoring peat swamp forests and creating wildlife corridors to protect habitats.

Efforts to reduce emissions include fire prevention measures, such as Fire Danger Rating Systems (FDRS), public awareness campaigns, and community training, which have led to a decline in peatland fires. Restoring peatland hydrology through canal blocking and check dam maintenance has also helped reduce carbon emissions by preventing peat oxidation. Furthermore, sustainable agriculture practices, such as MyGAP certification, have minimized environmental impacts, helping maintain peatland integrity. Integrated early warning system (Sabah): Improve the system and foster greater integration among agencies to enhance awareness and mitigate disasters that could impact economic development. This approach can serve as a pilot model and be replicated in other states.

- Financial Management and Execution

- Disbursement Rate (rating: Unsatisfactory)

As of 30th June 2024, the disbursement of IFAD grant fund (i.e. Grant No. 2000000958) was US$ 1.90 million or 20.10% against the total grant (i.e. FI No. 2000000958) of US$ 9.43 million including initial advances. IFAD has disbursed USD 3,244,400 or 34% of the total project budget.

The COVID-19 pandemic (2021-2022), along with the impacts of natural disasters (flooding) in project sites, caused significant delays in implementation and led to low disbursement rates. The complexity of administrative processes across multiple levels of government has slowed decision-making processes, due to the multiple layers of clearance and approval, such as the need for trust deeds at both the national and state levels. The mission noted that the project disbursement improved since the previous year, nonetheless, the project disbursement rate remains unsatisfactory. A no-cost extension of 18-months has been requested by the Project.

- Quality of financial management (rating: Moderately Satisfactory)

The mission assessed the soundness of the project’s financial management arrangement. A continued sound financial management, including risk management as part of the prudential financial management is emphasized.  The project should maintain regular and continued staff capacity building in technical areas relevant to financial management, ensuring better linkage between the project’s planning including budgeting, progress monitoring and reporting therefore ensuring the key functions such as expenditure realization; fund disbursement and timely submission of IFRs and WAs, and follow-up on audit opinions.

The project should, furthermore, pay special attention to the timely submission of AWPBs and IFRs.

AWPB Review: The project submitted the AWPB 2024 on 21 May 2024. IFAD approved it on 18 June 2024, allocating USD 4,526,927 from the GEF Grant. As of the mission date, implementation has been limited due to delays in establishing the AWPB. Ideally, the AWPB should be implemented over 12 months. However, due to delay on preparation of AWPB, the project should set up a maneuverer action to expedite the implementation of AWPB 2024 within six months (18 June – 31 December 2024), without sacrificing the output quality and pay attention to the deliverable deadline.

| Actions Project management | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| PMO FM capacity building Refresh the knowledge and skills of PMOs’ key officials and especially FM staff in financial management and fiduciary administration in line with the evolved IFAD instruments | NPMO and SPMOs | Dec 2024 and continuously | Agreed |

- Quality and timeliness of audit (rating: Unsatisfactory)

External Audit of the project’s financial statements for the Financial Year 2021 and Financial Year 2022 have been completed by the SALIHIN, Chartered Accountants. The unqualified audit reports of the project financial statements for the fiscal years 2021 and 2022 were submitted to IFAD on 21 Nov. 2023. The project should submit the audited financial statement and audit reports for FY 2023 to IFAD.

- Counterpart funds (rating: Moderately Unsatisfactory)

Record of government funding needs to be an integrated part of the project M&E and financial management systems. The mission witnessed success stories and good management practices during its field visits, but it was not clear how these activities were financed or co-financed. As consequence, governments’ actual contributions were partly missing in both M&E and financial progress reports, making it difficult for the mission to appreciate the governments’ contributions in financial terms.

| Actions Project management | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Government funding recording and reporting Integrate the government fundings of all levels into the M&E and FM systems to systematically record ad report the government contributions at all relevant levels | NPMO and SPMOs | Immediately and continuously | Agreed |

- Procurement Review (rating: Moderately Unsatisfactory)

The mission conducted the procurement review of the NPMO and SPMO in line with Malaysia’s procurement policies.

Procurement Plan. The implementation of the procurement plan is limited both at NPMO and SPMOs. The project delayed in submitting the 2024 project procurement plan, IFAD received it on 21 May 2024 then the IFAD granted the no-objection on 18 June 2024. This delay impacted to performance of project procurement, and project implementation. Some of the procurement listed in the 2024 Procurement Plan was prepared too generic; hence, the PP provides insufficient information. For instance, procurement for “Works on rehabilitation” in Pahang. No further information the object to be rehabilitated. The mission has provided guidance notes to the PMU on updating the project procurement plan, considering the PP is a living document and a tool for the project to monitor their procurement activities. The mission identified a need to refine the PP more informative and taking into account the implementation schedule as detailed in AWPB. Taking into account the procurement procedure that takes a long time due to the Government system, e.g. 4-5 months for procurement above RM 50k. In addition, the project is required to liaise with related technical parties to define the goods or service to be procured. For instance, the project should seek advice from Fire and Rescue Office for procurement of fire Extinguishing, fighting, preventing and controlling fires.

During the site visit, the project demonstrated infrastructure and equipment procured to support the project implementation. Taking into account the resource of SMPEM was from IFAD (GEF Grant), and other co-finance parties. The project should prepare the list of assets based on the financier and update it regularly. Including the record of asset handover to the beneficiaries.

| Actions | Responsibilities | Deadlines | Status |
| --- | --- | --- | --- |
| Submit an updated procurement plan to include the detail of items to be procured by NPMO and SPMOs | Admin and Finance Officer | Sep 2024 | Proposed |
| Prepare a list of assets based on the financier, and update it regularly. | Admin and Finance Officer | Sep 2024 | Proposed |
| Procurement Management Training for project staff | Project Coordinator and NRES Procurement Division | Oct 2024 | Proposed |

## Relevance

- Relevance (rating: Satisfactory)

The design of the SMPEM project has been validated as essential in in fulfilling Malaysia’s national commitment to sustainable peatland management and the regional haze-free commitment in ASEAN. The project’s goal is to strengthen national policy and institutional capacity to implement peatland-related strategies and plans, thereby (i) updating the National Action Plan for Peatlands (NAPP) to mainstream the APMS, (ii) developing the State Action Plan for Peatlands in Selangor, Pahang, Sabah, and Sarawak, and (iii) improving Integrated Peatland Management (IPM) in five target peatland landscapes across four states (Selangor, Pahang, Sabah, and Sarawak) in Malaysia.

The project’s target population includes communities in the identified peatland landscapes, focusing on poor, marginalized local communities and indigenous people. Additionally, SMPEM aims to conserve natural resources, prevent land degradation and fires, and generate benefits for present and future generations, supporting the government’s plan to contribute to the international pledge for UNFCCC (Climate Change) and the UNCBD Biodiversity.

The SMPEM project aligns with key GEF-6 focal area strategies, specifically CCM-2 Programme 4 and SFM-2 Program 5. Under CCM-2 Programme 4, the project focuses on conserving and enhancing carbon stocks in forests and other land uses, while promoting climate-smart agriculture. It aims to reduce greenhouse gas emissions from peatland forest drainage and burning, and improve plantation and agricultural management both locally and nationally by implementing and updating the National Action Plan on Peatlands and related strategies. In line with SFM-2 Program 5, the project seeks to increase the application of good management practices among government, local communities, and private sector actors in areas affected by seasonal fires, including forest reserves, national parks, and adjacent plantations. The SMPEM project’s objectives of reducing emissions through peatland protection, fostering climate-smart agriculture, and engaging diverse stakeholders in restoring critical forest ecosystems remain highly relevant to GEF-8’s continued focus on integrated, cross-cutting solutions to climate change, biodiversity loss, and land degradation.

The project is fully aligned with several key IFAD policies, including the IFAD Strategic Framework 2016-2025, Environmental Natural Resource Management (ENRM) Policy, and Climate Change Strategy, and the IFAD strategies on Gender Equality, Indigenous Peoples, Land Access and Tenure, and Knowledge Management.

The SMPEM project significantly contributes to global environmental benefits by promoting sustainable peatland management across Malaysia. The project targets key areas such as peatland forest conservation, reducing greenhouse gas (GHG) emissions, and enhancing biodiversity. Through activities like restoring degraded peatlands, preventing fires, and supporting sustainable agriculture, the project helps sequester carbon and reduce GHG emissions linked to land degradation and fires. It also promotes biodiversity by restoring peat swamp forests and creating wildlife corridors to protect habitats.

Efforts to reduce emissions include fire prevention measures, such as Fire Danger Rating Systems (FDRS), public awareness campaigns, and community training, which have led to a decline in peatland fires. Restoring peatland hydrology through canal blocking and check dam maintenance has also helped reduce carbon emissions by preventing peat oxidation. Furthermore, sustainable agriculture practices, such as MyGAP certification, have minimized environmental impacts, helping maintain peatland integrity.

- Update of needs in project support. The mission observed that needs of capacity building in both knowledge and skills, and equipment and materials have evolved since the project design undertaken in 2017 – 2018. Despite the government continued support programmes in the sustainable management of peatland ecosystems and improved capacities and resilience, the weather and geographical factors were identified as one of the increasing challenges. Extreme weather such as heavy rains, floods cause devastating damages to the peatland areas including its conservation and protection infrastructures. This to some extent confirms the necessity of continued and increased investments in sustainable management of peatland ecosystems, from both the Government and development agencies such as GEF and IFAD in one hand, and in another lead to the need of undertaking a revisit of needs and possibly priority activities, new and existing in line with designed project outputs and expenditure categories, in order to ensure further implementation’s relevance and improved responsiveness.

| Actions Project management | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Update on project focus support in peatland management Undertake a revisit of needs and possibly priority activities, new and existing in line with designed project outputs and expenditure categories, in order to ensure further implementation’s relevance and improved responsiveness | IFAD, Forestry Department, project states and PMOs | 01/2025 | Agreed |

## Modifications identified during the Mid-term Review mission:

| Modifications |  |  |
| --- | --- | --- |
| Extension of Project Completion Date | Yes | ☐X |
| Project implementation started during the severe lockdown imposed in Malaysia due to the COVID-19 pandemic in 2021-2022, along with the impacts of natural disasters (flooding) in project sites, caused significant delays in implementation and led to low disbursement rates. As of the end of June 2024, the GEF grant progress registered a total of USD 1.190 million, accounting for 13% of the total budget. The project has started to gain momentum and implementation of activities has recently accelerated. For example, target communities and degraded peat forest areas for rehabilitation have been identified by the SMPEM Project by means of stakeholder engagement activities and consultations, which have concurrently informed the implementation strategy. The National Peatland Steering Committee (NPSC) agreed on an 18-month extension during a meeting on 22 September 2023 to ensure the project’s goals and objectives are achieved. |  |  |
| Financial Fund Flow | Yes | ☐X |
| - Slow fund disbursement is likely due to lengthy administrative hurdles, which led to delayed implementation; the mission notes the disbursement is particularly slow. The complexity of coordinating across multiple levels of government has slowed decision-making processes, due to the multiple layers of clearance and approval, such as the need for trust deeds at both the national and state levels, hindering progress on policy enhancement and capacity building. |  |  |

## Lessons Learnt

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Project Design |  |  |  |  |  |  |  |

The key lesson learnt relates to the project design: the project was designed in 2017 – 2018 and for a period of four years to address policy dialogue and engagement at both national and state levels, which tend to be slow processes normally. The complexity of component interlinkage at three levels and involving multi-sector stakeholders were also demanding in effectiveness and efficiency of project management and coordination. This could have partly affected the slow progress of operational implementation, therefore causing low disbursement rate. Saying so, there were good achievements underway thanks to multi-sector stakeholder platforms and approaches enhanced by components 1 and 2; good practices of public-private partnership that engaging the rural communities were reported by the project and some witnessed by the mission. The SMPEM has laid down a good foundation for further focused investments at landscape level.

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Project Management |  |  |  |  |  |  |  |

High staff turnover can erode institutional capacity and continuity in project management and coordination. Sustaining stable, qualified, and sufficient staffing at both national and state PMOs is critical for maintaining built capacities and ensuring operational consistency, particularly in core functions like financial management, M&E, knowledge management, procurement, and coordination.

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Project Management |  |  |  |  |  |  |  |

Strengthening PMO capacity can be effectively supported by integrating additional technical focal points from relevant departments (e.g. Forestry, Environment) into core project functions on a part-time or ad hoc basis.

## GEF Core Indicators

| Core Indicator | Target |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Baseline | Mid-line | End-Line | Baseline | Mid-line | End-Line | Means of verification |
| Core Indicator 4 Area of landscapes under improved practices (hectares; excluding protected areas) |  | 80,000 ha | 450,000 ha | 0 | 91,045.40 Ha |  | NAPP, SAPP, IMP |
| Core Indicator 6 Number of tonnes of GHG emissions (CO2e) avoided and / or sequestered | Using data in 2021 | 1.0 million MT CO2e mitigated | 3.06 million MT CO2e mitigated |  | None Methodology for GHG measurement in development |  |  |
| Core Indicator 11 Number of individual benefiting from sustainable peatland management (with> 50% women) |  | 300 persons | 1,000 persons |  | 4,006 persons |  |  |

## Logframe

(as of August 2024)

| Results Hierarchy | Indicators |  |  | MTR Results (2024) |
| --- | --- | --- | --- | --- |
|  | Name | Mid-Term | End Target |  |
| Development Objective: Strengthen national policy and institutional capacity for implementing peatland-related strategies and plans and to enhance integrated peatland management in targeted landscapes | National Action Plan on Peatlands 2021-2023 adopted and resourced and under implementation (number) | - | 1 | - |
|  | Metric Tons of GHG emissions (CO2e) avoided and / or sequestered (MT CO2 e mitigated) | 1.0 million | 3.6 million | - |
|  | Number of persons benefiting from sustainable peatland management |  |  |  |
|  | Male | 150 | 500 | 2191 |
|  | Female | 150 | 500 | 1815 |
|  | Total | 300 | 1000 | 4006 3780 |
| Outcome 1: Enhanced resources, multi-stakeholder involvement and capacity for implementing the National Action Plan on peatlands and other policies and plans up to 2030 | % increase in financial resources (public, private, and external) channeled for sustainable peatland management |  | 30% | - |
| Output 1.1. Policies, Guidelines, institutional arrangements and capacity for sustainable peatland management enhanced | Number of new or revised laws, regulations, policies, plans, or strategies proposed to national-level policy makers for approval, ratification or amendment | 3 | 5 | 2 |
| Output 1.2. Investment framework for NAPP 2021-2030 developed and adopted | NAPP investment framework adopted by national and state-level stakeholders and mainstreamed into national development plan 2021-2025 | - | 1 | 0 |
| Output 1.3. Knowledge management and exchange to support scaling-up of sustainable peatland management | Peatland knowledge management system established and being used | - | 1 | 1 |
| Outcome 2: Improved sustainable management of peatlands in target states | Increase in the use of sustainable management practices in agriculture and plantations located on peatlands | + 100,000 ha | + 300,000 ha | 0 (SMPEM completed the guidance to develop SAPP in October 2024). |
| Output 2.1. State Action Plan on Peatlands (SAPP) developed and adopted by Pahang, Sabah, Sarawak and Selangor | Adoption of SAPPs | - | 4 | 0 |
| Output 2.2. Best management practices introduced in agriculture and plantation sectors in Pahang, Sabah, Sarawak and Selangor | Persons trained in agriculture and plantation sectors using BMP |  |  |  |
|  | Male | 113 | 375 | - |
|  | Female | 37 | 125 | - |
|  | Total | 150 | 500 | 12 |
| Output 2.3. Best management practices for peatland fire prevention and control in four states | Persons trained introduced in agriculture and plantation sectors using BMP | 130 | 300 | 132 |
| Outcome 3: Integrated Peatland Management Plans (IMPs) adopted and implementation initiated by multiple sectors in five peat landscapes | Area of peatland-dominated landscapes with IMP adopted and being implemented by multiple sectors (ha) |  | 450,000 ha | 91,045.40 Ha |
| Output 3.1. Review, update and implement existing Integrated Management Plan (IMP) for North Selangor Peat Swamp Forest (NSPSF), and develop a new IMP for South Selangor Peatland Landscape (SSPL) | IMPs for NSPSF implemented (number) |  | 1 | 1 |
|  | A new IMPs for SSPL developed (number) |  | 1 | 1 |
| Output 3.2. Review existing IMP for Southeast Pahang Peat Swamp Forest (SEPPSF) to update and expand the scope to cover the Southeast Pahang Peatland Landscape (SEPPL) | IMP for SEPPSF reviewed and to be included in IMP for SEPPL (number) |  | 1 | 0 |
| Output 3.3. Develop and implement new landscape level IMP for Klias Peninsula Peatland Landscape in Sabah | IMP for KPPL developed, adopted and implemented by the State Government (number) |  | 1 | 0 |
| Output 3.4. Develop and implement a landscape level IMP in the Maludam Peninsula, Sarawak | IMP for MPPL developed, adopted and implemented by the State Government (number) |  | 1 | 0 |

### Annex 1: Mission preparation and planning, TORs, schedules, people met.

GEF Supervision Mission – Malaysia

| MISSION DETAILS |  |
| --- | --- |
| Country of Assignment/Location: | Malaysia |
| Mission Name: | Mid-term Review mission |
| Mission Start Date: | 19 August 2024 |
| Mission End Date: | 30 August 2024 |
| Division/Department: | APR |
| Reports to (name and title): | Hani Elsadani Salem |

| INDIVIDUAL RESPONSIBILITIES, EXPECTED OUTPUTS AND REQUIRED COMPLETION DATES |  |  |
| --- | --- | --- |
| Full Name of mission member: | Description of Tasks (Expected Activities) | Expected Outputs/deliverables |
| Hani Elsadani Salem (Country Director) Yumi Sakata (Programme Officer) | The Country Director and the Regional Climate and Environment Specialist will provide overall technical and managerial guidance to the IFAD team, will lead the discussions with the NRES and JPSM from the IFAD side, and will ensure that the Aide Memoire and other documents to be prepared as a result of the Mid-Term review meet the expected quality standards. - Lead the team during the kick-off and wrap up MTR mission - Lead the strategic meetings with the government of Malaysia - Lead meeting with GEF OFP Malaysia |  |
| Team Leader & Project Management Specialist (TL) (Peter Situ - Independent consultant) | The Team Leader will be responsible for the following: - Assess SMPEM project progress, performance and quality of implementation in line with the defined objectives, and legal and financial agreement. - Identify barriers and challenges during the implementation of the project, and discuss with the Project team - solutions, strategy and action plan to address the barriers and challenges. - Assess current human capacity gap and staffing of the NPMU, SPMU. - Identify SMPEM project implementation bottlenecks and recommend actions to speed up project implementation. - Review and suggest revisions as necessary the current SMPEM implementation plans, AWPBs and procurement plans. - Review national and States implementation structures and discuss the integration of the others peatland project within these structures. - Propose project rating following IFAD Mission criteria and provide justifications. - Consolidate inputs from all team members and finalize the Aide Memoire in coordination with the other team members following IFAD’s formats and requirements. - Lead the compilation of the GEF Tracking Tools for the SMPEM project, updated at MTR. | Expected deliverables: - MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD – 30 August 2024 - Draft Aide Memoire summarizing the findings and recommendations of the mission, which are to be discussed and agreed with the NRES and other relevant stakeholders – 31 August 2024 - Final MTR report (in English) to be submitted, including a 2–3-page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided – 10 September 2024 |
| Programme Analyst & support to M&E and KM (Chiara Merola) | - Identify the Monitoring & Evaluation (ME) and Knowledge Management-Communication (KMC) concept and review the progress and the achievement to achieve the project outputs/outcomes. - Review the SMPEM M&E system and reporting (incl. logframe etc) in the absence of the baseline report, including tools for collecting information; M&E reporting (quality, timeliness), use of M&E for planning/AWPB and reporting (SAPR, PIR). - Identify gender and youth-targeted activities in the project and propose any recommendations for improved engagement where necessary. - Identify potential knowledge products (KPs) from the project and support the review of produced KPs when necessary. - Propose and recommend for the M&E and knowledge management improvements for SMPEM including knowledge products (i.e. publications, videos, etc.), as well as outreach and project visibility aspects. - Review and provide inputs on SMPEM-related NRES and JPSM Management Information System (MIS) and websites. - Review the knowledge/outreach products and define the key recommendations for sustainability knowledge and information. - Review the exit strategy document from the project. - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to M&E and Knowledge Management arrangements, process, and records – 30 August 2024 - Contribute for Final MTR report (in English) as guided by TL – 7 September 2024 |
| Environment and Natural Resources Management Specialist (ENRMS) Praise Uke (Independent consultant) | Will be responsible for: - Assess SMPEM project progress, performance and quality of implementation in line with the defined objectives, and legal and financial agreement. - Identify barriers and challenges during implementation of the project, and discuss with the Project team - solutions, strategy and action plan to address the barriers and challenges. - In coordination with other team members identify SMPEM project bottlenecks and provide necessary support to speed up project implementation. - Keep track on the mission reporting timeline and follow up on the IFAD internal process. - In coordination with SPMS and ECO, discuss on the next SMPEM implementation plan including review their AWPB. - Contribute in the assessment of project performance and quality of implementation with a focus on (a) peatland policy, regulations and institutional mechanisms and capacity enhanced, (b) PHU mapping, (c) development of integrated management plan (IMP) for KG & GB PHUs (c) enhancement of community livelihood from sustainable peatland management practice (under Components 1 and 3); - Contribute to the assessment of project performance and quality of implementation with a focus on (a) assessment of GHG emission reduced, identify any bottlenecks and provide recommendations, (b) assessment of progress of peatland fire prediction, monitoring and warning systems (under Component 2); - Propose project rating following IFAD Mission criteria and provide justifications especially on (a) overall project performance (b) likelihood of achieving project objectives, outputs and outcomes, (c) implementation progress related to Component 2 and beyond. - Assess and review the environment, social and climate change impacts identified in PDR/CER, and its consistency with the county systems and/or IFAD SECAP procedure in 2021 - Support compilation of the GEF Tracking Tools for the SMPEM project - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Review and report the SECAP – 30 August 2024 - Update the GEF Tracking tool for SMPEM – 30 August 2024 - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to environment, secap and technical issues – 30 August 2024 - Contribute for Final MTR report (in English) as guided by TL – 7 September 2024 |
| Environment & Climate Change Specialist (Dudy Nugroho) | Will be responsible for: - Coordinate communication between the project team and NRES/JPSM staff. - In coordination with other team members identify SMPEM project bottlenecks and provide necessary guidance and support to speed up project implementation with a focus on (a) assessment of GHG emission reduced, identify any bottlenecks and provide recommendations, (b) assessment of progress of peatland fire prediction, monitoring and warning systems (under Component 2). - In coordination with Team Leader, Senior Peatland Management and ENRMS discuss on the next SMPEM implementation plan including a review their AWPB. - Review performance against and alignment with AWPBs. - Propose project rating following IFAD Mission criteria and provide justifications, especially on (a) likelihood of achieving project objectives, outputs and outcomes, (b) implementation progress related to Component 2 and beyond. - Identify and prepare knowledge product to showcase best practices and/or lessons learned on peatland management based on project implementation. - Review national/federal and state implementation structures and discuss the integration of the upcoming SaPPLIM project within these structures; and - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Share the supporting documents to be used for the MTR mission – 18 August 2024 - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to technical issues in the log frame and GEF indicator– 30 August 2024 - Contribute for Final MTR report (in English) as guided by TL – 7 September 2024 |
| Procurement Specialist (Muhammad Iskandar) | Will be responsible for: - Assess and review the procurement arrangements, and process of the SMPEM Procurement Plans (PPs), and their consistency with the county systems and/or IFAD Procurement Guidelines and Handbook. - Assess the challenges and motives for the turnover project staff and make recommendations. - Provide recommendations for improvement on the following: - The thresholds, ceilings and preferences to be applied in the implementation of procurement under the project. - The contract types and contractual arrangements for goods, works and consulting services required to implement the projects. - The proposed methods of procurement. - The related IFAD review procedures and provide suggestions to improve the overall quality of the procurement processes. - Review a minimum sample of 10% of all procurement contracts for compliance. - Carry out spot checks on past procurement activities and assess the extent these adhere to Government and/or IFAD Procurement Guidelines and Handbook; in particular, verify that the goods, services and works procured correspond with the approved AWPB and Procurement Plan, in terms of quality and quantities. - Review the procurement, contracting and implementation processes and timeliness and appropriateness of procurement actions. - Assess contract administration and management procedures. - Assess the procurement capacity of all entities to be reviewed in terms of manpower, levels of training of procurement staff, work environments and independence of procurement staff to carry out their statutory assignments. - Determine whether adequate systems are in place for procurement planning, implementation and monitoring, and whether documentation are maintained as per required standards and can be relied upon. - Review issues identified in the previous procurement review and aide-mémoire and procurement related issues identified in project audit reports. - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to procurement arrangements, process and records – 30 August 2024 - Contribute for Final MTR report (in English) as guided by TL – 7 September 2024 |
| Finance Specialist (Gadzhi Murad Abdulvadudov) | Will be responsible for: - Review and assess financial management, including but not limited to statement of expenditures, audit report, AWPBs, fund flows, bank accounts setting, and withdrawal applications, and contribute to the FM sections of the Aide Memoire in line with IFAD’s procedures. - Review the arrangements for financial management and fund flow to ensure it is in line with IFAD procedures and the project budget and AWPBs. - Identify risks related to financial management, develop mitigation measures, and provide recommendations for improvement when applicable. - Review the results of the latest external Audit Report (including specifically the Management letter) to ascertain whether any issues raised by the auditor identify potential fiduciary risks - where relevant follow up on issues arising by meeting on-site. - Consult main findings, requests for clarification and action plan proposed by FMD with the latest audit review exercise. - Identify and measure the co-financing that has been achieved by the SMPEM project from government or other sectors. - Use the original FMAQ as the basis to review the relevant information to re-assess the strengths and weaknesses of financial management systems. - Review sample Withdrawal Applications and Statements of Expenditure to verify the adequacy, completeness and validity of claims - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to financial management arrangements, process, and records – 30 August 2024 - Contribute for Final MTR report (in English) as guided by TL – 7 September 2024 |

### Itinerary of the Mid-term Review (MTR) of the GEF6 SMPEM project in Malaysia

| Day/Date | Mission Schedule | Location & Participants |
| --- | --- | --- |
| Mon, 19 Aug | Team meeting: JPSM, SMPEM, IFAD and Consultant | JPSM office (KL) 7 participants (Male: 6 & Female: 1) |
| Tue, 20 Aug | Kick off the MTR mission (NRES, JPSM, SMPEM team, IFAD and Consultant) | Ministry of Natural Resources & Environmental Susaiatibility (NRES) office (Putrajaya) Hydrib meeting & participated by 26 participants (Male: 13 & Female: 13) |
|  | Travel to the field from Putrajaya. | Team-1: Pahang Team-2: Sarawak |
| Wed, 21 Aug | Team-1 (Pahang) - Field visit to Pekan Forest Reserve (Durian Sebatang vicinity) to see the effects of forest fire and usage of thermal drones. - Field visit to Ladang PKPP Sei Jelutong (Check Dam) | Team- 1 IFAD: Peter Situ, Gadzi, Muhammad Iskandar. SMPEM: Dr. Ainnudin, Amilin, Baizura. 28 participants (Male: 22 & Female: 6) |
|  | Team-2 (Sarawak) - Field visit to Maludam & meeting with Sarawak Forestry Corporation | 10 participants (Male: 8 & Female: 2) |
| Thu, 22 Aug | Team-1 (Pahang) - Meeting with Pahang Forestry Department Depart to Selangor | 13 participants (Male: 8 & Female: 5) |
|  | Team-2 (Sarawak) - Meeting with SMPEM management & Forest Department Sarawak - Depart to Sabah (pm) | 8 participants (Male: 5 & Female: 3) |
| Fri, 23 Aug | Team-1 (Selangor) - Meeting with SMPEM Management in Selangor State - Field visit to Selangor Peatland Landscape | 21 participants (Male: 13 & Female: 8) 26 participants (Male: 16 & Female: 10) |
|  | Team-2 (Sabah) - Meeting with SMPEM Sabah Management at NRO Office - Meeting with Sabah Forestry Department at Klias Peatswamp Field Centre, Beaufort (led by Mr. Christopher) | 12 participants (Male: 8 & Female: 4) 7 participants (Male: 4 & Female: 3) |
| Sat, 24 Aug | Team-2 (Sabah) - Field visit to Community Pineapple Farm in Beaufort | 25 participants (Male: 12 & Female: 13) |
|  | - Visit to Sago production by the community in Beaufort | 10 participants (Male: 5 & Female: 5) |
| Fri, 30 Aug | Wrap-up MTR mission: NRES, JPSM, IFAD and Consultant at NRES office (Putrajaya) | 31 participants (Male: 12 & Female: 19) |

### List of Documents Reviewed

- GEF6 SMPEM Full Proposal (PDR) agreed by GEF Secretariat (include the cost tabulation)

- SMPEM Financial Agreement

- SMPEM Letter to the recipient and Amendment Letter

- SMPEM GEF Tracking Tools (compiled at design for LD, SFM, and CCM)

- SMPEM Annual Work Plan and Budget (AWPB) and Procurement Plans (PP) 2024 and previous ones

- SMPEM Project Implementation Manual (PIM)

- SMPEM 1st Project Implementation Reports (PIRs)

- SMPEM 2nd Project Implementation Reports (PIRs)

- SMPEM 3rd Project Implementation Reports (PIRs)

- SMPEM Semi-Annual Progress Reports (SAPRs)

- SMPEM Implementation Support/Supervision Mission (2021 – 2022) Resume of Meeting (aide memoire)

- SMPEM Inception Workshop Report

- SMPEM Financial Reports (include the audit reports)

### List of Stakeholders Consulted

            - The Ministry of Natural Resources and Environmental Sustainability (NRES)

            - Forestry Department of Peninsular Malaysia (Jabatan Perhutanan Semanjung Malaysia – JPSM)

            - Selangor Forestry Department (State Level)

            - Pahang Forestry Department (State Level)

            - Sarawak Forestry Department (State Level)

            - Sabah Forestry Department (State Level)

            - Economic Planning Unit (Sabah State Government)

            - Economic Planning Unit (Pahang State Government)

            - National Project Management Office

            - State Project Management Office (Selangor, Pahang, Sabah & Sarawak)

            - Enggang Foundation (Pahang – Private Sector)

            - Global Environment Centre – GEC (NGO)

            - Maludam National Park (Government)

            - Community Group in Maludam

            - Department of Agriculture (Pahang, Sabah, Sarawak)

            - Fire and Rescue Department (BOMBA – Selangor, Pahang, Sabah & Sarawak)

            - Community Group in Beaufort – Sabah (pineapple)

            - Community Group in Beaufort – Sabah (sago)

            - Malaysia Plam Oil Board (MPOB)

            - Natural Resources Office (NRO – Sabah State Government)

GIZ Sustainable Use of Petland and Haze Mitigation in ASEAN (SUPA) commissioned by German Federal Ministry for the Environment, Nature Conservation and Nuclear Safety (BMU), co-funded by European Union,  and implemented by GIZ from 2018 – 2024.

At the time of the Mid-Term Review (MTR), implementation of the Integrated Management Plans (IMPs) had not yet commenced. However, the project initiated implementation activities soon after, in January 2025. The IMPs cover two key landscapes in Selangor, comprising a total of 91,045.40 hectares: 81,530.96 ha in the North Selangor Peat Swamp Forest and 9,514.42 ha in the South Selangor Peatland Landscape.