WWF GEF Agency

Project Implementation Report

“Enduring Earth: Accelerating Sustainable Finance Solutions to Achieve Durable Conservation” (GEF-7) (GEF ID:  11014)

Project Report information:

| Report Author(s) | Robbie Bovino |
| --- | --- |
| Report Completion Date | September 15, 2025 |

| 1. General Information | PIR Submission Date | 15 September 2025 |
| --- | --- | --- |
|  | Agency Approval Date | 18 February 2024 |
|  | Fiscal Year | FY24/25 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 1st PIR |
| 2. Current Year Ratings | Overall DO rating | S - 89% |
|  | Overall IP rating | S – 83% |
|  | Overall Risk rating | Low |
| 3. Key dates | Actual Implementation Start Date | 8 January 2024 |
|  | First Disbursement Date | 16 January 2024 |
|  | Expected Mid-Term Review Date | 2027, May |
|  | Expected Completion Date | 31 December 2029 |
|  | Expected Financial Closure | 2030, February |
|  | Actual Completion Date | n/a |
| 4. BUDGET | Total Project Budget (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | $22,635,780 (GEF TF) |
|  | Total GEF disbursement (USD) through June 30 of the FY for project that has been in implementation for at least 1 FY (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | $467,572 |
|  | Committed Co-finance | $98,958,731 |
|  | Materialized Co-finance | $9,835,953.25 |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |

| Project Manager | Velice Nangavo | velice.nangavo@tnc.org |
| --- | --- | --- |
| M&E Officer | Julie Byun | Julie.byun@tnc.org |
| Grants officer | Edgar Odhiambo | Edgar.odhiambo@tnc.org |

WWF GEF Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Robbie Bovino | Robbie.Bovino@wwfus.org |
| M&E Specialist | Amelia Kissick | Amelia.Kissick@wwfus.org |
| Program Operations | Tracey Smith | Tracey.Smith@wwfus.org |
| Safeguards Specialist | Soledad Altrudi | Soledad.Altrudi@wwfus.org |
| Gender Specialist | Nathalie Simoneau | Nathalie.simoneau@wwfus.org |

Instructions:

The WWF GEF Project Manager is responsible for completing the PIR in coordination with the Project Management Unit. It may be necessary to consult with other experts for current data (e.g. Safeguards, Gender, RBM, etc). Please include the following annexed documents:

- Completed Tracking Tool with Results Framework and Annual Work Plan and Budget Tracking (for project year)

- Tracking tools (eg. METT), if applicable

- Knowledge Management products (if links were not provided in the section directly)

- Other supporting documents: meeting minutes, stakeholder consultation, photos, maps, reports, etc.

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year X |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective | S – 89% |  |  |  |  |  |  |
| Implementation Progress | S – 83% |  |  |  |  |  |  |
| Risk | Low |  |  |  |  |  |  |

Justification for Current Year Ratings:

Development Objective The Development Objective rating was calculated using the Results Framework (RF) approved in September 2023, and the Implementation Progress rating calculated using the Year 1 Annual Work Plan and Budget (AWPB) approved in May 2024. Progress against targets for all indicators in the RF and AWPB can be found in Annex 1. PPR Year 1 Tracking tool_RF, AWPB.xlsx. In year 1, 12 objective and outcome indicators were reportable. Only one indicator, concerning the completion of METT baseline in Gabon, achieved less than 80%. The PFP design processes (development of conservation plans, financial models, etc.) in both Namibia and Gabon (which will receive the bulk of project funds) have advanced well this reporting year, with closings expected in both countries by the end of 2025. In anticipation, deal teams in each geography with support from the PMU have advanced preparations for the CTFs (PFP fund administrators) to operationalize and to receive the GEF’s PFP capital contributions through, e.g.: staff hiring (Gabon); preparation of ESMS (Gabon); preparation of disbursement checklist tools (both countries); consultations on the conditions and expectations concerning GEF funds (both countries); and planning for trainings (expected in late 2025/ early 2026)(both countries). Progress in ETP to support the design of a regional durable finance mechanism has been steady, and the global coordination work of the Enduring Earth Coalition has helped strengthen the partnership and build a foundation for future productive collaborations on PFP. Implementation Progress Only Component 1 achieved less than 80%, primarily due to the late start of the activities (Year 1 AWPB approved in May 2024 for all EAs), and subsequent delays in contracting consultants in Gabon and selecting the Conservation Trust Funds (CTF) in Namibia. Gabon also experienced significant disruptions in the PFP planning process following the administrative changes brought about by the 2023 coup. Risks Risks associated with the project remain low. Across the 24 identified risks (encompassing both low and modest risk levels; there are no assessed substantial or high risks), mitigation strategies have significantly decreased potential impacts.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Progress Overview The PFP design processes (development of conservation plans, financial models, etc.) in both Namibia and Gabon (which will receive the bulk of project funds) have advanced well, with closings expected in both countries by the end of 2025. In anticipation, deal teams in each geography with support from the PMU have advanced preparations for the CTFs (PFP fund administrators) to operationalize and to receive the GEF’s PFP capital contributions through, e.g.: staff hiring (Gabon); Board formation and training; preparation of ESMS (Gabon); preparation of disbursement checklist tools (both countries); consultations on the conditions and expectations concerning GEF funds (both countries); and planning for trainings (expected in late 2025/ early 2026)(both countries). In ETP, despite the challenges of working with four different national governments to design a regional durable finance mechanism (see below), Pew continues to advance its activities through strong collaboration with its main partner, the CMAR Secretariat. Over the course of the year, the team has successfully updated key sections of the Durable Finance Mechanism Feasibility Assessment, in particular, those regarding the evaluation of CTFs in the region; political risk analysis; and sustainable financing opportunities. The project has also supported the preparation of the 10-year CMAR Action Plan which will be completed in late 2025; helped to articulate a global treaty that will underpin a regional durable finance mechanism; and assessed CTFs for their capacities to support the implementation of a mechanism. Enduring Earth Coalition. The Coalition has helped to forge relationships with key constituencies (CTFs and their global and regional communities) in line with its role under the project to support knowledge exchange and capacity development across the Enduring Earth partnership with a view to promoting the replication and scaling of the PFP approach. Highlights of this reporting period include: coordination of a south-south exchange on PFP between Costa Rica and Gabon; webinars to launch and disseminate a white paper on CTFs and their role in driving progress for nature / biodiversity conservation; launch of a consultancy to identify scalable and replicable sustainable finance mechanisms (SFMs) for the PFP model; and the launch of a process to develop an Enduring Earth Coalition monitoring and evaluation system. Challenges Gabon. The project has experienced significant uncertainty and delays due to changes in government leadership (following elections in April 2025), which have slowed but not stalled decision-making processes with respect to the PFP. One of the key unresolved issues is the governance structure for the project —specifically, the designation of the chairperson for the Project Steering Committee – which remains unclear and has hindered coordination and oversight. TNC Gabon and its partners are engaging directly with relevant government counterparts to clarify roles and reaffirm commitments under the project framework. Nevertheless, the development of the PFP has proceeded throughout this period, with close expected in December 2025. ETP. In June 2025, CMAR appointed its first permanent Secretariat, based in Panama, replacing the previous rotating, temporary secretariat. See: New Regional Governance Body Announced at COP16 to… ¦ Bezos Earth Fund. This marks a significant step forward in strengthening the organization's long-term capacity and leadership, but this institutional change poses some risk of delays. Pew is working with the Secretariat to ensure it is fully briefed on project objectives and progress to date and that it remains informed moving forward. Implementation in the ETP is further challenged by the potential for delays associated with the focal countries’ different election cycles. Elections in Ecuador in April 2025 resulted in key personnel changes, including the Minister of Environment. In February 2025 the Minister of Environment in Colombia stepped down. The Pew team has made a focused effort to keep key stakeholders well-informed of project status, decisions and next steps to minimize the risk of delays. Detailed Update on Progress Across Outcomes Outcome 1.1 Conservation goals, funding package and PFP conditions agreed by key stakeholders (including government, donors, NGO partners) in target countries, for improved financial sustainability and management of priority conservation areas This outcome’s focus is the creation of key enabling conditions for the execution of PFPs in Gabon and Namibia. These conditions are being developed largely through direct co-financing. Activities in Gabon have been executed by TNC Gabon; activities in Namibia by WWF Namibia with support from WWF US. Gabon The Gabon Project Finance for Permanence (PFP) is on track to close in November 2025, marking a significant milestone in the country’s efforts to secure long-term biodiversity conservation. A key institutional achievement has been the successful establishment of the Board of Directors for the Fonds de Préservation de la Biodiversité au Gabon (FPBG). Comprising seven members with diverse expertise in conservation, finance, the private sector, and legal affairs, the Board provides oversight and strategic direction to the Trust, laying a strong foundation for the fund’s credibility and effectiveness. In April 2025, the Board approved the Environmental and Social Management System (ESMS), a critical policy framework that ensures all FPBG-supported activities adhere to international best practices in environmental and social risk management. The ESMS promotes inclusivity, transparency, and accountability, guiding project screening, risk assessment, stakeholder engagement, and monitoring to maximize positive outcomes for both people and nature. The Board also reviewed and approved the Grants Manual, which was separated from the Operations Manual so that it can be shared publicly. During this reporting period, significant progress was made in developing a comprehensive conservation plan and financial model. The conservation plan is structured around four key objectives: leveraging protected areas for local economic and social development; redefining governance and strengthening management capacities of existing protected areas; achieving the 30:30:30 target through innovative conservation models; and establishing sustainable financing mechanisms to support conservation and community development. This plan was shaped through extensive stakeholder consultations involving government ministries, departmental representatives, and environmental NGOs. Further advancing the operationalization of the PFP, the Minister of Water and Forests signed a ministerial decree on May 15, 2025, formally establishing a Project Management Unit (PMU) tasked with overseeing the implementation, coordination, and monitoring of the PFP. A subsequent decree on May 19 appointed a PMU Coordinator, ensuring leadership and strategic direction. The coordinator will serve as the primary liaison between the Ministry, stakeholders, and implementing partners, and will be responsible for the day-to-day management and reporting of project progress. These developments collectively signal strong momentum toward timely closing and implementation of the Gabon PFP and the long-term sustainability of biodiversity conservation efforts in the country. Namibia The closing date for the N4L project has been extended from June to November 2025 to allow for the completion of fundraising efforts and to give the Green Climate Fund (GCF) time to assess its potential involvement. This extension also will allow for updates to the Critical Extension Services Plan and Financial Model to better align with GCF priorities. The Implementation Manual is being finalized, and CCFN continues to strengthen governance and operations based on earlier assessments. Of the $75 million fundraising target, $54 million has already been secured, leaving a $21 million gap. This includes a potential $10 million from the GCF, with two $2 million proposals already submitted. Additionally, a donor has indicated interest in contributing $5–7 million if the gap narrows to $10 million. Revisions to the Critical Extension Services Plan (the conservation plan) are ongoing in collaboration with NACSO and other CBNRM stakeholders. Each of the Extension Services workstream leads is working to ensure alignment with the financial model and GCF priorities, with a draft to be shared with stakeholders ahead of a third-quarter meeting. Similarly, the financial model is being updated to reflect current fundraising progress and GCF considerations, with a draft to be reviewed by CCFN and thematic workstream partners. A draft N4L Implementation Manual is also in development to complement the existing CCFN Institutional Operations Manual. It will include PFP-specific content such as closing and disbursement conditions, introductory material from the Critical Extension Services Plan and SEDF, and implementation arrangements like grant-making procedures. This work is expected to be completed during the upcoming third-quarter (2025) stakeholders’ meeting, with efforts underway to fully onboard and engage CCFN in finalizing all key milestones. Outcome 1.2 Enhanced capacity for domestic resource mobilization in Gabon to achieve PFP goals and commitments. Gabon: The Gabon Project Finance for Permanence (PFP) initiative launched the process to develop its financial model. This process is grounded in a series of foundational studies and technical consultancies that are generating the data, insights, and strategic direction needed to inform the model’s design. One key consultancy is focused on assessing the current investment landscape for conservation tourism in Gabon. This includes mapping existing investments, identifying barriers and opportunities within the enabling environment, and proposing reforms to attract greater private sector engagement. The consultancy is also tasked with estimating the scale of financial investment required to transition from the current state to a more robust, sustainable conservation tourism sector. The findings from this study will directly inform the structure and assumptions of the financial model under development. In parallel, another consultancy is underway to explore the potential for Payment for Ecosystem Services (PES) in Gabon. This work involves a comprehensive review of the country’s legal and institutional frameworks to assess their readiness to support PES schemes. It also includes an evaluation of viable PES opportunities—such as carbon credits, watershed protection, and biodiversity offsets—and the development of a national roadmap to guide the implementation of PES mechanisms. Together, these studies are laying the groundwork for a financial model that is both evidence-based and tailored to Gabon’s unique ecological and economic context. The foundational studies are being financed through GEF funds, while the development of the financial model itself is co-financed. Namibia This is not a condition of the Namibia PFP and outputs appearing under this outcome will not be produced for Namibia. Outcome 1.3 Improved protected area management effectiveness and creation of new conservation areas (Gabon) and improved management effectiveness of conservancies (Namibia) during the transition period The Gabon Project Finance for Permanence (PFP) is making steady progress toward closing, and therefore to the articulation of a shared vision for establishing new protected areas and implementing Other Effective Area-based Conservation Measures (OECMs). The Management Effectiveness Tracking Tool (METT) baseline assessment is nearly complete. Out of the 30 protected areas targeted, only four remain to be assessed as of July. The data collected using the Integrated Management Effectiveness Tool (IMET) will be converted into METT format by the National Parks Agency (ANPN), utilizing a specialized conversion tool and handbook developed by a technical expert. This work, supported through co-financing, will provide a standardized baseline for evaluating and improving protected area management. In parallel, Panthera has continued its technical support to establish a baseline for the creation of five potential new protected areas and the expansion of five existing ones. This includes identifying study needs and estimating the budget required for each site. The baseline will be completed by December, 2025. Panthera’s use of nationally validated methodologies for participatory mapping underscores a strong commitment to inclusive and transparent conservation planning. This initiative is jointly funded by GEF and co-financing sources. Another significant step was the signing of a grant agreement in December 2024 with Okala, a private consultancy firm. This contract focuses on conducting a technical and financial study to implement biomonitoring systems across three key ecosystems—marine, terrestrial, and freshwater. The baseline data generated through this study will be instrumental in shaping both the conservation plan and the financial model, ensuring that strategies are evidence-based and responsive to ecological and community needs. Additionally, GEF funds are supporting the renewal of village-level committees and stakeholder representatives for the Community Conservation Governance and Leadership (CCGL) platforms. This process involves identifying outgoing members, facilitating community engagement in the nomination and selection of new representatives, and ensuring inclusive participation across gender, age, and stakeholder groups. The objective is to strengthen local ownership and ensure that these platforms remain representative, responsive, and effective in guiding conservation efforts at the community level. Outcome 1.4: Endowment funds capitalized to invest in improved management effectiveness in priority conservation areas. Gabon: The PMU is working with the CTF management to ensure systems are in place that comply with enumerated disbursement conditions for GEF funds. Work in this area is on track (e.g. Board in place; operations and grant-making manuals are complete; ESMS is developed; investment policy and investment advisor are in place). Namibia This outcome is supported fully by cofinance. The Namibia Trust Fund, Community Conservation Fund of Namibia (CCFN), is actively working to strengthen its internal structures and systems to effectively manage the Endowment Fund, in direct response to recommendations from the due diligence assessment conducted in 2025. This process includes enhancing financial oversight mechanisms, refining investment governance frameworks, and ensuring compliance with international standards for endowment fund management. These improvements are aimed at reinforcing the fund’s long-term sustainability, transparency, and accountability. CCFN is also focusing on building internal capacity and aligning its operational procedures with best practices to ensure readiness for managing and disbursing endowment resources. Full onboarding of CCFN into the PFP structure is currently underway, and a comprehensive update on the progress of these institutional strengthening efforts will be presented during the fourth quarter of 2025. Outcome 2.1 Enabling conditions assessed and necessary conditions developed for a durable finance mechanism in the Eastern Tropical Pacific (ETP) This outcome’s focus has been developing a viability/feasibility assessment and work planning for the enabling conditions of the financial mechanism in the ETP. Progress towards achieving this outcome is captured below. In 2025, Pew played a pivotal role in advancing the Eastern Tropical Pacific (ETP) marine conservation agenda through its support to the CMAR (Eastern Tropical Pacific Marine Corridor) initiative. Pew supported the finalization of the 10-year CMAR Action Plan, which is the blueprint to be adopted by the four countries for regional conservation actions. The Action Plan is now complete and undergoing final review by CMAR. In parallel, a GEF-supported consultancy conducted a legal assessment on the national and regional implications of a treaty to anchor a regional durable financing mechanism, engaging with each of the four CMAR countries—Ecuador, Colombia, Panama, and Costa Rica—both individually and collectively. In April 2025, the consultant presented findings to the CMAR technical and ministerial committees in Panama City, sharing legal options and gathering feedback. This led to the development of a roadmap to finalize binding treaty text within one year. Following the consultation, the consultant drafted a “head of terms” document outlining key treaty elements and shared examples of similar international agreements for comparison. During a virtual meeting on 27 June 2025, CMAR members reviewed the draft, provided input, and agreed on next steps. Pew also continued to advance on the assessment of Conservation Trust Funds (CTFs) in the region that could manage long-term financial resources associated with a durable finance mechanism. One CTF review has been completed in an ETP country, and another is nearing completion. These assessments are derived from the Conservation Finance Alliance’s CTF Standards, ensuring alignment with global best practices. Additionally, Pew engaged Posaidon Capital who conducted a fiscal analysis of each CMAR country and proposed structures for a regional conservation finance mechanism. Posaidon will design an outcome-based finance mechanism for the ETP. Key performance indicators will be developed along with Global Fishing Watch and Migramar and will be aligned with the conservation targets in the CMAR 10-year Action Plan. In April 2025, CMAR established a permanent Secretariat in Panama, marking a new chapter in CMAR’s operational capacity. Previously, a rotating chair was responsible for managing CMAR affairs. Finally, Pew also supported the CMAR technical committee meeting held in Panama City in April 2025, which advanced discussions on the treaty, CMAR 10-year Action Plan, budget, and potential governance structure for the DFM. At the UN Ocean Conference in June 2025, Pew participated in the Eastern Tropical Pacific Connect to Protect Donor Coalition meeting, alongside the GEF. This coalition, comprising public and private funders, has mobilized substantial financial and technical support for CMAR. The meeting, attended by the ministers of environment from Panama and Costa Rica and senior environment officials from Ecuador and Colombia, reaffirmed regional commitment to coordinated governance and long-term conservation in the ETP. Outcome 2.2 Improved knowledge base for PFPs among key stakeholders (global) This outcome continues to focus on building a robust foundation for knowledge exchange and capacity development across the Enduring Earth partnership, with emphasis on enhancing the ability of Conservation Trust Funds (CTFs), PFP deal teams, and Enduring Earth technical partners to advance sustainable finance and durable conservation outcomes. In the first half of 2025, Enduring Earth made significant strides in advancing peer learning, and monitoring systems across its global partnership. In January, Enduring Earth, in collaboration with RedLAC, CAFÉ, and the GEF, hosted a global webinar titled How Conservation Trust Funds Drive Progress for Nature as part of the dissemination strategy for the jointly developed CTF white paper. With 64 participants from around the world, the session highlighted the critical role of Conservation Trust Funds (CTFs) in achieving biodiversity goals, sustaining protected areas, and supporting communities, while also showcasing key findings from the report. To further technical collaboration, the CTF Community of Practice—comprising experts from all Enduring Earth partner organizations—convened six times during this period. This group continues to serve as a platform for advancing effective CTF design, operations, and long-term impact through shared goals and coordinated workstreams. The mandate of this group is limited to representing and liaising with PFP deal teams. Finally, a South-South Exchange between Costa Rica and Gabon brought together PFP practitioners, CTFs, government representatives, and local leaders to share implementation experiences and strengthen collaboration. Additional exchanges included a visit by Bhutan for Life to Mongolia, marking the first cross-learning effort between the two Asian PFPs, and a May visit by the Mongolia CTF to Canada, hosted by Coast Funds, which provided insights into Indigenous-led governance and operational models. The Knowledge Management Community of Practice met regularly to align tools and strategies across partners, with 2025 priorities including onboarding materials, updating the EE contact base, expanding the PFP Knowledge Library, and addressing knowledge gaps. Enduring Earth also delivered two high-impact learning events. In February, a workshop on how Sustainable Tourism figures in PFPs brought together participants from seven countries to explore tourism as a conservation finance tool, featuring global case studies and interactive sessions that generated actionable insights. In July, just after the reporting period, the Mid-Year Townhall convened 69 participants and featured reflections from Jen Morris and a practitioner panel with representatives from the Great Bear Sea, SINAA Qikiqtani, and WWF Peru, focusing on adaptive problem-solving and implementation insights. Building on foundational work from Year 1, Enduring Earth also finalized the launch of a consultancy to identify scalable and replicable sustainable finance mechanisms (SFMs) for the PFP model. The contract was signed on July 9, with a kick-off meeting scheduled immediately after the reporting period. This consultancy, scoped during Q1 and Q2, will deliver a baseline report on market-based and blended finance solutions relevant to PFPs, convene innovation focus groups with global thought leaders such as the GEF, World Bank, BIOFIN, and NatureVest, and develop two prototype finance solution roadmaps tailored to Enduring Earth’s portfolio geographies. These efforts are expected to enhance financial durability strategies across the PFP portfolio. Finally, development of a Monitoring & Evaluation (M&E) system progressed steadily. In January, the MEL Working Group began defining key questions and use cases, including how to measure ecological outcomes and assess costing and capacity needs. Consultants are currently supporting the migration and organization of the Enduring Earth file library, and Terms of Reference for a dedicated M&E consultancy are being finalized, with recruitment planned for Q3. A second MEL Working Group meeting is scheduled for the week of July 14 to continue system design and partner consultations. Outcome 3.1: Effective project knowledge management and M&E contributes to efficient decision making and adaptive project management This reporting period focused on reinforcing the project’s monitoring systems established in Year 1, including the quarterly meetings with M&E focal points with each Executing Agency. These meetings enhanced clarity on Year 2 indicators and confirmed the deployment of monitoring tools—such as the Grievance Log and the Closing Condition Checklist. It also ensured timely adaptations to the Results Framework on key indicators such as the carbon and direct beneficiary indicators. The second priority was responding to Executing Agency requests for M&E technical support. In Gabon, this included oversight of the METT baseline consultancy, leadership in developing the PFP M&E framework, support in recruiting FPBG’s M&E Officer, and providing technical guidance for FPBG’s organizational M&E framework. These efforts aim to ensure critical systems and governance structures are in place ahead of the Single Close. There were no requests from other executing agencies. On Safeguards Gabon The Environmental and Social Management System (ESMS) for the Fund for the Preservation of Biodiversity in Gabon (FPBG) was developed in Q1 2025 through a consultancy with oversight from the TNC safeguards specialist. The design was reviewed by the GEF Agency and WWF Safeguards teams prior to the FPBG board review and approval in April 2025. A tailored training on the ESMS was provided to FPBG and relevant staff from the TNC Gabon PFP team in May, including a comprehensive introduction to the FPBG grant-making cycle and the foundational purpose of the ESMS. It covered how the ESMS aligns with International Finance Corporation (IFC) Social and Environmental Standards, including risk categorization, safeguards, and stakeholder responsibilities throughout project implementation. Participants practiced using tools such as screening checklists, the E&S management measures table, and learned how to navigate the Complaints Mechanism to ensure accountability and transparency. Following the review of the ESMS, and in anticipation PFP implementation, the Global PMU facilitated a series of discussions with the GEF Agency to ensure FPBG’s safeguards management and governance structure aligns with GEF requirements. These discussions have focused on staffing and the delineation of roles and responsibilities across the safeguards functions of the Agency, the Global PMU, and FPBG. In addition to the internal orientation outlined in section D, the TNC Gabon’s Community Engagement and Social Inclusion Officer plans to provide safeguards training to ANPN (National Park Agency) ahead of their socio-economic survey. The training, planned for July 22, 2025, will focus on the following points: - Social safeguards policies in GEF-funded conservation projects - General introduction Human rights and safeguards - including key aspects of the ESMF - Human rights and social framework (WWF/GEF and CNT commitments, legal framework in Gabon, etc.) - Overview of the project and its main environmental and social risks (based on the GEF 7 Environmental Safeguard screening tool) - Mapping of the villages/stakeholders that will be involved in the project and their main environmental and social sensitivities - Protocols/rules of engagement during field investigations (e.g. how to organise meetings and approach stakeholders, how to facilitate meetings, how to conduct interviews in a culturally appropriate way, how to ensure inclusive and meaningful engagement, etc.). - Gender and disadvantaged groups - how to ensure their inclusion and representation (e.g. interviewing women in separate groups from men where necessary, ensuring the inclusion of older people and young people, etc.). - Grievances - how villages/stakeholders can practically lodge complaints. Namibia WWF Namibia is planning on designing a section on Environment and Social Safeguards and Grievance Redress Mechanism within the Implementation Manual, which is the addendum to CCFN’s original operations manual to meet PFP standards and requirements. The design on the safeguards section has not started yet. The implementation Manual is expected at the end of September. WWF-Namibia team will engage the Safeguards Specialist at the WWF GEF Agency during the design of the section.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

Gabon Two key workshops were held in October and December 2024, where PFP technical groups representatives of 15 government administrations and 15 NGOs attended. Both workshops were attended by the same participants which are listed in Annex 7. Workshop Reports. To ensure a coherent and agreeable PFP design, TNC Gabon facilitated the continuous engagement of all technical members by having the workshops convened by the Prime Minister's office. Based on the results of the stakeholder and power mapping conducted in 2024, workshops were organized with the ministries of Water and Forests (DGFAP, DGEA), Environment (DGPEN, etc.), Fisheries (DGPA), Land Use Planning, Tourism, and Agriculture as these were the administrations with the most influence in legislation, regulation and policy, for the PFP planning and design of the logical framework. A total of 144 government and NGO stakeholders participated in the workshop with approximately 50% of participants being female. Under the CCGL (Local Management Advisory Committee) renewal initiatives (contracted to WWF-Gabon), significant progress has been made across seven Protected Areas. Seven stakeholder engagement missions successfully sensitized over 1,300 individuals—spanning local communities, administrative authorities, NGOs, and economic operators—on the revised CCGL governance instruments, such as charters and rules of procedure, and CCGL’s roles. These were complemented by five missions to formally renew village committees and stakeholder representatives through General Assemblies. Namibia In 2024, a three-day online workshop was held, attended by over 100 PFP stakeholders (69 female and 63 male), including representatives from government, NGOs, and communities. The workshop aimed to conduct an end-to-end review of the PFP design, scope, and purpose, and to solicit input, particularly on the Conservation Plan, Extension Services, and the Socioeconomic Development Fund (SEDF). Key Areas of Success included general alignment and support for the PFP from stakeholders, as well as strong political willingness to support the PFP, especially from the incoming administration. Challenges remain around agreeing on the exact scope of work and cost of the Extension Services plan, which caused some activities to be delayed and required challenging conversations with stakeholders. In 2025, all stakeholder engagement grants to local NGOs were extended to continue strengthening their involvement in facilitating the participation of conservancies during the N4L development process. An overall stakeholders online meeting, involving representatives from conservancies, government, NGOs, private sector and other in-country development partners (KfW), was organised in April to share N4L status update, including PFP governance, and announcing the appointment of CCFN as the Fund Manager. ETP Region Key workshops, of which some were co-financed, were held on the Durable Finance Mechanism with the CMAR Secretariat. Notable engagements included: Durable finance workshops were convened in Santa Cruz, Ecuador (September 2024) and Cali, Colombia (October 2024). Other notable workshops included a session with PACIFICO, the regional Conservation Trust Fund (CTF), on October 5, 2024, to address regional conservation challenges, CMAR, and governance structures; the virtual CMAR Project Steering Committee meeting (11 February); a March 2024 workshop reviewing the 10-year CMAR Action Plan with participation from Pew; and inter-ministerial treaty consultations held on 21 March that was facilitated by the legal team engaged by Pew with GEF funding. Technical and ministerial committee sessions took place in Panama (April 2025) and at the UN Ocean Conference in Nice, France (June 2025), alongside additional CMAR-led workshops focused on strengthening governance structures and sustainable financing strategies. The Connect to Protect Donor Coalition, of which Pew is a member met several times virtually over the past six months and in person in Nice, France at the UN Ocean Conference. The Coalition is a collaborative initiative bringing together philanthropic organizations, government agencies, and non-governmental organizations to mobilize technical and financial support for marine conservation and strengthening governance in the ETP. The Coalition works in alignment with the priorities of CMAR governments and fosters coordination among donors to ensure complementarity and strategic impact. EE Hub Stakeholder engagement is foundational to achieving component 2.2. The Enduring Earth (EE) Hub achieved significant success in bringing together diverse groups relevant to PFPs, including CTF CEOs, Indigenous leaders, government representatives, and donors, to foster collaboration and strengthen partnerships. In the first year, the focus was on establishing networks and open working relationships based on trust to develop an enabling environment for knowledge exchange among the PFP community. EE held a steering committee meeting on 18th December to review and approve the 2025 AWPB. Efforts were made to ensure the active participation of indigenous voices in panels and speaking engagements. Similarly, gender and social inclusion were evident in initiatives like the Women in Conservation Finance Roundtable, which highlighted women’s leadership. The Enduring Earth Annual Meeting was an opportunity to bring together partners who are designing, planning, and implementing PFPs in-country. Participatory methodologies and targeted outreach strategies ensured that engagement was inclusive, impactful, and aligned with project objectives.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

The Gender Analysis and Action Plan were approved as part of the CEO Endorsement package on November 1, 2023. During Project Year 1, the project Gender Action Plan, initially developed during the ProDoc design phase, was reviewed and revised to align with changes in the project design. The updated Gender Action Plan (Annex 4. Revised Gender Action Plan) now features more accurate actions, with clear timelines and indicators, improving upon the previous version. The Executing Agencies reviewed and revised the plan for Gabon, Namibia at the end of 2024. - One limitation of the revision for Gabon and Namibia is that accurate gender actions could only be established for Year 2 during the PFP Planning phase, where the Executing Agencies are engaged. Gender actions relevant to the PFP Implementation phase must be designed and confirmed by the CTFs post-close. The Global PMU will initiate discussions as soon as the CTFs are onboarded, and a working relationship is formed. - Furthermore, during the Adaptive Management workshops, all executing agencies agreed that, as they are phasing out in Year 2 post-close, gender training needs to be provided to the CTF staff. Once the CTFs are in place, the global PMU will consult the CTFs on the training needs and coordinate with the GEF Agency gender specialist as necessary. - A detailed theory of change for the project has been reconstructed based on the activities outlined in the ProDoc. The TOC integrates GAP indicators to the M&E Plan which will help executing agencies and the global PMU to keep track of the gender mainstreaming of the activities. Gabon During this reporting period, TNC Gabon’s Community Engagement and Social Inclusion Officer provided gender guidelines to the Gabon PFP team ahead of field missions to Mont de Cristal and Loango parks. These guidelines were designed to ensure inclusive, respectful, and equitable engagement with local communities. Key principles included avoiding the reinforcement of existing inequalities, consulting local authorities before field activities, and adopting a gender-sensitive approach that respects local customs and uses accessible language. The team was also advised to hold separate meetings when necessary to encourage participation from women and youth, ensure diverse representation in consultations and visual materials, and disaggregate socio-economic data by gender and age. These measures aim to ensure that project benefits are equitably distributed among men, women, youth, and marginalized groups, reinforcing the project's commitment to social inclusion and community empowerment. Overall, the meetings in Mont de Cristal and Loango were inclusive, bringing together men, women, young people, the elderly and people with disabilities. Over 42% of the participants were women. National Park; Towns/villages; Men; Women; Total. Loango; Bonne Terre, Ntchongorove; 22; 13; 35. Crystal Mountains; Andock Foula; 8; 9; 17. Total; 30; 22; 52. Furthermore, key PFP design documents are in development with gender-mainstreaming in sight as per the Gender Action Plan. The Conservation and Community Plan will feature a dedicated gender section outlining gender-specific and gender-sensitive implementation strategies across all PFP objectives. Drafting of the narrative section is underway. In parallel, development of the PFP Operations Manual is being guided by a commitment to gender mainstreaming across all operational components, with both documents scheduled for completion in Q3 ahead of negotiations. In Year 1, gender was prioritized in the staffing of the CTF (FPBG) by ensuring that gender considerations were made for the CEO's hire and mainstreamed in the staffing plan. As a result, out of the total four staff, two are female, including the CEO and the general manager of business and finance. Once the full CTF staff is hired, a training plan will be implemented, which will include gender training to further support gender inclusivity. Namibia All gender actions due in Year 2 were integrated in Namibia’s AWPB. For Activity 1.1.1.10 regarding ensuring that the CTF, CCFN, is trained on gender and social inclusion – the onboarding plan that is currently under development, will include an orientation of the Gender Action Plan and conducting Gender Analysis. For Activity 1.1.1.6, which focuses on gender mainstreaming within the Operations Manual, no work has commenced. The WWF Namibia PFP team has committed to directly engage the WWF GEF Agency’s Gender Specialist to support the design of the relevant sections and will continue to keep the Global Project Management Unit informed throughout the process. ETP Region The work undertaken in the past six months did not include gender assessments as it pertains to the development of a durable finance mechanism. In the work that will be undertaken by Posaidon on sustainable finance, gender inclusivity will be part of the assessments to determine the profile of marine users as well as how funding may be accessed by different user groups. The legal assessment that was completed for the treaty did include some review of laws that are relevant to natural resource access and rights. These are being considered in the development of the treaty. In the work undertaken during this reporting period, Pew worked to ensure gender representation among stakeholders and within key governance structures, to the extent possible. During the CTF assessments completed during this reporting period, gender representation was reviewed to determine representation on the governance structure, staff, and beneficiaries. Pew monitors gender representation in all workshops and stakeholder engagements organized by Pew. By tracking sex-disaggregated participation, Pew aims to ensure gender inclusion. Additionally, Pew is intentional about maintaining gender balance in the hiring of consultants. For example, the team of attorneys hired to support the countries in developing a treaty are majority female, and the new technical lead for Pew for the ETP is female. In Year 1, the gender action plan for ETP included ensuring gender representation among stakeholders and within key governance structures. Pew accomplished this by encouraging good gender representation (over 50% female) in key bodies such as the CMAR Secretariat and Technical Committee. The permanent CMAR Secretariat established this year consists of one male and two female staff, while the CMAR Technical Committee has an equal representation of four female and four male members. Key stakeholders, such as PACIFICO and the Conservation Trust Funds in the region, have leadership predominantly composed of females. Furthermore, gender representation is monitored in all workshops and stakeholder engagements organized by Pew, using the Stakeholder Engagement Tracker (Annual PPR Annex 10). By tracking sex-disaggregated participation, Pew aims to ensure gender inclusion. Additionally, Pew is intentional about maintaining gender balance in the hiring of consultants. In Year 1, Pew hired four male and five female consultants across all contracts to ensure that the efforts supporting a strengthened and durably funded CMAR are gender inclusive.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

EE Project Communications Strategy The project has developed a comprehensive communication strategy in collaboration with the EE Hub. This strategy outlines key messaging, target audiences, communication channels, and timelines to effectively disseminate project outcomes and engage stakeholders. It has undergone thorough review by the GEF Agency to ensure alignment with broader programmatic goals and standards. Most of the planned communication activities are scheduled for implementation in Quarter 4 (Q4/2025) during FPBG and CCFN inception meetings. Efforts will be made to ensure that the communication strategy is closely aligned with the knowledge management initiatives led by the EE Hub. This includes harmonizing messaging, coordinating timelines, and leveraging shared platforms to maximize visibility and impact. The goal is to create a cohesive narrative that supports both communication and knowledge-sharing objectives across the project. List knowledge activities/products (including links) developed during the reporting period: - Official Project Webpage The GEF project webpage was launched on October 16th, after receiving the necessary approval from the EE partners. The webpage acts as a comprehensive central hub for all project-related information. The webpage can be accessed here: https://www.nature.org/en-us/what-we-do/our-priorities/protect-water-and-land//gef-enduring-earth/ - Year 1 Lessons Learnt Brief : https://www.nature.org/en-us/what-we-do/our-priorities/protect-water-and-land/gef-enduring-earth/ As a key milestone in Year 1 knowledge management, the Global PMU developed a Lessons Learned Brief synthesizing insights across the Adaptive Management with EAs. The brief identifies two recurring implementation challenges—responding to complex political dynamics and designing operational frameworks for multi-stakeholder settings—and showcases actionable responses and peer-informed practices to address them. By capturing these experiences early in the PFP lifecycle, the brief strengthens institutional learning and promotes cross-country exchange. It also reinforces the project's commitment to embedding adaptive learning and strategic knowledge dissemination at the core of Enduring Earth’s implementation approach. The brief has been disseminated to the GEF Agency, all Executing Agencies and their PFP teams, and the Enduring Earth Hub for circulation during relevant knowledge management events. - ETP Bezos Earth Fund (co-finance) news on ETP https://www.bezosearthfund.org/news-and-insights/connect-to-protect-coalition-surpasses-original-pledge-triples-marine-protected-areas-eastern-tropical-pacific Remarkable progress has been made in protecting the globally significant Eastern Tropical Pacific Marine Corridor (CMAR), thanks to the unified efforts of governments, NGOs, and funders. The Pew Charitable Trusts, through the Enduring Earth collaboration, is committed to ensuring this progress leads to sustained impact for both people and nature and will continue collaborating with the four CMAR countries to develop a durable finance mechanism." – Fred Boltz, Head of Programming, Global Environment Facility - News coverage on CMAR Presidency Inauguration https://cocosisland.org/en/cmar-pro-tempore-presidency-panama-to-colombia/ Panama City, April 25, 2025. In an official ceremony held at the Ministry of Foreign Affairs of Panama, the Minister of Environment of Colombia assumed the Presidency of the CMAR, taking over from the Minister of Environment of Panama. - Enduring Earth Gabon-Cost Rica Learning Exchange Trip https://enduringearth.org/south-south-conservation-knowledge-exchange/ https://fpbg.org/le-pfp-au-gabon-ce-que-la-visite-au-costa-rica-nous-enseigne/ In April 2025, Enduring Earth facilitated a high-impact South-South Knowledge Exchange between conservation leaders from Costa Rica and Gabon. Hosted by Costa Rica’s Herencia team, the exchange brought together over 40 participants—including government officials, Indigenous leaders, CTF representatives, and implementing partners—from both countries. The week-long visit enabled rich peers to learn on topics such as Conservation Trust Fund governance, legal frameworks, community engagement, and long-term financing strategies. This exchange not only deepened bilateral relationships but also strengthened alignment on key aspects of PFP implementation. Participants emphasized the value of practical, candid conversations and site visits in understanding how different national contexts address shared challenges. The event reinforced the importance of South-South collaboration in scaling durable conservation and demonstrated Enduring Earth's commitment to inclusive, practitioner-led learning across its portfolio. - 5: EE Hub webinars •CTF Webinar: How Conservation Trust Funds Drive Progress for Nature – Co-hosted with RedLAC, CAFÉ, and GEF to share findings from the CTF White Paper (64 participants) (link below). •CTF Community of Practice: Monthly meetings (6 held in 2025 to date) involving technical experts from all EE partners to strengthen CTF design, operations, and peer learning. •South-South Exchange: Costa Rica–Gabon: Peer learning visit hosted, with participants from both countries engaging on CTF governance, legal frameworks, and community engagement. https://enduringearth.org/south-south-conservation-knowledge-exchange/ •Asia Regional Exchange: Exchange between Bhutan for Life and Mongolia PFP to share early implementation lessons and explore collaboration as Asia’s two PFPs. •Mongolia–Canada Technical Exchange: Learning visit by Mongolia’s CTF to Coast Funds to observe Indigenous-led governance systems and operational best practices. •Knowledge Management Community of Practice: Regular coordination space for KM leads from all partner organizations, focused on onboarding tools, KM alignment, and Toolkit adoption. Sustainable Tourism in PFPs Workshop: Learning session with global case studies and breakout groups; identified tourism investment needs and enabling conditions for conservation finance • Publications: Supported the launch of a white paper in collaboration with the Global Environment Facility and Conservation Trust Funds (CTFs), highlighting CTF contributions to conservation and offering scalable solutions for global challenges: https://www.thegef.org/newsroom/publications/how-conservation-trust-funds-are-driving-progress-nature • Communities of Practice: Established working groups on Monitoring, Evaluation, and Learning (MEL), Conservation Trust Funds, and Sustainable Finance at the Enduring Earth Annual Meeting, creating ongoing forums for knowledge sharing. These groups met 2-4 times during the year.

### Reflows (for NGIs only)

Note: This field is not publicly disclosed.

Please attach the actual reflow (both cumulative, and reflow in the current year), the potential reflows, and other relevant information, including the quarterly investor reports and/or presentations materials the Executing Agencies provide to GEF Agencies. Select the disclosure level based on each document’s confidentiality. Please provide an explanation for any deviations between projected and actual reflows, along with any updates to reflow projections. Include any relevant changes to the project, events, or notifications received from Executing Agencies that may adversely affect future reflows

### Adaptive Management

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☒ Results framework; Revision of Outcome Indicators (statements and definitions) for outcomes : 1.1.2, 1.2.2, 1.31, 1.3.2, 1.3.3, 1.4.1, 2.1.1, 2.2.1, 3.1.1, 3.1.2, 3.1.3. Revised targets for : Core indicator 1.1.: Revised project lifecycle target from 1,861,437 ha to 3,856,770 ha CI 1.2: Revised target from 6,115,713 to 3,169,394 C.I 2.2: Year 3 targets removed. C.I 6.1 : Year 2 targets removed. Revised targets: Gabon : 3.3 mil tCo2 eq to 43.9 mil. tCo2 eq. Namibia : 7.7 mil tCo2 eq to 137.4 mil tCo2 eq Core Indicator 11: Revised targets for Gabon : 60,000 to 16,728 Namibia : 250,000 to 2,.616; - Revised based on feedback received from GEF Agency Results Based Management Lead Specialist (June 2024). - Deleted duplicative indicators and those no longer relevant to the project implementation. - Ensured indicators are aligned with the outcome statements and measure the quality of long-term results rather than simply tracking project progress (output-type indicators). - Enhanced clarity and added indicator definitions. - Revised timeline and target according to changes made to the indicators. Earlier inclusion Ramsar sites (6,115,713 ha) in Gabon’s protected area coverage was corrected, as these sites are not yet legally designated under national law. As a result, the target for CI 1.2—currently protected terrestrial area under improved management effectiveness—was reduced, while the target for CI 1.1—newly protected terrestrial area—was revised upward (target calculation: 30% of Gabon’s terrestrial area – currently protected PA). For CI 1.2 and 2.2, baseline METT assessments will be completed in Year 2; the follow-up originally planned for Year 3 has been removed, with the next assessment scheduled for Year 6 to align with the start of PFP implementation (Year 3, post-close) and allow sufficient time for measurable improvements. Both Gabon and Namibia PFPs remain in planning phase, so Year 2 carbon benefit targets have been deleted. Gabon’s surface area target (CI 1.1.) was corrected in the ExAct Tool as per the above. Additionally, Year 3–5 targets removed as gazettement is expected only in Year 6. For Namibia, the deforestation rate was updated using a reliable, citable source, the Global Forest Watch, instead of the original informal source. Target was recalculated using GEF’s definition of “direct beneficiaries”—individuals who receive identifiable, tangible support and are aware they are benefiting. The original targets submitted in the ProDoc included individuals considered indirect beneficiaries under GEF guidance.; Dec 3rd, 2024 June 12, 2025. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. ☐Implementation schedule. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☒ Safeguards; Gabon/ Namibia - Specified activities to enhance clarity on the action, by whom and when - Removed actions that are no longer relevant to the PFP design - Added quantitative indicator for all actions to enable tracking by M&E ETP - Added quantitative indicators; The original GAPs were developed during the ProDoc phase. As the PFP designs are being finalized during the planning phase (project years 1 and 2), refinement of the GAP was needed to align to the changes in PFP implementation strategy. The GAPs for Gabon and Namibia implementation have been revised to better align with the PFP implementation plan.. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change.

### Geolocation Information

Please provide a location name, latitude and longitude for key locations of GEF-financed activities. Depending on the scope of the project, it may only be necessary to provide geolocation of the capital city. The format should be in Decimal Degrees WGS84 format only – e.g. not degrees, minutes or seconds. Please use ‘-‘ instead of ‘S’ and avoid inserting ‘°’). As an alternative, you may enter a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide for additional details. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). San Jose; 9.931477469020935; -84.09206412567556. Quito; -0.2222989158249721; -78.5102098503938. Panama City; 8.98237101072077; -79.49572976950365. Bogota; 4.709870536330519; -74.06182245378339. Windhoek, Namibia (86 conservancies); -22.55941 Shape files available here: https://tnc.box.com/s/u6srdu528ccnemgf3pqj1n3s8i1k1xey; 17.08323. Libreville, Gabon (PA system); 0.390100 Shape files available here: https://tnc.box.com/s/u6srdu528ccnemgf3pqj1n3s8i1k1xey; 9.454400.

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

Total GEF disbursement defined as amount of project budget spent by the Executing Agency, as a total from project start until June 30 of reporting FY.

The PFP teams in Namibia and Gabon are in the early stages of scoping a multi-country GCF project that would support PFPs in Gabon and Namibia, inter alia.