## GEFID 11066 (RG-Q0112)-2026-
GEF Annual Portfolio Monitoring Report 2026
Update on GEF Project Implementation (PIR)
Inter-American Development Bank [IDB Lab]
PIR # 2
|  | Reporting date (mm/dd/yyyy): | 2026-06-30
Project/Facility-level Information |  | GEF Focal Area(s): | Climate Change
GEF ID | 11066 |  | Land Degradation
Trustee ID |  |  | Climate Change
Facility/ Project Number | RG-Q0112 |  | Chemicals & Waste
Facility/ Project Name | Yield Lab Opportunity Fund I: Accelerating technology and local innovation for sustainable and decarbonized food systems in Latin America and the Caribbean
GEF Cycle | GEF-8 | GEF Operational Programs: | CCM-1-4, LD-1, CW-2. | as stated in approved CEO Endorsement document
Date of GEF Sec Clearance Letter (WP inclusion) | 2023-06-01
Date of GEF Council Approval (or CEO End./Approval, if applicable) | 2024-03-12 | GEF Project Type: | Full-sized Project | choose from dropdown menu
Date of GEF Trustee Commitment Letter | 2024-03-18
Facility/ Project Approval Date by IDBG (mm/dd/yyyy) | 2024-03-28 | Additional GEF Agencies (if applicable): | Not applicable
Actual Implementation Start Date | 2024-05-30
Date of 1st Disbursement from Facility/ Program - GEF funds | 2024-10-10 | Partner Entities: | The Yield LAB LATAM GP LTD | (e.g. Fund manager, Sponsors, etc)
Date 1st Disbursement was registered on GEF Portal | 2024-11-22
Total GEF Amount approved - by GEF Council/ CEO | 6000000
Total GEF Amount disbursed to date (cumulative) | 3847310.11
GEF funds invested/ in negotiation (calculated from subprojects) | N/A
GEF funds undisbursed (calculated from subprojects) | 2152689.89
Total Co-financing proposed at approval - by GEF Sec | 27275000 | (copied from Co-financing table)
Co-financing committed to date (calculated from subprojects) | 39782828.28 | Matches co-financing table
Expected Reflow Amount at approval - GEF funds | 9800000 | (Capital & Earnings)
Investment-level Information
Sub-project/ IDB Contract Number | N/A
Sub-project/ IDB Contract Name | N/A
Country/ies where private sector is benefitted | The countries possibly involved in the portfolio are Argentina, Bolivia, Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Jamaica, Mexico, Panamá, Paraguay, Perú, and Uruguay
Status/ Stage (please select from dropdown menu) | Investment/ Commitment period terminated
Currency (USD, EUR etc) | USD
GEF Amount | 6000000
IDBG non-GEF Amount (if applicable) [*] | 4000000
Other Co-financing Amount (if applicable) [*] | 35782828.28
[*] Please fill out detailed co-financing table in evaluation section including all non-GEF amounts from all subprojects
Eligibility Date | 2024-10-08
IDBG Board Approval of subproject (mm/dd/yyyy) | 2024-03-28
Effectiveness date of subproject (mm/dd/yyyy) | 2024-05-30
Date of most recent disbursement - GEF funds (mm/dd/yyyy) | 2025-12-15
Amount of most recent disbursement - GEF funds | 789777.69 |  |  |  | Total disbursement as of June 30, 2026
Cumulative disbursement to date - GEF funds | 3847310.11 |  |  |  | 3847310.11
Reflow Amount Expected at Closure - GEF funds | 9800000
Actual Reflows to date - GEF funds (calculated from table below) | 0
Difference Actual vs. Expected Reflows (calculated) | 9800000
Remaining Expected Reflows | TBD
Reflow start date (mm/dd/yyyy) | 2027-01-01
Reflow end date (mm/dd/yyyy) | 2033-05-31
Reflow period (years) | 6
Comments:
Financing Product/ Instrument (pick from dropdown menu) | Equity
Depending on Instrument, please fill out relevant section:
Loan/Guarantee/Debt
Interest Rate (% per year)
Interest Payment Dates & Payment Interval
Equity Terms
Expected Amount of Total Equity to be Raised | Not extra funding expected for this Fund. The final closing was in 2025.
Probability of Loss (expected) | TBD, it is still very early to estimate
Exit Conditions | TBD
Expected Return Rate | TBD
Interim Return/Dividends | TBD
Principal and Interest Repayment Schedule - GEF funds
(Please update both "Actual/ Realized" and Expected Values; also, please indicate Expected values for the full amount of reflows expected until maturity/ end of divestment period)
Subproject/ Investment | Repayment Date (mm/dd/yyyy) | Amount | Reflow Category (Capital/ Principal or Earnings/ Interest) | Status (Expected or Actual/Realized)
Actual/ Realized (add rows as needed when applicable)
Subproject #
Expected (add rows as needed)
Subproject 1
Subproject 1
Subproject 1
Subproject 1
Reflows 2026
Please provide an explanation for any deviations between projected and actual reflows, along with any updates to reflow projections. Include any relevant changes to the project, events, or notifications received from Executing Agencies that may adversely affect future reflows. Note: This field is not publicly disclosed. | No changes about reflows projections at this point. A clearer projection will be developed at the beginning of the divestment phase.
Please indicate any reports and/or public documents—along with links—related to the Agencies’ blended finance projects that include a GEF-supported element. Note: This field is not publicly disclosed. | No external reports documents to share at this point related to reflows. Impact and financial information is recollected and analyzed during LPs meetings. If a specific detail about the financial information is needed please let us know.
Please include the actual reflow (both cumulative, and reflow in the current year), the potential reflows, and other relevant information, including the quarterly investor reports and/or presentations materials the Executing Agencies provide to GEF Agencies. When uploading these documents, please select the disclosure level based on each document’s confidentiality. Note: This field is not publicly disclosed. | No changes at this point from the stated at the CEO Endorsement document. A clearer projection could be developed at the beginning of the divestment phase.
Co-financing Table (See Request for CEO Endorsement document -Table C- as a reference)
Sources of Co-financing | Name of Co-Financier | Type of Co-financing | Amount Indicated at CEO Endorsement | Actual Amount to date
Opportunity Fund
Private Sector | Nestle Ventures | Investment mobilized - Equity Investment | 5000000 | 2500000
GEF Agency | IDB Lab | Investment mobilized - Equity Investment | 4000000 | 4000000
Private Sector | Innovali S.A (Grupo Bimbo) | Investment mobilized - Equity Investment | 3000000 | 3000000
Private Sector | Impact Latam Fund | Investment mobilized - Equity Investment | 3000000 | 3000000
Private Sector | Red Surcos S.A | Investment mobilized - Equity Investment | 1000000 | 1000000
Private Sector | SQM | Investment mobilized - Equity Investment | 1000000 | 1000000
Private Sector | Tondena LTD | Investment mobilized - Equity Investment | 1000000 | 1000000
Private Sector | Yield Lab Latam GP Commitment | Investment mobilized - Equity Investment | 500000 | 457828.28
Private Sector | Dos Leguas S.A | Investment mobilized - Equity Investment | 500000 | 500000
Private Sector | Llorente Hnos S.A | Investment mobilized - Equity Investment | 500000 | 500000
Private Sector | Tridon Participacoes LTDA | Investment mobilized - Equity Investment | 500000 | 500000
Private Sector | Platynum Ventures (Grupo Gloria) | Investment mobilized - Equity Investment | 500000 | 500000
Private Sector | Altuy SA | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Bernardo Llorente | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Bioetanol Rio Cuarto SA | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Guillermo WilliI | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Inversiones y Asesorías Vial Wood Ltda | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Kikel S.A | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Thad Simons | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Agropecuaria las Semillas SRL | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Industrias Rurales SRL | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Los Canticos S.A | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Marcelo Carrique | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Patricia Ines Ortiz de Urbina | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Santa Angelina S.A. | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Morning Coffee by the pool inc | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Post Scriptum Holding | Investment mobilized - Equity Investment | 250000 | 250000
Private Sector | Promotosa Social Mexico | Investment mobilized - Equity Investment | 0 | 500000
Private Sector | Atanacio Capaceta Castro | Investment mobilized - Equity Investment | 0 | 250000
Private Sector | Nesters Uruguay | Investment mobilized - Equity Investment | 0 | 300000
Private Sector | FUNDEA | Investment mobilized - Equity Investment | 0 | 4000000
Private Sector | FOCIR | Investment mobilized - Equity Investment | 0 | 4000000
Private Sector | Garces VC SA | Investment mobilized - Equity Investment | 0 | 3000000
Private Sector | iAlumbra | Investment mobilized - Equity Investment | 0 | 3000000
YLL E ATG Collaborative
Private Sector | SD&G Administração e Participações Ltda | Investment mobilized - Equity Investment | 200000 | 200000
Private Sector | EGGS & CO. Holding de Participacoes Ltda. | Investment mobilized - Equity Investment | 200000 | 200000
Private Sector | Carlos Ernesto Agustin (Petrovina) | Investment mobilized - Equity Investment | 200000 | 200000
Private Sector | UBY Agroquimica S.A. | Investment mobilized - Equity Investment | 200000 | 200000
Private Sector | Alex Sandro Rodrigues Scandian | Investment mobilized - Equity Investment | 100000 | 100000
Private Sector | Antonio Paulo Magalhães | Investment mobilized - Equity Investment | 100000 | 100000
Private Sector | Mathias Zanforlin Soares | Investment mobilized - Equity Investment | 100000 | 100000
Private Sector | Luiz Antonio Ribeiro Venturi Caldas | Investment mobilized - Equity Investment | 100000 | 100000
Private Sector | Joao Leopoldo Samways Filho | Investment mobilized - Equity Investment | 100000 | 100000
Fideicomiso The Yield Lab Latam Acelerador
Private Sector | Adrian Radnic | Investment mobilized - Equity Investment | 150000 | 150000
Private Sector | Agrolam S.A | Investment mobilized - Equity Investment | 150000 | 150000
Private Sector | La Victoria S. A | Investment mobilized - Equity Investment | 150000 | 150000
Private Sector | Don Osvaldo S.A | Investment mobilized - Equity Investment | 150000 | 150000
Private Sector | Ricardo Negri | Investment mobilized - Equity Investment | 125000 | 125000
Private Sector | Galicia | Investment mobilized - Equity Investment | 1000000 | 1000000
|  | TOTAL (automatic): | 27275000 | 39782828.28
Modifications to Co-financing (planned at CEO Endorsement vs. during implementation):
Please indicate and briefly explain all changes in (anticipated) amounts, sources, names, and type of co-financing, compared to the co-financing indicated at CEO Endorsement; please add information without deleting text from previous reporting periods. | No additional funding since last year PIR. Not extra funding expected for this Fund. The final closing was in 2025.
Performance & Evaluation of Facility/ Program
# of last PIR submitted (Date submitted) | PIR 1 submitted on 9/15/2025 | if less than 12 mth in implementation, please put "no PIR submitted yet"
Facility/ Project Approval Date - by IDBG (automatic) | 2024-03-28
Expected Mid-Term Evaluation/ Review Submission Date | 2028-12-01
Actual Mid-Term Evaluation/ Review (MTR) Submission Date | TBD | Main Findings of MTR: | TBD
(date once finalized)
Expected Date of Completion (last financial transaction) | 2034-06-01
Actual Date of Completion (last financial transaction) | TBD
Expected Terminal Evaluation Submission Date | 2035-06-01
Actual Terminal Evaluation (TER) Submission Date | TBD | Main Findings of TER: | TBD
Expected Date of Financial Closure of Facility (Audited) | 2034-12-01 | (date once finalized)
Actual Date of Financial Closure of Facility (Audited) | TBD
| Current FY PIR's ratings (use dropdown menu if applicable): | FY 25 PIR ratings for reference
Development Objective Rating: | Satisfactory [S] | Satisfactory [S]
Implementation Progress Rating: | Satisfactory [S] | Satisfactory [S]
Risk Rating: | Modest Risk (M) | Modest Risk (M)
Additional Details on Above Ratings:
Please provide information on implementation of project activities (free text), including: A) Progress and achievements by component (outcomes and outputs) from July 1, 2025 until June 30, 2026., as well as | The Fund has built a diversified portfolio of 25 companies across Latin America, deploying over USD 20 million since inception. During the years 2025-2026, the Fund continued investing in new companies while placing a strong emphasis on follow-on rounds, including several recapitalizations and valuation adjustments that reflect broader venture capital market conditions in 2025. As expected, portfolio performance has been mixed, with some companies demonstrating strong growth, others maintaining stable operations, and a first write-off, reflecting the expected dynamics of an early-stage venture portfolio in the current environment. From an impact perspective, the portfolio is reaching approximately 150k farmers across the region, with an estimated 40k adopting climate resilience solutions and 50k adopting productivity-enhancing technologies. Looking ahead, as the Fund approaches the final stage of its investment period (through May 2027), it expects to complete a limited number of new investments (up to three companies) while prioritizing follow-on capital. The focus will be on supporting portfolio growth and actively building exit roadmaps to drive value realization.
B) Challenges during implementation. | No specific challenges to be reported at this stage. As expected, portfolio performance has been mixed, with some companies demonstrating strong growth, others maintaining stable operations, and a first write-off, reflecting the expected dynamics of an early-stage venture portfolio in the current environment.
Update on Stakeholder Engagement:
(Information on Progress, challenges and outcomes; make reference to corresponding sections, annexes and/or action plans included or referred to in CEO Endorsement/Approval document, if applicable) | The Yield Lab LATAM continued engaging a broad range of stakeholders, including startups, producers, investors, corporations, research institutions, government entities, and development partners. Activities included for example the Agri Innovation Roundtables in Colombia and Uruguay, the Northern Triangle Tour in Central America, the Global Cattle Innovation Platform, and ecosystem-building initiatives in Costa Rica. These efforts connected stakeholders around field-level challenges, technology adoption, startup scalability, investment, and food-system resilience. Several engagements moved beyond networking and dialogue toward concrete action, including innovation pilots in Colombia and an acceleration program supporting ten Costa Rican AgriTech startups in collaboration with PROCOMER, Fundación CRUSA, INA, and IICA.. Notably, the AgroInnova program provided mentoring support to 60 startups from the Northern Triangle, while regional tours and ecosystem events brought together startups, corporates, government institutions, and innovation enablers around shared agricultural and climate challenges. These activities contribute directly to the project's objective of accelerating technology deployment and local innovation for sustainable food systems.Also, are helping connect Latin American innovators with international investors, technical expertise, and market opportunities. While challenges remain in translating innovation into scalable commercial adoption across diverse markets, the growing number of partnerships, pilots, mentorship programs, and cross-border collaborations demonstrates increasing ecosystem maturity and stronger foundations for long-term impact. Examples of these actions can be seen in the following websites: https://www.linkedin.com/company/theyieldlablatam/posts/?feedView=all
Update on Gender-Responsiveness:
(Information on Progress, challenges and outcomes; make reference to corresponding sections, annexes and/or action plans included or referred to in CEO Endorsement/Approval document, if applicable) | Yield Lab LATAM continued efforts to strengthen women’s visibility and leadership within the investment and AgriFoodTech ecosystem. Four Yield Lab team members were recognized in LAVCA’s Women Investors lists, including two as Top Women Investors and two as Emerging Women Investors. During the last year, women members of the team also represented Yield Lab in investment panels, climate-finance discussions, internationalization sessions, and ecosystem initiatives across the region. Gender inclusion remains strong, with approximately one-third of portfolio companies having at least one woman in a founder or C-level role. Yield Lab continues to support gender as a core element in its thesis and actions.
Update on Knowledge Management:
(Information on Progress, challenges and outcomes; make reference to corresponding sections, annexes and/or action plans included or referred to in CEO Endorsement/Approval document, if applicable) | Knowledge development remained an important part of Yield Lab’s activities. The organization convened panels, webinars, roundtables, strategic gatherings, and knowledge-exchange missions on topics such as artificial intelligence in agriculture, digital finance for smallholders, regenerative agriculture, ESG management, climate finance, water stewardship, and technology adoption. It also disseminated market analyses and portfolio case studies, including the “Fintechs Weekly Stories” series and a quarterly analysis of Latin American food and agriculture markets. These activities helped translate practical experiences from founders, producers, investors, and corporations into insights that can support investment decisions and wider technology adoption. Examples of these actions can be seen in the following websites: https://www.linkedin.com/company/theyieldlablatam/posts/?feedView=all
Sustainability & Innovation:
(Please comment on quantitative and/or qualitative results that the sub-projects are achieving in relation to sustainability or innovation - these may include results from the Results Matrix or the GEF's GEB, or may be unexpected results observed during implementation). | Yield Lab continued supporting technologies and financial models intended to strengthen the sustainability, efficiency, and resilience of agrifood systems. Reported examples include AI-enabled agricultural decision-making, geospatial and satellite-based farm intelligence, water-management solutions, biological inputs, socio-environmental traceability, wildfire prevention, rural finance, and ESG management systems. The Fund activities show an approach that combines technology, finance, field adoption, and impact measurement to advance more sustainable food systems. In the last year, the Fund continued to advance its development outcomes by expanding access to agtech solutions for micro, small and medium-sized producers across Latin America. The portfolio is reaching approximately 150k farmers, with an estimated 40k adopting climate resilience solutions and 50k adopting productivity-enhancing technologies, contributing to improved efficiency and sustainability. Gender inclusion remains strong, with approximately one-third of portfolio companies having at least one woman in a founder or C-level role. Progress across indicators reflects a more efficiency-driven environment, where some companies have scaled while others have stabilized or adjusted to market conditions. As a result, certain indicators such as job creation or revenue growth have progressed more moderately than initially expected. Nevertheless, this has led to more resilient business models, supporting the Fund’s ability to achieve its long-term development objectives. Results and the built portfolio so far demonstrate increasing adoption of sustainability-focused technologies and stronger innovation ecosystems. Examples include deployment of nanobubble technology in Mexico to improve water-use efficiency for crops such as maize and alfalfa, implementation of innovation pilots with corporate partners in Colombia, and growing integration of artificial intelligence solutions designed to improve farm productivity while generating measurable environmental and financial value. Portfolio companies are also achieving significant commercial growth and market validation, suggesting that climate-smart and resource-efficient technologies are increasingly attracting customers, investors, and strategic partners. Together, these results indicate meaningful progress toward more sustainable, resilient, and technology-enabled food systems while strengthening the innovation pipeline needed to generate longer-term global environmental benefits.
Insights and Lessons Learned from Implementation:
(Please comment on Successes and Challenges, providing a short summary of insights/lesson learned in a way that it is understandable to someone unfamiliar with the project.) | The activities reported by Yield Lab reinforce that capital alone is insufficient to scale agricultural innovation. Startups also require active governance, mentoring, corporate connections, field validation, market access, and trusted relationships with producers to scale up and grow. Yield Lab experience so far highlights that successful technology adoption depends on clear operational use cases, reliable data and infrastructure, intuitive solutions, measurable returns, and alignment with producers’ actual needs. Cross-border partnerships and practical “support rails” are also important for moving innovations from research or pilot stages into commercial and field-level application.
Results - Contribution to GEF's Core Indicators/ Global Environmental Benefits (GEBs):
GEF Indicators to which Program will contribute | Unit of Measure | Target - CEO Endorsement/Approval doc | Actual Results achieved at MTR | Source/ Verification means for Actual Results at MTR | Actual Results achieved at TER | Source/ Verification means for Actual Results at TER
Indicator 1. Startups financed, aligning with the investment thesis. | # | 20 | TBD | TBD | TBD | TBD
Indicator 2. Knowledge products developed by YLL per year (acceleration programs, innovation challenges, roundtables, whitepapers, events, growth programs, etc.) | # | 20 | TBD | TBD | TBD | TBD
Indicator 3. Chemicals of global concern and their waste reduced, disposed of/destroyed, phased out, avoided or eliminated from the environment, and in process, materials, and products | Metric tons | 15680 | TBD | TBD | TBD | TBD
Indicator 4. Land under better sustainable practices. | hectares | 11550000 | TBD | TBD | TBD | TBD
Indicator 5. people benefiting directly from the proje | # | 200000 | TBD | TBD | TBD | TBD
Indicator 6. emissions avoided and mitigated | Metric tons of CO2eq. | 29732240 | TBD | TBD | TBD | TBD
At Mid-term & Terminal Evalution stage for projects approved during or after the GEF-6 cycle, in addition to the information provided here, please submit the completed Core Indicator Worksheet. |  |  | Link to Core Indicator Worksheet template
Project Geo Location Information | Location Name | City HQ | Country HQ | Latitude | Longitude | GeoNames ID
Please include the Location Name, Latitude and Longitude as required fields. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. These IDs are available on the GeoNames’ geographical database containing millions of placenames and allowing to freely record new ones. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format (e.g., for Washington DC, Latitude 38.89511 and Longitude -77.03637) and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com | Ucrops | Tigre | Argentina | -34.4258 | -34.4258 | 3427761
| Kilimo | Córdoba | Argentina | -31.4064 | -64.1883 | 3860259
| The Climate Box | Montevideo | Uruguay | -34.9031 | -56.1881 | 3441575
| EIWA | Buenos Aires | Argentina | -34.6178 | -58.4772 | 3435910
| Solena | Ciudad de México | Mexico | 19.4283 | -99.1275 | 3527646
| Sioma | Apartadó | Colombia | 7.8828 | -76.6258 | 9172037
| Agroforte | São Paulo | Brazil | -23.5475 | -46.6361 | 3448439
| Auravant | Buenos Aires | Argentina | -34.6178 | -58.4772 | 3435910
| Symbiomics | Florianópolis | Brazil | -27.5967 | -48.5492 | 3463237
| Agree | Buenos Aires | Argentina | -34.6178 | -58.4772 | 3435910
| Circular | Buenos Aires | Argentina | -34.6178 | -58.4772 | 3435910
| Seedz | Belo Horizonte | Brazil | -19.9208 | -43.9378 | 3470127
| UmGraumeio (UGM) | Jundiaí | Brazil | -23.1864 | -46.8853
| GoFlux | São Paulo | Brazil | -23.5475 | -46.6361 | 3448439
| Beeflow | Los Ángeles | Argentina | -28.4864 | -65.9519
| Courageous Land | São Paulo | Brazil | -23.5475 | -46.6361 | 3448439
| Kigui | Ciudad de México | Mexico | 19.4283 | -99.1275 | 3527646
| Phage Lab | Santiago | Chile | -33.4569 | -70.6483 | 3871336
| Agricapital | Medellín | Colombia | 6.2458 | -75.5794 | 3674962
| Blooms Capital | Ciudad de México | Mexico | 19.4283 | -99.1275 | 3527646
| Verqor | Ciudad de México | Mexico | 19.4283 | -99.1275 | 3527646
Modifications to Project Design or Implementation:
(If applicable, please detail all changes since the last Update to the project design (objectives, thematic or geographic scope, components, activities, products, results, beneficiaries, costs, monitoring & evaluation), implementation modality or timeline, vis-a-vis the design, modality or timelines approved by the GEF) | No changes to report since CEO Endorsement.
*In addition to providing the performance assessmente above, please feel free to add links or annex supporting information (and ensure that the above text clearly indicates what elements/arguments are supported by that information).
*** PLEASE DON'T OVERWRITE THIS SECTION! *** | GEF-3
GEF-4
Loan - Harder Term | GEF-5 | Capital/ Principal | Investment mobilized - Grant | Highly Satisfactory [HS]
Loan - Softer Term | GEF-6 | Earnings/ Interest | Recurrent expenditures - Grant | Satisfactory [S]
Loan - Senior in USD or EUR | GEF-7 |  | Investment mobilized - Loan | Marginally Satisfactory [MS]
Loan - Senior in local currency hedged | GEF-8 | Expected | Recurrent expenditures - Loan | Marginally Unsatisfactory [MU]
Loan - Contingent recovery | GEF-9 | Actual/ Realized | Investment mobilized - Equity Investment | Unsatisfactory [U]
Guarantee - First loss | GEF-10 |  | Investment mobilized - Public Investment | Highly Unsatisfactory [HU]
Guarantee - Second loss | GEF-11 | GEF Agency | Investment mobilized - Guarantee
Grant - Contingent recovery or convertible | GEF-12 | Donor Agency | Recurrent expenditures - In-kind | High Risk (H)
Debt - Subordinated/ mezzanine instrument with income participation |  | Recipient Country Government | Investment mobilized - Other | Substantial Risk (S)
Debt - Subordinated/ mezzanine instrument with convertible features | Biodiversity | Private Sector | Recurrent expenditures - Other | Modest Risk (M)
Equity | Climate Change | Civil Society Organization |  | Low Risk (L)
| Land Degradation | Beneficiaries
Eligible | Chemicals & Waste | Other
Approved | International Waters
Signed/ Closing
First disbursement | Full-sized Project
Investment/ Commitment period terminated | Medium-sized Project (1-step)
Divestment/ Repayment period terminated | Medium-sized Project (2-step)
Last financial transaction completed | Enabling Activity
Audit completed
Fully closed (technical & financially)
Cancelled
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To GEF: Actual Agency Approval Date
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effectiveness date/ Signature date of Facility or of first investment that reaches effectiveness/ siganture stage under Facility
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please state amount indicated in CEO Endorsement/ Approval document - Financial terms annex.
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No changes since approval
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Actual Eligibility Granted" Date in Maestro
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Closing/ Signature Date in Maestro
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please state amount indicated in CEO Endorsement/ Approval document - Financial terms annex.
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If "Difference Actual vs. Expected Reflows" is negative and no additional reflows are expected (i.e . Remaining Expected Reflows = 0), please briefly explain reason for difference.
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Final Repayment Date (Maturity)" in Maestro
Note on B159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Panned Maturity Date in Maestro; Original Last Disbursement Expiration Date (OED) in Convergence
Note on B160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual Maturity Date in Maestro; in Convergence, Current Last Disbursement Expiration Date (OED) IF & ONLY IF CED has already passed
Note on B164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Planned Project Closure in Maestro; Estimated Operational Close (EOC) in Convergence
Note on B165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in Maestro, Actual Project Closure; in Convergence, Operative Close (COO)
Note on B190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please copy-paste indicators exactly as stated in CEO Endorsement/Approval document approved by the GEF. Please do not use the Program's Results Matrix as the source for this information.
Note on D190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please enter the quantitative target stated in the CEO Endorsement/ Approval document, using sub-indicators where applicable (refer to Core Indicator Worksheet).