## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | #NAME?
#NAME?

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Latin America and the Caribbean (RLC)
Country(ies): | Antigua and Barbuda, Barbados, Belize, Grenada, Guyana, Haiti, Jamaica, St. Lucia
Project Title: | Caribbean Small Island Developing States (SIDS) Multicountry Soil Management Initiative for Integrated Landscape Restoration and Sustainable Food Systems: Phase 1 (CSIDS-SOILCARE Phase 1)
FAO Project Symbol: | GCP/SLC/214/GFF – GCP/SLC/215/SCF
GEF ID: | 10195
Type of Trust Fund(s): | GFF, SCCF (Multi trust fund)
GEF Focal Area(s): | Land Degradation, Climate Change Adaptation, MFA
Project Executing Partners: | Partnership Initiative For Sustainable Land Management (PISLM)
Initial project duration (years): | 4
Project Dates
GEF CEO Endorsement Date: | 2021-09-23
Actual Agency Approval Date | 2021-01-20
Project Implementation Start Date/EOD: | 2021-11-24
First Disbursement Date | 2021-12-31
Planned Project End Date/NTE1: | 2025-11-23
Revised project implementation End date (if approved)2:
Actual Completion Date: | n/a
Expected Financial Closure Date: | 2026-11-23
Funding
GEF Grant Amount (USD): | 8155205
Total GEF grant delivery (as of June 30, 2025 (USD): | Total: 5,449,942.21 GFF (GEFTF): 5,009,756.02 SCCF 440,186.19
Total Co-financing amount (USD)3: | 25797816
Total estimated co-financing materialized as of June 30, 2025: | 8302551
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 2024-03-11
Expected Mid-term Review date5: | n/a
Actual Mid-term review date (if already completed): | 2025-02-19
Expected Terminal Evaluation Date6:
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Moderately Satisfactory
Overall implementation progess rating: | Moderately Satisfactory
Overall risk rating: | Substantial
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 3rd PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Trevor Thompson, PISLM
Budget Holder (BH) | Renata Clarke, Sub-Regional Coordinator for the Caribbean
GEF Operational Focal Point (GEF OFP)
Lead Technical Officer (LTO) | Melvina Medina
GEF Technical Officer (GTO) | Neila Bobb-Prescott
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
Project Manager | Yes | Trevor Thompson, May 2022 tthompson@pislmsids.org
SOILCARE Integration Specialist | Yes | Calvin James, cjames@pislmsids.org, Nov2021
Procurement Officer | Yes | Shawnette Collins, Nov2021 scollins@pislmsids.org
Project Secretary and Office Assistant | Yes | Kiefer Jackson, Nov2021 kjackson@pislmsids.org
PISLM Liaison Officer | Yes | Tricianna Maharaj, May 2022 tmaharaj@pislmsids.org
Regional Technical Officer | Yes | Lakeram Singh, Nov2021 lsingh@pislmsids.org

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
To Strengthen Caribbean SIDS with the necessary tools for adopting policies, measures and reforming legal and institutional frameworks to achieve Land Degradation Neutrality LDN and Climate Resilience | Outcome 1.1: Caribbean countries use soil data to make informed decisions and contribute to regional and global soil and climate knowledge systems | Increased national and regional capacities for soil analysis through the establishment of the Caribbean Soil Laboratory Network (CARLAN) | Though some soil analytical capability exists in some of the participating Member States, considerable strengthening is required to complement the capability, which resides at the University of the West Indies, St. Augustine Campus, Trinidad and Tobago. | An assessment of the soil analytical capability of the participating Member States has been undertaken, the strengths and weaknesses of these facilities identified, and a Programme to Enhance their Capability outlined and is being implemented. | Caribbean Soil Laboratory Network established and operational at the Soil Science Laboratory of the University of West Indies (UWI), St. Augustine, Trinidad and Tobago at its apex. Soil laboratory capacities (equipment, human talent and harmonization processes) in Caribbean member states are enhanced under GLOSOLAN Soil Samples have been collected, analyzed and the data stored in CARSIS under Standard Operation Procedures. | Lab equipment procured and shipped to all participating countries, except Haiti due to the social and security issues. - CarSoLaN established and functioning with meetings held quarterly to dicuss progress on the workplan. - CarSoLaN was given a COTED mandate at the 109th Session of COTED [Agriculture] to serve as the Regional agency to provide standardization services to thesoil labs in the Caribbean. - CarSoLan representatives have been involved in various capacity buiding efforts inclusive of LAB SOP workshop in the Caribbean as well as part of wider ASLAC programme. - Haiti national soil sampling concept note and budget is finalised with sampling expected to start within the third quarter. Belize soil samples have been shipped to The UWI, St. Augustine Campus for analysis. -Guyana national soil sampling was setback from an unfortinate vehicular accident that claimed the life of one person, it is expected that the soil sampling would be completed this quarter. | 80% | Satisfactory (S)
|  | Caribbean Soil Information System (CARSIS) for monitoring soil health located at a central repository and managed by the Caribbean Soil Support Group | The participating countries do not possess soil information systems, although recent projects have allowed for collection of new soil data. Furthermore, the information is not organized on a Sub-regional basis, particularly in the form of a Caribbean Soil Information System and integrated with Regional and Global Soil Information Systems (e.g. SISLAC and GLOSIS). | The basic infrastructure for the establishment of a Caribbean Soil Information System (CARSIS) is in place integrated to the Regional and Global Soil Information Systems (e.g. SISLAC and GLOSIS) and served by national soil information systems. | The Caribbean Soil Information System (CARSIS) is operational and composed by national soil information systems fully integrated with Regional and Global Soil Information Systems (e.g. SISLAC and GLOSIS). Enhanced capacities on soil survey and digital soil mapping are available in all participating countries. | The CARSIS is being developed in preparation for the creation of digital soil maps, FAO/GSP representatives conducted a 4 part series virtual training session to further capacitate countries on the process of transforming the data into a database capable of generating these soil maps. All SOILCARE P1 Countries Participated - on average per session 32 Males and 17 Females attended. - Grenada, St. Lucia, Antigua and Barbuda, and Jamaica held in country (face to face) workshops in LDN Indicators and Google Earth Capacity Building to use the digital soil maps being created - with an of average 11 males and 6 females attending across the four islands. - The GSP assisted the PISLM with the creation of 7 single property maps each for Antigua, Barbados, St. Lucia, Jamaica, and Grenada. - In April 2023, the project facilitated an introductory workshop into digital soil mapping which saw participation from all countries 11Males, 3 females
| Outcome 2.1: Land and Soil Degraded Areas in Haiti, Guyana, St. Lucia; Grenada and Barbados are rehabilitated, ecosystem services restored and sustainable livelihoods built. | Number of hectares of degraded lands rehabilitated and ecosystem services restored, with a target of 25,000 ha | Most of the sites earmarked for rehabilitation are heavily denuded and have been identified through the LDN Target Setting exercise. | At least 7,500 hectares (50 percent) of degraded lands were rehabilitated and ecosystem services restored, | 15,000 hectares of degraded lands rehabilitated, and ecosystem services restored | All Site assessment surveys were completed (including visual soil assessments and visual and historical analysis of the site). Analysis of all soil samples from the 25 intervention sites have been completed. DPSIR reports completed and validated in all 7 project participating countries. Barbados and Grenada have finalized their plans for the work in this component. | 25% | Unsatisfactory (U)
|  |  |  | Strategies (Community-Private Partnerships etc.) for the engagement of the private in the rehabilitation of degraded lands are prepared and being implemented. |  | Validation workshops completed in seven target countries which focused on the soil analysis data, land capability analysis and climate-smart agriculture options. Approval was obtained for actions proposed for all intervention sites. 384 stakeholders were engaged in these sessions across all countries.
|  | Greenhouse gas emissions avoided/captured from rehabilitation and restoration activities | 0 |  | 5 million tonnes GHG emissions captured or avoided | Not yet actioned
|  | Number of people that benefit from project activities (i.e. direct beneficiaries and from project upscaling), disaggregated by gender |  | 500 | 1,250 beneficiaries (475 women) | In Grenada Les Avocat site 12 persons benefitted directly, 3 women and 9 men
| Outcome 3.1: Soil productivity restored through Climate Smart Agriculture, Model Farms established on selected landscapes in Guyana, St. Lucia, Haiti, Grenada, and Barbados and applied regionally | Hectares of arable lands that have adopted SSM/SLM and CSA measures, | Land suitability assessment produced in Output 1.1.2 | Climate risk assessment for all the CSA Model Farms have been undertaken and the information and data accessible to the participating farmers. Good practices adopted according to the Voluntary Guidelines for Sustainable Soil Management, the manual of good practices and others following an ecosystem approach. | A total of at least 20,000ha hectares of agricultural lands converted into farms that employ climate resilient and sustainable soil management/farming practices as follows: Barbados: 3,000 hectares Grenada: 3,000 hectares Guyana:4,000 hectares Haiti: 7,000 hectares St. Lucia: 3,000 hectares | The intervention sites have been visited by the CSA expert to record the historical data and interact with communities and national stakeholders regarding potential interventions. Field Report was submitted to the PMU for review. -Climate risk analysis was completed for all intervention sites with validation workshops completed. The CRA reports were adopted by stakeholders and formed an integral part of the DPSIR reports. - Regional Guidelines for Climate Smart Agriculture have been prepared and submitted in draft to the PMU for review and approval. -Concept notes for the climate smart model farms at Nature Fun Ranch Barbados and Little Biabou Guyana finalized. | 25% | Unsatisfactory (U)
|  | Greenhouse gas emissions avoided/captured from climate smart farms | 0 |  | 0.4 million tonnes GHG emissions captured | Not yet actioned.
|  | Number of people that benefit from CSA/Model Farms (i.e. direct beneficiaries and from project upscaling), disaggregated by gender | 0 | 800 | 1,800 beneficiaries (750 women) | No such information as yet
| Outcome 4.1. Food production systems and alternative livelihood options implemented with innovative technologies and private sector support are more resilient and adapted to climate change in Belize, St. Lucia, Carriacou-Grenada, Jamaica and Barbados | Number of hectares where adapted food production systems and alternative livelihood options are implemented Improvement in on-farm productivity with respect to crops and livestock Percent increase in Annual household income from agricultural activity for project beneficiaries | No recent Land Capability Assessment exist for the sites identified | Assessment of Land Capability of the Selected Sites completed | 20,000 ha Adapted Land Use/ Food Production Systems established creating Alternative Livelihood Options using innovative technologies and approaches with private sector support as follows: Barbados: 1,500 hectares Belize: 8,000 hectares St Lucia: 1, 500 hectares Grenada: 2,000 hectares Jamaica: 7,000 hectares | -Consultants have conducted visual site assessments of all intervention sites countries except Haiti . - Land Capability Assessments report submitted - RAC NAT Facility is operational and concluded an experiment on hot pepper production with preliminary findings from a 3-acre plot indicating a total harvest of 260 bags (20 lbs each) of hot pepper. Field performance varied across treatments. Notably, the most promising yields were observed in fields treated with half the recommended rate of synthetic fertilizer combined with compost. This suggests a potential for reducing input costs while maintaining or enhancing productivity through integrated soil fertility management. | 20% | Unsatisfactory (U)
|  | Number of people that benefit from improved food production systems (i.e. direct beneficiaries and from project upscaling), disaggregated by gender | 0 | 500 | 1,800 beneficiaries (750 women) | No such information as yet.
| Outcome 5.1 Regional capacity development and training programme established | Percent persons trained in SSM, SLM and CMA methods and techniques from the participating countries that contribute to the development of components 1 to 4, disaggregated by gender. | Major gaps exist in Caribbean SIDS with respect to the integration of climate resilient methods and approaches in SSM and SLM training and application. In addition, major gaps in knowledge accessibility of information and data on SSM and SLM as well as investments by the private sector in these areas. Insufficient effort is currently directed to regional climate modelling and Projections that can feed into or inform SLM in Caribbean SIDS. Significant capacity gaps exist in Caribbean SIDS with respect to SSM and SLM as well as the integration of these concepts into Regional Policy Frameworks. | The Regional Infrastructure for addressing these gaps and weaknesses are well established through this project for addressing the identified gaps and weaknesses. | The basic Regional Infrastructure for Mainstreaming SLM and Sustainable Soil Management (SSM), particularly in Regional Policy Frameworks; Strengthening Knowledge Management as it relates to SSM and SLM, the training a cadre of stakeholders in climate resilient methods and approaches, including in Climate Modelling and Projections for SLM; the Building of Financial Capability to Implement SLM the basis for preparing a Regional LDN Strategy is well established and provides a Foundation for other interventions on SSM and SLM. | Completed scholarship award which included advertising, establishing of evaluation committee, evaluation of applications and award of 5 scholarships in Soils science. The scholarship awardees have submitted research proposals to their relevant superviosrs and commence work. -Land Use Expert and the UWI team have visited and trained extension officers and forest officers in soil sampling methodologies. -FAO-GSP conducted training in Digital Soil Mapping for all country parties in April, 2023. -FAO-GSP conducted training in soil sampling methodologies in January, 2023. - Regional Capacity Development Plan developed and transmitted to countries for input. - PISLM facilitated a 3-day HNVI training workshop in Guyana in October 2023 with attendance from all eight SOILCARE Phase I countries - In country HNVI C-SAC Train the Trainers workshops completed in Guyana, Grenada , Antigua and Barbuda, Haiti, Jamaica, Belize and Barbados. -Convened three (3) Caribbean Ministers responsible for UNCCD meetings and had the resolutions of each meeting endorsed and or adopted by both COTED [Environment] and COTED [Agriculture] (as applicable); these Ministerial outcomes were also adopted at OECS Ministers of Environment. The Sustainable Soil/Land Management Framework Agreement Group was established and functioning. This group is now an organ of the PISLM and serves as the advisory group to the Executive Committee of PISLM. Because this group comprises several Caribbean Institutions it provides appropriate input, based on their expertise, into the several policies and projects being carried out by PISLM. Currently, this group is providing input into the development of SOILCARE Phase 2. Conversely, due to its insertion into the PISLM family, SSM and SLM policies are also inserted into their individual organization policies and projects. The Ministerial Council approved the report of a study commissioned by PISLM for the establishment of a regional SLM/SSM funding mechanism and instructed the PISLM Secretariat to operationalize the fund. It was agreed that the Fund would be headquartered in the Commonwealth of Dominica. PISLM is collaborating with FAO (Rome) to establish the framework for the operationalization of the Fund. In December 2024, training was done for all country parties on laboratory SOP's and interpretation and fertilizer reccommendations at the UWI as part of the RAC/NAT's mandate. M10, F8 In February 2025, training was done for all country parties on the creation of soil organic carbon sequestration maps,led by the GSP. M20, F8 | 70% | Satisfactory (S)
| Outcome 5.2. SLM/LDN Knowledge Management, Technical Assistance and Communication in SLM and SSM strengthened and enhanced | Knowledge products/materials produced and disseminated to stakeholders in the region. Social Learning Platform being used to network, share, collaborate and exchange ideas to solve problems. Indigenous Peoples Network established and used by Indigenous Peoples to strengthen Regional Networking | Major gaps exist within Caribbean SIDS with respect to adequacy of information on SLM and SSM as well as an effective mechanism for facilitating the movement of technical expertise to address specific issues and problems relating to LD, SLM and SSM, among many others. | The basic infrastructure for Knowledge Management, technical assistance and communication on SLM and SSM are established | A number of initiatives are launched and operational, namely, the Caribbean LDN and SLM Knowledge Hub which is designed to capture data and information generated through SOILCARE Phase 1 and to facilitate its use and transfer across the region, thus increasing accessibility; and the Caribbean SLM/LDN SIDS-SIDS Cooperation Mechanism which will provide a mechanism for the identification and transfer of specific expertise across the region to address specific issues and problems. | The PISLM Knowledge Hub (Caribbean LDN and SLM Knowledge Hub is complete, and its efficacy is being assessed in a ‘Sandbox environment’ to ensure that it meets the objectives it was designed for. Further, the PISLM Knowledge Hub has been selected by another GEF funded project, the SIDS – SIDS Knowledge Hub, where it would serve as the Land and Soil sub – hub within the SIDS – SIDS Knowledge Hub. The Hub was launched at the Ministerial Pre – COP Meeting on 9 August 2024 in the Bahamas. With respect to the SIDS – SIDS Cooperation Mechanism, two (2) projects were programmed to the be carried out on this platform: i. Indigenous Peoples Forum of Soil and, ii. A SIDS – SIDS Forestry Programme. With respect to the former the Indigenous Peoples Forum was created and is functional. They developed a project which was approved by the Ministerial Council to be funded in SOILCARE Phase 2. As it relates to the later initiative, a proposal was developed to have Foresters from the OECS visit Haiti for an exchange programme. The Youth Initiative entered into with the Caribbean Youth Environment Network, completed a Youth In Agriculture capacity building Workshop during the month of May 8- 9, 2024, at the Sugar Cane Mall in Barbados. The workshop saw participation of 17 youths (11 females and 5 males) from Antigua & Barbuda, Barbados, Belize, Grenada, Guyana, Jamaica and St. Lucia . Caribbean Land-Soil Outlook first and second editions have been submitted to the countries and published on the Website. | 65% | Satisfactory (S)
| Outcome 5.3. Climate Resilient SLM and Regional LDN Strategy Mainstreamed/Integrated into Caribbean Community Regional Policy Frameworks, Decision Making Processes and into National Level planning processes | Number of Caribbean Community Regional Policy Frameworks, reviewed, amended and approved. | Currently SSM and SLM are not sufficiently well integrated into the Caribbean Community Policy Frameworks. | The various Caribbean Community Organs have met and a decision taken to integrated SSM and SLM into the various Caribbean Community Policy Instruments and the necessary revisions in the Policy Frameworks made. | The Outcomes and Outputs of SOILCARE Phase 1 are integrated into the various Community Policy Instruments, namely, the Caribbean Community Agricultural Policy, Draft Community Environment and Natural Resources Policy Framework etc. and adopted by the relevant Community Organ(s), as well as the mainstreaming of adaptation. In addition, the establishment of a sub-regional SSM framework agreement contributing to LDN; an updated sub-regional implementation plan for SSM and LDN, and an operational soil/LDN platform across institutions and decision-making bodies are also established. | The Decisions approved at the 5th PISLM High- Level Forum of Ministers in June 2023 were presented to the 109th Session of the COTED [Agriculture] in August of 2023 where that meeting endorsed Decision 2 and Decision 3 of the 5th PISLM High – Level Meeting. The Decisions approved at the 5th PISLM High- Level Forum of Ministers in March 2023 were also presented to the 108th Session of the COTED [Environment] in June 2023 where that body endorsed Decision 3 and Decision 5 of the 5th PISLM High – Level Meeting. The 6th and last Session of the PISLM High – Level Meeting and the 1st Session of its replacement, the Ministerial Council was held 12 April 2024 in Grenada and the resolutions coming out of those meeting was presented to COTED[Environment] for adoption as follows. At the 112th Session of COTED [Environment] Decision 1, 2 and 4 of the 6th Session of the PISLM High –Level Meeting were endorsed and, at that same COTED meeting Decision 4 of the 1st Ministerial Council was endorsed; the meeting also endorsed the establishment of a UNCCD SIDS Forum and the setting up of SIDS Pavilion at UNCCD COP 16 The Sustainable Soil/Land Management Framework Agreement Group was established and is functioning. This group met at its 3rd Session on 22 May 2024 in Trinidad where discussions were held on how the various agencies in this group can participate in SOILCARE Phase 2 and the Caribbean LDN Transformative Project. The group also met in the first quarter of 2025 to discuss its workplan and support for Regional Soils activities - total of 21 members were present. Belize has successfully held stakeholder engagements and has reviewed and produced a new Land Use Policy. This is now at the level of the Cabinet awaiting its approval. | 65% | Satisfactory (S)
| Outcome 5.4. Promotion of Investment and financing in SLM/SSM and climate resilience with Private and Public Sector | The Caribbean SIDS LDN Transformative Fund Mechanism is established and funded. | Currently no such mechanism exist to facilitate the Promotion of Investment and financing for SLM, SSM and Climate Resilience with Private and Public Sector entities. | The Feasibility Study to explore the possibility of establishing the Regional Fund to ensure the necessary resources are available to stakeholders, in particular, small farmers, to incorporate SLM and Climate Smart approaches and methods into their farming systems is undertaken and approved by the participating countries and the PISLM and efforts are under the way to resource it. | The Caribbean SIDS LDN Transformative Fund Mechanism is established and resources mobilised for climate-resilient SSM/SLM | The feasibility study was completed and presented to the CARICOM Ministers responsible for the UNCCD at its 6th High-Level Forum in Grenada in April 2024. The Ministers adopted the recommendations proffered by the report and passed a resolution for the PISLM Secretariat to proceed with the operationalization of the Fund . It was further agreed, that the headquarters for the Fund shall be the Commonwealth of Dominica. Talks are ongoing between FAO (Rome) and PISLM on the modalities of operations. The Ministers responsible for UNCCD were apprised of this at the PISLM's Ministerial Council meeting in June 2025. | 70% | Satisfactory (S)
|  | Private and public investment mobilized which mainstream climate adaptation considerations | 0 |  | TBD at inception
| Outcome 5.5 An effective Gender Sensitive Monitoring and Evaluation Framework in Support of Project Implementation established | Project Monitoring System supports project delivery while following a Results Based Management approach | Currently no such modality for undertaking an effective Gender Sensitive Monitoring and Evaluation Framework for Climate resilient SSM and SLM exists in Caribbean SIDS | The operational modalities for undertaking an effective Gender Sensitive Monitoring and Evaluation Framework in Support of Project Implementation is well established | An effective Gender Sensitive Monitoring and Evaluation Framework in Support of Project Implementation | A Gender Sensitive Monitoring and Evaluation Framework for SOILCARE Phase 1 was develop and approved at the 6th Session of the PISLM High – Level Forum. Prior to that PISLM used its internal Gender policy Subsequently, a Gender and monitoring report, and a Gender and resilient Foods System report to ensure gender mainstreaming in all activities was generated. Finally, a Gender and mainstreaming workshop held for all PISLM and PMU staff in May 2024. Thus far, project activities have impacted : 316 Females 279 Males Project Monitoring and Evaluation schedule implemented according to the results and deliverables framework. -Half Year Progress Reports Submitted and Validated for 2024 -Quarterly Funds Request Reports submitted with associated expenditure documentation. -Financial Spot-Check conducted in March 2024 by PMU at UWI by FAO. Gender and Livelihoods consultant submitted Gender and monitoring report, Gender and resilient Foods System report to ensure gender mainstreaming in all activities. The project has concluded its Mid-Term review between November 2024 to May 2025. The PMU and the FAO have collaboarted on this with unput from country parties. | 65% | Satisfactory (S)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
53.89% | 95% | #VALUE!
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Moderately Satisfactory (MS) | Moderately Unsatisfactory (MU) | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | Although implementation in components 2,3,and 4 is severely lagging behind, strong performance in Components 1 and 5 are strong indications that all outcomes will be achieved. Activities ongoing for components 2 to 4 are expected to ensure that all targets are achieved during the next 6- 8 months. | This project remains extremely relevant to supporting the regional thrust for food security. It is however severely delayed compared to the initial workplan, particularly regarding on-the-ground implementation in the demonstration sites. That is now jeopardizing the achievement of the expected outcomes and impact. Extending the project beyond its current NTE (November 2025) will be needed to enable delivery, including revised targets and a detailed and feasible workplan agreed between the project parties. FAO remains commited to project sucess and reiterates its offer of intensified support, in particular regarding technical input to reports, to the design of site-specific responses to degradation, and to the formulation and implementation of the site intervention plans. For that, FAO would need to be granted access to technical documents beyond the compulsory project reports, so meaningful contributions are enabled and FAO can put its full technical capability to the service of the project. Reviewing and strengthening mechanisms to improve communication, coordination and technical exchanges among the partners would be critical in that regard. A meeting between FAO and the Executing Agency is suggested, so the mentioned aspects are discussed with the EA's new management team, and corrective actions are agreed and taken. | Implementation, specially with respect to the on-the-ground project activities and regarding the originally planned timeline and the approved 2024 workplan is very delayed. However, the project approach remains relevant and technically adequate, and is still considered to be capable of delivering its overall objective, although an extension of project NTE would be required. Measures for ensuring sustainability of results and impact are suggested, in particular actions to strengthen capacity development through more targeted approaches , as it is one of the main issues identified by the EA. |  | The MTR reports mixed results from program implementation--namely delays in field activities and important advances under the soil mapping and knowledge components. Both partners (PISLM and FAO) and committed to implement the program to allow it to reach its commitments. To do this, the MTR recommends a 2-year extension. The program remains highly relevant and is the basis for the SOILCARE 2 program currently under review and the upcoming phase 3 (GEF9) focusing on drought.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 2.1: Land and Soil Degraded Areas in Haiti, Guyana, St. Lucia; Grenada and Barbados are rehabilitated, ecosystem services restored, and sustainable livelihoods built. |  | Coordinate closely with country officers to finalize plans for intervention sites - Complete procurement evaluation to support commence intervention actions. - Procure equipment, inputs, staff to support field operations. |  | PISLM PMU Project Manager and Project Focal Points |  | 2025-08-01
Outcome 3.1: Soil productivity restored through Climate Smart Agriculture, Model Farms established on selected landscapes in Guyana, St. Lucia, Haiti, Grenada, and Barbados and applied regionally |  | Coordinate with the Agriculture directorates within each country to draft Smart contracts and marketing Plans |  | Project Manager and CSA Consultant |  | 2025-12-01
Outcome 4.1. Food production systems and alternative livelihood options implemented with innovative technologies and private sector support are more resilient and adapted to climate change in Belize, St. Lucia, Carricou-Grenada, Jamaica and Barbados |  | Coordinate with the Agriculture directorates within each country to draft and finalize the Procurement plans |  | Project Manager and CSA Consultant |  | 2025-12-01
Outcome 5.2. SLM/LDN Knowledge Management, Technical Assistance and Communication in SLM and SSM strengthened and enhanced |  | Engage the ICT service provider to begin building the platform |  | Project Manager and ITC Officer |  | 2025-12-01
Outcome 5.5 An effective Gender Sensitive Monitoring and Evaluation Framework in Support of Project Implementation established |  | Fully enforce a gender sensitive tracking tool in all activities Invite FAO Gender division to provide guidance |  | Project Manager and Gender and Livelihoods Consultant |  | 2025-12-01
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.1. Caribbean countries use soil data to make informed decisions and contribute to regional and global soil and climate knowledge systems | Increased national and regional capacities for soil analysis through the establishment of the Caribbean Soil Laboratory Network (CARLAN) | All countries have receivd their lab equipment with the exception of Haiti due to civil unrest CARSOLAN members attended training on laboratory SOPs, interpretation of results and fertilizer reccomendations
| Caribbean Soil Information System (CARSIS) for monitoring soil health located at a central repository and managed by the Caribbean Soil Support Group | The GSP assisted the PISLM with the creation of 7 single property maps each for Antigua, Barbados, St. Lucia, Jamaica, and Grenada.
Output 1.1.1 Caribbean Soil Support Group for SSM/SLM established and collaborating, with the Latin American and Caribbean Soil Partnership | A Cooperative Framework (e.g. Caribbean Soil Support Group for SSM/SLM) for the Focal Points for the UNCCD and the Global Soil Partnership (GSP) to work together is established and operational. | Policy Guidance framework for the CSSG finalized with a COTED Mandate
Output 1.1.2 National soil data including soil organic carbon reviewed and updated supported by integrated field sampling, laboratory analysis and remote sensing in support of local, national and regional planning and international reporting | Number of national soil information systems (NSIS) established) | National soil survey data and analysis reports received for Jamaica in this period |  |  | Delivery of analysis took a long time due to delays in shipping and clearance of soil samples in Trinidad. This resulted in further delays at the lab as its use for student sessions were prioritized.
| Number of Soil Organic Carbon (SOC) and soil organic carbon potential sequestration maps available as the basis for Soil Organic Carbon Monitoring, with a target of 8 (1 per country) | SOC maps produced for Grenada and Carriacou, St. Lucia, Antigua and Barbuda, Barbados. SOC seq map produced for Antigua and Barbuda |  |  | The project conducted the SOCseq training in February 2025. However, being a new concpet to many, progress on map production has been slow.
| Number of Land Suitability maps for crop production (at least 5 crops) with a target of a set of 5 suitability maps per country | No maps produced as yet. |  |  | Due to delays in sampling and analysis, maps have not been fully elaborated. Also, the countries identifed low capacities in their GIS departments which caused a slow uptake of the maps produced by the GSP.
| Land degradation assessment maps available for participating countries | No maps produced as yet. |  |  | Delays in processing higher resolution imagery has been the main limiting factor
Output 1.1.3 Caribbean Soil Laboratory Network (CARLAN) established based on the strengthening of national soil laboratories under the standards of GLOSOLAN | Five National Soil Laboratories fully functioning under standards of CARLAN and GLOSOLAN Caribbean Soil Laboratory network functioning with participation of at least 5 laboratories for enhancing capacities and ensuring harmonization | Shippment was received in all countries except Haiti National representatives (18) from all SOILCARE countries participated in a workshop on a LATSOLAN laboratory SOP and data intrepretation in December 2024. |  |  | The social unrest and security concerns in Haiti resulted in delays
Output 1.1.4 Caribbean Soil Information System (CARSIS) established and integrated with Regional and Global Soil Information Systems (SISLAC and GLOSIS) and digital soil mapping capacities built. | Caribbean soil Information System operational At least 10 national experts fully trained digital soil mapping, its applications and National Soil information Systems | Single-property digital soil maps for 4 countries completed and ready for upload into the system. Training was conducted in Feburary 2025 in Grenada on SOCseq map production with approximately 22 persons trained. |  |  | Lack of regional capacity on soil information databases and related software, including GEE is affecting deliverable timeline.
Outcome 2.1: Land and Soil Degraded Areas in Haiti, Guyana, St. Lucia; Grenada and Barbados are rehabilitated, ecosystem services restored and sustainable livelihoods built. | Number of hectares of degraded lands rehabilitated and ecosystem services restored, with a target of 25,000 ha | Barbados and Grenada have completed their concept notes and begun work in their respective sites
| Greenhouse gas emissions avoided/captured from rehabilitation and restoration activities | NIL
| Number of people that benefit from project activities (i.e. direct beneficiaries and from project upscaling), disaggregated by gender | In Grenada Les Advocat site 12 persons benefitted directly thus far, 3 women and 9 men
Output 2.1.1 Participatory strategies for rehabilitation and restoration and Intervention plans available and implemented based on the hot and bright spots identified in the land degradation assessment. | Number of hectares covered by Intervention Plans (IP) and Participatory Strategies for Rehabilitation and Restoration (PSRR) | Work has started in Grenada at the Les Avocat Site with the clearing of invasive bamboo and Blue and white Mahoe and land preparation for replanting over 10 acres in ecologically sensitive parts of the watershed. |  |  | There has been difficulties in coordinating local authorities to finalize their procuremenet needs.
Output 2.1.2 Community Propagation Centres established and/or upgraded to Facilitate the Provision of Plant Materials and Soil Amendments | Number of community propagation centres established or upgraded Number of plants propagated by country | Work has started in Barbados on upgrading the propagation centre located at the Soil Conservation Unit. The Soil Conservation Unit has completed its assessment of the facility and proposed measures to get it operational. PISLM has signed a contract with a service provider to begin the removal of inoperable parts of the facility and removal of debris. |  |  | There has been difficulty in coordinating local authorities to finalize their procuremenet needs.
Output 2.1.3 Integrated Landscape Management (ILM), including analog forest and agroforestry systems implemented in target areas in five participating States. | Number of hectares under ILM Number of advocacy and awareness raising events on the prevention of land/soil degradation | Haiti has conducted community awareness events in intervention sites aimed at sensitizing them to the planned work. Two sessions were held, one in the community of Samana and one in Rio Marion with 50 farmers engaged (40M, 10F) |  |  | There has been difficulty in coordinating local authorities to finalize their procuremenet needs.
Output 2..1.4 Cost-Benefit Analysis (goods and ecosystem services) of the restoration strategies are conducted, documented, and shared as a basis for scaling out to other locations in participating States and to other SIDS. | Validated restoration strategies based on cost benefit analysis for different farming context are documented and shared through the Caribbean Soil Information System and FAO’s regional information communication system | NIL |  |  | Delays in implementation have hindered this activity.
Outcome 3.1 Soil productivity restored through Climate Smart Agriculture, Model Farms established on selected landscapes in Guyana, St. Lucia, Haiti, Grenada, and Barbados and applied regionally | Hectares of arable lands that have adopted SSM/SLM and CSA measures, | NIL |  |  | Delays in implementation of model farms have delayed further outscaling
| Greenhouse gas emissions avoided/captured from climate smart farms | NIL
| Number of people that benefit from CSA/Model Farms (i.e. direct beneficiaries and from project upscaling), disaggregated by gender | NIL |  |  | Data will be available when works are completed
Output 3.1.1 Climate Change Implications Assessed and Validated at the farm and landscape levels and the Results used and promoted to support climate resilient and viable/ productive farming systems and value chain integration at the regional level | No. of Climate Risks and vulnerability assessments conducted | NIL
Output 3.1.2 Climate Resilience Measures Integrated into Model Farms and the Information Gathered Use to Form the Basis of the Regional Guidelines which will Guide Farmers in Transitioning to Climate Smart Agriculture Production at the Regional Level | Number of Climate Smart Model Farms implemented No of climate resilient agricultural practices and technologies applied | Work has begun on the CSA model farm in Barbados. The Service provider has been engaged and has begun providing the materials for the shade house structure. Shadenetting and ground cover has been procured. |  |  | There has been difficulty in coordinating local authorities to finalize their procuremenet needs.
Output 3.1.3 Climate Smart Agriculture baseline and marketing strategy designed and applied and legal agreements established as a basis for scaling out successes, under a gender equality approach | Marketing strategy designed and under application Number of legal agreements established to scale out CSA | NIL
Output 3.1.4 Baselines, indicators and methods for the implementation of Climate Smart Model Farmland and Landscapes established using the High Nature Value Index (HNVI) | Percent of farms that show an increase by the HNVI, by country. | CSA training have been conducted in St. Lucia, Belize and Jamaica in this period |  |  | Delays in precursor activities
Outcome 4.1: Food production systems an alternative livelihood options implemented with innovative technologies and private sector support are more resilient and adapted to climate change in Belize, St. Lucia, Carricou-Grenada, Jamaica and Barbados | Number of hectares where adapted food production systems and alternative livelihood options are implemented Improvement in on-farm productivity with respect to crops and livestock Percent increase in Annual household income from agricultural activity for project beneficiaries | RAC NAT Facility is operational and concluded an experiment on hot pepper production with preliminary findings from a 3-acre plot indicating a total harvest of 260 bags (20 lbs each) of hot pepper. Field performance varied across treatments. Notably, the most promising yields were observed in fields treated with half the recommended rate of synthetic fertilizer combined with compost. This suggests a potential for reducing input costs while maintaining or enhancing productivity through integrated soil fertility management
| Number of people that benefit from improved food production systems (i.e. direct beneficiaries and from project upscaling), disaggregated by gender | NIL
Output 4.1.1 Land use, food and livelihood systems assessed as a basis for identifying alternative options and innovations and setting a baseline for monitoring, as a basis for developing Resilient Food Production Systems and Alternative Livelihood Options | Percent target sites that have a land capability assessment completed (per country) Number of SSM and SLM practices for which their impact is assessed in the framework of the soil monitoring programme | NIL
| Number of technologies demonstrated | Works started in Barbados intervention sites. Contract signed for the construction of shadehouses, shade netting procured. In Belize, the local authoritieis have conducted their feasability assessments and have identfied a biofertilizer factory to be constructed. Concept notes for other countries being finalized.
| Number of hectares of improved | NIL
4.1.2 Financial Options for Enhancing SSM and SLM Including Opportunities for Private Sector Collaboration and Potential Financing Identified | Percent of bankable project prepared with project resources financed by private sector investment | NIL
4.1.3 Promotion of Innovation in Agricultural Systems, considering a gender approach | Regional Research Facility on New Climate Resilient Adaptation Technologies (RRF-NAT) is operational Number of new climate resilient adaptation technologies tested. Number of farmers that have benefitted from information provided by RRF-NAT | Regional PISLM RAC NAT Facility concluded an experiment on hot pepper production with preliminary findings from a 3-acre plot indicating a total harvest of 260 bags (20 lbs each) of hot pepper. Field performance varied across treatments. Notably, the most promising yields were observed in fields treated with half the recommended rate of synthetic fertilizer combined with compost. This suggests a potential for reducing input costs while maintaining or enhancing productivity through integrated soil fertility management. The housing structure for the BIOFLOC has been completed. |  |  | Biofloc operationalization delayed due to factors such as water access and unstable electricity
Outcome 5.1 Regional capacity development and training programme established | Percent persons trained in SSM, SLM and CMA methods and techniques from the participating countries that contribute to the development of components 1 to 4, disaggregated by gender.
Output 5.1 Capacity of Stakeholders strengthened to (i) undertake national soils surveys, (ii) apply climate resilient methods and approaches (iii) apply Risk Assessment and CC adaptation best practices for Agriculture | No. of technicians from Member States supporting the upgrading of national soils surveys. | None in this period
| No. of persons trained under the Train the- trainers programme including Agricultural Extension officers and other government officials | CSAC in country Training session held in Jamaica, Belize, St. Lucia in this period, 54 Males, 22 Females
| No. of farmers trained to support the implementation of the various Components of the project, in particular Components 2 to 4 | Not actioned yet |  |  | Delays in precursor activities
| No. of postgraduate scholarships awarded to young talents to study areas relevant to the issues/problems in SSM and SLM in Caribbean SIDS | Completed
Outcome 5.2. SLM/LDN Knowledge Management, Technical Assistance and Communication in SLM and SSM strengthened and enhanced | Knowledge products/materials produced and disseminated to stakeholders in the region. Social Learning Platform being used to network, share, collaborate and exchange ideas to solve problems. Indigenous Peoples Network established and used by Indigenous Peoples to strengthen Regional Networking
Output 5.2.1. Caribbean LDN and SLM Knowledge Hub established and operational | Caribbean LDN and SLM Knowledge Hub operational | The Hub is operational and material are being formatted for upload.
| Number of issues of the Caribbean Land-Soil Outlook 2030 published | 2 reports submitted to the countries for review. |  |  | A lack of data from countries severely hampered the rate of progress
Output 5.2.2. Regional Cooperation in SLM and SSM Encouraged and Facilitated | Number of persons in the database supporting the Caribbean SLM/LDN SIDSSIDS Cooperation Mechanism Number of Cooperation Assistance provided by the mechanism throughout the duration of the project | NIL
Outcome 5.3. Climate Resilient SLMand Regional LDN Strategy Mainstreamed/Integrated into Caribbean Community Regional Policy Frameworks, Decision Making Processes and into National Level planning processes | Number of Caribbean Community Regional Policy Frameworks, reviewed, amended and approved.
5.3.1. Review and Updating of the Caribbean Community Regional Policy Frameworks and Adoption by its Decision-making Processes | Number of Policy Instruments Reviewed, Updated and Approved Number of Joint Meeting of COTED for environment/sustainable development and agriculture convened | Project deliverables that are meant for regional participation were presented at the COTED Agriculture in October 2024 and COTED-Environment (POST COP Briefing) in February 2025
| Number of countries that update their national policies or legal frameworks to include SSM, SLM and climate resilience in line with the Caribbean Community Regional Policy Framework | Belize - National consultations are complete and Belize Naitonal Land Use Act submitted to the Cabinet
5.3.2. A Sub-regional Sustainable Soil Management (SSM) Framework Agreement Contributing to LDN and Strengthening Regional Efforts to Address Climate Change Established | No of Institution which sign the Framework agreement and participate actively in the Sub-regional Sustainable Soil Management (SSM) Framework Agreement | No meetings in this period
5.3.3. Building Synergies and Strengthening Cooperation Between SOILCARE Phase 1 and the SIDS Island Programme on Chemicals | The operational modalities for facilitating synergies and strengthen cooperation between SOILCARE Phase 1 and the SIDS Island Programme on chemicals | No further progress in this period
Outcome 5.4. Promotion of Investment and financing in SLM/SSM and climate resilience with Private and Public Sector | The Caribbean SIDS LDN Transformative Fund Mechanism is established and funded. | NIL
| Private and public investment mobilized which mainstream climate adaptation considerations | NIL
Output 5.4.1. Caribbean SIDS LDN Transformation Funding mechanism established and resources mobilised for climate resilient SSM/SLM | Caribbean SIDS LDN Transformation Funding mechanism established, resourced and operational | NIL |  |  | Delays at the Ministerial level
Outcome 5.5 An effective Gender Sensitive Monitoring and Evaluation Framework in Support of Project Implementation established | Project Monitoring System supports project delivery while following a Results Based Management approach
5.5.1. Monitoring and Evaluation Process for the Project executed in accordance with GEF Guidelines | An independent mid-term evaluation undertaken to inform results of project implementation | Mid Term review conducted and the results and recommendation were submitted to PISLM
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Moderately Satisfactory (MS) | Moderately Unsatisfactory (MU) |  | Moderately Satisfactory (MS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project has made significant progress with implementation of Components 1 & 5. Challenges stil exist because of limited capacity in project counteies with the digital/ GIS mapping which was overcome to some extent with the support of other locally trained officers from other project countries. This has resulted in the the maps prodiuced by the GSP being readied for uploading to the CARSIS & DSS. Only Haitis national soils survey is outstanding and it is hoped it wil commence in August. Works has started in two countries intervention sites and the procurement process is almost complete for the remaining countries including Haiti. we have exceeded the capacoty building targets and the gender activities will be completed as scheduled in 2025. All countries are engaged in activities and are making substantial contributions to achieving all project deliverables on time. There is high commitment to ensure project meets all objectivities by both Ministries and stakeholders | On-the-ground activities pertaining to components 2, 3 and 4 remain particularly delayed regarding the original project plan, and compared to the annual workplan, with little progress in this reporting period. Component 1, although also very delayed compared to the initial workplan, has progressed in the reporting period with a solid technical approach, with technical support from FAO, and the prospects of delivery by NTE remain good. Component 5 has shown good overall progress, in particular regarding outreach and policy aspects, although advances in this reporting period have been slow. The overall recommendation is still to strengthen implementation capacity through more targeted approaches that facilitate increasing implementation rate, and to intensify FAO technical backstopping to on-the-ground implementation. Coordination between stakeholders also needs to be strengthened for a faster as well as technically sound implementation. | Efforts to increase implementation rate during last year appear not to have suceeded, acording to the advances reported in this document. Components 2, 3 and 4 are still showing very limited progress in this reporting period. Since reduced capacity is reported as one of the main reasons causing delay, reinforced technical backstoping from FAO is suggested and offered, to strengthen execution capability at all levels and to support increased coordinaton between the stakeholders that enables, e.g., a faster production of technically sound documents and intervention plans, and their more agile implementation. Increased bidirectional communication between FAO and the Executing Agency will be essential to radically improve implementation rate, and urgent measures must be agreed in that regard. A request for no-cost extension is under development. It is essential that revised work plans be completed asap providing assurance that the lagging components will be fully delivered. | Comments | This is an ambitious and complex project. The recent mid term review confirms that the project is strategically relevant, coherent with ongoing interventions in the region, but it's not on track to achieve its objectives, particularly those referred to field activities (components 2-4). At the same time, signficant progress is seen under components 1 and 5, including very likely long term sustainability. Both PISLM and FAO continue to be committed to meet program commitements and are working on a plan to achieve these results, including a 2-year no-cost extension. The results from this program (Phase I), including the capacity built in PISLM and the participating countries, will be key to the implementation of SOILCARE Phase II, currently under review and due for CEO Endorsement by December 2025
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Significant progress has been achieved under Component 1 of the SOILCARE Phase 1 initiative. National-level soil sampling activities have been successfully undertaken across all participating countries, with the exception of Haiti, where operations are scheduled to begin by August 2025. In Guyana, sampling is nearly complete, with only a few sites pending due to a vehicular accident during field operations. All intervention site soil sampling and analysis have been completed. Laboratory equipment has been procured and distributed to all countries, except Haiti, due to ongoing social unrest. Building on the succesful completion of the training on Standard Operating Procedures (SOPs) and data interpretation which was conducted to ensure appropriate use of the new lab equipment, a SOC Training for heads of labs, Labs technicians, Agronomist, and Extensions Officers was successfully completed with over 26 participants from the 8 countries participating. Additionally, several technical assessments—including DPSIR Reports, Climate-Smart Agriculture (CSA) and Vulnerability Assessments, Land Capability Assessments, and CSA Guidelines—have been finalized and validated, with field implementation activities set to commence in the third quarter of 2025. With support form the Global Soil Partnership, five countries now have updatd soil information for many parameters, and importantly for organic carbon stocks. With Support from teh GSP, countries have been trained to create SOC sequestration maps with one being produced for Antigua and Barbuda. Institutional strengthening efforts have advanced significantly. The Caribbean Soil Support Group and the Sustainable Land and Soil Management Framework Agreement Group have been formally established and endorsed by Ministers responsible for the Environment. These bodies held their inaugural in person meeting in May 2024. The Caribbean Soil Laboratory Network (CarSoLan) has also been fully formulated and recognized by CARICOM Ministers. These bodies have completed their TOR for operations, meet frequently and are also providing support to ongoing regional soils and land management initiatives. They also participate in Global Soils activities. Capacity building and stakeholder engagement activities have seen strong participation. A total of 451 stakeholders (316 males and 123 females) were engaged through Climate-Smart Agriculture Compliant (C-SAC) and DPSIR Intervention Site Capacity Building workshops. In total, over 500 individuals were trained in areas including HNVI C-SAC, soils database management, CARSIS, Land Degradation Neutrality (LDN), the Soils Doctors program, and gender mainstreaming. A specific gender mainstreaming workshop was also conducted for SOILCARE staff.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Several challenges persist. The major challenge in the past 12 months is the issue of coordinating with local authorities to finalize thier plans for the intervention sites. The PMU places high regard for local input and authorization of activites before commencement but the lengthy Delays in shipping and clearing soil samples through Trinidadian customs have impacted timely analysis of samples from both national and intervention sites. This persist with lonbg waiting periods for the permits to be renewed. A regional lack of expertise in geo-statistics has delayed the creation of national soil maps necessary for the CARSIS system, hindering its operationalization. Furthermore, countries' limited technical capacity and scheduling conflicts between trainers and national programs have affected the implementation of in-person training activities. One challenge that must not be overlooked is the delay in funding for the initiation of the project. The final PRODOC was signed off in September 2021 and funds were only transferred to the PISLM in December 2021. This must be given due regard as it posed challenges in the mobilization of human resources from the Executing Entity and the National stakeholders. December to January are two months in which government officesare otherwise occupied and as such, without finances on hand to facilitate in-country launches and workshops, this led to a late start. The impacts of national disasters such as hurricanes on project sites affects implementation along with the limited number of input supppliers and capacity for installations of equipment available to complete procurement. The PMU continues to grapple with the social conflict still ongoing in Haiti which has affected the delivery of soil lab equipment and participation of technical officers in regional training sessions. Additionally, the lack of capacity within the countries and the difficulty of coordinating among all the Government stakeholders responsible for approving the intervention site plans has proved to be an ongoing issue that has caused severe dealys in starting the work in the sites.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | NO
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | YES. The activities that have commenced have been implemented in line with already existing mandates given to national authorities. The type of capacity building that have already been done within these departments are also in line with the priorities identified at the inception of the regional capacity building plan. 1. The project has successfully trained over 500 local officers in the area of soil sample methodologies which is a task that is continously needed especially in the agriculture industry. These officers are now equipped to teach farmers and other individulas how to obtain and store soil samples if needed for testing. 2. The project has equipped 7 out of 8 soil analytical labs with equipment to reach Tier1 of the GLOSOLAN standards, enabling them to conduct their own soil analysis to keep updating their national data and to enable land used to make immediate decisions on soil amednments and planting. 3. The PMU is building a strong relationship with communities and farmers that will foster greater acceptance and particiption in outscaling activities. This is already evident in Belize and Barbados.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | LOW
New environmental and social risks. | No new environmental and social risks identified in this period
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects)
Grievance Redress Mechanism (GRM) | The PMU to date has not received any grievances from any level of stakeholder. The PMU maintains that all work must be authorized by the governing authorities and through consultations with land users.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Environmental |  | Moderate | Yes | The participating countries are prone to Natural Disasters, including, inter alia, hurricanes and other tropical systems, flooding, as well as volcanoes and earthquakes, which if occur can pose a risk to achievement of the project outputs. In the case of hurricanes their intensity may be increasing. As a consequence significant damage can result to agriculture, as well as to fruit crops. A good example of this is the case of Grenada after hurricane Ivan in which Grenada’s most important commercial crop, nutmeg, was devastated in a few hours by the hurricane. Since the crop requires 7-8 years, little or no foreign exchange from this source would have been received for almost a decade. | The PMU has enacted a disaster response effort which will enable the PMU to track the impacts of natural disasters in interventions sites.Following the passage of Hurricane Beryl, the PMU directed its National Project Assistants to coordinate with local authorities to conduct a damage assessment with intervention sites.
2 | Social |  | Low | Yes | Active Participation of Indigenous Peoples | The PMU has put systems in place to practice the fundamentals of FPIC before engagement of indigenous communities.
3 | Economic |  | Low | Yes | Farmers resistant to transitioning to the adoption of climate-smart tools, methods and technologies and sustainable livelihood practices | All farmers targeted for interventions have been made aware of the intended interventions and how they will augment their activites.
4 | Partnership & Coordination |  | Low | Yes | Slow pace of Consideration of the Outputs by the relevant Caribbean Community Organs | The PMU has built a healthy relationship with key technical staff and maagers within relevant regional institutions to allow for more frequent engagements.
5 | Environmental |  | Moderate | Yes | Climate Variability and Climate Change | The PMU has requested support from the regional body, CIMH, in accessing early warning systems and reports.
6 | Safety & Security |  | Low | Yes | The Implications of COVID- 19 | The PMU continues to monitor the situation and activley consuders reports of this and other diseases, from countries.
7 | Economic |  | High | No | Cost of commodities/financial transactions | The PMU tries its best to schedule events involving travel, well in advance to secure better prices. For this reason, most training sessions are held in Trinidad where most flights terminate and where accomodation options are greater.
8 | Safety & Security |  | High | No | Social conflict in Haiti hindering the participation of Haitian delegates and project implementation | The FAO’s local office has been utilized to provide the necessary oversight to the project activities. Additionally, the local personnel have been provided with the resources to conduct the soil sample collection.
9 | Institutional |  | High | No | Low Capacity of national and regional agencies results in slow uptake of project activities | The PMU has engaged the PSC to reallocate funding to procure additional personnel to work on techical aspects of work in intervention sites
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Moderate | Substantial | Work planned in intervention sites cannot proceed without the necessary authorization by the national authorities. However, because of the time take for them to give feedback and approval, schedules are constantly being redone to accommodate and an agile approach has to be undertaken.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | a) The government of Belize has requested assistance under the project to update their Land Use Policy. This was presented at the 2nd Project Steering committee meeting. | 2nd December 2022 | The Regional Project Steering Committee
Components and cost | The PMU requested the move of 50,000USD from BL3210 (Capacity) to BL4201 (Procurement of Soil Lab Equipment) The PMU requested the move of 50,000USD from BL4207 (Reforestation Activity) to BL 1203 (National Assistant) toaddress the lack in capacity in Ministries to support the implementation of work in components 2 , 3 and 4. | 14th May 2024, Fourth session of the PSC | The Regional Project Steering Committee
Institutional and implementation arrangements
Financial management | a) In relation to the point mentioned above re Belize, at said meeting it was suggested that 50,000 USD under BL4209 allotted to Belize be reallocated to this activity. b) Utilization of funds from BL4702 to cover initial round of analysis of soil samples from target sites totalling approximately 8,000.00 USD. | 2nd December 2022 | The Regional Project Steering Committee
Implementation schedule
Executing Entity
Executing Entity Category
Minor project objective change
Safeguards
Risk analysis
Increase of GEF project financing up to 5%
Co-financing
Location of project activity | Haiti has changed its target site under Component 2 from ‘Lac Azeui of Fond Parisien’ to ‘Marion River Watershed’. Under Component 3 the site has changed from Rio Marion watershed to the Samana Watershed. St. Lucia – Component 2 site change from ‘Choiseul’ to ‘Saltibus Choiseul’; Component 3 changed from ‘Bois Den Jacmel’ to ‘Grand Riviere, Dennery’; Component 4 site change from ‘Cendre de Feu/Sarot Bexon’ to ‘Roseau, Quarter of Anse La Raye’. | 2nd December 2022 | The Regional Project Steering Committee
Other minor project amendment (define)
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Ministries of Environment and Agriculture in the participating countries | Cofinancing | Ministries have coordinated the holding of national workshops. The Government process of obtaining approvals for many activities has been slow and has caused delays.
Government Institutions | National Focal Points in the Participating Countries for SLM (UNCCD); SSM (Global Soil Partnership); Climate Change (UNFCCC); and GEF. | Cofinancing | Busy schedule and mandate of focal points have led to delays in some aspects of the project implementation.
NGOs | Food and Agriculture Organization of the United Nations | Implementing partner | FAO has assisted greatly with the creation of soil sampling designs, soil maps, training sessions and review of reports.
Others | Farmers organizations in the Participating countries | Strategic Partner | Many farmers have been engaged in validating the reccommendations for the intervention sites.
Others | Academia, in particular, the University of the West Indies, St. Augustine Campus, Trinidad and Tobago; the University of Guyana, Guyana; and the University of Belize, Belize. | Strategic Partner | Feedback from the UWI has been slow regarding the implementation of the RAC on NAT on the 25 acres facility. Analysis of soil samples has been delayed due to reduced capacity of the lab in light of regular scheduled classes.
Government Institutions | The PISLM High Level Ministerial Group | Cofinancing | The Ministers have given their full support to the project's objectives but feedback can sometimes be delayed which delays key activities.
IGOs | The Caribbean Community and its Organs (e.g., the Conference of the Heads of Government, Council on Trade and Economic Development (COTED), etc.). | Strategic Partner | The CARICOM Secretariat has been a valuable partner, helping to get the achievements of the project to the wider government spheres.

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | No
b. Improving women's participation and decision making | Yes | The PMU has made significant strides in ensuring female participation in regional and national capacity building initiatives.
c. generating socio-economic benefits or services for women | No
Any other good practices on gender | Yes | Gender equality is encouraged at every level and information on participation levels are recorded.

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level.
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far.
Communication strategy: Does the project have a communication strategy?
Please provide a brief overview of the communications successes and challenges this fiscal year.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits.
Please provide links to related website, social media account
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any.
Please indicate the Communication and/or knowledge management focal point's name and contact detais.

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. ALL intervention sites plans have been created through consultations with the community members. Final reccommenations have been presented to the community members for approval before commencing procurement processed. On the ground consultations were done with community members during their PMU's first site visits. In person sessions were conucted to present the reccommednations to the communities and the government stakeholders.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | Antigua y Barbuda - Min. Environment | In-kind | 800000 | 300316
Recipient Country Government | Barbados | In-kind | 722600 | 350000
Recipient Country Government | Belize | In-kind | 442600 | 220000
Recipient Country Government | Grenada - Min. Agriculture, Lands and Forestry | In-kind | 5000000 | 750000
Recipient Country Government | Guyana - Lands and Survey Commission | In-kind | 2968204 | 1491319
Recipient Country Government | Haiti - Min. Environment | In-kind | 6100000 | 3225000
Recipient Country Government | Jamaica - Ministry of Agriculture | In-kind | 800000 | 300000
Recipient Country Government | St. Lucia - Dept of Agriculture | In-kind | 787100 | 400676
Recipient Country Government | St. Lucia - Dept of Agriculture | In-kind | 200000 | 65240
Recipient Country Government | University of West Indies | In-kind | 4520000 | 200000
Recipient Country Government | PISLM | In-kind | 1500000 | 1000000
| FAO |  | 1657312
| FAO - Global Soil Partnership |  | 300000
Total |  | Total | 25797816 | 8302551
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.