GEF-7 REQUEST FOR ONE-STEP project endorsement/

APPROVAL

Project Type:

Type of Trust Fund:

part i: project information

| Project Title: Seventh Operational Phase of the GEF Small Grants Program in Ecuador |  |  |  |
| --- | --- | --- | --- |
| Country: | Ecuador | GEF Project ID: |  |
| GEF Agency: | UNDP | GEF Agency Project ID: | 6255 |
| Project Executing Entity: | UNOPS | Submission Date: | 03/01/2019 |
| GEF Focal Area: | Biodiversity | Expected Implementation Start | 06/01/2019 |
|  |  | Expected Completion Date | 05/31/2023 |
| Name of Parent Program |  | Parent Program ID: |  |

- Focal Area Elements

| ### Programming Directions | ### Focal Area Outcomes | ### Trust Fund | ### (in US$) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| BD 1-1: Mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors |  | GEF | 1,826,484 | 3,097,134 |
| Total project costs |  |  | 1,826,484 | 3,097,134 |

- Project description summary

| Project Objective: To enable community networks to build social, economic and ecological resilience through bio-enterprises in nine landscapes located in the coastal, highlands and Amazon region for global environmental benefits and sustainable development |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Component Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| Develop community bio-enterprise initiatives through capacity building, knowledge management and upscaling in resilient socio-ecological landscapes for sustainable development and global environmental benefits | TA | 1. Community bio-enterprise initiatives are strengthened in the targeted landscapes of four globally important ecosystems - Andean Paramo, Mangrove, Coastal dry forest, Tropical rainforest - with improved market access | 1.1 Community bio-enterprise initiatives practice biodiversity conservation and agroecological resource management in the nine targeted landscapes 1.2 Community bio-enterprise initiatives add value to agroecological crops and biodiversity conservation goods and services through the development of innovative products 1.3 Innovative financial mechanisms, like crowdfunding, strengthen bio-enterprises and engage new partners | GEFTF | 1,026,326 | 2,152,129 |
|  |  | 2. Multi-stakeholder bio-entrepreneurship networks established and operational for effective governance of selected landscapes and coordinated market access | 2.1 Multi-stakeholder bio-enterprise networks established and operational in the nine target landscapes 2.2 Bio-enterprise networks develop value chain strategies that promote and articulate biodiversity conservation and sustainable production practices across the nine target landscapes 2.3 Bio-enterprise networks implement value chain strategies to access new markets within and across landscapes and at regional and national levels | GEFTF | 715,676 | 945,005 |
| Subtotal |  |  |  |  | 1,742,002 | 3,097,134 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 84,482 | ----- |
| Total project costs |  |  |  |  | 1,826,484 | 3,097,134 |

- confirmed sources of Co-financing for the project by name and by type

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| CSO | Community organizations | In cash | Investment mobilized | 230,000 |
| CSO | Community organizations | In kind | Recurrent expenditures | 586,450 |
| GEF Agency | UNDP CO | In cash | Investment mobilized | 10,000 |
| GEF Agency | UNDP CO | In kind | Recurrent expenditures | 50,585 |
| Government | Ministry of Environment – Socio Bosque | In cash | Investment mobilized | 1,978,635 |
| Government | Ministry of Environment – Socio Bosque | In kind | Recurrent expenditures | 41,464 |
| Donor Agency | ICCA Consortium | In Cash | Investment mobilized | 200,000 |
| Total Co-financing |  |  |  | 3,097,134 |

- Trust Fund  Resources Requested by Agency,  Country, Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country | Focal Area | Programming of Funds | (in US$) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c) = a+b |
| UNDP | GEF TF | Ecuador | Biodiversity |  | 1,826,484 | 173,516 | 2,000,000 |
| Total GEF Resources |  |  |  |  | 1,826,484 | 173,516 | 2,000,000 |

E.1.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.1.

PPG  Amount requested by agency, Trust Fund,  country and the Programming  of funds

| GEF Agency | Trust Fund | Country | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total (c = a + b) |
| Total PPG Amount |  |  |  |  |  |  |  |

E.2. Does the project include a “non-grant” instrument?    No

F.     Project’s Target Contributions to GEF 7 Core Indicators

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (Million Hectares) | 189,268 |
| 2 | Marine protected areas created or under improved management for conservation and sustainable use (Million Hectares) | 2,637 |
| 3 | Area of land restored (Million Hectares) |  |
| 4 | Area of landscapes under improved practices (excluding protected areas) (Million Hectares) | 2,220 |
| 5 | Area of marine habitat under improved practices (excluding protected areas) (Million Hectares) |  |
|  | Total area under improved management (Million Hectares) | 194.125 |
| 6 | Greenhouse Gas Emissions Mitigated (Million metric tons of CO2e) |  |
| 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management |  |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (thousand metric tons) (Percent of fisheries, by volume) |  |
| 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (thousand metric tons of toxic chemicals reduced) |  |
| 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent gTEQ) |  |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 8,533 (3,413 m / 5,120 w) |

Project Taxonomy

Please see the GEF Taxonomy Worksheet provided in Annex G to find the most relevant keywords/topics/themes that best describe the project.

part ii:  project justification

1a. Project Description

- Global environmental and/or adaptation problems, root causes and barriers that need to be addressed (systems description)

From 2008 to 2012, according to the central government, an average of 65,880 hectares of forests were deforested annually. At a national level, there were 100 contaminated rivers and 1,200 mining concessions working without environmental permits, and 49% of local governments (GAD) had open-air garbage dumps. Ecuador´s economy is based on a linear, ‘take-make-waste’ model in which over 60 billion tons of natural resources are extracted per year, and over 13 billion tons of wastes are disposed into landfills, incinerators, and waterways.

In Ecuador, approximately 47% of the territory suffers from land degradation. The main causes are deforestation of fragile ecosystems for cultivation of new crops or pastures; excessive tillage of soils at planting or harvesting of products; use of fire for land clearing and grassland regeneration; overgrazing; planting on hillsides and slopes; intensive use of agrochemicals; deforestation in water recharge zones and river protection; and inadequate irrigation management.

The areas for production represent 8.7 million hectares: 45% on the Coast, 36% in the Sierra, and 19% in the rest of the country. Grasslands correspond to 57% of the national total, 15% to agricultural mosaics, 13% to annual crops, 11% to permanent crops (oriented to export).

Ecosystem descriptions and threats

  - Highland region - paramo

Bosque siempreverde montano alto y montano alto superior de páramo

The Paramo ecosystem is found from 3,000 to 4,500 meters above sea level (masl), from tree line to the highest rocky slopes and snow-caps. The paramos fulfil important natural, cultural and economic functions, providing multiple ecosystem services related to their ability to intercept, store and regulate surface and underground water flows. The ecosystem hosts about 5,000 different plant species. About 60% of these species are endemic, adapted to the ecosystem´s specific physio-chemical and climatic conditions, such as low atmospheric pressure, intense ultra-violet radiation, and the drying effects of wind. The vegetation consists of tussock grasses, ground rosettes, dwarf shrubs, cushion plants and conspicuous giant rosettes such as Espeletia sp and Puya.

The highland region is divided into two zones in the SGP Ecuador intervention strategy: the northern area that comprises the middle eastern part of the Cayambe – Coca National Park and the southern zone, adjacent to the Chimborazo National Park buffer zone and Cañar province. These regions comprise two very dynamic landscapes, with changes in coverage and land use caused primarily by rural households, monoculture activities and the recent interest of government in mining activities. The main problems of conservation and poverty in the ecosystem have been recognized for the past century, but only recently has there been an explosion of interest in this ecosystem in ecological and anthropological terms. Furthermore, a growing number of scientific studies suggest that the increase in human activities can significantly alter the hydrological behaviour of these ecosystems, directly affecting the water supply function.

In this area, government and local communities have prioritized conservation and sustainable use of water-generation strategies, due to its importance. According to government, the high Andean forests, paramos and wetlands that provide the resource and maintain the ecological flow of streams, rivers, aquifers and springs, are a priority, since they are the main sources for human consumption (including the main cities), irrigation and hydroelectric projects.

The paramos show a remarkable biodiversity at the scale of ecosystems thanks to three main factors: the equatorial location, the presence of the Andes mountain range and other minor mountain ranges, the existence of a perhumid Amazonian source and several cold and warm ocean currents off the coast. The people of the paramo, in many cases marginalized, very poor and lacking in alternatives, threaten their own survival by pushing the agricultural frontier much higher than what soil aptitude would advise.

The process of natural recovery of the paramos takes a long time, and repeated burning and grazing cause permanent long-term damage, making them more vulnerable than tropical forests, since the paramos can be easily adapted for farming and livestock with only the burning of above-ground biomass.

According to L'lnstitut de Recherche pour le Developpement, paramo soils are considered a "sponge" that enhances water retention and buffers the water flow downstream. However, new agricultural practices modify soil properties, altering infiltration and run-off regimes and disturbing the primary hydrological function of the paramos. Therefore, any degradation or inappropriate land use alters these soils with a negative effect on the water availability for a large population living downstream.

  - Coastal region

Ecuador is also characterized by a high diversity of marine and coastal ecosystems. In the country there are 24 of the 27 marine and coastal ecosystems recognized globally; these are: 12 coastal ecosystems (coastal wetlands, cliffs, dunes, beaches, mangroves, estuaries, rocky shores, barrier islands, intertidal flats, coastal plains, deltas and alluvial banks) and 12 marine ecosystems (bays, soft bottoms, platform hard bottoms, low rocky, low sandy areas, reefs, islands, outcrops, slopes, canyons, etc.).

    - Dry forest

Bosque seco pluvioestacional

In Ecuador, dry forests are found in the southwest of the provinces of Loja, Santa Elena, Guayas, Manabí and El Oro. There, the sustainable use of natural resources is promoted among communities, prioritizing the conservation of high forest biodiversity. Dry forest is part of the Tumbes-Chocó Magdalena hotspot, which extends from southern Panama in the Darién region, through the western foothills of the Andes mountain range of Colombia and Ecuador to the Tumbesian region of northern Peru. The Chocó-Ecuadorian Conservation Corridor also includes the western foothills of the Andes, which are part of the Tropical Andes hotspot. This vast region has been identified as one of the most important areas of the world for conservation due to its great biological diversity and the strong pressures it faces.

The flora and fauna of these forests have acquired certain physiological-adaptive characteristics that allowed them to survive extremes of temperature and aridity. Dwarf and branched shrubs, thickened leaves and thorny plants are adaptations to the harsh conditions of this ecoregion. This evolutionary pressure increases a well-recognized species endemism and this ecoregion is highly vulnerable to human intervention. Approximately 180 tree species have been classified, and it is estimated that about 19% of the region’s vegetation is endemic to western Ecuador.

This unique ecosystem is found nowhere in the world but southern Ecuador (87,000 ha.) and northern Peru. Important species include trees of the Moraceae family (Pseudolmedia), bignonaceas (Exarata chocoensis) and several species of Algarrobo (Prosopis fuliflora); Barba salvaje (Tillandsia usneoides); Barbasco (Jacquenia pubescens); Bototillo (Cochlospermum vitifolium); Cactus (Cereus sp.); and Ceibo (Ceiba trichistandra), etc., as well as medicinal products (Myroxylon peruiferum and Bursera graveolens), animal feed (Prosopis juliflora and Ceiba trichistandra); fruit (Malpighia emarginata), and for fishing (Piscidia carthagenensis).

106,000 people live in this ecosystem and depend directly on it for survival. The dry forest regulates the hydrological cycle for the coastal region. Dry forests are very fragile and have vanished from a huge portion of their original area, placing them among the world’s most endangered ecosystems.

    - Mangroves

Manglar

Mangroves are key ecosystems because they harbour great biodiversity. They are very peculiar ecosystems: the only forests that grow on saline soils and act as a natural barrier against the effects of climate change and natural disasters. They harbour great biodiversity, provide protection to the coast and store carbon. In addition, they are the area of ​​reproduction and feeding of many species of fish, molluscs and crustaceans of primary importance for nutrition and the economic wellbeing of local communities.

In the last four decades 56,396 hectares of mangrove have been lost in Ecuador. Until 2014, the MAE estimated that there were 157,004 hectares of mangrove in Cayapas, Muisne, Río Chone, Golfo de Guayaquil and Jambelí.

Over 70% of the coastal mangroves have been progressively eliminated through logging and shrimp farming promoted by the shrimp industry. On the coast, there has been an over harvest of the products provided by mangroves, including timber, firewood, fish, and crustaceans. To protect the mangroves, the Ministry of Environment (MAE) has implemented Socio Manglar (Mangrove Partner); this initiative encourages the conservation of these ecosystems. Currently, more than 23,000 hectares of mangrove are part of ¨Socio Manglar¨.

For the state, the challenge has been that it has not been possible to develop tourist clusters in the coastal strip, and the investment that is developed is basically residential real estate. Marine coastal protected areas still have little relevance as tourist destinations. There has been a lack of coherent proposals to promote sustainable community tourism for the coastal strip, as well as studies of acceptable carrying capacity on the beaches of the continental coast.

During SGP implementation in GEF5, two projects worked in the coastal region on the recovery of the mangrove crab (Ucides occidental) and conch (Anadara tuberculosa), with 11 communities and 105 families. Among the inhabitants of these communities, the care of the mangrove was promoted and accepted because it is part of their resource collection livelihood.

  - Amazon region

Bosque siempreverde de la penillanura del oeste de la Amazonía

Ecuador’s Amazon rainforest covers 30% of the country’s total land area (13,909 km2), making it the country’s largest bio-geographical region and one that has been characterized as “hyper-diverse”, where there are more than half of the known animal and plant species in Ecuador. In tropical moist forests there are multiple benefits for living beings, especially for humans. including food, medicines and even industrial products.

In this region live 245,014 people belonging to indigenous groups over an area of 1,569,000 hectares. The largest number of indigenous peoples and nationalities live in the Ecuadorian Amazon, cultures that possess knowledge and ancestral practices strongly linked to the jungle and its biodiversity. There are also large oil and mining interests and strong impacts produced by livestock, which have led to the loss of thousands of hectares of forests.

According to the National Strategy for Biodiversity, in the scenario estimated for 2020, the risk of deforestation rises in the zones of ancient colonization in the north and in the indigenous territories of the middle-Amazon (Achuar, Shiwiar and Kichwa) and south (Shuar and Saraguro).

It is also possible to recognize the Amazon region as a continuation of historical processes of land use conversion, both in the north, around the area of ​​oil influence near Lago Agrio-Coca-Shushufindi-Tarapoa, and in the Amazon South, around on the Gualaquiza – Macas - Puyo axis along the foothills of the Eastern Cordillera. At least 11 species of fish are threatened, seven Endangered and four Vulnerable, all of them important both to subsistence fishing and commercial fishing. Among the main threats to the conservation of fish in the Amazon region are: i) pollution of rivers by oil spills, by leaching chemicals used in monocultures and by discharging wastewater from local populations. In response to this problem, the MAE, through the Socio Bosque Program, conserves around 888,000 hectares of tropical rainforest benefiting about five thousand citizens with the economic incentives provided by this program for its maintenance.

On the other hand, the Ministry of Agriculture and Aquaculture (MAGAP), through the National Program of Participatory Technological Innovation and Agricultural Productivity (PITPPA from its Spanish acronym), plans to consolidate and diversify production of peasant family agriculture by implementing an agroecological proposal in the highlands and the Amazon.

Main threats

General threats to biodiversity in the Paramo, coastal dry forest/mangroves, and the Amazon forest are wholesale forest and grassland conversion to other uses, ecosystem fragmentation across the landscape, and generalized ecosystem degradation from unsustainable harvest of timber and non-timber forest products, overgrazing, maladaptive agricultural practices, and invasive alien species. While some threats are driven by development of large unsustainable commercial enterprises and unsound infrastructure development decisions, many others stem from the aggregate effects of more small-scale production activities that are defined by limited opportunities, incentives, knowledge, capacities and resources that could enable smallholder communities to adopt and implement sustainable production practices .

The primary cause of deforestation and land conversion in these ecosystems is land clearing for agriculture, forestry or aquaculture, including plantations of oil palm (coast and Amazon regions) and pine (Paramo), as well as shrimp farming (mangroves). Land clearing for livestock is also a driver of deforestation in the Amazon and the dry coastal forests but also, on a lesser scale, in the Paramo.

As farmers clear land for agriculture or other uses, forest and/or other patches of natural vegetation are left standing as islands in a sea of land uses that are generally incompatible with long-term conservation and landscape resilience goals. Forests become drier and hotter, and with nothing to break air flow, wind speeds accelerate leading to ideal conditions for the spread of fire. When used as a tool to clear biomass prior to planting, fire may escape the control of farmers and spread to nearby forest or grasslands, reducing valuable habitat for biodiversity, diminishing valuable ecosystem services, generating huge volumes of greenhouse gases and leading to permanent conversion of natural habitat to other uses.

Another driver of forest and grassland fragmentation is the ongoing subdivision of communal lands in the three regions, under the responsibility of the Communes to provide new lands to young landless families, as well as due to the growing land market in which the Communes are pressured to sell to private owners (dry forest/mangroves), and permit colonization and settlement (Amazon).

With the loss of biodiversity and degradation of ecosystem services, the social and ecological resilience of these landscapes is increasingly compromised. With growing climate change and the weather and climate variability delivered by El Niño, communities must manage their landscapes to increase their resilience to climate and other shocks and pressures.

The preferred solution is:

The GEF SGP Ecuador Country Program will tackle the root causes of biodiversity loss in three key biodiversity areas of Ecuador: Highlands (Paramo) north and south, Coastal region (dry forest/mangroves), and the Amazon (tropical forest).

In GEF-7, SGP Ecuador will continue to adapt and improve the innovative landscape planning and management approach developed in GEF 5 and 6 by supporting communities to establish and operate landscape-based bio-enterprises around sustainably produced, biodiversity-conserving Products with Territorial Identity (PITs, for Productos con Identidad Territorial in Spanish). While these products are currently being produced by communities in their respective landscapes as a result of previous SGP grants, the economic motivation to sustain biodiversity friendly production practices is weak, primarily due to obstacles constraining market access.  These barriers include issues of scale (sufficient volume of high-quality production to meet buyers’ requirements), value addition, access to financing, and enabling partnerships with private enterprises and government programs that can provide longer-term support.

The approach proposed here tackles biodiversity loss through grant support to implementation by communities and producers’ organizations of sustainable production initiatives for PITs in selected landscapes in collaboration with the Socio Bosque Program and the Ministry of Environment (discussed below under the Baseline).  These partners will provide technical assistance to help communities overcome obstacles to sustainable production and help in engaging new social and political actors. This joint partnership between SGP Ecuador, Socio Bosque and the Ministry of Environment will be structured around the creation or strengthening of community bio-enterprise initiatives and their conformation into interconnective networks known as bio-enterprises at landscape level (see below under Proposed Alternative Scenario for more detail).  These multi-stakeholder platforms will include all members of the PIT value chains, including producers, buyers, input, technical assistance and financial resource providers, and others with the aim of overcoming barriers to market access that limit the economic incentives for sustainable production.

Barriers

Under GEF-5 and GEF-6, significant steps were taken to enhance socio-ecological resilience in the landscapes of the Bio-Corridors for Living Well, including community bio-enterprise initiatives that supported comprehensive landscape strategies that joined ecological connectivity objectives with sustainable production and social cohesion and inclusion goals. Nevertheless, a number of barriers remain that make it difficult to successfully establish, strengthen and maintain bio-enterprises as a primary vehicle for achieving the goals and objectives of these landscape strategies.

- Promising community bio-enterprise initiatives do not yet have full capacities to define and implement viable production and management practices due to weak technical skills and unaccustomed practices

The decline in land and water productivity stems from land degradation, water logging and/or decline in water provision. To mitigate and reverse land degradation, smallholders need to practice an integrated approach to the management of soils, plant nutrients, water, and other inputs, particularly chemical inputs to avoid potential pollution.

Communities must develop the skills and knowledge required to apply agroecological principles to current farming systems and practice with the aim of maintaining or increasing productivity while conserving species and habitats that are important for ecological connectivity and biodiversity conservation, both foundations of landscape resilience. Agroforestry systems and low-input agricultural practices such as multi-cropping, polycultures, composting, fallowing, cover crops, and other soil conservation measures can raise yields through increased soil productivity and maintain them over longer periods, perhaps, even permanently, thereby reducing the need to clear new land for agriculture, as is the case under current systems.

Crop diversification provides farmers with a wider choice in the production of crops in a given area by expanding production related activities for different crops and bringing down the overall economic risk associated with potential crop loss. For example, in dryland areas crop diversification is practiced reducing the economic risk associated with failure of a single crop due to drought. Crop diversification can take place thanks to new governmental policies, market reforms, infrastructure development, government subsidies (e.g. through Socio Bosque), and certain other price-related support mechanisms. Higher profitability and stability in production can also induce crop diversification.

SGP has supported communities to develop systems for successful production practices that benefit the global environment, local sustainable development, and rural livelihoods. These include initiatives related to agroecological production, sustainable production of non-timber forest products, fisheries management, aquaculture, and alpaca breeding. To achieve economic development momentum in the market, these practices must be consolidated, replicated and scaled-up through broader adoption by larger numbers of smallholders and communities.

During GEF-5 and GEF-6, biodiversity conservation was directly linked to a change in production for the communities. A central focus was the development of Products with Territorial Identity (PIT) - products derived from biodiversity and agrobiodiversity that incorporated innovation and creativity from value-added processing so that they could be sold in local and regional markets. Revenue generated from the sales of PITs will provide the economic incentives to smallholders and communities to continue to apply and adapt practices that improve the sustainability of production systems.  To successfully market PITs, producers must have enough volumes of high-quality products to meet buyers’ requirements.

- Community groups lack the means and abilities to access new markets for their products.

During GEF-6, SGP supported communities in the different landscapes in the development of Products with Territorial Identity (PIT). Nevertheless, these initiatives encountered barriers to successful marketing for several reasons: little knowledge of urban consumers and their tastes and demands, lack of marketing skills, weaknesses in identifying private-sector partnerships, difficulties in achieving production at sufficient scale across landscapes, and an absence of value addition to their raw products.

In addition, some normative barriers include specific requirements for the commercialization of products from the Ministry of Public Health and the Ministry of Agriculture. In the case of perishables, this includes a sanitary registry and for non-perishables, the application of the Manual of Good Agricultural Practices. In both cases, small producers - given their economic capacities and production perspectives – often have substantial difficulties in complying. Inability to comply with these technical demands contributes to the abandonment of agricultural production, especially by the younger population, and further limits their capacities to create and operate profitable enterprises. At the same time, these low capacities further discourage community enterprises from identifying and developing new products or services that would further landscape resilience and global environmental goals.

In the landscapes where SGP has been supporting communities in developing and implementing resilience-enhancing strategies, communities and their organizations must have proven alternatives for the sustainable use of natural resources that allow them to generate income or achieve food security through innovative products with access to dynamic markets at different levels. Products with limited entry or access to new markets discourage producers from trying new sustainable practices or systems and dissuade new partners from joining the initiative.

The PIT strategy initiated in GEF-5 and further strengthened in GEF-6 has prioritized product value addition and learning about ways to overcome the barriers smallholders face to achieving market access. During GEF-7, the upscaling process conducted via bio-enterprises will ensure that biodiversity-related products meet national norms and regulations, since the SGP will collaborate with the Socio Bosque Program, which has already communicated regulations and norms to the direct beneficiaries of the project. Successful community enterprises will be the vehicles by which communities generate global environmental benefits through biodiversity conservation and sustainable use.

- Community groups lack the means and capacities to plan and coordinate their entrepreneurial activities for conservation and sustainable use of biodiversity among themselves and with other relevant stakeholders

Communities assume a major responsibility for the use and conservation of their landscape’s biodiversity. As a strategy for biodiversity conservation, communities need to create strategic alliances and practical partnerships that support their proposals for management of biodiversity for sustainable use and production.

Communities have formal and non-formal mechanisms for communal decision making, as well as local governance. However, these generally lack an explicit strategic vision for landscape resilience and sustainable development. During GEF-5 and GEF-6, SGP promoted the establishment of the Bio-corridor Working Groups (MTB in Spanish), focusing on the development and maintenance of production landscapes as biological corridors. This required a high degree of planning and governance within and between communities, as well as with other relevant stakeholders, based on an agreed strategic vision for landscape resilience and sustainable development, supported by an appropriate policy and incentive framework. This multi-stakeholder management approach has been crucial for communities to speak with one voice with governmental authorities and other interested parties and potential partners.

With central government recognition of the importance of green entrepreneurships in the landscapes based on incentives delivered directly to the stakeholders, it has become clear that community and inter-community coordination can be used to leverage greater economic benefits through scale economies associated with sustainable income generating activities. The ability of communities to collaborate across the landscape in developing complementary production and commercialization activities is crucial to achieving and sustaining biodiversity conservation impacts at the landscape and regional levels.

At the same time, central government institutions and Decentralized Autonomous Governments (GAD) - who must maintain complementary and collaborative relations in the implementation of public policy, aligned with the Development Plans and Zoning (PDOT) - are characterized by a low level of coordination and funding challenges that include weak capacities and high staff turnover in some governamental institutions. It is also important to mention that gender equity-supported activities tend to decline at this level, as technical staff lack the neccesary capacities to mainstream gender into local projects.

- Absence of incentives for private companies to partner with and support community bio-enterprise initiatives

It is difficult for community bio-enterprise initiatives in and of themselves to fully develop new opportunities for sustainable use of biodiversity or pursue other land-based investments at sufficient scale for successful income generation that motivate the adoption of production systems that support biodiversity conservation. Conventional partnerships between private companies and communities have shown a tendency to mismanage the distribution of resources and knowledge in favor of the first. These problems could well be mitigated by clearly identifying rights and obligations of both parties; nevertheless, communities and local networks do not generally have the capacities to adequately negotiate, implement or monitor fair trade contracts.

The SGP has sought to strengthen the production components of the initiatives it supports. Considering the legal framework agreements of the United Nations System and the United Nations Development Program (UNDP) in its links with the private sector, the SGP Ecuador Country Program signed agreements in 2005 with private companies such as CORPEI's Biocommerce Initiative, Ecuadorian Ecotourism Association-ASEC, Wong Foundation, Water Fund-FONAG, Kraft Initiative, and Deloitte & Touché. More recently, SGP has developed a crowdfunding platform – GreenCrowds - which, since 2015, has developed alliances with private sector entities to promote campaigns in their networks to generate new donations. Several model coworking spaces, including universities, social media, and entrepreneurship incubators, are supporting GreenCrowds: Working Up, Universidad de las Fuerzas Armadas/Innovativa, Consejo Empresarial para el Desarrollo Sostenible del Ecuador - CEMDES, Buen Trip, IMPAQTO, Ecuador, Tierra Incógnita, Media Lab UIO, Crisfe Foundation, and Alianza para el Emprendimiento e Innovación - AEI.

In recent years, a number of social actors and private sector entities have worked together to match communities with interested investors, facilitated by clarification of the rights of and obligations to communities and other stakeholders, and with more clearly defined incentive structures. Recent experience with social investing indicates that Ecuadorian entrepreneurs are increasingly inclined to support sustainable development initiatives, instead of investing in traditional assistance projects. Also, national legislation requires large enterprises to source at least 15% of their inventory from popular economy-related entrepreneurships, such as community or rural biodiversity products. This has generated interest of the private sector as well as motivation to welcome community ventures into their supply chains.

The multi-stakeholder landscape management methodology that SGP advocates and implements will provide significant ongoing monitoring of CBOs, as well as on-going evaluation. Some strategies to mitigate risks include the development of market research partnerships with universities; technical assistance to improve and maintain quality processes in production; multi-stakeholder dialogue with governmental parties, and funding exploratory activities.

- Baseline scenario and associated baseline projects

With the political change in 2017, the Ministry of Environment defined several strategies, including the National Biodiversity Plan, Reforestation and Restauration Plan, and National Protected Areas Program, and in 2018, it launched the "Reverdecer Ecuador” program. This program was established to promote conservation, sustainable cities, environmental education, forest management, land use planning, reforestation, and bio-economic strategies. This program seeks to address the country’s socio-environmental problems, to guarantee the rights of nature, and to ensure the living well (Sumak Kawsay) of current and future generations. There are seven key pieces to this program:

The development of biocommerce and green entrepreneurships has been present in the country through initiatives promoted by the public and private sectors, with at least 80 green entrepreneurships registered in the National Sustainable Biocommerce Program that have been supported by the GEF Small Grants Program and the National Socio Bosque Incentive Program, the funding mechanism operated by the SNAP Financial Sustainability Project and the National System of Protected Areas (SNAP) Support Program, all implemented by the Ministry of the Environment.

In March 2018, Reverdecer Ecuador was established in the National Development Plan "Toda una Vida". This initiative promotes citizen participation to guarantee the rational use of resources and the commitment to conserve forests and raise awareness about the negative impact of activities that degrade ecosystems and the expansion of the agricultural frontier.

During 2018, the Ministry of Environment focused its attention on promoting and articulating the development of the bio-economy in the country. It has signed several cooperation agreements with the Technical University of Loja (UTPL), the Alliance for Entrepreneurship and Innovation (AEI), Polytechnic School of the coastal region (ESPOL), among others to strengthen the entrepreneurship and innovation network in Ecuador. The aim has been to advance in the structuring of territorial clusters of entrepreneurship and innovation, as well as in the conformation of the first centre to promote sustainable businesses (bio-businesses), which will promote different initiatives in bio-economy in a systematic way and over the long term.

Based on these documents together with the national strategies already underway, the Ministry – through the SNAP - seeks to focus on the work of bio-entrepreneurships from a multi-stakeholder perspective. This process has resulted in a request for the SGP to join forces with the Socio Bosque Program, integrating its methodological multi-stakeholder and expenditure-approach experience into the country’s bio-commerce policy.

This methodology of articulating stakeholders, biodiversity conservation and bio-commerce within the landscape management approach will be executed in areas jointly selected by the Ministry of the Environment and SGP.  The Socio Bosque Program provides financial incentives to community groups for conservation agreements; these can be used as co-financing to SGP grants supporting the economic basis for motivating sustainable production of biodiversity.

GEF Small Grants Program - Ecuador

The Ecuador GEF Small Grants Program was established in 1994. During its 22 years of operation Ecuador’s SGP Country Program has funded 390 projects for a total of USD 26.84 million, of which USD 12.54 million has been GEF funding and USD 14.30 million in co-financing. These projects have addressed all GEF Focal Areas, with the majority of projects in the biodiversity focal area (263 projects). The program has adjusted its strategy overtime to reflect lessons learnt and to adapt to emerging issues and opportunities.

During GEF-5, the Ecuador SGP Country Program adopted an innovative landscape approach modeled on the UNDP ART initiative (Articulation of Territorial Networks for Sustainable Human Development) based on three elements: ecological connectivity; sustainability and resilience of production landscapes; and social solidarity partnerships. This was a strategically important step for the Country Program as it squares with Ecuador’s “Organic Code for Territorial Organization, Autonomy and Decentralization (COOTAD)”. COOTAD made political and administrative decentralization compulsory and devolved land use planning and decision-making regarding natural resource management to local (provincial, municipal and parish) government levels. Therefore, adopting the landscape approach strategically aligns SGP with the Government’s decentralization approach and ensures that SGP works with key decision-makers at both local and national levels responsible for land use planning and natural resource management, and thus those responsible for biodiversity conservation.

In GEF-5, SGP Ecuador developed, adapted and began to implement a participatory methodology (ART/UNDP) that coordinates priorities and activities with local governments, allowing them to link their local development programs with the strategic objectives of the SGP Country Program and community proposals, through Bio-corridor initiatives.

SGP Ecuador’s Management Strategy has shown very positive results during the implementation of GEF-5 and GEF-6. This was particularly highlighted during the GEF/SGP Upgraded Country Program (UCP) Global Workshop that took place in Quito, Ecuador (15-19 April 2018), where SGP Ecuador shared the results of the landscape approach in the Bio-corridors for Living well with the SGP Upgrading Country Programs from around the world.

The key innovation from GEF-5 was the shift from the traditional allocation of grants based on proposals submitted by individual organizations scattered across the country to a new system based on a landscape approach. Under the previous operation, even when the projects were located in prioritized areas, they were implemented by a single organization without major involvement of other neighboring groups. The new landscape approach was defined as “Bio-corridors for Living Well” and addressed this constraint by having the grant-receiving organizations negotiate with and include other organizations in the funding and implementation of the project with the aim of developing working relationships between them and achieving larger landscape level impacts in ecological connectivity, sustainable production, ecosystem resilience, etc.

This innovation is a clear example of how the SGP can overcome the inherent constraints associated with the scale of small grants and, by focusing on a limited geographic area and leveraging ecological and economic synergies among grant projects, can generate larger impacts with significant additional benefits in terms of community wellbeing.

During GEF-6, SGP enabled community organizations in Bio-corridors for Living Well to take collective action for adaptive landscape management for socio-ecological resilience. Community organizations have developed significant progress towards land use changes, biodiversity conservation strategies and social strengthening of organizations. The GEF-5 approaches to implementation were successful because they integrated community participation into landscape planning and management as a strategy to achieve Global Environmental Benefits while improving the beneficiary’s quality of life through sustainable production. In GEF-6, SGP Ecuador continued with the guiding principles of ecological connectivity, sustainable production landscapes, and Bio-corridor partnerships across the landscape.

Nevertheless, during GEF-6, to achieve scale across the landscape, activities carried out by community bio-enterprise initiatives needed to be implemented through joint projects that reflected the strategic objectives of establishing and maintaining a Bio-corridor. This also involved co-financing institutions, as GEF-6 continued with a multi-stakeholder approach that provided credibility and popular support to the landscape planning and management process and led to the heightened involvement and commitment of stakeholders in implementation.

During GEF-6, SGP Ecuador supported 270 community organizations who became involved in resilient socio-ecological landscapes for sustainable development and global environmental protection by implementing strategies and activities affecting landscape resilience. Ten geographically-defined Bio-corridors for Living Well were selected to increase and reinforce the initial impacts from GEF-5 initiatives in support of implementation of conservation strategies at community level for globally important ecosystems. This process was led by ten management committees responsible for participatory processes that oversaw the implementation of the projects in the ten selected landscapes.

During GEF-6, SGP strengthened ten farmers’ organization and 26 indigenous organizations linking 226 communities. At the same time, indigenous communities, farmers’ organizations and community organizations implemented their projects through their Management Committees and met quarterly in Bio-corridor multi-stakeholder platforms for discussion and decision-making regarding the development of Bio-corridor projects, providing indigenous and farming groups with a safe environment for sharing their concerns and problems. SGP Ecuador worked with the following indigenous communities and organizations in these territories:

Andean Region from the Quechua People: Asociación Regional de Soberanía Alimentaria del Territorio Kayambi, Fundación Kawsay, Grupo de Mujeres Mushuc Yuyay de la Unocc, Unión de Organizaciones Campesinas de San Juan, Kamach, Union de Comunidades Indígenas de Gonzales Suárez, Productores Agroecológicos el Buen Vivir de Pedro Moncayo, Sumak Pacha, Asociación de Campesinos Agroecológicos de Íntag, Asociación de Trabajadores Agrícolas la Esmeralda Chica Cebada Loma, Comuna Altar Curiacu de Cubilan, Comuna Caguanapamba, Asociación de Productores Agroecológicos Qhapaq Ñan, Asociación Artesanal Flor Andina, Comité de Gestión Ambiental Tambo-Burgay, Asociación  de Productores Agroecológicos Sumak Mikuna, Zhamuy (Zhud Ayllu Muyunti Mushuk Yuyaita Yanapak), Unión de Organizaciones Comunitarias y Sociales de Santa Isabel, Asociación de Productores Agropecuarios Yanuncay.

Amazon communities from the Kichua, Waorani and Shuar peoples: Alto Tena, Santo Domingo, Waysa Yaku, San José, Santa Rita, Wambula, Manduro Yaku, Shandia, Runashitu, Raya Yaku, Selva Viva, Amanecer Campesino, Runashito, Selva Viva, Rayayaku, Anwae, Tsatsayaku. AMWAE, Territorio Shuar Arutam.

Coastal Indigenous People:  Pueblo Manta

GEF-6 stakeholders and partnerships

During GEF-6 the SGP Country Program collaborated with 42 decentralized autonomous governments (GAD), eight Governmental Organizations (including the Ministries of Environment, Agriculture, and Tourism, among others), 11 universities, 12 NGOs and additional actors involved in this process. Through these meetings, more than USD 1,388,345 (cash and in-kind) were raised as counterpart resources, benefiting 270 communities and 511 families directly and indirectly from SGP initiatives.

During 2017, work began on strengthening, replicating, scaling up and consolidating good practices and lessons learned from GEF-5. During GEF-6 the co-financing achieved from Bio-corridor projects is USD 1,495,523.  There are other projects that have contributed to co-financing: ICCA/GSI (USD 50,000), UNDP (USD 66,000), COMDEKS (USD 65,000); funds for the earthquake emergency (USD 76,000). Co-financing reported till now is: USD 1,752,523. These organizations are SGP partners and support projects technically and operationally. They operate in all Bio-corridors.

At national level, a key strategy for SGP Ecuador has been to support the Global Initiative to Support Indigenous Peoples and Areas Conserved by Local Communities known as ICCA-GSI. This project was developed to broaden the range and quality of diverse governance types in recognizing ICCAs and achieving the Aichi 2020 targets. ICCA-GSI's objective is to improve the recognition and overall effectiveness for biodiversity conservation, sustainable livelihoods, and resilience to climate change of territories and areas conserved by indigenous peoples and local communities.

  - Ministry of Environment (MAE)

The Ministry of Environment (MAE) was a primary partner supporting Bio-corridor projects in strengthening ecological connectivity.  In GEF-5, the Ministry contributed USD 651,084 and in GEF-6, USD 557,440 along with stand-alone financing of three Bio-corridor projects and three mainstreaming projects (participatory mapping for Bio-corridors and development of Products with Territorial Identity). MAE has also been a member of the SGP National Steering Committee and provided significant support to the implementation and sustainability of the GEF-6 projects, as they have been involved in project approvals as well as in the evaluation and monitoring processes.

In August 2018, the central government decided, as a strategy to improve optimization in the use of state resources, to fuse the Ministry of Environment with the Water Secretariat (SENAGUA), transforming it into the Ministry of Environment and Water. It is expected during GEF-7 that this fusion will bring coherence between the implementation of biodiversity programs with water conservation policies and projects.

  - Support to the National Protected Areas System – PASNAP/MAE

The Program to Support National Protected Areas (PASNAP/MAE) aims to strengthen prioritized National Protected Areas by incorporating regional and local stakeholders into its management. The PASNAP/MAE’s mission is to ensure efficient environmental management that guarantees a harmonic relationship between the country’s economic, social, and environmental strategies, and the sustainable utilization of the country’s strategic natural resources to achieve Living Well.

In GEF-5, PASNAP/MAE and SGP Ecuador signed an inter-institutional cooperation agreement for implementation of the connectivity management policy for conservation. The Ministry of Environment awarded SGP Ecuador financial and technical resources to implement selected projects in geographical landscapes of common concern. This step shaped PASNAP/MAE into a strategic partner for SGP Ecuador, with a key focus on biodiversity conservation.

During GEF-6, PASNAP/MAE financed six SGP projects, as described above: three Bio-corridors and three mainstreaming projects that focus on restoration, recovery, and articulation of remaining prioritized landscapes in Ecuador. This partnership has strengthened the connectivity approach in the Bio-corridors by producing landscape mapping and cartographic information in GEF-5 and GEF-6.

  - Socio Bosque Program/MAE

The Government of Ecuador, in compliance with the National Development Plan, established a goal of 50% reduction in the deforestation rate. The main objective of Socio Bosque, a program that has been in operation since 2008, is the conservation of native forests and paramos. Socio Bosque provides economic incentives to peasants and indigenous communities who voluntarily commit themselves to the conservation and protection of their native forests, paramos, or other native vegetation. After initial socialization, consultation, and confirmation of their nationality, the owners sign a conservation agreement with the Ministry of Environment (MAE) for a duration of 20 years, after which the Ministry transfers an economic incentive for each hectare to the owners.

This incentive program gives owners the possibility of a permanent source of revenue. The delivery of this incentive is conditional, based on the protection and conservation of forests. This means that owners receive the incentive once they have complied with the monitoring conditions that are determined by the agreement with the Ministry of Environment.

Between September 2008 and December 2015, Socio Bosque registered 2,775 agreements, benefiting more than 187,000 people from grassroots organizations and indigenous communities such as Aí Cofán, Andwa, Awá, Achuar, Chachi, Kichwa, Sekopai, Shuar, Shiwiar, Sapará, Waorani; Afro-Ecuadorian people, montubios, and mestizos throughout continental Ecuador, conserving approximately 1,500,000 hectares of forests, paramos, and mangroves. Total investment since its creation reaches $55.6 million. In 2015, non-reimbursable external cooperation and the Ecuadorian private sector contributions totalled 23% of the annual investment of the programme.

- Proposed alternative scenario with a description of outcomes and components of the project

In Ecuador, communities have generally seen conservation as running counter to the economic well-being of people living from natural resource commercialization. Since 2012, SGP has responded to this perception with its innovative approach of integrating biodiversity conservation, sustainable production, and social strengthening around the establishment and maintenance of resilient landscapes - Bio-corridors. Stakeholders are motivated to sustain their efforts through increased income from the marketing and sale of Products with Territorial Identity that also produce global environmental benefits.

The development of Products with Territorial Identity (PITs) is a process involving many producers in initiatives that demonstrate creativity, innovation and the potential to produce in ways that continue to sustain ecosystem services and biodiversity. Nevertheless, these initiatives find barriers to commercialization resulting from weak marketing strategies and policies by producers’ organizations; municipal ordinances that do not recognize agroecological/agroforestry for their positive effects on the global environment; weak knowledge of the supply of PITs by urban consumers; weaknesses in the production at scale in order to sufficiently meet demand in a consistent and predictable way; and low quality of brand development, among other factors.

SGP Ecuador’s experience with support to sustainable production initiatives has shown that they can generate income based on the conservation and sustainable use of species, habitats and ecosystems. Nonetheless, to achieve sustainability of production practices and systems that generate global environmental benefits, communities should have sufficient business planning and management skills to offer sufficient volume of innovative products of high quality to local, regional and national markets.

During GEF-6, SGP Ecuador supported producers’ organizations to build their capacities to meet market requirements as well as helped consolidate previously successful interventions that promoted green business development.  This benefited from the introduction of the concept of Products with Territorial Identity through a comprehensive new strategy called "empowerment methodology” using the experience of the NGO In Terris/Talent Management to enhance the PITs and their commercial and ecological sustainability within the framework of the Bio-corridors for Living Well.

This methodology ensures the development of capacities such as entrepreneurial skills, development and operation of contact networks, and the design of business models that guarantee effective commercialization in local, national and even international markets. Capacity building of entrepreneurs includes five areas: financial/legal, entrepreneurial skills, business, networking and emotional. With SGP Ecuador support, this methodology was adopted for continued development of the Bio-corridors for Living Well and has shown that grassroots communities engage more effectively and efficiently in biodiversity conservation if sustainable production and biodiversity conservation is an integral component of a resilient landscape. This concept transforms individual communities across a defined landscape into physical networks that collectively become and act as bio-enterprises. This innovation is a result of the experience of GEF-6.

Bio-enterprises in GEF-7

In short, the bio-enterprise concept combines both strategy and method to achieve global environmental benefits by providing sufficient economic incentives for producers to adopt sustainable production practices/systems. The economic incentives are provided by markets for goods produced through conservation and sustainable use of biodiversity and ecosystem services. Access to emerging markets for these kinds of products is difficult for individual smallholders given the scale of their production systems, their weak abilities to assume risk, and the demands by buyers for consistency in volume and quality. The landscape level bio-enterprise is aimed at bringing together multiple producers in specific value chains with other stakeholders, including buyers, government agricultural experts, NGOs, input providers, and others. These multi-stakeholder bio-enterprises are able to organize and support production of PITs that enhances landscape level socio-ecological resilience and global environmental benefits - sustained over time by producers motivated by the incentive of sufficient income generation.

| Bio-enterprise concept |  |  |
| --- | --- | --- |
| Method | Strategy | SGP proposal |
|  | Specific actions/techniques taken to achieve the proposed intervention goals related to the sustainable development of communities | SGP´s project outputs are designed to achieve successful bio-enterprises in each landscape |
| Successive steps based on a landscape strategy to support communities in rural areas generating global environmental benefits | They seek to change the determinants/factors that affect local sustainable development while accomplishing global environmental benefits | The proposal is based on the fact that people's quality of life will be improved through their participation in effective bio-enterprises |
| The bio-enterprise methodology is built upon SGP experience and the diverse roles taken by the different stakeholders | The activities carried out by the communities with the support of SGP in selected landscapes hinge on the design to create/strengthen a bio-enterprise |  |

The project proposed here pursues a suite of outputs related to bio-enterprise establishment and operations, with a central focus on biodiversity conservation and the aim of enabling community networks to build social, economic and ecological resilience in nine landscapes located in the coastal, highlands and Amazon region through bio-enterprises for global environmental benefits and sustainable development.

Areas of intervention

During GEF-6, the SGP Country Program and the Ministry of Environment (MAE/PASNAP) generated maps with information on land use and vegetative cover in Bio-corridors. These indicated the activities carried out during GEF-5 to identify the proposed long-term impacts of SGP support in each Bio-corridor. Building on GEF-5 and GEF-6 outputs and activities, SGP will work in accordance with the articulation/coordination strategy of the Ministry of Environment, in collaboration with the Socio Bosque Project (SBP) and Program of Support to the National System of Protected Areas (PASNAP in Spanish).

During consultations in the planning stage for the project proposed here, SGP Ecuador worked closely with the Socio Bosque program to define the key activities for replication and upscaling based on the results achieved in GEF-6; these would include components of conservation and integration with the policies and programs of the Ministry of Environment. At the same time, SGP Ecuador aims to leverage financial support from important institutions and stakeholders at national and landscape levels, where working together will be crucial with the support of the Ministry of Environment (MAE), as the government agency for conservation policy.

The MAE (through PASNAP/SBP) and the SGP identified the landscapes and areas for support in GEF-7 guided by the successful outcomes of previous SGP Operational Phases in Bio-corridors, the GEF-7 guidelines for biodiversity (core indicator 1.1), and the Convention on Biological Diversity (CBD) for the adoption of measures that prevent or minimize the risk of considerable reduction or loss of biological diversity, among other sources. As well, the pragmatic approach to be applied in this project of conserving biological diversity through sustainable production for market by landscape level bio-enterprises requires substantial investments. These are expected to generate considerable economic and social benefits. Indeed, the premise of this project is that these will provide substantial motivation to producers to adopt and apply new biodiversity and ecosystem friendly production practices into the foreseeable future. This proposal follows national guidelines in the National Development Plan (Plan Toda una Vida) and the Inter-ministerial Environmental Agenda.

Nine landscapes were carefully chosen based on an analysis of the areas that overlap the Bio-corridors for Living Well (SGP GEF-5, GEF-6), the National System of Protected Areas (SNAP), and communities as well as individual conservation areas of the Socio Bosque Project, with special emphasis on areas where the landscape bio-enterprise strategy will have a positive impact for conservation and sustainable development. This new strategy promotes maintenance of the natural forest of Ecuador by a) protecting it from land use changes such as the expansion of the agricultural frontier or other human pressures that reduce habitat and populations of key species or result in land degradation; and b) simultaneously presenting livelihood options for forest dependent peoples. Another variable considered was the existence of potential bio-enterprises and consolidated areas providing a framework for success in conservation projects and sustainable development.

Nine maps were developed, identifying key project areas according to their biodiversity importance (hotspots), presence of bio-enterprises, and proximity to protected areas (Bio-corridor landscape approach), where focused support could prove beneficial for local development and maintenance of the biodiversity of these globally significant landscapes.

- In the Highlands, the SGP Ecuador Country Program will prioritize bio-enterprises in the buffer zones of Cayambe-Coca National Park, the north Andes region and the north-east area of the Chimborazo National Park buffer zone.

- In the Coastal region, the SGP Country Program will prioritize bio-enterprises in the buffer zones of Santa Elena province area, next to the Chongon-Colonche Bio-corridor, as well as within the Chongon-Colonche conservation area itself.

- In the Amazon region, the SGP Country Program will prioritize bio-enterprises in the buffer zones of the Sumaco - Napo - Galeras National Park region and the north-east zone of the Yasuni, working directly with the Waorani communities.

The selected areas are as follow:

| Landscape | Partners (Socio Bosque) | SNAP | SGP Ecuador | Total Area (hectares) |
| --- | --- | --- | --- | --- |
| Cayambe - Zuleta | Zuleta, Gallo Rumi | Cayambe-Coca | Bio-corridor Cayambe-Coca | 13,917 |
| Chimborazo | San Rafael de Chuquipogio, Pulingui San Pablo, la Silveria, Casaiche Arenal, Chorrera mirador alto, Ganquis Cuquiiloma; (Cañar: cooperativa San Andres de Malal) | Buffer zone Chimborazo | Bio-corridor Chimborazo | 10,288 |
| Condor Chuquiragua Cañari | Cañari people | Buffer zone of Sangay National Park | Cañar – Alpacas, agroecology and food products | 7,350 |
| Chongon - Colonche | Salanguillo, Sinchal, Barcelona, Febres Cordero, Dos Mangas, Loma Alta, Olón, Las Balsas | National Park Machalilla | Chongón Colonche Bio-corridor (GEF-6) | 46,757 |
| Jipijapa | Sancán Cantagallo | Bosque Protector Sancán Cantagallo | Portoviejo Bio-corridor (GEF-6) | 2,256 |
| Choco - Esmeraldas | Comuna Playa de Oro, Centro Chachi Tsejpi, Centro Chachi San Miguel, Comuna Chispero, Centro Chachi Jeyambi, San Miguel Negro | Cotacachi - Cayapas |  | 20,582 |
| Jima - CPSHA | Jima, CPSHA | Tambillo, buffer zone Quimi, El Cóndor |  | 13,890 |
| Sumaco – Yaku Samay | Pucunu Chico, Avila Viejo, Guacamayos, Rucullacta, Wamani | Sumaco Napo-Galeras | Yaku Samay (GEF-5 Bio-corridor) | 34,170 |
| Waorani | Waorani communities | Yasuni | Akllak Sacha - GEF-5 Bio-corridor | 42,695 |

The main concept under which the SGP will work is the consolidation, replication and upscaling of results from GEF-6, particularly those involving collective action for adaptive landscape management for socio-ecological resilience.  Consolidation considers strengthening involvement of the most representative stakeholders in the landscape.  Upscaling will occur through the organization of multi-stakeholder, landscape level bio-enterprises around particular value chains for products (PITs) that conserve biodiversity and ecosystem services within a landscape resilience strategy. Community organizations have developed significant progress as a result of SGP support in GEF-6, and SGP will continue strengthening their capacities to lead the process.

Outcomes and Outputs

To comprehensively achieve the project objective and outcomes, in accordance with GEF-7 programming directions, SGP works under the bio-enterprise methodology with a multi-stakeholder approach in the selected areas.

| GEF-7 programming directions | Component of the project | Project Outcomes |
| --- | --- | --- |
| Ecosystem restoration that reduces the causes of decline and improves basic functions of the bionetworks | Develop community bio-enterprise initiatives through capacity building, knowledge management and upscaling in resilient socio-ecological landscapes for sustainable development and global environmental benefits | Community bio-enterprise initiatives are strengthened in the targeted landscapes of four globally important ecosystems - Andean Paramo, Mangrove, Coastal dry forest, Tropical rainforest - with improved market access |
| Ecological restoration that enhances native habitats, sustains ecosystem resilience, and conserves biodiversity |  | Multi-stakeholder bio-entrepreneurship networks established and operational for effective governance of selected landscapes and coordinated market access |

Outcome 1: Community bio-enterprise initiatives are strengthened in the targeted landscapes of four globally important ecosystems - Andean Paramo, Mangrove, Coastal dry forest, Tropical rainforest - with improved market access

This new operational phase is expected to maintain - in conjunction with the Socio Bosque Program and PASNAP/MAE - an area under community management strategies for conservation of about 191,905 hectares linked to community participation in the Socio Bosque Program and PASNAP/MAE protected areas. The strengthening of bio-enterprises will focus on local priorities such as food security, income generation, and the development of social solidarity partnerships. The project’s emphasis on multi-stakeholder partnerships around these bio-enterprises will explicitly facilitate development of cross-cutting projects to upscale successful SGP-supported technologies, practices or systems identified from previous phases of the Ecuador SGP Country Program that strengthen the resilience of socio-ecological landscapes such as soil conservation practices, agroecology-agroforestry for coffee and cacao, CC mitigation via alternative energy efficiency technologies and short commercialization circuits related to sustainable use of trees-outside forest areas.

Three Outputs will contribute to achieving this Outcome:

- Output 1.1 Community bio-enterprise initiatives promote improved agroecological land management practices and conservation in targeted landscapes

- Output 1.2. Community bio-enterprise initiatives conserve and add value to biodiversity resources through the development of innovative products

- Output 1.3. Innovative financial mechanisms, like crowdfunding, strengthen community bio-enterprise initiatives and engage new partners

Output 1.1 Community bio-enterprise initiatives promote improved agroecological land management practices and conservation in targeted landscapes

The main strategy for the SGP Ecuador - GEF-7 is to support community bio-enterprise initiatives that reduce habitat fragmentation, enhance sustainability of agroecosystems, and address the identified barriers to biodiversity conservation and sustainable use in each landscape through partnerships within a multi-stakeholder platform. This strategy involves civil society organizations, public institutions, academic institutions, CBOs and CSOs, the private sector and local governments who come together to develop and implement a landscape management strategy that prioritizes socio-ecological resilience based on global environmental benefits generated through socio-economic incentives to producers and community groups.

For GEF-7, sustainability of agroecological production through Community-Based Natural Resources Management strategies will be an essential criterion in selecting the products on which the larger scale bio-enterprises will be established and operationalized. These strategies will be developed and implemented with the support and collaboration of the Socio Bosque Program or with new donors interested in investing in sustainable agro-ecosystem management practices and production systems. Traditional knowledge of agroecosystem production and management systems will be an important source for identification and development of innovation processes. Practices and systems may include agroforestry systems, improved grazing systems, cut-and-carry livestock feeding, multi-cropping, composting, green manures, cultivation of underutilized crops important to crop genetic resource conservation, contour farming and soil conservation measures (bunds, gully plugs, gabions, etc.) and other low-input agricultural practices.

The following traditional but declining species of Andean crops will be promoted: nasturtiums, quinoa, melloco, oca, beans, several varieties of potatoes and medicinal plants. This will generate benefits to local communities by enhancing food security and improving nutrition through crop diversification and increased revenue through improved market access for agricultural products, particularly underutilized crops. With ongoing technical support to sustainable harvesting, communities can derive tangible benefits from the services provided by forests (e.g. firewood, timber, oil, food, resins) without exhausting the ecosystem. The diversification of production benefits families by providing employment and income generating opportunities for youth and women. Increased vegetative cover generates multiple environmental benefits: stabilization of watersheds, carbon sequestration, soil conservation, habitat for wildlife, improve moisture retention and microclimates. The community agreements for native forest conservation originating in the Community Based Natural Resources Management strategies have the potential to prevent the expansion of the agricultural frontier, which is one of the most serious threats to native forests and biodiversity in Ecuador.

Forest landscape restoration or reforestation and agroforestry initiatives will emphasize increasing tree cover in production landscapes. These would include those initiatives that generate income through agricultural production, such as fruits and nuts, vegetables, cocoa, coffee, or cinnamon. In the landscapes of the mountains and coast, the SGP Country Program will support strengthening and increasing the areas of agroforestry cultivation of coffee, rosewood on the coast, and several agricultural products related to prevention of degradation of arable land. In the Amazon SGP will support communities in sustainable management of Chambira palm (Astrocaryum chambira) for the production of handicrafts, in addition to sustainable forest management systems.

Other sustainable production practices and systems that will be promoted also include artisanal fishing and shellfish harvesting in mangroves, which have been tested in previous Operational Phases and are ready for broader dissemination and adoption. Fish pools operated sustainably by communities in the Amazon landscape will also be supported based on native fish, particularly the cachama species (Piaractus brachypomun).

The basis for this support is the projects carried out during GEF-6 that produced these results:

- Coast Region (seven projects) implemented agroforestry system, agroecological production, artisanal fishery (black shell and blue crab - Callinectes sapidus), and aquaculture (chame - Dormitator latifronts).

- Amazon region (five projects) implemented agroforestry farms (chakras) with new aquaculture practices (native recovery species, cachama - Piractus brachypomus).

In GEF-6, SGP Ecuador initiated implementation of a project to support Indigenous and Community Conservation Areas (ICCA) whose objective was the self-strengthening of existing or potential ICCAs and the promotion of their recognition at local and national levels regarding a broad vision incorporating well-being, conservation, sustainable livelihoods and rights. The project provided funding to indigenous peoples and local communities to identify eight to ten "emblematic" ICCAs, two in each of the SGP working landscapes in Ecuador. The lands identified possess the characteristics of ICCAs or have important potential to evolve as such. Therefore, during GEF-7 this work will be continued and strengthened, and SGP Ecuador will promote bio-enterprise projects regarding natural resources use and conservation in ICCAs. Community elders will be encouraged to transfer traditional knowledge to younger people as part of SGP support to ICCAs.  With the support of SGP, the ICCA project will carry out workshops on “Strategic support to territories and areas conserved by indigenous peoples and local communities” based on collective and nature rights.

Through implementation of this output at least 2,500 hectares of agricultural land will be used sustainably and productively through implementation of Community-Based Natural Resources Management strategies developed to optimize the sustainable use of biodiversity related products through a bio-enterprise approach.

Activities include:

    - Communities in the landscape adopt new agroecological and agroforestry practices to optimize ecosystem function and conserve biodiversity on farm and in the overall landscape while producing products for market with a bio-enterprise perspective.

    - Indigenous knowledge is recognized and encouraged as a source of participatory innovation development for natural resource conservation across the landscape.

    - At least two marine species are managed sustainably by local coastal communities using environmentally friendly practices to improve mangrove conservation areas.

    - Fish pools are operated sustainably by communities in the Amazon landscape using native fish, particularly the cachama species (Piaractus brachypomun)

Output 1.2. Community bio-enterprise initiatives conserve and add value to biodiversity resources through the development of innovative products

Community bio-enterprise initiatives supported under Output 1.1, above, will produce a variety of goods and services that need to be transformed under Output 1.2 through value addition to meet market demand in terms of volume and quality.  The products to be supported with SGP and co-financing resources have been produced in quantities of variable sizes during previous GEF Operational Phases and with increasing quality and have been assessed as viable candidates for upscaling through landscape level bio-enterprises.

While the raw materials are being produced or harvested using methods, practices and systems that promote the sustainability of ecosystem services and biodiversity, the economic incentive to continue these practices and systems lies with the revenues generated by the sale of goods and services produced by the community and producers’ groups involved.  To maximize the revenues obtained by their sale, community bio-enterprise initiatives must learn to add value to the raw materials they produce.

This will require training and capacity development for different producers’ and community groups across the landscapes to understand market demand, basic business principles and business planning, legal and sanitary regulations, processing, preservation, packaging, branding and other aspects. For example, strengthening of “alpaquero” value addition might include organizational capacity building, exchanges of experiences among producers, improving the quality of alpaca clothing and marketing and branding.

Viable products vetted through production (trialing, replication) with added value over previous SGP phases include:

- Food products with added value: quinoa and amaranth noodles (gluten free), coffee, chocolate; bakery products (achira bread – from rhizomes of Canna edulis), oca cookie (gluten free); native Andean tubers (wide variety of potatoes and others), mashua yogurt; and chame (fish - Dormitator latifrons); “agroecological baskets” (seasonal variety of products delivered on an agreed schedule, similar to Community Supported Agriculture in the US and Europe); cinnamon products

- Handicrafts and clothing: alpaca garments, bamboo products (Guadua angustifolia) – furniture, kitchenware, housing material); chambira (Astrocaryum chambira) fiber for handicrafts

Products, whose community-based production is well tested from previous phases, but which have experienced less value addition, will be supported in piloting or trialing new value-addition methods or practices.  These include:

- Mangrove crab (Ucides occidentalis) and Black shell (Pustulose Ark - Anadara tuberculosa);

- Cachama (Colossoma macropomum) – fish species from the Amazon

- Wild and domestic honey from a variety of different pollinators

For those products with less experience of value addition, longer-term strategies will be developed by bio-enterprises to broaden their markets, including possible gastronomic development with local/national chefs and limited local supply contracts.

SGP Ecuador will strengthen communities’ and family’s capacities to develop and implement ecotourism activities with a microbusiness perspective. Ecotourism has the potential to help in establishing links between different communities in a landscape, for example, by creating a local market for sustainably produced agricultural products and handicrafts. Individual ecotourism initiatives can be linked in wider networks to increase the “supply” of ecotourism services with the aim of prolonging the average ecotourist stay in country.

Over the last two GEF Operational Phases, SGP Ecuador has developed close collaborative relationships with universities, NGOs, government technical institutes and others to channel their expertise and resources to help community groups address the challenges of sustainable production, including product system improvement, new production techniques, effective and efficient business management, understanding national norms and standards, etc. Communities in the selected landscapes will receive technical support for packaging, labelling designs and marketing strategies from these partners.  These partners will also be instrumental in providing youth and women in communities with capacities to produce adequate volumes of high-quality conservation-compatible products, add value, and introduce them to market. This includes capacities to plan and manage land use coherent with the conservation objectives of protected areas and biological corridors, as well as business management skills and abilities.

As a result of this output at least 16 innovative products will receive value-addition in preparation for market access and sale.

Activities include:

    - Community groups producing food products learn appropriate value addition methods and practices, including understanding the relevant legal and sanitary regulations, business planning and management, processing, preservation and packaging, branding, and other aspects.

    - Community groups producing handicrafts and clothing learn appropriate value addition methods and practices, including understanding the relevant legal regulations, business planning and management, processing and packaging, branding, and other aspects.

    - Community groups harvesting Mangrove crab (Ucides occidentalis) and Black shell (Anadara tuberculosa) learn basic food preparation and preservation techniques, are linked to the wider gastronomic and culinary community and receive simple business planning and management training.

    - Community groups harvesting cachama fish learn basic food preparation and preservation techniques, are linked to the wider gastronomic and culinary community and receive simple business planning and management training, including in regard to catch and cook fish tourism.

    - Community groups developing ecotourism initiatives learn hospitality skills (including awareness raising regarding biodiversity, ecosystem services, etc.), business planning and management, and relationship building with local providers of sustainably produced goods and services.

    - Universities, NGOs and government institutes establish collaborative relationships with distinct community bio-enterprise initiatives to improve production and value-addition methods, practices and systems.

Output 1.3. Innovative financial mechanisms, like crowdfunding, strengthen community bio-enterprise initiatives and engage new partners

SGP and the co-financing partners in this project are only initial investors in community bio-enterprise initiatives. To sustain the new and innovative practices adopted by communities as a result of their implementation of community bio-enterprise initiatives will require continuous access to sufficient capital to re-invest in biodiversity friendly production, particularly in adapting periodically to dynamic environments of social, economic and ecological change. Most community bio-enterprise initiatives are perceived as too risky for standard banks and other financial institutions, so they are dependent over the short term on more innovative instruments and mechanisms. This risk will decline over time due to the growth in community capacities, experience and organizational and business expertise, when they will have a more viable profile for access to production credit.  The financial mechanism proposed here – crowdfunding - is a first step in leveraging greater and more sustained funding, as well as developing partnerships that will benefit community producers strategically.

Crowdfunding lets any individual contribute to the financing of a project. It was created to fill the gap when banks stopped financing small businesses during the recent worldwide recession. Crowdfunding is a medium in which projects are funded through private contributions from credit cards or bank accounts. Crowdfunding works to fund ideas, initiatives, and projects that are technically viable, but that lack funds for development.

Nonetheless, crowdfunding is not simply a mechanism to raise funds, but rather exists as well to launch products to the market, measure audience interest, and create an initial support community. The collected money is a by-product of the company’s success in finding an initial audience for their offer. In other words, crowdfunding offers a boost of initial validation that the entrepreneur can use to start in taking steps towards the next stage of growth.

To take advantage of these opportunities, SGP has been implementing a digital platform – GreenCrowds - since 2015 for the collaborative funding (crowdfunding) of community bio-enterprise initiatives focused on generating global environmental benefits by improving the socio-economic status of local communities through innovation in production practices.

The activities funded via crowdfunding to date effectively show how they contribute to biodiversity conservation.  SGP has considerable experience in funding successful community bio-enterprise initiatives and the capacity to promote projects for alternative financing. A primary outcome of this project will be the upscaling of GreenCrowds to include the MAE/PASNAP communities under Socio Bosque. At the same time, the private sector as well as social groups interested in joining this process will become members of this community, helping GreenCrowds to become self-sustainable over time. GreenCrowds works as an alternative finance service for small-scale initiatives and other enterprises, while capitalizing on SGP’s knowledge and expertise and creating shortcuts to reach new markets.

This Output will support sustainable community entrepreneurships by building their capabilities to engage and sustain new partnerships as steps towards greater financial and commercial viability. This Output will improve the skills and competencies of selected community groups to prepare them to take advantage of crowdfunding instruments. These community groups will learn how to market their initiatives as investments or attract donors to become potential crowdfunding partners, learn monitoring and reporting methods and other essential skills to attracting and maintaining productive partnerships.  At the same time, SGP will support the development and implementation of crowdfunding campaigns to interest and engage potential donors and investors.

Activities include:

    - Selection and preparation of selected community bio-enterprise initiatives for participation in crowdfunding campaigns

    - Training of selected community groups in monitoring, reporting, marketing and other relevant aspects

    - Preparation and implementation of crowdfunding campaigns, including marketing campaigns, communication strategies, and monitoring and evaluation

Outcome 2: Multi-stakeholder bio-entrepreneurship networks established and operational in the target landscapes for landscape governance and coordinated market access

During GEF 5 and 6, SGP Ecuador supported the formation of multi-stakeholder Landscape Working Groups comprised of local CSOs and government authorities, NGOs, and others, whose overall objective was the management and governance of their socio-ecological landscapes. These groups participated in the development of landscape management strategies aimed at encouraging behavior and production practices and systems that would enhance resilience to ecological and economic shocks and pressures. These strategies thus functioned as broad programming frameworks for community bio-enterprise initiatives that were financed by SGP and co-financiers.

These Working Groups have been significant in their abilities to bring disparate stakeholders together to discuss long-term trends in socio-ecological resilience, relating their economic production systems to the conservation of biodiversity and optimization of ecosystem services through sustainable land management. These Groups have slowly built consensus around the need to innovate production practices and systems to achieve both higher productivity and greater sustainability.  The innovations proposed by community groups during GEF 5 and 6 reflect this. Community implementation of initiatives has strengthened their technical, analytical and organizational capacities, while producing a growing set of innovative products.

To achieve positive behavioral change, it’s necessary to reinforce the links between implementation of biodiversity friendly production practices and the economic incentives required to sustain them over time. While community groups have become more adept at generating biodiversity friendly products, access to markets has been difficult given the need to meet consumer demand at the scale, timeliness and with the quality required. At the same time, demand for some biodiversity friendly products needs to be stimulated through marketing campaigns highlighting their environmental benefits, as well as their health, economic, lifestyle and other advantages.

Different landscapes tend to produce different products that are specific to the ecological and social conditions of that landscape. These products can be branded and marketed as Products with Territorial Identity (PITs) if the different producers in the landscape adhere to a common set of production, processing and marketing standards. To achieve acceptance of and compliance with these standards, multiple producers need to cooperate. This is especially true if producers hope to reach the scale, timeliness and quality that the market demands, and in particular in the context of biodiversity conservation and optimization of ecosystem services.

As such, this Outcome will build on the experience, structure and best practice of the landscape working groups to support the establishment and operations of landscape level bio-enterprises for the coordinated production, marketing and sale of Products of Territorial Identify (PITs).  Three Outputs will contribute to achieving this Outcome:

  - Multi-stakeholder bio-enterprise networks established and operational in the nine target landscapes

  - Bio-enterprise networks develop value chain strategies that promote and articulate biodiversity conservation and sustainable production practices across the nine target landscapes

  - Bio-enterprise networks implement value chain strategies to access new markets within and across landscapes and at regional and national levels

Output 2.1: Multi-stakeholder bio-enterprise networks established and/or strengthened in selected landscapes

Under this Output, the SGP Country Program will support emerging networks of community groups producing prospective PITs in the selected landscapes together with the landscape working groups from GEF 5 and 6 to form bio-enterprises to which all stakeholders in the PIT value chains will be invited to participate. Bio-enterprises will bring together producers, buyers, input providers, technical assistance workers, potential credit providers, and others to coordinate production, processing, marketing and sale of innovative, biodiversity friendly products.

Multi-stakeholder bio-enterprises will ensure that community priorities are considered by local governments, national institutions, and universities, and that this is an effective mechanism to bring together stakeholders from throughout the landscape to support biodiversity conservation, agroecological production for sustainable livelihoods, and direct participation of indigenous and peasant organizations with a high involvement of women and young people. Bio-enterprises will be instrumental in formulating, implementing and adapting landscape management strategies for socio-ecological resilience.

A key feature of this approach is the identification of common objectives at the local level, considering ecological, economic and social aspects, which are then specified in local plans (PDOT) through the different government levels. This ensures that SGP support is aligned with the needs, interests and aspirations of GAD and social organizations.

In bio-enterprise meetings, different stakeholders and their proposals are considered. The prospect of financial support to stakeholder proposals motivates the different groups to participate in discussing and addressing common socioenvironmental concerns and interests. The MAE/PASNAP Socio Bosque Program will also act as a crucial partner to involve new players and stakeholders.

To achieve this output, it is vital that the stakeholders are committed to work in coordination, responsibility and convergence. Differences in their strengths, weaknesses, opportunities and threats need to be considered and addressed through targeted capacity building to avoid imbalances in participation and partnerships within the bio-enterprise.

At the end of GEF-6, the SGP, along with the Ministry of Environment (MAE/PASNAP), generated maps with information on land use and vegetative cover in the selected landscapes (Bio-corridors). Maps of each Bio-corridor were produced identifying the achievements of communities supported by SGP and partners as well as the replication, consolidation and scaling up initiatives of GEF-6. These maps support the analysis of core areas and corridors comprising ecological connectivity. With these maps, landscape working groups and now bio-enterprises can prioritize and evaluate land management practices and conservation in the targeted landscapes.

At the same time, the maps have served to support analysis of the impacts and achievements accomplished through the support from other actors in the landscapes. This has allowed stakeholders to reach agreements on key points of the SGP Ecuador proposal in GEF 7. The key institutions are the GADs, as well as state institutions such as the Ministry of Agriculture and Livestock, Ministry of Environment, higher education institutions, and the different organizations that are present in the area. Their involvement in the landscape working groups and bio-enterprises is vital for the development of the communities because they can provide continuity to the activities of the project until they become sustainable.

This Output will produce:

- Nine multi-stakeholder bio-enterprises in the selected landscapes that are representative of all stakeholders in the selected PIT value chains with special emphasis on gender equality and participation of youth.

- Nine sets of maps with information on land use, biodiversity, vegetative coverage and other factors that identify critical areas for conservation and sustainable use initiatives to be integrated into the bio-enterprises

Activities include:

    - Surveys and mapping of all potential stakeholders in landscapes and PIT value chains

    - Organization of nine bio-enterprises around specific PITs and analysis of capacities

    - Legal establishment of bio-enterprises

    - Capacity development of organizational skills, PIT value chains, structures, value addition and flows, etc.

    - Participatory mapping of land use, biodiversity, etc., in the nine landscapes and identification of potential GEF 7 initiatives

Output 2.2. Bio-enterprise networks develop biodiversity friendly value chain strategies to access markets to the scale, timeliness and quality standards required

Each bio-enterprise will develop a value chain development strategy for a selected landscape PIT. By involving all stakeholders in the value chain, the bio-enterprise will increase cooperation and partnership development among the different actors, increase the potential for investment and co-investment in production, processing and marketing, and build the capacities of producers and community groups to innovate biodiversity friendly products with less risk.

Each bio-enterprise will target the commercial sustainability of its biodiversity products by developing a strategy that may include the strengthening of business planning capacities, improving business models, analysis of production chains, and marketing and distribution circuits, market studies, links to other actors (private sector, universities, GAD, community based organizations external to selected landscapes, international cooperation, etc.) and implementation of novel mechanisms (competitions, exchanges of experiences, unconventional marketing, crowdfunding, etc.), quality improvement, and protocolization in production to standardize quality, image improvement, and packaging.

Each strategy will reflect the different degrees of experience of the different community groups in the landscapes with some strategies more sophisticated than others in terms of specific needs in relation to production, processing or marketing.

Youth and women in communities will be particularly targeted in strategy development to build their capacities to produce adequate volumes of high-quality conservation-compatible products, add value, and introduce them to market. This implies capacities to plan and manage land use that is coherent with the conservation objectives of protected areas and ecological connectivity, as well as business management skills and abilities.

This output will also help to increase Denomination of Origin Processes for PITs, build producer-consumer relationships through new local markets, and augment the interest of private companies to link with communities to operationalize their Corporate Social Responsibility. This process will generate knowledge, provide technical assistance and share good practices in private sector-led skill development.

Strategy development overall will be guided by a bio-enterprise support team, who will provide expert training and technical assistance in market access and identifying new networks. The methodology implemented by the technical team considers production improvement, new productions techniques, effective and efficient business management, national norms and standards, design of marketing strategies, promotion of products in new markets and social media, quality improvement and production, application of quality control knowledge, and market diversification at the local and national level.

To ensure full participation in strategy development, stakeholders will receive initial training in sustainable management of products with value added, improve production and processing techniques, business development and management and the understanding of market demands, quality standards and marketing techniques.  Other topics might include landscape management planning, environmental law, biodiversity conservation, sustainable land use, collective rights, socio-environmental conflict resolution, gender or other issues. Other stakeholders from NGOs and Government will be invited to participate in capacity building processes.

This output will guide communities to other linked training processes to manage their sustainable production landscapes and soil management by adopting Sustainable Land Management (SLM) practices, included in the landscape management strategy. For its implementation, SGP - MAE/Socio Bosque have determined several bio-enterprises that share these principles and are ready to strengthen their capacities based on the PIT methodology from GEF 6. At the same time, training programs will be designed and implemented within the scope of the bio-enterprise methodology to improve leadership capacities for youth and women.

This Output will produce nine bio-enterprise value chain strategies corresponding to the selected target landscapes, as well as strengthen the capacities of the community groups and other stakeholders in the bio-enterprises to understand and develop PIT value chains.

Activities include:

    - Nine workshops (one per bio-enterprise network) where SGP/GEF will support the efforts to strengthen existing weaknesses in the supply-chain approach, specifically by identifying critical points in the process;

    - Meetings with government and major actors from across the supply chain to achieve deeper collaboration, coordination, and understanding;

    - Capacity building programs during bio-enterprise strategy development to promote a shared-responsibility agenda regarding sustainable use of natural resources.

    - Specific gender-appropriate training and technical assistance to women and youth to participate in bio-enterprises;

    - One national workshop/contest identify initiatives for the development of alternative markets with the support of national stakeholders and MAE/PASNAP Socio Bosque Program.

    - One strategic project is implemented for the four landscapes selected that will coordinate multi-stakeholder partnership articulation and bio-enterprise strategy.

Output 2.3. Bio-enterprise networks implement value chain strategies to access new markets within and across landscapes and at a regional and national level.

Bio-enterprise stakeholders will define and execute a plan for execution of their PIT value chain strategies. This will include participatory identification of specific community bio-enterprise initiatives to manage biodiversity, land and other resources in the landscape that produce global environmental benefits as well as produce increased income. These community-based initiatives will form part of value chain development and will include development of partnerships with other bio-enterprise stakeholders and others, to reduce risk from uncertainty from lack of investment, hesitant purchasing commitments by prospective buyers, weak input supply chains, etc. Other initiatives may address bio-enterprise goals at a broader level, bringing together various community groups in a particular landscape or around a specific PIT to achieve a larger strategic objective or economies of scale in training, purchasing, marketing, or technical assistance.

Those private businesses, who are stakeholders in the bio-enterprises, will be encouraged by SGP and UNDP to enter into formal contractual relationships with producers. Companies may wish to train community organizations to ensure supply and purchase of raw materials, provide initial capital as credit or improve value addition prior to marketing. SGP Ecuador will also work with the private sector to mobilize cash financing to co-finance programs and projects as investors, especially with those companies that promote green activities as social responsibility strategies. The link with the private sector has been strengthened by SGP through the GreenCrowds platform, since the private sector is an important ally to generate contributions from employees and/or from corporate social responsibility strategies.

This Output will produce nine bio-enterprise action plans, community-based initiatives in support of value chain development, contractual agreements between community groups and other bio-enterprise stakeholders, private sector co-financing and lessons learned from the experiences by bio-enterprises of value chain development.

Activities include:

    - Workshops to produce bio-enterprise action plans, including community-based proposals

    - Partnership meetings between private sector entities and producers and community groups

    - Investment promotion meetings with private sector entities

    - Monitoring and evaluation of value chain strategy implementation and systematization of the different experiences for lessons learned and potential policy dialogues

- Alignment with GEF focal area and/or impact program strategies

The project proposed here is in full conformity with the policy for upgrading of SGP Country Programs as first described in GEF/C.36/4 Small Grants Program Execution Arrangements and Upgrading Policy for GEF-5 and then in GEF/C.46/13 GEF Small Grants Program: Implementation Arrangements for GEF-6, approved by GEF Council in Cancun. The outcomes of the project proposed are fully aligned with the SGP Strategic Directions for GEF 7 found on pages 144-146 of GEF/R.7/19, GEF Programming Directions, approved by GEF Council in April 2018. This GEF SGP Upgrading Country Program will continue to follow the SGP’s Operational Guidelines to ensure compliance with longstanding best practice and GEF policy for the SGP.

The document is also in agreement with the four-year Framework of Program Priorities for the Seventh Replenishment Period (2018-2022) of the GEF Trust Fund (Decision CBD/COP/DEC/XIII/21). This Framework includes specific program priorities to be addressed by the GEF-7 Biodiversity Focal Area investments and other associated GEF programming to harness opportunities for synergy in implementing related multilateral environmental agreements as well as the 2030 Agenda for Sustainable Development and its Sustainable Development Goals, in particular the goal 15.

Collectively, these investments seek to deliver impact at scale by addressing key underlying drivers of biodiversity loss as well as direct drivers/pressures while responding to the biodiversity mainstreaming agenda of COP 13 and the most challenging elements of the Strategic Plan for Biodiversity, 2011-2020.

This project will support the Aichi goals, SDGs and the strategies defined by the Ecuadorian government through the Ministry of Environment, as well as the implementation of the GEF-7 Four-year Framework through the Biodiversity Focal Area investments and other integrated programming, particularly the Impact Programs on Food Systems, Land Use, and Restoration, and Sustainable Forest Management (SFM). Landscape-scale interventions based on comprehensive land use planning (agroecology and agroforestry) will be supported by this project to foster a transformational change in food systems and land use that is more environmentally sustainable.

  - Indigenous people

SGP Ecuador has worked closely with indigenous communities and peasant organizations from the Andean coast and Amazon region. Indigenous and peasant communities play a significant role in biodiversity conservation, rural development, food production, and poverty eradication. They work as guardians and protectors of their ancestral territories. These social organizations work towards food sovereignty, the defense of biodiversity and the recovery of ancestral knowledge as priorities, using the development and implementation of associative projects as important mechanisms. As part of the innovation of Products with Territorial Identity and agroecological production, they held dialogues, meetings, and multiple events for the recovery of native seeds, the recovery of ancestral knowledge regarding land management, and the conservation of Pachamama.

- Strategic support to territories and areas conserved by indigenous peoples and local communities

SGP Ecuador prioritizes its work with indigenous and rural community organizations. During GEF-6 this approach was strengthened, especially in the territories and areas conserved by the ‘indigenous peoples and local communities (ICCA) project. During GEF-7, this will continue with an ICCA strategic project that considers several outcomes:  creating an ICCA working group in the country, design the peer review process and submit candidates for inclusion in international registries. This implies the adaptation and application of appropriate methodologies for the Free and Informed Prior Consent (CPLI in Spanish) to register and design culturally appropriate mechanisms for the effective and efficient monitoring of the ICCA.

During GEF-6 - from November 2016 to December 2018 - and within the framework of the GSI project, the SGP Country Program sought to consolidate the ICCA proposal with the understanding that the ICCA Consortium is a space that articulates local communities and indigenous peoples in processes of recuperation of knowledge and defense of their territories in alliances with a wide range of social organizations and civil society, with a long-term vision that would guarantee sustainability and scale up of the work done in the Bio-corridors (OP6), strengthening strategic support to the territories and areas conserved by indigenous peoples and local communities in Ecuador.

- Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF and co-financing

SGP/GEF-7 proposal contributes to the long-term solution of collective action and adaptive management by community organizations of important landscapes in the four selected regions for social, economic, and ecological resilience. This proposal is linked to the Aichi goals, Sustainable Development Goals, Convention on Biological Diversity, National Development Plan, and the National Biodiversity Plan, thus providing an integral and comprehensive strategy for a scenario where the selected initiatives attain their goals, while achieving global benefits related primarily to biodiversity conservation and sustainable land management, but which also may affect climate change adaptation and integrated water resources management.

Funding will also be available for initiatives to build the organizational capacities of specific community groups as well as landscape level organizations to plan and manage complex initiatives and test and evaluate and disseminate community level innovations. These results will heavily impact the development of commercial and production activities in the territory, especially where the SGP allocates funds and promotes its methodology for articulation by landscape actors.

Moreover, SGP and other social and governmental actors will work together toward a joint strategy to include bio-enterprise products, based on an analysis to complement and enhance current activities carried out by the Ministry of Environment (MAE) through its Socio Bosque program. At the same time, the SGP strategic grant modality to upscale proven technologies, systems or practices based on knowledge gained from analysis of community innovations from past experiences during previous phases of the SGP Ecuador Country Program, will benefit not only initial consultation projects, but also new communitarian initiatives that will arise during the execution phase.

Without an SGP/GEF intervention, the communities’ part of the Socio Bosque initiative will continue to work under the same methodology, nonetheless, it will require more resources and time during which more biodiversity will be lost. At the same time, the proven experience of the SGP with territorial products could be the missing link necessary to reach new markets and distribution options for the communitarian productive initiatives.

Despite the agreements reached and GEF-5 achievements, local community participation is still insufficiently robust, and community organizations remain weak or underrepresented in zones under the threat of biodiversity loss, especially where vulnerabilities are at their peak due to human intervention or extractive politics. Multi-stakeholder groups—working around the bio-enterprises—will be key to maintaining the current biodiversity remnants and will include representatives of civil society and other actors that could potentially become part of the conservation and bio-enterprise process, either as beneficiaries or counterparts.

- Global environmental benefits (GEFTF)

Global environmental benefits (GEB) will be in the biodiversity focal area based on the programs included for each of the program’s components. These will result from the synergistic implementation of community-based landscape management initiatives proposed here over the short term, added to the long-term impact of governmental work in support of the Socio Bosque Program and its incentive program.

Given the nature of SGP – community driven proposals generated and approved and funded during implementation of the Project proposed here - it is impossible to define with precision or certainty the kinds and numbers of grant projects yet to be identified by communities and local actors.  Nonetheless, it is anticipated that at least two projects per each of the four territories selected in conjunction with the MAE will be funded. The numbers of grant projects are yet to be confirmed as products of landscape strategies and will be revised and agreed upon by the multi-stakeholder landscape management groups, MAE and the SGP; and confirmed with approval of grant projects by the National Steering Committee. The SGP secretariat will closely monitor and report on these targets throughout the life of the project.

Aichi goals

A central feature of this project is the development and implementation of sustainable land and resource management strategies at a local and territorial level. This procedure is based on an escalation and replication principle with the SGP taking into consideration its experience and articulation methodology to incorporate these concepts to new territories with regards to the MAE policy to focus efforts for conservation. The small grant projects financed by the project proposed here — will achieve global environmental benefits because of the synergistic effects of activities that increase communities’ governance, technical capacities and skills that produce livelihood benefits. This also strengthens the activities for conservation already carried out by the communities that are part of the Socio Bosque Program.

This project will contribute to all strategic Aichi goals, specifically to the targets and elements listed below:

- Target 2: SGP will contribute to local-level poverty eradication strategies by developing and implementing local and landscape sustainable and resource management strategies linking bio-enterprise projects with poverty reduction.

- Target 3: Working together with the beneficiaries of the Socio Bosque incentive program, SGP ensures that new organisations that are not part of these program could eventually join or maintain similar conservation strategies and monitoring conditions.

- Target 5: SGP will support sustainable production practices that help conserve terrestrial (including forests), freshwater and coastal/marine habitats and avoid ecosystem fragmentation and connect places.

- Target 7: SGP will support communities in these endeavours and will promote the use of native species in aquaculture and forestry community projects. It will also support early detection and eradication of invasive alien species, also contributing to Target 9.

- Target 13: SGP will support communities to maintain the genetic diversity of key species important for agriculture according to national and international conventions and regulation and help indigenous and rural communities keep their ancestral practices.

- Target 14: SGP will support communities to maintain key ecosystem services within their territories in the selected landscapes and seascapes, particularly those of forests.

- Target 15: SGP will support communities to sustainably use their forest biodiversity products (sustainable livelihoods) while maintaining and, where possible, enhancing carbon stocks.

The contribution of SGP to these targets will be addressed through bio-enterprise projects approved and implemented in alignment with landscape outcomes for biodiversity conservation and sustainable management. While an initial estimation of the global benefits can be achieved based on experience, more precise quantification of proposed targets will take place during the initial assessment and design of each project based on community priorities - with the direct involvement of landscape stakeholders and under the guidance of the Ministry of Environment and the SGP National Steering Committee.

SGP will scale up and replicate best practice within the project execution period in the selected landscapes for GEF-7 based on extensive experience during GEF-6 and previous phases. Broad strategic directions will include:

- Sustainable land management: Strategy of SLM implemented at the local level, with local or communitarian certifications. During GEF-7, this will be achieved through Community-Based Natural Resources Management as a strategy for enhancing conservation outcomes while improving rural livelihoods.

- Diversification of crop and livestock systems: Based on land use, agroforestry, agroecology, and cultural appropriation. This result seeks to deliver more product (food and other agricultural goods) per unit of resource, whilst preventing damage to natural resources and ecosystem services that underpin human health and wellbeing, both now and, in the future.

- Restoration of degraded production landscapes: As incentives for changes in land use or maintaining conservation of key ecosystems: to achieve this goal, during GEF-7, the SGP assist communities in the landscape to structure a comprehensive set of opportunities at landscape level and specify areas for investment in different activities (such as agriculture, forestry, livestock, mining, tourism, and others).

- Innovativeness, sustainability and potential for scaling up.

Innovativeness - A key innovation in the Ecuador SGP Country Program has been the shift from the traditional allocation of grants based on proposals submitted by individual organizations scattered across the country to a new system based on a landscape approach. Under previous operations, although projects were in prioritized areas, they were implemented by a single organization without major involvement of neighboring communities. A landscape approach addresses this constraint by having a single grant recipient organization that negotiates with and includes other organizations in funding and implementation with the aim of developing working relationships between them and achieving larger landscape level impacts in ecological connectivity, sustainable production, ecosystem resilience, etc.

In this scheme, organizations must think and plan at a larger scale, taking into consideration the proposals coming from several organizations, primary needs of the Bio-enterprise, and stakeholders. This innovation is a clear example of how the SGP can overcome limited impacts due to the constraints of its small-grant nature and aim to impact larger areas with significant additional benefits in terms of community wellbeing.

This innovation concept developed and implemented in GEF-5 and 6 was taken into consideration by the SGP and the Socio Bosque Program and PASNAP/MAE in reviewing the areas of work for the GEF-7 project. This was important because, in the design process, the Ministry of Environment remarked on the innovative methodology of the SGP in Ecuador in the GEF-6 areas. Therefore, it was requested that other areas be served using the same methodology and taking into consideration the Socio Bosque Program and PASNAP/MAE as a base line. Arguments for expanding multi-stakeholder arrangements include leveraging financing and coordinating functions, as they are considered to contribute to increasing the resources available for action and better policy and operational coherence.

On a local level, the PIT strategy has provided a key milestone for community partnerships and innovation, as Bio-corridor projects required sustainability to consolidate the production process until they achieved commercialization during GEF-5 and GEF-6. Therefore, the upgraded methodology designed during GEF-6 will be used as a basis for the strengthening of bio-enterprises during GEF-7.

Another key component for innovation is the SGP Ecuador crowdfunding platform, GreenCrowds, as it supports sustainable communitarian entrepreneurships by providing them not only with funding but also building their capabilities to set and achieve their own fundraising. GreenCrowds works as an alternative finance service for small-scale initiatives and other enterprises, while capitalizing on SGP´s knowledge and expertise, creating shortcuts to reach new markets, leading to a higher level of economic productivity.

Sustainability - The sustainability of landscape management and community bio-enterprise initiatives is based on the principle confirmed by SGP experience that global environmental benefits can be produced and maintained through community-based sustainable development projects.

Sustainability of landscape planning and management processes will be enhanced through the practice established in GEF-5 and GEF-6 - of formation of multi-stakeholder platforms, involving local government, national agencies and institutions, NGOs, the private sector, and others at the landscape level, with the innovative concept of building them around a bio-enterprises network, thus strengthening the actual process and creating the possibility to expand and sustain new shareholders and markets. This secures the areas of conservation while including strategic partners that will provide technical assistance: government, NGOs, universities, academic institutes, and other institutions.

SGP in GEF-7 will support the incorporation of young people and women in the process of strengthening biodiversity sustainability capacities in the communities, to underpin generational change and the incorporation of the interests of these sectors in the decision-making process. At the same time, the ICCA initiative will focus its work on indigenous people and rural areas where the methodology is to be replicated.

During GEF-7, the intervention strategy will focus primarily on bio-enterprise networks, using the incentives of the Socio Bosque Program to establish mechanisms to strengthen them and make them self-sustained. These initiatives will reach out to the central government, local governments, and the private sector for additional financial support and will strategically link with other relevant biodiversity conservation and agroecology initiatives in the country.

Upscaling potential - Building on experiences gained, a primary output of this project is replicating and upscaling GEF-6 lessons and methodologies in other selected landscapes. Some important achievements during GEF-6 are: recovery and conservation of agrobiodiversity species (highlands), recovery and sustainable harvest of mollusks and crustaceans (coast), native fish production (Amazon), agroecological approaches and marketing of surplus production (four regions), handicrafts – chambira, straw shawl, alpaca wool (four regions), community-managed sustainable tourism (four regions), sustainable harvesting and marketing of non-timber forest products (four regions), production, and commercialization of Products with Territorial Identity derived from biodiversity and agrobiodiversity products with added value that contribute to the conservation of these and other products (four regions).

These experiences, along with the upgraded PIT methodology and ICCA concept, will be taken into consideration for replication in the new upscaled initiatives in GEF-7. Identification of projects will take place during project inception, but preliminary possibilities include sustainable use and marketing of crop genetic resources, fish farming with native species, aquiculture, alpaca wool production, agroforestry systems, and sustainable tourism. The premise of upscaling in this context is that the aggregate of community adopters of successful SGP-supported technologies, practices, and systems from previous SGP phases have been slowly acquiring critical mass to reach a tipping point of adoption more broadly by rural constituencies of adaptive practice and innovation.

The innovative approach of the SGP Country Program in GEF 5-6 will be replicated in the selected landscapes that are developing bio-enterprises. This method ensures that new communities that are not already integrated in the consultation stage could join the ongoing process, ensuring the scaling up of the conservation territories and the marketing accessibility. This contributes to the rise of new actors, the transformation of old actors, and the configuration of new alliances in development.

1b. Project Map and Geo-Coordinates.

# 1c. Child Project?  No

2.  Stakeholders.

Indigenous Peoples and Local Communities;

Civil Society Organizations;

Private Sector Entities;

SGP/GEF/UNDP beneficiaries have been considered from the training and follow-up workshops through the consulting with In terris NGO (GEF-6 PIT proposal) and the monitoring results of the M&E team from GEF-6. In these meetings, as well as from the accompaniment methodology of SIMONAA, the necessary information has been gathered to prepare the intervention strategy of the SGP for GEF-7 to generate a comprehensive strategy of bio-enterprises in accordance with the new policy of the Ministry of the Environment. At the same time, regular meetings have been held with the Socio Bosque Program, both at technical and political level to coordinate efforts to prioritize territories due to their ecological and social importance. With these inputs, base maps were constructed that indicate the selected landscapes, the participating partners of both the SGP and MAE - PASNAP / Socio Bosque Program. Such as: UNDP, NGOs, Universities, International Cooperation and other key actors that also take part in the National Steering Committee of the SGP and that will maintain their role of accompaniment and evaluation during FO7.

Additionally, SIMONAA will be adapted to the new intervention strategy that revolves around the creation and strengthening of bio-enterprises in the selected territories. The active participation of all stakeholders at the different levels is considered, since this multi-stakeholder strategy has proved to be efficient and effective since the GEF-5.

Select what role civil society will play in the project:

Consulted only;

Member of Advisory Body; contractor;

Co-financier;

Member of project steering committee or equivalent decision-making body;

Executor or co-executor;

Other

3. Gender Equality and Women's Empowerment

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes  /no)

The project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision making; and or

generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes  /no)

SGP Ecuador has an updated Action Plan and Gender Analysis for GEF-7. The Program also has a mandatory gender approach that has been implemented in project activities since 2000. As a result, gender mainstreaming is considered throughout the project cycle. SGP Ecuador has prioritized gender, interculturality and cross-generational values and approaches.

The grant project application form has indicators that monitor the inclusion of women in the project. Also, the Monitoring, Evaluation and Accompaniment System (SIMONAA) includes specific information for the PIF targets as well as information about equal opportunities. The Systematization Guide implemented during GEF-5-GEF-6 contains specific subheadings regarding gender, intercultural and cross-generational approaches. Therefore, SIMONAA provides the required information for experiential systematization. These methodology documents will be updated for the GEF-7 intervention, regarding bio-enterprise initiatives.

Moreover, SGP Ecuador has developed during GEF-4 a guidebook to incorporate the gender approach in community projects which was implemented in all Bio-corridor initiatives.

The project strongly believes that having a gender mainstreaming approach is important for strengthening democracy and equity in decision making; women in community-based organization, indigenous and peasant communities have a significant role that they play in biodiversity conservation, rural development, food production and poverty eradication.

By empowering women in the bio-enterprise projects, women become leaders with a power of decision on community agreements. Their involvement contributes meaningfully to the family’s economy as they represent a key role in agricultural activities. Therefore, the integration of gender in the new methodology for bio-enterprise products will be a cross cutting approach in community projects. Women have increased their incomes, they have been involved in the activities for the Bio-corridor conservation, and they have involved other women in economic and ecological efforts.

# 4. Private Sector Engagement

As a general strategy, GEF-7 SGP seeks to create policy options for scaling-up existing technologies and good practices that reduce negative externalities along food value chains and for promoting access by land users to inputs and markets for products that drive sustainable production at scale.

The engagement strategy for the private sector will also facilitate crowding-in of private sector investments in land use systems using financial incentives, including non-grant financial instruments that can reduce the risk for investors, and help to create the economic underpinning of required system changes to sustain impact in the long run.

Mainstreaming private sector engagement is a long-term priority of the GEF SGP Country Program in Ecuador. Opportunities for engagement of the private sector can benefit from GEF-6 experience, as follows:

Circular economy: mass extraction, industrial production, consumption, and waste are all increasing at an alarming rate, resulting in natural resource depletion, ecosystem degradation, release of hazardous chemicals into the soil, air, water, GHG emissions, and marine debris. These issues require a circular economy model as a first step in bio-enterprises that emphasizes public-private sector partnerships to catalyze a closed loop approach to production and consumption through improved material use, product design, industrial process change, waste management, and material recovery and recycling. This will create sustainable and inclusive business focused strategies.

The SGP will seek to address issues in national and regional value chains and commodity markets through technical assistance and knowledge sharing to producer organizations. At the same time, it will try to develop community driven supply chains in key sectors such as agriculture, tourism, and retail, incorporating lessons learned from the Supplier Development Programs.

GreenCrowds: Since 2015, GreenCrowds has promoted three campaigns in Ecuador which were able to raise a total of $34,000. GreenCrowds is a crowdfunding platform implemented to support socioenvironmental projects. GreenCrowds has a strong innovative component, given that crowdfunding doesn´t serve just as a mechanism to raise funds, but it also exists to help promote communitarian products in the market, measure audience interest and create an initial investment fund for technological and social innovation, diversification and scaling, thereby improving the entire value chain and reaching new and diverse markets. The collected money is a by-product of the initiative’s success in finding an initial audience for their offer.

GreenCrowds’ experience demonstrated that private enterprises are interested in joining the platform to support innovative socioenvironmental causes, as part of their CSR approach. Identifying specific potential upscaling opportunities with private enterprise will take place during project inception along with SGP/UNDP and social partnerships relying on this GreenCrowds experience. This serves also to create linkages and facilitate peer-to-peer learning for sustainable and inclusive business across industries and geographic areas.

Furthermore, GreenCrowds has a strong innovative component, given that crowdfunding doesn´t serve just as a mechanism to raise funds, but it rather exists to help thrusting communitarian products to the market, measure audience interest and creates an initial investment fund for technological and social innovation, diversification and scaling, therefore improving the entire value chain and reaching new and diverse markets. The collected money is a by-product of the initiative’s success in finding an initial audience for their offer.

Amy Cortese, author of Locavesting: The Revolution in Local Investing and How to Profit from It, sustains that Crowdfunding will end up being legitimated in many economies. “Crowdfunding will orientate itself overall towards consumer goods,” she anticipates. “People want to invest in that which they know and understand.”

This is an advantage, because companies funded by Crowdfunding will gain a consolidated clientele and brand entrepreneurs. “It’s very different from the model of venture capitalism, which is interested only in the rapid expansion of the business.”

For this reason, it is important to understand and support the type of proposals which contributes to the strategies of Corporate Social Responsibility (CSR) of the businesses of the country, keeping in mind the impact that all of the aspects of its activities have on its customers, employees, stockholders, local communities, the environment, and the society in general. The activities developed in the framework of CSR have to be linked to the basic activity of the company, have a permanent vocation, and involve a commitment of the upper management.

Engagement in Focal Areas: for biodiversity, there are several opportunities, including efforts to develop payment schemes for ecosystem services that will rely on proper policy development and capacity building for actors in the private sector. This includes the Socio Bosque project and their communities and partners. In total, there are 38 groups that belong to this project that are being targeted by the SGP for GEF-7. Alongside this sector, the Program will adhere to the strategy of expanding certification, which is currently hampered by inadequate finance, lack of awareness and under-developed markets.

For this, local interventions could include corporate alliances, enabling policy, and capacity building, engaging with private sector actors along the entire value chain. GreenCrowds will be a key factor in a strategy to achieve this goal in less time, giving the bio-enterprises the possibility to have more funds alongside a network of potential costumers/distributors.

The multi-stakeholder platform for bio-enterprise initiatives will also serve to facilitate public-private dialogue that allows the private sector and foundations to take part in policy discussions, budgeting for the future, monitoring, reporting and accountability mechanisms, risk assessments, and advocacy. Inclusive policy dialogue supports the development of business-focused institutions, foundations and beneficiary groups, and ensures their inclusion in national policy making. This will serve to build trust among government, philanthropic organizations and the private sector.

The strategy also identifies ideas for expanded engagement around the Nagoya Protocol (NP), where GEF support is rooted in the vision that obtaining access to genetic resources under the terms of the NP by the private sector can deliver monetary and non-monetary benefits to be shared with the providers of the genetic resources.

# 5. Risks

The risk analysis has been divided into two sections. The first identifies risks that could potentially derail OP7 implementation. The second lists responses to the requirements of the GEF Minimum Environmental and Social Safeguard Standards and precedes fully compliant completion of UNDP’s Social and Environmental Screening Procedure (SESP), which will be annexed to the Project Document.

- Risks to environmental and social soundness and sustainability in the target areas

| # Identified risks | # Potential consequence | Risk rating L: Likelihood # I: Impact | # Mitigation measures | # Risk category |
| --- | --- | --- | --- | --- |
| # Multi-stakeholder coordination is weakened by faulty communication and lack of institutional continuity | Maintaining good coordination with the territorial governments is a big challenge. The relationship between government and civil society was weak during GEF-5 and ameliorated during GEF-6 by establishing a direct channel of communication. It is possible that the execution period of the project coincides with the period of regional elections and political parties, and they could fail to maintain previous agreements with the civil society. | L: medium I: high | Strengthen joint projects across communities and landscapes with beneficial effects for all stakeholders. MAE as a key stakeholder for meetings will be crucial in the process Meetings of potentially problematic RWGs or BWGs will be avoided until the electoral period is past. | # Programmatic and technical |
| # The development of socio-environmental conflicts in local project areas from negative effects of extractive practices | Extractive activities such as mining in areas such as REDD+ cause high conflict among the communities living there and the government. Furthermore, the Ministry of Agriculture, which regulates agricultural policy in Ecuador, has a conflictive approach to biodiversity conservation, seeking mass production instead of sustainability. | L: high I: medium | Multi-stakeholder landscape bio-enterprises will identity and incorporate necessary mitigation measures when required. SGP seeks to strengthen conservation actions through joint projects with beneficial effects for all stakeholders and strengthen landscape agreements legitimizing interventions with Local Governments and training in communities. | # Programmatic |
| # Difficult market access and weak financial sustainability jeopardize adoption of adaptive management practice | Weak development of domestic products and structural difficulties in access to markets by state control and adverse regulations | L: medium I: medium | A strategy to counter this risk is to develop market research partnerships with universities and technical assessment to improve quality processes in production. The new adapted methodology for bio-enterprises will take place during this phase, effectively reducing these risks. | # Programmatic and technical |
| # Diminished motivation to execute project activities | Associations lose motivation and enthusiasm because of an economic crisis in the country. | L: medium I: medium | SGP will raise the level of management with youth and women through training processes and complementarity of production projects with international cooperation | # Programmatic |
| # Weak process engagement by stakeholders | There could be cases where stakeholders commit to support the process and during its implementation, they do not engage with the activities that are their responsibility. This brings difficulties in co-financing. | L: Medium I: High | Disclosure of information, consultation and participation, monitoring, evaluation and learning throughout the project cycle should address grievances, and on-going reporting to stakeholders through the M&E System and direct contact with the SGP office. | # Programmatic and technical |

- Risk mitigation for Policy environmental and social safeguards standards

| Measure | Requirement | Risk mitigation activities |
| --- | --- | --- |
| Environmental and Social Impact Assessment | SGP conducted a screening process that consists of meetings between planner(s) of the project and relevant government officials, which included project-affected groups, indigenous peoples, and local CSOs. The Program also uses strategic, sectoral or regional environmental assessment, when appropriate. | SGP conducted a screening process with the principal stakeholders and had access to all the necessary information to determine the focus area of intervention and actor-mapping prior to project design. |
|  | Assess potential impacts of the proposed project on physical, biological, socioeconomic, cultural, and physical cultural resources. | Working with programs in the field that support communities with incentives and technical assistance to identify the design of the project and monitory progress. SGP will work in this area with communities in a coordination strategy with a multi-stakeholder methodology |
|  | Confirm that project activities that will contravene international obligations are not financed. | The local projects sign a MOA document where they specifically show that they will not contravene any national or international obligation. At the same time, SGP and the Ministry of Environment will ensure that these communities fulfill these commitments though their own M&E systems. |
|  | Alternative investment, technical, and siting alternatives are looked and considered in the project design. | SGP has a mandate that all projects have a counterpart in cash or in-kind for the same delivered amount. SGP is also looking for new kinds of joint programs to adhere to this intervention in Ecuador, such as: PROAMAZONIA / AEI with GreenCrowds. |
|  | All projects include mitigation measures, monitoring, institutional capacity development and training measures. | The MOA document and Project proposal at local level include all the mitigation measures identified as necessary during initial evaluation. At the same time, social and local partners ensure that these measures are put in place, especially regarding protected areas. |
| Protection of Natural Habitats | Determine if project benefits substantially outweigh potential environmental costs in the area of the intervention. | Criteria for the formulation of projects will be defined and clearly communicated to prospective proponents to address any latent environmental threat. The SGP will ensure that this commitment is fulfilled during project execution. |
|  | The project creates physical infrastructure investments only on lands where natural habitats have already been converted to other land uses | In the project selection process any issues are fully discussed and documented in the MOA. These criteria will be clearly communicated to proponents and will be priority eligibility criteria in the selection process by the SGP and NSC. |
|  | The initiatives avoid significant conversion or degradation practices in critical natural habitats |  |
|  | Appropriate conservation and mitigation measures are taken in locations where projects adversely affect non-critical natural habitats | SIMONAA is the monitoring system that procures the examination and evaluation of the process. This system along with the georeferenced monitoring in place will ensure that special conservation and mitigation measures are in place where necessary. |
|  | Appropriate experts and key stakeholders, including local NGOs and local communities are involved in the design, implementation, monitoring, and evaluation of projects, including mitigation planning. | All the appropriate stakeholders with technical support and consultation were taken into consideration during project design, but new actors will be called for specific activities such as core areas for conservation and sustainable market research. |
| Indigenous Peoples | The SGP Country Program team assesses the project area for the presence of Indigenous Peoples | Priority is given to vulnerable areas with indigenous people. The staff of Socio Bosque has helped with this identification, and it was one of the selection criteria for landscapes in the project. |
|  | SGP consults with affected Indigenous Peoples to confirm their interest and broad community support | ICCA methodology ensures indigenous participation as one of its key principles to mitigate possible risks. |
|  | The socioeconomic benefits regarding the intervention are planned in ways that are culturally appropriate, and gender and generationally inclusive. | A specific strategy ensures equitable development and sustainability. The project has a strong gender and generational strategy in place to ensure participation and strengthening of women and youth groups. |
|  | The program consults with Indigenous People in regard to use of cultural resources or knowledge. | ICCA methodology is based on participatory revaluation of cultural practices. There is also a relevant diffusion and knowledge management component in SIMONAA (M&E) and in the design of the project. |
| Accountability and Grievance Systems | The SGP Country Program designates a staff member to receive and respond to complaints related to the implementation of its projects. | Assistance by the SGP National Coordinator (NC) during meetings has been recorded and contact information is shared with the participants, so they can contact the SGP office directly. |
|  | The Program informs project stakeholders of the existence of the Agency’s Accountability and Grievance Systems. | During initial workshops the national coordinator office is in permanent contact with the project and clear and open communication channels are established. |

6. Institutional Arrangements and Coordination

The diagram above shows the project organizational structure (Fig.2). The roles and responsibilities of the various parties to the project are described in the SGP Operational Guidelines. UNDP will provide overall Programme oversight and take responsibility for standard GEF project cycle management services beyond assistance and oversight of project design and negotiation, including project monitoring, periodic evaluations, troubleshooting, and reporting to the GEF. UNDP will also provide high level technical and managerial support from the UNDP GEF Global Coordinator for the SGP Upgrading Country Programmes, who is responsible for project oversight for all upgraded country Programme projects. The SGP Central Programme Management Team (CPMT) will monitor upgraded country Programmes for compliance with GEF SGP core policies and procedures.

In accordance with the global SGP Operational Guidelines (Annex H) that will guide overall project implementation in Thailand, and in keeping with past best practice, the UNDP Resident Representative will appoint the National Steering Committee (NSC) members. The NSC, composed of government and non-government organizations with a non-government majority, a UNDP representative, and individuals with expertise in the GEF Focal Areas, is responsible for grant selection and approval and for determining the overall strategy of the SGP in the country. NSC members serve without remuneration and rotate periodically in accordance with its rules of procedure. The Government is usually represented by the GEF Operational Focal Point or by another high-level representative of relevant ministries or institutions. The NSC assesses the performance of the Country Programme Manager (formerly National Coordinator) with input from the UNDP RR, the SGP UCP Global Coordinator, and UNOPS. The NSC also contributes to bridging community-level experiences with national policy-making.

The Country Office is the business unit in UNDP for the SGP project and is responsible for ensuring the project meets its objective and delivers on its targets. The Resident Representative signs the grant agreements with beneficiary organizations on behalf of UNOPS. The Country Office will make available its expertise in various environment and development fields as shown below. It will also provide other types of support at the local level such as infrastructure and financial management services, as required. UNDP will be represented in the NSC and will actively participate in grant monitoring activities. The CO will participate in NSC meetings, promoting synergies with other relevant Programmes, and support the design and implementation of the SGP strategy, etc.

The Country team composed of a National Coordinator (also known as Country Programme Manager in CEO Endorsement) and a Programme Assistant, recruited through competitive processes, is responsible for the day-to-day operations of the Programme. This includes supporting NSC strategic work and grant selection by developing technical papers, undertaking ex-ante technical reviews of project proposals; taking responsibility for monitoring the grant portfolio and for providing technical assistance to grantees during project design and implementation; mobilizing cash and in-kind resources; preparing reports for UNDP, GEF and other donors; implementing a capacity development Programme for communities, CBOs and NGOs, as well as a communications and knowledge management strategy to ensure adequate visibility of GEF investments, and disseminating good practices and lessons learnt.

As GEF Project Agency, UNDP will provide overall Programme oversight and take responsibility for standard GEF project cycle management services beyond assistance and oversight of project design and negotiation, including project monitoring, periodic evaluations, troubleshooting, and reporting to the GEF.

UNDP (Headquarters) will also provide high-level technical and managerial support through the Low Emissions Climate Resilient Development Strategies cluster, and from the UNDP Global Coordinator for Upgrading Country Programme, who will be responsible for project oversight for all upgraded country Programme projects worldwide. SGP’s Central Programme Management Team (CPMT) will monitor for compliance of upgraded country Programme with the core policies and procedures of the SGP as a GEF Corporate Programme.

Grants will be selected by the NSC from proposals submitted by CBOs and NGOs through calls for proposals in specific thematic and geographic areas relevant to the SGP Country Programme strategy, as embodied in this document. Although government organizations cannot receive SGP grants, every effort will be made to coordinate grant implementation with relevant line ministries, decentralized institutions, universities and local government authorities to ensure their support, create opportunities for co-financing, and provide feedback on policy implementation on the ground. Contributions from and cooperation with the private sector will also be sought.

SGP utilizes consultants for specialized services, mostly for baseline data collection, capacity development activities, business development support, and to assist grantees when specialized expertise is required, or for tasks that require an external independent view such as the mid-term and terminal evaluations. Civil society organization networks may also benefit from SGP grants.

UNOPS will provide Country Programme implementation services, including human resources management, budgeting, accounting, grant disbursement, auditing, and procurement. UNOPS is responsible for SGP’s financial management and provides periodic financial reports to UNDP. The UNOPS SGP Standard Operating Procedures guide the financial and administrative management of the project.

A key service of UNOPS is the contracting of SGP staff as needed and required by the Programme, and once contracted, UNOPS provides guidance and supervision, together with the UNDP CO acting on behalf of UNOPS, to the SGP country staff in their administrative and finance related work.  UNOPS also provides other important services (as specified in the GEF Council document C.36/4) that include (1) oversight and quality assurance: (i) coordinate with the Upgrading Country Programme (UCP) Global Coordinator on annual work plan activities and (ii) undertake trouble-shooting and problem-solving missions; (2) project financial management: (i) review and authorize operating budgets; (ii) review and authorize disbursement, (iii) monitor and oversee all financial transactions, (iv) prepare semi-annual and annual financial progress reports and (v) prepare periodic status reports on grant allocations and expenditures; (3) project procurement management: (i) undertake procurement activities and (ii) management of contracts; (4) project assets management: (i)  maintain an inventory of all capitalized assets; (5) project risks management: (i) prepare and implement an annual audit plan and (ii) follow up on all audit recommendations; and (6) Grants management: (i) administer all grants, (ii) financial grant monitoring and (iii)  legal advice.

Under its legal advice role, UNOPS takes the lead in investigations of UNOPS-contracted SGP staff.  UNOPS services also include transactional services: (1) personnel administration, benefits and entitlements of project personnel contracted by UNOPS; (2) processing payroll of project personnel contracted by UNOPS, (3) input transaction instruction and automated processing of project personnel official mission travel and DSA; (4) input transaction instruction and automated processing of financial transactions such as Purchase Order, Receipts, Payment Vouchers and Vendor Approval and (5) procurement in UN Web Buy.

UNOPS will continue with a number of areas for enhancing execution services started in the previous the SGP GEF-5, including: inclusion of co-financing below $500,000; technical assistance to high risk/low performing countries; developing a risk-based management approach; strengthening the central structure to make it more suitable for an expanded Programme; resolving grant disbursement delays; enhancing country Programme oversight; improving monitoring & evaluation; increasing the audit volume and quality assurance work; and optimizing Programme cost-effectiveness. To facilitate global coherence in execution of services, guidance and operating procedures, UNOPS through a central management team and NSC, coordinates primarily with UNDP/GEF HQ respectively.

UNOPS will not make any financial commitments or incur any expenses that would exceed the budget for implementing the project as set forth in this Project Document. UNOPS shall regularly consult with UNDP concerning the status and use of funds and shall promptly advise UNDP any time when UNOPS is aware that the budget to carry out these services is insufficient to fully implement the project in the manner set out in the Project Document. UNDP shall have no obligation to provide UNOPS with any funds or to make any reimbursement for expenses incurred by UNOPS in excess of the total budget as set forth in the Project Document.

UNOPS will submit a cumulative financial report each quarter (31 March, 30 June, 30 September and 31 December). The report will be submitted to UNDP through the ATLAS Project Delivery Report (PDR) system and follow the established ATLAS formats and PDR timelines. The level of detail in relation to the reporting requirement is indicated in the Project Document budget which will be translated into the ATLAS budgets. UNDP will include the expenditure reported by UNOPS in its reconciliation of the project financial report.

Upon completion or termination of activities, UNOPS shall furnish a financial closure report, including a list of non-expendable equipment purchased by UNOPS, and all relevant audited or certified financial statements and records related to such activities, as appropriate, pursuant to its Financial Regulations and Rules.

Title to any equipment and supplies that may be furnished by UNDP or procured through UNDP funds shall rest with UNDP until such time as ownership thereof is transferred. Equipment and supplies that may be furnished by UNDP or procured through UNDP funds will be disposed as agreed, in writing, between UNDP and UNOPS. UNDP shall provide UNOPS with instructions on the disposal of such equipment and supplies within 90 days of the end of the Project.

The arrangements described in this Project Document will remain in effect until the end of the project, or until terminated in writing (with 30 days’ notice) by either party. The schedule of activities specified in the Project Document remains in effect based on continued performance by UNOPS unless it receives written indication to the contrary from UNDP. The arrangements described in this Agreement, including the structure of implementation and responsibility for results, shall be revisited on an annual basis and may result in the amendment of this Project Document.

If this Agreement is terminated or suspended in accordance with paragraph 140 above, UNDP shall reimburse UNOPS for all costs directly incurred by UNOPS in the amounts specified in the project budget or as otherwise agreed in writing by UNDP and UNOPS.

All further correspondence regarding this Agreement, other than signed letters of agreement or amendments thereto should be addressed to the UNDP-GEF Executive Coordinator and the UNDP Resident Coordinator.

UNOPS shall keep UNDP fully informed of all actions undertaken by them in carrying out this Agreement.

Any changes to the Project Document that would affect the work being performed by UNOPS shall be recommended only after consultation between the parties. Any amendment to this Project Document shall be affected by mutual agreement, in writing.

If UNOPS is prevented by force majeure from fulfilling its obligations under this Agreement, it shall not be deemed in breach of such obligations. UNOPS shall use all reasonable efforts to mitigate the consequences of force majeure. Force majeure is defined as natural catastrophes such as but not limited to earthquakes, floods, cyclonic or volcanic activity; war (whether declared or not), invasion, rebellion, terrorism, revolution, insurrection, civil war, riot, radiation or contaminations by radio-activity; other acts of a similar nature or force.

Notwithstanding anything to the contrary, UNOPS shall in no event be liable as a result or consequence of any act or omission on the part of UNDP, the government and/or any provincial and/or municipal authorities, including its agents, servants and employees.

UNDP and UNOPS shall use their best efforts to promptly settle through direct negotiations any dispute, controversy or claim which is not settled within sixty (60) days from the date either party has notified the other party of the dispute, controversy or claim and of measures which should be taken to rectify it, shall be referred to the UNDP Administrator and the UNOPS Executive Director for resolution.

This project will be implemented by UNOPS in accordance with UNOPS’ Financial Rules and Regulations provided these do not contravene the principles established in UNDP’s Financial Regulations and Rules.

UNOPS as the Implementing Partner shall comply with the policies, procedures and practices of the United Nations security management system.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# 7. Consistency with National Priorities.

Ecuador is a Party to the United Nations Framework Convention on Climate Change (UNFCCC) since Rio de Janeiro in 1992. Ecuador ratified the Kyoto Protocol in 1999 as a Non-Annex 1 Country (SNAP). The Ministry of Environment is the National Environmental Authority exercising stewardship over environmental management.

With the Constitution of the Republic of Ecuador (Year 2008), the rights of nature are instituted in article 71 on the basis of full respect for the existence, maintenance and regeneration of nature’s vital cycles, structure, functions and evolutionary processes. Ecuador is also committed to achieving the 17 Sustainable Development Goals and 169 targets which in the context of natural resource conservation is aimed at protecting the planet from degradation, including through sustainable consumption and production, sustainably managing its natural resources and taking urgent action on climate change, so that it can support the needs of both present and future generations.

As such, the national political framework seeks sustainable development planning under an eco-efficient model, based on Living Well (Sumak Kawsay in the Quichua language), and supported by the new Constitution, which contemplates the recognition and guarantee of the rights of nature.

The National Planning and Development Secretariat – to reach the SDG framed within the Living Well model targeted by Ecuador - developed a new National Territorial Strategy as an instrument for territorial planning on a national basis, which contains guidance for the short, medium and long term: The National Plan of Development 2017-2021 (Plan Nacional de Desarrollo).

This project is consistent with the National Plan of Development 2017-2021 in particular with the goals outlined in Objective 3: to Guarantee the rights of nature for current and future generations; in Objective 5: to Promote productivity and competitiveness for sustainable economic growth in a redistributive and solidary way; and Objective 6: to Develop productive and environmental capacities to achieve food sovereignty and rural Living Well.

At the same time, the project is consistent with the National Biodiversity Strategy 2015-2030, in all its four objectives. The main idea is to organize interventions around these goals that are related to the objectives of the Convention on Biological Diversity and its Strategic Plan for the decade 2011-2020. The project will contribute to the fulfilment of the strategic objectives 1, 2, 3, and 4 of the National Biodiversity Strategy. As in GEF-6, the SGP Country Program will consider strengthening proposals that have potential in bio-enterprises through the category of joint projects such “georeferenced program” and “PIT strengthening methodology consultation”.  Bio-enterprise projects work in the promotion of initiatives of sustainable community tourism, agroecology, agroforestry, recovery of ancestral knowledge, gender equality, security and food sovereignty, environmental education, and organizational strengthening.

This project contributes to the Strategic Plan for Biodiversity 2011-2020 and the Aichi Goals, Strategic Objective B: to reduce the direct pressures on biodiversity and promote sustainable use (goals 5 and 7); Strategic Objective C: to improve the situation of biological diversity by safeguarding ecosystems, species and genetic diversity (goal 13); Strategic Objective D: to enhance the benefits of biodiversity and effective functioning of the ecosystem for the benefit of all (Goals 14 and 15); and Strategic Objective E: to enhance implementation through participatory planning, knowledge management and capacity building (target 18). It is also aligned with the Convention on the Protection of the World Cultural and Natural Heritage: Article 4 and the Latin American and Caribbean Initiative for Sustainable Development (ILAC): Objectives B and C.

The project is aligned with Greening Ecuador Program that seeks to intervene comprehensively in the socio-environmental problems of the country, to guarantee the rights of nature and the living well of current and future generations. This project is also consistent with the Development Plans and Territorial Zoning of all provinces where the project is implemented through direct alignment with the bio-enterprise working groups.

Finally, for its new concept of intervention around bio-enterprises, this project is also aligned with Biocommerce programs in Ecuador. The UNCTAD Biotrade Initiative was launched in 1996, and since then a series of national and regional programs have been promoted. In the country, two important programs have been developed, the national Program of Sustainable Biotrade (PNBSE) between the period 2001 – 2008 and the Andean Biotrade Program or GEFCAF Biocommerce Project between the period 2009 – 2014.

8. Knowledge Management

The SGP has a systematic knowledge management process that is implemented through the Monitoring and Technical Assistance System (SIMONAA) supported by a specialized M&E NGO. This process is based on strengthening the abilities of organizations who are implementing projects to identify, replicate and disseminate the lessons they have learned themselves. The M&E NGO carries out monitoring visits and training to assure the achievement of the projects’ objectives and promote and enable learning-by-doing.

SIMONAA provides oversight of associative projects, allowing them to progress smoothly. This system takes the views of participants into account, as well as that of the implementing entity, as part of evaluation. It evaluates and communicates progress, explains and identifies in a timely manner those problems and obstacles to achieving the objectives, results, effects and impacts of the projects. It seeks to introduce any changes or adjustments necessary to increase the likelihood of achieving results in line with GEF criteria. SIMONAA has ensured that SGP associative projects have achieved (and in some cases surpassed) expected results. It includes a start-up workshop for each region, and then two workshops for sharing experiences (one at the end of the first year and the other at the end of the second) so projects can share their experiences. At the end of the projects, each one has to share its experiences with regards to ecological connectivity, productive landscapes and partnerships. As such, several published documents have been developed to share learning experiences with other stakeholders and partners. The SGP Ecuador Country Program has developed a Participatory Guide for the Systematization of Project Experience.

Through design and implementation of their grant projects, bio-enterprises will contribute to communications activities and to the generation and dissemination of information and knowledge.  Grantees are expected to actively participate in thematic networks, generate knowledge products and to disseminate their products as well as those of other groups within their landscape or network and beyond. Other promotional materials to be produced by the SGP Country Program will be disseminated on a regular basis through the SGP national website (www.ppd-ecuador.org), its Facebook site and Twitter. The Country Program team will produce a communications strategy/plan to guide all stakeholders on the type of communications activities, knowledge products, materials and other communications to address multiple audiences.

Each region (coastal, highland, Amazon) will develop at least one case study related to the establishment and/or maintenance of its bio-enterprises, their management plans and their activities. Knowledge management products will codify experiences on essential elements of the project such as land use planning, establishment of the bio-enterprise to boost communitarian sustainability and their governance, reduction of habitat fragmentation (ecological connectivity improvement) in the production landscape, sustainable use of biodiversity components, and production and marketing priorities.

Success in marketing these products will be analyzed and documented for wider dissemination in the form of a case study. These case studies will consolidate work done by the project at all levels and help stimulate replication and up scaling within and beyond the geographic areas where the project is focused. Knowledge management is also important for strengthening community organizations and other civil society networks.

Project monitoring and evaluation activities and results will provide a solid foundation for the Country Program’s communications and knowledge management activities framework. The Ecuador SGP Monitoring and Technical Assistance System (SIMONAA) enables project participants to identify results, limitations, innovations, and lessons learnt as a fundamental part of project design and implementation.

| Products | SGP Budget | Cofinancing |  |  | Timeframe (year) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Bio-enterprises | M&E NGO | Other | 1 | 2 | 3 | 4 |
| Start-up workshop for each region (4) | 20,000 | 2,000 | 2,000 | 20,000 | x |  |  |  |
| Two workshops for sharing experiences | 10,000 | 1,000 | 2,000 | 10,000 | x |  |  | x |
| Networking and in-situ promotion with media partners and UNDP office to promote the impact and evolution of the bio-enterprises | 20,000 | 5,000 | 5,000 | 20,000 |  | x |  |  |
| One case study to summarize and gather best-practices for bio-enterprises conformation and strengthening | 5,000 | 10,000 | 5,000 | 5,000 |  |  |  | x |
| SGP sharing material (webpage and social media) | 5,000 | 1,000 | 1,000 | 5,000 | x | x | x | x |
| Systematization of results in video presentation or animated video that will be shared worldwide through SGP/GEF/UNDP network | 15,000 | 10,000 | 5,000 | 15,000 |  |  |  | x |

9. Monitoring and Evaluation

The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

Project Manager:  The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Manager will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

The Project Manager will develop annual work plans based on the multi-year work plan included in Annex, including annual output targets to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. ESMP, gender action plan, stakeholder engagement plan etc..) occur on a regular basis.

Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Manager.

The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:  A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

a) Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

b) Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

c) Review the results framework and finalize the indicators, means of verification and monitoring plan;

d) Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

e) Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP, Environmental and Social Management Plan and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

f) Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

g) Plan and schedule Project Board meetings and finalize the first-year annual work plan.

The Project Manager will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Project Board.

GEF Project Implementation Report (PIR):  The Project Manager, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

GEF Focal Area Tracking Tools:  The following GEF Tracking Tool(s) will be used to monitor global environmental benefits:

The baseline/CEO Endorsement GEF Focal Area Tracking Tool(s) – submitted as Annex to this project document – will be updated by the Project Manager/Team (not the evaluation consultants hired to undertake the MTR or the TE) (indicate other project partner, if agreed) and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated GEF Tracking Tool(s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and approved by the Project Board.

Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Manager will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Mandatory GEF M&E Requirements and M&E Budget:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant (USD) | Co-financing |  |
| Inception Workshop | UNDP Country Office | 11,000 | 24,000 | Within two months of project document signature |
| Inception Report | Project Manager | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | Project Manager Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Manager | (4,000/year) 16,000 | 24,000 | Annually before PIR |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | (3,000 – 5,000/year) 20,000 | 0 | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Manager | 18,000 | 18,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP Country Office | 25,000 | 30,000 | On-going |
| Stakeholder Engagement Plan | Project Manager UNDP Country Office | 12,000 | 12,000 | On-going |
| Gender Action Plan | Project Manager UNDP Country Office UNDP GEF team | 5,000 | 5,000 | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office | as required | 0 | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Manager | 3,000 | 0 | At minimum annually |
| Supervision missions | UNDP Country Office | None | 10,000 | Annually |
| Oversight missions | UNDP-GEF team | None | 5,000 | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team | None | 0 | To be determined. |
| Mid-term GEF Tracking Tool to be updated by | Project Manager | 10,000 | 0 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | 20,000 - 30,000 | 2,000 | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool to be updated by | Project Manager | 10,000 | 0 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | 30,000 - 60,000 | 2,000 | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | 2,000 – 10,000 | 0 | As required. GEF will only accept reports in English. |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | 230,000 | 132,000 |  |

10. Benefits

The GEF-7 project is designed under the idea of achieving social and environmental benefits through strengthening of bio-enterprise networks in areas of global biodiversity importance. The GEF-7 project will support planning and management of landscapes with globally significant biodiversity, using a multifocal, multi-sectoral approach, and overcoming organizational barriers to the use of land for sustainable production and connectivity.

The project will increase the socio-economic benefits to stakeholders in the identified areas and other later-linked participants through sustainable use of biodiversity and other resources in these landscapes, using the improved methodology for “Products with Territorial Identity” developed by SGP during GEF-6. These initiatives will be supported in areas such as food security and land use and sustainability through a community-based natural resource management strategy, directly connected to the new development plan of Ecuador to procure income-generating activities while promoting biodiversity conservation. As an indirect result, these include improved soil productivity through agroecological practices and production systems, containing use of compost and organic fertilizer; improved micro-climate and water resource availability and volume from windbreaks, agroforestry systems, and cover crops; conservation and sustainable use of crop genetic biodiversity; greater pest control from agroecological, poly-cultural systems; as well as others to be identified and innovated by smallholder organizations.

At the same time, with the landscape planning approach, ecosystem services are identified for enhancement, providing substantial benefits to communities beyond the program’s direct area of influence. The ecosystem services provided by the Paramo, which include water retention, regulation, and carbon sequestration, are retained by setting aside areas for conservation, as well as through improved soil, water, and biomass management in the production landscape. The conservation of dry forest ecosystems and associated coastal mangroves provide direct benefits to communities through improved availability of marine fauna and flora for sustainable harvesting. Conservation or regeneration of coastal habitats provide protection of shorelines from erosion, tsunamis, and storms.

Generally, natural resources management and product development know-how can be very unequal between the private sector and communitarian entrepreneurships. Companies tend to keep this information as proprietary secrets even when communities are somehow involved in the process. This problem could be mitigated by clearly identifying rights and obligations of both parties and enforcing them to ensure knowledge transference.

PART IV: ANNEXES

Annex A: Project Results Framework

Annex B: Response to Project Reviews (not applicable at this stage)

Annex C: Project Maps and Coordinates

Annex D: GEF 7 Core Indicator Worksheet

Annex E: GEF Project Taxonomy Worksheet

FAO (2015) Forest Resources Assessments (FRA) (p.4). Rome, Italy.

Ministry of the Environment (2018) Reverdecer Ecuador Program. Quito, Ecuador.

Ministry of the Environment (2016) National Biodiversity Strategy 2015-2030 (p.179). Quito, Ecuador.

Ministry of the Environment (2016) National Biodiversity Strategy 2015-2030 (p.98). Quito, Ecuador.

Mena Vásconez, P. (2011). Wasteland. Landscape studied, inhabited, managed and institutionalized (p.25). Quito, Ecuador.

Working Group of Paramos Ecuador (GTP). Paramo (p.25-27). Quito, Ecuador.

Idem.

L'lnstitut de Recherche pour le Developpement (2004). Paramos Soils. New York, United States.

International Conservation Ecuador (2018). Ecuadorian Choco. Quito, Ecuador.

Aguirre, Zhofre & Kvist, Lars & Sánchez, Orlando & Editores, M & Moraes, Romis & Øllgaard, B & Borchsenius, F & Balslev, Henrik. (2006). Bosques secos en Ecuador y su diversidad. Botánica Económica de los Andes Centrales.

Ídem.

Ministry of the Environment (2016) National Biodiversity Strategy 2015-2030 (p.177). Quito, Ecuador.

Early Warning System (2015). Ecuador: manglares gestionados a través de concesiones comunitarias.

Víctor López A., Fernando Espíndola, Juan Calles L. y Janette Ulloa (2013). Amazonía ecuatoriana bajo presión. Quito, Ecuador.

Ministry of the Environment (2016) National Biodiversity Strategy 2015-2030 (p.133). Quito, Ecuador.

Ministry of Environment (2015). MAE promueve conservación y recuperación de bosques tropicales. Quito, Ecuador.

MAG (2018) Proyecto Nacional de Innovación Tecnológica Participativa y Productividad Agrícola (PITPPA) Quito, Ecuador.

Ministry of Environment, and United Nations Development Program - UNDP, 2018.

Holstein, W. (March 2014). Micromecenazgo. Obtained from http://compassmag.3ds.com/es/3/Negocios/MICROMECENAZGO

This is a methodology to connect suppliers and consumers, improving the products and services provided. Likewise, it seeks to improve the value chains of these entrepreneurships.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.