GEF-7 Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

PART I: Project Information

| Project Title: | Protecting biodiversity and recovering degraded ecosystems - RECOVER Honduras |  |  |
| --- | --- | --- | --- |
| Country(ies): | Honduras | GEF Project ID: | TBD |
| GEF Agency(ies): | UNDP; FAO | GEF Agency Project ID: | 6295 |
| Project Executing Entity(s): | Secretariat of Natural Resources and Environment (MiAmbiente+), International Union for Conservation of Nature (IUCN), UN Environment, Food and Agriculture Organization of the United Nations (FAO), United Nations Development Programme (UNDP) | Submission Date: | April 9, 2019 |
| GEF Focal Area(s): | Multi-focal Areas | Project Duration (Months) | 84 |

A. indicative Focal/non-Focal Area  Elements

| ### Programming Directions | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| BD-1-1 | GEFTF | 8,137,464 | 41,335,230 |
| LD-1-1 | GEFTF | 863,242 | 4,332,385 |
| LD-3-4 | GEFTF | 863,242 | 4,332,385 |
| Total Project Cost |  | 9,863,948 | 50,000,000 |

B. indicative Project description summary

| ### Project Objective: Strengthening the connectivity and management of Key Biodiversity Areas (KBAs) in Northern Honduras through restoration and reduction of threats to biodiversity from commodity production |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1. Enabling a territorial governance framework for the restoration of areas of importance for biodiversity and for sustainable production and diversification | TA | - Policy, institutional, and financial frameworks strengthened to sustainably manage production landscapes, including biological corridors, as indicated by the following: a. Updated agroforestry regulation facilitates implementation of the National Program for the Recovery of Degraded Ecosystems’ Goods and Services 2018-2028; b) Increase by X% in the financial resources available to support deforestation-free commodity value chains (palm oil and beef/dairy). - Increased capacity of palm oil production and cattle farming sectors and environmental authorities (technical staff and decision makers, including women) to effectively implement sustainable production and diversification, as indicated by the UNDP Capacity Development Scorecard Baseline and target will be confirmed during the PPG | 1.1. Forest Conservation and Development Institute (ICF) regulation developed clarifies the extent of agroforestry systems throughout its life cycle, including the contribution to the sustainable management of the landscape and the profitability of agroforestry systems. 1.2. Regulation of the ecosystem goods and services recovery program defined allows for a comprehensive articulation between sustainable production activities and the restoration of areas of importance for biodiversity. 1.3. Enhanced land tenure interinstitutional accreditation system (e.g., collective and private land titles [including indigenous and afro-Honduran peoples], long-term government or private lease-holds) enhanced facilitates the following: a) territorial planning to identify key stakeholders and sites for the restoration of areas of importance for biodiversity and sustainable production, among others; b) regulation of land tenure; c) access to financing to support sustainable production and restoration of degraded lands; and d) conflict resolution related to land tenure. 1.4. National Sustainable Palm Oil Platform strengthened by the following: a) a Multi-year Action Plan defined that considers sustainable territorial planning and co-programming and investment by key government, private sector, and civil society stakeholders; b) technical and financial mechanisms in place to support a Roundtable on Sustainable Palm Oil (RSPO) certification of small producers and cooperatives in Key Biodiversity Areas (KBAs) and surrounding landscapes, and the development of models and Good practices for financial and economic assessments of African oil palm to improve decision making and spatial analysis of production; and c) environmental licensing protocols linked to national and international certification to reduce costs for producers and complexity, and facilitates monitoring by environmental authorities (e.g., Secretariat of Natural Resources and Environment [MiAmbiente+], Municipal Environmental Units, and ICF). 1.5. Sustainable Livestock Farming Regional Roundtable (government [SAG, MiAmbiente+, Commerce Secretariat]; Regional Livestock Associations, and Dairy Collection Centers [CRELES]/ Honduran National Federation of Ranchers and Farmers [FENAGH]) strengthened through the following: a) training and technical support to promote intensive silvopastoral systems, production diversification, and the restoration of ecologically sensitive degraded lands; and b) subnational landscape standard for sustainable cattle developed using the methodology of the Livestock Environmental Assessment and Performance Partnership (LEAP) and piloted on the project farms through Component 3 contributes to the development of a national standard. 1.6. The Environmental Innovation Center strengthened by the government and private sector facilitates the following: a) supports small producers (including women) in sustainable production and business development (financial planning, market access, accounting, marketing, etc.); b) two (2) national green seals developed (palm oil and beef/dairy); and c) indicators to assess environment, social, and economic performance developed. 1.7. Financial products (credit lines, green bonds, guarantee funds, impact investment funds, payments by results, etc.) established with necessary institutional capacity in place for the financing of deforestation-free commodity value chains (palm oil and beef/dairy) associated with restoration, including the following: a) business agreements with international and national buyers through public-private mechanisms (e.g., partnership with the Honduran Bank for Production and Housing (BANHPROVI) and other financial institutions; b) compliance with environmental, social, and gender safeguards; c) link with the monitoring, reporting, and validation (MRV) system of the National REDD+ Strategy. 1.8. Framework for achieving land degradation neutrality (LDN) goals established based on validation of baselines for LDN over 196,000 hectares and action plan defined with key stakeholders. | GEFTF | 1,479,592 BD 1,220,620 LD 258,973 | 7,500,000 |
| 2. Restoring degraded areas in production landscapes to enhance biological connectivity in the Northern Honduras Corridor | TA | - Landscape management tools - LMTs (micro-corridors, enrichment of the forests, hedges, live fences, wind barriers, and agroforestry) deliver multiple global environmental benefits (GEBs) measured by the following: a) 30,000 hectares (ha) of restored biological corridors between production landscapes and 2 KBAs and 4 protected areas; b) Ecological Integrity Index for the jaguar increases from 1.68 (poor) to at least 2.00 (fair); c) the presence of hawks (Buteo sp.) confirmed; d) stable presence of Odonata (dragonflies) indicates the good ecological condition of freshwater ecosystems; and e) reduction of the erosion rate by X% by project’s end Baseline and target will be confirmed during the PPG. | 2.1. LMTs (micro-corridors, forest enrichment, hedges, live fences, wind barriers, and agroforestry) implemented enhance connectivity between KBAs and include the following: a) 1,000 conservation and good production practices agreements signed with the producers of palm oil and beef/dairy products to adopt LMTs that contribute to biodiversity conservation; b) 11 existing nurseries operated by the ICF strengthened and 2 new nurseries with cooperatives or producers’ associations (including women’s groups) established, providing 10,000 seedlings per nursery to be used with the LMTs and the restoration of biological corridors; and c) Restoration Plan for the rehabilitation of biological corridors linking production lands with biodiversity conservation and in line with the National Program for the Recovery of Degraded Ecosystems’ Goods and Service 2018-2028. 2.2. At least 10 community-based organizations and organizations of indigenous and Afro-Honduran peoples (for example, Garífuna and Pech), including women's groups, supported with small grants to support the recovery of goods and ecosystem services on degraded lands. 2.3. Good practices to reduce conflicts between producers and jaguars (Panthera onca) implemented, include the following: a) training of producers; b) handbook of good practices; and c) jaguar and prey (e.g., collared peccary, red brocket, Central American agouti, and lowland paca) monitoring plan which considers the protocol for the monitoring the jaguar in Honduras. 2.4. Good production practices implemented in the project’s farms promote sustainable alternatives for pepper, rambutan, and cocoa. 2.5. A system to monitor of project’s environmental benefits defined includes the following: a) a monitoring plan for key species which considers the recommendations of the National Biological Monitoring Board; and b) modeling tools (e.g., Livestock Environmental Assessment Model GLEAM] and Ex-Ante Carbon-balance Tool [EX-ACT]) used to measure GEBs resulting from implementation of LMTs in the Northern Honduran Corridor (including GEBs from Component 3). | GEFTF | 2,959,184 BD 2,441,239 LD 517,945 | 15,000,000 |
| 3. Sustainable value chains and production diversification reduce deforestation and improve producers’ income. | TA | - X% increased in the annual net income of participating small and medium producers of palm oil and beef/dairy derived from: a) RSPO certification; b) intensive silvopastoral systems; c) agroforestry and diversification products; and d) marketing of deforestation-free beef/dairy. - XX ha of deforestation avoided as a result of sustainable palm oil and beef/dairy value chains. - 196,000 ha of landscapes under improved practices. - 20% increase of productivity in participating palm oil and beef/dairy farms. Baseline and target will be confirmed during the PPG. | 3.1. Sustainable production training and extension services program implemented, with support from the Sustainable Livestock Farming Regional Roundtable, benefits 6,000 small and medium producers of palm oil (3,000) and beef/dairy (3,000) in key conservation areas. 3.2. At least five cooperation partnerships established with the private sector (buyers and businesses related to agroforestry products [e.g., cocoa, fruit products, and timber] resulting from the implementation of LMTs), and with processors and retailers (e.g., Wendy’s, Wal-Mart, McDonalds, LA Colonia) to promote deforestation-free beef/dairy. 3.3. Existing or new incentives (e.g., access to financing, tax exemptions, training, technical assistance, etc.) identified and made available to small and medium producers of palm oil and beef/dairy. 3.4. At least three cooperatives or groups of small and medium palm oil producers, including women’s groups, supported to comply with Principle 5 (Environmental responsibility and conservation of natural resources and biodiversity) of the RSPO. 3.5. 500 small and medium beef/dairy farms supported to implement intensive silvopastoral systems with production diversification through agroforestry systems and with verification using LEAP, GLEAM, Total Factor Productivity-Livestock (L-TFP), and Propensity Score Matching (PSM). 3.6 Spatial verification system (e.g., Land Use Change Monitoring System within Production Landscapes [MOCUPP]) for palm oil and beef/dairy production units free of loss of forest cover designed, includes training of environmental authorities (e.g., MiAmbiente+ and municipalities) for its implementation and an interactive online platform for information management and use. | GEFTF | 4,463,436 BD 3,682,202 LD 781,234 | 22,500,000 |
| 4. Knowledge Management, Monitoring and Evaluation (M&E) | TA | - Solutions and good practices shared with the Good Growth Community of Practice, the Conference of the Parties of the Convention on Biological Diversity, the Panorama Portal “Solutions for a Healthy Planet”, and other global events and communities of practice. - Knowledge and lessons learned systematized and disseminated through at least one (1) document per value chain for the replication and scaling up of successful experiences in other production landscapes and biological corridors. - Manual on mainstreaming gender in sustainable production systems | 4.1. Information and knowledge exchange platform established at the national level increases awareness about mainstreaming biodiversity in production landscapes, SLM, and gender aspects, among other topics. 4.2. South-south cooperation program implemented to exchange knowledge about supply chain good practices and market opportunities for sustainable products. 4.3 Project gender mainstreaming plan and M&E plan implemented and manual on gender mainstreaming developed. | GEFTF | 493,198 BD 406,874 LD 86,324 | 2,500,000 |
| Subtotal |  |  |  | GEFTF | 9,395,410 | 47,500,000 |
| Project Management Cost (PMC) (BD: 43,372; LD: 413,807) |  |  |  | GEFTF | 468,538 | 2,500,000 |
| Total Project Cost |  |  |  |  | 9,863,948 | 50,000,000 |

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | Secretary of Agriculture and Livestock (SAG) | Grant |  | 15,000,000 |
| Recipient Country Government | Honduran Bank for Production and Housing (BANHPROVI) | Loan |  | 25,000,000 |
| Donor Agency | Swiss Agency for Development and Cooperation (COSUDE) | Grant |  | 3,000,000 |
| Private Sector | Palm Oil Private Sector | Other |  | 500,000 |
| Private Sector | Livestock Private Sector | Other |  | 1,000,000 |
| Private Sector | Private Banks | Loan |  | 5,500,000 |
| Total Co-financing |  |  |  | 50,000,000 |

National and Private Banks: The Honduran Bank for Production and Housing (BANHPROVI) and private banks BANRURAL and Banco Atlántida are currently financing agriculture activities in in line with this proposed GEF 7 project. Financial products for restoration investments and deforestation free production will include loans, credit lines, and other financial instruments with technical assistance and government subsidies and other incentives for small farmers and local association of producers.

D. Indicative Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c)=a+b |
| UNDP | GEFTF | Honduras | Biodiversity |  | 8,137,464 | 773,059 | 8,910,523 |
| FAO | GEFTF | Honduras | Land Degradation |  | 1,726,484 | 164,016 | 1,890,500 |
| Total GEF Resources |  |  |  |  | 9,863,948 | 937,075 | 10,801,023 |

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEFTF | Honduras | Biodiversity |  | 200,000 | 19,000 | 219,000 |
| FAO | GEFTF | Honduras | Land Degradation |  | 100,000 | 9,500 | 109,500 |
| Total PPG Amount |  |  |  |  | 300,000 | 28,500 | 328,500 |

F.  Project’s Target Contributions to GEF 7 Core Indicators

| Project Core Indicators |  | Expected at PIF |
| --- | --- | --- |
| 3 | Area of land restored (Hectares) | 30,000* |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) | 166,000** |
|  | Total area under improved management (Hectares) | 196,000 |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | Women 64,800; Men 97,200 |

* Areas restored include ecologically sensitive areas (e.g., wetlands and riparian forests) degraded by non-sustainable production and rehabilitated using landscape management tools - LMTs (e.g., microcorridors, forest enrichment, hedges, live fences, wind barriers, and agroforestry systems).

** Landscapes under improved practices include areas with sustainable production of palm oil and beef/dairy production (including intensive silvopastoral systems with production diversification), and farms under good practices to promote sustainable alternatives for pepper, rambutan, and cocoa production.

G. Project Taxonomy

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing Models | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders | Indigenous Peoples |  |  |
|  | Private Sector | Financial intermediaries and market facilitators Individuals/Entrepreneurs |  |
|  | Beneficiaries/ Local Communities/ Civil Society | Community Based Organization, Non-Governmental Organization, |  |
|  | Type of Engagement | Information, Dissemination, Consultation, Participation, |  |
|  | Communications | Awareness Raising, Behavior Change |  |
| Capacity, Knowledge and Research | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Learning | Theory of Change, Adaptive Management, Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning | Knowledge Management, Capacity Development, Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality | Gender mainstreaming | Beneficiaries, Women groups, Sex-disaggregated indicators, Gender-sensitive indicators |  |
|  | Gender results areas | Access and control over natural resources, Participation and leadership Access to benefits and services, capacity development, Awareness raising, Knowledge generation |  |
| Focal Area/Theme | Biodiversity | Mainstreaming | Forestry (Including HCVF and REDD+, Agriculture & agrobiodiversity, Certification (national standards) Certification (International Standards) |
|  |  | Species | Threatened species, |
|  |  | Biomes | Wetlands, Tropical Rain Forests |
|  |  | Forest and Landscape Restoration |  |
|  | Land Degradation | Sustainable Land Management | Restoration and Rehabilitation of Degraded Lands, Sustainable Livelihoods, Income Generating Activities Sustainable Agriculture, Sustainable Pasture Management, Improved Soil and Water Management Techniques |
|  |  | Rio Marker | Climate Change Mitigation 0 Climate Change Adaptation 0 |

part ii:  project JustiFication

1a. Project Description.

1) The global environmental and/or adaptation problems, root causes and barriers that need to be addressed (systems description)

- This project will reduce biodiversity loss and land degradation in Honduras by mainstreaming biodiversity conservation and sustainable land management (SLM) approaches into the production practices of the main sectors driving these processes, namely the palm oil and livestock sector focusing in the Northern Honduras Corridor.

- Because of its geographical location that converges on tropical and subtropical ecosystems, Honduras possesses a high degree of diversity of terrestrial, marine and coastal, and freshwater biological resources. The country comprises a total area of 112,492 square kilometers (km2) and is home to approximately 9,750 plant species, 546 reptile and amphibian species, 770 bird species, and 221 mammal species. Honduras has a forest area equivalent to almost half of its territory. In 2014 the country’s forest cover was estimated at 5,384,424 hectares (ha), of which 57.1% corresponds to deciduous forest (3,074,310.15 ha), 36.7% to conifer forest (1,972,675.12 ha), 5.3% to mixed forest (285,468.77 ha) and 1.0% to the remnants of mangrove forest (51,970.84 ha). Additionally, 242,909.03 ha (2.16% of land use) comprise agroforestry systems in coffee plantations that were established as part of the country’s ecosystem restoration efforts. The country’s forests provide multiple ecosystem goods services to the Honduran people, including regulation of water regimes, protection of soil and erosion control, nutrient cycling, flood control, and climate regulation. In addition, the forest ecosystems provide goods such as water for domestic and agricultural use, timber, firewood, medicinal plants, and food, and habitat for biodiversity.

- The project target area within the Northern Honduras Corridor is part of the larger Mesoamerican Biological Corridor, which is home to 8% of the all the known species worldwide. It includes forest remnants within production areas that are key for providing connectivity between interior mountain protected areas and coastal protected areas, as follows: 1) Nombre de Dios National Park (NP) - Pico Bonito NP- Texiguat Wildlife Refuge (WR); 2) Pico Bonito NP - Cuero y Salado NP; and 3) Lancetilla Botanical Garden-Janett Kawas NP. Among these protected areas, Pico Bonito and Texiguat are also categorized as Key Biodiversity Areas (KBAs) It includes parts of the jaguar corridor within Honduras, and the ecosystems present contribute to providing habitat to up to 28% of all local and migratory birds in the country. It also includes some of the 46 officially recognized micro-watersheds present in the Northern Honduras Corridor. Species of global importance present are the jaguar (Panthera onca; VU); the mantled howler monkey (Alouatta palliata; LC); the giant anteater (Myrmecophaga tridactyla; VU); the American manatee (Trichechus manatus; VU); and the American crocodile (Crocodylus acutus; VU), among others.

- Honduras has a population of 8.3 million, more than half of whom reside in rural areas, Honduras is a low middle-income country that faces major challenges, with more than 60.9 percent of the population living in poverty in 2016. In rural areas, approximately one out of five Hondurans lives in extreme poverty. The country’s economy has experienced moderate growth over the last 10 years, which is driven by public investments, exports, and higher remittances. In 2017, the country’s economy grew by 4.8 percent, and in 2018 there was 3.6 percent growth. The economy is based on its natural resources that provide key ecosystem services for society but used to provide a broad range of agricultural products (e.g.,  coffee, bananas, sugar, palm oil and its derivatives) and forest products. Despite a favorable economic outlook, the country faces the highest level of economic inequality in Latin America and is vulnerable to setbacks from external forces. For example, the agricultural sector of Honduras lost nearly one-third of its revenue during the past two decades, in part due to the declining prices of the country’s export crops, especially banana and coffee.

- The outlook for International Trade in Latin America and the Caribbean in 2017, which was derived from the Economic Commission for Latin America and the Caribbean, places Honduras at the top in regional exports, with a 29.6% increase in total exports for commodities. Honduras is the ninth-largest producer of palm oil in the world (580,000 tons produced and 420,000 tons exported in 2018), and generated $430 million USD in foreign currency, second only to coffee. The production of palm oil represents 8.1% of the agricultural gross domestic product (GDP) (2018). More than 200,000 ha of oil palm are grown in Honduras, which are distributed among more than 20,000 producers (the majority of this cultivated area is located in the project’s target area). The palm oil sector in Honduras generates around 75,000 direct and indirect jobs. Currently, there are 15 oil extraction plants, operating at 59% of their installed capacity. At least three palm oil extraction plants, which process 17% of the total palm oil, have RSPO certification and an additional four plants are undergoing the RSPO certification process. Cattle farming contributes significantly to the economic development and food security of the country. It contributes 14% of the agricultural GDP and is practiced in more than 2.5 million ha nationwide (22% of the country’s total land area). Cattle farming creates more than 500,000 jobs in beef/dairy production. A total of 69,000 producers are dedicated to this activity nationwide.

Global environmental problem

- Threats to biodiversity: The principal threat to biodiversity in Honduras is habitat loss and fragmentation due to subsistence agriculture, widespread illegal logging, cattle farming, industrial scale agriculture and conversion to monoculture plantations, such as oil palms.  The expanding agricultural frontiers have led to fragmentation and loss of native forest habitat and forest degradation. Between 2000 and 2016, approximately 372,856 ha were deforested, at a deforestation rate of 23,304 ha per year. The humid broadleaf forest suffered the greatest deforestation, with 278,520 ha lost during that period (17,407 ha per year); encroachment of agricultural borders (extensive cattle farming and agriculture) and illegal logging were the main causes for the loss of forest cover. In northern Honduras, the humid broadleaf forest and coastal wetlands are negatively impacted by activities associated with African palm cultivation. Oil palm plantations increased from 24,626 ha in 1985 to 114,244 ha in 2015, resulting in the deforestation of 33,598 ha and changes in land use in 56,019.74 ha (from pasture and crops to oil palm). The projected deforestation from palm oil cultivation and the expansion of cattle farming over the next 7 years is 7,840 ha and 49,490 ha, respectively. It also leads to the emission of carbon from reduction of forest stocks and to land degradation processes and water and soil pollution. Firewood extraction, forest fires, and illegal timber extraction also contribute to the loss of forest cover. Pollution is also a principal threat to biodiversity; the overuse of  agrochemicals (pesticides and synthetic fertilizers), and the disposal of untreated wastewater solid waste into natural ecosystems has resulted in the degradation of natural resources and has been closely associated with the clearing of land for agriculture and other uses, including palm oil production. Finally, the effects of climate change exacerbate the negative effects on biodiversity, causing incremental shifts in biological communities as a result of elevated temperatures, changing precipitation patterns, and increasing frequency and severity of storms, among other factors.

- Land degradation: Land degradation in Honduras is closely related to the degradation of natural resources; that is, reduction or loss of forest cover, degradation of water sources, and soil erosion due to deforestation and unsuitable agricultural production practices and cattle ranching. Land degradation has resulted in the deterioration of biological, physical and chemical soil properties generating important negative environmental impacts that go beyond production. 72% of the country has slopes greater than 15 percent and up to 78% of land used for agriculture is on hillsides. Slope farming is not suited for the country’s soils, which are fragile and acidic. In addition, because of dry spells and seasonal water scarcity, secure water provision and soil erosion are major problems facing Honduras. Land degradation and desertification in Honduras would get worse due to climate change and variability. Honduras is among the countries most affected by extreme weather events, including drought. Climate change projections indicate an increase in average temperature by 1 degree Celsius (°C) to 2.5°C by 2050 and 3°C to 4.3°C by 2100, and an annual rainfall decrease of 9 to 14 percent by 2050 and 20 to 31 percent by 2100. The impacts of climate variability are already significant in Honduras and are principally affecting the rural poor who depend on rain-fed agriculture. Between 2012 and 2013 there was a 23% decline in coffee production due to a coffee rust outbreak, which was fueled by a more variable climate, changing moisture conditions and higher temperatures. In addition, 2 years of consecutive drought starting in 2014 led to a loss of 96% of maize yields and 87% loss of bean yields in the country’s Dry Corridor. On the other hand, more than half of Honduras’ total greenhouse gas (GHG) emissions come from land use change; the emissions for average deforestation for the period 2000-2016 have been estimated at 6,552,746.47 tCO2/year.

- The root causes of environmental degradation in Honduras  include: a) poverty: many of Hondurans living in poverty are landless or live in fragile areas not suitable for agriculture. With few economic opportunities, the poor seek to subsist by using the available natural resources, causing multiple environmental impacts; b) an inadequate policy-enabling environment: limitations and inconsistencies in the regulatory frameworks prevent effective environmental management; in addition, land use management legislation is mostly related to production sectors such as agriculture and animal husbandry, with limited consideration given to environmental aspects; c) weak institutional capacity: government entities charged with overseeing land use management and environmental protection are weak, with few budget resources, and with limited capacity for monitoring, control, or surveillance; and d) lack of environmental awareness: there is limited knowledge about natural resources among the population, and a lack of environmental education programs increases the threats to biodiversity, the land, and the forests.

- To address the country’s environmental challenges, Honduras has developed a regulatory and policy framework consisting of several laws and regulations, among which the most relevant are 1) the General Environmental Law (Decree No. 104-93), which among other things mandates the protection, conservation, restoration, and sustainable management of the environment and natural resources; and 2) the Forestry, Protected Areas, and Wildlife Law (Decree No. 98-2007), which establishes the legal aspects for managing forests, protected areas, and wildlife resources, and seeks sustainable development in harmony with the country’s social, economic, environmental, and cultural interests. There are also multiple government agencies directly or indirectly related to environmental and development factors. The most relevant among these agencies are the Secretariat of Natural Resources and Environment (MiAmbiente+); the National Institute of Conservation and Forests, Protected Areas, and Wildlife Development (ICF); and the Secretariat of Agriculture and Cattle Ranching (SAGA). In addition, Honduras is party to a number of international conventions, including the Convention of Biological Diversity (CBD); the United Nations Framework Convention on Climate Change (UNFCCC); the United Nations Convention to Combat Desertification (UNCCD); and the Convention for the Conservation of Internationally Important Wetlands (RAMSAR). Despite these efforts and synergies with civil society organizations (CSOs), as well as collaborations with multiple donor programs, the country’s environmental problems persist.

- The long-term solution consists of a strategy to enable policy, institutional, and financial frameworks for the delivery of multiple global environmental benefits (GEBs) through the implementation of strategies and tools to restore degraded areas in palm oil and livestock production landscapes, mainstreaming of environmental considerations into the management practices of production sectors with particular potential to generate threats to global environmental values and the strengthening of selected value chains through access to financing and sustainable markets as alternatives for generating income and production diversification. This strategy will be piloted in the Northern Honduras Corridor, in a landscape covering 196,000 ha and consisting of production lands and KBAs that are critical for the delivery of GEBs, but where the remaining forests are threatened by the expansion of commercial commodities. The dissemination of knowledge and experiences that result from the implementation of this strategy will contribute to the adoption of best practices for biodiversity conservation, SLM, and gender equality in other production landscapes and sectors. However, the following barriers prevent this objective from being reached:

| Weak territorial governance to sustainably manage landscapes for the production of commercial commodities such as palm oil and beef/dairy | - There is still an incomplete regulatory framework for the implementation of agroforestry systems as part of the national strategy to restore degraded ecosystems and ensure the sustainable delivery of related goods and services. Territorial governance is also limited by the lack of coordination and mechanisms for cooperation between national-, local-, and private sector-level stakeholders; these institutional constraints limit integral territorial planning that gives consideration to environmental benefits, including reduced deforestation and the sustainable production of commercial commodities. In addition, there is legal uncertainty over land tenure (60% of producers do not have full ownership of the land), which limits the implementation of long-term strategies for operationalizing conservation-production strategies. This is further restricted by the lack of financial and market incentives to encourage producers to make use of sustainable production systems and for the restoration of degraded areas that result from poor farming practices in palm oil and beef/dairy production. Platforms such as the National Sustainable Palm Oil Platform, the Sustainable Livestock Farming Regional Roundtables, and the Environmental Innovation Center must be strengthened so that they may promote sustainable production systems among the associated producers. This would include providing producers with the training and tools that will lead to the accreditation of deforestation-free products through RSPO certification (in the case of palm oil), only until recently has been introduced in the country. Certification would also be made possible through the development of national green labels that provide a low-cost alternative to lengthy third-party international certification, which small and medium producers typically cannot afford. Finally, Honduras has not define LDN goals and lacks a framework to move forward to defining these goals. |
| --- | --- |
| Limited available tools to restore degraded lands and ecosystems that result from non-sustainable agricultural and livestock production practices | Despite a national commitment to restore degraded lands and ecosystems, including 1 million ha as part of the Bonn Challenge, there has been limited progress in achieving this goal. The proper landscape management tools (LMTs) are lacking, which would be used to help restore ecosystem connectivity and degraded soils using conservation agreements that have producers commit to restoring degraded lands using financial incentives and market mechanism, as well as small grants to local communities and vulnerable groups that have limited access to the national-level financial mechanisms. In the case of the Northern Honduras Corridor, there is a lack of region-specific restoration plans that implement restoration practices already defined in the National Program for the Recovery of Degraded Ecosystems’ Goods and Service 2018-2028. Producers, local communities, and vulnerable groups in the region lack the training to implement LMTs for restoration, including the implementation of agroforestry systems that promote production alternatives to traditional agriculture and livestock production practices, and diversification of farms. Finally, there is limited knowledge on the part of decision makers and other key stakeholders on the use of technical tools for measuring the benefits of biodiversity conservation and reduced land degradation that would result from the restoration of degraded lands using LMTs and from implementing sustainable agroforestry systems. |
| Limited availability of incentives to promote sustainable value chains with environmental and social benefits | Using incentives to promote sustainable value chains with environmental and social benefits once these are available, would require overcoming organizational, technical, and business management limitations among the producers that use them. There is a lack of sustainable production skills among small palm oil and beef/dairy producers as well as a lack of partnerships with the private sector that would provide security for the commercialization of products free of deforestation; in addition, extension services to support sustainable value chains are lacking, as traditionally these have focused on supporting conventional forms of production. In the case of small-scale palm oil producers that may opt for RSPO certification, there is not much support to help them comply with Principle 5 (Environmental responsibility and conservation of natural resources and biodiversity) of the RSPO. Among small- and medium-scale beef/dairy farmers, there is limited knowledge for implementing intensive silvopastoral systems that would free-up degraded lands to be rehabilitated, while at the same time increasing productivity. Finally, environmental authorities do not have the necessary tools or training, particularly at the local level (i.e., municipalities), to verify deforestation-free production at the proper spatial scales or make the information available to users. |
| Lack of mechanisms for sharing best practices and lessons learned regarding environmental-friendly production practices limits upscaling in other landscapes and other production sectors | There is a lack of mechanisms or platforms for sharing knowledge or targeted knowledge products in the country that would document and systematize best practices and lessons learned about biodiversity conservation, SLM, and gender mainstreaming in production landscapes. As a result, the possibility of replication and upscaling in other landscapes and production sectors is limited. In addition, there is a lack of systematic monitoring of results and limited available data to assess the impact of interventions and to guide future planning and investments. |

2) The baseline scenario and any associated baseline projects

- Baseline investments are valued at USD $53,000,000 for a 7-year period. Baseline projects will provide a foundation for this project. UNDP, FAO, and MiAmbiente+ will build synergies with these initiatives to ensure complementarities and avoid duplication.

- Northeastern Small Producers’ Economic and Social Inclusion Project – PROINORTE (2020-2025) financed by IFAD ($34 million USD), which will increase incomes and improve the living conditions of about 70,000 people through organizational strengthening, technical assistance, and building and/or upgrading rural infrastructure, including providing over 10,000 cookstoves.

- PROCACAHO Project (2019-2022) funded by the Swiss Agency for Development and Cooperation ($8 million USD) aims to promote better income and employment opportunities for producers of cocoa in Honduras through increased production, productivity, and quality of cocoa under agroforestry systems.

- Regional Coastal Biodiversity Project, financed by USAID ($1 million USD) and implemented by the IUCN, will contribute to the conservation of marine-coastal biodiversity in the Northern Honduras Corridor as part of a regional strategy to enhance economic integration with a strong emphasis on investments, leverage funding, and synergies with the private sector, security, stability, and governance.

- BANHPROVI/FIRSA (Trust Fund for the Administration and Investment for the National Program for the Reactivation of the Agro-food Sector of Honduras) will provide financing in the amount of $10 million USD for the cattle farming and palm oil production sectors.

3) The proposed alternative scenario with a brief description of expected outcomes and components of the project

- The project will overcome the previously mentioned barriers by strengthening the enabling and territorial governance framework for the restoration of KBAs and sustainable production areas, and the diversification of palm oil production and cattle farming, thereby restoring degraded areas in palm oil and livestock landscapes and strengthening the selected value chains through access to financing and sustainable markets for palm oil, beef/dairy, and other associated crops. This strategy will be piloted in production landscapes covering 196,000 ha in the Northern Honduras Corridor, where the production of commodities is a primary driver of deforestation and land degradation. Knowledge and lessons learned from implementation will be documented, allowing for the adaptive management of the project and replication and upscaling in other landscapes and sectors in the country.

- Component 1: Strengthening the enabling and territorial governance framework for the restoration of areas of importance for biodiversity and sustainable production and diversification of palm oil production and cattle farming. Through this component, the project will strengthen the policy, institutional, and financial frameworks to sustainably manage production landscapes, emphasizing the restoration of KBAs and sustainable production landscapes, and the diversification of palm oil production and cattle farming in biological corridors. To this end, the project will develop an ICF regulation to clarify the role of agroforestry of systems in ecosystem restoration. This will be complemented by regulation of the ecosystem goods and services recovery program, which will allow for a comprehensive articulation between sustainable production activities and the restoration of KBAs. These regulatory tools will facilitate the implementation of the National Program for the Recovery of Degraded Ecosystems’ Goods and Service 2018-2028, which is already in place. The project will also enhance the existing land tenure interinstitutional accreditation system (e.g., collective and private land titles [including indigenous and afro-Honduran peoples], which will facilitate the implementation of sustainable production systems (including agroforestry systems) and the diversification of production using long-term government or private lease-holds that will provide certainty to producers engaging in sustainable production ventures with long-term investment returns, as is the case with agroforestry. An enhanced land tenure interinstitutional accreditation system will also facilitate access to financing to support sustainable production and restoration of degraded lands and will contribute to reducing conflicts related to land tenure.

- Through this component, the project will strengthen the National Sustainable Palm Oil Platform and the Sustainable Livestock Farming Regional Roundtable in the Northern Honduras Corridor by providing producers with the training and tools to implement sustainable production practices and restore degraded lands. This will include support for the environmental certification (e.g., RSPO) of small producers and cooperatives in KBAs and surrounding landscapes. Similarly, the Environmental Innovation Center will be strengthened through the participation of the government and private sector to enhance support for small producers (including women) in sustainable production and business development, and by establishing for the palm oil and beef/dairy sectors to certify deforestation-free production as an alternative to less affordable certification schemes. Finally, the project will support the development of financial products (e.g., credit lines, green bonds, guarantee funds, impact investment funds, payments by results, etc.) working closely with national financial institutions for the financing of deforestation-free commodity value chains (palm oil and beef/dairy) and the restoration of degraded lands. Business agreements will be established with international and national buyers through public-private partnerships and mechanisms for compliance with environmental, social, and gender safeguards will be developed. Links will be established with the MRV system of the National REDD+ Strategy for documenting how the project contributes to curbing deforestation. The project will establish a framework for Honduras for achieving LDN goals based on validation of baselines for LDN over 196,000 hectares and define an action plan with key stakeholders, which will allow to maintain and restore Honduras land-based natural capital and contribute to biodiversity conservation and to maintain critical ecosystem services. To assess how the project will contribute to enhance national capacities to effectively implement sustainable production and diversification, the UNDP Capacity Development Scorecard will be used; the baseline and targets for the participating stakeholder (palm oil production and cattle farming sectors, and environmental authorities) will be determined during the PPG phase of the project.

- Component 2: Restoring degraded areas in palm oil and livestock production regions with LMTs limits the expansion of these commodities and promotes connectivity and conservation of KBAs in the Northern Honduras Corridor. The strategies and tools developed under Component 1 to restore degraded areas will be put into practice, focusing on selected production landscapes within the Northern Honduras Corridor. Restoration will be achieved using LMTs that enhance the connectivity between KBAs and deliver multiple GEBs. Restoration alternatives will be promoted, such as cocoa in agroforestry systems, assisted natural regeneration, forest enrichment with native species, microcorridors, cultivation of fruit trees, and the establishment of hedges, live fences, and wind barriers, among other environmentally friendly practices. To implement the LMTs, 1,000 conservation and best production practices agreements signed with palm oil and beef/dairy producers and 11 existing nurseries operated by the ICF will be strengthened, and two new nurseries with cooperatives or producers’ associations (including women’s groups) will established, which will provide the germplasm needed to implement the LMTs. In addition, a restoration plan for the Northern Honduras Corridor will be developed that focuses on areas critical for enhancing ecosystem connectivity. The restoration of degraded lands will also include the use of small grants to be awarded to at least 10 community-based organizations and organizations of indigenous and Afro-Honduran peoples (e.g., Garífuna and Pech), including women's groups, which have limited access to financial institutions to implement restoration initiatives in their lands.

- This component will implement best practices for reducing conflicts between producers and jaguars (Panthera onca) that may arise from improved connectivity between KBAs. The project will work with the Panthera Foundation in Honduras, which already has a well-established jaguar monitoring program in the Northern Honduras Corridor. Producers will be trained and a handbook of best practices will be distributed to enhance their coexistence with jaguars. This program will also contribute to the implementation of the National Plan for the Conservation of the Jaguar and the Regional Jaguar Conservation Roadmap for the America; in particular, it will contribute to enhancing connectivity between protected areas and KBAs by focusing on conservation efforts in production landscapes, which jaguars are sometimes required to cross and on reducing conflicts with farmers. Similarly, though this component, the project will support the implementation of best production practices on the project’s farms to promote sustainable alternatives for pepper, rambutan, and cocoa. Finally, a system to monitor the environmental benefits derived from the project will be put into place using multiple tools for evaluating the project’s core indicators and other indicators to evaluate biodiversity conservation and SLM benefits as indicated in Section 6 of this project concept.

- Component 3: Strengthening the selected value chains through access to financing and sustainable markets for palm oil, beef/dairy, and associated crops (cocoa, wood, and fruit) as alternatives for generating income and production diversification that favors sustainable practices and reduces GHG emissions. Through this component, the incentives and  financial and market mechanisms created through Component 1 will be made available to producers to develop sustainable palm oil and beef/dairy value chains and support production diversification (e.g., cocoa, wood, and fruit) with the goal of producing deforestation-free commodities. The project will implement a sustainable production training and extension services program that will benefit 6,000 small and medium producers of palm oil and beef/dairy in key conservation areas. In addition, at least five cooperation partnerships will be established with the private sector, including buyers and businesses related to agroforestry products and processors and retailers to promote and commercialize deforestation-free beef/dairy products. Support will be provided to 500 small and medium beef/dairy farms to implement intensive silvopastoral systems with production diversification through agroforestry systems; tools such as LEAP, GLEAM, L-TFP, and PSM will be used to verify the environmental, social, and economic benefits derived from good beef/dairy production practices. In the case of palm oil production, the project will provide support to at least three cooperatives or groups of small and medium palm oil producers, including women’s groups, so that they can comply with RSPO Principle 5 (Environmental responsibility and conservation of natural resources and biodiversity). By project’s end, it is expected that that the use of incentives and  financial mechanisms made available for sustainable value chains will increase the annual net income of participating small and medium producers of palm oil and beef/dairy. During the PPG, a detailed economic analysis will be completed to assess their feasibility and potential economic impact. In addition, by project’s end it is expected that 196,000 ha of production landscapes will be undergoing improved practices and deforestation will have been avoided on the participating farms. To verify deforestation-free production, the project will operationalize a GIS-based verification system (e.g., Land Use Change Monitoring System within Production Landscapes [MOCUPP]) for palm oil and beef/dairy production, and will provide training to environmental authorities (e.g., MiAmbiente+ and municipalities) for its use. The spatial verification systems will also include a user-friendly interactive online platform to use and share information. The project will overcome the previously mentioned barriers by strengthening the enabling and territorial governance framework for the restoration of KBAs and sustainable production areas, and the diversification of palm oil production and cattle farming, thereby restoring degraded areas in palm oil and livestock landscapes and strengthening the selected value chains through access to financing and sustainable markets for palm oil, beef/dairy, and other associated crops. This strategy will be piloted in production landscapes covering 196,000 ha in the Northern Honduras Corridor, where the production of commodities is a primary driver of deforestation and soil degradation. Knowledge and lessons learned from implementation will be systematized, allowing for the adaptive management of the project and replication and upscaling in other landscapes and sectors in the country.

- Component 4: Knowledge Management (KM), Monitoring and Evaluation (M&E). Through this component, the project will generate a set of KM products around the experiences of restoring degraded areas in production landscapes and promoting deforestation-free commodities while delivering GEBs. Solutions and best practices will be shared through different KM platforms nationally and globally, including the Good Growth Community of Practice, the Conference of the Parties of the Convention on Biological Diversity, and the Panorama Portal “Solutions for a Healthy Planet,” among others. In addition, knowledge and lessons learned will be systematized and made available through at least one document per value chain (palm oil and beef/dairy) for the replication and scaling-up of successful experiences in other production landscapes and biological corridors. Finally, this component will allow the implementation of a project gender mainstreaming plan and M&E plan, including the development of a manual on mainstreaming gender in sustainable production systems by producers, buyers of commodities, and other interested stakeholders.

4) Alignment with GEF focal area and/or Impact Program strategies

- The project is aligned with the GEF Biodiversity Focal Area, more specifically with Objective 1.1: Mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors. In addition, the project is aligned with the GEF Land Degradation Focal Area, more specifically with Objective 1.1: Maintain or improve flow of agro-ecosystem services to sustain food production and livelihoods through SLM; and Objective 3.4: Reduce pressures on natural resources from competing land uses and increase resilience in the wider landscape. The project will contribute to achieving Aichi Targets 1, 3, 4, 5, 7, 8, 12, 14, and 15; it will also contribute to the Sustainable Development Goals: 1, 5, 12, and 15.

5) Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, and co-financing

- The baseline investments described in Section 2 will contribute in some measure to restore areas of importance for biodiversity and reduce deforestation in palm oil and cattle ranching production landscapes. Progress will be made in strengthening small producers’ economic and social conditions in northeastern Honduras and promoting cocoa under agroforestry systems, which will contribute to an extent in restoring degraded lands and improve the income of cocoa producers. Baseline investments will also contribute to the conservation of biodiversity in the Northern Honduras Corridor, but will be limited to coastal areas. In addition, under the baseline financing will be available to cattle farming and palm oil producers but not necessarily directed to promoting sustainable production practices. Financing provided by the GEF will, through Component 1, significantly strengthen the policy, institutional, and financial frameworks to sustainably manage production landscapes, including biological corridors; aspects that are not considered under the baseline. The GEF’s financing will also support specific actions through Component 2 towards the restoration of degraded lands and connectivity and the conservation of KBAs, which will be a significant addition to the baseline. In addition, through Component 3, the GEF’s financing will strengthen the selected value chains through access to financing and sustainable markets for palm oil, beef/dairy, and associated crops, which will add to the baseline in terms of expanding certification opportunities for small and medium producers of palm oil (currently only large producers can afford certification), and expanding opportunities for implementing agroforestry and production diversification. It will also introduce intensive silvopastoral systems to improve productivity with environmental benefits. Overall, the GEF alternative will contribute to the reduction of deforestation from the expansion of selected commodities in the Northern Honduras Corridor that otherwise would remain unchecked under the baseline. These actions, which will be implemented during a 7-year period with a GEF investment of $10,011,009 USD and $103,000 million USD in cofinancing, will be added to the baseline investments delivering the GEBs that are described in the following section.

6) Global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF)

| Current practices (baseline) | Alternative proposed by the Project | Anticipated GEBs |
| --- | --- | --- |
| Weak policy, institutional, and financial frameworks | Policy, institutional, and financial frameworks strengthened to sustainably manage production landscapes, including biological corridors | - 196,000 ha of palm oil and beef/dairy production under improved practices - 30,000 ha of degraded areas restored - Improved ecological integrity index the near-threatened jaguar - Presence of hawks (Buteo sp.) confirmed - Stable presence of Odonata (dragonflies) indicates the good ecological condition of freshwater ecosystems - Reduction of the erosion rate by X% by project’s end - XX ha of deforestation avoided as a result of sustainable palm oil and beef/dairy value |
| Increase in fragmentation of natural ecosystems due to the expansion of palm oil and beef/dairy production | Enhanced connectivity between KBAs using LMTs, including agroforestry. |  |
| Commodity supply chains without consideration of environmental impacts. RSPO certification for palm oil has been introduced into the country only recently; there are no certification schemes for beef/dairy production. | Deforestation-free commodity supply chains enabled through best practices and certification. |  |
| Incentives are not being considered to promote environmentally friendly production practices and financing available; BANHPROVI and other financial institutions only support conventional agricultural practices. | Use of incentives and financial mechanisms involving BANHPROVI, other financial institutions, the private sector, and small and medium farmers to produce deforestation-free commodities. |  |
| Limited capacity of public institutions and the private sector to mainstream biodiversity into production lands and reduce land degradation. | Institutional capacity in place to mainstream biodiversity into production landscapes, use information to support biodiversity conservation, and SLM. |  |
| Limited monitoring of environmental threats in the Northern Honduras Corridor, including deforestation. | Enhance monitoring of environmental threats in the Northern Honduras Corridor, including deforestation at fine/farm scales. |  |

7) Innovation, sustainability and potential for scaling-up

- This project is innovative as an inclusive business model for small producers that will result in enhanced social and environmental benefits. Links between financial institutions and best practices in the production chains of selected commodities will allow producers to better position their products in markets. In addition, the use of a variety of tools to verify project performance, including the Livestock Environmental Assessment Performance Partnership (LEAP), Global Livestock Environmental Assessment Model (GLEAM), the Ex-Ante Carbon-balance Tool (EX-ACT), Total Factor Productivity-Livestock (L-TFP), Propensity Score Matching (PSM), and a spatial verification system similar to the MOCCUP that was developed in Costa Rica to monitor forest cover loss/gains in production lands, will add to the project’s innovative approach. Further innovations are the stakeholder forums for dialogue, supporting a framework for knowledge management and replication across the country, and institutional strengthening and communication strategies. Institutional sustainability will be achieved by strengthening policy, institutional, and financial frameworks to sustainably manage production landscapes. New regulations, incentives, and financial instruments to incentivize biodiversity conservation, restore degraded lands, and practice sustainable production will contribute to the project’s financial sustainability. Strengthened capacity of public, private sector, and civil society stakeholders at the national and local levels through improved tools for territorial planning, implementation of LMTs, sustainable production of palm oil and beef/dairy and other crops, and improved monitoring through the use of multiple tools and training of environmental authorities will reduce deforestation and ensure environmental sustainability. The project has a high potential for replicability. The project is designed to be scaled up within Honduras after the initial demonstration in the selected project area. A framework for replicability is already built into the project through Component 4. This will serve both for the project monitoring and to build a results framework and to generate knowledge for continuous learning. Good practices and lessons learned will be disseminated to a broader range of stakeholders through communication channels such as websites, information networks, fora and publications, among others, to support replication and scaling-up.

1b. Project Map and Coordinates. Please provide geo-referenced information and map where the project interventions will take place.

- Please refer to Annex A.

2. Stakeholders. Select the stakeholders that have participated in consultations during the project identification phase:

Indigenous Peoples and Local Communities;

Civil Society Organizations;

Private Sector Entities;

If None of the above, please explain why.

| Stakeholder | Role in the project |
| --- | --- |
| Secretariat of Natural Resources and Environment (MiAmbiente+) | MiAmbiente+ will be the project execution agency and will coordinate project execution in partnership with strategic partners. The agency will also provide guidance and technical for project implementation, monitoring of results, as well as presentation of project progress reports. |
| Agriculture and Cattle Farming Secretariat (SAG) | SAG will provide technical support for implementing sustainable production activities and facilitate access to incentives for producers. Additional consultation will be conducted during the PPG to further assess the role of SAG in the project. |
| National Institute of Forest Conservation and Development, Protected Areas and Wildlife (ICF) | ICF will play a key role in providing technical support for the restoration of degraded areas in palm oil and livestock landscapes with LMTs, including agroforestry and the operation of nurseries. |
| Association of Municipalities of Honduras (AMHON) and municipalities. | AMHON will provide technical support to the municipalities participating in the project, in particular for environmental licensing and monitoring of project activities related to sustainable production within their jurisdiction. Municipal Environmental Units will benefit from training to enhance capacity for permitting, and monitoring and control. |
| National Agrarian Institute (INA) | INA will coordinate with the ICF and MiAmbiente+ to provide access to information about land tenure and will lead the development of an enhanced land tenure interinstitutional accreditation system. |
| Financial sector organizations | Financial sector organizations will be instrumental in the development of financial products and will support investment opportunities for the small producers who participate in the project, and will implement sustainable production practices associated with selected commodities. These may include the Honduran Association of Banking Institutions (AHIBA), the Honduran Bank for Production and Housing (BANHPROVI), and the Honduran Federation of Savings and Loans Cooperatives (FACACH). |
| CSOs and NGOs | Multiple CSOs and NGOs work in the project area that will provide information and knowledge regarding SLM, biodiversity conservation, and sustainable production practices. These include the Organization of the Garífuna People, the Honduran Broadleaf Forest Management Network (REMBLAH), co-managers of protected areas within the project area, the INGA Foundation, the Foundation for Rural Business Development (FUNDER), and international organizations such as Solidaridad, the IUCN, and the Wildlife Conservation Society (WCS). During the PPG a more detailed mapping of the CSOs and NGOs that are present will be completed. |
| Research institutions | Research institutions will contribute with information about vulnerable KBAs, degraded lands, monitoring of biodiversity, and best sustainable agricultural practices. These may include the University of Forest Sciences (UNACIFOR), the National University of Agriculture (UNA), the National Autonomous University of Honduras (UNAH/CURLA), and the Honduras Foundation for Agricultural Research (FHIA). The Panthera Foundation Honduras will provide technical assistance for the conservation and monitoring of the jaguar in the prioritized landscape. |
| Private Sector | The private sector will support and promote the adoption of sustainable production practices by producers The private sector be a direct beneficiary of the project through the Sustainable Livestock Farming Regional Roundtable and the National Sustainable Palm Oil Platform. The sector will be represented through the National Association of Foresters of Honduras (ANASILH, the Federation of Agroforestry Producers of Honduras (FEPROAH), the Association of Honduran Cocoa Producers (APROCAHO), the Honduran National Federation of Ranchers and Farmers (FENAGH), the Industrial Association of Oil Producers of Honduras (AIPAH), the RSPO Oil Palm Committee, and local associations of cattle farmers. During the PPG a more detailed mapping of the private sector present will be completed. |
| Local Communities and Community Organizations | These organizations will be beneficiaries of training and education activities and incentives to promote sustainable production practices. Community-based organizations and organizations of indigenous and Afro-Honduran peoples (e.g., Garífuna and Pech), will receive small grants to support the recovery of goods and ecosystem services on degraded lands. Additional consultations will be conducted during the PPG to define their roles in strengthening territorial governance at the local level, restoring degraded ecosystems, and sustainable production and diversification. |

3. Gender Equality and Women’s Empowerment.  Briefly include below any gender dimensions relevant to the project, and any plans to address gender in project design (e.g. gender analysis). Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women empowerment?  yes  /no  / tbd  ; If possible, indicate in which results area(s) the project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision-making; and/or

generating socio-economic benefits or services for women.

Will the project’s results framework or logical framework include gender-sensitive indicators? yes /no  / tbd

- Women often take the lead in the selection and improvement of local production and in the more remote areas and they possess extensive knowledge of their location. The project recognizes that roles for women and men in natural resource management are different. Women will play a central role during project implementation, as they will be beneficiaries of incentives, technical support, and training for implementing palm oil and beef/dairy cattle production, as well as from restoration activities and production diversification, including agroforestry sustainable alternatives for pepper, rambutan, and cocoa. The project will ensure food security for women and their families by supporting sustainable agriculture practices and increasing the income of small and medium women producers of sustainable palm oil and beef/dairy. In addition, women’s groups, including indigenous and Afro-Honduran women, will receive small grants to support the recovery of goods and ecosystem services on degraded lands. Consultations were held at the national level with high participation of women. Consultations will continue during the PPG phase, including at the local level, and a gender expert will be hired to conduct a gender analysis for the Northern Honduras Corridor that includes information disaggregated by sex. This consultant will then develop a Gender Action Plan with gender-based indicators. Both women and men will benefit from this project, thus creating a gender-based governance framework for biodiversity conservation and SLM.

4. Private sector engagement. Will there be private sector engagement in the project? (yes  /no ).

- Participation by the private sector will be essential for restoring ecologically sensitive areas and reducing deforestation in palm oil and cattle ranching production landscapes. Initial consultations were conducted and will continue during the PPG phase so that financial mechanisms can be designed jointly with the financial sector and to commit companies and producers of palm oil and beef/dairy to invest in sustainable production and implement restoration and diversification actions. During project implementation, business agreements with international and national buyers will be promoted through public-private partnerships and access to loans through national banks (e.g., BANHPROVI) as part of a strategy for financing deforestation-free commodity value chains. Also, a Stakeholder Engagement Plan will be developed in which mechanisms to involve the private sector will be further defined, as well as their role as project co-financiers, which may include palm oil and beef/dairy processors and buyers such as LACTHOSA, LEYDE, ENGAHSA, HONDUPALMA, and UNPALA.

# 5. Risks.

| Risk | Level* | Risk Mitigation Strategy |
| --- | --- | --- |
| The potential outcomes of the project are sensitive or vulnerable to the potential impacts of climate change | M | Connectivity between KBAs will be enhanced, improving the resilience of biodiversity through increasing species’ mobility and providing refuge against climate variability. SLM and environmentally friendly production practices will create stable conditions that benefit vulnerable biodiversity, production systems, and human populations. |
| Limited interest by palm oil and beef/dairy sectors to adopt sustainable production practices | L/M | The project will work with the palm oil and beef/dairy sectors and landowners to generate increased awareness about the importance of biodiversity conservation and SLM, and will make incentives available (e.g., access to financing, tax exemptions, training, technical assistance, etc.) to encourage the use of environmentally friendly production practices and develop deforestation-free agricultural commodity supply chains. Training will also be delivered to support these goals. |
| Duty-bearers (municipal authorities and farmers) may not have the capacity to meet their obligations in the project | M | The project design includes several outputs related to strengthening territorial governance. In addition, the project includes training and technical assistance for the implementation of sustainable production systems and the restoration of degraded areas. During the PPG, training and technical assistance needs will be fully assessed and strategies will be defined and included in the final project design. |
| Poorly designed or executed project activities could damage critical or sensitive habitats, including introduction of invasive alien species (IAS) during restoration activities | M | The project will restore degraded ecosystem within and outside KBAs. The project will only use native species during restoration efforts and will make use of selected nurseries to provide the right germplasm and avoid the introduction of IAS. |
| Indigenous people might not be involved in project design and therefore not engaged in, supportive of, or benefitting from project activities; Free, Prior and Informed Consent (FPIC) has not yet been applied | H | During the PPG phase of the project, the full extent of indigenous peoples’ participation in production of palm oil, beef/dairy, other related products, and agroforestry in the prioritized landscape within the Northern Honduras Corridor will be assessed. If FPIC is determined to be a requirement, consultations will then be carried out with the objective of achieving initial consent from the specific rights-holders. FPIC would then be continued during project implementation. In addition, an Indigenous Peoples Plan will be developed together with an ESMP during the PPG. |
| The project does not effectively incorporate gender considerations | L | During the PPG a gender analysis will be performed to identify the needs and expectations of women with respect to biodiversity conservation and SLM. A gender analysis will be conducted, a Gender Action Plan will be developed, and gender safeguards will be further defined. |

* L = low; M = moderate; H = high

# 6. Coordination.

- UNDP and FAO will be the implementing agencies responsible for the project, including its monitoring and evaluation following GEF guidelines. The Implementing Partner for this project is the Secretary of Energy, Natural Resources, Environment and Mining (MiAmbiente+), who will be responsible for documenting project progress against agreed-upon work plans in accordance with the reporting schedule and formats. The IUCN and UN Environment will act as responsible parties. It is expected that all these organizations will be part of the Project Board, which will provide overall guidance and direction to the project. During the PPG, the complete institutional structure of the project will be outlined and a detailed project M&E plan and budget will be defined.

- Actions will be coordinated with the GEF6/UNDP project (2018-2025) Agroforestry Landscapes and Sustainable Forest Management that Generate Environmental and Economic Benefits Globally and Locally (GEF Project ID 9262), which aims to strengthen the connectivity between protected areas and production landscapes to generate environmental, social, and economic benefits in the dry-humid biological corridor of southwestern Honduras. Lessons learned and experiences will be exchanged regarding the implementation of sustainable production systems, biodiversity conservation and ecosystem connectivity, and restoration strategies.

- Actions will also be coordinated with the GEF5/UNDP project (2018-2025) Delivering Multiple Global Environment Benefits through Sustainable Management of Production Landscapes (GEF Project ID 4590), which aims  to mainstream biodiversity conservation, sustainable land management, and carbon sequestration objectives into production landscapes and sectors in humid broadleaved and dry zone agroecosystems

- The project will also consider lessons learned from the implementation of the GEF/World Bank project Mainstreaming Biodiversity in Sustainable Cattle Ranching (GEF Project ID 3574) regarding the use of agro-silvopastoral systems that combine trees, shrubs, and various herbaceous plant species to improve the sustainability and productivity of farms combining agriculture and cattle production, while creating an environment that is vastly more hospitable to biodiversity and is carbon-friendly.

- The project will also make use of lessons learned and best practices resulting from the implementation of the GEF Small Grants Program in Honduras. These will include experiences in biodiversity conservation on cattle farms, diversification of production, biodiversity habitat conservation, and restoration of degraded lands, among other related topics.

- The project will also coordinate actions with the Jaguar Corridor Initiative for the preservation of the genetic integrity and future of the jaguar by connecting and protecting core jaguar populations from Mexico to Argentina.

7. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no  ).

- Honduras ratified the CBD on 29 October 1995. The project is consistent with the National Biodiversity Strategy and Action Plan (NBSP), which recognizes biodiversity conservation as a pillar for development and the reduction of the poverty and promotes the creation of biological corridors to generate connectivity between KBAs and production landscapes. The NBSP also prioritizes agrobiodiversity to transform food production systems, including the sustainable use of livestock, forestry, and agricultural resources. The project will contribute to achieve these goals of the NBSP.

- Honduras ratified the UNCCD on 25 June 1997. The project is consistent with the National Action Program (NAP) 2005-2021 under the UNCCD, which aims at facing in a comprehensive and sustained way the causes of the degradation of natural resources that promote land degradation and desertification. The project is consistent with the NAP’s pillars for generating resilient food production systems; planning, conservation, and reforestation in watersheds; and institutional strengthening and development of local capacities.

- Honduras ratified the UNFCCC on 19 October 1995. Honduras is one of the first countries in Latin America to join the Nationally Determined Contribution (NDC) Partnership and develop a road map for the fulfillment of its NDCs as part of the Paris Agreement/UNFCCC. This includes the commitment to reduce GHG emissions from the agricultural production sector by 15% and to restore 1 million ha affected by deforestation and forest degradation, including 480,000 ha associated with sustainable oil palm and cattle farming nationwide. The project is consistent with the NDC and will contribute to achieving the related country’s commitments.

- The project is also consistent with EN-REDD+, which  promotes the restoration of landscapes that have been degraded and deforested due to the production of commodities such as palm oil and beef/milk. Similarly, the project is consistent with the National Program for the Recovery of Degraded Ecosystems’ Goods and Services, created though Ministerial Agreement No. 1030-18 of MiAmbiente+, which outlines strategic options for restoring areas in northern Honduras where the proposed project will be implemented.

8. Knowledge Management.

- Knowledge management activities will be part of Component 4 and will include the systematization of the knowledge generated and the sharing of lessons learned, including women’s experiences. Knowledge products/ publications will be developed. Results from the project will be shared within and beyond the project intervention area through a number of existing information-sharing networks and forums. The project may participate in UNDP-FAO-GEF sponsored networks that are organized for senior staff working on similar projects and in scientific and/or other networks that may be of benefit to project implementation. Identifying and analyzing lessons learned is an ongoing process, and the need to communicate lessons as one of the project's central contributions is a requirement to be delivered at least every 12 months.

part iii:  approval/endorsement by gef operational focal point(s)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP 
      endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Rosibel Martínez Arriaga | Director of External Cooperation and Resource Mobilization | Secretariat of Energy, Natural Resources, Environment and Mines | 4/5/2019 |

Annex A

PROGRAM/PROJECT MAP AND GEOGRAPHIC COORDINATES

(when possible)

Annex B

GEF 7 Core Indicator Worksheet

| Core Indicator 3 | Area of land restored (Areas restored include ecologically sensitive areas [e.g., wetlands and riparian forests] degraded by non-sustainable production and rehabilitated using landscape management tools - LMTs [e.g., microcorridors, forest enrichment, hedges, live fences, wind barriers, and agroforestry systems]) |  |  |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Hectares (3.1+3.2+3.3+3.4) |  |  |  |  |  |
|  |  |  | Expected |  |  | Achieved |  |  |
|  |  |  | PIF stage |  | Endorsement | MTR |  | TE |
|  |  |  | 30,000 |  |  |  |  |  |
| Indicator 3.1 | Area of degraded agricultural land restored |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
|  |  |  |  | 15,000 |  |  |  |  |
| Indicator 3.2 | Area of forest and forest land restored |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
|  |  |  |  | 15,000 |  |  |  |  |
| Indicator 3.3 | Area of natural grass and shrublands restored |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
| Indicator 3.4 | Area of wetlands (including estuaries, mangroves) restored |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
| Core Indicator 4 | Area of landscapes under improved practices (hectares; excluding protected areas) (Landscapes under improved practices include areas with sustainable production of palm oil and beef/dairy production [including intensive silvopastoral systems with production diversification], and farms under good practices to promote sustainable alternatives for pepper, rambutan, and cocoa production). |  |  |  |  |  |  | (Hectares) |
|  |  |  | Hectares (4.1+4.2+4.3+4.4) |  |  |  |  |  |
|  |  |  | Expected |  |  | Expected |  |  |
|  |  |  | PIF stage |  | Endorsement | MTR |  | TE |
|  |  |  | 166,000 |  |  |  |  |  |
| Indicator 4.1 | Area of landscapes under improved management to benefit biodiversity |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
|  |  |  |  | 166,000 |  |  |  |  |
| Indicator 4.2 | Area of landscapes that meet national or international third-party certification that incorporates biodiversity considerations |  |  |  |  |  |  | 15,000 |
| Third party certification(s): Roundtable on Sustainable Palm Oil (RSPO) certified 7,500 ha.National Green Label certified 7,500 ha. |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
|  |  |  |  | 7,500 |  |  |  |  |
|  |  |  |  | 7,500 |  |  |  |  |
| Indicator 4.3 | Area of landscapes under sustainable land management in production systems |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
| Indicator 4.4 | Area of High Conservation Value Forest (HCVF) loss avoided |  |  |  |  |  |  |  |
|  |  |  |  | Hectares |  |  |  |  |
|  |  |  |  | Expected |  |  | Achieved |  |
|  |  |  |  | PIF stage | Endorsement |  | MTR | TE |
| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  |  |  | Women 64,800; Men 97,200 Total: 162,000 |
|  |  |  |  |  |  |  | Number Achieved |  |
|  |  |  |  |  |  |  | MTR | TE |
|  |  |  |  |  | Female |  |  |  |
|  |  |  |  |  | Male |  |  |  |
|  |  |  |  |  | Total |  |  |  |

Annex C

Project Taxonomy Worksheet

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 0 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 0 |
|  |  |  | Climate Change Adaptation 2 |

Landscape management tools (LMTs) for biodiversity conservation in production landscapes are landscape elements that create or improve habitat, increase functional connectivity, or comply simultaneously with these functions to benefit the native biodiversity [Lozano-Zambrano, F. H. (ed). 2009. Herramientas de manejo para la conservación de biodiversidad en paisajes rurales. Instituto de Investigación de Recursos Biológicos Alexander von Humboldt y Corporación Autónoma Regional de Cundinamarca (CAR). Bogotá, D. C., Colombia. 238 p.]).

Nombre de Dios National Park (NP),  Pico Bonito NP, Texiguat Wildlife Refuge (WR), Cuero y Salado NP; Lancetilla Botanical Garden, and Janett Kawas NP.

DiBio. 2017. Estrategia Nacional de Diversidad Biológica y Plan de Acción 2018-2022. Dirección General de Biodiversidad (Mi Ambiente). Tegucigalpa, Honduras.

Estrategia Nacional de Bienes y Servicios Ambientales de Honduras

http://www.worldbank.org/en/country/honduras/overview

Análisis de Causas de Desforestación y Degradación de Honduras . ONU REDD Honduras. 2018.

http://www.miambiente.gob.hn/blog/view/mapa-nacional-de-degradacion-de-tierras.

Plan de Acción Nacional de Lucha Contra la Desertificación (PAN) Honduras 2005-2021.

Global Climate Risk Index 2018. https://germanwatch.org/sites/germanwatch.org/files/publication/20432.pdf.

Propuesta Nivel de Referencia de las Emisiones Forestales por Deforestación en la República de Honduras. Gobierno de la Republica de Honduras, 2017.

DiBio. 2017. Estrategia Nacional de Diversidad Biológica y Plan de Acción 2018-2022. Dirección General de Biodiversidad (Mi Ambiente). Tegucigalpa, Honduras.