This document presents data and text fields to be entered by the Implementing Agency in the GEF Portal, separately from the any related Agency report to be uploaded. Please note that all content shared in this document will be shared publicly on the GEF website. If you wish to share annexes with a smaller audience (e.g., GEFSec only), please do so as an attachment to the PIR in the GEF Portal, selecting the desired level of disclosure.

Word limits are strictly enforced.

[Instructions in grey and square parentheses to be deleted.]

| I |  | OVERVIEW |
| --- | --- | --- |

| A |  | Description |
| --- | --- | --- |

| Project Title: | Advanced Minamata Assessment in Thailand |  |  |
| --- | --- | --- | --- |
| Fiscal Year: | FY25 | Project Type: | EA |
| Country(ies) | Thailand | UNIDO ID | 190139 |
| Executing Agency(ies) | UNIDO | UNIDO Project Manager | Ozunimi Iti |
| GEFID | 10983 |  |  |

| Project Objective | Strengthen national capacity to fulfil obligations under the Minamata Convention on Mercury and promote effective implementation of its provisions. |
| --- | --- |
| Project Summary | This project sets out the activities necessary to prepare an Advanced Minamata Assessment to support efficient and effective implementation of the Minamata Convention within the national context. The project will assist Thailand to plan these post-accession activities while mainstreaming sound mercury management into legal and institutional structures which are fully in line with national priorities. The initiative will also help the country to collect baseline information on mercury use, emissions and releases that will serve as input to the design of future interventions required by the treaty, such as the development of a National Action Plan that may be required by the Conference of Parties within a few years of its entry into force. The planned Outputs are listed below: Output 1.1.1: National inventory of emissions and releases of mercury and mercury compounds (level 2 and in accordance with article 8 of the Convention) developed and key sectors identified for intervention: Output 1.1.2: National implementation plan (in accordance with Article 20 of the Convention and including national plan for controlling emissions and releases in accordance with Articles 8 and 9 of the Convention) and priorities for action on Mercury management drafted and put forward for endorsement: Output 1.1.3: Information disseminated, and awareness raised to increase understanding and involvement of relevant stakeholder groups (public and private sector, academia and civil society): |

| B |  | Ratings and Disbursements |
| --- | --- | --- |

|  | FY24 | FY25 |
| --- | --- | --- |
| Implementation Progress (IP) Rating: | Unknown | Moderately Satisfactory (MS) |
| IP Rating justification: | Project execution is in early stages with the recruitment if the necessary project staff and the engagement of services of national experts to carry out baseline data collection. Full execution will begin in the second half of 2025. Initial delays were the result of a request for a major amendment by the GEF OFP and the initially stipulated executing entity. |  |
| Development Objective (DO) Rating: | Unknown | Moderately Satisfactory (MS) |
| DO Rating justification: | Project execution is in early stages with focused on baseline data collection for mercury emissions in line with Minamata Convention guidelines. |  |
| Overall Risk Rating: | Choose an item. | Low Risk (L) |
| Overall Risk Rating justification: | Thailand is committed to mercury reduction and formally ratified the Minamata Convention in June 2017 and began legal implementation in September 2017, classifying mercury and mercury containing wastes as hazardous under national. It is actively reducing dental amalgam use, building capacity through GEF funded projects, and strengthening institutional frameworks to meet Convention obligations. |  |

| Project Financing: | USD 500 000 |  |  | Cumulative Disbursement: | GEF Trust Fund: 0 N/A |
| --- | --- | --- | --- | --- | --- |
| Cumulative Co-Financing mobilized up to FY25: | N/A | Original Co-financing: | USD $41 250 | Agency Fee: | USD 47 500 |

| C |  | Project Milestones |
| --- | --- | --- |

| UNIDO Approval Date: | 10/6/2022 | Implementation Start Date: | 12/21/2022 |
| --- | --- | --- | --- |
| First Disbursement Date: | N/A | Expected Completion Date: | 9/30/2026 |
| Original Completion Date: | 12/21/2024 | Expected Financial Closure Date | 12/31/2026 |
| Original Project Duration: | 24 months | Project Duration in FY25: | 36 months |

| II |  | PROGRESS STATUS AND ISSUES |
| --- | --- | --- |

| A |  | Progress: Information on progress outcomes of project implementation activities |
| --- | --- | --- |

Narrative assessment

[Provide max 250 words, focusing exclusively on outputs with progress in FY25. Use a bullet point format.] Following discussions on the project implementation and executing modalities in the previous year UNIDO received a request by the GEF OFP for a major amendment in the project executing entity from the Pollution Control Division to UNIDO. UNIDO notified GEF of the request for major amendment and submitted a new budget table explicating the project execution structure. GEF gave all clear for UNIDO to revise the project document on the GEF Portal. UNIDO submitted all revisions and received approval of the new project document. Following GEF re-approval in FY2025 UNIDO conducted meetings with national stakeholders and UNIDO Thailand Field Office on how to best develop the TORs for the national and international expertise required for project execution in a way that responds to national needs and priorities. Some of the necessary TORs were more complex and needed several iterations and input from UNIDO Procurement. The TORs were finalized and the request for proposals and recruitments are ongoing. FY25 activities have focused on start-up activities for achievement of Output 1.1.1: “National inventory of emissions and releases of mercury and mercury compounds (level 2 and in accordance with article 8 of the Convention) developed and key sectors identified for intervention:” through the set-up of coordination mechanisms such as the recruitment of a National Project Coordinator, establishment of the Project Management Unit and the Project Steering Committee. The activities that will be prioritized in the next few months include those specified in the project document: Activity 1.1.1.1: Conduct project coordination meetings; Activity 1.1.1.2: Establish Project Steering Working Group; Activity 1.1.1.3: Conduct national mercury inventory trainings (level 2); Activity 1.1.1.4: Collect data for the national mercury inventory (level 2); Activity 1.1.1.5: Develop national mercury inventory database; Activity 1.1.1.6: Produce a national material flow of mercury and identify key sectors for intervention.

Possible extensions

[Provide max 100 words, clarifying if the project is facing delays and is expected to request an extension. Use a bullet point format.]

| B |  | Challenges: Information on challenges of project implementation activities |
| --- | --- | --- |

Narrative assessment

[Provide max 250 words, focusing exclusively on FY25 implementation progress and related challenges. Use a bullet point format.] Following GEF re-approval in FY2025 UNIDO conducted meetings with national stakeholders and UNIDO Thailand Field Office on how to best develop the TORs for the national and international expertise required for project execution in a way that responds to national needs and priorities. Some of the necessary TORs were more complex and needed several iterations and input from UNIDO Procurement. The TORs were finalized and the request for proposals and recruitments are ongoing. Going forward the project team will fast track all procurement and recruitment activities and ensure the processes are carried out efficiently and feedback is received in a timely manner.

| C |  | Stakeholder Engagement |
| --- | --- | --- |

Narrative assessment

[Provide max 250 words, focusing exclusively on FY25 stakeholder engagement activities. This should include any formal feedback provided by national counterparts, GEF OFP, co-financiers, and other partners/stakeholders of the project (e.g. private sector, CSOs, NGOs, etc.). Use a bullet point format.] N/A Regular communications with the Pollution Control Division to consult on the Terms of Reference for recruitment and services. Please see attached letter from Pollution Control Division confirming no cost extension of project. - 10983_Letter-extension_MIA project

| D |  | Gender Equality |
| --- | --- | --- |

Narrative assessment

[Provide max 250 words, focusing exclusively on FY25 actions to promote gender equality, notably on implementing gender-responsive measures and using gender-sensitive indicators, as documented at CEO Endorsement/Approval (in the project results framework, gender action plan or equivalent). Use a bullet point format.] N/A

| E |  | Knowledge Management |
| --- | --- | --- |

Narrative assessment (This section is specific to GEF-7 Impact Programs and GEF-8 Integrated Programs)

[Provide max 250 words, focusing exclusively on FY25 actions for knowledge management activities/products. Use a bullet point format. Do not share links to materials that you wish to not be publicly shared, or to repositories hosted on non-public platforms.] N/A

| D |  | Reflows (for NGIs only) |
| --- | --- | --- |

Narrative assessment

[Exclusively for projects using non-grant instruments, provide max 250 words focusing exclusively on FY25 use of such funds. Use a bullet point format.]

| III |  | Minor Amendments |
| --- | --- | --- |

[Please, briefly elaborate on any minor amendments to the approved project that may have been introduced during the implementation period or indicate as not applicable (NA). As described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines, minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5%.

Please tick each category for which a change has occurred and provide a description of the change in the related textbox. You may attach supporting documentation, as appropriate.]

| Results Framework: | N/A |
| --- | --- |
| Components and Cost | N/A |
| Financial Management: | N/A |
| Implementation Schedule: | N/A |
| Executing Entity: | Major amendment of executing entity from Pollution Control Division to UNIDO |
| Executing Entity Category: | Now a GEF Agency (UNIDO) |
| Minor Project Objective Change: | N/A |
| Safeguards: | N/A |
| Risk Analysis: | N/A |
| Increase of GEF Financing up to 5%: | N/A |
| Co-Financing: | N/A |
| Location of Project Activity: | N/A |
| Others: | N/A |

| IV |  | Geographic Coordinates of Project Activities |
| --- | --- | --- |

[Kindly replicate the table below for each location relevant to the project.

The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure.

The Location & Activity Description fields are optional.

Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate.

Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as:  https://coordinates-converter.com

Please see the Geocoding User Guide by clicking here.]

| Location Name: | Thailand |  |  |
| --- | --- | --- | --- |
| Latitude: | N 15°30′00″ | Longitude: | E 101°00′00” |
| GeoName ID: | 1605651 |  |  |
| Location Description: | Enabling Activity |  |  |
| Activity Description: | Project activities will be carried out throughout Thailand in key mercury hotspots and areas where mercury data collection needs to take place or where key stakeholders are located. |  |  |

| V |  | Synergies and success stories |
| --- | --- | --- |

Synergies achieved

Thailand’s Minamata Initial Assessment will provide a comprehensive national mercury profile, identifying key sources, emissions, and regulatory gaps. It will guide the development of policies, capacity-building, and public awareness campaigns to support national mercury reduction. Regionally, Thailand will continue to play a leading role by fostering collaboration and knowledge-sharing in the Asia-Pacific, promoting harmonized approaches to mercury management. Globally, the assessment will contribute to the implementation of the Minamata Convention by supporting standardized reporting, inventory methodologies, and international cooperation. This will strengthen Thailand’s commitment to reducing mercury pollution and enhance global efforts to protect human health and the environment.

Success stories and communication materials

[Provide max 100 words.] N/A

|  |  | ANNEXES |
| --- | --- | --- |

Uploaded Document

[Kindly provide a bullet point list of all annexes attached to this PIR in the GEF Portal. Do not report content a second time if it has already been deliberately shared via links in the PIR itself.] 10983_Letter-extension_MIA project 10983_2025_Grant Delivery Report 10983_2025_ Budget

Financial implementation

[Provide information pertaining to the financial implementation progress of the project (e.g., Grant Delivery Report screenshot. *Please provide this as a separate attachment] Attached as 10983_2025_Grant Delivery Report

Workplan and budget

[Provide an updated project work plan and budget for the remaining duration of the project, as per last approved project extension *Please provide this as a separate attachment.] Attached as 10983_2025_ Budget

Explanatory note

- Timing & duration: Each report covers a twelve-month period, i.e. 1 July 2022 – 30 June 2023.

- Responsibility: The responsibility for preparing the report lies with the project manager in consultation with the Division Chief and Director.

- Evaluation: For the report to be used effectively as a tool for annual self-evaluation, project counterparts need to be fully involved. The (main) counterpart can provide any additional information considered essential, including a simple rating of project progress.

- Results-based management: The annual project/programme progress reports are required by the RBM programme component focal points to obtain information on outcomes observed.

| Global Environmental Objectives (GEOs) / Development Objectives (DOs) ratings |  |
| --- | --- |
| Highly Satisfactory (HS) | Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice”. |
| Satisfactory (S) | Project is expected to achieve most of its major global environmental objectives, and yields satisfactory global environmental benefits, with only minor shortcomings. |
| Moderately Satisfactory (MS) | Project is expected to achieve most of its major relevant objectives but with either significant shortcomings or modes overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environmental benefits. |
| Moderately Unsatisfactory (MU) | Project is expected to achieve some of its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives. |
| Unsatisfactory (U) | Project is expected not to achieve most of its major global environmental objectives or to yield any satisfactory global environmental benefits. |
| Highly Unsatisfactory (HU) | The project has failed to achieve, and is not expected to achieve, any of its major global environmental objectives with no worthwhile benefits. |
| Implementation Progress (IP) |  |
| Highly Satisfactory (HS) | Implementation of all components is in substantial compliance with the original/formally revised implementation plan for the project. The project can be presented as “good practice”. |
| Satisfactory (S) | Implementation of most components is in substantial compliance with the original/formally revised plan except for only few that are subject to remedial action. |
| Moderately Satisfactory (MS) | Implementation of some components is in substantial compliance with the original/formally revised plan with some components requiring remedial action. |
| Moderately Unsatisfactory (MU) | Implementation of some components is not in substantial compliance with the original/formally revised plan with most components requiring remedial action. |
| Unsatisfactory (U) | Implementation of most components in not in substantial compliance with the original/formally revised plan. |
| Highly Unsatisfactory (HU) | Implementation of none of the components is in substantial compliance with the original/formally revised plan. |

| Risk ratings |  |
| --- | --- |
| Risk ratings will access the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: |  |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold or materialize, and/or the project may face substantial risks. |
| Moderate Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only moderate risk. |
| Low Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only low risks. |