PROJECT IMPLEMENTATION REPORT (PIR)

for the project:

Strengthen Management and Climate Change Resilience in Angola's Conservation Areas for Sustainable Development

FY25

July 1, 2024 – June 30, 2025

Year 2

Executing Partners

The National Institute for Biodiversity and Conservation Areas (INBAC), African Parks, the International Conservation Caucus Foundation (ICCF), and Conservation International -Africa Field Management Unit (CI-AFMU)

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Title: | Strengthen Management and Climate Change Resilience in Angola's Conservation Areas for Sustainable Development |  |  |
| Country(ies): | Angola | GEF ID: | 10505 |
| GEF Agency(ies): | Conservation International | Duration In Months: | 110 months |
| Executing Agency(ies): | The National Institute for Biodiversity and Conservation Areas (INBAC), African Parks Network (APN), the International Conservation Caucus Foundation (ICCF), and Conservation International -Africa Field Division (CI-AfFD) | Actual Implementation Start Date: | August 1, 2023 |
| GEF Focal Area(s): | Biodiversity and Climate Change | Expected Project Completion Date: | September 30, 2032 |
| GEF Grant Amount: | US$ 14,818,349 | Expected Financial Closure Date: | March 31, 2033 |
| Expected Co-financing: | US$ 26,454,000 | Date of Last Steering Committee Meeting: | N/A - The first PSC had not yet been held |
| Co-financing Realized as of June 30, 2025: | US$ 485,368 | Mid-Term Review-Planned Date: | April 2028 |
| Date of First Disbursement: | TBD | Mid-Term Review-Actual Date: | TBD |
| Cumulative disbursement as of June 30, 2025: | US$ 964,778 | Terminal Evaluation-Planned Date: | January 2032 |
| PIR Prepared by: | CI-Angola (Maria Loa, Casimiro Sande, Israel Chauke and Fernando Cavalo) | Terminal Evaluation-Actual Date: | TBD |
| CI-GEF Project Manager: | Charity Nalyanya Meave Omuruli | CI-GEF Finance Lead: | Susana Escudero |

The CI-GEF Project Agency Project Implementation Report (PIR) is composed of seven sections:

Section I:    General Project Status Summary: provides a brief summary of the project as well as a table summarizing the trend on implementation progress rating, development objective rating, and overall project risk rating;

Section II:   Project Performance: describes the progress made towards (a) achieving the project objective and outcomes since the start of the project and (b) delivery of outputs and implementation of activities as well as recommendations to improve the project performance, when needed;

Section III:  Key Risks Status and Rating: describes the progress made towards managing and mitigating project risks, the project risks mitigation rating reassessment as needed, as well as recommendations to improve the management of project risks;

Section IV:  Project Environmental and Social Safeguards Implementation Status and Rating: describes the progress made towards

complying with the Environmental & Social Safeguards and the Plans prepared during the PPG phase, the safeguard plans implementation rating, as well as recommendations to improve the project safeguards;

Section V:  Project Implementation Experiences and Lessons Learned: describes the experiences learned by the project managers and the lessons learned through the process of implementing the project; and

Section VI: Project Geocoding: documents the precise and specific geographic location(s) of activities supported by GEF

investments based on information available in Project Document.

Section VII: Minor Amendment: describes the changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5%.

SECTION I: GENERAL PROGRESS STATUS SUMMARY

SUMMARY OF RATINGS AND TRENDS

| PROJECT PART | PRIOR FY25PROGRESS RATING | CURRENT FY25 PROGRESS RATING | RATING TREND |
| --- | --- | --- | --- |
| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | MU | MS | Improving |
| IMPLEMENTATION PROGRESS (OUTPUTS AND ACTIVITIES) RATING | MU | MS | Improving |
| OVERALL PROJECT RISK RATING | M | M | Unchanged |

# SECTION II: PROJECT PERFORMANCE

This section describes the progress made since the start of the project towards achieving the project objective and outcomes, the implementation progress rating of the project, as well as recommendations to improve the project performance. This section is composed four parts:

a. Progress towards Achieving Project Expected Objective: this section measures the likelihood of achieving the objective of the project

b. Progress towards Achieving Project Expected Outcomes (by project component)

c. Overall Project Results Progress Rating, and

d. Recommendations for improvement

## a. Progress towards Achieving Project Objective and Outcomes (Development Objective):

This section of the report assesses the progress in achieving the objective of the project.

| PROJECT OBJECTIVE: | To improve the management of national parks in targeted Trans-frontier Conservation Areas (TFCAs) in southern Angola and strengthen the resilience of local communities and ecosystems to climate change. |
| --- | --- |

| OBJECTIVE INDICATORS | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- |
| a. Total number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment (Target: 24,215 (30% women)) | 345 beneficiaries, 38% Women (201 Men and 144 Women), | IS | A total of 345 people (201 Men, 144Women) have benefited from the project since its commencement. These include: communities recruited as wildlife monitors, community scouts, and field assistants in Iona national parks, rangers trained on managing the patrol boat in Iona, and training of local communities on income-generating activities such as craft, sustainable agriculture, and capacity building on conservation-compatible initiatives |
| b. Area of terrestrial Protected Areas under improved management effectiveness (ha) (Target: 3,788,245 ha) | Zero (0) | IS | In Iona, the project has commenced the develop the Land Use Plan, which will be used to complement the existing Parks Management Plan that was finalized before the commencement of the project. In Luengue-Luiana, the preparation of the Management Plan will commence in FY25 |
| c. Area of land under climate-resilient management (ha) (Target: 35,000 ha) | Zero (0) | NS | To commence in FY26 Q2. |
| d. Number of policies, plans and development frameworks that mainstream climate resilience (Target: 12) | Zero (0) | IS | During FY25, the project commenced with a comprehensive review of key policies on nature-based tourism sectors to identify policy gaps, alignment opportunities, and leverage points for strengthening institutional frameworks that support conservation and sustainable tourism. |
| e. Number of people with enhanced capacity to identify climate risk and engage in adaptation measures (Target: 14,040 people (30% female). | Zero (0) | IS | In FY25, the project finalized the Terms of Reference (ToR) for conducting a comprehensive climate risk and vulnerability assessment across Iona and Luengue-Luiana National Parks. The ToR to be posted in FY26 Q1 |

This part of the report assesses the progress towards achieving the outcomes of the project.

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| 1: Component 1: Strengthening the resilience of local communities to climate change in targeted TFCAs |  |  |  |  |  |
| Outcome 1.1: Increased implementation of biodiversity-compatible adaptation practices (encompassing the eco-village approach) in the Angolan portions of targeted TFCAs. | Indicator 1.1.: Area (ha) of agricultural and silvopastoral land in and around Luengue-Luiana and Iona National Parks under climate-resilient and biodiversity-compatible production practices | Target 1.1.: At least 35,000 ha of agricultural and silvopastoral land in and around Luengue-Luiana and Iona National Parks are under climate-resilient and biodiversity-compatible production practices. | Zero (0) | IS | In Iona, the project started the consultation with the stakeholders to develop the Park Land Use Plan, as an integral part of the overall park management plan. This tool will help inform the need for improvement on the land use practices. In Lungue Luina, to commence in FY26 Q1. |
| Outcome 1.2: Additional climate-resilient and biodiversity-compatible livelihood activities and sources of income established in the Angolan portions of targeted TFCAs to decrease vulnerability of local communities to climate change and reduce degradation of ecosystems. | Indicator 1.2.: Number of people (male and female) living within the Angolan portions of the targeted TFCAs with additional climate-resilient livelihoods and sources of income to agriculture, pastoralism, and hunter-gathering. | Target 1.2.a: At least 2,500 people (30% female) residing within the Angolan portion of the KAZA have additional climate-resilient livelihoods and sources of income. | Zero (0) | D | The activities are set to commence in FY26. The grant agreement with INBAC to support the implementation of activities in Luengue Luiana has been signed. |
|  |  | Target 1.2.b.: At least 2,500 people (30% female) in the Angolan part of the Iona-Skeleton Coast TFCA have additional climate-resilient livelihoods and sources of income. | Zero (0) | IS | In Iona, 283 people, of whom 48% women (148 Men, 135 Women) have participated in the training on craft making and sustainable subsistence agriculture, and were sensitized on best practices on income-generating activities. Stakeholders and community consultations focus on climate vulnerabilities and livelihood alternatives have been undertaken. These initial findings will be validated through an in-depth Climate Risk and Natural Capital Assessment planned for FY26 Q1. |
| 2: Component 2: Improving conservation area management and wildlife conservation in targeted TFCAs |  |  |  |  |  |
| Outcome 2.1.: Improved management of conservation areas in the Angolan portion of the KAZA TFCA. | Indicator 2.1.a.: Area (ha) of terrestrial conservation areas in the Angolan portion of the KAZA TFCA under improved management (i.e. whose Management Effectiveness Tracking Tool (METT) scores have increased during the duration of the project) | Target 2.1.a.: 2,273,245 ha of terrestrial conservation areas in the KAZA TFCA are under improved management (i.e. whose Management Effectiveness Tracking Tool (METT) scores have increased during the duration of the project) | Zero (0) | NS | The introductory meetings to introduce the project to stakeholders and communities at the landscape level will take place in FY26 (August 2025). This will set a pace for the full roll-out of project activities in Luengue Luina. |
|  | Indicator 2.1.b.: Percentage change in the METT score of Luengue-Luiana National Park | Target 2.1.b.: 30% increase in the METT score of Luengue-Luiana National Park | Zero (0) | NS | Same as above |
| Outcome 2.2: Improved management of conservation areas in the Angolan portion of the Iona-Skeleton Coast TFCA. | Indicator 2.2.a.: Area (ha) of terrestrial conservation areas in the Angolan portion of the Iona-Skeleton Coast TFCA under improved management (i.e. whose METT scores have increased during the duration of the project) | Target 2.2.a.: 1,515,000 ha of terrestrial conservation areas in the Angolan portion of the Iona-Skeleton Coast TFCA under improved management (i.e. whose METT scores have increased during the duration of the project) | Zero (0) | IS | A patrol boat was equipped with two staff already trained, which will help in wildlife monitoring. In addition, the land use plan is being developed to facilitate the implementation of the management plan on Iona. The training on climate-adaptation and biodiversity practices to gain traction in FY26, as well as the equipment of the anti-poaching unit and bases. Additionally, 62 local community members, of which 15% women - (53Men, 9 Women) - were recruited as wildlife monitors, community scouts, and field assistants and rangers to support management of the park. |
|  | Indicator 2.2.b.: Percentage change in the METT score of Iona National Park | Target 2.2.b.: 30% increase in the METT Score for Iona National Park | Zero (0) | NS | Same as above |
| Outcome 2.3.: Decreased poaching of priority species in Luengue-Luiana National Park. | Indicator 2.3.: Percentage change in the annual number of incidents of poaching in Luengue-Luiana National Park | Target 2.3.: 20% reduction in the annual number of incidents of poaching in Luengue-Luiana National Park | Zero (0) | NS | To commence early in FY26. |
| Outcome 2.4.: Decreased poaching of priority species in Iona National Park | Indicator 2.4.: Percentage change in the annual number of incidents of poaching reported in Iona National Park | Target 2.4: 20% reduction in the annual number of incidents of poaching in Iona National Park | 1 case reported | IS | Illegal poaching was reported to INBAC and the provincial government, while the Espinheira Forward Operating Base was assessed for restoration. Sixty-eight (68) law enforcement staff received refresher training from African Parks, reinforcing SOPs, leadership, human rights, and patrol skills. In November 2024, Iona’s team completed a month-long operational training. Marine and aerial surveillance improved with a patrol boat and C-180 aircraft, though a full-time pilot is still needed. Joint patrols with Save the Rhino Trust remain suspended pending formal agreements. A law firm is retained, a draft LE Strategy is underway, and priority training is scheduled for FY26 to address persistent capacity gaps. |
| Component 3: Enhancing the technical and institutional capacity of climate change and conservation institutions |  |  |  |  |  |
| Outcome 3.1.: Enhanced institutional capacity of national government agencies to coordinate, plan and implement climate change and biodiversity strategies. | Indicator 3.1.: Number of sectoral strategies, policies and plans that integrate climate change adaptation and biodiversity conservation | Target 3.1.: Recommendations generated for the integration of climate change adaptation and biodiversity conservation into at least 5 sectoral strategies, policies and plans | Zero (0) | IS | The project has undertaken its initial mapping of key strategies, policies, and plans requiring review to strengthen biodiversity conservation and climate resilience efforts. In FY26 Q1, the project will focus on assessing gaps, ensuring policy alignment, and generating recommendations to improve coherence and effectiveness across national and site-level implementation policies, strategies and plans. |
| Outcome 3.2.: Improved technical and institutional capacity of sub-national government agencies to coordinate, plan and implement climate change and biodiversity strategies at provincial and municipal levels. | Indicator 3.2.: Number of members of decentralised Provincial Committees on Climate Change and Biodiversity, staff of selected CSOs and municipalities (male and female) with capacity to coordinate, plan and implement climate change and biodiversity strategies | Target 3.2.: At least 40 (50% female) members of decentralised Provincial Committees on Climate Change and Biodiversity and municipal and CSO staff trained and provided with tools to coordinate, plan and implement climate change and biodiversity strategies | Zero (0) | IS | Project activities have not yet commenced in Luengue-Luiana, but the project introductory workshop is planned for early in FY26 Q1, starting with local stakeholders engagement to understand the project objectives, scope and implementation approach. In Iona National Park. While a provincial committee is already in place, it requires assessment to determine the adjustments needed to align with the project’s thematic priorities, particularly climate resilience and biodiversity conservation. This evaluation will help ensure that governance structures are equipped to support inclusive implementation and deliver on key conservation outcomes. |
| Outcome 3.3.: Enhanced technical and institutional capacity to manage Angola's Conservation Area Network. | Indicator 3.3.: Degree to which the technical and institutional capacity and arrangements to lead, coordinate and support the management of Angola’s Conservation Area Network is strengthened. | Target 3.3.: At least a 20% increase in capacity scores at the end of the project | Zero (0) | IS | The project facilitated the formation of multi-stakeholder safeguard groups, comprising central government entities such as INBAC, international NGOs including United Nations Development Program (UNDP) and the Agency for the Development of People for People (ADPP), and various local organizations. Two capacity-building and training sessions were conducted with INBAC, African Parks and ICCF to strengthen partners’ understanding and application of safeguard measures, Gender Mainstreaming Plan (GMP), Stakeholder Engagement Plan (SEP), and Accountability and Grievance Mechanism (AGM) |
| Outcome 3.4.: Strengthened capacity of the private sector and other key stakeholders to develop Nature-based Tourism (NBT) and sustainable use activities in Angola's conservation areas. | Indicator 3.4.: Number of NBT enterprises in target conservation areas | Target 3.4.a.: A minimum of 1 new NBT enterprise established within Luengue-Luiana National Park | Zero (0) | D | The terms of reference for NBT have been finalized and will be published in FY26 Q1. This will pave the way for the identification of viable partnerships for tourism-led conservation and local development. |
|  |  | Target 3.4.b.: A minimum of 1 new NBT enterprise established within Iona National Park | Zero (0) | D | Same as above. |
| Outcome 3.5.: Increased ability of institutions in Angola to access climate and biodiversity finance. | Indicator 3.5.: Existence of an environmental fund in Angola. | Target 3.5.: A restructured, functional environmental fund acting as a source of finance for environment and conservation management. | Zero (0) | IS | The project commenced discussions with the National Directorate of Climate Action and Sustainable Development (DNACDS) to present its scope and explore areas for strategic collaboration, including potential support for existing environmental funding mechanisms. Building on this engagement, the next phase will involve a detailed analysis of the identified funds to assess gaps, alignment opportunities, and priority support areas. This review is scheduled to commence in early FY26 Q1 and will inform targeted contributions aimed at strengthening the national conservation financing architecture |
| Component 4: Facilitating project monitoring, knowledge management and sharing of lessons learned |  |  |  |  |  |
| Outcome 4.1.: Effective monitoring and evaluation of adaptation and biodiversity conservation interventions in the project target areas. | Indicator 4.1.: Existence of a functional monitoring, evaluation and learning system that houses datasets generated by the project | Target 4.1.: At least 1 functional monitoring, evaluation and learning system that houses datasets generated by the project | Zero (0) | IS | During FY25, the project, in collaboration with the CI-AFMU MEAL manager, successfully designed the Monitoring, Evaluation, and Learning (MEAL) system along with its associated data collection tools. In early FY26 Q1, the project will focus on completing the remaining components required to fully operationalize the MEAL system and enable systematic tracking of project performance and conservation outcomes. |
| Outcome 4.2.: Improved knowledge-sharing among institutions in Angola, and with other countries, donors, and key stakeholders across the wider TFCA landscapes. | Indicator 4.2.: Number of knowledge products generated and shared in-country and with other countries, donors, and key stakeholders | Target 4.2.: At least 14 knowledge products generated and shared by stakeholders across the TFCA landscape. | Five (05) | IS | The project launch blog was developed and shared the social media. The project also actively participated in two South-South learning exchanges aimed at strengthening technical collaboration and peer learning across regions. - Annual GWP conference held in Panama, in January 2025 - Exchange conference on nature-based tourism held in KwaZulu-Natal, South Africa. Discussions centered on tourism business models, opportunities for linking conservation with wildlife experiences, and mechanisms for equitable benefit sharing with local communities. . |

| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | JUSTIFICATION |  |
| --- | --- | --- |
| Moderately Satisfactory (MS) | This section is rated Moderately Satisfactory because 59% of the outcome indicators are under implementation, 24% have not started but are on track, and 17% are delayed. In FY25, the project demonstrated significant improvement in the implementation of activities compared to FY24, where 100% of the indicators had not yet started. The grant agreements with all project partners were signed, and the project held a successful launch in March 2025 in Luanda, Angola. Additionally, the terms of reference for climate vulnerability assessment, natural capital accounting, and identification/establishment of Nature Based Enterprises have been prepared, and are set to be published in Y26. The discussions with INAMET on setting up the hydrometeorological stations in the Iona and Lungue Lunina parks are ongoing. In Iona, African Parks commenced the equipping of a patrol boat, recruiting community patrols, preparing land use plans, and training two patrol staff and community members on biodiversity-compatible practices such as craft making and sustainable farming. x |

## b. Progress towards Implementation Progress (Delivery of Outputs and Implementation of Activities)

This part of the report assesses the progress towards delivery of outputs and implementation of activities planned for the year.

## Progress: Information on progress outcomes of project implementation activities

In FY25, the recruitment of the remaining PMU staff was finalized. The project also held a successful launch in March 2025 in Luanda, Angola, which was attended by state and non-state institutions and local communities from Iona and Luengue Luiana. Landscape-level introductory workshops to introduce the project at the landscapes are scheduled for July and August 2025. Below is the summary of the implementation of project activities per component. Component 1: Strengthening the resilience of local communities to climate change in targeted TFCAs: 14% of the activities are under implementation, and 86% have not started but are on track. In FY25, two terms of references for the climate risk and vulnerability assessment and natural capital accounting were prepared and approved, and set to be posted in FY26. The project commenced engagement with key national entities, including INAMET and DNACDS. The collaboration with INAMET focuses on building hydrometeorological capacity within parks and enhancing access to localized climate forecasting. The project also engaged organizations such as the Tony Blair Institute, with expertise in conservation agriculture and community training and started exploring areas of collaboration, and Halo Trust, exploring its logistical reach for remote areas like Luengue-Luiana. One output, the development of business plans, was delayed due to dependencies on the assessments, but is expected to be fast-tracked in early FY26 Q1. Component 2: Improving conservation area management and wildlife conservation in targeted TFCAs. African Parks leads interventions in Iona, while INBAC will direct efforts in Luengue-Luiana starting in FY26. Strategic discussions with INAMET, DNACDS, and the Tony Blair Institute, and finalized its workplan for Luengue-Luiana, including preparatory steps toward establishing the park’s hydrometric network. INBAC also completed its institutional restructuring and defined the staff framework for project delivery. African Parks registered substantial progress across multiple outputs. Its anti-poaching efforts included revising the law enforcement strategy, assessing Forward Operating Bases, and developing improvement plans. Surveillance and monitoring systems were strengthened through aerial operations, ranger training, and deployment of key technologies such as the EarthRanger App. Animal collaring activities were initiated to support species management. Coordination was enhanced via engagement with conservation partners like Save the Rhino Trust and cross-border informal dialogues with stakeholders in Namibia and Skeleton Coast National Park. To operationalize Iona’s management plan, a consultant was contracted and began inclusive consultations with communities and stakeholders to develop the park’s land use strategy. Component 3: Enhancing technical and institutional capacity of climate change and conservation institutions, INBAC will take the lead, supported by the PMU. While INBAC’s activities are slated to begin in FY26. ICCF also advanced work under this component, completing the preparatory process to recruit a consultant tasked with reviewing the legal framework underpinning nature-based tourism. Component 4: Facilitating project monitoring, knowledge management and sharing of lessons learned includes four outputs. The project initiated discussions with CI-GEF to adopt the Global Wildlife Program (GWP) tracking tool and establish the Management Effectiveness Tracking Tool (METT). With guidance from CI’s MEAL manager, the Monitoring, Evaluation, and Learning (MEAL) system was designed and accompanied by tailored data collection tools. This provides the foundation for phased METT implementation: Iona National Park in FY26 Q1 and Luengue-Luiana in FY26 Q2, enabling robust performance monitoring and adaptive management across both landscapes.

Challenges: Information on challenges of project implementation activities

- Project implementation during the first two years faced significant delays due to the need for further adaptation to the local context and to ensure demonstrable government capacity building. This led to major adjustments in implementation arrangements and budget realignment, including CI assuming an executing role, INBAC leading activities in Luengue Luiana, and the recruitment of project staff under INBAC - Delay in Conservation International’s clearance from the Angola Ministry of Justice to officially operate in Angola slowed down some of the activities on the ground, mainly the procurement processes - Slow onboarding of other key institutions to support in areas of policy reviews, environmental fund and hydrometric network planning due to the above factors

| IMPLEMENTATION PROGRESS (DELIVERY OF OUTPUTS AND IMPLEMENTATION OF ACTIVITIES) RATING | JUSTIFICATION |  |
| --- | --- | --- |
| Moderately Satisfactory (MS) | The implementation of project activities commenced in FY25 and the project is slowly getting traction. Additionally, there is established strong working relationship with the Ministry of Environment and INBAC key to the smooth implementation of the project activities. |

## c. Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| - Continually follow up with the designated government focal points to ensure their participation in events organized by the GWP and/or to secure the nomination of a government official to represent Angola in these events. | INBAC, CI-AFMU | Throughout the project cycle |
| - To date, no Project Steering Committee has been convened, hence the need to ensure this takes place in FY26 | MECCNAR, CI-Africa Field Management Unit | June 2026 |
| - Strengthen the M&E system to closely monitor project targets at the outcome level and ensure no duplication of project beneficiaries. | PMU | Throughout the project cycle |
| - Fast-track the preparation of the Standard Operating Procedures for the PMU and the project’s Operational Manual to guide the PMU in the implementation of project activities. | CI-AFMU, CI-GEF | FY26 Q! |
| - Provide regular updates to the Project Advisory Board by the project leadership team to ensure smooth execution of project activities and provide any corrective action | Project Leadership Team | Throughout the project cycle |
| - Continuously engage stakeholders, including communities at the landscape level, to ensure buy-in and smooth implementation of project activities. | INBAC, CI-Angola, African Parks and ICCF | Throughout the project cycle |

# SECTION III: PROJECT RISKS STATUS AND RATING

## a. Progress towards Implementing the Project Risk Mitigation Plan

This section describes the activities implemented to manage and reduce high, substantial, modest, and low risks of the project. This section has three parts:

a. Ratings for the progress towards implementing measures to mitigate project risks and a project risks annual reassessment

b. Recommendations for improving project risks management

Progress towards Implementing the Project Risk Mitigation and Plan Project Risks Annual Reassessment

| PROJECT RISKS | PRODOC RISK DEFINITION AND MITIGATION MEASURE | MITIGATION MEASURES IMPLEMENTATION PROGRESS | PRODOC RISK RATING | CURRENT FY25 RISK RATING |
| --- | --- | --- | --- | --- |
| CONTEXT |  |  |  |  |
| Climate change | Risk: Climate change may drive shifts in priority species distributions beyond the existing boundaries of the targeted conservation areas. Mitigation Measure: The management plans for the protected areas will account for long-term climate change projections so that strategic decisions can be made regarding species distribution shifts. Incorporating the Spatial Planning for Area Conservation in Response to Climate Change (SPARC)tool and datasets will aid in the effectiveness of this. The project also includes activities to strengthen the network of management among the transfrontier conservation areas, providing further flexibility in planning through collaboration beyond park and national borders. | In Luengue-Luiana the project is due to start activities in the FY26. In Iona National Park the project started the operationalization of the Park Management Plan, through carrying out series of consultation with local stakeholders to inform the development of land use plans, which will incorporate measures to mitigate identified risk. | Medium (M) | Medium (M) |
|  | Risk: There is some uncertainty regarding climate change projections and their resulting consequences for HWC as both species and resource distributions shift. There is also some uncertainty regarding some newly emerging HWC reduction strategies. These may result in unforeseen future HWC scenarios. Mitigation Measure: The project is designed with an iterative monitoring and evaluation process to ensure that strategies and management plans are updated as new information becomes available. The project will also focus on developing long-term adaptive strategizing skills among stakeholders and decision-makers so that they are able to respond to changing scenarios effectively. | In both project sites, the establishment of meteorological systems has been prioritized to support climate-informed planning. These systems are intended to improve rainfall forecasting and water availability monitoring, which are critical for wildlife management and for guiding local community livelihood strategies. While in Iona National Park the process is already underway, though in its early stages, the rollout in Luengue-Luiana National Park is scheduled to begin early in FY26. This intervention is expected to enhance adaptive capacity across both ecological and human systems. | Medium (M) | Medium (M) |
|  | Risk: Potential impacts of climate risks, including climate hazards and climate shocks that may delay or alter project implementation. Mitigation Measure: The project includes a full Climate Risk Screening (Appendix V) and the appropriate considerations and mitigation measures have been incorporated into the project design. Climate and weather hazards that may be present in the project area include droughts, extreme heat and flooding. These risks have been accounted for during the development of the project timeline and further considerations for these risks will be incorporated into all future planning and development within the project. Using the guidance of the Climate Risk Screening will ensure that the project is not severely impacted by climate risks and that the adaptation and mitigation measures are implemented effectively. | The terms of reference to conduct the climate risk and vulnerability assessment, which will include mitigation measures in Iona and Luengue Luina, have been prepared, and the procurement will start early in FY26. | Medium (M) | Medium (M) |
|  | Risk: Unpredictable changes in climate may result in some adaptation practices being outdated and ineffective. Mitigation Measure: Strategies will incorporate an ongoing adjustment process to ensure the most up-to-date practices are being implemented. As new information is available and as conditions change with the changing climate, so strategies will be updated in response. | The project finalized the terms of reference to conduct a climate risk and vulnerability assessment, which will also focus on assessing climate adaptation interventions in the two landscapes. The expected outcome of the assessment will resulst to a report which will be used to update the climate risk and vulnerability information for the two project sites. | Low (L) | Low |
| Environmental and Social | Risk: Corona Virus Pandemic: There may be delays in implementation and coordination resulting from limited face-to-face engagements and travel restrictions and other safety measures taken in response to the COVID-19 pandemic. Mitigation Measure: - The project will ensure that tools and support are made available for effective online engagement where possible to reduce the impact of the COVID-19 pandemic on project implementation while safeguarding the health of all stakeholders. Online engagement has become increasingly effective and free platforms ensure accessibility. This will also mitigate travel costs and time spent in transit for all stakeholders. (Considerations included in stakeholder engagement plan. - Quarterly technical and financial reports submitted to CI-GEF Agency will clearly indicate project implementation progress, any delays and adaptive measures being put in place by the project team. This measure will enable CIGEF to provide guidance on how best to adapt to the situation on the ground from technical and financial perspectives. - Project staff working in the protected areas will exercise caution by donating Personal Protective Equipment (PPE) for COVID prevention (e.g., face masks) to reduce the risk of infecting protected area authority employees and wildlife (particularly non-human primates). | - While COVID-19 is no longer a pandemic, the project will continue to monitor any of the guidelines and advisories provided by the Angolan Ministry of Health and WHO. | Medium (M) | L |
|  | Risk: Safeguard Plans developed during PPG Phase have information gaps: Due to Covid-19 travel restrictions, key stakeholders such as Park managers and communities residing in remote areas around the Protected Areas were not consulted in the development of safeguard plans. Additionally, a thorough capacity assessment of the Executing Agency (EA) was not undertaken since there was a delay in appointing the EA by the Government. As a result, there are information gaps in the Safeguard plans. Mitigation Measures: - A Safeguards specialist will be recruited to finalise/update the safeguard plans, conduct a limited Environmental and Social Impact Assessment (ESIA), undertake other safeguards-related tasks that were not completed during the PPG Phase, monitor and report implementation of safeguards. - Monitoring of all project indicators (including safeguard indicators) will be undertaken by a full-time Monitoring and Evaluation (M&E) Specialist. | - The project recruited a full time Safeguard and Compliance Officer. The Officer reviewed and updated the project’s safeguard plans, AGM, GMP, SEP. The finalization of the limited Environmental and Social Impact Assessment (ESIA) will be done in FY26 Q1 after the field visits in Iona and Luengue Luina National Parks. - The project’s Safeguard Officer has also provided EMSF training to all the project partners who will be mandated to track and report compliance. The ESMF indicators have also been integrated into the project’s MEAL system. | High | Moderate |
| Political and Governance | - Risk: Changes in government priorities, personnel, and structures may disrupt implementation. Mitigation Measure: - Political commitment will be ensured through the engagement at all levels of government with commitments made collaboratively with other stakeholders. - Financial incentives through business plans and the long-term benefits of adaptation strategies will ensure that outcomes align with the needs of the communities and nation. - Project stability will also be ensured through the involvement of project partners that are well-established within the project area, having worked on previous projects and served to support the national parks in various roles. These project partners will oversee and direct numerous project activities and will serve to buffer any shifts in government personnel and structures. | - The project is working closely with the Government, reviewing to smooth execution of activities. In the revised implementation structure, the project has established an Advisory Board which will focus on providing strategic direction and for the government is up-to-date on the implementation progress. t The project is also engaging with other government agencies, the National Institute of Meteorology and Geology (INAMET) and the National Directorate of Climate Action (DNACDS) and non-government entities (Tony Blair Institute and Halo trust), including discussing synergies to implement the project. | Medium (M) | M |
| INNOVATION |  |  |  |  |
| Institutional and Policy: | Risk: Weak capacity of conservation area management to implement introduced measures. Mitigation Measure: The project will work with and strengthen the capacity of a diverse set of institutions, operating at both the local and regional levels. This will allow for collaboration to build a network for improved overall management. Activities to support the governance structures of the conservation areas are also included. | - The project engaged and started working with African Parks, INBAC and ICCF and delivered training on ESMF components including supported partners to develop safeguard related tools. This is starting to build partners capacity. | Substantial (S) | M |
|  | Risk: Little or no long-term adoption of biodiversity-compatible adaptation practices by community members. Mitigation Measure: Long-term strategies will be developed collaboratively to ensure adequate incentives and benefits to these communities to secure buy-in. | - The project finalized the development of terms of reference to carry out natural capital accounting. The procurement will be launched early in FY26. One of the expected outcome of this assessment will inform long term strategies to adopt the biodiversity compactible adaptation practices | Low (L) | Low |
| Technological | Risk: Limited uptake of alternative livelihoods by local communities. Mitigation Measure: The eco-villages established by the project will serve as a working example and proof-of-concept for the alternative livelihoods introduced by the project. The development of these eco-villages will be collaborative with local communities to incorporate their unique needs into designs and strategies. This will improve the likelihood of uptake by ensuring that the alternative livelihoods meet the needs of local people and improve their well-being. | - To ensure that the eco-village model adopted reflects the local needs, the project initiated internal discussion with stakeholders in each part to understand they priorities and needs to inform the models to be adopted. At this stage we know that community is Iona are nomiadic and this needs to be taken into account. | Low (L) | Low |
|  | - Risk: International revenue for NBT may take some time to develop and be hindered by international travel restrictions during emergency periods (For example the COVID-19 lockdowns) Mitigation Measure: NBT business plans will have strong integration of local and short-distance tourism, reducing reliance on external international revenue for viability. | - During this reporting period the project exeuting agency International Caucus Conservation Foundation (ICCF) finalized the ToR to engage a legal consultant to review and understand the existing legal framework and how it related to nature based tourism. The procurement will be launched early in FY26. | Medium (M) | M |
|  | Risk: Little or no long-term adoption of biodiversity-compatible adaptation practices by community members. Mitigation Measure: Long-term strategies will be developed collaboratively to ensure adequate incentives and benefits to these communities to secure buy-in. | - The project finalized the development of terms of reference to carry out natural capital accounting. The procurement will be launched early in FY26. One of the expected outcome of this assessment will inform long term strategies to adopt the biodiversity compactible adaptation practices | Low (L) | Low |
| Financial and Business Model | Risk: Business viability may be vulnerable to shifts in large-scale economic dynamics. These could include a post-COVID-19 pandemic economic recession; changes in revenue generated by international tourism; and shifts in the supply and demand of crops under changing climate conditions. These would all impact the business prospects that are most extensively linked to the livelihoods of local communities in and around the project areas Mitigation Measure: The development of business plans will have robust engagement and market assessment, and account for as much variability as possible. By rooting business plans in adaptation and local ecosystem dependence, the financial stability of these business plans will be improved. The business plans will be designed conservatively, with a focus on long-term stability in favour of more extensive financial gains. | - Activity implementation to commence in FY25 | Sustancial (S) | S |
| EXECUTION |  |  |  |  |
| Capacity for implementation | Risk: High staff turnover in the Government of Angola will affect decision-making, resulting to delays Mitigation Measures: - CI will continually follow up with the Government of Angola to ensure the designated Government focal point is actively engaged in the project. - CI will also ensure there is buy-in from senior Government officials. | - The Government formally designated the Director of INBAC as the Project Director and official focal Point. This decision has further strengthened coordination between the project and INBAC, ensuring high-level leadership and strategic oversight for implementation activities. | High (H) | M |
|  | Risk: Executing arrangements were not finalized during PPG Phase. Identification of non-state partners and their roles was not completed during PPG Phase. Mitigation Measure: Executing arrangements, identification of partners and definition of their roles will be finalised during implementation phase as part of project set-up activities. This task will be completed within the first 6-months. | - In the FY 25 INBAC was formally designated as the executing agency, and this necessitated a comprehensive revision of the implementation arrangement to reflect its leadership role and operational responsibilities. This adjustment process involved aligning institutional mandates, governance protocols, and delivery frameworks across partners. The revised arrangement was finalized by the end of FY25 Q4, establishing a clear foundation for INBAC’s oversight and enabling streamlined coordination for field-level execution for Luengue-Luiana | High (H) | M |
|  | Risk: Delays in the monitoring and evaluation process may hinder the regular updating of the project strategies and the incorporation of lessons and feedback as the project progresses. Mitigation Measure: The project will provide the monitoring agents with project tracking tools and training in to use these tools to appropriately oversee and guide project implementation. The tools include the Global Wildlife Program (GWP) tracking tool and Management Effectiveness Tracking Tools (METT) to report project contributions to program-level indicators. | - During FY25, the project, in collaboration with CI-AFMU MEAL manager, successfully designed the Monitoring, Evaluation, and Learning (MEAL) system along with its associated data collection tools. In early FY26 Q1, the project will focus on completing the remaining components required to fully operationalize the MEAL system and enable systematic tracking of project performance and conservation outcomes | Moderate | M |
| Fiduciary: Financial Management and Procurement | Risk: Due diligence of the Executing Agency and partner institutions was not conducted by CI during the PPG Phase. Mitigation Measure: - This task will be completed within the first 6 months of the implementation phase. - Financial Risk Assessments (FRA) will be completed before granting to any selected partners. Granting will only be done when partners, including the Government, have met the requirements based on the financial risk assessment. The outputs of this assessment will be: - Partners identified and their respective detailed ToRs defining their roles developed and approved by the GoA. - Budgets allocated to the Partners in correspondence with their ToRs. Budget Allocations approved by the GoA. - Financial Risk Assessments (FRA) of partner institutions conducted and applicable mitigation measures put in place. - Contracts/Agreements signed. Following the above, the Project’s overall Budget and Work Plan will be realigned to reflect decisions from the Government and reflect the outcome of the partner mapping and assessment exercise. | - The project successfully completed the due diligence process for INBAC, confirming its institutional and fiduciary capacity to serve as the executing agency. This milestone culminated in the formal award of the grant to INBAC at the end of FY25 Q4. To ensure that identified risks are effectively addressed, the project incorporated targeted mitigation measures into its implementation framework. | High (H) | S |
| Stakeholder | Risk: Some stakeholder commitments may not be upheld long-term. Mitigation Measure: The project design will ensure that the value of the knowledge shared is made clear to all stakeholders to incentivise their long-term commitment and encourage more extensive engagements. | - During this FY25, the project involved various groups of stakeholders in the launch event to share the project scope, approach and targets. The project and its executing agencies will continue conducting consultations for different project components. | Low (L) | L |
| Other (e.g. NGI) | N/A | N/A | N/A | N/A |

| OVERALL RISK RATING | JUSTIFICATION | RISK RATING TREND |
| --- | --- | --- |
| Moderate (M) | The project’s risk rating is Moderate (M). All the grant agreements are signed, and execution of project activity are gradually gaining traction. Key actions included revising implementation arrangements to align with government guidance and hiring the remaining PMU staff. Conservation International will continue to working closely with the INBAC and the government to increase the momentum, with activities set to commence in FY25. | Unchanged |

## Recommendations

| MITIGATION AND CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| 1. Need to continually follow up with the designated Government focal points to ensure they are actively engaged in the project implementation phase and decision-making | CI-Angola, MINAMB, INBAC | Throughout the project cycle |
| 2. Need for CI-Angola and INBAC staff in the PMU to work collaboratively and coordinate closely in project management responsibilities | CI-Angola, INBAC | Throughout the project cycle |
| 3. Need for CI-Angola to work closely and enhance the capacity of the INABC team in the PMU for effective implementation of the project. | PMU, CI-Angola, INBAC | Throughout the project cycle |

SECTION IV: PROJECT ENVIRONMENTAL AND SOCIAL MANAGEMENT IMPLEMENTATION STATUS AND RATING

This section of the PIR describes the progress made towards complying with the approved ESMF plans, as well as recommendations to improve the implementation of the ESMF plans, when needed. This section is divided into six parts:

a. Progress towards complying with the CI-GEF Project Agency’s ESMF

b. Information on Progress, challenges and outcomes on stakeholder engagement

c. Information on the progress towards achieving gender sensitive measures/targets

d. Lessons learned and Knowledge Management products developed and disseminated

e. Overall Project ESMF Implementation Rating

f. Recommendations

a. Progress towards complying with the CI-GEF Project Agency’s ESMF

| MINIMUM ESMF INDICATORS | PROJECT TARGET | END OF YEAR STATUS | CUMULATIVE STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| ACCOUNTABILITY AND GRIEVANCE MECHANISM |  |  |  |  |  |
| - Number of times the Accountability and Grievance Mechanism is communicated/disseminated to stakeholders | 87 | 4 | 04 | IS | The project AGM started to be widely disseminated, following the launch of the project on March 25th, 2025. The project and its executing agencies will continue to disseminate it, FY26 and onward. The project AGM was disseminated 4 times before the end of the fiscal year. The low achievement rate is due to the late launching of the project and the delayed review and approval of the safeguards documents, which include the AGM. |
| - Percentage of conflict and complaint cases reported to the project’s Accountability and Grievance Mechanism that have been resolved | 100% | 69% | 69% | IS | The number of cases being analyzed relates to the figures reported by African Parks only. The remaining unresolved 31% are due to less regularity in the meetings of the Parks’ Grievance Resolution Committee (GRC). 15% of the total cases are fairly new, having been received in Q4, and will be discussed in the upcoming GRC meeting. African Parks are being trained in categorizing grievances. At the time of reporting, Categorization had not started, with training to take place in July 2025. |
| GENDER MAINSTREAMING |  |  |  |  |  |
| - Number of men and women that participated in project activities (e.g. meetings, workshops, consultations) | 10215 people (men 7150 and women 3065) | 1110 | 1110 | IS | The total of 1110 is a commulative number of people that attended overall project and PMU meetings (Male 689 Female 421) both virtual and presencial and benefited from different project interventions. |
| - Number of men and women that received benefits (e.g. employment, income generating activities, training, access to natural resources, land tenure or resource rights, equipment, leadership roles) from the project | 24215 people (men 16950 and women 7265) | 341 (201 M and 140W) | 341 (201 M and 140W) | IS | A total of 603 individucal s have received project benefits to date - Employment ( 53 M,9W) - Traning ( 90 M, 93W) - Equipment (58M, 38M) |
| - Number of strategies, plans (e.g. management plans and land use plans) and policies derived from the project that include gender considerations (this indicator applies to relevant projects) | 12 | 0 | 0 | IS | During this FY25, in Iona the project executing agency started series of consultation to develop the Land Use Plan (LUP), as part of the process to operationalize the Park management Plan. The draft of LUP will be shared for review and comments, early in FY26 |
| STAKEHOLDER ENGAGEMENT |  |  |  |  |  |
| - Number of government agencies, civil society organizations, private sector, indigenous peoples and other stakeholder groups that have been involved in the project implementation phase on an annual basis | 43 | 15 | 15 | IS | During this FY25 the project engaged the following stakeholders: Government: (04) INBAC; INAMET; MINAMB; and DNACDS NGO: (10); Halo Trust; ADPP, TNC, KAYA, AIDC, ACADIR, World Vision, Development Workshop and USAID Environment team UN Agencies: (01) UNDP |
| - Number persons (sex disaggregated) that have been involved in project implementation phase (on an annual basis) | 160 (Men 100 and Women 60) | 15 | 15 | IS | During this FY 25, 15 people participated in direct project implementation. In the FY25, more people will continue to be involved. , ICCF = 3, INBAC 4, African Parks = 8 |
| - Number of engagement (e.g. meeting, workshops, consultations) with stakeholders during the project implementation phase (on an annual basis) | 23 Meetings | 6 | 6 | IS | During the FY25 the project conducted: 04 Safeguards integration capacity building session; and 02 INBAC Safeguards integration sessions |
| ESS 1: Environmental and Social Impact Assessment Number of ESIAs carried out | 2 | 0 | 0 | NS | The project will carry out 2 ESIA 1 for Iona and for Luengue Luiana and both ESIAs will be done, in FY26 Q1. |
| ESS 4: Autochonous peoples |  |  |  |  |  |
| - Percentage of autoctonous people /local communities where FPIC have been followed and documented | 100% | 0 | 0 | IS | Partially achieved for Iona in late FY25. In the FY 26 Q1 the process will start in Luengue Luiana. Whilst no specific activity was achieved that directly relates to authoctonous Peoples, awareness of the African Parks team towards the need for FPIC was achieved through the development of the ESMP. FPIC related activities are expected to start in FY26. |
| - Number of autoctonous people present in the project sites that participated in the project | No target set at CEO ER | 0 | 0 | NS | Partially achieved for Iona in late FY25. In the FY 26 Q1 the process will start in Luengue Luiana. Whilst no specific activity was achieved that directly relates to authoctonous Peoples, awareness of the African Parks team towards the need for FPIC was achieved through the development of the ESMP. FPIC related activities are expected to start in FY26. |
| ESS 6: Cultural Heritage |  |  |  |  |  |
| - Number of physical cultural resources found in the project area - Number of measures taken to manage impact to avoid or manage impact to cultural heritage resources | No target set at CEO ER | 0 0 | 0 0 | NS NS | Activities not started. Only African Parks are now aware of the need for consideration of Cultural Heritage as part of the project, this was achieved through the finalization of the ESMP |
| ESS 8: Community Health, Safety and Security - Number of measures taken to address community health, safety and security measures. | No target set at CEO ER | 0 | 0 | NS | In FY25, in Year 1 of the project the focus was on development of guiding principles in the ESMP. The field implementation will effectively start early in FY26. |

## b. Information on Progress, challenges and outcomes regarding engagement of stakeholders in the project based on the description included in the Stakeholders Engagement Plan

Progress Since project inception in March 2025, preliminary stakeholder engagement activities have commenced in Luanda, Iona National Park (Namibe Province), and Luengue-Luiana National Park (Cuando Province). The project has begun operationalizing the Stakeholder Engagement Plan (SEP) as included in the CEO Endorsement submission, focusing on socializing key project objectives, expected roles and rights-based approaches with key government institutions (MINAMB, INBAC), civil society actors, and conservation area co-management partners, (African Parks ). Capacity-building, awareness-raising, and initial socialization activities are underway in Luanda to enable effective coordination among national-level institutions. In Iona, the groundwork for engagement is being laid through focal meetings with local authorities, park co-management units, and community representatives. The Accountability and Grievance Mechanism (AGM) has been validated and disseminated, providing a concrete tool to promote inclusive, rights-based stakeholder engagement. Challenges Given that the project is still in the early implementation stage, several challenges have emerged: - Logistical barriers in remote areas - The vastness and remoteness of Iona and Luengue-Luiana parks present serious logistical challenges in mobilizing and convening stakeholders, especially autocthnous Peoples and traditional leaders. - Stakeholder mistrust -Historical exclusion from decision-making, land use tensions and unfulfilled development promises have led to skepticism among rural communities and autoctonous groups, particularly in areas where prior projects lacked continuity (more pronounced in Iona National Parks). Since African Parks signed a co-management agreement with MINAMB, there has been a noticeable increase in trust from local communities towards park management achieved through continuous engagement over the last four (4) years. - Institutional coordination constraints-Coordination among government agencies, conservation NGOs, and local authorities is still nascent. Mainly unstreamlined and at times overlapping mandates have hindered rapid mobilization and role clarity. - Language and cultural barriers- Multilingualism ( Kwanhama, Portuguese) and deep cultural heterogeneity demand tailored, culturally appropriate communication strategies, still being developed and adapted. - Limited digital access-Low levels of connectivity and digital literacy in rural areas make it difficult to apply uniform communication tools, especially for grievance reporting and feedback loops. Strategies being advanced to overcome challenges The project is actively deploying the following strategies, as envisioned in the SEP and ESMF (Appendix VI): - Decentralized stakeholder platforms -Through the formation of localized engagement hubs ( park-based safeguard and community engagement officers and multi-stakeholder committees), the project is devolving stakeholder engagement to the field, with CI Angola and INBAC playing facilitative roles. - Culturally responsive outreach -The Gender Mainstreaming Plan (GMP) and SEP include protocols for engaging Indigenous communities, women, and youth using participatory rural appraisal tools, and traditional communication methods. - Use of safeguards tools -The project has introduced (in Luanda) context-adapted versions of the Accountability and Grievance Mechanism (AGM) to promote trust, transparency, and two-way feedback. The same will be effected for Iona and Luengue Luiana national parks. These tools will be deployed with interpretation into local languages and where possible with mobile phone-based accessibility in progress. - Capacity building and stakeholder mapping -Ongoing institutional capacity building is being provided to local government agencies (INBAC), CSOs, and will b extended to traditional authorities to build readiness for deeper engagement in co-implementation and M&E. A detailed stakeholder mapping is being finalized to guide targeted inclusion. Preliminary outcomes While full outcomes are premature, early signs of progress include: - Increased awareness of project objectives among key stakeholders in Luanda and Namibe. - Receptivity of park-level co-management actors to serve as bridges to community-level actors. - Initial buy-in from selected community representatives, including traditional chiefs and women’s groups, following the first rounds of stakeholder consultation in Namibe Province. - Operational introduction of safeguards tools like the AGM, establishing channels for community input and dispute resolution. FY 25 is an early phase which is crucial for building the foundation of trust and inclusion envisioned in the SEP. As implementation deepens, continuous learning and adaptation will be necessary, especially in integrating lessons into the project's monitoring, knowledge management, and grievance redress processes hase is

## c. Information on the progress towards achieving gender sensitive measures/targets and any intermediate gender result areas as documented at CEO Endorsement/Approval including gender-sensitive indicators contained in the project results framework or gender action plan

## Progress towards achieving gender-sensitive measures and intermediate results

## Were all activities anticipated by the Gender Mainstreaming Plan (GMP) implemented?

## No, implementation is still in early stages.

## The project officially started  in the FY25 Q3, and while not all activities outlined in the GMP have been implemented yet, significant groundwork has been laid. Initial actions have included:

- Socialization of the GMP among implementing partners (CI Angola, INBAC, African Parks, ICCF).

- Initial integration of gender-responsive language in mission plans, ToRs, and stakeholder communication.

- Awareness raising during the AGM dissemination, which included introductory elements on gender-sensitive grievance handling.

- Identification of focal points for gender-responsive engagement at national and park levels.

## Importantly, the training and rollout of tools such as the Gender Balance Tree, Empowerment Leadership Mapping, and Challenge Action Tree (as detailed in the GMP and as part of the rollingout of the Gender Action and Learning System - GALS)  started in the last quarter of FY25 and are planned for the next quarter in Iona and Luengue Luiana.

## Did the project face any challenges in implementing the GMP as initially proposed?

Yes, several contextual and logistical challenges were encountered:

- Remote geographies and infrastructure: Travel limitations to remote project sites have impacted access to and Luengue Luiana National Parks.

- Inadequate baseline gender data: Although sex-disaggregated data collection is a GMP commitment, comprehensive baseline information is still being gathered.

## Was adaptive management applied to promote women’s participation and gender-sensitive targets?

## Yes, Adaptive and context-responsive measures are already being employed, especially in Iona:

- Tailored communication approaches: The project is adapting materials and training content to Portuguese and ultimately contextualised local languages and cultural references to ensure better comprehension and acceptance.

- Phased capacity building: Rather than centralized workshops, gender training will occur in situ using participatory and visual-based tools to enhance engagement and inclusivity.

- Stakeholder mapping revision: The original mapping is being refined to ensure that women-led organizations, traditional female leaders, and youth associations are specifically targeted in community engagement and planning activities.

- Integration of gender in safeguards: The Accountability and Grievance Mechanism (AGM) now includes guidance to ensure that complaints from women, autocthonous women, and other marginalized groups are handled with appropriate levels of confidentiality, dignity, and sensitivity.

- These measures are aligned with Section 6 of the GMP, which emphasizes participatory processes, intersectional analysis, and inclusive planning as critical pathways to equitable gender outcomes.

## Were there any unintended gender-related outcomes observed?

Yes, both positive and negative early signals have emerged:

## Positive observations:

- In Namibe (Iona), during the first safeguard consultation meetings, women were notably vocal, expressing interest in roles related to eco-tourism and sustainable livelihoods.

Challenging observations:

- In park areas bordering autocthonous territories, quality engagement remains limited, creating barriers  that further limit acceptance and buy in from local communities. Given that this was an initial engagement,the initial observation is that autoctonous women, especially in bordering autochthonous territories of Iona were less able to access, engage, and influence project decisions. There is need to have more engagements, to overcome this barrier and ensure that  all stakeholders benefits iqually and  buy-in to the project.

NB: The dynamics observed in Iona underscore the need to complement the technical rollout of gender tools with social norm change strategies and gender-transformative facilitation.

## Recommendations for FY26

To continue making meaningful progress toward the GMP targets and principles, the following strategic actions are recommended:

- Complete appropriate baseline gender assessments: Prioritize the rapid finalization of community-level, sex-disaggregated baseline data in both parks, aligned with the indicators in the GMP (Annex C).

- Rollout of GALS tools: Initiate structured training and roll-out of the Gender Balance Tree, Empowerment Mapping, and Challenge Action Tree in  both parks and where ideal and possible have them  facilitated by EAs (male and female facilitators)

- Mainstream gender in all components: Ensure gender is reflected not only in Component 1 (community resilience), but also in component 2 (Protected Area management); Component 3 (institutional strengthening)  and Component 4 (knowledge and M&E)

## NB: While the gender mainstreaming is still at an early stage of implementation, the foundational conditions have been set. The project has already adapted its approaches to field realities and is poised to deliver inclusive and contextually grounded gender outcomes.

## d. Lessons learned on the Environmental and Social Management Implementation

Lessons learned from ESMF implementation

What Worked Well

Safeguards integration from the Start

- The ESMF, including ESS, gender, stakeholder engagement and the grievance mechanism, was mainstreamed from the project outset. This included the revision of all safeguards guidance documents and the ongoing effective dissemination of the grievance mechanism

- The AGM was one of the first tools operationalized. Its translation into portuguese and clear guidance on reporting channels resulted in building of  trust, especially in Luanda and Iona NP, Namibe Province.

Collaboration with African Park and ICCF

- Leveraging existing trust networks of African Parks and ICCF enhanced access to communities and other key platforms (parliamentary) and facilitated safeguards uptake at the local level.

What needs to be improved

- Capacity building on safeguards in general, as many stakeholders, particularly field-level government staff and CSOs, require further training to fully understand and implement ESS standards and  safeguards in general.

- Monitoring and documentation

- Safeguards monitoring systems are still under development. The lack of systematic documentation of safeguards outcomes (, gender-disaggregated  data, ESS compliance tracking) limits early learning and adaptive management.

Stakeholder engagement in remote areas

- Engagement of autoctonous Peoples and remote communities remains challenging due to logistics, language barriers & limited availability of qualified or appropriate facilitators.

- tracking) limits early learning and adaptive management.

Stakeholder engagement in remote areas

- Engagement of autoctonous Peoples and remote communities remains challenging due to logistics, language barriers & limited availability of qualified or appropriate facilitators.

## e. Overall Project ESMF Implementation Progress Rating

| SUMMARY: PROJECT ESMF IMPLEMENTATION RATING BY TYPE OF PLAN |  |  |
| --- | --- | --- |
| ESMF PLAN REQUIRED BY THE PROJECT (delete those not applicable) | CURRENT FY25 IMPLEMENTATION RATING | RATING TREND |
| Accountability and Grievance Mechanism | MS | No rating provided in FY 25 |
| Gender Mainstreaming Plan (GMP) | MS | No rating provided in FY 25 |
| Stakeholder Management Plan (SEP) | MS | No rating provided in FY 25 |
| ESS 1: Full/limited ESIA and Environmental & Social Management Plan (ESMP) | N/A | No rating provided in FY 25 |
| ESS 4: Indigenous Peoples Plan | N/A | No rating provided in FY 25 |
| ESS 6: Cultural Heritage Management Plan | N/A | No rating provided in FY 25 |
| ESS 8: Community Health, Safety and Security Management Plan | N/A | No rating provided in FY 25 |

| OVERALL PROJECT ESMF IMPLEMENTATION RATING |  |  |
| --- | --- | --- |
| RATING |  | RATING TREND |
| MS | The project has made progress in integrating the ESMF, particularly through dissemination of the AGM and implementation of the SEP and GMP. However, there were delays in the operationalization of the AGM and some gaps in the tracking and resolution of grievances. In addition, the rollout of training and monitoring tools at park and community level remains incomplete. The project has not yet commenced implementation of activities related to Environmental and Social Impact Assessments (ESIAs), Indigenous Peoples, Cultural Heritage, and Community Health, Safety, and Security. Some of these activities are expected to be undertaken in tandem with other technical interventions. | No rating provided in FY 25 |

## Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| Strengthen capacity building through targeted ESS training for field staff, implementing partners, and community focal points to improve safeguards application. Finalize and deploy ESMF monitoring templates, including gender and grievance tracking tools, to systematically capture implementation data. Collaborate more closely with trusted community organizations and CSOs to extend safeguards outreach and ensure contextual relevance. Enhance ESMF implementation by broadening AGM dissemination and timely grievance resolution, reinforcing stakeholder engagement through localized approaches (e.g., language and cultural facilitators), and promoting inclusive participation—particularly of women and Indigenous Peoples—while mainstreaming gender considerations across all safeguard activities. | Israel Chauke, Safeguard Officer/PMU | June 30th, 2026 |

SECTION V: PROJECT IMPLEMENTATION EXPERIENCES, KNOWLEDGE MANAGEMENT AND LESSONS LEARNED

## a. Progress on the implementation of the project’s KM approach approved at CEO Endorsement/Approval

During its first year of implementation, the project has laid the foundation for a robust knowledge generation and sharing strategy, despite being in its inception phase. While the volume of finalized knowledge products is still limited, the project has embedded a strong commitment to producing, utilizing, and widely disseminating knowledge across all components. And this approach is also being conveyed to the project Executing Agencies. Key materials developed to date include a project factsheet and a blog post published at the project launch (https://www.conservation.org/gef/news/2025/05/21/launch-of-angola-gef-7-project-strengthening-management-and-climate-change-resilience-in-angola's-conservation-areas-for-sustainable-development), which was shared via social media platforms. These products articulate the project’s vision, expected outcomes, and implementation approach, and serve to enhance visibility and stakeholder engagement. As part of its environmental and social safeguard commitments, the project produced operational plans such as the Gender Mainstreaming Plan (GMP), the Accountability and Grievance Mechanism (AGM), and the Stakeholder Engagement Plan (SEP). Capacity-building sessions were conducted for INBAC personnel and implementing agency staff to deepen their understanding of these instruments, enabling them to tailor safeguard plans for their specific components. In early FY26, the project intends to support INBAC in replicating and institutionalizing these safeguard frameworks across the national network of conservation areas. In addition, African Parks has already developed the GMP that is awaiting sign-off to begin implementation. AP has also developed a grievance mechanism, which is fully functional since February 2024, in Iona National Park. The Parks stakeholder engagement plan is currently under development. The benefit-sharing structure with local communities is also being developed and expected to be finalised between Q1/Q2 FY26. The project also facilitated the participation of INBAC and CI-Angola technical staff in a regional knowledge exchange workshop on nature-based tourism (NBT), held in Kwazulu Natal, South Africa. The event was co-organized by the GWP (https://myemail.constantcontact.com/News-from-the-GWP.html?soid=1128055713699&aid=22uRFV2qMj4; https://isimangaliso.com/index.php?option=com_zoo&task=item&item_id=2844&Itemid=1294) and the World Bank and Government of South Africa (see annex below). As NBT is a key vehicle for climate-resilient livelihoods within the project, this engagement provided valuable insights, particularly around designing community-centered tourism products and benefit-sharing mechanisms. These learnings will inform project strategies and help ensure that local communities understand the value of tourism and are empowered to conserve wildlife and nature.

b. Additional optional topics (please choose two)

- Interpretation and application of GEF guidelines

Following the launch of the GEF-7 Angola project, it became evident that the level of familiarity among INBAC staff and executing agencies with the Environmental and Social Management Framework (ESMF) and its associated safeguard plans was low, reflecting the novelty of these instruments within the institutional context. In response, the project initiated a structured socialization process, targeting INBAC personnel and technical teams to build a foundational understanding of the safeguards and prepare them to develop context-specific implementation plans.

As part of the project launch, dedicated training sessions were delivered to executing agency staff by CI-GEF Agency, focusing on the technical, financial, ESMF and prohibited practices, ensuring that project activities do not inadvertently generate harm. Recognizing the safeguards framework as a relatively new tool, the project will continue supporting partners in internalizing these principles and applying them consistently across all implementation phases.

This capacity-building initiative is now considered an emerging good practice, and INBAC has expressed interest in scaling this approach by disseminating safeguard awareness and guidance to all stakeholders operating in protected areas nationwide.

- Project institutional arrangements, including project governance

The process of reviewing and adjusting the project’s implementation arrangement to formally incorporate INBAC as a project executing agency in addition to African Parks and ICCF offered important insights that will inform future project design and adaptive governance. Integrating a government entity like INBAC elevated national ownership and legitimacy, ensuring that the project was better anchored within existing institutional mandates. This transition required early flexibility, demonstrating the value of adaptive management in responding to shifting realities without compromising strategic objectives.

The revision of the implementation structure will support the capacity building of the INBAC team to effectively and efficiently implement the project. This CI and INBAC helped foster mutual accountability and operational clarity and streamlined coordination.

Finally, INBAC’s onboarding included targeted training and socialization around safeguard tools, setting a precedent for inclusive and responsible project implementation. This experience is now viewed as an emerging model for how technical revisions can be paired with strategic capacity-building to strengthen execution.

SECTION VI: PROJECT GEOCODING

This section of the PIR documents the precise and specific geographic location(s) of activities supported by GEF investments based on information provided in the Project Document.  The following information should be contained in this section:

  - Geo Location Information of Project Location(s) for the current fiscal year

  - Project Map and Coordinates from Project Document

Geo Location Information of Project Location(s) for the current fiscal year (add additional columns as needed)

| Geo Location Information | Location No. 1 | Location No. 2 | Location No. 3 |
| --- | --- | --- | --- |
| CLASSIFICATION Indicate whether the site is NEW (for new sites this FY23), EXISTING (already existing in the previous PIR) or CEO Endorsed/Approved (indicate whether the site is included at CEO Endorsement/Approval). Please add more columns for projects with more than 3 locations. Note: if the site is NEW, provide a justification in the box after this table | Existing | Existing |  |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | 3348212 3348212 | 876154 |  |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Iona National Park | Luengue-Luiana National Park |  |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -16.68692 | -16.81667, |  |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 12.22872 | 20.4 |  |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. | National park | National park |  |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini-grid energy system”. |  |  |  |

Please provide a justification regarding changes in location during implementation. Justifications should also be provided in the event the geographic

location of key project activities cannot be provided at CEO Endorsement/Approval stage.

(Geo Name ID: Location Name) Justification:

Project Map and Coordinates

Please provide geo-referenced information and image map where the project interventions took place. If available, please provide attachments as

appropriate such as in the case of locations presented along geometric shapes in popular formats like shapefiles, KML and GeoJSON (See annex 1).

(Geo Name ID: Parque Nacional do Iona) Map:

Section VII: Minor Amendments

This section of the PIR captures the changes to the project design or implementation that do not have significant impact on the project objectives or scope as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Select any minor amendment that happened to the project during the latest fiscal year and provide a description of the minor amendment in a narrative format (max 100 words) as appropriate in the related textbox. You may provide supporting documents as attachment to this PIR.

| Minor Amendment Categories | Minor Amendment Justification |
| --- | --- |
| Results framework | Prior to the project launch, there were minor reviews and adjustments to the project outputs were made |
| Components and cost | No |
| Institutional and implementation arrangements | The project was reviewed, and adjustments were made to the project’s implementation arrangements to incorporate INBAC formally as a project executing agency. INBAC offers important insights that will inform future project design and adaptive governance. |
| Financial management | Following the revision of the project’s implementation arrangement and the formal designation of INBAC as the executing agency, dedicated funding will be allocated to support INBAC’s leadership in several project components. Specifically, INBAC will oversee the implementation of Component 2, which focuses on improving conservation area management and wildlife protection in Luengue-Luiana National Park, and Component 3, which targets the enhancement of institutional and technical capacities related to climate change and biodiversity conservation. In addition to these core responsibilities, INBAC will also contribute to cross-cutting interventions across other components, reinforcing its role as a strategic anchor institution within the project’s delivery framework. |
| Implementation schedule | The project implementation in the first two years was heavily delayed due to frequent changes in government leadership and politically driven variables, which also resulted in a significant redefinition of the project’s implementation arrangements and budget realignment. This led to the project being extended by one year. Thus, the end date will be September 2032. This extension ensures adequate time to fully implement the project activities |
| Executing Entity | No |
| Executing Entity Category | No |
| Minor project objective change | No |
| Safeguards | No |
| Risk analysis | No |
| Increase of GEF project financing up to 5% | No |
| Co-financing | N/A |
| Location of project activity | No |
| Other | No |

MINOR AMENDMENT RESPONSE FROM CI-GEF

Provide approval or reject minor amendment request along with a justification

APPENDIX I: PROJECT ANNUAL IMPLEMENTATION PROGRESS RATING

| Rating |  | Overdue (O) | Delayed (D) | Not started on schedule (NS) | Under implementation on schedule (IS) | Completed/Achieved (CA) |
| --- | --- | --- | --- | --- | --- | --- |
| Highly Satisfactory (HS) | HS | 0% |  | 100% |  |  |
| Satisfactory (S) | S | 20% |  | 80% |  |  |
| Moderately Satisfactory (MS) | MS | 40% |  | 60% |  |  |
| Moderately Unsatisfactory (MU) | MU | 60% |  | 40% |  |  |
| Unsatisfactory (U) | U | 80% |  | 20% |  |  |
| Highly Unsatisfactory (HU) | HU | 100% |  | 0% |  |  |

- Highly Satisfactory: 100% of the indicators:  a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Annual Workplan for the project. The project can be presented as an example of “good practice” project,

- Satisfactory: 80% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; except for only 20% that are delayed and/or overdue and need remedial action,

- Moderately Satisfactory: 60% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 40% are delayed and/or overdue and need remedial action,

- Moderately Unsatisfactory: 40% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 60% are delayed and/or overdue and need remedial action,

- Unsatisfactory: only 20% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 80% are delayed and/or overdue and need remedial action, and

- Highly Unsatisfactory: 100% of the indicators: a) are overdue, and/or b) delayed in their implementation, according to the approved/revised Project Annual Workplan for the project.

# APPENDIX II: RISK RATINGS

| Rating |  |
| --- | --- |
| Low (L) | L |
| Moderate (M) | M |
| Substantial (S) | S |
| High (H) | H |

- Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

- High Risk: There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

# APPENDIX III: PROGRESS TOWARDS ACHIEVING PROJECT EXPECTED OUTPUTS

| INDICATORS | PROJECT TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- |
| Outcome 1.1: Increased implementation of biodiversity-compatible adaptation practices (encompassing the eco-village approach) in the Angolan portions of targeted TFCAs. |  |  |  |  |
| Output Indicator 1.1.1: Number of climate risk and vulnerability assessments conducted for the Angolan portions of the targeted TFCAs. | Target 1.1.1.: 2 comprehensive climate risk and vulnerability assessments conducted (1 assessment for the Angolan portion of the KAZA TFCA and 1 assessment for the Angolan portion of the Iona-Skeleton Coast TFCA). | Zero (0) | IS | The consultancy Terms of Reference (ToR) to undertake this Climate Risk and Vulnerability Assessment in Iona and Luengue-Luiana National Parks. has been completed and will be posted FY26 Q1 |
| Output Indicator 1.1.2: Number of natural capital accounting assessments undertaken for the Angolan portions of the targeted TFCAs. | Target 1.1.2.: 2 natural capital accounting assessments undertaken (1 for the Angolan portion of KAZA and 1 for the Angolan portion of Iona-Skeleton Coast TFCA) | Zero (0) | IS | The preparation of the consultancy Terms of Reference to undertake the Natural Capital Accounting Assessment in Iona and Luengue-Luiana National Parks has been completed and will be posted in FY26 Q1 |
| Output Indicator 1.1.3: Number of local adaptation plans developed. | Target 1.1.3.: 2 local adaptation plans developed (1 in the Angolan portion of KAZA and 1 in the Angolan portion of Iona-Skeleton Coast TFCA). | Zero (0) | IS | In FY25, the PMU and INBAC have held discussions with the National Directorate of Climate Action and Sustainable Development (DNACDS) to determine the entry points to support the development of local adaptation plans and efforts in Iona and Luengue-Luiana National Parks. |
| Output Indicator 1.1.4: Number of people (% female) trained on climate-resilient and biodiversity-compatible adaptation practices. | Target 1.1.4: 5,000 people (30% female) trained on climate-resilient and biodiversity-compatible adaptation practices. | Zero (0) | NS | This activity will commence in FY 26 Q1 |
| Output Indicator 1.1.5: Number of community members (% female) provided with technical support and inputs to implement appropriate biodiversity-compatible adaptation practices identified in local adaptation plans. | Target 1.1.5.: 5,000 community members (30% female) provided with technical support and inputs to implement appropriate biodiversity-compatible adaptation practices identified in local adaptation plans. | Zero (0) | NS | This activity will start in FY26 Q1 |
| Output Indicator 1.1.6: Number of eco-villages established around Luengue-Luiana and Iona National Parks | Target 1.1.6: 10 eco-villages established around Luengue-Luiana National Park and 5 eco-villages around Iona National Park | Zero (0) | IS | CI-Angola held a virtual meeting to learn from the CI-regional team in South Africa on the approaches they are using in establishing the eco-villages in Botswana and to gain more knowledge on the best practices and challenges they faced. In FY 26 Q1, CI-Angola will organize a lessons learnt session between the project partners and CI Regional Team on the design of the eco-village models and also conduct a study tour to visit one of the models to get insights and determine what models can be replicated in Angola TFCA. |
| Output Indicator 1.1.7: Number of community members (% female) in communities not targeted by the project provided with knowledge on successful biodiversity-compatible adaptation measures | Target 1.1.7: 1,000 community members (30% female) provided with knowledge on successful biodiversity-compatible adaptation measures across the wider KAZA TFCA landscape (within and across international boundaries). 1,000 community members (30% female) provided with knowledge across the wider Iona-Skeleton Coast TFCA landscape (within and across international boundaries) | 140 (68 Men, 72 Women) | IS | In Iona, a total of 140 people, 51% Women, were provided with knowledge on the adoption of climate adaptation/biodiversity, including craft making and sustainable subsistence farming. In Lungue Luina, activity to commence in FY26 |
| Outcome 1.2.: Additional climate-resilient and biodiversity-compatible livelihood activities and sources of income established in the Angolan portions of targeted TFCAs to decrease vulnerability of local communities to climate change and reduce degradation of ecosystems. |  |  |  |  |
| Output Indicator 1.2.1.: Number of market assessments for additional climate-resilient and biodiversity-compatible livelihood options conducted. | Target 1.2.1: 2: Market assessments (1 for the Angolan portion of the KAZA TFCA and 1 for the Angolan part of the Iona-Skeleton Coast TFCA) | Zero (0) | IS | The consultancy ToR to undertake this market assessment in Iona and Lungeue Luina has been developed, and the procurement process to be launched in FY25 Q1. |
| Output Indicator 1.2.2.: Number of business plans developed | Target 1.2.2.: At least 6 business plans developed for viable additional climate-resilient and biodiversity-compatible livelihood options (at least 3 in the Angolan portion of the KAZA TFCA and at least 3 in the Angolan part of the Iona-Skeleton Coast TFCA) | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 1.2.3.: Number of community members (% female) trained on establishing and managing relevant viable additional climate-resilient and biodiversity-compatible livelihood options. | Target 1.2.3: 5,000 community members (30% female) trained on establishing and managing relevant viable additional climate-resilient and biodiversity-compatible livelihood options. | Zero (0) | NS | Activity to commence in FY26 Q1 |
| Output Indicator 1.2.4.: Number of community members (% female) provided with support and inputs to establish viable additional climate-resilient and biodiversity-compatible livelihood options. | Target 1.2.4: 5,000 community members (30% female) provided with support and inputs to establish viable additional climate-resilient and biodiversity-compatible livelihood options. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 1.2.5.: Number of community members (% female) in communities not targeted by the project provided with knowledge on viable additional climate-resilient and biodiversity-compatible livelihood options. | Target 1.2.5: 2000 community members (30% female) in communities not targeted by the project provided with knowledge on viable additional climate-resilient and biodiversity-compatible livelihood options (1,000 community members (30% female) across the wider KAZA TFCA landscape and 1,000 community members (30% female) across the wider Iona-Skeleton Coast TFCA landscape). | Zero (0) | NS | Activity to commence in FY26 Q1 |
| Outcome 2.1: Improved management of conservation areas in the Angolan portion of the KAZA TFCA. |  |  |  |  |
| Output Indicator 2.1.1: Number of people (% female) trained on climate change adaptation planning. | Target 2.1.1: 50 people (30% female) trained on climate change adaptation planning. | Zero (0) | NS | This activity will commence after the development of the climate adaptation action plan for Luengue Luiana. |
| Output Indicator 2.1.2.: Management plan that has integrated climate risk information | Target 2.1.2: 1 updated management plan for Luengue-Luiana National Park | Zero (0) | D | This activity did not start in FY25 due to the delay in signing INBAC’s grant agreement, occasioned by revisions to the implementation structure to include INBAC as part of the PMU and to implement the activities in Luengue Luina. The activity will commence in FY26 Q1 as the grant agreement with INBAC is now signed. |
| Out Indicator 2.1.3.: Percentage of priority interventions aimed at mitigating climate risk and strengthen biodiversity identified in updated management plan implemented. | Target 2.1.3: 50% of priority interventions aimed at mitigating climate risk and strengthen biodiversity identified in updated management plans implemented. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 2.1.4.: Number of hydrometeorological stations established | Target 2.1.4: At least 1 hydrometeorological station in Luengue-Luiana National Park | Zero (0) | IS | The PMU, together with INBAC, held discussions with INAMET to understand the current coverage of meteorological services, equipment specifications for hydrometeorological stationland existing needs in Luengue-Luiana. The PMU will continue working with INAMET and the Park management in Luengue-Luiana to carry out a needs assessment to inform the development of an action plan to guide the establishment of hydrometric systems in Luengue-Luiana and connect them to the national system. |
| Output Indicator 2.1.5.: Number of study tours conducted for conservation agencies in the wider KAZA TFCA landscape to Luengue-Luiana National Park | Target 2.1.5: 2 study tours conducted for conservation agencies in the wider KAZA TFCA landscape to Luengue-Luiana National Park | Zero (0) | NS | Activity to commence in FY26 Q4 |
| Outcome 2.2: Improved management of conservation areas in the Angolan portion of the Iona-Skeleton Coast TFCA. |  |  |  |  |
| Output Indicator 2.2.1.: Number of people (% female) trained on climate change adaptation planning. | Target 2.2.1.: 50 people (30% female) trained on climate change adaptation planning. | Zero (0) | NS | This activity will commence after the development of the climate adaptation action plan for Iona National Park. |
| Output Indicator 2.2.2.: Management plan that has integrated climate risk information. | Indicator 2.2.2: Management plan that has integrated climate risk information. | Zero (0) | IS | The PMU is reviewing the existing Management Plan for Iona National Park to ensure it has climate risk information integrated into it. Additionally, African Parks has commenced the preparation of the Park’s Land Use Plan (LUP), which will complement the existing Management Plan that was developed before the project commenced. The LUP will guide zoning for conservation, grazing, and community use, helping reduce human-wildlife conflict. The stakeholder consultations were completed in FY25, and the draft will be shared for review. |
| Output Indicator 2.2.3.: Percentage of priority interventions aimed at mitigating climate risk and strengthen biodiversity identified in updated management plans implemented. | Target 2.2.3: 50% of priority interventions aimed at mitigating climate risk and strengthen biodiversity identified in updated management plan implemented. |  | NS | In Iona National Park: - Key Species Mapping & Land Use Planning - completed the mapping of key species, including zebra, oryx, and springbok. Data analysis continues to refine movement corridors, mortality patterns, and land-use planning, supporting the ongoing Land Use Plan (LUP) development. - Wildlife Monitoring & Collaring Activities - The park has procured additional collars and is expected to arrive in Iona in FY26 Q1, with collaring scheduled for the same quarter. The park continues to closely monitor collared cheetahs, assessing their range, habitat use, and frequency in livestock areas, as cheetah predation on livestock remains a primary human-wildlife conflict concern. - Predator-Proof Corrals & Human-Wildlife Conflict Study -The delivery of solar-powered lights for predator-proof corrals is delayed and is now expected in FY25 Q4, with the pilot project launch immediately after delivery. - Human-Wildlife Conflict Study is scheduled for FY26 Q1 & Q2, aimed at evaluating conflict patterns and refining strategies for predator-proof corrals before scaling the initiative to additional localities. - Vocational Training & Park Operations- Five individuals have been recruited to provide training to work in the park operational team. - Rangeland Restoration & Specialist Consultation- Terms of Reference (ToRs) are currently under review for the recruitment of a Rangeland restoration consultant will assessing restoration feasibility in the park. The recruitment process and consultation are expected to begin in FY25 Q3/Q4. |
| Output Indicator 2.2.4.: Number of hydrometeorological stations established/strengthened. | Target 2.2.4.: At least 1 hydrometeorological station in Iona National Park. | Zero (0). | IS | Before the project commencement, African Parks had installed six hydrometeorological stations in Iona Park, which were not linked to INAMET’s national network. The PMU and African Parks, with guidance from INBAC, have commenced the discussion with INAMET. They agreed to develop a joint action plan to connect Iona’s hydrometeorological stations to the national network, ensuring technical compatibility, data sharing, and institutional coordination moving forward. Under this output, the project will support the strengthening of these stations. |
| Output Indicator 2.2.5.: Number of study tours conducted for conservation agencies in the wider Iona-Skeleton Coast TFCA landscape to Iona National Park | Target 2.2.5.: 2 study tours conducted for conservation agencies in the wider Iona-Skeleton Coast TFCA landscape to Iona National Park | Zero (0) | NS | Activity to commence in FY27 Q1 |
| Outcome 2.3.: Decreased poaching of priority species in Luengue-Luiana National Park. |  |  |  |  |
| Output Indicator 2.3.1.: Existence of anti-poaching strategy and action plan. | Target 2.3.1.: 1 anti-poaching strategy and action plan for Luengue-Luiana National Park. | Zero (0) | NS | Activity to commence in FY26 Q1 |
| Output Indicator 2.3.2.: Number of anti-Poaching Patrol bases established | Target 2.3.2: 8 anti-Poaching Patrol bases established | Zero (0) | NS | Activity to commence in FY26 Q1 |
| Output Indicator 2.3.3.: Number of APUs established/ strengthened and equipped | Target 2.3.3: 5 APUs established/strengthened and equipped. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 2.3.4.: Number and nature of introduced wildlife monitoring and reporting tools | Target 2.3.4.: At least 1 wildlife monitoring and reporting tool introduced. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 2.3.5.: Number of anti-poaching unit staff (% female) trained on operating introduced operational, communications and wildlife monitoring and reporting tools. | Target 2.3.5.: 30 anti-poaching unit staff (30% female) trained on operating introduced operational, communications and wildlife monitoring and reporting tools. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 2.3.6.a.: Number of meetings of transboundary law enforcement convened | Target 2.3.6.a.: 6 meetings (one per year from Year 2 of the project) | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Output Indicator 2.3.6.b.: Number of cross-border law enforcement Standard Operating Procedures (SOPs) developed | Target 2.3.6.b: At least 1 Standard Operating Procedures (SOPs) developed | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Outcome 2.4.: Decreased poaching of priority species in Iona National Park. |  |  |  |  |
| Output Indicator 2.4.1.: Existence of anti-poaching strategy and plan. | Target 2.4.1: 1 anti-poaching strategy and action plan for Iona National Park. | Zero (0) | IS | African Park has commenced reviewing the law enforcement strategy to be operationalized in Iona and has the anti-poaching action plan as a central component. The draft strategy will be shared with the Park for review and validation by INBAC and stakeholders.. |
| Output Indicator 2.4.2.: Number of Forward Operating bases established | Target 2.4.2: 8 Forward Operating bases established | Zero (0) | IS | African Parks conducted an assessment of the Espinheira Forward Operating Base (FOB), formerly the park’s headquarters, to evaluate rehabilitation and infrastructure improvement needs. African Park’s civil engineer carried out the inspection, identifying necessary upgrades to enhance the efficiency of operations, particularly in law enforcement and other critical departments. In FY 26, the project will finalize the improvement plans, ensuring the FOB is fully optimized to support conservation and security efforts within Iona National Park. |
| Output Indicator 2.4.3: Number of Anti-Poaching Units (APUs) established/ strengthened and equipped | Target 2.4.3: 8 APUs established/strengthened and equipped | Zero (0) | IS | In Iona National Park, the mobile patrol system to be adopted. The systems will be strengthened/equipped with the Aerial Surveillance and Illegal Activity Monitoring, Law Enforcement Operations and Partnerships, Legal Actions and Environmental Crime Prosecution and Vehicle Maintenance and Field Operations. The system will be integrated and linked to the EarthRanger App. |
| Output Indicator 2.4.4.: Number and nature of introduced wildlife monitoring and reporting tools | Target 2.4.4.: At least 1 wildlife monitoring and reporting tool introduced. | One (1) | IS | African Park has deployed the EarthRanger App to support wildlife monitoring a reporting in Iona National Park. In FY26 Q1 the park will further strengthen data collection and incident reporting, including carrying out capacity building training for Park technicians |
| Output Indicator 2.4.5.: Number of anti-poaching unit staff (% female) trained on operating introduced operational, communications and wildlife monitoring and reporting tools. | Target 2.4.5. 30 anti-poaching unit staff (30% female) trained on operating introduced operational, communications and wildlife monitoring and reporting tools. | Two (2) anti-poaching unit staff . | IS | A new boat for the Park (INP) has been fully equipped with maritime radios, and two Park staff were trained to use it. The boat is integrated into both park communication frequencies and maritime authorities' networks, ensuring seamless coordination for marine patrols. All necessary licenses for operation have been obtained, marking a significant step toward enhanced surveillance and enforcement in coastal areas. In FY 26, African Parks will continue working with the Port Authorities to provide training to more staff. Additionally, training on marine law enforcement operations are currently being explored, if deemed feasible, they could be rolled out in FY26 Q3 to strengthen coastal protection and enforcement capacity. |
| Output Indicator 2.4.6.a.: Number of meetings of law enforcement convened | Target 2.4.6.a.: 6 meetings (one per year from Year 2 of the project) | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Output Indicator 2.4.6.b.: Number of law enforcement Standard Operating Procedures (SOPs) developed | Target 2.4.6.b.: At least 1 Standard Operating Procedures (SOPs) developed | Zero (0) | IS | The Park started the process to update the law enforcement strategy, which will also include the development of SOP. African Park has also mapped key entities to be engaged under the law enforcement: the Namibian authorities or Skeleton Coast National Park (SCNP), and Save the Rhino Trust. This will strengthen the anti-poaching capacity and reinforce efforts to monitor and protect endangered species in the region. |
| Outcome 3.1.: Enhanced institutional capacity of national government agencies to coordinate, plan and implement climate change and biodiversity strategies. |  |  |  |  |
| Output Indicator 3.1.1.: Number of strategies, policies and plans reviewed | Target 3.1.1: 5 strategies, policies and plans reviewed | Zero (0) | NS | The activity to commence in FY26 Q1 |
| Output Indicator 3.1.2: Number of policy briefs and technical guidelines produced | Target 3.1.2: At least 3 policy briefs and technical guidelines produced |  | NS | Activity to commence in FY26 Q4 |
| Output Indicator 3.1.3: Data generated by the project captured in existing climate change databases. | Target 3.1.3: All of the data generated through the development of the comprehensive climate risk and vulnerability assessments captured in a climate change database. |  | IS | The project finalized the development of the ToR for the climate risk and vulnerability assessment. The ToR posting and recruitment of the consultant to be conducted in FY25 Q1.. |
| Outcome 3.2.: Improved technical and institutional capacity of sub-national government agencies to coordinate, plan and implement climate change and biodiversity strategies at provincial and municipal levels. |  |  |  |  |
| Output Indicator 3.2.1.: Number of decentralised Provincial Committees on Climate Change and Biodiversity | Target 3.2.1: 2 decentralised Provincial Committees on Climate Change and Biodiversity established (1 committee in Namibe Province; 1 committee in Cuando Cubango Province) | Zero (0) | D | This start has not commenced due to the delay in signing INBAC’s grant agreement, as the revisions of the implementation structure are being made to allow INBAC to be part of the PMU and implement the activities in Luengue Luina. The activity will commence in FY26 Q1 as the grant agreement with INBAC is now signed. |
| Output Indicator 3.2.2.: Number and nature of zoning and land-use planning tools developed | Target 3.2.2.: At least 1 province-level zoning and land-use planning tool developed and operationalised for the two provinces (Namibe and Cuando Cubango); at least 1 municipality-level zoning and land-use planning tool developed and operationalised for the municipalities surrounding the parks (4 for Luengue-Luiana and 1 for Iona), with additional tools developed at commune-level as necessary | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 3.2.3: Number of members (% female) of Provincial Committees on Climate Change and Biodiversity, staff of selected CSOs and municipalities trained. | Target 3.2.3: 40 members (30% female) of Provincial Committees on Climate Change and Biodiversity, staff of selected CSOs and municipalities trained. | Zero (0) | D | This start has not commenced due to the delay in signing INBAC’s grant agreement, as the revisions of the implementation structure are being made to allow INBAC to be part of the PMU and implement the activities in Luengue Luina. The activity will commence in FY26 Q1 as the grant agreement with INBAC is now signed. |
| Output Indicator 3.2.4.: Number of municipal master plans updated to integrate climate risk information, biodiversity conservation and gender considerations. | Target 3.2.4: At least 4 municipal master plans (2 per province) updated to integrate climate risk information, biodiversity conservation and gender considerations. | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Outcome 3.3.: Enhanced technical and institutional capacity to manage Angola's Conservation Area Network. |  |  |  |  |
| Output Indicator 3.3.1.: Number of memoranda of understanding prepared and circulated. | Target 3.3.1: At least 2 memoranda of understanding prepared and circulated. | Zero (0) . | IS | At the end of FY 25 Q4, one MoU was draft to guide the relation between CI-AfFD and the Government of Angola, Throuhg the Ministry of environment to support the country conservation network and guide both parties cooperation on various fields include on conservation network management.. This MoU will be signed early in FY26. |
| Output Indicator 3.3.2.: Number of meetings held. | Target 3.3.2.: 7 meetings held (one each year of the project). | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Output Indicator 3.3.3.: Number of training programmes on conservation areas management — that include climate change adaptation — developed and implemented. | Target 3.3.3.: 1 training programme on conservation areas management — that include climate change adaptation — developed and implemented. | Zero (0) | NS | Activity to commence in FY27 Q1 |
| Output Indicator 3.3.4.: Number of training programmes institutionalised at the Wildlife Ranger school in Menongue | Target 3.3.4.: 1 training programme institutionalised at the Wildlife Ranger school in Menongue | Zero (0) | NS | Activity to commence in FY27 Q2 |
| Outcome 3.4.: Strengthened capacity of the private sector and other key stakeholders to develop Nature-based Tourism (NBT) and sustainable use activities in Angola's conservation areas. |  |  |  |  |
| Output Indicator 3.4.1.: Number of business plans developed. | Target 3.4.1.: 2 business plans developed (1 for each national park). | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 3.4.2.: Number of investment summits conducted. | Target 3.4.2.: 1 investment summit conducted over the lifespan of the project. | Zero (0) | NS | Activity to commence in FY26 Q3 |
| Output Indicator 3.4.3.: Number of media and marketing strategies developed | Target 3.4.3.: 2 media and marketing strategies (1 for each park). | Zero (0) | IS | The Terms of Reference to engage a legal consultant to conduct a review of existing policies and legal frameworks to enable nature-based tourism interventions was prepared and will be posted in FY25 Q1. |
| Output Indicator 3.4.4.: Number of marketing campaigns conducted. | Target 3.4.4: 2 marketing campaigns (1 for each park, with annual events). | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Outcome 3.5.: Increased ability of institutions in Angola to access climate and biodiversity finance. |  |  |  |  |
| Output Indicator 3.5.1.: Existence of recommendations, policies, and standards for the restructuring of an environmental fund in Angola. | Target 3.5.1.: A set of recommendations, policies, and standards for the restructuring of an environmental fund in Angola. | Zero (0) | IS | The project held an initial meeting with the National Directorate of Climate Action and Sustainable Development (DNACDS) to introduce the project and understand the sector needs and priorities. In FY26 Q1, this project will resume these discussions |
| Output Indicator 3.5.2.: Existence of operational manual for the environmental fund | Target 3.5.2.: 1 operational manual for the environmental fund | Zero (0) | IS | The project held an initial meeting with the National Directorate of Climate Action and Sustainable Development (DNACDS) to introduce the project and understand the sector needs and priorities. In FY26 Q1, this project will resume these discussions. |
| Output Indicator 3.5.3.: Number of staff (% female) of the environmental fund trained. | Target 3.5.3.: 10 staff (30% female) of the environmental fund trained. | Zero (0) | NS | Activity to commence in FY26 Q2 |
| Output Indicator 3.5.4.: Existence of results-based management system | Target 3.5.4.: 1 results-based management system established | Zero (0) | NS | Activity to commence in FY26 Q1 |
| Outcome 4.1.: Effective monitoring and evaluation of adaptation and biodiversity conservation interventions in the project target areas. |  |  |  |  |
| Output Indicator 4.1.1: Number of project staff members trained. | Target 4.1.1: 5 project staff members trained (at least 2 female). | 15 (9 Men and 6 Women) | IS | During FY25 Q4, a preparatory session was held between the CI AfFD MEAL Manager and CI-Angola held the monitoring and evaluation training for both PMU and project partners. The training was tailored to the data collection instruments for each executing partners. In FY26 Q1, a training session will be conducted involving staff from all executing agencies to ensure effective use M&E tool developed. |
| Output Indicator 4.1.2.: Number of monitoring reports generated. | Target 4.1.2.: At least 7 monitoring reports generated (at least 1 per year). | Zero(0) | IS | Staff from each project executing partners were trained during the FY25 Q4 on the principles and practices of how to collect data and report in the MEAL system. |
| Output Indicator 4.1.3: Number of M&E reports submitted to CI-GEF and the GEF Secretariat | Target 4.1.3: 28 quarterly technical and financial reports submitted to CI-GEF throughout lifetime of project; 7 annual PIRs submitted to the GEF Secretariat; one Mid-Term Evaluation (MTE) report; and one Terminal Evaluation (TE) report submitted to the GEF Secretariat. | 2 Quarterly Report 1 PIR | IS | In FY25 the project produced 2 quarterly report sand 1 PIR submitted to CI-GEF. |
| Outcome 4.2: Improved knowledge-sharing among institutions in Angola, and with other countries, donors, and key stakeholders across the wider TFCA landscapes. |  |  |  |  |
| Output Indicator 4.2.1.a: Number of coordination meetings held between relevant institutions in Angola. | Target 4.2.1.a: At least 7 coordination meetings (1 per year) held where lessons learned from the project are shared. | Zero (0) | IS | The project established a Technical Coordination Committee that comprises all project partners. The Committee meets monthly to discuss project progress and share lessons learnt. The annual thinn and reflect workshops will commence in FY26. |
| Output Indicator 4.2.1.b.: Number of presentations on lessons learned given at national-level conferences. | Target 4.2.1.b: At least 4 presentations (1 per year for the last 4 years of the project) | Zero (0) | NS | Activity to commence in FY26 Q4 |
| Output Indicator 4.2.2.a.: Number of reports generated and shared with park administrators, other countries, donors, and key stakeholders | Target 4.2.2.a.: At least 7 reports (one each year of the project). | Zero (0) | NS | To commence in FY26 Q1 |
| Output Indicator 4.2.2.b.: Number of presentations generated and shared with park administrators, other countries, donors, and key stakeholders | Target 4.2.2.b.: 7 presentations generated and shared | Zero (0) | NS | Activity to commence in FY26 Q4 |
| Output Indicator 4.2.2.c.: Number of social media posts/blog posts generated and shared | Target 4.2.2.c.: 70 social media posts/blog posts generated and shared (10 posts/blog posts per year) | 1 blog post | IS | The project produced one blog post highlighting the official launch of the project implementation phase, along with a fact sheet that was widely disseminated to national and international stakeholders. These materials contributed to raising awareness, promoting transparency, and strengthening stakeholder engagement during the early phase of implementation. Link the GEF 7 launch of project implementation phase: https://www.conservation.org/gef/news/2025/05/21/launch-of-angola-gef-7-project-strengthening-management-and-climate-change-resilience-in-angola's-conservation-areas-for-sustainable-development Angola GEF 7 fact sheet: |

Progress (IP) Rating: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). For more details about IP rating, please see the Appendix I of this report

Rating trend: Improving, Unchanged, or Decreasing

Risk Rating: Low (L), Moderate (M), Substantial (S), High (H)

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

Rating trend: Increasing, Unchanged or Decreasing

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

EarthRanger App:is a real-time software platform developed by the Allen Institute for Artificial Intelligence (AI2) to support wildlife conservation and protected area management. It's designed for use by conservationists, ecologists, wildlife biologists, and protected area managers to make informed decisions using integrated data from the field: https://www.earthranger.com/