ANNUAL REPORT
06.30.23

Sostenibilidad de la biodiversidad nativa

Bionegocios

Ecuador

Project Implementation Review

CAF-GEF PIR for Fiscal Year:  2023

(Period: July 2022 to June 2023)

PART A – Project Implementation Progress & Risk Management

- PROJECT GENERAL INFORMATION

| Project Title: | Development of an Enabling Environment for Sustainable Businesses based on the Native Biodiversity of Ecuador |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementing Agency: | Heifer Foundation Ecuador |  |  |  |  |  |  |
| Direct beneficiary: | Ministry of Environment, Water and Ecological Transition |  |  |  |  |  |  |
| Project partners: | Ministry of Environment, Water and Ecological Transition (MAATE); Ministry of Agriculture and Livestock (MAG); Ministry of Production, Foreign Trade, Investments and Fisheries, (MPCEIP); Corporation for the Promotion of Exports and Investments (CORPEI); Pro-Ecuador; National Agency for Health Regulation, Control and Surveillance (ARCSA); the Phytosanitary and Zoo sanitary Regulation and Control Agency, (AGROCALIDAD). |  |  |  |  |  |  |
| Geographical Scope | National |  |  |  |  |  |  |
| Participating Countries: | Ecuador |  |  |  |  |  |  |
| GEF project ID: | 10219 |  | CAF Project ID: |  |  | CAF-GEF-016 |  |
| Focal Area(s): | Biodiversity |  | GEF OP #: |  |  |  |  |
| GEF Strategic Priority/Objective: | BD-1-1 |  | GEF approval date*: |  |  | 12/14/2021 |  |
| CAF approval date: | 04/22/2022 |  | Date of first disbursement*: |  |  | 17/01/ 2023 |  |
| Actual start date: | 07/18/2022 |  | Planned duration: |  |  | 48 months |  |
| Intended completion date*: | 07/17/2026 |  | Actual or Expected completion date: |  |  | 07/17/2026 |  |
| Project Type: | FSP |  | GEF Allocation*: |  |  | 3,119,266 |  |
| PPG GEF cost*: | USD 100,000 |  | PPG co-financing: |  |  | USD 0 |  |
| Expected MSP/FSP Co-financing*: | 21,201,297 |  | Total Cost*: |  |  | 24,320,563 |  |
| Mid-term review/eval. (Planned date): | 06/30/2024 |  | Terminal Evaluation (actual date): |  |  | 07/17/2026 |  |
| Mid-term review/eval. (Actual date): | 06/30/2024 |  | No. of revisions*: |  |  | 1 |  |
| Date of last Steering Committee meeting: | 09/1/2023 |  | Date of last Revision*: |  |  | 04/1/2023 |  |
| Disbursement as of June 2023 | 256.795,00 USD |  | Date of financial closure*: |  |  | 06/23/2023 |  |

| Date of Completion: | 06/30/2023 | Actual expenditures reported as of _______: | 23/06/2023 |
| --- | --- | --- | --- |
| Total co-financing realized as of_______: |  | Actual expenditures to date: | 188.936,39 USD |
| Leveraged financing: |  |  |  |

| Project summary | The current Ecuadorean business environment is inadequate for the development of bioendeavours. However, the adoption of Environmental Code (COA -spanish acronym) and its regulations (RCOA) open opportunities by stating that BioTrade must be promoted. Therefore, the project seeks to: (i) contribute to operationalize BioTrade as established in the COA and RCOA, (ii) to support MAATE to develop a robust conceptual framework and from there build intersectoral dialogue and collaboration to incentive bioendeavours and (iii) to implement actions to confront some key barriers (basic legal loopholes, access to business development training, and access to credit). In the long term, the project will contribute to establish the foundation for sustainable native biodiversity-based businesses as a key tool to confront biodiversity loss in a megadiverse country. The global benefits will be demonstrated through enhanced protection of native biodiversity, including agrobiodiversity. A central element of the project strategy is to work closely with four companies whose experience and expertise will be valuable in developing appropriate incentives and tools. Specific actions on strengthening the supply chains for pet frogs and mortiño will directly contribute to safe from extinction threatened Andean frogs and to conserve the populations of a wild native fruit which has not been domesticated. The specific actions on strengthening the supply chains for quinua, uvilla, aji, camote, white carrot, and chocho will contribute to expand organic agriculture and to sustain cultivars of native landraces in Andean chakras and smallholdings. The objective of the project is to create basic conditions in Ecuador that facilitate the development of businesses that sustainably use biodiversity. The project is organized into three components: - Component 1 will contribute to develop key enabling conditions for bioendeavours. This includes solving crucial regulatory gaps, implementing interagency collaboration and coordination mechanisms, and developing a platform for capacity building in entrepreneurial and business skills. - Component 2 will develop financing lines for bioendeavours. - Component 3 will generate on the ground learning collaboration with four biodiversity-based businesses and will document and share lessons and practical experience. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project status FY23 | In the first year, emphasis was placed on: i) creation of structures for participation and dialogue necessary to promote the interinstitutional agreements sought by the Project and ii) evaluation and strengthening of pilot businesses. In this context, MAATE´S bioendeavours working group has been established. This group is comprised of 18 officials from the Undersecretariats of Environmental Regulation: Natural Heritage and Climate Change and Water. This has allowed us to establish a roadmap that prioritizes the interests and areas of improvement of the departments responsible for the regulation and development of bioendeavours. The critical areas addressed in this roadmap are conceptual framework of bioendeavours, capacity building for institutional management on bioendeavours, incentives associated with the BioEcuador brand, and review of binding rules and procedures. Within this framework, the participatory process of reforming ministerial agreement 034, which conceptualizes bioendeavours, has begun and will conclude in the first quarter of year 2. This process is being conducted in coordination with other organizations (CODESPA, CEFOVE, Bioeconomy Fund) and strengthens the path to operationalize the development of Biotrade from the COA and RCOA. At the same time, the analysis of environmental and non-environmental legal gaps and loopholes in the development of bioendeavours has been launched with the incorporation of the legal advisor. The formulation of the conceptual and contextual gender framework has begun hiring of a specialized consultant. Progress has been made in training key Project stakeholders in gender approach. In this sense, members of the MAATE Working Group and the organizations of pilot interventions (COPROBICH, Ethniessense - COOPGRANACH and Wikiri) have participated in diagnostic and sensitization workshops. Interventions at the pilot demonstration supply chains has begun with a situational analysis of associative enterprises in a post-pandemic recovery scenario. The need to update the Project's baseline in relation to the area of land under sustainable management systems was identified. The update shows a lower number of hectares under certification of good agricultural or organic practices, which has been verified in the territory and has shown the need to create technical assistance plans from COPROBICH, Sumak Mikuy and Ethniessence. The latter has a validated plan. Priority was given to Project support to improve the management capacity of the associative businesses through the implementation of comprehensive strengthening plans that ensure not only the viability of the Project's investments but also the sustainability of the enterprises. On the other hand, in the private companies, initial investments have been deployed in accordance with the priorities of their organizations. With Wikiri, 75% progress has been made in expanding the production capacity of the Oophaga species at the La Florida farm through the construction of terrariums. Regarding Ethniessence support has been given to develop new products. |  |  |  |  |
| Planned contribution to strategic priorities/targets | The project aims to contribute to two strategic priorities; the first corresponds to core indicator 4: area of landscapes under improved practices (hectares excluding protected areas)" where the goal is to achieve 18,500 ha by 2026.The second priority responds to core indicator eleven. Number of direct beneficiaries disaggregated by gender as a co-benefit of the GEF investment", with a target of 19,000 people by the fourth year. |  |  |  |  |

- PROJECT OBJECTIVE

State the global environmental objective(s) of the project.

The project will contribute to establishing enabling conditions for the development of sustainable businesses based on native biodiversity. This will be done as a mechanism to expand the protection of native agrobiodiversity, fauna, and wild flora. The Project's actions will contribute to a larger area of the territory under a sustainable management model (good agricultural practices or organic production) as well as to the strengthening of two supply chains to contribute to its conservation: threatened Andean frogs and mortiño.

Please provide a narrative of progress made towards meeting the project objective(s). Describe any significant environmental or other changes (results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes (not more than three hundred words)

In the first year, progress has focused on strengthening MAATE's capacity to identify constraints and opportunities for improvement to regulate and develop bioendeavours. To this end, the Internal Working Group that has been formed in this Ministry integrates the areas with direct and indirect competence. With the participation of officials from these areas, the main lines of action have been prioritized. At the same time, a package of legal instruments that need to be reviewed by the Project's legal advisor has been defined. Also, through the updating of Ministerial Agreement 034, progress is being made in the operationalization of the COA and RCOA regarding Biotrade. Officials from Colombia and Peru are participating in this process to transfer their experiences and enrich the Ecuadorian process.

Regarding MAATE´s capacity building to regulate bioendeavours through the National Registry, an updated database has been generated containing approximately five hundred initiatives from the four regions of the country. This base constitutes an important progress because it constitutes a tool to size and characterize the productive system articulated to the objectives of the Project. In addition, it allows us to guide the activities of the Project in terms of communication strategies and design of incentives.

An important challenge has been the operationalization of the Interagency Working Group, which was delayed during the first year due to interministerial administrative dynamics and processes. This group has been created as a Bioeconomy Subcommittee and under this conceptual approach it will be a challenge to promote specific results at the bioendeavours level within the framework of a broader agenda.

Please provide a narrative of progress towards the stated GEF Strategic Priorities and Targets if identified in project document

The project reflects the overall result of its management regarding the area of landscapes under improved practices. In this regard, after the crisis caused by the Covid 19 pandemic, a national setback regarding farmers’ ability to comply with standards that allow them to certify their organic practices has been identified. In this regard, the figure reported by Agrocalidad as of March 2023 is 13,656.8 ha with organic certification compared to the 14.040,6 ha identified in the Project´s baseline with reference to the year 2017.

This setback is also evident at the pilot demonstration supply chains. One of the project's initial actions was to analyze the situation of the pilots and gather information to validate the initial situation. This allowed to identify that in COPROBICH out of the 906 hectares that were reported in the project baseline to have organic certification, there are only 235.06 hectares to date; likewise, for SUMAK MIKUY, there are no hectares with organic certification to date.

In addition, the Project has articulated a total of 580 direct beneficiaries (336 women, 244 men) who have participated in various training workshops on gender focus, spaces for discussion on regularization processes and incentives for bioendeavours and knowledge transfer experiences.

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the CAF Task Manager will make an overall assessment and provide ratings of:

(i)	Progress towards achieving the project objective(s)- see section 3.1

(ii)	Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The CAF Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - Progress towards achieving the project objective (s)

| Project objective and Outcomes | Description of indicator | Baseline level | Mid-term target | End-of- project target | Level on June 30, 2023, | Level on June 30, 2023 (%) | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Indicator 1 ML - 1 M&EP. Number of bioendeavours recorded into the national registry |  | 500 | 1.000 | 0 | 0% | S |
|  | Indicator 2 ML - 2 M&EP. Area of bioendeavours under sustainable management in Production systems (hectares). | 13.656,8 | 15.000 | 16.000 | 12.751,52 | 80% | S |
|  | Indicator 3 ML - 3 M&EP. Number of persons who get a loan from the project sponsored credit lines (Disaggregated by sex)- Men |  | 150 | 350 | 0 | 0% | S |
|  | Indicator 3 ML - 3 M&EP - GAPI 1. Number of persons who get a loan from the project sponsored credit lines (Disaggregated by sex)- Women |  | 150 | 350 | 0 | 0% | S |
|  | Indicator 4 ML. Area of landscapes under improved management to benefit biodiversity |  | 500 | 2.500 | 58,37 | 2% | S |
|  | Indicator 5 ML - 4 M&EP. Number of direct Beneficiaries disaggregated by gender |  | 1.000 | 19.000 | 580 | 3% | S |
|  | GAPI 2 GAP - GAPI.2 M&EP. Number of women-direct project beneficiaries. |  | 499 | 9.481 | 336 | 4% | S |
| Outcome 1: | Indicator 6 ML - 5 M&EP. Number of regulations to incentive bioendevours. | 1 | 2 | 3 | 1 | 33% | S |
|  | Indicator 7 ML - 6 M&EP. Level of MAATE bioendevours working group development and implementation. | 1 | 4 | 4 | 3 | 75% | HS |
|  | Indicator 8 ML - 7 M&EP. Level of interagency working group Development and implementation. | 1 | 3 | 4 | 1 | 25% | S |
|  | Indicator 9 ML - 8 M&EP - GAPI 3. GAP Level of integration of gender equality in the work of the MAATE bioendeavors working group and the interagency working group | 1 | 2 | 3 | 1 | 33% | S |
|  | GAPI 8 GAP - GAPI.8 M&EP. Number of trainings for gender equality - social inclusion -and bioendeavors in MAATE´s working group |  | 2 | 3 | 1 | 33% | S |
|  | GAPI 9 GAP - GAPI.9 M&EP. Number of Concept document and instrument to Operationalize gender equity in bioendeavours |  | 1 | 1 | 0 | 0% | S |
|  | GAPI 10 GAP - GAPI.10 M&EP. Number of trainings for gender equality - social inclusion -and bioendeavors in the interagency working group. |  | 2 | 3 | 0 | 0% | S |
|  | Indicator 10 ML - 9 M&EP -GAPI 4. Level of development of instruments to operationalize gender equality into bioendeavours. | 1 | 3 | 4 | 0 | 0% | S |
| Outcome 2: | Indicator 11 ML - 10 M&EP Level of development of the national registry of bioendeavours. | 1 | 4 | 4 | 1 | 25% | S |
|  | Indicator 12 ML - 11 M&EP Number of persons trained in bioendevour development (>50% women). |  | 1.000 | 9.000 | 0 | 0% | S |
|  | GAPI 5 GAP - GAPI.5 M&EP. Number of women trained in bioendeavors development (>50% women out of 10.500) |  | 50 | 5.250 | 0 | 0% | S |
|  | SAPI 2. Number of campaigns to explain bioendeavors to key audiences. |  | 2 | 3 | 0 | 0% | S |
|  | SAPI 3. Number of targeted guidelines to incentive bioendeavors using gender inclusiveness and intercultural aspects. |  | 1 | 1 | 0 | 0% | S |
|  | GAPI 11 GAP - GAPI.11 M&EP. Number of courses and trainings guidelines that integrates gender equality. |  | 1 | 1 | 0 | 0% | S |
|  | SAPI 4. Number of course-trainings curriculum & materials of selected institution that includes gender, intergenerational equality, and intercultural concepts. |  | 1 | 1 | 0 | 0% | S |
|  | GAPI 12 GAP - GAPI.12 M&EP. Number for grants given to women-led proposals |  |  | 8 | 0 | 0% | S |
| Outcome 3: | Indicator 13 ML - 12 M&EP. Amount of project sponsored credit lines issued in loans.USD |  | 4.000.000 | 11.000.000 | 0 | 0% | S |
|  | Indicator 14 ML. Number of persons from financial institutions trained. |  | 50 | 250 | 0 | 0% | S |
|  | GAPI 13 GAP - GAPI.13 M&EP. Number of course-trainings curriculum & materials of selected institution that includes gender, intergenerational equality, and intercultural concepts. . |  | 1 | 1 | 0 | 0% | S |
|  | GAPI 14 GAP - GAPI.14 M&EP. Number of meetings to learn from of project-related women savings groups. |  | 1 | 3 | 0 | 0% | S |
|  | GAPI 15 GAP - GAPI.15 M&EP. Number of documents of lessons learned regarding women-saving groups |  | 1 | 1 | 0 | 0% | S |
|  | SAPI 5. Number of document systematizing lessons from experiences from saving groups for production purposes. |  | 1 | 1 | 0 | 0% | S |
|  | SAPI 6. Number of workshops to promote exchange of experiences from saving groups for production purposes. |  | 2 | 4 | 0 | 0% | S |
|  | SAPI 7. Guidance on the use of saving groups on bioendeavors. |  | 1 | 1 | 0 | 0% | S |
|  | SAPI 8. Number of communications documents of guidance of use of saving groups to be distributed. |  | 1 | 2 | 0 | 0% | S |
| Outcome 4: | Indicator 15 ML - 13 M&EP. Level of development of mortiño harvesting plans for the Cotacachi – Cayapas and Cayambe – Coca National Parks | 1 | 4 | 5 | 1 | 20% | S |
|  | Indicator 15 ML - 13 M&EP. Level of development of mortiño harvesting plans for the Cotacachi – Cayapas and Cayambe – Coca National Parks. | 1 | 4 | 5 | 1 | 20% | S |
|  | Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha).: Sumak Mikuy | 14 | 18 | 21 | 0 | 0% | S |
|  | Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha): COPROBICH | 906 | 906 | 907 | 235,06 | 26% | S |
|  | Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha).: Ethnisnack COOPGRANACH - ha in transition to organic |  | 1 | 7 | 0 | 0% | S |
|  | Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha).: Ethnisnack COOPGRANACH – certified. |  | 3 | 10 | 0 | 0% | S |
|  | Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha).: Other producers. | 15,65 | 16 | 20 | 23,93 | 120% | HS |
|  | Indicator 17 ML - 15 M&EP. Areas of agriculture plots with “Good Agricultural Practices” certification. Sumak Mikuy |  | 18 | 21 | 0 | 0% | S |
|  | Indicator 17 ML - 15 M&EP. Areas of agriculture plots with “Good Agricultural Practices” certification: COPROBICH |  | 500 | 945 | 0 | 0% | S |
|  | Indicator 17 ML - 15 M&EP. Areas of agriculture plots with “Good Agricultural Practices” certification: Ethnisnack COOPGRANACH |  | 85 | 85 | 0 | 0% | S |
|  | Indicator 17 ML - 15 M&EP. Areas of agriculture plots with “Good Agricultural Practices” certification: Other producers. |  | 8 | 20 | 0 | 0% | S |
|  | Indicator 18 ML - 16 M&EP. Number of Oophaga frogs produced per year by Wikiri. | 385 | 577 | 770 | 491 | 64% | HS |
|  | Indicator 19 ML - 17 M&EP. Number of visitors per year to Wikiri Sapoparque. |  | 1.200 | 3.600 | 8.398 | 233% | HS |
|  | Indicator 20 ML - 18 M&EP. Percentage of Jambatu´s fixed costs covered by Wikiri. (%) | 6 | 8 | 10 | 9,19 | 92% | HS |
|  | Indicator 21 ML - 19 M&EP. Number of people who have participated in events for dissemination of project lessons. |  | 500 | 1.000 | 0 | 0% | S |
|  | Indicator 22 ML - 20 M&EP. Number of visitors per month (annual average) recorded in the network of electronic platforms used to disseminate project´s information and lessons. – Visits |  | 2.000 | 4.000 | 0 | 0% | S |
|  | Indicator 22 ML - 20 M&EP. Number of visitors per month (annual average) recorded in the network of electronic platforms used to disseminate project´s information and lessons. – Unique visits |  | 1.500 | 3.000 | 0 | 0% | S |
|  | GAPI 6 GAP - GAPI.6 M&EP. Number of women who have participated in events for dissemination of project lessons. |  | 200 | 400 | 0 | 0% | S |
|  | GAPI 16 GAP. Number of cuy production packages given to COPROBICH women members |  | 310 | 310 | 0 | 0% | S |
|  | GAPI 17 GAP - GAPI.16 M&EP. Number of documents assessing women economic contribution to selected production chains. |  | 1 | 3 | 0 | 0% | S |
|  | GAPI 18 GAP - GAPI.17 M&EP. Number of documents distributed regarding project learnings about women participation. |  |  | 1 | 0 | 0% | S |
|  | SAPI 9. Number of exchange visits among members of participating production chains. |  | 4 | 4 | 1 | 25% | S |
| Outcome 5: | Indicator 23 ML. Frequency of workplan adjustments based on Monitoring results. |  | 2 | 4 | 1 | 25% | S |
|  | Indicator 24 ML. Frequency of events to reflect, gather lessons and identify impacts. |  | 2 | 3 | 0 | 0% | S |
| PS1. Formal designation of members of the project board | SAPI 10. Number of representants of private sector in the decision-making body of the project. |  | 4 | 4 | 1 | 25% | S |
| PS2. Formal designation of members of the technical committee | GAPI 19 GAP - GAPI.18 M&EP. Number of institutions representing gender equality advocacy in the three technical working groups |  | 3 | 3 | 0 | 0% | S |
|  | GAPI 20 GAP - GAPI.19 M&EP. Number beneficiaries from women-led groups participating in technical groups in the three technical working groups: a) on use of native biodiversity. b) on use of business financing; and iii. on use of business Development |  | 3 | 3 | 0 | 0% | S |
| PS4. Sign agreement with project executing entity | GAPI 21 GAP - GAPI.20 M&EP. One gender and participation specialist as part of the project unit. |  | 1 | 1 | 1 | 100% | HS |
|  | GAPI 22 GAP - GAPI.21 M&EP. Percentage of women in the project unit. |  | 40 | 40 | 60 | 150% | HS |
|  | SAPI 11. One gender and participation specialist are part of the project unit |  | 1 | 1 | 1 | 100% | HS |
| PS6. Prepare project´s communication strategy and multi-year action plan. | GAPI 7 GAP - GAPI.7 M&EP. Number of projects’ communication strategy that integrates gender equality (inclusive language and concepts). |  | 1 | 1 | 1 | 100% | HS |
|  | SAPI 1. Number of communication strategies including diverse key audiences. |  | 1 | 1 | 1 | 100% | HS |
| GEF Core | Core Indicator 4. Area of landscapes under improved practices (hectares excluding protected areas) | 14.040,56 | 15.500 | 18.500 | 12.809,89 | 69% | HS |
|  | Indicator 4.1. Area of landscapes under improved management to benefit biodiversity |  | 500 | 2.500 | 58,37 | 2% | S |
|  | Indicator 4.3. Area of landscapes under sustainable land management in production systems. | 14.040,56 | 15.000 | 16.000 | 12.751,52 | 80% | HS |
|  | Core Indicator 11. Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  | 1.000 | 19.000 | 567 | 3% | S |

Overall rating of project progress towards meeting project objective(s) (To be provided by CAF-GEF Task Manager. Please add columns to reflect all prior year ratings)

| FY2022 rating | FY2023 rating | Comments/narrative justifying the current FY rating and explaining reasons for change (positive or negative) since previous reporting periods |
| --- | --- | --- |
| N/A | S |  |

Action plan to address MS, MU, U and HU rating (To be completed by CAF GEF Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |

This section should be completed if project progress towards meeting objectives was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |

  - (a) Project implementation progress

| Outputs | Expected completion date | Implementation status at the end of the reporting period (%) | Implementation status as of June 30, 2023 (%) | Comments if variance. Describe any problems in delivering outputs | Progress rating |
| --- | --- | --- | --- | --- | --- |
| PS1. Formal designation of members of the project board | sep-22 | 100 | 100 |  | S |
| PS2. Formal designation of members of the technical committee | sep-22 | 100 | 100 |  | S |
| PS3. Sign agreement with project executing entity | jul-22 | 100 | 100 |  | S |
| PS4. Contract project team | oct-22 | 100 | 100 |  | S |
| PS4.1. Purchase of personal property, computers (Fixed Assets) | dic-22 | 100 | 100 |  | S |
| PS4.2. Minor equipment purchases | dic-22 | 100 | 100 |  | S |
| PS4.3. Arrangement offices facilities | mar-23 | N/A | N/A | This activity was not done because there has not been a need to fix the working space. | S |
| PS4.4. Compra de moto | mar-23 | N/A | N/A | The pilot did not accept this activity. | S |
| PS5. Form communications working group with partners´ communication officers | nov-22 | 100 | 50 | The creation of a communication group was agreed among the following institutions MAATE, REDD, GIZ (BioValor), FIAS- AFD, CI, PSD2, FLACSO and Heifer – Ecuador. | S |
| PS6. Prepare project´s communication strategy and multi-year action plan. | feb-23 | 100 | 100 |  | S |
| PS7. Implement project´s communication strategy | dic-25 | 100 | 100 |  | S |
| Output 1.1: Environmental regulations that facilitate the sustainable use of native biodiversity. |  |  |  |  |  |
| Activity 1.1.1.: Contract legal advisor | jun-23 | 100 | 100 |  | S |
| Activity 1.1.2.: Form MAATE´s bioendevours working group | nov-22 | 100 | 100 |  | S |
| Activity 1.1.3. Prepare working group multiyear workplan | nov-22 | 100 | 100 |  | S |
| Activity 1.1.4.: Training of working group members on gender equality and social inclusion. | mar-23 | 100 | 100 |  | S |
| Activity 1.1.5.: Implement multiyear workplan | mar-26 | 10 | 100 |  | S |
| Activity 1.1.6.: Assess and update multiyear workplan | sep-25 | N/A | N/A |  | N/A |
| Activity 1.1.7.: Draft conceptual framework for bioendeavours to be analyzed in the interagency bioendevours working group. | mar-23 | 100 | 50 | The participatory update of AM 034 is underway. This process will have four rounds of workshops and the creation of a group of advisor experts. This process is being carried out by MAATE, CODESPA, CEFOVE and the Bioeconomy fund. This first workshop was already held, and the group of experts has been formed. | S |
| Activity 1.1.8: Diagnose status of regulation gaps | abr-23 | 100 | 40 | Some gaps have been identified based on interviews held with MAATE stakeholders. The legal advisor hired by the Project is developing this analysis in coordination with the MAATE Working Group created by the Project. | S |
| Activity 1.1.9: Prepare updated permit process to access wildlife for commercial use | sep-23 | N/A | N/A |  | N/A |
| Activity 1.1.10: Prepare instruments to clarify EIA and licensing process of bioendevours | sep-23 | N/A | N/A |  | N/A |
| Activity 1.1.11: Test new instruments and procedures. Process wildlife harvesting permits for mortiño and frogs. | dic-23 | N/A | N/A |  | N/A |
| Activity 1.1.12: Assess implementation of improved regulations and introduce adjustments as necessary | dic-24 | N/A | N/A |  | N/A |
| Activity 1.1.13: Prepare conceptual framework for gender equality in bioendeavours | jun-23 | 100 | 20 | The consultant has been hired to carry out this activity. Currently, the first product is being developed, which includes the analysis of existing legal instruments. | S |
| Activity 1.1.14.: Develop instruments to operationalise gender equality into bioendeavours. | jun-23 | 100 | 20 |  | S |
| Activity 1.1.15.: Integrate gender equality into regulations. | dic-24 | N/A | N/A |  | N/A |
| Activity 1.1.16.: Based on project lessons update regulations to incentive bioendevours | dic-25 | N/A | N/A |  | N/A |
| Output 1.2.: Relevant norms and regulations that support the development of businesses based on the sustainable use of native biodiversity. |  |  |  |  |  |
| Activity 1.2.1: Diagnose non-environmental regulation gaps | may-23 | 100 | 20 | The legal advisor hired by the Project is developing this analysis in coordination with the MAATE Internal Working Group. | S |
| Activity 1.2.2.: Develop instruments with interagency working group | jun-23 | 100 | 20 | The inter-agency working group has been created informally. It is expected to be activated through a formal invitation in the first quarter of the second year. | S |
| Activity 1.2.3.: Assess implementation of improved regulations and introduce adjustments, as necessary. | mar-25 | N/A | N/A |  | N/A |
| Output 1.3.: Interagency coordination mechanism for the promotion of businesses based on the sustainable use of native biodiversity. |  |  |  |  |  |
| Activity 1.3.1.: Form interagency bioendevours working group | jun-23 | 100 | 20 | The inter-agency working group has been created informally. It is expected to be activated through a formal invitation in the first quarter of the second year. | S |
| Activity 1.3.2.: Training of working group members on gender equality and social inclusion | jun-23 | 100 | 20 | The inter-agency working group has been created informally. It is expected to be activated through a formal invitation in the first quarter of the second year. | S |
| Activity 1.3.3.: Prepare working group multiyear workplan | mar-23 | 100 | 20 | The inter-agency working group has been created informally. It is expected to be activated through a formal invitation in the first quarter of the second year. | S |
| Activity 1.3.4.: Implement multiyear workplan | mar-26 | N/A | N/A |  | N/A |
| Activity 1.3.5.: Analise and agree bioendeavours conceptual framework | jun-23 | 100 | 50 | Currently, the MAATE Internal Working Group is not developing the conceptual framework. Once authorities decide to call the interagency group to meetings this activity Will be undertaken. | S |
| Activity 1.3.6.: Agree on a basic incentive package for bioendeavours | jun-23 | 100 | 0 | An agreement has been reached with the Ministry of the Environment on the development of the BioEcuador Brand application mechanism. We have supported the launching of AM 113, which establishes the regulations for the qualification of programs, funds and/or projects for prevention, protection, conservation, bio-enterprises, environmental restoration, and repair and for the certification of the beneficiaries of the additional 100% deduction for the calculation of the taxable income tax base. | S |
| Activity 1.3.7: Assess and update multiyear workplan | mar-26 | N/A | N/A |  | N/A |
| Output 2.1: Baseline and information integration of business initiatives based on the sustainable use of native biodiversity. |  |  |  |  |  |
| Activity 2.1.1.: Interagency working group conceptualize national registry of bioendevours | jun-23 | 100 | 10% | Although the ministerial authorities have not called for the creation of this group, a meeting was held to analyze and exchange experiences with the Colombian Green Business Office and PromPerú. Officials from MAATE, MPCEIP, MAG, the Ministry of Labor, and representatives of bio-businesses from various parts of the country participated in these meetings. | S |
| Activity 2.1.2: Contract development of web-based data collection and management linked to SUIA | jun-23 | 100 | 0 | MAATE is coordinating actions with GIZ. This institution is currently developing a registry to avoid the duplication of actions. GIZ is planning to finish the registry by December 2023.After this, the work will be handed over to this project to continue with its improvement. In parallel, progress has been made identifying current bioendeavours through the development of a database. | S |
| Activity 2.1.3.: Develop national registry of bioendevours | sep-23 | 80 | 10 |  | S |
| Activity 2.1.4.: Test trial of national registry of bioendevours | dic-24 | N/A | N/A |  | N/A |
| Activity 2.1.5.: Full operation of national registry of bioendevours | jun-26 | N/A | N/A |  | N/A |
| Activity 2.1.6.: Interagency working group assess performance and adjust. | sep-25 | N/A | N/A |  | N/A |
| Activity 2.1.7.: Communication campaign to motivate registration. | sep-24 | N/A | N/A |  | N/A |
| Output 2.2: Guidelines to promote businesses based on native biodiversity. |  |  |  |  |  |
| Activity 2.2.1.: Communication campaign to explain bioendevours to key audiences | jun-25 | N/A | N/A |  | N/A |
| Activity 2.2.2.: Prepare targeted guidelines to incentive bioendevours | sep-23 | N/A | N/A |  | N/A |
| Activity 2.2.3.: Present guidelines to specific audiences | dic-24 | N/A | N/A |  | N/A |
| Activity 2.2.4.: Assess assimilation of guidelines and adjust them. | jun-24 | N/A | N/A |  | N/A |
| Output 2.3.: Mechanism for capacity building and business support based on (i) self-directed online courses and (ii) technical assistance and mentoring to harness business development. |  |  |  |  |  |
| Activity 2.3.1.: Select partner(s) for capacity building work. | abr-23 | 100 | 0 | Process of contract is undergoing. | S |
| Activity 2.3.2.: Develop business support services to be provided. | sep-23 | N/A | N/A |  | N/A |
| Activity 2.3.3.: Ensure mainstreaming of key bioendevour concepts and language into services to be provided. | sep-23 | N/A | N/A |  | N/A |
| Activity 2.3.4.: Prepare strategy for long-term funding of training services | sep-23 | N/A | N/A |  | N/A |
| Activity 2.3.5.: Provide business support services linked to enrolment into national registry. | jun-26 | 2 | 100 | This item has been used to hire a full-time specialist in bio-business: the person hired has joined the team of the Project coordination unit. | S |
| Activity 2.3.6.: Assess utility of business support services and adjust them. | dic-25 | N/A | N/A |  | N/A |
| Output 2.4: Applied research in support of promissory business initiatives based on the sustainable use of native biodiversity. |  |  |  |  |  |
| Activity 2.4.1.: Prepare instruments for competitive fund for businesses (small grants), including affirmative action for women-led proposals. | dic-23 | N/A | N/A |  | N/A |
| Activity 2.4.2.: Call for proposals to competitive fund for businesses (linked to enrolment into national registry). | mar-24 | N/A | N/A |  | N/A |
| Activity 2.4.3.: Assign applied research small grants to businesses. | mar-24 | N/A | N/A |  | N/A |
| Activity 2.4.4: Monitor execution of applied research grants to businesses. | mar-25 | N/A | N/A |  | N/A |
| Activity 2.4.5.: Assess performance of competitive fund for businesses. | jun-25 | N/A | N/A |  | N/A |
| Activity 2.4.6.: Communication campaign to disseminate progress and results. | jun-25 | N/A | N/A |  | N/A |
| Activity 2.4.7.: Explore long-term mechanism to support research and development of bioendeavours | jun-25 | N/A | N/A |  | N/A |
| Output 3.1: Analysis of market-demand for sustainable products from native biodiversity. |  |  |  |  |  |
| Activity 3.1.1.: Analysis of market-demand in European countries | jun-23 | 100 | 0 | Contract process is undergoing. | S |
| Activity 3.1.2: Disseminate results to key audiences | dic-23 | N/A | N/A |  | N/A |
| Output 3.2.: Green financing lines for businesses based on native biodiversity. |  |  |  |  |  |
| Activity 3.2.1.: Contract Financial specialist. | feb-23 | 100 | 100 |  | HS |
| Activity 3.2.2.: Establish collaborative arrangements with partner financial institutions. | feb-23 | 100 | 20 |  | S |
| Activity 3.2.3.: Seek collaboration and synergy with other financial institutions | mar-23 | 100 | 20 |  | S |
| Activity 3.2.4.: Design project sponsored credit lines with affirmative actions for women-led businesses | jun-23 | 100 | 20 |  | S |
| Activity 3.2.5.: Develop tools for implementation of project sponsored credit lines | sep-23 | N/A | N/A |  | N/A |
| Activity 3.2.6.: Train personnel of partner financial institutions | sep-23 | N/A | N/A |  | N/A |
| Activity 3.2.7.: Technical support to partner financial institutions | sep-24 | N/A | N/A |  | N/A |
| Activity 3.2.8.: Launch project-sponsored credit lines (linked to enrolment into national registry) | dic-23 | N/A | N/A |  | N/A |
| Activity 3.2.9.: Implementation of project-sponsored credit lines (linked to enrolment into national registry) | jun-26 | N/A | N/A |  | N/A |
| Activity 3.2.10.: Meetings to assess performance of project-sponsored credit lines | jun-26 | N/A | N/A |  | N/A |
| Activity 3.2.11.: Document lessons from the implementation of project-sponsored credit lines. | dic-25 | N/A | N/A |  | N/A |
| Activity 3.2.12.: Workshops and training sessions to motivate financial institutions to engage into financing bioendevours. | sep-25 | N/A | N/A |  | N/A |
| Activity 3.2.13.: Prepare funding strategy and initial proposals to mobilize funding for the credit lines | sep-24 | N/A | N/A |  | N/A |
| Activity 3.2.14.: Seek investors to fun the credit lines | jun-26 | N/A | N/A |  | N/A |
| Activity 3.2.15.: Document lessons and best practice from savings groups for production purposes s | sep-23 | N/A | N/A |  | N/A |
| Activity 3.2.16.: Workshops to exchange experience from savings groups for production purposes. | mar-24 | N/A | N/A |  | N/A |
| Activity 3.2.17.: Prepare guidance on the use of savings groups on bioendevours | jun-24 | N/A | N/A |  | N/A |
| Activity 3.2.18.: Disseminate guidance on the use of savings groups on bioendevours | jun-26 | N/A | N/A |  | N/A |
| Activity 3.2.19.: Meetings of project-related women savings groups | dic-25 | N/A | N/A |  | N/A |
| Activity 3.2.20.: Document lessons from project-related women savings groups. | mar-26 | N/A | N/A |  | N/A |
| Activity 3.2.98. Financial specialist to provide technical assistance and on-the-job training to MAATE staff to operationalize biodiversity conservation budget tagging.[...] | sep-24 | N/A | N/A |  | N/A |
| Output 4.1.: Four optimized demonstration supply chains (community and private models). |  |  |  |  |  |
| Activity 4.1.1 Sign agreements with participating businesses | feb-23 | 100 | 75 | Signed agreements with WIKIRI, ETHNIESSENCE and COPROBICH. Agreement with UNORCAC - Sumak Mikuy is in progress. | HS |
| Activity 4.1.2.: Quarterly meetings for follow up | dic-25 | 30 | 100 | Follow-up meetings have been held more frequently than planned. | HS |
| WIKIRI |  |  |  |  |  |
| Activity 4.1.3.: Purchase materials for quadrants | may-23 | 100 | 100 |  | HS |
| Activity 4.1.4.: Build quadrants (five) in La Florida | abr-23 | 100 | 100 |  | HS |
| Activity 4.1.5.: Habitat enrichment in quadrants | jun-23 | 100 | 50% | The activity is ongoing due to a technical modification in the design of the quadrants which means more time for construction. | HS |
| Activity 4.1.6.: Increase capacity for cricket production to feed frogs | jun-23 | 100 | 50% | The company has been provided with all the equipment requested so far for the grill house. The Project has requested the detail of the remaining requirement. | HS |
| Activity 4.1.7.: Increase capacity of vivarium to house frog juveniles | jun-23 | 100 | 0 | This activity requires that the previous process in quadrants be carried out. | S |
| Activity 4.1.8.: Field work to collect broodstock | jun-23 | 100 | 0 | This activity requires that the previous process in quadrants be carried out. | S |
| Activity 4.1.9.: Training of personnel responsible for frog raising | jun-24 | N/A | N/A |  | S |
| Activity 4.1.10.: Install interactive module in Wikiri Sapoparque | jun-23 | 100 | 0 | This module was already implemented by Wikiri with its own resources before the Project started. In addition, support has been provided to improve signage in the Sapoparque. | S |
| Activity 4.1.11.: Develop Wikiri Sapoparque web page | abr-23 | 100 | 0 | Wikiri has developed its website in anticipation of the start-up of the Project and the process is underway. In addition, the Project is agreeing with Wikiri on the improvements that are relevant to this process. | S |
| COPROBICH |  |  |  |  |  |
| Activity 4.1.12.: Prepare biofactory business plan | dic-22 | 100 | 5 | Based on an evaluation of the company's situation, we have considered extending the scope of this plan to the entire management of the corporation. The terms of this consultancy have been approved by CAF and the selection process has been launched. | S |
| Activity 4.1.13.: Present biofactory business plan to “cabecillas” | dic-22 | 100 | 0 | The activity is consistent with the previous one and will be carried out in the second year. | S |
| Activity 4.1.14.: Exchange visit to an established biofactory | mar-23 | 100 | 0 | The biofactories identified by the Project to carry out the exchange had difficulties of availability to receive the members of the pilots on the agreed dates. The exchange is planned to be carried out December 2023 the latest. | S |
| Activity 4.1.15.: Purchase of land lot to install the biofactory | jun-23 | 100 | 100 | COPROBICH has proposed to carry out the construction on the premises of the plant it owns. | HS |
| Activity 4.1.16.: Prepare land lot for construction work | sep-23 | 100 | 0 |  | S |
| Activity 4.1.17.: Prepare engineering plans and structural calculations for the biofactory | dic-23 | 100 | 0 |  | S |
| Activity 4.1.18.: Construction of industrial shed for bokashi production | mar-25 | N/A | N/A |  | N/A |
| Activity 4.1.19.: Construction of industrial shed for production of liquid bio-fertilizers and natural pesticides | dic-23 | N/A | N/A |  | N/A |
| Activity 4.1.20.: Construction of warehouse | dic-23 | N/A | N/A |  | N/A |
| Activity 4.1.21.: Purchase of raw materials, supplies and materials for production of bokashi, bio-fertilizers and natural pesticides | mar-25 | N/A | N/A |  | N/A |
| Activity 4.1.22.: Prepare quality analyses and obtain permits for biofactory products | jun-24 | N/A | N/A |  | N/A |
| Activity 4.1.23.: Packaging design for products and sales promotion | jun-25 | N/A | N/A |  | N/A |
| Activity 4.1.24.: Annual training of “cabecillas” on use of organic fertilizers and natural pesticides and good agricultural practices | dic-25 | N/A | N/A |  | N/A |
| Activity 4.1.25.: Technical assistance to producers | jun-26 | N/A | N/A |  | N/A |
| Activity 4.1.26.: Provide cuy production packages to COPROBICH women members | oct-22 | 100 | 30 | Initially, COPROBICH presented a change in the production package that was contrary to the Project's approach. We worked with the organization's grassroots to socialize the Project's approach and to learn more about the needs of the beneficiaries. As a result, the delivery of the production package consisting of cuy has been validated with the group of women and community leaders. The technical specifications of the package have been defined and COPROBICH has made progress in cuy production training. The need to hire a business plan to support the commercial management of the initiative has been identified. The terms of reference have been submitted to CAF for consideration. | S |
| Activity 4.1.27.: Technical assistance and follow up of cuy production | dic-24 | N/A | N/A | COPROBICH has worked with MAG to train producers in cuy breeding. To date, 151 people have been trained. | N/A |
| Activity 4.1.28.: Final adjustment of mobile application to keep record of individual plots | dic-22 | 100 | 10 | This activity has been managed by COPROBICH with GIZ prior to the start of the Project. The relevance of supporting the continued use of the application in FY 24 has been identified, as well as the replication in other pilots. | S |
| Activity 4.1.29.: Test the mobile application with producers from Ethnisnack and Sumak Mikuy | abr-23 | 100 | 0 | These activities will be carried out after the previous activity. | S |
| Activity 4.1.30.: Implement the application with all organic producers of COPROBICH, Ethnisnack and Sumak Mikuy | jun-23 | 100 | 0 |  | S |
| Activity 4.1.31.: Identify and document lessons about the use of the application. | mar-23 | 100 | 0 |  | S |
| ETHNISNACK |  |  |  |  |  |
| Activity 4.1.32.: Install chocho dehulling process line in COOPGRANACH | jun-24 | N/A | N/A |  | N/A |
| Activity 4.1.33.: Install chocho flour process line in COOPGRANACH | jun-24 | N/A | N/A |  | N/A |
| Activity 4.1.34.: Organic certification of COOPGRANACH processing plant | sep-24 | N/A | N/A |  | N/A |
| Activity 4.1.35.: HACCP certification of Ethniessence processing plant | dic-23 | N/A | N/A |  | N/A |
| Activity 4.1.36.: BPA certification of all COOPGRANACH chocho producers (85 ha) | abr-24 | N/A | N/A |  | N/A |
| Activity 4.1.37.: BPA certification of current producers of camote, zanahoria blanca, papa and chocho39 (20 ha) | jun-23 | 100 | 0 | The start-up situation of the indicator was uncertain at the beginning of the Project and to solve this deficiency, ETHNIESSENCE has carried out a diagnosis to know the current situation of the producers. | S |
| Activity 4.1.38.: Undertake transition to organic chocho production with COOPGRANACH producers (17 ha) | sep-25 | N/A | N/A |  | N/A |
| Activity 4.1.39.: Organic certification of COOPGRANACH chocho producers (10 ha) | mar-24 | N/A | N/A |  | N/A |
| Activity 4.1.40.: Develop and launch a new chocho product | mar-23 | 100 | 80 | The company has developed new products. The project has provided the sachet machine and it is about to receive the necessary packaging for the launching. | HS |
| Activity 4.1.41.: Develop and launch a new product with camote and zanahoria blanca | dic-23 | 80 | 80 |  | HS |
| Activity 4.1.42.: Develop a new product format for “chochines” (fried chochos) | jun-23 | 100 | 80 |  | HS |
| Activity 4.1.43.: Develop a new product format for “julyz” (fried vegetable mix)) | jun-23 | 100 | 100 |  | HS |
| Activity 4.1.44.: Develop three new products using organic native vegetables | dic-23 | N/A | N/A |  | N/A |
| Activity 4.1.45.: Technical assistance to producers | jun-26 | 30 | 30 | The company has prepared a technical assistance plan with its producers based on the updated diagnosis of the situation of the plots. | S |
| Activity 4.1.46.: Develop and implement marketing and communication plan to increase sales in national and international markets | dic-25 | 30 |  | This year the company made progress in product development. In the following months, it will promote marketing and communication actions. | S |
| Activity 4.1.97. Ethnisnack. Annual training of producers on organic production and good agricultural practices. Includes training materials, travel, and refreshments. Two sessions per year. (Activity with Coprobich 4.1.24) | mar-26 | N/A | N/A | The need for a diagnosis of the technical assistance needs of Coprobich's producers has been identified, based on the issues identified by the Certifier. | S |
| Activity 4.1.99. Etnisnack. Vacuum fryer for the development of new products. | dic-23 | N/A | N/A | This activity is included in the budget but not in the programming. For this reason, it has been included in this report. | S |
| SUMAK MIKUY |  |  |  |  |  |
| Activity 4.1.47.: Technical assistance and support to chackra producers to obtain organic and BPA certifications. | jun-26 | N/A | N/A | Actions with this pilot were not carried out in the first year because it was necessary to wait for the results of the financial and legal audit reports contracted by UNORCAC. It was also necessary to know UNORCAC's decision regarding the need to repower the company. Once UNORCAR makes the decision to repower the company and given that they have requested the project support, a collaboration agreement must be signed. | S |
| Activity 4.1.48.: Expand plant nursery (two hundred m2) | dic-22 | N/A | N/A |  | S |
| Activity 4.1.49.: Produce and supply nursery plants for farmers (uvilla, aji, medicinal plants) | jun-26 | N/A | N/A |  | S |
| Activity 4.1.50.: Expand base stock of organic supplies in farm store | sep-23 | N/A | N/A |  | S |
| Activity 4.1.51.: Strengthen associative groups of mortiño collectors. | dic-25 | N/A | N/A |  | S |
| Activity 4.1.52.: Technical assistance and training of mortiño collectors. | dic-25 | N/A | N/A |  | S |
| Activity 4.1.53.: Provide personal protective clothing and field equipment to mortiño collectors | sep-23 | N/A | N/A |  | S |
| Activity 4.1.54.: Prepare and implement paramo conservation awareness strategy for children | dic-25 | N/A | N/A |  | S |
| Activity 4.1.55.: Develop: (i) corporate governance strategy, (ii) strategic business plan, (iii) updated bylaws and (iv) business regulations. | dic-23 | N/A | N/A |  | S |
| Activity 4.1.56.: Implement improved corporate management arrangements | jun-26 | N/A | N/A |  | S |
| Activity 4.1.57.: HACCP certification of processing plant | mar-24 | N/A | N/A |  | S |
| Activity 4.1.58.: Install dry fruit cleaning machine to remove mortiño peduncle | mar-24 | N/A | N/A |  | S |
| Activity 4.1.96. Conditioning and repair cold room to maintain the raw material in good condition. | jun-23 | N/A | N/A |  | S |
| Activity 4.1.95. Acquisition of seed crusher and other species. | sep-23 | N/A | N/A |  | S |
| Output 4.2. Learning and good practice from the project documented and disseminated |  |  |  |  |  |
| Activity 4.2.1.: Development of project website. | feb-23 | 100 | 80 | The development is in progress. It is expected to have the site functioning by July 2023. | S |
| Activity 4.2.2.: Maintenance and operation of project website. | jun-26 | N/A | N/A |  | S |
| Activity 4.2.3.: Exchange visits among members of participating production chains. | dic-25 | 30 | 30 | The first Exchange visit between COPROBICH and ETHNIESSECE (COOPGRANACH) was carried out. | S |
| Activity 4.2.4.: Assess women economic contributions to selected production chains (mortiño, quinua, chocho). | sep-23 | N/A | N/A |  | S |
| Activity 4.2.5.: Focus groups to identify challenges and learning | sep-25 | N/A | N/A |  | S |
| Activity 4.2.6.: Prepare and distribute project´s learning documents (three) | dic-25 | N/A | N/A |  | S |
| Activity 4.2.7.: Prepare and distribute project memoirs | dic-25 | N/A | N/A |  | S |
| Monitoring and evaluation |  |  |  |  |  |
| Activity M&E1.: Inception workshop | sep-22 | 100 | 100 |  | S |
| Activity M&E2.: Project board meetings | jun-26 | 25 | 25 | The planned meetings have been carried out. | S |
| Activity M&E3.: Annual measurement of project indicators | dic-25 | 30 | 30 |  | S |
| Activity M&E4.: Compile and analyze project indicators before MTR and TE | dic-25 | N/A | N/A |  | S |
| Activity M&E5.: Independent mid-term review | jun-24 | N/A | N/A |  | S |
| Activity M&E6.: Independent final assessment | mar-26 | N/A | N/A |  | S |
| GAP. Gender action plan |  |  |  |  |  |
| GAP1. A communication strategy that includes gender equality in project communications. | feb-23 | 100 | 100 |  | HS |
| GAP2. Ensure mainstreaming gender and social inclusiveness reflections in MAAE working group using available materials and methodologies. | mar-23 | 100 | 20 | The consultant has been contracted to carry out this activity, with a term of 3 months to complete. | S |
| GAP3. Ensure the existence of a conceptual framework for gender equality integration in bioendeavors and develop in a participatory manner, with the working group, the instrument to operationalize gender equality into bioendeavors to be adopted by MAAE | jun-23 | 100 | 20 |  | S |
| GAP4. Ensure mainstreaming gender and social inclusiveness reflections in the interagency working group using available materials and methodologies. | jun-23 | 100 | 20 | The Project is waiting for MAATE´s notification to continue. | S |
| GAP5. Ensure mainstreaming gender inclusiveness and intercultural appropriate concepts to the contents of the courses. | sep-23 | N/A | N/A |  | S |
| GAP6. Ensure mainstreaming gender equality in the process to support research initiatives of bioentrepreneurs. | mar-24 | N/A | N/A |  | S |
| GAP7. Ensure mainstreaming gender and intergenerational inclusiveness and intercultural appropriate concepts to the contents of the courses. It will include adequate language into services to be provided as well as pictures, case studies, examples. | sep-23 | N/A | N/A |  | S |
| GAP8. Ensure the learnings of inclusion of elements of gender equality. | mar-26 | N/A | N/A |  | S |
| GAP9. Ensure support given to vulnerable communities. Actions given to women as a measure to post pandemic recovery (COPROBICH women members) | jun-23 | 100 | 50 | The delivery of the production package consisting of cuy has been validated with the women's group and community leaders. It was pertinent to discuss the content of the productive package with the organization's bases, since there was a counterproposal that was not related to the project. | S |
| GAP10. Understanding women position and economic contributions in the production chains of native biodiversity. | dic-25 | N/A | N/A |  | S |
| GAP11. Learnings from the project implementation - and good practice regarding women participation. | sep-25 | N/A | N/A |  | S |
| GAP12. Adequate representation of institutions representing gender equality advocacy in technical groups of the project. | sep-22 | 100 | 10 | The need to include stakeholders in the technical groups has been discussed with the technical advisory committee. Work has been done on the formation of the technical design groups. | S |
| GAP13. Participation of women-led groups of beneficiaries in technical groups of the project to support empowerment and experience sharing to their bases ". | sep-22 | 100 | 10 |  | S |
| GAP14. Integration of appropriate and technical advice for the implementation of the project through a person specialized in gender and participation of diverse public, especially with intercultural participants. | dic-22 | 100 | 100 |  | S |
| GAP15. Establishment of quotas to ensure the participation of women in the project unit. | dic-22 | 100 | 150 |  | S |
| SAP. Stakeholders Action Plan |  |  |  |  |  |
| SAP1. A communication strategy that includes diverse key actors with inclusive and culturally appropriate approach that will give special attention to rural and urban, gender, intergenerational and intercultural aspects. | feb-23 | 100 | 100 |  | S |
| SAP2. Ensure adequate messages given to diverse key audiences with inclusive and culturally appropriate approach to explain bioendeavours. | jun-25 | N/A | N/A |  | S |
| SAP3. Ensure adequate messages given to diverse key audiences with gender inclusiveness and intercultural appropriate approach to explain bioendeavours. | sep-23 | N/A | N/A |  | S |
| SAP4. Ensure mainstreaming gender and intergenerational inclusiveness and intercultural appropriate concepts to the contents of the courses. | sep-23 | N/A | N/A |  | S |
| SAP5. Document best practices from saving groups. | sep-23 | N/A | N/A |  | S |
| SAP6. Exchange of experiences to learn from saving groups good practices. | mar-24 | N/A | N/A |  | S |
| SAP7. Learning from exchanges of knowledge among similar experiences of stakeholders on saving groups. | jun-24 | N/A | N/A |  | S |
| SAP8. Promoting learnings from experiences of stakeholders regarding saving groups. | jun-26 | N/A | N/A |  | S |
| SAP9. Learning from good practice from the project through the exchange of knowledge. | dic-25 | N/A | N/A |  | S |
| SAP10. Adequate representation of private sector as project beneficiaries in the decision-making board of the project. | sep-22 | 100 | 100 |  | S |
| SAP11. Integration of appropriate and technical advice for the implementation of the project through a person specialized in gender and participation of diverse public, especially with intercultural participants. | oct-22 | 100 | 100 |  | S |
| Operational closure |  |  |  |  |  |
| Activity PC1.: Operational closure | jun-26 | N/A | N/A |  | S |
| Activity PC2.: Prepare final project report | jun-26 | N/A | N/A |  | S |

Overall rating of project progress towards meeting project objective(s) (To be provided by CAF-GEF Task Manager. Please add columns to reflect all prior year ratings)

| FY2022 rating | FY2023 rating | Comments/narrative justifying the current FY rating and explaining reasons for change (positive or negative) since previous reporting periods |
| --- | --- | --- |
| N/A | S |  |

Action plan to address MS, MU, U and HU rating (To be completed by CAF GEF Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |
| n/a | n/a | n/a |

This section should be completed if project progress towards meeting objectives was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |

3.3.	Risk

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified during project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the CAF Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The CAF Task Manager should provide ratings in the right-hand column reflecting his/her own assessment of project risks.

RISK FACTOR TABLE

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not applicable applicable | To be determined |  | Low | Medium | Substantial | High | Not applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : The roles of the coordination unit are defined, so are the roles from the implementing entity and Project beneficiaries. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Risk mitigated |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : The project operation manual is a tool aimed to help implementation of activities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Governance bodies were well defined in the prodoc and the execution is following the design. |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | Project team member have fluid communication among them and with stakeholders. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Workflow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Projects inception process has started in a context where other cooperation projects are implementing similar actions. This has required to coordinate actions and adjust timing and activities´ scope such as the National Registry for Bioendeavours. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Minor changes which risks were mitigated |  |  |  |  |  |  |
| Co-financing | Co-financing is secured, and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: Activities undertaken by the Project have had co-financing that has been evaluated | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Cofinancing is flowing according the plan |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: The first year Budget has been implemented in a lower percentage than what it was approved initially because it has been necessary to first ensure conditions that allow actions viability and sustainability. In this regard, pilot projects prioritized the most convenient investments for the current year, which were not the ones that were previously approved. One of the pilots, (Sumak Micuy) was undertaking a financial, and legal audit process which determined that the project would wait the results of this audits and UNORCARC´s decision to continue with the implementation. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: the Steering Committee resolved to approve those changes in project´s time line. |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: All amounts have been reported according to what was demanded. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Risk mitigated |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues. | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues. | Serious concerns about quality and timeliness of project reporting. | X |  |  |  |  |  | PM: Technical and Financial reports have been presented on time | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agree |  |  |  |  |  |  |
| Stakeholders’ involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners. | Consultation and participation process seems strong but misses some groups or relevant partners. | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders. | X |  |  |  |  |  | PM: Work has been carried out with critical stakeholders that were identified since project inception. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted. | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Project team members have a fluid communication with entities and groups with whom they have direct relations. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Low Risk |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long-term perspective, particularly sustainability and replicability. | Project is interested in the short term with little understanding of or interest in the long term. | Longer term issues are deliberately ignored or neglected. | X |  |  |  |  |  | PM: Monthly monitoring to indicators is carried out to attained long term expected, always considering the projects objective. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Low Risk |  |  |  |  |  |  |
| Science and technological issues. | Project based on sound science and well-established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks. | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: The Project promotes the use of information, methodologies, outputs, and equipment consistent with current technological and scientific advancements. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Risk mitigated |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated. | Project is subject to a variety of political influences that may jeopardize project objectives. | X |  |  |  |  |  | PM: The Project has not received any political interferences in its management or decision-making processes | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Risk mitigated |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: n/a |  |  |  |  |  |  |

|  |  |  |  | Calificación del Gerente del proyecto |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk factor | Indicator of Low risk | Indicator of Medium risk | Indicator of High risk | Low | Medium | Substantial | High | Not applicable | To be determined |  | Low | Medium | Substantial | High | Not applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  | X |  |  |  | PM: The latest political events that have occurred and that are about to happen in the upcoming months could significantly affect the flow on project implementation. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: I disagree, political unstability is a medium risk, mitigated by the presence of technical staff of MAATE who manage the day to day of the project |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: The El Niño phenomenon will impact the country´s agricultural sector and this could be evident in bioendeavours located in vulnerable areas. The cross contamination in the soils of chocho farmers of COOPGRANACH is such that the project´s time frame will not be enough so that they can obtain an organic certification in the surface that was defined as a target (10ha). Also, the surface of crops in COPROBICH y SUMAK MICUY have reduced significantly due to unfulfillment of standards during the COVID 19 pandemic. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Agree. |  |  |  |  |  |  |
| Social, cultural, and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results. | Social or economic issues or changes pose challenges to project implementation, but mitigation strategies have been developed. | Project is extremely sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: It is expected that socio-economic factors have a low impact in projects development. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is extremely low at all levels and partners require constant support and technical assistance. |  |  | X |  |  |  | PM: Pilot projects require technical monitoring, for organizational and financial areas aiming at improving their management practices so that they can become in role models from which to extract lessons learn and practical experience. Sumak Mikuy shows structural weaknesses with impact on the financial department. Given this situation the company´s main shareholder , UNORCAC started a financial and legal audit process that will allow to learn more about the situation and from this make some decision. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agree |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

Rank – importance of risk

Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk

Who – person(s) responsible for the action

Date – date by which action needs to be or was completed

TOP RISK MITIGATION PLAN

| Rank | Risk Statement |  | Action to take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| High | The area of organic crops in COPROBICH and Sumak Mikuy has been significantly reduced due to non-compliance with standards during the COVID 19 Pandemic. | Organic production area targets may not be reached | Update the baseline for the indicator of area with organic and GAP certifications (completed). Prepare technical assistance plans to adjust annual goals and guide actions. Inclusion of a field technician for the project to strengthen agricultural processes (proposed). | Project coordinator based on team field reports. | 04/03/2022 |
| High | The Sumak Mikuy company has structural weaknesses that are leading to financial difficulties. Considering the situation, the company's majority shareholder, UNORCAC, has contracted a financial and legal audit to ascertain the situation and make the appropriate decisions. | The necessary measures to overcome the company's difficulties could not be taken by UNORCAR and cause the company's unsustainability and consequently the ineffectiveness of the Project with this pilot. | Support was requested from Heifer's Business and Social Capital Management Departments to analyze the company's situation and propose an intervention strategy. Working meetings were held with UNORCAC's Cabildo Central to provide advice. UNORCAC has decided to repower the company with the necessary resources and has requested the Project's support. The Project will support the repowering based on a strategy and action plan conditioned to meeting milestones. | Heifer Ecuador and Project coordinator. | 06/15/2023 |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY rating | FY2023 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| N/A | LOW | Besides impact of COVID19 to local farmers, Political Instability, The strong leadership of MAATE, and resilience of strategic partners and other stakeholders keep safe advancements according the project planning |
|  |  | If a risk mitigation plan had been presented for a previous period or because of the Mid-Term Review/Evaluation, please report on progress or results of its implementation |

- RATING MONITORING AND EVALUATION

Based on the answers provided to the questions in 4.1, 4.2 and 4.3 below, the CAF Task Manager

will provide ratings for the following aspects of project monitoring and evaluation:

(i)	Overall quality of the Monitoring & Evaluation plan

(ii)	Performance in the implementation of the M&E plan

4.1. Does the project M&E plan contain the following:

- Baseline information for each outcome-level indicator	Yes X No □

- An Indicators to track project outcomes	Yes X No □

- A clear distribution of responsibilities for monitoring project progress. Yes, x No □

4.2.	 Has the project budgeted for the following M&E activities:

- Mid-term review/evaluation	Yes X No □

- Terminal evaluation	Yes X No □

- Any costs associated with collecting and analyzing indicators’ related information

Yes X No □

Please rate the quality of the project M&E plan (use HS, S, MS, MU, U, HU):

  - Has the project:

- Utilized the indicators identified in the M&E plan to track progress in meeting the project objectives;	Yes X	No □

- Fulfilled the specified reporting requirements (financial, including co-financing and auditing, and substantive reports)	Yes X	No □

- Completed any scheduled MTR or MTE before or at project implementation mid-point;	Yes X	No □

- Applied adaptive management in response to M&E activities	Yes X No □

- Implemented any existing risk mitigation plan (see previous section) Yes X No □

Please rate the performance in implementing the M&E plan (use HS, S, MS, MU, U, HU):

4.4.	Please describe activities for monitoring and evaluation carried out during the reporting period.

In this first year of implementation, several activities have been carried out in monitoring and evaluation, among which the following stand out:  collect information from the different organizations that must submit co-financing values to the project through meetings, reports, and data cleaning. Work has been done on an additional group of indicators considered necessary to measure the project's contribution to reducing the poverty gap among direct beneficiaries, as well as its contribution to maintaining the environment through different practices.

We worked together with the company ETHNIESSENCE in a diagnostic study to know the situation of their raw material suppliers on organic production, since there is a setback in the processes reported until 2019 when the project was planned. We have collaborated with COPROBICH technicians to update the baseline of hectares under organic production. We also participated in meetings with MAATE to clarify the measurement of GEF indicators, as well as with Agrocalidad to obtain the necessary information for the reports required by the project.

In addition, a generalized mapping of the bioendeavours that MAATE, as well as different initiatives, projects and organizations have supported was carried out to have a first glimpse of the universe with which the national registry system and the different components would work.

In addition, to obtain feedback on the activities carried out with the different stakeholders, satisfaction surveys have been applied using the NPS (Net Promoter Score) and the Likert scale to find out how satisfied they are and, additionally, they have been asked what other topics they would like to discuss or learn about.

4.5.	Provide information on the quality of baseline information and any effects (positive or negative) on the selection of indicators and the design of other project monitoring activities.

The project was designed in 2019 and started implementation in 2022, i.e., there is a time difference of 3 years. During this period, events such as the COVID 19 pandemic process have occurred, which have caused the project baseline to vary in some of its indicators, especially those related to areas under sustainable management systems. These indicators have had to be updated.

4.6.	Provide comments on the usefulness and relevance of selected indicators and experiences in the application of the same.

The indicators presented in PRODOC are relevant for measuring the expected scope of the project. This work has been done with the support of different organizations and entities involved in the project, as well as with the advice from a Heifer Ecuador specialist.

At the beginning of the project, the Steering Committee requested the selection of a smaller group of indicators that would be more representative of the work to be carried out, so ten main indicators were selected:

- Indicator 1 ML - 1 M&EP. Number of bioendeavours recorded into the national registry.

- Indicator 5 ML - 4 M&EP. Direct project beneficiaries disaggregated by sex (individual people).

- Indicator 6 ML - 5 M&EP. Number of regulations to incentive bioendevours.

- Indicator 12 ML - 11 M&EP Number of persons trained in bioendevour development (>50% women).

- Indicator 13 ML - 12 M&EP. Amount of project sponsored credit lines issued in loans. (USD)

- Indicator 14 ML. Number of persons from financial institutions trained.

- Indicator 16 ML - 14 M&EP. Area of agriculture plots certified organic (ha). (Broken down by organization).

- Indicator 17 ML - 15 M&EP. Areas of agriculture plots with “Good Agricultural Practices” certification. (Broken down by organization).

- Indicator 22 ML - 20 M&EP. Number of visitors per month (annual average) recorded in the network of electronic platforms used to disseminate project´s information and lessons. – Visits.

- Indicator 24 ML. Frequency of events to reflect, gather lessons and identify impacts.

4.7. 	Describe any challenges in obtaining data relevant to the selected indicators; has the project experienced problems to cover costs associated with the tracking of indicators?

During the first year of implementation, some challenges have been encountered, such as discrepancies in the wording of the means of verification and conceptualization of indicators. Specifically, this is the case of indicator 4.1. Area of landscapes under improved management for the benefit of biodiversity, where certificates issued to Sumak Mikuy are requested and the CAF Manual states that they correspond to areas of landscape managed to benefit biodiversity but are not certified. To clarify this, GEF´s focal point in MAATE criteria will be requested. It has also been a challenge to work with WIKIRI to measure the areas in which it promotes sustainable management systems, given that its intervention model is complex and involves difficulty in quantifying the impact at the surface level of its combined activities of research, breeding, restocking and commercialization of frogs. To define the measurement of this indicator, a meeting will be held with Wikiri and MAATE technicians in the first quarter of the second year.

Likewise, it was decided to work hand in hand with ETHNIESSENCE to carry out a situational diagnosis of their raw material suppliers, in order to have a clear vision of the current situation of the farmers' land with whom they work, and the actions proposed to achieve the goals until the end of the project. This work required an additional co-financing investment by the pilot and logistical support from the Project.

4.8.	Describe any changes in the indicators or in the project intervention logic, including an explanation of whether key assumptions are still valid.

Regardless of the variations specified in the baseline of the indicators, it is considered that the project´s logic intervention continues and that the original assumptions are valid.

4.9.	Describe how potential social or environmental negative effects are monitored.

Given the announcement of the presence of the El Niño phenomenon in Ecuador in the coming months, Heifer's monitoring, and evaluation area (and this includes the Project's related personnel) periodically follow up on the intensity and consequences forecast information.

4.10.	Please provide any other experiences or lessons relevant to the design and implementation of project monitoring and evaluation plans.

Implementing monitoring and follow-up with a cross-cutting approach to gender and communication has been an enriching process to optimize the distribution of activities and their execution.

- PROJECT IMPLEMENTATION EXPERIENCES AND LESSONS

5.1. summarize any experiences and/or lessons related to project design. Please select relevant areas from the list below:

  - The Project's evaluation of the financial situation of the associative pilots has been very timely in identifying weaknesses in their business management systems. Based on this analysis, the organizations recognize the relevance of developing and implementing comprehensive strengthening plans, i.e., at the level of governance and administrative, technical, commercial, and financial management.

  - In the Project's pilot demonstration chains, the value of the services provided by the companies to the producers linked to the raw material supply line is weighted. In addition to the economic profitability that the member producers expect from the business organization, there is also a social value that is also recognized and provided in the form of bio-inputs, technical assistance, and other types of benefits such as the mortuary fund, for example. This helps the Project to define an orientation to address the scope and focus of the technical assistance actions to be provided.

  - the experiences generated during this period and the analysis of the factors that affect the implementation of the communication strategy, partnerships should be considered for dissemination actions and the creation of information channels to ensure the sustainability of the Project.

  - Design educational materials with graphic elements and information that allude to the specific characteristics of the region where work is being done to facilitate community ownership.

  - It is important to take advantage of the workshops generated with key stakeholders and pilot companies to propose training spaces to strengthen internal and external communication according to the needs identified, such as the use of digital channels: web, social networks, and internal communication.

  - Develop materials that are easy to understand and establish the most suitable channels considering the social and cultural characteristics of each audience.