UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5483 | Umoja no.: P1-33GFL-000817 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Enhancing livelihoods in rural communities of Armenia through mainstreaming and strengthening agricultural biodiversity conservation and utilization |  |  |
| Duration months | Planned |  | 36 months |  |  |
|  | Extension(s) |  | 31 August 2019 |  | 10 months added |
| Division(s) Implementing the project |  |  | Ecosystems Division, GEF Biodiversity and Land Degradation Unit |  |  |
| Executing Agency(ies) |  |  | Bioversity International (IPGRI) |  |  |
| Names of Other Project Partners |  |  | Ministry of Nature Protection of the Republic of Armenia |  |  |
|  |  |  | Institute of Botany of Academy of Sciences |  |  |
|  |  |  | Armenian Forest NGO |  |  |
|  |  |  | Env Public Alliance NGO |  |  |
|  |  |  | Agro X Fund NGO |  |  |
|  |  |  | Armenian Agrarian University |  |  |
| Project Type |  |  | MSP |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Europe |  |  |
| Names of Beneficiary Countries |  |  | Armenia |  |  |
| Programme of Work |  |  | POW 2018-19 Subprogramme 3 Healthy and Productive Ecosystems, EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | UNDAF 2016-20, PA 4: Environmental sustainability and resilience-building Outcome 7: By 2020 Sustainable development principles and good practices for environmental sustainability resilience building, climate change adaptation and mitigation, and green economy are introduced and applied |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG2 (2.4.1, 2.5.1); SDG 4 (4.7.1); SDG5 (5.5.2) |  |  |
| GEF financing amount |  |  | 883,242 |  |  |
| Co-financing amount |  |  | 4,852,463 |  |  |
| Date of CEO Endorsement |  |  | 08 July 2015 |  |  |
| Start of Implementation |  |  | 18 November 2015 |  |  |
| Date of first disbursement |  |  | 16 March 2016 |  |  |
| Total disbursement as of 30 June |  |  | 337,386 US$ (Bioversity) US$ 450,593 (Armenia) |  |  |
| Total expenditure as of 30 June |  |  | US$ 332,534 (Bioversity) US$ 431,593 (Armenia) |  |  |
| Expected Mid-Term Date |  |  | PIR for 2018 used as MTR |  |  |
| Completion Date |  | Planned | 31 October 2019 |  |  |
|  |  | Revised | 31 December 2019 |  |  |
| Expected Terminal Evaluation Date |  |  | June 2020 |  |  |
| Expected Financial Closure Date |  |  | 30-06-2020 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Sub-programme 3: Ecosystem Management/Healthy and Productive Ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) EM (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized […] at the national and international levels. (i) Increase the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems |
| --- | --- |
| The project’s contributions toward above-stated indicator can be summarized as follows: An Intergovernmental Coordination Committee on Agro-Biodiversity has been established and its Charter is approved by the Order of Ministry of Nature Protection #110, as of 4 November 2017. The first round-table meeting of the Coordination Committee was organized on 29 April 2019, with representatives of the Ministry of Environment, Ministry of Economy, Ministry of Education and Science, Ministry of Energy Infrastructures and Natural Resources, Ministry of Emergency Situations, Focal Points on CBD, UNFCCC, UNCCD, International Trade, and on Wetlands participating. National Guidelines on Agricultural Biodiversity Conservation and Use are developed. A strategic document for the guidelines is developed by the project in consultation with government agencies, Ministry of Agriculture, Ministry of Environment and community leaders. 5 policy briefs were produced and disseminated by the project, focusing on agrarian policy, its burning issues, results of analyses of national policy frameworks on conservation and use of agro-biodiversity, importance of local biodiversity use, and conservation. A national law on “Conservation of Wild Fruit Trees in Specially Protected Areas of Armenia” is drafted and circulated among relevant stakeholder institutions and agencies for their comments. Regulations on the conservation of genetic resources (seeds) of fruit trees are developed and will be submitted to relevant government agencies for their review and follow up actions with further approval. 41 manuals on sustainable management of priority plant species for use by farmers, local communities and extension service as well as 86 public awareness materials are produced by the project. Project web site www.agroecoarm.com is developed and operational. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |
| N/A GEF 5 project |  |

| Planned linkages with UNDAF | The project is promoting good practices on sustainable management of in situ and on farm agrobiodiversity at all levels including government agencies and local communities. The project put enormous efforts to bring together through Inter-governmental Coordination Committee various government agencies dealing with agrobiodiversity including Ministry of Economy, Ministry of Nature Protection, Ministry of Agriculture. This Committee will serve as a platform to discuss and make decisions on issues related to conservation and use of agrobiodiversity including cultivated plants and their wild relatives. At community level the project united farmers and other community members in the project sites through establishment of Farmers’ cooperatives and trained them on adding value and marketing agrobiodiversity rich products. Moreover, the project tries to involve private commercial companies benefiting from local agrobiodiversity in agrobiodiversity conservation actions as supporting farmers to maintain local agrobiodiversity, increase areas under local varieties of agricultural crops and populations of their wild relatives. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | SDG 2: The project developed “Guidelines on Conservation and Use of Agrobiodiversity” in consultation with government agencies and local communities. The Guidelines provides information on status of in situ and on farm conservation of agricultural and food plants as well as guiding principles including legal framework on conservation of crops biodiversity in Armenia. SDG 4: Women and youth in the project sites were involved in implementation of the project’s activities. They broadened their knowledge and gained the skills on agrobiodiversity management and marketing at the trainings, round tables, workshops organized by the workshop. Two Young generation Agricultural Clubs are established by the project to maintain interest of youth in farming and agrobiodiversity conservation as well as to involve them in the decision-making process including value adding and marketing of agrobiodiversity products. SDG 5: One of the two Farmers’ Cooperatives established within the project is chaired by a female member. |
| --- | --- |

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| The project made good progress in achieving its development objective. Among the main achievements at national level was the organization of a round table meeting of the Intergovernmental Coordination Committee on Agro-biodiversity on 27 June 2019. Representatives of Ministry of Environment, Ministry of Economy, Ministry of Education and Science, Ministry of Energy Infrastructures and Natural Resources, Ministry of Emergency Situations, Focal Points of CBD, UNFCCC, UNCCD, International Trade, and Wetlands participated in the meeting. The project also strongly invested in raising the awareness of various stakeholder groups including local communities and policy makers on the role of local agrobiodiversity for local livelihoods. A number of policy briefs (5) and national legal documents (3) were developed, together with numerous materials for use by both policy makers and local resource users alike. At local level, farmers’ cooperatives and young generation agricultural clubs were established in two project sites to ensure sustainable management of local agrobiodiversity through marketing of agrobiodiversity-rich products. |  |  |  |  |  |

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Implementation progress of the project is assessed as satisfactory (S) considering that it produced all outputs and deliverables planned for the reporting period, despite of challenges faced by the project in connection with continuous process of reforms in government and a volatile political situation in Armenia in 2018-2019. Fulfillment of co-financing commitments is also a sign of dedication of the project team and its project partners to its successful implementation. |  |  |  |  |  |

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L | L |  |  |
| Due to the project’s well-established partnership with government partners, it was able to very flexibly mitigate against the changing political structures: In 2019 the government of Armenia continued reforms in government structure. As a result, Ministry of Agriculture became a part of Ministry of Economy, Ministry of Nature Protection was renamed into Ministry of Environment. Ministry of Energy Infrastructures and Natural Resources was reformed into Ministry of Territorial management and infrastructures. All these changes were reflected in the structure of the Intergovernmental Coordination Committee on Agro-biodiversity. As soon as the structure of the Committee was finalized, the project team organized its first round-table meeting on 29 April 2019. Due to the reforms the finalized version of the Guidelines on Agricultural Biodiversity Conservation and Use was re-circulated among government agencies to get their approval for further publicizing of the document. After obtaining approval from all stakeholders the Guidelines were published in the reporting period. In the framework of the project in consultation with all national partners it was decided that Institute of Botany will lead and coordinate the work on development of national law on “Conservation of Wild Fruit Trees in Specially Protected Areas of Armenia” and “Regulations on conservation of the genetic resources (seeds) of the fruit trees”. In the reporting period, national partners drafted the law and regulations, which were circulated among relevant stakeholder institutions and agencies for their comments. |  |  |  |  |  |

| Stakeholder engagement | All government partners were continuously engaged and consulted despite an extensive reform affecting government ministries and entities. The project was capable of integrating these changes into the already established coordination committee and organized its first roundtable with broad ministry participation. Diverse policy briefs and policy analyses were broadly shared for comments among stakeholders. Smallholders are continuously engaged in the development of implementation plans for agro-forestry and the improvement of value chains. The project further invests in creating community-based agro-cooperatives and clubs for youth engagement. |
| --- | --- |

| Gender mainstreaming | The project established a specific gender lens onto rural development and focusses on disadvantaged groups, including women and young people. Activities ensure that the specific needs of women and men are addressed when selecting priority species, best practices and products. It produced for example a brochure on "Selection and use of plants in Armenia: preferable plants for men and women, gender preferences for plant growing and food crops.” The project made good progress in involving women in the project activities. Around 100, or 25% of participants of training workshops, rounds table discussions, exchange visits on sharing good practices and knowledge in agro-biodiversity management are women. One of the two Farmers’ Cooperatives established by the project is chaired by a woman. Two Young Generation Agricultural Clubs are established in Nor Ughi Community in Ararat project site and in Kalavan Community in Gegharcunik project site. |
| --- | --- |

| Knowledge activities and products | In total 41 manuals on sustainable management of priority plant species for use by farmers, local communities and extension services as well as 86 public awareness materials were produced by the project. Strategic documents such as “Guidelines on Agricultural Biodiversity Conservation and Use”, “Guidelines for certification of biodiversity-friendly food products” and “Guidelines on marketing of priority crops: sea-buckthorn (Hippophaë rhamnoides L.), lentil (Lens culinaris), apricot (Armeniaca vulgaris L.) and grape (Vitis vinifera L.)” were developed in consultation with government agencies, Ministry of Agriculture, Ministry of Environment, leaders of local communities in the project sites. 5 policy briefs focused on agrarian policy, its burning issues, results of analysis of national policy framework on conservation and use of agrobiodiversity, importance of local biodiversity use and conservation were produced and disseminated by the project. TV programmes promoting the use of fruit trees in agriculture were developed, reaching out to local stakeholders. |
| --- | --- |

| Stories to be shared |  |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-term target or Milestones | End-of-project target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Enhanced conservation and use of existing agricultural biodiversity in Armenia, to support adaptation to environmental and agricultural challenges and improvement of rural livelihoods. | Land area under biodiversity friendly management practices. Existence of local and national agencies that focus on sustainable use of Armenia’s agricultural biodiversity. Identified coordination mechanisms and procedures in place (joint committees, meetings, implementation procedures, agreements on action). | Currently, there are significant development trends ongoing in Armenia that are detrimental to maintenance of agro-biodiversity (e.g., mining, urbanisation). The potential national and global value of Armenia’s agro-biodiversity is not well recognized. Markets for specifically certified products are not available and the general knowledge of farmers and consumers about the benefit of agro-biodiversity is low. Some opportunities have been identified in the eco-tourism sector but these are disjointed and largely fragile and unsustainable. | Mechanisms have been identified to enhance and coordinate agro-biodiversity friendly management practices and market potential. Dialogue amongst political decision makers has been established. | An increase of land under agro-biodiversity-friendly management practices of 20% in at least one of the project sites. Establishment of a national coordination body. Availability of a National Biodiversity Strategy. At least 2 new agro-biodiversity friendly products are available in local and national markets. | Based on the Indicators of Logical Framework of the Project a questionnaire was developed to conduct end-of-project survey on project outputs against baseline criteria. Analysis of the collected information will be carried out in the second half of 2019. Intergovernmental Coordination Committee on Agro-biodiversity has been established and its Charter is approved by the Order of Ministry of Nature Protection #110 of 4 November 2017. National Guidelines on Agricultural Biodiversity Conservation and Use are developed. The project team in consultation with local communities, commercial companies, retailers and certification agencies identified sea-buckthorn beverage as an agro-biodiversity product to be launched by the project. | S |
| Outcome 1: Strengthened national coordination and cooperation for effective management of agricultural biodiversity through mainstreaming integrated approaches to agricultural biodiversity conservation and use into Armenia’s policy framework. | Establishment of a coordination committee; Number of relevant policy documents produced. | There are some efforts being taken in Armenia to address the issue of land degradation and loss of agro-biodiversity. However, responsibilities are spread over several Ministries and other organizations. There is currently no coordinated effort. | Dialogue amongst key ministries and stakeholders has been established and date and venue for first round-table meeting has been agreed. | Intergovernmental Coordination Committee on Agro-biodiversity established by end of Year 2 and has issued at least 2 policy briefing documents by end of Year 3. | Intergovernmental Coordination Committee on Agro-biodiversity has been established and its Charter was approved by the Order of Ministry of Nature Protection #110 of 4 November 2017. The first roundtable meeting of the Intergovernmental Coordination Committee on Agro-biodiversity was organized on 29 April 2019. Representatives of Ministry of Environment, Ministry of Economy, Ministry of Education and Science, Ministry of Energy Infrastructures and Natural Resources, Ministry of Emergency Situations, Focal Points on CBD, UN Conventions on Climate Change, Desertification, International Trade, Wetlands participated in the meeting. Strategic document “Guidelines on Agricultural Biodiversity Conservation and Use” is developed by the project in consultation with government agencies, Ministry of Agriculture, Ministry of Environment, leaders of local communities in the project sites. In total five policy briefs focused on agrarian policy, its burning issues, results of analysis of national policy framework on conservation and use of agrobiodiversity, importance of local biodiversity use and conservation were produced and disseminated by the project. National law on “Conservation of Wild Fruit Trees in Specially Protected Areas of Armenia” is drafted and circulated among relevant stakeholder institutions and agencies for their comments. “Regulations on conservation of the genetic resources (seeds) of the fruit trees” is developed and will be submitted to relevant government agencies for their review and follow up actions with further approval. | S |
| Outcome 2: Increased area devoted to sustainably managed agricultural biodiversity through the mainstreaming of diversified practices and products. | Area (Ha) under sustainable management. Number of households (disaggregated by sex of household head) practicing sustainable management. | Baseline varies for different countries e.g. in Armenia, no computerized information system containing farming practices in the target districts are not taking agro-biodiversity into consideration. | Draft guidelines, documents and training materials for sustainable management and use of agro-biodiversity available. Initial set of priority species and best practices identified and promoted. | Area under sustainable management vis-à-vis baseline study (to be conducted at the beginning of the project) in the project sites has increased by at least 20%. At least 20% of farmers (disaggregated between men and women) in at least 1 project site are using sustainable agro-biodiversity friendly production and/or harvesting methods for priority species. | Baseline report on “Priority species, current best management and harvesting practices for cultivated and wild plants and their products” was produced by the project based on the survey conducted in the beginning of the project in 2016. In total 41 manuals on sustainable management of priority plant species for use by farmers, local communities and extension service as well as 86 public awareness materials are produced by the project. Project web site www.agroecoarm.com is developed and operational. From the date of the start of the project in total 399 people, including farmers, local community members, extension service staff and government agencies of which around 25% are women benefited from training workshops, rounds table discussions, exchange visits on sharing good practices and knowledge in agro-biodiversity management methods,organized in three project sites. | S |
| Outcome 3: Increased availability of agricultural biodiversity friendly products in local and international markets that provide farmers with additional rewards and income. | Number of new products derived from agro-biodiversity. Volume of sale of agro-biodiversity-derived products. | Currently there are few products in the local, national and international markets with the exception of some drinks, (herbal teas, lemonades), condiments and dried fruits. | 1-2 new priority products have been identified. | At least 2 new bio-diversity friendly products are available in the local market and one product is tested for the international market. | Guidelines for certification of biodiversity-friendly food products are developed. The organic sector in Armenia was identified as the sector most concerned with agrobiodiversity-based products. Through participatory process in close consultation with local communities in the project sites two crops in each project site were identified as priority species for certification and marketing agrobiodiversity products: apricot (Armeniaca vulgaris L.) and grape (Vitis vinifera L.) in Ararat project site, sea buckthorn (Hippophaë rhamnoides L.) and lentil (Lens culinaris) in Gegharkunik project site. The project team in consultation with local communities, commercial companies, retailers and certification agencies identified sea-buckthorn beverage as an agro-biodiversity product to be launched by the project. | S |
| Outcome 4: Project implementation based on results based management and application of project lessons learned in future operations facilitated. | Timely implementation of the project activities. | Baseline documents provided as reports prepared for PDF B and summarized in national documents and project Annexes. | Project operating framework is in place, key staff is hired, supervisory mechanisms in place. | On-time delivery of project outputs and relevant reports. | Project’s progress is assessed against indicators in project’s logical framework. Community leaders in project sites participate in meetings on monitoring and evaluation of project. These meetings are organized every six months and so twice a year. In the reporting period two meetings on monitoring and evaluation of project’s progress were organized on 25 December 2018 and on 27 June 2019. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project made good progress in achieving its development objective. Among the main achievements at national level was the organization of a round table meeting of the Intergovernmental Coordination Committee on Agro-biodiversity on 27 June 2019. Representatives of Ministry of Environment, Ministry of Economy, Ministry of Education and Science, Ministry of Energy Infrastructures and Natural Resources, Ministry of Emergency Situations, Focal Points of CBD, UNFCCC, UNCCD, International Trade, and Wetlands participated in the meeting. The project also strongly invested in raising the awareness of various stakeholder groups including local communities and policy makers on the role of local agrobiodiversity for local livelihoods. A number of policy briefs (5) and national legal documents (3) were developed, together with numerous materials for use by both policy makers and local resource users alike. At local level, farmers’ cooperatives and young generation agricultural clubs were established in two project sites to ensure sustainable management of local agrobiodiversity through marketing of agrobiodiversity-rich products. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets |  |  |
| on stakeholder engagement |  |  |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results |  |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1: National institutional arrangements in place and capacity developed to mainstream and promote agricultural biodiversity in relevant land use sectors | Dec 2019 | 90% | 98% | Intergovernmental Coordination Committee on Agro-biodiversity has been established and its Charter was approved by the Order of Ministry of Nature Protection #110 of 4 November 2017. Due to elections of the president of Armenia and consequent movement to the government headed by the Parliament, there was continuous process of reforms in the government structure. In 2019 number of national ministries was reduced from 19 to 12 in the new government structure. All these changes were reflected in the new structure of Intergovernmental Coordination Committee on Agro-biodiversity and the first roundtable meeting of the Coordination Committee was organized on 29 April 2019. Representatives of Ministry of Environment, Ministry of Economy, Ministry of Education and Science, Ministry of Energy Infrastructures and Natural Resources, Ministry of Emergency Situations, Focal Points on CBD, UN Conventions on Climate Change, Desertification, International Trade, Wetlands participated in the meeting. Issues on the need of inter-agency cooperation on agrobiodiversity conservation and land degradation matters, organization of ad-hoc consultation meetings during emergencies and further close collaboration were discussed at this meeting. Next meetings of the Committee will be organized with support of government and public funds to ensure sustainability of the project’s activities on conservation of local agrobiodiversity. In the reporting period, three meetings of Technical Advisory Committee (TAC) were organized to review overall progress in project implementation and providing recommendations to the project team on thematic issues of the project. 84 officers and farmers, including 28 female participants participated in three training events on “Land-use and importance of agro-biodiversity and Inter-sector collaboration”. Trainings were focused on increasing knowledge of local communities and local authorities on importance and need of inter-sector collaboration within communities and between communities for effective conservation of agrobiodiversity. The project team continuously works on raising public awareness. Two radio interviews, one TV interview, 2 newspaper stories, 11 posters and 11 brochures in Armenian language for use by stakeholders, including policy makers and local communities were produced in the reporting period. So far 86 materials in total are produced and used for campaign on raising public awareness on agrobiodiversity issues. All produced are also available at project web-site http://agroecoarm.com In total five policy briefs focused on agrarian policy, its burning issues, results of analysis of national policy framework on conservation and use of agrobiodiversity, importance of local biodiversity use and conservation were produced and disseminated by the project. | S |
| Output 1.2: National agricultural biodiversity strategy developed that takes account of unique diversity, ecosystem function and opportunities for sustainable intensification | Nov 2019 | 80% | 100% | Based on results of analysis of national policy and legislation related to national security and economic development, agriculture development and nature protection the strategic document on “Guidelines on Agricultural Biodiversity Conservation and Use” was developed by the project in consultation with government agencies, Ministry of Agriculture, Ministry of Nature Protection, leaders of local communities in the project. All national stakeholders provided their input in finalization of the document. Due to reforms in government structure the finalized version of the Guidelines on Agricultural Biodiversity Conservation and Use was re-circulated among government agencies to get their approval for further publicizing of the document. After obtaining approval from all stakeholders the Guidelines were published in the reporting period. In the framework of the project in consultation with all national partners it was decided that national Institute of Botany would lead and coordinate the work on development of national law on “Conservation of Wild Fruit Trees in Specially Protected Areas of Armenia”. In the reporting period, national partners at the Institute jointly with project experts developed draft version of the law, which was circulated among relevant stakeholder institutions and agencies for their comments. The project also developed “Regulations on conservation of the genetic resources (seeds) of the fruit trees”. These regulations will be also submitted to relevant government agencies for their review and follow up actions with further approval. | S |
| Output 1.3: Agriculture and environment programmes adopt a participatory approach to include all relevant stakeholders for planning, implementation and management. | June 2019 | 90% | 100% | Two Farmers’ Cooperatives are established in the project sites: Farmers’ cooperative “Garun V Gegharkunik” in Gegharkunik project site and Farmers’ cooperative “Garun V Ararat” in Ararat project site to support participation of local communities in decision making process on conservation and benefiting of local agrobiodiversity including marketing of its products. Farmers’ cooperative “Garun V Gegharkunik” unites 8 large holder farmers and 24 smallholder farmers. This cooperative is chaired by female farmer Ms. Varsik Hovsepyan. 13 of 32 members of this cooperative are women. Farmers’ cooperative “Garun V Ararat” unites 15 large holder farmers and 35 smallholder farmers. 20 of 50 members of this cooperative are women. Charter of Farmers’ cooperative “Garun V Gegharkunik” and Charter of Farmers’ cooperative “Garun V Ararat” were approved by State Registry Service of Ministry of Justice of the Republic of Armenia on 20 December 2017 and on 30 April 2018 respectively. The Charters consists of sections on General Conditions, Purposes, Legal Framework, Method of Acceptance of New Members in the Cooperative, Use of Common Goods, Rights of Farmers, Scope of Work, Obligations. Events on launching the Farmers’ Cooperatives “GARUN V-Ararat” and the Farmers’ Cooperative “GARUN V-Gegharkunik” were organized on 4 July 2018 Ararat project site and on 6 July 2018 in Gegharkunik project site. | S |
| Output 2.1: Participatory and sustainable management practices identified that support traditional crop varieties, crop wild relatives, medicinal species, pollinators and other beneficial insects, and developed to improve local diversity for marginal environments in the project site location. | May 2019 | 90% | 100% | Baseline report on “Priority species, current best management and harvesting practices for cultivated and wild plants and their products” was produced by the project based on the survey conducted in 2016. Prioritization of the species was made by the following criteria: - Origin: Primary (Wild relatives), Secondary (Wild relatives not belonging to the same species), Species, Ecotype species; - Economic: Demand for agricultural market, Demand for the food processing market; - Natural, Artificial; - Highly threatened, Less threatened; - Frost resistant (Hardiness), Drought resistant, Salinity resistant; - Adapted to land conditions; - Use as forage. - Best management practices and identification area Based on an the results of analysis of the gathered information, the “Guidelines for selection and cultivation of high-value agricultural crops and their wild relatives in Armenia” were produced by the project. The project team organized consultations with local communities in the project sites and identified two crops in each project site as priority species for participatory research: apricot (Armeniaca vulgaris L.) and grape (Vitis vinifera L.) in Ararat project site, sea buckthorn (Hippophaë rhamnoides L.) and lentil (Lens culinaris) in Gegharkunik project site. Based on studies conducted on improved management practices of selected priority crops “Guidelines on best practices on apricot, grape, lentil, sea buckthorn cultivation” including conservation, processing technologies and export opportunities of products of these species were produced. In the reporting period, the project team has also conducted study on “Role of agrobiodiversity in local livelihoods”. The objective of this research was focused on helping rural community to realize the role of biodiversity in sustainable improvement of their wellbeing. So far, based on ‘’Guidelines for trainings” developed in the framework of project in total 41 training manuals and guidelines were produced in Armenian language by national project team in close consultation and cooperation with national partner institutions. From the date of the start of the project in total 100 farmers in three project sites benefited from exchange visits on sharing good practices and knowledge on conservation and use of agrobiodiversity. Four trainings were organized for 69 extension workers. | S |
| Output 2.2: Guidelines and standards for sustainably managing and harvesting priority plants and products are established and implemented in the project site locations. |  | 93% | 100% | In total 41 manuals on sustainable management of priority plant species for use of farmers, local communities and extension service are produced by the project. The project established and maintains the database, which contains description of best practices documented in Ararat and Gegharqunik project sites. These practices include organic agriculture of priority crops in Gegharqunik project site; adaptation and mitigation measures to climate change effects in Gegharqunik project site; water-saving irrigation technologies applied in Ararat project site; measures on climate adaptation and mitigation developed by “International Action on Adaptation and Climate” and “Integrating Climate Change Adaptation into Development”. So far, the database contains 41 technical resources and 86 public awareness materials produced by the project. Three demonstration plots are established in two project sites. - In Ararat project site: - Demonstration orchard in area of 8.5 ha was established in June 2017 in land under the community property in Nor Ughi Community. Currently three local varieties of apricot: Yerevan (Shalakh), Spitak and Sateni (Aghjanabad); three local peach varieties: Ararati, Armaviri and Narnji; and two apple varieties: Simerenko and Demrchyan have being maintained in this demonstration plot. - Demonstration site in a green house with radish and carrot vegetables was established in June 2017 in the Taperakan Community in Ararat Province in collaboration with commercial company “Spayka LLC”.  In Gegharqunik project site: - Demonstration plot with berry crops was established in June 2017 on public land of Kalavan Community. Two raspberry varieties as Goliaf and Novo-Kitayevska, two varieties of blueberry (Vaccinium myrtillus), three varieties of grape as Muscati, Hadis and Sevani and three local species of currant (Ribes vulgaris, Ribes nigrum and Ribes rubrum) are maintained in this demonstration plot. Vegetable crops as garden asparagus (Asparagus officinalis), cabbage (Brassica oleracea var capitata) and lettuce (Lactuca sativa) are also planted in the plot to demonstrate opportunities for cultivation of vegetables crops to local communities in order to diversify their income sources and reduce pressure on natural habitat of these species in wild. These demonstration plots are used to train farmers on best practices in management of local agrobiodiversity, organic farming and marketing products of local agrobiodiversity. | S |
| Output 2.3: Farmers and local communities in the project pilot sites have enhanced skills and capacity to undertake agricultural biodiversity friendly farming and other relevant agricultural biodiversity friendly practices, and community-based approaches for sustainable agricultural biodiversity conservation and utilization strategies are developed. | June 2019 | 80% | 100% | 86 public awareness materials in total are produced by the project team within the project to run the awareness campaign. Produced PA materials were disseminated during field visits and meetings as well as through the project’s web-site http://agroecoarm.com. In total 399 farmers and local community members benefited from 14 training workshops and rounds table discussions organized by the project on agro-biodiversity-friendly production and harvesting methods. Based on consultations with local communities organized during field visits to the project sites Young Generation Agricultural Clubs were established in Nor Ughi Community in Ararat Province and Kalavan Community in Gegharcunik Province. In close consultation with community members and administrative bodies Charters of these clubs were developed. Events on launching the Agricultural Clubs were organized on 5 March 2019 in Nor Ughi Community with participation of 25 young farmers and on 11 March 2019 in Kalavan Community with participation of 30 young farmers. Bringing young farmers together through the clubs will ensure sustainability of involvement of local communities and raising their voice in decision making process. | S |
| Output 3.1 Guidelines developed for certification of biodiversity-friendly food products. | Dec 2019 | 60% | 95% | The project team conducted study on “Exploring the potential of agricultural biodiversity-friendly certification strategy”. The project team studied requirements for certification of wild leafy vegetables, fruits and berries to understand major bottlenecks and opportunities for certification of agrobiodiversity products. The project team has explored options existing in Armenia for certification of agrobiodiversity products prioritized by the project: apricot (Armeniaca vulgaris L.) and grape (Vitis vinifera L.) in Ararat project site, sea buckthorn (Hippophaë rhamnoides L.) and lentil (Lens culinaris) in Gegharkunik project site. The project team found out that the organic market is the most relevant for certification and marketing agrobiodiversity products prioritized by the project. Currently ECOGLOBE is the only agency in Armenia, which provides certification for organic products. The project team also studied all international certification standards for organic products. The project team also clarified whether the national legislative framework in Armenia allows the foreign agencies (such as FAIRWILD for wild collected crops, etc) to provide authority to Armenian companies for organic products certification. It is important to note that the organic market in Armenia has started to evolve with new momentum since 2015, when the Organic Support Initiative (OASI) project started in this country. At present, more than 45 companies and individuals are engaged in organic agriculture and have certification provided by ECOGLOBE. There are already the companies and individuals in Armenia, which are producing certified organic apricots, grapes, sea-buckthorn, lentils and berries. The project organized workshops in the project sites to demonstrate to farmers benefits of certification of the agrobiodiversity products, At the workshops the Chairman of the Gegharkunik farmers’ cooperative shared his experience on production of certified organic compost and organic fertilizer which he sells to the local farmers, flower shops and other consumers. He also explained all the steps needed for organic products certification provided by Ecoglobe – a local certification company. This was a good example for participants that production of certified agrobiodiversity products is possible and beneficial. Based on results of the study and consultation with stakeholders “Guidelines on certification for organic food products” was drafted by the project and is currently being reviewed by International Consultant on Marketing for finalization. | S |
| Output 3.2 Marketing programmes for certified and non-certified (including organic and geographically identifiable agriculture products) agricultural biodiversity friendly products are in place and implemented through a supply chain approach. | Dec 2019 | 85% | 90% | List of experts which includes 25 national experts in plants breeding, climate change, agro-ecology, botany, agricultural sciences, market chain and certification was compiled by the project to establish panel of experts to identify and promote priority products. Survey to assess current availability of agro-biodiversity products in Armenia conducted through internet search, survey of food outlets, hotels and tourist shops showed that in general agro-biodiversity food products are available at informal seasonal food markets as local street markets. However they are not represented in formal food sector as supermarkets and restaurants agro-biodiversity products since they should meet certain standards related to food safety. Moreover, at formal food markets there is big demand for properly processed and packed agro-biodiversity products. Results of the survey were discussed by the panel of experts and workshops were organized with participation of farmers, marketing specialists, and agriculture experts to assess market opportunities for selected priority species: apricot (Armeniaca vulgaris L.) and grape (Armeniaca vulgaris L.) for Ararat project site and of sea-buckthorn (Hippophaë rhamnoides L.) and lentil (Lens culinaris) for Gegharkunik project site using Rapid Market Appraisal (RMA) tool. Taking into account that the organic market is the most relevant for marketing agrobiodiversity products prioritized by the project the team conducted study and consultation on importance and possibilities of organic agriculture in Armenia, identification and evaluation of organic market opportunities for priority crops. The project organized in the project sites national workshops on value chain development for agricultural biodiversity with participation of local communities, local processing and trading companies. The objective of the workshops was to help farmers in finding ways to overcome potential barriers in market value chain of local agrobiodiversity products, establishment of contacts with retailers, processors, traders, export agencies and engagement of all these actors in the conservation actions. Participants discussed the issues on marketing of agrobiodiversity products, including approaches to identify products and markets. All this work helped the project team to identify sea-buckthorn beverage as an agro-biodiversity product to be launched by the project. In consultation with local communities the project developed packaging of alcoholic beverage made from wild sea buckthorn for launching as a new local agro-biodiversity-friendly product. Based on outputs of this work the project developed “Guidelines on marketing agrobiodiversity products” in collaboration with local commercial companies, NGOs and cooperatives. The guidelines highlights close linking agrobiodiversity conservation activities such as the demonstration plots to the sales of agrobiodiversity products. | S |
| Output 3.3 International and national marketing and promotional opportunities identified for key high value Armenian agricultural products and wild medicinal and food plant products. | Nov 2019 | 68% | 97% | The project carried out market study for organic products and conducted individual interview to assess opportunities for local organic food produced of local crop diversity. Questionnaire was developed by International Consultant on Marketing for assessment of organic sector in Armenia to generate better understanding of market niches for organic vegetables, medicinal plants, spices and fruits. RMA covered the groups of organic shops, retailers, wholesalers, processors and traders. Exercises on Market Intelligence Fact Sheet (Format for Rapid Market Appraisal) were completed together with local communities in Ararat and Gegharkunik project sites. As result of the exercises it was identified that there are opportunities for organic products of priority species as sea buckthorn (Hippophaë rhamnoides L.), lentil (Lens culinaris), apricot (Armeniaca vulgaris L.) and grape (Vitis vinifera L.). Particularly, during the study it was revealed that products of organic sea buckthorn and lentil are available at local market. Local private company “Bison-1 Co.Ltd” is famous for its organic “Meron Berry Tea” and sea buckthorn oil. Sea buckthorn juice “Yan” produced by “SIS NATURAL CJSC” is popular at the organic market. Local company “Agrolog CJSC” produces organic products of lentil. There are also local companies producing organic apricots and grapes. Database with contact details of 10 journalists, 5 newspapers, 5 TV and radio channels was developed to launch an advertisement campaign for alcoholic sea buckthorn beverage - a new local agro-biodiversity product offered by the project through radio, newspaper, TV channels. The project supported participation of local communities at the Third Annual Raspberry Fest organized on 28 July 2018 in Ashotavan, Syunik Province. This event provided a good opportunity to the project team to establish new contacts and cooperation with other organizations and enterprises dealing with production and marketing of products of berry crops. The event was organized by local organization “World Vision Armenia”. The Fest was aimed on providing support in sustainable local value chain development of berry products at local and export markets. The Fest was also attended by many visitors from countries outside Armenia. | S |
| Output 4.1 Project monitoring system operating providing systematic information on progress in meeting project outcome and output targets. Materials prepared and information disseminated. | Dec 2019 | 93% | 100% | During the First meeting of Project Steering Committee on 2 March 2016 framework for project monitoring and evaluation was discussed and approved by national partners. Project’s progress is assessed against indicators in project’s logical framework. Community leaders in project sites participate meetings on monitoring and evaluation of project. These meetings are organized every six months and so twice a year. In the reporting period two M&E meetings on monitoring and evaluation of project’s process were organized on 25 December 2018 and on 27 June 2019. | S |
| Output 4.2. Midterm and final evaluation conducted. | July 2019 | 50% | 50% | Midterm review of the project is made through the PIR process and final evaluation is scheduled for 2020. | S |
| Output 4.3 Project-related “best-practices” and “lessons-learned” published. | Dec 2019 | 0 | 80% | Based on the Indicators of Logical Framework of the Project a questionnaire was developed to conduct end-of-project survey on project outputs against baseline criteria. Analysis of the collected information will be carried out in the second half of 2019. The project team is working on preparing publication on best practices on agrobiodiversity management, which were documented within the project. | S |
| Output 4.4 Website to share the experience and information dissemination. | Dec 2019 | 80% | 100% | Project web site www.agroecoarm.com is developed and currently functional. Information on the web-site is updated regularly. Web-site has sections on Experts, Partner institutions, Links, Maps, Priority species, Project outputs, Project sites, Publications, Site map, List of species, News, Contacts. | S |
| Output 5: Project Management | Dec. 2019 | 100% | 100% | Project Implementation Unit (PIU) was established to provide overall administration of the project. National Project Coordinator and his assistants are hired. Project Steering Committee (PSC) was established according to institutional arrangements of the project document. Representatives of 9 institutions are members of NSC. The first meeting of NSC was held on 2 March 2016 in Yerevan, Armenia. The second Project Steering Committee (NSC) meeting was held on 2-3 October 2017 in Yerevan, Armenia. Third PSC meeting scheduled for June 2019 was postponed due to replacement of UNEP Task Manager for the project. Budgeting and accounting system is fully implemented and continuously refined. Letter of Agreements (LOA) for each year are signed between Bioversity and Ministry of Nature Protection of the Republic of Armenia. LoA determines schedule of payments and reports submission. Financial reports are provided to Bioversity and UNEP at quarterly basis. Communication chart is developed and agreed with all national partners involved in the project implementation. Communication with national project partners and institutions is maintained by PIU through phone calls, emails and face to face meetings. National project coordinator regularly visit national partner institutions and meet them to discuss any challenge in project implementation. Bioversity and PIU are communicating through email, skype and phone. Ministry of Nature Protection, a national executing agency, at the meetings of its Ministry Board with representation of all stakeholders groups is keeping a loop at the project implementation; during each Board meeting, the Minister asks participants about their suggestions that can be applied in the project implementation. Project web-site http://agroecoarm.com is established for communication with broader audience. Request for Non-cost extension and revised work-plan until 31 August was submitted to UNEP to complete the outstanding activities of the project postponed due to changes in government structure in Armenia. The NCE request was approved on 17 April 2019. |  |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Implementation progress of the project is assessed as satisfactory (S) considering that it produced all outputs and deliverables planned for the reporting period, despite of challenges faced by the project in connection with continuous process of reforms in government and a volatile political situation in Armenia in 2018-2019. Fulfillment of co-financing commitments is also a sign of dedication of the project team and its project partners to its successful implementation. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Climate change or other environmental events remove diversity and lead to expansion of desert and arid zones in Armenia | Necessary mitigation measures and good practices of mitigation will be identified and included in the National Agricultural Biodiversity Strategy and national policies to be developed within framework of the project. Emphasis will be placed on the active participation of local communities in the identification and implementation of adaptation measures. This will help the proposed project design measures aimed at increasing the resilience and adaptability of important agroecosystems in Armenia. | The project developed a number of policy documents on in situ and on farm conservation of agrobiodiversity including “Guidelines on Agrobiodiversity Conservation and Use”. Intensive public awareness campaign was organized by the project to raise awareness of broad audience including policy makers and local communities on value of indigenous agrobiodiversity and ecosystem services provided by it for environment sustainability and local livelihoods. As a result Inter-governmental Coordination Committee on Agrobiodiversity was established at national level as well as Farmers’ cooperatives and Young Generation Agricultural Clubs at local level in the project sites. Exchange visits of farmers were organized to the project sites to share and learn on good practices in sustainable management of agrobiodiversity including environment friendly organic farming. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| There is failure of the private sector and NGOs to engage | Past experience has shown that it is difficult to engage the private sector in production of crops without, or little, monetary value. This might be aggravated by inadequately developed markets for potential agricultural biodiversity products. However, there is growing demand for products that can demonstrate a sustainable production base. | Survey conducted by the project showed that there is emerging market for organic agricultural products. Local agrobiodiversity with high capacity of adaptation to stress-factors of environment and possessing high nutritional value is an important component of organic products production process. National commercial companies were approached by the project within the framework of agrobiodiversity marketing activities and involved them in the discussion with local communities on how agrobiodiversity rich products can enrich local and export market with new products. As a result, commercial companies expressed their willingness to support agrobiodiversity conservation activities in the project sites. This work will be continued by local NGOs involved in the project and dealing with organic farming. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Commitment to in situ and on farm conservation of agricultural biodiversity may not be desirable to all farmers and communities. | To mitigate this, the project will explore the use of incentive measures to make this more attractive to farmers. | The project explored opportunities for adding value and marketing agrobiodiversity products to create incentives to farmers and local communities to maintain local agrobiodiversity in sustainable way. Thorough study was conducted by the project and it was found out that emerging market for organic products provides excellent niche for agrobiodiversity rich products and the project linked farmers in the project sites with NGOs and commercial companies dealing with organic market, including certification of organic products. Consultation workshops were organized to bring together farmers and commercial companies. Trainings on adding value and organic certification were organized for farmers and local communities. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Certification procedures are not manageable and/or are detrimental to broad use of proposed product. | A thorough survey and close collaboration with standards-giving authority and other stakeholders will provide relevant information at an early stage. Certification will only be used as a tool in increased marketing if it is not detrimental to the overall objectives of this project. | “Guidelines on organic certification” is produced by the project. These guidelines are aimed to guiding farmers in the process of certification of their agrobiodiversity rich products wince the organic market was found by the project as the most relevant instrument to create incentives for farmers and local communities to maintenance agrobiodiversity both in situ and on farm in sustainable way. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | Armenia went through a period of government restructuring; however, the projects’ well-established partnership network and good engagement with stakeholders at all levels allowed to flexibly respond to this challenge. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems |  |  |  |  |  |  | PM Roles and responsibilities clearly defined and understood by national project team | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR |  |  |  |  |  |  | PM: Third PSC meeting scheduled for June 2019 was postponed due to the government reforms and uncertainties of representation in the PSC. Despite of this, the project governance is in place due to regular meeting of Technical Advisory Committee and meetings of national partners on review of the project progress. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment |  |  |  |  |  |  | PM: Inter-sectoral communications is enhanced | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  |  |  |  |  |  | PM: Project progresses according to work plan agreed with national stakeholders and the relevant reports are regularly submitted to international and national executing agencies | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  |  |  |  |  |  | PM: Co-financing is done on timely manner despite of changes in structure of co-financing national partner organizations caused by recent changes in political structure of the national government. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  |  |  |  |  |  | PM: Before financial request all actions are agreed with international and national executing agencies | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  |  |  |  |  |  | PM: Financial reports on project’s expenditures are submitted on quarterly basis. Budget is developed in consultation with national project team. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  |  |  |  |  |  | PM: Reporting requirements for both financial expenses and project technical progress are set up, and followed by the project. However, considerable delays are observed with submission of technical progress reports caused by the need to communicate with national partners on clarification of reported details. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  |  |  |  |  |  | PM: Institutional engagement structure was developed during the proposal development stage. This structure ensures involvement of all stakeholder groups dealing with agrobiodiversity conservation in Armenia in decision making process of the project. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  |  |  |  |  |  | PM: Project is producing wide range of public awareness materials, communication strategy is developed, mechanism for participatory monitoring and evaluation of the project is developed and implemented | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  |  |  |  |  |  | PM: Project is designed in the way that short-term outputs are contributing to long-term impact of the project. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  |  |  |  |  |  | PM: Scientific staff of Bioversity International provides technical backstopping to the national project team and highly qualified experts from advanced national research institutes and universities are involved in the project implementation. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  |  |  |  |  |  | PM: Project decisions and choices are made in consultation with all stakeholder groups including NGOs, local communities, researchers and government agencies. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  | X |  |  |  |  | PM: Armenia faced some frequent changes in government in 2018-2019. However, political situation is stable |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; however, the situation requires monitoring and flexibility |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | X |  |  |  |  |  | PM: At PPG phase all pilot sites were selected in the way to ensure their accessibility the whole year around | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: Government of Armenia at national and local levels supports the project, local communities actively participates in the project activities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: Gap exists in national technical expertise in market and certification area which is filled by expertise provided by Bioversity’s international expert. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree. Project should continue to focus on transferring capacities locally to increase the project impacts’ sustainability |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- |
| L | L | L | Armenia faced some frequent changes in government in 2018-2019. However, the political situation appears to be stable. The established robust platform for consultation and dialogue with all groups of stakeholders supported the project team to flexibly and successfully implement the project’s activities and to contribute to achieving its objectives. |
|  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Add rows if your project has more that 3 key indicators per objective or outcome.

Depending on selected indicator, quantitative or qualitative baseline levels and targets could be used (see Glossary included as Annex 1).

Many projects did not identify Mid-term targets at the design stage therefore this column should only be filled if relevant.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). See Annex 2 which contains GEF definitions.

Add rows if your project has more than 4 objective-level indicators. Same applies for the number of outcome-level indicators.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.