UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 5367 |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | PCB Reduction in Cameroon through the use of local expertise and the development of national capacities |  |  |
| Duration months | Planned |  | 60 |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |  |  |
| Executing Agency(ies) |  |  | Ministry of Environment, Protection of Nature and Sustainable Development (MINEPDED), Department of Standards and Control |  |  |
| Names of Other Project Partners |  |  | ENEO (formerly AES Sonel) – Electrical Facility); CREPD; PAN Environmental Control Centre; ENSAI (Laboratory); SABC; AFAIRD; Foncham International Limited. |  |  |
| Project Type |  |  | FSP |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | AFR |  |  |
| Names of Beneficiary Countries |  |  | Cameroon |  |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |  |
| GEF Focal Area(s) |  |  | POPs |  |  |
| UNDAF linkages |  |  | Strategic pillar No. 2: Health and nutrition |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Good health and well-being (SDG3) Clean and affordable energy (SDG7), Measures to combat climate change (SDG13) |  |  |
| GEF financing amount |  |  | 3000000 |  |  |
| Co-financing amount |  |  | 13345622 |  |  |
| Date of CEO Endorsement |  |  | 16/10/2015 |  |  |
| Start of Implementation |  |  | 17/03/2016 |  |  |
| Date of first disbursement |  |  | 12/05/2016 |  |  |
| Total disbursement as of 30 June |  |  | 1,033,494 |  |  |
| Total expenditure as of 30 June |  |  | 828,404 |  |  |
| Expected Mid-Term Date |  |  | 2020Q1 |  |  |
| Completion Date |  | Planned | 16/03/2021 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  |  |  |  |
| Expected Financial Closure Date |  |  |  |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Sub-programme(s) Chemicals and Health Subprogramme | Specify the relevant Expected Accomplishment(s) & Indicator(s) "a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM (ii) Increase in the number of private companies/industries that have developed or implemented a strategy or specific actions on sound chemicals management using UNEP analysis or guidance50 a(iii) Increase in the number of civil society organizations that have undertaken action on improving chemicals management using UNEP analysis or guidance51 |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] PoW indicator a(i): National Governmental Agencies and Universities in Cameroon have implemented activities for deleting, managing PCBs and monitoring their impact on the environment and human health. PoW indicator a(ii): Private companies and laboratories have partnered with the Project Executing Agency to support activities. PoW indicator a(iii): Five NGOs have been identified and trained on the methodology to conduct sensitization on PCB risks and management |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. Health and nutrition: The project has; - Elaborated guidelines on the ESM of PCBs throughout their life cycle. These guidelines, if properly used, contribute significantly to the protection of the environment and human health; - Conducted a national PCB inventory and analysed collected samples in light of their final disposal where results are positive for PCBs; - Developed a regulatory framework for ESM of PCBs throughout their lifecycle [Section to be shared with Monitoring Unit within PPD] |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Good health and well-being (SDG3): The project has; - Elaborated guidelines on the ESM of PCBs throughout their life cycle. These guidelines, if properly used, contribute significantly to the protection of the environment and human health; - Conducted a national PCB inventory and analysed collected samples in light of their final disposal where results are positive for PCBs; - Developed a regulatory framework for ESM of PCBs throughout their lifecycle Clean and affordable energy (SDG7). - Some PCB Holders have bought transformers that are PCB-free. When these will be put in use, it will contribute towards the production of clean, efficient and affordable energy. Measures to combat climate change (SDG13). - The project is in the course of conducting a study on CO2 emissions - Replacing of old PCB transformers with new PCB-free transformers will reduce Carbon emissions. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2ndPIR | 3rdPIR | … PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS | MS |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. Output1(86%): -We could not attain 100% due to the fact that other activities continue in the following years of the project; - The import/export system proved very complicated since we had no reference in other countries having already developed such a system which is operational; - Import/export control system developed but needs to be upgraded to take into account the variance of the customs system and the GUCE (guichet unique des operations du commerce exterieur), the training workshop of customs officers will be conducted in year 3 (Contract for the training signed) - The National Regulation on PCBs (decree) is adopted and signed by the Prime-Minister, Three additional texts will be developed in accordance with the PCB decree (item not taken into account in the project document and thus not budgeted for). Output2(88%): - The GIS database has been developed and the filling of database are in course Training workshop of PCB holders and investigators conducted. - Training of the administrator and the relevant staff has been done and training will continue when the application is updated - Inventory of disused transformers has already been conducted - Inventory of in-use transformers has been conducted except for Two Regions - Analysis of PCB contaminated oil and PCB contaminated soil has been done by L2000 DX and the results are available. - The analysis of PCB contaminated oil and PCB contaminated soil samples of the second phase are in course and certain results will be available in late August 2019 - Expert is recruited for Completion of Carbon emission reduction study - Laboratory of ENSAI/University of Ngaoundere is upgraded by new GC and technicians trained on the use of GC and the analysis of PCBs. - NEG trained on all aspects of the life cycle of PCBs. The 7 training sessions were organised over a period of 5 days of intense training. - The Five guideline documents are available Output3(54.28%): - The analysis of PCB contaminated oil and soil by L2000 have been conducted and the results are available. The analysis of PCB contaminated oil and soil samples during the second phase by GC are in course - the inventory of two regions is pending - tender for the selection of consultant for assessment of PCB contaminated sites launch - 7 contaminated sites were identified during the national PCB inventory - Construction of the PCB temporary storage facility completed - TOR for the recruitment of a national company for the centralization of disused PCB transformer is being finalized - Draft of tender for exportation of 200 tons of PCB equipment for disposal available - Sampling protocols for in-service and decommissioned transformers available - tender for the recruitment of consultant in charge to develop PCB decontamination options launch Output4(94.16%): - document of national awareness needs assessment available - Document of a national awareness strategy available - PCB Project Facebook page created and regularly updated - Awareness raising materials developed and produced - Sensitization stakeholder and PCB holders conducted - Sensitization of public by mass media - The sensitization events and workshop conducted - 5 NGOs have been identified and trained on the methodology to conduct sensitization on PCB risks and management |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS | MS |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. 2017 - Inventory of PCB transformers that are out of use - All other activities conducted in the first year of the project are aimed towards achieving the stated GEF strategic priorities and targets, such as; - Regulatory framework upgraded /developed and disseminated including Stockholm Convention targets and guidelines for the environmentally sound management of PCBs. - Training program for a National Expert Group on the: new regulatory framework for PCBs. - Import control system (including procurement) for transformers, capacitors and dielectric oil established, and enforced by Customs authorities. - Information system housing inventory and PCB management data operationalized and includes GIS. - National Expert Group formed and trained in all aspects of PCB life cycle - Development of national awareness materials and communication strategy 2018 Output1(86%): -We could not attain 100% due to the fact that other activities continue in the following years of the project; -The import/export system proved very complicated since we had no reference in other countries having already developed such a system which is operational; -Import/export control system developed but training of customs officers has not yet been conducted (the server of the ministry is being upgraded by the national technician); -The training of customs authorities will be done once the server is upgraded (ToR available); -New regulatory framework (ministerial decree) signed, NEG members trained and 03 guideline documents developed; Output2(72.5%):-Training workshop of PCB holders and investigators on GIS, training of GIS administrator to be done in due course; -Inventory of disused transformers already conducted, inventory of in-use transformers has been launched; -Difficulty to find an expert for Carbon emission reduction study, ToR available; -Laboratory Equipment purchased and will arrive at the Yaoundé airport in July and technicians’ training workshop will be done after their reception; -NEG trained on all aspects of the life cycle of PCBs, 05 guideline documents available; Output3(33.75%):-We have launched the procedure of elimination of disused PCB transformers in 2018; -ToR of national PCB inventory available, national inventory launchedand will also identify potential PCB contaminated sites (ToR for the selection of consultant available); -ENEO has already carried out her analysis of disused equipment, samples of other holders will be analysed by the project in due course; -Building of PCB temporary storage facility completed - Draft of tender for the export of 200 tons of PCB equipment for disposal available; - Document of sampling protocols for in-service and decommissioned transformersavailable; -Difficulty to find an expert to conduct the activity of formulation of PCB decontamination options, ToR available Output4(80%):-Project face book page available; -Awareness raising materials developed and being produced; -5 NGOs have been identified, however their capacity building is required since they only have knowledge on Chemicals in general and not PCBs in particular; -NGO already identified and recruited for execution of national PCB awareness implementation plan. 2019 Output 1 Three additional texts are developing in accordance with the PCB decree (item not taken into account in the project document and thus not budgeted for) Output 2: - Training workshop of PCB holders and investigators conducted. - Training of the administrator and the relevant staff has been done and training will continue when the application is updated. - Inventory of in-use transformers has been conducted except for Two Regions. - Analysis of PCB contaminated oil and PCB contaminated soil has been done by L2000 DX and the results are available. - The analysis of PCB contaminated oil and PCB contaminated soil samples of the second phase are in course and certain results will be available in late August 2019 - Laboratory of ENSAI/University of Ngaoundere is upgraded by new GC and technicians trained on the use of GC and the analysis of PCBs. - The Five guideline documents are available Output 3 - The analysis of PCB contaminated oil and soil by L2000DX have been conducted and the results are available. - The analysis of PCB contaminated oil and soil samples during the second phase by GC are completed - 7 contaminated sites were identified during the national PCB inventory - TOR for the recruitment of a national company for the centralization of disused PCB transformer is being finalized Output 4 - Awareness raising materials developed and produced; - Sensitization of public, stakes holders and PCB holders conducted - Identified NGOs have been trained on the methodology to conduct sensitization on PCB risks and management - Sensitization of public by mass media, stakeholders and PCB holders conducted - The sensitization events and workshop |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M | M | M |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] Key stakeholders have been identified in the public and private sectors, as well as in the community. In the public sector, these include stakeholders from: the Ministry of Environment, Protection of Nature and Sustainable Development, Ministry of Industry, Mining and Technological Development, Ministry of Health, Ministry of Labour and Social Security, Ministry of Energy and Water, Ministry of Justice, Ministry of Research and Scientific Innovation, and the Department of Customs. These public sector stakeholders will be well consulted during project preparation on the feasibility of the project design, and their potential respective contributions to the project outcomes. Key industry stakeholders include personnel and management staff from the following companies: ENEO, CIMENCAM, ASECNA, ADC, ALUCAM, SONARA, CAMTEL, and GICAM. As key owners of PCB contaminated equipment, the cooperation of these private sector partners is essential to the project's success. As such consultation with these partners during the development of Cameroon's NIP. Consultation continued throughout project development, to ensure that the private sector understands the goals of the project, the dangers posed by PCBs, the planned regulatory developments in Cameroon, and is supportive and cooperative. The following research institutions have also been identified and will be consulted during the project development: ENSAI, Centre Pasteur du Cameroun, University of Yaoundé I, HYDRAC, and the BOCOM analytical laboratories.ENSAI will contribute to the project through the laboratory analysis of mineral oil from in-service transformer and other samples. The Research and Education Centre for Development (CREPD) is a Cameroon based NGO that aims to bridge the gap between science and action in Cameroon and sub-Sahara Africa. CREPD’s activities are focused on health and environmental issues in collaboration with government, industry, and non-governmental organizations. CREPD has been involved in successful projects on sound management of persistent toxic chemicals (mercury, lead, cadmium) in products including cosmetics, batteries, leather, and on POPs. CREPD will be a key partner in executing this project. The Association of Honest Africa Women for the Research and Development (AFAIRD, Association des Femmes Africaines Intègres pour la recherche et le development) will collaborate with the project to ensure that women’s needs and roles are addressed by the project, The Pan Environmental Control Centre, is the young waste management enterprise, accredited by the Ministry of Environment and experienced in PCB management. The Centre has many partnerships in France, and in the USA involved in PCB management. It is envisaged that the Centre will be a key partner in managing the PCB waste generated during the project, including the provision of a transformer storage site for dechlorination. FONCHAM International, an NGO will contribute in providing other options for PCB treatment techniques that are environmentally friendly, awareness raising in POPs and also, it has a very good mastery in the management of other POPs in the Waste electrical, electronic equipment. All the public and private administrations, the analysis laboratories identified in the PPG phase as well as the PCB holders are engaged in the realization of the project. All the stakeholders are either members of the PSC or the NEG. Some stakeholders realize certain project activities to accompany the project coordination unit. In addition, new NGOs have been identified and are committed to supporting the project with communication activities. The PCB holders accompanied the project in carrying out the inventory and ENSAI laboratory make analysis of oils and soils sample during the inventory. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. In terms of gender, in daily life, men, women, and children are exposed to different kinds of chemicals in varying concentrations. Biological factors (notably size and physiological differences between women and men and between adults and children) influence susceptibility to health damage from exposure to toxic chemicals. Social factors, primarily gender-determined occupational roles, also have an impact on the level and frequency of exposure to toxic chemicals, the kinds of chemicals encountered, and the resulting impacts on human health. These gender dimensions need to be reflected at both site- and policy-level interventions for sound chemical management (for reference see UNDP (2007): Gender Mainstreaming (Key driver of development in environment and energy) Chemicals Management. Women and children are often exposed through secondary exposure from vectors such as washing of contaminated laundry and casual contact with family members themselves directly exposed to PCB. Linked to this point the electrical sector in the region predominantly employs men as engineers and maintenance personnel. As a result the primary social groups exposed to PCB impacts are men. These can manifest in terms of immediate health impacts related to direct exposure and in terms of negative impacts on make fertility and other long term health impacts related to endocrine disruption. Women were involved as investigators in the national PCB inventory, they are members of the NEG, some served as national consultants and women are also represented as members of the project coordination unit. [section will be uploaded into the GEF Portal] |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval - A good number of university students have used PCBs as a theme for their dissertations - Most of the PCB inventory investigators were university students and they gained a lot of knowledge from the training they received on how to conduct the inventory and use the GIS database - A series of other capacity building were conducted during the training of: - NEG on management of PCBs throughout their lifecyle - NEG on regulatory framework on PCBs - PCB holders on the PCB GIS database and PCB import/export control system [section will be uploaded into the GEF Portal] |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. - Development of a PCB Geographic Information System (GIS) database for traceability, and PCB import/export control system - Signing of a partnership agreement between the Ministry of Environment and the University of Ngaoundéré under the framework of building national capacities in the form of upgrading the ENSAI laboratory and training laboratory technicians on the use of GC for PCB analysis - Mass media campaign on the management of PCBs over the national radio station in French, English, and popular local dialects - Realization of a documentary on the PCB project and various activities carried out with the aim of informing the general public about the project - High collaboration and engagement of stakeholders in their willingness to put their PCB transformers out of service so as to benefit from their final disposal free of charge by the project - Construction of a PCB temporary storage facility (TSF) for the centralisation of all PCB equipment for disposal abroad [section to be shared with communication division/ GEF communication] |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision)approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Increase national capacity to identify, manage and dispose of existing PCBs in Cameroon in an environmentally responsible manner in order to meet Stockholm Convention country commitments and minimize the risks to the population and the environment. | 1.Establishment of the in-the-country capacity to deal with PCB contaminated electrical equipment and other related material; | Regulatory review completed as part of NIP process | Year 1: - Trained cadre of individuals managing full life-cycle of PCBs - regulatory review - development of 3 guidelines on PCB management |  | - Reports of training workshop - Signed regulatory - guidelines document available | S |
|  | 2.Functioning import control system including: labeling using GHS; updating of PCB database; and PCB-free certificate. | Preliminary inventory complete, 3781 pieces of equipment identified but yet to be tested. | Year 1: - development of import/export control system - development of GIS database Year 2: - conduction of national PCB inventory - Analysis of PCB samples Year 3: - Analysis of PCB samples - labelling of PCB equipments - recording of the GIS database |  | - import/export control system and GIS database operational and online - National PCB inventory report and analyses results available - All PCB equipment and areas containing such labelled - Some data already recorded in the PCB GIS database | HS |
|  | 3.Trained cadre of individuals managing full life cycle of PCBs. | NEG established comprising of local environment, health, customs staff, and members of the private sector | Year 1: training of NEG of the ESM of PCB throughout their lifecycle | - Training of customs officers, environmental inspectors and NEG | - Training report of NEG available | S |
|  | 4.Analytical laboratory equipped with staff and infrastructure for PCB analysis. |  | Year 2: Analytical laboratory equipped with staff and infrastructure for PCB analysis | - Continue using the laboratory to conduct similar analyses | - Laboratory upgraded and analyses carried out | MS |
|  | 5. No. of PCB contaminated materials exported for treatment, and amount of equipment reclaimed or disposed of locally. | Preliminary inventory complete, 3781 pieces of equipment identified but yet to be tested. | Year 2: - Construction of a PCB temporary storage facility Year 3: - Call for tender for PCB decontamination options - Elaboration of call for tender for centralisation of PCB equipment | - Phase-out of pure PCB equipment and decontamination of PCB contaminated equipment - Risk management of PCB contaminated sites | - PCB temporary storage facility completed | MS |
|  | 6.Vulnerable communities informed of PCB risks and taking actions to protect themselves | Some awareness materials developed for: Regional Approach to Environmentally Sound Management of PCB Liquid Wastes and Transformers and Capacitors Containing PCBs | Year 1: - Assessment of awareness and communication needs - development of awareness, information and communication strategy - Identification of 5 NGOs to implement awareness, information and communication strategy Year 2: - Producing of awareness tools/materials - sensitization of PCB holders and public by mass medias |  | - awareness, information and communication strategy available - 5 NGOs identified and trained - Awareness raising materials produced and partly diffused - PCB holders sensitized | MS |
| Outcome 1: Shift in regulatory framework allows Cameroon to facilitate the implementation of the Stockholm Convention | 1 Legal framework includes all the impacts of PCBs: health, environment, worker protection; and traceability system. | Regulatory review completed as part of NIP process | Year 1: Regulatory framework available and adoption |  | - PCB decree and regulatory framework signed | S |
|  | 2. Functioning import control system including: labeling using GHS; updating of PCB database; and PCB-free certificate. | No import control system NEG established comprising of local environment, health, customs staff, and members of the private sector | import control system developed |  | Import/export control system online | S |
| Outcome 2: Technical and administrative capacities for the sound management of PCBs reinforced and allows Cameroon to develop and implement a sustainable and participatory PCB management /elimination plan decreasing the risk to humans and the environment | 1. Trained cadre of individuals managing full life cycle of PCBs. | Preliminary inventory complete | Year 1: Trained cadre of individuals managing full life-cycle of PCBs |  | Report | S |
|  | 2. Analytical laboratory equipped with staff and infrastructure for PCB analysis. | Preliminary review of laboratories. Discussions and consultations with ENSAI. | Year 2: Analytical laboratory equipped with staff and infrastructure for PCB analysis. |  | Report | MS |
|  | 3. Quantification of the reduction of carbon emissions, and therefore the climate change mitigation benefits, through replacement of PCBs, and recovery of metals. | No management plans in place, nor studies on potential reductions of carbon emissions. | Year 3: - Study quantifying the reduction of carbon emissions in progress - Calculation of energy efficiency - Development of a national decontamination and disposal plan |  | Report Report | MS |
| Outcome 3 Sound management and elimination of contaminated oils and equipment drastically reduce the risk of PCB contamination in the population and the environment | Risk to human health and the environment mitigated through export and disposal of contaminated oils, and decontamination of equipment | Preliminary inventory complete, 3781 pieces of equipment identified but yet to be tested | - PCB Temporary Storage Facility constructed -National PCB Inventory conducted -Calls for tender for PCB decontamination options launched - Draft tender for centralisation of PCB equipment elaborated | Risk to human health and the environment mitigated through export and disposal of 200 tons of contaminated oils, and decontamination of 1600 tons of equipment | - Inventory Report | MS |
| Outcome 4 Key stakeholders and the broader community well informed and included in the sound management of PCB in Cameroon allows to better understand the problem and to take actions to protect the population and the environment | Needs assessment identifies awareness needs | Some awareness materials developed for: Regional Approach to Environmentally Sound Management of PCB Liquid Wastes and Transformers and Capacitors Containing PCBs | Year 1: - Assessment of awareness and communication needs - development of awareness, information and communication strategy - Identification of 5 NGOs to implement awareness, information and communication strategy Year 2: - Producing of awareness tools/materials |  | Report - awareness, information and communication strategy available - 5 NGOs identified and trained - Awareness raising materials produced and partly diffused - PCB holders sensitized | S |
|  | Vulnerable communities informed of PCB risks and taking actions to protect themselves | CREPD and AFAIRD identified as interested and qualified NGOs, to assist in project execution. | - sensitization of PCB holders and public by mass medias | >200 vulnerable people attend sensitization workshops, and initiate actions to protect themselves from PCBs |  | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The project has made progress in achieving the objective albeit a few delays in the laboratory capacity reinforcement and finalisation of the inventories |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - Some activities not budgeted for in the project document ( calculation of energy efficiency, disposal plan, development of 3 ministerial orders on PCB decree, etc); - Low budget for awareness raising; - Low budget for national PCB inventory; - Unsuccessful funds transfer leading to the loss of over 10 months of project time. |  |
| on stakeholder engagement | - |  |
| on gender actions | - |  |
| on safeguards | - Identification of the weight of certain PCB equipment |  |
| on delivering GEF Core Indicators | - |  |
| on delivering of PoW EA | - Availability of experts for certain activities |  |
| on sustainability of results | - The project does not take into account the restoration of PCB contaminated sites; |  |
| others | - No leave for project coordination unit |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: (copy & paste from approved Results Framework) [activities may be included for reference, but the rating should focus on output delivery] 1.1: Regulatory framework upgraded /developed and disseminated includes Stockholm Convention targets and guidelines for the environmentally sound management (ESM) of PCBs 1.2: Training of National Expert Group, on new regulatory framework for PCBs 1.3 Import and export control system (including procurement and sale) for transformers, capacitors and dielectric oil established, and enforced by Customs authorities | May 2017 Mai 2017 Mars 2021 | 100% 100% 65% | 100% 100% 65% | -Training of customs officers and environmental inspectors will be conducted in a span of several years -Lack of funds during the previous year contributed in slowing down this activity | S |
| Output 2: [activities may be included for reference, but the rating should focus on output delivery] 2.1 Information system housing inventory and PCB management data operationalized and includes GIS 2.2 Feasibility of economic, or market-based instruments to promote ESM and disposal for PCBs evaluated, and included in the PCB management plan 2.3 Analytical and laboratory capacity strengthened through equipment upgrades, staff training and intercalibration studies at ENSAI 2.4 National Expert Group formed and trained in all aspects of PCB life cycle 2.5 Local guidelines and standards developed for the ESM of PCBs (oil and contaminated equipment) | May 2017 Year 3 Year 3 Year 1 Year 2 | 100% 17% 100% 100% 80% | 50% NA NA 100% | Filling of the database is in course -Feasibility studies for the calculation of energy efficiency of the elimination plan is in progress -Lack of funds during the previous year contributed in slowing down this activity -2 activities were not budgeted for (calculation of energy efficiency and reduction of CO2) | MS |
| Output 3: 3.1 National PCB inventory, including contaminated site assessments, improved 3.2 PCB contaminated oil and contaminated equipment securely packed and transported to centralized collection locations 3.3 Export of PCB contaminated equipment and oils in accordance with Basel Convention 3.4 Transformers are tested, and those deemed contaminated are decontaminated and recommissioned for use; and PCB contaminated oil dechlorinated | Year 3 Year 3 Year 3 Year 5 | 33,75% 60% 10% 40% | 54.28% 60% 10% 62% | -This englobes many activities that are still on going Construction of the PCB temporary storage facility completed TOR for the recruitment of a national company for the centralization of disused PCB transformer is being finalized Waiting for the centralization operation -Failure to declare an important amount of transformers by certain PCB holders led to the delay in the completion of this activity -Laborous procedures for the acquisition of consumables of the Gaseous phase chromatography -Draft of tender available | MS |
| Output 4: 4.1 Development of national awareness materials (including audio visual materials 4.2 Identification of NGOs to assist with dissemination of information and communication materials 4.3 National PCB awareness strategy implemented and includes civil society, local communities and tribes. | Year 2 Year 1 Year 4 | 100% 125% 100% | 100% NA 100% | -5 NGOs were identified instead of 4 Sensitization of PCB holders Sensitization of public by media | S |

Overall project implementation progress (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Some key milestones achieved this year which will allow more progress next year |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Guidelines and standards are available, but not adhered to. | The new regulatory framework will take this into account to render it obligatory | Government | From date of publication |
| Project identifies more PCBs than are budgeted for | Additional funds will be sought from UNEP/GEF. | UNEP/GEF | End of year 4 (dec 2020) |
| Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment | Assistance provided to such holders | UNEP/GEF Government Stakeholders | End of year 3 (feb 2020) |
| Minor budget reallocation needed | budget needs reallocation | TM and PM | MTR/MTE |
| Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Sensitisation will be intensified to achieve project objective | Government Holders | Throughout the project |
| the decree signed provides three additional orders, yet the project did not provide funds for this purpose | budget needs reallocation | TM and PM | Sep 2019 |
| absence of nameplate of some PCB transformers that do not allow for the mass of equipment to be read | weigh transformers without a nameplate during the centralization phase | Government Holders | Dec 2019 |
| difficulty of having experts for carrying out certain activities | make available to the coordination a list of experts or proposals from the publication sites of calls for tenders | UNEP | Throughout the project |
| the inventories were not conducted in the national electricity company in two regions of the country because of insecurity | wait for calm to return and provide funds for this inventory phase | Government Holders | Until when the situation is resolved and funds made available |
| the PCB temporary storage facility is located 30 km from the insecure area, it could have incursions during centralization | reinforce security around the PCB temporary storage facility | Government | During centralisation and disposal phase |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Project identifies more PCBs than are budgeted for | The project has been designed around maximizing cost effectiveness, particularly in relation to disposal methods, and the need to minimize the quantities of equipment exported for disposal, and to maximize the quantities of equipment disposed of in Cameroon. Locally relevant disposal options have been studied, including the potential for retrofilling, dechlorination, decontamination of non-porous metallic components. According to the project disposal plan only 200 tons of PCB equipment (ie with PCB concentrations >2,000ppm) will be disposed of internationally. If the amount of PCB equipment identified is >200 tons additional co-finance will be sought from PCB holders. | - PCB holders are encouraged to surrender their PCB equipment for disposal - PCB holders are also encouraged to include the replacement and disposal of their PCB equipment in their financial budget. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: H |
|  |  |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
|  |  |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| ESERN [add cells as appropriate to capture all Medium and High Risks] |  |  |  |
| Overall Risk Rating Project Manager |  |  | H |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
|  |  | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below |
| Guidelines and standards are available, but not adhered to. | Guidelines and standards are available, but not adhered to. | - The risk ranking has not changed |
| Project identifies more PCBs than are budgeted for | Project identifies more PCBs than are budgeted for | - The PCB inventory confirmed that there are more PCBs than budgeted for. This shows that the risk is relatively high. |
| Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment | Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment | - The inventory revealed most of the PCB equipment still in use is due to the fact that Holders lack funds to replace them. High risk |
| Minor budget reallocation needed | Minor budget reallocation needed | - In both 2018 and 2019, there was need for budget reallocation for certain activities |
| Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | - Lack of funds to replace PCB equipment by Holders - Prolonged period of lack of funds by the project due to Funds transfer failures, leading to the postponement of activities for a period of over 10 months - Certain project activities not budgeted for in the project document |
|  | the decree signed provides three additional orders, yet the project did not provide funds for this purpose | - If these 3 ministerial orders are not elaborated, it can compromise the attainment of project objectives |
|  | absence of name plate of some PCB transformers that do not allow for the weight of the equipment to be known | - This makes it difficult to know the actual weight of dielectric fluid and that of the equipment. |
|  | difficulty of having experts for carrying out certain activities | - Delays in the realisation of such activities |
|  | the inventories were not conducted in the national electricity company in two regions of the country because of insecurity | - The project objectives will not be realised 100% - The national disposal plan will not be exhaustive |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems |  |  |  |  |  |  | PM : Team work with high team spirit; individuals readily available and engaged | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR |  |  |  |  |  |  | PM : The steering committee and NEG is constituted of PCB holders and other administrations who are in high collaboration with each other and committed to the speedy realisation of the project objective | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment |  |  |  |  |  |  | PM: Excellent working relations | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  |  |  |  |  |  | PM: The project team and PCB holders are very keen on the rapid elimination of PCB equipment | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  |  |  |  |  |  | PM: some PCB owners who were not initially financial partners of the project have agreed to be co-financers by carrying out activities that can be capitalized as part of the co-financing of the project | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  |  |  |  |  |  | PM: Poor budget allocation: - budget allocation by project component / activity does not reflect budget allocation by calendar / year; - budget needs reallocation - some activities are under-budgeted for - some activities are NOT budgeted for | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  |  |  |  |  |  | PM: A project accountant is needed, but the project did not make provisions for that | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  |  |  |  |  |  | PM: Positive | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  |  |  |  |  |  | PM: Positive | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  |  |  |  |  |  | PM: Stakeholders and practitioners have a good understanding of the project. The public has been sensitised by media on a low scale. However, the general public still needs more sensitisation | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  |  |  |  |  |  | PM: The project has put in place a state-of-the-art laboratory and PCB temporary storage facility. The project envisages to put in place a decontamination device | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  |  |  |  |  |  | PM: The government is motivated by the objective of the project to rid Cameroon of PCBs | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  |  |  |  |  | PM: , the project is receiving enough support from administrations | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  |  |  |  |  |  | PM: Cameroon has well defined seasons (dry and rainy), thus making it easy to curb climatic risks | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  |  |  |  |  |  | PM: - The crisis in the north west and south west regions has a negative impact on the activities to be carried out in these regions . - In addition, the National electricity company is recording high financial losses and hence is unable to honour its co financing engagements |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  |  |  |  |  |  | PM: Robust national capacity building initiatives adopted and conducted |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| Substantial | Guidelines and standards are available, but not adhered to. | - PCBs are not sustainably managed in Cameroon | The new regulatory framework will take this into account to render it obligatory Ministerial Orders will be signed | Government | From date of publication |
| Substantial | The inventory of PCB equipment of National electricity company not conducted in north west and south west regions | - Date line not respected | wait for calm to return and provide funds for this inventory phase | - Government - Holders - UNEP - GEF | Until when the situation is resolved and funds made available |
| Substantial | Difficulty to find experts for certain consultancies | - Activities concerned will not be executed - Project objectives not met | make available to the coordination a list of experts or proposals from the publication sites of calls for tenders | UNEP | Throughout the project |
| High | Project identifies more PCBs than are budgeted for | - local structures not having adequate funds for PCB elimination will be affected | Additional funds will be sought from UNEP/GEF. | UNEP/GEF | End of year 4 (dec 2020) |
| High | Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment | - PCBs risk not being eliminated - local companies may be forced to close down | Assistance provided to such holders | UNEP/GEF Government Stakeholders | End of year 3 (feb 2020) |
| substantial | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | - The population and holders will not be willing to cooperate or participate | Sensitisation will be intensified to achieve project objective More funds required | Government Holders UNEP/GEF | Throughout the project |
| substantial | Minor budget reallocation needed | -activities will be delayed | Budget needs reallocation | TM and PM | MTR / MTE |
| High | the decree signed provides three additional orders, yet the project did not provide funds for this purpose | - Objectives of the project will not be met | Budget needs reallocation | TM and PM | Sept 2019 |
| substantial | absence of nameplate of some PCB transformers that do not allow for the mass of equipment to be read | - Actual weight of dielectric fluid and equipment not known and may influence centralisation and final disposal | weigh transformers without a nameplate during the centralization phase | Government Holders | Dec 2019 |
| low | the PCB temporary storage facility is located 30 km from the insecure area, it could have incursions during centralization | - Poor security of equipment | reinforce security around the PCB temporary storage facility | Government | During centralisation and disposal phase |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| Delays in national adoption of revised regulatory framework | NA | National regulation signed |
| Limited time given by the new national PCB regulation to conduct inventory | Limited time given by the new national PCB regulation to conduct inventory |  |
| Difficulty to find experts for certain consultancies | Difficulty to find experts for certain consultancies |  |
| Key member of national expert group unavailable for training | Key member of national expert group unavailable for training | Certain members of NEG are regularly change by their company |
| Inspections not completed as inspectors are busy with other duties Changes in personnel, means loss of trained Customs workers | Inspections not completed as inspectors are busy with other duties Changes in personnel, means loss of trained Customs workers |  |
| Database, once established is not updated | Database, once established is not updated |  |
| Holders do not complete management plans | Holders do not complete management plans | New regulation has taken account |
| Costs of required laboratory upgrades are greater than the available budget | NA | laboratory upgrades and analysis done |
| Guidelines and standards are available, but not adhered to. | Guidelines and standards are available, but not adhered to |  |
| Access to sites not provided as site is on privately owned land Exposure to PCBs of communities residing close to sites. | Access to sites not provided as site is on privately owned land |  |
| Accident, causing spillage during transport | Accident, causing spillage during transport |  |
| Transformer holders not willing to grant access to their facilities for the identification of target transformers. | lack of logistics facilities to conduct field raids as part of the inventory |  |
| More than 10 target groups are identified. |  | Sensitization conducted |
| Suitable and capable NGO cannot be identified. NGO does not have experience in PCB management. | NA | 5 NGOs are identified and trained |
| Lack of understanding by at risk communities | Lack of understanding by at risk |  |
| Project identifies more PCBs than are budgeted for | Project identifies more PCBs than are budgeted for |  |
| Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment | Delays in releasing PCB equipment for elimination by holders due to lack of funds to purchase PCB free equipment |  |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.