FAO GEF PROJECT DOCUMENT

| Project Title: | Strengthening agro-ecosystems’ adaptive capacity to climate change in the Lake Chad Basin (Lac, Kanem, Bahr El Ghazal, and part of the Hadjer-Lamis Province) |
| --- | --- |
| Project symbol: | GCP /CHD/040/LDF |
| Recipient Country(ies): | Chad |
| Executing partner(s): | Ministère de la Production de l’Irrigation et des Equipements Agricoles (MPIEA) is the principal executing partner, which will closely work with three Ministries (Ministry in charge of Livestock, Environment and Land Planning). |
| Expected EOD (Starting Date): | 2020 |
| Expected NTE (End Date): | 2024 |
| Contribution to FAO’s Strategic Framework: (Indicate as appropriate) | SO2: Make agriculture, forestry and fisheries more productive and sustainable; SO5: Increase the resilience of livelihoods to threats and crises. Country Programming Framework (2017 - 2021) priorities : 1. The development of sustainable agricultural value chains addressing the challenge of sustainable food production in the sectors of crops, livestock and forestry. 3. The sustainable management and use of natural resources to build community, institutional and household resilience. |
| Contribution to GEF Focal Area Strategic Objectives and Programs: | CCA-1 Reduce vulnerability and increase resilience through innovation and technology transfer for climate change adaptation CCA-2 Mainstream climate change adaptation and resilience for systemic impact CCA-3 Foster enabling conditions for effective and integrated climate change adaptation |
| Environmental and Social Risk Classification | low risk x moderate risk high risk |
| Gender Marker | G0 G1 G2a x G2b |
| Total Budget: | TOTAL: USD 22,635,913 GEF: USD 4,050,913 Co-financing: USD 18,585,000 |
| Executive Summary Chad is a vast, poor land-locked country of 1,284,000 km2 in Central Africa, two thirds of which is located in the Lake Chad Basin. The population numbers about 15 million people, 75% of whom live in rural areas and largely depend on agro-sylvo pastoral and fisheries activities. Chad is considered to be one of the most vulnerable countries to climate change in Africa. At the same time, it receives less international climate change funding in comparison to other Sahelian countries due to weak governance at the provincial level and a risky environment. Moreover, the country is surrounded by severe conflicts worsening the vulnerability context for rural communities and the State, with Boko Haram terrorist groups severely hampering socio-economic development. The impacts of climate change are important on the Lake Chad Basin and its agro-sylvo-pastoral and freshwater ecosystems and on the security context. The National Adaptation Programme of Action assessments revealed a number of major problems, including a significant decline in the flow of the Logone and Chari river systems feeding Lake Chad, resulting in the shrinkage of the lake, a decrease in groundwater recharge, and degradation of vegetation cover and soil in the watershed. These conditions create negative impacts on agricultural production and exacerbate inter-community conflicts over natural resources. The overall objective of the project is “to increase the resilience of agro-sylvo-pastoral and freshwater production systems to climate change in four provinces of the Lake Chad Basin - Bahr El Ghazal (BEG), Hadjer Lamis, Kanem and Lac”. The main results expected from the project are: - Improved local governance through dialogue, planning and co-ordination in order to mobilize funds for climate change adaptation measures. - Improved resilience of ecosystems to climate change through the development of pastoral and agricultural areas, with improved access to water, energy and restoration of degraded lands. - A more effective extension system through multidisciplinary teams composed of three decentralized technical services (Agriculture, Livestock and Environment) to promote innovative models and practices adapted to climate change. - An increase in agricultural and fodder production and market development for sesame, spirulina, dried vegetable products, fodder and other livestock feed with strong participation of women and youth. - Enhanced political dialogue between the local and national levels, especially on land tenure issues, in order to improve land use rules and regulations and their implementation the provinces. The project will be implemented over a period of 48 months (4 years). The overall resources required for this project amount to USD 22,635,913. Of this amount, USD 4,050,913 are requested from the GEF Least Developed Countries Fund (LDCF), while USD 18,585,000 in co-financing has been committed by the Chadian government from projects financed by the African Development Bank (AfDB) and the International Fund for Agricultural Development (IFAD). The Ministry of Agriculture will have the overall execution and technical responsibility for the project, working closely with three Ministries in charge of Livestock, Environment and Land Planning. The project will also work with local level institutions including the High Council of Autonomous Communities and Traditional Chiefdoms (HC-CACT), Provincial Action Committees (PACs), Producers’ and agropastoralists’ federations and other NGOs. FAO will serve as the GEF agency, providing oversight and technical assistance to the execution of the project. |  |

TABLE OF CONTENTS

SECTION 1 – PROJECT JUSTIFICATION	5

1.1	 PROJECT BACKGROUND	7

1.1.1	National Context	7

1.1.2	Policy and Institutional Frameworks	9

1.1.3	Project area	14

1.2	 CURRENT SITUATION	20

1.2.1	Main environmental threats and drivers	20

1.2.2	Baseline initiatives	21

1.2.3	Remaining barriers to tackle	27

1.3	THE GEF ALTERNATIVE	30

1.3.1.	The Project strategy	30

1.3.2.	Project objectives, outcomes and outputs	32

1.3.3.	Adaptation benefits	45

1.3.4.	Socio-economic benefits	46

1.4	STAKEHOLDER CONSULTATION AND COMMITMENT	47

1.4.1	Project stakeholders	47

1.4.2	Grievance mechanism	49

1.5	 ALIGNMENT AND STRATEGIC FIT	51

1.6	 COMPARATIVE ADVANTAGES	52

1.7	 KNOWLEDGE MANAGEMENT AND COMMUNICATION	53

1.7.1	Knowledge sharing	53

1.7.2	Lessons learned	55

1.7.3	Communication	57

SECTION 2 – FEASIBILITY	57

2.1 	IMPLEMENTATION ARRANGEMENTS	57

2.2	 FINANCIAL PLANNING AND MANAGEMENT	62

2.3	 RISK MANAGEMENT	62

2.4	 MONITORING & EVALUATION AND REPORTING	64

2.4.1	Monitoring mechanism	64

2.4.2	Reporting	65

2.5 	EVALUATION PROVISIONS	67

2.6 	INFORMATION TECHNOLOGY	67

SECTION 3 – SUSTAINABILITY	68

3.1	CAPACITY BUILDING	68

3.2	FINANCIAL AND ECONOMIC SUSTAINABILITY	68

3.3	ENVIRONMENTAL SUSTAINABILITY	69

3.4	INNOVATION AND SCALE UP	70

3.5	DECENT RURAL JOBS	70

3.6	GENDER EQUALITY	71

3.7	INDIGENOUS PEOPLES	72

APPENDIX I. Logical framework	73

APPENDIX II. Work Plan	78

APPENDIX III. Budget	91

APPENDIX IV. Risk management	92

Section A: Risks to the project	92

Section B. Environmental and social risks from the project	95

APPENDIX V. Stakeholder engagement	97

APPENDIX VI. FAO’s internal roles	100

APPENDIX VII. Financial management	102

ACRONYMS

| ADP | Aquaculture Development Plan |
| --- | --- |
| AfDB | African Development Bank |
| ANADER | National Agency for Rural Development (« Agence Nationale de Développement Rural ») |
| ANGMV | National Agency for the Great Green Wall (« Agence Nationale de la Grande Muraille Verte ») |
| APFS | Agro pastoral Field School |
| APMR | Annual Project Monitoring Report |
| APPRR | Annual Project Progress Review Report |
| CC | Climate Change |
| CCAP | Climate Change Adaptation Plan |
| CNCPRT | Chadian rural producers’ National Dialogue Council (« Conseil National de Concertation des Producteurs Ruraux du Tchad ») |
| CONIFET | Interprofessional Confederation of the Livestock Breeding Sector in Chad (“Confédération Interprofessionnelle de la Filière Elevage au Tchad”) |
| DLP | Delegation of Land Planning |
| DPIA | FAO Investment Center for Africa |
| EU | European Union |
| FAO | Food and Agriculture Organization of the United Nations |
| FAOR | FAO Representation |
| FAO RAF | FAO Regional Office for Africa |
| FE | Final Evaluation |
| FFS | Farmer Field School |
| FOTPAPE | Federation for Fishing and Aquaculture promotion and environnement protection ( Faitière des Organisations Tchadiennes pour la Promotion de la Pêche et de l’Aquaculture). |
| FP | Focal Point |
| FTP | Financial and Technical Partner |
| HC-CACT | High Council of Traditional Chiefdoms (« Haut Conseil des Collectivités Autonomes et des Chefferies Traditionnelles ») |
| IFAD | International Fund for Agricultural Development |
| LBOD | Local Body for Guidance and Decision-making (« Instance Locale d’Orientation et de Décision ») |
| LCB | Lake Chad Basin |
| LCBC | Lake Chad Basin Commission |
| MDG | Millennium Development Goal |
| MEIA | Ministry in charge of Equipment, Irrigation and Agriculture |
| MEWF | Ministry in charge of Environment, Water and Fisheries |
| MFFS | Mother Farmer Field School |
| MLPH | Ministry in charge of Land Planning, Housing Development and Urban Planning |
| NAPA | National Adaptation Plan for Climate Change |
| NAPFD | National Action Program to fight against Desertification |
| NDP | National Development Plan |
| NEAP | National Environmental Action Plan |
| NFNP | National Food and Nutrition Policy |
| NGGWS | National Great Green Wall Strategy |
| NLBDP | National Livestock Breeding Development Plan |
| NLRP | National Land Recovery Plan |
| NPRLWB | National Program for the Restoration of Land, Water and Biodiversity |
| NPRP | National Poverty Reduction Strategy |
| NRM | Natural Resources Management |
| NSBFM | National Strategy for Bush Fire Management |
| NSFCC | National Strategy to fight against Climate Change |
| NTDS | National Territorial Development Scheme |
| NTFP | No-Timber forest product |
| NSPB | National Strategy and Plan for biodiversity |
| NSPS | National Social Protection Strategy |
| NGP | National Gender Policy |
| NGO | Non-Governmental Organization |
| NRM | Natural Resource Management |
| PAC (CPA) | Provincial Action Committee (« Comité Provincial d’Action ») |
| PCCA | Provincial Climate Change Adaptation Plan |
| PPU | Provincial Planning Unit |
| PSC | Project Steering Committee |
| SDG | Sustainable Development Goals |
| SNLCC | National Strategy to Combat Climate Change (« Stratégie Nationale de Lutte contre le Changement Climatique ») |
| UNDP | United Nations Development Program |
| ULP | Local Planning Unit (« Unité locale de planification») |
| VC | Value Chain |
| WSMP | Water and Sanitation Master Plan (« Schéma Directeur de l’Eau et de l’Assainissement ») |

# SECTION 1 – PROJECT JUSTIFICATION

### PROJECT BACKGROUND

### National Context

- Physical Overview. Chad is a vast landlocked country of 1,284,000 km2 populated by 15 million inhabitants with a population growth rate of 3.5% (the 4th highest in the world). Two-thirds of its territory consists of the Lake Chad Basin (LCB) which covers an area of ​​about 2.4 million km2, half of which is a desert. The LCB spans across seven countries, four directly bordering the lake (Nigeria, Chad, Niger and Cameroon), the Central African Republic (CAR) in the South which holds 80% of the Lake’s springs, and in the North and East, Libya and Sudan respectively.

- The Lake Chad Basin is self-enclosed because of its long history of climate change (CC). The lake is a remnant of an ancient Paleolithic internal sea covering a large part of the actual territory of Chad. This sea progressively reduced in size over the last 8000 years, and its salt content reduced until it became a freshwater body. The water of the lake comes mainly from the Chari River, the main tributaries of which are the Logone River shared by Chad and Cameroon, the Kamadougou Yobe shared by Niger and Nigeria, the Yedseram (Nigeria) and the El Beïd (Cameroon). Once one of the largest water bodies on earth, the lake has shrunk by 90% from 25000 square kms in 1963 to less than 1,500 square kilometres in 2001. This has been attributed to climate change and variability and human pressure on the basin’s water over recent decades.

Figure 1. Chad and the Lake Chad

Source: NTDS (2014 – 2035) and World Bank, 2018

- Administratively, the country is divided into 23 provinces, 107 departments and 377 communes. The country remains highly centralized with nominated governors representing the State at provincial level. Canton and village chiefs are basic relays to the central authorities in matters of population administration. Governors lead Provincial Action Committees (PACs) which are supposed to be coordination bodies managed by the local technical services to pilot socio-economic development.

- Socio-economic and poverty context. 75% of the Chadian population live in rural areas while approximately 70% of the total population depends on agriculture as a livelihood source. Agro-sylvo-pastoral activities and fisheries represent 43.5% of the GDP (21% for agriculture, 18% for livestock and 4.5% for Fisheries). The main exports are cotton, live cattle and gum arabic while the country imports manufactured products. Overall, the country is pursuing non-oil diversification strategies such as agriculture as a buffer to volatile global oil prices. However, the agriculture sector is characterized by low productivity attributed to factors such as inadequate institutional capacities, climatic shocks, land degradation, dwindling natural resources even as population increases, conflicts, use of poor technologies and weak policies.

- Chad became an oil producing country in 2003, which changed the structure of its economy. The oil boom doubled the country’s per capita income, from USD 497 in 2001/02 to approximately USD 967 in 2014. However, the income was not equitably distributed. Oil price drops from 2014 onwards and the worsening of the security situation plunged the country into a harsh recession resulting in public spending restrictions and sluggish foreign direct investments. The deteriorating security conditions in the Lac Province have blocked the transboundary live cattle trade between Chad and Nigeria, resulting in substantial income losses for large numbers of agro-pastoralists.

- While poverty is slowly declining, it still affects nearly half of the population (46.3%), amongst them 26.3% are extremely poor, struggling to cover their most basic needs, notably food, education and health. Chad is ranked 185th out of 188 countries in the Human Development Index (HDI) of UNDP.  The incidence of poverty remains high in rural areas especially in households headed by people with low literacy levels, female and youth-headed households, and households with more than twelve members.  Poverty is also prevalent in households with the unemployed as unemployment remains high among the youth.  Additional vulnerable groups include migrants (temporary, refugees and displaced people) and hosted communities. These vulnerable groups need support to strengthen their livelihoods and improve their access to natural resources.

- Many Chadian citizens are deprived of basic social services and most of the Millennium Development Goals (MDGs) have not been reached. Although the oil boom period contributed to the reduction of poverty and the improvement of some social indicators such as child mortality rates and infant and maternal mortality rates (MICS, 2015), poverty reduction has not been sustained. The country is again highly vulnerable due to the economic and financial crisis, environmental degradation, climate change, and population growth. In recent years, insecurity in neighboring countries increased the number of refugees and displaced populations needing humanitarian assistance. Chad is currently hosting about 400,000 refugees from Sudan, the Central African Republic (CAR), and Nigeria, making the hosted communities more vulnerable. As a result, government spending is affected as Chadian government has to divert part of the national resources to security and hosting refugees.

- On gender issues, women rank lower than men on various aspects. The female adult literacy rate is 14% compared to male adult literacy which is at 38% . Women headed households are approximately 23% with 54% of these living on less than one dollar a day.  Women typically practice subsistence agriculture but even with this, lack access to fertile lands such as wadis, farm inputs and extension services. In comparison to other countries, the country ranks 140 out of 144 countries on Global Gender Gap Index.

- Food security and nutrition. Malnutrition is high in nearly all the regions of the country. Over 40% of children under the age of five are reportedly stunted, 20% of new-borns have low birth weight and over 46% of women suffer from anaemia .

- Climate and agro-ecological zones. There are three major climatic zones in the country namely Saharan with an average annual rainfall of 200mm, Sahelian with an average annual rainfall of between 200-700mm and Sudanian with an average annual rainfall of between 700-1,250mm. These climatic zones vary from arid in the North to tropical climate in the South. However, majority of the country lies within the Sahel region typified by erratic climatic conditions. In the last 80 years, the relatively dry Sahelian and Saharan climate has continued to progress South by over 150km.

- Rainfall has been on a decreasing trend especially in the Lake Chad region while temperatures have been increasing in the entire country. Recent drastic decreases in rainfall during dry season resulted in droughts affecting crop yields and decline in harvests and productivity of the livestock sector, as agriculture in mainly rain-fed.  Recurrent natural disasters affecting the country are mainly floods and droughts that continue to affect populations already food insecure and undernourished. These problems are exacerbated by weak national capacities to carry out forecasting, disaster preparedness, plan effective responses and develop adaptation plans.

- The country is susceptible to both long and short-term climate risks. Climate projections show patterns of increasing hot and dry conditions which will lead to low crop and pasture yields resulting in loss of incomes and livelihoods for families dependent on agriculture and revenue loss from cash crops such as cotton. Loss of land cover due to climate change will result in further degradation as well as expansion of cultivated areas at the expense of grasslands and forestlands. These may lead to irreversible degradation. Rising temperatures also create perfect conditions for human and livestock diseases and rise in pests. The fisheries sector, dependent on seasonal river flooding, is particularly threatened by reduced rainfall and rising temperatures. Agriculture and water are the most vulnerable sectors to climate change with women and children the most affected group.

### Policy and Institutional Frameworks

Development, Environment and Climate policies

- The Republic of Chad’s Constitution guarantees sound and sustainable management of agro-sylvo-pastoral and fisheries systems. To this effect, various general legal and regulatory texts have been adopted. Among these legal provisions are the Environment Act, the Agro-sylvo-pastoral and fish orientation law, the natural resources management (NRM) Act (including forest, wildlife and fisheries), the transhumance regulation Act, and the Water Code and Charter. Even though, these national laws generally take climate change into account, they are poorly enforced due to the absence of provincial development and investment plans and weak capacities and coordination of relevant local public and users’ organizations.

- The 2030 Vision for development’s objective is to make Chad an emerging country by 2030 able to ensure food security, access for all to water and energy through several national and sectoral policies and strategies, including the National Development Plan (NDP, 2017-2021). NDP aims at modernizing agriculture and diversifying Chadian economy while improving overall quality of life for Chadians.  It comes against a backdrop of the National investment Plan for the Rural Sector (PNISR, 2014-2020) which had the goal of turning the rural sector into an economic driver that also delivers on food security and nutrition.  Other sectoral policies are the National Poverty Reduction Strategies I and II (NPRS), the National Strategy and Plan for biodiversity (NSPB, 2014 – 2020), and the National Adaptation Programme of Action (NAPA, 2010). The NAPA identified urgent adaptation actions in order to counter the negative impacts of CC in key priority sectors including agriculture, livestock, fisheries and water resources.

- The National Territorial Development Scheme (NTDS, 2014-2035), aligned to the 2030 Vision, highlights the long-term vision for land use planning and the willingness to build a national territory that is economically competitive and in favour of peace, social justice and cohesion, and for which the sustainable development and population’s well-being are guaranteed. The document is strategic for the development of regions/provinces in a country that remains strongly centralized. NTDS is a unique strategic document for land use planning through specific regional strategies. Priority sectors for investment are water, energy, food security and sustainable development.

- The national land use planning policy has four strategic objectives: (i) Organizing the rational use of the national territory and redressing territorial imbalances related to the geographic location of the regions and to their different human capital and natural resources endowments; (ii) Ensuring food sovereignty and access to water for all; (iii) Ensuring coherence  and equity for investments, equipment and public administrations; and, (iv) Taking leadership to guide equity-oriented land planning.

- The country is divided into six regions, each of which has a regional development strategy to guide investment programs:

- The Saharan region grouping Borkou – Ennedi and Tiberti (BET)

- The Grand Kanem region grouping the provinces of Lac, Kanem and Barh-El-Ghazal

- The Center Region grouping Chari-Baguirmin, Hadjer Lamis and N’Djamena

- The East-center region grouping the provinces of Ouaddaï, Wadi-Fira, Batha and Sila

- The South-East region grouping the provinces of Guéra, Salamat and Moyen-Chari

- The South-West region grouping the Provinces of Mandoul, Logone Oriental, Logone Occidental, Tandjilé, Mayo-Kebbi Est and Mayo-Kebbi Ouest

- The Water and Sanitation Master Plan (WSMP, 2003-2020) is a strategic and multisector orientation framework for sustainable water improvement and management in order to satisfy people’s primary needs and ensure the country’s economic and social development while protecting the environment.

- The National Strategy to combat Climate Change (SNLCC, 2017) looks to sustainably and consistently integrate CC adaptation and reduction implications in national development policies while ensuring efficient coordination and converging efforts in terms of CC action in Chad.

- The National Framework for Climate Services (CNSC) 2016-2020, is an integrated priority action plan aimed at the production, dissemination and use of up to date information on climate change. It aims to bring together skills and resources with optimal collaboration and coordination of various sectors. The action plan was adopted in 2016 and is prepared within the context of the Global Framework of Climate Services (GFCS) - a UN-led initiative to guide the development and application of science-based climate information and services in support of decision-making in climate sensitive sectors.

- Furthermore, at the sectoral level, Chad has developed various national plans : the National Livestock Breeding Development Plan  (PNDE 2010-2017), the Aquaculture Development Plan (2018), the National Action Program to fight Desertification (PAN/LCD), the National Environmental Action Plan (PNAE), the Biodiversity Action Plan (SNPA/DB amended in 2019), the National Land Recovery Plan (2018), the National Great Green Wall Strategy and the National Strategy for Bush Fires Management (NSBFM, 2012-2022).

- In the specific areas of Environment and biodiversity conservation, various legal texts relating to the development of protected areas (national parks, wildlife reserves, biosphere reserves, etc.) and Natural Resource Management (NRM) emphasize environment and natural resource protection, but do not refer explicitly to resilience and adaptation to climate change.

- Land tenure. In Chad, three formal systems of law overlap, namely the traditional (or customary), the Islamic law and modern regimes. It is a very complex system but the State holds all private and public land as shown below:

- Public property: State holds land as either Natural public property such as lakes, streams and classified forests and artificial public property such as airports, irrigation channels, waterways, monuments, etc.

- Private property: Any State land that is not defined as public property is considered “private property of the State,” which individuals can acquire.

- Under customary law, another layer of ownership; communal ownership, exists. The ndouba is a community owned village land. A traditional leader holds the land in trust on behalf of the communities.

- The Islamic law that governs the central and northern regions recognises both collective and individual ownership of land with the former being an individual property and the latter collectively governed by a religious leader on behalf of the community.

- The land legislation dating from 1976, does not adequately address evolving land tenure issues such as changes from communal land to individual rights, access rights to grazing areas and use of rangelands in face of growing population. As such spatial planning that could guarantee a decent living and peaceful co-existence that reduces conflicts on land use and resources is not well developed. The result is frequent conflicts between farmers and pastoralists and among pastoralists over control of water points and grazing lands resulting in damage and loss of property and lives. Discussion fora and codification organizations are present at the local level - in villages and within extended families (customary regimes) but these sometimes lack capacities to deal with environmental threats such as desertification, water scarcity and biodiversity loss. At the larger scale (canton) level, little consideration is given to the governance of tenure issues even though secure tenure rights is strategic for improving landscape and natural resource management. Land tenure governance has further been weakened by a conflict-prone environment amidst environmental and ecological challenges resulting from a combination of anthropic pressures and climate change (CC).  Besides, numerous stakeholders including women, youth and some marginalized groups, have little access to fertile wadi and polder lands, and weak rights of access to natural resources.

- Chad is currently engaged in the process of updating the land law with the purpose of improving land governance, and addressing the problems of natural resource competition leading to conflicts and gender discrimination. The land law revision is led by a national committee established by ministerial decree and composed by representatives of various ministries.

- Gender and social strategy. The National Gender Policy (NGP, 2016) suggested corrective actions to address gender imbalance. The National Social Protection Strategy (SNPS, 2014-2025), aims at setting up a social protection system covering risks, reducing vulnerability and improving access for all to basic social services. The National Food and Nutrition Policy (NFNP, 2014-2025), emphasizes the improvement of populations’ socioeconomic conditions, in particular the most vulnerable layers (children, pregnant and breastfeeding women, the elderly).

Institutional Framework and Governance

- Four major technical Ministries are key in the implementation of climate  change adaption strategies:

- The Ministry in charge of Agriculture, Irrigation and Equipment (MAIE)

- The Ministry in charge of Livestock

- The Ministry of Environment, Water and Fisheries (MEWF)

- The Ministry of Land use Planning, Housing Development and Urban Planning

- At provincial level, the Decentralized Technical Services (DTS) of these ministries have the mandate to implement the sectoral policies and the national territorial development scheme in support of the six regional development strategies. However, due to limited technical and implementation capacities, the DTS are not able to fulfill their mandate effectively.

- Provincial action committees (PAC) were created in 1997 as coordination structures for the decentralized technical services in support of integrated socio-economic development. As with the DTS, the capacity and performance of PAC in coordinating and monitoring local interventions is very weak.

- The Ministry of Land use Planning, Housing Development and Urban Planning (MLPH) and its provincial delegations is responsible for the implementation of the National Territorial Development Scheme (NTDS, 2014-2035) and provincial land plans. This ministry also has the specific mandate over land tenure, in particular through its role as chair of the national committee on land reform, which is composed of representatives of ministries concerned with land issues, civil society, academia and other experts. MLPH is a key player in the provinces but to be effective, they need to develop planning, coordination and monitoring capacities of their land planning delegations (DLPs).   The ministry needs to strengthen policy dialogue on land to face new challenges including human and livestock population pressure, climate change and discrimination and inequalities in women, youth and vulnerable groups’ access to land and ecosystem services (water, non-timber forest products and other products).

- Two national agencies are in charge of executing rural development investments: the National Agency for Rural Development (ANADER) and the National Agency for the Great Green Wall (ANGMV).

- The National Agency for Rural Development (ANADER) was created in 2016 as a public administrative and technical legal entity with an autonomy for management. This new agency is the consequence of a strong reform transforming the ancient ONDR (Office national de développement rural) into a national agency administered by a board of directors and a Directorate-General. Its resources come from subsidies and other contributions from Government, consulting services and other resources from national and international organizations, and donations. They have also been endowed with assets of the Lake Development Company (SODELAC) and the National Food Security Program (PNSA). The agency is the most important public extension service provider to support the intensification and diversification of agricultural, animal, fish and forest production, and the creation and structuring of farmers’ organizations.

- ANADER is divided into four technical Directorates and ten regional branches. The project area (target provinces of Bahr El Ghazal (BEG), Hadjer Lamis, Kanem and Lac) include three branches, each divided into sectors and sub-sectors for the location of extension agents. The coverage rate is weak (12% of the national territory). Technicians lack the capacity and means for implementing gender-sensitive participatory approaches - only 10% of the extension agents are women, and there are no female extension agents in BEG and Kanem - integrating agriculture, livestock and forestry and providing support to market- oriented value chains. (See Table 1 below).

Table 1. Distribution of ANADER agents in the four provinces covered by the project

- The Great Green Wall National Agency (ANGMV), was created in 2012 under the supervision of the Ministry of Environment. Its first mission was to achieve a green barrier against the advance of the desert in the Sahelo-Saharan belt between isohyets of 100 mm and 400 mm per year, the most vulnerable area to climate change with high prevalence of food and nutrition insecurity.  The Agency has been assigned offices in N’Djamena for the Directorate General, and has two branch offices at the local level. Since 2014, the agency has been confronted to severe financial restrictions from the State and became reliant on external resources. The agency is engaged in a process of reform in its mandate and its strategy for better impact on ecosystems and rural communities. The Ministry of Environment has given to the agency, a new task of coordinating the National Program for the Restoration of Land, Water and Biodiversity (NPRLWB, 2018) in the 23 Provinces of the country.

- ANGMV implements agro-pastoral investments through a village land use planning approach with the participation of chiefdoms. Several actions have been promoted such as stabilisation of sand dunes by planting or by fencing, introducing grazing bans of revegetated areas, natural regeneration and agroforestry to restore degraded lands and develop production. The institution is limited in terms of equipment, human physical and financial resources to fulfil its mandate and support massive restoration programs to sustainably impact on the resilience of the ecosystems and livelihoods. Actions implemented are limited and weakly sustainable due to lack of effective planning processes and dialogue with land users and chiefdoms at local level.

- The Lake Chad Basin Commission (LCBC) is the Basin Authority comprised of six member States, including the original four signatory countries (Cameroon, Chad, Nigeria, and Niger) and two countries that joined later, the Central African Republic (1994) and Libya (2008). LCBC has the mandate to manage, in a sustainable and equitable manner, water and other transboundary resources of the LCB, to preserve and conserve ecosystems of the Basin, to promote regional integration, and preserve peace and security within the Basin. Its traditional financial and technical partners are the African Development Bank (AfDB) and GIZ. The LCB Strategic Action Programme (SAP) is a regional policy framework document with appropriate support from international partners. The Lake Chad Water Charter (2012) is the first legal instrument after the 1964 Fort Lamy Convention to be collectively assented by the highest political authorities as a binding document to cover the entire Lake Chad Basin. It is a vehicle for sub-regional integration and security, formally adopted at the 14th Summit of the LCBC Heads of State and Government held on the 30th April 2012 in N’Djamena, Chad. Four out of the six Presidents (Niger, Nigeria, Chad and CAR) of the LCBC states personally assented to the document, while the two others (Cameroon and Libya) endorsed the agreement through their authorized representatives.

- LCBC has received long-term support from GIZ (CC Adaptation Program 2012-2017), and by AfDB for the ecological monitoring of terrestrial and freshwater ecosystems and to develop regional socio-economic projects (PRESIBALT). A new UNDP-GEF project has been formulated to enhance LCBC’s institutional capacity. Bilateral donors have financed several micro initiatives for this regional institution. LCBC also contributed to the design of the Water Law and the Water Charter and, with IUCN support, is contributing to the creation of a new transboundary protected area.  FAO (with funding from PRESIBALT) is responsible for designing the Aquaculture and Fisheries strategy. LCBC is a strategic partner for all concerns related to scientific data and information for water and natural resources management and for ecological monitoring.

- Due to the security problems related to Boko Haram, transboundary security became a major challenge, resulting in military cooperation between LCB member states to combat the severe regional crisis. A military joint force was put in place to combat the terrorist group. The Multinational Joint Task Force (MNJTF) involving Chad, Niger and Cameroon, has the mandate of security and protection of civilian populations in the Basin. MNJTF shares military information and organizes joint military operations. It has established a community-driven radio to inform and communicate local people in the Kanembou language (Ndorason Radio). The presence of MNJTF in the region is an important aspect because stable security environment is necessary for successful implementation of the proposed project.

- Overall, institutional capacities and coordination, particularly at local – provincial level are not sufficient for rural development, environmental governance and implementation of natural resources management and climate change adaptation interventions.  Planning and dialogue frameworks between local stakeholders (regional government bodies, chiefdoms and various users’ representatives) are weak. There is a need to set up multi-actor platforms to dialogue, plan, implement and secure investments. The various local institutions need to be capacitated in order to promote climate change adaptation models and practices in a participatory and sustainable manner.

### Project area

- The Lake Chad Basin. Located between the 12th and 14th parallel at the desert limit, Lake Chad is the third largest outlet free lake in the world. Its main affluents are the Chari (which flows through the Central African Republic (CAR), Chad and Cameroon), the Logone (which flows through Cameroon and Chad) and the Kamadougou Yobe (flowing through Niger and Nigeria), Yedseram (in Nigeria) and El Beid (in Cameroon). The Chari drains more than 90% of the water feeding the lake. It is the only year-round tributary, along with the Logone.

- The aspect, shape and contour of the lake vary significantly according to seasonal water levels and rainfall. The eastern part of the lake is made up of a network of narrow and shallow channels flowing around sandy islands making it hard, even almost impossible to navigate those parts of the lake.  The number of emerging islands may vary from 400 to 600, depending on the water level. Only the southern part of the lake has a year-round water flow. This part of the lake is rather shallow (an average of 5.5 m of depth in usual conditions). The water level is influenced by the balance of inflow and water loss by evaporation. Measurements from meteorological stations around the lake show an annual surface evaporation level of 2,500 mm. During the dry season, water levels drop significantly. From July to January, waters rise higher and may reach their maximum level in January. After this culminating period, waters gradually recede until the June-July period.

- The Project spans four adjacent provinces (Kanem, Bahr El Ghazel (BEG), Hadjer Lamis and Lac) in the western part of the country, all located in the Lake Chad Basin. The four provinces cover two regions for investment program established by the SNAT (See Figure 2):  (i) the overall Grand Kanem region comprising of Kanem, BEG and Hadjer Lamis Provinces; and, (ii) one (Hadjer Lamis) out of three provinces of the central region comprising of Chari-Baguirmi, Hadjer Lamis and N’Djamena. The total population is estimated at 2.17 million inhabitants.  Population distribution by province is presented in the below table 2.

- The project area is characterized by three climatic zones:  the Saharan zone (<100 mm annual rainfall) includes North Kanem and North BEG; the Sahelo-Saharan zone (100-200mm) includes the rest of BEG and Kanem while the Sahelian zone (upper limit of 300 mm) includes the Lac and Hadjer Lamis (Source: SNLCC 2017).

- Each Province is governed by a Governor nominated – and not elected - to represent the State at the Provincial level. The Governor is responsible of economic development and administration of the population in close collaboration with the Provincial Action Committee (PAC) which is a local coordination platform composed of officers of the provincial delegations (see also previous section 1.1.2).

Figure 2. Project area

Source:  NTDS 2014 – 2035

Table 2. Population by Province

Table 3. Administrative breakdown and pre-identified cantons

- Poverty situation in the region. The majority of the population (59%) consists of poor and very poor households. These households are relatively small in size (6 to 8 persons), have small arable land holdings (less than 0.2 ha) and small herds. Rich or middle-income households (41%) own larger herds of small ruminants and cattle and have larger land holdings (more than 0.4 ha). In the agro-pastoral area of South BEG, income comes mainly from livestock, gardening, small-scale business, labour migration and local wage labour. When disaggregated by household, per capita income tends to be similar among the very poor and the poor with respectively XAF 67,694 (USD 113) and XAF 72,338 (USD 120). In contrast, for the affluent category, per capita income is twice as high as very poor and poor persons (XAF 136,866– USD 228) and 20% higher than middle income persons (XAF 114, 855– USD 195) (OXFAM, 2011).

- Livestock systems. Livestock breeders may have transhumant, semi-transhumant or sedentary lifestyles.  Different ethnic groups specialize in raising different livestock (camels are bred by the Toubou and Gorane, cows and small ruminants are bred by Arab, Peuhl and Boudouma communities) and have a variety of practices, depending on ethnic groups and ecosystems. Cross-breeding is observed between different breeds along with population and livestock structure evolutions.

- Transhumant pastoralism is historically dominant in the northern and eastern part of the project area, up to the Batha border, which is a large pastoral area in the center of Chad. Transhumance is a highly suitable strategy for arid areas with scant vegetation. Breeders move along traditional pasture belts to feed and water (wells and ponds) the herd.  Bovine livestock breeding is most popular. Pastoral itineraries are inherited through generations but they are not clearly marked on the ground, leading to many resource management conflicts. With rising human population and livestock numbers, pressure on land is increasing leading to conflicts and the spontaneous or forced displacement of people. The result is long-term occupation of traditional pastoral zones that further intensifies related conflicts.

- Dromedary transhumance is the longest, with distances reaching 500 kilometers on average, from the Saharan to the Sahelo-Saharan zone. Transhumance consists of extensive livestock grazing in the scarce green areas of the desert during the wet season, and when pastures are exhausted, heading south towards the dry season pastures near Lake Chad. Salt extracted from natron remains the sole complementary nutritional product in livestock feeding and is an important source of income for the herders.

- Medium-distance transhumance of bovine herds is mainly done by agro-pastoralists. They pass the wet season in camps in the North, where the herds find more nutritious grass and encounter fewer diseases. During the dry season, families split into different task groups with men dedicated to nomadic herding covering long distances while women and children stay closer home to continue  farming and taking care of semi-intensive small ruminant breeding in the village. Occasionally, short-distance transhumance is also practiced by sedentary farmers who own livestock. The herds’ mobility is limited to nearby pasture areas.

- High livestock concentrations are found where the Sahara meets the Sahel, along the main trade routes, along the Bahr El Gazal, the Chari river and by the Lake. Pasture areas managed according to customary rules are increasingly threatened by encroaching crop farming, and in the areas where farms are adjacent to transhumant livestock itineraries, conflicts are common.

- Farming systems. There are three main farming systems: (i) Recession agriculture on the humid plains and islands of the lake; this is the most profitable system using low levels of labour and capital and benefiting from the high fertility of the alluvial soils; (ii) Agriculture on dry sandy lands (Hadjer Lamis and South Kanem); and (iii) Irrigated agriculture in the wadis and polders (BEG, Kanem and Lac). When wadis are developed, they gradually evolve into oases, with date palms as the main landscape feature. Cereals (such as corn and sorghum in the wadis and polders, millet on sand dunes, flood-recession grown sorghum on the Lake) are grown for grain, and stalks fed to the livestock. Groundnut and sesame are grown on highlands while the irrigated wadis are dedicated to fruit-tree and vegetable husbandry.

- Rainfed crops and pasture on the dunes cause land degradation and siltation of areas located downwind. This process can only be halted and reversed by dynamic and concerted measures to fix the dunes and restore their vegetation and protect them once they are restored.

- Fishing is practiced in the Lake, along the wadis or in ponds. This activity is actually severely hampered by the insecurity in the Islands, which are a refuge for rebels. The Government of Chad has resettled the people living on the islands in areas along the lake to secure the area and carries out regular military operations there. Many fisher folk have become internally displaced people (IDP) while herders lost access to dry season grazing areas.

- The area was already affected by high food and nutrition insecurity, and the situation has worsened with the presence of Boko Haram armed groups at the borders with Nigeria and Cameroon resulting in the forced resettlement described above. This has prompted important spontaneous population movement towards regions such as Kanem and BEG, increasing the pressure on already scarce resources. The situation has been further aggravated by climate shocks. The prevalence of food insecurity is high in the Kanem and BEG provinces. The humanitarian profile established in this region by the United Nations Office of Coordination of Humanitarian Affairs (OCHA, 2016) shows that 56% of the population in the Kanem region suffers from overall food insecurity, including 25% in critical situation. The negative impacts due to disruptions in trans-border trade to household incomes is further aggravated by the economic crisis in Nigeria with the rising inflation rates.

- Markets. Market areas, which are often small, are difficult to reach due to sandy roads. The region imports food (cereals) and exports livestock, which depends on natural pastures hence need for ability to access healthy pastures. The rural exodus of men, especially youth, is very important in the area as it results in a lack of labour force during the dry season to develop wadi lands. At the same time, out-migration of some members is a family strategy for diversifying incomes for social groups with limited access to land and financial resources.

- Rural territories and natural resources management. Agro-pastoralists combine agricultural and livestock activities through division of labour within their extended families. Pastoral and agricultural lands are not clearly demarcated, and often have overlapping land use claims and reciprocal benefits such as animal manuring the land as they feed on plant residues. Transhumance corridors may change and cause competition with agriculture. But sometimes crop farmers encroach on the livestock corridors. As nomadic herders increasingly settle and grow crops, and as farmers invest in livestock and practice short-range transhumance to benefit from pastures near the villages, the reciprocal relationship that has existed in the past is weakened and conflicts over resources become more common. The overall structure of the livestock population is also changing with an increase in sedentary small ruminants owned by women, partly attributed to the humanitarian interventions and resilience projects.

- Since the 1980s, under the influence of droughts and human and livestock population growth, the southward transhumance to Southern Chad and Northern CAR has become more important. The transhumance to Lake Chad to benefit from pasture on the humid island plains is hampered by the Boko Haram conflict.

- There are no reliable statistics on North-South and East-West movements of livestock herds, making it hard to appreciate quantitatively whether the pressure on pastoral ecosystems is increasing. This lack of information does not facilitate the resolution of conflicts, which are frequent and often bloody. Strong competition between agriculture and livestock in the agro-pastoral lands are giving rise to new challenges in terms of land management and land tenure. Figure 3 below illustrates the importance and complexity of livestock movement, and the related potential for conflict over natural resources, and thus demonstrates the importance of improved land use planning and regulation of natural resource use, taking into consideration climate change impacts, that the GEF-LDCF project will fund.

Figure 3.  Transhumance in the Lake Chad Basin

- Conflicts have intensified because the organizations in charge of managing them (Government and traditional chiefdoms) and regulatory systems are unable to adequately address the human and livestock pressures and to tackle the land and resource tenure arrangements needed for effective land use planning and regulation of the use of natural resources. It is necessary to strengthen the fora for dialogue within and between villages and cantons and to adopt new practices to optimize natural resource use and restore degraded ecosystems. There are two main types of conflicts over natural resources: (i) conflicts between pastoralist groups over watering spots and pastures; and (ii) conflicts between pastoralists and farmers due to livestock damage to crops and the occupation of pastoral land and transhumance paths by farmers (Bonnet et al. 2014).

- Local organizations. Social organization relies on canton and village chiefs, traditional land chiefs and religious leaders (sheikhs, priests or pastors). Traditional chiefdoms have the mandate to manage land, apply customary law, collect taxes and prevent, manage and resolve conflicts. In the project area, to be a traditional chief is a lifelong role passed on through patrilineality, with a son taking over when his father dies. In various localities, traditional chiefs stated that they were affiliated to the new institution of the High Council of Autonomous Collectivities and Traditional Chiefdoms (HC-CACT). Religious leaders also play a substantial role in maintaining social harmony between local communities. In fact, they are often resorted to, to resolve family or inter-ethnic conflicts.

- The three major socio-professional organizations that are represented in the project area include the Interprofessional Confederation of the Livestock Breeding Sector in Chad (“Confédération Interprofessionnelle de la Filière Elevage au Tchad” (CONIFET), the Chadian Rural producers’ National Dialogue Council (Conseil National de Concertation des Producteurs Ruraux du Tchad (CNCPRT) and the apex organization of fishing and aquaculture promotion and environment protection (FOTPAPE).

- Local land rights regulation systems. At the local level, customary institutions – through the Association of Chad’s Traditional Chiefdoms (ACTT) – are responsible for land dispute management. Customary and traditional rules regulate water and land access. At the local level, there are two co-existing traditional land right systems: customary law and Islamic law. The main regulation bodies are customary organizations and administrative constituencies. For large hydro-agricultural developments, land plots are allocated by public authorities with prior agreement of traditional chiefs. The influence of local authorities is significant in this type of land allocation system. Article 21 of  Act n°24/PR/67 of the 22nd of July 1967 regulating the land property regime and customary rules, states that in the framework of agricultural, forestry or animal production development, the State may select, by decree, areas whereby land status is statutorily and legally defined.

- As stated, the land legislation dealing with people’s rights and obligations regarding land access dates from 1967, and is not adapted to the current context of higher human population and livestock numbers, and increasing natural resource scarcity. Livestock-breeding and pastoralism are given little focus, while the risk of natural resource user conflicts (e.g. herder vs herder and farmers vs herders) is expected to further increase in the coming years (FAO, 2014).

### CURRENT SITUATION

### Main environmental threats and drivers

- Climate change in Chad. The climate is dry and tropical, characterized by two alternating seasons (dry and rainy). Since 1960, the mean annual temperature has increased by 0.7°C with an average increase of 0.16°C per decade. In the last half-century, Chad has been experiencing several serious droughts, and other climate related shocks including floods and erratic rainfalls, which have further hindered its economic development.

- Chad is considered to be one of the most vulnerable countries to CC in Africa, while at the same time, it receives  less international CC funding compared to other Sahelian countries. Moreover, Chad is surrounded by severe conflicts worsening the vulnerability context for rural communities and the State.

- The impacts of CC on the Lake Chad Basin hydrologic system, and the agro-sylvo-pastoral and freshwater ecosystems, are important. The National Adaptation Programme of Action revealed a number of major problems, one of them being the 40-60% decline in the flow of the Logone and Chari river systems feeding Lake Chad, resulting in the shrinkage of the lake, a decrease in groundwater recharge, and degradation of vegetation cover and soil in the watershed. These conditions create negative impacts on biomass, genetic diversity, and food production, and exacerbate inter-community conflicts between land users.

- Changes in climatic and socio-economic conditions have contributed to landscape and geographical transformation. The dichotomy between pastoral and agricultural livelihoods within families and farming systems have become less marked. Diversification of economic activities, human and livestock mobility in quest for livelihoods (water, pasture, and financial resources through outmigration) are socio-economic strategies adopted by agro pastoralist families to face the challenges of natural resource scarcity and drying-up of the Lake Chad ecosystems.

- Although there are uncertainties regarding future changes, recent modelling exercises forecast the highest average annual temperature increases for the central and the east of the Lake Chad Basin, of around 3 to 6 °C by 2100. Increases in temperature will be accompanied by an increase in evapotranspiration, reduction in rainfall and water resources, and loss of viable agricultural lands. These conditions will affect the already highly vulnerable ecosystem and the populations that depend on it. (See also paragraphs 10-12).

- Ecosystem degradation has considerably intensified due to extension of cultivated areas and livestock population growth, which increased tremendously as a result of the oil boom. Farmland increased threefold and livestock growth has been remarkable from 2005 onwards, reaching 114 million heads, of which about 30% live in the project area. Ground vegetation degradation by trampling and clearing of grasslands for cultivation has created shifting sand areas. Between 1975 and 2013, sandy areas have increased by 22%. The ongoing conflict that is reducing the scale and flexibility of livestock mobility will only lead to further degradation due to over concentration of animals in certain areas as herders cannot adequately use opportunistic resources available over space and time.

- There are four main landscape types, each facing environmental threats due to pressure on resources:

- Wadis and polders (20% of surface) mainly dedicated to farming (cereals and vegetables) are threatened by siltation from sand dunes when the latter are no longer stabilized by vegetation, and by salinization. This is due to overexploitation of resources in the surrounding agro-pastoral area. Siltation causes loss of arable land and lowering of water tables making water pumping more expensive. Sand dunes which are oriented south-west north-east where cereals such as millet are grown during the rainy season and used as a pastoral zone for sedentary small ruminants are under great pressure. This area is threatened by deforestation, overgrazing and ploughing for crops, threatening its function as a bulwark against sand invasion. Restoration programs on these degraded lands require village and inter-village consultations to protect areas to be revegetated.

- The vast pastoral area north of Kanem and along the Barh El Gazal is divided into transhumance corridors around and between watering holes. Water networks determine herd itineraries that are generally related to the presence of pasture and water. Livestock populations have increased in recent years around pastoral wells while pasture yields have declined in some areas. These pasture lands are degrading by over exploitation.

- The high steppe lands of Hadjer Lamis are under threat of overexploitation by agro-pastoral activities.

- The lake areas (lake, river, pond and groundwater) are receding and the water tables are falling, leading to the reduction of freshwater resources, such as spirulina, the production of which has become more seasonal in many places. However, it remains an important food supplement and a significant source of cash income for the region’s population, especially the poorest women. Small-scale projects implemented recently by FAO and SOS Sahel have succeeded in tripling spirulina revenue of participating women’s groups.

### Baseline initiatives

- The subsection focuses on what the Government of Chad and its financial and technical partners have done to address the issues highlighted above, including past and ongoing initiatives that comprise the baseline upon which the proposed GEF-LDCF project is built upon.

- Overall, with the Boko Haram conflict hampering investments, the majority of the current activities in the Lake Chad region are short-term projects focused on humanitarian, peace and security concerns, though resilience projects in the Kanem, BEG and Hadjer Lamis provinces have a stronger emphasis on productive investment.

- Four strategic financial partners are highlighted below. The first two are confirmed co-financiers for a total of USD 18,585,000, while the last two are under negotiation:

- The AfDB through “Building resilience to food and nutrition insecurity in the Sahel” (P2RS) project in 2 provinces (Kanem and BEG) and implemented by the Ministry of Agriculture which signed a co-financing letter for an amount of USD 11,085,000. The GEF-LDCF co-financing will complement its investment and reinforce its strategy through institutional and innovation support.

- The IFAD “Strengthening Productivity and Resilience of Agropastoral Family Farms Project (RePER)” in the provinces of Hadjer Lamis, Kanem and BEG. Due to the size of this project (USD 49.3 million loan + USD 5.3 million grant = USD 54.6 million) covering 5 provinces with an extension to two new provinces (Kanem and BEG), taking into account its GCF co-financing for USD 17.2 million, REPER is a strategic financial partner in the Hadjer Lamis Province, and has confirmed co-financing of USD 7.5 million for the GEF-LDCF project.

- The regional project to be financed by the World Bank in the Province of Lac (PROLAC) with potential  extension in the provinces of Kanem and BEG intends to partner with LCBC, French Cooperation, and NGOs to implement its activities in Chad, Lac province. This project could become an additional source of co-financing in the Lac province.

- The Regional Sahel Pastoralism Support Project (PRAPS) financed by the World Bank aims at improving access of production and services for transhumant herders located between 11th and 16th parallels. The targets are pastoralists and agro-pastoralists and areas with high concentration of cattle, along corridors and water spots. PRAPS could also become an additional source of co-financing for the GEF-LDCF project.

- Two other projects that are currently under preparation - limited in terms of financial resources but strategic in terms of capacity building  for improved coordination and policy dialogue – have been identified as potential co-financiers to support the GEF-LDCF policy dialogue: (i)  FAO regional project on Land Governance financed by Germany (nearly USD 150,000 to be mobilized by the FAO Land tenure Unit in 2020) and, (ii)  the OXFAM Land-at scale project financed by the Netherlands on land governance (USD 1.5 – 2 million to be mobilized in 2020). FAO is facilitating the integration of these initiatives and the co-financing with the GEF-LDCF project to support the road map of the Chad land reform process in partnership with the National Commission on Land reform and the Ministry of Land Use Planning.

- Tables 4a, 4b and 4c below list investment and resilience projects ongoing or under preparation in the project area. Table 4a includes projects that are already financed, and that have confirmed co-finance. Table 4b  lists projects under preparation that are potential additional co-financiers and Table 4c lists other relevant projects in the area that have not confirmed a co-financing relationship but are complementary to the proposed GEF project, including projects implemented by LCBC.

Table 4a. Portfolio of investment and resilience projects confirmed for co-financing

| Project | Donor | Province | Objectives, implementing agency and Investments |
| --- | --- | --- | --- |
| P2RS - 2015 – 2035 - Phase 1 2015-2020, - Phase 2 2021-2025 - Co-finance USD11,085,000 | AfDB | Kanem and BEG | The twenty-year regional (multi-country) project is divided into four phases of five years each. The first phase 2015-2020 is ending and the second phase (2021-2025) is currently under formulation. In Chad the project is implemented by the ministry in charge of Agriculture Investments realized for rural communities are pastoral wells (30), warehouses for cereals (30) and fodder, shops for inputs (34), drip irrigation (studies for 345 ha). The project is expected to invest in supplementary pastoral and agriculture wells, market infrastructure for cattle (2), slaughterhouses (2) vaccination parks (10) and Multi-purpose service Platforms (10). |
| Strengthening Productivity and Resilience of Agropastoral Family Farms Project – REPER Co-finance USD 7.5 million | IFAD | Salamat Guéra Batha Hadjer Lamis Chari Baguirmi Planned Extension Zone: Kanem and Lac | This new project formulated in 2019 to help Chadian farmers to adapt to climate change and boost the agriculture sector in five provinces of Chad. Beneficiaries are sedentary agropastoralists (1 million) The project is expecting to raise the performance and resilience of agropastoral family farms by strengthening agricultural water infrastructure, rehabilitating rural feeder orads, intensifying and diversifying family farming production systems, supporting values chains, improving nutrition and adult literacy, supporting farmers’ organizations and improving access to financial services. The new IFAD COSOP expects to extend IFAD area of intervention to the provinces of Lac and Kanem. |

- The AfDB and IFAD projects have a strong national component involving government bodies. The Delegations for Land Use Planning (DLPs), however, are not supported, whereas in a context of weak decentralization, they represent a strategic administration to plan and monitor provincial action plans, in partnership with traditional chiefdoms and land user’s organizations. The GEF-LDCF resources will complement the activities financed by these strategic financial partners by financing vigorous capacity development programs for four local technical administrations (DTSs for Agriculture, Environment, Livestock and Land Use Planning) and ANADER; and investments in innovative innovative technical-economic models adapted to climate change and to markets. Strengthened capacities at the local level will also benefit the implementation and sustainability of AfDB and IFAD projects and mainstreaming of concrete climate change adaptation models in these, and new and future investments highlighted below.

Table 4b. New investment projects that will likely provide additional co-finance for the project

| Project | Donor | Province | Objectives, implementing agency and Investments |
| --- | --- | --- | --- |
| Recovery and Development in the Lake area (PROLAC) - 2020-2024 - Chad : USD 45 million | World Bank | Lac Kanem and BEG under discussion | This five-year regional project is in a process of formulation for the province of Lac, and potentially the provinces of Kanem and BEG. The project strategy will use a faire-faire approach for implementation through major international partners such as LCBC, French co-operation, and NGOs. It will invest into roads, economic infrastructure and value chains. |
| Regional Sahel Pastoralism Support Project - PRAPS | World Bank | Kanem, Lac and | This regional 20-year project, implemented in Chad by the ministry in charge of Livestock, aims at improving access of production and services for transhumant herders located between the 11th and 16th parallels. The target beneficiaries are pastoralists and agropastoralists in areas with high concentration of cattle, along livestock corridors and watering points. Investments include pastoral wells, market infrastructure, support to livelihoods; the approach is territorial and uses dialogue between users before investing in any infrastructure. |
| FAO regional project on Land Governance | FAO and Germany | National (Policy dialogue) | This three-year regional initiative on tenure governance to be financed by Germany, is expected to be implemented in five Sahelian countries (Chad, Mali, Niger Mauritania and Senegal). FAO will be an executing agency through the Land Tenure unit and in close collaboration with FAO Chad. FAO will implement the Chadian component of the regional project in close collaboration with the Ministry in charge of Livestock as well as other key ministries, such as the Ministry in charge of land planning and the Ministry of Agriculture, to support the land reform process. Other key stakeholders, such as civil society actors and traditional chiefs, will also be key partners of the project to support a holistic multi-stakeholder approach to the land reform process. The regional project will help to strengthen the capacities of the local and national stakeholders to make use of Voluntary Guidelines on responsible governance of tenure as a tool for conflict prevention and for improving access to land for women, youth and other marginalized groups. This project will contribute to the financing of a national Forum on land reform, as well as the action plan, which is expected to take into consideration climate change. In the view of building this strategic partnership, the GEF-LDCF project will provide guidance to the land reform process through the national Commission on Land reform and the Ministry in charge of Land Planning for which FAO will provide TA to write TORs and facilitate the negotiations between the Ministry of Land Planning, the Ministry of Livestock and OXFAM/ Land-at-scale project to be financed by the Netherlands. The GEF-LDCF project will support the Government’s road map for the land reform process, including the national forum aiming at integrating CC into land policy and strategies. Throughout the land reform process FAO will play a key role in providing technical back-stopping and capacity development support to all key stakeholder groups engaged in the process, in particular through capacity building on the voluntary tenure guidelines |
| « LAND-at-Scale » Programme - 2020-2024 - € 1.5-2 million | OXFAM | Bahr El Gazal, Guera, Logone Oriental, Logone Occidental, Mayo Kebi Ouest, Ouaddai, Mandoul, Chari Baguirmi | This national two-year initiative on Land Governance is expected to be implemented by OXFAM from 2020. Its objective is an inclusive and sustainable governance through conflict mitigation, support to the land tenure reform and reduction of discriminations on land access. This project is expected to be implemented in the BEG province. It is expected to be a strong partner to launch the national Forum on land in partnership with the GEF-LDCF project. |

Table 4c. Portfolio of other relevant and complementary investment projects in the GEF project area

| Project | Donor | Province | Objectives, implementing agency and Investments |
| --- | --- | --- | --- |
| Programme to rehabilitate and strengthen the resilience of Lake Chad basin systems (PRESIBALT). - 2014-2019 - USD 7.8 million | AfDB | Lac | This regional project covering five Member State countries (Chad, Cameroon, CRA, Niger and Nigeria). It is implemented by LCBC though three components. Investments to rehabilitate and strengthen the resilience of socio-economic and ecological systems of the Lake Chad Basin an enhancing the resilience of vulnerable populations who depend on the Lake basin’s natural resources. Three components: (i) Preservation and development of water resources; (ii) Development of ecological services and value chains; and (iii) Institution building and programme management. FAO signed a convention to formulate the freshwater resource development strategy (“Schéma d’aménagement des ressources halieutiques”). Actions concern preservation and valorization of water resources, including meteorology infrastructure for water scientific monitoring, early warning system and information system for agriculture, development of ecological services and capacity-building programs for national/regional institutions. The project invested into small irrigation schemes, pastoral wells, roads, heath centers and energy. |
| Tandal Project €10 million | French Cooperation AFD | Lac | This infrastructure oriented project is implemented by international NGOs to invest into a hydro-agricultural development of 10,000 ha of polder lands with total water control for irrigation. The project could be a potential partner to protect and restore degraded pastoral lands around the irrigation scheme. |
| Resilience Project € 15 Million | EU | Kanem, Lac, BEG | This project, implemented by a consortium of local and international NGOs led by OXFAM, aims to support livelihoods through distribution of small ruminants, income generating activities and HIMO. |
| RESTE Programme € 27 Million | EU | Lac | This project, implemented by a consortium of local and international NGOs, aims at building social and economic stability in the Lac province. Improve the access of youth, women and other vulnerable groups to economic opportunities, improve food and nutrition security, access to fresh water and capacity building programs for local public organizations, social cohesion and governance. Investments: water access, income generating activities (small ruminants), capacity-building programs for local public institutions. |
| Sahel Women’s Empowerment and Demographic Dividend (SWEDD) - 2014 – 2023 - USD 170 million | World Bank / UNFPA | Lac and Kanem | This regional project covers 7 countries: Benin, Burkina Faso, Chad, Ivory Coast, Mauritania and Niger to help empower women and adolescent girls and improve their access to quality education and reproductive, child and maternal health services. 13,000 young girls benefitted from social support for their education and 168 women benefitted from professional training to develop specific skills. This project could be a partner for the development of capacity-building programs for women. |
| Improving Lake Chad management through building resilience and reducing ecosystem stress through implementation of the Strategic Action Plan (SAP) - 2018-2023 - USD 5.8 million | GEF through UNDP | Lac | The objective of the UNDP-GEF- LCBC project is to develop and implement sustainable management policies to rectify unsustainable land/water management practices and respond to CC threats in accordance with the agreed SAP for the Lake Chad Basin. Expected outcomes: (i) A strengthened LCBC; (ii) Strengthened and harmonised approaches to implementing sustainable legal and policy instruments across the Basin countries leading to greater water availability; (iii) Technical capacity and awareness of national ministries, institutions and other stakeholders to contribute to the sustainable management practices of the natural resources in the basin at both national and basin levels; (iv) data and information on Land, Water, and Biodiversity Resources; (v) upscaling sustainable ecosystem management and alternative livelihoods; and (vi) a broad investment programme to further assist SAP implementation. |

### Remaining barriers to tackle

- Four key barriers to effectively addressing climate change and environmental degradation in the Lake Chad Basin  have been identified:

Barrier 1: Weak environmental governance and implementation capacity in the provinces, limiting fundraising and local implementation of climate change adaptation investments.

- Generally speaking, knowledge and understanding of CC impacts are insufficient, leading to weak local-level adaptation strategies. This includes lack of capacities to generate, communicate and act on information relating to climate risks. As agro-sylvo-pastoral landscapes continue to be subjected to degradation of natural resources and ecosystem services due to pressures including climate change, there is a need for strong multi-sectoral actions based on a mid to long-term vision to manage landscapes to render them more resilient to climate change and other threats and to improve rural communities’ livelihoods.

- Provincial Governors’ offices have the responsibility for the governance of the environment with technical support from decentralized technical services (DTS). The public agencies at Provincial level are poorly equipped and funded (transport, communication means, and equipment) and have limited planning, coordination and monitoring and evaluation capacity. Furthermore, rural communities are not sufficiently organized at inter-cantonal level to dialogue and deliberate in order to agree with the government on a common vision for land use at various scales, contributing to conflicts over the management of natural resources that feed and aggravate the prevailing context of insecurity.

- Many CC adaptation initiatives and policies related to climate change are implemented in an isolated fashion, without dialogue across sectors. Lessons learned about practices and innovations are not shared and capitalized upon. There is little effort to integrate rural communities’ knowledge and practices related to CC adaptation with scientific knowledge. Tools such as computers and satellite imagery to generate data and information for rural extension services and meteorological forecasting are lacking. Documentation to enable better decision-making in the livestock sub-sector is particularly scarce. Scientific knowledge based on livestock and pasture ecology indicators to facilitate decision making and provide an operational framework for evaluating the impacts of public policies and private investments, is still largely missing.

- The National Agency for the Great Green Wall (ANGMV) has two important weaknesses:  the socioeconomic gender factors are not sufficiently taken into account, whereas they are key for project actions addressing needs of a particularly vulnerable group-women while being effective and sustainable.  In the absence of a clear vision on the management of agro-sylvo-pastoral landscapes, local initiatives have had limited impact. The inter-cantonal dimension of the dialogue and the deliberations for planning investments and use of the landscapes are essential for enhancing positive impacts on ecosystems while avoiding potential conflicts. ANGMV needs to build strategic alliances with LCBC for ecological monitoring, and DTSs, policy-makers, programmes and projects, in order to transform its approach to planning and execution.

- GEF resources will help build a framework for dialogue in each province for financial and technical partners (FTPs) engaged in agricultural development and climate investments. FTPs will be federated around a local land use and natural resource management plan that will involve the delegations for Land Planning (DLPs), local projects and local land users organized in LBODs. These five-year plans will incorporate a coherent adaptation strategy to address CC, rationalize investments, and harmonize approaches between FTPs to increase impact. The project will support the four provinces to strengthen planning and monitoring capacities within the Provincial Action Committees (CPAs).

Barrier 2: Sectoral agencies lack capacity to propose and implement actions that take into account climate change adaptation and markets.

- Rural communities are increasingly combining agricultural, pastoral and freshwater production systems, in order to reduce risk and optimize the management of landscapes and resources. Extension approaches therefore need to integrate the different technical services in the provinces taking into account local adaptation strategies. Innovations in techniques and practices need to be sustainable, socially acceptable and economically viable.

- There is poor research and extension capacities in the country. For example, the results of an assessment of the national agricultural research and extension system done in 2008 are still valid as the State is still incapable of providing extension for all the main crops in the country. The national extension system is hindered by lack of information and technical knowledge of innovative practices that are adapted to climate change. Extension programs are segmented, focused mainly on cropping and livestock raising techniques, rather than on the ecosystems and their interdependencies, notably between farming, livestock production and the environment. Extension approaches are top-down, with little integration of local knowledge, or adaptation to ecological challenges, such as the reduction of soil fertility and pasture production, the drying up of streams and ponds and the siltation of wadis and polders. Government funding of research and extension is also weak hindering generation of new information and transfer of technologies between research bodies and agro-silvo-pastoral stakeholders.

- GEF resources will strengthen the capacities of the decentralized technical services to adopt and sustain an integrated approach in the dissemination of innovative technical-economic models adapted to climate change and to markets. A multi-disciplinary team consisting of three decentralized technical services (Agriculture, Livestock and Environment) will be established and supported by the project to disseminate techniques and practices adapted to climate change and to the social environment as well as to market demand. Particular attention will be paid to gender, women and youth empowerment, in order to facilitate inclusive and equitable local transformation.

Barrier 3: The land law dates back to 1967 and has not been designed to take into account current human and livestock population pressures on natural resources, and climate change.

- Natural resources are facing considerable pressure from population pressure, increased completion and climate change which are impacting livelihood activities, land and resource use strategies and rights to property and resource use. Relations with the land are modified by new livestock grazing practices. Land acquisition by urban elites in fertile alluvial plains in Hadjer Lamis and in the South of Lake are starting to give rise to landlessness. Conflicts are numerous, diverse and not well addressed within the current legislative frameworks.  Inter and intra-community conflicts are attributed to access and management of pastures and water resources (seasonal water bodies, pastoral watering holes).

- A number of legal texts define the land allocation mechanisms, notably the Law N°23/PR/67 of 22 July 1967, on the status of State land, Law N° 24/PR/67 of 22 July 1967 on the formal land regime and customary rights, and Law N°25/PR/67 /PR/67 of 22 July 1967 on the limitation of land rights. These laws turn out to be obsolete in terms of addressing changes and problems in land use and access to land. In Chad, three land rights regulation systems are juxtaposed, customary rights that are controlled by traditional chiefs, islamic law administered by religious chiefs and modern rights administered by the State. The latter is little known among Chad’s citizens. In Chad’s customary rights’ systems, the land managers are the local chiefs who are the guarantors of rules agreed by the communities. Under modern land law, the State is the holder of the land and assures its distribution, while recognizing use rights of local communities. Therefore, the State can wield important power to improve access to newly equipped areas.

- The land question is very sensitive in Chad and warrants a thorough dialogue. The new text on the Livestock Law that was submitted to the national assembly has not been adopted, which demonstrates the complexity of this political subject matter. The Chadian State wants to have certain use rights recognized for local communities, but the legal problems linked to land persist, in the absence of a redefinition of the rules and of local institutions to apply them.  Rural communities need to be fully engaged in the management of natural resources, alongside the State. This implies the adoption of the principle of a “just and equitable sharing” of production areas, and the promotion of a participatory management of natural resources. Improving capacities of rural communities to advocate for these and other issues is thus paramount.

- The fact that climate change is not taken into account in the legislative and regulatory texts on land – which are obsolete – does not favour the resolution of conflicts nor adaptive management to sufficiently address current complexities from climate variability to resource scarcity. In addition, the technical services don’t integrate the CC dimension sufficiently in their extension themes and there are no training facilities for teaching land use models adapted to climate change.

- The GEF resources will facilitate a policy dialogue and consultations at local, provincial and national level, based on the Voluntary Guidelines for the Responsible Governance of tenure. The project aims to also address the constraints to access land for women and certain other discriminated groups (displaced people and youth) and secure resource use rights for these groups. The project will facilitate dialogue and discussions with traditional Chiefdoms, crop and livestock producer organizations, and associations for securing land use rights and redefining the rules for the use of rural landscapes. The local-level results of the project, and of other relevant efforts, will be shared and compiled in a National Land Forum, in order to accompany the land law reform process together with the State, the National Commission on land law reform, representatives of traditional chiefdoms, representatives of land users, civil society and the private sector. These exercise will also be sources of knowledge and improved capacities for local communities to negotiate and advocate going forward their claims to and access rights to natural resources and their subsequent management.

Barrier 4:  National climate change adaptation policies and strategies are not translated into action at local level.

- In Chad, many policy documents and legal texts have integrated the dimension of climate change, but these texts have not been translated to modify the land use practices of rural producers. The project will contribute to the dissemination of three laws and their application texts, supported by public agencies, civil society (HC-CACT) and traditional Chiefdoms. It will improve certain institutional aspects in order to coordinate and execute measures for enhancing adaptation and resilience at local level. The project will help create a local-level planning unit in the Governor’s Office led by the delegation for Land Planning and composed of decentralized technical services. At central level, the focal points of the ministries concerned will be strengthened to bring about cross-sectoral synergies. The key is to mobilize financial resources to implement provincial- and local-level climate change adaptation plans as well as ensuring coherence within the various CCA interventions. Therefore, land use planning will help structure local organizations and mobilize funding in close collaboration with the national execution team.

### THE GEF ALTERNATIVE

### The Project strategy

- Improving provincial environmental governance to enhance climate change adaptation. The strategy for this GEF project recognizes that vulnerability of local livelihoods due to climate change and vulnerability to food and nutrition insecurity are closely related. This requires a systemic approach combining the improvement of environmental governance to protect ecosystems and restore degraded lands, thus increasing resilience of production systems on the one hand, and sustainable economic development to improve agro-pastoralists livelihoods and market access on the other hand. Scaling up this approach in turn requires improving the framework for planning and implementing CC adaptation investment strategies, and strengthening cross-sectoral policy dialogue to better align sectoral strategies.

- The GEF project will support the National  Land Use Planning Scheme (SNAT) through supporting provincial government bodies (PACs grouping main DTSs and DLPs) to formulate, implement, monitor five-year CC Adaptation Plans and coordinate Financial and Technical Partners (FTPs). SNAT has divided the country into six regions for investment programs. The project area covers the Grand Kanem region and part of the central region (Hadjer Lamis). The GEF project will support the regional participatory formulation process of five-year CC Adaptation Plans, incorporating provincial-level investments, to be co-financed by the three main strategic financial partners investing in the area through national and regional projects: AfDB / P2RS and PRESIBALT, IFAD  / REPER, and World Bank / PRAPS and PROLAC (see tables 4a and 4b).

- The Ministry of Land use Planning, Housing Development and Urban Planning (MLPH) becomes a new key player for regional development and planning and to lead the policy dialogue on land reform. DLPs are responsible for planning and monitoring provincial plans while CPAs implement them with ANGMV, chiefdoms and land user associations represented in multi-stakeholder platforms.

- Priority areas for the GEF project in the four provinces are those with: (i) the highest concentrations of people and livestock, located along the lake and the wadis, and, for livestock, between the Sahelian and Saharan zones (rainfall: about 200 mm/year) around pastoral wells, ponds and along transhumance corridors. The pastoral zone will be mapped and monitored (carrying capacity, herd size and fodder production, pastoral wells and ponds, biomass level) with herders' organizations and technical agents; (ii) Production and marketing potential for spirulina, sesame,  animal feed and dried tomato/okra value chains; (iii) Presence of FTPs investing in  infrastructure in the areas of investment targeted by the GEF project.

- Investment and implementation strategy with FTPs. Despite the EU’s strong support for strengthening the national policy framework, including the land law reform process (pastoral and land code), and the design of the SNAT and the Water and Sanitation Master Plan, its field-level investments are all executed by NGOs, in order to improve the delivery. These resilience investment projects, however, lack meaningful involvement of local public institutions. NGOs provide seed and distribute small ruminants to target groups, and organize HIMO employment schemes. Without provincial plans led by the Governors, however, investment planning is inexistent and coordination between local partners is weak. NGOs tend to support short-term actions that rarely include medium to long-term CC adaptation measures, and therefore have a limited impact and weak sustainability and often lack ownership with the beneficiaries.

- AfDB and IFAD are supporting projects involving national and provincial government bodies. The Delegations for Land Use Planning (DLPs), however, are not supported, whereas in a context of weak decentralization, they represent a strategic administration to plan and monitor local action plans, in partnership with traditional chiefdoms and land user’s organizations. Therefore, the GEF project will build financial partnerships with projects meeting three conditions: (i)  ministerial leadership and national execution; (ii) strong involvement of provincial DTSs; and (iii) investment in infrastructure related to CC adaptation actions.

- The GEF resources will complement the activities financed by these strategic financial partners by financing vigorous capacity development programs for four local technical administrations (DTSs for Agriculture, Environment, Livestock and Land Use Planning); and investments in four priority areas to face climate threats: (i) Pastoral and agricultural Water infrastructure; (ii) Energy; (iii) Food and nutrition security; and (iv) Sustainable NRM.

- The GEF project will establish, and enhance the capacity of a national execution team comprised of five officers nominated by their respective administration and led by the GEF focal point to ensure effective liaison between the national and provincial levels, mobilize and diversify funding to support provincial CC adaptation measures. The project will also support the planning and coordination processes at the provincial level through strengthening four local public services and two national agencies, ANADER and ANGMV. Because of the highly innovative nature of the project interventions – cross-sectoral land use planning, CC adaptation investments – FAO will provide strong technical assistance to this national executing team and to DLPs, ANADER and ANGMV, in order to enhance their participatory planning and implementation capacity.

- Supporting dialogue and strengthening rules and regulations on land and natural resource use through the establishment of Local Bodies for Dialogue and Decision (LBODs) composed of local chiefdoms and farmers and herders’ associations. These new multi-stakeholder platforms at the inter-cantonal level are key players to formulate and implement landscape-level investment plans that take into account CC adaptation.  The local land users’ associations, representing the interests of all local stakeholders, will be the main interlocutors for the planning of land use investments with ANGMV and local public institutions. LBOD, supported by NGOs and HC CACT financed by the GEF project, will facilitate dialogue between the administration, ANGMV and traditional chiefdoms and promote access to fertile land and natural resources for discriminated social groups such as women, youth and displaced persons.

- Supporting the policy dialogue on land reform process. The main stakeholders for this policy dialogue are: (i) National sectoral ministries (Livestock, Agriculture and Environment) and the MLPH (including its delegations who are responsible for planning  at the provincial level); (ii) the civil society, professional organization and private sector representatives, who are the users of land and natural resources, and who are confronted with the negative impacts of climate change and human and livestock population pressure; (iii) Chiefdoms and the HC-CACT for rules on the use of land and natural resources, conflict mitigation and social reform to fight against discrimination; (iv) NGOs such as OXFAM which supports the establishment of multi-stakeholder platforms for dialogue on the governance of land and natural resource tenure, and who participate as resource persons in the formulation and implementation of the provincial plans, and in the policy dialogue at the national level.

- FAO will provide TA to guide the land reform process and to support innovations such as drip irrigation, online GIS, digitalization of public services, agro-ecology and methodology of work especially for the national team.

- Project implementation strategy. The first year of the project will be dedicated to: (i) Staff recruitment, procurement  of equipment for the project, information and communication campaigns on the project strategy in the cantons, and baseline studies to update and fill gaps in the baseline assessments conducted during project preparation; (ii) Setting up of multidisciplinary teams composed of technicians in each province and providing training on the APFS approach, the use of tablets and drip irrigation, and identifying techniques and varieties adapted to CC with agro-pastoralists; (iii) Investment in demonstration FFS to train facilitators in nine pre-identified techno-economic models resilient to CC; (iv) Organization of inter-cantonal consultation workshops to set up the LBODs, elect the members of the bureau, undertake land and resource tenure negotiations and codify use rules; and (v) Design of five-year climate change adaptation agro-sylvo-pastoral and freshwater management plans (PCCAs).

- Years 2 and 3 are dedicated to: (i) Implementation of the PCCAs with DLPs, PACs, DTSs, LBODs, ANGMV, and private sector; (ii) Capacity building programs for local organizations, especially on the Voluntary Guidelines for Responsible Governance of Land and Other Natural Resources (VGGT), on ecologic M&E with the use of landsat images, and implementing capacity for the national team.

- Year 4 prepares the exit strategy of the project by: (i) transferring the skills and equipment managed by the project to the local planning units led by DLP within each Province under the responsibility of the Governing Body and in liaison with the CPA; (ii) mobilizing new technical and financial partners to engage them in execution and updating of the PCCAs ; (iii) facilitating partnerships between smallholder producers (including their organizations) and rural financial service providers and private sector buyers to support inclusive and competitive value chains; (iv) encouraging Haut Conseil aux collectivists autosomes et aux chefferies traditionnelles (HC-CACT) to take over support of LBODs; (v) professionalizing of services such as solar maintenance, small mechanics and rural crafts and the digitization of extension services.

- The following depicts the main results to be delivered by the project:

Figure 4. Summary of expected project results

### Project objectives, outcomes and outputs

- The overall objective is to increase the resilience of agro-sylvo-pastoral and freshwater production systems to climate change in four provinces downstream of the Lake Chad Basin (BEG, Kanem, Hadjer Lamis and Lac).

- The main results expected from the GEF project are:

- Improved local governance through dialogue, planning and co-ordination in order to mobilize funds in favour of CC adaptation measures. The four DLPs and Provincial Action Committees (CPA) and a national cross-sectoral team led by the GEF focal points will be professionalized.

- Improved resilience of ecosystems to CC through the development of pastoral and agricultural areas. Through improving access to water, energy and fixation and restoration of dunes to combat siltation of polders and wadis, and restoring degraded lands. Strong dialogue between various public and private stakeholders organized into multi-actor platforms will be supported to decrease conflicts over the management of natural resources and strengthen local regulatory systems as well as facilitate better application of laws and use rules.

- A more effective extension system through multidisciplinary teams composed of three decentralized technical services (Agriculture, Livestock and Environment) to promote FFS approach and new techniques and know-how, especially digitalization. The project will support the recruitment of female technical staff and improve social inclusion and gender-sensitivity of land use interventions. Nine Technical models (9) adapted to CC will be promoted, as well as innovative techniques and practices piloted by farmers and herders that are worthy of replication.

- An increase in agricultural and fodder production and market development for sesame, spirulina, dried vegetable products, fodder and other livestock feed with strong participation of women and youth (80% of participants in target groups).

- Enhanced political dialogue between the local and national levels, especially on land tenure issues, in order to improve land use rules and regulations and disseminate three laws and their respective implementation texts in the Provinces.

Figure 5. Schematic view of the three main areas to be developed and monitored with geospatial tools

- The project objective and results will be realized through the implementation of the following three technical components plus one cross-cutting M&E component.

Component 1: Strengthening provincial governance to reduce the vulnerability of agro-sylvo-pastoral and freshwater production systems to the adverse effects of climate change.

Outcome 1.1: Governance is improved at the provincial level to identify, prioritize, monitor and evaluate CC adaptation strategies and measures.

- As already mentioned, provincial governance is weak, leading to limited impact and lack of sustainability of interventions, whether on natural resources or on local livelihoods. In the absence of medium to long term provincial plans and of dialogue with local organizations, interventions fail to create synergies necessary for optimal impact.

- The EU has funded water resources management plans in the provinces to improve access for human and livestock (2012-2017). The P2RS program is also financing human and livestock water supply in BEG and Kanem. These investments have not led to the establishment of a sustainable financing mechanism to continue planning efforts to further CC adaptation investments. Public planning and technical service institutions at the provincial level (delegations for Land Planning – DLPs and DTSs) have received little support to improve governance and poorly – in terms of human resources, capital and transport.

- The GEF project will address these gaps by strengthening planning and coordination capacities of DLPs in the four target provinces, who will lead the development of participatory and gender-sensitive CC adaptation plans, in close collaboration with multi-actor platforms representing various use interests.

- Three government bodies will be strengthened at the local level: the DLPs and Provincial Action Committees (CPAs), DTSs, and the Great Green Wall National Agency (ANGMV). In addition, the project will assist in the creation and support of new land user platforms in the provinces – Local Bodies for Dialogue and Decision (LBOD). The LBOD is a model that has been successfully tested in other provinces of Chad, in projects supported by the EU and GIZ. The LBODs include customary chiefdoms as well as local associations and professional producer associations representing various types of users. The LBODs will serve as important platforms for discussion and decisions on provincial CC visions and land use plans – taking into account CC adaptation – and for their implementation with local chiefdoms and users.

- Three outputs are expected to contribute to the first outcome:

Output 1.1.1: Four (4) five-year Provincial climate change adaptation Plans (PCCAs) are developed and implemented, one in each of the four Provinces covered by the project.

- Resource mapping and inventory. This activity will be carried out by a team of four (4) national and two (2) international experts, working together with financial and technical partners (FTPs).

- Resource mapping will lead to zoning of landscapes (wadis, dune lands, shifting sand dunes, cropland, agro-pastoral and pastoral land) complemented by resource inventory (forests, non-timber forest products (NTFPs), forage, spirulina, fish, pastoral wells and natron, etc.), and by technical studies and complementary field surveys carried out in each province by the four (4) national experts. These resource mapping exercises aim to: (i) Idefine the current ecological situation (degree of siltation, evolution of water tables and watering points, state of pasture, NTFPs and spirulina) and social situation (sources and types of conflicts, conflict resolution methods, regulatory systems and discrimination) ; (ii) Prioritize degraded areas to be restored ; and (iii) Identify local institutions responsible for managing natural resources and for assessing discriminations on access to land and resources.

- Plan design. On the basis of these ecological, technical and socio-economic studies, a five-year Provincial Climate Change Adaptation Plan (PCCA) will be formulated for each province with the support of the national and international experts to quantify the activities to be carried out, the territories to be developed and partnerships to be supported. The expert team will work with DLPs and Provincial Action Committees (CPAs) to facilitate the participatory development of the PCCAs through strategic planning workshops engaging representatives of crop and livestock producer organizations, traditional chiefdoms which are members of LBOD, ANGMV and FTPs. The project will ensure that women are represented in this process.

- PCCAs will be placed under the responsibility of the Governorate and executed by the four DLPs in close collaboration with the CPAs. The DLPs will be responsible for monitoring its implementation. With a duration of five (5) years, each plan will define a common vision of development resilient to CC. The Investment Plan will be implemented in a participatory manner, through structuring and mobilizing local communities and collaborating with financial and technical partners (FTPs).

Output 1.1.2: The planning, monitoring and coordination capacities of the four DLPs and the four PACs are strengthened.

- Equipping of DLPs and PACs. DLPs will be equipped with, two 4x4 vehicles (one by program-region), 4 computers and printers, solar panels for energy , 4 tablets and Internet connection to design and monitor the provincial plans

- Online GIS will be developed with support from FAO’s geospatial experts, to monitor land use and restoration investments in partnership with ANGMV and LCBC, for better decision-making and partner coordination.

- PACs will be supported to organize quarterly meetings to coordinate all stakeholders, engaged in the implementation of the plan

Output 1.1.3: At least four Local Bodies for Dialogue and Decision (LBODs) are created and strengthened.

- LBODs, consisting of representatives of land and natural resource users (producer organizations, pastoralists, women and young people) and traditional chiefs, will be established. These inter-cantonal consultative platforms will have the mandate to facilitate the integrated and concerted management of natural resources and to define management rules conducive to CC adaptation, and to reduce community and inter- community conflicts. They will allow traditional chiefs to learn new rules and decision modalities by formulating and signing Charters on the management of landscapes, land and natural resources. They will contribute to better integration of farming and pastoral activities, in order to reduce conflicts and protect resources (pasture, forest and freshwater resources). They will facilitate social change through information sharing and advocacy. This will help to ensure equitable access to resources for women, youth and other marginalized social groups, and support the implementation and planning of development projects over time.

- Three main activities will be funded with GEF resources:

- Two information and communication campaigns targeting traditional chiefdoms during the first two years of the project. A communication plan will be developed at project inception (Cf component 3) that integrates this activity. A Letter of Agreement (LoA) will be signed in year 1 and year 2 with the High Council of Autonomous Communities and Traditional Chiefdoms (HC-CACT) to carry out information and communication campaigns in order to sensitize customary chiefdoms on the project, including on the purpose of LBODs, project objectives and benefits, funding and participation modalities in the development and implementation of PCCAs.

- LBOD creation, promotion campaigns to prioritize local interventions, negotiations on access to land, elaborating landscape and resource management charters are activities that will be entrusted to an international NGO. The latter, in collaboration with the HC-CACT, will help LBODs to define the statutes and by-laws, codify use rules and enforcement provisions – and have these recognized by the provincial administration, to plan annual investments with traditional chiefdoms and to execute the multi-stakeholder agreements. The NGOs will transfer the management of these structures to HC-CACT. The LBODs will be established during the first two years, after the local organizations’ identification phase. They will be formalized through legal provisions. Consultative workshops gathering canton chiefs and other users will be held in order to prioritize actions and sign execution agreements (4 workshops per year and per province).

- Capacity building of LBOD members: LBOD members’ capacities will be built to engage in multi-stakeholder processes, and in conflict prevention and resolution. Gender concepts, non-violent communication, CC adaptation strategies, contract negotiation and execution (2 training workshops per year) will also be covered. Consultations on land tenure will be facilitated with the traditional chiefdoms to decide upon the areas to be developed, types of developments, use rights and rules, and the physical and financial participation of the beneficiaries during activities. The LBODs will support Plan implementation at inter-cantonal level. They will sign execution contracts with the Great Green Wall National Agency (ANGMV) and private companies.

Outcome 1.2. Agro-sylvo-pastoral and freshwater production systems’ vulnerability is reduced and natural resource management regulation is strengthened.

- Two outputs are expected to contribute to this second outcome.

Output 1.2.1:  PCCAs implemented: water access is improved, pastoral land is restored and cropland is developed with drip irrigation schemes (water supply, equipment and technical advice).

- This product relates to the structuring of GEF investments to support the climate change adaptation agro-sylvo-pastoral and freshwater management plans (PCCAs), which is the project’s main tool to facilitate CC adaptation of local people’s livelihoods. A public-private partnership (PPP) will be supported for the implementation of actions coordinated by the DLPs and executed by the ANGMV and the private sector, with the participation of LBODs. This inclusive and participatory concept promotes linkages between the cantonal, provincial and national levels.

- Multi-stakeholder agreements will be signed between the Project, ANGMV, private hydraulic companies, LBODs and the beneficiary chiefdoms to execute annual plans. Consultations with local communities will be carried out three months before each intervention, to agree on user rules, stakeholder responsibilities, and to organize activities to be carried out by ANGMV. HC-CACT will sensitize traditional chiefdoms to involve them in LBODs and facilitate access to lands for women youth and marginalized groups. NGOs will build the capacity of LBOD members to assist with business planning and mobilize civil society for participation in local policy dialogue feeding the national policy dialogue on land reform (component 3).

- ANGMV will carry out four main activities for the project: (i) extensive half-moon mechanical ploughing combined with HIMO works between May and July (3 months of intensive work per tractor); (ii) the distribution of fodder seeds to pastoralists to sow in degraded lands; (iii) ecological monitoring of restored areas and management of an ecological database and of an online GIS in close collaboration with LCBC; (iv) implementation of the drip irrigation program in consultation with authorities in charge of Agriculture, the solar program for hydraulics and infrastructure for the Ministry in charge of Environment and the forage program with the Ministry of Livestock. Each sub-program will benefit an agreement and will be a strategic document for resource mobilization.

- The investments will be co-financed by investment-oriented projects in the four target provinces. In BEG and Kanem, the GEF project will partner with P2RS for financing complementary activities for infrastructure such as pastoral and vegetable wells and warehouses. GEF resources will finance solar pumps and panels and the maintenance system, drip irrigation and land restoration. Negotiations will be conducted during implementation by the project national team to establish additional co-financing partnerships, for instance with IFAD and Wold Bank projects outlined in table 4b. Table 5 below highlights areas of investment supported by the GEF project and FTP co-financing investments.

Table 5. Area of investment for CC adaptation action, co-financing sources and result indicators

| Area of Investment for CC Adaptation actions | Co-financing | GEF | GEF Result Indicators |
| --- | --- | --- | --- |
| Targets | - 500,000 people - Project area: 15 cantons amongst the most populated with high pressure of animals in two regions defined in the NTDPS: the overall Grand Kanem and one province out of three of the central region (Hadjer Lamis) |  |  |  |
| Restoration of degraded pastoral lands |  | X | 20,000 ha of pastoral and agropastoral lands (5000 ha in each province) |
| Pastoral water supply | X | X | 150 solar pumps for pastoral and horticulture wells and maintenance system functional (Solar Program/ Ministry of Environment) |
| Village water supply | X | X |  |
| Drip irrigation | X | X | 150 ha are irrigated with drip irrigation for vegetable production and 500 ha of agro-forest land (hedgerow, orchards, date palms, and agro-forestry parks) (2,500 beneficiaries including 80% of women and young people) |
| Energy Supply for storage infrastructure and service providers |  | X | 4 energy service providers to support micro processing, 100 solar panels and 50 solar ovens |
| Strengthening public and private services | X | X | - 100 nursery gardeners trained and established (20 to 30 per province) - 200 technicians are trained in maintenance of solar pumps and electricity, installation of drip irrigation systems, Farm Machinery Operators, craftsmen. |

- The project will  support CC adaptation taking into account three strategic zones to be developed and restored: vast pastoral zone (around 80 percent of the territory), the agriculture zone in the dried plains (Hadjer Lamis) and fertile depressions where water table is close to the surface, the polder lands in the Lac province,  and the wadis lands in the Kanem and BEG provinces; and finally, the agropastoral lands around the villages and the wadis which are overused by both agriculture and livestock activities.

Output 1.2.2 Planning and implementation capacities of the National Agency for the Great Green Wall (ANGMV) are strengthened.

- ANGMV does not have an action plan for its agro-sylvo-pastoral management activities and is actually going through a financial crisis putting into question its intervention strategy for supporting climate change adaptation activities. In 2019, the Ministry of Environment gave the ANGMV the new mandate of implementing the national plan for restoring degraded lands, which foresees restoration investments in the 23 provinces of Chad. The GEF project will take into account this plan to prioritize areas of investment, in close collaboration with LBOD and DLP Planning Units. ANGMV’s involvement in implementing the GEF project will strengthen its planning capacity, by strengthening its links with DLP Planning Units and LBODs to facilitate identification and mapping of the areas to be managed or restored.

- ANGMV has a head office for the General Directorate in N’Djamena as well as two branch offices in the provinces. The agency has a considerable stock of heavy equipment, including trucks and vehicles and heavy machines for earth works, acquired a few years ago for land restoration activities. This capacity needs to be improved and complemented with additional resources to allow the agency to implement the restoration plan.

- Four activities will be funded:

- Diagnosis of training needs will be carried out during the first year to help design a capacity building program for the Agency's human resources and partner structures. This diagnosis will assess both the current skills and approaches of the Agency, and improvements needed, by drawing lessons from the past to better address CC challenges. Methodological capabilities will be improved together with ICRAF and FAO).

- Support to the mapping unit for baseline technical studies in order to map the ecological zones to be monitored and developed, in collaboration with livestock administrative units.

- Ecological monitoring of restored areas and resources with the ministry of livestock in close collaboration with LCBC. The Agency will become a consultative and advice structure for the ministry, herders' organizations and users’ associations (LBOD) to help optimize herd movements.

- ANGMV Equipment. The agency will be provided with two tractors with Nardi ploughs to undertake intensive soil restoration work with the participation of nomadic and sedentary agro-pastoralists.

- The Agency will carry out restoration of 20,000 ha of degraded pastoral lands (seeding of forage and woody species with half-moon ploughing, direct seeding of tree seeds, selected shrubs and herbaceous plants in consultation with agro-pastoralists and nursery growers). Of the 20,000 ha to be restored (5,000 ha per province), one third is located around wadis and polders that are threatened by siltation. In each province, 2,500 ha will be planted in the form of an agro-forestry park, thanks to deferred small ruminant grazing measures to be taken in consultation with local organizations and women, while another 2,500 ha will be treated with assisted natural regeneration (ANR), including on dried lands of Hadjer Lamis and 100 ha of orchards in the wadis of BEG and Kanem. The Agency will introduce solar pumping systems, along with water storage tanks for 100 village and pastoral wells.

- The Agency will also carry out two sub-programmes, the first on drip irrigation and the second on solar energy in association with the units of the ministries of Agriculture and Environment to develop national capacities and revolutionize irrigation, in a sub-desert environment (see output 1.2.2). ANGMV will work in collaboration with the livestock unit and agropastoral field schools (See component 2) to develop fodder production by selecting, with agro-pastoralists, fodder seeds and other woody species useful for humans (including NTFPs such as gum arabic), negotiating with the traditional authorities to guarantee land use authorizations and access rights, and developing infrastructure to help transform practices (e.g. small ruminant penning and cattle feed value chains). The Agency will engage in supply contracts with private nursery networks and collaborate with the private sector and other financial partners.

Component 2: Enhancement and diversification of agro-sylvo-pastoral and freshwater production systems.

Outcome 2.1.   Agro-sylvo-pastoral and freshwater production systems are resilient to climate change through scaling up of innovative technologies, practices and know-how.

- The P2RS and REPER projects are supporting various types of value chains to improve incomes of rural communities. The main ones are: vegetable production, raising chicken and small ruminants. P2RS plans to fund a feasibility study for the establishment of drip irrigation perimeters. GEF resources will complement these projects through strengthening extension methods and the establishment of “mother” agro-pastoral field schools (APFS) for demonstration of nine innovative technologies adapted to CC and the digitization of public services. Four promising value chains have been identified to be supported by the GEF: forage and dried vegetables (tomatoes, okra) in all four provinces; spirulina in Lac Province, sesame and gum arabic in Hadjer Lamis. The GEF project partners will help the project to reach its target groups and to facilitate linkages between public services and the private sector (partnerships, value chain contracts).

Output 2.1.1 Eight (8) demonstration FFSs and fifty (50) agro-pastoral field-schools (APFSs) are established in order to disseminate CC and market adapted farming techniques and practices.

- The Project will fund the following activities:

- Capacity building of decentralized technical services (DTSs) and ANADER by supporting an integrated local team made up of 6 agents from Agriculture (2), Environment (2) and Livestock (2) in each Province, or a total of 24 technical agents including at least 4 women to strengthen gender capacity and socio-economic vision in extension services.

The agents of each administration will be selected by ANADER and the project and trained to carry out component 2. Each agent will be equipped with a motorcycle and receives a transport allowance for the follow-up of activities, a tablet, a mobile phone and Internet connection. The project will ensure and incentivize representation of at least one female worker per team.

The technical agents will remain under the tutorship of their respective administrations but work under the responsibility of ANADER to train farmer-facilitators in the ”mother” farmer field schools (FFS) and agro-pastoral field schools.  Monthly meetings will be held for interaction and planning.

The local ANADER will be equipped with computer and related equipment to monitor crop and fodder production and yields. ANADER, local technicians and farmer facilitators (200) will be trained in the use of digitalized technical services and use of telecoms to perform extension services for CC adaptation.

- Skill development for 24 agents and 160 farmer-facilitators. Agents will be trained in (a) digitalization of services through the use of tablets (years 1 and 2, 15 person days, national expertise), along with farmer-facilitators , (b) the field-school approach (Years 1 and 2, three months) with the selection of CC and market adapted technical topics.

Three sub-programs will be developed for each of the technical units within each administration (three different contracts): (a) The drip irrigation program with ANGMV, and the organic fertilizer program with ANADER; (b) The livestock feed program based on crop residues and forage program with the Ministry of Livestock; (c) The program of assisted natural regeneration, agro-ecology, micro-pisciculture with the Ministry of Environment and ANGMV.

These three sub-programs are intertwined and aimed at supporting the agro-sylvo-pastoral approach locally and at integrating support services. Each sub-program will be managed by a ministry, and co-funded by other donors. Focal points of technical ministries and the GEF Focal Point at national level will be responsible for advocating for new funds. (See component 3).

The agents will be in charge of disseminating nine (9) techno-economic models adapted to CCs and markets and supporting and training farmer-facilitators to disseminate them among through farmer field-schools.

- Support for the establishment of “mother” farmer field schools (MFFS) and agro-pastoral field schools (APFSs).   MFFSs (8) will be established in an area of human concentration and therefore close to the markets, to become, in 5 years, mini demonstration and training centers or service hubs for crop and livestock producers in each of the four provinces. These mini-centers will be co-managed by public authorities and crop and livestock producer organizations. Investments will be concentrated there, to build training grounds for innovation.

In total, 21 basic technical training topics are planned to support CC resilient farming and livestock raising. Training topics are gender sensitive. Plant nursery networks are integrated with the CEP for the production and sale of Faidherbia albida plants, gum trees, date palms, fodder hedges and fruits.

Farmer-facilitators will be assisted in selecting one to two techno-economic models from a range of nine pre-identified models for their ability to adapt to CC and their market potential, which will then be validated and adopted by other farmers, including women.

The models will include drip irrigation, forage and feed production, small ruminant stabulation, assisted natural regeneration and agroecology (Tables 6 and 7 below).

Table 6. Technical Training Topics for Trainers (Agents and Farmer-Facilitators)

| Activity area | CC adapted topics | Number of training sessions, duration, and type of expertise |
| --- | --- | --- |
| Agriculture | Drip Irrigation | 2 sessions of 15 days / year (Years 1 and 2) x International Expert (FAO) + Tutorials and setting up an online monitoring system for trained agents |
|  | Organic fertilization and biological control | 2 sessions of 15 days / year (Years 2 and 3) x 1 National Expertise |
| Livestock raising | Fodder and livestock production | 2 sessions of 15 days (Years 2 and 3) x 2 years x 1 National Expertise |
|  | Animal stabulation and animal health | 2 sessions of 15 days x 2 years (Year 2 and 3) x 1 National Expertise |
| Environment | Agroecology | 1 session of 15 days x 1 year x 1 International Experience (FAO/ Agroecology) |
|  | Nursery work | 2 sessions of 15 days x 2 years x 1 National Expertise |
|  | Micro fish farming | 2 sessions of 15 days (Years 1 and 2) x 1 International Expertise (FAO) |
|  | Assisted Natural Regeneration (ANR) | 2 sessions of 15 days x (Year 2) x 1 International Expertise (ICRAF) |
| Processing and storage technology | Corn / sorghum silage production | 1 session of 15 days (Year 3) x 1 International Expertise (FAO) |
|  | Storage and preservation of fodder | 2 sessions of 15 days (Years 3 and 4) x 1 National Expertise |
|  | Okra and pepper drying | 1 session of 15 days (Year 3) x 1 International Expertise (FAO) |

Table 7. Nine CC adapted techno-economic models

|  | Model to be disseminated | Investments | Results and changes | Number and type of beneficiaries |
| --- | --- | --- | --- | --- |
| No. | Wadi area |  |  |  |
| 1 | Drip irrigation for vegetables, hedgerow | - Solar pumped water well + water storage tank - Dripper line for (500ha) - Agro-forestry for fertility, fodder, fruits and NTFPs (date tree, fruit tree, Faidherbia albida, moringa, leucaemia, gum arabic and Doum palm | Doubling of agricultural production of cereals and vegetables with 2-3 crops per year spread from September to June) and improvement of soil fertility. 20% growth of forage production based on crop residues by ANR Parroting and feeding of sedentary small ruminants and increase in biomass around the wadis / polder | 3.000 sedentary agro-pastoralists in wadis, 80% of whom are women and young people |
| 2 | Nurseryman Gardener | - Nursery + Kit gardening equipment for the production and sale to producers of seedlings and seeds of quality and black earth - Seed collection and organic manure | Improvement of ecosystem fertility and organic matter production | 100 (20-30 per province) of which 80% are young people |
| 3. | Stabulation of small ruminants in the dry season) | Fence for park with ruminants in natural meadow + planning + animal health | Deferred grazing in the restored areas, streamlining management of the small flock | 3,000 of whom 80% are women and young people |
| 4. | Poultry with henhouse and removable wire mesh + poultry feed + | Kit | Increased poultry and fish production; contract with urban restaurant managers | 300 with 80% of young people |
| 5. | Micro-pisciculture in a 3 m3 tray | Kit |  | 100 |
| 6. | Conservation / drying of processed products | Kit | AGR for women | 1000 / Province = 4000 of which 80% are women and young people |
| No. | Pastoral zone (semi-transhumance) |  |  |  |
| 7 | Restoration of degraded lands | - Pastoral wells with solar pumping + storage tank - ANR for pasture around wells: sowing of forage seeds + sesame and associated arboreal species (gums) with breeders. If necessary, the tree seeds are stuffed in a clay ball and sown directly with sesame after a mechanical half-moon plowing | 30% increase in forage and extensive sesame production 4-year survival rate for reforested areas: 60% | 50% of nomadic agro-pastoralists are beneficiaries 2,000 ha by province x 4 provinces = 8,000 ha |
| 8 | Support for the production of feed lines for small ruminants based on crop residues and fodder mowing. | 10 motorized quads + 30 mechanical mowers + Storage infrastructure x Fodder bank Forage and supplements conservation techniques Mills for silage rod production |  | 1,000 agropastoralist / provinces x 4 provinces |
| No. | Excavated crop and agropastoral lands (Hadjer Lamis) |  |  |  |
| 9 | Production of quality seeds + sesame production in association with gum arabic in degraded lands | Extensive half-moon plowing Seed production contract Seed collection and sale contract | Sub-regional production and sub-regional exports of sesame generating revenue for sedentary and nomadic agropastoralists of Hadjer Lamis | 1,500 farmers in Hadjer Lamis |

Outcome 2.2 Production is increased, and markets are improved for sesame, spirulina, livestock feed and dried vegetables.

- Spirulina was identified as the main focus in the PIF. Three other promising value chains in addition to Spirulina have been identified: sesame in Hadjer Lamis, Forage and livestock feed in three provinces (BEG, Kanem and Lac) and finally, dried vegetables (BEG, Kanem and Lac).

- Animal feed and fodder value chains have become critical for feeding sedentary small ruminants herds, which have increased massively due to donor programmes in recent years, aggravating pressure on fragile lands around villages and wadis. This value chain is a means to transform the extensive management of large numbers of small ruminants owned by women and youth and organize protected grazing areas. The GEF project will also target sesame in the province of Hadjer Lamis because of its good international market opportunities, especially with increasing Asian demand. Chinese collectors are already based in West Africa and Chad might become a collection area for this crop. Moreover, seeding sesame in association with Acacia gum trees is a win-win strategy tested in Sudan to restore degraded pastoral lands with agropastoralists, while increasing their incomes. Finally, the project area is producing vegetables. Drying vegetables is a means both to conserve these products and generate income for women. There is a strong national demand for dried tomato and okra.

- The project will sign Letters of Agreement (LoAs) with NGOs and crop and livestock producers’ federations to provide assistance to each of these value chains.

Output 2.2.1 Producers, especially women and the youth are integrated into profitable value chains.

- Sesame in the province of Hadjer Lamis. In close collaboration with the REPER project, the GEF project will facilitate connections and contracts between the National Federation of Farmers (CNCPRT), and Chinese exporters/buyers based in Burkina Faso, to collect, produce, sell and transport quality hulled sesame processed throughout the province, from Hadjer Lamis’ fields to Burkina Faso's markets. A funding agreement will be signed with CNCPRT and the federation of livestock producers for the extensive production of sesame to provide additional income to nomadic agro-pastoralists and encourage them to regenerate pasture.

- APFSs will be set up in Hadjer Lamis for sedentary and nomadic agro-pastoralists. It is planned to produce extensively sesame with mobile agro-pastoralists by planting it in association with gum seeds in degraded areas mechanically plowed in half-moon but also intensively sesame (400 kg/ha yield) with sedentary agro-pastoralists.

- The project will subsidize the production of quality seeds adapted to the buyers' request during the first two years of the project by validating production contracts with seed groups. Over the following two years, the project facilitates connections between buyers and producers to make Chad a collection area for this product. Alliances are facilitated between Chinese buyers, Chadian carriers and unionized groups to produce and distribute quality seeds, collect and store sesame and transport it to the processing area. The project also facilitates negotiation with banks and private operators for campaign plans.

- Spirulina in Kanem and Lac. Project preparation studies have shown that although in some areas, spirulina production has become more seasonal, it remains a very important income generating activity for poor rural women. The predicted CC will not threaten this production, given the temperature increase tolerance reported in spirulina scientific literature. An economic study will evaluate the possibilities of increasing the value generated by spirulina, by seeking more efficient processing methods, identifying more profitable domestic and international markets, and by promoting the geographical certification of Lake Chad and Kanem wadis spirulina to guarantee the unique quality of this product and its recognition at international level. The project will rely on the Chamber of Commerce to identify buyers, put them in touch with producer groups and support a quality approach. The project will subsidize equipment lines for women's groups in consultation with buyers to improve the quality of their production. Once spirulina production is scaled up sufficiently, the buyer may be able to obtain a fair-trade label (and a price premium) on international markets. The validation workshop underlined the need to build the entire Chadian certification system which does not exist.

- Forage and livestock feed are of strategic importance for the management of agro-pastoral lands, in all areas. Their production requires changes in the herding and feeding practices of small ruminants. Groups of young farmers are supported in the production, mowing and storage of fodder in fodder banks with the involvement of female small ruminant herders. Small equipment such as corn/sorghum silage crushers (50), mechanical mowers (50) and quad tractors (10) will be procured. The project will engage banks and suppliers to develop the sector. 10 fodder banks co-funded with P2RS will be set up in BEG and in Kanem, managed by youth and women's associations. P2RS funds the storage infrastructure according to appropriate standards and with wire barbed stalls to park small ruminants in developed areas. GEF will co-fund the electrification of the infrastructure. 20 CEAP will support this activity in all project provinces.

Component 3: Mainstreaming climate change adaptation into national and local policies and strategies.

- A regional FAO project on governance of land and natural resources funded by the German international cooperation in five Sahelian countries (Senegal, Mali, Burkina Faso, Niger and Chad) is under formulation. In Chad, the regional project anchored with the ministry in charge of Livestock will build on the results of four provincial workshops (to be held in year 1) on the Voluntary guidelines for the responsible governance of tenure (VGGT), with particular emphasis on conflict prevention, especially in pastoral areas, in order to prepare a national forum on land governance in Chad (year 3). These activities will be carried out in partnership with the National Commission on Land Reform led by the Ministry in charge of Land Use Planning (MLPH).

- In addition, GEF resources will enable the dissemination in the Provinces of three national laws and their implementation decrees, with the support of HC-CACT, local media and local authorities. Finally, GEF resources will support a national implementation team led by the GEF focal point to participate in the national-provincial liaisons, coordination of FTPs, supervision and resource mobilization to diversify funding sources for the implementation of provincial CC adaptation plans.

Outcome 3.1. Climate change adaptation mainstreamed into key national laws on management of and natural resources and their implementation at provincial level.

Output 3.1.1. Institutional mechanisms at the national level are in place to facilitate implementation and mobilize resources.

- Four main activities will be implemented to achieve this output (see also component 1 – linked to outcome 1.1 ):

- At the national level, a national execution team composed of four (4) focal points (Agriculture, Livestock, Environment and Land Planning) to facilitate implementation within each of their administrations. They will be appointed by their respective ministries to oversee the implementation during the four years with FAO technical assistance (TA). Building the integration of services at the national level, they will supervise and report to their respective administration. They will meet once a quarter to plan and manage their activities.  Focal points participate in supervision missions (Years 1, 2 and 3), 2 focal points x 21 days, and the final evaluation mission (Year 4) 1 focal point for 30 days. The GEF focal point participates in the mid-term evaluation mission (Year 3) and advocates with FTPs to mobilize additional resources to fund full implementation of the PCCAs. This will rely in part on 2 documentary films to be produced in Years 3 and 4 and on the results of the M & E to communicate on approaches and innovations implemented with local communities (drip irrigation, women's organizations, etc.).

- A communication plan on the project and on CC will be designed in the first year of the project by a national expert to be executed for two years with the HC-CACT, with whom the project will sign an LOA. The HC-CACT will sensitize the traditional chiefdoms, and the local administrations in charge of peace and security (police, army, justice) on the project, beneficiaries, the funding mechanisms, female and youth to resources, regulations concerning the management of natural resources. At national level, the communication plan will be used by the different ministries, the ANGMV and the GEF focal point to mobilize new technical and financial partners for the implementation and updating of PCCAs (Component 1) and the three technical sub-programs (Component 2). It targets different types of beneficiaries (traditional chiefs, local governments, and the private sector) and facilitates project implementation and beneficiaries’ full engagement.

- Develop a resource mobilization strategy for additional funding to support the provincial Plans.

Output 3.1.2   Three (3) national laws and their implementation decrees are disseminated.

- Act n°14, the agro-sylvo-pastoral act, the biodiversity conservation and the protected area management act will be disseminated in the provinces to raise widespread awareness among the populations of the four provinces and to identify enforcement measures that are suitable to the local settings. The project will sign an agreement with HC-CACT for three years (years 2, 3 and 4) to advocate on this legislation in all prefectures.

- Three main activities are performed to achieve this output:

- Information workshops with cantonal and religious leaders and other actors, led by the HC-CACT, and dealing with legal issues raised by implementation of legal provisions. These workshops lead to recommendations for the local application of each regulatory provision mentioned in the drafting of implementing provisions by national legal experts.

- Three provincial sensitization workshops are organized for 3 days with local administrations responsible for peace and security (6), technical units (6), representatives of LBODs ( 6) and change agents (6), to train them on the law and analyse ways to apply it at local level, with provisions to adapt it to the local context, if necessary.

- Preparation of brochures, flyers and handbooks for users in cantons.

- Radio programs funded by the project with national radio and regional emission Ndorason radio (5 for each law, meaning a total of 15 radio programs to be funded) for provincial coverage of radio broadcasts.

Output 3.1.3. A National Forum on Land is conducted at national level.

- Chad is currently in the process of updating the land and estate code, which dates back to 1967, so that it can better respond to current pressing issues such as conflicts over natural resource access and management, climate change, gender inequality, the strengthening of customary rights and the need for land tenure security. The revision of this law aims to improve land governance in Chad. It is led by a committee established by ministerial order and composed of representatives of the technical ministries concerned with land issues, representatives of civil society, international organizations, experts and University academics.

- The GEF project, in partnership with the Regional Project on the Voluntary Guidelines for Responsible Governance of Tenure implemented by FAO and with the collaboration of OXFAM, will co-finance this two-year political dialogue process (Year 1 and 2) including a national workshop on land issues, led by the national Committee on land reform.

- Several activities are co-funded by both projects:

  - The organization of four provincial workshops on the Voluntary guidelines for responsible governance of tenure with a focus on conflict prevention issues, especially in the pastoral field (Year 1). These workshops serve as a support to the preparation of the national forum on land tenure in Chad.

  - The strengthening of local and provincial mechanisms (including local branches of HC-CACT) to consult on access and control rights over natural resources, in order to improve planning and management of agro-sylvo-pastoral and freshwater resources and to agree new land use rules and practices.  Policy dialogue will also concern access to property for women, youth and marginalized groups.

  - Preparation and organization of a multi-stakeholder national forum co-financed with OXFAM/land at scale project and FAO/regional project on financed by Germany (year 2).

### Adaptation benefits

- The project interventions strengthen the resilience of agro-sylvo-pastoral and freshwater production systems in arid environments by adopting an integrated approach linking agriculture, livestock breeding and forestry. Concrete benefits to be delivered include:

  - In four years, environmental governance at the provincial level is improved by strengthening planning, monitoring, coordination and consultation between provincial and local organizations. As a result, four (4) five-year climate change adaptation agro-sylvo-pastoral and freshwater management investment plans (PCCAs) are under implementation with co-financing from financial partners.

  - The project benefits 11 000 people, including: 3 000 mobile agro-pastoralists; 5 000 sedentary agro-pastoralists farming in wadis (80% of whom are women and young people); 2 500 sesame producers (40% of whom are women and young people), 500 spirulina producers (women) and 500 village and canton chiefs.

  - 150 ha of wadi lands, including 100 ha of orchard, are developed and drip irrigated; 20 000 ha of degraded lands, including 15 000 ha of pastures and 5 000 ha of agropastoral lands around wadis/polders, are restored (set aside and developed in the form of agro-forestry parks to combat siltation) and 15 000 ha of Assisted Natural Regeneration (ANR) in pastoral zones to increase forage production. Small ruminant herds are stocked in managed areas and fed with fodder and complementary feeds.

  - 8 “mother” farmer field-schools and 50 “daughter” agro-pastoral field-schools have been set up, 24 agents, 200 farmer-facilitators and 5 000 sedentary agro-pastoralists (80% of whom are women and young people) and 3 000 nomadic agro-pastoralists are trained in techniques and practices adapted to CC and markets. 21 training topics and nine high-performance techno-economic models are disseminated with a target adoption rate of 60%.

  - In four years, Chad becomes a crop collection area especially for Chinese sesame buyers based in Burkina Faso. Fodder production increases by 30% and the quality of production of spirulina and dried vegetables is improved. The Chadian spirulina is labelled to improve prices on international markets.

  - In four years, the project mobilizes additional resources to fund the PCCAs (see (i) above), raises awareness on three laws, and improves the political dialogue on land reform.

- Although, for LDCF funding, the project is not obliged to generate GEF global environmental benefits, some of the adaptation options promoted will result in significant CC mitigation benefits. This is the case for the restoration of degraded pasture (15,000 ha), the stabilization of sand dunes and the establishment of agroforestry parks (5,000 ha).

### Socio-economic benefits

- The project strengthens environmental and land governance and political dialogue by promoting integration of technical units and consultation of users to strengthen peace, security and the socio-economic development of territories.

- The project helps to organize resource users in LBOD in order to develop agro-sylvo-pastoral and freshwater production systems in their territories. The development is conditioned by consultation between users and traditional chiefdoms to decide on the area to be invested, the type of development/infrastructure, costs, user rules, beneficiary participation to works and/or costs. The beneficiaries will define use rules for each area, which will be codified in resource management charters, including Land and Water. LBODs will be responsible for enforcing the rules in collaboration with local authority systems (traditional leaders and judicial and police/army authorities). This approach empowers beneficiaries (nomadic agro-pastoralists, families and communities) in the management of territories and natural resources. Inter-user and inter-canton conflicts are expected to decrease thanks to dialogue and improvement of local regulatory systems.

- The project improves socio-economic conditions for women and youth by developing their livelihoods and markets and by supporting transformations in their agro-silvo-pastoral and freshwater production practices. Women and young people will become important actors in the livestock feed, spirulina and dried products sectors. The project works towards improving the access of women, young people and marginalized groups to land and strengthening their rights and representational power in local public and private organizations. It promotes the recruitment of female technicians and people trained in socio-economics to ensure that technical topics meet their needs and that women and youth organizations are represented in LBODs.

- The project will develop the technical capacities of local technical agents and farmer-facilitators. It supports technical innovations and practices in parent farmer field-schools with demonstrations of techno-economic models adapted to CCs and markets.

- Drip irrigation saves labour as it is an autonomous watering process. This is a solution to a challenging constraint in the dry season. The communities can carry out two cycles of irrigated crops (October - January and February - June) which makes it possible to double the market gardening production. Drip irrigation combined with solar water pumps will revolutionize irrigation in arid conditions, under the condition putting in place sustainable financial mechanisms to support their dissemination and develop markets and take measures to avoid unsustainable levels of water extraction.

- Producers of the sesame, livestock feed, spirulina, dried food products value chains will increase their production and their income, and membership bases for producer federations are enlarged. Sector alliances with the private sector to execute contracts are promoted in collaboration with the banks and ongoing initiatives (Sesame Project, OLAC PR, etc.).

### STAKEHOLDER CONSULTATION AND COMMITMENT

### Project stakeholders

- The direct beneficiaries of the project are sedentary (5 000) and nomadic agro-pastoralists (3 000), 80% of which are women and young people. In addition, a number of institutions at local level will also benefit from the project: the 4 Provincial Action Committees (CPAs), the decentralized technical services (DTSs) (24 technical unit agents from Agriculture, Livestock and Environment) and 200 farmer-facilitators, LBODs and ANGMV - See Table 8.

Table 8. Number and type of beneficiary, execution structure and financial partners

| Type of beneficiary | Target (Number of beneficiaries) | Implementing organizations (Contracts) | Project partners (FTPs) |
| --- | --- | --- | --- |
| Farmer-facilitator | 200 FFS are trained and subsidized for develop APFSs (50) | - ANADER | - P2RS / AfDB - REPER project / IFAD |
| Sedentary agro-pastoralists | 6,000 households including 80% women (3,000 in BEG and Kanem, 2,500 in Hadjer Lamis (HL) and 500 in Lac) including: - Sesame producers in HL (2,500) - Vegetable producers in wadis (5,000) - Small ruminant herders (3,000 women and young people) - Nurserymen/Gardeners (500) - Micro-pisciculturists (100 in Lac) - Fodder processing agents (500) - Dried product processing agents (250) | STD ANGMV NGO (RESILAC, OXFAM and ACORD) | - P2RS / AfDB - REPER project / IFAD - Sesame project / UNIDO |
| Mobile agro-pastoralists | 3,000 poor agro-pastoralists, 100% of whom are men | STD ANGMV | - P2RS / AfDB - REPER project/ IFAD |
| Spirulina producers | 500 in Lac and Kanem | NGO | - FAO/TCP |
| Craftsmen | 500 well diggers, ironmongers, electricians, and mechanics | FAO | World Bank project on skills development |

- Institutional stakeholders are summarized in Table 9 below.

Table 9. Number and type of institutional stakeholders, their roles and benefits

| Type of beneficiary organization | Number | Benefits |
| --- | --- | --- |
| DLP/Planning unit | 4 | Equipment: 2 vehicles + 8 motorbikes 4 Computers and Office Kits and 4 tablets + internet access - Technical assistance from FAO |
| DTS | 24 agents including 30% women | - Equipment: motorcycle, tablets, internet access 4 Computers and office kits + 8 motorcycles - Capacity building: FFS approach, farming techniques, gender mainstreaming and factoring and digitalization services |
| ANGMV | 2 Officers | - Investment: 2 tractors with Nardi ploughs - Diagnostic study for Agency staff skill development - Mapping system and ecological monitoring - Three funding agreements: the first with a duration of 2 years and the following two with a duration of one year to execute development plans |
| LBOD | 250 user representatives and traditional leaders | - Support for planning capacity structuring and strengthening and for sustainable environmental management and conflict mitigation, social justice - Information and communication - Policy dialogue on land |
| HC-CACT | 6 Experts (2 per region) | - CC information and communication campaign in traditional chiefdoms, LBOD and popularization of national laws (6 months a year, year 1 and 3) |
| Focal Points (FP) Agriculture, Livestock, Environment, Territory planning and GEF | 5 | - 3 supervision missions for 2 FPs (Years 1, 2 and 3) + 1 evaluation mission for 1 GEF FP (Year 4) - Staffing for quarterly planning workshop |
| Producer' and breeder’ Federations (CNCPRT) | 2 | - Implementing agreement x Structure FOs at the grassroots level and help them connect to the markets through industry contracts |

- A full description of implementation arrangements and how stakeholders will be engaged in execution is given in Section 2.1 Implementation Arrangements and in Appendix V Stakeholder Engagement.

### Grievance mechanism

- FAO is committed to ensuring that its programs are implemented in accordance with the Organization’s environmental and social obligations. In order to better achieve these goals, and to ensure that beneficiaries of FAO programs have access to an effective and timely mechanism to address their concerns about non-compliance with these obligations, the Organization has entrusted the Office of the Inspector-General with the mandate to independently review the complaints that cannot be resolved at that level.

- FAO will facilitate the resolution of concerns of beneficiaries of FAO programs regarding alleged or potential violations of FAO’s social and environmental commitments. For this purpose, concerns may be communicated in accordance with the eligibility criteria of the Guidelines for Compliance Reviews Following Complaints Related to the Organization’s Environmental and Social Standards, which applies to all FAO programs and projects.

- Concerns must be addressed at the closest appropriate level, i.e. at the project management/technical level, and if necessary at the Regional Office level. If a concern or grievance cannot be resolved through consultations and measures at the project management level, a complaint requesting a Compliance Review may be filed with the Office of the Inspector-General (OIG) in accordance with the Guidelines. Program and project managers will have the responsibility to address concerns brought to the attention of the focal point.

- The principles to be followed during the complaint resolution process include: impartiality, respect for human rights, including those pertaining to indigenous peoples, compliance of national norms, and coherence with the norms, equality, transparency, honesty, and mutual respect.

Project-level grievance mechanism

- The project will establish a grievance mechanism at field level to file complaints during project inception phase. Contact information and information on the process to file a complaint will be disclosed in all meetings, workshops and other related events throughout the life of the project. In addition, it is expected that all awareness raising material to be distributed will include the necessary information regarding the contacts and the process for filing grievances.

- The project will also be responsible for documenting and reporting as part of the safeguards performance monitoring on any grievances received and how they were addressed.

- The mechanism includes the following stages:

- In the instance in which the claimant has the means to directly file the claim, he/she has the right to do so, presenting it directly to the Project Management Unit (PMU). The process of filing a complaint will duly consider anonymity as well as any existing traditional or indigenous dispute resolution mechanisms and it will not interfere with the community’s self-governance system.

- The complainant files a complaint through one of the channels of the grievance mechanism. This will be sent to the Project Coordinator to assess whether the complaint is eligible. The confidentiality of the complaint must be preserved during the process.

- Eligible complaints will be addressed by the Project Steering Committee (PSC). The PSC will be responsible for recording the grievance and how it has been addressed if a resolution was agreed.

- If the situation is too complex, or the complainer does not accept the resolution, the complaint must be sent to a higher level, until a solution or acceptance is reached.

- For every complaint received, a written proof will be sent within ten (10) working days; afterwards, a resolution proposal will be made within thirty (30) working days.

- In compliance with the resolution, the person in charge of dealing with the complaint, may interact with the complainant, or may call for interviews and meetings, to better understand the reasons.

- All complaint received, its response and resolutions, must be duly registered.

Internal process

- Project Management Unit (PMU). The complaint could come in writing or orally to the PCU directly. At this level, received complaints will be registered, investigated and solved by the PCU.

- If the complaint has not been solved and could not be solve in level 1, then the Project Coordinator elevates it to the FAO Representative.

- Project Steering Committee (PSC). The assistance of the PSC is requested if a resolution was not agreed in levels 1 and 2.

- FAO Regional Office. FAO Representative will request if necessary the advice of the Regional Office to resolve a grievance, or will transfer the resolution of the grievance entirely to the regional office, if the problem is highly complex.

- The FAO Regional Representative will request only on very specific situations or complex problems the assistance on the FAO Inspector General who pursuits its own procedures to solve the problem.

Resolution

- Upon acceptance a solution by the complainer, a document with the agreement should be signed with the agreement.

| Project Coordination Unit (PCU) | Must respond within 5 working days. |
| --- | --- |
| FAO Representation | Anyone in the FAO Representation may receive a complaint and must request proof of receipt. If the case is accepted, the FAO Representative must respond within 5 working days in consultation with FAO's Representation and Project Team. FAO-TD@fao.org |
| Project Steering Committee (PSC) | If the case cannot be dealt by the FAO Representative, he/she must send the information to all PSC members and call for a meeting to find a solution. The response must be sent within 5 working days after the meeting of the PSC. |
| FAO Regional Office | Must respond within 5 working days in consultation with FAO's Representation. RAF-ADG@fao.org |
| Office of the Inspector General (OIG) | To report possible fraud and bad behavior by fax, confidential: (+39) 06 570 55550 By e-mail: Investigations-hotline@fao.org By confidential hotline: (+ 39) 06 570 52333 |

### ALIGNMENT AND STRATEGIC FIT

- The project is fully aligned with the National Adaptation Action Plan (NAPA, 2010) and contributes to its implementation on four of the ten priority areas: (i) water control and management for CC adapted agropastoral activities; (ii) development of intensive and diversified crops adapted to extreme climate hazard; (iii) soil preservation and restoration infrastructure for the development of agricultural activities; (iv) improvement of intercommunity pasture areas to reduce the risk of conflicts related to migratory movements of pastoralists. . The project will also incorporate several new adaptation options of the agricultural and livestock breeding sectors identified in the second national communication to the UNFCCC (2012), entitled "promoting and disseminating new agroforestry techniques: assisted natural regeneration (ANR) ; value agro-industrial by-products and agricultural residues for livestock feed. All these priorities have been renewed in Chad's National Strategy for Combating Climate Change (SNLCC) in 2016. Finally, the project will also contribute to the adaptation priority contained in the Intended Nationally Determined Contribution (CPND, 2015) to safeguard pastoral resource use rights, transhumance improvement through community grazing areas, to the creation and extension of fodder banks.

- The project also takes into account several other national plans and strategies, including: (i) the National Development Plan (PND, 2017-2021) - which promotes economic diversification by targeting the sectors of agriculture, livestock breeding and fishing; (ii) the National Livestock Development Plan; (iii) the National Food Security Program; (iv) the National Plan to Combat Desertification (PNLCD, 2006); and (v) the National Action Plan for the Great Green Wall (PANGMV, 2010).

- With respect to alignment with the LDCF GEF strategy in relation to CC adaptation, the project will contribute to all three objectives, namely: (1) Reducing the vulnerability of people, their livelihoods, physical assets and natural ecosystems to the negative impacts of CC; (2) Strengthening technical and institutional capacity for effective adaptation to CC, and (3) integrating CC adaptation into relevant policies and plans, as well as related processes.

- With regard to FAO, the project is aligned with the three priority areas of its Country Program Framework (CPF, 2017-2021) agreed with Chad, namely (1) the development of value chains in agriculture, livestock, forestry, fisheries and aquaculture, to strengthen food and nutrition security; (2) the formulation and implementation of sectoral policies and strategies for food and nutrition security; and (3) the enhancement and sustainable management of natural resources to build resilience. The project will also contribute to strategic objective 2, intensify and improve the provision of goods and services from agriculture, forestry and fisheries in a sustainable manner, and strategic objective 5, improve resilience of livelihoods in the face of threats or crises, of the revised FAO Strategic Framework adopted by its Council in 2013.

### COMPARATIVE ADVANTAGES

- Throughout its 70-year history, FAO has developed a strong technical and management capacity based on field experience and projects that address comprehensively food security, agricultural production, forestry, sustainable management of natural resources and adapting agriculture to climate variability and change.

- In Chad specifically, the Organization has been implementing resilience projects in Kanem, BEG and Hadjer Lamis Provinces to support the livelihoods of vulnerable agropastoralists, including women and the youth. Among these projects are:

The GCP/CHD029/EC project for the development of the “dihé” value chain (spirulina) in Chad between 2007 and 2013.

Project OSRO/CHD/703/BEL “Response to pastoral humanitarian needs following the Boko-Haram crisis in Chad”

The OSRO/CHD/704/EC Project "Food security support for the improvement of the nutritional status of host, returnees and displaced populations, victims of the Boko Haram Crisis in the Lac and Kanem Regions"

Project OSRO/CHD/802/CAN "Food and nutrition security support for the improvement of the nutritional status of populations, victims of the current pastoral crisis in Lac and Kanem Regions"

Project OSRO/CHD/803/SWE "Supporting farming and livestock breeding livelihood resilience of vulnerable households, including women and the youth in Lac, Kanem and BEG Regions"

The UNJP/CHD/047/PBF Project "Peacebuilding project through adaptation to climate change and livelihood resilience of the people of the Lake Chad Region”

The TCP/CHD/048/PBF project "to prevent inter-community conflicts and contribute to the consolidation of peace through the development of resilient pastoralism in the cross-border area of ​​Diffa and Kanem (Niger/Chad)"

The project OSRO/CHD/806/IRE "Sustainable relaunch of agricultural systems in the oases of Kanem"

Project TCP/CHD/3704 "Development of the spirulina (dihé) value chain to contribute to food security and the improvement of the nutritional status of the most vulnerable populations in the provinces of Lac, Kanem and Hadjer-Lamis, Chad”

Project TCP/CHD/3703 "Improvement of oasis farming productivity in the Kanem Region"

- The execution of these projects aimed to (i) improve the food and nutrition status of host, returnee and displaced households through the purchase of cattle at subsidized prices and through dried meat distribution to households with malnourished children and mothers, (ii)  improve the living conditions of beneficiaries through the “destocking” of livestock, (iii) to build women’s capacities through savings and loan schemes the distribution of small ruminants and other agricultural activities and capacity building actions for the management and mitigation of threats and disasters, (iv) promote non-timber forest products (NTFPs); (v) build stakeholder capacities in knowledge and rational management of natural resources, and knowledge of sustainable forest resource management techniques as a means of livelihood; (v) support the climate change adaptation program through the Green Wall Initiative.

- The wadi project in Kanem has been used to test approaches to land negotiation and consultation with traditional chiefdoms, to improve women's access to wadi lands and has experimented several agro-ecological actions in the wadis. Numerous technical and organizational lessons have been integrated in the design of this proposed LDCF project and will be useful in its implementation.

### KNOWLEDGE MANAGEMENT AND COMMUNICATION

### Knowledge sharing

- The project will share knowledge with and learn from relevant projects and initiatives through various channels/mechanisms. At provincial level these include: land user platforms (Local Bodies for Dialogue and Decision) and Provincial Action Committees, bringing together multi-actors including financial and technical partners with investments in the Lake Chad Basin and in Chad – partners such as the AfDB and IFAD. At national level, the integrated national team consisting of the GEF Focal Point and officers nominated from relevant administration and the Project Steering Committee will contribute towards knowledge sharing. The national team, in particular, will serve as an important link for coordination and knowledge exchange with relevant initiatives including the following GEF/LDCF and GCF investments:

  - Community-based Climate Risk Management in Chad. This project aims to strengthen the responsive capacity of vulnerable populations to better cope with climate shocks by responding earlier to warning signals and adopting financial risk transfer mechanisms. The project is led by UNDP with the Ministry of Agriculture serving as the executing agency.

  - Chad National Adaptation Plan. The project is intended to integrate climate change adaptation into medium and long-term planning and budgeting of climate-sensitive sectors. It is also led by UNDP with the Ministry of Environment and Fisheries as the executing agency.

  - GCF Readiness: Strengthening capacities ad partnerships for assessing mitigation and adaptation opportunities and enabling their implementation in the forestry and land use sectors in the context of the Great Green Wall (GGW). This project is being implemented by

- The table below shows the proposed knowledge management plan with main products to be shared with stakeholders:

| Type of Knowledge | Key deliverables and responsible organization/consultant | How to disseminate / share the knowledge | Cost | time line |
| --- | --- | --- | --- | --- |
| Planning process | Manual for Climate Change Adaptation Plan (1) explaining the methodoly for planning through the use of Landsat images and consultation with the main stakeholders including LBODs and ANGMV. | General Directorate of Land Planning, Housing Development and Urban Planning will disseminate the manuals to the four Designated Land Planning units, ANGMV and the integrated national team led by the GEF Focal Point. | 3 Weeks x 2 consultants | The first year before the design process |
|  | Leaflets (4 pages) and national radio broadcasts to disseminate the Climate Change Adaptation Plans and the main project results per year | The integrated national team led by the GEF focal point is responsible for disseminating the leaflets to technical and financial partners including NGOs, provincial administrations and LBODs | 1 national expert - Communication x 15 m/d x 400 USD/day + Editing + 2 radio broadcasts / year x 4 years | Within the life of the project |
|  |  | One day workshop per year at the national level to inform resource mobilization | 5000 USD / workshop x 4 years |  |
| Ecological monitoring | Monitoring reports on the main results of adaptive measures on cultivated, pastoral and agropastoral zones, and on water (quality and quantity) ANGMV and Lake Chad Basin Commission. | Annually reports are disseminated by email to the General Directorate of the Ministries in charge of Environment, Agriculture, Livestock, and the national integrated team of FPs by Email. | - | Within the life of the project |
|  | Virtual site for the ANGMV mapping service |  |  |  |
| Conflicts on natural resources | Mapping of the conflicts by cantons is annually updated by DLPs and Governorates | The maps are disseminated in the Governorates, justice, police | USD for Editing | Within the life of the project |
| LBDOs | Exchange trips on lessons learned with other initiatives in Chad | 4 members of LBDO x 4 LBDO in Mayo-Kebbi | National Trip per member | Year 3 and 4 |
|  | Documentary film (30 mnts max.) National expertise - Communication | The film is shown to canton chiefs, rural groups, local administration, HC-CACT and ANGMV to sensitize on the concertation and dialogue approach | 3400 USD | Year 3 and 4 |
|  | Leaflets for the Charters | Dissemination of Land/water use rights and rules | 6000 USD for editing | Year 2, 3, and 4 |
| Lessons learned on technical innovation and in practices | National workshop to capitalize lessons learned on the integrated approach for extension services and digitalization of public services | Main technical and financial partners, representatives of the four Delegations and national administrations | 7000 USD for two days | Year 4 |
|  | 20 video Tutorials are produced for farmers and facilitators (200) | Dissemination to farmers and herders’ organizations and other partners/initiatives. | 25 000 USD | Year 2 and 3 |
|  | Leaflets on adaptive techniques (2 pages) PMU |  | 6000 USD for editing | Within the life of the project |
|  | Documentary film (30 mnts max.) on APFS approach National expertise - Communication | The film is shown to producer’s organizations, provincial administration, HC-CACT and ANGMV to promote concertation and dialogue for land users | 3400 USD |  |

A communication strategy to complement and support the implementation of the knowledge management plan will be developed in the first year of the project – as described in section 1.7.3 below.

### Lessons learned

- Local Body for Orientation and Decision platforms (LBOD) have been successfully tested in Chad since the 2000s, under the impetus of development programs and projects in the Mayo-Kebbi West Provinces (PGRN and PRODALKA) and in Ouaddai (PADL-GR N). These platforms for multi-stakeholder consultation support the organization of local NRM and environmental protection actions based on the traditional management models of community resources. The process consists of bringing together leaders of the different communities but also representatives of the various producer organizations and socio-professional groups in the framework of the general assemblies, to lead debates from which guidelines and collective decisions will emerge for a peaceful management of resources and landscapes. These inter-communal and inter-cantonal consultations prompt all stakeholders to take a new look at space and resources, the degradation phenomena observed and the means to curb them. They also provide an interface with the local administration, local chiefdoms and socio-professional organizations. The user and practice rules are clarified and codified in management charters, and conventions are signed with the ANGMV to develop the territories based on concerted plans. LBODs do not constitute new institutions in the local landscape of natural resource development and management. Actually, they bring together local actors who are mobilized around issues of sustainable use of resources (decision-making centres, farmers' organizations, heritage protection associations). The main achievement is first and foremost, learning new modes of consultation, debating on orientations and strategic decisions regarding modalities of access to common spaces and resources.

- Spirulina, by its scientific name Spirulina platensis but commonly called "dihé" in Chad is produced naturally in the wadis of Kanem and Lac. In the Lac province, the blue alga is permanently produced in the canton of Isseroom, 68 km off Bol, the canton capital, on twenty (20) sites. In Kanem, spirulina was traditionally exploited in four wadis, but due to salinization and silting up of wadis, production declined and became seasonal in only two sites. There are women's groups that are organized to produce and sell this alga, which boasts high nutritional and food value and has a potential for export and for local marketing. Chad spirulina is not certified although it has specific properties related to the ecological properties of the area. Past experience of support to women's groups show that producing higher-quality outputs, and the cost implications of equipment needed, require access to lucrative export markets to make the value chain profitable for these groups. The quality of Chadian spirulina needs to be improved and recognized through the development of value chain contracts with international buyers who may value the product under an ethical and environmental label recognizing the properties of this valuable product derived from a unique ecosystem.

- FAO developed between 2007 and 2013, a project for the development of spirulina in Chad. It is clear today that the dihé industry has much improved and generates more income for women than was the case in the past. The quantities sold, which amounted to 15 tons in 2012, are believed to exceed 500 tons now. This represent significant revenues. It is important to emphasize that there are 3 options for the development of this sector: (i) Maintain natural production without adding technologies likely to improve women’s living conditions, while sustaining production and traditional consumption by the already accustomed populations; (ii) Improve dihé's traditional production generating a strong social impact (net increase in income). This solution has the advantage of offering very low production costs (less than € 7/kg) with regard to competition (minimum € 25/kg) and a large number of potential consumers (low income population), (iii) developing intensive production in the basin which allows for better quality control and higher yields but which will however generate rather high costs (at best 25 €/kg) for a product demand which, at this price level, remains rather low.

- Currently an FAO Technical Cooperation (TCP) project on Spirulina is in progress. It will improve the quality of dihé through better harvesting, drying and packaging techniques.

- The FAO Kanem Wadi project, supported since 2010, has shown that improving the food and nutrition security of poor women living in the wadis depended on improving their access to land. The project facilitated the access of women and marginalized groups to the arable lands of the wadis by negotiating loans with landowners for a period of five years to develop market gardening. The women were trained in good agricultural practices and developed market gardening, raising small ruminants and income-generating activities. The project introduced drip irrigation which is coveted because it saves scarce labour. Line dripper suppliers have settled in N'Djamena's markets, but the technique is not disseminated by government technicians as they are not familiar with it. There is a need to support a drip irrigation program for the development of technology and to improve land access for women and youth. Technology has multiple advantages for the environment: manpower rationalization, reduced climate hazard and optimized water management and plant growth in arid environments. Drip irrigation and solar panels are revolutionizing irrigation in arid lands and are a support for land use planning strategies to develop oases. The implementation of this program by ANMGV, in consultation with ANADER, supports concerted management strategies because cropland areas are linked to pastoral and agro-pastoral areas. Access to irrigation water and the network of pastoral water points determine the success of a development program.

- ANGMV has capitalized on approach strategies in terms of planning and is in a transformation process. At the time of its creation, it had a “green wall” approach, planning to plant a “wall” of trees crossing 8 administrative regions namely Lac, Kanem, Bahr El Ghazal, Batha, Wadi Fira, Borkou, Ennedi Est and Ennedi Ouest. After the implementation of the first generation of the strategic plan and taking into account the recommendations of studies and other assessments made on the extent of the phenomena of land degradation, food insecurity, malnutrition and adaptation to climate change, the Ministry of Environment, Water and Fisheries has through a decree (No. 106/PR/MEEP/DGM/2019) on the organization and operation of the national coordination of the National Land and Biodiversity Restoration Program in the 23 Provinces of Chad, expanded the field of action and the area of ​​intervention of the Great Green Wall (GMV) to all the Provinces of the country. In the operational plan, the Agency has promoted local management approaches with village committees but has not worked on an inter-cantonal scale by strengthening consultation structures between local leaders in order to have more impact. The development of a wadi depends on the development of water points and pasture in the agro-pastoral and pastoral zone, because these resources regulate the herd/crop/forest balance. Therefore, introducing an integrated and collaborative management dimension through the creation of LBOD will allow it to transform its approach. Rural communities are no longer simply relays for the Agency, they are co-creators of a management plan formulated in consultation between users who decide to take responsibility for their lands and territories.

- Collaborative management practices condition the separation and integration of livestock, crop and forestry activities. The top-down approach works poorly. There is a need for a social and participatory approach. Technical skills must be combined with socio-economic skills to adapt techniques to human constraints and spaces. Strategies for sedentary small ruminants are not the same as those for large nomadic herds. Developed wadis where human investments are concentrated, and areas around wadis that protect them against invasion by sand dunes, as long as they are not deforested, cannot be freely accessible to pastoralists. ANGMV is a key institution for building a concerted and integrated CC adaptation strategy.

- Farmers and farmer federations in Chad need to strengthen their membership base by developing seed contracts with national, sub-regional and international buyers to boost upstream activities. Livestock breeder federations also need to support the concerted approach and spatial planning to produce and protect pastoral resources and channel livestock movements to water points, pasture and markets. There is a need to clarify the public and private space by strengthening consultation.

### Communication

- A communication plan will be developed in the first year to disseminate the project's main messages to communities and governorates, decentralized technical units, judicial authorities and other local authorities and technical and financial partners.

- As part of implementation of the communication plan, information campaigns will be carried out in the first two years of the project with HC-CACT and NGOs to sensitize the traditional authorities on the consultation approach in order to establish LBODs and improve female and youth land access. Implementation of the plan will be done with the support of a communications expert to develop messages and tools to engage communities in planning and co-management dynamics.

- The information dissemination channels will include:

- Project factsheets with objectives, expected outcomes and the different funding mechanisms for rural communities.

- Messages and radio broadcasts with community radios and with the national radio.

- Ten-keyword documentaries targeting beneficiaries or informing on innovations.

# SECTION 2 – FEASIBILITY

### IMPLEMENTATION ARRANGEMENTS

- The Ministry of Agriculture will be have the overall execution and technical responsibility for the project through a Project Management Unit (PMU). The PMU will be established in the office of the Directorate General (DG) in N’djamena.  The main function of the PMU, following the guidelines of the Project Steering Committee, will be to ensure the coordination and implementation of the project as indicated in the annual work plans and budgets (AWP/Bs). The PMU will be composed of a National Project Coordinator (NPC), an international consultant as Chief Technical Adviser (CTA), monitoring expert and administrative and budget/operations officers.

- Other national institutions will have an important role in project execution, with specific roles agreed during the validation workshop. These institutions are (i) the Provincial Action Committee (CPA)/Provincial Planning Unit (PPU); (ii) The National Agency for Rural Development (ANADER); (iii) The Great Green Wall National Agency (ANGMV); (iv)The High Council of Autonomous Communities and Traditional Chiefdoms (HC-CACT); and the Ministry of Land Use Planning (MLPH). Their engagement in project execution will also constitute a capacity development process, necessary for sustainability, replication and scale-up of project outcomes.

- The Government will designate the National Project Coordinator (NPC). The NPC will be an expert from Ministry of Agriculture staff and will have the responsibility of supervising and guiding the Chief Technical Adviser on the government policies and priorities. He/she will also be responsible for coordinating the activities with all the national bodies related to the different project components, as well as with the project partners. He/she will be responsible for requesting FAO the timely disbursement of GEF resources that will allow the execution of project activities, in strict accordance with the Project Results-Based Budget and the approved AWP/B for the current project year.

- Specifically, the PMU led by the NPC will be in charge of daily project management and technical supervision including:

- coordinating and closely monitoring the implementation of project activities;

- day-to-day management;

- coordination with related initiatives;

- ensuring a high level of collaboration among participating institutions and organizations at the national and local levels;

- tracking the project’s progress and ensuring timely delivery of inputs and outputs;

- overseeing the project’s monitoring and communications plans;

- organizing annual project workshops and meetings to monitor progress and preparing the Annual Work Plan and Budget (AWP/B);

- submitting the six-monthly Project Progress Reports (PPRs) with the AWP/B to the PSC and FAO;

- preparing the Project Implementation Review (PIR);

- supporting the organization of the mid-term and final evaluations in close coordination with the FAO Budget Holder and the FAO Independent Office of Evaluation;

- ensuring that gender issues are adequately addressed during project implementation. Likewise, under FAO rules and procedures and in conformity with this project document, the NPC will identify expenses and disbursements that should be requested to FAO for the timely execution of the project, in support to the budget holder responsibilities.

- A Project Steering Committee (Comité de pilotage (CP)) led by the Ministry of Agricultural Production, Irrigation and Equipment (MPIEA), will be established. It will consists of five (5) focal points (GEF Focal Point and focal points from Ministries of Environment, Livestock, Land Development and Planning), Great Green Wall National Agency (1), representatives of NGOs and civil society (2) and co-financing partners (2), and the National Project Coordinator (1). The Steering Committee will make decisions in case of political or security difficulties and facilitate the integration of services and linkages between the project activities and the institutional frameworks. With the NPC and PMU serving as Secretariat, the Steering Committee will:

- Review and approve annual work plans and budgets;

- Review and supervise project progress, especially the delivery and quality of outputs and outcomes;

- Facilitate close collaboration between the project and other projects and programs to diversify funding sources;

- Sustain, replicate and scale-up the main achievements of the project, through ongoing and new initiatives;

- Assist in effective coordination of stakeholders.

- The Steering Committee will meet twice a year in N'Djamena, meaning that eight (8) meetings will be held during the life of the project.

- The Food and Agriculture Organization of the United Nations (FAO) will be the GEF Implementing Agency for the proposed project, and as such, will provide project cycle management services as established in the GEF Policy. FAO will be responsible for providing oversight, technical backstopping and supervision of project implementation to ensure that the project is being carried out in accordance with agreed standards and requirements. Technical backstopping will be provided by FAO in coordination with the Project Steering Committee. As the GEF Implementing Agency, FAO is responsible for performing the following tasks:

Administrate funds from GEF in accordance with FAO rules and procedures;

Supervision of project implementation in accordance with the project document, work plans, budgets and according to FAO rules and procedures;

Performance of at least one supervision mission per year;

Technical assistance to ensure that quality is applied in all activities and certain skills are transferred to local institutions;

Report to the GEF Secretariat and the GEF Evaluation Office, through the annual Project Implementation Review (PIR), on project progress and provide financial reports to the GEF trustee.

- The project structure will be as follows:

Figure 6. Project structure

5 Focal Points led by the GEF Focal Point (resource mobilization and supervision)

Coordination level

Bilatéral meeting

FAO Representative

Minister Agriculture

Five (5) focal points (GEF, Ministries of Agriculture, Environment, Livestock, Land Development and Planning), AGNGMV (1), representatives of NGOs and civil society (2) and co-financing partners (2) and the National Project Coordinator (1)

The PMU composed of the National Project Coordinator (NPC), an international consultant as the Chief Technical Adviser (CTA), the monitoring expert and administrative and budget/operations officers.

Project Steering Committee

Project management Unit (PMU)

PMU at provincial level

Two Technical Experts

Political level

Decision political level

Lead Technical Unit (DLP, PAC)

ANGMV

ANADER

HC-CACT

LBOD

Federation OP

NGO

Execution level (provincial)

- Based on consultations with the Government (Ministry of Agriculture and the GEF Operational Focal Point), given the fragile security situation and lack of expertise at the national level and considering the absence of national and local institutions with fiduciary capacity and strong presence in the target provinces, it was recommended that FAO directly executes, together with partners, sub-components of the project. FAO direct execution of specific subcomponents is proposed with the main objective of supporting a learning-by-doing process for local institutions, which will play a major role in co-execution and in future scale-up.

- FAO will sign letters of agreements (LoAs) with implementing partners, transferring funds for the delivery of specific outputs. The main implementing partners identified during project preparation include:

- Provincial Action Committee (CPA)/Provincial Planning Unit (PPU) for the harmonization of approaches and local coordination of interventions (spatial and sectoral), for progress monitoring and evaluation. ULPs will consist of three agents who will also be in charge of the project's M&E system at provincial level. They will liaise with focal points at national level.

- The National Agency for Rural Development (ANADER)     for the establishment of agro-pastoral field schools (APFSs) in partnership with decentralized technical services (DTSs) for popularization of techno-economic models adapted to CCs and markets and support to Agropastoral Field Schools.

- The Great Green Wall National Agency (ANGMV) for the execution of provincial five-year agro-sylvo-pastoral and freshwater Management Plans (PCCAs) with the participation of the LBODs, traditional well diggers and hydraulic companies. The PCCAs will be divided into annual plans. Multiparty agreements will be formulated annually and by province and agreed by local authorities (CPA) and the LBODs.

- The High Council of Autonomous Communities and Traditional Chiefdoms (HC-CACT) for awareness raising and advocacy among traditional chiefdoms, on the project and the interest in organizing themselves through LBODs to consult and decide on CC adaptation, CC adaptation extension and on the three national laws providing legal CC adaptation provisions.

- NGOs for LBODs’ active management, consultation, regulation and investment planning improvement. They will help LBODs draft texts and annual plans and provide capacity-building actions to LBOD board members.

- The National Focal Points (PF) under the responsibility of the GEF focal point to capitalize on the integrated, cross-sectoral approach, facilitate implementation through their respective administrations (Agriculture, Livestock, Environment and Spatial Planning). The GEF focal point advocates for the project with TFPs to mobilize resources and diversify partnerships. The GEF project thus becomes a catalyst for CC adaptation funding.

- Producers’ and livestock breeders’ federations for (i) Mobilization of sedentary breeders’/agro-pastoralists’ organizations to advocate for their adhesion to LBODs for a better management of natural resources (water, pasture and NTFPs); and (ii) Execution of value chain contracts for sesame, spirulina and fodder/ cattle feed and assistance to producers in the management of cereal and forage stocks.

- In addition to coordination of implementation at national level, there will be two national experts, recruited with GEF resources, deployed in two local field offices during the life of the project. The two field office experts (managers) will provide technical support to the ULP where they are assigned. This project team is supported by logistics and equipment (2 vehicles, computers, printers, and means of operation). The ULP provides the interface between Government, the central and local administrations and user organizations. It is an advocacy and mobilization structure for CC adaptation funding.

- The two national experts cover each 2 PPUs/CPA. They fulfil the following duties:

- Establish within the CPA, a monitoring and activity planning unit comprising the three provincial delegates (Livestock, Agriculture and Environment) in charge of executing the Agro-sylvo-pastoral and freshwater management plan (PCCA) in consultation with the LBODs. The Plan, set up in a participatory fashion, drives local organizations, technical and financial partners in the area of ​​intervention. Technical assistance includes activity planning and convention development, activity monitoring thanks to online GIS and bi-annual meetings to inform progress and support to supervision and evaluation missions.

- Establish the M&E system to track outcome (6) and output (3) indicators and share them at quarterly meetings.

- Stimulate local consultation by organizing information meetings between CPA, ANGMV, LBOD, the private sector and TFPs. The consultations result in annual agreements for plan execution which are assessed and carried forward. The project stimulates public-private partnerships to develop territories and improve CC adaption.

- Stimulate political dialogue at local level, through the organization of provincial workshops on the Guidelines for responsible governance of land and natural resources, and between local and central levels (Years 1 and 2) so that local organizations make their voices heard on the land issue.

- Report at national level and capitalize upon CC adaptation strategies, participation and consultation, extension and gender approaches.

### FINANCIAL PLANNING AND MANAGEMENT

- The total cost of the project will be USD 22 635 913, of which USD 4 050 913 will be from the GEF and USD 18 585 000 will be co-financing from different partners

- Table 10 presents the cost per component and source of funding and the sources and types of confirmed co-financing. FAO, as GEF agency, will be responsible only for the management of the GEF resources and FAO co-financing. Co-financing is detailed in Table 11.

Table 10. Financial plan by components

| Project Components | (in $) |  |
| --- | --- | --- |
|  | GEF Financing | Co-financing |
| Component 1 | 1,571,905 | 7,085,000 |
| Component 2 | 1,080,255 | 10,000,000 |
| Component 3 | 427,490 | 1,000,000 |
| Component 4 | 778,363 | 500,000 |
| Subtotal | 3,858,013 | 18,585,000 |
| Project Management Cost (PMC) | 192.900 | - |
| Total Project Cost | 4,050,913 | 18,585,000 |

Table 11. Project co-financing

| Sources of Co-financing | Institutions/Actors | Type of Co-financing | Amount ($) | Description |
| --- | --- | --- | --- | --- |
| Recipient Government | Ministry of Agriculture | Grants | 11,085,000 | Building resilience to food and nutrition insecurity in the Sahel (P2RS) |
| Donor Agency | Donor Agency | Grants | 7,500,000 | Strengthening Productivity and Resilience of Agropastoral Family Farms Project |
| Total |  |  | 18,585,000 |  |

Table 12. Building resilience to food and nutrition insecurity in the Sahel (P2RS) Co-finance

- Cost effectiveness. The project is cost-effective in a number of ways, including:

- Implementation of activities is mostly through national and provincial institutions,  which also ensures sustainability of capacities and continuous implementation of provincial adaptation plans beyond the project;

- Catalysing partnerships and investments from financial and technical partners, as reflected in the co-financing commitments already made (see above tables).

Furthermore, the project seeks to create an enabling environment to attract investments to the provinces through strong support to public services to derisk the context and create business opportunities through innovations, especially for women and youth.

### RISK MANAGEMENT

### Potential risks to the project

- Potential project risks were identified and analyzed during the preparation phase and mitigation measures have been incorporated into the project design (see Risk Management in Appendix IV). With the support and supervision of FAO, the Project Steering Committee will be responsible for the management of these risks as well as the implementation of the mitigation measures. The M&E system will be used to manage outcome, output indicators, project risks and mitigation measures. The Project Management Unit will also be responsible for effectively monitoring mitigation measures, adjusting mitigation strategies as needed, identifying and managing any new risks that may not have been identified during the preparatory phase of the project, in collaboration with partner projects.

- The six-monthly Project Progress Report (PPR) is the main monitoring and risk management instrument. The PPR includes a section of systematic risk monitoring and mitigation actions. It also includes a section to identify any new risks or risks that have not been addressed yet. FAO will also monitor project risks and follow up as needed, providing support to the PMU for implementing and adjusting mitigation strategies. The preparation of reports on risks monitoring and rating will also be part of the Annual Project Implementation Review (PIR) prepared by FAO and submitted to the GEF Secretariat.

- A summary of the risks identified during the preparation phase, their occurrence probability and the suggested mitigation measures are presented in Appendix IV.

### Environmental and social risks related to the project

- The project was considered of moderate risk level. An Environmental & Social Analysis was undertaken during project preparation. A summary of the results, findings and recommendations is included in the Environmental and Social Risk Management Plan in Appendix IV.

### MONITORING & EVALUATION AND REPORTING

### Monitoring mechanism

- Project oversight will be carried out by the Project Steering Committee (PSC) and FAO. Oversight will ensure that: (i) project outputs are produced in accordance with the project results framework and leading to the achievement of project outcomes; (ii) project outcomes are leading to the achievement of the project objective; (iii) risks are continuously identified and monitored and appropriate mitigation strategies are applied; and (iv) agreed adaptation benefits are being delivered.

- FAO will provide oversight of GEF financed activities, outputs and outcomes largely through the annual Project Implementation Reports (PIRs), periodic backstopping and supervision missions.

- Day-to-day project monitoring will be carried out by the Project Management Unit. Project performance will be monitored using the project results matrix, including indicators (baseline and targets) and annual work plans and budgets. At inception the results matrix will be reviewed to finalize identification of: i) outputs ii) indicators; and iii) missing baseline information and targets. A detailed M&E plan, which builds on the results matrix and defines specific requirements for each indicator (data collection methods, frequency, responsibilities for data collection and analysis, etc) will also be developed during project inception by the M&E officer.

| Type of M&E Activity | Responsible Parties | Time-frame | Budget in USD |
| --- | --- | --- | --- |
| Inception Workshop | FAO Country Office | Within two months of project document signature | 15,000 |
| Project Inception Report | Project Manager | Within two weeks of inception workshop | Project manager staff time. |
| Supervision visits | FAO | Annually | GEF Agency fee. |
| Monitoring field missions | PMU staff, consultants and FAO |  | 61,900 |
| Project Progress Reports (PPR) | Project manager and M&E officer | Annually | PMU staff time. |
| Project Implementation Review report (PIR) | Drafted by PMU finalized by FAO (Lead Technical Officer and Budget Holder). Approved and submitted to GEF by the FAO-GEF Coordination Unit. | Annually (July) | PMU staff time and Agency fee. |
| Co-financing Reports | Project Management Unit | Annually | Staff time. |
| Project Steering Committee Meetings | Project Management Unit | 2X year | 30,000 |
| Mid-term review | Consultant, FAO-GEF Coordination Unit. | Project mid-term | 20,000 |
| Final evaluation | External consultants, FAO Independent Evaluation Office | At least three months before operational closure | 40,000 |
| Terminal Report | Project Manager | Within two months of project closure | 7,000 |
| Translation of MTR and TE reports into English/French | FAO country office |  | 5,000 |
| Total Budget |  |  | 178,900 |

### Reporting

- Specific reports that will be prepared under the M&E program are: (i) Project inception report; (ii) Annual Work Plan and Budget (AWP/B); (iii) Project Progress Reports (PPRs); (iv) annual Project Implementation Review (PIR); (v) Technical Reports; (vi) co-financing reports; and (vii) Terminal Report. In addition, assessment of the GEF Monitoring Evaluation Tracking Tools against the baseline (completed during project preparation) will be required at midterm and final project evaluation. In each of the reports a dedicated session will be included with information on gender-related progress made and results achieved, with some sex-disaggregated data and gender-sensitive lessons learned

- Project Inception Report. The Project Management Unit (PMU) will prepare a project inception report in consultation with the Lead Technical Officer (LTO), Budget Holder (BH) and other project partners. The report will include a narrative on the institutional roles and responsibilities and coordinating action of project partners, progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation. It will also include a detailed first year AWP/B, a detailed project monitoring plan. The draft inception report will be circulated to the PSC for review and comments before its finalization, no later than one month after project start-up. The report should be cleared by the FAO BH and LTO and uploaded in the Field Programme Management Information System (FPMIS) by the BH.

- Results-based Annual Work Plan and Budget (AWP/B). The draft of the first AWP/B will be prepared by the PMU in consultation with the FAO Project Task Force and reviewed at the project Inception Workshop. The Inception Workshop (IW) inputs will be incorporated and the PMU will submit a final draft AWP/B within two weeks of the IW to the BH. For subsequent AWP/B, the PMU will organize a project progress review and planning meeting for its review. Once comments have been incorporated, the BH will circulate the AWP/B to the LTO and the FAO GEF Coordination Unit for comments/clearance prior to uploading in FPMIS by the BH. The AWP/B must be linked to the project’s Results Framework indicators so that the project’s work is contributing to the achievement of the indicators. The AWP/B should include detailed activities to be implemented to achieve the project outputs and output targets and divided into monthly timeframes and targets and milestone dates for output indicators to be achieved during the year. A detailed project budget for the activities to be implemented during the year should also be included together with all monitoring and supervision activities required during the year. The AWP/B should be approved by the Project Steering Committee and uploaded on the FPMIS by the BH.

- Project Progress Reports (PPR). PPRs will be prepared by the PMU based on the systematic monitoring of output and outcome indicators identified in the project’s Results Framework (Appendix I). The purpose of the PPR is to identify constraints, problems or bottlenecks that impede timely implementation and to take appropriate remedial action in a timely manner. They will also report on projects risks and implementation of the risk mitigation plan. After LTO, BH and Funding Liaison Officer (FLO) clearance, the FLO will ensure that project progress reports are uploaded in FPMIS in a timely manner.

- Annual Project Implementation Review (PIR). FAO (BH, LTO) in collaboration with PMU will prepare an annual PIR covering the period July (the previous year) through June (current year) to be submitted to the FAO GEF Coordination Unit Funding Liaison Officer (FLO). The FAO GEF Coordination Unit will submit the PIR to the GEF Secretariat and GEF Evaluation Office as part of the Annual Monitoring Review report of the FAO-GEF portfolio. PIRs will be uploaded on the FPMIS by the FAO GEF Coordination Unit.

- Technical Reports. Technical reports will be prepared by national, international consultants (partner organizations under LOAs) as part of project outputs and to document and share project outcomes and lessons learned. The drafts of any technical reports must be submitted by the PMU to the BH who will share it with the LTO. The LTO will be responsible for ensuring appropriate technical review and clearance of said report. The BH will upload the final cleared reports onto the FPMIS. Copies of the technical reports will be distributed to project partners and the Project Steering Committee as appropriate.

- Co-financing Reports. The PMU will be responsible for collecting the required information and reporting on co-financing as indicated in the Project Document. The co-financing report, which covers the period 1 July through 30 June, is to be submitted on or before 31 July and will be incorporated into the annual PIR.

- Terminal Report. Within two months before the end date of the project, and one month before the Final Evaluation, the PMU will submit to FAO, a draft Terminal Report. The main purpose of the Terminal Report is to give guidance at ministerial or senior government level on the policy decisions required for the follow-up of the project, and to provide the donor with information on how the funds were utilized. The Terminal Report is accordingly a concise account of the main products, results, conclusions and recommendations of the project. The target readership consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and needs for insuring sustainability of project results.

### EVALUATION PROVISIONS

- A mid-term review will be undertaken at project mid-term to review progress and effectiveness of implementation in terms of achieving the project objectives, outcomes and outputs. Findings and recommendations of this review will be instrumental for bringing any necessary improvement in the overall project design and execution strategy for the remaining period of the project’s term.

- An independent final evaluation will be carried out three months prior to the terminal review meeting of the project partners. The final evaluation will aim to identify the project impacts and sustainability of project results and the degree of achievement of long-term results. This evaluation will also have the purpose of indicating future actions needed to sustain project results

### INFORMATION TECHNOLOGY

- The project supports the digitalization of public services by distributing tablets to technicians, CPA and agents of farmers' and breeders' federations. Mobile Webservices will be offered to farmers' and breeders' federations to support promising value chains and the creation of a platform architecture, displaying online interconnected information. The project will develop several actions to promote these technologies including:

- The establishment of messaging on CC adapted good agricultural and livestock practices. The WhatsApp Messenger application will enable the creation of focus groups for extension workers, trainer-facilitators and farmers, and give them the opportunity to share photos and videos (the project aims to have a dozen of group messaging lists created).

- The use of video tools: video tutorials (Target: 6 per year x 3 years) are created by professionals with technical agents on technical topics. The videos will be sent to producers, for their use as a training medium and receive quality information in their local language. They will also be able to train other farmers.

# SECTION 3 – SUSTAINABILITY

### CAPACITY BUILDING

- Capacity building is at the core of this project.  The project will strengthen the capacities of local institutions and land users in integrated planning, coordination, resource mobilization and implementation of medium to long-term provincial climate change adaptation investment plans (PCCAs), with accompanying resource mobilization strategies.

- The project will help build a framework for dialogue in each province for financial and technical partners (FTPs) engaged in agricultural development and climate investments. FTPs will be federated around PCCAs that will involve the delegations for land planning, decentralized technical services and local land users. These five-year plans will incorporate a coherent strategy to address CC, rationalize investments, and harmonize approaches between FTPs to increase impact, and for long-term sustainability.

- Capacities of decentralized technical service and farmer-facilitators to support the establishment of farmer field schools and agro-pastoral field schools will be strengthened. The field schools will be the main vehicles for the promotion of techno-economic models adapted to CC and markets and supporting and training farmer-facilitators to disseminate them among through farmer field-schools. A number of FFS established will become, in 5 years, mini demonstration and training centers or service hubs in each of the four target provinces. These mini-centers will be co-managed by public authorities and producer organizations with investments concentrated there to build training grounds for innovation.

- The project will strengthen consultation and dialogue capacities of the various land and natural resources users through the creation of Local Bodies for Dialogue and Decision (LBODs). As described in previous sections, these inter-cantonal consultative platforms will have the mandate to facilitate the integrated and concerted management of natural resources and to define management rules conducive to CC adaptation, and to reduce community and inter- community conflicts. They will allow traditional chiefs to learn new rules and decision modalities by formulating and signing Charters on the management of landscapes, land and natural resources. They will contribute to better integration of farming and pastoral activities, in order to reduce conflicts and protect resources (pasture, forest and freshwater resources). They will facilitate social change through information sharing and advocacy. This will help to ensure equitable access to resources for women, youth and other marginalized social groups, and support the implementation and planning of development projects over time.

  - FINANCIAL AND ECONOMIC SUSTAINABILITY

- There are a number of elements integrated into the project design that should contribute to financial and economic sustainability:

  - Establishing a strong coalition around agreed investments plans (PCCAs) with financial partners already investing in the target provinces.

  - Provincial Action Committees (CPAs), decentralized technical services (DTS) and traditional chiefdoms are all sustainable organizations. The sustainability of the provincial planning units (PPUs) to be established depends on the ability to mobilize funds. Similarly, LBODs representing users are new structures that need public resources to be invested on a longer term than the project, to ensure their sustainability, which is very fragile so far. They will have to win adhesion by the relevance of their approach to investment planning, by improving user rules and reducing conflicts.

Therefore the project will support the development of resource mobilization strategies for the target provinces, to ensure the sustainability of the new structures and for continued implementation of the PCCAs.

  - The sustainability of farmer field-schools (FFS) depends on the dynamism of the groups and their affiliation to federations in order to develop promising markets. In many FFS projects implemented by FAO, FFS facilitators trained by FAO have become private extension agents, paid by the farmers they provide advice to, thus guaranteeing the financial sustainability of the approach. The techno-economic models are based on the presence of equipment suppliers on the national market and on the availability of technical and financial banking services.

  - The project will fund practices and technologies that can be sustained when beneficiaries have access to financial services e.g. value chains such as spirulina, sesame, cattle feed, onion and dried products.

  - The sustainability of the economic sectors supported by the project depends on the capacity of stakeholders to develop markets and therefore their affiliation to the producers' federations (CNCPRT and farmers' federations). Sector alliances are being set up for sesame, with buyers from West Africa, to make Chad a collection area, and to negotiate financial products with banks and the private sector. Regarding spirulina, the project will work with the Chamber of Commerce to bring in international buyers and producers of spirulina and have this product recognized on international markets by supporting a labelling process. The potential for sesame and livestock feed is high considering international and local markets. Financial services will have to be tailored to allow sector stakeholders to take over after the project and to maintain growth.

### ENVIRONMENTAL SUSTAINABILITY

- Environmental sustainability is embedded within the objective and strategy of this project. As mentioned, the project adopts a systemic approach combining the improvement of environmental governance to protect ecosystems and restore degraded lands, thus increasing resilience of production systems on the one hand, and sustainable economic development to improve agro-pastoralists livelihoods and market access on the other.

- The participatory climate change adaptation plans to be developed based on ecological, technical and socio-economic studies, will include a strong component on restoration of vast pastoral and agro-pastoral lands including around villages and wadis which are overused by agriculture and livestock activities.

- The sustainability of the restored degraded lands in the pastoral zones depends on the water points network system, and the farmers’ ability to get along and structure their activities, in order to maintain a balanced ecosystem carrying capacity. Consultative structures already exist within families and clans, but they need to be strengthened at community level – which the project will do by strengthening the local platforms and through agro-pastoral field school. The carrying capacity will be monitored by livestock public authorities in collaboration with ANGMV.

- Similarly, the sustainability of the agro-pastoral zone around the wadis and polders depends on the ability of women and young people to buy fodder to feed small ruminants during the seven-month dry season period and to organize themselves so that flocks roam over the planted spaces. Women need to connect to feed value chains in order to offset these costs. They also need access to wadis and polders to reduce their pressure on agropastoral land which is the very last bulwark against silting. Overexploitation of this area is related to local social relations with land. The environmental sustainability of this area will also depend on the improvement of women’s condition and on a more equitable distribution of land.

- The plant selection for the regeneration of degraded lands will be done in consultation with the communities in agro-pastoral field-schools. The choice of seeds will takes into account climate resistance, income potential (gum arabic) and fodder production potential for animal feeding. Communities will be jointly accountable for these areas. This approach requires socio-economic and negotiating skills of local technicians, whose capacity in participatory approached will be strengthened by the project.

### INNOVATION AND SCALE UP

- The project promotes many technical, social and practical innovations to stimulate change dynamics for climate change resilience.

- On the technological area, the project will introduce two innovations:

- Drip irrigation is a water-saving technology that increases plant growth and decreases climate risks, provided that technicians and producers develop the capacity to set up the system and train farmers to the use of this technology, a substantial vendor network and quality equipment are also needed; when products are successfully sold on urban markets, the return on investment makes it possible to attract the banks. The drip irrigation reduces the plant watering chore, which is ideal in an area where there is a lack of workforce and water during the dry season.

- Solar energy for water pumping on market and hydraulic wells is a technological innovation that saves workforce and alleviates work hardship, especially for women. This requires building maintenance capacities for proper operation of this technology among young users and technicians who are literate in commonly spoken languages. It also requires networking with solar panel suppliers and providing for high capacity water storage tanks for gravity irrigation.

- The project will introduce use of an online GIS to plan and monitor project investments and digitalization of public services in order to cater for remote areas, develop tutorials and distant consulting. These technologies make it possible to innovate and transmit knowledge dissemination.

- Regarding organizations, Local Bodies for Dialogue and Decision (LBODs) are new social organizations that will be created by the project to support landscape planning and enactment of local land rules. These will reduce conflicts and tensions over land and natural resource use, demonstrating the ability to jointly manage, enact and enforce user rules.

- In terms of practices, these will be promoted:

- The stabulation of small ruminants in managed wadis is an innovation in women’s livestock rearing practices that requires (a) available production areas to stock small livestock for 7 months, during the dry season and fed with fodder and crop residues; (b) support to women in the self-management of shared spaces; (c) development of livestock feed value chains, and storage capacities through fodder banks, and support to small-scale grain processing (corn/sorghum silage).

- The digitalization of technical units and services and distant learning through tutorials, to address geographical access challenge and to popularize technical consulting.

### DECENT RURAL JOBS

- The project will help support the creation of decent rural jobs, especially for women and young people. Techno-economic models make it possible to develop decent rural activities. The project will contribute to the creation of jobs for young people through the solar and drip irrigation program, which supports a farming business model that is suitable to young people. The project will also support job creation in ancillary services such as farm machinery operation, craftsmanship and digital services (see description of components 2 and 3).

### GENDER EQUALITY

- Access to resources can be a source of conflict in a precarious ecological context with soaring population growth – such as in the Lake Chad Basin and specifically the target provinces. This has consequences for ecosystems, and women play an important role in developing landscapes because they tend to have a sedentary lifestyle and they are major users of natural resources. Women are drivers of change.

- Women's access to land is dependent on the agro-ecological zones which are regulated by customary rules, marital status and economic power. The main mode of access is the use of the family domain. In general, women have access to land but do not have control over it. They face challenges to access to polders and wadis that are owned by traditional chiefs and they have limited resources for off-season market gardening. They pay a fee to have the right to exploit spirulina. This situation of land discrimination requires the intervention of public authorities to facilitate and improve female access to production areas.

- Women are users of degraded agro-pastoral zones around wadis, for grazing small ruminants or for growing rainfed crops such as pearl millet. Wadi area and pastoral lands are under the control of male heads of households and clan leaders.

- Although they are the primary users, women do not have control over water and are little involved in fishing. They also have poor access to inputs, equipment and innovations. Women's activities need to be integrated into value chains which are profitable enough to enable re-investments that enhance productivity.

- Women account for 75% of production. In addition to domestic chores, they devote a significant portion of their time to production, processing and marketing activities. They are poorly represented in decision-making circles in the farming sector, where they represent only 19% of decision-makers. Women are also poorly represented in local governance bodies such as traditional, administrative and military authorities, according to the Country Strategy Paper 2010-2014.

- The project will improve women's access to wadi lands by negotiating with the traditional chiefs to release plots on new areas to be developed by women, so they can invest in and benefit from the yield of their own land. The project will help women improve the rearing of small ruminants by developing fodder chains and setting up areas to park livestock during the dry season.

- The project will support women's groups around spirulina processing (equipment, training and supply chain contracts), fodder production and improved management of small ruminants (training and development of zones for small ruminant stalling), market gardening (access to land and training) and product drying (solar ovens and training). 60% of target beneficiaries are women and young people.

- The project will strengthen engagement of women in LBODs by promoting their election and participation in decision-making bodies, so that their concerns are given due consideration in the CC adaptation agro-silvo-pastoral resource management investment plans (PCCAs). Women will also be beneficiaries and facilitators of farmer field-schools focusing on spirulina production, drip irrigation, rearing of small ruminants, food product drying/smoking and other processing activities.

- HC-CACT, Traditional chiefs and administrations will be sensitized and trained on gender issues and gender-based violence. Steps and strategies will be taken for their accountability, and their commitment to resolve and manage land-related community conflicts that affect women, minorities, refugees, returnees and displaced persons, and ensure equitable management and sharing of natural and financial resources, giving due attention to women and young people.

### INDIGENOUS PEOPLES

- In Chad, there are no so-called indigenous populations because the term “indigenous” is often considered as pejorative and with contemptuous intent. Rather, one may talk about the vulnerability of nomadic pastoralists. The most vulnerable nomadic populations are specifically called "Fulbe" and more commonly referred to as M'Bororo Peuls. They form a minority community in the territory and represent an identity group, with typical cultural and traditional practices. They are vulnerable to climate change and insecurity: they are constrained to leave/travel far in quest for pasture and water for their livestock, in the face of environmental degradation, inter-community conflicts and aggravation of security related to terrorism and political conflicts.

- These nomadic “Fulani” are being increasingly accepted as a community and live without concern today, because they are governed by the same laws in force at national level and enjoy the same rights as other Chadians. Other majority nomadic communities live in the same conditions and are integrated in communities.

# APPENDIX I. Logical framework

|  | Logical framework |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Results | Indicators | Baseline | Mid-term | End of Project Target | Means of Verification | Assumptions |
| Project Objective: To increase the resilience of agro-sylvo-pastoral and freshwater production systems to climate change in four provinces downstream of the Lake Chad Basin (Bahr El Gazal (BEG), Kanem, Hadjer Lamis and Lac). | Number of direct beneficiaries by gender (nomadic and sedentary agro-pastoralists, sesame producers, spirulina producers and village chiefs) : - 7,000 women - 4,000 men | 0 | 11,000 beneficiaries. | 11,000 beneficiaries. | M&E system reports. Mid-term review and evaluation. Field supervision missions. | - The main assumption is a strong political will to support the formulation and implementation of provincial climate change adaptation agro-sylvo-pastoral and freshwater management plans. - Ownership and support of Governors and Provincial Action Committees, facilitating consultations and mobilization of local resources. - Security situation in the Lac province, especially, does not disrupt implementation. - The administrations involved in implementing the project communicate at the national level to facilitate the integration of public services at the provincial level, for the establishment and sustainability of agro-pastoral field schools that promote market-oriented and climate resilient techniques and technologies. |
|  | Hectares of pastoral and agricultural land under sustainable management and restoration for climate resilience: - 15,000ha degraded pastures under restoration; - 5,000ha agroforestry parks to stabilize sand dunes. | 0 | 50% of target | 20,000 hectares. | M&E system reports. Mid-term review and evaluation. Field supervision missions |  |
|  | % increase in volume of investment (USD) for climate change adaptation mobilized by province, type of beneficiary and gender. | 0 | Target to be determined in year 1. | Target to be determined in year 1. | M&E system reports. Mid-term review and evaluation. Field supervision missions |  |
| Results | Indicators | Baseline | Mid-term | End of Project Target | Means of Verification | Assumptions |
| Component 1: Strengthening provincial governance to reduce the vulnerability of agro-sylvo-pastoral and freshwater production systems to the adverse effects of climate change. |  |  |  |  |  |  |
| Outcome 1.1: Improved governance at the provincial level to identify, prioritize, monitor and evaluate CC adaptation strategies and measures. | Indicator 1.1.1 Number of Provincial Land Use Planning units (PPUs) established (under delegations for land planning – DLPs) and functional (effectively facilitating Provincial Action Committees (PACs)). | 0 | 4 | 4 | Project reports. Plans, documents. Project progress reports. LBODs, PAC reports. |  |
|  | Indicator 1.1.2 Number of Local Bodies for Dialogue and Decision-making (LBODs) established and functional. | 0 | 4 | 4 |  |  |
|  | Indicator 1.1.3 Number of five-year climate change adaptation agro-sylvo-pastoral and freshwater management investment plans (PCCAs) successfully formulated and under implementation with co-financing from financial partners. | 0 | 4 | 4 |  |  |
| Outcome 1.2: Agro-sylvo-pastoral and freshwater production systems’ vulnerability reduced and natural resource management strengthened. | Indicator 1.2.1 CC adaptation subprograms successfully implemented (improved water access, agropastoral land restoration, irrigation and energy): - Ha under restoration; - Functional pastoral and village water supply systems; - Ha under drip irrigation; - # Energy supply system for storage infrastructure. - # of technicians trained for installation and maintenance services. | 0 | - 8,000 ha under restoration; - 2 pastoral wells, 50 horticultural wells and 75 water towers and tanks; - 100 ha under drip irrigation; - 50 solar panels; - 150 technicians. | - 20,000 ha under restoration; - 4 pastoral wells, 100 horticultural wells and 150 water towers and tanks; - 150 ha under drip irrigation; - 100 solar panels; - 300 technicians. | Field supervision reports. Project progress reports. ANGMV. Training reports. |  |
|  | Indicator 1.2.2 Effectiveness of National Agency for the Great Green Wall (ANGMV) capacity development program. | 0 | Indicators and targets to be defined in the design of the program. | Indicators and targets to be defined in the design of the program. |  |  |
| Results | Indicators | Baseline | Mid-term | End of Project Target | Means of Verification | Assumptions |
| Component 2: Enhancement and diversification of agro-sylvo-pastoral and freshwater production systems. |  |  |  |  |  |  |
| Outcome 2.1: Agro-sylvo-pastoral and freshwater production systems are resilient to climate change through scaling up of innovative technologies, practices and know-how | Indicator 2.1.1 Number of Farmer field-schools (FFSs) and agro-pastoral field-schools (APFSs) operational and disseminating CC and market adapted farming techniques and practices. | 0 | 8 FFS & 50 APFS | 8 FFS & 50 APFS | Project M&E reports and reviews. Field supervision mission reports. |  |
|  | Indicator 2.1.2 Number of farmer facilitators and # of agents from integrated team of decentralized technical services (DTSs) and ANADER trained. By gender. | 0 | 24 agents & 160 farmer facilitators (at least 30% women) | 24 agents & 160 farmer facilitators (at least 30% women) |  |  |
| Outcome 2.2: Production is increased, and markets are improved for sesame, spirulina, livestock feed and dried vegetables. | Indicator 2.2.1 Extent of adoption of climate resilient technologies/practices (by gender) | 0 | 70% | 70% |  |  |
|  | Indicator 2.2.2 % Increase in production and revenue. | 0 |  | - Production of cereals and vegetables with 2-3 crops per year spread from September to June) doubled. - 30% increase in fodder production. - Labelled spirulina. |  |  |
| Results | Indicators | Baseline | Mid-term | End of Project Target | Means of Verification | Assumptions |
| Component 3: Mainstreaming climate change adaptation into local policies and strategies and national land reform. |  |  |  |  |  |  |
| Outcome 3.1: Climate change adaptation mainstreamed into key national laws on management of and natural resources and their implementation at provincial level | Indicator 3.1.1 # Institutional mechanisms at national level are in place to facilitate implementation and access to climate finance. | 0 | National team in place (linked to provincial coordination structures – component 1). | National team. | Project reports and reviews. Resource mobilization strategies and signed financial or funding agreements. |  |
|  | Indicator 3.1.2 CC adaptation, gender and women empowerment inputs integrated in the land reform process (recommendations). | 0 | CC adaptation, and gender and women empowerment inputs integrated in the land reform process. | CC adaptation, gender and women empowerment inputs integrated in the land reform process (recommendations). |  |  |
| Component 4: Monitoring and evaluation |  |  |  |  |  |  |
| Outcome 4.1: Effective monitoring, reporting and dissemination of results to facilitate corrections and CCA scale-up. | Indicator 4.1.1 Effective project M&E system linked to relevant national M&E systems. | 0 | 1 M&E system operational. | 1 | Project implementation reviews. Mid-term review and final evaluation. |  |

# APPENDIX II. Work Plan

| Output | Activities | Responsible | Year 1 |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 |  |  | Q3 |  | Q4 | Q1 | Q2 |  | Q3 |  | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  | Q3 |  | Q4 |
| Component 1: Strengthening provincial governance to reduce the vulnerability of agro-sylvo-pastoral and freshwater production systems to the adverse effects of climate change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.1 Four (4) five-year climate change adaptation agro-sylvo-pastoral and freshwater management plans (PCCAs) are developed and implemented, one in each of the four Provinces covered by the project. Indicator: Number of Plans formulated | - Studies: Inventory of natural resources and land use and vegetation maps, conflict on land and natural resources, local organizations, customary rules, gender discriminations – Activity linked to output 1.2.2. Costs: 4 national experts x 30 days x USD 400 USD/Expert | National experts FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Organization of four three-day Provincial planning workshops in the Provinces in close collaboration with the four Provincial Action Committees (PACs) and under the supervision of the Governorates. Costs: (2 International Experts x USD 900 / Expert + 2 national Experts x USD400 / Expert) x 20 h/d | Project Management Unit (PMU) FAO PACs (4) Governorates (4) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Design by province (4) of the PCCAs Costs: 2 International Experts x 10 h/j | PMU FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Workplans and Drafting of LOA for the Great Green Wall National Agency (ANGMV) Costs: 2 International Experts x 30 h/j) x 900 USD/day | PMU FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.2. DLP's capacity for planning, monitoring, and coordination strengthened Indicator: Effectiveness in monitoring annual plans and coordinating various stakeholders | - Quarterly Planning and coordination Meetings lead by DLP/CPA and grouping the main local stakeholders engaged in the workplan implementation. Follow-up of activities and results. Costs: Provision for travel costs (500 USD/ mois / CPA x 48 months x 4 CPs) + Provision for operating costs (300 USD/mois/CPA x 4 CPAs. | CPA / PPU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Equipment of the 4 Provincial Planning Units (PPUs). Costs: 4 computers + printers + internet access + Tablets + Kit of solar panel + 2 motorbikes | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - GIS on line for the PUs to monitor activities and results and climate indicators; Costs 1 international Expert from FAO Geospatial Unit x 15 h/j x 2 missions (year 2 and 3) x USD 900 /Expert | FAO Geospatial unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.3. At least four Local Bodies for Dialogue and Decision (LBODs) created and strengthened. Indicator: Number of LBOD recognized and equipped and number of Charters drafted.. | - Information and communication campaigns targeting local administrations and traditional chiefs and leaders on (i) project strategy (area of intervention, beneficiaries and benefits, partners, and financial mechanisms) (ii) climate threats conflicts on land use and natural resource management, and adaptation measures; (iii) Adhesion to LDOBs. LOA x HC-CACT for two years. Costs : 2 Facilitators x 24 months + Provision for travel costs + Provision for operating costs (USD500 / month x 24 months) | HC-CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Inter cantonal Dialogue, organization of users and local chiefs to set up LBODs ; Drafting of regulatory texts ; Costs: 4 three-day workshops by province / year x 2 years | NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Priority areas for restoration and development, land negotiations, drafting of local Charters on land use and natural resource management, Mobilization of beneficiary contributions and work plans Cost: 6 three-day workshops per year per LBOD | NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Capacity-building programs for LBOD’s members Costs : 2 three-day sessions per year x USD 2,500/session | NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Equipment for LBODs and NGOs Costs: 2 motorbikes per province = 8 motorbikes | FAO PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1 Effective Investment in CC adaptation increased and stakeholder engagement strengthened Indicator: Volume of investment (USD) per year by Province, Type of beneficiary, and Gender | - Drafting of annual multipartite contract for land restoration and development involving LBOD, ANGMV and enterprises | ANGMV Private sector LBOD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Implementation of the annual investment plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output1.2.2: Planning and implementation capacities of the National Agency for the Great Green Wall (ANGMV) are strengthened. Indicator: Effectiveness in planning, implementing , monitoring annual plans and number of HR trained | - Equipment: 2 tractors with Nardi hoes | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Development of Mapping skills | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Study on ANGMV human resources development capacity | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Human resource capacity development programs: Gender, socio-economy, participatory approaches. Target: 6 sessions, International expert (1 Expert x 15h/j x 3 sessions) + National Expert (1 Expert x 15 h/j) | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Flock and ecological monitoring in collaboration with the Ministry of Livestock and Environment; Provision for service operation (500 USD / month x 24 months) | ANGMV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Preparation of the two-year LOA x ANADER to lead three technical services at the provincial level, responsible for the establishment of demonstrative farms and APFFSs, and advice for facilitators and producers / herders ; incentives allowances for women Indicator : Nb. of training sessions Targets: 30% of technicians are women | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Enhancement and diversification of agro-sylvo-pastoral and freshwater production systems. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.1. Eight (8) demonstration FFSs and fifty (50) agro-pastoral field-schools (APFSs) established to promote sustainable natural resource management and climate change adaptation models, farming techniques and practices. Indicator: Extent of adoption of climate-resilient technologies/practices/ models by Gender | - Training on Digitalization: use of tablets and video tutorials for technicians (24) and facilitators (100) ; + 1 national expert x 30 days / year Indicator: number of beneficiary trained by gender Costs : 24 STD by province (leaders of LBOD, agro pastoralist groups) | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Training of trainers on FFS approach, identification of farmers / herders’ innovations adapted to climate threats to be spread widely Costs: One by province, 1 national expert x 30:h/j x 24 STD + 100 facilitator farmers into two classrooms) | FAO Chad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Technical trainings amongst a panel of nine agriculture /livestock/Fishery and dried products models Target: 4 sessions (2 every two years) per technician = 24 sessions 1 International expert (21 h/j x 6 sessions) + 1 National expert (21 h/j x 18 sessions) | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Support to the AFSs: equipment and training of local facilitators and producers Target: 80 percent of beneficiary are women and youth. Indicator: a) Number of people trained by Gender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Equipment for 24 Technicians from three decentralized technical services (ANADER, Livestock, Forestry) Motorbikes, transport allowances, tablets, 1 kit by team of computer + printer + internet access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.2 Producers, particularly women and youth are integrated into profitable value chains (4) Indicator: production (kg), yield (kg/ha), sale (quantity and, price, revenue, nb of VC contracts developped by value chain, distribution of the added value | - Support to spirulina value chain Target: 50 woman groups (500 beneficiaries) | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Study on spirulina certification quality approach at each step of the process, process to obtain a Geographical Indication with international private sector 1 International expert x 30 wd | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Equipment for spirulina women groups for scaling up pilot actions of FAO TCP Target: (Provision of USD 300 per woman x 500 women) | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Capacity-building programs for women groups on quality approach, leadership and empowerment, basic literacy and accountability; and entrepreneurship skills Target: 500 women trained , 2 one-week sessions; 1 national expert x 21 h/d | NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Support to fodder and cattle feeding VCs Target : 110 groups (3000 beneficiaries) amongst them 80 per cent of women and youth | FAO NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1. Equipment for herder groups (60): 10 quads and trailers for fodder transportation , 50 mowers-brush | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 Grinding machine (50) for women groups to produce small ruminants feeding | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.3. Capacity-building programs for women / herder groups : Technical and entrepreneurship development trainings; 2 three-day sessions/group/year x 110 groups = 220 sessions | NGO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.4. Warehouses for fodder Banks (10) | P2RS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.5. Feasibility study for the installation of 10 Power Generation Unit (86,4 kW per day), 10 units) and maintenace 1 international Expert x 21 h/d | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.5. Power Generation Unit Solar panel Kit + inverter + Expertise in the installation of the unit 1 national Expert x 10 h/d/year | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Support to the dried vegetable products (okra and tomatoe) Target: 50 woman groups (2500 beneficiaries) | Federation of herders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1. Feasibility study : 1 International Expert x 30 h/d | FAO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2. Equipment of woman groups : Solar unit for vegetable product (USD 300 per unit) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3. Capacity-building programs for woman groups : Technical and entrepreneurship development trainings Target: 2 sessions per year per group x 50 groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Support to the sesame value chain Target 50 groups (2500 beneficiaries) amongst them 40 percent of women and youth and 10 | Federation of producers and herders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1. Contracts with grower groups (10) for the Production purchase and distribution of basic seeds. The contracts are 100 percent subsidized |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.2. Negotiation with buyers and banks to support strategic partnerships within value chain stakeholders. Provision to subsidize contracts for collection and transportation of the products | FAO CNCPRT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.3. Capacity-building programs for sesame groups: technical training in the FFS (10) and organization | ANADER CNCPRT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.4. Extensive sesame production and Negotiation and contract with herder groups (10) for fodder seed collection / distribution / extensive seeding to mobile agropastoralists in partnership with land restoration activities with ANGMV (sesame IS associated with gum tree seeds) | Federation of herders ANGMV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.5. Equipment for 2 Federations: 4 motorbikes, support to 4 technicians and provision, 20 tablets | FAO Chad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Mainstreaming climate change adaptation into national and local policies and strategies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.2. Three (3) national laws and their implementation decrees are disseminated at the provincial and local levels | - Communication services: Radio broadcasts (5 per law x 3 laws x=15 broadcoasts) Flyers, leaflets and booklets | HC-CACT LBOD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - 14 one-day local Workshops (one by canton x14) x 3 laws = 42 with local chiefs groups by canton (4 workshops per law x 3 laws) | FAO Chad CPA HC CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.1: Institutional mechanisms at the national level are in place to facilitate implementation and mobilize resources Indicator: Performance of the national and regional Bodies (Focal Points, PU, CPA) to lead, coordinate and support the integration of climate change adaptation into relevant national and regional plans and associated processes | - Support to the establishment of four Planning Units (PUs) in each province by a Ministerial Decree (MSP). Institutionnal arrangement to lead and coordinate the integration of CC adaptation measures into Provincial Plans under the responsibility of the Gouvernorates – Activity linked to Output 1.1.1 | MSP Governorates FAO Chad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Quarterly meeting between the five focal points under the responsibility of the GEF FP for operations and connection with their respective administration. ¨Provision for communication, monitoring, and liaison (USD 1000 per year x 4 years) | GEF Focal Point |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Supervision mission (1 per year x 2 focal points x 21 h/d) + 1 evaluation mission (GEF focal point x 30h/d) x USD 200/d | Focal Points |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Advocacy for resource mobilization. Provision for communication USD 2,000 / year and meetings | GEF focal point |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Nnational workshop on the integrated approach, and extension services facing CC 2 national experts x 21 h/d | FAO – MPIEA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.3. A National Multi-Actors Forum on Land and CC is conducted at national level. | - Study on lessons learned for the future of land tenure in Chad ; (1 international Expert + 1 National Expert) x 30 h/d | FAO Chad FAO regional project on land governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Preparation for various stakeholders (Government, civil society, HC-CACT, and religious leaders) to bring together competencies, lead consensual positions and identify main issues to be addressed | FAO Chad OXFAM HC CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Establishment of a national communication/advocacy team for dialogue sessions with local communities in the Provinces | FAO Chad OXFAM HC CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - 4 local workshops (Provinces) on Responsible Governance on Land Tenue and Natural Resources with various local stakeholders (civil society, traditional Chiefs, Farmers’/Herders’ Organizations, Chiefs of the Land, religious leaders, police and army) | FAO Chad FAO regional project on land governance HC CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Mobilization of Technical and financial partners for helping with the set-up of the national Forum | FAO Chad GEF Focal point MPIAE – Ministry of livestock – MPWF - MPP HC-CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Support for the implementation of the of the national forum roadmap and multi-actors dialogue frameworks | FAO FAO regional project on land governance OXFAM HC-CACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Capacity-building programs for change agents on guidelines to test innovative approaches aiming at promoting the land rights for women and youth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# APPENDIX III. Budget

# APPENDIX IV. Risk management

### Section A: Risks to the project

| RISK DESCRIPTION | CONSEQUENCE | RISK SCORE |  | MITIGATION ACTION | Action owner |
| --- | --- | --- | --- | --- | --- |
|  |  | Likelihood | Impact |  |  |
| Limited partnership-building constrains project implementation and durability of project results. | Under funding of the plans (PCCAs) | Medium | Medium | Advocacy for resource mobilization and partners’ engagement | - GEF Focal Point - FAO |
| Conflicts between pastoralists and crop farmers, and between different groups of pastoralists have been on the rise in Chad, where livestock populations have increased dramatically over the last decade. Conflicts are both inter and intra-community. | Such conflicts can be further aggravated by security issues and prolonged droughts rendering pastures unusable, thus threatening the participatory multi-stakeholder land use planning mechanisms promoted by the project. | Medium | Medium | Putting in place mutually agreed land use rules in order to reduce conflicts between pastoralists and crop farmers, and between different groups of pastoralists. The project will mitigate this risk head-on through some of the main planned activities: building trust among different land user groups; adapting the regulatory framework with regards to land and natural resource tenure and use rights; establishing or restoring secure livestock mobility corridors and pasture grounds; and increasing livestock feed availability through the promotion of new fodder value chains. | - Local Bodies for Dialogue and Decision (LBODs) |
| Instability of political power (Ministers and Governors) and staff in the public administrations is a key concern in Chad, especially in areas vulnerable to insecurity. Large parts of territories are not covered by local administration while they are confronted to armed rebel groups. It is difficult to lead and apply policies and strategies over rural territories. | Staff trained may be outposted. | Medium | Medium | The project will finance technical assistance to transfer skills, tools and knowledge to local administration and offer incentives for 26 staff of technical services from Agriculture, Livestock and Environment. They will also benefit from strong capacity-building programs to develop the integrated approach and new CCA Agricultural / Livestock extension practices and technologies. | - Project Steering Committee - National Project Coordinator |
| Security concerns in Lac Province (but also to some extent in Kanem Province) limit the project’s ability to implement field-level activities in the areas affected | Areas of intervention are not reachable by car and regional trade is affected by insecurity. | Medium | Medium | In Lac Province, the project will invest in ecosystem restoration and protection alongside major donor investments where security of project staff, partners and beneficiaries can be guaranteed. With the help of the UNDSS office in N’Djamena, FAO will monitor new security developments closely, enabling the project to adapt. If necessary, emergency / security plans will be developed by the project stakeholders including FAO and the responsible ministries. | - FAO - National Project Coordinator |
| Limited capacity of local government institutions, such as ANADER. Chad has never made a major decentralization effort, and limited capacity in provincial and local technical services – aggravated by staff constantly moving around – is a well-known constraint. | Technical and Financial Partners plan without consultation of the local administrations. Actions are not coordinated and integrated to better impact on communities. | Medium | Medium | The project will mitigate this risk by setting up Local Planning Units within Provincial Action Committees (PACs), and building on the decision-making and implementation capacity of civil society (e.g. customary land chiefs, producer organizations and their federations) and by fielding approaches based on dialogue and public-private partnerships. In addition, NGOs that will be contracted for execution in partnership with government agencies for project implementation will work intensively with government and integrate their action within the local Plans and gradually transfer skills to government counterparts. Furthermore, capacities of decentraliszed technical services and ANADER will be strengthened through vigorous capacity development programs, and ensuring their direct engagement (applying the capacities) in the execution of the project components. | - Provincial Governors - Ministry of Land Use Planning - National Project Coordinator |
| High costs and difficulties in intervening in remote locations undermine project impact. The Project intervention area (the four Provinces) is very large and transport infrastructure in most of the area is very limited. Hence it may be costly, impractical to intervene across the area. | Project areas are too concentrated creating inequitable access to opportunities and resources between sous-préfectures | Low | Low | This is considered low risk. First, the nature of this project is to deal largely with pastoralists, many of whom are semi-transhumants, hence difficulties in reach project stake-holders are integral to the project and overcoming these is part of the project design. Moreover, this only applies to a small percentage of project site. Finally, the project will often work with/through locally active organizations and this will increase outreach and lower costs. Digitalization of technical services by the use of tablets. | - Provincial Action Committees - National Project Coordinator |
| Difficulty to engage women technicians and socio-economic skills for ANGMV and decentralized technical services | Lack of women empowerment and inequalities in implementation, access to resources and benefits. | Medium | Medium | Providing incentives for women. Dialogue at all levels and the project incorporating conditions for women participation in the planning and implementation of the provincial plans. Sensitization of local authorities and chiefs. | - Project steering committee - National Project Coordinator |

### Section B. Environmental and social risks from the project

| ESS Standard | Risk | Classification | Mitigation action | Indicator |
| --- | --- | --- | --- | --- |
| ESS 1 | Negative impact on natural resources; land tenure; result in a reduction of the adaptive capacity to climate change for any stakeholders in the project area? | Low | The project aims for sustainable management of natural resources including through community dialogues to reduce conflicts and increased agricultural and fodder production. The project would support small-scale, highly water-efficient drip irrigation schemes in the ouadis in Kanem and Bahr al Gazal Provinces. The project’s planned investments in stabilizing and restoring dune ecosystems near the ouadis would actually protect the ouadi ecosystem functioning. Regarding tenure, actually, the project activities would strengthen tenure rights through improved dialogue on land issues, land use plans in agro-pastoral areas and relevant laws and regulations in support of rights of access to natural resources. Also, the project will collaborate with FAO’s regional project to further the application of FAO’s Voluntary Guidelines on the Governance of Tenure in a number of Sahelian countries, including Chad, which is funded by Germany’s International Climate Initiative (IKI). The project aims to increase resilience of ecosystems and local communities to climate change. |  |
| ESS 2 | Negative impact on biodiversity, ecosystems and natural habitats | Low |  |  |
| ESS 3 | Non-sustainable use of genetic plant resources | Low | Plant genetic resources for food and agriculture • The project will involve the importing or transfer of sesame seeds for cultivation adapted to the need of the market and West African buyers • The project will import seeds from neighbouring Burkina Faso as the local stakeholders requested for this during the project preparation thus accepted by farmers and consumers. • It is expected that the procurement, use and storage of these seeds will adhere to set FAO standards including ensuring that seeds are free from pests and diseases. • To achieve the above, at implementation, the type of seeds will be agreed again with together the farmers and other stakeholders representing consumers and clearances for procurement of seeds will be sought from Plant Genetic Resources and Seeds Unit. • It has also been established that saving of seeds is permissible in Chad. |  |
| ESS 4 | Non-sustainable use of genetic animal resources | Low |  |  |
| ESS 5 | Management of pests and pesticides | Low | Pest and pesticides management - Pesticide use is not foreseen in the project, as integrated pest management (IPM) will actively be followed through the field schools. - However, in the event that the absolute need to use pesticides arises, guidance and clearances will be sought from Pest and Pesticide Management (AGPMC). |  |
| ESS 6 | Resettlements and involuntary displacements | N.A. |  |  |
| ESS 7 | Promotion decent employment | Low | The project will promote decent employment when supporting rural livelihoods. |  |
| ESS 8 | Gender inequality | Low | The project specifically supports women empowerment and livelihoods, promoting their active engagement in land-use decision making and use. | Number of women supported by the project |
| ESS 9 | Limited direct and informed participation of indigenous peoples Displacement of traditional and local uses of the forests | Low. N.A. |  |  |

# APPENDIX V. Stakeholder engagement

| Stakeholder Name | Stakeholder profile | Consultation methodology during PPG | Consultation findings | Engagement in Implementation |
| --- | --- | --- | --- | --- |
| Ministère de la Production de l’Irrigation et des Equipements Agricoles (MPIEA) | Civil Society Organization | Meetings in N’Djamena | Inputs to the project design and validation of the project document | Bilateral meetings with FAO at political level |
| 4 Focal points (Agriculture, Livestock, Forestry and GEF) | Non-Gonvernmental Organization | Meetings in N’Djamena | Inputs and agreement on the project multi-disciplinary approach, CC adaptation strategies, GEF intervention in Chad | Members of the Steering Committee. The focal points will facilitate the integrated approach and implementation at the national level, and contribute to national-provincial linkages |
| National Directorates of Agriculture / Livestock / Forestry and Territory Planning ( (Aménagement du territoire) | National Government Institution body | Meetings in N’Djamena | Contributed to the analysis of national policy and institutional frameworks and design of project components. | Engagement in implementation. |
| ÂNADER | National Government Institution body | Meetings and email exchanges | Inputs to the analysis and proposals on institutional reform, Integrated approach, area of intervention human resource capacity for implementation | Direct involvement in implementation through a letter of agreement (execution agreement) for some subcomponents |
| Projet P2RS de renforcement de la résilience pour la sécurité alimentaire Financement BAD | Resource Partner/Donor | Meetings, email exchanges | Technical and financial partnership in BEG and Kanem (comp.1 and 2), area of intervention to better impact on rural communities. Co-financings | Engagement in preparation of provincial plans (PCCAs) - the technical and financial partnership: areas of intervention, investments Year 1, 2, 3, 4 |
| Projet FAO Sahel sur les Directives Volontaires pour une Gouvernance responsable des régimes fonciers | Resource Partner/Donor | Several skype call meetings and email exchanges | Support to policy dialogue in favor of responsible governance of land tenure, co-financing | Engagement in preparation of provincial plans (PCCAs) - technical and financial partnership: areas of intervention, investments Year 1 and 2 |
| Projet RESILAC (redressement économique et social inclusif du Lac Tchad) Financement UE / AFD | Resource Partner/Donor | Meetings, email exchanges | Partnership in the Lake Province, Bagassola and Bo, cofinancingl (comp. 1 and 2) | Engagement in preparation of provincial plans (PCCAs) - technical and financial partnership: areas of intervention, investments Year 1, 2, 3, 4 |
| Projet de Réaménagement hydroagricole de Tandal NGuimi Financement AFD | Resource Partner/Donor | Meeting | Implementation context in the Lake Province, 1000 ha to develop with full water control € 10 M. | Engagement in preparation of provincial plans (PCCAs) - technical and financial partnership: areas of intervention, investments Year 1, 2, 3, 4 |
| Projet PROLAC de Relance et de Développement de la Zone du Lac Tchad Financement Banque Mondiale | Resource Partner/Donor |  | Information on the ongoing formulation of the program, USD 45 million for Chad component. Infrastructure, capacity building. | Engagement in preparation of provincial plans (PCCAs) - technical and financial partnership: areas of intervention, investments Year 2 , 3, 4 |
| Comité Provincial d’Action | Regional Government Institution/body | Meetings | Strengths and weaknesses for coordination and planification |  |
| Decentralized State technical services | Regional Government Institution/body | Meeting in N’Djamena and email exchanges with ANADER, several meetings in the field with the three technical services | Strengths and weaknesses to support agropastoralists, capacity of intervention, | Execution through Letter of Agreement. |
| HC CACT Haut Conseil des collectivités autonomes et des chefferies traditionnelles | Civil Society Organization | Meetings | Implementation of information / communication campaigns (comp.1 and 3), advocacy vis-a-vis traditional chieftaincies | Execution through Letter of Agreement. |
| ANGMG – Agence Nationale de la Grande Muraille Verte | National Government Institution body | Meetings and email exchanges | Implementation of comp1 (techniques for land restoration), National Restoration Plan, institutional framework | Execution through Letter of Agreement. |
| OXFAM | Non-Gonvernmental Organization | Meetings | Implementation of LBOD (comp.1) and Policy Dialogue on Land issue for the mobilization of the civil society (comp.3) | Execution through Letter of Agreement. |
| Federation of producers / Herders | Civil Society Organization | Meetings in N’Djamena | Food chain approach, contract for sesame and fodder VCs, structuration of local producer groups, relevance of wharehouses | Full engagement in project implementation through LBODs, consulted. |

# APPENDIX VI. FAO’s internal roles

The Food and Agriculture Organization (FAO) will be the GEF Implementing Agency for the proposed project, and as such, will utilize the GEF fees to provide project cycle management services. FAO will be responsible for providing oversight, technical backstopping and supervision of project implementation to ensure that the project is being carried out in accordance with agreed standards and requirements. As the GEF Agency, FAO will:

- Administrate funds from GEF in accordance with the rules and procedures of FAO;

- Oversee project implementation in accordance with the project document, work plans, budgets, and the rules and procedures of FAO;

- Provide technical guidance to ensure that appropriate technical quality is applied to all activities;

- Conduct at least one supervision mission per year; and

- Report to the GEF Secretariat and the GEF Evaluation Office, through the annual Project Implementation Review, on project progress and provide financial reports to the GEF Trustee.

Budget Holder and Lead Technical Officer

The Budget Holder (BH) is a key role in FAO’s project cycle. Every project in FAO has a designated BH, who is responsible and accountable for the financial oversight and management of project resources. For FAO-GEF projects, this FAO role meets important fiduciary responsibilities FAO bears as a GEF Agency.  For this role in FAO, the BH receives a portion of the GEF fee. In this project, the FAO Representative in Equatorial Guinea will be the BH and will be responsible for timely operational, administrative and financial management of GEF resources. The budget holder will be also responsible for the following; i) review and clear financial and progress reports received from executing partners and certify request for funds ii) review and clear budget revisions and annual work plans and budgets; iii) ensure that the Project implements all actions and recommendations agreed upon.

The BH will establish an interdisciplinary Project Task Force (PTF) within FAO. The PTF is a consultative body that integrates the necessary technical qualifications from relevant FAO units to support the project. The PTF comprises the Budget Holder, the Lead Technical Officer (LTO), the Funding Liaison Officer (FLO) and one or more technical officers based in FAO Headquarters and the Regional or Sub-regional offices.

The BH will assign a Lead Technical Officer (LTO) for the project. The LTO will be responsible for the technical supervision of the project. For this role in FAO, the LTO receives a portion of the GEF fee. Specifically, the LTO will:

- Provide technical guidance on technical aspects and implementation.

- Review and give no-objection to TORs for consultancies and contracts to be performed under the project, and to CVs and technical proposals short-listed for key project positions and services to be financed by GEF resources;

- Review and clear final technical products delivered by the project.

- Ensure the technical quality of the six-monthly Project Progress Reports (PPRs).

- Supervise the preparation and ensure the technical quality of the annual PIR.

- Conduct annual supervision missions.

- Provide comments on final evaluation TORs; provide information and share all relevant background documentation with the evaluation team; participate in the final workshop with all key project stakeholders, as required.

- Monitor implementation of the Risk Mitigation Plan, in accordance with the FAO Environmental and Social Safeguards.

The FAO-GEF Coordination Unit will act as Funding Liaison Officer (FLO). The FLO will undertake supervision missions as necessary and review and clear PPRs and the annual PIRs for submission to the GEF Secretariat. The PIRs will be included in the FAO GEF Annual Monitoring Review submitted to GEF by the FAO GEF Coordination Unit. The FLO may recommend the development of corrective actions in the project implementation strategy if needed to mitigate eventual risks affecting the timely and effective implementation of the project. The FAO GEF Coordination Unit may also participate in the final evaluation, The FAO GEF Coordination Unit will in collaboration with the FAO Finance Division request transfer of project funds from the GEF Trustee based on six-monthly projections of funds needed.

The FAO Financial Division will provide annual Financial Reports to the GEF Trustee and, in collaboration with the FAO-GEF Coordination Unit, request project funds on a six-monthly basis to the GEF Trustee.

# APPENDIX VII. Financial management

Financial management of GEF resources will be carried out according to FAO rules and procedures.

Financial Records. FAO shall maintain a separate account in United States dollars for the project’s GEF resources showing all income and expenditures. Expenditures incurred in a currency other than United States dollars shall be converted into United States dollars at the United Nations operational rate of exchange on the date of the transaction. FAO shall administer the project in accordance with its regulations, rules and directives.

Financial Reports. The BH shall prepare six-monthly project expenditure accounts and final accounts for the project, showing amount budgeted for the year, amount expended since the beginning of the year, and separately, the un-liquidated obligations as follows:

Details of project expenditures on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the project document, as at 30 June and 31 December each year.

Final accounts on completion of the project on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the project document.

A final statement of account in line with FAO project budget codes, reflecting actual final expenditures under the project, when all obligations have been liquidated.

Financial reports for submission to the donor (GEF) will be prepared in accordance with the provisions in the GEF Financial Procedures Agreement and submitted by the FAO Finance Division.

Budget Revisions. Semi-annual budget revisions will be prepared in accordance with FAO standard guidelines and procedures.

Responsibility for Cost Overruns. The BH is authorized to enter into commitments or incur expenditures up to a maximum of 20 percent over and above the annual amount foreseen in the project budget under any budget line provided the total cost of the annual budget is not exceeded.

Any cost overrun (expenditure in excess of the budgeted amount) on a specific budget line over and above the 20 percent flexibility should be discussed with the GEF Coordination Unit with a view to ascertaining whether it will involve a major change in project scope or design. If it is deemed to be a minor change, the BH shall prepare a budget revision in accordance with FAO standard procedures. If it involves a major change in the project’s objectives or scope, a budget revision and justification should be prepared by the BH for discussion with the GEF Secretariat.

Savings in one budget line may not be applied to overruns of more than 20 percent in other lines even if the total cost remains unchanged, unless this is specifically authorized by the GEF Coordination Unit upon presentation of the request. In such a case, a revision to the project document amending the budget will be prepared by the BH.

Under no circumstances can expenditures exceed the approved total project budget or be approved beyond the NTE date of the project. Any over-expenditure is the responsibility of the BH.

Audit. The project shall be subject to the internal and external auditing procedures provided for in FAO financial regulations, rules and directives and in keeping with the Financial Procedures Agreement between the GEF Trustee and FAO.

The audit regime at FAO consists of an external audit provided by the Auditor-General (or persons exercising an equivalent function) of a member nation appointed by the Governing Bodies of the Organization and reporting directly to them, and an internal audit function headed by the FAO Inspector-General who reports directly to the Director-General. This function operates as an integral part of the Organization under policies established by senior management, and furthermore has a reporting line to the governing bodies. Both functions are required under the Basic Texts of FAO which establish a framework for the terms of reference of each. Internal audits of imprest accounts, records, bank reconciliation and asset verification take place at FAO field and liaison offices on a cyclical basis.

G2a:  Gender is fully relevant, but is not the main objective of the project. Gender is integrated (mainstreamed) in all relevant dimensions of the project (results, activities, monitoring framework).

World Bank 2018.

FAO. Lake Chad, a system under threat.

National Development Plan (PND) 2017-2021

World Bank, 2018

UNESCO 2020. Chad Country Profile

USAID, 2017. Land links

World Bank. 2018.

IFAD, 2018.

Government of Chad. National Plan for Implementation of Chad’s CNSC

Changing Climate Over Chad: Is the Rainfall Over the Major Cities Recovering?

IFAD, 2018. President’s report for proposed debt framework grant to Republic of Chad.

The land Act of 1967, which does not take into account climate change, is the exception to this observation – see the text re Barrier 3 below

Politique nationale de l’aménagement du territoire, de l’urbanisme et de l’habitat, 2017.

Schéma Directeur de l’Eau et de l’Assainissement

A wadi is a dry riverbed that contains water during the (short) rainy season. Wadi land is very fertile, as the river deposits fine clay there.

See also paragraph 17 above.

Libya is not part of the current UNDP-GEF project

The priority cantons identified during project preparation are highlighted in yellow. Following a recommendation from the project validation workshop held in N’djamena, they will be reviewed based on the latest information (security, synergies with other investments), and possibly modified, during project inception.

For the B1 and A2 scenarii respectively, with larger increases during the spring and fall. " Africa Supra Regional, Adaptation to Climate Change in the Lake Chad Basin, GiZ 2015, https://www.giz.de/en/downloads/giz2015-en-climate-change-study-africa-supraregional.pdf

This project is currently under discussion with the donor and is expected to start in 2020.

Compliance Reviews following complaints related to the Organization’s environmental and social standards: http://www.fao.org/aud/42564-03173af392b352dc16b6cec72fa7ab27f.pdf

Original french title: « Promouvoir et vulgariser les nouvelles techniques agroforestières : régénération naturelle assistée (RNA) »

See https://www4.unfccc.int/sites/ndcstaging/PublishedDocuments/Chad%20First/CPDN%20TCHAD%20Version%20officielle%2028%20sept%202015.pdf

Many women’s groups returned to previous, artisanal production methods once project support ended and equipment could not be replaced.

FAO internal arrangements detailed in Appendix VI.