UNEP GEF PIR Fiscal Year 2020

Reporting from 1 July 2019 to 30 June 2020

| - Identification |  |  | GEF ID.: 4634 | Umoja no.: GFL/5060-2711-4C40; S1-32GFL-000370 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Conserving, Enhancing and Managing Carbon Stocks and Biodiversity in the Chernobyl Exclusion Zone |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  | 35 months |  | 31 December 2021 |
| Division(s) Implementing the project |  |  | UNEP Ecosystems Division |  |  |
| Name of co-implementing Agency |  |  | N/A |  |  |
| Executing Agency(ies) |  |  | UNEP Europe Office |  |  |
| Names of Other Project Partners |  |  | Ministry of Ecology and Natural Resources of Ukraine |  |  |
|  |  |  | State Agency on Chernobyl Exclusion Zone |  |  |
| Project Type |  |  | Full Size Project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Europe |  |  |
| Names of Beneficiary Countries |  |  | Ukraine |  |  |
| Programme of Work |  |  | POW 2018-2019 Subprogramme 3. Healthy and Productive Ecosystems, EA (a) the health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national international level |  |  |
| GEF Focal Area(s) |  |  | Multi Focal Area |  |  |
| UNDAF linkages |  |  | Partnership Framework Area: Environment and Climate Change / Outcome 1 – Government of Ukraine adopts policy frameworks and mechanisms to ensure reversal of environmental degradation, climate change mitigation and adaptation, prevention and response to natural and man-made disasters. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Goal 15 – Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. 15.1 – By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements. 15.1.1 – Forest area as a proportion of total land area. 15.1.2 – Proportion of important sites for terrestrial and freshwater biodiversity that are covered by protected areas, by ecosystem type. 15.2.1 Progress towards sustainable forest management. |  |  |
| GEF financing amount |  |  | US$ 4,863,955 |  |  |
| Co-financing amount |  |  | US$ 28,340,000 |  |  |
| Date of CEO Endorsement |  |  | 12 December 2014 |  |  |
| Start of Implementation |  |  | 16 March 2015 |  |  |
| Date of first disbursement |  |  | 16 March 2015 |  |  |
| Total disbursement as of 30 June |  |  | US$ 4,863,955 |  |  |
| Total expenditure as of 30 June |  |  | US$ 3,502,041 |  |  |
| Expected Mid-Term Date |  |  | 01 March 2020 |  |  |
| Completion Date |  | Planned | 31 December 2018 |  |  |
|  |  | Revised | 31 December 2021 |  |  |
| Expected Terminal Evaluation Date |  |  | 30 October 2021 |  |  |
| Expected Financial Closure Date |  |  | 31 May 2022 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) PoW 2018-19 Subprogramme 3 Healthy and productive ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels Indicator (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems Indicator (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services |
| --- | --- |
| National Biosphere Reserve established in the Chernobyl Exclusion Zone by the Decree of the President of Ukraine. Close contacts developed and maintained with the Polessky Radiological Reserve in Belarus, thus effectively creating a transboundary protected zone in the areas of Ukraine and Belarus affected by the Chernobyl nuclear accident. Staff and management of the Biosphere Reserve are in place, and a scientific research plan was presented to Government. The development of a comprehensive database capturing critical knowledge on ecosystems and development of landscapes was further advanced, while protocols for public access need to be agreed upon. A comprehensive ecosystem services assessment in the ChEZ is under development, providing the backbone for the PA management plan. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |
| N/A – GEF 5 project |  |

| Planned linkages with UNDAF | Partnership Framework Area: Environment and Climate Change / Outcome 1 – Government of Ukraine adopts policy frameworks and mechanisms to ensure reversal of environmental degradation, climate change mitigation and adaptation, prevention and response to natural and man-made disasters. The project has supported the development of a complex approach to the protection of natural ecosystems in the Chernobyl Exclusion Zone, including adaptation and readiness to fire intensity in the radiologically contaminated Chernobyl forest as a result of climate change impacts. The ongoing ecosystem services assessment incorporates habitat rehabilitation, carbon stock management and biodiversity conservation. All baseline studies for the establishment of the ChEZ Research and Environmental Protection Center (REPC) have been completed. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The Chernobyl Biosphere Reserve that the project helped establish as well as the collection and synthesis of scientific data on the biodiversity in the area and ecosystem services contribute to the achievement of targets 15.1.1; 15.1.2; and 15.2.1. |
| --- | --- |

| Implementation Status | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR |

| Development Objective Rating FY | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | S | MS | MS |
| It was an unusual year for the project implementation, due to the COVID-19 pandemic and ensuing global lock-down. Considering the circumstances, the project made some progress on its development objectives and recovered from some delays incurred during the previous period, when delayed project financing caused some implementation delay. Although, the Project made some progress and the government counterpart continues to demonstrate a strong project ownership and actively promotes the achievement of project objectives and public outreach, the Project needs to catch up the lost time to deliver planned outcomes. In line with the project’s overall objective, the Biosphere Reserve is established and decreed, including a management plan emphasizing the linkages to the Polessky Reserve in Belarus (indicator of outcome 2). Amid intensive stakeholder consultations, staff and management of the Biosphere Reserve are in place, and a scientific research plan is developed and presented to Government (outcome 1). The development of a comprehensive database capturing critical knowledge on ecosystems and development of landscapes is completed and protocols for public access are in the final stage of being agreed upon (outcome 3). Considering the unusual circumstances that the project operated in, a satisfactory level of progress seems to be a fair assessment for the project this year. |  |  |  |  |  |

| Implementation Progress Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | S | MS | MS |
| Considering the challenges faced in the project preparation and approval period, the project has fallen behind the planned schedule. The status in the delivery of outputs is progressing in a positive way compared to the previous stages., Steady progress along all project activities was achieved in the period under review, despite the unusual circumstances for half of the year caused by COVID-19. The Mid-term Review held in December 2019 also recognized a stable progress in the project implementation, despite the slow inception phase and temporary setbacks in the previous periods. Recommendations made by the MTR were reviewed by the project Steering Committee Meeting and relevant response measured included in the current year’s workplan. The ChEZ Research and Environmental Protection Center (REPC) is established and operationalized, with gradual expansion of its stakeholder base; full ecosystem services assessment in the ChEZ although slightly delayed because of the COVID-19 lock-down, is on the right track of implementation (outputs under outcome 1).ChEZ Protected Area is fully established and measures for its financial and institutional sustainability are under the direct control of the management of the State Exclusion Zone Agency. Government attaches high priority to this subject, therefore the financial mobilization for the ChEZ Biodiversity Reserve is mainstreamed into the government funding policy (outputs 2). The compilation of lessons learned and recommendations on habitat rehabilitation, carbon stock management and biodiversity conservation is ongoing, as are efforts for their wider distribution (outputs under outcome 3). The mid-term review of project achievements has been conducted with positive results (output 4). |  |  |  |  |  |

| Risk Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 |
| --- | --- | --- | --- | --- | --- |
|  | M | M | L | L | L |
| Through the years of project implementation, the main risk factor – unstable government – was adequately addressed by the project team, thus contributing to reducing the impacts on project performance. The global CODIV-19 pandemic obviously introduces a substantial risk factor. However, the strong national ownership demonstrated by the government and the stable project progress allow to assess the risk as low. |  |  |  |  |  |

| Stakeholder engagement | The project Inception Meeting and regular stakeholder engagement meetings have ensured even involvement of stakeholders in the project implementation all the way through. The project provides excellent opportunity to involve government ministries and agencies at local and national levels, as well as national, regional and international academic and research institutions, the private sector, NGOs and other stakeholders. They work together under the leadership of the MENR and coordinated by the PMU to fill knowledge gaps and participate in the successful creation and management of a protected area network in and around the ChEZ. |
| --- | --- |

| Gender mainstreaming | Stakeholder outreach programme implemented by the project includes gender segregated data collection. |
| --- | --- |

| Environmental and social safeguards management | The MTR recommended that conducting a periodical socio-economic survey in the ChEZ neighbouring areas of Ivankiv and Zythomyr districts will be beneficial to understand the social and economic status of the region, and define activities for the dissemination of the Project results and further improvement of the management plan and proposed impacts from the project especially in social dimension. This task will be taken onboard by the Chernobyl Radiological and Biosphere Reserve and will be incorporated in the project workplan., as referred in Output 2.1. in Project Results Framework. |
| --- | --- |

| Knowledge activities and products | The Project team has not reported any Knowledge activities in this period |
| --- | --- |

| Stories to be shared | A publication to share project results and a major international scientific conference are planned for the next year. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Enhanced Conservation, and Management of Carbon Stocks and Biodiversity in Forest and non-Forest Lands in the Chernobyl Exclusion Zone (ChEZ), in Ukraine. | Number of hectares declared as Biosphere Reserve with formalized links to Polessky Nature Reserve. | The current extent of protected area within the ChEZ is approximately 20% (46,000ha), with generally a low level of protection; Lack of formalized links with the Polessky nature reserve. | Legislative and regulatory mechanisms necessary to long-term management of the newly protected areas in place by the end of year 2; | Presidential Decree upgrading the ChEZ to Biosphere Reserve (230,000 ha) status expected by mid- year 3; | Biosphere Reserve is established by the Presidential Decree. Institutional arrangements are accomplished, with the management and staff of the Biosphere Reserve fully in place. The Project has contributed significantly to the smooth start of the Biosphere Reserve. | S |
|  |  |  | Extensive stakeholders consultations for establishment of the new PA initiated by end of year 1. | By beginning of year 4 sustainable use activities through development and implementation of a “Triad Approach” has begun; Results of the triad approach are apparent and are quantified by the end of year 4. | Extensive stakeholder consultations have been held by the Project to involve all interested stakeholder groups and institutions into the development of the management plan. A recent visit by the Biosphere Reserve and Project staff to a donor coordination meeting in Belarus revealed significant transboundary efforts undertaken by the Project and a potential for the further transboundary development of the GEF Project. | S |
|  | A formally adopted Protected Area Management Plan for the ChEZ | No sustainable management plan has been implemented for the ChEZ; some initial forestry planning | By mid-year 2 draft management plan developed; Final draft submitted to government for approval and funding by the end of year 2. | At end of year 2/mid-year 3 a sustainable management plan has been developed for a 230,000 ha Biosphere Reserve, with formalized links to Polessky Nature Reserve. | The management plan is developed with a strong emphasis of linkage with the Polessky Reserve in Belarus. | S |
|  | Formally established and operational ChEZ Research Environmental Protection Center (REPC) | The current Chernobyl Research Center is understaffed and underfunded; Limited Center focus on environmental protection 4. | Beginning of year 2 center staffing and budgetary needs detailed and submitted to government for approval; End of year 2 centre staffed and working with an approved research plan; | End of year 4 the Center is fully functional with full complement of staff, approved budget, and agreed upon research agenda. A collaborative transboundary international program on radioecological research, monitoring and management of carbon stocks in forest and non-forest lands, and protected areas management is initiated with the Polessky State Reserve in Belarus. | All baseline studies completed. Center staffing and budgetary needs determined. The blueprint of the future scientific and research centre presented to the government. | S |
| Outcome 1: Improved monitoring and research for large areas of forests, wetlands, and other habitat types and associated carbon benefits in the ChEZ | Environmental monitoring systems designed and operational and generating information on state of the ChEZ environment. | No conservation based research or field experiment program in place in ChEZ; Limited research program that does not meet the requirements of an expanded and upgraded protected area in the ChEZ. | By mid year 2 a stakeholder driven research plan developed; End of year 2 research plan forwarded to government for appropriate action. Linkages with at least four relevant national and/or international educational institutions established | Center based activities (e.g. publishing and making available monitoring data) Begin by the end of year 3. End of year 3, linkages created with relevant international agreements and platforms (e.g CBD, Ramsar, CCD). | Stakeholder driven research plan developed; Environmental monitoring system is in place. Linkages with CBD, Ramsar and other relevant international agreements and structures are developed. | MS |
| Outcome 2: Improved management of natural resources and carbon stocks within and around the ChEZ. | Number of hectares declared as Biosphere Reserve with formalized links to Polessky Nature Reserve; Stakeholders contributing to maintain and protect nature reserve; Approved management plan. | Current amount of PA in ChEZ approximately 20% (46,000ha), but low level of protection; Legislation to expand PA in ChEZ not in place; Assessment of carbon stocks and other natural capital in ChEZ incomplete in some cases and not undertaken in others. | Legislation focused on expanded ChEZ PA in place by mid-year 2; Draft of ew/expanded protected area plan by mid- year 2; Established cooperative arrangements with Polessky Nature Reserve end of year 2. Public consultations have occurred by end of year 2. | At end of year 2 a sustainable management plan has been developed for a 230,000 ha Biosphere Reserve, with formalized links to Polessky Nature Reserve, and submitted to government for approval. PA management structure in place end year 3; Records or public involvement contain gender segregated data. | Expanded protected area plan developed. Cooperation arrangements with the Polessky Natural Reserve established. Records of public involvement meetings contain gender segregated data. | S |
| Outcome 3: Increased availability and access to critical information needed for decision-making for effective sustainable management of the ChEZ. | System for tracking number of requests for data and other information. | Substantial knowledge gaps exist; What knowledge does exist is scattered which makes access and availability difficult. | By end of year 2 establishment of a comprehensive data base that would drive efforts to physically or electronically repatriate critical knowledge in the REPC initiated. | By end of year 4 comprehensive data base completed and located in the REPC; Repositories in place and access protocols and data sharing agreements finalized by end of year 4. | Development of a comprehensive database capturing critical knowledge on ecosystems and development of landscapes is nearly completed. Data access protocols and data sharing agreements are being finalized. | MS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | This year, being an unusual one because of the global COVID-19 situation, obviously had a negative impact on the project implementation. However, despite that, the project managed to recover from the setbacks of the previous year caused by interruptions in the project financing and managed to achieve and maintain steady progress on project activities. Although, the Project made some progress and the government counterpart continues to demonstrate a strong project ownership and actively promotes the achievement of project objectives and public outreach, the Project needs to catch up the lost time to deliver planned outcomes. In line with the project’s overall objective, the Biosphere Reserve is established and decreed, including a management plan emphasizing the linkages to the Polessky Reserve in Belarus (indicator of outcome 2). Amid intensive stakeholder consultations, staff and management of the Biosphere Reserve are in place, and a scientific research plan was presented to Government (outcome 1). The development of a comprehensive database capturing critical knowledge on ecosystems and development of landscapes is in its final stage, and protocols for public access are being completed. (outcome 3). |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects are free to put N/A to sections or add additional rows for other problems/risks such as those identified at CEO Endorsement.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving Mid-Term and End of Project Targets as identified above | Objectively slow speed of administrative and operational procedures necessitating prolongation of implementation of the planned activities. | As recommended by MTR and as approved by the PSC meeting, the project duration will be extended by 12 months at no additional cost. |
| on delivering GEF Core Indicators |  |  |
| on stakeholder engagement | Due to the COVID-19 situation, stakeholder meetings and other forms of broad stakeholder engagement can be hampered. | Stakeholder engagement meetings are rescheduled to a later period, other forms of stakeholder engagement, e.g. through online communication are being evaluated. |
| on gender actions | Insufficient understanding of gender mainstreaming priority among many stakeholders and project implementing partners. | Consistent gender mainstreaming policy and gender-segregated data management applied by the PMU. |
| on safeguards |  |  |
| on sustainability of results | Risk of degradation of project results after the project completion. | Strong government ownership and close integration of the PMU with the Biosphere Reserve allow to minimize this risk. |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2019 | Implement-ation status as of 30 June 2020) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1 The REPC established and fully functional |  | 90% | 95% | Work nearly completed on the REPC establishment but its full operationalization and access to stakeholders got delayed due to the COVID-19 situation. | MS |
| Output 1.2 Comprehensive assessment of the current state and trends of natural ecosystems in ChEZ |  | 100% | - | All relevant activities have been completed. | S |
| Output 1.3 Assessment of the status of ecosystem services and their values, enhancement of carbon benefits in terms of meeting LLUCF targets in the ChEZ |  | 90% | 95% | Data assessment and synthesis are in advanced stage nearing completion. | MS |
| Output 2.1: The ChEZ is upgraded to the status of Protected Area network to enhance the conservation and management of carbon stocks and secure the long-term basis for appropriate management, monitoring and research for large areas of forests, wetlands, and other habitat types |  | 100% | - | The Biosphere Reserve is fully functional and expanding its network. | S |
| Output 2.2 Measures developed to ensure financial and institutional sustainability of multi-sector conservation programs |  | 80% | 90% | Government has mainstreamed this into its core policy. | MS |
| Output 3.1 A set of lessons learned and practical recs. developed and published on habitat rehabilitation, carbon stocks management and biodiversity conservation emerged from prior and ongoing work in the ChEZ, and applicable to similar situations |  | 80% | 90% | Material is prepared for publication in the nearest time. | MS |
| Output 3.2 The results are widely disseminated nationally and internationally |  | 90% | 95% | Work in steady progress. A major scientific conference is planned for the next year. | S |
| Output 4 Monitoring and Evaluation |  | 80% | 90% | Mid-term evaluation conducted with positive results. | S |
| Output 5 Project Management |  | 90% | 95% | Work continuously in progress. PMU is provided by the Biosphere Reserve. | S |

Overall project implementation progress

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Considering the challenges faced in the project preparation and approval period, the project has fallen behind the planned schedule. The status in the delivery of outputs is progressing in a positive way compared to the previous stages., Steady progress along all project activities was achieved in the period under review, despite the unusual circumstances for half of the year caused by COVID-19. The Mid-term Review held in December 2019 also recognized a stable progress in the project implementation, despite the slow inception phase and temporary setbacks in the previous periods. Recommendations made by the MTR were reviewed by the project Steering Committee Meeting and relevant response measured included in the current year’s workplan. The ChEZ Research and Environmental Protection Center (REPC) is established and operationalized, with gradual expansion of its stakeholder base; full ecosystem services assessment in the ChEZ although slightly delayed because of the COVID-19 lock-down, is on the right track of implementation (outputs under outcome 1).ChEZ Protected Area is fully established and measures for its financial and institutional sustainability are under the direct control of the management of the State Exclusion Zone Agency. Government attaches high priority to this subject, therefore the financial mobilization for the ChEZ Biodiversity Reserve is mainstreamed into the government funding policy (outputs 2). The compilation of lessons learned and recommendations on habitat rehabilitation, carbon stock management and biodiversity conservation is ongoing, as are efforts for their wider distribution (outputs under outcome 3). The mid-term review of project achievements has been conducted with positive results (output 4). |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks, if any (e.g. procurement delays, reputational risks etc).  The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Risk to the project implementation rate due to disruptions with project financing. | Financial reporting format and practice to be clarified and improved between the Executing Agent and Implementing Agent. | FMO of Executing Agent / Project Manager | Done |
| Project progress reports delayed | Project Progress Reports to be developed and circulated on a timely manner | Project Manager | continually |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Climate Change Over the past several years severe forest fires have increased in intensity and seasonal duration in the vicinity of the ChEZ, and climate change is suspected as being a major contributor to this change. | The research plan that will be developed during project implementation will include climate change mitigation strategies, deemed especially important in relation to fire hazards in the ChEZ as described below. | Climate change mitigation measures for the Chernobyl forests are developed. | CEO: M |
|  |  |  | TM: M-L |
|  |  |  | PM: L |
| Fire hazards In forests contaminated by radiation fire poses a continual risk (in addition to carbon emissions): forest fires could send clouds of smoke carrying radioactive material into the atmosphere, contaminating fire fighters and posing a risk to food production. Forest fires in the ChEZ contain radioactive cesium, strontium and often plutonium. In the products of combustion (ash and partially burnt fuels), the concentration of radionuclides sharply increases. A part of the radioactive ash remains at site, while the remainder in released in smoke aerosols and transported over various distances. The observed and anticipated pattern of climate change, with modified rainfall patterns and extended periods of drought, are expected to increase the risk of forest fires, as well as the risk of attack by insect pests. | The project will promote a range of applicable sustainable land-use and forest management practices that will reduce wildfire hazards, while also enhancing carbon stocks. These may include i.e.: silvicultural measures for reducing wildfire hazard in coniferous forests, particularly the introduction of less flammable and economically valuable broadleaved tree species intermixed in pure coniferous stands; thinning operations and sanitary cuts; construction of anti-fire barriers consisting of firebreaks and internal fuel breaks, fire-resistant forest edges and shaded mineralized shelterbelts. | Fire protection and monitoring systems are being deployed by the project to minimize the fire hazard. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Reduced commitment to the conservation-based nature of project objectives and outcomes due to changes in government | Changes in government commitment cannot be excluded and are difficult to assess. The recent change in government serves as an example of this risk. For this reason, among others, the project has been based on inclusion of a wide group of stakeholders at each step of project formulation, and this will continue to be the case during implementation, which increases the chances for continuity and sustainability. Further, the utilization of existing institutional structures in e.g. the MNRE, MoE, Academy of Science, National Universities and in the existing ChEZ Centre, as well as at technical working levels will have a mitigation effect in case of higher-level government changes; such bodies often continue to exist beyond governmental life cycles. | National project counterparts are demonstrating full commitment to and ownership of the project. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Weak institutional capacity | Within national governmental institutions as well as at local levels, the risk of a weak understanding of sustainable, ecosystem-based management approaches is high. However, the project’s strategy is founded on close interaction and capacity building at all levels of intervention in order to address this challenge, and government commitment is well demonstrated through substantial co-finance. Early and continuing stakeholder mapping and engagement (as initiated during the PPG) will help ensure project success. | Project management team has ensured stakeholder engagement since the inception stage of the project and payed particular attention to the institutional strengthening of the partner institutions the project has been dealing with to ensure the sustainability of the results. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Inability of the Government to meet its financial and co-financial commitment | The Government has made clear that its letter of co-finance continues to be valid. However, social, political and financial uncertainty remains | The amount of paid co-finance so far proves the commitment of the government. | CEO:M/H |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Continuing civil and international conflict may jeopardize the ability of the Government to properly focus on the project | As the project will be centered in Kiev and in the and around the immediate vicinity of the ChEZ, areas not in the south and east of the country where civil and international strife has occurred, this risk is seen as manageable | The situation in Ukraine has significantly stabilized over the years of the project implementation, which lowers the probability of this risk. | CEO: M/H |
|  |  |  | TM: M-L |
|  |  |  | MP: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

Assessment of Possible COVID-19 Impacts to the Project, GEF id: # _________

| COVID-19 impacts | - Has the COVID-19 pandemic impacted project implementation? If so, how? Yes, the general lock-down in Ukraine during the months of March-May 2020 and subsequent slow recovery from the crisis caused significant delays in implementation. - Is there a pattern to the kinds of project activities/outputs that have been significantly impacted by the COVID-19 impacts? Yes No If Yes, please explain: Typically, all the activities that involve field work, surveys, sampling and other similar activities requiring local travel had to be rescheduled. - Is there a pattern to the kinds of project activities/outputs, if any, that have not been seriously impacted by COVID-19 and are somehow able to continue? Yes No If Yes, please explain: Production of desktop reviews, outreach to stakeholders through online means of communication were not suffered. - Will COVID-19 impacts, as of 30 June 2020, have implications on the project’s ability to finish by the expected completion date? Yes No. If Yes, please estimate the likely additional extension required: 12 months. (we realize that, until such a time that work conditions have returned to normal, this could likely be an underestimate). - Will COVID-19 impacts have implications on the project’s budget for PMC? Yes No. If Yes, please explain: It might, given the need to extend the project duration and revisit project management arrangements. It is hard to tell at the moment and all measures will be taken to minimize the impact. |
| --- | --- |

Project overall risk rating (Low, Medium, Substantial or High)

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current FY risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | In the recent few years Government managed to stabilize the volatility of the Cabinet, which is also reflected in the leadership of the Ministry of Ecology and National Resources. Moreover, in the past few years the role of the State Agency on the Exclusion Zone as the project national authority was clearly defined and strengthened, which distinctly reflected on the overall improvement of the project implementation rate. This being carried through the last four years of the project implementation allows to lower the overall risk level of the project. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : National Project Authority and the Project Management Unit have been demonstrating full ownership of the project. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The lack of a national coordinator is increasing the challenge of coordination between UNEP ROE, SAUEZM, Science coordinator, SC, TC and the stakeholders. |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : PSC and Advisory Expert Group established and meets regularly. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:The SC is operational again and had met in 2020. |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: There is a good flow of information among the PMU and the members of the PSC and Advisory Expert Group. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The lack of a national coordinator is increasing the challenge of coordination between UNEP ROE, SAUEZM, Science coordinator, SC, TC and the stakeholders |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Project Workplan was changed by the PSC to better match the shifting targets of the project, within the overall defined objectives, and better plan project activities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: Disruptions with project financing existing in the previous year have been eliminated. The Government co-financing to the project remains traditionally reliable. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: Minor budgetary reallocations might be needed due to the no-cost extension of the project by 12 months. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  | X |  |  |  |  | PM: Financial reporting, although improved from the previous periods, remains slow and deficient. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  | X |  |  |  |  | PM: Reports are accurate but delays may still occur due to the overall slow turnaround of administrative tasks. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: There is general interest among stakeholders to the project and the objectives it is trying to achieve. Some divergence of opinions about the future use of the Exclusion Zone exists which is mitigated by the Government’s plans to establish a Biosphere Reserve and a comprehensive Management Plan which will improve the stakeholder coordination. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: External communication improved in the project with the project website fully operational and intensified international outreach of the project scientific findings. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: The situation with political stability around the project has significantly improved over the last year although the overall situation in Ukraine remains tense. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: Data collection and synthesis exercise which has been completed significantly reduced the scientific uncertainty. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: The project is reasonably immune to politically motivated decisions however the establishment of the Biosphere Reserve among others depends on the political will of authorities to implement the envisaged plans. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: There is sufficient amount of stability in the MENR and the Exclusion Zone Agency which reflects on the project ownership by the National Project Authority. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  |  | X |  |  |  | PM: The ChEZ by definition continues to be uninhabitable and is prone to forest fires with high radioactivity release risk. |  |  | x |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM: The Government considers various views and proposals regarding the future use of the ChEZ, some of which may impede the realisation of the nature conservation objectives pursued by the project. However, the establishment of the Biosphere Reserve and direct coordination by the Government allow expecting that a balanced approach will be chosen to combine sustainable economic activity with nature conservation and scientific research. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM: After many leadership changes which have negatively affected implementation, the national authorities demonstrate strong ownership of the project and adequate capacity of institutions involved in the project implementation. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:agreed |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| 1 | Project financial reporting and financing needs to be regularized to ensure adequate completion of activities. | Delays in implementation | Set up a rigorous financial recording system and regular reporting to improve the financial flow to the project. | Executing Agency / PM | Continuous |
| 2 | Economic crisis in Ukraine | Inability of the Government to fully fulfil its co-financing commitments | To develop a robust resource mobilization plan and continuously look for additional co-financing | PMU and Executing Agency | Continuous |
| 3 | COVID-19 | Unpredictable impact on the project implementation and completion plans. | Envisage measures for protection of project personnel from unnecessary risk exposure. Introduction of online communication methods to minimize physical contact. | PMU / Executing Agency | Continuous |
|  | Management structure | The lack of a national coordinator is increasing the challenge of coordination between UNEP ROE, SAUEZM, Science coordinator, SC, TC and the stakeholders | TOR for the position will be prepared and vacancy ad will be placed conduct the recruitment exercise. | PMU / Executing Agency | October 2020 |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2020 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.