F

# Section 1. Project Identification

1.1	Project title:				Effective Management of Wadi El-Rayan and

Lake Qarun Protected Areas

1.2	Project number:				GEF ID 9671

PMS: 01475

1.3	Project type: 				MSP

1.4	Trust Fund:				GEFTF

1.5	Strategic objectives:

GEF strategic long-term objective:	BD1

Program 1: Improving Financial Sustainability and Effective Management of the National Ecological Infrastructure

Strategic programme for GEF 6:	Outcome 1.2: Improved management effectiveness of protected areas.

1.6	UN Environment priority: 	Ecosystem management:

EM (a) Use of the ecosystem approach in countries to maintain ecosystem services and sustainable productivity of terrestrial and aquatic systems is increased.

1.7	Geographical scope:			National

1.8	Mode of execution:			NGO Execution

1.9	Project executing organization:	IUCN-ROWA

1.10	Duration of project:			36 months

Commencing:		1 October 2018

Technical completion:	30 September 2021

Validity of legal instrument:		36 months

    - Cost of project

| Cost of project | US$ | % |
| --- | --- | --- |
| Cost to the GEF Trust Fund | 1,319,864 | 13.4 |
| Co-financing |  |  |
| Cash |  |  |
| Egyptian Environmental Affairs Agency (EEAA) | 1,200,000 | 12.2 |
| Sub-total for cash co-financing | 1,200,000 | 12.2 |
| In-kind |  |  |
| Centre for Environment and Development for the Arab Region and Europe – CEDARE | 3,000,000 | 30.6 |
| Italian Development Cooperation | 2,000,000 | 20.4 |
| IUCN-Regional Office for West Asia (IUCN-ROWA) | 300,000 | 3.1 |
| Egyptian Environmental Affairs Agency (EEAA) | 2,000,000 | 20.4 |
| Sub-total in kind co-financing | 7,300,000 | 74.3 |
| Total (cash and in-kind) | 8,500,000 | 86.6 |
| Grand total for GEF and co-financing | 9,819,864 | 100 |

    - Project summary

This project aims to strengthen the overall management of the Wadi El-Rayan and Lake Qarun protected areas to safeguard biodiversity by addressing a range of threats. It seeks to enable community involvement, capacity building and gender equality as the principle means toward improving effectiveness.

Project Objective: To improve the management effectiveness of the Wadi El-Rayan and Lake Qarun protected areas through community involvement and capacity building.

| Component 1 | Strengthen management capacities of targeted PAs for the conservation of threatened and important species and their habitats. |
| --- | --- |
| Outcome 1.1 | Improved management effectiveness (strengthened PA management tools, processes and capacities) demonstrated at two targeted PAs (Wadi El-Rayan and Lake Qarun). |
| Output 1.1.1 | PA management frameworks of Wadi El-Rayan and Lake Qarun PAs developed, including participatory approaches. |
| Output 1.1.2 | Field monitoring programs within Wadi El-Rayan and Lake Qarun PAs to assess the conservation status of key ecosystems and threatened and important species developed and implemented. |
| Component 2 | Establish effective community participation in PA management and conservation / management of natural resources. |
| Outcome 2.1 | Participatory approaches to PA management have strengthened PA management and reduced unsustainable resource uses in areas within and adjacent to two targeted PAs (Wadi El-Rayan and Lake Qarun). |
| Output 2.1.1 | Programmes for community participatory planning and involvement in PA Management developed and implemented at targeted PA sites. |
| Output 2.1.2 | Controls and monitoring programmes to conserve ecosystem services and reduce overharvesting by local communities within Wadi El-Rayan and Lake Qarun PAs developed and implemented. |

# Table of Contents

Section 1. Project Identification	1

Table of Contents	4

List of Figures	6

List of Tables	6

Acronyms and Abbreviations	7

Section 2. Background and Situation Analysis (Baseline course of action)	8

2.1.	Background and context	8

2.1.1 	National context	8

2.1.2 	Description of Wadi El-Rayan Protected Area	10

2.1.3 	Description of Lake Qarun Protected Area	13

2.2.	Global significance	15

2.2.1 	Global significance in a national context	15

2.2.2 	Global significance of Wadi El-Rayan Protected Area	18

2.2.3 	Global significance of Lake Qarun Protected Area	19

2.3.	Threats, root causes and barrier analysis	20

2.3.1 	Threats affecting the two target sites	22

2.3.2 	Barrier analysis	25

2.4.	Institutional, sectoral and policy context	27

2.4.1	Institutional and sectoral context	27

2.4.2 	National legislation and policy context	28

2.5.	Stakeholder mapping and analysis	29

2.5.1	Government institutions	29

2.5.2 	NGOs + Academic Organizations	31

2.5.3 	Community institutions and local enterprises:	32

2.6.	Baseline analysis and gaps	32

2.7.	Linkages with other GEF and non-GEF interventions	34

2.7.1 	Strengthening protected area financing and management systems (SPAFAM)	38

2.7.2 	Egyptian Italian Environmental Cooperation Programme, phase III (EIECP III)	39

Section 3. Intervention Strategy (Alternative)	41

3.1.	Project rationale, policy conformity and expected global environmental benefits	41

3.2.	Project goal and objective	46

3.3.	Project components and expected results	47

Output 1.1.1: PA management frameworks of Wadi El-Rayan and Lake Qarun PAs developed, including participatory approaches.	48

Output 1.1.2: Field monitoring programs within Wadi El-Rayan and Lake Qarun PAs to assess the conservation status of key ecosystems and threatened and important species will be developed and implemented.	51

Output 2.1.1: Programmes for community participatory planning and involvement in PA management developed and implemented at the targeted PA sites.	55

Output 2.1.2: Controls and monitoring programmes to conserve ecosystem services and reduce overharvesting by local communities within Wadi El-Rayan and Lake Qarun PAs developed and implemented.	59

3.4.	Intervention logic and key assumptions	60

3.4.1 	Theory of change	60

3.4.2 	Key assumptions	61

3.4.3 	Gender aspects	64

3.5.	Risk analysis and risk management measures	66

3.6.	Consistency with national priorities or plans	68

3.7.	Incremental cost reasoning	69

3.7.1 	Scenario without GEF involvement	71

3.7.2 	Scenario with GEF involvement	72

3.8.	Sustainability	73

3.9.	Replication	74

3.9.1 	Scaling up	74

3.9.2 	Innovation	75

3.10.	Public awareness, communications and mainstreaming strategy	75

3.11.	Environmental and social safeguards	75

Section 4. Institutional Framework and Implementation Arrangements	76

4.1. 	Implementation and execution	78

4.1.1 	Implementing agency-UN Environment	78

4.1.2 	Executing agency-IUCN ROWA	78

4.2. 	Project management and technical support	79

4.2.1 	Project Management Unit (PMU)	79

4.2.2 	Protected Area Management Unit (PAMU)	80

4.3.	 Project steering committee	80

Section 5. Stakeholder participation	81

Section 6. Monitoring and evaluation Plan	84

Section 7. Project Financing and Budget	86

7.1 	Overall project budget	86

7.2 	Project co-financing	87

7.3 	Project cost-effectiveness	88

References	89

Appendices	92

## List of Figures

Figure 1. Egypt's system of protected areas. Site #12-Lake Qarun Protected Area, #13-Wadi El-Rayan Protected Area (NBSAP, 2016).	10

Figure 2. Wadi El Rayan Protected Area.	12

Figure 3. Lake Qarun Protected Area.	14

Figure 4. Problems, causes and effects (problem tree analysis).	21

Figure 5. Common outcomes of related initiatives.	37

Figure 6. Holistic approach to management (Paleczny, 2007).	47

Figure 7. Theory of change.	63

Figure 8. Project governance.	77

## List of Tables

Table 1. List of species of primary focus of the project.	16

Table 2. Summary of government stakeholders.	30

Table 3. Summary of related initiatives.	35

Table 4. Project contributions to GEF6 objectives and programs.	41

Table 5. CBD strategic goals and Aichi targets and examples of project activities.	42

Table 6. Project risk matrix.	66

Table 7. Incremental cost reasoning.	69

Table 8. Roles and responsibilities in project implementation.	81

Table 9: Summary GEF budget for project implementation by component.	86

Table 10: Summary of GEF budget for project implementation by year.	86

Table 11: Summary of total project co-financing partners and amounts committed.	87

Table 12: Co-financing by source and component in USD.	87

## Acronyms and Abbreviations

| CBNRM | Community-Based Natural Resources Management |
| --- | --- |
| CBO | Community-based organization |
| CEDARE | Centre for Environment and Development for the Arab Region and Europe |
| EEAA | Egyptian Environmental Affairs Agency |
| EIECP | Egyptian Italian Environmental Cooperation Programme |
| GEF | Global Environment Facility |
| GoE | Government of Egypt |
| IUCN | International Union for the Conservation of Nature |
| IUCN ROWA | IUCN Regional Office for West Asia |
| LQPA | Lake Qarun Protected Area |
| M&E | Monitoring & Evaluation |
| MALR | Ministry of Agriculture and Land Reclamation |
| MDG | Millennium Development Goal |
| MEA | Millennium Ecosystem Assessment |
| MoFA | Ministry of Foreign Affairs |
| MOPIC | Ministry of Planning and International Cooperation, Egypt |
| MoT | Ministry of Tourism |
| MSEA | Ministry of State for Environmental Affairs |
| MWRI | Ministry of Water Resources and Irrigation |
| NAP | National Action Program, under the UNCCD |
| NCPSLU | National Centre for Planning State Land Uses |
| NCS | Nature Conservation Sector |
| NGOs | Non-Government Organizations |
| NWRC | National Water Research Centre |
| PA | Protected Area |
| PAMU | Protected Area Management Unit |
| PMU | Project Management Unit |
| PSC | Project Steering Committee |
| PPG | Project Preparation Grant |
| ProDoc | Project Document |
| RAMSAR | Convention on Wetlands of International Importance |
| SDGs | Sustainable Development Goals |
| CBD | Convention for Biodiversity |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UN Environment | United Nations Environment Program |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| WHS | World Heritage Site |
| WRPA | Wadi El-Rayan Protected Area |

# Section 2. Background and Situation Analysis (Baseline course of action)

## Background and context

2.1.1 	National context

Despite being consistently arid or semi-arid, Egypt’s varied eco-zones are home to an extensive diversity of terrestrial habitats, fauna, flora and microorganisms, and although the country has comparatively low species numbers and few endemics, its biodiversity is exceptionally diverse in composition and has high global significance. Egypt’s high biodiversity is due partly to its location at the juncture of four bio-geographical regions, namely the Irano-Turanian, Mediterranean, Saharo-Sindian and Afrotropical regions, and to its diversity of landscapes and topographic features, ranging from the rugged mountains of South Sinai and the Eastern Desert (up to 2,641 m) to the Qattara Depression (134 m below mean sea level), to flat featureless gravel plains and complex hilly country. The Nile River and the 2,450 km of coastline on the Red Sea and the Mediterranean (two seas with very different marine ecosystems) also contribute greatly to the diversity of Egypt’s habitat types and the communities inhabiting them. Existing data indicates that Egypt is home to approximately 22,000 species, including over 2,145 species and 220 infra-specific taxa of native and naturalized vascular plants, 175 species and subspecies of mosses, 13 hepatics, 111 mammals (40 threatened with extinction), 480 birds (26 threatened with extinction), 109 reptiles (27 threatened with extinction), 9 amphibians, more than 1,000 fish species, 800 Mollusca, 1,000 Crustacean, more than 225 species of coral reefs, 10,000 – 15,000 species of insects (including 63 butterflies), 2,420 species of fungi, and thousands of algae, bacteria and viruses. A significant part of these species is found in nationally designated protected areas. Egypt hosts a sizeable and growing number of species recognized by the International Union for the Conservation of Nature (IUCN) as needing conservation management. At least 345 species of threatened animals are to be found in the country, including the globally Vulnerable Barbary Sheep (Ammotragus lervia), Nubian Ibex (Capra nubiana), Four-toed Jerboa (Allactaga tetradactyla), Lappet-faced Vulture (Torgos tracheliotos), Marbled Polecat (Vormela peregusna); the Endangered Slender-horned Gazelle (Gazella leptoceros), Egyptian Vulture (Neophron percnopterus), Green Turtle (Chelonia mydas); and the Critically Endangered Hawksbill Turtle (Eretmochelys imbricate), African Wild Ass (Equus africanus), and Egyptian Tortoise (Testudo kleinmanni). Threatened plants include the Endangered Gebel Elba Dragon Tree (Dracaena ombet) and the Critically Endangered Argun Palm (Medemia argun), found in desert mountains and in desert oases respectively.

A number of laws in Egypt provide the enabling environment that supports biodiversity management in the country. Law 102/1983 provides the legislative framework for establishing and managing protected areas in Egypt. The sole category referred to in this law is the natural protectorate, which is defined as “any area of land or coastal or inland water characterized by flora, fauna and natural features having cultural, scientific, tourist or aesthetic value.” These are designated by Prime Minister’s Decrees upon recommendations of the Egyptian Environmental Affairs Agency (EEAA), which proposes boundary maps and is entrusted with the management and supervision of such protected areas. According to Law 102/1983, it is forbidden to undertake actions, activities or procedures, which would destroy, damage or degrade the natural environment, or harm terrestrial, marine or plant life, or detract from its aesthetic quality in a protected area. Law 4/1994 for the Environment (amended by Law 9/2009) contains additional provisions for inside and outside protected areas. The law assigns a major role to EEAA in the management and monitoring of protected areas, including the management of the licensing and permit system for any activity undertaken in protected areas requiring EIAs. All activities carried out in protected areas are to be subjected to the EEAA’s control, which can take steps to enforce the rules and stop any illegal activity.

Nationally, coverage of the protected area network has grown over the last three decades to include 30 protected areas covering 14,680 km2 or approximately 14.6% of the country’s terrestrial environment, as well as 1.7% of the country’s marine environment (figure 1).  Despite the progress achieved to date, coverage does not yet meet the CBD 2020 Aichi Target 11 to protect at least 17% of terrestrial and inland water areas and 10% of coastal and marine areas. However, coverage of some important and threatened habitats is still incomplete or severely limited. If the Egyptian National Biodiversity Strategy and Action Plan (NBSAP) is fully implemented, there should be good representation of the major habitats known from the country, however some of the sites that were selected in the late 1990s (particularly along the Mediterranean coast) might have become already altered or degraded beyond repair and alternative sites might need to be identified or site boundaries need to be revised. There 34 Important Bird Areas (IBAs) in Egypt covering an area of 35,000 km2 or some 3.5% of Egypt's territory, and comprising a wide range of habitats critical for birds, such as wetlands, high altitude mountains, desert wadis, coastal plains and marine islands. Fifteen IBAs are within the existing protected area network, including within each of the two protected areas targeted by this project. Four of the 34 IBAs in Egypt are also designated RAMSAR sites, while eight IBAs have the potential to qualify for designation based on the water bird populations they host. The project will work in two PAs, Wadi El Rayan and Lake Qaron as described in sections 2.1.2 and 2.1.3 respectively.

These two protected areas are located within the Fayoum Governorate (province), within two-three hours’ drive from Cairo and its 18.5 million people (ARE, 2018).  Fayoum has 3.7 million people and is one of the poorest of Egypt’s provinces (WFP, 2013).

Figure 1. Egypt's system of protected areas. Site #12-Lake Qarun Protected Area, #13-Wadi El-Rayan Protected Area (NBSAP, 2016).

2.1.2 	Description of Wadi El-Rayan Protected Area

Wadi El Rayan Protected Area (WRPA) was declared in 1989.  Located in the south-western part of the Fayoum depression, WRPA encompasses 175,901 ha, including 11,434 ha of lakes, 1,583 ha of wetlands, 160,949 ha of desert, and the Al-Oyoun oasis that covers 1,935 ha.  WRPA is classified IUCN category II and VI and has been designated as a Ramsar site, Important Bird Area and Key Biodiversity Area.  In 2005, the Wadi El-Hitan (the Valley of the Whales) area (20,105 ha) located within WRPA was designated by UNESCO as the first natural World Heritage Site in Egypt; the valley contains 40-million year old whale fossils and is considered the most significant site in the world to demonstrate the evolution of whales from land-based to ocean-going animals.

WRPA is comprised of two man-made wetlands formed by the flooding of a desert depression.  WRPA’s diverse natural landscapes, including the only waterfalls in all of Egypt as well as various oases, sandy beaches, rock formations, and other areas of natural beauty, are a popular attraction for national and international visitors for sightseeing, camping, and bird watching, with over 150,000 visitors coming to WRPA annually and another 20,000 visitors to Wadi El-Hitan World Heritage Site annually.  The area also has historical significance as a major crossroad that was used for many centuries by travelers between the Nile Valley and the oases of the Western Desert, and the remains of human settlements from the Egyptian and Roman-Greek eras are found in the area.

WRPA contains a sandy depression that supports three natural springs and extensive desert scrub vegetation (the Al-Oyoun oasis); a limestone escarpment surrounds this depression on all sides except the east, where it is closed off by a series of high longitudinal dunes. The vegetation is dominated by shrubs of Alhagi, Nitraria, Calligonum and Tamarix. This part of WRPA is an excellent and rare example of an undeveloped Saharan oasis.

In 1973, excess agricultural drainage water began to be channelled into the area in order to slow-down the rise of the water tables in the Fayoum main depression and Qarun Lake, and as a result, two lakes were formed in the lower portion of the Wadi El Rayan depression.  These lakes, which cover an area of about 4,800 ha and 4,590 ha, are high in salinity but support fish stocks and significant shoreline vegetation.

The natural resources and ecosystem services of WRPA support the livelihood activities of many local communities, such as fish farming, fishing in the Rayan Lakes, agriculture in the land reclamation area, and tourism. Fishing and agriculture are the major sources of livelihood for local residents, and the annual fish catch has been increasing markedly.

- An estimated 1,724 persons fish from boats in the upper and lower Rayan lakes, while another 253 fish from the shore.

- About 129 individuals work in fish farming in an area of about 550 ha (1,300 feddans); this area includes more than 90 intensive (cement) fish ponds, 30 extensive (sludge) fish ponds, 3 cage culture operations.

- Approximately 12,240 individuals are employed in agricultural production in an area of around 1,900 ha (4,575 feddans), producing olives, guava, grapes, palm dates and various vegetables on a small scale. In recent years, unapproved expansions of agricultural plots have occurred in the PA.

- The PA includes an operating oil field comprised of five operating wells. The Qarun Oil Company (affiliated with the American Apache Company) began production in 1997, following a full environmental assessment. Monitoring and waste removal protocols are in place to reduce the risk of accidental oil leaks. About 25 people are employed in this sector. PA staff meet with the company up to four times per year.

- Small scale salt mining employs about 50 individuals.

- About two dozen people are employed in tourism (cafeterias, private tour boat owners).

- Three land reclamation villages exist within the PA (two on the lower lake and one on the north boundary). The proximity of villages located around the periphery of the PA has resulted in frequent unapproved intrusions (e.g., building, cattle grazing, dumping, etc.)

- There is a population of about 30 monks in a Coptic monastery located in the core zone of the protected area adjacent to the Al-Oyoun oasis. Since 2013, the monks have occupied this oasis and it is believed that the resident population of Dorcas Gazelle no longer inhabits this area.

The designation of the Wadi El-Hitan as a World Heritage Site in 2005 means that WRPA has received increased financing from the Government of Egypt for conservation-related activities. The Government of Egypt’s budget for WRPA in 2015 was $15 per km2, giving it the 10th highest funding level among the 30 PAs in Egypt. Since 1998 to the present, WRPA has been supported through three phases of the Italian-funded programme to increase management capacity and develop ecotourism and educational resources, with total financial inputs of approximately US$6.5 million. As a result of these and other investments, WRPA has previously had a comprehensive management plan and an operating plan (both are now out of date), monitoring and patrolling programmes, staff training in PA management functions, and a sizeable staff by Egyptian standards (previously exceeded 45). Despite these advances, the discontinuous nature of project funding coupled with increasing growth and pressure (noted above), has resulted in the need for greater inputs in terms of staff monitoring and patrols, liaison, awareness and routine management.

Figure 2. Wadi El Rayan Protected Area.

PA Boundary

2.1.3 	Description of Lake Qarun Protected Area

Lake Qarun Protected Area (LQPA) (134,042 ha) occupies the lowest part of the Fayum Depression, at 43m below sea level, and consists of the lake itself (23,000 ha) and surrounding landscapes (111,000 ha).

The PA is classified IUCN category Ia and has been designated as a Ramsar site and Important Bird Area owing to its wetland feature in the desert and use by wintering waterbirds. Lake Qarun, the third largest lake in the country and the only existing natural lake of any size in Middle Egypt, is slightly more saline than saltwater. During Pharonic times it was fed by a channel branching from the Nile River but now receives agricultural drainage water through a number of canals and drains.

A small island, Gezert El Qarn El Zahbi (Qarn Island), located in the middle of Lake Qarun and covering an area of about 1.5 km2, is an important site for nesting birds. The surrounding desert contains spectacular geologic formations, globally significant fossil deposits, and cultural heritage sites that include Neolithic sites and Roman cities and temples.  Lake Qarun was declared as a protected area in order to conserve the biological, archaeological and geological diversity of the area.

The rich, highly diversified, and well-preserved palaeoflora and paleofauna make Lake Qarun PA one of the most important fossiliferous areas in the world and highly important for scientific research into the history of life on earth.  The Gebal Qatrani area within the PA provides by far the most complete view of endemic African fauna before the significant faunal interchanges of the Miocene resulted in a major influx of other groups.  The most significant fossil group of Qatrani is the mammals, which is unlike any other known mammalian fauna, living or extinct. The mammal community consisted of a mixture of endemic groups that have now become extinct or greatly reduced in diversity, plus some important immigrant groups from Eurasia. Of the 28 orders of placental mammals known to exist today globally, 12 are found in Gebel Qatrani. As with the mammals, the reptile fossils in the PA also include many taxa unknown in Africa today. The Gebal Qatrani area is also rich in fossil plants, including angiosperms, pteridophytes and algae, over 40 species of monocots, dicots and pteridophytes, and over 160 species of algae. This area is currently being nominated for world heritage status. In February of 2018, the Nature Conservation Sector launched an open air museum as a means to establish a management presence at the site and provide interpretation and tourism opportunities.

The southern shore of Lake Qarun is heavily used for traditional agriculture and more recently for fish farming; it is also the site of several tourist resorts.  Around 20,000 people live within or adjacent to the PA, the majority of whom are engaged in agricultural production, including fruit trees, olives, maize, wheat, onions, tomatoes, etc. Several commercial fisheries exist in Lake Qarun, including Egyptian sole (Solea aegyptiaca), Redbelly tilapia (Tilapia zillii), six species of mullet, and three species of shrimp. The overall catch increased from 703 tons in 1995 to 3400 tons in 2009, employing approximately 4,000 fishermen. Numerous earth fish ponds operate on the southern shore. During the 1970s, the government began to explore options for salt extraction that could reduce the salinity levels in Lake Qarun while also providing economic benefits to the area.

In 1984, the Egyptian Salts and Minerals Company (EMISAL) constructed four ponds and a plant on the southern shore of the lake to extract salts from the lake water, with a designed capacity of 100,000 tons per year of high quality anhydrous sodium sulfate. Due to domestic and industrial pollution and irrigation water entering the canals, Lake Qarun has very high levels of salt (35 g/l) and heavy metals, thus compromising the environmental quality of the lake (refer to further discussion in section 2.3, threats). The company has plans to establish a second salt extraction facility on the north-east shore of the lake to increase salt extraction (Dr Gamal Samy Aly, Governor, pers com) with the aim of lowering the concentration of salt in the lake.

The lake is easily accessed from Cairo along several well-paved highways. Various forms of tourism exist in the PA, including ecotourism, desert safaris, adventure tourism, cultural tourism, bird watching, water sports, fishing, bicycling and walking trips, horse and donkey rides, guided tours to the famous fossil and antiquities areas, camping in the desert and working with local craftsmen. Hotels and holiday resorts are found along the southern shore of Lake Qarun, and tourism services such as restaurants, cafeterias and hotels provide employment opportunities for many residents of the area. The northern shore of Lake Qarun has been recently designated as an “ecotourism development area”.

In addition, Lake Qarun contains Gebel Qatrani, which is on the World Heritage tentative list. This area has become a popular destination for visitors from Cairo, which means that it is more likely to be able to generate funds (a visitor fee system will be established for Lake Qarun PA, based on modalities already applied in WRPA) and to receive financing from the Government of Egypt for conservation-related activities.

Figure 3. Lake Qarun Protected Area.

The PA infrastructure is limited to a headquarters/administrative office building located in the village of Shakshouk and a mix of paved and unpaved roads. A new open air museum opened in February 2018, including areas with fossils on display and interpretive signs. Although Lake Qarun PA has put significant emphasis and resources on field monitoring and patrolling, the PA’s current resources remain insufficient to address key threats that include visitor damage, illegal hunting and illegal / improper fossil collection, mining activities and tourism development. These activities continue to threaten the natural and cultural attractions of the PA. However, targeted support for improved PA management, monitoring and patrolling at this site has the strong potential to protect its natural and cultural attractions and thereby enable the PA to sustain appreciation and use of the area by visitors that can provide substantial benefits, including increased public support and direct and indirect economic benefits for conservation and local communities.

## Global significance

2.2.1 	Global significance in a national context

Egypt’s varied eco-zones are home to an extensive diversity of terrestrial habitats, fauna, flora and microorganisms despite being consistently arid or semi-arid. Although the country has comparatively low species numbers and few endemics, its biodiversity is exceptionally diverse in composition and has high global significance. Egypt’s high biodiversity is due partly to its location at the juncture of four bio-geographical regions, namely the Irano-Turanian, Mediterranean, Saharo-Sindian and Afrotropical regions, and to its diversity of landscapes and topographic features, ranging from the rugged mountains of South Sinai and the Eastern Desert (up to 2,641 m) to the Qattara Depression (134 m below mean sea level), to flat featureless gravel plains and complex hilly country.

Six antelope species used to inhabit the Egyptian desert; of these, four were extinct by the end of the last century (Saleh 1987, El Alqamy and El Din 2006), and of the two remaining species, the Dorcas gazelle (Gazella dorcas) is threatened and the Slender-horned Gazelle (Gazella leptoceros) is at the brink of extinction (Saleh 1987, Ryder 1987, Alqamy and Din 2006, Bahaa-el-din 2007).  The Dorcas gazelle is the smallest member of the genus Gazella and is an extreme habitat generalist (ALGADAFI et al. 2017) represented in Egypt by two distinct subspecies, G. d. dorcas and G. d. isabella (=littoralis). The latter sub-species occupies the Eastern desert and Sinai region (Osborn and Helmy 1980, El Alqamy and El Din 2006), while the former sub-species is found in the Western desert. The Slender-horned gazelle is represented in Egypt by one subspecies G. leptoceros leptoceros endemic to Egypt (Osborn and Helmy 1980, Alqamy and Din 2006, Bahaa-el-din 2007), and distributed in the Western desert.

The presence of Dorcas gazelle (Gazella dorcas) and Slender-horned Gazelle (Gazella leptoceros) in the Western desert is believed to contribute to the maintenance of ecological systems. Unlike most other herbivorous species, gazelle are browsers not grazers; this allows the vegetation cover of desert ecosystems to survive and persist and also provide a means for the dispersal of plant seeds (Osborn and Helmy 1980, Alqamy 2002, Alqamy and Din 2006). Gazelle also are the main prey for the Cheetah (Acinonyx jubatus), which in other parts of Africa showed declines as a consequence of the gazelle’s decline (Durant et al. 2017).

Egypt has 381 species of birds, of which 14 (4%) are globally threatened (i.e., vulnerable, endangered) (Birdlife International, 2018). WRPA has 170 species of birds (WRPA, 2007) of which six are globally threatened (Birdlife International, 2018).

The species of concern in the project are listed in the table below. However, a common challenge is the lack of data about species presence and abundance in the two protected areas.

Table 1. List of species of primary focus of the project.

| Class | Common name | Scientific name | IUCN red list category | Protected area |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | WRPA | LQPA |
| Mammals | Four-toed Jerboa | Allactaga tetradactyla | Data deficient (anticipated endangered) | X |  |
|  | Dorcas Gazelle | Gazella dorcas | Vulnerable | X | PR |
|  | Slender-horned Gazelle | Gazella leptoceros | Endangered | PR | PR |
|  | Striped Hyena | Hyaena hyaena | Near threatened | PR | PR |
|  | Fennec Fox | Vulpes zerda | Least concern | X | X |
|  | Ruppell’s Sand Fox | Vulpes rueppelli | Least concern | X | X |
|  | Flower's Shrew | Crocidura floweri | Data deficient | X |  |
| Birds | Ferruginous Duck (diving duck) | Aythya nyroca | Near Threatened | X |  |
|  | Pallid Harrier | Circus macrourus | Near threatened | X |  |
|  | Common Pochard | Aythya farina | Vulnerable | X |  |
|  | Black-tailed Godwit | Limosa limosa | Near threatened | X |  |
|  | Sooty Falcon | Falco concolor | Vulnerable | X |  |
|  | Meadow Pipit | Anthus pratensis | Near threatened | X |  |

X-recorded occurrence, expected; (PR)-previously recorded and may occur but not substantiated in recent times

The Ferruginous Duck (Aythya nyroca) is classified as Near Threatened (NT) on the IUCN Red List. It is also listed on Appendices I and II of the Convention on Migratory Species (CMS or Bonn Convention), Appendix III of the Bern Convention on the Conservation of European Wildlife and Natural Habitats, Annex I of the EC Birds Directive, and Annex 2 of the African-Eurasian Migratory Waterbird Agreement.

Purple Gallinule (Porphyrio porphyrio) in the Mediterranean has declined due to habitat loss, hunting and pesticide use, and while ranked as ‘least concern’ requires strict protection.

2.2.2 	Global significance of Wadi El-Rayan Protected Area

WRPA is an Important Bird Area and a designated Ramsar wetland of international importance; it includes globally significant biodiversity.  In addition, the PA fossils are of immense scientific importance and as a result the site has been inscribed on the World Heritage list (see section 2.1.2).

The lakes and natural oases (springs) play a critical role in the life cycles of a significant diversity of species, including 29 fish species, 170 bird species, 24 mammal species, 14 reptile species and 38 plant species.

Birds are the most visible wildlife in the protected area and can be seen in the lakes, desert, oases and farmlands. Bird watching is possible throughout the year, but the greatest numbers and diversity of birds occur in winter when the lakes are teeming with migrant water birds.  The lakes of Wadi El Rayan are important wintering grounds for water birds, and the area provides a resting-place for migratory bird species including migratory Lanner and Peregrine falcons and is a significant breeding ground for water birds.  Overall, about 170 species of birds have been identified (WRPA, 2007) including ducks, eagles, falcons, swans, herons, storks, and many birds of prey.

The PA includes important habitat for the Ferruginous Duck (Aythya nyroca) and Pallid Harrier (Circus macrourus), both of which are “Near Threatened”. In addition, they have been colonized by some resident species, such as purple gallinule (Porphyrio porphyrio). WRPA provides habitat for a number of Sahara–Sindian biome restricted species, of which at least four are known or are expected to breed in the area: Sooty Falcon (Falco concolor), Pharaoh Eagle-Owl (Bubo ascalaphus), Mourning Wheatear (Oenanthe lugens), and Greater Hoopoe-Lark (Alaemon alaudipes).

A total of 29 fish species have been recorded in the Wadi El Rayan lakes. Tilapias are represented by four major species -- Tilapia zillii, Oreochromis aureus, Oreochromis niloticus and Sarothrodon galailus; and mullet fish by six species -- Mugil cephalus, Liza ramada, Liza sliens, Liza aurata, Chelon labrousus and Liza craniate.  Other species, such as Nile Perch (Latus niloticus), Grass-carp, Silver-carp, Seabass, Claris, Bagrus spp. and other species, are present in smaller numbers.

Several threatened mammals resident in WRPA are noteworthy. Of particular importance is the population of the Dorcas gazelle (Gazella dorcas) in WRPA (threats are described in section 2.3), which has been assessed as vulnerable (IUCN Red List, 2018; SSC Antelope Specialist Group, 2017).  The presence of this species is believed to contribute to the maintenance of ecological systems; unlike most other herbivorous species, gazelles are known to be browsers not grazers, which allows the vegetation cover of desert ecosystems to survive and persist and also provides a means for the dispersal of plant seeds (Osborn and Helmy 1980, Alqamy 2002, Alqamy and Din 2006). The Fennec Fox (Vulpes zerda, LC), Ruppell’s Sand Fox Vulpes rueppelli (DD) and the Four-Toed Jerboa (Allactaga tetradactyla, DD) are scarce due to illegal hunting. The Flower’s shrew (Crocidura floweri, DD), an endemic species to Egypt, occurs in WRPA.

2.2.3 	Global significance of Lake Qarun Protected Area

LQPA is an Important Bird Area and a designated Ramsar wetland of international importance; it includes globally significant biodiversity. In addition, the PA fossils are of immense scientific importance and as a result has been nominated for World Heritage Site designation (see section 2.1.3).

Lake Qarun includes notable biological diversity, including about 80 species of birds representing ducks, eagles, falcons, hornbills, macaws, swans and parakeets (documentation is poor and it is likely that many more species, similar to WRPA exist in Qarun PA). Lakeshore vegetation and swampy margins along the southern shoreline of the Lake are probably the most valuable habitats in the PA and the most threatened due to intensive human impacts. Mudflats and very shallow waters are particularly important for wintering waders and flamingos (Phaenicopterus ruber). The agricultural landscape along the southern shores of Lake Qarun, although largely man-made, does support considerable biodiversity, including many microhabitats that represent relicts of the original wet savannah-like habitat that once existed in the region and even today support many wetland and grassland species.

Lake Qarun is considered to be a globally important bird area (IBA) on account of its importance for wintering and breeding water birds. In the winter, Lake Qarun holds large numbers of waterfowl; Great Crested and Black-necked Grebes (Podiceps cristatus and P. nigricollis, respectively) are particularly abundant.  According to BirdLife International (2011), the site is known to hold more than 1% (1,000 breeding pairs) of the biogeographic population in Europe / North Africa of the Slender-billed Gull (Larus genei, LC), and just above 1% of the Egyptian Eared Grebe (Podiceps nigricollis, LC).  Other important waterbirds include Shoveler (Anas clypeata, LC), Little Tern (Sterna albiforns, LC), Eurasian Teal (Anas crecca), Tufted Duck (Aythya fuligula) and Eurasian Coot (Fulica atra).  At least ten species of waterbirds are known to breed in the area, the most prominent of which are Cattle Egret (Bubulcus ibis), Spur-winged Lapwing (Vanellus spinosus), Kentish Plover (Charadrius alexandrines), Little Tern (Sterna albifrons) and Slender-billed Gull (Larus genei).  Species inhabiting agricultural landscapes on the southern shores of Lake Qarun include the Little Green Bee Eater (Merops orientalis, LC), Common Bulbul (Pycnonotus barbatus, LC), Crested Lark (Galerida cristata, LC), Senegal Thick-knee (Burhinus senegalensis, LC) and Senegal Coucal (Centropus senegalensis). Desert and semi desert habitats support fewer species but include the Hoopoe Lark (Alaemon alaudipes, LC), Brown-necked Raven (Corvus ruficollis, LC) and small numbers of Egyptian Nightjar (Caprimulgus aegyptius, LC).

Several land mammals found in the PA are now very rare, including the Dorcas gazelle (Gazella dorcas, VU), the Ruppell’s Sand fox (Vulpes rueppelli, LC), and the Fennec fox (Vulpes zerda, LC).  The PA harbours rare reptiles including the Egyptian Cobra, red-spotted and coral snake, as well as 15 species of fish.  The Fayoum Depression harbours several relict species not documented elsewhere in Egypt, such as the Egg-eating Snake (Dasypeltis scabra) and the Cape Wolf Snake (Lycophidion capanse); and the occurrence of an endemic bird (Sylvia melanocephala norrisae), a subspecies of Sardinian Warbler. These cases indicate a special biogeographical history of the Fayoum Depression and attest to its relative isolation for extended periods of time.

## Threats, root causes and barrier analysis

Threat analyses were carried out for the two protected areas by IUCN as part of the Egyptian-Italian Environmental Cooperation Programme (EIECP) phase 2 (Paleczny, Allam and Talaat, 2007 a+b). An assessment of threats on vegetation was conducted by Afefe et al., 2016. Community situational analyses were conducted by the EIECP phase 3 team for both protected areas in November 2016 as part of their work to advance Community-based Natural Resources Management (CBNRM). These studies were reviewed and threats were discussed with stakeholders during the mission to prepare this project document.

Overall, the number of high to very high inter-linked threats indicates an area under significant pressure. While many tactical activities have been undertaken to study or manage various components, the area lacks a cohesive ecosystem-based strategy to reconcile natural values, ecosystem services, and increasing threats including growing competing uses. Under such intense pressure, the potential benefits derived from a clean, healthy natural environment cannot be realized.

Figure 4. Problems, causes and effects (problem tree analysis).

2.3.1 	Threats affecting the two target sites

Illegal hunting / poaching is a significant threat to biodiversity in both PAs. The El Fayoum region has traditionally been a popular site for European hunting parties visiting Egypt in winter and although there have been recent attempts to control and regulate hunting, evidence indicates that there are many violations, both by foreign hunting parties and by locals who kill many protected species and cause much disturbance to both wintering and breeding birds. Fauna are used for commercial, semi-commercial and subsistence purposes through both formal and informal markets, including mammals for wild meat and recreational hunting, birds for food and the pet trade, and amphibians for traditional medicine and food. In WRPA, illegal hunting and especially falcon-catching are very evident, and the recently established tarmac road encircling the two lakes has made the area more accessible, drastically increasing the opportunities for illegal hunting and habitat destruction. Refer to habitat conversion threats affecting gazelle.

Unsustainable use of natural resources occurs in or around the two PAs. Fishermen use inappropriate techniques to increase their catch, resulting in the killing of under-sized fish and in the deaths of large numbers of non-target species. Unlicensed grazing occurs in both PAs with unknown impacts on shoreline vegetation, habitat and water quality. In WRPA, tourism visitation has caused significant disturbance to wildlife in some areas, notably the oases, as well as damage to cultural and historical sites.  In addition, the unauthorized collection of fossil specimens at the world heritage site reduces the scientific and cultural value of the area.

Development and habitat conversion pose threats to gazelle (described above), as well as fisheries and bird habitat along shorelines and critical gazelle habitat. For example, tourism development is destroying important habitat for waterbirds, particularly mudflats and saltmarshes, and will lead to increased disturbance to birds.  In 2011, plans were announced to build a 263 ha tourism development on the northern shore of Lake Qarun, which has the potential to negatively impact birds and their habitats in Lake Qarun protected area. The opening of a new asphalt road running north of the lake and linking it to the Cairo-Fayoum highway is expected to increase traffic and further boost tourism development in the area. The government is also considering a land-reclamation project that would increase the area under cultivation within WRPA by 6,300 ha (15,000 feddan), and a new salt extraction plant was recently approved along the northeastern coast of Lake Qarun. Oil production poses additional threats; the Qarun Petroleum Company is now operating close to Lake Qarun PA, while the Edison International Company has received permission to explore for oil in an area to the north of WRPA. The spread of fish farms along the southern shoreline of Lake Qarun is destroying natural habitat and causing increased disturbance to wintering waterbirds. Finally, although efforts have been made to stop basalt extraction in Lake Qarun PA, active quarries are still present within the PA boundaries and threaten some of the most valuable natural and cultural heritage sites in the PA.

Impacts to habitat (as well as illegal hunting) have greatly reduced the populations of the Dorcas gazelle (Gazella dorcas) and the Slender-horned gazelle (Gazella leptoceros) in Egypt in the northern region of the western desert (Ryder 1987, Saleh 2001, El Alqamy and El Din 2006), including the two PAs targeted by this project. The population in WRPA in the late 1990’s was estimated to be between 6 and 14 animals. By 2008, three Dorcas gazelle were confirmed through a systematic survey within and nearby WRPA, indicating the minimum population size (Attum, 20018). No Slender-horned gazelle were found in or nearby WRPA during that same survey.  By 2012, a further decline in the population of the gazelles is believed to have occurred, and today, it is not known if any Dorcas gazelle currently inhabit the Springs oasis. This is concerning as the Springs oasis was key habitat, linked to outlying vegetation patches that were used by Dorcas gazelle—consequently, loss of the Springs oasis population would indicate the loss of the remaining Dorcas gazelle population in north-eastern Egypt (Attum, 2008). Despite this, previous studies have demonstrated that gazelle are able to proliferate even in the presence of human activities if effective hunting controls are in place (Yom-Tov and Ilani 1987, Ryder 1987). Accordingly, it is hoped that the Dorcas gazelle could still be conserved in their desert habitats. Overall, it is believed that a number of threats have negatively impacted upon gazelle in and around WRPA, including:

- Illegal hunting supported by relative easy road access to the habitat.

- Illegal drilling of water wells without a permit.

- Enlarged land reclamation area nearby, which includes a significant number of feral dogs roaming in the area; and

- Habitat destruction, particularly during the 2011 uprising in Egypt that resulted in extensive habitat alteration and destruction, especially in Wadi Al-Rayan with the monks assuming control of the Springs oasis. Conversion of the Springs for agricultural use and construction of a wall around the springs has negatively impacted upon the gazelle.

There is a lack of current information about gazelle is a key limitation in achieving management effectiveness (see section 2.3.2).

Declining water quantity and quality threaten natural values and human use and safety. The crux of the problem is that all water entering the PA lakes comes initially from the Nile River after passing through the drainage basin and used for agricultural irrigation. Three key issues are at play, creating a synergistic problem:

- Lower lake levels are the result of reduced rate of water inflow to Lake Qarun and the Rayan Lakes through the canals and drains. A higher priority has been placed on the use of water for agriculture.

Water entering the Wadi El-Rayan lake system is less than the total rate of water use and evaporation, and this places the future of the lake system in jeopardy. The declining water levels and water quality are also a threat to the economic values (fishing, agriculture, tourism) supporting local communities within and outside of WRPA.

- Soils in the basin are naturally saline.

The extensive irrigation and runoff results in drainage water that is very high in salinity. With the intensification of cultivation and irrigation since the early part of this century, salinity levels at Lake Qarun increased from 30.9% in 1971 to 42.8% in 1999–2000 (Mashal, 1973; Anonymous, 1997; Ali, 2003). At both PAs, this increase of salinity presents a serious threat to biodiversity and populations of plankton, fish and birds; swamp and marsh vegetation is now restricted to the vicinity of drain outlets, on the eastern and southern shores of the lake, and Nilotic aquatic fauna has mostly disappeared, being replaced by many marine species that have been introduced from the Mediterranean to restock the ecologically modified lake. In the second lake of WRPA, salinity levels increased from 2.4% in 1984-1985 to 14.3% in 2010, which threatens biodiversity and fish stocks and is likely to diminish the area’s ability to support populations of waterbirds. As noted in section 2.1.3, the Egyptian Salts and Minerals Company (EMISAL) extracts salt from Lake Qarun to reduce the lake’s salinity.

- The canals and drains that carry the agricultural drainage also carry wastewater drainage from domestic and industrial sources.

Although Lake Qarun was designated as a protected area in 1989, the lake continues to suffer from a serious water pollution problem due to uncontrolled solid and liquid domestic and industrial waste disposal practices, in addition to agrochemical contamination and lack of sustainable wastewater management.  Wastewater flows from fish farms directly into the lake and increases organic matter and nutrient levels, and communities adjacent to the lake have inadequate sewage disposal systems, which along with untreated agricultural runoff, is causing pollution in the protected area. As a result, Lake Qarun has elevated concentrations of phosphorous and nitrogen that have produced algal blooms, and high levels of Total Organic Carbon (TOC) in sediment that have led to decreased benthic abundance and biomass, in addition to oxygen depletion and accumulation of potentially toxic reduced chemicals that affect the animal and plant life in the lake. Furthermore, the presence of high trace metals levels in water and sediment has led to the accumulation of metal in fish stocks.  In WRPA, the growth of cage and pond fish farming on the shorelines of the lakes is causing similar water pollution problems. In terrestrial ecosystems, increased development, the encroachment of human presence in areas surrounding the PAs, and the projected increase in tourism activities are likely to lead to increased solid waste problems if adequate procedures for waste disposal are not put into place.

The issue of domestic and industrial water pollution is beyond the scope of this project proposal. A significant European Union project in the order of $450 million Euros has recently been approved to construct water treatment plants that will address pollution issues for 81 communities. However, this UN Environment-GEF project will seek to improve water quantity and quality issues related to conservation of biodiversity and resource users (e.g., fish farms).

2.3.2 	Barrier analysis

The long-term solution to the threats described above is to improve the management effectiveness of protected areas through community involvement and capacity building of both PA management authorities and local communities. However, several barriers exist to implementing this approach to protected area management, as further described below for the two components of this project:

- Lack of sufficient management capacities in targeted PAs to conserve threatened and important species and their habitats.

- The two targeted protected areas are not managed based on planning tools. A management plan for Lake Qarun was drafted in 2008 but never approved, and the WRPA management plan is now outdated. In 2007, management effectiveness evaluations were conducted, which were beneficial in informing priority actions. However, with the passage of time and key historical events that have impacted on management capacity (i.e., the revolutions), these key tools need to be developed with the involvement of local communities.  There is a need to clearly define a long-range vision and clear objectives, in order to recognize and balance resource use and development with conservation of critical habitat and species.

- A lack of institutional coordination is a key barrier. The plans and activities of a variety of agencies and authorities that operate inside these two PAs need to be coordinated, including the Ministry of Agriculture and Land Reclamation, Ministry of Petroleum, Ministry of Oceans/Fisheries, Ministry of Irrigation, Ministry of Tourism, Ministry of Defence, Ministry of Interior, as well as tourism and environmental police. In addition, the mandate and operational rules of the protected areas constrain them from addressing broader needs associated with threatened and important species conservation, for example addressing pressures that come from beyond the boundaries of the PA sites and involve a wider range of management of natural resources.

- PA staff do not have sufficient capacities to implement control and enforcement measures for the increasing number of visitors at both sites, or to plan for, monitor and mitigate the potential negative impacts of tourism, agriculture, fishing and other economic activities at the sites. Both WRPA and LQPA also have inadequate infrastructure to manage visitors (signage, demarcation, visitor/interpretation facilities) or to deal with their potential impacts (i.e. ranger outposts, restroom and waste facilities, etc.).

- A lack of information about the habitat and populations of key species, such as the gazelle, prevents PA managers from establishing suitable management targets. There is a need to develop standardized criteria for monitoring system across the PA estate, in order for management to extract information for decision making at different levels of the management hierarchy. Specifically, there is a lack of current information about the present status of gazelle in WRPA, as well as seasonal and daily movements and feeding ecology of key species such as gazelle, and about the activities of poachers and other disturbances. A lack of on the ground capacity to conduct inventory, monitoring and research activities, and tools (e.g., camera traps) are key limitations.

- Associated with the lack of information is the lack of an information management system to properly store data inputs and other information for ongoing use. As a result, past investments and efforts to collect data are not available to support ongoing decision making.

- A lack of staff professionalism is a barrier, resulting from significant staff turnover and lack of financial resources for training, uniforms and field equipment.

- Lack of local community and stakeholder participation in the management of the two targeted PAs:

- Currently, PA management of the two PAs is considered as the exclusive responsibility of the PA management authorities and as a result there is limited coordination between the PA Management Units (PAMUs) and the local communities and the stakeholders that have an impact on the effective management of the PAs.

- A lack of coordination among stakeholders and with local communities exists. There is a need to establish the necessary platforms for coordination and linkages with other sectors.

- Local communities have expressed a low degree of awareness about the protected areas and the benefits they bring to their communities, in part due to a lack of outreach materials and activities from the PAs to engage with local-level stakeholders (communities, tourism businesses, etc.). This limits support for the actions of PA managers and creates a missed opportunity for resolving conflicts and encouraging community participation in PA management. There is a need to expand the management of the PAs outside of the area of PAs, as many of the habitats and other services provided and necessary for effective species conservation are located outside the PAs.

- The lack of community participation itself is a key barrier, as it reduces community cooperation in preventing hunting impacts (particularly by outside parties), and in organizing community efforts to balance development and conservation objectives and to limit development impacts within the PAs (particularly infrastructure development and uncontrolled agricultural and fishing practices that threaten to degrade the aquatic environments and resources on which many residents depend).

## Institutional, sectoral and policy context

Many national institutions are involved in environmental protection, management and land use activities at the national and governorate levels.

2.4.1	Institutional and sectoral context

According to the environmental Law 4/1994, the mandate of the Egyptian Environmental Affairs Agency (EEAA) is to protect and promote the environment (ARE, 2001).  The agency has a public juridical (law-making) role and operates under the Minister for Environmental Affairs with an independent budget.  It has several branches in the Governorates of Egypt.  EEAA formulates the general policy and lays down the necessary plans for protecting and promoting the environment.  It follows up the implementation of such plans in coordination with the competent administrative authorities.  It also has the authority to implement pilot projects.  The agency is responsible for strengthening environmental relations between Egypt and other countries and regional and international organizations.

The challenge of Egyptian environmental policy is to achieve a balance between the needs of aand  developing nation while protecting its natural resources.  Environmental policy is set formally by the Ministry of State for Environmental Affairs (MSEA) and is the product of consultation with legislative, political and public representatives.  It also includes representations from the private sector and from environmental NGOs. EEAA is the executive arm of the MSEA.  National-level ministries, including EEAA, have local delivery units in the Governorates that are coordinated by Governors.

The strategic objective of environmental policy in Egypt is to introduce and integrate environmental concerns relevant to protecting human health and managing natural resources into all national policies, plans, programs and projects. The medium-term objective is to preserve natural resources, biological diversity, and national heritage within a context of sustainable development.  The short-term objective is to reduce current pollution levels and minimize health hazards to improve the quality of life in Egypt.

NGOs, community-based organizations and other forms of non-government entities can contribute to environmental planning and management initiatives at many points, thereby improving the quality of life in low-income communities.  Law 4/1994 expanded the role of NGOs in environmental protection as article 103 entitles them and any individual to report any violations of the law. According to this law, the EEAA’s Board of Directors includes three members representing NGOs as well as other members of civil society.  Egyptian environmental NGOs are of three types:

- NGOs with broad interest in the environment and large membership.  Examples here include the National Association for Protection of Environment (NAPOE) and Friends of the Environment Association in Alexandria (FEA).

- Single-issue organizations with open but small member ships.  Examples here include the Association for the Protection of the Environment (APE) and the Association for Health and Environmental Development (AHED).

- NGOs such as scientific societies and some research institutions that deal with environmental problems.  Examples are the National Society for Environmental Protection and the Egyptian Society for Marine Sciences and Technology.

The effectiveness of NGOs in the field of environment has been recognized by the EEAA, who is providing NGOs with technical assistance and support in mobilizing resources essential for funding their projects. The MSEA/ EEAA has made an effort to inform NGOs about environmental problems and corrective actions needed to limit the negative consequences of these problems.  The NEAP noted that capacity of NGOs to carry out their environmental functions is constrained by both internal originations and the external political and legal problems, and therefore NGOs should be enabled and strengthened to help design and implement the EEAA programs and projects (ARE, 2001).

2.4.2 	National legislation and policy context

Law 102/1983 provides the legislative framework for establishing and managing protected areas in Egypt.  The sole category referred to in this law is the natural protectorate, which is defined as “any area of land or coastal or inland water characterized by flora, fauna and natural features having cultural, scientific, tourist or aesthetic value.” These are designated by Prime Minister’s Decrees upon recommendations of the EEAA, which proposes boundary maps and is entrusted with the management and supervision of such protected areas. According to Law 102/1983, it is forbidden to undertake actions, activities or procedures, which would destroy, damage or degrade the natural environment, or harm terrestrial, marine or plant life, or detract from its aesthetic quality in a protected area.

Law 4/1994 for the Environment (amended by Law 9/2009) contains additional provisions for inside and outside protected areas. The law assigns a major role to EEAA in the management and monitoring of protected areas, including the management of the licensing and permit system for any activity undertaken in protected areas requiring EIAs. All activities carried out in protected areas are to be subject to the EEAA’s control, which can take steps to enforce the rules and stop any illegal activity.  The Executive Regulations prohibit hunting inside and outside protected areas and gives the EEAA responsibilities for coordinating hunting management. Importantly this Law calls for the establishment of an environmental protection fund and a system of incentives to encourage the protection of the environment. The EEAA has prepared guidelines on the EIA procedure which list the establishments and projects that are required to conduct an EIA.

There is a National System Plan for Protected Areas developed in 1998 by the Egyptian National Protected Area Identification Mission with financial support from the European Union (EU), which had the primary goal of defining the future shape and size of Egypt’s Protected Area Network. The recommendations of this plan are being implemented and have been integrated into national strategies and plans.  The plan proposed a total of 19 new protected areas for declaration, totalling some 100,000km², nearly doubling the size and number of sites. To date, 30 sites have been declared as protected areas, including Siwa, White Desert, Wadi El Gemal, Gelf El-Kabir combined with the existing protected areas, the total area would be 150,000 km², or about 15% of the total land of Egypt. Proposed protected areas were evaluated and identified according to predefined criteria. The new additions focused on habitats, natural regions and resources underrepresented in the current protected areas network; and on sites of exceptional potential for nature based economic activities.  The proposed expanded network greatly improves the coverage and representation of all recognized natural regions in Egypt and of critically important biodiversity resources. This expansion goes beyond mere increase in size, but also increases the diversity of resources represented in the network and attempts to promote and accommodate a broader function for protected areas in the Egyptian economy in the future.

## Stakeholder mapping and analysis

This section provides a description of key actors and their responsibilities relevant to the management of protected areas and the conservation of biodiversity in Egypt. Section 5 describes the specific role of stakeholders in the project.

2.5.1	Government institutions

The Egyptian Environmental Affairs Agency (EEAA) provides oversight for the protection and management of Egypt’s environment, including operation of the environmental protection fund and management of the Environmental Impact Assessment process, which is the country’s main tool for controlling and regulating the environmental impacts of development projects.

The Nature Conservation Sector (NCS) is the leading governmental body responsible for PA management and the conservation of biodiversity. NCS leads the design and implementation of policy and regulatory changes to ensure compliance with habitat and species protection legislation, and all issues related to biodiversity conservation within the broader landscape. NCS sits within the Egyptian Environmental Affairs Agency (EEAA) under MoE. The Government of Egypt has been considering the establishment of a new governmental body to enable a more effective protected areas function. While the NCS will remain within EEAA, the new protected areas authority will report directly to the Minister of Environment. This structural change is anticipated to occur over the next year.

A number of other ministries have mandates associated with the use of natural resources (see table below). They are established at the national level and operate at the sub-national (provincial) level in the Fayoum and Giza Governorates. Most of the lands adjoining the protected area are in the Fayoum Governorate, with a small portion in the Giza. Through the Governor, the Governorates are responsible for local administration as well as infrastructure, social and economic development. Although the responsibilities and powers are centralized in sectoral ministries, the Governorates have budgets and programmes for administration, social and economic development at the provincial level. The Governorate controls the local administration of two municipalities. Within the Governorate boundaries, the Governor has the responsibilities for: co-coordinating activities of different ministries; promoting tourism development; issuing building permits; and, selling municipal and Governorate controlled land within the town limits. All municipal zoning, tourism projects and building permits are authorized and issued by the Governorate.

Table 2. Summary of government stakeholders.

| Institution | Mandate |
| --- | --- |
| Ministry of State for Environmental Affairs (MSEA) | The Ministry of State for Environmental Affairs (MSEA) establishes environmental law and policy for Egypt. EEAA is the executive arm of the MSEA. NCS sits within the Egyptian Environmental Affairs Agency (EEAA) under MSEA. |
| Egyptian Environmental Affairs Agency (EEAA) | Egyptian Environmental Affairs Agency (EEAA) provides oversight for the protection and management of Egypt’s environment, including the Nature Conservation Sector, operation of the environmental protection fund, and management of the Environmental Impact Assessment process, among other functions. |
| The Nature Conservation Sector (NCS) | The Nature Conservation Sector (NCS) is the leading governmental body responsible for PA management and the conservation of biodiversity. NCS leads the design and implementation of policy and regulatory changes to ensure compliance with habitat and species protection legislation, and all issues related to biodiversity conservation within the broader landscape. |
| Fayoum Governor and governorate authorities | National-level Ministries operate at the governorate (provincial) level. Through the Governor, the Governorates are responsible for the coordination, local administration as well as infrastructure, social and economic development. The Governor can approve decrees pertaining to resource-uses. The relevant Ministries are listed below, including the authorities that operate under the coordination of the Governor. |
| Ministry of Agriculture and Land Reclamation | The ministry and several of its subsidiary organizations are actively involved in the region. The ministry, through the Desert Research Center, is finalizing an agreement for a local community development project in the southern part of the Eastern Desert with funding from the World Food Program, which could involve the introduction of widespread water harvest measures (e.g. small dams in Wadis) and drilling shallow wells, etc. Desert Research Center (DRC) is a parastatal that supports the implementation of the UNCCD in Egypt. The Center functions mostly as a research entity, made up of experts and specialists on all aspects of managing drylands in Egypt. Agricultural Research Center focuses on livestock and crop research. General Authority for Rehabilitation Projects & Agricultural Development is a statutory authority that works closely with local farmers (e.g., establishing drip irrigation rules for the reclaimed areas). |
| Ministry of Water Resources & Irrigation | General Authority for Development of Fish Resources is a statutory authority in charge of regulating and developing fisheries and fish resources in Egypt. It has a large interest in any management measures that might affect the fish production in any region. This authority works closely with local fish farmers and fishers in Lake Qarun. The Water Research Institute carries out water-related research throughout the country. |
| Ministry of Tourism | Fayoum Tourism Authority focuses on tourism research, contracting services for its hotel operations and marketing tourism assets through exhibitions. It also enhances the capacity of local people in the tourism industry through training. |
| Higher Council for Antiquities | This is a statutory agency in charge of archaeological sites. It has responsibility for surveying and protecting antiquities and archaeological sites, many of which are either included in the protected areas system or are tied to the development of a desert tourism product and face similar pressures from tourism use. |
| Ministry of Interior | The ministry is concerned with security. The ministry has under its authority the Police (including its various branches). It is the executive authority for Egyptian civil legislation. |
| PA Staff | The staff at the two PAs play an important role in carrying out day to day activities, to the extent possible with the limited equipment, staffing, training and budgets. Their work is mostly of an operational nature such as compliance monitoring and enforcement, biological monitoring, and environmental and interpretation activities within the PAs and in the nearby communities. |

2.5.2 	NGOs + Academic Organizations

IUCN-ROWA: IUCN ROWA shares critical conservation knowledge with all stakeholders and partners and currently focus on providing services, which brings added value to the ongoing activities. One of the many IUCN ROWA strengths is its ability to catalyse policy. IUCN works supportively and in collaboration with project stakeholders and partners, which include NGOs and governments, to achieve a new paradigm for sustainable development based on the concept of people cantered development.

Centre for Environment and Development for the Arab Region and Europe (CEDARE): Based in Cairo, CEDARE is a knowledge-based and technology-driven centre of excellence established by the Arab Ministers of Environment. CEDARE maintains a strong network of governmental, non-governmental and supra-national partners within the Arab region.

Nature Conservation Egypt: This national-level Egyptian NGO is focused on promoting biodiversity conservation and appreciation of nature, and lobbying government on conservation issues. A member of NCE works locally in Fayoum as a volunteer (informal group called Egyptian Association for Bird Protection) to promote awareness of hunting rules and no-hunting areas.

Fayoum Environmental Center: This local Fayoum city-based NGO focuses on community development, women and youth training. They conduct skill development training and environmental awareness through online and in-situ activities in schools and communities.

Message (Resala): This local youth NGO focuses on engaging youth and getting the environmental message out.

2.5.3 	Community institutions and local enterprises:

Local communities: Numerous small communities are found within the local area of the two PAs, such as Shakshouk Village, Yusef Sadeek Village, Tunis Village, Sydra Mousa and Sydra Kedra Land Reclamation Villages within WRPA, and many others.

Resource users: Many thousands of local agricultural farmers, fish farmers, salt extractors, and others operate within or adjacent to the two PAs. They should be part of the solutions for issues related to irrigation, runoff, pollution, grazing, etc.

Private tourism businesses (e.g. tour operators, hotels, ecolodges, restaurants, etc.): Private companies are important users of natural resources and a key partner for local communities to generate income and employment opportunities. As beneficiaries of healthy ecosystems and well-managed PAs, they have a direct stake in the ecological state of the region and should have an interest in maintaining a high-quality environment in the region. Local and national companies involved in serving the tourism industry should be part of the solutions for issues related to protocols, limits, regulations, etc. pertaining to tourism visitors, (e.g., hotels, tour guides, etc.).

## Baseline analysis and gaps

Without this proposed project, the current conditions and threats are expected to persist. As described in section 2.3 (threats, root causes analysis) and illustrated in the problem tree, several interconnected issues are undermining the ecological integrity of the area and degrading the potential to realize associated ecosystem services. In particular, the Lake Qarun fishery has collapsed and lake water quality and quantity continues to decline. This situation will continue to worsen, causing negative health, social, economic and environmental impacts. The current situation is further considered below, in the context of the project’s components.

Baseline Component 1. Strengthen management capacities of targeted PAs for the conservation of threatened and important species and their habitats.

Presently, the two protected areas lack capacity to develop and implement management tools and processes. Management plans, management effectiveness assessments and business plans have been developed in the past for WRPA but are outdated. A management plan for Lake Qarun is in preparation. Some basic-level biological monitoring activities have occurred, but with staff turnover, the process has not persisted. Enforcement controls are undertaken periodically, however there is no strategy to guide activities.

Under the baseline scenario, it is expected that a coordinated field monitoring activities within Wadi El-Rayan and Lake Qarun PAs to assess the conservation status of key ecosystems and threatened and important species would not be developed and nor implemented. Similarly, a coordinated, strategic approach to compliance monitoring, permitting and enforcement would be developed nor implemented.

The current shortcomings are due to a multitude of factors, including:

  - having an insufficient number of staff.

  - a lack of training, experience and equipment. The full range of training is required, including: public engagement skills and methods, planning, enforcement, biological monitoring and research, etc.

  - a lack of a coordinated response to needs (e.g., a long-term ecosystem-based strategy for Lake Qarun).

Baseline Component 2. Establish effective community participation in PA management and conservation / management of natural resources.

Very limited participatory approaches to PA management have been undertaken to date in the two PAs. This is due primarily to a lack of training and experience in designing community participatory approaches, facilitation and conducting public engagement activities. No meaningful impact on improving the participation of women has been realized to date.

No protocols and best practice guidelines have been developed to guide the sustainable use of natural resources as a means to abate threats on the protected areas, conserve ecosystem services and reduce overharvesting by local communities. Furthermore, such protocols and practices have not benefited from community knowledge and experience, or technical and scientific knowledge.

With limited capacity, management activities are primarily undertaken by the PAMU staff in the absence of participatory approaches with local resources users. The EIECP phase III project at WRPA is focusing on developing staff skills to enable Community-based Natural Resources Management approaches.

Under the baseline scenario, it is expected that some progress on CBNRM will be achieved in the areas under consideration of the EIECP. However, an improved, locally-focused process for biodiversity and compliance monitoring and enforcement will not be developed.

## Linkages with other GEF and non-GEF interventions

There is an opportunity for this proposed UN Environment GEF6 project to work synergistically with other GEF and non-GEF interventions, as described below.

Communication and coordination with individual projects will be established by the Protected Area Management Units (PAMUs) during the inception period, facilitated by IUCN, UN Environment, NCS and others, in order to optimize synergies, examine the potential for cost sharing and ensure efforts are complementary. At a strategic level, the Project Steering Committee (PSC) will ensure coordination and synergies between projects (section 5).

Table 3. Summary of related initiatives.

| Related initiative | Brief description | Linkage and potential collaboration |
| --- | --- | --- |
| UNDP-GEF project “Strengthening protected area financing and management systems” | Objective is the establishment of a sustainable protected area financing system, including ensuring that levels of financial resource mobilization are adequate for effective conservation-oriented management of Egypt’s PA system. | - Potential to cooperate on local engagement activities, and to link decisions pertaining to revenue generation to sustainability of ecosystems and species. - Cooperate on visitor fee system. - Cooperate on GIS/remote sensing system. - Establishment of the new General Authority for Protected Areas in Egypt (approval of new legislation is pending) is expected to yield sustainable levels of financing through increasing revenue generation. The current, existing fees are very low and will be increased; new fees for certain activities or permits may be considered; and in the case of QLPA no fees are presently collected but will be in the new system. The expected result will be increased revenues for the PAs, which will directly benefit the sustainability of operational programs at the PAs. - The SPAFAM is leading all aspects pertaining to fee structures and new legislation for the new General Authority. The project has completed an economic evaluation for WRPA and some willingness to pay surveys (how to raise fees) in several PA sites. |
| Egyptian-Italian Environmental Cooperation Programme, Phase III (EIECP III) | Focussing on a strategy of Community-based Natural Resources Management (CBNRM) to support sustainable development and ecotourism. | - The CBNRM modality is complementary to this project. The proposed activities in Component 2 of this project (e.g., engagement of local communities in monitoring, developing protocols, identifying management actions, etc.) will benefit from the CBNRM mechanism. Close collaboration will be sought. - The Fayoum tourism association, established through the EIECP III project, will provide advice on priorities and approaches for encouraging the development of new opportunities and/or improving existing initiatives. - Development of a community-based environmental education centre, consistent with the WRPA Integrated Eco-tourism and Development Plan. - The EIECP III project has developed an awareness strategy for the PAs in Fayoum and Wadi El Gemal. The strategy contains activities that could be implemented through the current EIECP III project as well as the proposed GEF project—this will be executed in a coordinated manner to support the projects. - The EIECP III project is preparing an ecotourism strategy for Fayoum PAs and an action plan for the main attraction sites. This will inform the planning and implementation of activities in this project. - EIECP III is doing infrastructure work, including fee stations, to improve management. |

Figure 5. Common outcomes of related initiatives.

2.7.1 	Strengthening protected area financing and management systems (SPAFAM)

This UNDP-GEF project is being implemented by EEAA’s Nature Conservation Sector (NCS) with a GEF contribution of USD 3,616,000. The project objective is the establishment of a sustainable protected area financing system, with associated management structures, systems and capacities needed to ensure the effective use of generated revenues for priority biodiversity conservation needs. The project is designed to remove or significantly reduce a wide range of barriers to sustainable financing by:

- Strengthening legal, policy, regulatory and institutional frameworks that facilitate revenue generation and retention and other aspects of sustainable PA financing.

- Ensuring that levels of financial resource mobilization are adequate for effective conservation-oriented management of Egypt’s PA system.

- Establishing business planning and cost-effective management systems that ensure the effective allocation and management of mobilized resources.

The SPAFAM project is particularly focused on policy changes that will enable NCS to substantially increase its levels of revenue generation, while also ensuring that the bulk of these revenues remain available to NCS for hiring and compensating staff, developing site infrastructure, etc.

A key to ensuring the sustainability of the policy changes will be to ensure that the funding made available to NCS is disbursed in an efficacious and cost-effective manner.  For this reason, the project will guide the investment of re-injected funds into a number of high priority sites and activities, where it will seek to leverage additional funding and establish planning, allocation, management and monitoring tools to demonstrate the impact and cost effectiveness of these investments, thereby providing NCS with a powerful set of arguments for continuing long-term investment, financing and expansion of Egypt’s PA system, mainly through self-generated revenues.

One of the eight sites included in the SPAFAM finance project is Wadi El-Rayan.  At this site, the project will focus on strengthening the process for collecting entrance fees; developing and printing awareness materials; upgrading the visitor centre, and improving the quality of the road network within the PA.

The SPAFAM finance project contributes to BD1 program of the GEF6 Biodiversity Strategy:

- Outcome 1.1. Increased revenue for protected area systems and globally signiﬁcant protected areas to meet total expenditures required for management.

The proposed UN Environment GEF6 project focuses on the complementary outcome of this program, i.e., Outcome 1.2. Improved management effectiveness of protected areas. The proposed UN Environment GEF6 project will complement the SPAFAM finance project by:

- Enhancing the legal framework and oversight mechanisms for PA spatial planning.

- Strengthening the management of PAs on the ground safeguarding key landscape and biodiversity assets.

- Enhancing the recognition and sustainable use of biodiversity.

This proposed project will not develop system tools for enhanced financial flows, however as part of its strategy, it will apply the frameworks and mechanisms developed under the SPAFAM finance project and implement them at the local level at the two targeted PA sites. Tools and lessons learnt will be adapted from the SPAFAM finance project through coordination via the respective project management units.

2.7.2 	Egyptian Italian Environmental Cooperation Programme, phase III (EIECP III)

This three-year project aims to further the consolidation of the Nature Conservation Sector to promote community-based income-generating mechanisms for the management of Egypt's protected areas (PAs) system. It is being implemented by EEAA and UNDP with the support of Italian Cooperation in the amount of USD 3,935,190, and is expected to finish in mid-2019.

The EIECP III project document describes the project’s strategy. Efficacy of a PA in preserving natural and cultural values is related to the tangible benefits that the local communities can receive from the sustainable use of such values. This enables the establishment of a management paradigm that, instead of prohibition mechanisms, is based on the strong sense of ownership and the consequent commitment of the local citizens toward the conservation of the PA's ecosystem and the sustainable use of the services it provides. Hence, the EIECP III strategic approach and implementation methodologies are built around the paradigm of CBNRM which, through the analysis of the relevant ecosystem structure and services, aims at identifying those sustainable uses of natural resources that can generate adequate income for the local communities. Such communities, in turn, become more dependent on the PA's natural and cultural values and, thus, develop a strong sense of ownership of such values and, therefore, act themselves as the primary "driving force" toward the conservation of the very values. See box text for key variables.

EIECP III includes the promotion of responsible and sustainable eco-tourism activities and the integration of all other potential local economic activities, such as agriculture, grazing and fishing in the CBNRM schemes in and around PAs. The said CBNRM schemes will thus be critically analysed

CBNRM:

The principles of good governance, such as participation, partnership and enabling, responsive, inclusive, transparency and accountability are at the heart of CBNRM approaches to ensuring stakeholder participation and, thus, increasing the sustainability also by providing a forum for the resolution of possible conflicts.

A successful CBNRM initiative results in the following outcomes:

- Proximity to resources. Those in the closest contact with, and whose livelihoods are impacted by, natural resources are best placed to ensure effective stewardship.

- Equity. Natural resources should be managed to ensure equitable benefits for the diverse interest groups within a population.

- Capacity. Communities often have better knowledge and expertise in the management of the natural resources than government agencies/private industry.

- Biodiversity. Multiple-purpose management of natural resources by communities generally provides more varied land use, with greater species diversity than private/industrial management systems.

- Cost-effectiveness. Local management may help reduce government costs.

- Development philosophy. Local participation, decentralization, and subsidiarity are considered important development objectives.

(Source: EIECP III project document)

to highlight PAs management best practices and, on this basis, prepare guidelines and methodological tools for their replication in other contexts.

WRPA is one of the demonstration sites in the EIECP III project. It is intended that the lessons learned can be adapted and applied to other protected areas, including LQPA.

The key outputs for EIEP III are:

- Output 1: The management schemes currently in use for the project's selected Intervention Areas (IAs) are enhanced through the integration of effective CBNRM mechanisms to support sustainable development. Activities include: preparing a detailed baseline and needs assessment; conducting a stakeholders’ analysis to identify the local political map of power and interests; designing CBNRM modalities suitable to each IA; and promoting sustainable development through CBNRM in the project IAs.

- Output 2: Responsible and sustainable eco-tourism promoted in the project Intervention areas. Key activities include: establishing effective coordination between partners (e.g., Ministry of Tourism, Ministry of Environment and Ministry of Antiquities) through the establishment of issue-specific working groups to promote responsible and sustainable eco-tourism; strengthening the capacities and raising awareness of the project IAs within local communities for the management of responsible and sustainable eco-tourism businesses; developing and implementing innovative responsible and sustainable eco-tourism business plans for the project IAs.

- Output 3: Innovative participatory approaches for inclusive growth around Egypt's PAs tested and ready for institutionalization. Activities include: evaluating experiences gained in the project IAs for their replication in other areas of Egypt with special emphasis on women; and, proposing a sustainable financing framework for Egypt's PAs system.

The proposed UN Environment-GEF6 project will work cooperatively and seamlessly with the EIECP III in the approach to CBNRM. The proposed project will bring the complementary focus on:

- Technical aspects of biodiversity inventory, monitoring and research.

- Compliance monitoring and enforcement practices.

- Protocols and best practice approaches.

- Technical aspects of management planning, species plans, and ecosystem-based planning (e.g., Lake Qarun restoration/rehabilitation strategy).

# Section 3. Intervention Strategy (Alternative)

## Project rationale, policy conformity and expected global environmental benefits

The proposed project will support the biodiversity goal of GEF6 and will contribute primarily to achieving Focal Area Program Objective 1 and Program 1: Improving Financial Sustainability and Effective Management of the National Ecological Infrastructure. The project will also contribute indirectly to achieving other elements of GEF6 Biodiversity Strategy.

The project will improve the management effectiveness of existing PAs for the conservation of priority endemic and threatened species (and endangered species if confirmed present) and their critical habitats, through the development of adaptive management frameworks, operational capacities and mechanisms for the participation of local communities.

Table 4. Project contributions to GEF6 objectives and programs.

| Focal Area Objectives | Programs | Expected Outcomes & Indicators |
| --- | --- | --- |
| Objective 1: Improve sustainability of protected area systems | Program 1: Improving Financial Sustainability and Effective Management of the National Ecological Infrastructure | Outcome 1.2: Improved management effectiveness of protected areas. Indicator 1.2: Protected area management effectiveness score. |

The project will put in place measures to strengthen the management of protected areas that include globally important landscapes, and the enforcement of policies and regulations to protect native flora and fauna, in particular globally significant and threatened species at sites within or adjacent to the Wadi El Rayan and Lake Qarun protected areas.

The project is expected to produce tangible conservation benefits for species noted in section 2.2.

Investments, training, and participatory management arrangements will address priority conservation planning and management problems common to many important and threatened biodiversity sites throughout Egypt, and therefore will generate models for replication in priority conservation sites in other parts of the country and region.

The project will contribute to Egypt’s achievement of the CBD Strategic Plan for Biodiversity 2011-2020 and the Aichi biodiversity targets as follows (UNEP/CBD/COP/DEC/X/29 October 2010):

Table 5. CBD strategic goals and Aichi targets and examples of project activities.

| CBD strategic goal and Aichi target | Examples of project activities |
| --- | --- |
| Strategic goal A. Address the underlying causes of biodiversity loss by mainstreaming biodiversity across government and society |  |
| Target 1: By 2020, at the latest, people are aware of the values of biodiversity and the steps they can take to conserve and use it sustainably. | - Increasing citizens’ awareness of the values of biodiversity and the steps they can take to conserve and use it sustainably. - Engagement in planning and developing strategic and practical local solutions. |
| Target 4: By 2020, at the latest, Governments, business and stakeholders at all levels have taken steps to achieve or have implemented plans for sustainable production and consumption and have kept the impacts of use of natural resources well within safe ecological limits. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhanced compliance monitoring and enforcement activities. |
| Strategic goal B. Reduce the direct pressures on biodiversity and promote sustainable use |  |
| Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhanced compliance monitoring and enforcement activities. |
| Target 6: By 2020 all fish and invertebrate stocks and aquatic plants are managed and harvested sustainably, legally and applying ecosystem based approaches, so that overfishing is avoided, recovery plans and measures are in place for all depleted species, fisheries have no significant adverse impacts on threatened species and vulnerable ecosystems and the impacts of fisheries on stocks, species and ecosystems are within safe ecological limits. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhancing compliance monitoring and enforcement activities. - Enhancing biological inventory, monitoring and research activities. |
| Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhancing compliance monitoring and enforcement activities. |
| Target 8: By 2020, pollution, including from excess nutrients, has been brought to levels that are not detrimental to ecosystem function and biodiversity. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhancing compliance monitoring and enforcement activities. - Lake Qarun ecosystem-based rehabilitation strategy. |
| Target 9: By 2020, invasive alien species and pathways are identified and prioritized, priority species are controlled or eradicated, and measures are in place to manage pathways to prevent their introduction and establishment. | - Strengthening PA management capacity and landscape level approaches to BD conservation that will reduce the introduction and spread of IAS into natural habitats. - Enhancing biological inventory, monitoring and research activities. |
| Strategic goal C: Improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity |  |
| Target 11: By 2020, at least 17 per cent of terrestrial and inland water areas, and 10 per cent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes. | - Adding additional natural habitats to the PA system toward achieving the 17% target, and improving the overall ecological representativeness of the national PA system. |
| Target 12: By 2020 the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has been improved and sustained. | - Enhancing biological inventory, monitoring and research efforts, and compliance and enforcement activities for the protection of threatened species and their habitats. |
| Strategic goal D: Enhance the benefits to all from biodiversity and ecosystem services |  |
| Target 14: By 2020, ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being, are restored and safeguarded, taking into account the needs of women, indigenous and local communities, and the poor and vulnerable. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. - Enhancing compliance monitoring and enforcement activities. - Developing a Lake Qarun ecosystem-based rehabilitation strategy. |
| Strategic goal E. Enhance implementation through participatory planning, knowledge management and capacity building |  |
| Target 18: By 2020, the traditional knowledge, innovations and practices of indigenous and local communities relevant for the conservation and sustainable use of biodiversity, and their customary use of biological resources, are respected, subject to national legislation and relevant international obligations, and fully integrated and reflected in the implementation of the Convention with the full and effective participation of indigenous and local communities, at all relevant levels. | - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. |
| Target 19: By 2020, knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied. | - Improving biological inventory, monitoring and research efforts. - Implementing communications, awareness and public education actions. - Citizen and stakeholder engagement to develop new regulations, protocols and best practices for the sustainable use of natural resources, in and adjacent to protected areas. |

The project will contribute to the following goals of the CBD Programme of Work on Protected Areas (PoWPA):

- 1.2 to integrate protected areas into broader land- and seascapes and sectors so as to maintain ecological structure and function.

- 1.4 to substantially improve site-based protected area planning and management.

- 1.5 to prevent and mitigate the negative impacts of key threats to protected areas.

- 2.2 to enhance and secure involvement of indigenous and local communities and relevant stakeholders.

The project will contribute to the Sustainable Development Goals and Vision 2030, in particular to:

- SDG 6: Ensure access to water and sanitation for all. Several targets are pertinent as they relate to access to water quality; efficient use of water; integrated resource management; protection and restoration of ecosystems; capacity building; and, participation of communities including women and girls,

- SDG 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. Target 15.5 pertains to taking urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species.

The project is aligned with UN Environment’s programme of work:

- Ecosystems Sub programme Expected Accomplishment 1: Use of the ecosystem services and sustainable productivity of terrestrial and aquatic systems is increased.

The project is also aligned with the IUCN One Programme:

- Valuing and conserving nature enhances IUCN’s heartland work on biodiversity conservation, emphasising both tangible and intangible values of nature.

- Promoting and supporting effective and equitable governance of natural resources consolidates IUCN’s work on people-nature relations, rights and responsibilities, and the political economy of nature.

- Deploying nature-based solutions to societal challenges expands IUCN’s work on nature’s contribution to tackling problems of sustainable development, particularly in climate change, food security and social and economic development.

https://www.iucn.org/about/programme-work-and-reporting/programme

The project is consistent with the United Nations Development Assistance Framework for Egypt (UNDAF-Egypt). Specifically, UNDAF-Egypt outcomes respond to a number of challenges under Pillar III of the Situational Analysis. In summary:

- Pillar III (environment and sustainable natural resources) covers all elements of natural resources including agricultural land, water, energy and their sustainability. The purpose is to analyze the status of the agricultural development strategy and issues of food security, water and irrigation. Pillar III also pays special attention to the impact of growth and development on Egypt’s environment and related sectors, including water, sanitation, health and waste management. The importance of introducing environment-friendly practices such as ecotourism is highlighted. Pillar III is especially concerned with the potential threats of climate change, water and energy scarcity, and the need for adaptation.

- Outcome 5.2:  The Government of Egypt, private sector and civil society have complied with multi-lateral environmental agreements, adopted policies, and implemented operational measures towards a green and sustainable economy and society. This outcome also responds to four specific challenges identified in the SA: renewable energy, energy security, energy efficiency, and environmental protection.

- Outcome 5.3: The Government of Egypt and local communities have strengthened mechanisms for sustainable management of, and access to, natural resources such as land, water and ecosystems. UN action under Outcome 5.3 makes a contribution to addressing a range of challenges related to investment needs in the agriculture sector, deteriorating land efficiency, land allocation, strengthening technical and institutional capacities for managing natural resources, expanding fisheries, water shortages and environmental protection.

This project supports UNDAF-Egypt outcomes by providing factually-accurate biodiversity information to support planning and decision making in the areas of resource uses and environmental protection.

## Project goal and objective

Project Objective: To improve the management effectiveness of the Wadi El-Rayan and Lake Qarun protected areas through community involvement and capacity building. The project comprises two key components, as follows:

- Component 1: Strengthen management capacities of targeted PAs for the conservation of threatened and important species and their habitats.

- Component 2: Establish effective community participation in PA management and conservation / management of natural resources.

In keeping with the principles of the ecosystem approach and adaptive management, a holistic approach to management will be taken when implementing the components, so that PA managers can effectively plan, implement, monitor, assess and adjust actions (see figure 6).

Figure 6. Holistic approach to management (Paleczny, 2007).

## Project components and expected results

Component 1: Strengthen management capacities of targeted PAs for the conservation of threatened and important species and their habitats.

Outcome 1.1: Improved management effectiveness (strengthened PA management tools, processes and capacities) demonstrated at two targeted PAs (Wadi El-Rayan and Lake Qarun).

The term ‘management effectiveness’ is meant to address how well the protected area is being

managed – primarily the extent to which it is protecting values and achieving the goals and objectives for which the PA was established (IUCN 2006). Management effectiveness reflects three main themes:

- Design issues relating to both individual sites and protected area systems;

- Adequacy and appropriateness of management systems and processes; and

- Delivery of protected area objectives including conservation of values.

To address these three themes, a variety of approaches and tools are used synergistically to develop and improve PA planning including identification and mitigation of threats; information, financial and human resource inputs; processes and implementation activities in the PAs; outputs of activities; and outcomes.

Under this outcome, the project aims to set clear plans for the future, increase biodiversity information to support decision making, reduce threats, and ultimately, secure the ecosystems and species of the PAs (per Theory of Change, figure 7).

The activities will help PA authorities to address and prevent developments and practices that transform or degrade habitats within the PAs, and in adjacent areas that produce negative impacts on PA ecosystems, by creating management plans and PA regulations that control and minimize development activities and by strengthening the capacity of PA authorities to better monitor potential developments and important ecosystem and biodiversity values. A principle underpinning associated with effectiveness is that local communities and other key stakeholders are involved in the processes and activities.

Output 1.1.1: PA management frameworks of Wadi El-Rayan and Lake Qarun PAs developed, including participatory approaches.

This output includes several activities to conserve threatened and endangered species and their habitat, enable participatory management approaches, address local resource management and access considerations, control visitors and their impacts, and other priorities. The approaches will be developed jointly between PA authorities and local stakeholders (consistent with component 2). Planning is a recognized tool to enable effective management. With community and stakeholder engagement in component 1 activities, planning can provide clarity and broad agreement on priorities.

Activity 1.1.1.1: Update and implement protected area and World Heritage management plans

This activity focuses on three tasks:

- Undertake a management effectiveness evaluation for the two PAs to confirm the specific threats and challenges impacting biodiversity and effective management. The results will be documented in a report so that comparisons on changes over time can be made. Similar evaluations were undertaken in 2007 (Paleczny et al., 2007 a+b). This task will enable a comparison of threats and status of ecosystems since that time. During this 11-year period, the country experienced two revolutions, which impacted on the capacity and effective management, and as a result, the condition and status of ecosystems in the PAs. The results will inform the following task to prepare management plans and contribute documentation for the IUCN Green List for Protected Areas.

- Review and update the management plans for the two PAs. WRPA management plan was initially prepared in 2002 and implemented for a five-year period. A review was initiated in 2007 but not completed; as a result, the World Heritage Site values and operational priorities have not been addressed, and a full review is needed. LQPA PA management plan was drafted in 2007 but never completed. Since that time, Gebel Quatrani has been nominated for World Heritage status, and as part of the nomination process a site management plan was prepared to address world heritage fossil values and associated development to secure and manage the site (EEAA, 2016). Overall, the conditions in LQPA have continued to change and problems continue to impact the PAs (see section 2.3). The management plans will identify the priority regulations to be established.

- Implement the two management plans. As part of this task, the PAMU will make a record of the activities that have been implemented with an assessment of their effectiveness. This will support the next review of the management plans and provide documentation in support of future listing of the PAs under the IUCN Green List initiative.

Activity 1.1.1.2: Develop Key Biodiversity Area classifications for WRPA and LQPA

This activity will develop the Key Biodiversity Areas classifications for the two PAs, following the IUCN’s KBA standard (IUCN 2016). This work will identify sites contributing to the persistence of biodiversity in the two PAs. By using the KBA Standard, comparisons of sites can be made over time. This will be the first application of the guideline in Egypt and will provide insight for a wider application in other protected areas. Associated mainstreaming activities will include training and participation of other PA staff to support its uptake and application.

Activity 1.1.1.3: Develop and implement habitat and species conservation plans

This activity focuses on developing and implementing a holistic habitat and species conservation plans for threatened and endangered species (see list of species in section 2.2). Specifically, the plans will include the following types of information and will be implemented:

- A description of the species and its needs.

- Assessment of the availability of the species' critical habitat in WRPA.

- Analysis of the specific threats to survival of the species, including activities that are likely to threaten the critical habitat.

- The goals and objectives for conservation of the species.

- Operational tactics and costs for securing species and habitats (e.g., patrolling schedules, community involvement, biological site requirements, training needs, guidelines for any development, operational costs, etc.).

- Identification of information gaps.

- Means for reviewing and assessing effectiveness of the plans after it has been implemented.

Priorities for species and habitat conservation plans will be based upon Red List species in the PAs (per section 2.2) and the findings of the biological inventory, monitoring and research activities and compliance monitoring and enforcement activities to be carried out per output 1.1.2. The species and habitat plans in this activity will focus specifically on the species and habitat aspects to ensure conservation of biodiversity values. This work will be carried out in close cooperation with the EIECP III project to ensure the work is complementary and not duplicative. For example, further work on the Integrated Eco-Tourism and Development Plan, developed through the EIECP III, will consider the key conservation needs, while this GEF project will delve into species and habitat needs in significant detail and will inform other planning and operational programmes.

Activity 1.1.1.4: Establish and implement regulations, best practice guidelines and manuals

This activity will establish regulations, best practices guidelines and manuals to strengthen and clarify the rules for activities in and around the protected areas, including dealing with unsustainable uses or practices that may threaten protected area ecosystems and values. This includes developing and reviewing proposed practices with local communities and other stakeholders for their input.

The following topics will be prioritized:

- Grazing and irrigation practices to ensure sustainability and minimal impacts, and where possible, methods to mitigate impacts. A determination on the most suitable approach (regulation and/or guideline) will be made through the community engagement process.

- Visitor use, including: and how to assess the potential negative effects on biodiversity values associated with the activity; how to set an appropriate carrying capacity for sensitive sites; when to close valuable or vulnerable areas to public access; how to mitigate the negative effects of over-use; driving only on defined, marked tracks, etc.

- Engaging women and youth: This guideline will focus on successful approaches to improving the involvement of women and youth in the PAs. It will include workshops and training to share the information with the beneficiaries.

Activity 1.1.1.5: Conduct PA staff training and community training to conserve biodiversity

Raising capacity of staff and community members is a key need to conserve biodiversity inside and around the PAs. This activity will deliver the following training:

- Conservation and management practices.

- Key concepts and international approaches, e.g., PA management planning, evaluation of management effectiveness, Key Biodiversity Areas, IUCN Green List, IUCN Red List.

- Biological monitoring procedures and reporting (focused on threatened species).

- Compliance monitoring and enforcement approaches and tactics.

- Enabling participatory community management, including skill development in the areas of effective meetings and workshops and facilitation.

- Communications, education and public awareness principles and practices.

- Use of software as required for different positions.

- Information management best practices, including database maintenance, and use of GIS and remote sensing tools.

- Soft skills (active listing, giving feedback, facilitating, negotiating, etc.) for dealing with various stakeholders and tourists, as well as working collaboratively with others (e.g., stakeholders, community members on committees, etc.).

The target will be to train 50 staff and 300 individuals from local communities. In 2007, a system-wide training needs analysis was conducted and delivered through the Egyptian-Italian phase II project. Similar needs were validated during interviews to prepare this project document. However, there has been nearly full turnover of staff since the last training programme, and the new staff have little to no experience or training in the technical areas. Accordingly, a training needs analysis will be conducted for the two PAs and include further consideration of key training needs for community members to enable their effective participation in PA management discussions. After 25th January revolution, major changes in local community settlements happened, i.e., new people living inside or adjacent to the two targeted PAs have very weak awareness about the roles of PAs for their livelihoods. The project will design and implement a series of training events to increase the awareness of the new and old settlements.

Methods of training can vary with the level of complexity. For example, during the project, consideration will be given to: in-service training programmes, academic courses, specialized national or international short-courses, MOOCs (massive online courses), and structured study tours.

Output 1.1.2: Field monitoring programs within Wadi El-Rayan and Lake Qarun PAs to assess the conservation status of key ecosystems and threatened and important species will be developed and implemented.

The project will establish key systems for effective management, including:

- A biological inventory, monitoring and research program for threatened and endangered species and their ecosystems (refer to section 2.2 for priority species).

- A compliance monitoring and enforcement workplan.

- A biodiversity information management unit.

The results of this output will be used to support several activities in outputs 1.1.1, 2.1.1 and 2.1.2.

Experience gained will be used to identify problems and challenges for monitoring programs, and to help establish improved standard criteria for Egyptian biodiversity monitoring programs. They will also provide direct inputs to setting implementation priorities, planned for under output 1.1.1 above.

Activity 1.1.2.1: Design and implement a monitoring and reporting program for threats and status of ecosystems and species

The term ‘program’ is meant to be inclusive of the range of needs from the more strategic-level considerations (what is needed and why) through to the more operational activities, tools, approaches, methodologies. This activity focuses on establishing a monitoring program, by:

- Preparing an overall action plan to guide biological inventory, monitoring and research activities, based on the threatened and endangered species (section 2.2).

- Identifying indicators for monitoring ecosystem changes and species status, including baseline thresholds and targets.

- Identifying and using standard methodologies (including GIS and remote sensing to detect changes in conditions of the lakes, resource ues, etc).

- Setting an appropriate schedule for monitoring species, taking into account species movements and use of habitats.

- Establishing partnerships with universities to carry out research on key topics that require detailed investigation.

- Engaging community participation in the development of the programme, including the Community Advisory Committee.

Specific inventory, monitoring and research work on gazelle will be undertaken to confirm their presence or absence within the PAs. Work is needed to improve knowledge of their feeding behavior, daily and seasonal movements, and habitat needs and limitations to understand optimum size of the herds, and potential viability of herd rehabilitation and/or reintroductions. Specifically, the following actions will be undertaken:

- Repeat the 2008 gazelle survey of WRPA and surrounding area again. With the baseline data from the 2008 survey, there would be an opportunity to compare results and possibly provide further insight into the status of the local population.

- Survey the other habitats in Wadi Ryan to see if there are any gazelle signs or if they have gone extinct from the area.   After the survey, new or priority areas or actions can be identified.

- Conduct an assessment of the feasibility of establishing a gazelle captive breeding center in WRPA. This assessment will include:  options and practical approaches to address opportunities and challenges (e.g., site requirements, technical and maintenance needs, development options, species re-locations and associated needs and costs for operating a transfer program, etc.); partnership opportunities with IUCN, the Environment Agencies in the United Arab Emirates, the Sarhara Conservation Fund, and others; and recommendations for next steps. IUCN will source technical expertise for this activity. This preparatory work will enable future decisions on whether to proceed with such an initiative.

Existing systems for monitoring and early warning of external threats will be strengthened, such as:  changes in land use, tenure or social/governance structures and proposed land change developments (i.e., tourism, mining, salt extraction, and other developments) with the potential to negatively impact ecosystem services and species. This work will build upon past management effectiveness evaluations.

Reporting the threats and status of ecosystems and species will be conducted annually (see activity below).

This activity will standardize the approach for translating the results of biological inventory, monitoring and research initiatives and compliance monitoring into technical reports and communications products that are accessible for their intended audiences. Specific information products will be needed to support effective community participation in protected area management (see Component 2 regarding CEPA).

The project will work with CEDARE in building the capacities of park management in Earth Observation (EO) modelling and in data exploitation.

Supporting equipment will be procured (e.g., camera traps, collars, drones, etc.). The information outputs of this activity will inform the compliance monitoring and enforcement activity, and the biodiversity information management activity (below).

Activity 1.1.2.2: Develop and implement a compliance monitoring and enforcement program

This activity will develop and implement a compliance and enforcement workplan for each PA. A progressive, graduated approach will be designed to include the spectrum of tools from education and awareness to compliance checks to stricter enforcement actions when required. The plan will:

- Draw upon the key biodiversity values and threats (identified through other activities) to establish the compliance and monitoring priorities (e.g., gazelle and falcon poaching; disturbance of species; illegal duck hunting; overuse of resources, impacts of high visitor levels).

- Establish the specific actions, including patrolling schedules.

- Set out the key measures to evaluate progress. The workplan should be reviewed and updated annually.

- Engage community participation in the development of the programme, including the Community Advisory Committee.

Equipment will be purchased to enable and strengthen compliance monitoring and enforcement actions (e.g., communications, photographic and observation equipment). This will lead to improved intelligence and surveillance, and as a result, a reduction in illegal hunting, over-harvesting, activities that have an impact on PA values. This activity will strengthen the capacities of the PAMUs and local communities to effectively promote compliance with protocols and regulations, and where necessary enforce regulations.

A monitoring and enforcement program for the PAs does not currently exist due to a near complete loss of capacity during and following the revolution. Sufficient equipment is not available. While there is some guidance available on past approaches, there is a need to stake stock of the current needs and implement an approach that is suitable for the current context. This includes training. It is anticipated that the Government of Egypt will continue with this important work at the end of the project by taking advantage of new resources expected through the establishment of the new protected areas authority (refer to section 2.5.1).

Activity 1.1.2.3: Establish and facilitate a PA biodiversity information management unit

This activity will establish a comprehensive biodiversity information management unit for the two PAs at PAMU headquarters in Shakshok in Fayoum. This will achieve the following needs:

- Enable proper decision support with factual, accurate and timely information about the PA’s biodiversity and associated threats.

- Design and develop the appropriate information management system to integrate biological inventory, monitoring and research information and the results of compliance monitoring and enforcement (per output 1.1.2).

- Provide decision support tools (e.g., GIS and remote sensing products).

- Integrate Earth Observation tools and approaches (per CEDARE contribution).

- Establish protocols for scheduled and proper system management, back-ups, etc..

This activity will also compile a database on the use and users of natural resources within the protected areas and in adjacent areas where use of resources has the potential to threaten protected area values. in collaboration with to ensure data investments are secured. This information will support efforts to track site specific issues and interventions, and to set targets for improvements. The information will support the identification of other needs, and the reporting of progress toward achieving management effectiveness.

This activity will be carried out in collaboration with NCS and the UNDP-GEF5 project to ensure coordination. The results will be up-scaled for wider application across the protected area system.

Equipment and materials will be procured to enable the unit (e.g., computers, software, plotters, etc).

Component 2: Establish effective community participation in PA management and conservation / management of natural resources.

Outcome 2.1: Participatory approaches to PA management have strengthened PA management and reduced unsustainable resource uses in areas within and adjacent to two targeted PAs (Wadi El-Rayan and Qarun).

The project’s Theory of Change (section 3.4.1, figure 7) emphasizes the critical importance of an engaged citizenry. Through meaningful forms of engagement, the project aims to create an enabling environment for engagement and collaboration, which in turn will support the design and delivery of the project activities and outputs in both component one and two.

Under this outcome, the project will work with local planning authorities and communities to control development pressures while also addressing the livelihood needs of local communities, taking advantage of the skills, experience, and knowledge within the communities, and strengthening relationships between the project executing agency (EEAA, NCS) and local stakeholders, and thereby increasing the social, environmental and financial sustainability of the project.

Training and information materials will be provided to members of local communities to enable their effective participation in activities.

Output 2.1.1: Programmes for community participatory planning and involvement in PA management developed and implemented at the targeted PA sites.

The project will work closely with local communities living in or near the two targeted protected areas who are dependent on PA ecosystem services and resources, as well as local municipalities, NGOs, and others. The involvement of women and youth is specifically addressed in the activities.

The project will focus on synergies between actors by supporting the development of platforms for coordination and linkage among stakeholders. The goal is to strengthen cooperation between PA authorities and local communities on PA management activities (e.g., enforcement, planning, monitoring, etc.). This is expected to mitigate negative effects of resource activities, improve management effectiveness and improve conservation of habitats for threatened and IBA trigger species.

The project will work closely with the Egyptian-Italian Environmental Cooperation Programme (phase III) on nurturing a Community-based Natural Resources Management (CBNRM).

Activity 2.1.1.1: Develop and implement a Communications, Education and Public Awareness (CEPA) plan

Through this activity, a comprehensive Communications, Education and Public Awareness (CEPA) Plan will be prepared and implemented. The plan will address the CEPA objectives, target audiences (including women and youth), methods of delivery, costs, and measures for assessing effectiveness of CEPA activities. The focus of this CEPA plan will be on the elements of this project; close coordination with the EIECP III project will ensure that duplication is avoided and tactics are complementary.

The CEPA Plan will address all activities in this project document as well as ongoing CEPA activities of the PAMU to ensure effective and efficient coordination of efforts. The plan will include the following elements, and will be reviewed and updated annually:

- Community-based workshops and fairs in all neighbouring communities to share information and encourage discussion about the protected areas.

- Community tours and school visits to sites within the protected areas.

- Information about protocols and agreements that are designed to promote an understanding of the importance of observing sustainable use practices and ecosystem carrying capacities (e.g., sustainable levels of fish harvesting, irrigation, etc.).

- Information and analyses to support the effective involvement of the Community Advisory Committee.

- Information campaigns targeting relevant ministries and related groups to increase awareness and understanding of the PAs’ biodiversity values and associated threats.

- Information for the Governorate will be targeted given their roles respecting tourism, agriculture, fisheries and water resources.

- Information about mitigating the effects of activities in the El Oayun oasis to reduce disturbance of gazelle.

- Public awareness activities to enhance local understanding of the benefits of protected areas and their relationship to human health and well-being, and opportunities to participate in PA management.

- Information sharing about best practices to support up-scaling of project results (per section 3.8).

The implementation of this plan will be jointly executed by both EEAA and the project with sharing the cost of the activities through the co-finance sources.

Activity 2.1.1.2: Establish and operate a community environmental education center

This activity will support the establishment of a community environmental education center, which will be located at the new main gate of WRPA. This location is complementary with the WRPA Integrated Eco-tourism and Development Plan, prepared under the EIECP III project. The center will include classrooms and space for community gatherings, as well as space for local environmental and health NGOs to locate and work together.

Support to environmental education NGOs (e.g., the Fayoum Environmental Center; local health and environmental groups) will be given to enable the groups to develop and deliver environmental education programs, within the center and in the PAs. The project will promote awareness and education initiatives that emphasize the strong connections between healthy environment, healthy parks and healthy people. Women and youth will be encouraged to participate in all activities.

All costs related to the establishment of the community environmental education center will be covered through co-finance funding from the EEAA and EIECP III project. The current project will support costs related to the operation of the center during the project life span. Also, the project will support activities related to the capacity building of the stakeholders and local communities as it is the heart of sustainability of the project after it finished.

Activity 2.1.1.3: Establish and facilitate a Community Advisory Committee

A Community Advisory Committee will be established to engage local communities in the management of the two protected areas. The two protected areas share similar challenges and many of the same local communities and local government officials. The committee’s Terms of Reference will be:

- Purpose: Provide advice on the array of matters that affect PA management and conservation of species and their habitats. Given the multiple interests in resource uses and potential benefits of the PAs for the communities, a coordinated approach to resolving management issues and realizing benefits for the local communities will be promoted.

- Key topics: Threats affecting species and habitat conservation; sustainable levels of resource use; water quality and quantity; health issues associated with the environment; ways to participate in PA management; how to create economic opportunities for local communities such as jobs (direct or indirect); how to address grazing, land reclamation and other issues; provide input on draft management effectiveness evaluations (threats and status of biodiversity and draft management plans; and advice on best practices for engaging the communities in PA management activities. Provide input on resource-use protocols and agreements.

- Membership: The committee will engage approximately 10-15 members representing local communities inside and outside the protected areas. Members may represent NGOs, local government, business sector, etc. Half of the members should be women. At least one youth representative will be invited to participate.

- Mode of operation: It will be co-chaired by the PA Manager and a committee member. The PAMU will provide support to the committee. To encourage participation, a stipend will be provided to the members. The committee will meet quarterly, or more as needed.

This will include conducting a survey of local populations to identify their interests and opportunities for such things as those listed in the following activity.

While the Community Advisory Committee will be a key means toward improving local community engagement, other approaches will be necessary to gain widespread support (refer to output 2.1 regarding a CEPA Plan).

It is expected that the committee will become self-sustaining in the long term if the members can clearly see the value and importance of the work the committee undertakes (i.e., if the results are helpful for the participants, they will want the committee to continue). It is anticipated that the EEAA will financially support the operation of the committee if its value for the community and the PAs can be demonstrated.

Activity 2.1.1.4: Support community-based eco-tourism infrastructure developments, services, product development and product sales

This activity will enhance the economic benefits of biodiversity for local entrepreneurs. This activity will support the assessment of eco-tourism developments and activities within and adjacent to the protected areas. Eco-tourism is more suitable than mass tourism activities within PAs if planned properly. It will complement the plans and activities of the EIECP III project (i.e., the WRPA Integrated Eco-tourism and Development Plan) so that a coordinated approach will deliver specific intended benefits.

Through this activity, the following actions will be taken:

- The environmental education centre (this project) will be located at the WRPA main gate, which will be re-developed under the EIECP III project. This coordinated approach will enable direct benefits to location residents.

- Identify potential eco-tourism services by working with local communities, such as bird watching, canoeing, camel treks, camping, involving fishers during the closed fishing season in guiding people on recreational fishing, bird watching or sightseeing; use of solar boats, etc.).

- Identify opportunities for local product development and sales (e.g., locally-made handicrafts, medical and aromatic herbs, organic vegetables grown in the communities, fresh fish, etc.).

- Provide biological information to support interpretation and education activities and product development.

- Provide financial support for developing and marketing eco-tourism services and products. IUCN will work with communities in providing financial support through a tested and effective micro-finance scheme (e.g., as practiced in Jordan/Lebanon).

- Support training opportunities to improve product development and services. Opportunities to engage successful local entrepreneurs in training others will be implemented. Attendance at provincial, national or international venues may be considered.

- Interpreting the results of biological inventory, monitoring and research activities (per output 1.1.2) so that it can be used in Environmental Impact Assessment processes.

- Providing advice on the location of proposed developments and the type of activities that may negatively impact upon species and ecosystems.

- Providing information about the PA’s biodiversity to support sensitive and compatible  eco-adventure activities and awareness.

- Developing protocols to monitor development and operations of eco-tourism ventures to ensure protection of habitats and to guarantee that they are consistent with the long-term vision and management objectives of the PAs.

The Fayoum Tourism Association, established through the EIECP III project, will provide advice on priorities and approaches for encouraging the development of new opportunities and/or improving existing initiatives. EEAA will ensure that proposed developments are carefully evaluated through the Environmental Impact Assessment process and financially supported either through the co-finance sources or through partnership agreements with the private sector. especially with investors from local communities around the two PAs.

Output 2.1.2: Controls and monitoring programmes to conserve ecosystem services and reduce overharvesting by local communities within Wadi El-Rayan and Lake Qarun PAs developed and implemented.

The project will enable local stakeholders to participate actively in the sustainable management of the ecosystem goods and services on which they depend, such as water quality management, water conservation, grazing areas, sustainable management of fisheries, and conservation of scenic landscapes for ecotourism, through training and participatory management mechanisms.

Activity 2.1.2.1: Develop and implement regulations, resource-use protocols and agreements

Regulations, resource-use protocols and agreements will be developed -- with the participation of resource users, the Local Advisory Committee and governorate departments -- to specify best practice guidelines, detailed approaches, and agreements. Regulations and/or protocols will be developed for the following resource uses:

- Grazing within the protected area: who can access certain areas, when, for how long, etc.

- Use of chemical pesticides, fertilizers and other inputs for fish cage farming and agriculture.

- Site-specific protocols (for each of the two PAs) for waterfowl hunting to indicate species, timing, locations, etc.

Following local engagement, the Project Steering Committee (see section 4.3) will review and recommend such regulations and/or protocols for approval (e.g., by decree of the Governor).

The project will re-invigorate meetings between EEAA and the ministries of Agriculture & Land Reclamation, Water Resources & Irrigation and the Water Police concerning water use and levels, including:

- Developing agreements to reduce the level of extraction of water from the lakes.

- Convening regular meetings of relevant partners in order to present and discuss the results of the monitoring activities carried out by the PAMU.

- Controlling unsustainable practices such as the amount of pesticides and fertilizers used in agriculture.

To ensure sustainability, EEAA will cover most of the cost of this important activity through the co-finance contribution and will continue to support this activity after the end of the project as this activity is an effective mechanism to support the implementation of SDGs locally after it will be tested during this project.

Activity 2.1.2.2: Establish a resource user permit system

This activity will develop and test pilot system for issuing user permits within the two PAs to control and monitor utilisation of natural resources (fisheries, hunting, grazing, firewood collecting) in order to reduce pressure on biodiversity and ecosystem services. Under these permit systems, PA authorities will issue permits to local resource users based on ecosystem carrying capacities developed under output 1.1.2, while also taking into account traditional community norms and practices.

PA staff will then work with community leaders to monitor compliance with the permit conditions. In this way, local stakeholders will participate in both the setting of offtake levels, the creation of offtake monitoring guidelines and protocols, and the enforcement of harvesting guidelines. Detailed assessment of the permit systems will be carried out with the aim of establishing a model for potential replication throughout Egypt’s protected areas system. Establishing suitable regulatory supports will be implemented, as needed.

This activity is a good opportunity for mainstreaming biodiversity within the different sectors. EEAA will cover the whole cost of this activity as it is part of its role in Egypt. But the project will share the cost related to development of guidelines, online permits system, etc.

## Intervention logic and key assumptions

In many parts of the world, local use of natural resources is seen as a threat to the integrity and wellbeing of natural ecosystems. At the same time, conservation practices have impacted human well-being and at times have undermined local livelihoods, local knowledge, tenure and rights (McNeely and Mainka, 2009). In recent decades, there has been a shift toward enabling local sustainable use of natural resources through the participation of local communities. Accordingly, the Theory of Change model for this project recognizes that both natural values and human use values should be accounted for in addressing threats, barriers and solutions.

3.4.1 	Theory of change

The Theory of Change model (figure 7) emphasizes the project’s overall aim to secure the PAs, species, habitats and ecosystem services. The two PAs are in close proximity and share many of the same issues, barriers, challenges and solutions, as described in section 2.3 (figure 4). In general terms, a dichotomous situation exists: declining quality of the environment and increasing unsustainable use of resources. This situation is negatively impacting upon local peoples’ health and quality of life. Key drivers to harvest food and avoid poverty are adding to the stress on the environment through unsustainable levels of use, and as a result, negatively impacting upon the natural habitats and species of the PAs. Similarities in the two protected areas include:

- Natural values (wildlife, threatened species, habitats); important bird areas; fossil world heritage values.

- Threats (poaching, water quality and quantity, infrastructure development, increased access, unsustainable use of resources).

- Shared communities and resource users (fish farming, grazing, tourism, crop farmers).

- Low number of staff and consequent need for training and capacity building.

- A need for increased community involvement in protected areas and the management of the two sites is open for new innovative management arrangements and opportunities to realize the benefits of the PAs.

Similar management actions will be needed, resulting in cost savings through economies scales. Lessons learnt in one protected area will be very much appropriate for the other.

The Theory of Change illustrates the principle change processes that are predicated upon an engaged citizenry. Through meaningful forms of engagement, such as a Community Advisory Committee made up of equal numbers of women and men, and the Community-based Natural Resource Management (CBNRM) methods, the aim is to create an enabling environment for engagement and collaboration. In turn, this will support the design and delivery of the project activities and outputs. Three inter-locking change processes – participatory implementation, reliable technical information to support decision making, and sound management direction – will be the foundational elements for delivering the project’s primary outcomes (effective management, community participation, reduced unsustainable use), which in turn will lead to the mid-term impacts of the project, and ultimately to long-term impacts. Several assumptions are associated with the Theory of Change (next section), and performance indicators identified on the figure, are presented in the Results Framework (appendix 3).

3.4.2 	Key assumptions

The following assumptions are illustrated in the project’s Theory of Change (Figure 7).

A1. A key assumption is that community engagement will be welcomed by the community, that local communities have the capacity and interest to participate in protected area management activities, and that it will be effective in reducing threats on protected areas, ecosystems and species. Other countries have realized success with CBNRM approaches. It will require significant staff and community training to enable an effective process.

A2. It is assumed that government will actively support local engagement in protected area management. This requires an enabling environment, not only by EEAA but also by other ministries that have a stake in the work.

A3. It is assumed that government ministries will agree upon targets for sufficient water quantity and quality entering Lake Qarun and the Rayan Lakes (e.g., as part of management planning) to improve their overall health. Poor quality environment is a significant threat to human well-being, and a basic limiting factor toward realizing incremental improvements over time.

A4. It is assumed that government will provide active leadership and encourage wide involvement for establishing long term strategies (vision, goals, objectives, actions) for complex and potentially contentious issues. For example, developing strategies (for inclusion in the LQPA management plan) for the rehabilitation of Lake Qarun may require resolution of various issues pertaining to water quality, quantity and use, as well as recognition of costs and benefits. It is assumed that the development of such strategies will improve the likelihood of future implementation and enable future investments.

A5. It is assumed that the anticipated re-structuring of the NCS, pending passage of the current bill to establish a new General Authority for Protected Areas, will create a suitable, enabling environment for this project, and ensure long-term sustainability.

A6. It is assumed that related projects (EICEP III, UNDP-GEF financing project) will deliver their intended activities and that close cooperation with the proposed UN Environment GEF6 project will occur and reinforce the results.

A7. It is assumed that capacity building activities will be effective and lasting, and that staff turnover won’t undermine the overall advancement of capacity.

Figure 7. Theory of change.

3.4.3 	Gender aspects

While degradation of natural ecosystems has an impact on all rural residents, women have frequently suffered more than men from the loss of traditional access to natural resources, particularly as they often play a critical role in collecting wild foods and medicines and in ensuring household food security. In addition, despite their critical role in the management of natural resources, women have limited property rights to ensure their access to natural resources; gender disparity in access to and use of natural resources is a major contributor to poverty among women.

Human development indices provide an overall context for gender considerations in Egypt, as follows (UNDP, 2016):

- Egypt’s Human Development Index (HDI) value for 2015 is 0.691— which puts the country in the medium human development category, positioning it at 111 out of 188 countries and territories. (low values close to zero have high human development while higher values close to one have low human development)

- The female HDI value for Egypt is 0.640 in contrast with 0.724 for males, resulting in a Gender Development Index (GDI) value of 0.884, a medium level in comparison to other countries.

- Egypt has a Gender Inequality Index (GII) value of 0.565, ranking it 135 out of 159 countries in the 2015 index. In Egypt, 2.2 percent of parliamentary seats are held by women, and 54.5 percent of adult women have reached at least a secondary level of education compared to 68.2 percent of their male counterparts. Female participation in the labour market is 22.8 percent compared to 76.1 for men.

Female adult literacy in Egypt in 2013 was 67.18%, lagging behind adult literacy rate of 75.06%. Similarly, female youth literacy rate was 90.33%, lower than youth literacy at 92.02% (UNESCO, nd).

UNDP has stated that despite the visible progress to achieve the Millennium Development Goals (MDGs), Egypt has not reached the anticipated targets for poverty reduction, environment protection and gender equity. On the latter, while positive trends are beginning to emerge, Egypt is still working on issues related to gender equality and the empowerment of women (UNDP, 2018).

At the local level in rural villages nearby the PAs, women are primarily involved in the care of the household, agricultural production, and making handicrafts for the tourism sector. Some villages such as Tunis have skilled potters and crafts people who are benefiting from sales to tourists. Mousa and Kedra villages located in the land reclamation area within WRPA are focused on agriculture, though a women’s organization has operated in the past with some activity in kilim weaving and sewing, enabled through micro-financing. Training on handicraft making was carried out in these two villages in 2008 as part of the EIECP II project. In general though, a key challenge has been linking local production with potential markets. Other groups in Fayoum and the vicinity of the PAs are involved in other areas of skill building and environmental education (e.g., Fayoum Environmental Center).

Several groups have focused their efforts on creating a more enabling environment and on developing opportunities for women such as:

- UN Women Egypt has supported the establishment of the ﬁrst Professional Master in Gender and Development, which was launched in 2016 at the Faculty for Economic and Political Sciences (FEPS) at Cairo University. This two-year multi- and inter-disciplinary applied degree empowers students with the knowledge, critical analysis skills and practical competencies to engage with global, national and local development problems through a lens that is both gender and context sensitive (UN Women, 2016).

- Fayoum Agro-Organic Development Association, among many programmes, has been training girls and women on environmental handicrafts through a professional technical support team, improving their products and helping them in marketing (FAODA, nd). They have also focused training and development on organic farming.

- Fayoum Environmental Center conducts awareness raising about biodiversity in local schools, WRPA and LQPA. They have a significant involvement of women and youth in the organization and target skill building activities for women. The organization has 6 permanent staff (3 female), 10 part-time staff (6 female), 35 volunteers (30 female); 100 paying members for 50 LE first time membership and 20 LE/year after; about 50/50 male/female; Board of directors (5 with 3 female) (IUCN, 2018).

- Italian Agency for Development Cooperation has had a long-standing involvement in local projects that target rural women. The Egyptian-Italian Environmental Cooperation Programme (EIECP phase III) is addressing gender issues with specific targets and activities for business development that will include women. It is implementing training programmes for all members of the community particularly women (e.g., training on handicrafts, ecotourism guiding, food safety, packaging, labelling and pricing and developing the handcraft itself), as well as a training of trainers programme that has worked very well with women who are now training other members of their villages. Other Italian projects include: Empowering Women in Fayoum Rural Areas (EWFRA) (2017-20), Developing the Handicraft Skills and Enhancing the Economic Status of Women in Upper Egypt (WEE) (2013-17), and Building Rural Assets with Valuable Opportunities (BRAVO) (2012-16).

Project implementation will ensure that gender considerations are an integral part of all project activities, following CBD COP guidance. The project will ensure that targeted interventions tackle issues of concern to women, and indicators will be included in the project monitoring system to track the participation of women in project activities. Awareness raising and training with communities will be based on an analysis of the often-distinct roles and needs of women and men. This will be accomplished through the participation of women in all project activities, but particularly in forums where their voice must be heard (e.g., Local Community Advisory Committee and Scientific & Technical Advisory Committee). Design and implementation of activities will be carried out in close cooperation with the EIECP III.

Gender marking will measure the following data at the end of year 2 and at the end of the project:

- The number of women and men among the full-time project staff.

- The number of women and men that are project board members.

- The number of women and men who are employed in jobs created by the project.

## Risk analysis and risk management measures

A number of project risks identified at the PIF stage were reviewed, validated and updated during the PPG stage.

Table 6. Project risk matrix.

| # | Stage | Risks | Likelihood/ Severity* | Risk Management Measures |
| --- | --- | --- | --- | --- |
| 1 | PIF | Government resources (e.g. counterpart staff) and co-financing contributions are not forthcoming in a timely manner. | Low/ High | - Monitor. - The project assumes a six-month start-up phase (3 months hiring and 3 months inception period) to bring all staff, partners, and government agencies on board. Co-financing commitments with EEAA and other partners are presented in this proposal. |
| 2 | PIF | Change in leadership in relevant governmental bodies could cause delay in implementation of the project activities. | Low/ Medium | - Monitor. - The establishment of a Project Steering Committee (PSC) will ensure that the policy agreements reached during the Inception Phase remain in place, as the PSC will be tasked with developing and monitoring clear terms of reference for all project partnerships. - Communication and awareness efforts will ensure support and understanding for the project within relevant institutions. |
| 3 | PIF | Limited local expertise to lead and participate in project activities. | Medium/ High | - Actively monitor. - An international Technical Advisor (TA) will provide technical skills and support to the project team and its partners. However, since such external expertise is not sustainable over the long-term, the TA will be tasked with training and transferring knowledge to staff of the NCS, including its monitoring team. - The monitoring core team within NCS that will be established during the lifetime of the project will work with the international TA to ensure that training and knowledge transfer takes place in a comprehensive and timely manner. |
| 4 | PIF | Failure of government agencies to implement project activities or reach agreement or to resolve conflicts among different stakeholders. | Medium/ High | - Actively monitor. - The project will institute a collaborative management structure for decision-making and will strengthen policymaking, planning, monitoring, and enforcement functions of local authorities to enable them to fulfil their statutory responsibilities for environmental management. All relevant stakeholders will be involved from the start to create ownership and strengthen commitment to proposed changes and reforms. |
| 5 | PPG | Insufficient engagement of stakeholders, including women and youth. | Low/ Low | - Actively monitor and manage. - The project will implement a variety of engagement activities targeting specific groups that have direct or indirect influence on the success of management initiatives. - Close coordination between the two PAs and with other projects will enable a sensitive approach to engagement. |
| 6 | PPG | Cost of implementing plans and strategies may be pre-emptive (e.g., addressing pollution in Lake Qarun). | Medium/ High | - Actively monitor and manage. - The project will identify a range of options and solutions, with thorough analyses, that could be implemented in a sequential, coordinated manner. This would allow incremental improvements over time. |
| 7 | PPG | Data collected during the project is inadequately secured and not available for future use. | Medium/ High | - Actively monitor and manage. - The project will identify needs at the PA and national office (NCS) level and implement appropriate solutions. |

*Impact Likelihood/Severity:

- Low likelihood and low impact expected (Considered low priority in risk management)

- Low likelihood and high impact expected (Need to be monitored)

- High likelihood and low impact expected (Need to be monitored)

- High likelihood and high impact expected (Require extensive monitoring and management)

## Consistency with national priorities or plans

The project objective is grounded in key national policy and planning documents.

The project is consistent with Egypt’s National Biodiversity Strategy and Action Plan (NBSAP) 2015-2030, which is the principle policy document that drives biodiversity conservation in Egypt. In 2014, Egypt revised its NBSAP in line with the new CBD Strategic Plan for Biodiversity 2011–2020. After initial stocktaking and appraisal of the current status of national biodiversity and the underlying causes of biodiversity loss, six strategic goals were identified to address the decline in biodiversity and to achieve the Aichi Targets.

The revised NBSAP also calls for the further development of “the management and infrastructure of the protected area network, including the development and implementation of management plans. These plans should address the integration and development needs of local communities, the sustainable utilization of the resources which they contain, [and] the potential for eco-tourism”.

The project will help Egypt to achieve the NBSAP’s Strategic Goal 1: “Conserve and manage terrestrial and aquatic biodiversity to ensure sustainable use and equitable benefits to the people”, by supporting the following targets under this strategic goal:

- By 2030, PAs network secured and expanded to cover 17% of total terrestrial and inland water and at least 5% of coastal and marine representative areas, especially priority sites of particular importance for biodiversity and key ecological processes and effective management of PAs.

- By 2020, develop and implement unified Egyptian methodology for the identification and monitoring of priority components of biodiversity, according to the international standards, to ensure the maintenance or rehabilitation of 50% of our most threatened species, focusing on mammals and reptiles to a favourable conservation status.

- By 2030, national conservation and/or rehabilitation programmes of the largest part of threatened species and endemic species at risk are developed and implemented with measures to evaluate its implementation.

- By 2020, all invasive alien species (IAS) and pathways are identified and prioritized with measures in place to update and verify these pathways, in addition to development of national programmes to control and manage IAS.

The project is also consistent with Egypt’s National Development Plan (NDP) as it will enhance the sustainability of development activities within and around protected areas, and will support the need to balance economic growth with biodiversity conservation considerations and to address trade-offs between economic development and ecosystem resilience.

The project is consistent with Egypt’s Water Policy (2010) of the Ministry of Water and Irrigation,  includes the following key priorities: improving the efficiency of the present use of the water resources; and, protecting the environment and reducing water related health hazards.

## Incremental cost reasoning

The table below summarises the environmental and other incremental benefits.

Table 7. Incremental cost reasoning.

| Baseline Scenario (business as usual) | Alternative Scenario (what the GEF project will contribute) | Key Benefits (outcomes expected with alternative scenario) |  |
| --- | --- | --- | --- |
| Component 1: Strengthen management capacities of targeted PAs for the conservation and sustainable use of endangered ecosystems and species. |  |  |  |
| - Management planning instruments are either outdated or non-existent resulting in uncoordinated development and little regulation. - Existing planning instruments were developed without the participation of local communities and other stakeholders. |  | - Management instruments will be developed jointly between protected areas and local stakeholders resulting in a local buy-in, support and champions for the implementation of such plans. - Management direction will be current and relevant. | - Increased financing for the protected areas and less costs as a result of local support and less enforcement due to this support. - Less habitat loss of threatened species and IBA trigger species. - Improved PA management effectiveness indicated through METT scores. |
| - Adjustment of boundaries of two protected areas through the updating of the PA Law (Law 102/1983) with no or limited information on the two PAs and its ecology and the species that use it as habitat. |  | - Informed decision making through community engagement and improved monitoring systems to address threats to the biodiversity of the PAs will inform the expansion of the boundaries of the PAs. | - Reduced habitat loss of threatened species and IBA trigger species. |
| - Fragmented data/information (e.g. Earth Observation) that is not channelled/coordinated and available for use in PA management decision making. |  | - Strengthened systems for monitoring and early warning of external threats with a specific focus of improving water quality | - Improved PA management effectiveness indicated through METT scores. - Increased water quality result in improved ecosystem health and human health. |
| - Fragmented and mostly absent information/data on key ecosystem and threatened and important species in the target PAs. - Different PAs use different criteria to set up monitoring systems in PAs and many systems not geared to address threats to the ecosystem or species |  | - An information management system is in place to ensure proper storage of monitoring data and enable use of data in decision-making. - Agreed indicator species to monitor in target PA in order to measure outcome improvement in PA management. - Monitoring programs established for endangered species and ecosystems. - Standard criteria for Egyptian biodiversity monitoring programs. | - Outcome evidence of increase in PA management effectiveness. - Improved monitoring of endangered species and habitat/ecosystems resulting in action to address threats. - Data from monitoring is meaningful and can be used for decision-making at various levels of the management hierarchy. |
| Component 2: Establish effective community participation in PA management and conservation/management of natural resources |  |  |  |
| - PA management is considered as the exclusive responsibility of the PA Management and therefore little coordination with communities and sectors that are influencing the successful management of the PAs. - PA management is not linked to areas adjacent to the PA, although many of the habitats and services provided are outside or are provided from areas outside the PAs. |  | - Platforms for coordination and linkage among stakeholders are established. - Strengthened cooperation between PA authorities and local communities on enforcement activities. - Planning, management and monitoring instruments address both the PAs themselves and the surrounding areas. | - Reduced threats from outside the PAs on the threatened biodiversity and IBA trigger species and their habitats. - Increase of area of habitats of the threatened and IBA trigger species as a result of including management of areas outside PAs as part of the management responsibility. |
| - Little awareness of the potential benefits of PAs and low support from the community and local stakeholders for the management of the PAs. |  | - Increased participation in citizen monitoring and enforcement resulting in greater local commitment. - Enhanced and targeted awareness activities. | - Enhanced local understanding of the benefits of protected areas and of the opportunities. - Greater community engagement and support for the PAs. |
| - Communities either overharvest or harvest the natural resources illegally for which they are prosecuted, resulting in unsustainable practices and reduced ecosystem services for all. |  | - Permit systems established in the two PAs, with the involvement of local communities, to control and monitor utilisation of the natural resources (fisheries, hunting, grazing, firewood collection) with the full involvement of local communities. | - Increased positive attitude of the local community towards the PA management and appreciation of the PAs. - Increased citizen monitoring and enforcement. - Reduced threats due to sustainable utilisation of natural resources by communities and local stakeholders. |

3.7.1 	Scenario without GEF involvement

Natural desert ecosystems in Egypt are under severe pressure.  During the last 25 years, about 40% of plant species in desert ecosystems became extinct as a result of overexploitation for food and medicine, while drought and unregulated hunting activities during the last 60 years have resulted in the extirpation of numerous faunal species, including four of Egypt’s six species of gazelle (Mountain Gazelle (Gazella gazella), Scimitar-Horned Oryx (Oryx dammah), Addax (Addax nasomaculatus) and Bubal Hartebeast (Alcelaphus buselaphus)).

Today, even those species that remain -- the Dorcas Gazelle (Gazella dorcas) and Slender-horned Gazelle (Gazella leptoceros) -- are threatened with extinction due to the contraction of their ranges.

Bird populations at IBAs face excessive mortality and disturbance due to unregulated hunting for sport, food and supplementary income, as well as improper pest control practices.

Protected areas are one important mechanism for conserving desert ecosystems and the biodiversity they harbour, and for several decades national and foreign donor-supported projects, including projects by the EU, USAID, Italian Cooperation, UNDP/GEF and World Bank/GEF, have worked on protected areas issues in Egypt. However, while these projects have succeeded in helping Egypt to establish new PA units, in general they have not succeeded in creating PAs that are effectively managed over the long-term.  In part this is a problem of insufficient financing, and projects are now underway to improve PA financing frameworks. However, financial resources are likely to remain very limited for the foreseeable future, in particular if local/regional stakeholders are not invested in or participating in actions to support the management of PA units.

In addition, local support and partnering on PA regulations and monitoring and enforcement will remain low, and communities within and adjacent to PA sites will continue to engage in unsustainable resource uses and actions that damage ecosystem services.

Thus, in the absence of the proposed GEF project, Egypt will continue to lack demonstrated models of PAs that have sufficient resources, capacities, and partnerships for effective management of endangered ecosystems and species; as a result the status of desert ecosystems and biodiversity will continue to decline.

3.7.2 	Scenario with GEF involvement

The project will build on existing initiatives at two PA sites in Egypt to conserve globally significant biodiversity by strengthening the capacities of PA management and staff and by demonstrating the potential for participatory community management as a strategy for strengthening the management of protected areas (i.e., by getting local stakeholders to participate in PA planning and become more invested in the success of PAs, to support monitoring and enforcement efforts to conserve biodiversity and protect ecosystem services and resource, to reduce over-use of natural resources and destructive resource use practices within PAs and also in adjoining areas where such activities might negatively impact PAs, etc.).

In so doing, the project will provide Egypt with demonstrations of the efficacy of participatory PA management that can serve as a model for other protected areas in the country. At the same time, the project will have helped the EEAA to reduce the current level of threats to the desert ecosystems and species at the Wadi El Rayan and Lake Qarun protected areas, and thereby offer better protection to globally threatened species listed in IUCN Red Data List. The project will play the role of catalyst for bringing the existing baseline activities and information together in a well-directed and forward-looking plan and monitoring system that focuses on improving the management effectiveness of the PAs and the capacity to implement the management plans.

At present, the livelihoods of most of the members of the communities located in the project’s target areas are dominated by primary production for subsistence: in terrestrial areas, principally the production of maize, beans and smaller amounts of a number of other crops, fishing for both local consumption and sale. In both cases, the production systems are characterised by limited technologies and marketing and, consequently, low productivity and profitability. The implementation of programmes for the conservation and sustainable management of threatened species has the potential to generate direct and indirect income for local communities, such as: establishment of businesses based on ecotourism and associated services; employment as guides, provision of accommodation and catering services for tourists. Such activities are expected to lessen the threats on endangered species and their habitats that are currently associated with agricultural and fishing practices).

## Sustainability

The Government of Egypt is currently developing a new organization—the General Authority for the Protected Areas of Egypt; legislation is currently progressing through the parliamentary process. The new authority will have the institutional tools to improve revenue generation and revenue retention, for re-investment in the country’s PAs. The sustainability of the project interventions will be assured through this new structure.

At the national level, the project will raise awareness in government and other decision makers on the importance of conserving the two protected areas and their wildlife, thereby increasing their support for additional funding for conservation and for mainstreaming conservation objectives across all branches of government, including in particular Finance, Tourism, and Planning and Natural Resource Management.

The overall sustainability of the project results will be supported by embedding capacity into the institutions and entities that need and can make good use of strengthened abilities and resources. Capacity building will strengthen the on-going ability of EEAA and NCS with jurisdiction over species and their habitats, and of rural communities dependent on natural resources for their livelihoods, to continue to carry out activities that can benefit wildlife and ecosystem services.

Developing effective PA management frameworks, building good policies, strong legislation and the capacity to implement them will establish the enabling environment for protecting the Wadi El-Rayan and Lake Qarun PAs and their critical ecosystems and endangered species.

Securing alternative development pathways that rely on a resilient and healthy environment (clean water, wildlife stocks) that benefits communities will reduce the incentives for rural populations to engage in illegal wildlife hunting or destructive ecosystem management practices.

The project will seek to create stable situations on the ground where there is participatory monitoring and enforcement carried out in partnership with local communities so that the mechanisms and capacities for such activities are embedded not just in PA staff but also among local stakeholders, thereby reducing the need for long-term financing of such actions.

In addition, the project activities to establish conservation-compatible activities that generate local benefits will provide incentives for local stakeholders to support conservation over the long-term.

## Replication

3.9.1 	Scaling up

The project will identify important best practices and lessons learned that can be of value to all key stakeholders, specifically national decision makers in the EEAA and NCS and the Governorates in the project area, as well as important development actors in the country. These best practices and lessons learned will be documented; the project team will prepare guidelines for facilitating the wider replication and “up-scaling” of results from the project; and UN Environment will provide a format and assist the team in categorizing, documenting and reporting on lessons learned.  Subsequently, the project will make systematic efforts for the dissemination of lessons learned both within and beyond the project intervention zone, utilizing a number of existing information sharing networks and forums, publications in written and digital format, dissemination workshops and cross-fertilization activities. In addition, the project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation through lessons learned.

The proposed project will address capacity building for EEAA and PA management staff on managing information systems for PA monitoring, poaching and illegal hunting, as well as training on PA management for staff at the targeted PA sites, which together will allow for best practices and lessons learned to be widely up-scaled to overall national wildlife protection operations and throughout the national protected area system.

Training of local communities within and adjacent to the targeted PA sites in wildlife protection and community co-management processes will be crucial for developing models that can be replicated elsewhere in the country, and replication of lessons and best practices may be enabled in areas such as monitoring, enforcement, ecotourism and other biodiversity-compatible livelihood opportunities. International exchanges with other countries practicing Community Based Natural Resource Management will be used to further strengthen skills in these technical areas among stakeholders at the targeted PA sites, who can then provide peer training to their colleagues at other sites in Egypt.

UN Environment-ROWA will also facilitate the regional upscaling of lessons / models from Egypt’s protected areas network through its established mechanisms within the League of Arab States and its biodiversity ministerial fora, and through the coherent implementation of biodiversity-related MEAs and promotion of synergies amongst CBD, CMS, Ramsar, WHC and CITES.  UN Environment’s Task Manager will provide advice and support in this respect, including connecting the right people to enable information sharing.

Similarly, linkages will be made to other GEF projects in the region that are carrying out similar work, such as Initial Steps for the Establishment of the National Protected Areas Network in Iraq (PAN Iraq). The PAN Iraq project is dealing with a number of similar activities that would strengthen the execution of this project and enhance lesson learnt, and also assist in upscaling the lessons on protected areas conservation to other countries in the region. Examples of PAN Iraq initiatives that are relevant to this project, include:

- Capacity building, training needs analysis.

- Site-specific baseline ecological and land-use surveys and data collection through ground surveys and remote sensing.

- Institutional set-up and supporting legal framework. Recent KBA studies, as well as experience and best practice on Protected Areas management.

- Infrastructure, staff, equipment and outline management plans.

- Public awareness and outreach activities.

3.9.2 	Innovation

Development of PA management frameworks that include participatory approaches is not yet a widespread practice in Egypt and the associated methodologies will be applied for the first time. The project will catalyse different innovations that can be deployed at other sites, such as: integrating management effectiveness evaluations with management planning processes; and, identifying consensus indicators to measure success in conserving wildlife populations and ecosystem services). The equipment, devices and intervention strategies that are proposed for adoption by the EEAA and at the site level are innovations in the national context. For example, drone monitoring will be considered and is not yet a recognised PA monitoring option in Egypt. Innovation will also be infused in the training and capacity building methods that the project will promote.

## Public awareness, communications and mainstreaming strategy

Capturing and sharing knowledge and lessons learned will constitute an important element of the project and an essential way to ensure sustainability and replicability of project achievements.

A Communications, Education and Public Awareness (CEPA) Plan will be prepared for the project to coordinate the CEPA objectives, target audiences (including women and youth), methods of delivery, costs, and means for assessing effectiveness of CEPA activities (refer to section 3.2, output 2.1.1).

## Environmental and social safeguards

During the PPG phase, potential environmental and social impacts were examined in accordance with UN Environment’s ESERN procedure (Appendix 16).

No specific environmental concerns were raised for the project. Gender and youth engagement were identified as requiring more attention. Accordingly, specific actions have been included in the proposed activities (section 3.3).

# Section 4. Institutional Framework and Implementation Arrangements

This section provides a description of the project’s implementation, execution, governance, and relevant actors and their responsibilities.  Appendices 10 and 11 provide further details of specific roles and responsibilities.

The Egyptian Environmental Affairs Agency (EEAA) is the host agency for the project and its primary body, the Nature Conservation Sector (NCS) is responsible for PA management and the conservation of biodiversity, and thus will play the lead governmental role in implementing the project.

Figure 8. Project governance.

## 4.1. 	Implementation and execution

4.1.1 	Implementing agency-UN Environment

UN Environment is the implementing agency. Overall project supervision will be the responsibility of UN Environment, with UN Environment’s Task Manager providing support and working closely with the IUCN ROWA.  The Task Manager, located in Nairobi, Kenya, will ensure consistency with GEF and UN Environment policies and procedures. Operational oversight will include ensuring that the project practices due diligence with regard to Environmental, Social and Economic Review Note (ESERN). UN Environment will also have representation on the Project Steering Committee (PSC).

- Project supervision missions by the Task Manager will be described in the project supervision plan, which will be developed. UN Environment will also report to the GEF Secretariat on progress against milestones outlined in the CEO ER, as well as inform the GEF Secretariat of any substantive changes in co-financing that could impact on the project objectives, scope, conformity with GEF criteria, outcome of the project, or likelihood of project success. UN Environment will also be responsible for the following:

- Submitting the overall annual Project Implementation Review (PIR) to the GEF Secretariat and Evaluation Office, which will include an annual rating of the project in terms of progress toward meeting project objectives, project implementation progress, risk, quality of project monitoring and evaluation.

- Arranging for the independent terminal evaluation by the Evaluation Office and submit the evaluation report to the GEF Evaluation Office.

- Managing and disbursing GEF funds in accordance with rules and procedures of UN Environment.

- Linking the project activities to the ongoing regional upscaling of PAs networks in the Arab Region, and promoting synergies among biodiversity related MEAs and SDGs at the global, national and PA levels.

- Supporting the capacity building of the PAs staff through specialized training programs (e.g. ecosystem based-management tools, Aichi targets, etc.).

4.1.2 	Executing agency-IUCN ROWA

The International Union for the Conservation of Nature’s (IUCN) Regional Office for West Asia (ROWA) will serve as the executing agency for the project, and as such will work closely with the NCS and PMU to deliver the project. IUCN ROWA’s mandate is to oversee the execution of the project, and to work supportively and collaboratively with project stakeholders and partners, which include NGOs and governments, to achieve a new paradigm for sustainable development based on the concept of people-cantered development. One of the many IUCN ROWA strengths is its ability to catalyse policy.

The key responsibilities include the following:

- Oversee project implementation and manage agreements with the partners in coordination with the NCS.

- Work closely with NCS in ensuring effective oversight of the project and the Project Management Unit (PMU), including collaborating with NCS on hiring and supervising the project manager.

- Provide scientific and technical support to the project, including expertise in PA management planning and management effectiveness; biological monitoring, compliance monitoring and enforcement, etc.

- Promote and ensure the integration of cross-cutting issues such as gender mainstreaming. This is a recognized challenge since environmental priorities are intimately associated with poverty, equity, security and conflict. Therefore, implanting and mainstreaming conservation efforts with the development agenda is essential.

- Share critical conservation knowledge with all stakeholders and partners and focus on providing services that bring added value to the activities.

- Provide administrative, logistical and financial management support to the project.

- Recruit and administer international and national consultants for specific tasks foreseen in the project.

- Procure goods and services, travel arrangements and other miscellaneous support as required by the PMU.

Following endorsement of the project by the GEF CEO to UNEP and before the start of the project, an executing agency agreement will be signed between UNEP and IUCN, through its Regional Office in West Asia (ROWA).

## 4.2. 	Project management and technical support

4.2.1 	Project Management Unit (PMU)

A Project Management Unit (PMU) will be established with three positions: a National Project Manager, Technical Programme Assistant, and an Accountant/administrator Officer. They will be recruited nationally and will plan and execute the project (Appendix 11 provides the reporting relationships and Terms of Reference for project personnel). The PMU will work closely with IUCN ROWA, NCS the Protected Area Management Unit (PAMU) in Fayoum.

The PMU will be responsible for overall implementation of the project, including the following:

- Managing project execution according to the agreed workplan, budget and reporting tasks and close cooperation with NCS (on behalf of EEAA) and IUCN ROWA.

- Organizing the project steering committee meetings and act as the Secretariat for the steering committee.

- Developing the annual workplans and budgets.

- Recruiting and managing international and national consultants through IUCN ROWA.

- Conducting national level training, participatory planning, stakeholder engagement and other activities in the project.

- Coordinating activities with the other complementary projects underway in the protected areas (EIECP III, UNDP GEF finance project) and take precaution to avoid over-extending local community participation. A coordinated approach will help to alleviate this and be more efficient.

- Compiling and submitting progress, financial and audit reports.

- Supporting a mid-term review of the project (in accordance with UN Environment procedures, a mid-term review may be undertaken for medium-sized projects, as opposed to a formal external evaluation that is required for full-size projects).

- Serving as the Secretariat to the PSC.

- Ensuring execution and all technical aspects of project implementation implemented according to the workplan and budget.

4.2.2 	Protected Area Management Unit (PAMU)

A combined PAMU for the two protected areas has the primary responsibility, as a governmental unit, to carry out day to day operations and management of the PAs. The key responsibilities include:

- Working closely with the PMU, to ensure project activities are appropriately scoped and tailored for the needs of the PAs and greatest impact.

- Maintaining close contact and liaison with local communities, local government officials and departments in the Fayoum and Giza Governorates. This lead role aims to ensure long term sustainability of the relationships and processes established during the project.

- Leading certain project activities (e.g., public involvement processes) and/or participating in the delivery of the project to ensure the capacity of PA staff is improved.

- Participating in the PSC.

- Co-chairing the Local Community Advisory Committee.

- Ensuring that project investments are efficiently and effectively deployed for the optimum and long-term benefit of the PAs.

## 4.3.	 Project steering committee

The project steering committee (PSC) will provide overall guidance, strategic direction and oversight to project management. The PSC will be multi-disciplinary and multi-sectoral in fields related to sustainable use of natural resources and protected area management.

Member institutions/offices will be requested to nominate individuals that will be members of the PSC. The PSC will be formally launched during the project inception meeting. The PSC will meet annually thereafter, or more as required.

The PSC will be made up of representatives of the following:

- The CEO of the EEAA will chair the PSC.

- Director of Biodiversity, EEAA.

- Director of NCS, EEAA.

- Partner national institutions that have a direct role in sustainable use of natural resources (i.e., Ministry of Agriculture and Land Reclamation; Ministry of Water and Irrigation, Fayoum Tourism Authority).

- UN Environment, the implementation agency.

- IUCN-ROWA, the executing agency.

- Co-financiers of the project (i.e., Italian Development Cooperation, CEDARE).

- The co-chair of the Community Advisory Committee.

- The PA Manager (PAMU).

- The Project Manager (PMU) as the Secretariat.

The main responsibilities of PSC will include:

- Acting as the project advisory board.

- Reviewing annual project workplans and budget.

- Monitoring project progress and delivery.

- Linking the project with strategic opportunities national, regionally and globally.

- Identifying and promote opportunities that will enable the success of the project.

- Reviewing and recommending protocols for approval (e.g., by decree of the Governor).

# Section 5. Stakeholder participation

Table 8 below gives a detailed description of the roles of stakeholders. Local community involvement and full participation in the design of site level components on PA management, species conservation, sustainable resources uses, etc. of this project is critical and is an important sustainability trigger for the project as a whole. The Community Advisory Committee (output 2.1.1 and section 4) and emphasis on local community engagement, underlines the importance of this aspect.

Private companies are important users of natural resources and a key partner for local communities to generate income and employment opportunities, and they will be consulted intensively during implementation of the project. Similarly, local resource users and government departments play a critical role in environmental sustainability and will be involved.

Table 8. Roles and responsibilities in project implementation.

| Organizations | Role in the project |
| --- | --- |
| Government |  |
| Egyptian Environmental Affairs Agency (EEAA) | EEAA will be responsible for coordination with the other line ministries and public administration bodies, as well as with the agencies and authorities under them. EEAA is responsible for developing project activities related to policies and laws on biodiversity conservation and wildlife management. |
| Nature Conservation Sector (NCS) | NCS will design project activities related to policy / regulatory changes to ensure compliance with habitat and species protection legislation, and all issues related to biodiversity conservation within the broader landscape. |
| Ministry of Agriculture and Land Reclamation | This ministry will ensure activities are aligned with national priorities and investments. They will be called up to offer their expertise on best management practices that focus on conservation practices and pollution prevention. The Desert Research Centre and Agricultural Research Center will be called up to offer their expertise on best management practices that focus on conservation, livestock, crops and pollution prevention. |
| Ministry of Water Resources & Irrigation | This ministry will assist the project by ensuring activities are aligned with national priorities and investments. They will be called up to offer their expertise on best management practices that focus on conservation practices and pollution prevention. The Water Research Institute will be asked to set baselines and targets for indicators for Qarun and Rayan lakes. |
| Tourism Department | This ministry will assist the project by ensuring activities are aligned with national priorities and investments. They will be called up to offer their expertise. |
| Fayoum Governor and Governorate | The involvement of the Governor and the Governorate authorities in Fayoum will be crucial in light of their local relationships. The Governor will be briefed periodically and asked to approve the protocols and instruments developed under the project. The Governorate authorities associated with the ministries (above) will bring their knowledge and experience to the design and implementation of projects. The following ministry authorities will play a key role: The General Authority for Rehabilitation Projects & Agricultural Development will work closely with local farmers (e.g., establishing drip irrigation rules for the reclaimed areas). The General Authority for Development of Fish Resources will bring forward technical information and experience pertaining to fisheries management. They should provide guidance on the development of best management practices, protocols and regulations, giving consideration to the FAO Code of Conduct for Responsible Fisheries (CCRF) and the FAO-Voluntary Guidelines on Small Scale Fisheries (VGSSF). The Fayoum Tourism Authority will bring forward their experience in marketing and operation of eco-tourism facilities to aid in the design of project activities. |
| Water and Environmental Police | The police will bring forward technical information and experience pertaining to compliance monitoring and enforcement. They should provide guidance on the development of protocols and regulations. |
| Security Department | The Security Department will bring forward technical information and experience pertaining to compliance monitoring and enforcement. They should provide guidance on the development of protocols and regulations. |
| NGOs + Academic Organizations |  |
| Academic Institutions | Some universities will assist the project design and implementation by providing data through research and outreach activities. |
| IUCN/ROWA | IUCN ROWA's role is to implement the activities and coordinate with the project partners. They will oversee implementation of the project and the PMU, including supervising the project manager. A focus will include cross cutting issues such as gender mainstreaming and natural resource management. |
| UN Environment | UN Environment/ROWA’s role is to link the project activities to the ongoing regional upscaling of PAs network in the Arab Region. UN Environment/ROWA will ensure the synergies among biodiversity related MEAs and SDGs at both national and PA’s levels. UN Environment/ROWA will work to improve the capacity building of the PAs staff through specialized training programs (e.g. ecosystem based-management tools – Aichi targets – etc.). |
| Centre for Environment and Development for the Arab Region and Europe – CEDARE | CEDARE will invest USD 1.5 million in support of the two protected areas in building the capacities of park management in Earth Observation (EO), modelling and in data exploitation. With the regional experience, the park management will be provided access and engagement with the complete ecosystem of EO stakeholders. During the project CEDARE will focus on promoting the uptake of EO services which are relevant to climate change and improved food security and water resources development. CEDARE will also raise local communities’ awareness on environmental issues and support rangeland management in areas in or adjacent to the PAs during the project period. |
| Nature Conservation Egypt | NCE will be called upon to provide advice on approaches to conservation. This national-level Egyptian NGO is focused on promoting biodiversity conservation and appreciation of nature, and lobbying government on conservation issues. A member of NCE works locally in Fayoum as a volunteer (informal group called Egyptian Association for Bird Protection) to promote awareness of hunting rules and no-hunting areas. |
| Fayoum Environmental Center | This local Fayoum city-based NGO focuses on community development, women and youth training. They conduct skill development training and environmental awareness through online and in-situ activities in schools and communities. |
| Message (Resala) | This local youth NGO focuses on engaging youth and getting the environmental message out. |
| Communities, Businesses |  |
| Local communities and resource users | Local community involvement of local governments, farmers, fish farmers and others will be part of the solutions for issues related to irrigation, runoff, pollution, grazing, etc. Communities include: - Mousa and Kedra villages located in the land reclamation area within WRPA nearby the El Ayoun (Springs Oasis). A women’s organization has operated in the past and will be included. - Shakshouk Village, the largest in the local area with about 14,000 residents. - Yoseph Sadeek and Tunis villages, among many others. |
| Private businesses (e.g. tourism companies) | Private companies are important users of natural resources and a key partner for local communities to generate income and employment opportunities. Local and national companies involved in serving the tourism industry should be part of the solutions for issues related to protocols, limits, regulations, etc. pertaining to tourism visitors, (e.g., hotels, tour guides, etc.). |
| Secondary stakeholders | The media and donor agencies that support activities are important secondary stakeholders. They will be involved in the project as opportunities arise. |

# Section 6. Monitoring and evaluation Plan

The project will follow UN Environment standard monitoring, reporting and evaluation processes and procedures. Substantive and financial project reporting requirements are summarized in Appendix 8. Reporting requirements and templates are an integral part of the UN Environment legal instrument to be signed by the executing agency and UN Environment.

The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework (Appendix 3) includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables and benchmarks included in Appendix 6 will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are summarized in Appendix 6. Other M&E related costs are also presented in the Costed M&E Plan and are fully integrated in the overall project budget.

The M&E plan will be reviewed and revised as necessary during the project inception workshop to ensure project stakeholders understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Day-to-day project monitoring is the responsibility of the project management team but other project partners will have responsibilities to collect specific information to track the indicators. It is the responsibility of the Project Manager to inform UN Environment of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

The project Steering Committee will receive periodic reports on progress and will make recommendations to UN Environment concerning the need to revise any aspects of the Results Framework or the M&E plan. Project oversight to ensure that the project meets UN Environment and GEF policies and procedures is the responsibility to the Task Manager in UN Environment-GEF. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of scientific and technical outputs and publications.

Baseline data gaps will be addressed during the first year of project implementation.

Project supervision will take an adaptive management approach. The Task Manager will develop a project supervision plan at the inception of the project, which will be communicated to the project partners during the inception workshop. The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring. Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed with the Steering Committee at agreed intervals. Project risks and assumptions will be regularly monitored both by project partners and UN Environment. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

In-line with UN Environment Evaluation Policy and the GEF’s Monitoring and Evaluation Policy the project will be subject to a Terminal Evaluation. Additionally, a Mid-Term Review will be commissioned and launched by the Project Manager before the project reaches its mid-point. If project is rated as being at risk, a Mid-Term Evaluation will be conducted by the Evaluation Office instead of a MTR.

The Evaluation Office will be responsible for the Terminal Evaluation (TE) and will liaise with the Task Manager and Executing Agency(ies) throughout the process. The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. It will have two primary purposes: (i) to provide evidence of results to meet accountability requirements, and (ii) to promote learning, feedback, and knowledge sharing through results and lessons learned among UN Environment, the GEF, executing partners and other stakeholders. The direct costs of the evaluation will be charged against the project evaluation budget. The Terminal Evaluation will be initiated no earlier than six months prior to the operational completion of project activities and, if a follow-on phase of the project is envisaged, should be completed prior to completion of the project and the submission of the follow-on proposal. Terminal Evaluations must be initiated no later than six months after operational completion

The draft Terminal Evaluation report will be sent by the Evaluation Office to project stakeholders for comments. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six-point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the report is finalised and further reviewed by the GEF Independent Evaluation Office upon submission. The evaluation report will be publicly disclosed and may be followed by a recommendation compliance process.

The GEF tracking tools are found in Appendix 15. These will be updated at mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. As mentioned above the mid-term and terminal evaluation will verify the information of the tracking tool.

# Section 7. Project Financing and Budget

## 7.1 	Overall project budget

The overall budget over the 3-year project period amounts to USD 9,819,864, comprising USD 1,319,864 from GEF and USD 8,500,000 from co-financing. Details of the budget according to UN Environment budget lines are contained in Appendix 1 (GEF budget) and Appendix 2 (co-finance budget).

Table 9: Summary GEF budget for project implementation by component.

| Component | Amount (USD) |
| --- | --- |
| Component 1 | 559,940 |
| Component 2 | 659,924 |
| PMC | 100,000 |
| TOTAL Project Cost | 1,319,864 |

Table 10: Summary of GEF budget for project implementation by year.

| Year | Amount (USD) |
| --- | --- |
| Year 1 | 333,353 |
| Year 2 | 502,866 |
| Year 3 | 483,644 |
| TOTAL | 1,319,864 |

## 7.2 	Project co-financing

A total of USD 8,500,000 is committed as co-financing. Of this, USD 1,200,000 is in cash and USD 7,300,000 is in-kind. The breakdown per project component is provided in Appendix 1.

Table 11: Summary of total project co-financing partners and amounts committed.

| Co-financing Partner | Cash (USD) | In-kind (USD) | Total (USD) |
| --- | --- | --- | --- |
| EEAA | 1,200,000 | 2,000,000 | 3,200,000 |
| IUCN-ROWA |  | 300,000 | 300,000 |
| Italian Development Cooperation |  | 2,000,000 | 2,000,000 |
| CEDARE |  | 3,000,000 | 3,000,000 |
| TOTAL | 1,200,000 | 7,300,000 | 8,500,000 |

A further breakdown of the co-financing commitments by component is shown below. Refer to Appendix 2 for details.

Table 12: Co-financing by source and component in USD.

| Co-financing source | Cash (USD) | In-kind (USD) | Total (USD) |
| --- | --- | --- | --- |
| Component 1 |  |  |  |
| Egyptian Environmental Affairs Agency | 292,200 | 255,000 | 547,200 |
| IUCN-Regional Office for West Asia |  | 220,000 | 220,000 |
| Centre for Environment and Development for the Arab Region and Europe – CEDARE |  | 1,200,000 | 1,200,000 |
| Sub-total | 292,200 | 1,675,000 | 1,967,200 |
| Component 2 |  |  |  |
| Egyptian Environmental Affairs Agency | 907,800 | 1,745,000 | 2,652,800 |
| IUCN-Regional Office for West Asia |  | 80,000 | 80,000 |
| Centre for Environment and Development for the Arab Region and Europe – CEDARE |  | 1,800,000 | 1,800,000 |
| Italian Development Cooperation |  | 2,000,000 | 2,000,000 |
| Sub-total | 907,800 | 5,625,000 | 6,532,800 |
| TOTAL | 1,200,000 | 7,300,000 | 8,500,000 |

* includes PMC costs

## 7.3 	Project cost-effectiveness

The co-financing arrangements by the Government of Egypt and other partners demonstrates a commitment toward achieving the project goals.

Two projects underway—EICEP III and UNDP-GEF finance project, provide mutually re-enforcing and complementary outcomes.

The two protected areas in this project are nearby and share many similarities in their operating context, such as: shared local communities, similar natural values and human-use values, similar threats and challenges, etc. Specific actions are proposed to ensure efficiencies.

The project seeks to improve the overall health of ecosystems and their services inside and outside of the protected areas. It focuses on delivering a cohesive suite of activities and outputs that provide the enabling environment for improvements, including: community engagement, clear plans and strategies, capacity, regulations and protocols, and wide public awareness and support.

It will provide a foundation upon which to further invest in healthy ecosystems.

## References

Abdel-Satar and Goher. 2010. Recent Environmental Changes in Water and Sediment Quality at Lake Qarun, Egypt. Journal of Fisheries and Aquatic Sciences. National Institute of Oceanography and Fisheries.

Abdelwahab A. AFEFE, El-Bialy E. HATAB, Mohamed S. ABBAS, El-Sayed I. GABER. 2016.  Assessment of Threats to Vegetation Cover in Wadi El Rayan Protected Area, Western Desert, Egypt. International Journal of Conservation Science, Volume 7, Issue 3, July-September 2016: 691-708.

Abdelhaleem, Fahmy S., Ahmed M. El-Belasy, Entessar A. El-Ghoreb. 2013. Managing Water and Salt Balance of  Wadi El-Rayan Lakes, El-Fayoum, Egypt, Mansoura Engineering Journal, Vol. 38, No. 1, March 2013, Hydraulic Research Institute, National Water Research Centre, Egypt.

Arab Republic of Egypt (ARE). 2001. The National Environmental Action Plan of Egypt 2002/17. Cairo.

Arab Republic of Egypt (ARE). 2018. Central Agency for Public Mobilization and Statistics. http://www.capmas.gov.eg [Accessed April 24, 2018].

Attum, Omar. 2008. The Gazelle Monitoring Program in Wadi Rayan Protected Area. Egyptian-Italian Environmental Cooperation Program, EEAA.

BirdLife International. 2018. Country profile: Egypt. Available from http://www.birdlife.org/datazone/country/egypt. Checked: 2018-03-30.

El Alqamy, H. 2002. Developing and assessing a population monitoring program for the dorcas gazelle (Gazella dorcas) using distance sampling in South Sinai, Egypt. – M. Phill. thesis, University of St. Andrews, Scotland, p. 109.

El Alqamy, H. and Baha El Din, S. 2006. Contemporary status and distribution of gazelle species (Gazella dorcas and Gazella leptoceros) in Egypt. Zoology in the Middle East 39, 5–16.

Egyptian Environmental Affairs Agency. 2007. Qaroun Protected Area Management Plan (draft). Ministry of State for Environmental Affairs, Nature Conservation Sector Planning Unit, Cairo.

Egyptian Environmental Affairs Agency. 2016. Qatrani World Heritage Site Plan. Strengthening Protected Area Financing and Management Systems Project, Ministry of Environment, Egypt, Global Environment Facility and United Nations Development Programme.

Egyptian Environmental Affairs Agency. No date. Wadi El Rayan Protected Area Integrated Eco-tourism and Development Plan. Egyptian-Italian Environmental Cooperation Programme, Phase III.

Fayoum Agro-Organic Development Association (FOADA), nd. http://faoda.org/aboutus_en.html, accessed May 28, 2018.

Gerrie, R. and Kennerley, R. 2017. Allactaga tetradactyla. The IUCN Red List of Threatened Species 2017: e.T850A22201540. http://dx.doi.org/10.2305/IUCN.UK.2017-2.RLTS.T850A22201540.en. Downloaded on 04 March 2018.

Italian Agency for Development Cooperation, nd. Projects in Egypt. Available online: http://www.aicscairo.org/projects/, accessed May 28, 2018.

IUCN, 2018. Mission Report: Management Effectiveness at Wadi El-Rayan and Lake Qarun Protected Areas (GEF6 UN Environment PPG Phase), March 2018.

IUCN and World Commission on Protected Areas. 2016. IUCN Green List of Protected and Conserved Areas: Standard, Version 1.1. Gland, Switzerland: IUCN.

IUCN. 2016. A Global Standard for the Identification of Key Biodiversity Areas, Version 1.0. First edition. Gland, Switzerland: IUCN.

IUCN SSC Antelope Specialist Group. 2017. Gazella dorcas. The IUCN Red List of Threatened Species 2017: e.T8969A50186334. http://dx.doi.org/10.2305/IUCN.UK.20172.RLTS.T8969A50186334.en

McNeely, J.A. & Mainka, S.A., 2009. Conservation for a new era. Gland: International Union for the Conservation of Nature.

Ministry of Water Resources and Irrigation, 2005. Water for the Future, National Water Resources Plan. Arab Republic of Egypt.

Paleczny, D. & Allam Harhash K., 2008. Egyptian site level assessment. In: F. Leverington, M. Hockings, H. Pavese, K.L. Costa & J. Courrau, eds. Management effectiveness in protected areas – a global study, supplementary report no. 1: Overview of approaches and methodologies. Gatton, Australia: The University of Queensland, IUCN WCPA, TNC, WWF, 2008. pp.46-54.

Paleczny, Dan. Khalid Allam Harhash, M. Talaat. 2007a. The State of Wadi El-Rayan Protected Area and Valley of the Whales World Heritage Site, An Evaluation of Management Effectiveness. Egyptian-Italian Environmental Cooperation Programme, Nature Conservation Sector Capacity Building Project, Cario.

Paleczny, Dan. Khaled Allam Harhash, Mohamad Talaat. 2007b. The State of Qaroun Protected Area, An Evaluation of Management Effectiveness. Egyptian-Italian Environmental Cooperation Programme, Nature Conservation Sector Capacity Building Project, Cairo.

Saleh, M.A. (1987) The Decline of Gazelles in Egypt. Biological Conservation 39, 83-95.

Soultan, Alaa Eldin. 2011. Identifying the current and future distribution of antelopes in Egypt under different scenarios of climate change. A dissertation submitted to the University of East Anglia, Norwich, in partial fulfilment of for the degree of Masters of Science in Applied Ecology and Conservation.

UNDP, 2016. Human Development for Everyone: Briefing note for countries on the 2016 Human Development Report, Egypt. Available online: http://hdr.undp.org/sites/all/themes/hdr_theme/country-notes/EGY.pdf , accessed May 28, 2018.

UNDP, nd. About Egypt. Available online: http://www.eg.undp.org/content/egypt/en/home/countryinfo.html, accessed May 28, 2018.

UNESCO, nd., Egypt Socio-economic indicators. Institute for Statistics. Available online: https://en.unesco.org/countries/egypt, accessed May 28, 2018.

UN Women, 2016. Empowering Women, Empowering Egypt Achievement Report, Egypt Country Oﬃce. Available online:  http://egypt.unwomen.org/en/digital-library/publications/2017/09/achievement-report-2016,  accessed May 28, 2018.

Wacher, Tim & Durant, Sarah & Pettorelli, Nathalie & Gilbert, Tania. 2016. Desert Antelopes on the Brink: How Resilient is the Sahelo-Saharan Ecosystem? 253-279. 10.1002/9781118409572.ch13.

Wadi El Rayan Protected Area (WRPA) 2007. Birding in Wadi El Rayan Protected Area and Checklist of the Birds. Egyptian-Italian Environmental Cooperation Program, IUCN, CultNat, EEAA.

World Food Programme (WFP) 2013. The Status of Poverty and Food Security in Egypt: Analysis and Policy Recommendations. Available online:  http://documents.wfp.org/stellent/groups/public/documents/ena/wfp257467.pdf.

## Appendices

Appendix 1.	Budget by project components and UN Environment budget lines

Appendix 2.	Co-financing by source and UN Environment budget lines

Appendix 3.	Results framework

Appendix 4.	Incremental cost analysis

Appendix 5.	Workplan and timetable

Appendix 6.	Key deliverables and benchmarks

Appendix 7.	Costed M&E plan

Appendix 8.	Summary of reporting requirements and responsibilities

Appendix 9.	Standard Terminal Evaluation TOR

Appendix 10.	Decision-making flowchart and organizational chart

Appendix 11.	Terms of reference for key project personnel

Appendix 12.	Co-financing commitment letters from project partners

Appendix 13.	Endorsement letters of GEF National Focal Points

Appendix 14. 	Draft procurement plan

Appendix 15.	Tracking Tools

Appendix 16.	UN Environment Environmental, Social and Economic Review Note (ESERN)

Egyptian NBSAP v2: https://www.cbd.int/doc/world/eg/eg-nbsap-v2-en.pdf

This protected area is identified as an Important Bird Area (IBA) (Key Biodiversity Area for Birds) by the Integrated Biodiversity Assessment Tool (IBAT - https://www.ibat-alliance.org) based on the presence of significant congregations of one or more bird species at certain times in their lifecycle or seasonal migration.

http://www.birdlife.org/africa/news/%E2%80%9Cporto-fayoum%E2%80%9D-tourism-development-planned-lake-qarun-important-bird-area-and-proposed

Information in this section is drawn from the National Environmental Action Plan (ARE, 2001).

The IUCN Green List of Protected and Conserved Areas Programme aims to encourage, achieve, and promote effective, equitable and successful protected areas (IUCN, 2016). The objective of the IUCN Green List Programme is to increase the number of protected and conserved areas that deliver successful conservation outcomes through: (a) good governance (b) sound design and planning (c) effective management, (d) successful conservation outcomes (per the PAs goals and objectives).

Ecotourism is "responsible travel to natural areas that conserves the environment, sustains the well-being of the local people, and involves interpretation and education" (The International Ecotourism Society, 2015).