United Nations Development Programme

| Project title: 7th Operational Phase of the GEF Small Grants Programme – Part 1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country(ies): Global | Implementing Partner (GEF Executing Entity): UNOPS |  |  |  | Execution Modality: Agency Execution |
| UNDP Strategic Plan Outputs: 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste 2.1.1: Low emission and climate resilient objectives addressed in national, sub-national and sectoral development plans and policies to promote economic diversification and green growth 1.5.1: Solutions adopted to achieve universal access to clean, affordable and sustainable energy 2.5.1: Solutions developed, financed and applied at scale for energy efficiency and transformation to clean energy and zero-carbon development, for poverty eradication and structural transformation 3.4.1: Innovative nature-based and gender-responsive solutions developed, financed and applied for sustainable recovery |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: moderate |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Award ID: |  |  | Atlas Project/Output ID: |  |  |
| UNDP-GEF PIMS ID number: 6271 |  |  | GEF Project ID number: 10084 |  |  |
| LPAC meeting date: March 2020 |  |  |  |  |  |
| Latest possible date to submit to GEF: September 2019 |  |  |  |  |  |
| Latest possible CEO endorsement date: |  |  |  |  |  |
| Planned start date: April 2020 |  |  | Planned end date: March 2024 |  |  |
| Expected date of posting of Mid-Term Review to ERC: NA |  |  | Expected date of posting Terminal evaluation report to ERC: |  |  |
| Brief project description: The direct involvement of local communities who depend on natural resources for their livelihoods and therefore have the strongest incentive to develop appropriate solutions is most pertinent in local and global efforts to address serious environmental challenges that we face today. The SDGs and the Paris Agreement on Climate Change also recognized the importance of participation of communities and Civil Society Organizations (CSOs) if we are to achieve the SDGs and halt the threat of serious climate change. In this regard, the UNDP implemented, GEF financed, Small Grants Programme (SGP) is a proven programme that was set up to support community-based initiatives led by the civil society and community-based organizations addressing the environment and development issues of global relevance. Over the last 26 years, the SGP has implemented over 24,000 projects in total 133 countries, providing grants totaling USD 611.6 million. In the new phase, the SGP will adopt and strengthen primarily five interrelated approaches including empowering local communities, supporting community innovation on emerging issues, promoting partnerships and broader adoption, serving as a dependable global community-based grant mechanism and platform for the environment etc. In doing so, the SGP aims “to promote and support community-based innovative, inclusive, and impactful initiatives, and foster multi-stakeholder partnerships to tackle global environmental issues” in programme countries. SGP will employ several strategic initiatives (SI) namely: community-based conservation of threatened ecosystems and species; sustainable agriculture and fisheries, and food security; low-carbon energy access co-benefits; local to global coalitions for chemicals and waste management; catalyzing sustainable urban solutions; CSO-Government-Private Sector Policy and Planning Dialogue Platforms; Enhancing social inclusion; and Monitoring and Evaluation and Knowledge Management. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund Core first tranche |  |  | USD 61,538,462 |  |  |
| - Total Budget administered by UNDP |  |  | USD 61,538,462 |  |  |
| CONFIRMED CO-FINANCING |  |  |  |  |  |
| Cash co-financing |  |  | USD 4,000,000 |  |  |
| In-kind co-financing |  |  | USD 55,500,000 |  |  |
| Programme partnerships |  |  | USD 4,500,000 |  |  |
| - Total confirmed co-financing |  |  | USD 64,000,000 |  |  |
| Grand-Total Project Financing (1)+(2) |  |  | USD 125,538,462 |  |  |
| UNFUNDED FINANCE |  |  |  |  |  |
| Core second tranche |  |  | USD 61,538,462 |  |  |
| STAR tranches |  |  | USD 38,461,538 |  |  |
| Cash co-financing |  |  | USD 6,000,000 |  |  |
| In-kind co-financing |  |  | USD 91,500,000 |  |  |
| Programme partnerships |  |  | USD 4,500,000 |  |  |
| Grand total Project Financing (confirmed and un-confirmed) |  |  | USD 202,000,000 |  |  |
| Signatures |  |  |  |  |  |
| Signature: Dionyssia Geka Director, New York Service Cluster UNOPS |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: Pradeep Kurukulasuriya Executive Coordinator & Director- Global Environmental Finance & Head, Natural Capital and the Environment |  | Agreed by UNDP |  | Date/Month/Year: |  |
| Key GEF Project Cycle Milestones: Project document signature: within 25 days of GEF CEO endorsement First disbursement date: within 40 days of GEF CEO endorsement Inception workshop date: within 60 days of GEF CEO endorsement Operational closure: within 3 months of posting of TE to UNDP ERC Financial closure: within 6 months of operational closure |  |  |  |  |  |

# Table of Contents

Table of Contents	3

I.	Development Challenge	4

II.	Strategy	7

III.	Results and Partnerships	24

IV.	Project Results Framework	33

V.	Monitoring and Evaluation (M&E) Plan	36

VI.	Governance and Management Arrangements	41

VII.	Financial Planning and Management	44

VIII.	Total Budget and Work Plan	46

IX.	Legal Context	47

X.	Risk Management	48

XI.	Annexes	51

Annex 1: SGP Operational Guidelines ……………………………………………………………………………………………………………….51

Annex 2: Monitoring Plan:	53

Annex 3: UNDP Risk Log	58

Annex 4: GEF 7 Taxonomy	60

# Development Challenge

- Global environmental problems and root causes

- The most serious environmental problems of the twenty-first century have the potential to alter the course of life on this planet. Global warming, biodiversity decline, depletion of natural resources, problems with toxic waste, water and air pollution, acid rain, and shrinking energy supplies are serious challenges that may threaten our future if we do not face up to them. Take for example biodiversity decline. Biodiversity has continued to decline globally. The global rate of species extinction is escalating and is now estimated to be up to 1000 times the natural rate. Evidence is growing that critical ecosystem services are under great pressure globally. According to one estimate, approximately one quarter of the potential net primary production has been converted by humans, either through direct cropping, land-use-induced productivity changes, or human-induced fires. Such is the indication of the substantial impact of humans on natural ecosystems. National and international attention has focused on the political imperative to convert international target into hard economic decisions, concerted implementation, and concrete national actions, and despite some encouraging achievements these came up short of halting the biodiversity decline. This is partly because where conservation targets have been established, lack of appreciation of the effective contribution of customary sustainable management of natural resources have often-times resulted in top-down approaches that often exclude local actors. In many countries, policies and programmes still do not adequately support or promote indigenous peoples and local communities (IPLCs) traditional knowledge on natural resource management and the conservation of biodiversity. In the worst cases, conservation effort may even negatively affect IPLCs through exclusionary approaches, leading to human rights violations, with detrimental results to biodiversity and the long-term viability and health of ecosystems.

- Moreover, new evidence provided in a recent report from the Rights and Resources Initiative, Woods Hole Research Center, World Resources Institute (WRI) and Environmental Defense Fund shows that Indigenous Peoples and local communities worldwide manage massive amounts of carbon in the trees and soil of their forests—at least 293,061 million metric tons. That's 17 percent of the total carbon stored in the world's forestlands, which if released at once, would equal 33 times the total global energy emissions of 2017. Increased policy action such as the adoption of the Strategic Plan for Biodiversity 2011-2020 and Aichi Targets mean a stronger recognition of the role of IPLCs in voluntarily conserving biodiversity. CBD Aichi Target 11 now includes a reference to “other effective area-based conservation measures” (OECMs) including Indigenous Community Conservation Areas (ICCAs) and private protected areas, as central to expanding the global coverage of protected areas (PAs) from 12% to 17%. Scientific consensus is also emerging that government-managed protected areas will not avert the biodiversity crisis.

- The situation is similar with regards to food production and land degradation. While there may be sufficient potential for food production in the world, there will still be problems of food security at the household or national level. In urban areas, food insecurity usually reflects low incomes, but in poor rural areas it is often inseparable from problems affecting food production. The focus of sustainable land and forest management focal areas should be geared towards enhancing climate smart innovative agroecology practices and up holding agroecology principles. These principles will be realized through appropriate climate-sensitive agriculture and improved agroecosystem service provision to achieve short-and-long-term agricultural development priorities at local level. These approaches will help to enhance community and ecosystem resilience and to integrate other land-based development priorities in the production landscapes.

- Similarly, increased risks of exposure to toxic and hazardous chemicals and wastes predominantly affect the poor, who routinely face such risks because of their occupation, poor living standards and lack of knowledge about the detrimental impacts of exposure to these chemicals and wastes. According to the World Health Organization (WHO), acute pesticide poisoning affects three million people and account for 20,000 unintentional deaths each year. In many communities and nations, those living in poverty, women and children continue to be disproportionately exposed to pesticides, making this an issue of fairness and environmental justice. Between 2005 and 2020, the accumulated cost of illness and injury linked to pesticides in small scale farming in sub-Saharan Africa alone could reach USD $90 billion. According to some assessments, the total anthropogenic emissions of mercury to the atmosphere in 2010 are estimated at 1960 tonnes.  Artisanal and small-scale gold mining (ASGM) and coal burning are the largest sources of anthropogenic mercury emissions to air, followed by the production of ferrous and non-ferrous metals, and cement production. Annual emissions from ASGM are estimated at 727 tonnes, making this the largest sector accounting for more than 35% of total anthropogenic emissions.  E-waste is the fastest growing waste stream.  In the United States, an estimated 70% of heavy metals in landfills come from discarded electronics.  This negative trend is spreading to the rest of the world, including developing countries. Another study by UNEP estimated that the amount of e-waste being produced - including mobile phones and computers - could rise by as much as 500 percent over the next decade in some countries, such as India.

- Climate change remains a defining issue of our time, despite recent significant progress in development of new low carbon technology and growing momentum for climate action. The concentration of greenhouse gases in the atmosphere continues to rise and the impacts are increasingly felt around the globe with climate-related disasters responsible for thousands of deaths and $320 billion dollars in losses during the last year. The poor and vulnerable populations are disproportionally affected with economic and security risks amplifying and runaway change beyond the adaptive ability of human societies and natural ecosystems is a real possibility. The historic Paris Agreement has put in place a framework defining countries’ climate action for the next few decades, setting up a mechanism for countries to put forward and implement Nationally Determined Contributions (NDCs) outlining their commitments. The next 2-3 years are crucial for successful implementation of the agreement, as the NDCs are required to be updated every 5 years and the challenge now is to raise the ambition and accelerate the transition to low -carbon resilient economy. The time to stop catastrophic climate change is running out and many investment decisions taken today will shape the future for decades.

- In this regard, the energy sector, producing two thirds of global emissions, presents a large scope for cost effective emissions reductions. Besides, energy access is a crucial area for investment, as expanded access to electricity and clean cooking improves productivity, reduces poverty and improves health with the largest benefits for women. According to the New Climate Economy report from the Global Commission on the Economy and Climate, 1 billion people do not have access to electricity, and over 2.9 billion people do not have access to clean cooking. By 2030, planned policies are expected to deliver clean energy to millions, but population growth is expected to outpace progress, leaving 674 million people lacking electricity access and more than 2 billion people without clean cooking. The report calls for increased government support for and investment in decentralized electricity and clean cooking as a crucial step to accelerate climate action and transition to new low-carbon economy. Investing in local solutions and mobilization of civil society is also key for raising the ambition of NDCs, galvanizing support and ensuring their implementation.

- Global environmental problems are inter-connected and require an integrated approach: It is now increasingly recognized that a powerful and complex web of interactions is contributing to unprecedented global trends in environmental degradation. These forces include rapid globalization and urbanization, pervasive poverty, unsustainable consumption patterns and population growth. Often serving to compound the effects and intensity of the environmental problems, global environmental challenges require concerted responses on the part of the international community. In an influential paper, Nakicenovic, N et. al. discussed how “in a globalized world, effects of individual actions and decisions are leading to emergent behavior at the Earth system scale, the “Anthropocene effect” behavior that cannot be predicted from analysis of individual parts”. Given the scale of industrial impacts, the authors suggest that if previously effective common resource management approaches and regimes could be re-applied to govern and steward the “global commons” significant benefits and advances could be felt. Due to the unprecedented impacts we are having on our planet’s life support system, they note that human beings must be part of the solution arguing “that humanity must be the steward of the planet’s natural resources – the ecosystems, biomes and processes that regulate the stability and resilience of the Earth system, or what is termed as the global commons”.

- Moreover, it is becoming increasingly evident that the major environmental problems — biodiversity, land degradation, climate change, energy, issues with food security -- cannot be understood or addressed in isolation.  They are systemic problems, which means that they are all interconnected and interdependent. Many environmental thinkers describe this interconnected and interdependent nature of the global environmental challenges. For instance, Lester Brown, of the World Policy Institute, posits that the vicious circle of demographic pressure and poverty leads to the depletion of resources — falling water tables, shrinking forests, collapsing fisheries, eroding soils, and so on — and how this resource depletion, exacerbated by climate change, produces failing states whose governments can no longer provide security for their citizens, some of whom may even turn to terrorism in sheer desperation. To address global environmental challenges, requires a radical shift in our perceptions, our thinking, our values” – to one that considers a systemic, interconnected, and integrated approach. An interdependent approach is also critical from a policy perspective. Well-written policies made in one country cannot achieve success in combating threats to the global commons without concerted actions in tandem with other governments, civil society actors and the private sector.

- Further, as described in a recent document of the Scientific and Technical Advisory Panel (STAP) of the GEF, “a lack of integration is a major detriment to achieving sustainability”. For example, a review of progress in achieving global environmental goals, including those Multilateral Environmental Agreements (MEAs) supported by the GEF, underscored fragmentation as a major cause of slow progress. The review emphasized the need for integration between (i) types of problems and identified solutions; (ii) the responsibilities and resources available to implementing institutions; and (iii) in governance structures. Among others, the STAP document recommended that the GEF project design process to “engage stakeholders, including local communities, civil society networks, industry associations or other key private sector actors as appropriate (not just government officials) from project inception and from design through completion”. This is where the SGP can play an important role by piloting such integrative approaches including building on its decades of experience in participatory design and implementation and lesson-sharing.

- This need for an integrated and inclusive approach is also reflected in the UN 2030 Sustainable Development Goals (SDGs). The SDGs marked a turning point in the target-setting of the United Nations for human development. The 17 SDGs provide a time-bound and comprehensive narrative for achieving the desired future and normative human development goals – a world free from hunger, injustice and absolute poverty, a world with universal education, health and employment with inclusive economic growth, based on transparency, dignity and equity, including an explicit call for the protection of the Earth system. The SDGs acknowledge that the challenges faced across the 17 goals are interrelated and interconnected and should be achieved in such a way as to maximize synergies and minimize tradeoffs. Achieving one SDG will often contribute to achieving others. For example, achieving SDG 7, the energy goal, can support goals related to water, health and climate. Moreover, the SDGs call for inclusive development, including vulnerable and marginalized communities such as women, indigenous peoples, youth, and persons with disabilities, under the approach on “leaving no one behind.”

# Strategy

- The long-term solution – role of SGP to address global environmental issues

- The SGP is a proven GEF programme that was set up to support community-based initiatives led by the civil society organizations and local initiatives dealing with the environment and development issues of global relevance. Many evaluations of the programme including the 2015 Joint Evaluation by the GEF and UNDP’s IEOs indicates that the “SGP grants continue to support projects that have high levels of success in securing global environmental benefits in both mature and newer program countries”. Thus, the SGP is successfully achieving its aim as described in the GEF-7 Programming Directions to enable “communities as solution providers and key partners to address the drivers of global environmental degradation and engine for systemic change”. Based on the IEO Evaluation, lesson learned and inputs from stakeholder consultations, including with government, Convention focal points, and the private sector, under GEF-7 the SGP will place greater focus on promoting strategic and results-based investments at the local level in alignment with the GEF’s proposed focal area investments and Impact Programs. SGP financed projects will have greater focus in promoting and supporting innovative and strategic initiatives at the local level to address global environment issues in priority landscapes and seascapes.  It will also support projects that would serve as “incubators” of innovation, with the potential for broader replication of successful approaches through larger projects supported by the GEF and/or other partners.  SGP grantees and partners will also act as an effective and important social constituency to mobilize bottom up, civil society movements for systemic change, and in promoting environmentally sound sustainable development at the national, regional, and global levels.

- Barriers

- Several barriers however impede the above long-term solution proposed for the SGP.

Barrier 1: Limited diffusion of effective models of scalable community-based management and governance for the conservation of biodiversity constrain realization of the full potential of the role of local communities including indigenous peoples in the conservation and sustainable use of threatened ecosystems and species.

- In many rural areas of the world, local communities possess vast knowledge of the local species and ecosystems and have been effective conservation stewards of biodiversity. However, their role has been often undermined in national policies and actions related to biodiversity conservation and sustainable use. Lack of knowledge and incentive at the community level on “biodiversity friendly” methods of production in agriculture, forestry and fisheries is another important barrier. This is often exacerbated by the limited experience that government agencies and related stakeholders (often also local communities) have in incorporating biodiversity conservation and sustainable use objectives into land and resource use practices. Moreover, local level strategies for community based natural resource management often stop at measures that promote participation in specific activities such as providing labour for agriculture and plantations, and do not meaningfully involve communities as partners in the effective governance of ecosystems and species with clarified roles and responsibilities. There is a need to recognize that many communities and indigenous peoples as solution providers that have been managing and conservation key biodiversity areas. This is especially important given the essential role of other effective conservation measures in achieving the bold conservation targets that the world has agreed on.

Barrier 2: Community level capacities for adopting sustainable agriculture, fisheries and food security strategies and practices are limited.

- While the focus on land degradation focal area is geared towards enhancing climate smart innovative agroecology practices and up holding agroecology principles as well as adopting sustainable land management practices, at the local level, this is often constrained by limited capacities and incentives to adopt them. Local communities lack exposure to appropriate sustainable land management (SLM) technologies and have limited knowledge and access to climate smart innovative agriculture practices. In order that strategies and approaches will ensure enhancement of community and ecosystem resilience, design and implementation of climate smart agriculture, fisheries and food strategies should be accompanied by appropriate capacity building measures including farmer training, extension messaging (i.e. through master farmers for horizontal knowledge exchange) and targeted support to farmers to adopt practices which green the production and supply chains of key local commodities. In many parts of the world, small-scale artisanal farmers, pastoralists and fisher-folk continue to lack adequate market knowledge and have limited exposure to key marketing strategies such as certification, and ecolabeling.

Barrier 3: Community-level limitations restrict adoption of low carbon technologies and improved land-use and forestry practices that reduce GHG emissions.

- Significant emissions savings from adoption of low carbon technologies at the community level are currently not implemented due to several community level constraints. First, many communities are not aware of low carbon technologies and land-use practices and associated health, economic, nutritional and environmental co-benefits.  Second, even when the technologies are available at the market, specific solutions for use in local contexts are not yet available. As these technologies are new, innovative adaptations are needed to tailor them to productive needs even in advanced countries, much more so in developing countries.  Another important barrier is severely limited know-how of various low carbon technology options and even when such technologies are distributed, their use is limited as communities lack the knowledge and ability to operate and maintain them. Local stakeholders generally are also not able to afford the upfront costs related to purchase of even low-cost technologies particularly due to lack of public-private partnership model that could facilitate and overcome such issues. Also adopting climate friendly land use and forestry practices requires learning and initial investment of time and resources. Further investment is needed in developing local expertise as well as in supporting entrepreneurs involved in the energy service business to ensure affordability and sustainability.

Barrier 4: Inadequate experience with dealing with sound management of chemicals and waste: Many communities are at the forefront of threats related to chemicals and waste as users of consumers.

- However, they lack the necessary knowledge of the harmful effects of such chemicals and, even when aware, using or consuming such harmful chemicals remains their only option either due to availability and cost, or because their livelihoods depend on such industries. Further, many countries, particularly SIDS and LDCs still lack necessary legislation and management system to reduce and control the use of harmful chemicals and wastes. There is a need to provide target support at the community level for safe disposal of chemicals and waste including those of global concern including mercury and plastic wastes. There is also a need to engage with local academic institutions and other relevant actors to develop and promote practical, viable and acceptable waste and chemicals management strategies, while awareness raising on harmful chemicals and waste should be implemented in tandem. Targeted support for specific chemicals and sectors such as artisanal and small-scale gold mining to reduce the use of mercury is necessary.

Barrier 5: Limited or absence of inclusive community-oriented urban solutions: Urbanization is a defining trend all over the world and especially in developing regions of Asia, Africa and Latin America.

- Some estimates point that by 2030, over sixty percent of the global population will be urban residents. It is widely accepted that cities can be hotspots of extreme deprivation and environmental degradation especially where the bulk of poor will be located with potentially serious impacts from environmental hazards. This calls for innovative partnerships for sustainable urban solutions such as provision of affordable renewable energy, water supply and waste management services that will benefit the urban poor while delivering on the global environmental outcomes. However urban poor and vulnerable communities currently do not have the capacities themselves to adopt such solutions while municipalities and city governments may not be in the position to fully integrate different needs of the population particularly women and girls, youth and persons with disability in their plans due to financial and other constraints. There is a need for public-private partnership promoted by civil society and local communities to provide an integrated package of sustainable urban solutions for energy, waste management and other environmental services. Support is also needed to open space for CSOs for engagement and participation in local decision-making and inform better urban governance and accountability related to urban environmental issues.

Barrier 6: There is limited availability of community-oriented tools, mechanisms and platforms that are inclusive and facilitate local communities to meaningfully participate and provide inputs to national / global environmental and development policy making.

- While the capacity of CSOs and local communities on policy advocacy has improved over the years, there is still a great need to demonstrate inclusive community-oriented networking and support systems, that can not only connect community groups with each other but can also link up communities with the government and private sector for policy and programme dialogues related to environment and sustainable development both at the national and global levels.  Barriers remains particularly for vulnerable population, including women and girls, indigenous peoples, youth and persons with disabilities to effectively participate, voice their concerns, and influence policy decisions that affect their lives.  development.  Enabling environment needs to be created to expand community-based action at scale through positive national policy dialogue and development planning that brings in the different needs, knowledge, and opportunity of community and CSO stakeholders at large.

- The baseline scenario and any associated baseline projects

- Civil society organizations and local communities continue to play an under-utilized and under-valued role in addressing global environmental and sustainable development issues in most parts of the world.  CSOs and CBOs can play a variety of critical roles and can be extremely effective agents for the necessary transformative change in society and flip the current trajectory on global environmental crisis by: (i) catalyzing innovation, testing new approaches, and responding to emerging challenges and opportunities bringing global experience and good practice to local contexts; (ii) transferring  innovative and traditional knowledge and skills and knowledge to government agencies and the private sector, leading to better policy and business practices; (iii) catalyzing innovation, testing new approaches and responding to emerging challenges and opportunities; (iv) brokering partnerships among traditional and non-traditional actors; and (iv) ensuring that projects and programs are beneficial to local people, such as by protecting vital ecosystem services and providing sustainable livelihood options.

- During the past 25 years, participating countries to the SGP has steadily increased from the initial 35 countries to the current 125 countries.  Most of the countries that SGP serves (77 in total), are Least Developing Countries (LDCs) and Small Island Development States (SIDS), including several which are in post-conflict or crisis situations. The SGP funds small grants up to maximum of $50,000, with an average grant amount of approximately $25,000. A strategic project window has also been added for grantmaking up to a maximum of $150,000 to allow for scaling up and to support initiatives that cover many communities, either within in a critical landscape or seascape, or towards a thematic priority.  Small grants are targeted primarily towards local communities and civil society organizations, the poor and vulnerable, to access appropriate level of funding as they develop their capacity, take measured risks in testing new methods and technologies, and to innovate at the local level.  Each SGP country programme has a multi-sectoral National Steering Committee (NSC) which assures a country-driven approach to SGP implementation and allows civil society leadership and capacity development in the management of a country programme.

- The 2015 Joint Evaluation by the GEF and UNDP’s IEOs concluded that the SGP continues to play a key role in promoting the GEF’s objectives. It specifically noted that SGP continues to support projects that are relevant, effective and efficient in achieving global environmental benefits, while addressing issues of livelihoods, poverty, gender equality and women’s empowerment. The evaluation also reported evidence of strong replication, scaling-up, sustainability, and mainstreaming of the Programme activities.  The Sixth Comprehensive Evaluation of the GEF (OPS6) noted long-term support through SGP has enabled small-scale interventions to be broadly adopted. It recognizes SGP’s role in providing GEF presence and visibility at the community level, and further concludes that SGP delivers grants that address local environmental concerns of global relevance at the national or subnational level, and links communities to long-term environmental management through income-generating activities. The evaluation mentions that one of the main characteristics differentiating the SGP from other GEF programs is its ability to function as a demand-based type of community support, thereby engendering community/country ownership. The SGP has also been cited as an effective channel to share information and raising awareness among stakeholders at the local level in several countries. Several evaluations of the GEF (for example Engagement with Indigenous Peoples (IPs); Gender mainstreaming) specify the SGP’s value addition on social inclusion, noting that the SGP is the primary modality for the GEF’s engagement with indigenous peoples and gender within the GEF partnership.

- The SGP plays an important role in meeting the objectives of the Multilateral Environmental Agreements (MEAs), for which the GEF serves as financial mechanism. For example, the MEAs emphasize the need for social inclusion and broader participation, including involvement of civil society organization, indigenous peoples, and local communities. The SGP has been effectively implementing socially inclusive, integrated approaches that promote multi-sectoral solutions to environmental challenges across the MEAs.  The Conference of the Parties of the Convention on Biological Diversity (CBD) has provided specific guidance to the SGP to further strengthen and expand its support to local communities in the developing countries, including Least Developing Countries (LDCs) and Small Island Development States (SIDS). In each participating country, the SGP is facilitating close linkages and synergies with MEA related policies and strategies such as National Biodiversity Strategy and Action Plan (NBSAP), National Action Plan (NAP), Nationally Determined Contributions (NDC), and others, all of which emphasize the importance of engaging wider stakeholders, including CSOs, IPs, and gender, to achieve the objectives. Finally, it may be noted that the GEF 7 period coincides with the key phase in implementing the Paris Agreement that requires multi-stakeholder efforts, including civil society and communities, in meeting its goal. On the chemicals and wastes, the Stockholm and the Minamata Conventions are also increasingly recognizing the role of civil society in addressing their challenges and have been closely working with the SGP to reach out to the local and community level. The Programme’s strategic importance and relevance is further recognized, particularly with the adaption of the Sustainable Development Goals and recognition for a socially inclusive sustainable development.

- Despite efforts made by other related initiatives, local CSO and community involvement in global environment and sustainable development actions could continue to be limited and slow in engagement without the facilitative role of GEF SGP. Given the accelerating global environmental threats, inclusive environmental governance at all level is crucial. Good environmental governance considers the role of all sectors and actors including that of the local CSOs and communities, so that effective cooperation is achieved towards a sustainable future. As recommended by the STAP guidance on integration (2018), for integrated projects to be successful, all sectors and actors including local communities, civil society networks, industry associations or other key private sector actors as appropriate should be engaged. SGP’s role to enhance the capacity of local CSOs and communities to engage in such process and influence the design of interventions to address global environmental challenges gains prominence. However, without such support, contributions from the CSOs and CBOs, particularly by vulnerable and marginalized communities will remain limited. Furthermore, there is also needing to consolidate assets of projects that supported such local CSO and communities’ capacity building for scaling up, mainstreaming and replication. The many community-based and CSO-led projects that SGP has supported, as well as its development as a funding modality that are highly regarded by both CSOs and government in participating countries, can be considered as built-up assets that can serve as effective foundation for expanded work in GEF-7.

- Portfolio overview: Since its inception in 1992, the SGP has implemented over 24,000 projects in total 133 countries (some SGP country programme have closed as they graduated from being an eligible country of the GEF), providing grants totaling USD 611.6 million in global and upgraded country programmes. During GEF-6, around 3500 new projects were approved, and 4,187 projects have been completed. With regards to focal area distribution during GEF-6, biodiversity focal area remained as the largest portfolio (39%), followed by climate change mitigation (23%), land degradation (21%). Some key aggregated results and achievements through the SGP projects from completed projects during the GEF-6 period are presented below:

- Biodiversity: Positively influenced management of 1,782 protected areas, including Indigenous Peoples and Community Conserved Territories and Areas (ICCAs), covering approximately 33 million hectares.

- Climate Change Mitigation: Application of low-carbon technologies, with 41 percent of the portfolio concentrated on renewable energy, 28 percent on energy efficiency solutions, and 26 percent on conservation and the enhancement of carbon stocks. Projects have supported 54,636 households in their efforts to achieve energy access co-benefits, including increased income, health benefits and improved environmental services.

- Land Degradation: 1.6 million hectares of land were brought under improved management practices, including forests, agricultural land, and water courses. 992,370 community members were able to improve agricultural land and forest management practices; and 2,008 farmer organizations and networks disseminated enhanced climate smart agro-ecological practices.

- International Waters: 103,186 hectares of marine and coastal areas and fishing grounds brought under sustainable management.

- Chemicals and Waste Management: 159 tons of pesticides appropriately disposed of, and 55,098 tons of solid waste avoided from open burning.

- Capacity Development: The SGP has strengthened the capacities of 3,490 CSOs and 2,793 CBOs, comprising over 95,174 people, to address multiple challenges across all the relevant MEAs.

Grantmaker Plus: Results

- Under GEF-6, the SGP employed a strategy to expand its role beyond that of grantmaking. Grantmaker Plus enhances the overall effectiveness of the GEF-6 portfolio by engaging in knowledge platforms, policy dialogues, and social inclusion. During the GEF-6 period, the introduction of the Grantmaker Plus initiative has yielded the following key results:

- Knowledge Sharing and Capacity Development: SGP supported 2,547 peer-to-peer exchanges; 3,754 training sessions on varied themes relating to global environment and project management. During this period, as an annual average -78% of SGP country programmes worked on strengthening grantee networks; 74% of SGP country programmes connected grantees with enabling NGOs; and 72% of SGP country programmes connected grantees with government extension services. In addition, SGP supported the knowledge flow and technology transfer among countries and regions by facilitating South-South exchanges.

- CSO-Government Dialogue: SGP policy dialogue platforms have leveraged existing and potential partnerships, as well as built trust and fostered joint networking relationships between civil society and government partners on national policies, strategies, and development plans. During GEF-6 period, 298 such dialogue platforms were initiated, involving 9,699 CSO/CBO-represented dialogues relating to policy and development planning. For example, SGP has facilitated CSO-Government Dialogues in 26 countries to bring local voices to their INDC development, as a critical process leading to the Paris Agreement.

- Social Inclusion: The SGP continues to head the way and increase integration of marginalized groups in environment and development initiatives, including women, indigenous peoples, youth, and persons with disabilities. The improvement of livelihoods remains a key strategy of the SGP, since the sustainable management of land, biodiversity, and other ecosystem resources directly affects the generation of global environmental benefits that contribute to the wellbeing of local communities. On average, during GEF-6 period, 30% of completed projects were led by women, 16% addressed and engaged issues.

Broader Adoption: Scale Up and Replication

- Broader adoption of SGP project results and approaches, including their scale up, replication, and mainstreaming continued to be a core objective of GEF-6 SGP programming. Under GEF-6, at least 626 completed projects were reported to have been replicated or scaled up through CSOs/CBOs and governments, and 377 projects had influenced policy, representing an average of 15 percent and 9 percent, respectively, of closed projects each year. In addition, investments and assets also resulted from SGP’s work with GEF Full-Sized Projects (FSPs), in synergy as well as in a supportive role, in implementing community components of these projects. Globally, several UNDP and donor co-financed programmes have also been implemented by the SGP, including inter alia: (i) Community-Based Adaptation programme funded by AusAid; (ii) Community-Based REDD+ programme in partnership with UNREDD and with financing from Norway; (iii) Community Development and Knowledge Management in the Satoyama Initiative (COMDEKS) funded by the Japan Biodiversity Fund in collaboration with UNEP and UNU; the (iv) EU funded Environmental Governance and NGO Strengthening project.

- All these foundational assets and existing investments from government, bilaterals, donor agencies and international NGOs will be treated as “baseline” from which SGP Country Programme Strategies will develop its priorities and approaches which then feed into supporting the development (i.e. partnership and co-financing components) and selection of individual small grants projects to ensure the strategic and catalytic nature of SGP grantmaking.

- GEF-7 SGP Key Approaches:  Reiterating the challenges recognized through the GEF 2020 Strategy, the GEF-7 Programming Directions Paper points that the global environment—the ecosystems, biomes and processes that regulate the stability and resilience of the Earth system—are being stretched to a breaking point.  Radical transformation of human activities is required to reverse such degradation trends. The GEF Small Grants Programme (SGP), implemented by United Nations Development Programme on behalf of the GEF Partnership, is a key mechanism of the GEF that contributes to such transformational change by mobilizing and empowering civil society and local communities from the bottom up.

- The SGP finances community-led initiatives to address global environmental and sustainable development issues. It is specifically designed to mobilize bottom up actions by empowering local civil society organizations, and poor and vulnerable communities, including indigenous peoples and women.  Local communities have a profound understanding and knowledge of their environment and community needs and play a key role as stewards of the local and global commons. The program works to empower them to find innovative solutions in addressing global environmental challenges. The active participation of local communities in developing, testing and applying innovative solutions can play a key catalytic role for transformational change across a range of socio-economic settings, ranging from LDCs, SIDS, as well as middle and upper-middle income countries.

- In line with the approved GEF Council paper on GEF Small Grants Programme: Implementation Arrangements for GEF-7, SGP financed projects will have greater focus in promoting and supporting innovative and scalable initiatives at the local level to address global environment issues in priority landscapes and seascapes.  SGP will also support projects that would serve as “incubators” of innovation, with the potential for broader replication of successful approaches through larger projects supported by the GEF and/or other partners.  In this context, the SGP will strengthen its partnership approach as a CSO-led multi-stakeholder platform, by working closely particularly with private sector and government. The SGP grantees and partners will act as effective and important force to mobilize bottom up, civil society movements for systemic change in promoting environmentally sound sustainable development at the national, regional, and global levels.

- After 26 years of implementation, the SGP is poised to build on its successes and transform into a global platform for promoting community-based actions for global environmental issues. It will adopt and strengthen the following approaches to increase the effectiveness of program implementation under GEF-7:

(a)	Empowering local communities

- As a unique global mechanism and platform which aims to empower local communities, particularly vulnerable peoples, to address global environmental challenges, during GEF7 the SGP will increasingly strengthen social inclusion by effectively reaching out to local communities with a focus on women, indigenous peoples, youth, and persons with disabilities. Most of the grants will be provided directly to the beneficiaries while, at the same time, supporting those CSOs that act as facilitators and intermediaries. Communities targeted by SGP are often the poorest and most vulnerable; they typically have low levels of personal and institutional capacity to adequately address global environmental problems. Building on the evidence base of the 2015 IEO and other evaluations, the SGP has inter alia been recognized as the prime modality for GEF engagement with indigenous peoples (GEF, 2017c), and plays a leading role on gender equality and the empowerment of women (GEF, 2017a).

(b)	Targeting support to LDCs and SIDS

- Under GEF-7, the SGP will further strengthen its support to LDCs and SIDS by providing (i) priority access to funding and support; (ii) capacity development and training; and (iii) learning, sharing, and networking. Approaches and tools promoted through SGP projects are considered particularly relevant to LDCs and SIDS, where the capacity of CSOs and local communities remains limited. Furthermore, the relatively smaller scale of interventions through SGP projects can ensure significant and lasting impact in many of the smaller countries. The SGP is currently operational in 69 LDCs and SIDS that are eligible for GEF funding. As opportunities arise, the SGP aims to include a few additional LDCs and SIDS that have requested SGP participation. Notwithstanding the above, the SGP continues to contribute to a vital unmet need in many middle and upper-middle income countries, consolidating lessons learned and results through the UCPs and other mature SGP country programmes for dissemination at the global level through the global South-South knowledge transfer platform.

(c)	Supporting community innovation on emerging issues

- Innovation often arises when there is freedom to experiment and take calculated risks, and local conditions and situations are respected during project development and implementation. The SGP seeks to maximize local knowledge and capacity by providing greater flexibility and enhancing project adaptability. Communities are thus empowered to seek solutions and make decisions through SGP project support. Such a demand-driven approach, combined with flexibility, accessibility, and risk taking constitute the SGP as an incubator and accelerator of innovation. The 2015 Joint IEO Evaluation noted that the “SGP pilots, innovates, and contributes to knowledge about what works and what does not in different contexts. Seeking to measure only ‘results’ overlooks this and could even discourage innovations and risk-taking” (GEF and UNDP, 2015: page 44). To encourage SGP Country Programmes and communities to adopt innovative solutions, the SGP proposes to launch several programs to identify and support emerging new themes under its strategic initiatives. The SGP will combine its country-driven approach in terms of project identification and selection, with greater global strategic guidance, capacity development, and knowledge sharing on emerging issues. It also intends to scale up and mainstream successful practices on a global scale by leveraging partners that include philanthropic foundations, the private sector, and other donors. By coordinating with other GEF-7 Impact programs and multi-agency initiatives , the SGP plans to support various emerging issues, including inter alia: (i) community-based, artisanal, small-scale gold mining and mercury management; (ii) sustainable dryland management in the Sahel and other arid regions; (iii) community-based conservation of threatened landscapes and seascapes, including recognition of new governance types of conserved areas, and conservation of the habitat of iconic species; (iv) inclusive conservation approach partnering with indigenous peoples in the Congo Basin, Amazon and other globally important forests; and (v) women and eco-entrepreneurship to crowd in partnerships in support of sustainable value chains.

(d)	Promoting partnerships and broader adoption: scaling up and replication results

- Building on its mission, Local Actions, Global Impact, the SGP provides a network of local ideas and approaches that contribute to and influence policies and strategies at all levels. The Sixth Comprehensive Evaluation of the GEF (OPS6) highlights the success of broader adoption (e.g., scaling up, replication, and mainstreaming), demonstrated by SGP projects. Adoption of successful initiatives will continue to increase through the SGP’s CSO-Government-Private Sector Dialogue Platform and its Global Knowledge Platform (e.g., South-South cooperation, digital library, knowledge fairs), as well as by the creation of spaces for CSOs/CBOs to engage in policy and program development at the national and subnational levels. The SGP also will seek active partnership with relevant institutions to leverage resources and scale up its initiatives for more wide-reaching results and impacts.

(e)	Serving as a dependable global community-based grant mechanism and platform for the environment

- Building on its 25 years of experience, the SGP is well positioned to act as a dependable community-based and grant mechanism and platform to address global environmental issues in many developing countries. The SGP aims to strengthen its partnership and synergies with organizations and initiatives to effectively benefit CSOs and local communities at the global, regional, and local levels. The SGP also will liaise closely with the GEF Secretariat and GEF agencies on relevant programs and projects, including its Impact Programs and Programmatic Approaches, as well as Full-sized and Medium-sized projects, particularly in relation to community issues. The SGP has already played a key role as a community-based grant mechanism under several FSPs, such as the “child” projects under GEF Programmatic Approaches on Wildlife Management and International Waters and the Integrated Approach Pilot on Food Security. This collaboration between different modalities of GEF funding available to countries has created strategic linkages between SGP and other GEF projects at the country level. It is also intended to ensure that innovative local actions, supported by the SGP, will be scaled up at the national and subnational levels within the parameters of GEF FSPs.

- Objective and Strategic Initiatives

- The objective of the project is “to promote and support community-based innovative, inclusive and impactful initiatives and foster multi-stakeholder partnerships at the local level to tackle global environmental issues in priority landscapes and seascapes”.

- This objective will be achieved through several strategic initiatives as described below. In alignment with the overall GEF-7 programming, the SGP will focus its efforts on targeted strategic initiatives that promote integrated approaches in addressing key global environmental issues.  As an overarching strategy, the SGP will adopt and strengthen its landscape and seascape approach to focus and concentrate its programming on globally recognized important ecosystems (including Key Biodiversity Areas).  It will seek synergies, implement multi-sectoral approaches by involving communities at the landscape/seascape levels, and facilitate community actions to effectively manage the complex mosaic land/seascapes. The SGP will seek participation in further conceptualizing Impact Programs and relevant focal area programs

and projects, at the same time welcoming local community perspectives.

- Depending on country and stakeholder priorities under the updated SGP Country Programme Strategy, each SGP Country Programmes may elect to focus on only a few of the strategic initiatives to further sharpen the scope of SGP grantmaking and achieve greater strategic impacts.

Strategic Initiative 1 – Community-based conservation of threatened ecosystems and species: land and water

- Under this Strategic Initiative, the SGP will demonstrate for conservation and sustainable use of threatened ecosystems and species in priority landscapes and seascapes through an integrated approach in alignment with GEF-7 biodiversity, land degradation, and international waters focal area strategies and Impact Program on Sustainable Forest Management. The SGP grants under this strategic initiative will focus on both conservation and sustainable use: including management of protected areas and corridors, integrated river-basins, and large marine ecosystems with active involvement of communities (e.g. Indigenous and Communities Conserved Areas (ICCAs) and private protected areas) as well as mainstreaming biodiversity in key production sectors (e.g. agriculture, forestry, fisheries, and infrastructure).  Specifically, the SGP will support appropriate community-based measures that conserve biodiversity and support implementation of protected area/landscape management plans in priority landscapes or seascapes bringing under improved management at least 1.2 million ha of terrestrial PAs and MPAs.

- With the active involvement of civil society organizations (CSOs) and IPLCs, the project, under threatened ecosystems and species strategic initiative will focus on inter alia:

- Improved management effectiveness of terrestrial and marine protected areas and corridors; including Indigenous Peoples and Community Conserved Territories and Areas (ICCAs), private protected areas, KBAs and other effective conservation measures (OECMs);

- Improved community-led biodiversity-friendly natural resource use practices and approaches, including agriculture, fisheries, forestry, tourism, infrastructure, etc.

- Freshwater and integrated river-basin management, especially prevention, reduction and management of land-based pollution that flows into rivers and other freshwater systems.

- Community solutions in blue economy, including promotion of sustainable fisheries, aquaculture, eco-tourism and conservation and management of coastal habitats for sustainable community livelihoods.

- Enhanced community-led actions for threatened species conservation, including addressing human-wildlife conflicts.

- Access and benefit sharing of genetic resources, particularly in support of indigenous peoples’ traditional knowledge and customary rights.

During project period, SGP will also support better expression of the value of projects for ecosystem services and ecosystem-based adaptation as well.

43. The SGP will employ such approach that will promote a ‘polycentric governance’ approach, involving coordinated actions and interventions from different actors, including the government, communities, and private sector. Priority land/seascape areas will be identified taking into consideration partnerships with relevant GEF FSPs, as well as other projects and partners, to enhance local capacity to form regional networks of communities to deepen cooperation among stakeholders. Under this strategic initiative, the SGP will also be addressing cross cutting issues such as: (i) improving knowledge and information collection and management systems to enhance awareness about best practices on conservation of land and seascapes and their associated biodiversity and ecosystems through communication, documentation and dissemination; (ii) support community-based efforts to improve policies that support conservation and sustainable use; (iii) and ensuring gender considerations mainstreamed into natural resources management. The strategic initiative will  implement recommended actions under the SGP gender mainstreaming strategy including, but not limited to, making sure that gender and socially inclusive perspective is applied to all SGP grant making procedures and activities while also making sure that at the national and project level information is collected and shared across gender and social divides.

Strategic Initiative 2 – Sustainable agriculture and fisheries, leading to food security:

44. This strategic initiative will aim to test and promote community-based climate resilient agriculture, fisheries and food practices that improve productivity and increase ecological connectivity and deliver other benefits. The SGP will also promote community-based biodiversity friendly practices and approaches (agriculture, forestry, fisheries and infrastructure) through focusing the grant-making strategy to provide consolidated support to target sectors in previous SGP operational cycles. During project period, four specific areas of work will be supported including:

- Increased efficiency and effectiveness of overall environmentally sound food production and value chain, including certification schemes of organic agriculture, fair trade, and others;

- Agrobiodiversity conservation, including extending support to producer networks, movements and value chains among small-holder farmers

- Promotion of agroecological production methods, including diversification and improved livelihoods; and

- Community-based sustainable fisheries, including promotion of traditional fisheries practices and knowledge

- Implement community-based actions to remove deforestation from supply chain and expand restoration of degraded lands.

- Special attention will be given to agriculture in fragile ecosystems, including mountain communities to improve livelihoods of mountain peoples.  Specifically, under the project, the SGP will work with local farmers and fishers to promote and shift to sustainable agricultural production, support transformation of consumer level production systems and re-focusing attention to increasing efficiency and effectiveness of overall food production and value chain addition processes both on-farm and off farm. In addition, support will be provided for integrated projects that aim at restoring ecosystem services or reducing the negative environmental trends such as land degradation and deforestation, biodiversity loss and climate change emissions induced anthropogenic activities on land. This strategic initiative will also aim at promoting diversification and improved livelihoods, such as through water harvesting, post-harvest management, business skills development to empower communities to better manage their natural resources and lead to global environment benefits.

- This outcome will develop and implement several community-based sustainable land management actions that integrate climate resilient sustainable practices and other standards (e.g. land tenure, community participation). These will be complemented by at least 2 CBOs/farmer leaders adopt and demonstrate improved climate resilient SLM practices per landscape. In this way, more than 1.24 million ha of landscapes and over 50,000 ha of marine habitats will be brought under improved management and/ or restored for multiple benefits while appropriate and improved SLM technologies will be applied to at least 140,000 ha. Beyond that the SGP will support the community level measures that promote sustainable fisheries including appropriate efforts to promote a ridge to reef approach by linking coastal zone management and land use activities in up lands with marine habitat use and management. Under this strategic initiative, the SGP will work with women entrepreneurs and women led organizations as well as farmers, focusing on agricultural production through improved yields, value addition processes and helping farmers (men/women) to better market their farm products at the right time and with proper prices. Gender roles will be identified and integrated into training and other SGP interventions (e.g. on post-harvest technology to reduce loses in agriculture production).

Strategic Initiative 3 – Low-carbon energy access co-benefits:

- Under this initiative, the SGP will aim to demonstrate and scale up low carbon, viable and appropriate technologies and approaches demonstrated and scaled up in partnership with private sector and government that improves community energy access, in line with larger frameworks such as SDGs and NDCs. The focus will be on providing low-cost bottom-up energy solutions with high potential for carbon emissions reductions using integrated approach going beyond energy sector aiming at increasing climate resilience, reducing poverty, enhancing gender equality and achieving the sustainable development goals. Such solutions will continue to form a crucial part of the “decarbonization” and transition to low carbon economy, while laying the groundwork of new infrastructure at community level, addressing energy service needs of rural, urban and remote communities and entrepreneurs, who cannot be served by the central grid in case of electricity or centralized distribution systems in case of cooking and heating fuels. SGP will continue documenting community innovations, tracking typologies of new community technologies, particularly those emerging from South-South exchanges.

- In supporting community level actions for implementation of the Paris Agreement with an increased focus on the NDCs, SGP will focus on the following initiative under this strategic initiative:

- Promotion of renewable and energy efficient technologies providing socio-economic benefits and improving livelihoods, including innovative and catalytic financing.

- Support off-grid energy service needs in rural and urban areas.

- SGP will utilize its proven mechanisms such as the CSO-Government-Private Sector dialogues to galvanize a ‘whole of society’ effort to raise the ambition for climate action, hold local and national governments accountable to the NDC climate measures and ensure inclusion of community voices and priorities in any national and/or local efforts to implement the NDCs. To ensure this complementation, all SGP country program will be required to hold consultations to assess the status of NDCs development and implementation in a respective country and conduct at least one CSO-government-private sector dialogue focusing on NDCs during the project period. In the countries, where NDCs implementation is at the initial stages and/or facing challenges, the dialogue may serve, at a minimum, to familiarize stakeholders with the key aspects of climate policies and create awareness.

- Moreover, the focus on low-cost bottom up energy solutions will ensure that significant co-benefits are generated from supporting energy access that contribute towards the achievement of the SDGs. In continuation of efforts of the SGP to identify, describe, measure, and quantify the co-benefits of the decarbonization interventions, during the project period, the SGP will build on this knowledge and broaden its focus to document the links between Paris Agreement and 2030 Agenda at the local level. Several recent studies demonstrated that climate actions highlighted in the NDCs also have the potential to generate mutual benefits across the 17 SDGs. In this vein, SGP will conduct pilot studies in select countries using new tools and approaches developed by UNDP and partners to demonstrate such links at the local level.

- SGP will support innovative technologies and approaches with initial catalytic financing and then encourage wider deployment and scaling up.  The absence of effective local applications, tailored to the country and community context, often constitutes a barrier for adoption of low carbon technologies, even in developed countries, despite the availability of certain technologies globally. SGP will support innovative technologies and approaches with initial catalytic financing and then encourage wider deployment and scaling up. SGP will focus on capacity building, knowledge management and systematization, putting in place enabling frameworks and mechanisms at the community level and will partner with national and global initiatives to ensure that innovations are implemented based on programmatic approach creating larger impacts. Continuing the efforts started previously, the SGP will also focus on building partnerships with larger initiatives in order to scale up successful innovations to national and global level.

Strategic Initiative 4 – Local to global coalitions for chemicals and waste management:

- The SGP will aim to demonstrate, deploy and transfer innovative community-based tools and approaches to sound chemicals and waste management, with support from national and international partners, networks and platforms. Under this the SGP will focus its support towards communities in the forefront of threats related to chemicals and waste either as users or consumers.  Activities will include support for innovative, affordable and practical solutions to chemicals and waste management in joint effort with partners including with government agencies, research institutions, private sector and international agencies.  The SGP will seek to establish systems of local certification of producers and/or their products, which could then expand to the national level through producer-consumer agreements scaled up to national policies.

- The SGP will consolidate its work particularly on pesticide management, waste management, and mercury, and work with partners to promote local to global coalitions and networks that could effectively bring local knowledge and experiences to policy dialogue and vice versa.  SGP will also build on its successful previous projects on community-level artisanal and small-scale gold mining in reducing/eliminating use of mercury, and coordinate with the related GEF programs for further replication and scaling up. During the project period, the SGP will develop a viable portfolio on community-based circular economy and plastics management and continue engagement with at least two local-to-global coalitions and networks, including Basel, Rotterdam and Stockholm Convention Secretariat, governments, the private sector, and local to global NGOs. Other chemicals of global concern (e.g. mercury) and their waste will also be reduced, disposed, eliminated and avoided through targeted initiatives while a comprehensive awareness and outreach strategy for sound chemicals and waste management will be implemented all SGP countries.

- During the project period, among others, SGP will focus on the following four areas of support:

- Prevent or reduce mercury use and promote alternative to mercury in Artisanal and Small-scale Gold Mining (ASGM) –implemented mainly through a global innovation program on ASGM and mercury management, the SGP will support 1-2 community projects on ASGM in around each of the 5-6 country programs, including eight GOLD participating countries and 1-2 active SGP country programs. Indicative activities include piloting and testing mercury free technologies and innovation in artisanal gold mining; measures to reuse/recycle mercury to reduce emissions in ASGM and training and demonstrations to miner communities in precautionary measures to reduce negative health effects; awareness and knowledge sharing to facilitate cross-community learning;

- Plastics, solid waste management and circular economy – SGP will support local communities and grassroots solutions contributing to the implementation of the plastics management and circular economy by providing circular solutions to plastic waste problems through community-based actions to “reduce, reuse and recycle” plastics, known as “3Rs” ranking by the priority of actions. Priority actions will focus on reduction of plastics and development of alternatives to plastics so that the tap source of pollution will be turned off. The types of activities may include: 1) material engineering and product design to promote 3Rs; 2) consumer use and behavior shift due to campaigns, awareness raising and capacity development; 3) waste collection and management to avoid open burning of solid waste;

- Reduce/remove chemicals in sustainable agriculture – SGP will support community level measures for the production and use of organic manure, including organic waste collection and composting to reduce the use of chemical fertilizer, production and application of organic and natural pesticides to replace the use of pesticide and other innovations to reduce pesticides use in agriculture;

- Enhance local to global coalitions on chemicals, waste and mercury management – SGP will continue collaborations with the European Environmental Bureau’s Zero Mercury Working Group and the International POPs Elimination Network to develop and strengthen local to global coalitions on chemicals, waste and mercury management to ensure actions at local, national and global level are connected, coordinated and mutually re-enforcing.

- Under the chemicals and waste management portfolio, many projects have been led by women (these cases were well documented in the SGP publications: “Community-based Chemicals and Waste Management” and the publication “Plastics and Circular Economy: Community Solutions”). While we recognize the importance to engage most vulnerable and marginalized groups in the projects, it is also concerning to point out that waste management, especially informal waste picking and sorting, is often undertaken by women, youth and disabled people who cannot find more profitable, cleaner and respectable jobs, and could also reinforce negative social norms and roles. In GEF-7, SGP under this strategic initiative will focus on organizing and formalizing the waste management sectors informally managed by poor women and help them to develop income-generating activities models such as organic farming, recycling, waste to resource production, and alternative livelihoods, such that SGP interventions support gender transformations rather than entrenching established gender roles. Furthermore, SGP will continue promoting awareness raising, capacity development and networking among women for sound chemicals and waste management.

Strategic Initiative 5 – Catalyzing sustainable urban solutions:

- This strategic initiative will support the promotion of appropriate integrated community-oriented sustainable urban solutions in partnership with private sector and government. In doing so, the SGP activities will align with and contribute to the GEF Sustainable Cities Impact Program. The SGP will pilot activities to target vulnerable people and communities in urban contexts. During the rapid urbanization process, traditional connections, linkages and networks among local communities can be disrupted and lost, making urban environmental governance more challenging. The SGP will promote an integrated management approach to address urbanization challenges from the point of origin (i.e. in rural areas and migration corridors) to the destinations of people’s movement during this urbanization transition.

- Under this strategic initiative, during the project period, SGP will focus on:

- Improved capacities to promote community-driven, socially inclusive and integrated solutions to address low-emission and resilient urban development by strengthening capacities of key service providers at the local municipality level to promote community-driven and integrated solutions to address low-emission and resilient urban development. These solutions will cover at least 12-13 SGP countries.

- Demonstrate innovative socially-inclusive urban solutions/ approaches (including waste and chemical management, energy, transport, watershed protection, ecosystem services and biodiversity). This will involve working with various sectors and actors including the private sector, in at least 12-15 countries, the SGP will demonstrate selected urban solutions addressing several key urban environmental issues – these may include waste and chemicals management; urban wetland and watershed management; energy and transport; and ecosystem services and biodiversity conservation.

- Promote public-private partnership approach to sustainable urban solutions for marginalized urban communities. In several countries the SGP will develop and implement a viable public-private partnership approach to sustainable urban solutions for marginalized urban communities. Private sectors will be actively engaged and leveraged to support this strategic initiative.

- Under catalyzing sustainable urban solutions, women as a subsection of the population, particularly with the current migration trends from rural/peri- urban areas to urban areas, are most vulnerable to access to basic services and negative effects of environmental, social and economic impacts. SGP will place an emphasis on building capacities as well as a gender equity-based access herein. This will include support to entrepreneurship, in green jobs, development of new partnerships of private sector- communities and government to support engendered access to green microfinance, skills development and using community evidence to support policy level changes and scaling up of initiatives.

Cross cutting initiatives:

In addition to the above thematic strategic initiatives, SGP will deploy the following cross-cutting initiatives as Grantmakers Plus and social inclusion activities to further enhance innovation, inclusion, and impact. With respect to the grant maker plus initiatives, while programming directions and procedures are defined at the global level, the actual activities are identified, planned and implemented at the country level applying the same process as all SGP grants. As such all resources ear-marked as grant-maker plus will be delivered as grants to appropriate CSO/CBO grantees.

1. CSO-Government-Private Sector Policy and Planning Dialogue Platforms:

- The aim of this is to ensure that community voices and participation are promoted and enhanced in the global and national strategy development related to global environment and sustainable development issues. During the project period, the SGP will expand its innovative CSO-Government Dialogue Platforms towards a greater engagement of private sector to leverage its potential to invest and support sustainability at the local level.  These platforms will also provide opportunities to discuss possible shifts in relevant policies and practices to promote sustainability. At least 1 national-level targeted CSO-Government dialogues will be convened in each country to support policy and planning development of the government and key stakeholders. At the international level, around 4 global CSO-government and other stakeholder dialogue on the global environment will be organized while to expand the dialogue platform for greater engagement of private sector. At the national level, around 10 CSO-government private sector/business forum will be facilitated to foster CSO-Govt-private sector dialogue on environment.

2. Enhancing social inclusion

- The SGP is well recognized for its inclusive approach that promotes social inclusion and equity by working and engaging with women, youth, indigenous peoples and persons with disabilities.  It will further enhance its approach to champion and advocate for the involvement and active participation of vulnerable groups as key stakeholders for environmental action and advocacy. This strategic initiative aims to ensure that social inclusion, particularly empowerment of women, indigenous peoples, youth and persons with disabilities, is further enhanced through both specific initiatives/projects that targets these populations as well as mainstreaming inclusive approach through all SGP projects on environment and livelihood improvement.

- The SGP Country Programmes will actively support actions to promote women’s role in implementation of projects and promote gender equality and women’s empowerment relevant to the local context.  To this end, all SGP country programmes will ensure that gender mainstreaming considerations are applied consistently. SGP will contribute to the GEF gender strategy by the following: concrete contributions will be made to close gender gaps in access to and control over resources in at least 30% of SGP new portfolio; at least 30% of SGP projects are led by women or institute mechanisms for increased participation and decision-making by women; women and girls constitute at least 50% of beneficiaries of all SGP projects.

- On Indigenous Peoples, SGP will expand the Indigenous Peoples’ Fellowship Program, and further build capacity of IPs through targeted support for IPs to have an increased role in the decision-making in relevant countries. Further, in alignment with the GEF 7 biodiversity focal area on inclusive conservation (i.e. role of ICCAs to the CBD Aichi and post-2020 Targets), and in complementarity with efforts to increase IPs engagement with climate mitigations efforts (i.e. CBR+ and other REDD+ standards), the SGP IP Fellowship program will be expanded to include IPs across a range of SGP national-level activities including inter alia: (i) governance and membership of National Steering Committees (NSCs); (ii) SGP country programme strategy (CPS) development, including a dedicated funding window and/or call for proposals from IP organizations as relevant; and (iii) monitoring and evaluation of SGP project outputs and outcomes, including culturally-appropriate formats and methodologies.

- The SGP will continue to demonstrate the involvement of youth in SGP projects in at least 30 to 35 percent of its projects. Guidelines and best practices on engaging youth will be developed and widely shared with countries. SGP’s youth approach will be realized through systematic piloting in participating countries. Grantmaking will include direct project level investments in priority landscapes and seascapes incorporating youth theory of change for a selected few projects through both working with youth as individuals and as organizations/ networks/ councils tackling global environmental issues. Support to capacity Development will include investments in skills trainings, mentorship programmes, and channeling youth perspectives in community, national and international discourses- this will usually be provided through a grantee organization with a focus on youth and through global and regional partnership such as with the UNDP Youth Co-Lab and the INYD. Youth activities will also be integrated in SGP grant-maker plus initiatives such as promoting CSO/youth-government dialogues and ensuring that certain IP fellowships go to IP youth. SGP will also venture into developing youth thematic focus such as in climate change and urban waste management. The Youth Global Video competition on climate change in partnership with UNFCCC will serve as an important starting point. Efforts to distill and codify key lessons and promotion of effective partnerships with local networks and coalitions and engaging private sector, academia, media etc. will leverage SGP grant making results.

- Finally, with regards persons with disabilities (PwD), SGP programming will demonstrate and generate lessons and good practices on how environment related projects have the potential to actively promote participation of PwD to ensure concrete results on both environment and socio-economic issues. Engagement with disabled persons organizations will enable integration of important perspectives from the disable communities into guidelines. SGP grant-making will entail support to community projects with PwD that brings together cross-sectoral implementation of the SDGs as well as the consideration of the “Sendai Framework” on Disaster Risk Reduction and Recovery (DRR&R).  Working with a disability focused organization, SGP will also support capacity development including training to proponents on appropriate project design and monitoring and evaluation.  In the spirit of integration, SGP will invest in efforts to promote integrated approaches that address all social inclusion aspects – gender, youth, indigenous peoples, PwD – wherever possible, feasible and appropriate.

3. Monitoring and Evaluation

- During the project period, SGP will develop a common, robust M&E and knowledge management strategy is implemented in all countries. Building on the recommendations of the 2015 Joint GEF-UNDP Evaluation, efforts will be made to improve existing M&E, design more streamlined and useful tools and activities that balance the need to measure and capacity of local CSOs and communities.  SGP will revamp its Results Based Management Strategy, capturing key objectives, processes and responsibilities. An online database to support generation of both quantitative and qualitative analytics will be undertaken. The SGP will also monitor, measure and report its contribution in alignment with 7 of the 11 most relevant GEF-7 results framework and indicators (please see relevant section 6 Monitoring and Evaluation Plan for further details).

4. Knowledge Management

- The objectives knowledge management in SGP are to: capture knowledge, leverage local expertise and give voice to civil society, identify new approaches and ways of learning, improve effectiveness, improve capacities of staff and grantees, promote and encourage innovation, address operational and programmatic challenges effectively, influence policy and scale up good practices.

- To implement the SGP knowledge management system, different actions at the three levels of global, national and project level are envisaged. At the global level, SGP provides guidance on how to capture and disseminate knowledge and conduct knowledge exchange at the local level so that it can be aggregated at the global level; shares technical publication and provides guidance of each focal and cross cutting areas of work; organizes regional workshops to exchange knowledge and provide training to its staff; and shares good practices emerging from the portfolio at global conferences and events. SGP also establishes partnerships with a variety of partners to upscale best practices in environmental conservation and and works to capture and disseminate the lessons learned and best practices of its massive portfolio in case studies, fact sheets, publications, and new media. Below is a description of key KM practices done at the global level. Key global level knowledge management practices include: the knowledge management platforms including the digital library of community innovations, communities connect platform; bringing CSO voices to global forums; Portfolio reviews and case studies; Best practices; Coaching and mentorship; Story-telling, mapping technologies and expert locators; and communities of practice (CoPs).

- At the national level, each country programme composed by a National Steering Committee, a National Coordinator and sometimes a Programme Assistant, work directly with the communities in (i) capturing their lessons; (ii) conducting knowledge exchanges; (iii) organizing training workshops; (iv) establishing and nurturing networks of NGO’s and CBO’s; (v) working with the government in achieving national environmental priorities; (vi) and helping to scale up and replicate best practices and lessons learned. Each country programme outlines a knowledge management plan as part of their Country Programme Strategy for each operational phase of the programme. In addition, country programme teams provide guidance and develop capacity of local communities and standardize the uptake of information, lessons learned and best practices. Based on these experiences, country programmes routinely produce knowledge materials in local languages, including project fact sheets, informational brochures and case studies, to disseminate at key national events and conferences. Some of the specific activities carried out at the national level include: knowledge fairs; stakeholder workshops; creating or strengthening networks; centres of excellence or demonstration sites; training and how to manuals; leverage the NSC and knowledge broker.

- At the project level, each project needs to include a knowledge management plan with a corresponding budget that allows the programme to capture their experience as well as to access the training needed to carry out the projects. Knowledge management activities at the project level could include peer to peer learning, training and facilitated exchange of knowledge.

- Thus, under GEF-7, specific knowledge management initiatives will be envisioned to strengthen project and country level activities with a focus to scale up, replicate and mainstream successes and disseminate the learnings.  At the global level, knowledge exchanges and innovation will be promoted through SGP’s revamped knowledge platforms: The Digital Library of Community Innovations and the South-South Exchange Initiative. The digital library is an effort to document and curate the innovative solutions developed by indigenous peoples and local communities to environment and sustainable development challenges. The SGP will partner with relevant organizations to expand the reach and use of these practices.

- The South-South Exchange initiative will continue to support knowledge transfer and exchange across countries and regions encouraging replication of good practices supported by the portfolio. These initiatives produce high impact and scaling up of the innovations and practices developed by SGP grantees, as well as other CSOs at the regional level. Another is Communities Connect, a collaborative platform started in partnership with the GEF CSO Network, to promote the solutions created by communities and civil society organization to sustainable development issues which will be revamped and strengthen during GEF7 period.

- The goal of the South-south cooperation initiative is to support communities in mobilizing and taking advantage of development solutions and technical expertise available in the South. In this regard, learning opportunities and technology transfer from peer countries will be further explored during project implementation. This complements current SGP grant-making results, as the south-south initiative will support the achievement of impactful results and scaling up of the innovations and practices developed by SGP grantees, as well as other CSOs at the regional level, as currently all grant making, and associated knowledge exchange happens at the national level. SGP will partner with relevant UN and other agencies as appropriate, including the UN Office for South-South Cooperation, the UNDP South-South Exchange Platforms, and other organizations, such that activities by partner organizations are complemented and a critical mass of south-south knowledge exchange is created during the project period.

- Alignment with GEF focal area and/or Impact Program strategies

- As a GEF corporate programme, SGP has always aligned its strategies to that of the GEF with the expectation that its role is to translate such strategies to community and local CSO actions and provide a testing and evidence base for further scaling up. SGP contributes to achieving GEF’s strategy outcomes by supporting innovative initiatives at the level of communities. The results framework SGP and associated targets for global environmental benefits will also align with the overall GEF-7 results architecture.

- During GEF-7, a key vehicle for the GEF to help countries pursue holistic and integrated approaches for greater transformational change in key economic systems, and in line with their national development priorities are the Impact Programs. These collectively address major drivers of environmental degradation and/or deliver multiple benefits across the many thematic dimensions the GEF is mandated to deliver. The Impact Programs also contribute in significant ways to each of the Focal Area Strategies while at the same time delivering multiple benefits across several MEAs.  As noted in the GEF Council approved paper on  GEF Small Grants Programme: Implementation Arrangements for GEF-7, SGP will seek to coordinate and provide community-level inputs to the Food, Land Use, and Restoration Impact Program through its activities under the Strategic Initiative on Sustainable Agriculture and Fisheries, while the approaches under the Strategic Initiative on Catalyzing Sustainable Urban Solutions will be implemented and closely aligned with GEF−7 Impact Program on Sustainable Cities.  Modality for coordination will be further explored as the Impact Programs are being designed.  Initial discussions on synergy with the Sustainable Forest Management (SFM), Food and Land Use and Restoration (FLUR), and the Sustainable Cities impact programs are underway.

- In order to enable strategic investments that are strongly aligned with the GEF focal area and Impact Programs, SGP grantmaking at the country level will be implemented based on the Country Programme Strategy (CPS) that further clarifies alignment based on country specific context. The SGP CPS will be prepared by each country to enable country-driven and integrated investments at the country and landscape/seascape levels. In all countries, the CPS development process will be undertaken in a consultative manner to identify SGP's value added within the priority global environmental issues in line with the concerned MEAs and national policies and plans to guide SGP grantmaking and ensure its complementarity with other donor and country supported initiatives. The SGP CPS will ensure that the SGP grant-making strategy is consistent with the GEF-7 Programming Direction and specific focal area strategies.  For example, in Biodiversity, the project will support the CBD's Aichi targets, those related to protected areas (11), ecosystem services (14) and traditional knowledge, innovations and practices (18), and contribute to the negotiations and development of the post-2020 targets to be agreed upon at CBD COP15 in China in 2020. During GEF7, SGP will contribute directly to the relevant GEF core indicators such as the area of terrestrial and marine PAs under improved management and governance effectiveness, area of landscapes/seascapes under improved management to benefit biodiversity and ecosystems. Similarly, for Land Degradation, SGP initiatives will contribute to the Land Degradation Neutrality (LDN) and promote sustainable agriculture, fisheries and food systems at the community level through improving productivity, livelihoods diversification and improvement and promotion of technologies such as sustainable land management, harvesting, post-harvest management, business skills development to empower communities to better manage their natural resources. It will contribute directly to GEF-7 core indicators such as the area under SLM. Likewise, SGP programming at the country level will be in alignment with and contribute towards the achievement of the country’s NDCs including as appropriate supporting community-level actions to enhance ambition and delivery of NDC measures at the local level.

- Incremental/additional cost reasoning and expected contributions from the baseline and co-financing

- The SGP provides support to communities and CSOs in their work to contribute to both local and global environmental benefits. A defining characteristic that differentiates the SGP from other GEF programs is its ability to function as a demand-based type of support modality, thereby engendering strong community/country ownership. This is evidenced by the strong global environmental benefits (as described under the results section above) that are derived from the SGP operations at the local and national scales.

- Furthermore, the SGP is an excellent facilitator of replication of innovations supported by the GEF. The GEF IEO 2015 evaluation report demonstrated broader replication in GEF by describing how replication of SGP innovations occurs at different scales – from local to national, to global levels. Replication of innovation is often identified at the local level from neighbor to neighbor, ultimately being mainstreamed at the local scale, wherein local governments integrate SGP interventions into their plans and strategies. The same IEO report cites an example of how SGP grantees in Uganda worked with the local governments to introduce and implement waste management programs -- the results of which directly helped attract additional investment, including from the World Bank. Similarly, broader adoption at the national level is facilitated by the SGP through influencing national government policies and frameworks. For example, SGP support to community-based PA management in Jordan resulted in wider changes in the protected area laws in the country. In some cases, promising innovations of the SGP are picked up by multi-lateral development banks (MDBs) for large scale replication – a case in point being the scale up of an SGP grantee project on sustainable extraction of oil from coconuts by the Inter-American Development Bank in Panama.

- Without the GEF support through SGP grant-making, building on the strong results on environmental protection, rehabilitation and overall sustainable development delivered so far, replication and scaling of innovations that have been nurtured by the SGP will not be taken to the next level. The baseline scenario described shows that much more needs to be done as increasing populations of poor and vulnerable communities try to increase their agricultural productivity, access energy, and use fisheries, often-times through unsustainable means, further jeopardizing their livelihoods and the ecosystems these depend on. While many developing country governments have started to put more resources to local development and to CSOs as partners, the demand for socio-economic development coupled with the lack of awareness, as well as mechanisms to integrate this demand to similarly compelling environmental concerns, have led to an imbalance in the allocation that is inimical to environmental needs. Moreover, for many disadvantaged groups including Indigenous Peoples, the SGP remains one of the only sources of concrete support. This is true even in the case of the GEF, as supported by a dedicated GEF Independent Evaluation Office (IEO) brief that assessed the engagement of the GEF with Indigenous peoples.

- In addition, the SGP has formed robust and mutually beneficial long-standing partnership with a broad range of international, national and community-level initiatives and partners. The SGP will strengthen these partnership models, including with a possibility to strengthen donor platform coupled with a proven decentralized delivery mechanism.  The program will actively seek closer coordination and synergy with relevant partners, including foundations and the private sector. This is a win-win for all parties as the tried-and-tested mechanism can effectively and efficiently support delivery of community-level interventions for GEF FSPs and other large-scale initiatives. This is fully supported by the findings of the GEF IEO 2015 evaluation report which underscores that “good integration of well-established SGP national programs with the respective overall GEF country portfolio—possibly through a formal mandate to deliver the community-level components of GEF projects with the active participation of local communities—can increase the likelihood of sustainability and generate cost savings to the GEF as a whole”.

- Beyond that, the SGP will mobilize partnership for complementary activities that support further scaling up of community-based initiatives building on the strong collaboration established with the governments of Australia, Germany, Japan and Norway among others.  Further, the SGP will work with the private sector to upscale pilot innovations to the mainstream as discussed above. The SGP will act as an incubator helping to connect successful and promising initiatives with other channels for continued support while advocating for enabling environment and supportive policies. Finally, the SGP will actively promote linkages with relevant GEF-7 Impact Programs and Focal Area programs for cooperation and complementarity.  The SGP will seek to develop coordination mechanism with the relevant programs at the global and country levels and continue to identify opportunities to share successful methodologies and approaches and to support implementation of community components of GEF Full-sized and Medium-sized Projects. Evaluative evidence gathered from many countries and stakeholders supports such a role for the SGP. According to IEO 2015 report the SGP “has been cited as an effective channel to share information and raise awareness among stakeholders at the local level in a number of countries”

# Results and Partnerships

- Expected Results

- The GEF SGP provides support to achieve global environmental benefits at the community level.  The SGP strengthens the capacity of communities and civil society organizations, increases their knowledge and awareness about environmental threats, and provides them financial support to overcome short-term decision-making that negatively affects environmental resources. In this way, SGP delivers five key categories of development results, often interrelated namely: (i) global environmental benefits; (ii) socio- economic benefits; (iii) innovation; (iv) capacity development; (v) broader adoption of SGP (scaling up, replication, mainstreaming and policy influence). Moreover, within the GEF, UNDP, and other agencies, tested SGP approaches, lessons learned, country staff, and stakeholder networks have become resources in the design and/or implementation of larger projects.

- In line with SGP’s overall objective to secure GEBs through community-based initiatives and actions, SGP will continue to support projects that render high levels of success in securing global environmental benefits. In this regard with the GEF-7 funding, SGP has plans to deliver the following global environmental benefits under the current project:

- On biodiversity, grant-making approach will target to improve management and governance effectiveness of 1.2 million hectares protected areas and indigenous and community conserved areas (ICCAs) including significant area of marine habitats and marine PAs (estimated around 50,000 ha). Such measures will also include community level biodiversity compatible practices in production landscapes and seascapes.

- On climate change mitigation, SGP portfolio will apply low carbon technologies that will target around 7500 households and increase installed total renewable energy (RE) capacity of 150 KW from around 25 technologies that will be demonstrated. SGP interventions will also support 7500 hectares of forest restoration/avoided deforestation. Likewise, for sustainable urban solutions, SGP will identify, test and demonstrate around 25 innovative integrated urban energy solutions.

- On land degradation, around 240,000 hectares of land (forest, agricultural and other production sector lands) will be brought under improved management practices, including at least 50,000 hectares of marine habitats that will be positively impacted; improved SLM technologies at the farm level will be applied to around 140,000 hectares while several CBO/farmer leaders will be established to promote and demonstrate climate resilient SLM approach.

- For international waters, efforts will be implemented to curb land-based pollution, including solid waste, sewerage, waste water, and agricultural waste from entering the waterbodies, and open burning avoided, will be continued (target to be assigned). This will benefit around 50,000 ha of marine habitats.

- On chemicals and waste management, a total of 150 tons of POP containing products/materials will be removed or disposed while a comprehensive strategy to deal with all chemicals of global concern will be implemented together with an awareness and outreach strategy on sound chemicals management in all countries.

- SGP will implement sustainable urban solutions related activities in at least 10 countries piloting at least 10 different urban solutions to address significant urban environmental issues from the community end.

- Beyond the global environment benefits, SGP will deliver the following important results through the project:

- SGP interventions will directly impact 200,000 beneficiaries out of which 50% are female through enhanced capacities and improved livelihoods and lives

- SGP will support CSO-Government-Private Sector dialogues in at least 25 countries to have scaled up policy impact

- Under social inclusion, the SGP will ensure that 30% of its projects are led by women, that at least 50% of all SGP beneficiaries are women

- At least 20 percent of relevant SGP country programs integrate appropriate models to engage youth and 15 percent of countries have targeted support for indigenous peoples;

- At least 15 countries will undertake south-south exchanges such that cross-fertilization and learnings between communities, CSOs and other partners are promoted;

- The discussion in earlier sections on SGP strategic approaches and initiatives for GEF-7 describes an enhanced set of strategies to ensure that SGP contributes to GEBs at multiple levels, starting from the global level, prioritized at the national level through the CPS, and translated into small grant actions in the field. Firstly, SGP priorities will be fully aligned to that of the GEF-7 Programming Directions Paper and its outcomes to meet the GEF-7 targets. Secondly, greater attention will be focused to creating synergy among individual projects using landscape or seascape approaches, as well as taking all opportunities for complementation with larger projects of the GEF and other donor agencies. Thirdly, SGP local initiatives will link to global initiatives and platforms as well as fostering joint efforts with global networks. Finally, the implementation of “Grantmaker+” set of roles has been designed to support scaling up, mainstreaming and replication that will provide higher level capacity development (i.e. IP Fellowships), networking and institutional support, knowledge sharing (e.g. through South-South exchanges), and advocacy mechanisms at national levels (i.e. CSO-Government-Private Sector Dialogue Platforms), and where relevant, all of these to extend to regional and global levels.

- In terms of results measurement, data will be captured at the project (grantee level) with each of the SGP projects electing results to measure from a roster of indicators including GEF 7 core indicators, socio-economic indicators. A strengthened database will support aggregating these results at the country level that will require timely entry of data on all projects. The annual country report produced from this will serve as a useful tool to benchmark overall progress of the country programme against the objectives set in the CPS, allowing each country programme to take appropriate and adaptive management decisions. At the global level, efforts will be made to track and report on progress on impacts achieved at the global programme level, by monitoring targets and indicators as indicated in the Results Frameworks. Annual Monitoring Reports will be prepared based on this data to assess the overall implementation and achievement of results of the global programme. In addition, SGP will produce global portfolio monitoring and thematic portfolio reviews including impact reviews as appropriate.

- Partnerships

- SGP grants are never implemented in isolation but are rather embedded in a web of partnerships that extend from the local to the national to the global. SGP partnerships have increased broad-based support for global environmental and sustainable development approaches and policies. They have enabled capacity development and learning at different levels; leveraged both financial and technical resources to strengthen programmatic approaches as well as individual projects; and helped to ensure the sustainability of initiatives. SGP synergies with partners have allowed them access to SGP staff, resources, methodologies, tools, knowledge, and experience, making the partnerships mutually beneficial.

- Partnerships with local and national governments, other donor programs and projects, the private sector, and NGOs and CBOs contribute in-kind or financial resources that allow GEF SGP projects to fully cover sustainable development objects that are critical for their success.  They have also provided financial resources for essential programmatic activities that cannot be undertaken with GEF funds. SGP dedicates efforts to build strong partnership with specific national level organizations including Indigenous Peoples Organizations as a successful targeting strategy to not only raise awareness about SGP project opportunities but to also coordinate strategic efforts in resource mobilization and policy impact.

- In line with the partnership-based approach, SGP will work international partners especially in the biodiversity area such as: (i) voluntary IUCN Commissions, including the World Commission on Protected Areas (WCPA), Commission on Ecosystem Management (CEM), and Species Survival Commission (SSC) which has a number of specialist sub-groups working on particular species; (ii) Global ICCA Consortium, a membership-based coalition of grass-roots CSOs working to support the objectives of the CBD; (iii) Birdlife International’s network of site support groups (SSGs); (iv) Fauna and Flora International (FFI), active in supporting locally-managed marine areas; (v) The Nature Conservancy (TNC), including with respect to private protected areas and marine conservation area spatial planning ; as well as (vi) the Wildlife Conservation Society (WCS), who have strong comparative advantage in relation to baseline scientific assessments and wildlife monitoring techniques.

- Within UNDP, collaboration will be explored with the ‘Lion’s Share Fund’ working with private sector companies that use threatened species as part of their logos and/or marketing campaigns. Partnerships may also be established with Medium of Full-Size GEF projects, either through UNDP and/or other accredited GEF agencies, in support of GEF7 Impact programmes, including for example with respect to the Sustainable Forest Management, the Sustainable Cities and the Food Systems, Land Use and Restoration impact programs. In this partnership approach, SGP will continue exploring opportunities to serve as a delivery mechanism for GEF full-sized projects as well as large projects and programs of other donors, funding facilities, and national governments. SGP achieves greater impact in GEF’s focal areas by incorporating and expanding the community-based approach to the design and implementation of medium-sized or full-sized projects.

- SGP will continue to build synergies and align interventions with development partners including the World Bank, regional development banks, bilateral agencies and GEF full size projects to scale up successful innovative initiatives. In the climate change area, the alignment with NDCs will help bring SGP interventions to scale and integrate them into national energy and climate policies. Wider application of the CSO-Government- private sector dialogue instrument will also help initiate new partnerships and inform national policies. These larger initiatives will provide a platform for scaling up SGP work as well as possible co-financing and joint efforts in national and global planning and policy advocacy. SGP will also encourage strong partnerships with the private sector to co-finance and eventually commercialize successful projects with the aim to shift renewable energy interventions from pilot innovations to the mainstream. SGP is also collaborating with global and regional organizations to leverage resources to implement and scale up community-based actions, in specific geographic regions and/or thematic areas. Many such collaborations are underway including with the SOS-Sahel, with the Slow Food International and FAO Mountain Partnership on sustainable mountain products, with the Caribbean Biodiversity Fund (CBF) etc. In implementing these collaborations, SGP and the partnering organization commit parallel resources that are utilized to fund joint initiatives in the target countries, thereby achieving increased efficiency and synergy in scaling up successful community driven and innovative activities.

- At a global level, CPMT is developing partnerships with leading research institutions to inform the design and outcomes of small-scale energy investments to maximize impacts and sustainability as well as measure results effectively. Likewise, in sustainable chemicals management, the SGP will seek to work with GEF GOLD program, UNEP, UNDP and others to ensure linkages and synergies of project activities in the field and facilitate sharing and learning. SGP will continue working with IPEN and Zero Mercury Working Group to promote local to global coalitions. CPMT is also investing in exploring partnership for potential funding from the Green Climate Fund (GCF) for Indigenous Peoples. Building on the UNDP collaboration with Climate Justice Resilience Fund (CJRF) and Tebtebba on IPs engagement with GCF, CPMT led a global consultation workshop at COP22, Marrakech (UNDP, Tebtebba, CJRF, partners) followed by several national level engagement with GCF National Designated Agencies (NDAs) in target countries. The aim is to motivate for a dedicated call for proposals for IPs while building capacity for IP organizations to access such funds.

- Partnerships among GEF SGP grantees and CSO partners over time yield networks that enable improved natural resource management, capacity development, knowledge exchange, policy advocacy, and sustainability of SGP and related initiatives. These networks expand SGP’s reach, involving greater numbers of organizations and communities in activities related to SGP objectives, and lead to greater impacts through replication and policy influence. This has been highlighted as a key factor by the GEF IEO study on scaling up as for successful scaling up outcome.

- Risks

- Given the wide presence on the ground in around 125 countries and at least 26 years of extensive experience applying appropriate, proven and adaptive approaches and tools at the community level, the likelihood of extreme risks to the programme is unlikely. SGP has in place mechanisms to ensure the early identification of potential risks and through established practices and experience, the progamme can develop and implement risk mitigation measures in an efficient manner. Despite challenges of working mostly with remote, community-based and non-governmental organizations with low level of technical and management capacities, SGP has consistently ensured that more than 90 percent of its grants achieve planned outcomes successfully. This is unprecedented and is a testament to SGP’s tested model of dedicated emphasis on developing grantee capacity as an integral part of SGP grant portfolio management. UNOPS provides a neutral financial oversight thereby further reducing the financial risks.

- Beyond that, the SGP also reduces risk by supporting replication and re-validation of good practices that have proven to deliver on GEF strategic priorities at the community level.  In each country, the National Steering Committee, with representation from civil society leaders, government institutions, and donors provides further support for effective design and implementation of SGP projects.  Some additional risks may be anticipated from the increased geographic coverage of SGP, as new eligible countries join the SGP, especially in countries with post conflict situations, capacity challenges, etc. The SGP grant maker plus approaches have been especially designed to mitigate such risks by allowing greater flexibility and efficient response in SGP programming at the country level.

- From experience, the most likely risks faced by SGP projects is the exposure and the need to adapt to weather extremes. In fact, many projects which were designed to develop tools and measures to adapt to these extremes as surrogate to what could be increased impacts of climate change are now part of routine programming directions for the SGP. For instance, SGP community projects draw on lessons and tools developed through its Community-Based Adaptation (CBA) projects to integrate climate change adaptation measures, including required vulnerability assessments and the inclusion of effective measures generated by communities in similar situations. SGP is less affected by social risks as SGP grant-making is demand-driven and community-based. As such, each project, by community design and commitment, is developed not only to meet environmental objectives but also the social, cultural and economic needs of its members, a de-facto prior informed consent, for community proponents including indigenous peoples. In addition, it may be noted that SGP NSCs that review project proposals have obligatory requirements to include focal points for gender and women empowerment, for youth, and where relevant for IPs, to ensure that key concerns and needs of these sectors are fully considered.

- UNDP has also developed its Social and Environmental Standards (SES) and accompanying Social and Environmental Screening Procedures (SESP).  SGP has applied the UNDP’s SESP to the design of this Project Document and in the review for approval of SGP Country Programme Strategies. Related compliance mechanism and accountability frameworks will also be referred to. For ad-hoc issues that may arise in the process of grantmaking, the NSCs are tasked to manage the appropriate conflict resolution measures. The use of the landscape and seascape approach allows more frequent visits to clustered projects and risks can be more regularly monitored and mitigated. The SGP also plans to strengthen its Technical Advisory Groups (TAGs) to include those experts that can advise on risk assessments and management at both project design and implementation stages. The system of grant-making will also provide for capable assisting NGOs to support first-time community and CBO implementers. Given all the above checks and balances in place, the potential risk of any negative social and environment impact of SGP projects is expected to be negligible.

- Stakeholder engagement plan

- SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous peoples, the private sector, government, academia, and donor partners. Civil society organizations (CSOs) will be both beneficiaries and direct participants in SGP through their inclusion in NSCs, where non-governmental members must be in the majority, as well as by taking on the role as National Host Institutions (NHIs) and other key roles related to knowledge sharing and policy advocacy.  Although grants are targeted towards CSOs particularly community-based and non-governmental organizations, a broad range of stakeholders are engaged as active partners in program management and during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers.

- Regarding indigenous peoples and persons with disabilities (PwD), SGP has developed a guideline document on each and follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle to allow these groups to access SGP support. The programme has pioneered numerous user-friendly, accessible modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video (PV), Almanario, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages so long as these concepts and proposals adhere to the basic project elements. SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. SGP makes extra efforts to reach out people and groups that are often marginalized or disadvantaged, including through the use of planning grants that facilitate development of full proposals and through the use of alternative proposal formats (e.g. video, photo stories) to improve access to SGP projects from these groups. Empowering women and engaging youth are two important initiatives of SGP. SGP NSC at the country program level designated focal points for gender and youth to ensure their voices are heard. Additionally, through stakeholder workshops, communication through mass media and targeted outreach by the NC in respective countries, CSOs can learn of SGP projects and activities and provide inputs on how to improve on them. In fact, an independent consultant review confirm that support to indigenous peoples constitute at least 30 percent of the SGP portfolio in 90 countries with Indigenous Peoples. The review reports that SGP support to IPs have remained significant and relatively stable or growing over time, with IPs and their organizations are managing over half of their SGP project or portfolio.

- As for the private sector, SGP will include mechanisms for engaging with private sector through both targeted platforms such as the CSO-Government-Private sector dialogues and through regular grant projects by fostering enhanced involvement of private sector through public-private partnership and other means. In line with the GEF 7 Programming Directions emphasis on engagement with the private sector, the SGP will enhance its engagement explore opportunities to engage with private sector through a number of ways: by developing a private sector strategy by reviewing past and existing portfolio and analyze potential ways to enhance engagement with private sectors: including engagement at the local/national level to influence businesses toward sustainable practices and options that generate multiple environmental benefits; and explore potential opportunities for finance and technical support that can help scale up SGP innovations. The SGP projects at the local and national levels are designed to provide community-based solutions to complex environmental problems. Given the inter-related and integrated nature of such environmental problems, engagement with and partnership with a wide variety of stakeholders and actors including the private sector will be important if the programme is to effect meaningful and transformative change – be this through transforming policies and regulatory frameworks or through building capacities at the community level. SGP will include mechanisms for engaging with private sector through both targeted platforms such as the CSO-Government-Private sector dialogues and through regular grant projects by fostering enhanced involvement of private sector through public-private partnership and other means. unstructured means such as by sharing information on SGP operations widely and facilitating private sector-grantee linkages. Please also see section 4 below for a detailed consideration of how SGP will engage with the private sector.

- In GEF 7, SGP financed projects will give more attention to the promotion and support of innovative and scalable initiatives at the local level to address global environment issues in priority landscapes and seascapes. It also will support those projects that could serve as incubators of innovation, with the potential for broader replication of successful approaches through larger projects supported by the GEF and/or other partners. In this context, the SGP will strengthen its partnership approach as a CSO-led multi-stakeholder platform by working closely with the private sector and with governments. With this aim, in GEF 7, the SGP will expand its innovative CSO-Government Dialogue Platform toward greater engagement of the private sector to leverage its potential to invest and support sustainability at the local level, including businesses relating to tourism, agriculture, forest and other relevant sectors. These platforms will provide opportunities to discuss possible shifts in relevant policies and practices to promote sustainability.

- Engagement with the private sector will be explored across all the thematic areas. For instance, in the agriculture and food, the SGP will foster partnerships with the private sector and other stakeholders to explore innovative, affordable, and practical solutions to chemicals and waste management while also seeking to establish systems of local producer and/or product certification as an initial step toward expanding to producer-consumer agreements – a process in which the private sector should be fully engaged with. Likewise, in the climate change thematic area, the role of the private sector is critical in ensuring the sustainability and affordability of low carbon technologies promoted at the community-level and similarly private sector partnership and support will be crucial for delivering the GEF 7 Strategic Initiative on catalyzing sustainable urban solutions. In biodiversity, SGP projects will explore opportunities to engage with private sector in supporting community-based eco-tourism activities to generate incentives to local communities for managing / conserving biodiversity. Private sector involvement is also important under the sustainable agriculture, fisheries and food security Strategic Initiative. SGP country programs will explore opportunities to link smallholder producers and pastoralists to markets and technologies. Finally, under the chemicals thematic area, SGP country programs will work with other national and local stakeholders to identify and support exploration of incentives for private sector involvement to sustainably eliminate chemicals. To this end, the SGP will strive to share information on its operations in respective countries widely with the private sector and explore opportunities for cooperation.

- At the start of each new SGP operational phase, the SGP Operational Guidelines requires each country programme to prepare a detailed programming and strategic document entitled the Country Programme Strategy (CPS). The CPS will facilitate a wide range of consultations during the process of its preparation. Such consultations will take into account both institutional stakeholders in the context of their involvement in the project (such as the Government and UNDP Country Office) and also more broadly for non-governmental stakeholders and prospective beneficiaries (Community-Based Organizations and community groups). A number of meetings and workshops will be conducted to the extent possible to discuss the overall strategy for grant making during GEF-7 and importantly reach general consensus on key country programme outcomes, outputs, activities and institutional arrangements for the country programme. The table below provides a broad description of the role and responsibilities of key stakeholders and their involvement mechanisms and strategies. Mechanisms and strategies for stakeholder involvement will ensure that the relevant shareholders receive and share information and provide their inputs in the planning, design, implementation, monitoring and evaluation of grant projects and as appropriate play a role in sustaining the initiatives during and at the end of the grant project period and the closure of overall grant making.

Table: Major Stakeholders, mandate and role in SGP

| Key Stakeholder | Responsibilities / mandate | Proposed role in SGP |
| --- | --- | --- |
| UNDP-GEF | The UNDP Global Environmental Finance (UNDP-GEF) Unit partners with environmental vertical funds to support countries with simultaneous eradication of poverty and significant reduction of inequalities and exclusion, by catalysing environmental finance for sustainable development. The UNDP-GEF Unit provides programming and implementation support services to countries. | UNDP is the GEF implementing agency and as such assumes overall accountability to the GEF for the meeting the project objectives and sound financial management of GEF resources. UNDP-GEF chairs the project board and provides oversight to the SGP operations. |
| CPMT | The Central Programme Management Team (CPMT) is a specialized programme and management team established at the UNDP-GEF HQ responsible for the strategic management of the SGP global programme. CPMT has overall responsibility for supervising the SGP Country Programme and for the technical and substantive quality of SGP country portfolios, coordinating KM and M&E activities, mobilize resources and facilitate partnerships for effective programme operation. | CPMT develops global strategy, guidelines and standards in the development of SGP projects with the objective of ensuring effective and efficient programme operation globally in over 110 countries. CPMT supervises SGP National Coordinators on both technical and managerial issues of programme operation, and facilitates the start-up of new Country Programmes. |
| UNOPS | UNOPS is an operational arm of the United Nations, supporting the successful implementation of its partners’ peacebuilding, humanitarian and development projects around the world. The UNOPS GMS is a one-stop shop for managing environmental programmes and projects through grants. | As the UNDP implementing partner, UNOPS provides execution services to the SGP, assuming full responsibility and accountability for the use of UNDP resources. UNOPS is a member of the Project Board and provides programme execution services including administrative, financial, legal, operational, and procurement for the SGP. |
| UNDP Country Office (CO) | UNDP COs are located in more than 170 countries. They provide oversight functions for all UNDP-GEF projects and programs. The UNDP CO is the primary conduit through which UNDP engages with the host government and other national entities. | UNDP CO provide support for SGP start-up, recruitment of national coordinators, local supervisions, and resource mobilization. UNDP CO is an institutional member of the NSC and also provide, as per request by and as agreed with UNOPS, any needed operational oversight for the SGP Country Programme. |
| GEF Operational Focal Point (OFP) | The GEF OFP is the designated focal point of the Government in the country, responsible for coordinating GEF programing and makes key decisions on the national ownership and determination of allocation of GEF resources (STAR). | The GEF OFP is the other institutional member of the NSC for the SGP. The OFP is kept abreast of the SGP operations in the country by the NSC and the National Coordinator through sharing of progress reports and other communication. |
| National Steering Committee (NSC) | In each SGP country, a multi-sectoral NSC will be composed of government representatives and majority nongovernmental membership to reflect the program’s mandated focus for CSO capacity building. UNDP and GEF OFP are the only institutional members. All other NSC members perform their role in their individual capacity. | The NSC will provide overall country guidance and provide direct linkages to national policymaking, development planning, knowledge dissemination, and leveraging of SGP's catalytic role. The NSC is responsible for selecting and approving projects, and for ensuring their technical and substantive quality. |
| Allied agencies and ministries | Several Government allied agencies including the Ministries of Planning, Agriculture, Environment, Rural Development, Women’s Affairs etc. may have a remit for SGP activities in the country | The SGP will collaborate in grant making procedures and activities other allied government agencies as appropriate to identify gaps, priority issues and solutions for sustainable environmental management issues in the country. SGP will partner with such agencies in providing consultations, information and experiences and also explore support in upscaling, dissemination and application of best practices and lessons learned. |
| Academe | In many SGP countries, academic institutions are the primary source for technical know-how, knowledge management and capacity building opportunities. | SGP will collaborate as appropriate with the Academe to identify, design and deliver capacity building initiatives in environmentally friendly approaches and practices. Certain academic members may also participate as members of the Technical Advisory Group. |
| Local communities and community- based organizations (CBOs) | Local communities are custodians, primary users and managers of the environmental resources and key beneficiaries and target groups for all activities of the SGP. | Local communities, including CBOs, will participate in the implementation of project activities through access to SGP grants and participation in the decision making of the SGP. They are the direct beneficiaries of project investments. |
| Indigenous Peoples | Indigenous groups and Indigenous Peoples have different history, traditions, and diverse material lives. Mainly they rely on natural resources, especially forests, for their livelihoods. | Indigenous Peoples will directly participate in decision making processes related to specific interventions that relate to indigenous lands and resources. Moreover, SGP interventions will support capacity building, implementation of livelihood and in benefit sharing for indigenous peoples. Specific investments for Indigenous Groups will be guaranteed. |
| Mass media organizations, and other media organizations | Mass media has the responsibility for the dissemination of information and awareness on state policies, strategies and plans to the general public at the national and regional level through mainstream channels of television, radio and print. | Partnerships with key media organizations will support dissemination of information at global, regional and national levels, including on SGP interventions, grant making announcements (CfP), training and capacity building events as well as results and best practices. |
| Development Partners | A number of development partners including bilateral and multilateral development agencies are usually present in specific SGP countries. | The SGP will engage relevant development partners as partners to facilitate coordination and collaboration while, as appropriate, exploring opportunities for cost-sharing and co-finance opportunities. |
| Private Sector | The SGP will engage private sector as much as possible. The private sector will involve in the development and implementation of sustainable natural resource-based enterprises or other initiatives. | The SGP will develop a private sector engagement strategy under GEF-7. Among others, private sector collaboration will be explored in community-based business or partnership opportunities e.g. in the implementation of and support to responsible tourism initiatives, community-based waste management, agri-food processing and post-harvest value addition, linkage to markets etc. |

Initiatives to ensure stakeholder engagement

- The following initiatives at the global and country level will ensure stakeholder engagement in the project. At the global level, multi-stakeholder inception workshops will be organized with the purpose to create awareness amongst global stakeholders of the project including the various teams among partners, UNDP and UNOPS. At the country level, a communication initiative will facilitate awareness, review and informing of policy, stakeholder participation and documentation of best practices related to the SGP in the country.  The new phase of the SGP will effectively be launched with the Call for Proposals (CfP), a process by which SGP publicizes the opportunity for SGP grants through various means including through mass media. The meetings of the NSC are important opportunities for engagement of the main stakeholders with agenda items that discuss achievements, challenges faced, corrective steps that should be taken etc. At such meetings, progress on planned grant making activities are also shared.

- As for engagement of local communities, this is SGP’s forte. SGP will employ a highly participatory approach to facilitate the involvement and participation of local communities, either as groups through their CBOs or represented by CSOs/NGOs that represent their interests particularly through the consultative country programme strategy development, capacity development workshops, outreach and communication activities. SGP will ensure the inclusion of both men and women in the planning and implementation of the grant activities. SGP will also continue to employ the proven capacity building approaches to ensure greater participation while also continue to adopt innovative and accessible forms of project grant templates (e.g. grant proposals through recorded form) to maximize participation.

- Gender equality and Women’s Empowerment

- An internal review carried out as part of the AMR reporting to assess gender equality and women’s empowerment in its portfolio during the GEF-6 period which showed that 82% of total SGP projects completed were reported to be gender responsive, while at least 30% of completed projects were led by women. These efforts have been recognized. For instance the  UNDP publication “Evaluation of UNDP’s Contribution to Gender Equality and Women’s Empowerment, 2015” report that (i) the majority of the CPSs mention practical steps to promote gender in SGP projects; (ii) the majority of stakeholders of SGP at the national level (60%) find that the SGP grant selection process includes consideration of gender equality to a great extent and 47% find that grants have effectively contributed to gender equality and women’s empowerment; (iii) NCs and NSCs are perceived to have some level of gender expertise; and (iv) actual results on the ground are evident and half of the projects were found to have benefitted women and men equally, or to have disproportionately benefited women.  Many other projects benefited women, although not to the same extent as men.

- The SGP will build on these strong results to deliver concrete gender outcomes by reviewing and enhancing its gender strategy and guideline for program and project operation. This could include reviewing strategy to enhance gender equality in SGP governance (e.g. National Steering Committee and Country Program team composition), and grant selection and management. The SGP will also fully roll out the GEF Gender Implementation Strategy in the grant-making process, the four action areas. At the portfolio level, the SGP will measure and report on the GEF gender tags such as: (a) contributing to closing gender gaps in access to and control over resources; (b) improving the participation and decision-making of women in natural resource governance; and (c) targeting socio-economic benefits and services for women. The current project has established targets for these gender tags (please see table B).

- Furthermore, the SGP has been an active member of the GEF Gender Partnership, contributing to the review of gender indicators and the gender policy. The GEF Gender Partnership launched the first online course on gender and environment during the 5th GEF assembly in June 2018. During the project, the SGP will expand the online course to offer modules in French and Spanish. This was also recognized by the GEF IEO (OPS Sub-study) on “Evaluation of Gender Mainstreaming in the GEF 2017” which noted that the important SGP contribution to gender equality, specifically, the design and roll out of the e-learning on gender and environment to support capacity development in agencies and partners. In addition, SGP will also pilot a focused innovation programme on women entrepreneurship with the objective to upgrade and expand existing green women-led enterprises for wider replication and scale up.  This programme will provide women-led enterprises with business management training, technical training, product development and design, business counselling, marketing assistance, finance facilitation and business networking and business linkages.

- Innovativeness, Sustainability and Potential for Scaling Up

- Innovation is a cross cutting thread across SGP’s interventions; innovation is not just as an integrated approach for project execution but is also a key result. The micro, and local nature of SGP projects, lends feasibility to undertake risk, and experiment with pilot development- as a test and trial for effective and efficient community led solutions that work in a given context, or may have broader scaling up potential and replicability. A demand driven approach, combined with flexibility, accessibility, and risk taking constitute SGP as an incubator of innovation. SGP has developed a standardized innovation measure for a project. These include: (a) distinct way to discern the problem; (b) reorganized (and often better) use of available resources; (c) unique ways to connect; (d) incremental revolutionary conception; (e) original creation; (f) and powering local innovators. Thus, SGP’s approach encourages local innovation and creativity through its bottom-up and participatory practice in the design of projects, in the recognition of the relevance and value of local or traditional knowledge, and in allowing greater flexibility and adaptive management of projects.

- Community innovations in SGP are manifested in the testing and ground-truthing of low-cost technologies and sustainable production methods, in new methodologies for the involvement of stakeholders, and in integrating traditional decision-making processes within the wider frameworks and actions relevant to meeting country commitments to international environmental agreements. Since SGP funding is modest and its interventions are designed to be initially small scale, the programme can readily support community-based experimentation. Once a novel idea has been tested on the ground and proven to be effective in meeting community needs, it can often take off more widely through grantee networks as well as networking with other CSOs, further resulting in more innovations and eventually attracting additional donor and or government support for wider application. This innovation process is supported through digital library of community innovations, building on the tens of thousands of SGP-supported projects, as well as a South-South Community Innovation Exchange Platform to share these innovations across countries.

- To encourage innovation within the portfolio, and to fully explore the potential of the SGP to be an incubator, the SGP will track such innovation results in terms of the invention of product, service or process, leveraging local assets and resources, relevance to local unmet needs, potential of scaling up/ replication. Building on recommendations to collect and aggregate common standardized measures across SGP projects, during the GEF7, the SGP will implement the initial piloting of a measurement called the SGP Innovation Meter. This measure will cover different types of innovations, including disruptive and sustaining/ incremental innovations that SGP is involved. It will measure innovation both from the standpoint of the coverage of the portfolio and also the depth of innovation in the portfolio. In addition, SGP will continue with the design and implementation of Innovation Programs with interested and relevant SGP Country Programmes to emerging environmental issues for scaling up and/or pilot innovative approaches and tools on specific thematic issues. Knowledge management and leveraging resources will retain prominence in the Innovation Programs.

- Achieving sustainability of project outcomes is central to SGP.  According to IEO Joint Evaluation in 2015, the SGP has secured a high success rate in sustaining project results. Project proponents are required to build measures into their project design that increase the likelihood of outcome sustainability, including through the development of an appropriate exit strategy. The screening of project proposals by the National Steering Committee (NSC) includes a systematic assessment of whether such measures are sound and based on realistic assumptions. Project logical frameworks include outcome indicators that are monitored periodically. Project monitoring activities are designed to verify that initial assumptions hold, and that the required elements for outcome sustainability are in place. Most grants include a capacity development component and a sustainable livelihoods component to ensure that achievements will be sustained at the smallholder and resource-user level. Proactive adaptive management is applied throughout the life of the projects by the National Coordinator (NC) who works with SGP grantees to take corrective action whenever there are indications that project outcomes may be compromised or may not be sustained after the project ends. SGP does not generally support the creation of new organizations, but rather strengthens existing CBOs and NGOs.

- Although most communities continue applying acquired skills in their day-to-day work, SGP ensures retention of new skills through various means: (i) inviting leaders or members of former grantee organizations to new training; (ii) using former SGP grantees as trainers for other communities and projects; (iii) continuing monitoring former grantees and trouble-shooting as much as possible; and (iv) establishing mentoring and peer-to-peer support among communities. Ultimately, the sustainability of SGP projects results from the strong ownership of the community or CSO grantee-partners to the actions taken and resulting outcomes, the empowerment built in the process of implementation, and the fact that these projects are meeting their most important needs particularly for sustainable livelihoods. SGP’s Grantmakers Plus initiatives is specifically geared towards sustainability and will promote an enabling environment to scale up the impacts of SGP Strategic Initiatives, nationally and globally, through networking and knowledge exchange.

- With regards to scaling up, the majority of SGP innovations have scaling up potential. This is emblematic in the fact that among the 60 cases assessed for a study by the GEF IEO in 2019 for evaluating scaling up in GEF, 14 consisted of SGP projects.  This is because successful SGP projects are solutions that are relevant to a thousand-fold more communities under similar situations within the country of implementation, and across other countries. Community-based approaches are inherently more cost-effective in their utilization of existing resources and hitherto untapped resources thereby providing a good model for larger projects concerned with efficiency and sustainability. The highly consultative and participatory processes, including the direct access to funds, practiced in SGP projects, can provide valuable lessons for larger government and donor programs. Notable too is the global reach of SGP – 128 participating countries – which combined with good sharing systems, can scale up, mainstream, and replicate successful community projects. Moreover, as pointed out by the GEF IEO study, UNDP-SGP “structure is particularly conducive for interactions” [frequent interactions to exchange knowledge and information] due to its unique structure, at the country level, SGP’s long term and local presence, commitment to building multi-stakeholder networks, are crucial factors for scaling up success.

- Scaling up, as well as mainstreaming and replication, however, are processes that require a proactive approach and additional resources especially for communities and CSOs that have only recently completed their first projects. SGP’s main role in the scaling up process is to demonstrate or showcase the successful innovation to a wider set of stakeholders, as well as to establish networks/linkages for pooling of effort and resources by various actors.  At the portfolio level, SGP has utilized its NSCs, grantee-partner networks and allied CSO networks to have community innovations and successes recognized and adopted at the national level by policy-makers.

- SGP will also encourage strong partnerships with the private sector to commercialize successful projects with the aim to shift renewable energy projects from pilot innovations to the mainstream. This will be achieved through, but not limited to, the CSO-Government-Private Sector dialogue platforms. The Grant Maker Plus funds that support such CSO-government dialogues was recognized by the IEO study as enabling SGP country programs to provide a platform for stakeholders to reflect on issues such as how implementation at the higher scale could be adapted to improve outcomes.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): Goals 7, 13, 14, 15, 17 |  |  |  |  |
| --- | --- | --- | --- | --- |
| This project will contribute to the following UNDP SP Outputs: 1.4.1; 2.1.1; 1.5.1; 2.5.1; 3.4.1 |  |  |  |  |
|  | Objective and Outcome Indicators | End of Project Target | Verification Means | Assumptions |
| Project Objective: | Mandatory Indicator 1: # direct project beneficiaries disaggregated by gender (individual people) | 100,000 (male) 100,000 (female) | Annual Monitoring Report (AMR) | All countries are incorporating social inclusion areas as part of CPS design and implementation |
|  | Mandatory Indicator 2: # indirect project beneficiaries disaggregated by gender (individual people) | 300,000 |  |  |
| Project component 1 | Community-based conservation of threatened ecosystems and species |  |  |  |
| Outcome 1 - Community-based models and biodiversity friendly practices and approaches promoted for conservation and sustainable use of threatened ecosystems and species in important terrestrial and coastal/ marine ecosystems | Indicator 3: Area of landscapes under improved management to benefit biodiversity (hectares) (GEF core indicator 4.1) | 1,100,000 ha | AMR Grantee Monitoring Report Impact reviews SGP database | Mobilized multi-stakeholder support for the landscape/seascape approach (including the government, local CSOs/CBOs, NSCs) Technical support provided, along with capacities, to facilitate the landscape/ seascape approach |
|  | Indicator 4: Marine protected areas under improved management effectiveness (hectares) (GEF core indicator 2.2) | 50,000 ha |  |  |
|  | Indicator 5: Area of marine habitat under improved practices to benefit biodiversity (hectares; excluding protected areas) (GEF core indicator 5) | 50,000 ha |  |  |
| Outputs to achieve Outcome 1 | Output 1.1: Community-based NRM measures that integrate biodiversity and sustainable community use including management and governance of PAs and ICCAs developed Output 1.2: Sustainable biodiversity friendly community oriented natural resources-based enterprises and sustainable livelihood activities supported Output 1.3: Community-based measures supporting improved management of PAs including ICCAs promoted among PA adjacent communities and within ICCAs |  |  |  |
| Project component 2 | Sustainable agriculture and fisheries, and food security |  |  |  |
| Outcome 2 - Climate-smart integrated practices improve productivity, food security, and livelihoods of smallholder farmers and supports achievement of national LDN targets. | Indicator 6: Area of landscapes under sustainable land management in production systems (hectares) including fisheries (GEF core indicator 4.3) | 140,000 ha | AMR Grantee Monitoring Report Impact reviews SGP database | Landscapes address a production system Collaboration with full-sized projects to support vertical linkages for sustainable agriculture and fisheries, and food security |
|  | Indicator 7: Area of degraded agricultural lands restored (hectares) (GEF core indicator 3.1) | 100,000 ha |  |  |
|  | Indicator 8: Number of SGP countries supporting linkages and partnerships for sustainable food production practices (such as diversification and sustainable intensification) and supply chain management including in sustainable fisheries management | 50 countries |  |  |
| Outputs to achieve Outcome 2 | Output 2.1: Community level SLM actions that reduce land degradation, support restoration and aligned with national LDN targets Output 2.2: Climate-resilient SLM technologies adapted to local conditions implemented Output 2.3: Guidelines and best practices on SLM technologies developed and disseminated Output 2.4: Viable linkages and value-chain improvement initiatives that enhance production and enhance income supported |  |  |  |
| Project component 3 | Low-carbon energy access co-benefits |  |  |  |
| Outcome 3 - Low carbon, viable and appropriate technologies and approaches demonstrated and deployed across sectors. Initiatives scaled up that improve community energy access and build a low carbon infrastructure in line with larger national frameworks such as SDGs and NDCs. | Indicator 9: Increase in installed renewable energy capacity from local technologies (e.g. on types of renewable energy technology biomass, small hydro, solar). | 150KW | AMR Grantee Monitoring Report Impact reviews SGP database | Communities and CSOs have innovative and implementation capacity |
|  | Indicator 10: Number of typologies of community-oriented, locally adapted energy access solutions with successful demonstrations or scaling up and replication | 25 local energy access solutions |  |  |
|  | Indicator 11: Hectares of forests and non-forest lands with restoration and enhancement of carbon stocks initiated. | 7,500 hectares |  |  |
| Outputs to achieve Outcome 3 | Output 3.1: Low-cost bottom-up energy solutions promoted including measures to reduce forest degradation and deforestation Output 3.2: Community innovations, including technologies for low carbon energy options including financing opportunities documented Output 3.3: Capacity building and transfer of knowledge for effective deployment of low carbon, sustainable energy solutions at community level |  |  |  |
| Project component 4 | Local to global coalitions for chemicals and waste management |  |  |  |
| Outcome 4 - Innovative community-based tools and approaches demonstrated, deployed and transferred. Organize and strengthen multi-stakeholder coalitions with support from sound chemicals and waste management platforms. | Indicator 12: Quantity of POPs/Mercury containing materials and products directly avoided (GEF core indicator 9.6) | 150 tons | AMR, SGP database Grantee Monitoring Report Impact reviews SGP database | Issue buy-in existing at communities and CSO level in a given context |
|  | Indicator 13: Number of local to global coalitions and networks established and/or strengthened (e.g. IPEN and Zero Mercury Working Group) | 2 coalitions |  |  |
|  | Indicator 14: Number of SGP countries working on increasing awareness and outreach for sound chemicals, waste and mercury management. | 25 countries |  |  |
| Outputs to achieve Outcome 4 | Output 4.1: Community-based innovative, affordable and practical solutions to chemicals and waste management supported Output 4.2: Consolidation of efforts on pesticide management, waste management, and mercury to promote local to global coalitions and networks Output 4.3: Community-level artisanal and small-scale gold mining in reducing/eliminating use of mercury demonstrated |  |  |  |
| Project component 5 | Catalyzing sustainable urban solutions |  |  |  |
| Outcome 5 - Appropriate integrated community-oriented sustainable urban solutions in partnership with government and private sector. These may often be first time innovations and are administered with a socially inclusive lens. | Indicator 15: Number of SGP countries with improved capacities to promote community-driven integrated solutions for low-emission and resilient urban development. | 12 countries | AMR, SGP database Annual Country Monitoring Report | Synergize efforts with Global Platform for Sustainable Cities (GPSC) Identified pockets of geographic areas or thematic issues to focus on (in the absence of landscape/ seascape approach here) |
|  | Indicator 16: Number of community-based urban solutions/ approaches (including chemical and waste management, energy, transport, watershed protection, ecosystem services and biodiversity) deployed. | 12 urban solutions |  |  |
| Outputs to achieve Outcome 5 | Output 5.1: Integrated community-oriented sustainable urban solutions in partnership with private sector and government identified and implemented Output 5.2: Capacity building for key service providers and local communities on low-emission and resilient urban development solutions |  |  |  |
| Project component 6 | Supporting broader adoption of community impact and innovation |  |  |  |
| Outcome 6 - CSO-Government-Private Sector Policy and Planning Dialogue Platforms promote community voices and participation in global, national and sub- national policy/strategy development on global environment and sustainable development issues. | Indicator 17: Number of high-level policy changes attributed to increased community representation through the CSO-government-private sector dialogues. | At least 50% of countries reporting significant policy outcomes | AMR, Annual Country Monitoring Report, Country impact reviews | Government responds to consultative processes Dialogues/ Exchanges undertaken in mature SGP country programmes/ countries with advanced community results |
|  | Indicator 18: Number of representatives from social inclusion group (indigenous people, women, youth, persons with disability, farmers, other marginalized groups) supported with meaningful participation in dialogue platforms. | 2 representatives from social inclusion groups per dialogue platform |  |  |
| Outcome 7 - South-South Exchange promoted to broker knowledge, build capacities and facilitate partnerships between communities, CSOs and other partners across countries on global environmental issues. | Indicator 19: Number of countries reporting adoption of improved practices or approaches as a result of South- South exchanges between communities, CSOs and other partners across countries. | 10 countries |  |  |
|  | Indicator 20: Number of south- south exchanges at global and regional levels to transfer knowledge, replicate technology, tools and approaches on global environmental issues. | 15 south-south exchanges |  |  |
| Outputs to achieve Outcome 6 and 7 | Output 6.1: National-level targeted CSO-Government dialogues Output 6.2: Global CSO-government and other stakeholder dialogues Output 7.1: South-south exchanges identified, supported and documented |  |  |  |
| Project component 7 | Promoting social inclusion |  |  |  |
| Outcome 8: Social inclusion, particularly empowerment of women, indigenous peoples, youth and people with disabilities, is mainstreamed and enhanced in SGP programming on environment and livelihood improvement | Indicator 21a: Number of SGP projects led by women. | 30% of SGP portfolio | AMR Annual Country Monitoring Report SGP database | Social and Environmental Standards are incorporated at country and project levels; Country programme level management, in particular National Steering Committees, reflect a socially inclusive model. Marginalized groups such as the youth and the disabled people are aware of and interested in working with SGP |
|  | Indicator 21b.: Number of projects contributing to closing gender gaps related to access to and control over natural resources | 20% SGP portfolio |  |  |
|  | Indicator c: Number of projects that improve the participation and decision-making of women in natural resource governance | 30% SGP portfolio |  |  |
|  | Indicator 21d: Number of projects that target socio-economic benefits and services for women | 70% SGP portfolio |  |  |
|  | Indicator 22: Number of SGP countries that have targeted support for Indigenous Peoples in terms of country level programming and management. | 20% of SGP country programmes |  |  |
|  | Indicator 23: Number of SGP countries that demonstrate appropriate models of engaging youth and for persons with disability. | 15% of SGP country programmes for each group |  |  |
| Outputs to achieve Outcome 8 | Output 8.1: Increased involvement and active participation and empowerment of women, indigenous peoples, youth and persons with disabilities mainstreamed in SGP initiatives Output 8.2: Expanded Indigenous Peoples’ Fellowship Program implemented Output 8.3: Guidelines and best practices on engaging youth and persons with disabilities will be developed and widely shared |  |  |  |
| Project Component 8 | Monitoring & evaluation and Knowledge management |  |  |  |
| Outcome 9 - A common, robust M&E strategy is developed and implemented in all countries at all levels (project, country and global)- establishing transparency, coherence and evidence-based decision making. | Indicator 24: Number of SGP country teams administering results management modalities in programme design, implementation and overall decision making using participatory mechanisms. | All SGP countries | AMR Annual Country Monitoring Report SGP database | Adequate availability of resources. M&E capacities built across global, country and project levels. Mechanisms of quality assurance and methodologically-sound thought production in place. |
|  | Indicator 25: Number of country/cross-country impact reviews undertaken that generate evidence of SGP impact and lessons learnt. | 3 impact reviews |  |  |
| Outcome 10 - Networking and knowledge sharing leverage local actions for global change to safeguard global environment | Indicator 26: Number of SGP countries using citizen-based knowledge platform (digital library of community innovations) to document and curate community-based solutions to environment issues. Indicator 27: Number of knowledge fairs | All SGP countries | SGP intranet AMR | Access to internet connectivity is available. Communities and CSOs have capacity to curate their knowledge. |
| Outputs to achieve outcome 9 and 10 | Output 9.1: SGP M&E system deployed at country and project levels Output 9.2: Selected country level impacts reviews conducted Output 10.1: Citizen based knowledge platform supported generating thematic and geographic specific knowledge products |  |  |  |

# Monitoring and Evaluation (M&E) Plan

- The SGP places strong emphasis on strengthening results management, monitoring and evaluation (M&E). An agile M&E system integrated across project, country and global levels, is intended to address needs for accountability, adaptive management with informed decisions and actions, and learning from both success and failure. It enables tracking progress, and a deeper understanding of ‘what’ works and ‘why’ in the communities we serve, thereby generating evidential bases for broader adoption of the Programme and net developmental change due to it.

- GEF SGP Monitoring and Evaluation Strategy (2019), builds a model of change for SGP results that facilitates an understanding of how the programme creates change, and defines SGP results as follows: (i.) global environmental benefits; (ii.) socio- economic benefits; (iii.) innovation; (iv.) capacity development; and (v.) broader adoption of SGP (scaling up, replication, mainstreaming and policy influence). With the above results in focus, a measurement system has been developed, which is compliant with GEF Results Guidelines, other GEF Policies and UNDP Strategic Plan Results Framework. Three criteria were utilized to define SGP’s measurement for its results: is the measurement a reasonable indication of progress on a given result; will it serve as a suitable metric to manage adaptive programming; and is it practical to have quality, representative and cost-effective data on the measure.

- Briefly, the measurement system is composed of (i.) SGP global environmental indicators guided by GEF-7 results architecture.  SGP is aligned with 6 of the 11 GEF-7 core indicators; (ii.) introduction of two new socio- economic indicators. These are number of beneficiaries with improved livelihoods and well-being, and number of beneficiaries benefitting from SGP, disaggregated by social inclusion groups; (iii.) introduction of a new prospective measure on innovation (to be piloted); (iv.) integration of methodologies to assess change at meta level (landscape/ country); and (vi.) programme efficiency measures. Lastly, in alignment with GEF Gender Equality Policy, SGP will explore piloting additional gender indicators. Details are available in the GEF SGP M&E Strategy.

- On the new prospective measurements, SGP will pilot a new tool- SGP Innovation Meter, which aims to measure portfolio-wide innovation strength. It will use a six-point criterion to assess innovation coverage and depth of SGP projects, country and global portfolio. These are (i.) new way of thinking; (ii.) new use of resources; (iii.) new ways to connect; (iv.) novel improvements of existing product/ service/ delivery process; (v.) original creation; and (vi.) powering local innovators. The approach and tool will be piloted across a regionally/ typology distributed sample of the portfolio, refined with feedback, and rolled out across the portfolio during project period.  On meta level change assessment, with the administration of Impact Reviews in mature country programmes, SGP will focus on assessing change and broader adoption at landscape/ country level. The intent is to build a repository of evaluative evidence over time to inform work on broader adoption (scaling up, replication, mainstreaming and policy influence), multiplier effects, and change affected due to the SGP.

- Guided by the Joint GEF-UNDP Evaluation of Small Grants Programme, 2015, tracking SGP’s programme efficiency as a funding mechanism will also be undertaken. These include monitoring of programme and project cycle effectiveness, funding delivery rates, results driven implementation, integration of corporate standards in programming, stake holder involvement (partners/ NSCs), and financing.

- SGP’s multi-tiered approach will be supported with dedicated M&E procedures, templates and guidance at global, country and project levels. The M&E system mirrors the three tiers of programming and will be operationalized in an integrated manner across the three levels. Here, community projects are nested within country programmes which are in turn nested within the global programme.  In the SGP, the global programme provides the overall strategic programming framework with strategic initiatives described and grant maker plus activities that guide, enable or support programming at country and community levels. Country Programme Strategies (CPS) are developed and formulated by National Coordinators and National Steering Committees within this general framework, adapting the global programme’s objectives to country level conditions and contexts, in particular to selected landscapes and seascapes for focused support. Community organizations within these landscapes, as part of the participatory landscape strategy planning process, identify community projects and strategic initiatives to be programmed in pursuit of landscape level outcomes as framed in each Country Programme Strategy.

- At the project level, there will be a lean M&E framework to support harmonized data collection and reporting across SGP portfolio. Each of the SGP projects picks from a Roster of Indicators, and a given project can be linked to a minimum of one of the GEF-7 Global Environmental Indicators and at most three. Grantees will have the flexibility to select any additional indicators as part of their M&E plan as maybe context appropriate. These indicators will be tracked as a two-step process. At project commitment stage, as part of the Memorandum of Agreement process between SGP and CSO/ CBO Grantee, the grantees, with support from NC, will select from the indicator roster with a quantitative target, and commit to their tracking as part of planned project monitoring and reporting. This will also enable identification of early capacity needs on grantee end. These indicators and quantitative results would thereupon be reported in SGP project mid-term and final progress reports, at project conclusion stage.

- At the country level, SGP country programme teams, as well as the NSC, undertake monitoring of grant portfolio on an ongoing basis. Each project is visited at least once during the life cycle of project. In close collaboration between NCs and NSCs, periodic project reviews and monitoring of CPS implementation is undertaken. A strengthened database will support producing annual results at the country level. Country level results reporting is intended to serve as a useful tool to benchmark overall progress of the country programme against the objectives set in the CPS, allowing each country programme to take appropriate measures and adaptive management decisions. In addition, the NSC will review progress of projects that received support as well as the achievement of results by completed projects. Results of reviews and relevant reports will be shared with country GEF Operational and Political Focal Points, relevant Rio Convention focal points and UNDP Country office. In coordination with NCs, NSCs use these reviews for upstream proliferation of SGP results, broker learning and connect project grantees and key partners. Please see attached operational guidelines for further details.

- At Global level, in compliance with GEF Monitoring Policy, a consolidated annual monitoring report is submitted to the GEF secretariat, including the status of the Programme; results across applicable core Indicators; project financing approved, committed, and disbursed by operational phase, with a breakdown between grants to civil society and community-based organizations and other costs, as well as core funds and additional funds from country allocations; and any other information as required by relevant GEF policies. The global level will track and report on progress on impacts achieved at the global programme level, by monitoring targets and indicators in the in the Results Framework. Reporting to GEF, UNDP, conventions and other partners will be done herein. Global portfolio monitoring and thematic portfolio reviews will also be periodically produced to measure impact achieved. Advanced production of data analytics will support both tracking and reporting of SGP performance. This includes annual production of data reports and regional factsheets. Such an analysis of the portfolio will serve as a basis to identify key projects, successful pathways and tracking evidence.

- Quality assurance, and building a culture centered on evidence, are pivotal elements of SGP M&E approach going forward. Methodological toolkits and checklists will be provided to support a participatory approach towards credible data across the three levels. Integration in indicator selection and target setting process between global, country and project levels will also be ensured. For global and country level linkage: with both global indicators and targets defined in the SGP Project Document, all country programme strategies (CPS) will respond and aggregate towards them. CPS results framework will integrate some of the key global level indicators in areas of country focus and develop corresponding targets for them. In line with SGP’s demand driven programmatic nature, CPS has flexibility to go over and above globally defined indicators to address local civil society priorities. For country and project level linkage: CPS commitments will be reflected at the time of project selection with NSC assessing linkage of a given project with CPS indicators and targets. Preference will be given to selecting projects with high degree of alignment on CPS indicators and their ability to contribute to targets.

- SGP M&E will be guided by a set of principles to seamlessly integrate project, country and global levels. These provide: (i.)  clear objectives for each of the three levels; (ii.) focus to what success looks like with application of RBM principles. With a focus on reducing reporting burden faced by grantees, project level will be directed by principles to minimize data collection and reporting burdens on grantees, aligning project results with strategic objectives of SGP country programmes and tracking SGP’s non-financial contribution towards successful implementation of the project. Country level is guided by drawing on key project level data to measure progress towards country programme strategy, recognizing country results are more than the sum of project results, and focusing efforts to capture broader change due to the programme. Key principles to guide Global level results management efforts include aligning with stakeholder needs for accountability, assessing change due to SGP intervention, measuring for SGP contribution and attribution, and undertaking endeavors to build an evidence-based learning culture across the Programme.

- In accordance with the GEF Policy on Monitoring (GEF/C.56/03/Rev.01, June 12, 2019), SGP will provide annual monitoring report that covers results and financial information by operational phase. While specific UNDP requirements are not outlined in this project document, SGP country teams will work with UNDP country Office and other relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. SGP’s monitoring and evaluation system will be fully in-line with GEF and UNDP monitoring and evaluation policies and minimum standards, including consistency with UN Evaluation Group standards and norms. The M&E strategy also presents a set of differentiated roles and responsibilities have also been developed for each of the constituents: Project Grantee, SGP country team (National Coordinator/ Programme Assistant), National Steering Committee, and Global level team. Activities outlined in the M&E plan will be undertaken as necessary and appropriate to ensure cost-effectiveness at each level.

- The broad categories for SGP’s M&E budget are as below and the M&E work plan is presented in the table that follows:

| - Field based monitoring (including travel) |  |
| --- | --- |
| - Country level (110 countries) | $1,270,000 |
| - Global level (CPMT) | $ 283,000 |
| - Impact reviews / evaluations | $ 300,000 |
| - Audits | $ 480,000 |
| - SGP database | $ 200,000 |
| - Quality assurance / technical assistance | $ 180,600 |
| Total | $ 2,713,600 |

Monitoring and Evaluation workplan

| M&E Activity | Purpose | Responsible Parties | Budget Source | Timing |
| --- | --- | --- | --- | --- |
| PROJECT LEVEL |  |  |  |  |
| Project M&E plan | Ensure compliance with minimum project design standards and norms | Grantee and NC | NC staff time | At project commitment stage |
| Participatory Project Monitoring | Monitoring; learning; adaptive management | Grantee | Covered under project grant amount | Ongoing throughout project implementation |
| Project Evaluation (as necessary / cost effective) | Assess project effectiveness | Grantee, NC, NSC, third party | Covered under project grant amount | Upon completion of project activities, as appropriate |
| Project Progress Reports (Midterm progress report, final progress report) | Reporting of results; adaptive management | Grantee | Covered under project grant amount | At mid-term and final tranche |
| Financial Reports (usually 2, per agreed disbursement schedule) | Financial accountability and assessment of cost-effectiveness | Grantee | Covered under project grant amount | At each disbursement request |
| Project monitoring (as necessary / cost effective) | Monitoring, adaptive management | NC, NSC | Country Operating Budget | At least once per project cycle |
| Maintain project description/results in global project database | Enable efficient reporting to CPMT, GEF, donors, others | PA and NC | Staff time | At start of project, on ongoing basis, and at project completion |
| COUNTRY LEVEL |  |  |  |  |
| M&E Activity | Purpose | Responsible Parties | Budget Source | Timing |
| Country Programme Strategy elaboration | Framework for action including identification of community projects. | NC, NSC, country stakeholders, grantees | SGP planning grant | At start of project |
| As part of NSC meetings, ongoing review of project results and analysis. This includes an Annual CPS Review. | Assess effectiveness of projects, country portfolio; learning; adaptive management. | NC, NSC, UNDP Country Office. Final deliberations shared/ analyzed with CPMT colleagues. | Staff time, Country Operating Budget | Minimum twice per year to ensure SGP CPS is on track to achieve its results and make timely and evidence-based modifications to CPS as may be needed. |
| Annual Monitoring Report Survey | Enable efficient reporting to CPMT and GEF. It serves as the primary tools to record and analytically present results to donors. | NC/PA in close collaboration with NSC. CPMT supports the process. | Staff time | Once per year in June- July |
| Country Portfolio Review | Methodological results capture for impact level change. Supports reporting to stakeholders, learning, and strategic development/ implementation of CPS. | NC, Global M&E staff | SGP planning grant | Once per operational phase |
| SGP Database | Ensure recording of all Project and Country Programme inputs in SGP database. | NCs, PAs | Staff time | Throughout the operational phase. |
| Audit | Ensure compliance with project implementation/management standards and norms. | UNOPS/ External | Global Operating Budget | Annually for selected countries on risk-assessment basis |
| GLOBAL LEVEL |  |  |  |  |
| Implementation of new SGP M&E strategy | Strengthened results management across the three levels. | CPMT | Global M&E budget and staff time | Ongoing |
| Revamping and maintenance of SGP Database | Streamlining, alignment with other systems (such as one UNOPS), serve as an instrument to implement new strategy | CPMT | Global M&E budget and staff time | Ongoing |
| SGP Annual Monitoring Report | Accountability, learning, presentation of results to donor | CPMT with inputs from NCs | Global M&E budget and staff time | Annually |
| Production of annual data analytics- by regions, typologies | Availability of data for decision making and presentation of results | CPMT | Global M&E budget and staff time | Annually |
| Administration of Impact Reviews across countries and themes | Assess change due to SGP at meta level; support generation of methodologically sound evidence | CPMT working to support NCs | Global M&E budget and staff time | Ongoing |
| Programme Delivery Reports (GEF Financial Reporting) | Assessment of implementation efficiency | UNOPS to UNDP-GEF | Covered under UNOPS operating costs | Quarterly |
| SGP Reporting for GEF APMR | Presentation of results to donor as financial mechanism for Conventions | CPMT to GEF Secretariat | Global operating budget and M&E budget and staff time | At least one month prior to deadline for GEF Secretariat reporting |
| Inputs to UNDP and GEF country and thematic evaluations | Provide lessons; assess effectiveness, relevance, results and impact | CPMT, SGP country teams, UNDP and /or GEF Evaluation Offices | Covered under budgeted staff time | Ad Hoc |
| SGP Independent Evaluation | Assess effectiveness, continued relevance, cost-efficiency; learning; adaptive management | CPMT, UNDP and GEF Independent Evaluation Offices | Global operating budget and M&E budget and staff time | Once per Operational Phase |

- Building on a solid foundation from previous phases of the SGP, the development of a multi-year SGP Results Based Management (RBM) Strategy, capturing key objectives, processes and responsibilities, is an immediate step going forward. An agile RBM system integrated across project, country and global levels, will address needs for accountability, adaptive management with informed decisions and actions, and learning from both success and failure. Principally, across the three levels (i) there will be a focus on developing normative frameworks; (ii) development of an enhanced online database as a mechanism to manage and report on the varied needs of grantees, country programmes and global portfolio; (iii) build robust capacities of people, processes, and systems- and institutionalize a programme-wide RBM culture; (iv) enhance data quality and assurance mechanisms; and (v.) introduce M&E innovations to capture non-linear and long term developmental change and impact.

# Governance and Management Arrangements

- SGP’s government and management arrangement has been discussed and agreed by the GEF Council through the GEF-7 SGP Implementation Arrangement paper. Below section summarizes the governance and management arrangement of the SGP.  Further details could be found in the SGP Operational Guidelines that is annexed in this project document.

- SGP management and implementation is governed by the updated SGP Operational Guidelines (provided in annex 5).  The principles and practices included in the Operational Guidelines are the results of practices that have proved effective and greatly useful in SGP operations for more than a decade.  UNOPS execution processes, policies, guidance and templates related to all matters of SGP administration are consolidated in the UNOPS SGP Standard Operating Procedures (SOPs) which are updated on an annual basis and available on the UNOPS intranet. The SGP Project Board has also approved a matrix of roles and responsibilities between UNDP and UNOPS and the programme’s various management units.

- Global level

- SGP Steering Committee:  As a GEF Corporate Program, the SGP is guided by a Steering Committee. The GEF SGP Steering Committee provides strategic corporate programme vision and long-term strategy for the SGP, as well as enables linkages with the GEF, its Agencies and CSO stakeholders. It is composed by GEF Secretariat as Chair, the UNDP GEF unit, the GEF CSO Network and the SGP Central Programme Management Team as secretariat to the committee. The Committee is tasked to: (1) Provide overall strategic direction to SGP in terms of corporate programme vision and long-term strategy; (2) Provide guidance and enable linkages with the GEF, its Partner Agencies and CSO stakeholders; (3) Establish country participation policy to include start-up of new Country Programmes as well as upgrading of existing ones; (4) Strongly support SGP’s resource mobilization efforts and facilitate establishment of strategic partnerships where useful; (5) Promote strengthened linkages between SGP and GEF projects and programmes; (6) Review, strengthen, and endorse the SGP Strategy, and; (7) Based on the SGP Annual Monitoring Report, help address any strategic issues arising during implementation.

- SGP Programme Board. The Programme Board is chaired by UNDP-GEF on behalf of UNDP as the ‘Project Executive’ member of the Board, and includes participation of UNOPS as the Implementing Partner, and SGP CPMT as the Project management team. The purpose of the Programme Board is to provide overall guidance, direction and oversight to the programme, including its management, and is accountable for progranne success.  The Programme Board usually meets twice annually to review strategic matters concerning programme implementation and oversight.

- Implementing Agency:  Given broad country presence, UNDP will continue to implement the SGP. UNDP implements the SGP as a global GEF corporate programme for both GEF funded activities and co-financed projects delivered through SGP. In this way, UNDP provides value-added benefits as programme implementation proceeds in synergy with overall UNDP and UNDP CO programming. Moreover, UNDP provides quality assurance and oversight services for the SGP through its headquarters, regional and country office levels. As defined by the GEF Council, these services cover: (a) project cycle management services which entail quality assurance and oversight across the full project cycle of project identification, preparation of project concept, preparation of detailed project document, project approval and start-up, project implementation and supervision, and project completion and evaluation; and (b) corporate services in relation to the formulation of policy and strategy for the GEF.  UNDP is represented on the SGP Steering Committee as well as the Project Board as described below.

- Executing Agency: The executing agency of the Programme will continue to be UNOPS, as has been the case since inception. Thus, UNOPS is the UNDP Implementing Partner for SGP. The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document. UNOPS provides programme execution services including administrative, financial, legal, operational, and procurement for the SGP as described in detail in the UNOPS SGP Standard Operating Procedures (SOPs). The UNOPS Grant Management Services works closely with the CPMT and UCP teams.  The relationship between UNOPS and UNDP (including COs) is guided by the umbrella MOU signed by both agencies. These include the arrangements covering UNDP CO support to SGP local administration and activities.  To facilitate global coherence in execution of services, organizational policies, and operating procedures, UNOPS maintains a central management team, which coordinates with SGP CPMT and UNDP/GEF HQ respectively. This central UNOPS team also represents UNOPS on the Project Board, which is coordinated by UNDP/GEF HQ, and includes the SGP CPMT.

- Other Agencies: particularly international NGOs, including Conservation International, International Union for Conservation of Nature, and World Wildlife Fund, have been involved closely with SGP operations in many countries. Representatives of international NGO country offices are frequently involved as NSC members. Local CSO partners of these GEF Agencies have been mobilized to apply for and access SGP grants. These GEF Agencies are often engaged in cofinancing SGP projects, knowledge sharing, and collaboration on related events and workshops at the country level. The SGP will continue to proactively pursue collaboration with other GEF Agencies for relevant activities and events to enable mutual learning and knowledge exchange, as well as explore strategic partnerships at the global and country levels. There also is a potential of a SGP Country Programme to act as a community-based granting mechanism for GEF and non-GEF funded projects of GEF Agencies, as has taken place for several projects with UN Environment.

- The SGP Central Programme Management Team (CPMT) at UNDP manages the SGP Global Programme and has overall responsibility for supervising the SGP Country Programme and for the technical and substantive quality of SGP country portfolios. CPMT develops global strategy, guidelines and standards in the development of SGP projects with the objective of ensuring quality, while also facilitating the design of proposals. CPMT supervises SGP National Coordinators and facilitates the start-up of new Country Programmes. CPMT is supported by and coordinates the work of UNOPS, which provides execution services. The CPMT consists of a Global Manager, a Deputy Global Manager, Programme Specialists responsible for matrixed country support and focal area guidance, Programme Specialists for Knowledge Management and for M&E, and Programme Associates.

- Country level

- UNDP Country Offices: located in more than 170 countries also will play a key role in providing the necessary support at the country level. UNDP provides oversight functions of the program at the global and national levels. In particular, with UNDP’s nearly universal presence in countries, its Country Offices have supported the start-up of SGP Country Programmes, recruitment of national coordinators, local supervisions, and resource mobilization. The UNDP Country Offices provide, as per request by and as agreed with UNOPS, any needed operational oversight for the SGP Country Programme. The UNDP Resident Representative/Coordinator or delegated staff is a member of the SGP National Steering Committee. While the SGP NC reports to the CPMT Global Manager as primary supervisor for global technical and substantive matters, the NC has the UNDP RR as secondary supervisor, in particular on assuring that he/she performs according to the high professional and ethical standards of the UN. In a limited number of countries, a National Host Institution (NHI), contracted through UNOPS, supports the administration of the programme

- SGP National Steering Committee (NSC):  in each country is composed of government representatives and a majority of nongovernmental membership to reflect the program’s mandated focus for CSO capacity building. The NSC will provide overall country guidance and provide direct linkages to national policymaking, development planning, knowledge dissemination, and leveraging of SGP's catalytic role. The NSC is responsible for selecting and approving projects, and for ensuring their technical and substantive quality with support from a Technical Advisory Group. In addition, NSC members are expected to support the Country Programme in resource mobilization and in mainstreaming SGP lessons learned and successes in other national contexts. The primary functions of the SGP Country Programme Office and NSC are the identification, review, and approval of qualified grant proposals that support priorities.

- SGP Country Programme Team: For each participating country, there is an SGP Country Programme Team often consisting of the National Coordinator (NC) and Programme Assistant (PA), for the operation of the SGP Country Programme on a day-to-day basis. The NC is responsible for all aspects of country programme operations and management, including implementation, management, partnership development, knowledge management and M&E of the programme.  When fulfilling his/her functions, and in adherence to the country-driven nature of the programme, the NC seeks guidance and support from, and in a sense also reports to the National Steering Committee (NSC) on progress in programme implementation.  Most SGP Country Programme Team are hosted by the UNDP Country Office, providing required local supervision and oversight of the program. In a limited number of countries, a National Host Institution is selected among the national NGOs with necessary capacity. The SGP Country Programme Strategy: is developed in each country that guides the SGP operation within country, enabling strategic use of resources and articulating how the SGP supports national and GEF strategic priorities. SGP Country Programme Team is responsible for all aspects of SGP management in the country, in particular with the work of the NSC, while also facilitating global coherence in SGP implementation through its reporting links to the SGP

SGP organization structure – simplified version:

# Financial Planning and Management

- The total GEF Core grant fund that has been approved by the GEF-7 Replenishment and Council is $128 million, along with the provision to have additional STAR allocations as per the SGP implementation Arrangement for GEF-7.  The Part 1 project, which consists half of the GEF-7 core funding, is financed through a GEF grant of USD $64 million with co-financing of US$ 64 million as per the PIF that was approved by the GEF Council in Dec 2018.  Furthermore, the current project’s scope and activities will be specific to the SGP project (GEF ID 10084), whilst contributing to the overall strategic directions of the SGP 7th operational phase. Thus, each project of the SGP will collectively and cumulatively contribute to the agreed approach, strategy, and results of the SGP in the respective GEF replenishment period.

- As per earlier practice and as recommended under the GEF council document, SGP grant allocation to countries will be based on “initial allocations [that] are made equally across all eligible and interested countries” with the provision to make “reallocation of any unused core funds across eligible and interested countries with a view to promoting the effective and efficient utilization of the GEF-7 core envelope.”  Thus, under this project (GEF ID 10084), initial allocation is expected to be around US $300,000 – US$ 350,000 per country (depending on the number of new countries that may join during the period) for existing countries while the amount will be prorated for new OP7 countries depending on when they join the SGP during GEF-7. UNDP, as the GEF Implementing Agency, is responsible for the oversight of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Budget Revision and Tolerance: As per UNDP requirements outlined in the UNDP POPP, should budget revision is required, SGP Global Manager will seek the approval of the UNDP-GEF team and Programme Steering Committee as required, particularly for budget re-allocations among components in the project when necessary.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop.

- Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, and if there is no increase of the project budget, extension of the operational closure date beyond the initial duration of the project may be approved by the UNDP-GEF Directorate. However, all costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed.

- Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project management Unit (team) complete their assignments.

- Financial completion (closure):  The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision). The project will be financially completed within 6 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report.  UNOPS will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Award ID: | 00121215 | Atlas Output Project ID: | 00117051 |
| Atlas Proposal or Award Title: | 7th Operational Phase of the GEF Small Grants Programme – Part 1 | Atlas Business Unit | UNDP1 |
| Atlas Primary Output Project Title | GEF-SGP Operational Phase 7-Country Projects |  |  |
| UNDP-GEF PIMS No. | 6271 |  |  |
| Implementing Partner | UNOPS |  |  |

|  | BUDGET PART 1 A-GEF GRANT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Expenditure Category | Details/Notes | GRANT COMPONENT | NON-GRANT COMPONENT |  |  |  |
|  |  |  | M&E | TA | PMC | Total |
| Grants | Grants to CSOs/CBOs. Approx 300k-350k per country will be allocated depending on the total number of new countries that will be joined | $39,000,000 |  |  |  |  |
| Sub-total Grant |  | $39,000,000 |  |  |  |  |
| Non Grants |  |  |  |  |  |  |
| International Consultants | Consultants include experts for M&E, KM & communication and capacity development activities |  | $61,114 | $150,886 | $0 | $212,000 |
| Local Consultants | Consultants include experts for M&E, KM & communication and capacity development activities |  | $243,800 | $604,200 | $0 | $848,000 |
| Salary and benefits | Salaries costs of NCs and PAs on Fixed Term and UNOPS International Consultant Agreement, and for Global staff (GM, DGM, 4 Technical Managers - each covering 30 countries and focal areas, Comm/KM, RBM, & 2 admin staff) |  | $826,800 | $3,473,387 | $2,157,100 | $6,457,287 |
| Contractual Services | Country Programme staff under Service contract, Database, K&M products and services |  | $424,000 | $9,105,588 | $914,506 | $10,444,094 |
| Trainings, Workshops, Meetings | Organization and participation on trainings, national and International level workshops and capacity development activities for country programme staff |  | $183,380 | $185,500 | $0 | $368,880 |
| Travel | Monitoring and Evaluation, start-up missions |  | $710,200 | $508,800 | $477,000 | $1,696,000 |
| Premises (Office rental) | Countries and global office rental and maintenance |  | $0 | $0 | $1,060,000 | $1,060,000 |
| Audits | 10-12 country level audits per year |  | $254,400 | $0 | $0 | $254,400 |
| Office Supplies | Administrative supplies |  | $0 | $0 | $106,000 | $106,000 |
| Other Operating Costs | Miscellaneous Costs - includes bank charges, cost of equipment and vehicle maintenance, purchase of office equipment and furniture, payments for printing services, other communication costs such as internet etc. |  | $212,000 | $0 | $879,800 | $1,091,800 |
| Sub-total non-Grant |  |  | $2,915,694 | $14,028,361 | $5,594,406 | $22,538,461 |
| Grand Total |  | $39,000,000 | $2,915,694 | $14,028,361 | $5,594,406 | $22,538,461 |
| Grand Total Budget Part 1 A |  |  | $61,538,461 |  |  |  |

| Grand Total Budget Part 1 B Agency Fee 4% | $2,461,539 |
| --- | --- |
| Grand Total Budget Part 1 A+ B | $64,000,000 |

| BUDGET PART 2- CO-FINANCING |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  | Government |  | CSO |  | Private Sector |  | Beneficiaries |  | Grand Total - Co-financing |
| Cash Co-financing | In-kind Co-financing | Cash Co-financing | In-kind Co-financing | Cash Co-financing | In-kind Co-financing | Cash Co-financing | In-kind Co-financing | Cash Co-financing | In-kind Co-financing |  |
| $4,000,000 |  |  | $11,000,000 |  | $20,000,000 | $1,500,000 | $1,500,000 |  | $26,000,000 | $64,000,000 |

| FINANCING PLAN |  |
| --- | --- |
| SGP CORE (First Tranche) Submitted | $61,538,462 |
| SGP CORE (Second Tranche (Un-Funded) | $61,538,462 |
| SGP STAR (Un-Funded) | $38,461,538 |
| Agency fee | $6,461,538 |

Total 			             $168,000,000

# Legal Context

- This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP.

- UNOPS is the Implementing Partner. The responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. The Implementing Partner shall: (a) put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried out; (b) assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan. UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- UNOPS shall not make any financial commitments or incur any expenses that would exceed the budget for implementing the project as set forth in this Project Document. UNOPS shall regularly consult with UNDP concerning the status and use of funds and shall promptly advise UNDP any time when UNOPS is aware that the budget to carry out these services is insufficient to fully implement the project in the manner set out in the Project Document. UNDP shall have no obligation to provide UNOPS with any funds or to make any reimbursement for expenses incurred by UNOPS in excess of the total budget as set forth in the Project Document.

- Any changes to the Project Document that would affect the work being performed by UNOPS shall be recommended only after consultation between the parties. Any amendment to this Project Document shall be effected by mutual agreement, in writing.

- UNDP and UNOPS shall use their best efforts to promptly settle through direct negotiations any dispute, controversy or claim which is not settled within sixty (60) days from the date either party has notified the other party of the dispute, controversy or claim and of measures which should be taken to rectify it, shall be referred to the UNDP Administrator and the UNOPS Executive Director for resolution.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

- UNOPS as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.) In the implementation of the activities under this Project Document, UNOPS as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures. Notwithstanding the foregoing, the UNOPS, as the Implementing Partner, will notify UNDP of any such allegations and investigations it may conduct further to such allegations.

- UNOPS as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient that is not a UN entity:

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNOPS’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

  - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

  - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

- UNOPS reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

- In the performance of the activities under this Project, UNOPS as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or handle SEA and SH.

- UNOPS agrees to undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The Implementing Partner and UNDP will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

- Annex 1: SGP Operational Guidelines

- Annex 2: Monitoring Plan:

This Monitoring Plan and the M&E Plan and Budget in Section VI of this project document will both guide monitoring and evaluation at the project level for the duration of project implementation. Please note targets noted in this table reflect the entirety of operational phase.

| Monitoring | Indicators | Targets | Description of indicators and targets | Data source/Collection Methods | Frequency | Responsible for data collection | Risks/ Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project objective from the results framework | Indicator 1 | 200,000 (male) 200,000 (female) | Number of direct project beneficiaries disaggregated by gender (individual people) | Annual Monitoring Report | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | All countries are incorporating social inclusion areas as part of CPS design and implementation |
|  | Indicator 2 | 600,000 | Number of indirect project beneficiaries disaggregated by gender (individual people) |  |  |  |  |
| Project Outcome 1 - Community-based models and biodiversity friendly practices and approaches promoted for conservation and sustainable use of threatened ecosystems and species in important terrestrial and coastal/ marine ecosystems | Indicator 3 | 2,200,000 ha | Area of landscapes under improved management to benefit biodiversity (hectares) (GEF core indicator 4.1) | AMR Grantee Monitoring Report Impact reviews SGP database | Annually Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Mobilized multi-stakeholder support for the landscape/seascape approach (including the government, local CSOs/CBOs, NSCs) Technical support provided, along with capacities, to facilitate the landscape/ seascape approach |
|  | Indicator 5 | 100,000 ha | Area of marine habitat under improved practices to benefit biodiversity (hectares; excluding protected areas) (GEF core indicator 5) |  | Annually |  |  |
| Project Outcome 2 - Climate-smart integrated practices improve productivity, food security, and livelihoods of smallholder farmers and supports achievement of national LDN targets. | Indicator 6 | 280,000 ha | Area of landscapes under sustainable land management in production systems (hectares) (GEF core indicator 4.3) | AMR Grantee Monitoring Report Impact reviews SGP database | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Landscapes address a production system Collaboration with full-sized projects to support vertical linkages for sustainable agriculture and fisheries, and food security |
|  | Indicator 7 | 200,000 ha | Area of degraded agricultural lands restored (hectares) (GEF core indicator 3.1) |  | Annually |  |  |
|  | Indicator 8 | 50 countries | Number of SGP countries supporting linkages and partnerships for sustainable food production practices (such as diversification and sustainable intensification) and supply chain management |  | Annually |  |  |
| Project Outcome 3 - Low carbon, viable and appropriate technologies and approaches demonstrated and deployed across sectors. Initiatives scaled up that improve community energy access and build a low carbon infrastructure, in line with larger national frameworks such as SDGs and NDCs. | Indicator 9 | 300KW | Increase in installed renewable energy capacity from local technologies (e.g. on types of renewable energy technology biomass, small hydro, solar). | AMR Grantee Monitoring Report Impact reviews SGP database | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Communities and CSOs have innovative and implementation capacity |
|  | Indicator 10 | 50 local energy access solutions | Number of typologies of community-oriented, locally adapted energy access solutions with successful demonstrations or scaling up and replication |  | Annually |  |  |
|  | Indicator 11 | 15,000 ha | Hectares of forests and non-forest lands with restoration and enhancement of carbon stocks initiated. |  | Annually |  |  |
| Project Outcome 4 - Innovative community-based tools and approaches demonstrated, deployed and transferred. Organize and strengthen multi-stakeholder coalitions with support from sound chemicals and waste management platforms. | Indicator 12 | 300 tons | Quantity of POPs/Mercury containing materials and products directly avoided (GEF core indicator 9.6) | AMR, SGP database Grantee Monitoring Report Impact reviews SGP database | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Issue buy-in existing at communities and CSO level in a given context |
|  | Indicator 13 | 2 coalitions | Number of local to global coalitions and networks established and/or strengthened (e.g. IPEN and Zero Mercury Working Group) |  | Annually Annually |  |  |
|  | Indicator 14 | 50 countries | Number of SGP countries working on increasing awareness and outreach for sound chemicals, waste and mercury management. |  | Annually |  |  |
| Project Outcome 5 - Appropriate integrated community-oriented sustainable urban solutions in partnership with government and private sector. These may often be first time innovations and are administered with a socially inclusive lens. | Indicator 15 | 25 countries | Number of SGP countries with improved capacities to promote community-driven integrated solutions for low-emission and resilient urban development. | AMR, SGP database Annual Country Monitoring Report | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Synergize efforts with Global Platform for Sustainable Cities (GPSC) Identified pockets of geographic areas or thematic issues to focus on (in the absence of landscape/ seascape approach here) |
|  | Indicator 16 | 25 urban solutions | Number of community-based urban solutions/ approaches (including chemical and waste management, energy, transport, watershed protection, ecosystem services and biodiversity) deployed. |  | Annually |  |  |
| Project Outcome 6 - CSO-Government-Private Sector Policy and Planning Dialogue Platforms promote community voices and participation in global, national and sub- national policy/strategy development on global environment and sustainable development issues. | Indicator 17 | 50 national/ sub-national CSO-government-private sector dialogues | Number of CSO-government-private sector dialogues convened to support community voice and representation in national/ sub-national policy development. | AMR Annual Country Monitoring Report Country impact reviews | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Government responds to consultative processes Dialogues/ Exchanges undertaken in mature SGP country programmes/ countries with advanced community results |
|  | Indicator 18 | 2 representatives from social inclusion groups per dialogue platform | Number of representatives from social inclusion group (indigenous people, women, youth, persons with disability, farmers, other marginalized groups) supported with meaningful participation in dialogue platforms. |  | Annually |  |  |
| Project Outcome 7 - South-South Exchange promoted to broker knowledge, build capacities and facilitate partnerships between communities, CSOs and other partners across countries on global environmental issues. | Indicator 19 | 20 countries | Number of countries undertaking South- South exchanges between communities, CSOs and other partners across countries. |  | Annually | Project, Country level (with portfolio wide data aggregation at Global level) |  |
|  | Indicator 20 | 15 south-south exchanges | Number of south- south exchanges at global and regional levels to transfer knowledge, replicate technology, tools and approaches on global environmental issues. |  | Annually |  |  |
| Project Outcome 8 - Social inclusion, particularly empowerment of women, indigenous peoples, youth and people with disabilities, is mainstreamed and enhanced in SGP programming on environment and livelihood improvement | Indicator 21 a | 30% of SGP portfolio | Number of SGP projects led by women 21 | AMR Annual Country Monitoring Report SGP database | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Social and Environmental Standards are incorporated at country and project levels. Country programme level management, in particular National Steering Committees, reflect a socially inclusive model. Marginalized groups such as the youth and the disabled people are aware of and interested in working with SGP |
|  | Indicator 21 b | 20% SGP portfolio | Number of projects contributing to closing gender gaps related to access to and control over natural resources |  | Annually |  |  |
|  | Indicator c: | 30% SGP portfolio | Number of projects that improve the participation and decision-making of women in natural resource governance |  |  |  |  |
|  | Indicator 21 c | 70% SGP portfolio | Number of projects that target socio-economic benefits and services for women |  | Annually |  |  |
|  | Indicator 22 | 20% of SGP country programmes | Number of SGP countries that have targeted support for Indigenous Peoples in terms of country level programming and management. |  | Annually |  |  |
|  | Indicator 23 | 15% of SGP country programmes | Number of SGP countries that demonstrate appropriate models of engaging youth and/or persons with disability. |  | Annually |  |  |
| Project Outcome 9 - A common, robust M&E strategy is developed and implemented in all countries at all levels (project, country and global)- establishing transparency, coherence and evidence-based decision making. | Indicator 24 | All SGP countries | Number of SGP country teams administering results management modalities in programme design, implementation and overall decision making using participatory mechanisms. | AMR Annual Country Monitoring Report SGP database | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Adequate availability of resources. M&E capacities built across global, country and project levels. Mechanisms of quality assurance and methodologically-sound thought production in place. |
|  | Indicator 25 | 6 impact reviews | Number of country/cross-country impact reviews undertaken that generate evidence of SGP impact and lessons learnt. |  | Annually |  |  |
| Project Outcome 10 - Networking and knowledge sharing leverage local actions for global change to safeguard global environment | Indicator 26 | All SGP countries | Number of SGP countries using citizen-based knowledge platform (digital library of community innovations) to document and curate community-based solutions to environment issues. | SGP intranet AMR | Annually | Project, Country level (with portfolio wide data aggregation at Global level) | Access to internet connectivity is available. Communities and CSOs have capacity to curate their knowledge. |

- Annex 3: UNDP Risk Log

| # |  | Description | Date Identified | Risk Category | Impact & Probability | Risk Treatment / Management Measures | Risk Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | GUIDANCE: | Enter a brief description of the risk. Risk description should include future event and cause. Risks identified through HACT, SES, Private Sector Due Diligence, and other assessments should be included. (In Atlas, use the Description field. Note: This field cannot be modified after first data entry) | Enter date | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other Subcategories for each risk type should be consulted to understand each risk type (see Deliverable Description for more information) (In Atlas, select from list) | Describe the potential effect on the project if the future event were to occur. Enter probability based on 1-5 scale (1 = Not likely; 5 = Expected) Enter impact based on 1-5 scale (1 = Low; 5 = Critical) (in Atlas, use the Management Response box. This field can be modified at any time. Create separate boxes as necessary using “+”, for instance to record updates at different times. Check “critical” if P x I = 20 or above) | What actions have been taken/will be taken to manage this risk. (in Atlas, use the Management Response box) | The person or entity with the responsibility to manage the risk. (in Atlas, use the Management Response box) | Status and effectiveness of management measures. (in Atlas, use the Management Response box to describe status of management measures. Update Probability and Impact as needed) |
| 1 |  |  |  | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other | Text P = I = |  |  |  |
| 2 |  |  |  | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other | Text P = I = |  |  |  |
| 3 |  |  |  |  |  |  |  |  |

- Annex 4: GEF 7 Taxonomy

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

UNEP (2009). Recycling – from e-waste to resources

Nakicenovic, N., Rockstrom, J. Gaffney, O. and Zimm, C. (2016). Global Commons in the Anthropocene: World Development on a Stable and Resilient Planent. IIASA Working Paper.

Brown, R.B. (2009). Plan B 4.0: Mobilizing to Save Civilization. Earth Policy Institute. Washington, DC.

Bierbaum, R. et al. 2018. Integration: to solve complex environmental problems. Scientific and Technical Advisory Panel to the Global Environment Facility. Washington, DC.

Evaluation of GEF Engagement with Indigenous Peoples (2017)

Joint GEF-UNDP Evaluation of the Small Grants Programme (2015) report that that “since 2006, the SGP has undertaken several steps to promote gender mainstreaming and women’s empowerment, with results evident on the ground”.

Laura Ledwith (2019). Strengthening GEF SP support to Indigenous Peoples: A review of SGP’s 25-year portfolio

https://erc.undp.org/evaluation/evaluations/detail/7076

http://www.gefieo.org/evaluations/evaluation-gender-mainstreaming-gef-2017

According to the ILO (2009), enterprise development can make a significant contribution to women’s empowerment and gender equality and has a key role in gender strategies.

Cases (projects) were selected for assessment based on their degrees of quantitative and qualitative information on scaling up outcomes. Additionally, the review identified 65 cases in 50 countries where some extent of scaling up in SGP projects had occurred.

GEF IEO (2019). Evaluation of GEF Support to Scaling up Impact. 56th GEF Council Meeting Document. Washington, DC

To ensure cost-effectiveness, project level monitoring and evaluation activities, including project site visits, are conducted on a discretionary basis, based on internally assessed criteria including (but not limited to) project size and complexity, potential and realized risks, and security parameters.

Please note SGP CPS is regarded as a dynamic document and can be updated by the SGP country team and NSC on a periodic basis to reflect any necessary adjustments to ensure maximum impact. This CPS update process should be part of the Annual CPS Review.

Timely and quality country level submissions to Annual Monitoring Process are mandatory. As a Global Programme, it enables aggregated reporting by CPMT to GEF, UNDP and other stakeholders.

Memorandum of Understanding For a Strategic Partnership Between the United Nations Development Program (UNDP) and the United Nations Office for Project Services (UNOPS), signed by Ad Melkert, UNDP Associate Administrator and Jan Mattson, UNOPS Executive Director, June 5, 2009.

This UNOPS central management team or small grants cluster with fully dedicated staff and based in New York is for fast and efficient delivery as well as regular face-to-face meeting on admin and finance matters with CPMT.

Small Grants Programme: Management of Core Funding and Results Framework for GEF-7 (GEF/C.55/Inf.05)

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Per advice from the GEF Secretariat, the results and targets under this project has been adjusted to fit the scope of the project.  The reporting on the results will follow the Policy on Monitoring (GEF/C.56/03/Rev.01, June 12, 2019) by operational phase.