UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 5494 | SB-000689.36.01 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Development of Mercury Risk Management Approaches in Latin America |  |  |
| Duration months | Planned |  | 36 months |  |  |
|  | Extension(s) |  | 60 months |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |  |  |
| Executing Agency(ies) |  |  | Basel Convention Coordinating Centre, Stockholm Convention Regional Centre, for Latin America and the Caribbean Region (BCCC-SCRC) hosted by Uruguay |  |  |
| Names of Other Project Partners |  |  | UNEP |  |  |
|  |  |  | MIAs |  |  |
| Project Type |  |  | MSP |  |  |
| Project Scope |  |  | Regional |  |  |
| Region (delete as appropriate) |  |  | LAC |  |  |
| Names of Beneficiary Countries |  |  | Regional (Argentina, Ecuador,Nicaragua,Peru,Uruguay) |  |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |  |
| GEF Focal Area(s) |  |  | POPs |  |  |
| UNDAF linkages |  |  | Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Where appropriate, insert the most relevant SDG target(s) and indicator(s) to which the project contributes |  |  |
| GEF financing amount |  |  | 916000 |  |  |
| Co-financing amount |  |  | 2894434 |  |  |
| Date of CEO Endorsement |  |  | 18-Nov-13 |  |  |
| Start of Implementation |  |  | 09-Jun-14 |  |  |
| Date of first disbursement |  |  | 09-Jun-14 |  |  |
| Total disbursement as of 30 June |  |  | 842197 |  |  |
| Total expenditure as of 30 June |  |  | 856921 |  |  |
| Expected Mid-Term Date |  |  | 09-Dec-15 |  |  |
| Completion Date |  | Planned | Na |  |  |
|  |  | Revised | 31-Dec-18 |  |  |
| Expected Terminal Evaluation Date |  |  | Q2 2019 |  |  |
| Expected Financial Closure Date |  |  | Q4 2019 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Chemicals and Health Subprogramme | Specify the relevant Expected Accomplishment(s) & Indicator(s) a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] PoW indicator a(i): National Governmental Agencies are regionally supporting the intergovernmental processes developing and bringing into force the Minamata Convention on Mercury. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] The medium-term strategy for the years 2014-2017 on mercury comprises supporting the intergovernmental processes developing and bringing into force the Minamata Convention on Mercury. During the project execution have been developed national inventories, assessed national legislation and identified current gaps and needs in mercury management. All activities have contributed to the environmental sustainability of participant countries and, in the medium and long term, to reduce the risk associated to mercury management. All countries participant ratified Minamata convention during the project. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes [section to be shared with SDG unit] The project addresses the main problems related to mercury according to the following SDGs: SDG 1: End poverty in all its forms and everywhere The urban and rural poor people systematically face unacceptably high exposure risks to mercury due to their occupations (eg: mercury extraction, artisanal and small-scale gold mining, waste management, recycling), their living conditions, proximity to landfills and open burning areas and their lack of knowledge about the possible health effects of exposure to mercury. SDG 2: Eradicate hunger, achieve food security and improve nutrition and promote sustainable agriculture One of the main sources of exposure to mercury is the consumption of fish and shellfish contaminated with it. The consumption of fish with high mercury content, particularly those found at the upper levels of the food chain, due to bioaccumulaton and biomagnification of mercury could have serious health consequences. SDG 3: Ensure healthy lives and promote well-being for all at all ages Mercury is toxic to human health and constitutes a specific threat to the development of the fetus and the child in its first years of life. Human exposure occurs mainly through the inhalation of elemental mercury vapors during industrial processes and through the consumption of contaminated fish and shellfish, which can cause mercury poisoning. SDG 7: Ensure everyone's access to affordable, reliable, sustainable and modern energy The combustion of coal is the second most important anthropogenic source of mercury emissions into the atmosphere. SDG 8: Decent work and economic growth One form of exposure to mercury is the inhalation of its vapors. It is very likely that this exposure occurs in the workplace. The most dangerous professions and livelihoods in terms of exposure to mercury are artisanal and small-scale gold mining, the handling and recycling of waste, mercury refining, and medical and dental care. SDG 12: Ensure sustainable consumption and production patterns Reduction of mercury contamination and mercury-containing waste through the introduction of mercury-free alternative products, processes and technologies that are cost-effective and in line with the best available techniques guidelines. SDG 14: Conserve and sustainably use oceans, seas and marine resources for sustainable development The level of mercury in certain types of fish (eg, tuna red, swordfish) has become so high that some governments warn against their consumption or have banned their importation. To reduce the use and release of mercury in various activities carried out on land, prevents mercury from reaching aquatic sources and reduces the accumulation of mercury in the food chain. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | MU | MS | MS | S |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. BCCC-SCRC was the Executing Agency and it coordinated all project activities implemented by the participant countries, and it also provided technical assistance and guidance to the countries. Ecuador, Peru and Uruguay implemented their activities through their respective Ministries of Environment and BCCC-SCRC managed the project funds for these countries. In Argentina, the National Executing Agency was BCRC-INTI hosted by Argentina. Nicaragua decided to quit de project due to the lack of funds (USD 43.000) to implement all the activities. The Minister of Environment Ms. Juanita Argeñal Sandoval sent a letter to the BCCC-SCRC indicating her decision, March 15th, 2016. All countries set up national coordination groups/committees to keep the main stakeholders informed and participating in the different project activities. BCCC-SCRC took two key actions that allowed saving of both, time and GEF resources. The first action was the close implementation of this project with the MIAs regional project, both executed by BCCC-SCRC. This decision was aimed to have a positive impact on project's finances from saving on air tickets, accommodation, venues for workshops and international consultants. The second action taken was the management of funds for Peru and Ecuador by BCCC-SCRC, which facilitated the implementation of project activities in these countries, by directly hiring consultants and services proposed by national coordinators and performing the required disbursements. The project was dynamic, based in the country’s reality was maintained a balance between the project´s outputs and required for the Minamata Convention. The BCCC-SCRC translated the mercury toolkit into Spanish to facilitate the use of it by other Spanish speaking countries October, 2015. The BCCC-SCRC signed an agreement with UNITAR, in accordance with the countries involved on the project, to review the toolkit of countries. Argentina, Ecuador, Peru and Uruguay finalized their Mercury releases inventories level 2. The inventories have been reviewed by UNITAR. The BCCC-SCRC organized specific activities and workshops to respond to the different countries needs to strength their capacities for the elaboration of national action plans and risks management approaches. Follow REGIONAL ACTIVITIES (description of the activities by date order) Regional workshop (inception, medium term and final workshop). Trainings. Evaluations. - Regional workshops (inception, medium term and final workshop). INCEPTION WORKSHOP The inception workshop was held in Montevideo (November 18th - 20th, 2014) and the report of this meeting was presented to UNEP (Implementing Agency). The participant’s countries were: Argentina, Bolivia, Brazil, Chile, Costa Rica, Dominican Republic, Ecuador, Mexico, Nicaragua, Paraguay, Peru and Uruguay. Argentina, Ecuador, Nicaragua, Peru and Uruguay belonged to this Project. Bolivia, Chile, Dominican Republic and Paraguay belonged to a Project named Minamata Initial Assessments (MIAs), where UNEP was the Implementing Agency and the BCCC-SCRC was the Executing Agency. Brazil, Costa Rica and Mexico were executing their own similar projects on this topic and were invited to share their experiences at Regional Level. At the inception workshop several items were identified for regional cooperation between the 12 participant’s countries: • To coordinate the development of national/regional emission factors on mercury. To identify priorities sectors basing on the calculation of emissions (eg. mining); different countries / projects could develop different emission factors and exchange them with other countries in order to optimize efforts. • To ensure a standard implementation of the toolkit supported by a regional consultant, addressing issues of analysis sensitivity, uncertainty and data validation. To make possible the knowledge sharing between technical personnel in charge of inventories development among participant countries (eg. through webinars). The Project Steering Committee met during the inception workshop. MID-TERM WORKSHOP At the Project MID-TERM workshop, held in Montevideo, Uruguay, October 18th - 20th, 2016, the involved countries (Argentina, Ecuador, Peru and Uruguay) have reviewed the work plan and the budget. The countries redefined the regional consultancies for the Project. FINAL WORKSHOP - The Project final workshop was held in Montevideo, Uruguay, 21st to 22nd, November, 2017. It was attended by 25 representatives from the governments of Argentina, Bolivia, Chile, Dominican Republic, Ecuador, Nicaragua, Paraguay, Peru and Uruguay. Argentina, Ecuador, Nicaragua, Peru and Uruguay belonged to this Project. Bolivia, Chile, Dominican Republic and Paraguay belonged to a Project named Minamata Initial Assessment (MIA), where UNEP is the Implementing Agency and the BCCC-SCRC is the Executing Agency. ### The objectives were to share the outcomes and lessons learned during the execution of the projects in all participating countries, closing and assessment of regional projects. - The main outcomes and lessons learned were presented in thematic panels. The panels were: - Mining and contaminated sites. - Monitoring and analysis. - Legislation, regulations and national plans. - Inventories, gaps for implementing the Convention, opportunities for future activities, etc. - Conclusions: - The main problems in the region are related to artisanal gold mining, waste management in general and, especially, mercury-containing products. - Final disposal sites are a great challenge for the region and are a common factor. Countries also share the need for risk studies in relation to cases of contaminated sites. - The following needs stand out among the comments from the attendees: To develop regional mercury emissions factors for emissions inventories to be more representative, mainly by characterizing certain ores from the region (Toolkit Level 1 and 2). - To develop specific solutions, with tangible results, especially in relation to the interim or permanent storage of mercury and mercury-containing waste. - To carry out projects for strengthening monitoring in biotic and abiotic matrices. - To coordinate with other stakeholders at the national and regional level for planning future actions. - To generate more opportunities for monitoring emissions. - To share experiences, practical exercises and specific case studies. - To prepare a database for locating contaminated sites. - To have more technical support and plan more training activities. - To have more resources for fulfilling these objectives. - Trainings A Subregional Workshop on Enhancing Parties Capacities for Environmentally Sound Management of Mercury Wastes, in the framework of the Basel Convention, was organized by the Joint Secretariat of the Basel, Rotterdam and Stockholm Convention in cooperation with the BCCC-SCRC, in Uruguay (November 17th - 19th, 2015). It was attended by 35 participants representing governments of Argentina, Bolivia, Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay and Venezuela, as well as several international experts on the subject. This 3-days workshop, has intended to improve capabilities of the environmentally sound management of mercury waste through awareness rising. Participants also received training in the areas of Environmental Biomonitoring, Contaminated Sites, Assessment and Risk Communication. The participation of Dr. Davis Bellinger, from Harvard University, expert on Mercury in health sector was charged to this Project. A risk communication training was carried out in Ecuador and Peru (May 15th -19th, 2017), by specialists of the Centers for Disease Control and Prevention (CDC) from USA, in Argentina and Uruguay the same course was held on August 14th -18th, 2017. The courses’ topics were: risk communication, risk perception, the need to communicate and how, the development of models and methods of communication, among others. This training made possible to improve the capacities of risk managers in the countries where was performed (authorities and experts), under conflict situations as artisanal and small-scale gold mining. Training on contaminated sites with mercury was carried out at the Center for Energy, Environmental and Technological Research (CIEMAT), Madrid, Spain. The training course was 5 days long, October 23rd to 27th, 2017. Training in monitoring and analysis of mercury in different biotic and abiotic matrices, it was conducted at the Department of Environmental Sciences, Jozef Stefan Institute, in the City of Ljubljana, Slovenia. The training course was 10 days long, November 8th to 18th, 2017. A Webinar on Communication of Mercury risks was organized by UNITAR and the BCCC-SCRC, the general objective was the different ways to deal with the communication obligations of mercury risks and the stages to follow in order to develop an information campaign. This webinar, part 1 was held on December 7th, 2017 and part 2 was held on January 25th, 2018. Based on the conclusions and needs of the countries emerged at the final workshop, and due to the existence of funds to be able to carry out new outcomes, in order to strength the project and its countries members, 3 activities was organized to strengthen the capacity of participating LAC countries: - A training course on environmental matrices and speciation of mercury was conducted at the Department of Environmental Sciences, Jozef Stefan Institute, in the City of Ljubljana, Slovenia. This course was 10 days long, July 9th to 20th, 2018. - Considering air could be an obligatory matrix to measure the effectiveness evaluation of the Minamata Convention, the steering committee decided to hire the Consiglio Nazionale delle Ricerche (CNR) to obtain air primary results. The four countries members of the project selected the monitoring sites according to the CNR’s Standard Operation Procedure (SOP). The Mercury Passive air monitoring took 5 weeks (from September 2018 to October 2018), the samples were analysed at CNR, Rome, Italy. Results are confidential. - 9 Laboratories took part in the Mercury laboratory Inter-comparison exercise in different matrices (standard solutions, biota and/or human hair) with the Research Centre for Toxic Compounds in the Environment (RECETOX), Brno, Check Republic. - Evaluations Terminal evaluation was prepared for the Evaluation Office of UN Environment by Jorge Leiva Valenzuela as the Lead Consultant. The report was reviewed by the BCCC-SCRC July 2019. Terminal evaluation summary: The project addressed important issues related with mercury management in all countries, thus making it relevant for updating/upgrading information gaps and to improve current regulations or develop new ones. It was also important to GEF and UN Environment in order to strengthen national capabilities of participant countries to comply with national commitments. However, the project had some weakness in its formulation. The M&E system was not properly delineated in the project document and important components such as the requirement for elaboration of an exit strategy was missing. In addition, elaboration of indicators for outcomes and objectives were mostly for products rather than results. The project reached most of its desired outcomes and contributed to effectively identifying information gaps in all countries through the search of current national regulations dealing with mercury and chemicals. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | MU | MS | MS | S |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. The project reached most of its desired outcomes and contributed to effectively identifying information gaps in all countries through the search of current national regulations dealing with mercury and chemicals. In the same way each national inventory updated relevant information on mercury sources and thus, assessed priority actions for decision making processes and elaboration of regulations to comply with Minamata Convention provisions. On the other hand, activities of strengthening of analytical capacities in each of the participant countries contributed to determination of mercury in several environmental matrices such as air, soil, water and fish. Thanks to these, all countries could either elaborate or update their action plans with more precise data for decision taking. Finally, analytical capacities were improved in all countries and it will contribute to update the list of potentially contaminated sites in all countries. PROGRESS SUMMARY 1- The inception workshop was held in Montevideo, Uruguay, November 2014. 2- During the inception workshop took place the Toolkit inception training. 3- The Project Steering Committee met for first time during the inception workshop. 4- The agreements with Argentina, Peru and Uruguay were signed (Memorandum of Understanding - MOUs) in 2015. These countries held their initial workshops and hired their respective national consultants. The Peru’s and Uruguay´s funds were managed by the Centre, as were requested for these countries, to facilitate the project implementation on them. In Argentina, the National Executing Agency was BCRC, hosted by Argentina. 5- A Sub-regional Workshop on Enhancing Parties Capacities for Environmentally Sound Management of Mercury Wastes was held in Montevideo (November 17th - 19th, 2015). 6- Nicaragua decided to quit de project due to the lack of funds (USD 43.000) to implement all the activities. The Minister of Environment Ms. Juanita Argeñal Sandoval sent a letter to the BCCC-SCRC indicating her decision, March 15th, 2016. 7- Uruguay hired a consultant who worked for the project, he made the Uruguayan update inventory and developed a Survey Report of Importers of Medical Products and Technologies containing Mercury (May 2016). It is important to remark that Uruguay elaborated guidelines for the management of mercury medical waste. 8- Uruguay worked on the opening of some customs codes for mercury products and is facing the challenge of electrical and electronic products, as lamps for example, since there is no customs code associated with the amount of mercury and many times within the same code there is a great variety of lamps. 9- Peru organized a National Conference on Measurement and Reduction of mercury emissions, it was held in Lima, June 20th to 21st, 2016. This meeting allowed the exchange of experiences with international experts on control technologies and measurement of mercury emissions, as well as an improvement in the implementation of Minamata Convention. The conference was attended by representatives of Governmental Agencies, specialists in the cement industry, chlor-alkali, mining, lime, consulting firms, etc. 10- In Peru, the Project contributed to the technical assistance in Madre de Dios Department, where 11 Districts in Madre de Dios were declared on emergency State by Mercury pollution. Three experts identified by United Nations travelled and stayed at the place for one week (June 20th to 24th, 2016), working together to take integrated actions by the country and for the establishment of a regional monitoring network (within Peru). 11- Project MID-TERM workshop, was held in Montevideo, Uruguay, October 18th - 20th, 2016, the involved countries (Argentina, Ecuador, Peru and Uruguay) reviewed the work plan and the budget. They redefined the regional consultant component. The steering committee report is attached. 12- The project cooperation agreement between the BCCC-SCRC and Ecuador was signed on November, 2016. Ecuador’s funds were managed by the Centre, as was requested by the country, to facilitate project implementation on it. The reasons of the delay on the signature of the MOU were basically the changes of the Environmental Minister (3 times since the initial workshop), and the focal point who management all the project information Ms. Paulina Villamar left the Environmental Ministry on December 2015. 13- A Risk communication training course was carried out in Ecuador and Peru (May 15th -19th, 2017), by specialists of the Centers for Disease Control and Prevention (CDC) from USA, in Argentina and Uruguay the same course was held August 14th -18th, 2017. 14- All countries finalized their Mercury releases inventories level 2 (Argentina, Ecuador, Peru and Uruguay). The inventories have been reviewed by UNITAR. The BCCC-SCRC has signed an Agreement with UNITAR to make the countries inventories revision process in accordance with the involved countries. 15- A training course on mercury contaminated sites was carried out at the Center for Energy, Environmental and Technological Research (CIEMAT), Madrid, Spain. The training course was 5 days long, October 23rd to 27th, 2017. 16- A training in monitoring and analysis of mercury in different biotic and abiotic matrices was conducted at the Department of Environmental Sciences, Jozef Stefan Institute, in the City of Ljubljana, Slovenia. The training course was 10 days long, November 8th to 18th, 2017. 17- Peru has developed different Consultancies instances along the project execution: - Contaminated Sites. - Identification and meta-analysis of the studies on mercury monitoring in humans and the environment. - Research work on the hydrometallurgical recovery of gold and mercury from tailings of the amalgamation of artisanal mining - case study, which is being carried out by the National University of San Marcos, through the San Marcos Foundation. 18 - Peru organized several workshops on Clean Technologies on artisanal mining. 19- Project FINAL WORKSHOP, was held in Montevideo, Uruguay, November 21st – 22nd, 2017. It was attended by 25 representatives from the governments of Argentina, Bolivia, Chile, Ecuador, Nicaragua, Paraguay, Peru, Dominican Republic, Uruguay and UN Environment. 20- A Webinar on Communication of Mercury risks was organized by UNITAR and the BCCC-SCRC, January 25th, 2018. 21- A training course on environmental matrices and speciation of mercury was conducted at the Department of Environmental Sciences, Jozef Stefan Institute, in the City of Ljubljana, Slovenia. This course was 10 days long, July 9th to 20th, 2018. 22- 9 Laboratories took part in the Mercury laboratory Inter-comparison exercise in different matrices (standard solutions, biota and/or human hair) with the Research Centre for Toxic Compounds in the Environment (RECETOX), Brno, Check Republic. 23- Peru’s final workshop was held in Lima in December 18th - 20th, 2018. 24 - The steering committee decided to hire the Consiglio Nazionale delle Ricerche (CNR), from Rome, Italy, to obtain primary results of mercury on air. The four countries members of the project selected the monitoring sites according to the CNR’s SOP. The Mercury Passive air monitoring was performed for 5 weeks (from September 2018 to October 2018), the samples were analysed at CNR. Results are confidential. 25- The final regional report was developed based on the national reports and regional activities. The focal points of the project reviewed and approved it. Base on the final regional report the BCCC-SCRC made a brochure with the project results. Link: http://ccbasilea-crestocolmo.org.uy/resultado/folleto-con-resumen-de-resultados-de-8-paises/ 26- Peru has organized a National Conference on amalgams, held in Lima in June 19th - 20th, 2019. 27- Peru also organized a Training in monitoring and analysis of mercury in different biotic and abiotic matrices, held in Madre de Dios in June 24th to 28th, 2019. 28- Terminal evaluation was prepared for the Evaluation Office of UN Environment by Jorge Leiva Valenzuela as the Lead Consultant. The report was reviewed by the BCCC-SCRC on July 2019. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | S | M | L | L |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 Nicaragua left the project in 2016, since it considered that the assigned resources were insufficient to cover the country’s needs and started a preparation of a more comprehensive mercury project with UNDP. The extension of the project’s deadline due to bureaucratic issues in the different countries has been a challenge. |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] All the stakeholders got involved and worked thoroughly to achieve objectives and outcomes. Project activities strengthen the technician network related to mercury issues. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] This project is an old project, so there were not any activities gender oriented. However, some training activities took into consideration the special exposure to mercury by women (for example mercury analysis in cosmetic and use dental amalgam during pregnancy) On the other hand, technicians and decision makers are mostly women. |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval [section will be uploaded into the GEF Portal] Definition was not found. |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/ GEF communication] Title: Quality life improvement of miners in Peru. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To strengthen the capacity of participating LAC countries (Argentina, Ecuador, Peru, Nicaragua and Uruguay) to identify mercury sources and the priority actions to be undertaken. | Mercury inventories developed for five participating countries. National mercury risk management approaches with agreed priorities developed for five participating countries. | While some partial inventories have been completed for specific sectors in participating countries, no comprehensive inventories exist. No national mercury risk management approaches exist. | 5 draft Inventories. 5 draft national mercury risk management approaches developed. | 5 complete Inventories. 5 national mercury risk management approaches completed. | 4 complete Inventories which were reviewed by UNITAR. 4 National mercury actions plans developed. Nicaragua left the Project. | S |
| Outcome 1: Information needs identified in participating countries | 1.1 Workplan, budget and M&E plan endorsed by all participating countries | 0 | 1 | 1 | 1 |  |
|  | 1.2 Existing materials and information on mercury identified and utilized | Each participating country has provided initial data to BCCC – SCRC pertinent to mercury uses and releases, and information on their regulation | Baseline information collated by BCCC-SCRC for each of the 5 participating countries. | Comprehensive set of guidance documents used. | Baseline information collected by BCCC-SCRC for each of the 5 participating countries. | S |
| Outcome 2: Comprehensive information on mercury sources and releases enable a better understanding of mercury risks to human health and the environment for participating countries | 2.1 Level 1 and Level 2 mercury inventories for each participating country, identifying key sectors | UNEP Global Assessment (2008) | >5 Level 1 mercury inventories, one for each participating country, including detailed Level 2 inventories for key sectors identified in each country. | >5 Level 1 mercury inventories, one for each participating country, including detailed Level 2 inventories for key sectors. >2-3 key industrial sectors with Level 2 inventory in each participating country. | 3 complete Inventories level 2 reviewed by UNITAR. Argentina developed level 1 inventory at National level and level 2 in 4 key sectors, reviewed by UNITAR. Nicaragua left the Project. | S |
| Outcome 3: Enhanced understanding of mercury priority sources and capacity for mercury management through the development/ identification of national mercury risk management approaches including the identification of management gaps and needs | 3.1 Number of mercury priorities set in each participating countries. | Preliminary data from some countries. | Inventories developed and available for setting priorities on each country, and a national priority setting workshop. | 3 National priorities clearly articulated in national mercury risk management approaches. | This outcome was achieved as expected by the project document, which focused its intervention in governmental institutions and key private sector stakeholders. All countries completed this activity (except Nicaragua). | S |
|  | 3.2 Number of assessments on regulatory aspects and means for mercury emissions control | The majority of participating countries have a lack of specific regulations related to mercury | Inventories developed and available for use in the regulatory assessment. | 5 Regulatory assessments which should cover key mercury emissions sectors. | All countries made a screening of legal, technical and scientific information available and identified the gaps and needs to address the sound management of mercury products and waste (except Nicaragua) | S |
|  | 3.3 Number of data sets collected and analysed greatly contribute to the development of national risk management approaches | Scattered studies on mercury monitoring in humans or environment, lack of consistency in the approaches | At least 5 datasets identified and analysed | At least 10 data sets identified, collected and analysed Populations living around priority sites defined and consulted on issues related to mercury pollution and development of risk management approaches. | Under this component, several training and exchange activities were carried out to update analytical techniques to determine mercury in humans, soil, water and air. The aim was to perform monitoring of this element and provide reliable data on pollution in several matrices. Peru analyzed, besides de former samples, cosmetics (whitening creams) and Ecuador biota and sediments. | S |
|  | 3.4 Number of prioritized national mercury risk management approaches for mercury reduction | Some participating countries have partial inventories and have developed initial national mercury risk management approaches for some key mercury release issues | Inventory data available and published in inventory, in 5 countries allowing for the development of national mercury risk management approaches in each country | 5 prioritized national mercury risk management approaches completed. | At the inception workshop the Project Steering Committee met and decided to change National mercury risk management approaches to national management plans, since the amount of resources available for this component was considered insufficient to meet this goal. 4 actions plans completed. Nicaragua left the Project. | S |
| Outcome 4: Lessons learned available and shared regionally allow better practices in future projects | 4.1 Number of regional key sector identifying mercury management gaps | No detailed regional assessments of key sectors currently available | To work focused on national level data collection | 10 key emissions sectors | It was found 3 key emissions sectors, not 10, due to the main problems in the region are related to artisanal gold mining, management of waste in general and, especially, mercury-containing products. | S |
|  | 4.2 Final project report on lessons learned and main outputs (inventories, national mercury risk management approaches) endorsed and diffused | No regional lessons learned report currently available | NA | Endorsement of regional lessons learned report Lessons learned report disseminated among stakeholders in participating countries, and also to focal points in non participating countries | Final regional report with lessons learned and brochure in Spanish and in English languages. | S |
|  | 4.3 Number of Steering Committee Meeting reports available as part of the M&E plan | 0 | 2 STC meeting reports | 3 STC meeting reports | 3 STC meeting were carried out. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | The project team has put a lot of efforts to achieve all the objectives during the year. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets |  |  |
| on stakeholder engagement |  |  |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results |  |  |
| Others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |

| Output 1: Workplan, budget and M&E plan endorsed by all participating countries and use to guide the achievement of the project | 4 months then start |  |  | Workplan, budget and M&E plan endorsed by all participating in the inception workshop (November 18th - 20th, 2014). | S |
| --- | --- | --- | --- | --- | --- |
| Activity 1: Organize an inception workshop to confirm stakeholder’s commitment to the project and revise and agree on the work plan and budget | 4 months then start | 100% | 100% | The inception workshop was held in Montevideo (November 18th - 20th, 2014) and the report of this meeting was presented to UNEP (Implementing Agency). The participant’s countries were: Argentina, Bolivia, Brazil, Chile, Costa Rica, Dominican Republic, Ecuador, Mexico, Nicaragua, Paraguay, Peru and Uruguay. Argentina, Ecuador, Nicaragua, Peru and Uruguay belong to this Project. Bolivia, Chile, Dominican Republic and Paraguay belong to a Project named Minamata Initial Assessment, where UNEP was the Implementing Agency and the BCCC-SCRC was the Executing Agency. Brazil, Costa Rica and Mexico were executing their own similar projects on this topic and were invited to share their experiences at Regional Level. | S |
| Output 2: Basic information and guidance on mercury management available to relevant stakeholders | 8 months then start |  |  | The BCCC-SCRC has translated the mercury toolkit into Spanish to facilitate the use of it by Spanish speaking countries. | HS |
| Activity 2: Identify initial guidance materials and existing studies and information needs | 8 months then start | 100% | 100% | Workshop preparation included: identification of information gaps and needs for regulations and infrastructure to implement sound mercury management systems. | S |
| Output 3: Mercury level 1 and 2 inventories available in each participating country | 16 months then start |  |  | Argentina, Ecuador, Peru and Uruguay have developed and/or upgraded mercury inventories, levels 1 and 2. The final documents were reviewed by UNITAR (except Nicaragua). |  |
| Activity 3: Develop and/or upgrade mercury inventories in participating countries | 16 months then start | 100% | 100% or 80% due to Nicaragua?? |  | S |
| Output 4: National priorities identified in each participating country | 22 months then start |  |  | All countries completed this activity (except Nicaragua). | S |
| Activity 4: Develop criteria and prioritize mercury sources in each participating country | 22 months then start | 100% | 100% or 80% due to Nicaragua?? | All countries completed this activity (except Nicaragua). | S |
| Output 5: National regulatory framework for mercury assessed (report) and recommendation provided in each participating country | 22 months then start |  |  | All countries made a screening of legal, technical and scientific information available and identified the gaps and needs to address the sound management of mercury products and waste (except Nicaragua). | S |
| Activity 5: Assess the regulatory aspect of mercury management in each participating country | 22 months then start | 100% | 100% or 80% due to Nicaragua?? |  | S |
| Output 6: Good quality data on mercury levels in the environment, biota and humans, and on mercury in emissions from key sectors in participating counties collected and supporting the mercury risk management approaches | 22 months then start |  |  | Under this component, several training and exchange activities were carried out to update analytical techniques to determine mercury in humans, soil, water and air. The aim was to perform monitoring of this element and provide reliable data on pollution in several matrices. | S |
| Activity 6: Collect data of good quality on mercury levels in the environment, including biota and humans, and mercury emissions at the source | 22 months then start | 80% | 100% | Considering air could be an obligatory matrix to measure the effectiveness evaluation of the Minamata Convention, the Project' steering committee decided to hire the Consiglio Nazionale delle Ricerche (CNR) to obtain primary results. The four countries members of the project selected the monitoring sites according to the CNR’s SOP. The Mercury Passive air monitoring took for 5 weeks (from September 2018 to October 2018), the samples were analyzed at CNR, Rome, Italy. Results are confidential. | S |
| Output 7: Risk management approaches for mercury reduction developed including long, medium and short term measures to decrease mercury releases | 30 months then start |  |  | At the inception workshop the Project Steering Committee met and decided to change National mercury risk management approaches to national management plans, since the amount of resources available for this component was considered insufficient to meet this goal. | S |
| Activity 7: Identify and/or develop national mercury risk management approaches in each participating country | 30 months then start | this output was changed | this output was changed |  | S |
| Output 8: Report on existing lessons learned in key sectors developed |  |  |  | This outcome was achieved as expected by the project document, which focused its intervention in governmental institutions and key private sector stakeholders. | S |
| Activity 8: Compile regional lessons learned in key sectors and develop regional report and organize 1st lessons learned workshop | 4 months then start | 100% | 100% | Lessons learned workshop (November 18th - 20th, 2014). | S |
| Activity 9: Compile regional lessons learned in key sectors and develop regional report and organize 2 nd lessons learned | 16 months then start | 100% | 100% | Mercury waste workshop, November, 2015 Mid-term workshop, October, 2016. | S |
| Activity 10: Compile regional lessons learned in key sectors and develop regional report and organize 3 rd lessons learned | 32 months then start | 80% | 100% | The last lessons learned workshop (regional closing workshop) was held in Montevideo (November 21th - 22th, 2017). | S |
| Output 9: Final regional lessons learned report developed and disseminated | 36 months then start |  |  | Report of the regional closing workshop and lessons learned from the project. |  |
| Activity 11: Develop and disseminate a final report on lessons learned report and organise last lessons learned workshop | 36 months then start | 80% | 100% | The last lessons learned workshop was held in Montevideo (November 21th - 22th, 2017). The final regional report was developed based on the national reports and regional activities. The national focal points of the project reviewed and approved it. Base on the final regional report the BCCC-SCRC made a brochure with the project results. Link: http://ccbasilea-crestocolmo.org.uy/resultado/folleto-con-resumen-de-resultados-de-8-paises/ | S |
| Output 10: Monitoring and evaluation plan fully implemented assess rate of project’s success | During all the project | 60% | 80% | At the Project MID-TERM workshop, held in Montevideo, Uruguay in October 18th - 20th, 2016, the involved countries (Argentina, Ecuador, Peru and Uruguay) have reviewed the work plan and the budget. The countries redefined the regional consultancies for the Project. The steering committee report is attached. The technical revision is ongoing, and the financial audit is ongoing. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | Efforts have been put to complete all the activities successfuly |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Data collection risk, in terms of non-validated reports or other data that could be incorrect or misstated. | A focus of this project will be the development of new partners and new data sources beyond the project itself, moving toward a scenario with multiple data sources, some of which will be sources that can be used to validate other claims of progress or results. Example: the partnership with National Bureau of Statistics in Nigeria. |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| Partners, having made implementation commitments and set goals, back away from or abandon their goals as deadlines approach. | Broadly speaking, the project serves to support the partners and help them maintain progress on reaching their goals by providing a beneficial non-partisan political exposure, which partners will gain through their participation. The project will closely track partners’ implementation and will leverage in a diplomatic fashion on its soft power to ensure that they deliver on their commitments. Specific webinars and one-on-one sessions will be organized with those partners which achieve commitments to share their success stories and best practices. |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| Drafted and proposed legislation is not passed into law | Project activities tap the right expertise through GLOBE’s extensive partnerships to inform and justify needed policy changes. Chapter and/or executive‐level engagement activities create the necessary political will, momentum, and leadership for change. Legislation is the ideal to which the project will aspire, but where immediately feasible, regulatory responses may be sought in the interim. The the project-proposed legislation changes will be explained comprehensively and put in an international context in order to increase cross-party ownership and support. |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| ESERN [add cells as appropriate to capture all Medium and High Risks] |  |  |  |
| Overall Risk Rating Project Manager |  |  |  |
| Overall Risk Rating Task Manager |  |  |  |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
|  |  | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR |  | X |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  | X |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  | X |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | Low risks at this stage in the project |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Uruguay and Peru have completed Level 1 inventories and will focus on Level 2.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.