Annexure 1

Project Logframe with updated status FY25

Project: “Promoting eco-friendly crop protection solutions for Persistent Organic Pollutant (POP) and Highly Hazardous Pesticide (HHP) Reduction in Asia” (ID 210183)

| Project Strategy | KPIs/Indicators | Baseline | Target level | Progress in FY25 |
| --- | --- | --- | --- | --- |
| Component 1 – Government regulatory capacity |  |  |  |  |
| Outcome 1.1: Enabling environment for introduction of crop protection solutions to reduce POPs & HHPs |  |  |  |  |
| Output 1.1.1: Legislative and Policy framework covering clear definitions for biopesticides, their registration modalities, import/export rules harmonized among India and the Philippines Activity 1.1.1.1: Carry out analysis of the current regulation on pesticide, with specific focus on registration modality Activity 1.1.1.2: Prepare a guidance document to streamline the existing registration modality for biopesticides to facilitate cooperation among the two participating countries among the matter Activity 1.1.1.3 Carry out analysis of the current rules for the export / import of bio-pesticides and identify the most suitable Harmonized System (HS) codes for bio-pesticides. Activity 1.1.1.4 Hold a consultative workshop with relevant stakeholders (decision makers, technical officers, scientific community, academia, etc.) on policies and procedures on bio-pesticides. Activity 1.1.1.5 Develop fair market policies for bio-pesticides | • Assessment report on pesticide registration for each country • Guidance document for biopesticide registration in the 2 countries • Analysis report on import / export rules and HS codes in the 2 countries • Number of people attending the consultative workshop | A registration regulation for pesticides with detailed procedures in place in the 2 countries, however, the registration procedure in India is too cumbersome for biopesticides and discourages the registration of biopesticides at national level. In the Philippines, under FPA there is no distinction between biopesticides and conventional pesticides, therefore some provisions may not be suitable for biopesticides Currently, no guidance document for harmonised registration of biopesticides available in the 2 countries, which may hinder commercial exchange among them | • Initial consultation carried out and consultation plan and methodology prepared. • One consultative workshop carried out at the end of the second year. • Fair-price packages for bio-pesticides and IPM | Activities 1.1.1.1 – 1.1.1.2: - Analysed the existing regulation mechanism. India statutory regulation is in place. Central Insecticides Board (CIB) is the nodal body for registration of bio-pesticides in the country. Prepared a combined report of India and Philippines. Activity 1.1.1.3: - Identification of HSC codes as per the international nomenclature and implementation by the Government. India is having a well-defined HS mechanism. HIL will coordinate with the Philippines counterpart for implementation and HSN Synchronization and also synchronization of Export/Import rules Activity 1.1.1.5: - Fair market policy for biopesticides in place in India. |
| Component 2 – Finance and Investment |  |  |  |  |
| Outcome 2.1: Enhancing finance and investment in development, production and application of biopesticides |  |  |  |  |
| Output 2.1.1: Technology transfer and upscaling of biopesticide production Activity: 2.1.1.1 Select viable techno-commercial technology providers in India on neem based, Btk, and Trichoderma biopesticides Activity: 2.1.1.2 Draft and sign a Memorandum of Understanding (MoU) for technology transfer from technology providers to HIL Activity: 2.1.1.3 Generate data for the registration of bio-pesticides for use in the agriculture sector in India Activity: 2.1.2.1 Assess and establish communication strategy on cost effectiveness associated with the use of bio-pesticides on selected crops Activity: 2.1.2.2 Provide support to farmers to access existing financing mechanisms Activity: 2.1.2.3 Develop insurance schemes to protect participating farmers from unexpected events in the transition phase and beyond | Report on the identification of technologies for biopesticide manufacturing MOU signed with technology providers Registration dossiers | Neem: HIL is in the process of setting up production of 5 Neem based formulation products for public health segment under UNIDO’s DDT alternative project. Neem formulations are under process of registration. Btk: One of the elite institutions of Indian Council of Agricultural Research has developed the technology using local strain Trichoderma: Technology partner has been identified | - Technology provider identified - MOU with technology provider preferably along with the dossier for registration signed - India guidance document in place. - Number of farmers informed on the cost of bio-pesticides and IPM approaches in comparison to conventional practices - Data are available to file application for registration of biopesticides for agriculture use within 18 months from project start - Assessment report to be developed | Activity 2.1.1.1: - - Activity involved is identification of technology provider/ partner & formulation, Lab-scale Technology transfer of biopesticides such as Btk, Trichoderma and neem based biopesticides for commercialization under FARM Project. - Technology partner identified for Btk formulation, lab scale technology also transferred. - Technology partners for other formulations are being finalized. Activity 2.1.1.2: - HIL has signed MoU with the ICAR-NBAIR for transfer of Lab-scale technology of Btk based biopesticides. Activity: 2.1.2.2 A report will be prepared to access and establish communication strategy on cost effectiveness associated with the use of biopesticides with IPM on selected crops Activities: 2.1.2.2-2.1.2.3 A compendium on existing financial mechanisms for farmers prepared. This shall be used to train farmers in the ToT organized by HIL. |
| Output 2.1.4: Scaling up of biopesticides manufacturing and phasing out of POPs and HHPs in India Activity: 2.1.4.1 Establish the industrial infrastructures to scale up the manufacturing of Btk (up to 250 t/y) with associated reduction of POPs and HHP production Activity: 2.1.4.2 Establish the industrial infrastructures to scale up the manufacturing of Neem (from 300 kL/y to 600 k/y) with associated reduction of POPs and HHP production Activity: 2.1.4.3 Establish the industrial infrastructures to establish the manufacturing of Trichoderma (up to 200t/y) with associated reduction of POPs and HHP production | Large scale production of Bt-based pesticides established Quantity of registered biopesticides manufactured and placed on the market Quantity of POPs and HHP phased out and avoided | Lack of domestic manufacturing capacity of bio-pesticides formulations | - Total POPs avoided during project life: DDT: 1200t Dicofol: 200t Total HHP avoided during project life: - 11950t Total manufacturing during project lifetime: Btk: 700t Neem: 750t Tricoderma: 550 t |  |
| Component 3 – Component 3: Capacity and knowledge dissemination |  |  |  |  |
| Outcome 3.1: Capacity building and awareness raising in the formulation, production and application of biopesticides, safe chemical alternatives and other biocontrol agents carried out |  |  |  |  |
| Output 3.1.1.1 Conduct the programme on “Trainers of trainees (TOT)” and awareness raising for farmers and agriculture workers Activity 3.1.1.2 Conduct training for formulators, manufacturers and relevant stakeholders (decision makers) on the registration of bio-pesticides as well as laboratories on accreditation procedures Activity 3.1.1.4 Conduct training on the environmental code of practices for relevant stakeholders in the bio- pesticide supply chain | - Number of trainers trained on IPM and biopesticides disaggregated by gender Number of people trained in the private and public sectors, disaggregated by gender Number of accredited laboratories | No structured training has been conducted on biopesticides in India | Capacity awareness program conducted at different locations Number of people trained in the private and public sectors, disaggregated by gender Number of accredited laboratories India will prepare the 5 ECOPs documents | Activities: 3.1.1.1 – 3.1.1.4 - 60 “Trainers of Trainers" (ToT) programs and awareness-raising activities were carried out in the year-1 of execution. Similar programs are planned throughout the year. |
| Activity 3.1.2.1 Design of the digital hub Activity 3.1.2.2 Develop and enter project related content in the digital hub |  |  | All project relevant data entered in the digital hub | Activities: 3.1.2.1 – 3.1.2.2 A digital hub has been made as a hyperlink to the existing website of HIL. this is currently under testing phase. Once the hub is up, all project relevant data shall be entered. |
| Component 4: Monitoring and evaluation |  |  |  |  |
| Outcome 4.1: Project Monitoring and Evaluation based on lesson learnt ensured |  |  |  |  |
| Output 4.1.1. Project Inception and Monitoring carried out Activity 4.1.1.1. Hold the Inception workshop and preparation of the inception report Activity 4.1.1.2. Prepare and approve Periodic Project reports (PIR, AWP, APR) and risk monitoring | Number of workshops held; number of participants disaggregated by gender Project monitoring and planning documentations. |  | - Project implementation monitored and results assessed against the set of indicators - Periodic Project reports submitted | Activity 4.1.1.1 Inception launch of the Regional FARM Child Project in India & the Philippines was carried out on 24th July 2025 at New Delhi, India. Activity 4.1.1.2 All the relevant reports (PIR, AWP, APR) have been prepared and submitted |