Work Plan-2025 (Year 2)

Project: “Promoting eco-friendly crop protection solutions for Persistent Organic Pollutant (POP) and Highly Hazardous Pesticide (HHP) Reduction in Asia”

The proposed work plan of FARM Project for 2025 is summarized below:

| Activity | Outcome | Stakeholder | Timeline | Proposed Budget ($) |
| --- | --- | --- | --- | --- |
| Component 1: Government regulatory capacity |  |  |  |  |
| Outcomes 1.1: Enabling environment for introduction of crop protection solutions to reduce POPs & HHPs |  |  |  |  |
| Output 1.1.1: Legislative and Policy framework covering clear definitions for biopesticides, their registration modalities, import/export rules harmonized among India and the Philippines. |  |  |  |  |
| Activity 1.1.1.1: Carry out analysis of the current regulation on pesticide, with specific focus on registration modality | A registration regulation for pesticides with detailed procedures in place in the 2 countries. The registration procedure in India is too cumbersome for biopesticides, however, the Government of India is currently promoting the registration of biopesticides at national level. A meeting with relevant stakeholders viz. Central Insecticides Board and Ministry of Agriculture, Government of India shall be organized to review & gap analysis of the registration procedure including prioritizing the registration mechanism in case of biopesticides. | Central Insecticides Board, Ministry of Agriculture DCPC, DGFT | Jun-25 Oct-25 |  |
| Activity 1.1.1.2: Prepare a guidance document to streamline the existing registration modality for biopesticides to facilitate corporation among the two participating counties among the matter: | Indian guidance document in place. HIL will Coordinate with the Philippines counterpart for the compiling the policy guidelines of both the countries. The India Document will be compiled with the inputs provided by the Philippines. | HIL DOST-PCCAARD | August-2025 |  |
| Activity 1.1.1.3: Carry out analysis of the current rules for the export/ import of biopesticides and identify the most suitable Harmonized System Codes (HSC) for biopesticides: | Identification of HSC codes as per the international nomenclature and implementation by the Government. India is having a well-defined HS mechanism. HIL will coordinate with the Philippines counterpart for implementation and HSN Synchronization. | HIL DOST-PCCARD | August-2025 |  |
| Activity 1.1.1.4: Hold a consultative workshop with relevant stakeholders (decision makers, technical officers, scientific community, academia, etc.) on policies and procedures on biopesticides | A stakeholder meeting was conducted in June- 2025 with six stakeholders (MoU partners) in presence of UNIDO, to create the action plan for Year 2 for the activities to be carried out along with the stakeholders. Consultative workshop shall be carried out by HIL with the participations from Government Ministry (Ministry of Agriculture & Farmers Welfare, Ministry of Chemicals & Fertilizers), Regulatory Body (Central Insecticides Board), Academic representatives, Scientific officers, etc. to identify the gap in the biopesticide regulation Propagation of use of bio-pesticides and other safe alternatives to HHPs & POPs for gradual reduction of HHPs and phase out of POPs. Similar stakeholder meetings shall be organized in Q3/Q4 2025. | NHRDF, RLBAU, CSAUT, Sova Foundation Trust, YSPUHF, CCRI | August-2025 November-2025 | 5,000 |
| Component 2: Finance and investment |  |  |  |  |
| Outcome 2.1: Enhancing finance and investment in development, production and application of biopesticides |  |  |  |  |
| Output 2.1.1: Technology Transfer and upscaling of biopesticides production |  |  |  |  |
| Activity 2.1.1.1: Select viable techno-commercial technology providers in India on neem based, Btk, and Trichoderma biopesticides: | Activity involved is identification of technology provider/ partner & formulation, Lab-scale Technology transfer of biopesticides such as Btk, Trichoderma and neem based biopesticides for commercialization under FARM Project. | ICAR and other Central Agricultural Universities, CIB, etc | July/August-2025 | 10,000 |
| Activity 2.1.1.2: Draft and sign a Memorandum of Understanding (MoU) for technology transfer from technology providers to HIL | HIL has signed MoU with the ICAR-NBAIR for transfer of Lab-scale technology of Btk based biopesticides. MoU with the technology partner for other products like Trichoderma & Neem will be signed in July-2025 | ICAR and other Central Agricultural Universities | July-2025 | 90,000 |
| Output: 2.1.2 Financing mechanisms established including loans, marketing infrastructure and insurance schemes, quality enhancement application and fair price initiatives to facilitate the shifting from conventional pesticides to biopesticides. |  |  |  |  |
| Activity 2.1.2.1: Assess and establish communication strategy on cost effectiveness associated with the use of biopesticides with IPM on selected crops: | A report will be prepared to access and establish communication strategy on cost effectiveness associated with the use of biopesticides with IPM on selected crops | Ministry of Agriculture, Ministry of Chemical & Fertilizer | July/August- 2025 |  |
| Activity 2.1.2.2: Provide support to farmers to access existing financing mechanisms: Activity 2.1.2.3: Develop insurance schemes to protect participating farmers from unexpected events in the transition phase and beyond | Module is in place. Suitable financing institutions will be identified to educate the farmers & MoU shall be signed with these institutions for collaboration under FARM Project. | NABARD, SIDBI, Ministry of Agriculture, Ministry, Private Banks, National Banks, etc | Sep-2025 | 5,000 |
| 2.1.4 Scaling up of manufacturing facility and phasing out of POP’s |  |  |  |  |
| Output 2.1.4: Scaling up of bio-pesticides manufacturing and phasing out of POPs | Establish the industrial infrastructures to scale up the manufacturing of Btk, Trichoderma and neem based biopesticides with associated reduction of POPs and HHPs production | HIL & other EPC/ LSTK agencies | Oct 2025 to Dec -2026 | 641,010 |
| Component 3: Capacity and knowledge dissemination |  |  |  |  |
| Outcome 3.1: Capacity building and awareness raising in the formulation, production and application of biopesticides with Integrated Pest Management practices |  |  |  |  |
| Output 3.1.1: Relevant stakeholders in the agricultural sector (decision makers, manufacturers in public and private sector, farmers including women and youth, and others trained and awareness raised on greener and eco-friendly alternatives |  |  |  |  |
| Activity 3.1.1.1 Conduct the programme on “Trainers of trainees (TOT)” and awareness raising for farmers and agriculture workers including women, youth and indigenous | "Trainers of Trainers" (ToT) programs and awareness-raising activities will be carried out throughout the year. These programs are targeted to cover 1 million farmers in the year 2025. Technology exchange workshops on manufacturing biopesticides will also be held regionally. | NHRDF, RLBAU, CSAUT, Sova Foundation Trust, YSPUHF, CCRI | 2025 | 46,350 |
| Activity 3.1.1.4 Conduct training on the environmental code of practices for relevant stakeholders in the bio- pesticide supply chain | India will develop ECOPs by Q3 2025, which will be used to train stakeholders in both countries. | Ministry of Environment, Forests & Climate Change, Ministry of Agriculture, and Family Welfare, Ministry of Chemicals & Fertilizers | July-2025 |  |
| Other Project Management Activities | PMU Related activities, Miscellaneous expenditure. |  |  | 85,950 |
| Proposed budget for year-2 |  |  |  | $883,310 |