UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 5351 | Umoja no.: |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Strengthening the Network of New Protected Areas in Madagascar |  |  |
| Duration months | Planned |  | 60 months |  |  |
|  | Extension(s) |  | N/A |  | N/A |
| Division(s) Implementing the project |  |  | PROJECT MANAGEMENT UNIT within the Directorate of Renewable Natural Resources and Ecosystems Management |  |  |
| Name of co-implementing Agency |  |  | N/A |  |  |
| Executing Agency(ies) |  |  | Ministry of the Environment and Sustainable Development |  |  |
| Names of Other Project Partners |  |  | Durrell Wildlife Conservation Trust |  |  |
|  |  |  | The Peregrine Fund |  |  |
|  |  |  | Missouri Botanical Garden |  |  |
| Project Type |  |  | Full-size project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Africa |  |  |
| Names of Beneficiary Countries |  |  | Madagascar |  |  |
| Programme of Work |  |  | 3 - Ecosystem management 4 - Environmental Governance |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | Objective 1. Vulnerable populations in the intervention areas gain access to income and employment opportunities, improve resilience and contribute to inclusive and equitable growth for sustainable development |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Target 13, 14, 15. |
| GEF financing amount |  |  | $ 3,905,265 |  |  |
| Co-financing amount |  |  | $ 45,407,409 |  |  |
| Date of CEO Endorsement |  |  | August 10, 2017 |  |  |
| Start of Implementation |  |  | September 07, 2017 |  |  |
| Date of first disbursement |  |  | January 05, 2018 |  |  |
| Total disbursement as of 30 June |  |  | $ 330,260 |  |  |
| Total expenditure as of 30 June |  |  | $ 330,260 |  |  |
| Expected Mid-Term Date |  |  | June 2020 |  |  |
| Completion Date |  | Planned | December 2019 |  |  |
|  |  | Revised | N/A |  |  |
| Expected Terminal Evaluation Date |  |  | September 2022 |  |  |
| Expected Financial Closure Date |  |  | March 2023 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Healthy and productive ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels. Indicators i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems. (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services. |
| --- | --- |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |

| Planned linkages with UNDAF | The Project contributes to the objective related to Effect 1 of UNDAF Madagascar (2015-2019) “Vulnerable populations in the intervention areas have access to income and employment opportunities, improve their resilience capacities and contribute to inclusive and equitable growth for sustainable development». The strategic objective is “to reduce the extreme poverty rate from 52.7% (2012) to 40% by 2019 |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project through the planned activities such as forest enrichment and restoration, Ardeola idae habitat restoration, conservation of key biodiversity endemic species, will contribute to SDG Goal 15: Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss”. The project contributes to reach the following targets: - 15.1. By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements - 15.5. Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species .. |
| --- | --- |

| Implementation Status | FY 2019 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2019 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS |  |  |  |  |
| The project is making progress toward meeting project result, however, the delivery is not at the speed expected |  |  |  |  |  |

| Implementation Progress Rating | FY 2019 | FY 20 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S |  |  |  |  |
| The managers of the New Protected Areas involved in the project as well as other stakeholders affected by the project became familiar with the project following the project launch activities and Steering Committee meetings. The discussions that took place during these events as well as the elaborated work plans converge towards the objectives of the project Furthermore, the forest administration's control activities in collaboration with the local communities and the gendarmeries helped to control and reduce illegal logging, overexploitation of mangroves and clearing for the conversion of forest ecosystems. in agricultural parcels In addition, the reforestation projects carried out by the project contributed to the restoration of ecosystems in protected areas and the maintenance of wildlife habitat endemic to Madagascar. Finally, a lot of awareness-raising actions have been carried out. This made it possible to inform stakeholders about the importance of biodiversity conservation and to mobilize more and more stakeholders in the rational management of natural resources. The project has contributed to several World and International Day celebrations. Through these different events, we have been able to improve the visibility of the project at local, national and international level. In addition, the celebration of the International Biodiversity Day 2018 has raised awareness of the importance and value of biodiversity. The actions undertaken in the context of the implementation of the Convention since its ratification by Madagascar were thus highlighted, with a view to informing the public and those concerned about the efforts made and the various advantages that have been achieved. could draw. In the same vein, communication sessions on the National Biodiversity Strategy and Action Plan were held to inform and remind citizens and stakeholders of their duties in the context of implementation of the Convention Also, the participation of different authorities from different departments in these events demonstrates the commitment of the government in achieving the project objective and the realization of biodiversity conservation activities. In addition, it should be emphasized that mainstreaming of the gender approach has been maintained in the different activities that the project has carried out. |  |  |  |  |  |

| Risk Rating | FY 2019 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M |  |  |  |  |
| There are no major risks to the project and the mitigation strategies seem to be appropriate, while closely monitored. |  |  |  |  |  |

| Stakeholder engagement | The capacity of all stakeholders has been strengthened, including the PMU, managers of protected areas and mangrove sites, local communities, steering and monitoring committees. These actors were able to benefit from computer equipment, training in project management and protected area. Stakeholder commitments were respected and coordination of actions was visible during the implementation of project activities. |
| --- | --- |

| Gender mainstreaming | A study on gender mainstreaming was launched as part of the project strengthening the network of new protected areas in Madagascar (S2NPA). In the preliminary report, gender analysis was highlighted in the effective management of protected areas, in mangrove sites, in knowledge management. Recommendations and a draft action plan for the project have been proposed. This action plan aims to contribute to the promotion of positive discrimination and eliminate the factors blocking equity. It is about identifying gender policies in the environmental field and particularly in the S2NPA project, the different implementation strategies. The action plan consists of the mainstreaming of the "gender dimension" which is the process of assessing the implications for women and men of all planned actions in all areas and at all levels. This strategy aims to ensure that the concerns and experiences of women and men are integral to the design, implementation, monitoring and evaluation of policies and programs. |
| --- | --- |

| Knowledge activities and products | Awareness campaigns on the conservation of mangroves and other ecosystems were conducted in the project intervention sites. Communication materials were produced during the celebration of World Days for Biodiversity and Mangroves. |
| --- | --- |

| Stories to be shared |  |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Madagascar’s strengthened network of PAs provides enhanced protection and better representation of key ecosystems, and deliver economic and environmental benefit to local communities | 1. Representation of key ecosystems in the permanent Protected Area Network (% of total area covered by PAs) |  Rainforest - 51.0%  Western Dry Forest - 24.4  South Western Dry Spiny Forest Thicket - 39.5%  Wetlands - 25.9%  Mangroves - 35.2%  Western Sub-Humid Forest- 9.3%  Tapia Forest - 21.1%  Littoral Forest - 38.0%  Western Humid Forest - 52.3%  South Western Coastal Bushland - 0.6% | MT targets to be established at project inception | EOP Target to be established at project inception: | Currently, 10 new protected areas have been created in Madagascar | S |
|  | 2.Level of protection of the New PAs: a) Total annual number of patrols b) Total annual number of discovered violations | a) To be established at project inception = 36annual patrols | a) MT target to be established at project inception = 54 annual patrols | a) EOP Target to be established at project inception = 72 annual patrols | 64 control and patrol missions were carried out at the 9 sites | S |
|  | 3. Number (%) of local people benefiting from new PAs via CBNRM, alternative sources of income and ecosystem restoration | 0 | 50% of Persons Affected by the Project (PAPs) | 100% of PAPs | We do not yet have exact figures on this indicator, but income-generating activities have been identified as beekeeping, ecotourism and implementation will be carried out | MU |
| Outcome 1.1: Strengthened policy, governance, and financing frameworks for PA management, including for conservation of biodiversity and mangrove ecosystems | 1. Capacity of MEEF, SAPM Commission, and Inter- ministerial Committee to manage and develop PA Network (measured using the UNDP Capacity Scorecard) | Capacity scoring to be carried out at inception stage | Increase of 10% in each agency’s capacity score | Increase of 35% in each agency’s capacity score | i. Capacity for engagement:1 ii. Capacity to generate, access and use information and knowledge: 1 iii. Capacity for strategy, policy and legislationdevelopment:1 iv. Capacity for management and implementation: 1 v. Capacity to monitor and evaluate: 1 | MU |
|  | 2.Number of government decrees enacting the permanence of the target PAs | 0 | 3 | 6 | The 6 decrees of creation are all promulgated for the 6 NAP of the project | S |
|  | 3. National conservation policy documents approved and implemented by government: a) Monitoring system for PA biodiversity and management effectiveness b) National mangroves conservation plan c) PA funding strategy | a) None b) None c) None | a) Approved b) Approved c) Approved | a) Implemented 90 b) Implemented c) Implemented | a) IMPLEMENTED b) not initiated c) not initiated | S |
| Outcome 2.1: 6 new PAs and 3 critical mangrove sites within existing PAs are managed in a participatory manner and generating BD conservation and livelihoods benefits | 1. METT Scores for 9 new Protected Areas (6 NPAs and 3 mangrove sites) | Bemanevika (38)  LacAlaotra (33) Makirovana - Tsihomanaomby (50)  Ranobe/PK 32 (26)  Pointe à Larrée (44) Ambaro Bay (20) Tsimembo - Manambolomaty (46) BoanamaroBayis (19)  Morondava (19) | 10% improvement in METT score at each site | 30% improvement in METT score at each site | Bemanevika (41)  LacAlaotra (34) Makirovana - Tsihomanaomby (62)  Ranobe/PK 32 (28)  Pointe à Larrée (69) Ambaro Bay (25) Tsimembo - Manambolomaty(65) Boanamaro Bayis (22)  Morondava (22) | S |
|  | 2. # of Integrated Management Plans (IMPs) and area (ha) under approved and implemented IMPs | 0 / 0 | 5 IMPs / 100 000 ha | 9 IMPs / 354 859 ha | 6 IMPs/317450 Ha | S |
|  | 3. Number of sustainable small business and CBNRM projects developed by local communities in cooperation with the Pas | 0 | 20 | 40 | Bemanevika and Tsimembo: (2) Seed support Tsimembo: (1) vaccination of poultry (1) dynamic agroforestry Point to Larré: (1) Poultry (1) Sea fishing (1) cloves | MU |
| Outcome 3.1: Increased public awareness and policy integration of TEK and biodiversity conservation | 1. Number of official documents and local community projects that use TEK | 0 | 3 | 10 | 0. Currently, we are at the beginning of the project. | U |
|  | 2. Number of project lessons on PA management and CBNRM used by other projects and PAs | 0 | 2 | 6 | 0. Currently, we are still at the beginning of the project. The website for the broadcast is being created | U |
|  | 3. Percentage of population in the project sites that understands PA value and approves their activities | 0 | 50% | 80% | 5% | U |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| N/A | MS | The project is making progress toward meeting project result, however, the delivery is not at the speed expected |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets |  |  |
| on stakeholder engagement |  |  |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results |  |  |
| Others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: National PA agencies (DAPT, DREEF, CIREEF, CEEF, and CSAPM) have increased capacity to develop and manage the PA system | 2022 |  | 39.5 | National protected area management officers received capacity building in terms of management tool, texts, and received material support | S |
| Activity 1.1.1.1 Develop and implement training programs (needs assessment and training plan development) | 2202 | 0 | 25 | The development of training programs is underway and is based on the needs of the administration in charge of protected areas, protected area managers, local communities and protected area system commissions. The themes identified in the training program are based on the standard of competence of protected area managers and the needs of stakeholders. The S2NPA AP-Mangrove Project Team received training on financial and technical project management tools, GEF / UN-Environment procedures in the implementation of GEF projects. The project also supported the training of forty-six (46) technicians from the Directorate of Protected Areas on: - the treatment, analysis and database management of Protected Areas (2 beneficiaries) - Geographic Information System GIS (1 beneficiaries) - Communication and website management tools WEB (12 beneficiaries) - Benefits Sharing and Research in Protected Areas and Mangrove Sites - Tools for creation and management of protected areas - Management and coordination, - Monitoring and evaluation of protected area management - Statutory texts: COAP (Protected Areas), POLFOR (Forestry), SPANB (Biodiversity), …. ABS (access and benefit sharing considering the Traditional for Ecological knowledge | S |
| Activity 1.1.1.2 Strengthen the competence of the Madagascar PA System Commission (CSAPM) | 2022 |  | 25 | Exchange and information sharing between the Ministry in charge of Mines (BCMM) and the Ministries in charge of Protected Areas (DGEF) on the superposition of mining tiles, the shapefile of protected areas and national forest domains. Meetings between the Ministry of Fisheries and the Ministry of the Environment on the management and governance of mangroves. The salient points discussed are: - The diagnosis the inventory of mangroves in Madagascar - The development of national strategy of Management and Governance of mangroves - Strengthening the synergy of actions day | S |
| Activity 1.1.1.3 Develop project management tools | 2019 |  | 62 | The Procedural Manual was developed jointly with the COKETES project (100%) The project management tools are being finalized. Data and information were collected for the development of the three tools: - Strategy and communication plan (50%) - Monitoring and evaluation plan (50%) - Gender study (50%) |  |
| Activite 1.1.1.4 Organize Project inception workshop and Project inception workshop and project steering committee meetings | 2022 |  | 80 | The launching workshops were carried out at national and regional level with the different project stakeholders, in which the general context of the project was presented (project history, objective, expected results sites concerned, project management) Two workshops of the Steering Committee were organized with the member institutions of the Steering Committee. This Committee is responsible for providing political, strategic and technical guidance for the implementation of the project. During these workshops, the general direction for the conduct of the project and the annual work plan and budget (PTAB) were discussed and approved. At the end of the second meeting of the COPIL, the Budget and Trimestral Activity plan(PTAB) was adopted subject to the following recommendations: - Require the implementation plan for all Income Generating Activity - Ensure the application of the sectors concerned in the implementation of the Income Generating Activity - Consider socio-political parameters such as election periods in the planning of activities - Harmonize interventions with other funding and co-financing - Budgeting the implementation of the IMP - Adjust indicators according to related objectives - Highlight the tools developed and good practices from other projects like MRPA - Include Technical Committee for Environmental Assessment ad relevant sector (tourism, mine,) as capacity building beneficiaries - Provide the supervision of the VOI | S |
| Activity 1.1.1.5 Strengthen the Capacities of AP / PMU National Agencies | 2022 |  | 25 | Computer equipment, supplies and office supplies were acquired by the PMU and the Protected Areas Directorate | S |
| Activity 1.1.1.6 Activities monitoring | 2022 |  | 20 | The PMU carried out technical and financial monitoring in the regions of DIANA (Ambaro Bay), SOFIA (Bemanevika) and Atsimo Andrefana (Ranobe PK 32). Technical and financial monitoring consists of collecting and consolidating technical data on the progress of activities and financial data in order to provide managers / DREDD with information on the use of funds allocated and the objectives achieved. During the mission the following recommendations were proposed: - Increase the area of ​​forests to be restored and mangrove to be reforested - Finalize the update of the IMP for each site - To standardize the budget allocated to each site, the PMU will propose expenditure execution standards for each type of activity and the cost of activities should not exceed the forecasts - Update Mapping and Management Transfer Databases - Strengthen the visibility of the project, for example by displaying the maps of the TGRN with logo in the sites - Strengthen development activities to reduce exploitation of natural resources - During the field visit to Ambaro Bay, VOI members proposed reinforcements of patrol officers (polisinala) with motorcycles and uniforms | S |
| Output 1.1.2: Management instruments for PAs and mangroves are developed, discussed with stakeholders and submitted to the Government for approval | 2022 |  | 22.5 |  | S |
| Activity 1.1.2.1 Standardize / update PA management tools | 2022 |  | 25 | The following management tools are standardized and should be used by all protected area managers: - METT for the evaluation of the management effectiveness of protected areas - SMART for patrols, monitoring and ecological monitoring in protected areas | S |
| Activity 1.1.2.2 Redynamize and/or create SAPM sub-committees | 2022 |  | 20 | Redynamization workshops were organized: SAPM Commission, COS, Interministerial Committees (Mining, Land, Fisheries, Forestry) | S |
| Output 1.1.3: Monitoring and evaluation tools to measure the management effectiveness of PAs are identified and introduced to PA agencies | 2022 |  | 17.5 | The METT tool is adopted to evaluate the protected area S management effectiveness index |  |
| Activity 1.1.3.1 Develop monitoring and evaluation tools for each pilot site | 2022 |  | 25 | - Technical and financial monitoring sheets have been developed by the PMU team to facilitate technical and financial monitoring - The monitoring and evaluation plan is being validated - The self-assessment of the management effectiveness of protected areas is underway | S |
| Activity 1.1.3.2 Carry out Training and Information Sessions for relevant stakeholders (central and deconcentrated MEDD, COS, COE) on evaluation monitoring tools | 2022 |  | 10 | The METT tool was shared with all stakeholders and stakeholders. The team training of the Directorate of Protected Areas is planned in the second half (S2) but the regional training sessions could not be carried out because of the delay in funding. | S |
| Output 1.1.4: National Action Plan for mangrove conservation is formulated | 2022 |  | 3.3 | The national action plan for mangrove conservation and management is not yet finalized. Negotiations between the Ministry of the Environment and the Ministry of Fisheries are under way for the activation of the release of the draft Interministerial Order setting a transitional manner of management of the mangrove ecosystem at the national territory level. | MS |
| Activity 1.1.4.1. Valuation of mangrove ecosystem assets | 2022 |  | 5 | The study on the state of mangroves is currently underway | MS |
| Activity 1.1.4.2 Develop regional action plans and strategies for the sustainable and rational management of mangroves | 2022 |  | 5 | The development of a regional action plan and national strategy is underway with the diagnosis of the state of mangroves | MS |
| Activity 1.1.4.3 Elaborate the national plan of action for the sustainable and rational management of mangroves | 2022 |  | 0 | This activity will be postponed next year, after the realization of the inventory of mangroves |  |
| Output 1.1.5: Legal and regulatory amendments to ensure permanent protection of mangroves and effective PA management are developed | 2022 |  | 10 | Negotiations between the Ministry of the Environment and the Ministry of Fisheries are under way for the activation of the release of the draft Interministerial Order setting a transitional manner of management of the mangrove ecosystem at the national territory level | MS |
| Activity 1.1.5.1 Hold technical workshops for the harmonization and coherence of intersectoral activities | 2022 |  | 10 | Meetings were held between the technical team of the Ministry of Fisheries and the technical team of the Directorate General of Environments and Forests on mangrove management. Participation in the National workshop on mangroves was planned on September 2019 in South West (Tulear) in the second semester (S2) |  |
| Activity 1.1.5.2. Revising legal and regulatory texts | 2022 |  | 10 | The revision of the regulatory texts will be postponed next year after the development of national mangrove management strategy |  |
| Output 1.1.6: Funding Strategy for new PAs is developed | 2022 |  | 0 | The elaboration of the Protected Areas Sustainability Strategy will be elaborated next year after the development of the business plan of each protected area |  |
| Output 2.1.1: Integrated Management Plans for 9 PAs are developed | 2022 |  | 25 | The 6 protected areas currently have management and management plans and need to be updated |  |
| Activity 2.1.1.1 Develop / update the Integrated Management Plan (IMP) | 2022 |  | 25 | 6 IMPs already exist but need updating Mission Data Collection for Boanamary and Point à Larrée | S |
| Output 2.1.2: PA staff with increased capacity for PA management in collaboration with local communities | 2022 |  | 13.3 | The integration of local communities into PA management has increased with capacity building for VOIs and managers. | S |
| Activity 2.1.2.1 Strengthen the skills of PA managers | 2022 |  | 20 | Capacity building of the local community in natural resource management took place in Bemanevika. Only half of the training courses were completed this year. All VOIs from AP Bemanevika and those from the ring road are beneficiaries of the training | MS |
| Activity 2.1.2.2 Strengthen the capacity of PA managers | 2022 |  | 10 | Managers received capacity enhancements in Lafa forum: database, GIS | MS |
| Activity 2.1.2.3 Integrate the Gender Approach on Natural Resource Management | 2022 |  | 10 | Active contribution of DREDD agents and managers, local communities in the realization of the gender study within the S2NPA / AP mangroves project. Sharing the study and integrating the gender approach into the planning of project activities | MS |
| Output 2.1.3: Local communities in areas adjacent to PAs and mangrove micro-sites have improved ability to participate in CBNRM, development of alternative sources of income and ecosystem restoration |  |  | 15 |  | MS |
| Activity 2.1.3.1 Identify alternative activities | 2020 |  | 25 | four out of nine sites identified their alternative activities Tsimembo Manambolomaty: The implementation of the ecotourism plan will be in 2019) AtsimoAndrefana: the promotion of improved energy wood Bemanevika: Fish farming Point à Larrée: Promotion of the fish conservation unit | MS |
| Activity 2.1.3.2 Train communities on alternative activities | 2022 |  | 5 | Community formation on IGAs is ongoing | MS |
| Output 2.1.4 : Pilot projects on CBNRM, alternative sources of income and ecosystem restoration are developed and under implementation | 2022 |  | 15 | The development of the AGR is in progress because the project is in the start-up phase | MS |
| Activity 2.1.4.1. Identify the people affected by the creation and management of the Protected Area and Mangroves (PAPS) | 2020 |  | 50 | For the six protected areas, the populations affected by the project are already identified, Identification of PAPs in the three mangrove sites will be postponed until 2020 | S |
| Activity 2.1.4.2 Build and rehabilitate conservation infrastructure | 2022 |  | 5 | Invited tender procedure (Makirovana) The construction of a micro-irrigation dam is planned for Bemanevika in year 3 | MS |
| Activity 2.1.4.3 Perform control activities, biodiversity surveillance and ecological surveillance | 2022 |  | 20 | To maintain the state of biodiversity and specific habitats of the Protected Area. Unannounced raids and control actions were carried out within Protected Areas to preserve the integrity of the state of natural resources. This monitoring activity was carried out in collaboration with the local patrol and gendarmerie committees on the basis of information collected in the field. The main elements that have been descended: - Illegal logging and overexploitation of mangrove woods: firewood, timber; - The manufacture and transport of illicit firewood (coal) in PAs - conversion of forest ecosystems to agricultural parcels - clearing 64 missions of control and patrols were carried out | S |
| Activity 2.1.4.4 Create and / or reinvigorate the NRMT (Natural Resource Management Transfer) and CFM (Contracted Forest Management) | 2022 |  | 5 | Based on Secured Local Management (GELOSE) contracts, the Regional Directorates contributed to the evaluation of management transfer contracts around protected areas and in mangrove sites (4 Ranobe PK32 sites, Bemanevika, Point à Larrée, Boanamary). The contracts were examined in the light of numerous criteria that made it possible to gauge their ecological, economic and social impacts. Recommendations came out of these evaluations in order to sustain the management of natural resources. | S |
| Activity 2.1.4.5 Promote restoration activities | 2022 |  | 10 | The restoration of 200ha of mangrove in Morondava is planned in the second half (S2). Planning for this activity is currently underway | MS |
| Activity 2.1.4.6 Put in place the devices for prevention and fight against bush fires | 2022 |  | 10 | Faced with fire propagation issues, PA managers have defined a strategy composed of several activities, among others: public awareness through radio, village film screening, establishment of fire vigilance committee by village, creation and maintenance of firewalls and law enforcement governing firing. The goal was to create 2km of new firewalls and maintain 8.5km of the old 30m wide firewalls. 1950m long and 30m wide new firewalls were created in Sahafandrano and 3.6km of old firebreaks were maintained. Due to the delay in starting the project, we had to prioritize the most sensitive areas for firewalls. | MS |
| Activity 2.1.4.7 Restore and enhance the sacred and cultural sites | 2022 |  | 10 | A sacred site restored in the AP Bemanevika. The stele was renewed by putting concrete fences. The Tsimihety people still hold their traditions. Indeed, many venerated steles are observed, especially near the lakes that are considered sacred in the AP Bemanevika itself. People came there to perform ritualizations. The presence of such cult sites and respected in the site is an asset for the management of AP. Indeed, we must look for ways to harmonize conservation with respect for local cultures. | MS |
| Activity 2.1.4.8 Delimit the Protected Area | 2022 |  | 0 | Postponed to year 3 |  |
| Activity 2.1.4.9 Follow the implementation of the IMP | 2022 |  | 20 | The update of the Management Planning Plan is essential for the renewal of the management delegation. This plan has been defined for a period of five (05) years. Although there has been some progress, currently the main pressures on natural resources still remain. Indeed, it is important to evaluate them, analyze their values ​​and identify the priority actions for each identified threat. Also, this revised Management Planning Plan (PAG) is essential in the context of sustainable management of site resources while taking into account various local socio-economic issues. During the workshop in Antananarivo, MBG was able to deduce that fires and illegal timber cuts still remain the main threats of NAP, after the recrudescence of land grabbing in the NAP as well as biological invasions. In general, the levels of efficiency and feasibility vary from one threat to another. | MS |
| Activity 2.1.4.10. Support the community in the implementation of rural development projects | 2022 |  | 0 | Postponed year 3 |  |
| Activity 2.1.4.11. Activities monitoring | 2022 |  | 20 | The Regional Environmental Departments have carried out missions to monitor activities in the sites | S |
| Activity 2.4.12 Conduct awareness at the site | 2022 |  | 16 |  | MS |
| Output 3.1.1: Traditional Ecological Knowledge (TEK) database is developed and introduced to decision makers and local communities. | 2022 |  | 0 | To be postponed for next year |  |
| Activity 3.1.1.1 Identify the place of traditional and local knowledge on bio-diversity conservation issues | 2022 |  | 0 | Ongoing as part of the project sharing benefits |  |
| Output 3.1.2 : Lessons learned by the project are disseminated by different means at national and international levels | 2022 |  | 6.6 | We are still in the start-up phase | MS |
| Activity 3.1.2.1 Develop ways to disseminate lessons learned | 2020 |  | 0 | To be postponed for next year. The creation of the Project Website is underway |  |
| Activity 3.1.2.2 Participate in the celebration of world and international days | 2022 |  | 20 | Participations: - World Wetlands Day - International Day of Forests - International Day of Biodiversity | S |
| Activity 3.1.2.3 diffuse lessons learned from the project | 2022 |  | 0 | Postponed for next year |  |
| Output 3.1.3: Awareness raising campaign on conservation of mangroves and other ecosystems is developed and implemented | 2022 |  | 16,6 | Awareness campaigns have been conducted by the Regional Directors and site managers. Radio broadcasts on FM radio in Soanierana Ivongo to raise public awareness about biodiversity conservation | MS |
| Activity 3.1.3.1 Organize awareness campaigns | 2022 |  | 20 | Awareness sessions were held during the celebration of World Biodiversity Days | S |
| Activity 3.1.3.2 Develop communication supports | 2022 |  | 10 | S2NPA / APmangrove Project website development is underway | MS |
| Activity 3.1.3.4 Strengthen the Capacities of National AP Agencies in Relation to Communications | 2022 |  | 20 | Capacity building of 46 officers of the Directorate in charge of Protected Areas for communication and database management | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The managers of the New Protected Areas involved in the project as well as other stakeholders affected by the project became familiar with the project following the project launch activities and Steering Committee meetings. The discussions that took place during these events as well as the elaborated work plans converge towards the objectives of the project Furthermore, the forest administration's control activities in collaboration with the local communities and the gendarmeries helped to control and reduce illegal logging, overexploitation of mangroves and clearing for the conversion of forest ecosystems. in agricultural parcels In addition, the reforestation projects carried out by the project contributed to the restoration of ecosystems in protected areas and the maintenance of wildlife habitat endemic to Madagascar. Finally, a lot of awareness-raising actions have been carried out. This made it possible to inform stakeholders about the importance of biodiversity conservation and to mobilize more and more stakeholders in the rational management of natural resources. The project has contributed to several World and International Day celebrations. Through these different events, we have been able to improve the visibility of the project at local, national and international level. In addition, the celebration of the International Biodiversity Day 2018 has raised awareness of the importance and value of biodiversity. The actions undertaken in the context of the implementation of the Convention since its ratification by Madagascar were thus highlighted, with a view to informing the public and those concerned about the efforts made and the various advantages that have been achieved. could draw. In the same vein, communication sessions on the National Biodiversity Strategy and Action Plan were held to inform and remind citizens and stakeholders of their duties in the context of implementation of the Convention |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| N/A | N/A | N/A | N/A |

3.3. Risk Rating

| RISK DESCRIPTION AND LEVEL | MEASURETO BE UNDERTAKEN BY THE PROJECT | MITIGATION MEASURE AT IMPLEMENTATION | RISK RATING |
| --- | --- | --- | --- |
| Migration and high rate of urban unemployment around the target sites: newcomers are identified in different locations, which increase the sites’ loads leading to overexploitation and competition over accessible natural resources. Sometimes, natives and migrants are fighting because the latter do not respect the habits and local customs, especially Dinas (local collective agreements.) For mangroves: the risks are very high because the surrounding cities are the big mangrove wood consumers (charcoal and timber); for the PAs, the risks are low to medium due to the presence of managers and effective law enforcement. | Building project proponents capacity in conflict management Establishing promising IGAs especially for vulnerable populations so that they no longer depend on forests or mangrovesnatural resources Promoting energy wood other than like Acaccia sp and Eucalyptus sp.mangroves (case of Ambaro and Boanamaro) Collaboration between all stakeholders in sites conservation and development, and especially involving the services in the Ministry of Justice and judicial officers. Strong awareness-raisingand accompaniements ofVOIs Integrating the PAs and mangroves in local territorial strategies (SRAT and SAC) | The project is using the NO one Left Behind approach | At CEO: L PM: L TM: L |
| Institutional instability:the frequent changes of officials often discontinue actions thayt have been undertaken and the newly appointed officials are often lost as far as objectives are concerned. | Appointing the Project National Team that depends on the project because the project Team remains despite political change | The project team is established with recruited and secondment staff. The changes of official continue to be a challenge | At CEO: M PM: M TM: M |
| # Other problems linked to Political Instability: Various risks are presented by an often tumultuous and changing political situation in Madagascar. Despite this, the NPAs are granted with their permanent decree of creation through the commitments made by the Senior Governmental Officials (executive, legislative), so the project is insultated to some degree. The present COAP Law was enacted in February 2015. It reinforces particularly the community-based PAs, Category V and VI, thereby allowing direct management of the concerned by the local population.At the level of the decentralized territorial authorities (Region, for eg. Boeny, Menabe), actions for the territorial development plan (SRAT for the regions, SAC for the Communes) are in progress.However, populist speeches of political authorities (e.g. Electoral campaigns in the Alaotra Lake PA) that do not support PA activities do also represent a project risk. | For better project governance and in order to spare it from any institutional change on sudden political uncertainty, composite 4 is included in this project. It is an independent technical body attached to the DAPT. It also ensures the project visibility both nationally and internationally. The governance of natural resources is worth strengthening and supported at all levels. The project has planned various capacity-building activities at the local, central, and regional levels. Implementation of activities: Governmental commitment at very high levels, such as: commitment of the President in terrestrial and marine protected areas creation. | Political instability remains a challenge in the country. However, the conservation is still having a high profile. The awareness raising and strengthening of the legal framework have been at the centre of project intervention | At CEO:M to H PM: M TM: M |
| Sectoral conflicts of interests Each entity has its own interest especially concerning mines and oils which are the crucial challenges for Madagascar’s development. Most of these PAs are full of resources in their sub-soil and as soon as information about discovery is heard, people are illicitly and illegally rushing in these PAs and causeenormous damages on the integrity of these PAs. Recently the discovery of precious stones in the PA of South Anjanaharibe causes clearings and holes everywhere and the massive newcomers crucially disrupt its wildlife. | Strengthening the effectiveness of CPANM and of sectoral subcommittees of Forestry -Land, Forestry-Mining or oil, Forestry-Fishing, Mangrove Commission in resolving the confilts and especially involving governmental VIPs. An activity is dedicated to this in the project (see Component 3) | The country commitment to sustainable development and sectors collaboration together with enforcement of the environment impact assessment Law are contributing to an enabling environment for conservation | At CEO: H PM:M TM: M |
| Lack of objectivity of the eligibility criteria for funding (subjectivity in awarding funds, no transparency, etc.) Currently, two foundations in Madagascar fund the PAs and Biodiversity. But only ten PAs are funded but he eligibility criteria are not clear and not transparent i.e. no call for bids and no good governance at all | Integrating the PANM in the Board of these two foundations, especially the representatives of PAs managers. | The two foundation are active partners in the project execution | At CEO: M to H PM:M TM:M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | There are no major risks to the project and the mitigation strategies seem to be appropriate, while closely monitored. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM :LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: MEDIUM |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: MEDIUM |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM:LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM:LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  | X |  |  |  |  | PM: MEDIUM | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM:LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM:MEDIUM |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM:MEDIUM |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM:LOW | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
|  | Low |  |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.