## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE)
3. IMPLEMENTATION PROGRESS (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
GEF-5 LDCF Indicators
GEF 6&7 LDCF Core Indicators
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Africa
Country(ies): | Burundi
Project Title: | Support for sustainable food production and enhancement of food security and climate resilience in Burundi's highlands
FAO Project Symbol: | GCP/BDI/040/GFF
GEF ID: | 9178
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Multi Focal Area:, Biodiversity, Climate Change Mitigation, Land Degradation, IAP Food Security
Project Executing Partners: | Burundian office of Environment Protection (OBPE) Rural Engineering Department (GR) Burundi Geographic Institute (IGEBU) Institute of Agronomic Sciences of Burundi (ISABU), Bioversity International, General Directorate of Environmental Planning, Agriculture and Livestock, Centre for Multiplication of Vegetable and Fruit Seeds 3 Provincial Office of Environment, Agriculture and Livestock, Burundi Office of Standardization and Quality Control 2 local NGOs : ADISCO, APROCUVI ADRSEPAL for FPIC.
Initial project duration (years): | 5
Project Dates
GEF CEO Endorsement Date: | 2017-04-04
Actual Agency Approval Date | 2017-01-04
Project Implementation Start Date/EOD: | 2017-09-04
First Disbursement Date | 2017-09-29
Planned Project End Date/NTE1: | 2021-09-05
Revised project implementation End date (if approved)2: | 2025-06-30
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2026-06-30
Funding
GEF Grant Amount (USD): | 7396330
Total GEF grant delivery (as of June 30, 2025 (USD): | 7356826.81
Total Co-financing amount (USD)3: |  |  |  | 4505728
Total estimated co-financing materialized as of June 30, 2025: | 45090000
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 2025-04-25
Expected Mid-term Review date5: | N/A
Actual Mid-term review date (if already completed):
Expected Terminal Evaluation Date6: | 2025-08-31
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Satisfactory
Overall implementation progress rating: | Satisfactory
Overall risk rating: | Low
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 8th PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Oscar NIYONZIMA |  | Oscar.Niyonzima@fao.org
Budget Holder (BH) | Pissang Tchangaï Dadémanao |  | Dademanao.PissangTchangai@fao.org
GEF Operational Focal Point (GEF OFP) | Emmanuel NDORIMANA |  | ndorimel@yahoo.fr
Lead Technical Officer (LTO) | Anne Sophie POISOT |  | AnneSophie.Poisot@fao.org
Alternate LTO | Stefano Mondovi |  | Stefano.Mondovi@fao.org
GEF Technical Officer (GTO) | Sandra Corsi |  | Sandra.Corsi@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was established during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
Project Coordinator | Yes | From 2018, Salvator Ndabirorere Salvator.Ndabirorere@fao.org
Project Coordinator | Yes | From 24th, April 2023, Oscar Niyonzima,Oscar.Niyonzima@fao.org |  | Came to replace Ndabirorere Salvator
MEAL Expert | Yes | From 15th, May 2018, Léonard Bacamurwanko,Leonard.Bacamurwanko@fao.org
FFS Expert | Yes | From 3rd, April 2018, Donatien Karumbete,donatien.karumbete@fao.org
Value Chain Expert | Yes | From March, 2018, Jean Paul Nzosaba
Value Chain Expert | Yes | From 19th Jully, 2019, Dieudonné Kameca,Dieudonne.Kameca@fao.org |  | Came to replace Jean Paul Nzosaba

## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 0
0

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Region:
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
Increase adoption of resilient, improved production systems for sustainable food security and nutrition through integrated landscape management and sustainable food value | Outcome 1 Multi-stakeholder and multi-scale platforms operational in supporting policy, institutional and knowledge sharing mechanisms for scaling out of sustainable agriculture systems and integrated natural resources management approaches | IAP TT LD-4 (ii): Type of mechanisms, institutions, legal and regulatory frameworks | Mechanisms i) National and Provincial GSADR existing | Mechanisms i) N-GSADR and P-GSADRs actively supporting INRM scaling out in Mwaro, Gitega and Muramvya (concrete actions) | Mechanisms i) P-GSADR has demonstrated success in scaling out INRM in 3 provinces (intersector policy and actions etc) | 3 workshops to harmonize and scale up INRM approaches organized (1 in each targeted Province) with a participation of 151 stakeholders 2 workshops of GSADR on National Level have been organized. | 75% | Satisfactory (S)
GCP/BDI/040/GFF
|  | ii) Knowledge sharing and planning mechanism on ILM | ii) No KS or coherency across sectors on SLM/INRM scaling out approaches | ii) KS mechanisms set up and being piloted: 1 national, 3 provincial, 4 local | ii) KS mechanisms (1 national linked to WOCAT global, 3 provincial GSADR, 4 local) effectively sharing best practices on INRM and value chains | SLM National Group (with 24 multidisciplinary technical governmental staff) in place and their capacities reinforced. Thanks to the LOA with DGPEAE, the DGPEAE enhances the knowledge sharing mechanism through (i) the design of a consolidated sharing information system on SLM/INRM and (ii) the popularization and dissemination of 3 main strategic policies related in INRM | 68% | Satisfactory (S)
|  | Legal & regulatory frameworks: iii) No ILM framework in place/piloted | Legal & regulatory frameworks: iii) Consultations held, including community, gender and Batwa representation, for developing harmonised guidance for implementing INRM FFS and interlinked value chains | Legal & regulatory frameworks: iii) Harmonised guidance in place for implementing INRM, erosion control, BD, and interlinked value chains | i) 9 reports on Community Action Plan for 9 targeted watersheds developed and under implementation ii) Study report on NFPIC developed and now available. | i) 9 Community Action Plans for 9 targeted watersheds under implementation ii) Study report on NFPIC developed and implemented. | 100% | Satisfactory (S)
|  | (iv) National FFS strategy (extent of operationalization) | iv) National FFS strategy is available but has not yet been operationalized | iv) FFS strategy partly operationalised | iv) FFS strategy fully operationalised | Road map of FFS institutionalisation is still underway according to the new governmental approach related to environmental agricultural and livestock policy namely “Radiation Center” approach (l’ Approche “Centre de Rayonnement”) | 55% | Moderately Satisfactory (MS)
|  | (v) Country Strategic Framework (CSIF) (applied) | v) CSIF in place but does not include INRM/landscape aproaches and not effectively applied | v) Consultations held, including community, gender and Batwa representation, for planning CSIF implementation at provincial (3), communal (3) and watershed (3) levels | v) CSIF applied/ integrated in plans and budgets at provincial (3), communal (3) and watershed (3) levels | A national strategy of watershed management and erosion control adopted by the government has been integrated in the project implementation through the 9 community actions plans (erosion control, agroforestry and forestry, riverbank protection) | 100% | Satisfactory (S)
| Outcome 2: Increased land area and agro-ecosystems under integrated natural resources/ landscape management and supported by FFS and sustainable value chains for increased production and sustainable livelihoods | i) IAP TT LD-3 (ii): Application of INRM practices in the wider landscape | i) 0 catchments | i) 9 catchments with diagnostics completed and community plans developed for INRM including enhanced ABD (at genetic, species and habitat levels) | i) 9 catchments implementing INRM with enhanced BD (at genetic, species and habitat levels) | 1. Biophysical and socio-economic characterisation completed in 9 catchments 2. Land Use Systems characterisation with Collect Earth tool for 3 provinces 3. 9 Watersheds topographic maps developed (by Rural Engineering Department of MINEAGRIE) in addition to communities’ vision maps 4. Varietal diversity analysis of main crops of the project by DATAR tool | 95% | Satisfactory (S)
|  | ii) extent of adoption of SLM/integrated landscape management practices | ii) HH-BAT baseline: shows that many farmers use advised practices but not in a systematic manner so as to improve productivity and ES (manuring 93% crop rotation 83%, agroforestry 79%, agro-sylvo-pastoral integration 75%, intercropping 68%, contour lines 56%.) | (ii) Diverse improved SLM practices adopted in a combined approach and being monitored and documented by FFS and communities in the 9 catchments | ii) Integrated agrosilvopastoral systems with well designed SLM practices effectively combined across 9 catchments and multiple benefits on livelihoods and ES documented and demonstrated ii) 30,000 ha of combined SLM practices in place by the project end plus 50,000 ha scaled up through baseline projects and watershed plans | 1)106 FFS located in 58 Collines (46 652 ha) of 9 catchments adopted agro-sylvo-pastoral best practices such as erosion control on 1007,6 Km, 19.467.226 forestry and agroforestry trees plantation, 873 improved stoves, 11030 improved composts for Soil Fertility Management. 2) Land area covered by forestery and agrorestery: 31724 ha 3) Production and plantaion of 2897.263 bamboo trees to protect 300 km of riverbanks of Ruvubu, Kayokwe and Kaniga river banks. Production of 40.000 avocado seedlings, 3.000 false mango seedlings and 3.000 celery palm seedlings as part of “Green City Initiative” Promotion of small-scale irrigation to increase climate resilient and food production even during the dry season on 1352ha with 2641 HH beneficiaries. 4) 19.467.226 forestry and agroforestry plants produced, so that the project reached a covered area of 31 724ha. | 100% | Satisfactory (S)
|  | iii) % of farmers producing for market (disaggregated by gender) | iii) HH-BAT baseline: 53% produce for markets of which 37% female led HHs | iii) 2,500 (>30% female headed households, 20% orphan headed households) | iii) 8,930 (> 30% female headed households, 20% orphan headed households) | 2529 farmers members of cooperatives with 1773 women and 765 men produce for the market (75%of all the FFS members) | 100% | Satisfactory (S)
|  | iv) % farmers with improved production (disaggregated by gender) | iv) no systematic information on total yields and diversification (baseline collected through FFS) | iv) FFS monitored and demonstrating production and diversity increases compared to normal practice (+25% by 100 FFS) | iv) FFS monitored and demonstrating production and diversity increases compared to normal practice (+25% by 200 FFS) | FFS monitored and demonstrating production and diversity increases compared to normal practice (+25% by 200 FFS) | 100% | Satisfactory (S)
|  | v) metric tons of CO2 eq avoided |  |  | over a duration of 5 years: On-farm (increase in biomass/agri. crops): 28,213t CO2 eq avoided On-farm (increase of tree cover): 97,920t CO2 eq avoided The indirect benefits (over a capitalization phase of 15 years): - On-farm (increase in biomass/agri. crops): 564,266t CO2 eq avoided - On-farm (increase of tree cover): 1,958,407t CO2 eq avoided | On-farm (increase of tree cover during the reporting period): -8 194 054 008 t CO2 eq avoided (using the Ex-Act Carbon Balance tool) | 450% | Highly Satisfactory (HS)
| Outcome 3 | Targeted institutions: IGEBU, OBPE, MINAGRIE, MEEATU, universities (i) Staff in concerned institutions trained and applying tools and systems for monitoring GEBs, SLM/INRM and interlinked value chains and their impacts on food and livelihood security and ecosystem services | i) 0 staff trained and applying tools for monitoring impacts | i) 80 staff trained and applying tools for monitoring multiple impacts | i) 200 staff trained and applying tools for monitoring multiple impacts | 254 Governmental staff of which 62 FFS Facilitators trained – ( 210 men and 44 women) on different SLM monitoring and evaluation tools (LADA-WOCAT, EX-ACT, Collect Earth, DATAR and SHARP) | 125% | Highly Satisfactory (HS)
|  | (ii) Farmers applying Participatory impact | 0 Farmers applying Participatory impact | 250 farmers applying Participatory impact Monitoring tools and Sharing results through FFS exchanges | 636 farmers applying Participatory Impact monitoring Tools | 1330 farmers applying Participatory Impact monitoring tools | 200% | Highly Satisfactory (HS)
|  | (iii) Communication Strategy in place (visibility and Communication for Development) Availability of project results and communication materials in country and shared with regional Hub | no information and communication materials | Communication strategy in place and project experiences shared through diverse, targeted communication and technical materials (at least 6 per year) SLM/INRM impacts compiled and shared on a 6 monthly basis for discussion and decision making/ planning at all levels including through project steering committee and GSADR | Communication Strategy effectively implemented and project experiences shared through diverse, targeted communication and technical materials (at least 10 per year) SLM/INRM impacts compiled and shared on a 6 monthly basis and workshops to discuss findings and policy implication at a provincial (3) and national (1) levels (e.g.GSADR and BPEAEs) and regional hub level | Communication Strategy effectively implemented and project experiences shared through diverse, targeted communication and technical materials (at least 10 per year) SLM/INRM impacts compiled and shared on a 6 monthly basis and workshops to discuss findings and policy implication at a provincial (3) and national (1) levels (e.g.GSADR and BPEAEs) and regional hub level | 100% | Satisfactory (S)
|  | Number of project reports submitted in time | 0 | 8 | 15 | 19 reports in which 12 PPR and 7 PIR Developed and approved | 110% | Highly Satisfactory (HS)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | Strategy in place | and | Monitoring tools and | Participatory | Developed and
79.6% | 200.6% | (visibility and | communication | Sharing results through | Impact monitoring | approved
|  | Communication for | materials | FFS exchanges | Tools | tools
|  | Development) |  |  | - On-farm (increase of tree cover): 1,958,407t CO2 eq avoided
Availability of project
results and
communication
materials in country
and shared with
regional Hub
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Satisfactory (S) | Satisfactory (S) | Highly Satisfactory (HS) | Satisfactory (S) | Highly Satisfactory (HS)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project has continuously recorded satisfactory results until at its technical end date (30th June 2025). The delivery rate is satisfactory (99,5%). At its end, (i) necessary skills have been set to project beneficiaries for acquired knowledge good management, (ii) an exit strategy has been implemented (iii) and the common anchoring of good practices and lessons learned from the project have been ensured. | The Project has made a long-lasting contribution to sustainable land management and climate resilience. The project's achievements are visible on the ground. The results are consolidated and maximized for a real impact. The impacts are remarkable at the community level and on the overall environment in the project area. Globally, the project has been technically, administratively and financially well managed and has built a good relationship with all stakeholders and partners. | It is one of the most successful projects I have had the opportunity to follow closely in my 30-year career, from a technical, managerial, administrative, and field impact perspective. The project components and various activities were intelligently integrated, which enabled the achievement of long-term, sustainable development progress. The connection between the FFSs and the cooperatives was well managed and led to excellent results on the ground (nutrition, food security, landscape management, climate change adaptation and mitigation, strengthening of value chains), ensuring a real improvement in livelihood of the communities involved, even in the future. | Based on the field visits carried out throughout the project area, I can say that the achievements, results and impact are clearly visible both at the level of direct beneficiaries and in the indirect communities. I can affirm that the project was managed effectively and efficiently. | The project is nearing completion and has achieved most of its intended outcomes. Field missions confirm visible results on the ground, with strong stakeholder engagement and delivery of key activities.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1: Multi-stakeholder and multi-scale platforms operational in supporting policy, institutional and knowledge sharing mechanisms for scaling out of sustainable agriculture systems and integrated natural resources management approaches.
Output 1.1: Agriculture and Rural Development Sector Working Groups (GSADR) at national (1) and provincial (3) levels strengthened and watershed management committees and multi-year | Number of Communal GSDAR | Output achieved as it was the last year of the project end
Output 1.2: Functioning multi-stakeholder knowledge sharing mechanism in place at national (1), provincial (3), and local (4) levels (watershed; FFS networks) and promoting exchange of experiences and lessons learned (success and failure) on scaling out SLM /INRM at landscape scale | Number of exchange visits | Output achieved as it was the last year of the project end
Output 1.3: Legal and regulatory frameworks on SLM, sustainable use of agrobiodiversity and agricultural and environmental strategies and plans better known at national (1) and provincial level (1) and applied in communal development plans and watershed management plans | Number of fairs on agrobiodiversity organized | Output achieved as it was the last year of the project end
Output 1.4: National strategy for harmonization of FFS-INRM operationalized in 3 provinces with particular attention to resilient and sustainable food and agricultural systems | A FFS national strategy operationalized | Roadmap adopted |  |  | To take account Governmental approach, discussion will continued with the FOA Contry Office
Output 1.5: Communities consulted through a participatory negotiated territorial development (PNTD) and Free prior informed consent (FPIC) process (from 2) | FPIC implemented | Output achieved as it was the last year of the project end
Outcome 2: Increased land area and agro-ecosystems under integrated natural resources/ landscape management and supported by FFS and sustainable value chains for increased production and sustainable livelihoods
Output 2.1: Micro-watershed management plans developed and implemented (9) using combined appropriate SLM technologies and a harmonized INRM approach | Number of action plans implemented | Output achieved as it was the last year of the project end
Output 2.2: National FFS curricula (1) updated and FFS master trainers (25) and facilitators (100) trained on the job with 318 FFS groups which are practicing and supported in SLM/ INRM at farm and watershed scale | National FFS Curricula developed and adopted | Output achieved as it was the last year of the project end
Output 2.3: Network of (pre) cooperatives/producers organizations and FFS groups supported and demonstrating improved access to food value chains | Number of cooperatives group supported | Output achieved as it was the last year of the project end - 40
Outcome 3: M&E framework in place and capacity of relevant institutions built capacitated in carrying-out monitoring activities and communicating experiences and impacts for informed decision making
Output 3.1: Government staff and extension workers trained and able to use relevant M&E tools and approaches, also in archiving and analyzing data | Number of government staff trained | 60 |  |  | Training provided as part of the exit strategy. Now this output achieved as it was the last year of the project end
Output 3.3: Project results and experiences compiled, communicated widely and shared with the project regional hub and partner projects | Number of technical papers developed and shared | 10 |  |  | Technical papers developed and sharedin the frame of good practices capitalization process
| Number of public –reporting realized | Output achieved as it was the last year of the project end - 2
Output 3.4: Project progress reports prepared on time, mid and final review/ evaluation conducted | Number Project progress reports prepared | Output achieved as it was the last year of the project end - 2
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Highly Satisfactory (HS) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | During the fiscal year (July 1 2024, to June 30, 2025), all planned results have been achieved.The satisfaction rating level of comes also from the testimonies of the beneficiaries, published during the final closing workshop of the project organized on 06/26/2025. In 2025, the project definitively transferred to the communities a large number of community and private woodlands, a large number of hillside irrigation infrastructure, storage sheds for production from the value chains, equipment for processing agricultural production and all this accompanied by a good exit strategy for the sustainability of these achievements, which greatly satisfies the communities, the local technical and administrative authorities as well as the development partners. | All activities were completed, leaving excellent results in the field. In the final phase, a strong effort was also made to capitalize on best practices, which were well thought out and organized, and will remain valuable references and replicable examples within the country. | The overall progress of results from July 1 2024, to June 30, 2025 have been achieved and the project definitively transferredall its achievements to the communities through a good exit strategy which greatly satisfies all stakeholders | Based on the field visits carried out throughout the project area, I can say that the achievements, results and impact are clearly visible both at the level of direct beneficiaries and in the indirect communities. I can affirm that the project was managed effectively and efficiently. | Despite early delays, the project has caught up on implementation and maintained steady progress through its final year. Execution is largely complete, and the project has delivered in line with its work plan. Coordination and adaptive adjustments have contributed to this result.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
As we are at the end of the project, the project implementation progress consistent show that there are on the ground: *Nine (9) agricultural product storage sheds built (8) / rehabilitated (1). *Six (6) hydro-agricultural infrastructure projects for hillside irrigation. *One (1) marshland equipped with an irrigation system, the Ndebe marshland, for the benefit of 23 cooperatives operating in the marshland. *More than thirteen (13) community afforestation sites on public communal lands of more than 5 hectares in the provinces of Gitega, Mwaro, and Muramvy have been established since 2019, as well as around one hundred other small private afforestation sites established by watershed communities. *46,652 hectares of 9 watersheds with improved integrated agro-sylvo-pastoral practices, with 947.95 km of contour lines dug for erosion control. *25,980 hectares of agricultural land covered by forestry and agroforestry thanks to the project. *Five (5) types of equipment for processing agricultural products (pineapple juice extractors, stainless steel tables, bottles, caps, and cappers) for the TWIJABUTSE cooperatives in Ndava and TWIYUNGURE in Giheta to support pineapple processing. *Three (3) types of equipment for preservation and sterilization (laminar flow hood, autoclave, refrigerator) for the Akantu Kagirwa Nakandi Association (AKA-SOVERT) to support the production and preservation of mushroom seeds; ix. Two (2) pig breeding centers, each with 33 pigs, 1,950 pigs, 540 rabbits, and 47 cattle distributed to the FFSs that have evolved into cooperatives (a total of 66 pigs for both) were established by the end of 2023 for the benefit of model and progressive agri-pastoralists, including Marc MANIRAKIZA in Kayokwe and the IFRET Cooperative in Gitega. *1,950 pigs, 540 rabbits, and 47 cattle distributed to the FFSs that have evolved into cooperatives, supervised by the project through the community solidarity chain in the nine municipalities of the project intervention area. *Two (2) access roads to community infrastructure were developed in the municipalities of Bukeye and Ndava.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The major challenges to the smooth running of activities are linked to the Country socio-economic context (lack of currency on the local market, shortage of fuel, and surge in prices of necessities) which has slowed down the construction of community infrastructure and supplier delays in the delivery of inputs ordered by the project.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | Yes, the project has developed and implemented an exit strategy that consists of ensuring the sustainability of the project's achievements after the end of its external funding. The exit strategy was about guaranteeing that communities, local institutions and partners are able to continue, adapt and disseminate the good practices introduced by the project. This exit strategy is currently operational.
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The project enhancing institutional capacities to foster country ownership for more durable / sustained results throug local capacity building, institutionalization of practices, community ownership and local governance and community monitoring and evaluation systems by communities, local institutions and partners.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low
New environmental and social risks. | No one
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | Not Applicable
Grievance Redress Mechanism (GRM) | Two conflicts between project suppliers reached FAO, but these did not involve FAO or the beneficiaries. Suppliers were advised to refer to local technical, administrative, and legal authorities.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Safety & Security |  | Low | No | COVID -19 | Strategic measures in place to continue developing minimum activities on the fields
2 | Safety & Security |  | Low | No | Rift valley Fever | Community awareness of the disease scope on animal farms and ways to reduce its spread
3 | Economic |  | Moderate | No | Country socio-economic context (lack of currency, shortage of fuel, and surge in prices of necessities) which slowed down inputs ordered by the project | Relaunch the tender documents for project supplies and services several times to reach many potential suppliers
4
5
6
7
8
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
L | Low | The main challenge is currently Country socio-economic context (lack of currency, shortage of fuel, and surge in prices of necessities) but the situation have been and is constantly monitored as the projet budget is in USD.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1: Multi-stakeholder and multi-scale platforms and knowledge-sharing mechanism: Expand the mandate of the GSADR to include considerations related to the knowledge-sharing mechanism (WOCAT-DATAR Group), the management of good practices (Communal Platform on Good Practices) | 3 meetings organized between FAO, MINEAGRIE and the 3 proviancial BPEAE to facilitate and organize National and Provincial GSADR, organize knowledge sharing mechanism and design policy and regulatory Framework in INRM.
Recommendation 2: Establish a dynamic with the Sub-regional Office to create an expert pool at the national and/or regional level: 1. Form a pool of experts at the regional level for the tools: Exact, DATAR, WOCAT with a view to having national and sub-regional expertise available and at a lower cost in order to overcome the difficulty of not having international experts available. | Not applicable for the project.
Recommendation 3:Transform the Community Watershed Management Plans into a "bankable" document and facilitate ownership of the watershed management plans once the management committees are in place | The community, Watershed Management Plans are now part of Communal Community Development Plans that are used as bankable documents by partners.
Recommendation 4: Highlight the Resilience Fund approach implemented by the project. Highlight the Resilience Fund approach in the logframe and implementation reports. The Resilience Fund approach implemented by the project, although very effective, is not sufficiently highlighted and promoted by the project because no related indicators are clearly developed in the project's monitoring and evaluation system for the economic and social pillars | Indicators related to the Resilient Fund approach have been integrated into project’s logical framework and regularly tracked.
Recommendation 5: Produce initial capitalization documents on knowledge management The evaluation recommends that the project produce simple materials in the local language, "Kirundi"-and also in pictorial form, radio programs, videos, plays, etc., to disseminate messages more effectively. This strengthens SLM/INRM integration and awareness of the many synergistic benefits of SLM technologies. The institutionalization of the RWH approach underway with the ministry's extension services will also strengthen the knowledge sharing mechanism. The project can also produce a map of all reforested areas | As part of the capitalization of the project's achievements, 10 documentation sheets of good practices have been shared to the LTO to be disigned and published
Recommendation 6: Consolidate the structuring, functioning of existing FFSs, promote pilot value chains, and consider the concerns of indigenous populations | The project focuses on consolidate and support 106 existing FFS groups. These FFS groups have been transformed into 43 functional cooperatives including indigenous people where 9 value chains are promoting six sustainable value chains in which 2 are reaching the professional level (waiting for labeling)
Recommendation 7: Identify good practices according to the FAO approach and share knowledge of them with stakeholders | Good practices have been identified and the development of 10 documentation sheets of good practices have been shared to the LTO to be disigned and published
Recommendation 8: Organize additional training for the 15 other untrained managers to set up a functional system for collecting data on impact indicators related to household food security, resilience and nutritional aspects | 2 main activities registered by the project, namely: (i) the development of tools for digital data collection to monitor and assess the FFS implementation and results and (ii) the organization of a training on the digital data collection tool for the monitoring good practices and their contribution in the four betters.
Recommendation 9: Continuously document all quantitative and qualitative data related to the project's implementation at the FFS level | The project continues to collect data regarding the project progress with participation of FFS groups and/or cooperatives and facilitators
Recommendation 10: Improve the speed of the project's procurement process through greater involvement of the FAO Country Office and clarify misunderstandings about procedures to anticipate possible blockages in the project's implementation | The project has implemented an anticipative purchasing strategy, which has proven effective in meeting procurement needs so that most supplies are at the end process schedule.
Recommendation 11: Request an extension of the project for 12 months and re-budget the remaining activities, prioritizing those related to improving the living conditions of the local beneficiary communities. It will also be necessary to take into account the new activities resulting from the recommendations of the MTR | The project team has requested and obtained another extension to ensure consolidation of project achievements for beneficiary interest. The new project closure is planned at the end of June 2024

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | No change
Components and cost | No change
Institutional and implementation arrangements | No change
Financial management | No change
Implementation schedule | No change
Executing Entity | No change
Executing Entity Category | No change
Minor project objective change | No change
Safeguards | No change
Risk analysis | No change
Increase of GEF project financing up to 5% | No change
Co-financing | No change
Location of project activity | No change
Other minor project amendment (define) | No
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | IGEBU | Executing Agency | Closed since 2024
Government Institutions | DGPEAE | Executing Agency | Closed since 2024
Government Institutions | CMSMF | Executing Agency | Closed since 2024
Government Institutions | BPEAE Gitega | Executing Agency | Closed since 2024
Government Institutions | BPEAE Mwaro | Executing Agency | Closed since 2024
Government Institutions | BPEAE Muramvya | Executing Agency | Closed since 2024
Government Institutions | BBN | Executing Agency | Closed since 2024
NGOs | APROCUVI | Executing Agency | Closed since 2024
NGOs | ADISCO | Executing Agency | Closed since 2024

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | As about 70 % of beneficiaries are women, during the project implementation, gaps in access to and control overal natural resources have ben enchanced and women and men are trained on natural conflicts resolution
b. Improving women's participation and decision making | Yes | In the project, when the president of cooperative is a man, a woman is vice president and vice versa. The project pays attention all the time that the participation in decision makers is important.
c. generating socio-economic benefits or services for women | Yes | In cooperatives activities, Women are encouraged to participating all the time in benefits or services that generating socio-economic advantage
d. Any other good practices on gender |  | An analysis of gender integration level in the project intervention is regulary made

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The project has a knowledge management strategy that allows collection and documentation of good practices through the organization of workshops involving all stakeholders.During this reporting period, the project’s knowledge management strategy focused on capitalization on good practices and project exit strategy. In this context, 10 documentation sheets for said practices have been developed and are being published.The project enhancing institutional capacities to foster country ownership for more durable / sustained results throug local capacity building, institutionalization of practices, community ownership and local governance and community monitoring and evaluation systems by communities, local institutions and partners.
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | The ten (10) good practices, including key-technical and/or institutional innovations, from the project have have been developed and are being published. There are (1)Contribution of Farmer Field Schools to Improving Well-being, (2) Improving the Nutritional Situation and Income of Vulnerable Households through Mushroom Farming, (3) Contribution of Labor-Intensive Activities to the Climate and Economic Resilience of Rural Communities, (4) Contribution of Farmer Field Schools to Improving Nutrition, (5) Contribution of Farmer Field Schools to Improving Production, (6) Contribution of Farmer Field Schools to Improving the Environment, (7) Contribution of Banana Tree Sheath Baskets to the Production of Agroforestry and Native Forest Plants, (8) Contribution of Hillside Irrigation to Increasing Production and Climate Resilience of Communities, (9) Stabilizing Riverbanks through Bamboo Planting, (10)Strengthening the Connection of Farmer Field Schools (FFS) and Cooperatives to Markets
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | The project has a knowledge management strategy that allows collection and documentation of good practices. During this reporting period, the project’s knowledge management strategy focused on capitalization on good practices and project achievements.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | 1. From destitute to entrepreneur, Silas Ntahondereye’s journey to success thanks to the FFS: https://www.fao.org/burundi/programmes-et-projets/histoires-de-reussite/fr/
Please provide links to related website, social media account | Video links: 1. https://www.youtube.com/watch?v=7N8t9CHtnTY 2. https://www.youtube.com/watch?v=4gNer96ef7I Articles: 1. https://www.fao.org/burundi/actualites/detail-events/fr/c/1738139/ 2. https://www.fao.org/burundi/actualites/detail-events/fr/c/1731729/ 3. https://burundi.un.org/fr/295612-investir-dans-lavenir-le-projet-iap-fs-renforce-la-s%C3%A9curit%C3%A9-alimentaire-%C3%A0-gitega-muramvya-et 4. https://burundi.un.org/fr/288819-la-myciculture-une-aubaine-pour-les-coop%C3%A9ratives-encadr%C3%A9es-par-la-fao 5. https://www.fao.org/burundi/actualites/detail-events/fr/c/1739540/ 6. https://www.fao.org/burundi/actualites/detail-events/fr/c/1739540/ 7. https://www.fao.org/burundi/actualites/detail-events/fr/c/1709200/ 8. https://www.fao.org/burundi/actualites/detail-events/fr/c/1683201/ 9. https://www.fao.org/burundi/actualites/detail-events/fr/c/1675758/ 10. https://www.fao.org/burundi/actualites/detail-events/fr/c/1634753/ 11. https://www.fao.org/burundi/actualites/detail-events/fr/c/1599955/ 12. https://www.fao.org/burundi/actualites/detail-events/fr/c/1492034/ 13. https://www.fao.org/burundi/actualites/detail-events/fr/c/1468676/ 14. https://www.fao.org/burundi/actualites/detail-events/fr/c/1467579/ 15. https://www.fao.org/burundi/actualites/detail-events/fr/c/1457393/ 16. https://www.fao.org/burundi/actualites/detail-events/fr/c/1300270/ 17. https://www.fao.org/burundi/actualites/detail-events/fr/c/1236567/ 18. https://www.fao.org/burundi/actualites/detail-events/fr/c/1207381/ 19. https://burundi.un.org/fr/288819-la-myciculture-une-aubaine-pour-les-coop%C3%A9ratives-encadr%C3%A9es-par-la-fao 20. https://burundi.un.org/fr/270577-capitalisation-des-bonnes-pratiques-dans-le-cadre-du-projet-integrated-approach-pilot-food 21. https://burundi.un.org/fr/259236-la-fao-%C3%A0-l%E2%80%99actif-de-l%E2%80%99am%C3%A9lioration-de-l%E2%80%99environnement-et-des-moyens-d%E2%80%99existence-des 22. https://www.iwacu-burundi.org/projet-iap-fs-un-projet-efficace-qui-a-change-les-conditions-de-vie-des-beneficiaires/
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | Regarding publications, 1. Two videos were published online on the partners' websites. 2. A newsletter was published. 3. More than 20 articles were published on the FAO website and the United Nations website. 4. Most of the articles appeared in the monthly newsletter of the United Nations in Burundi. 5. Several tweets were published on the FAO in Burundi page X.
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Joseph Nsabiyabandi e-mail: Joseph.Nsabiyabandi@fao.org

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. Yes, the project has FFS group including Batwa (Burundi indigenous people) involved in SLM and livelihoods activities in Mwaro Province.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | IFAD – PRODEFI | In-kind | 21440000 | 21440000
Recipient Country Government | World Bank - PRODEMA | In-kind | 6000000 | 3800000
Recipient Country Government | World Bank – PADZOC | In-kind | 14110728 | 2800000
Recipient Country Government | MINAGRIE | In-kind | 3000000 | 4500000
Beneficiaries | FAO | In-kind | 500000 | 1500000
Recipient Country Government | MINAGRIE-IFAD/PRODER | In-kind | 0 | 11050000
Total |  | Total | 45050728 | 45090000
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
The World Bank's PRODEMA and PADZOC projects have not provided all of the co-financing since CEO Endorsement/Approval due to the COVID-19 context, which did not allow for the consistency of field activities to complete the co-financing. However, MINEAGRIE and FAO have each adopted to complete the required co-financing through new projects, as shown in the co-financing table.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report? |  |  |  |  | No
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.