## Work Plan
Tentative Project Work Plan and Time Schedule
Project Objective: To promote the concept of circular economy (CE) in the textile and garment (TG) sector of Lesotho, Madagascar and South Africa through the reuse, recycling and conversion of textile/garment discards and related wastes into economically viable and socially beneficial products and services.
Project Work Plan | Project Details and Information | Year 1 - 2022-2023 | [11 empty] | Year 2 - 2023-2024 | [11 empty] | Year 3 - 2024-2025 | [11 empty] | Year 4 - 2025-2026 | [11 empty] | Year 5 - 2026-2027
|  | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
Component 1 | Strengthening of regulatory and institutional capacities for adoption and promotion of Circular Economy (CE) in the textile and garment sector
Output 1.1 | Legal and institutional framework for life cycle management of the TG supply/value chains. | bar: Year 1 - 2022-2023 11 to Year 2 - 2023-2024 11
Output 1.2 | Regulations and incentive scheme for promotion and sustainability of circular economy in the TG sector. | bar: Year 2 - 2023-2024 9 to Year 3 - 2024-2025 6
Output 1.3 | Technical Committee for Circular Economy in the TG sector | bar: Year 1 - 2022-2023 3 to Year 5 - 2026-2027 6
Outcome 1 | Strengthened regulatory and institutional framework and capacities for adoption of Circular Economy in the TG sector
Component 2 | Recyclability of textile and garment wastes is enhanced through POPs-free textile manufacturing process and the implementation of BAT/BEP and RECP investments.
Output 2.1 | Technical guidelines for environmental sound management of POPs chemicals and wastes | bar: Year 1 - 2022-2023 10 to Year 3 - 2024-2025 12
Output 2.2 | Standard operating procedures (SOPs) and checklists POPs pollution prevention and control | bar: Year 1 - 2022-2023 3 to Year 2 - 2023-2024 11
Output 2.3 | Techno-economic feasibility of BAT/BEP and RECP options | bar: Year 2 - 2023-2024 7 to Year 2 - 2023-2024 12
Output 2.4 | Training and Capacity building in BAT/BEP, RECP and Circular Economy. | bar: Year 1 - 2022-2023 3 to Year 5 - 2026-2027 6
Output 2.5 | BAT/BEP and RECP options identified and implemented in at least one facility for each country. | bar: Year 2 - 2023-2024 10 to Year 5 - 2026-2027 6
Outcome 2 | BAT/BEP/RECP and Circular Economy concept are implemented through technical assistance in selected textile production facilities for the ESM and prevention / reduction of POPs, hazardous chemicals and wastes while improving process efficiency and profitability at plant level.
Component 3 | Introduction of Circular Economy concept for UPOPs emission reductions through ESM of textile and garment wastes and pilot demonstration of textiles/garment wastes recycling and reuse.
Output 3.1 | Environmentally sound management (ESM) plan for textile/garment wastes. | bar: Year 1 - 2022-2023 11 to Year 2 - 2023-2024 4
Output 3.2 | Training and capacity building in ISWM and BAT/BEP for ESM of textile and garment wastes. | bar: Year 2 - 2023-2024 12 to Year 4 - 2025-2026 7
Output 3.3 | Financing mechanisms and business models for circular economy. | bar: Year 2 - 2023-2024 12 to Year 4 - 2025-2026 7
Output 3.4 | Techno-economic feasibility study of BAT/BEP options for recycling/reuse of textile and garment wastes. | bar: Year 1 - 2022-2023 5 to Year 2 - 2023-2024 12
Output 3.5 | Socio-economic impact assessment of project intervention
Output 3.6 | Partnership and cooperation mechanism supply chain management
Output 3.7 | BAT/BEP demonstration for ESM of POPs chemicals and textile/garment wastes | bar: Year 2 - 2023-2024 1 to Year 5 - 2026-2027 6
Outcome 3 | BAT/ BEP and Circular Economy concept are implemented through technical assistance in selected TG and recycling facilities for the reuse, recycling and ESM of textile and garment wastes.
Component 4 | Knowledge management for scaling up
Output 4.1 | National capacity and awareness programs developed and implemented to increase ability of textile sector and policy makers to control POPs and CoCs
Output 4.2 | Regional and Global Knowledge Exchange and Management tools produced and accessed by users globally
Output 4.3 | Gender and Social Action Plan implemented, and benefits accrued to women workers
Outcome 4 | Upscaling of project results to global textile and garment sectors and reporting to MEAs
Component 5 | Monitoring and Evaluation
Output 5.1 | Project progress monitoring and reporting
Output 5.2 | Mid-term and terminal evaluations results shared with stakeholders | bar: Year 3 - 2024-2025 11 to Year 3 - 2024-2025 1; Year 5 - 2026-2027 4 to Year 5 - 2026-2027 6
Outcome 5 | M&E framework in accordance with UNIDO and GEF requirements

## Budget breakdown per year
| YEAR 1 - 2023 | [5 empty] | YEAR 2 - 2024 | [5 empty] | YEAR 3 - 2025
| NCPC | Lesotho | Madagascar | Africa Institute | Total |  | NCPC | Lesotho | Madagascar | Africa Institute | Total |  | NCPC | Lesotho | Madagascar | Africa Institute | Total
Output 1.1 | 8740 | 6857.75 | 6357.75 | 53459 | 75414.5 | Output 1.1 | 26223 | 20573.25 | 19073.25 | 160377 | 226246.5 | Output 1.1 | 0 | 0 | 0 | 0 | 0
Output 1.2 | 0 | 0 | 0 | 0 | 0 | Output 1.2 | 13996 | 11382 | 10582 | 31288 | 67248 | Output 1.2 | 20995 | 17073 | 15873 | 46933 | 100874
Output 1.3 | 0 | 0 | 0 | 0 | 0 | Output 1.3 | 11401 | 9322.5 | 8722.5 | 10141 | 39587 | Output 1.3 | 7600 | 6215 | 5815 | 6761 | 26391
Output 2.1 | 2713 | 2011.8 | 2011.8 | 24121 | 30857.6 | Output 2.1 | 3102 | 2299.2 | 2299.2 | 27567 | 35267.4 | Output 2.1 | 1938 | 1437 | 1437 | 17229 | 22041
Output 2.2 | 0 | 0 | 0 | 0 | 0 | Output 2.2 | 11402 | 8924 | 8924 | 66083 | 95333 | Output 2.2 | 0 | 0 | 0 | 0 | 0
Output 2.3 | 0 | 0 | 0 | 0 | 0 | Output 2.3 | 11402 | 8924 | 8924 | 31917 | 61167 | Output 2.3 | 0 | 0 | 0 | 0 | 0
Output 2.4 | 4882 | 4009.04 | 3849.04 | 10932 | 23672.08 | Output 2.4 | 14035 | 11525.99 | 11065.99 | 31429 | 68055.98 | Output 2.4 | 14035 | 11525.99 | 11065.99 | 31429 | 68055.98
Output 2.5 | 0 | 0 | 0 | 0 | 0 | Output 2.5 | 144304 | 115098 | 114098 | 29167 | 402667 | Output 2.5 | 57721 | 46039.2 | 45639.2 | 29166 | 178565.4
Output 3.1 | 1638 | 1325.9 | 1325.9 | 7708 | 11997.8 | Output 3.1 | 11468 | 9281.3 | 9281.3 | 53956 | 83986.6 | Output 3.1 | 3276 | 2651.8 | 2651.8 | 15416 | 23995.6
Output 3.2 | 0 | 0 | 0 | 0 | 0 | Output 3.2 | 2952 | 2469.1 | 2469.1 | 7472 | 15362.2 | Output 3.2 | 20663 | 17283.7 | 17283.7 | 52302 | 107532.4
Output 3.3 | 0 | 0 | 0 | 0 | 0 | Output 3.3 | 1675 | 1357.6 | 1357.6 | 4455 | 8845.2 | Output 3.3 | 11723 | 9503.2 | 9503.2 | 31185 | 61914.4
Output 3.4 | 0 | 0 | 0 | 0 | 0 | Output 3.4 | 16382 | 13259 | 13259 | 102383 | 145283 | Output 3.4 | 0 | 0 | 0 | 0 | 0
Output 3.5 | 17477 | 14211 | 14211 | 36050 | 81949 | Output 3.5 | 0 | 0 | 0 | 0 | 0 | Output 3.5 | 0 | 0 | 0 | 0 | 0
Output 3.6 | 3656 | 2222.04 | 2222.04 | 21446 | 29546.08 | Output 3.6 | 6703 | 4073.74 | 4073.74 | 39318 | 54168.48 | Output 3.6 | 6703 | 4073.74 | 4073.74 | 39317 | 54167.48
Output 3.7 | 0 | 0 | 0 | 0 | 0 | Output 3.7 | 647206 | 561809.5 | 558309.5 | 20831 | 1788156 | Output 3.7 | 323603 | 280904.75 | 279154.75 | 20832 | 904494.5
Output 4.1 | 5235 | 4196.76 | 3716.76 | 5863 | 19011.52 | Output 4.1 | 9598 | 7694.06 | 6814.06 | 10749 | 34855.12 | Output 4.1 | 9598 | 7694.06 | 6814.06 | 10749 | 34855.12
Output 4.2 | 2559 | 2108.4 | 2108.4 | 45852 | 52627.8 | Output 4.2 | 4694 | 3865.4 | 3865.4 | 84061 | 96485.8 | Output 4.2 | 4694 | 3865.4 | 3865.4 | 84060 | 96484.8
Output 4.3 | 4228 | 2960.28 | 3080.28 | 1063 | 11331.56 | Output 4.3 | 7752 | 5427.18 | 5647.18 | 1949 | 20775.36 | Output 4.3 | 7752 | 5427.18 | 5647.18 | 1949 | 20775.36
Output 5.1 | 16784 | 14608 | 14608.2 | 19400 | 65400.2 | Output 5.1 | 16784 | 14608.2 | 14608.2 | 19400 | 65400.4 | Output 5.1 | 16784 | 14608.2 | 14608.2 | 19400 | 65400.4
Output 5.2 | 0 | 0 | 0 | 0 | 0 | Output 5.2 | 0 | 0 | 0 | 0 | 0 | Output 5.2 | 22165 | 10292.4 | 10292.4 | 119250 | 161999.8
|  |  |  | TOTAL YEAR 1 | 401808.14 |  |  |  |  | Total Y2 | 3308890.04 |  |  |  |  | Total Y3 | 1927547.24
| YEAR 4 - 2026 | [5 empty] | YEAR 5 - 2027
| NCPC | Lesotho | Madagascar | Africa Institute | Total |  | NCPC | Lesotho | Madagascar | Africa Institute | Total
Output 1.1 | 0 | 0 | 0 | 0 | 0 | Output 1.1 | 0 | 0 | 0 | 0 | 0
Output 1.2 | 0 | 0 | 0 | 0 | 0 | Output 1.2 | 0 | 0 | 0 | 0 | 0
Output 1.3 | 11400 | 9322.5 | 8722.5 | 10141 | 39586 | Output 1.3 | 7600 | 6215 | 5815 | 6761 | 26391
Output 2.1 | 0 | 0 | 0 | 0 | 0 | Output 2.1 | 0 | 0 | 0 | 0 | 0
Output 2.2 | 0 | 0 | 0 | 0 | 0 | Output 2.2 | 0 | 0 | 0 | 0 | 0
Output 2.3 | 0 | 0 | 0 | 0 | 0 | Output 2.3 | 0 | 0 | 0 | 0 | 0
Output 2.4 | 14036 | 11525.99 | 11065.99 | 31430 | 68057.98 | Output 2.4 | 14036 | 11525.99 | 11065.99 | 31430 | 68057.98
Output 2.5 | 57722 | 46039.2 | 45639.2 | 0 | 149400.4 | Output 2.5 | 28861 | 23019.6 | 22819.6 | 0 | 74700.2
Output 3.1 | 0 |  |  | 0 | 0 | Output 3.1 | 0 | 0 | 0 | 0 | 0
Output 3.2 | 5903 | 4938.2 | 4938.2 | 14943 | 30722.4 | Output 3.2 | 0 | 0 | 0 | 0 | 0
Output 3.3 | 3349 | 2715.2 | 2715.2 | 8910 | 17689.4 | Output 3.3 | 0 | 0 | 0 | 0 | 0
Output 3.4 | 0 | 0 | 0 | 0 | 0 | Output 3.4 | 0 | 0 | 0 | 0 | 0
Output 3.5 | 0 | 0 | 0 | 0 | 0 | Output 3.5 | 0 | 0 | 0 | 0 | 0
Output 3.6 | 6702 | 4073.74 | 4073.74 | 39318 | 54167.48 | Output 3.6 | 6702 | 4073.74 | 4073.74 | 39318 | 54167.48
Output 3.7 | 194161.95 | 168542.85 | 167492.85 | 0 | 530197.65 | Output 3.7 | 129442 | 112361.9 | 111661.9 | 0 | 353465.8
Output 4.1 | 9599 | 7694.06 | 6814.06 | 10749 | 34856.12 | Output 4.1 | 9599 | 7694.06 | 6814.06 | 10748 | 34855.12
Output 4.2 | 4694 | 3865.4 | 3865.4 | 84060 | 96484.8 | Output 4.2 | 4694 | 3865.4 | 3865.4 | 84060 | 96484.8
Output 4.3 | 7752 | 5427.18 | 5647.18 | 1949 | 20775.36 | Output 4.3 | 7753 | 5427.18 | 5647.18 | 1948 | 20775.36
Output 5.1 | 16784 | 14608.2 | 14608.2 | 19400 | 65400.4 | Output 5.1 | 16783 | 14608.2 | 14608.2 | 19399 | 65398.4
Output 5.2 | 0 | 0 | 0 | 0 | 0 | Output 5.2 | 27092 | 12579.6 | 12579.6 | 145750 | 198001.2
|  |  |  | Total Y4 | 1107337.99 |  |  |  |  | Total Y5 | 992297.34

## South Africa
| Y1 | Y2 | Y3 | Y4 | Y5 |  |  | Budget NEE ($) | Output | Budget NEE ($) | Y1 | y2 | y3 | y4 | Y5
Output 1.1 | 25% | 75% | 0 | 0 | 0 |  | Component 1 | 107955 | Output 1.1 | 34963 | 8740 | 26223 |  |  |  | 34963
Output 1.2 | 0% | 40% | 60% | 0% | 0% |  |  |  | Output 1.2 | 34991 | 0 | 13996 | 20995 | 0 | 0 | 34991
Output 1.3 | 0% | 30% | 20% | 30% | 20% |  |  |  | Output 1.3 | 38001 | 0 | 11401 | 7600 | 11400 | 7600 | 38001
Output 2.1 | 35% | 40% | 25% | 0% | 0% |  | Component 2 | 380189 | Output 2.1 | 7753 | 2713 | 3102 | 1938 | 0 | 0 | 7753
Output 2.2 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.2 | 11402 | 0 | 11402 | 0 | 0 | 0 | 11402
Output 2.3 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.3 | 11402 | 0 | 11402 | 0 | 0 | 0 | 11402
Output 2.4 | 8% | 23% | 23% | 23% | 23% |  |  |  | Output 2.4 | 61024 | 4882 | 14035 | 14035 | 14036 | 14036 | 61024
Output 2.5 | 0% | 50% | 20% | 20% | 10% |  |  |  | Output 2.5 | 288608 | 0 | 144304 | 57721 | 57722 | 28861 | 288608
Output 3.1 | 10% | 70% | 20% | 0% | 0% |  | Outcome 3 | 1421385 | Output 3.1 | 16382 | 1638 | 11468 | 3276 | 0 | 0 | 16382
Output 3.2 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.2 | 29518 | 0 | 2952 | 20663 | 5903 | 0 | 29518
Output 3.3 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.3 | 16747 | 0 | 1675 | 11723 | 3349 | 0 | 16747
Output 3.4 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 3.4 | 16382 | 0 | 16382 | 0 | 0 | 0 | 16382
Output 3.5 | 100% | 0% | 0% | 0% | 0% |  |  |  | Output 3.5 | 17477 | 17477 | 0 | 0 | 0 | 0 | 17477
Output 3.6 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 3.6 | 30466 | 3656 | 6703 | 6703 | 6702 | 6702 | 30466
Output 3.7 | 0% | 50% | 25% | 15% | 10% |  |  |  | Output 3.7 | 1294413 | 0 | 647206 | 323603 | 194161.95 | 129442 | 1294412.95
Output 4.1 | 12% | 22% | 22% | 22% | 22% |  | Outcome 4 | 100201 | Output 4.1 | 43629 | 5235 | 9598 | 9598 | 9599 | 9599 | 43629
Output 4.2 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.2 | 21335 | 2559 | 4694 | 4694 | 4694 | 4694 | 21335
Output 4.3 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.3 | 35237 | 4228 | 7752 | 7752 | 7752 | 7753 | 35237
Output 5.1 | 20% | 20% | 20% | 20% | 20% | 5.2 | M&E |  | 49257 |  | 0 | 0 | 22165 | 0 | 27092 | 49257
Output 5.2 | 0% | 0% | 45% | 0% | 55% | 5.1 | PMC |  | 83919 |  | 16784 | 16784 | 16784 | 16784 | 16783 | 83919
[7 empty] | Total |  | 2142906 |  | 67912 | 961079 | 529250 | 332102.95 | 252562 | 2142905.95
National Cleaner Production Centre of South Africa (NCPCSA) (NEE)
[10 empty] | Total per year | 67912 | 961079 | 529250 | 332102.95 | 252562 | 2142905.95
4881.92
[9 empty] | 14035.52 |  |  | 1028991
2023
2525700
2024
1852300
2025
1636700
2026
1385300

## Regional Executing Entity
| 2023 | 2024 | 2025 | 2026 | 2027 | Africa Institute for Environmentally Sound Management of Hazardous and Other Wastes, South Africa
| Y1 | Y2 | Y3 | Y4 | Y5 | Regional/both | Budget REE ($) | Output | Budget REE ($) | 2023 | 2024 | 2025 | 2026 | 2027
Output 1.1 | 25% | 75% | 0 | 0 | 0 | Component 1 | 325861 | Output 1.1 | 213836 | 53459 | 160377 | 0 | 0 | 0 | 213836
Output 1.2 | 0% | 40% | 60% | 0% | 0% |  |  | Output 1.2 | 78221 | 0 | 31288 | 46933 | 0 | 0 | 78221
Output 1.3 | 0% | 30% | 20% | 30% | 20% |  |  | Output 1.3 | 33804 | 0 | 10141 | 6761 | 10141 | 6761 | 33804
Output 2.1 | 35% | 40% | 25% | 0% | 0% | Component 2 | 361900 | Output 2.1 | 68917 | 24121 | 27567 | 17229 | 0 | 0 | 68917
Output 2.2 | 0% | 100% | 0% | 0% | 0% |  |  | Output 2.2 | 66083 |  | 66083 |  |  |  | 66083
Output 2.3 | 0% | 100% | 0% | 0% | 0% |  |  | Output 2.3 | 31917 |  | 31917 |  |  |  | 31917
Output 2.4 | 8% | 23% | 23% | 23% | 23% |  |  | Output 2.4 | 136650 | 10932 | 31429 | 31429 | 31430 | 31430 | 136650
Output 2.5 | 0% | 50% | 20% | 20% | 10% |  |  | Output 2.5 | 58333 | 0 | 29167 | 29166 | 0 | 0 | 58333
Output 3.1 | 10% | 70% | 20% | 0% | 0% | Outcome 3 | 555160 | Output 3.1 | 77080 | 7708 | 53956 | 15416 | 0 | 0 | 77080
Output 3.2 | 0% | 10% | 70% | 20% | 0% |  |  | Output 3.2 | 74717 | 0 | 7472 | 52302 | 14943 |  | 74717
Output 3.3 | 0% | 10% | 70% | 20% | 0% |  |  | Output 3.3 | 44550 | 0 | 4455 | 31185 | 8910 |  | 44550
Output 3.4 | 0% | 100% | 0% | 0% | 0% |  |  | Output 3.4 | 102383 |  | 102383 |  |  |  | 102383
Output 3.5 | 100% | 0% | 0% | 0% | 0% |  |  | Output 3.5 | 36050 | 36050 |  |  |  |  | 36050
Output 3.6 | 12% | 22% | 22% | 22% | 22% |  |  | Output 3.6 | 178717 | 21446 | 39318 | 39317 | 39318 | 39318 | 178717
Output 3.7 | 0% | 50% | 25% | 15% | 10% |  |  | Output 3.7 | 41663 |  | 20831 | 20832 |  |  | 41663
Output 4.1 | 12% | 22% | 22% | 22% | 22% | Outcome 4 | 439810 | Output 4.1 | 48858 | 5863 | 10749 | 10749 | 10749 | 10748 | 48858
Output 4.2 | 12% | 22% | 22% | 22% | 22% |  |  | Output 4.2 | 382093 | 45852 | 84061 | 84060 | 84060 | 84060 | 382093
Output 4.3 | 12% | 22% | 22% | 22% | 22% |  |  | Output 4.3 | 8858 | 1063 | 1949 | 1949 | 1949 | 1948 | 8858
Output 5.1 | 20% | 20% | 20% | 20% | 20% | 5.2 M&E 51 |  | 265000 |  | 0 | 0 | 119250 | 0 | 145750 | 265000
Output 5.2 | 0% | 0% | 45% | 0% | 55% | 5.1 PMC 53 |  | 96999 |  | 19400 | 19400 | 19400 | 19400 | 19399 | 96999
[6 empty] | Total |  | 2044730 | [6 empty] | 2044729
[9 empty] | Total per year | 225894 | 732543 | 525978 | 220900 | 339414 | 2044729
[7 empty] | Actually the sum of all outputs is | 2044729
45851.16
2044729
0
For 2.5 and 3.7 for Africa Institute, please just split the amounts in 2 and give half in 2024 and the rest in 2025 since they will only be monitoring.

## Lesotho
Lesotho | Y1 | Y2 | Y3 | Y4 | Y5 |  | Lesotho | Budget NEE ($) | Output | Budget NEE ($) | Y1 | y2 | y3 | y4 | Y5 | Total
Output 1.1 | 25% | 75% | 0 | 0 | 0 |  | Component 1 | 86960 | Output 1.1 | 27431 | 6857.75 | 20573.25 |  |  |  | 27431
Output 1.2 | 0% | 40% | 60% | 0% | 0% |  |  |  | Output 1.2 | 28455 |  | 11382 | 17073 |  |  | 28455
Output 1.3 | 0% | 30% | 20% | 30% | 20% |  |  |  | Output 1.3 | 31075 |  | 9322.5 | 6215 | 9322.5 | 6215 | 31075
Output 2.1 | 35% | 40% | 25% | 0% | 0% |  | Component 2 | 303905 | Output 2.1 | 5748 | 2011.8 | 2299.2 | 1437 |  |  | 5748
Output 2.2 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.2 | 8924 |  | 8924 |  |  |  | 8924
Output 2.3 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.3 | 8924 |  | 8924 |  |  |  | 8924
Output 2.4 | 8% | 23% | 23% | 23% | 23% |  |  |  | Output 2.4 | 50113 | 4009.04 | 11525.99 | 11525.99 | 11525.99 | 11525.99 | 50113
Output 2.5 | 0% | 50% | 20% | 20% | 10% |  |  |  | Output 2.5 | 230196 |  | 115098 | 46039.2 | 46039.2 | 23019.6 | 230196
Output 3.1 | 10% | 70% | 20% | 0% | 0% |  | Outcome 3 | 1221132 | Output 3.1 | 13259 | 1325.9 | 9281.3 | 2651.8 |  |  | 13259
Output 3.2 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.2 | 24691 |  | 2469.1 | 17283.7 | 4938.2 |  | 24691
Output 3.3 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.3 | 13576 |  | 1357.6 | 9503.2 | 2715.2 |  | 13576
Output 3.4 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 3.4 | 13259 |  | 13259 |  |  |  | 13259
Output 3.5 | 100% | 0% | 0% | 0% | 0% |  |  |  | Output 3.5 | 14211 | 14211 |  |  |  |  | 14211
Output 3.6 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 3.6 | 18517 | 2222.04 | 4073.74 | 4073.74 | 4073.74 | 4073.74 | 18517
Output 3.7 | 0% | 50% | 25% | 15% | 10% |  |  |  | Output 3.7 | 1123619 |  | 561809.5 | 280904.75 | 168542.85 | 112361.9 | 1123619
Output 4.1 | 12% | 22% | 22% | 22% | 22% |  | Outcome 4 | 77212 | Output 4.1 | 34973 | 4196.76 | 7694.06 | 7694.06 | 7694.06 | 7694.06 | 34973
Output 4.2 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.2 | 17570 | 2108.4 | 3865.4 | 3865.4 | 3865.4 | 3865.4 | 17570
Output 4.3 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.3 | 24669 | 2960.28 | 5427.18 | 5427.18 | 5427.18 | 5427.18 | 24669
Output 5.1 | 20% | 20% | 20% | 20% | 20% | 5.2 | M&E |  | 22872 |  |  |  | 10292.4 |  | 12579.6 | 22872
Output 5.2 | 0% | 0% | 45% | 0% | 55% | 5.1 | PMC |  | 73041 |  | 14608.2 | 14608.2 | 14608.2 | 14608.2 | 14608.2 | 73041
[7 empty] | Total |  | 1,785,122 | [6 empty] | 1785123
[10 empty] | Total per year | 54511.17 | 811894.02 | 438594.62 | 278752.52 | 201370.67 | 1785123
[8 empty] | Actual total according to TOR is | 1785123
Note on U23: AGULABA AMBI, Helmine Egokom: again just like in the case of Madagascar the bidget is 1 dolar less

## Madgascar
| Y1 | Y2 | Y3 | Y4 | Y5 |  |  | Budget NEE ($) | Output | Budget NEE ($) | Y1 | y2 | y3 | y4 | Y5
Output 1.1 | 25% | 75% | 0 | 0 | 0 |  | Component 1 | 80960 | Output 1.1 | 25431 | 6357.75 | 19073.25 |  |  |  | 25431
Output 1.2 | 0% | 40% | 60% | 0% | 0% |  |  |  | Output 1.2 | 26455 |  | 10582 | 15873 |  |  | 26455
Output 1.3 | 0% | 30% | 20% | 30% | 20% |  |  |  | Output 1.3 | 29075 |  | 8722.5 | 5815 | 8722.5 | 5815 | 29075
Output 2.1 | 35% | 40% | 25% | 0% | 0% |  | Component 2 | 299905 | Output 2.1 | 5748 | 2011.8 | 2299.2 | 1437 |  |  | 5748
Output 2.2 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.2 | 8924 |  | 8924 |  |  |  | 8924
Output 2.3 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 2.3 | 8924 |  | 8924 |  |  |  | 8924
Output 2.4 | 8% | 23% | 23% | 23% | 23% |  |  |  | Output 2.4 | 48113 | 3849.04 | 11065.99 | 11065.99 | 11065.99 | 11065.99 | 48113
Output 2.5 | 0% | 50% | 20% | 20% | 10% |  |  |  | Output 2.5 | 228196 |  | 114098 | 45639.2 | 45639.2 | 22819.6 | 228196
Output 3.1 | 10% | 70% | 20% | 0% | 0% |  | Outcome 3 | 1214132 | Output 3.1 | 13259 | 1325.9 | 9281.3 | 2651.8 |  |  | 13259
Output 3.2 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.2 | 24691 |  | 2469.1 | 17283.7 | 4938.2 |  | 24691
Output 3.3 | 0% | 10% | 70% | 20% | 0% |  |  |  | Output 3.3 | 13576 |  | 1357.6 | 9503.2 | 2715.2 |  | 13576
Output 3.4 | 0% | 100% | 0% | 0% | 0% |  |  |  | Output 3.4 | 13259 |  | 13259 |  |  |  | 13259
Output 3.5 | 100% | 0% | 0% | 0% | 0% |  |  |  | Output 3.5 | 14211 | 14211 |  |  |  |  | 14211
Output 3.6 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 3.6 | 18517 | 2222.04 | 4073.74 | 4073.74 | 4073.74 | 4073.74 | 18517
Output 3.7 | 0% | 50% | 25% | 15% | 10% |  |  |  | Output 3.7 | 1116619 |  | 558309.5 | 279154.75 | 167492.85 | 111661.9 | 1116619
Output 4.1 | 12% | 22% | 22% | 22% | 22% |  | Outcome 4 | 74212 | Output 4.1 | 30973 | 3716.76 | 6814.06 | 6814.06 | 6814.06 | 6814.06 | 30973
Output 4.2 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.2 | 17570 | 2108.4 | 3865.4 | 3865.4 | 3865.4 | 3865.4 | 17570
Output 4.3 | 12% | 22% | 22% | 22% | 22% |  |  |  | Output 4.3 | 25669 | 3080.28 | 5647.18 | 5647.18 | 5647.18 | 5647.18 | 25669
Output 5.1 | 20% | 20% | 20% | 20% | 20% | 5.2 | M&E |  | 22872 |  |  |  | 10292.4 |  | 12579.6 | 22872
Output 5.2 | 0% | 0% | 45% | 0% | 55% | 5.1 | PMC |  | 73041 |  | 14608.2 | 14608.2 | 14608.2 | 14608.2 | 14608.2 | 73041
[7 empty] | Total |  | 1,765,122 |  | 53491.17 | 803374.02 | 433724.62 | 275582.52 | 198950.67 | 1765123
[10 empty] | Total per year | 53491.17 | 803374.02 | 433724.62 | 275582.52 | 198950.67 | 1765123
[7 empty] | Actual total from TR is | 1765123
1765123