FAO-GEF Project Implementation Report

2020 – Revised Template

Period covered: 1 July 2019 to 30 June 2020

Basic Project Data

General Information

| Region: | Latin America and Caribbean |
| --- | --- |
| Country (ies): | Ecuador |
| Project Title: | Conservation and Sustainable Use of Biodiversity, Forests, Soil and Water to Achieve the Good Living (Buen Vivir / Sumac Kawsay) in the Napo Province |
| FAO Project Symbol: | GCP/ECU/082/GFF |
| GEF ID: | 4774 |
| GEF Focal Area(s): | MFA (Biodiversity, Land Degradation, Sustainable Forest Management) |
| Project Executing Partners: | Decentralized Autonomous Government of the Province of Napo (NPG), Ministry of the Environment of Ecuador (MAE) |
| Project Duration: | Four years |
| Project coordinates: (Ctrl+Click here) | Province of Napo Latitude: S 0° 37' 44'' Longitude: W 77° 49' 53'' |

Milestone Dates:

| GEF CEO Endorsement Date: | 18–Jul–2014 |
| --- | --- |
| Project Implementation Start Date/EOD: | 9-Apr-2015 |
| Proposed Project Implementation End Date/NTE: | 31-Dic-2019 |
| Revised project implementation end date (if applicable) | 31-Oct-2020 |
| Actual Implementation End Date: | Non applicable |

Funding

| GEF Grant Amount (USD): | USD 2,628,283 |
| --- | --- |
| Total Co-financing amount as included in GEF CEO Endorsement Request/ProDoc: | USD 12,320,504 |
| Total GEF grant disbursement as of June 30, 2020 (USD m): | USD 2,541,965 |
| Total estimated co-financing materialized as of June 30, 2020 | USD 8,487,000 |

Review and Evaluation

| Date of Most Recent Project Steering Committee: | November 14, 2019 |
| --- | --- |
| Mid-term Review or Evaluation Date planned (if applicable): | September 2017 |
| Mid-term review/evaluation actual: | September – December 2017 |
| Mid-term review or evaluation due in coming fiscal year (July 2020 – June 2021). | No |
| Terminal evaluation due in coming fiscal year (July 2020 – June 2021). | No |
| Terminal Evaluation Date Actual: | October 2019 |
| Tracking tools/ Core indicators required | Yes |

Ratings

| Overall rating of progress towards achieving objectives/ outcomes (cumulative): | S |  |
| --- | --- | --- |
| Overall implementation progress rating: | S |  |
| Overall risk rating: | M |  |

Status

| Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 5th PIR (Final PIR) |
| --- | --- |

Project Contacts

| Contact | Name, Title, Division/Affiliation | E-mail |
| --- | --- | --- |
| Project Manager / Coordinator | Kelvin Cueva, Project Chief Technical Advisor | kelvin.cuevarojas@fao.org |
| Lead Technical Officer | Ana Posas Guevara, Agricultural Officer for Latin America and the Caribbean | ana.posasguevara@fao.org |
| Budget Holder | Agustín Zimmermann, FAO Representative in Ecuador | agustin.zimmermann@fao.org |
| GEF Funding Liaison Officer | Valeria Gonzalez-Riggio, FAO-GEF Coordination Unit Chris Dirkmaat, FAO-GEF Coordination Unit | valeria.gonzalezriggio@fao.org chris.dirkmaat@fao.org |

| Progress Towards Achieving Project Objectives and Outcomes (Cumulative) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project objective and Outcomes | Description of indicator(s) | Baseline level | Mid-term target | End-of-project target | Level at 30 June 2020 | Progress rating |
| Objective(s): Promote the conservation of biodiversity, the sustainable management of land, forests and water, through strategic investment of public resources, participatory environmental governance, incentive mechanisms, community-based ecotourism and biotrade in the Napo province. |  |  |  |  |  |  |
| Outcome 1.1: Participatory environmental governance has been improved | At least 6 PDOTs have established a formal commitment to incorporate environmental themes (sustainable forest management, ecological restoration, fostering sustainable agricultural practices - cocoa in the farm, naranjilla limpia, sustainable livestock - fostering community tourism in natural areas, fostering biotrade through biotrade venture projects bio-enterprises, ecosystem services in watersheds), for the conservation and sustainable use of natural resources. | No policies articulated between government levels. Low capacity of the Decentralized Autonomous Governments (GADs) to regulate the management of Natural Resources and agricultural use |  | The GADs have established a formal commitment to incorporate environmental criteria into 6 PDOTs (1 provincial PDOT, 5 municipal and parish PDOTs). | All 6 GADs: 1 Provincial, 5 cantonal and parish, analysis of their PDOTs updating processes, under the accompaniment of the National Secretariat "Plan Ecuador", for which they have the following tools that ensure the environmental criteria reports: -Ecological Economic Zoning (ZEE) Napo province map, -Proposal of the provincial PDOT of Napo (2019-2023), endorsed by the Provincial Planning Council. -Resolution of the Napo provincial chamber, for the modification of environmental principles, guidelines and criteria in the cantonal and parish PDOTs. -Indicators and guidelines in the provincial PDOT to guarantee: i) a culture responsible for the environment; ii) that ensures the provision of ecosystem services; iii) reduction of vulnerabilities caused by climate change; and iv) good environmental governance. | S |
| Outcome 1.2: Increased investments for the management of natural resources | LD-3 indicator PMAT iii. Increase in investments for integrated landscape management: 100% increase in investments for incentives in comparison to the baseline: US$ 952,000 | LD-3 indicator PMAT iii. Increase in investments for integrated landscape management: Investments in incentives by 2013: Socio Bosque program: US$ 400,000 Forest management: US$: 36,000 Reforestation: US$: 40.000 Total: US$ 476.000 | 60% increase in investments for incentives in comparison to the baseline: US$ 761,600 | 100% increase in investments for incentives in comparison to the baseline: US$ 952,000 | During the project management period, the SocioBosque program expanded incentives in Wamani and Akoki for an investment of US $ 531,657.74. The Productive Transformation Agenda of the Amazon (ATPA) for more than US $ 228,093.7 in Kits for the integral production of farms. In addition, the incentive of the Productive Development, Irrigation and Drainage Directorate of the Napo Provincial Government (Productive GAD) has improved the efficiency of investments through project management, for an approximate amount of USD 700,000 / year (approximate average 2015 to 2019). The Provincial GAD assumes the Irrigation and Drainage competence in 2012 and begins to receive economic resources in 2013, resources that have gradually increased and have remained stable between 2015 and 2019. | HS |
| Outcame 2.1: Production systems have incorporated good practices in the conservation and management of natural resources in 4 priority sites of the Napo province | LD 3. Indicator ii) Spatial coverage of integrated management practices of natural resources in the landscape: 1,720 ha with sustainable and culturally friendly intensification (120 ha of naranjilla, 400 ha of cocoa, 1,200 ha of livestock). | LD 3. Indicator ii) Spatial coverage of integrated management practices of the natural resources in the landscape: 250 ha of livestock under sustainability criteria; naranjilla limpia: 30 ha | 1032 ha with sustainable and culturally friendly intensification (72 ha of naranjilla, 240 ha of cocoa, 720 ha of livestock. | 1.720 ha with sustainable and culturally friendly intensification (120 ha of naranjilla, 400 ha of cacao, 1.200 ha of livestock). | In total, 1370 families (80 in naranjilla, 1200 in cocoa and 90 in silvopastures) have made progress in applying good practices in approximately 1,952.5 ha (22.5 in naranjilla, 1680 in cocoa and 250 in silvopastures), of which the greater coverage is applied by the partners of the Kallari, Wiñak and Tsatsayacu organizations. This is because these partners have managed to renew and to obtain the organic certification for the export of fine aroma national cocoa beans. | S |
|  | LD 1 indicator 1. iii) Area of productive systems with greater plant cover (conservation agreements): 1,764 hectares of forest conserved by producers of naranjilla (400 ha), cocoa (1,000 ha) and cattle (364 ha) through incentives. | LD 1 indicator – iii) Area of ​​productive systems with greater plant cover (conservation agreements): 0 | 1058 ha of forest conserved by naranjilla (240 ha), cocoa (600 ha) and cattle (218 ha) producers through incentives. | 1,764 hectares of forest conserved by producers of naranjilla (400 ha), cocoa (1,000 ha) and cattle (364 ha) through incentives. | We have signed individual conservation agreements with the Provincial Government of Napo that reach 1.47 ha in Sta. Rita and 3.18 ha in Cuyuja. At the community level, conservation agreements have been established with Pacto Sumaco with 52.44 ha; Santa Rita with 162.95 ha and Yanayaku with 300 ha. In early 2018, the Socio Bosque program expanded the area under conservation agreements in 340 ha with the Wamani community and in 642.92 ha in the Akoki territory. Total: 1502.96 ha | S |
| Outcome 3: The pressure on the forests of the Sumaco Biosphere Reserve has been reduced through the implementation of a strategy for Sustainable Forest Management (SFM) | As a direct impact of the project, the deforestation rate will not increase after 2014, remaining at 2,735 ha / year during the 4 years of the project. 15% reduction in deforestation rate through SFM and conservation agreements. | For the period 1990-2000, the deforestation rate reaches 1,682 ha / year. For the period 2000-2008, the rate registers 2,735 ha / year. Based on these historical deforestation rates for the Napo province, a historical reference level (as suggested by the IPCC) is proposed as the baseline for the project, based on the most conservative historical rate of 2,735 ha / year , which will be maintained for the 4 years of the project's validity. |  | As a direct impact of the project, the deforestation rate will not increase after 2014, remaining at 2,735 ha / year during the 4 years of the project. 15% reduction in deforestation rate through MFS and conservation agreements. | Based on official reports from the Ecuadorian Ministry of the Environment, the net deforestation rate for the Napo province in the period 2014 to 2016 averaged 2,310 ha / year and for the period 2016-2018 it reached an average of 2,267 ha / year. Both periods are below the reference level of 2,735 ha / year. These data allow verifying that the net rates for the period from 2015 to 2018 were reduced beyond the proposed goal of -3%, -6%, -10% and -15% progressively and respectively for each of the 4 years of project management. This important result of reducing net deforestation in the province of Napo constitutes the effect of multiple actions, both public policy, national and local programs and projects, development of productive incentives, economic cycles, etc., as well as the work displayed by the project. | HS |
|  | 1,689,959 Tons of avoided CO2eq emissions through forest protection and deforestation reduction. 59,709 Mg of CO2eq is kept sequestered by agroforestry systems and forest restoration. | With information provided by MAE, preliminary data estimates indicate that the emissions of the Napo province for the four years of the project's life could be 5,005,050 t CO2eq considering 125 t C / ha. Deforestation rate: 2,735 ha / year (period 2000-2008). Preliminary data from MAE indicate that the forests of the Napo province store 120,018,390.29 tons of carbon - 439,267,308.46 CO2eq-, 129.38T / ha carbon - 473.53 CO2eq. Forest conservation initiatives exist, but avoided net emissions have not been quantified. |  | Tons of avoided CO2eq emissions through forest protection and reduction of deforestation reach 1,689,959 Mg CO2eq, during the 4-year term of the project. Through the establishment of agroforestry systems and forest restoration processes, it is expected to achieve a carbon sequestration that reaches 59,709 Mg CO2eq. | Based on deforestation rates for the period 2015 to 2018, the avoided emissions reach the following values: Due to the reduction of the deforestation rate 817,095 Mg CO2eq. By conservation agreements in community forests 2,713,095 Mg CO2eq. By forest conservation agreements around agricultural systems 687,604 Mg CO2eq. Total avoided emissions: 4,217,795 Mg CO2eq; which represents 250% of the established goal. The improvement of carbon sequestration, based on the areas under agroforestry and silvopastural systems established, maintained and managed with the support of the project, is estimated at 21,770 Mg CO2eq. Due to advances in forest restoration processes, around 36,220 Mg CO2eq are sequestered and maintained. Total sequestered 57,990 Mg CO2eq, which represents 97% of the established goal. | HS |
| Outcome 3.1: Conservation and sustainable use of biodiversity and improved livelihoods through the promotion of tourism and bio-commerce. | 1,000 ha of forests conserved through conservation agreements and designated to community tourism and sustainable bio trade practices in the community or private properties. | 0 | 600 ha of forests conserved in (community or private) lands through conservation agreements. | 1,000 ha of forests conserved in (community or private) lands through conservation agreements. | There are conservation agreements in community forests signed between the Oyacachi and Runashito bio-enterprises with the Napo Provincial Government, which covers the following areas: Oyacachi 5000 ha and Runashito 900 ha. Total: 5,900 ha, which represents 590% of the proposed goal. | HS |
|  | 10% increase in the current average income of 200 producers (100 women). | Based on the socioeconomic study of the families of producers and members of tourism and bio-commerce organizations, for 2016 a net income was estimated, reaching between US $ 600 to 750 / year; and between US $ 50 and 63 / month. | 6% increase in the current average income of 100 producers (70 women). | 10% increase in the current average income of 200 producers (70 women). | To estimate the socioeconomic effect of the project, between December 2019 and March 2020 a detailed valuation study was carried out applied to bio-enterprises in the value chains, tourism and bio-commerce. In general, a level of increase in the income of bio-enterprises was established above 27% (doubling in some cases), which benefits 1,980 associates, of whom more than 50% are women (990 women aprox). More significant income and with relative greater regularity correspond to the most consolidated ventures. To reinforce the strengthening and sustainability of the value chains of bio-enterprises in Napo, the process of technical accompaniment and cooperation has been complemented with the projects of Mechanism for Forests and Farms (FFF) and Climate Smart Cacao that works directly with the Napo cocoa entrepreneurship consortium, both projects are implemented by FAO. | HS |
| Outcome 4.1: Implementing the project based on a "results-based management" approach and facilitating the application of lessons learned and good practices in future actions | Project implemented based on results-based management. |  | 82% progress in achieving results. | Results of the project have been achieved and prove sustainability. | 17 of the 19 products of the project have been completed 100%, remaining to fulfill the endorsement of the Ministry of Economy and Finance for the constitution of FODESNA and its pilot phase; as well as the publication of the systematization of the process, experience and lessons learned from the project. Based on the different elements of the project's monitoring system, an overall progress of 97.6% is estimated. | S |

Action plan to address MS, MU, U and HU rating

| Outcome | Action(s) to be taken | By whom? | By when? |
| --- | --- | --- | --- |
| - | - | - | - |

Progress in Generating Project Outputs

| Outputs | Expected completion date | Achievements at each PIR |  |  |  |  | Implement. status (cumulative) | Comments. Describe any variance or any challenge in delivering outputs |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR |  |  |
| Output 1.1.1 Participatory inter-institutional strategy for the management of natural resources has been designed, implemented and monitored | Q4 4Y | Maps of institutional stakeholders related to the Protected Areas Committee and Forestry Committee (Mesa de Áreas Protegidas and Mesa Forestal) and the actions of the Planning Council of the Province have been developed | So far, through 4 inter-institutional coordination meetings, and by resolution of the provincial chamber of Napo, the process of expanding the SUMACO biosphere reserve (RBS) to the entire provincial territory has begun:a process that sets an inter-institutional management of Natural Resources based on the planning and management of the GADs linked to the MAE and other stakeholders. | There is a comprehensive document for the expansion of the transition area of the Sumaco biosphere reserve (RBS), which has been shared with institutional actors in the province of Napo and Orellana. This proposal has been discussed with the MAE representative for biosphere reserve issues and with UNESCO in Ecuador. Adjustments are currently being made to the document, for its formal presentation to the MAE and UNESCO, and to begin the process of integration of the RBS inter-institutional committee. Parallel to the processes of expansion of the RBS, constitution of FODESNA and updating of the Provincial PDOT, a consultancy will be developed for the integration of the natural resources management strategy, whose main inputs (axes of the strategy) have already been consolidated with component 1 of the project. | The process of convening and selecting the consultant for the elaboration of the inter-institutional strategy for the management of Napo's natural resources has been developed. The strategy articulates three elements of provincial planning and management: the updated PDOT 2019 - 2023, the management committee of the Sumaco RBS Biosphere Reserve and the financial mechanism of FODESNA. | There is the strategy of the inter-institutional coordination committee for the management of the Sumaco Biosphere Reserve (RBS), which includes a context of the state of natural resources; the actors map; the management model and guiding framework The strategy has the endorsement of the Napo provincial chamber and the MAE, through the document and a new management model established in the process of expanding the transition area of the Sumaco biosphere reserve (RBS). | 95% | The statute and operational plan are in place for the management of the coordinating committee led by the management of the Sumaco National Park, Napo - Galeras, the Provincial Government and local enterprises. Approval is expected of the Ministry of the Environment (MAE) of the new statute for its formal application. |
| Output 1.1.2 The GADs have established a formal commitment to incorporate environmental criteria in 6 PDOTs (1 provincial PDOT, 5 municipal and parish PDOTs). | 4Y | -Integration of the work platform with the planning directorates of the provincial GAD, the five municipal GADs (Archidona, Quijos, Chaco, Tena) and the Parish Council of Cuyuja. -Proposal of a PDOTs assessment matrix based on the guidelines of SENPLADES, the COOTAD competences and the new Law on Territorial Planning, Land use and management. | -A comprehensive evaluation methodology has been developed for the inclusion of environmental criteria in PDOTs. -The environmental assessment process of the Provincial PDOT of Napo has begun, as input for its update in the second half of 2017 -The process of selecting a consulting team for the development of the province's economic ecological zoning map has begun. | The process of updating the Napo provincial PDOT is progressing, with an emphasis on integrating environmental criteria into provincial management indicators, goals, projects, and regulations. There are guidelines agreed with the GADs (cantonal and parish), for the integration of environmental criteria in the updating processes of the PDOTs to be carried out in 2019 (period established by SENPLADES). The Ecological Economic Zoning map of the Napo province is available; a spatial input for territorial planning that facilitates the incorporation of environmental criteria in the PDOTs. | The updated integral document of the Provincial PDOT of Napo 2019-2023 has been generated, in which principles, guidelines and environmental criteria are integrated. The Provincial Assembly of the Citizen Participation System has endorsed this document. Municipal and parish GADs agreed on guidelines for the integration of the principles, guidelines and environmental criteria in the processes of updating the PDOTs to be carried out in 2019 (period established by SENPLADES). | There is a comprehensive document updating the Napo provincial PDOT for 2019-2023, in which it incorporates environmental principles, guidelines and criteria (at the level of policies, indicators, goals, projects and budgets). With the participation of all the GADs represented in the Napo provincial chamber, a resolution was generated that recommends the incorporation of environmental principles, guidelines and criteria in the updating processes of the cantonal and parish PDOTs, currently facilitated by the national secretariat of planning "Plan Ecuador". | 100% | The secretary "Planifica Ecuador" leads the inter-institutional group where the updating process of the cantonal and parish PDOTs for the period 2019-2023 is accompanied. |
| Output 1.1.3 2 Committees (Protected Areas and Sustainable Livestock) created and functioning | 4Y | The Protected Areas (PA) Committee has been created and, is being legalized in the MAE as a PA Management Committee, whose main function is to articulate, coordinate and define guidelines for the integrated management of PAs in the province. The application of a stakeholder analysis matrix has begun to create a Sustainable Livestock Committee. | - Progress has been made in the execution of the 2017 work plan of the thematic coordination spaces of the protected areas committee, the themes that have been discussed are environmental education; tourism in protected areas; and forest conservation and management. -A rapid analysis and diagnosis of the management state of the provincial agrarian assembly of Napo has been conducted, and specifically of the Livestock Thematic Commission, in order to establish a strengthening work plan as a space that brings together all the livestock organizations of the province. | The management process of the protected areas committee in the Napo province continues. The expansion process of the RBS transition is being validated. In this sense, coordination spaces have been developed in Napo and Orellana. On the other hand, the process of accompanying the consultative committee and Livestock Producer Network of the upper part of the Napo province has begun. This has been made to facilitate promoting the application of good practices in the management of dairy cattle, a process that is coordinated with the MAG and the Climate-Smart Livestock Project PGCI of MAE-MAG-FAO-GEF | - Through the Protected Areas (PA) Committee in Napo province, the process of extending the transition area of the RBS, forest restoration processes and the implementation of co-management plans has been validated. Together with the Climate-Smart Livestock –GCI project (MAE-MAG-FAO-GEF) has been accompanying the space of the consultative committee and network of breeders of the upper part of the Napo province to facilitate the promotion of the application of good practices in the management of dairy cattle, a process that is coordinated with the Provincial Directorate of the MAG. | The inter-institutional coordination committee remains active for the management of the Sumaco Biosphere Reserve (RBS), which is a space for co-management of the protected areas of the province of Napo, led by the MAE, GADs and the enterprises associative. Along with the Climate-Smart Livestock Project PGCI of MAE-MAG-FAO-GEF , it accompanies the space of the advisory committee and network of ranchers of the upper part of the province of Napo, to facilitate the promotion of the application of good practices in the dairy cattle management; process that is coordinated with MAG´s Provincial Directorate. | 100% | The inter-institutional coordination committee for RBS management is established as the space to support participatory management of protected areas and define management guidelines for sustainable production systems such as livestock. |
| Output 1.1.4 Stakeholder capacities have been built in an integrated manner with a natural resources governance approach. | 4Y | A capacity building strategy has been structured for decision makers, GAD technicians and leaders of local organizations. | In the development of the Napo Aprende, Emprende y Protege (Napo Learns, Undertakes and Protects) program, more than 104 technicians of the provincial GADs have participated in the five technical training courses, and more than 58 leaders/decision makers (Prefect, Mayors and Parrish Committee Presidents) participated in the two seminars on sustainable development and Natural Resources-based economy. | More than 110 technicians from provincial GADs have completed the technical updating process developed in eight courses on territorial planning and Natural Resources governance topics. More than 60 leaders/decision makers (Prefect, Mayors and Parrish Committee Presidents) participated in three seminars on sustainable development, bio-enterprises and Natural Resources-based economy. The training process of 70 community leaders has begun. Training is on the development of community learning scenarios on good agricultural production practices, including the development of a Farmer Field School ECA to manage cacao. | 165 technicians from the province GADs, public and private entities have completed the process of technical updating developed in eight courses on topics of territorial organization and natural resources governance. More than 25 leaders and decision-makers (Prefect, Mayors and Parish Boards Presidents) participated in three seminars on sustainable development, bio-entrepreneurship, economics of natural resources and Agroecology. A completed training process for 83 community leaders in topics such as the development of community learning scenarios on good agricultural production practices, including the development of an ECA (Farmer Field School) for cacao management. Total: 273 people trained | In total 270 people, including 165 technicians, more than 25 decision makers (Prefect, Mayors and Presidents of Parish Boards) and 83 Community Leaders have been trained in the development of the capacity-strengthening program that included technical update courses, seminars and national and regional congresses in partnership with universities. As well as, the development of practical workshops, under andragogy methodologies of learning directed to leaders and community leaders. | 100% | The training process for technicians and community leaders had the academic endorsement of the Graduate School and Continuing Education of the Amazon State University (ASU). Other entities that have participated in the capacity-building program are the Consortium of Provincial Governments of Ecuador CONGOPE; the Association of Municipalities of Ecuador AME (online platform), the IKIAM Regional University, the IGM Military Geographical Institute, the Ecuadorian Space Institute IEE, among others. |
| Output 1.1.5 Information management system for the planning and management of natural resources generated and administered by MAE and GADPN | 4Y | We have worked on an analysis of the information systems currently in operation, with the available information and the architecture and requirements for the design of the system. The ToR have been validated to hire a computer consultant to start the process of generating the Natural Resources information system. | The architecture of the information system is ready. It has been generated based on the agreement between the GADPN and the Zonal Node of SENPLADES, with the contribution of CONDESAN and EcoCiencia. - Progress has been made in the development of the information system, the interactive map - geo-viewer in a laboratory website (www.infonapo.org) -The information system interacts with the National Information System of SENPLADES, the Environmental Information System of the MAE and MAGAP's Information System, and other | - The information system allows the distribution of geographic information, through the GeoServer, and statistical information on the various topics of Natural Resources management in the Napo province. The information can be found here: http://infonapo.org/assets/pdf/Plan-comanejo-ACOKI-2017.pdf The ZEE and more information can be found here: http://infonapo.org - For a greater functionality of the system, a server has been equipped in the data centre of the Napo Provincial Government, and information management and access manuals have been developed. - Capacities have been strengthened in the generation of the spatial data infrastructure (IDE), with all the information management stakeholders of the Napo province. | The integrated information system with the following features: -A viewer configured and operating, -A structured geographic database based on IGM guidelines -One numerical alpha database (documentary) configured in the virtual library, -An metadata manager operating, -A public inter-sectorial web platform developed and updated -Technological equipment of high range that strengthen the technological infrastructure of the GAD Provincial -User and technical manuals of each solution developed. | An interdisciplinary team operates the natural resources information system from the Technology, Planning and Production departments of the Napo GAD. The information system was established with the geographic and environmental information base for updating the Provincial PDOT, the Ecological Economic Zoning (EEZ), the development of co-management plans in protective forests and other planning instruments. | 100% | An exchange space was developed between the Planifica Ecuador Secretariat, the Provincial Government of Imbabura, and the technical team of the Provincial Government of Napo, so that the information system of the NRNN becomes the main structure of the Local Information System (LIS) of Napo province. |
| Output 1.2.1 6 incentives strengthened and articulated, and active for the conservation and sustainable use of biodiversity | 4Y | A diagnosis has been generated of the six (6) incentives to support the project, defining an articulation plan and establishing technical agreements with the Productive Transformation Agenda of the Amazon ATPA and the productive GADPN for its application, development and innovation of their proposals methodological and technological at the farm level in the areas of project attention. | -The pilot process has been generated and the validation of new protocols and feasibility, planning, monitoring and evaluation matrices of the incentives of the Productive GAD mechanism has begun, for its application at the sustainable associative productive enterprises level. -The new proposal of the Productive GAD establishes an institutional and operational mechanism for the mapping, coordination and complementariness with all the incentives in the province, including national incentives such as SocioBosque, ATPA, the National Restoration Plan, commercial crops and others. | The process of expanding the conservation areas of the Socio Bosque incentive in the Akoki and Wamani territory has been supported, including the training of community inspectors. The application of the newly integrated matrix of the project cycle in the Productive GAD mechanism has been strengthened, as well as the structuring of the entity in charge of monitoring the effects of the incentives. There are a tool and space available for the coordination of national and local incentives of the Napo province, available at the Directorate of Production, Irrigation and Drainage of the Provincial GAD. | The updating of life plans in Runashito and Wamani has been strengthened for SocioBosque program incentive investments, including the co-management plans in protective forests. In addition, the management and training spaces of the regional and national network of Socio Bosque partners were supported. The management of the Productive GAD has been strengthened through the application of the project cycle matrix and the automated archive system (using the Open Foris Software). The database of information and articulation of national and local incentives of the province of Napo was updated by the Provincial GAD. | Support was given to the process of implementing life plans in the Runashito, Wamani, Akoki and PKR communities for investments in the SocioBosque program incentive. The application of incentives for farm improvement plans was coordinated with MAG, under the ATPA methodology. The implementation of incentive projects of the Directorate of Productive Development of the Provincial GAD was monitored, through the application of the project cycle matrix and the automated filing system (applying the Open Foris Software). Three incentives in Napo have been strengthened: Socio Bosque Conservation; Productive Transformation Agenda of the Amazon (ATPA); and Productive GAD, through which the project's goals have been achieved. Other national incentives such as Socio Bosque Restauration; Concurrent National Plan; and Plantations for commercial purposes were deactivated during the project execution period, so the project management focused on the three active incentives; which was reported in the PPR, PIR and in the mid-term evaluation of the project. | 100% | The implementation of the Runashito life plan was coordinated through a project financed by the Forest and Farm mechanism (FFF), with an emphasis on the development of the Humo community tourism initiative. |
| Output 1.2.2 Provincial Sustainable Development Fund Created and operational | 4Y | A workshop is being organized for the experience exchanges in fiduciary funds creation for environmental management, including the socialization of the pre-feasibility analysis of the provincial development fund. Furthermore, there are guidelines in place for the ToR for hiring a consultancy service for the creation of the fund. | Based on the process of delegation, quotation and national call for the contracting of the FODESNA consultancy, the selection process of the consulting firm has initiated to develop the feasibility analysis, constitution and pilot phase of FODESNA. The phases, outputs and activities proposed for the creation of FODESNA have been established based on the systematization of the experiences and processes developed by other environmental funds in the country. The proposal of the new cycle, protocols and matrices of projects to be supported by the mechanism of incentives of the Productive GADPN, is based on the guidelines of the investment programs to be established with the FODESNA, in order to advance with a robust proposal that will be fostered by FODESNA. | The validated FODESNA feasibility study is available, which defines the guidelines to be followed in the process of constituting the trust. Because of political decision, the Provincial Government of Napo will be the main constituent of FODESNA, with a seed contribution of one hundred thousand dollars in 2018 and two hundred thousand dollars in 2019, which will be maintained as a recurring resource through an ordinance. This fund will count with the investment of one hundred thousand dollars by the project. The possibility of the FODESNA being part of the FIAS (Sustainable Environmental Investment Fund) is being analyzed or, failing that, having FODESNA work directly with the CFN National Financial Corporation, for which the legal document for the fiduciary contract, is being prepared. | There are the resolutions of the Napo provincial chamber so that the Provincial GAD is the main constituent and transfers financial resources to FODESNA (initial USD 210,000). Likewise, the financial mechanism has been socialized to the Organizations of producers of Napo to integrate into its constitution. There is a preliminary endorsement from the Ministry of Economy and Finance MEF to advance the process of preparing the trust contract with the National Finance Corporation CFN. The Provincial Government of Napo has hired the CFN for the constitution and administration of FODESNA, currently progress is being made in the preparation of the trust contract, its review and validation. | The FODESNA trust memorandum / contract has been presented to the Ministry of Economy and Finance (MEF) for its endorsement; which has been reviewed by the Sub-secretariat of Fiscal Relations and the additional enabling documentation for the guarantee has been prepared. The provincial ordinance of FODESNA has been officially issued to facilitate the joint management of the Trust from the provincial, cantonal and parish GADs. There is the FODESNA strategic plan, operating manual, administrative manual and project format for financing. | 75% | The FODESNA process has passed under the change of three administrations of the Napo Prefecture, which has delayed the progress of the process. In order to complete the project support process, two parallel processes are being advanced: i) accompaniment of the administrative process of endorsement and constitution of FODESNA and ii) developing a pilot project for adjustments of the manuals and FODESNA management experience, including the management of first results for their socialization with the map of possible new constituents and contributors. |
| Output 2.1.1 3 technological packets of good practices for cacao, naranjilla and livestock, and conservation agreements signed with small and medium producers | 4Y | There are agreements and community plans for the application, adaptation and innovation of good practices for the production of cocoa, naranjilla and livestock. Extension and advisory activities are being developed through the participatory preparation of comprehensive farm plans. Up to now, good production practices have been applied in Naranjilla: 50 families, 12.5 ha. Cacao: 72 families, 72 ha. Livestock: 40 families, 120 ha. Total: 204.5 ha. | -3 technological packets systematized and applied through farm improvement plans, are based on standards of organic certification, integrated management of the MIC crop, and clean production. So far, demonstrative scenarios have been consolidated in the application of good production practices in: Naranjilla: 50 families, 12.5 ha. Cacao: 100 families, 100 ha. Livestock: 40 families, 120 ha. Total: 190 families and 232.5 ha. The following has been promoted through the management of direct partners: Naranjilla: 30 families, 10 ha. Cacao: 500 families, 500 ha. Livestock: 50 families, 130 ha. Total: 580 families and 640 ha. The farm management plans are developed based on the methodological proposal of incentives at the farm level of the ATPA Amazon Productive Transformation Agenda of MAGAP. | Technological packets of good practices for cocoa, naranjilla and livestock have been systematized, implemented and monitored. This process includes the generation of educational-communication material (infographics and flipcharts) for the training of producers. In total, 770 families (80 in naranjilla, 600 in cacao and 90 in silvopastures) have progressed in applying good practices in approximately 1112.5 ha (22.5 in naranjilla, 840 in cocoa | The application of technological packages of good practices for cacao, naranjilla and livestock is monitored through the Open Foris system. In total, 1370 families (80 in naranjilla, 1200 in cacao and 90 farmers) have been applying good practices, approximately 1952.5 ha (22.5 in naranjilla, 1680 in cacao and 250 in silvopastures). The good practices applied are articulated with organic certification standards (for the European Union, United States, Japan) reached by local cacao organizations, and with the implementation of practices established in the provincial ordinance of the Amazonian Chakra system. | 3 technological packages of good practices for cocoa, naranjilla and livestock production have been designed, implemented and monitored, which are systematized in 6 infographics and 3 flipcharts for the application processes and continuous training for producers of Napo The good practices applied are articulated with the organic certification standards (for the European Union, the United States, Japan) reached by the local cocoa organizations, and with the standards and good practices established in the provincial ordinance of the Amazon Chakra system. 2 families have established conservation agreements individually in Santa Rita and Cuyuja with the Provincial GAD. At the community level, conservation agreements have been established with the Sumaco Pact, which corresponds to 73 families; in Santa Rita with 147 families and with Yanayaku 40 families. Through the expanded conservation agreements with the Socio Bosque program in Wamani it corresponds to 17 families and in the Akoki territory with 123 families. Total: 402 families with conservation agreements (90 naranjilla, 311 cocoa and other products; 1 livestock). | 100% | The process of implementation and promotion of good agricultural production practices has been coordinated with the technical teams of local producer organizations, the Production Directorate of the Napo Provincial Government, the Ministry of Agriculture MAG, ATPA, the Institute of Agricultural Research INIAP, GIZ, Maquita Cuchunchi, FECD, PROAmazonia and other institutions. |
| Output 2.1.2 2 updated, implemented and monitored value chain plans for cacao and naranjilla | 4Y | There is a map of all the actors related to the MFS which are part of the provincial Forestry Roundtable, including an analysis of the regulations that contribute to the sustainable forest management of the MAE, and the definition of a proposal of key articulating and thematic lines to structure the provincial MFS strategy | The implementation process of the cocoa value chain plans continues, in the Tsatsayacu, Wiñak and Kallari organizations, and the approaches for the strengthening of Amanecer Campesino. Traceability tools are strengthened with compliance with organic certification standards, and obtaining sanitary registrations for processed products (chocolate paste and chocolate bars). In total, 147 members of the Tsatsayacu organization, 257 members of Wiñak, 700 members of Kallari and 80 members of Amanecer Campesino are directly and indirectly supported. Total: 1,184 cocoa partners. The creation of the company and the naranjilla transformation plant directly benefits 33 members of the Sachalara organization and 70 Asoprovisun members. Total: 103 partners. The strengthening process has allowed reaching marketing agreements with processing companies and stores in the USA (Whole Foods), Italy (Venchi), Switzerland (Max Felchlin), Canada (Choco Sol) and Japan (Nutrition SA) and an export volume of 120 tons of cocoa beans (10.5 containers). It has been possible to sell 12.5 tons at an organic product price In the national market, Progress was made in the structuring of the naranjilla value chain plan, including the creation of the local juice and pulp processing and marketing company, in the Sachalaran association. In addition, the provision of equipment of the naranjilla processing plant is supported in coordination with the Provincial Government of Napo | Progress is being made in the implementation of the cocoa value chain plan, through the Napo cocoa consortium (Tsatsayacu, Wiñak and Kallari and Campesino Amanecer). The processes and traceability have been improved for the collection, drying, transformation and commercialization in the national and special markets abroad. International stores have been selected for holding contracts for the sale of cocoa. These are the following: USA (Whole Foods), Italy (Venchi), Switzerland (Max Felchlin), Canada (Choco Sol), Japan (Nutrition SA) and France (EQUACACAO S.A.S). In coordination with the Provincial Government of Napo and the Cantonal Government of Archidona, final arrangements have been made for the Naranjilla pulp, juice storage and processing plant. This plant will allow the selling of the finished naranjilla products under commercial agreements with local and national stores in considerable volumes. It will also facilitate the improvement of sanitary registrations and the delivery volumes of the producers of the Sachalaran, Asoprovisum and Asoproagriwi organizations. Currently, pulp and naranjilla juice are being sold at the local Hatun Sumaco fair, at the MAG Fair in Quito, and at stalls in the city of Tena. | Quality standards (certification), volumes and export processes of cacao are accomplished through the Napo Cacao consortium: Tsatsayacu, Wiñak and Kallari. There are tools for cacao traceability. The application of the accounting administrative system "SAC" in cacao organizations, with support of CEFA and GIZ, for improving their administrative efficiency. For 2019 harvest, the cacao sales contracts are maintained with: USA (Whool Food), Italy (Venchi), Switzerland (Max Felchlin), Canada (Choco Sol), Japan (Nutrition SA) and France (EQUACACAO S.A.S). The final restoration is completed in the pulp, juice and other Naranjilla derivatives collection and transformation plant. The inspection has been carried out and the procedures for the operating permit have been initiated in the National Agency for Health Regulation, Control and Surveillance (ARCSA). A training process for the management of the naranjilla transformation plant has begun, as well as for juices, pulps and dehydrated fruits process. In addition, a process packaging, labels and product presentations analysis has been developed for local and national commercialization. | The implementation of the cocoa value chain plan has been completed, which includes compliance with quality standards, strengthening of administrative and traceability systems. Throughout this period, national sales contracts have been maintained with PAKARI, Ecuatoriana de Chocolates, Salinerito, Tulicorp, Cofina and others, and internationally at stores such as Whool Food (United States), Venchi and Giraudi (Italy), Max Felchlin (Switzerland), Choco Sol (Canada), Nutrition SA (Japan) and EQUACACAO S.A. (France), etc. The naranjilla value chain plan is in place, which has allowed the development of the capacity building process in the areas of product registration and traceability, food quality and safety standards, business administration and management, occupational and industrial safety, good manufacturing practices (BPM), management of health records and branding, among others. The skills of managers, 33 partners, and more than 20 youth in the organization have been improved. Currently, the marketing of naranjilla, arazá and other Amazonian fruit pulp is carried out at the plant's store, at the traditional Guamaní fair, at provincial and national promotion fairs, and by order or direct distribution in stores, restaurants and to officials of institutions in the city of Tena. | 100% | Letters of agreement between the forest and farm mechanism (FFF) and the communities of Sacha Larana, Wiñak and Tsatsayaku are executed to strengthen the production, transformation and marketing processes of their products. The implementation of the Climate Smart Cacao project has begun, to strengthen capacity-building processes, production under the climate change approach and the expansion of the cocoa and its derivatives commercialization process. |
| Output 2.2.1 Provincial strategy for a concerted, implemented and monitored MFS | 4Y | There is a map of all the actors related to the MFS which are part of the provincial Forestry Roundtable, including an analysis of the regulations that contribute to the sustainable forest management of the MAE, and the definition of a proposal of key articulating and thematic lines to structure the provincial SFMS strategy. | In several inter-institutional workshops with representatives of various entities related to the forestry sector of the province of Napo, the sustainable forest management strategy proposal has been structured, based on national policies and regulations, the competences of the local governments, and the interests and needs of local actors. Several guidelines established in the provincial SFMS are being developed based on the actions of the inter-institutional space partner entities. | There is a comprehensive version of the Sustainable Forest Management Strategy, which is being executed through the actions of all the stakeholders related to the forestry sector in the province of Napo. As a management model for the follow-up and monitoring of the implementation of the MFS strategy, the indicators and goals of the strategy are being articulated with the updating process of the PDOT of the province of Napo. The Ecological Economic Zoning map and the new National Environmental Code are new inputs that have strengthened the SFMS. | The Provincial Strategy of Sustainable Forest Management has been developed with the support from all the actors related to the forestry sector in the Napo Province. To facilitate the monitoring and evaluation process, the EMFS is articulated with the goals, indicators and actions detailed in the new proposal of PDOT for the Provincial GAD 2019 – 2023. As a model of management and institutional sustainability, SFMS will be integrated into Napo inter-agency strategy for natural resource management. | The SFM Strategy includes the programs, processes and action plans developed by each of the actors in the Napo forest sector, which were aligned to a vision, objectives, areas and agreed strategic guidelines, which frame a practical forest management process and exercised from the actions, resources and powers of each of the actors. To facilitate the monitoring and evaluation processes, the SFMS is articulated with the goals, indicators and actions of the new proposal for the PDOT Development and Territorial Planning Plan of the Provincial GAD 2019 – 2013. As a management and institutional sustainability model, the SFMS has been included in the management model and guiding framework of the Strategy of the Inter-institutional Coordination Committee for the Management of the Sumaco Biosphere Reserve. | 100% | The SFM Strategy is managed from the management model of the Inter-institutional Coordination Committee for Sumaco Biosphere Reserve Management, and its operation from the action plans of each of the actors in the Napo forest sector. |
| Output 2.2.2 23 co-management plans for the Protective Forests of La Cascada, Cerro Sumaco and Colonso drafted, implemented, and monitored (40.927 ha) | 4Y | Agreements have been defined and rapid diagnoses have been developed on organization, land tenure, planning tools, among others of the prioritized communities, as input for the preparation of Co-management Plans in the Colonso and Cerro Sumaco protective forests. In addition, consultant teams are being selected for the participatory development of the first 7 co-management plans that cover approximately 5,220 ha in Cerro Sumaco and 140 in Colonso. Total: 5,360 ha | Through the development of a participatory process of diagnosis, zoning and planning, three co-management plans have been created for the Nueva Libertad community in the Colonso Protective Forest, María Antonieta community and Akoki territory (which includes 5 communities) in the Sumaco Protective Forest. The Ministry of the Environment has legally approved these plans and programming of their implementation and monitoring has begun. The participatory process of updating the co-management plan of the community of Wamani, which covers a territory of 5054 ha, is progressing. The minutes of approval of the Kichwa Rucullacta PKR People's Assembly have been approved to initiate the drafting of the co-management plan for the natural resources of its territory, which encompasses 41,888.55 ha. | Progress is being made in the process of implementing the co-management plans for the Nueva Libertad community in Colonso PF, María Antonieta community and Akoki territory (which includes 5 communities) in PF Sumaco. Plans that encompass 9,890.36 ha. The updating and implementation of the Wamani co-management plan that includes 5,054 ha. is being supported. The plan for the co-management of natural resources in the Sumaco Protective Forest territory corresponding to the Kichwa People of Rucullacta PKR has been completed. It includes 17 communities and covers an area of 41,888.55 ha. In addition, a process of socialization of the different co-management plans has been carried out with the local governments and public and private institutions. In total, there are co-management plans for 25 communities, total approximately 56,832.94 hectares. | The process of monitoring the implementation of co-management plans in protective forests has been carried out in Nueva Libertad, María Antonieta, Akoki territory, PKR territory and Wamani, which includes 25 communities and a territory of approximately 56,832.94 he has. This monitoring process has been carried out with the support from the Ministry of the Environment, the Provincial Government, Cantonal and Parish, NGOs and cooperation entities. In order to integrate the dossier of the co-management plans approved by the environmental authority, the evaluation reports have been sent to MAE. | The process of accompanying the implementation and monitoring of co-management plans in protective forests has been continued: Nueva Libertad, María Antonieta, Akoki territory, PKR and Wamani territory, which includes 25 communities and territories that add up to approximately 56,832.94 ha. At the request of the MAE and thanks to the results achieved, the updating and delivery to the MAE of the documents of the co-management plans of the Chalwayaku, Sumaco Volcano, Jatun Sumaco and Wawa Sumaco communities was supported. The process and results of the management of co-management plans developed with the MAE have been socialized to different cooperation institutions and initiatives to develop co-management plans in the Ecuadorian Amazon. | 100% | Through the co-management plans, the territorial management units and executives have obtained support and the application of new projects from different sources of financing (GADs and Cooperation) to advance in the implementation of the co-management plans. |
| Output 2.2.3 2,500 ha restored with techniques of analogue forestry, reforestation or natural regeneration under conservation agreements and incentives. | 4Y | The areas suitable for restoration on community and private lands have been defined, based on community information, the farm plans and the agreements of the restoration program of the MAE. As a complementary action, information has been gathered on the experiences of natural and assisted restoration in the province, for the application of successful methods through the assistance of the project. The general criteria for the development of passive or active restoration activities are protection and conservation priority, community or family interest, land tenure, the degree of alteration and ecological conditions, the persistence of disturbances and costs. The areas identified by the national restoration program amount to 845 ha. | A map of areas for restoration in Napo Province elaborated, considering the biophysical and accessibility criteria established by the technical team of the project and the experiences of MAE, MAGAP, FONAG, NCI and others. The methodological and technological manual (good practices) for active and passive restoration in family and community properties have been systematized. 40 ha of active restoration and 8.5 ha of passive or natural restoration have been established in areas of the ecological easement, in community territories, as demonstration and learning scenarios, for their promotion through the local governments and other restoration programs of the Province. The Environment Directorate of the GADPN through student and communal work campaigns, including producers on the farms, has managed to establish active and passive restoration processes in 289.89 ha | Cooperation agreements with the local governments of Chaco, Archidona, Arosemena Tola, Quijos and Hatun Sumaco are signed in order to advance the process of forest restoration in the prioritized sites of Napo province. Under these agreements, 285.11 hectares of active restoration and 37.43 hectares of passive or natural restoration have been established in areas of ecological easement, both in the community and private properties. It goes from the collaborative work with the Directorate of Environment of the GADPN, to the student and communal work campaigns. It also includes producers on the farms. This process has helped to establish active and passive restoration processes in 289.89 ha. These scenarios are monitored by the project. Total: 612.34 ha. | 500 ha of active forest restoration processes have been implemented and monitored, including 2,503 ha of passive restoration. In addition, 289.89 ha of active and passive restoration scenarios were carried out by the Provincial GAD Environment Directorate. Total: 3292,89 ha Meetings to coordinate, information delivery, visits to areas, training and development of monitoring activities have been held with professors and students of the Regional University IKIAM, who will continue to monitor the post-project restoration scenarios. | The follow-up and monitoring process of 3,292.89 ha of active and passive restoration has been continued in coordination with the Environment directorates of the provincial GAD of Napo, cantonal GADs and various Parish GADs. This process include a contest of university professors and students in the Ikiam Regional University. The new proposal for MAE´s National Restoration Plan considered the methodology and results of the project's forest restoration process. | 100% | In total, 396 people participated in the practical processes of restoration and training, of which 62.6% were men and 34.4% women and 3% corresponded to representatives, directors of organizations such as associations, communities or local GADs. |
| Output 2.2.4 Timber traceability system for SFM in the province, designed and implemented in Cerro Sumaco (Guamaní and Akoki communities), as a pilot for Napo province. | 4Y | The proposal for the National System of Traceability of Timber Forest Products (native forest) is a chapter of the new sustainable forest management regulations. This chapter is being processed in the MAE. For this reason, the project, in consultation with the Management Committee decided to follow this process for the province. Additionally, there is an economic study (cost/benefit) regarding the implementation of the National System of Traceability of Timber Forest Products, established as a proposal by the MAE. This study defines technical recommendations and key incentives for the design, implementation and sustainability of the traceability system in the Napo. | Participated in the inter-institutional working group to support the development of the National Traceability System led by the MAE. The outputs generated through this group are traceability regulations proposal, traceability implementation plan, the creation of the traceability module in the Forest Administration System (SAF) of the MAE and the prioritization of complementary studies for the efficient development of the system. The key inputs for the development of the national traceability system are: -Approval of regulations through a ministerial accord -Incorporation of the traceability module in the SAF | The structuring of the National Wood Traceability System of the MAE has been supported. The inputs generated by the project are: - Cost/benefit study of the traceability system in Napo. -Review of the MAE traceability regulations. -Project outline/traceability conceptual note, adjusted for funds application through the BNDES-Brazil. -Operational model and implementation of the traceability system. -Process Flowchart for the traceability system. -Systematization of consultancies and traceability pilots carried out within the International Cooperation framework. - Diagnosis of infrastructure and equipment necessary for the implementation of the forest traceability system in the field. | A follow-up process has been carried out to the process of generation of the legal and technological instruments for the establishment of the wooden traceability system in the DNF The inputs generated in the current period are: -Traceability system operation manuals, -Manuals of system users, -Participation meetings for the validation of principles and criteria for the green point recognition for forest exploitation. | To advance with the development of the traceability system of MAE´s National Forestry Directorate, all the inputs generated by the project have been delivered to complementary support programs. For example, ProAmazonia, KfW and others, who manage the traceability module in the SAF Forest Administration System, the revision of national regulations and other inputs for the operation of the system. | 100% | The national traceability system for wood and Non-Timber Forest Products (NWFP) have the Organic Environmental Code (COA) and its regulations as an umbrella, making it necessary to ratify the national standard and complement the traceability module in the Forest Administration System. |
| Output 3.1.1 Conservation agreements (1000 ha) and good sustainable community tourism practices implemented. | 4Y | General diagnoses of the seven prioritized community tourism ventures have been drawn up, which have allowed the delineation of improvements, requirements and training for the legalization of tourist offerings, as well as the hiring of a consultant team for the preparation of good practice manuals, according to attractions and services they offer. | The Community Tourism Good Practice Guidelines have been prepared for the 7 ventures supported by the project, which have been validated by community organizations, the MAE, the Ministry of Tourism, the tourism section of the GADPN and other stakeholders. Conservation pre-agreements have been established covering over 500 ha with the organizations of the 7 supported projects. Progress was made in the drafting of Implementation Plans of the Good Practice Guidelines and technical support. The Legalization of Amarun Pakcha as a Community Tourism Center at the Ministry of Tourism has been facilitated. | Progress is being made in the implementation of the Good Practices of Community Tourism, in the 7 ventures supported by the project, in coordination with the MAE, the MINTUR, and Tourism section of the GADPN. The registration of Amarun Pakcha, Santa Rita and Oyacachi as Community Tourism Centers - CTC in the Ministry of Tourism has been facilitated; and other enterprises are being trained to achieve this license. There is a conservation agreement with Amarun Pakcha for 50 ha. New dossiers are being generated to subscribe new agreements based on the technical-legal format developed by the project and management for Socio Bosque coverage in these bio-entrepreneurships. With these actions, it is expected that the project’s goal will be met. There is a system for visitor records, customer service and services, incorporated into the monitoring system of the project under Open Foris. | Thanks to the application of the Community Tourism Good Practice Guidelines, the Pacto Sumaco enterprise has started the process to reach the CTC category in the MINTUR, which has been verified and is ready for approval, which will allow that 4 of the 7 project support projects reach this license. Coordination meetings and processes have been established to include entrepreneurship companies in the national circuits of the Runa Tupari Native Travel community tourism operator, http://www.runatupari.com/index.php/nuestros-tours/por-destino/nacionales.html The building and delivery of basic adaptations to the entrepreneurship companies have been completed, such as signage, bathrooms and dressing rooms, information centers, water services and others. Forest conservation agreements have been signed between the entrepreneurship companies and the Napo Provincial Government, in the following areas: Oyacachi 5000 ha and Runashito with 900 ha. Total: 5900 ha. | The obtaining of licenses as Community Tourism Centers has been completed for Santa Rita, Amarun Pakcha, Oyacachi and Pacto Sumaco, which has allowed them to have greater visibility and promotion, as they appear in the national tourist cadastre and access advertising strategies for the sector public, including obtaining credits, certifications and consolidating marketing processes. Santa Rita and Laguna Azul have been included in the circuits of the national operator of community tourism Runa Tupari Native Travel http://www.runatupari.com/index.php/nuestros-tours/por-destino/nacionales.html, with the support of Maquita Cuchunchi NGO. The seven ventures supported by the project have basic adaptations such as signage, arrangement of bathrooms and dressing rooms, information centers, water services, and others, to improve service delivery. The forest conservation agreements established between the enterprises and the Napo Provincial Government have been followed up in the following areas: Oyacachi 5000 ha and Runashito with 900 ha. Total: 5900 ha. | 100% | Runashito's community tourism venture has a strengthening project financed by the Forests and Farms (FFF) mechanism, generating a local tourism operator that brings together a network of community tourism initiatives in Napo. |
| Output 3.1.2 Bio-trade products with management plans and/or “Chakra” ecological seal produced in the priority areas (Archidona and Tena) under conservation agreements. | 4Y | In the process of developing five (5) bio-trade products and prioritized organizations: orchid – Tamia Yura Kichwa Center, palm - Shalcana, guayusa - Kichwa People of Rukullakta - Cooperativa SaBio, vanilla - Kallari, Tikaso - Inti and Tálag. They have identified and established collaborative work agreements with communities, organizations and private enterprises; including a rapid diagnosis of the productive, technological, organizational aspects of each product; and consultations of the current regulations of the MAE for its sustainable management. In addition, there are ToRs validated by the MAE for the hiring of a consultant team for the development of management plans for the five outputs | Management plans have been prepared with a focus on the value chain for the 5 bio trade products: orchids - Tamia Yura Kichwa Center; palm - Shalcana; guayusa - Kichwa People of Rukullakta - Cooperativa SaBio; vanilla - Kallari; Tikaso - Inti and Tálag), which have the approval of the MAE for obtaining the stockpiling, processing, and marketing patent. The Provincial Ordinance of the participative guarantee system of the Chakra seal has been created. It was approved in the plenary session of the provincial chamber of Napo, in May 2017. The process of drafting the regulations for the awarding of the Chakra seal to families and producing organizations has begun | Operational strategies have been agreed with the MAE to comply with the requirements for the licenses and product mobilization guides. This has been done based on the management plans of the 5 bio-commerce products. According to the compliance with the requirements, the license for vanilla is in the process of being approved, as well as the generation of guides for the use of Guayusa and palm fiber. The promotion of dried pods and vanilla powder, energy drinks, and guayusa infusions were supported at local and national fairs. In coordination with the MAG and MIPRO, the process of advising on the production and drying of Tikaso with the INTI association continues. In order to facilitate orchid spotting by tourists, the relocation of orchids has been done in paths of forest remnants in cooperation with the MAE and the orchid gardens on which the project focuses. There is a draft manual for granting the Chakra seal to producers and bio-enterprises that comply with the provincial ordinance. This manual is reviewed in the inter-institutional space of the Chakra Group, led by the Provincial Government. | Progress was made in the implementation process of the management plans for bio-commerce and NTFP products: The first report of compliance with the Vanilla management license for MAE was made, as well as support for the design of logos for the new products: dried pods and vanilla powder. -New partners of Rukukawsay - PKR have plans to improve the Guayusa. In addition, they have improved the labels and containers for the commercialization of the three flavors of Guayusa energy drinks. -The consolidation of an artisans network from Napo - "Napu Teje" - who work with natural fibers and particularly palm fiber. Palm handicrafts are sold in tourism ventures of the network, NAPUMARKA and others. -The infrastructure of the orchid reproduction nursery is ready, which is part of the Tamiayura tourism circuit. In addition, training workshops in management, traceability and attention to tourists were held. - The manual, regulation and logos are available to continue with the constitution of the SPG Guarantee Participatory System process for the granting of the “chakra” stamp to organizations that comply with the provincial Ordinance of the Chakra seal. | The following advances are synthesized: -Application of the comprehensive vanilla management plan; monitoring of the compliance report of the Vanilla driving license for the MAE; support in printing the new labels for dry pods and vanilla powder; identification of the vanilla species by molecular analysis. -Application of the comprehensive management plan for guayusa: new Rukukawsay - PKR partners have property registration in the MAE SAF; the three energy drinks have sanitary registration; and the improvement of the infrastructure of the local plant supported by the Provincial GAD is carried out. -Application of the comprehensive management plan for palm fiber: registration of farms in the MAE SAF and maintenance of mobilization guides; the management of the Napo artisan network - “Napu Teje” strengthened. As well as improved craftsmanship designs and fabric quality; there is a NapuTeje brand manual; support to the elaboration of a project for the FFF mechanism; participation in local and national fairs, sale of products in NapuMarka stores; and provision of banner for fairs. -Application of the comprehensive management plan for the orchid nursery in Tamia Yura: provision of orchid breeding racks; development of a training cycle in the reproduction and management of orchids; registration of the nursery in AGROCALIDAD; provision of a banner for fairs. -Implementation of the Tikaso comprehensive management plan in the INTI association: support in the generation of logo and label design for the oil and biscuit makeup process; generation of the INTI logo; signing of a new seed sale contract to Suma Sacha Ecuador; supply of labels and bottles; and delivery of a banner for fairs. For the constitution of the Participatory Guarantee System (SPG) for the granting of the Chakra Seal, the management model has been generated: organic structure and functions of the ethics committee, technical committee and group of observers. | 100% | The endorsement of the Ministry of Agriculture and Livestock has been obtained and the file of the Amazon chakra system has been presented to the secretariat of the FAO GIAHS program in Rome. This process seeks to achieve global recognition of the Chakra system as an Globally Important Agricultural Heritage System (GIAHS) which represents a great opportunity for the revaluation, conservation and promotion of the system, and to manage access to new markets at the national and international level. |
| Output 4.1.2 Mid-term and final evaluations carried out | 2Y | A system of monitoring and operative planning of the project has been developed, based on the results, outputs and activities established in the POA. This system will be complemented with the generation of progress registration, database and report generation tools. A semi-annual progress report and the present PIR have been prepared. | The monitoring and evaluation system of the project has been put into operation, through the application of progress monitoring matrices in the achievement of the project's outputs and goals. Additionally, there has been work done on the automation of monitoring matrices, to facilitate the continuous recording of information and generation of reports. Three PPR semi-annual reports and 2 PIR annual reports have been prepared (including this report) | There is an automated system for monitoring the progress of outputs and goals of the project through an adaptation of the free software Open Foris Collect, which facilitates the generation of continuous reports and progress statistics. 4 semi-annual PPR reports and 3 PIR annual reports have been made (including this report undergoing approval). | Monthly monitoring and planning meetings have been held with the project team, as well as the analysis of the monitoring system reports in the Open Foris Collet free software. From programs of the representation of FAO Ecuador, the monthly monitoring of the advances in the POA and PAC has been carried out. In addition, meetings have been held to analyze progress and technical recommendations from the management committee of the CGP project. In total, 6 semi-annual PPR reports and 4 annual PIR reports have been made. | The integral monitoring system of the project was consolidated, in which progress was recorded in an Excel electronic sheet matrix; and its subsequent automation of the monitoring system in the Open Foris software, for each of the technical products of the project. Monthly monitoring of the progress of the POA and PAC has been carried out by FAO Ecuador representation, based on the Excel monitoring matrix. In addition, progress analysis meetings and technical recommendations have been held from the CGP project management committee. In total, 8 semi-annual PPR reports and 5 annual PIR reports have been made. | 100% | Thanks to the adaptability of the OpenForis software, this tool has been applied in the project information system; in the monitoring of indicators of the provincial PDOT; and in the file system of the GADPN Productive Development Directorate. |
| Output 4.1.2 Mid-term and final evaluations carried out | 2Y |  | The ToRs have been generated for the mid-term evaluation of the project and the call for consultants has begun. This process is coordinated with the FAO-OED evaluation unit | The Mid-Term Evaluation of the Project has been fully developed. The recommendations of this evaluation have been incorporated into the 2018 POA and PAC. | For the final evaluation of the project, the TORs were reviewed in a process coordinated with the FAO - GEF unit. | The final evaluation of the project has been completed. The recommendations have been incorporated into POA 2020. | 100% | The analysis through the application of the theory of change has become an important input to determine break points in the systematization of the project. |
| Output 4.1.3 Good practices and lessons learned from the project published. | 4Y | The generation of continuous registration matrices, databases and report documents will facilitate the generation of information for the systematization of the experiences and processes of the project. |  | There are systematization drafts of the following project products: -Methodology of environmental criteria evaluation in PDOTs -Good agricultural production practices -Methodology and Technology for Forest Restoration and, -Good Community Tourism Practices There is a digital publication of the summaries of the processes of the bio-business of bio-commerce. | The integral systematization plan for the project has been carried out, including the definition of the systematization axes. This activity has allowed generating draft documents detailing the processes, experiences and lessons learned at the product level. In addition, advanced systematization documents of the gender approach and the free and informed prior consultation process for the execution of the project have been generated. | A comprehensive document has been generated to systematize the process and experiences of the project, as well as a first editing review. The process of preparing the ToRs has begun to contract the edition, layout and publication of the systematization document. | 90% | The publication of the systematization is based on the formats and publication standards of FAO – GEF. |
| Output 4.1.4 Website for the dissemination of information and experience exchange | 4Y | The ToRs for hiring the computer specialist includes the review of the project’s website and the design and operation of a geo-viewer | Through the implementation of the provincial information system, a website has been established, which allows the processes, progress and outputs of the project to be socialized and made transparent: http://infonapo.org/ | Project progress and outputs have been continuously published through the provincial information system website http://infonapo.org/ Between the end of 2017 and the beginning of 2018, a communication strategy for the project's processes and outputs was completed. Based on the communication strategy, a process of generation of educational-communicative instruments of the project has been initiated. | Project progress and outputs have been continuously published through the provincial information system website http://infonapo.org/ In the present semester, the design of the website has been improved to promote and facilitate user navigation. The process of generating edu-communicative instruments and disseminating the project has been completed: newsletter, 3 videos, flipcharts and infographics. In addition, news has been published on the social networks of FAO EC. | Project progress and outputs have been continuously published through the provincial information system website http://infonapo.org/ Flipcharts and infographics have been shared and delivered educational-communication tools for the training processes of the project's partner organizations and institutions The website is being managed and updated from the GADPN technology team | 95% | The website is currently being updated with the latest versions of the project's outputs. |

Information on Progress, Outcomes and Challenges on Project Implementation

Please briefly summarize main progress achieving the outcomes (cumulative) and outputs (during this fiscal year): Max 200 words: Until the present period, the execution of the project is consolidated, complying with 17 outputs of the 19 planned in the project. The contribution is defined in 1.1) the incorporation of environmental criteria in the PDOTs; 1.2.) Investment in national and local incentive systems, establish an approximate accounting of 3,559,751.44 up to the present period. Component 2 has achieved 2.1) the application of good agricultural production practices in 1,370 families and more than 1,952.5 ha of sustainable production. 2.2) From 2015 to 2018 MAE´s deforestation rate has been reduced by a percentage greater than 15% in reference with the baseline, reducing emissions by MFS and conservation agreements by a total of 4,217,795 Mg CO2eq. This includes the improvement of carbon stocks in agroforestry, silvopastoral systems and areas under active and passive forest restoration for a total of 57,990 Mg CO2eq. In component 3: 3.1) 6,345.28 ha under conservation agreements and according to the study evaluating the socio-economic effect, a level of increase in income from bio-enterprises is established above 27%, benefiting 1,980 associates , of which more than 50% are women. Finally, in component 4: 4.1) the project achieves an overall progress of 97.6% of physical-technical execution and 96.7% of budget execution. What are the major challenges the project has experienced during this reporting period? Max 200 words: The institutional implications for the financial mechanism Napo Sustainable Development and Water Conservation Fund (FODESNA) constitution has demanded a process of socialization, technical support and monitoring of the generation of political decisions by the new authorities of the Napo Provincial Government, including mayors of five cantons and representatives of Parish Boards that are part of the provincial council of Napo. These institutions have generated the resolutions, provincial ordinance and all the necessary documentation for the trust approval by the Ministry of Economy and Finance (MEF) of Ecuador based on environmental, legal and financial feasibility. However, the unforeseen replacement of the Napo Prefecture in January 2020, due to the passing of the current prefect, involved a process of ratification of decisions and commitments to advance with the constitution of FODESNA, under new leadership and in a scenario of social distancing due to the health crisis (COVID-19).

Development Objective Ratings, Implementation Progress Ratings and Overall Assessment

|  | FY2020 Development Objective rating | FY2020 Implementation Progress rating | Comments/reasons justifying the ratings for FY2020 and any changes (positive or negative) in the ratings since the previous reporting period |
| --- | --- | --- | --- |
| Project Manager / Coordinator | HS | S | The project has contributed to achieving global environmental objectives in an integral way, achieving each of the goals and indicators of the six proposed results, generating 100% of 17 of the 19 products established in the four components of the project. These results include the development of sustainability processes and instruments such as ordinances, institutional resolutions, legal instruments, development plans and territorial ordering, capacity building, innovation of value chains, compliance with regulations, standards and quality of services, strengthening of bio -business, diversification and expansion of markets, among others To a large extent, the achievement of the project's results and products is due to the adequate interaction of the project's governance spaces (Steering committee, Management committee and technical team), the timely application of the recommendations of the FAO missions and of the Midterm and Final Evaluation. In addition, the good conceptualization and interdisciplinary work of the project team, which has allowed us to transcend processes and products. As complementary processes to position the environmental and socio-economic quality of the products of associative bio-enterprises, the generation of the participatory guarantee system (SPG) for the award of the chakra seal stands out, the process for the recognition of the chakra system as a GIAHS. As well as new projects implemented by producer organizations through the Forest and Farm Facility (FFF) and the implementation of the Climate Smart Cocoa project to reinforce the application of good practices in the Napo consortium of cocoa organizations. |
| Budget Holder | S | S | The project is on the final year of implementation. The project team for this final stage is reduced and concentrated on putting on operation the FODESNA. The creation of FODESNA is key in this final phase of the project and has become into a challenging activity due to changes on local administrators, national processes in the MEF and health emergency during the last three months. Since January the project has focused in implementing the FODESNA. For this reason, a change in the NTE with no addition cost was approved until October 2020. This is necessary due to the current conditions and needs of operational closures |
| Lead Technical Officer | S | S | The project is highly satisfactory, has managed to institutionalize the process in the Napo region and has the potential to be replicated in the Amazon territory. This project coordinates actions with the sustainable livestock project that is implemented in some common municipalities. The beneficiaries have appropriated the process and integrated it into their daily lives. |
| GEF Operational Focal Point | S | S | The Good Living Project GEF Napo in its years of implementation has consolidated several important processes for the Amazon development of the country. Supporting the actions of the National Government with the support in the elaboration of the Plans of Development and Territorial Planning, the strengthening of the value chains especially of the Amazon cocoa, as well as supporting the creation of Humu Center for Environmental and Tourist Interpretation, promoting the strengthening of capacities of its beneficiary population and strongly supporting the social and economic development of the intervention areas. Additionally, the project has made significant efforts in biodiversity conservation issues, demonstrated through conservation agreements, the implementation of good agricultural practices, as well as in the reduction of the deforestation rate. Additionally, it should be noted that the good management of the project team continues to work on the establishment of the Napo Sustainable Development and Water Conservation Fund (FODESNA) to give sustainability to the initiatives developed during implementation. Finally, it is important to highlight that the project has demonstrated the adequate articulation of key actors such as GADs, peoples and nationalities, NGOs, academia, without neglecting other ongoing projects such as Climate Smart Livestock, the Forest and Farm Mechanism, and the Climate Smart Cacao project. Likewise, this project has served as a good basis for strengthening other initiatives that are being carried out in the territory. It is necessary to rescue that, although the initiatives have been good, they must be taken advantage of by the actors and be strengthened with the aim of being able to scale them beyond community initiatives. |
| FAO-GEF Funding Liaison Officer | S | S | The Napo project has been a pioneer project in the region. This last year of implementation is allowing the project team to consolidate the project lessons learnt and publications, as well as establishing the FODESNA for future implementation. It would be interesting that new GEF- or other donor-financed projects support the scale up of the FODESNA tool to increase BD mainstreaming in the Amazon provinces. Potential linkages could be explored with the GEF-7 IP ASL2. The recognition of the chackra as GIAHS site can lead to the inclusion of the Napo areas in a future GIAHS global program. |

Risks

- Environmental and Social Safeguards (Under the responsibility of the LTO)

| Overall Project Risk classification (at project submission) | Please indicate if the Environmental and Social Risk classification is still valid. If not, what is the new classification and explain. |
| --- | --- |
| C | It remains valid. |

Please make sure that the below risk table include also Environmental and Social Management Risks captured by the Environmental and social Management Risk Mitigations plans.

Risk ratings

RISK TABLE

The following table summarizes risks identified in the Project Document and reflects also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant.

|  | Risk | Risk rating | Mitigation Action | Progress on mitigation actions | Notes from the Project Task Force |
| --- | --- | --- | --- | --- | --- |
| 1 | Institutional risk: Duplication and lack of complementarity and synergy due to lack of will and commitment among the different actors (MAE, MAGAP and GADP) to exchange information and coordinate | L | - Inter-institutional spaces for cooperation and coordination have been strengthened -Generation of information exchange instruments. | - Coordination spaces: cacao consortium, cattle dealer network, chakra group, inter-institutional group for PDOT´s update and NapuMarka network. - Provincial information system | A continuous inter-institutional coordination process has been maintained. |
| 2 | Political risk: Biodiversity Conservation and Integral Management of Natural Resources does not have political interest at the regional level. | L | - Local planning and regulatory instruments have been socialized and articulated with regional and national policies. This contribute to biodiversity conservation and natural resource management. | -Application of the organic law of spatial territorial jurisdiction Amazon. -Socialization and articulation with the National REDD + program -Support for the elaboration of the regulation of the National Environmental Code -Support for the conceptualization, axes and lines of action of the MAE's bioeconomy approach. - Recognition process of the Chakra System as GIAHS. | - Coordination with the PROAmazonia program of MAE and MAG. - Advances in the recognition of the chakra system as GIAHS. |
| 3 | Political risk: The State prioritizes that public resources, including those from the extraction of non-renewable natural resources, are invested in other sectors. | L | - Socialization and strengthening of public policies: competences of the GADs in environmental management and of natural resources. -Socialization of new laws and regulations that facilitate investment in the environmental field and sustainable development. | - Strengthening of the GAD Napo Productive Directorate for the expansion of incentives. -Socialization and participation in application areas of the Amazon Law. -Focus on the processes of productive reactivation and recovery of livelihoods. | -Coordination with the Provincial Government of Napo for the productive reactivation. |
| 4 | Institutional risk: Potential change of authorities of local governments, the commitments generated around the implementation of the sustainable development fund are dismantled by provincial elections. | M | -Socialization and permanent communication of the processes, products and results of the project -Facilitation of transitional spaces for project activities between the outgoing and incoming authorities of GAD Provincial de Napo. | -Coordination and permanent cooperation with authorities, directors and technical teams of local governments. -Follow-up to the implementation process of the provincial government's operational plans - Intensive accompaniment to the constitution process of FODESNA. | -Progress is being made in the reaffirmation of commitments and generation of the enabling documentation for the constitution of FODESNA. |
| 5 | Institutional risk: Change in the Ministry of Environment and MAGAP policies regarding the implementation of incentives for conservation, ecological restoration, and sustainable production. | L | - Permanent coordination with the Directors and technical teams from MAE and MAG incentive programs. -Establishment of spaces for the articulation of national and local incentives. | -Facilitating the expansion of areas under conservation agreements between Socio Bosque and communities co-management plans. -Analysis and improvement of the farm planning methodology for ATPA incentives – MAG. -Approach to the management of the technical secretary of the Amazon spatial territorial circumscription. | -Maintenance of national incentives in Napo -Management of new incentives through the technical secretary of the Amazon spatial territorial circumscription. |
| 6 | Institutional risk: Lack of awareness in signing conservation agreements without the granting of effective incentives and direct and rapid benefits for the producers involved. Non-compliance with conservation agreements by suppliers and users of environmental services. | L | - Together with representatives of national and local incentives, training spaces have been developed in the management of incentives for the maintenance of conservation commitments and activities. | -Various communities and organizations of Napo have submitted applications to access to the Socio Bosque Program. -The monitoring of Socio Bosque conservation agreements is supported. -Monitoring of conservation agreements between entrepreneurship companies and the Provincial Government of Napo. | -The Napo Provincial Government has prioritized the extension of conservation agreements by managing incentives to promote sustainable production. |
| 7 | Socio-economic risk: Producers’ poverty prevents productive investments. | S | -Support and strengthening of the entrepreneurship companies from producer organizations. -Strengthening and facilitation of access to national and local incentives. -Revaluation of traditional practices and technologies. | -Increase of partners in the organizations and sales volumes of processed and quality products in local, national and special markets at an international level. -Progress in the generation of participatory guarantee system to grant the chakra seal to products of small producers. -Licenses granted by the MAE for biocommerce products, and licenses to tourism enterprises such as Community Tourism Centers from MINTUR. -Improvement of services and number of visitors to community tourism ventures. | From the policies and programs of local governments, the strengthening of bio-enterprises is promoted. Support through the forest and farm mechanism (FFF) and the Climate Smart Cacao project. The Climate Smart Cocoa Project (CCI) is financed by the Italian Ministry of the Environment, Land and Sea (IMELS), which will run until March 2022. |
| 8 | Socio-economic risk: Resistance of owners to the adoption of good sustainable forestry production and management practices, sustainable community tourism, and sustainable biodiversity use. | L | -Development of processes of participatory extension, under an intensive support plan. -Application of non-monetary incentives for good practices implementation focused on the value chain. -Generate scenarios and strengthen of demonstrative entrepreneurship companies for opening of markets. -Application of the gender approach. | - The application of good practices validated with organic certification processes has been encouraged. -The tourism entrepreneurship companies have reached CTC category approved by the Ministry of Tourism. -The transformation process has been strengthened, in compliance with quality regulations and the commercialization of products in the local, national and international markets. | -The chakra system file as a GIAHS has been presented to the FAO´s GIAHS program secretariat. -There is the ordinance, manual, regulation and structure of the SPG for the granting of the chakra seal. |
| 9 | Environmental risk: Impact of climate change on key ecosystems in landscapes and agricultural production (e.g. water availability). | L | -Application of good agricultural practices for adaptation to climate change. -Increase of vegetation cover in agricultural systems through silvopastures and agroforestry to mitigate climate change | -An important area and number of families that apply good practices in their family farms have been reached. - An important area of forest conservation agreements has been generated in agricultural landscapes, since the management of the Provincial GAD. -Both the Forest and Farm Mechanism (FFF), as well as the climate-smart cocoa project, aim and focus to improve the resilience of production system. | -The revaluation of the chakra agroforestry system constitutes a system with high resilience to climate change, thanks to the high agro-biodiversity content, the forest canopy and traditional knowledge for its management. |

Project overall risk rating (Low, Medium, Substantial or High):

| FY2019 rating | FY2020 rating | Comments/reason for the rating for FY2020 and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| M | M | Most of the risks analyzed and initially established by the project have been managed by defining mitigation actions that have generated relatively effective results. For this reason, the vast majority of outputs and the goals set for the project were achieved. However, the issue of political instability due to regular and unforeseen changes by the authorities of the Napo Provincial Government has had a huge impact on the progress of the institutional constitution of the financial mechanism of the Napo Sustainable Development and Water Conservation Fund (FODESNA). That represents the main pending output, which is of special importance due to the support of financial sustainability that it can contribute to the proposal of comprehensive management of Napo's natural resources. The commitments reaffirmed with the new authorities and their operation through lines of work agreed with their technical teams, highlight the collaborative and coordinated actions in this final phase of the project. This is allowing progress in the process of constitution of FODESNA and in the planning of the fund´s pilot project, which is expected to complete and generate the first lessons learned until the end of the project. On the other hand, the publication and socialization of the systematization of the experience and lessons learned from the project will be completed. This will help local governments and partner institutions to consolidate and strengthen the proposal for comprehensive management of natural resources, based on the analysis of break points or theory of change, developed to mitigate risks and the sustainability of processes. |

Adjustments to Project Strategy

Please report any adjustments made to the project strategy, as reflected in the results matrix, in the past 12 months

| Change Made to | Yes/No | Describe the Change and Reason for Change |
| --- | --- | --- |
| Project Outcomes | No |  |
| Project Outputs | No |  |

Adjustments to Project Time Frame

If the duration of the project, the project work schedule, or the timing of any key events such as project start up, evaluations or closing date, have been adjusted since project approval, please explain the changes and the reasons for these changes. The Budget Holder may decide, in consultation with the PTF, to request the adjustment of the EOD-NTE in FPMIS to the actual start of operations providing a sound justification.

| Change | Describe the Change and Reason for Change |
| --- | --- |
| Project extension | Original NTE: December 2019 Revised NTE: October 2020 Justification: During the development of this period, the technical-physical progress has been completed in 97.6% and in a similar proportion the budgetary investment, the indicators of the results being fully completed and in 100% 17 of the 19 outputs of the project. However, the changes of authorities and policy lines of the Napo Provincial Government during the second semester of 2019 have required a process of socialization, negotiation and alignment of the processes, instruments and management frameworks of the project with the new work plan of administration 2019 - 2023, so it has been necessary to extend the consolidation time of certain products. In particular, referring to FODESNA, the inter-institutional strategy for natural resource management, complement the systematization of processes and lessons learned, including the generation of final reports and the management of assets for the closure of the project. In this sense, since the analysis of the project management committee (CGP) and the decisions of the steering committee (CDP), the importance of requesting the extension of the project execution period (without additional costs) until October 2020 has been established. This is an adequate period to complete the constitution and management of the Napo FODESNA, due to its importance in contributing to the financial sustainability of the proposal for the comprehensive management of Napo's natural resources. |

Gender Mainstreaming

Information on Progress on gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable)

Was a gender analysis undertaken or an equivalent socio-economic assessment made at formulation or during execution stages? Please briefly indicate the gender differences here. Between the end of 2018 and the beginning of 2019, during the second stage of project execution, a systematization process of the application of the gender approach was carried out. The report established a brief background showing a general approach to gender gaps in the province of Napo in the fields of education, violence, use of time and political participation. This background describes that the average schooling in the province is 9.3%, of which 9.6% correspond to men and 8.9% to women. Rural disaggregation establishes 11.2% for men and 8.0% for women. Because the province of Napo has a larger rural population than the urban, the lowest percentages of schooling and illiteracy correspond to indigenous nationalities and poor rural peasants, and of these strata, women are those with the lowest opportunities to access education. The Gender Atlas indicates that in Napo 65% of women have suffered some type of violence throughout their lives, and 77.60% have suffered violence from their partner. These two indicators exceed the national figure for violence of 60.6%. In the province of Napo prior to 2010, 446 pregnancies were registered between the ages of girls and adolescents ranging from 12 to 19 years old, although the data does not disaggregate urban and rural areas, nor does it refer to ethnicity and cultural, it can be inferred that indigenous girls and adolescents formed an important part of this group. Based on the analysis in the elaboration of the co-management plans in protective forests, women dedicate at least 17 hours daily to the development of productive and reproductive activities; compared to men who dedicate 9 hours a day for these same activities, but with greater emphasis on productive tasks. The Ministry of Agriculture and Livestock (MAG) maintains that there is a sub-registry of female occupation in the field, their work in agriculture is not considered given that their contributions in agricultural activity are unknown. In turn, they are not seen as productive actors, since they declare themselves as housewives or economically inactive because they do not have a formal job that is remunerated, despite the fact that they dedicate more daily hours than urban women and rural men in agricultural work and care of minor animals. In the political sphere, based on a quick analysis of the exercise of positions of technical-political appointment in three GADs in the province of Napo, it was observed that of the 28 existing managerial positions, 23 are held by men, that is, the 82%, and only 5 were occupied by women, corresponding to 18%. The figures indicate that in addition to the 5 women, at least 9 stopped accessing these positions, which are occupied by men. On this basis, the project contemplated the application of the gender, generation and intercultural approach to ensure the active participation of women in each of the project's management stages. As well as to facilitate their empowerment as a basis for the sustainability of the processes of conservation, sustainable production and development of bio-enterprises, thanks to the increasingly leading role that women have been achieving in these initiatives. Although the project did not contemplate the development of an initial analysis of gender gaps, it did establish several key gender indicators for some outputs. For example participation of women in the knowledge management process, management of income opportunities for women in bio-commerce and tourism ventures, special advice to women in the management of incentives, gender mainstreaming in planning instruments, among others. Based on the important advances in the application of gender, from the midterm review (MTR) it was recommended to carry out a process of systematization of the experience, in order to generate recommendations to share with other processes and projects of the FAO representation in Ecuador, in line with the manuals and procedures established by the organization. Does the M&E system have gender-disaggregated data? How is the project tracking gender results and impacts? The project's monitoring system does include data disaggregated by gender. The system periodically registers the active participation of women and men in training processes, participatory workshops, planning processes, and execution of activities, among others. The following table establishes that the active participation of women reached 42.53%, higher than the proposed goal of the project of between 25-30%.30%. Output; Women (%); Men (%). PDOT and ZEE; 30,43; 69,57. Training and workshops. Natural Resources Information System. Training and workshops; 34,18; 65,82. Geographic information system. Training and workshops; 29,79; 70,21. Good agricultural practices. Training workshops; 51,99; 48,01. Value Chains. Training processes; 50,56; 49,44. Implementation of the chain plan; 45,71; 54,29. SFM Strategy. Strategy development workshops; 31,76; 68,24. Co-management plans. Participation in the development of co-management plans; 35,62; 64,38. Community tourism. Training workshops and application of good tourism practices; 51,64; 48,36. Capacity building program. Courses and training for update; 37,73; 62,27. Forest restoration. Training, restoration practices and monitoring; 35,42; 64,58. Bio trade. Training workshops and implementation of management plans; 67,67; 32,33. TOTAL; 42,53; 57,47. Does the project staff have gender expertise? In the team, there is a different level of knowledge and application of the gender approach. Most of the team has applied it in previous experiences and has received important training on the subject. In addition, during the implementation of the project, a national gender expert was hired, with training and feedback to ensure the good application of the approach. If possible, indicate in which results area(s) the project is expected to contribute to gender equality: - closing gender gaps in access to and control over natural resources; Although the project did not contemplate the initial analysis of gender gaps, the project team took the gender indicators established in project planning as the guide for applying the approach. In this sense, cultural relevance was the platform on which the specialists of the project based the technical contents; they considered the ancestral knowledge of women and men, as well as the relationships they establish with the resources of biodiversity, their differentiated sustainable management practices in the chakras and farms. These processes were put in value to make visible and highlight the work of women and men regarding the management of natural resources, both in the processes of diagnosis, planning, training, development of value chains, and compliance with quality standards, traceability, service provision and marketing. - improving women’s participation and decision making; and or generating socio-economic benefits or services for women During the project management period, an average active participation of 42.53% of women has been achieved in each of the outputs developed, both in the component: i) institutional strengthening and good governance; ii) landscapes and sustainable production; and iii) bio-enterprises for the sustainable use of biodiversity. The gender approach had special relevance in the project, taking as support the FAO gender equality policy, as well as international treaties such as the Convention on Biological Diversity (CBD), the Constitution of the Republic of Ecuador and other regulations and directives towards the management of Decentralized Autonomous Governments (GADs). Therefore, in each of the management activities and development of processes for the achievement of outputs and results, adequate and opportune spaces were established for the active participation of women, based on their access, control and interest systems, what which gradually facilitated greater empowerment and participation in decision-making and in the development of activities. Based on the assessment study of the socio-economic effect of the project, a level of income increase of bio-ventures supported by the project is established above 27%, benefiting 1,980 associates, of which more than 50% are women. Of the 14 ventures supported by the project, female leaders have chaired 8 and the Red Napu Teje and Tamia Yura correspond to ventures exclusively from women.

Indigenous Peoples Involvement

Are Indigenous Peoples involved in the project? How? Please briefly explain.

If applies, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. Based on the project's coverage, both grassroots and second-tier organizations of the Kichwa, Kijus nationalities and the Oyacachi ancestral Kichwa people have been directly involved in project management. These entities comprise the majority of the partners and represent more than 80% of the beneficiaries. Based on the systematization process of the Free, Prior and Informed Consent (FPIC) process carried out by the project, the main stages and moments of its application are described below: The main lessons learned from the FPIC application include: - FPIC is a right of peoples and nationalities, its application required the technical team and agroforestry promoters to prepare agendas and methodologies with cultural relevance. They developed skills to listen, learn and share mutual knowledge on equal terms. - The consultation made to nationalities´ leaders during the project formulation on the productive, environmental and institutional aspects contributed so that the organizations and ventures make the decision to participate in its implementation and give their free, prior and informed consent to the activities that were executed in their territories. - The commitments and counterpart agreements for the communities was part of their cultural practice of reciprocity. The FPIC broke the barriers of welfare and motivated participation on equal terms. - The change to a reference scenario due to the specific situation at the beginning of the implementation of the project in 2016 became an opportunity, far from being discouraged; the communities supported the planning of the new changes. This was because during the FPIC process had built relationships of trust and mutual respect. - The experience of applying FPIC in the “Conservation and Good Living GEF Napo” Project showed that communities need enough time to debate and decide whether or not to give consent, any decision is valid for the groups, provided it is in the spaces community and in their language. - The invitation to all or most of the people who make up a community to inform them about the project and ask them about their interest in participating, was the rule of the project, allowing more people to know its contents, facilitating the debate and the decision to participate.

Stakeholders Engagement

Please report on progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO Endorsement/Approval (when applicable)

If your project had a stakeholder engagement plan, specify whether any new stakeholders have been identified/engaged: If a stakeholder engagement plan was not requested for your project at CEO endorsement stage, please - list all stakeholders engaged in the project; - Please indicate if the project works with Civil Society Organizations and/or NGOs - briefly describe stakeholders’ engagement events, specifying time, date stakeholders engaged, purpose (information, consultation, participation in decision making, etc.) and outcomes. Stakeholder; CSO/ONG; Participation Event; Time; Purpose; Results. Napo Provincial GAD; Steering Committee - Management Committee; The entire project cycle; Participation in decision-making; Institutionalization of project processes and results.. Ministry of Environment and Water; Steering Committee - Management Committee; The entire project cycle; Participation in decision-making; Institutionalization of project processes and results.. GAD Tena; PDOT process, EEZ, capacity building; 2017 - 2019; Partner - promoting good practices; Application of the EEZ. GAD Quijos; PDOT process, EEZ, capacity building, good production practices, forest restoration.; 2017 - 2019; Partner - promoting good practices; Environmental criteria in PDOT; promotion of good forest production and restoration practices.. GAD Archidona; PDOT process, EEZ, capacity building, Good production practices, forest restoration, value chains, bio-commerce, community tourism.; The entire project cycle; Partner - promoting good practices; Environmental criteria in PDOT; promotion of good forest production and restoration practices.. GAD Arosemena Tola; PDOT process, EEZ, capacity building, good production practices, forest restoration.; 2017 - 2019; Partner - promoting good practices; Environmental criteria in PDOT; promotion of good forest production and restoration practices.. GAD El Chaco; PDOT process, EEZ, capacity building, good production practices, forest restoration.; 2017 - 2019; Partner - promoting good practices; Environmental criteria in PDOT; promotion of good forest production and restoration practices.. GAD Cuyuja; PDOT process, EEZ, capacity building, good production practices, forest restoration.; The entire project cycle; Partner - promoting good practices; Promotion of good practices in forest production and restoration. COCASINCLAIR EP; FODESNA; Partner - promoting good practices; Partner - promoting good practices. GIZ; ONG; Management Committee; Entire project cycle; Participation in decision-making.; Co-management of the capacity strengthening program. USAID; ONG; Good production practices; 2015; Partner – encouragement of good practices; Encouragement of good production practices.. Rainforest Aliance; ONG; Good production practices; 2015; Partner – encouragement of good practices; Encouragement of good production practices.. FAO; Steering Committee – Managing Committee; Entire project cycle; Participation in decision-making; Institutionalization of processes and project results.. Amazon State University (UEA); Strengthening capacities – Biocommerce; 2017 - 2019; Training - research; Endorsement of the program.. Geographic Military Institute (IGM); Informtation System - PDOT; 2017 - 2018; Information; Development of Spacial Data Infrastructure.. Ecuadorian Space Institute (IEE); Informtation System - PDOT; 2017 - 2018; Information; Information for the EEZ, provincial information system and PDOTs.. Autonomous Provincial Governments Consortium CONGOPE; Informtation System - PDOT; 2017 - 2018; Information – planning; Incorporation of environmental criteria into the PDOTs. Association of Municipalities of Ecuador (AME); Strengthening capacities - PDOT; 2017 - 2018; Information – planning; Co-management del of the capacity strengthening program.. Maquita Cuchunchi; ONG; Good production practices; 2016 - 2018; Information – planning; Encouragement of good agricultural production practices. GAD Cosanga; PDOT Process, ZEE, capacity strengthening, good production practices, forest restoration.; Entire project cycle; Partner – encouragement of good practices; Encouragement of good production practices and forest restoration.. GAD Hatun Sumaco; PDOT Process, ZEE, capacity strengthening, good production practices, forest restoration, community tourism.; Entire project cycle; Partner – encouragement of good practices; Encouragement of good production practices and forest restoration, community tourism.. IKIAM Regional University; Capacity strengthening – CO2 emissions measurement; 2017 -2019; Training - research; Biomass and CO2 measurement. Ecuadorian Cooperation Fund for Development FECD; ONG; Community tourism; 2017 -2019; Information – planning; Strengthening of the cocoa route. PROFAFOR Latinoamerica S.A.; FODESNA constitution process; 2017 - 2019; FODESNA constitution; Feasibility study and constitution process of FODESNA.. National Finance Corporation CFN; FODESNA constitution and management.; 2019; FODESNA constitution and management.; Trust agreement.. Federation of Napo Indigenous Organizations (FOIN); CSO; Coordination of work with peoples and nationalities originating in Napo.; 2017 - 2020; Consultation - Participation - FPIC; Governance, institutionalization and promotion of good agricultural practices - Chakra Seal.. Please also indicate if the private sector has been involved in your project and provide the nature of the private sector actors, their role in the project and the way they were involved Approaches have been made and several private companies from Napo and nationals have participated, to socialize the feasibility study process, constitution and the opportunities that FODESNA represents for the sustainable management of Napo's natural resources, under the corporate environmental responsibility concept. Among the companies that have participated in the FODESNA socialization workshops we have: Termas Papallacta; OCP Ecuador S.A .; Pacarí; Río Napo Foundation; ECOLUZ S.A .; Benchi; and others.

Knowledge Management Activities

Knowledge activities / products (when applicable), as outlined in knowledge management approved at CEO Endorsement / Approval

- Does the project have a knowledge management strategy? If not, how does the project collect and document good practices? Please list relevant good practices that can be learned and shared from the project thus far. The Project had two outputs that configure the main knowledge management strategy. On the one hand, the program to strengthen talents and capacities aimed at decision makers, technicians and producers, and community leaders, to which various public institutions, NGOs and producer organizations were articulated, with the support of the Amazon State University. The second pillar of the strategy was integrated by the development of the natural resources information system, through which geographic and environmental information of the Napo province is managed. The capacity-building program was articulated with the process of the School of Environmental Leadership (ELA) applied institutionally by the Provincial Government of Napo, through the Environment Directorate. The provincial information system is managed directly from the coordination unit between the technology, planning, productive promotion and environment departments of the Napo Provincial Government, who have been updating the geographic and environmental information permanently. These two pillars plus the permanent process of technical support, exchange and dialogue of knowledge has allowed the development of various instruments or good technological practices of planning, management and management of natural resources. For example, the economic ecological zoning of the province of Napo, the updated proposal of the provincial PDOT, the guide of analysis of environmental criteria in the PDOTs; the technical-legal document to establish conservation agreements; the procedure for preparing co-management plans in protective forests. In addition, it has allowed promoting silvopastoral systems in the upper part of Napo; organic cocoa production technologies; the processes of vegetative reproduction of naranjilla; value chain plans for cocoa and naranjilla. As well as the productive forest restoration methodology; community tourism good practice guides; management plans with a value chain approach for BioTrade products and Non-Wood Forest Products; the standards and functional organic structure for the Participatory Guarantee System of the Chakra Seal, among others. As support for the permanent application and promotion of these good practices, various governance and institutionalization instruments have been generated. Mainly provincial ordinances, resolutions of the Napo provincial chamber, articulation with organic and quality certification standards, compliance with regulations of the Ministry of the Environment, generation of statutes and regulations, as well as adaptation to traditional and community systems of natural resource management. - Does the project have a communication strategy? Please provide a brief overview of the communications successes and challenges this year. The Project developed a communication strategy based on the communication for development approach it was applied from the base of the technical support of the team to the beneficiary institutions and organizations. This included a dissemination process to make the project and partners visible at the local and national level, and the generation of edu-communicative instruments to strengthen the training processes and promotion of good practices. Among the main milestones of success of the communication strategy can be established the establishment of a continuous and fluid communication network between the project, partner and beneficiary entities; the generation of instruments of good natural resource management practices based on the dialogue of knowledge with the peoples and nationalities originating in Napo. In addition, a series of socialization programs of the processes and progress of the project were developed through the provincial media, both television and radio; the generation of edu-communicative material such as videos; infographics and flipcharts for training, among others. The communication strategy and its application was framed in the communication strategies applied by the Ministry of the Environment in the province of Napo, and particularly in planning of the Communication Directorate of the Provincial Government of Napo, who facilitated the contribution with specialized technical team and various media (television and radio) for the dissemination of the processes. Likewise, the instruments and practices of communication have been developing and expanding their application from the management of the Directorates of Productive Development and Environment of the Provincial Government of Napo. One of the main challenges in the application of communication instruments includes the positioning and dissemination of the products, experiences and results of the project to promote the application of FODESNA and other institutionalization processes, for the sustainability of the proposal for integrated management of the natural resources in Napo. FODESNA constitutes a complementary product to the various processes and instruments that have already been institutionalized in the Provincial Government of Napo, cantonal and parish GADs through ordinances, resolutions, local and national regulations (norms of the MAE). As well as through compliance with regulations, certification standards and various quality standards that have been applied from the various bio-enterprises supported by the project. - Please share a human interest story from your project, focusing on how the project has helped to improve people’s livelihoods while contributing to achieving the expected global environmental benefits. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. Women and sustainable community tourism in the Amazon More than 10 years ago, I witnessed a successful tourism experience in the province of Orellana; I met the Lodge Napo Wildlife Center offering a different proposal in terms of tourist services in the Amazon. This initiative quickly became the benchmark for community-based tourism in the country and Latin America for the offer of wildlife, nature within the rain forest and cultural experiences, combined with excellent services that take care of even the smallest detail. This experience has demonstrated two fundamental aspects: that the community can be of high quality, and that trained and prepared community actors are in a position to take on challenges within a competitive industry such as tourism. In 2011, this initiative promoted a new project, the Napo Cultural Center, led primarily by women from the community. This new proposal combined cultural, social, conservation and coexistence aspects with a business vision for an Amazon community. The visibility of women as the main protagonists of the tourist offer due to their important economic and cultural contributions has given very good results on the road to gender equality in this context. Currently the Napo Cultural Center is one of the most visited destinations by hikers and tourists who travel through the lower area of the Napo riverbank, thanks to their work. In 2015, I met a woman who, for her outstanding career in public and community management, is a benchmark in the Amazon, Mrs. Nely Shiguango. We agree to start a community-based tourism proposal that includes and incorporates certain aspects of successful tourism experiences in the Amazon, similar to the Napo Cultural Center that can be implemented in the Chontapunta area of the Tena canton in the province of Napo, in order to provide development alternatives to the communities in that area, mainly women. This model is incorporated as a proposal that has been strengthened with this project. This is how Humu Environmental and Tourist Interpretation Center was born, whose main offer is environmental education complemented with community-based tourist services. Humu shows the ichthyological richness and the biodiversity of the main rivers and tributaries of the upper Napo River area in order to raise awareness about poaching and indiscriminate fishing that restricts the communities' food source. 14 women and 10 men from the Runashitu community participate in Humu, led by Nely. The Humu Project is completing its construction phase, and with the leadership of Nely, the community organization carries out intense workdays, women carry out the same activities as men, they take care of all the details, including the preparation and service of food during mingas. Mainly women are leading the process of providing the Humu tourism service from the community, who have received training in administration and other operational matters to guarantee the success of the project. In the future, food, lodging and tourist transportation services will be incorporated, without a doubt they will put into practice the new knowledge and show all their capacity and commitment in the development of this proposal. Kichwa women sailing in the lagoon with tourists. Runashito Community. Napo. Story of Darwin Licuy, local tourism technician - Please provide links to publications, leaflets, video materials, related website, newsletters, or other communications assets published on the web. http://infonapo.org/ https://www.kallari.com.ec/ https://www.winak.org/ https://www.tsatsayaku.com/ https://www.youtube.com/watch?v=9GnK07YIhvY http://www.fao.org/gef/news-events/detail/es/c/1154402/ http://www.fao.org/ecuador/noticias/es/ http://www.runatupari.com/index.php/nuestros-tours/por-destino/nacionales.html https://www.youtube.com/watch?v=uwR-sX7R7Zc - Does the project have a communication and/or knowledge management focal point? If yes, please provide their names and email addresses Kelvin Cueva Rojas Kelvin.cuevarojas@fao.org

Innovative Approaches

Please provide a brief description of an innovative approach in the project / programme, describe the type (e.g. technological, financial, institutional, policy, business model) and explain why it stands

out as an innovation.

Virtuous articulation between incentives, associative ventures and forest conservation. The articulation of non-monetary incentives such as technical support, training, supplies, materials, equipment and other basic adjustments. As well as the support to the strengthening of associative ventures under the value chain approach (application of good practices in each of the links of the value chains) have allowed to improve the efficiency and marketing of biodiversity goods and services in a sustainable way , generating complementary income for partners. In return, the enterprises have established forest conservation agreements, which improve the environmental responsibility of the initiatives and the conservation of the natural capital base of the enterprise. As an example of the project's support for community tourism ventures; it can be emphasized that the tourist activity in Napo and in the Ecuadorian Amazon is directly related to the state of conservation of the natural attractions on which it is developed. Therefore the linking of conservation agreements for tourist use yielded the greatest results in forested areas conserved, which contributed to the project effect calculations to reduce emissions and conserve forest carbon stocks. In addition to the local and global benefits of climate change mitigation, the signing of these agreements represented an opportunity for community tourism ventures to access various incentives that allowed improving infrastructure and service provision. As well as to add value by promoting the environmental responsibility of the ventures before national and foreign tourists.

Co-Financing Table

| Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement / approval | Actual Amount Materialized at 30 June 2020 | Actual Amount Materialized at Midterm or closure (confirmed by the review/evaluation team) | Expected total disbursement by the end of the project |
| --- | --- | --- | --- | --- | --- | --- |
| Local Government | GAD Provincial Napo | Cash | 3.972.660,00 | 3.100.000,00 | 3.100.000,00 | 3.100.000,00 |
|  |  | In-kind | 2.015.000,00 | 1.600.000,00 | 1.600.000,00 | 1.600.000,00 |
| Local Government | Ministerio del Ambiente | Cash | 2.005.533,00 | 950.000,00 | 950.000,00 | 950.000,00 |
|  |  | In-kind | 930.467,00 | 460.000,00 | 460.000,00 | 460.000,00 |
| Local Government | GAD Tena | Cash | 90.000,00 | 50.000,00 | 50.000,00 | 50.000,00 |
|  |  | In-kind | 80.000,00 | 60.000,00 | 60.000,00 | 60.000,00 |
| Local Government | GAD Quijos | In-kind | 78.480,00 | 80.000,00 | 80.000,00 | 80.000,00 |
| Local Government | GAD Archidona | Cash | 80.000,00 | 50.000,00 | 50.000,00 | 50.000,00 |
|  |  | In-kind | 86.364,00 | 70.000,00 | 70.000,00 | 70.000,00 |
| Local Government | GAD Arosemena Tola | Cash | 35.000,00 | 35.000,00 | 35.000,00 | 35.000,00 |
|  |  | In-kind | 30.000,00 | 40.000,00 | 40.000,00 | 40.000,00 |
| Local Government | GAD El Chaco | Cash | 45.000,00 | 45.000,00 | 45.000,00 | 45.000,00 |
|  |  | In-kind | 175.000,00 | 80.000,00 | 80.000,00 | 80.000,00 |
| Local Government | GAD Cuyuja | Cash | 22.000,00 | 25.000,00 | 25.000,00 | 25.000,00 |
|  |  | In-kind | 5.000,00 | 15.000,00 | 15.000,00 | 15.000,00 |
| Public enterprise | COCASINCLAIR EP | Cash | 600.000,00 |  |  |  |
|  |  | In-kind | 400.000,00 | 20.000,00 | 20.000,00 | 20.000,00 |
| Cooperation Agency | GIZ | Cash | 140.000,00 | 180.000,00 | 180.000,00 | 180.000,00 |
|  |  | In-kind | 560.000,00 | 200.000,00 | 200.000,00 | 200.000,00 |
| Cooperation Agency | USAID | Cash | 50.000,00 | 50.000,00 | 50.000,00 | 50.000,00 |
| NGO | Rainforest Aliance | Cash | 500.000,00 | 500.000,00 | 500.000,00 | 500.000,00 |
| ONU Agency | FAO | Cash | 420.000,00 | 800.000,00 | 720.000,00 | 800.000,00 |
| Academy | UEA | In-kind |  | 20.000,00 | 20.000,00 | 20.000,00 |
| State Agency | IGM | In-kind |  | 10.000,00 | 10.000,00 | 10.000,00 |
| State Agency | IEE | In-kind |  | 15.000,00 | 15.000,00 | 15.000,00 |
| Consortium of Provincial GADs | CONGOPE | In-kind |  | 15.000,00 | 15.000,00 | 15.000,00 |
| Association of cantonal GADs | AME | In-kind |  | 6.000,00 | 6.000,00 | 6.000,00 |
| NGO | Maquita Cuchunchi | In-kind |  | 10.000,00 | 10.000,00 | 10.000,00 |
| Local Government | GAD Cosanga | In-kind |  | 13.000,00 | 13.000,00 | 13.000,00 |
| Local Government | GAD Hatun Sumaco | In-kind |  | 8.000,00 | 8.000,00 | 8.000,00 |
| Academy | IKIAM | In-kind |  | 60.000,00 | 60.000,00 | 60.000,00 |
|  |  | TOTAL | 12.320.504,00 | 8.567.000,00 | 8.487.000,00 | 8.567.000,00 |

Please explain any significant changes in project co-financing since Project Document signature, or differences between the anticipated and actual rates of disbursement Until the report of this PIR, a counterparty valuation is estimated, both in cash and in kind, which reaches 70% of the co-financing budget established upon project approval. This assessment is verified based on the co-execution reports of the letters of commitment and agreements with the different partners of the project, such as: Provincial Government, Cantonal Governments, Parish Governments, and alliances and joint activities carried out with public entities, NGOs. , Universities and other entities of International Cooperation. There are two main factors that have limited reaching the total initial co-financing of the project, on the one hand, the changes of authorities of the Decentralized Autonomous Governments (GADs), and on the other, the reduction and / or suspension of the incentive programs national and the adjustments of the GADs budgets from the economic crisis that the country has been facing since 2016; aspects that have been reported in the different PPR and PIR reports. These circumstances have been managed, based on the mitigation actions foreseen in the project's risk matrix, which include: permanent socialization of the activities, processes and results of the project with the new authorities; active participation of counterpart technicians and decision makers in the project works and spaces; generation of new letters of commitment and alliances to promote the results generated; and the establishment of policies, plans and regulatory frameworks to ensure the linking and continuity of actions from the management of local partners; among other. In this sense, the achievement of approximately 70% of the proposed budget constitutes an important advance in co-financing, thanks to the different actions promoted by the project team and the project's governance bodies such as the Management Committee (CGP) and the Steering Committee (CDP).

Annex 1. – GEF Performance Ratings Definitions

Development/Global Environment Objectives Rating – Assess how well the project is meeting its development objective/s or the global environment objective/s it set out to meet. DO Ratings definitions: Highly Satisfactory (HS - Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice”); Satisfactory (S - Project is expected to achieve most of its major global environmental objectives, and yield satisfactory global environmental benefits, with only minor shortcomings); Moderately Satisfactory (MS - Project is expected to achieve most of its major relevant objectives but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environment benefits); Moderately Unsatisfactory (MU - Project is expected to achieve of its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives); Unsatisfactory (U -  Project is expected not to achieve most of its major global environment objectives or to yield any satisfactory global environmental benefits); Highly Unsatisfactory (HU - The project has failed to achieve, and is not expected to achieve, any of its major global environment objectives with no worthwhile benefits.)

Implementation Progress Rating – Assess the progress of project implementation. IP Ratings definitions: Highly Satisfactory (HS): Implementation of all components is in substantial compliance with the original/formally revised implementation plan for the project. The project can be resented as “good practice”. Satisfactory (S): Implementation of most components is in substantial compliance with the original/formally revised plan except for only a few that are subject to remedial action. Moderately Satisfactory (MS): Implementation of some components is in substantial compliance with the original/formally revised plan with some components requiring remedial action. Moderately Unsatisfactory (MU): Implementation of some components is not in substantial compliance with the original/formally revised plan with most components requiring remedial action. Unsatisfactory (U): Implementation of most components is not in substantial compliance with the original/formally revised plan. Highly Unsatisfactory (HU): Implementation of none of the components is in substantial compliance with the original/formally revised plan.

As per FPMIS

In case of a project extension.

Actual date at which project implementation ends/closes operationally  -- only for projects that have ended.

This is the total amount of co-financing as included in the CEO document/Project Document.

Please see last section of this report where you are asked to provide updated co-financing estimates. Use the total from this Section and insert  here.

Please note that the Tracking Tools are required at mid-term and closure for all GEF-4 and GEF-5 projects. Tracking tools are not mandatory for Medium Sized projects = < 2M USD at mid-term, but only at project completion. The new GEF-7 results indicators (core and sub-indicators) will be applied to all projects and programs approved on or after July 1, 2018. Also projects and programs approved from July 1, 2014 to June 30, 2018 (GEF-6) must apply core indicators and sub-indicators at mid-term and/or completion

This is taken from the approved results framework of the project. Please add cells when required in order to use one cell for each indicator and one rating for each indicator.

Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

To be completed by Budget Holder and the Lead Technical Officer

Outputs as described in the project logframe or in any updated project revision. In case of project revision resulted from a mid-term review please modify the output accordingly or leave the cells in blank and add the new outputs in the table explaining the variance in the comments section.

As per latest work plan (latest project revision); for example: Quarter 1, Year 3 (Q1 y3)

Please use the same unity of measures of the project indicators, as much as possible. Please be extremely synthetic (max one or two short sentence with main achievements)

Variance refers to the difference between the expected and actual progress at the time of reporting.

Development/Global Environment Objectives Rating – Assess how well the project is meeting its development objective/s or the global environment objective/s it set out to meet. For more information on ratings, definitions please refer to Annex 1.

Implementation Progress Rating – Assess the progress of project implementation. For more information on ratings definitions please refer to Annex 1.

The LTO will consult the HQ technical officer and all other supporting technical Units.

Important: please note that if the Environmental and Social Risk classification is changing, the ESM Unit should be contacted and an updated Social and Environmental Management Plan addressing new risks should be prepared.

GEF Risk ratings: Low, Medium, Substantial or High

If a risk mitigation plan had been presented as part of the Environmental and Social management Plan or in previous PIR please report here on progress or results of its implementation. For moderate and high risk projects, please Include a description of the ESMP monitoring activities undertaken in the relevant period”.

Minor adjustments to project outputs can be made during project inception. Significant adjustments can be made only after a mid-term review/evaluation or supervision missions. The changes need to be discussed with the FAO-GEF Coordination Unit, then approved by the whole Project Task Force and endorsed by the Project Steering Committee.

Innovation is defined as doing something new or different in a specific context that adds value

Sources of Co-financing may include: Bilateral Aid Agency(ies), Foundation, GEF Agency, Local Government, National Government, Civil Society Organization, Other Multi-lateral Agency(ies), Private Sector, Beneficiaries, Other.