# UNEP GEF PIR Fiscal Year 18

(1 July 2017 to 30 June 2018)

- PROJECT GENERAL INFORMATION

| Project Title: | Global Forest Watch (GFW) |
| --- | --- |

| Executing Agency: | World Resources Institute |
| --- | --- |

| Project partners: | Ministry of Environmental Protection and Agriculture (MEPA) of Georgia, Ministry of Environment, Ecology and Forests (MEEF) of Madagascar |
| --- | --- |

| Geographical Scope: | Global – Georgia, Madagascar |
| --- | --- |

| Participating Countries: | Georgia, Madagascar |
| --- | --- |

| GEF project ID: | 5356 | IMIS number*: | GFL-11207-14AC0003-4E15 |
| --- | --- | --- | --- |
| Focal Area(s): | Multi-focal area (BD, CC and LD) | GEF OP #: |  |
| GEF Strategic Priority/Objective: | Ecosystem management, Climate Change, Environment under Review | GEF approval date*: | August 2015 |
| UNEP approval date: | September 2015 | Date of first disbursement*: | August 2016 |
| Actual start date: | October 2015 | Planned duration: | 36 months |
| Intended completion date*: | September 2018 | Actual or Expected completion date: | September 2019 |
| Project Type: | Full Size Project | GEF Allocation*: | $ 5,342,465 |
| PPG GEF cost*: | $ 136,987 | PPG co-financing*: | $ 0 |
| Expected MSP/FSP Co-financing*: | $ 27,894,000 | Total Cost*: | $ 33,236,465 |
| Mid-term review/eval. (planned date): | October 2017-Feb 2018 | Terminal Evaluation (actual date): |  |
| Mid-term review/eval. (actual date): | Feb 2018 – May 2018 | No. of revisions*: | 0 |
| Date of last Steering Committee meeting: | October 13, 2017 | Date of last Revision*: | N/A |
| Disbursement as of 30 June 2018*: | $ 1,707,009 | Date of financial closure*: | N/A |
| Date of Completion*: | N/A | Actual expenditures reported as of 30 June 2018: | $2,019,268 |
| Total co-financing realized as of 30 June 2018: |  | Actual expenditures entered in IMIS as of 30 June 2018*: | $ 1,683,035 |
| Leveraged financing: | $1,060,000 |  |  |

| Project summary | Maintaining and expanding global forest cover are critical aspects in supporting human livelihoods and planetary stability, since forests represent key components of local livelihoods and economies, carbon storage, water management and storehouses of biodiversity. Despite these extraordinary, and in many cases, irreplaceable values, high levels of deforestation and forest degradation continue. In response to these persisting challenges, WRI decided in 2011 to relaunch Global Forest Watch (GFW), a system for monitoring forest cover change that had first been developed in 1997. A prototype of the new GFW was presented at Rio+20 in 2012. Key partner organizations and financial donors joined in a Partnership, the first meeting of which was held in September 2013. In February 2014, following an active period of site development, the GFW beta website was officially launched. Through GFW, WRI and its partners seek to ignite a forest management transparency revolution by dramatically improving the availability and accessibility of forest information worldwide. GFW applies cutting-edge science and technology to generate the timeliest, most precise, and most reliable information available about what is happening in the world’s forests. The GFW platform is offering billions of people unrestricted access to this information in decision-relevant and actionable formats. The overall goal of the GFW effort—to which the GEF project contributes—is to reduce deforestation and improve rural livelihoods by transforming forest management and conservation at a global scale. The project objective is to empower decision-makers in government, the private sector, and civil society with technology and information necessary to reduce deforestation and land degradation, combat illegal activities, and conserve biodiversity in pilot countries and on a global scale. The project aims to address key barriers to better information availability and use, building upon existing resources, and developing innovative and technically advanced and user-friendly tools. In addition, it engages proactively with strategic user groups including government agencies, business and local NGOs to ensure that the information is used effectively and lessons learned are shared globally to accelerate progress elsewhere. The project operates at two distinct, but inter-connected geographic levels, namely global and national. Global-level activities are distributed across each of the project’s four components, while national-level, or pilot country, support to Georgia and Madagascar is concentrated within Component 1. Each pilot country offers important global benefit and demonstration opportunities. The Madagascar pilot supports conservation of that country’s critical and highly endemic biodiversity, while work in Georgia helps to demonstrate GFW’s potential contribution to sustainable use and conservation of Mediterranean forests, with significant replication opportunities. At the pilot country level, GEF support enables “deep dive” partnerships to achieve sustained impact, including through long-term partnerships with government agencies, civil society and the private sector. Forest stakeholders, including governmental officers, civil society, donors and buyers of commodities, in the pilot countries acquires capacity and gain easy access to near-real-time and reliable data to support their forest conservation, sustainable forest management, REDD+ efforts and risk management. The project includes the following components: • Component 1: Application and enhancement of GFW globally and in pilot countries • Component 2: System uptake and replication • Component 3: Strengthening and sustaining the GFW partnership • Component 4: Private sector application to reduce deforestation in key commodity sector supply chains |
| --- | --- |

| Project status FY16 | At the global level the project improved the quality of data available on the platform, the usability of the platform and its uptake among key stakeholders. Application and Enhancement of GFW: Improving data Through the first half of 2016, the GFW team added a ground-breaking new alert system to the platform that identifies tree-cover loss quicker and more precise than has ever been made available anywhere. In addition, the team provided context for tree loss data by improving visualization of plantations and fires. In March, the GFW team released the first Landsat-based alert system for tree cover loss: GLAD alerts, created by the GLAD (Global Land Analysis & Discovery) lab at the University of Maryland. While most existing loss alert products use 250-meter resolution MODIS imagery, GLAD alerts have a 30-meter resolution and thus can detect loss at a much finer spatial scale. New alerts are flagged whenever new cloud-free images are available (as often as every 8 days for every place on earth), and updated weekly on the GFW site. At this stage alert were only available in 3 pilot areas. The high resolution and frequent updates of the GLAD alerts posed a technical challenge for display and analysis on the website, and the team began work to overcome those challenges by restructuring the storage of the data. Also during this period, new data on land use help to put tree loss in context. The GFW team worked in partnership with Transparent World to map tree plantations in Brazil, Cambodia, Colombia, Indonesia, Liberia, Malaysia, and Peru for the years 2013 and 2014. This dataset, released in early 2016, provides important information on the drivers of tree cover change and helps delineate loss of natural forests from harvesting of tree plantations such as oil palm, rubber, and acacia. GFW also added updated data on aboveground woody biomass density. More recently, the team added data on mining concessions for Mexico, Brazil and Peru, a big step forward in increasing transparency on land use in Latin America, which has proven crucial for stopping illegal deforestation. GFW also continued to work with local organizations and governments to incorporate nationally-relevant land use data to better understand the drivers and legal status of tree cover change. New datasets include Congo Basin logging roads, Peru protected areas, Peru buffer zones, New Zealand land rights data, Sarawak protected areas, and Amazon Basin indigenous territories and mining concessions from Red Amazónica de Información Socioambiental Georref erenciada (RAISG). GFW also updated Liberia logging concessions and palm oil concessions data based on new information. System Uptake and improved usability In response to consistent user feedback, GFW launched the “My GFW” feature in February, which allows users to create a log-in to tailor their GFW experiences to meet their specific needs. For example, users can now upload their own shapefile to GFW and subscribe to alerts related to that area of interest. Users can also view and manage alert subscriptions. This feature will save time for users who regularly return to GFW for monitoring activities. It also lays the foundation for additional features that will provide targeted updates to policy makers or researchers depending on their specific interests across all GFW platforms (climate, fires and commodities). In June 2016, GFW released a 'how to portal' that provides users easy access to a wealth of educational materials on how to use GFW. Users can search for content in a variety of ways, including by function, application, and by popular search. The 'how to portal' deepens users' engagement with GFW, helping them more quickly learn how to use GFW to meet their specific needs. The 'how to portal' also provides the space needed to house additional tutorial materials (e.g., videos, instructional text, FAQs, etc.) for the growing GFW platform. Early in 2016, the GFW team launched its third round of the 'Small Grants Fund', selecting 11 high-impact projects from over 600 applicants from 95 countries. The selected grants cover a wide range of geographic areas and topics to advance the future of forest monitoring. For example, Global School Net Foundation built ties between classrooms in the United States, Russia, Canada, Taiwan, Brazil, Uruguay and Ghana by training high school students in investigative journalism techniques using GFW. Similarly in Ecuador, Regional Water Fund FORAGUA improved the local management, monitoring, and enforcement of 11 municipal watershed reserves by providing training on GFW to environmental technicians, high school science teachers, and journalists. A full description of recipients is available at: http://blog.globalforestwatch.org/gfw-community/announcing-the-2017-small-grants-fund-recipients.html Communicating GFW’s success November 2015 to June 2016, GFW was cited in over 700 media reports as a resource for understanding changes in forests globally. Early in 2016, the addition of GLAD alerts generated notable media interest with coverage in Nature, Reuters (cross-posted by a number of outlets, including The Guardian, Jakarta Globe, Business Insider), Phys.org, Mongabay and Take Part. In addition, an editorial by GFW director Crystal Davis detailing partnerships that are working to end deforestation was published in The Guardian. In April, GFW experts and others partners published a new article in Science Advances, “Tracking changes and preventing loss in critical tiger habitat”, using data available on Global Forest Watch. The study examined forest loss in tiger habitats, finding that tigers lost only 8 percent of their habitat in the past 14 years, much lower than expected. Researchers found that proper monitoring and conservation tactics could help tiger populations to double or even triple from their current number of 3,500. The paper and its accompanying blog were covered by the Guardian, Christian Science Monitor, Vice, Mother Nature Network, The Times of India, FOX News, International Business Times, ScienceNews, The Mirror, Inverse and Newsy. GFW team members in Indonesia also helped place the analysis in Tempo, The Jakarta Globe, and published an Op-Ed in the Jakarta Post on policy recommendations for Indonesia... In June, the launch of the PALM (Prioritizing Areas, Landscapes and Mills) Risk Tool on GFW Commodities drove notable news coverage. The tool reveals points in companies’ palm oil supply chains that are most likely to be associated with past and potential future deforestation. The team collaborated with Unilever for the launch, publishing a blog, press release, a collection of graphics, a step-by-step user guide, and a technical note. The story was covered by Reuters, Sustainable Brands, The Daily Mail, TakePart, Edie.net, TriplePundit, Mongabay, the Borneo Post, and UnDark. Strengthening GFW Partnerships The 3rd Annual GFW Partnerships Meeting (February 2-3, 2016) brought together 133 participants representing more partners than ever before, including new partners from Georgia and Madagascar. Notably, more private sector partners involved in supply chain management joined the event. The meeting succeeded in its four key objectives: (1) critically reflect on progress to date, including key successes and challenges; (2) solidify objectives for the next phase of GFW development (2016-18); (3) provide feedback and input to enhance GFW’s value and impact; and (4) strengthen the GFW partnership and identify new opportunities for collaboration. A complete meeting note is included as an attachment to this report. The GFW partnership network continued to grow, reaching a total of 94 contributing organizations. In March the team launched a high profile partnership with Cargill to monitor and manage deforestation and water risk across supply chains; initial work will focus on supply chains for soy in Paraguay and palm oil in Indonesia, which have high deforestation risks. Private sector engagement to prevent deforestation WRI launched the PALM (Prioritizing Areas, Landscapes and Mills) Risk Tool on the GFW Commodities platform at the RSPO European Roundtable in Milan on June 8, 2016. Developed in collaboration with Daemeter and Proforest and piloted with Unilever, the PALM Risk Tool illuminates points in companies' palm oil supply chains that are most likely to be associated with past and potential future deforestation. With this information, companies can proactively manage their supply chains – identifying highest priority areas to engage with suppliers to reduce and eliminate deforestation associated with palm oil production. Follow up on this tool led to deeper engagement with Proforest, Daemeter, and IDH (Sustainable Trade Initiative), and a subset of companies (including Cargill and Unilever) from the IDH-convened Traceability Working Group, to develop a conceptual prototype for a verification platform. This platform will facilitate the controlled exchange of "verification reports" commissioned by companies, particularly for suppliers listed as "high risk/priority" based on risk assessment results from the PALM Risk tool. This led to additional collaboration in 2017 (see below.) Structure To ensure smooth implementation of the project one of the earliest activities was the hiring of a project coordinator, Gabrielle Nussbaum. Pilot Countries In our pilot countries, WRI made progress to situate the GFW project and build stakeholder engagement. In both countries, an inception workshop, steering committee meeting and technical meetings were held and meetings were also held in the relevant ministries to ensure government cooperation and buy-in for the project. In addition, we conducted a thorough search for a GIS research analyst to be based in DC and provide support for the technical, data analysis, and national forest data management project objectives for Georgian and Madagascar. In FY16, the search was narrowed to two final candidates and a final candidate was hired at the beginning of FY 17. Georgia Workshops and Meetings WRI and the Ministry of Environment and Natural Resources Protection (MoENRP) jointly organized an inception workshop on March 2, 2016. Points discussed were the present situation of forest information systems in Georgia and the critical data and analytical needs. Representatives from MoENRP, Forest Policy Service, UNIQUE, Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ), Forest Inventory Department (NFA), the Adjara Environment and Natural Resources Department, Caucasus Environmental NGO Network (CENN), International Union for Conservation of Nature (IUCN) and WRI gave presentations during this meeting. WRI worked with in-country consultant, Ekaterine Nakashidze, to organize the cooperation between WRI, the ministry and other stakeholders. In June 2016 an advisory meeting was held to review the project's progress and provide recommendations. The advisory board recommended that further representatives should be added to the steering committee from additional organizations (Austrian Development Agency, DES, WWF, Adjara Forest Agency, Ministry of Justice). The committee also advised that capacity building in GIS and remote sensing should be a strong part of the project. Partnerships An MoU between WRI, GIZ and MoENRP was drafted and under review. CENN informally agreed to become a partner in the GFW project and negotiations were underway for CENN to act as a host institution for project activities in Georgia. Personnel WRI developed a project plan and conducted national searches within Georgia for key positions, with input from the ministry. Members of WRI, CENN and the ministry formed a recruitment committee, which chose top applicants and held interviews at the CENN office. In June 2016, WRI recruited intern, Moon Herrick, for one month. The intern started the process of GIS research, gathering and organizing data for the Georgia forest atlas, and building the first draft atlas. Madagascar Workshops and Meetings WRI and the Ministry of Environment, Ecology and Forests (MEEF) jointly organized an inception workshop and a project steering committee meeting. At the inception meeting, WRI presented the overall project and the roles WRI and MEEF will play in executing the project. Attendance included international and national NGOs, government, donor and private sector stakeholders. In addition, a representative from Project Manondroala (a collaboration between project partners, Finnish Association for Nature Conservation and Transparent World) presented on their expertise in remote-sensed data collection and validation in Madagascar, focusing on mapping forest degradation. The workshop attendees discussed the benefits of the project for Madagascar, particularly MEEF. Participants also stressed the potential risks of the project as lack of uptake by important user groups and capacity to sustain project objectives after the end of the project. The following day a smaller group of potential partners in the project convened to discuss project details. WRI presented details on the project objectives and budgets. Representatives from MEEF and the key offices and departments discussed who is mandated to fulfil certain roles and who has the expertise to help complete project objectives. This smaller group agreed to convene as the national steering committee for the project implementation in Madagascar and to meet regularly to advise project development. During the week of the inception workshop, the Prime Minister of Madagascar was forced out of office and a new Prime Minister was appointed. This change in government produced confusion at the project level due to likely changes of the minister and other heads of offices and departments. There is now a new Minister of MEEF and a new project focal point (Director of the Office of Climate Change Coordination). Partnerships WRI signed a subagreement with the Missouri Botanical Garden to act as the host institution for WRI activities in Madagascar. Discussion of an MOU between MEEF and WRI began to delineate the expectations and responsibilities of each party in the project. Personnel In consultation with representative from MEEF and MBG, WRI conducted a national search for a Malagasy National Coordinator for WRI's role in the project and narrowed the search to two final candidates after three phone/video interviews and candidate presentations. WRI presented an offer to the top candidate, but he accepted an offer from a private sector opportunity. The second candidate did not pass the reference stage of the process. WRI hired a consultant, Lucienne Wilmé, to manage daily activities of the project and spearhead the search for new candidates. |
| --- | --- |

| Project status FY17 | Progress FY 2017 yielded major developments for the Global portion of the project, the Global Forest Watch partnership and platform, both in terms of monitoring capabilities and mobilization. Top highlights include: A major breakthrough in near-real-time monitoring. GFW launched a weekly, 30-meter resolution deforestation alert system produced by the University of Maryland in a pilot study last March and expanded the product after significant work to host the heavy data load of weekly, high resolution alerts at scale. The alerts have now expanded to cover 15 countries in key forest biomes (Peru and Brazil in the Amazon, the Countries of the Congo Basin, Insular South East Asia, and the Russian Far East). The team is working to expand the coverage The team also created an image service for GLAD alerts, enabling users to easily import alerts into external data platforms. The Peruvian Ministry of Environment, the Zoological Society of London, and Greenpeace are using this image service. The GLAD alert system detects recent tree cover loss with unprecedented speed and precision, and presents the biggest opportunity for user mobilization since the launch of GFW in 2014. GFW partners are already captivated by the possible applications of GLAD alerts. GLAD alerts are already driving deeper engagement from users and catalyzing new partnerships. Online users who view GLAD alerts stay on the website 10 minutes longer on average and are almost twice as likely to return to GFW a second time. After GLAD alerts were released in Brazil and following targeted outreach efforts, user sessions from Brazil jumped to 15% of all sessions compared to 3% in previous months. Organizations around the world have been reaching out to WRI with interest to apply GLAD alerts in their work. New partners such as Interpol are working with WRI to design trainings for law enforcement agencies around the world. Greenpeace and Hivos are developing a major program to bring GLAD alerts to indigenous communities in Brazil and Ecuador. GFW’s private sector partners are eager to apply GLAD alerts for supply chain monitoring. In 2017, WRI developed tools and outreach strategies to facilitate uptake of GLAD alerts by GFW’s target audiences. Though the alerts are not yet available for Madagascar and Georgia those countries are priorities for the new round, currently under creation. GFW’s reach expands, while impact deepens. In September 2016, the GFW platform surpassed one million unique users. Website analytics show that more users are returning to the platform and engaging more deeply with key content. The GFW partnership also grew, now counting over 92 organizations from more than 23 countries. Meanwhile, WRI is accumulating a growing body of evidence documenting how partners and users are applying GFW data and technology to drive change. The Small Grants Fund has generated a fascinating array of impact stories (read them at globalforestwatch.org/small-grants-fund), from strengthening conservation policy in Brazil to securing community land rights in Nigeria. Other stories (often featured as ‘user profiles’ on the GFW blog) come from GFW partners or other organizations that seek out WRI to share their GFW experience. Together, these quantitative and qualitative measures of GFW’s reach and impact are informing smarter development and engagement strategies. A compelling vision and new momentum to achieve zero-deforestation commodity commitments. At the 2016 Partnership Meeting, GFW’s private sector partners issued a call to action. Following over a year of scoping, it was time to consolidate lessons learned and move towards industry-wide solutions for monitoring deforestation-free commodity commitments. The GFW Commodities and Finance teams crafted a concept note for the next phase of work, including creation of a new system that will unite GFW Commodities and Finance tools under a common platform. The platform will directly serve the day-to-day information management and decision-support needs of commodity companies and financial institutions. It will complement GFW’s public platform bringing greater transparency and accountability for commitments to reduce deforestation. In January at the World Economic Forum’s Annual Meeting 2017, GFW Commodities and Finance launched an international partnership to develop GFW Pro with 20 of the world’s largest commodity producers, traders, manufacturers, consultants, retailers, non-governmental organizations, research institutions and banks. A press release, article on WEF Forum Agenda, and presentation by WRI CEO Andrew Steer at the Tropical Forest Alliance’s action agenda meeting announced the new partnership. In March 2017, WRI presented the GFW Pro concept to the four biggest commodity trading companies in the world – Archer Daniels Midland, Bunge, Cargill and Dreyfus – at a meeting organized by the World Business Council for Sustainable Development. Rainforest Alliance, The Nature Conservancy (TNC) and The Forest Trust (TFT) joined the group to discuss opportunities for collaboration. All three NGOs aligned on strategy, with WRI focusing on scalable monitoring, measuring and management solutions in complement to Rainforest Alliance-led alignment on methodologies and TNC’s work on suitability planning for agricultural expansion In the second half of the year the team focused on design and establishing relationships with key user groups. Working with designers who specialize in private sector web tools, team completed more than 40 individual web pages and documented comprehensive requirements. GFW signed a contract with a web developer in March. Development will begin in early April; detailed web page and online architecture designs will be finalized by the end of April; and programming will continue through FY17. Public launch is tentatively planned in late 2017. The 2017 Global Forest Watch Partnership Meeting brought together 170 participants from 123 organizations in 29 countries (Argentina, Bolivia, Brazil, Cameroon, Canada, Central African Republic, Congo, Democratic Republic of Congo, Georgia, Germany, India, Indonesia, Liberia, Madagascar, Malaysia, Mexico, Netherlands, Norway, Peru, Singapore, Suriname, Switzerland, United Kingdom, Uganda, United States). The meeting represented the breadth of the partnership incorporating cutting-edge data and satellite imaging experts from the private sector with a community interested in reducing deforestation either from communities affected by it, or companies looking to reduce the footprint of commodities. The Major takeaways from the meeting included GFW’s commitment to making the most real-time forest data available accessible for on-the-ground actors who can respond to this data, and a new vision for a platform that enables businesses to more closely monitor and uphold zero-deforestation commitments. The Annual Global Steering committee meeting for this project followed the partnership meeting. In April 2017, the WRI Africa Forest Regional Meeting took place in Brazzaville, Republic of Congo to bring together over 50 WRI staff to exchange ideas on how to solve similar challenges, develop our next 5-year strategy for engagement in the continent and to share lessons learned and successes over the past two years. Staff from all nine countries and DC came together, including the team from Madagascar, our AFR100 management team, and staff from our new regional WRI office based in Ethiopia. Pilot Countries In Georgia and Madagascar, WRI made progress to create new partnerships and hire staff on-the-ground. In both countries, WRI strengthened its relationship with respective ministries and established additional relationships with relevant NGOs and civil society organizations. In addition, WRI hired GIS Research Analyst, Caio de Araujo Barbosa, who provides support for the technical and analytical objectives for Georgia and Madagascar. He also provides capacity building to stakeholders and to staff on-the-ground, working closely with the GIS technical Assistants hired in each country. Georgia Workshops and Meetings In August 2016, National Coordinator, Ekaterine Nakashidze, and Project Representative Gigia Aleksidze travelled to the Autonomous Republic of Adjara to meet with Deputy Minister Vakhtang Tsuladze and other members of the forest department in Adjara to understand the needs of the ministry and how the project can work in the region. In October 2016, four staff members from WRI's DC office visited Tbilisi, Georgia for one week. The outcomes of the trip were: (1) introducing all staff members to each other in-person to aid in future communications; (2) formally introducing all staff members to ministry officials; (3) providing training on GFW and showcasing its abilities to the MoENRP to better understand how it can be integrated into their workflows; (4) strengthening the project's partnership with GIZ and distributing tasks for the Forest Information Management System (FIMS) with UNIQUE; and (5) presenting the project's progress and discussing next steps at the project's advisory board meeting. In November 2016, Gigia Aleksidze attended the UNECE/FAO regional inception workshop for the project "Criteria and Indicators for Sustainable Forest Management in the Caucasus and Central Asia," in Yerevan, Armenia. Through his participation in the workshop, Gigia was able to introduce the project to new potential stakeholders, learn more about the UNECE/FAO project within Georgia, and see how the GFW Georgia project could work in collaboration. In February 2017, Gigia Aleksidze, presented GFW at a workshop for "Mainstreaming Biodiversity and Ecosystem Services in Eastern Europe and Caucasus;" a project funded by the Ministry of Foreign Affairs and the Ministry of Climate and Environment of Norway, and implemented by UNEP and the MoENRP. In March 2017, WRI hosted a workshop for NGO stakeholders to introduce the GFW project and find key alignments and areas of synergy. The workshop resulted in key partnerships with NACRES, Green Alternative and Ilia University to help conduct research for the project's use cases. In June 2017, WRI joined CENN and GIZ in a week-long journalist and media training on forest and deforestation issues, including using Global Forest Watch to monitor tree cover loss. In June 2017, Gigia Alekzidze attended the kick-off meeting for the EU Twinning Project, "Strengthening Sustainable Management of Forests in Georgia," where he presented the GFW project's activities, current status, and planned outcomes. Partnerships In July 2016, WRI signed a subagreement with CENN to act as a host institution for WRI's project activities in Georgia. In May 2017, WRI signed a second agreement with CENN to undertake fieldwork to monitor hazard hotspots in forested areas and to digitize old forest maps and identify border changes. WRI is currently reviewing subagreements with Centre for Biodiversity Research & Conservation (NACRES), Green Alternative, and Ilia State University to undertake fieldwork and spatial analyses regarding the project's use cases. These subagreements are on target to be signed in July 2017. WRI has received interest in a potential partnership by Azercosmos, the only satellite operator in the Caucasus. WRI is currently discussing with Azercosmos what this partnership would look like. Forest Atlas Development The Georgia forest atlas website has been developed and populated with data, and currently includes 74 spatial datasets. WRI established a central metadata catalogue system for existing datasets that can potentially be added to the atlas. Datasets acquired have been cleaned and translated, with metadata developed. Additional datasets are now being assessed for quality and relevance to the project. The domain forest.ge was acquired by the project for further use to redirect browsers from the domain to the Georgia forest atlas. In February 2017, GIS Research Analyst Caio de Araujo Barbosa visited Georgia to demonstrate the analytical capabilities of the forest atlas environment, interview ministry officials to better understand the analytical and data needs and to provide training and feedback on the developing atlas. Use Cases WRI is has drafted subagreements to work with partners NACRES, Green Alternative, Ilia State University, and CENN to perform field research and spatial analyses on 3 out of the 6 use cases: management of production forests, forest assessment inventory and monitoring, and protected area management. Subagreements with NACRES, Green Alternative and Ilia State University are still under review and work will start in the next fiscal year. A subagreement with CENN was signed in May 2017, with fieldwork recently starting in forest monitoring activities. Personnel WRI hired 3 key personnel in Georgia to carry out the project's activities. - National Coordinator, Ekaterine Nakashidze, represents WRI for the GFW project in Georgia and establishes partnerships with relevant NGOs, universities, civil society organizations and private sector companies. - Project Representative, Gigia Aleksidze, acts as a liaison between WRI and the different ministries in Georgia to ensure inter-sectoral cooperation and that the project is incorporated into ministerial workflows and fulfilling the ministries' needs. - GIS Technical Assistant, Nino Migriauli, collects and reviews datasets, cleans, organizes, standardizes and translates data, and uploads data into the atlas. Nino also provides input for the technical working group and will provide training on the atlas, once launched, to the ministry and other stakeholders that will use it. Madagascar Forest Atlas Development and Data Improvement The Madagascar forest atlas prototype is built and national datasets are being added to improve functionality. Three stakeholder workshops have been conducted (March and June 2017) with targeted user groups within MEEF and other partners to identify the data and analysis needs for forest and land use monitoring, the limitations and needs to improve capacity building, existing data quality protocols, and how to incorporate the system into the daily workflow of MEEF users. These workshops are an ongoing series to target the key stakeholders of the data inputs to the Madagascar Forest Atlas and subsequent workshops with additional stakeholders are planned for the beginning of FY18. In terms of data quality, the first workshop to start the process of “nationalizing” the UMD dataset was held in June 2017 and hosted by the national REDD+ office. The workshop included Peter Potapov (UMD) and Dmitry Askenov (TW) and their respective support teams as well as WRI staff from DC to help run the workshop. Workshop participants included a diverse set of GIS and forest technicians from different offices within MEEF, the official mapping institution (FTM) and the remote sensing and geography institute (IOGA). Participants learned the methodologies behind UMD dataset and started the initial process by validating 500 preliminary samples using Landsat, Google Earth and high resolution imagery. Use Cases and Communication of GFW Laura Vary presented at the Gestion des Zones Humides conference (Oct 2016) an analysis run by Caio de Araujo Barbosa of mangrove loss and potential scenarios for improvement and protection of the extent of mangroves in the Beony region of Madagascar using GFW data. We are currently expanding this analysis to include the entire mangrove distribution of Madagascar and will publish the results in peer-reviewed journal article. Lucienne Wilmé and Anjara Andriamanalina represented Global Forest Watch and WRI at America Week (April 2017) to celebrate 150 years of diplomatic relations between the United States and Madagascar. Lucienne Wilmé, Anjara Andriamanalina and Caio de Araujo Barbosa presented a poster at the National Forum for Research (June 2017) hosted by the University of Antananarivo. The poster shows an analysis on the need to nationalize forest data for Madagascar and received 4th place out of 49 posters judged during the event. Partnerships WRI signed a subgrant with the University of Maryland (UMD) for GLAD lab (Professor Hansen) to produce a national version of global forest watch for Madagascar with accuracy estimates to help with UNFCCC and REDD+ reporting. WRI also signed a subgrant with Transparent World (TW) to help support the development of this national version with their remote sensing expertise using high resolution imagery. Personnel and Team Structure WRI completed hiring for the project with Lucienne Wilmé as the National Coordinator and Anjara Andriamanalina as the GIS specialist. WRI attempted the role of project representative to the MEEF (Angela Tarimy) for a trial period of 3 months and received feedback from our government partners that it was not the appropriate personnel structure for the project, given the size and complexity of the ministry. We came to the agreement with the Secretary General of MEEF that focal points in the relevant government offices should be appointed to help complete the project activities in those offices. These people are currently being identified and appointed for the three offices we are working the most closely with in the Ministry: the National REDD+ office and two offices within Forest Department of MEEF. For future activities with new offices, focal points will be identified at the start of those activities. |
| --- | --- |

| Project status FY18 | Global Progress This year the global platform has continued to advance publicly available near-real time data, with a focus on transforming cutting edge data into actionable insights. We have also advanced uptake in many countries around the world in addition to the project pilot countries. Lessons from national implementation of forest monitoring tools support work in pilot countries and improve tool development for all users. New data improves Global Transparency for Forests The 2017 tree cover loss data is now available to view and analyze on the GFW map, and updated 2017 tree cover loss statistics are available on the global and country dashboards. The new data was paired with an in-depth blog in English, Spanish, Portuguese, French, and Bahasa Indonesia, as well as a technical blog focused on Brazil. This prominent launch generated more than 330 high-profile media stories in a week, the most public interest since 2014. Starting next quarter, GLAD alerts will be available for all Latin America between 30 degrees N and 30 degrees, which includes Central America, the Caribbean, Paraguay, Bolivia, and parts of Mexico, Argentina, and Chile. The expanded GLAD dataset, which is currently being tested on GFW’s staging website, will bring unprecedented forest monitoring capability to these countries; GLAD alerts already cover the Cong Basin and South-East Asia. Though the project team had requested of UMD researchers that they prioritize Georgia and Madagascar as pilot countries, however the process of finalizing the alerts is done most efficiently when applied to contiguous areas and strong requests were also coming from several government partners in Latin America and Asia. As a result the researchers decided that rolling the alerts out within the +30 to -30 degree latitudes for each continent at a time would provide the most coverage most quickly. They are expected to cover Madagascar by the end of 2018. Other new data shed light on the impacts of forest change. Updated Intact Forest Landscapes data show the current extent and location of intact forests and areas with shrinking intact forests since 2013. New biodiversity significant and biodiversity intactness data show 1) how important each pixel on the map is for conserving biodiversity using species range data on birds, mammals, amphibians and conifers; and 2) how close the current ecological community is to its natural state, based on models that measure how local biodiversity responds to human pressures. Read more about the new biodiversity data here. GFW researchers are now processing other new data layers from the University of Maryland including: - Soy cultivation for South America - Primary forest for Indonesia, Brazil and DRC - Advanced Very High Resolution Radiometer (AVHRR) record of forest change - Global biomass data (revision of Year 2000 global biomass layer from Woods Hole Research Center) Turning data into information How much natural forest is in Madagascar? Which states in Brazil had the most tree cover loss in protected areas? How much tree cover loss occurred in intact forest in Indonesia in 2016? The recently re-designed GFW country dashboards provide answers to these questions and many more. Using the interactive dashboards, users can produce new insights and customized analyses for their country or region of interest. According to Google Analytics, users of the redesigned country dashboards are more likely to interact with the dashboards by changing settings and using available features (65% increase in interactions), less likely to exit the website from these pages (exit rate decreased by 50%), and view more pages (188% increase in page views). Following the success of country pages, we released a new global interactive dashboard, which allows users to view and tailor global forest statistics to answer frequently asked questions about forest. For example, users can now view annual tree cover loss within Intact Forest Landscapes or tree cover within protected areas globally. Moreover, the backend architecture that supports the country dashboards provides a framework for this type of analysis for any area of interest. Over the coming year we’ll continue releasing global dashboards as well as dashboards for other important areas like watersheds and biomes. These types of analyses will also be made available for MapBuilder users to pull into their own customized apps. A new satellite imagery tool released this in June makes it easier to verify deforestation and fire alerts on GFW by comparing before/after imagery. Users can select a date range and minimum cloud coverage, and easily scan through all available images that meet the search criteria. MapBuilder updates support pilot countries The customizable analysis described above will now be available in MapBuilder – the system that powers all National Forest Atlases – as well as the main GFW platform. Users from pilot countries asked the team to include country specific analysis. For example, Liberia wanted to analysis its own land cover map, Georgia wanted to analyses fires in specific land classifications, Ethiopia its restoration potential. To do this the system needed to go beyond pre-set analysis, to analyze real-time satellite data with locally uploaded boundaries. Pilots countries like Madagascar and Georgia will now be able to do more locally relevant analysis more quickly. Thanks to the back-end work that enables country dashboards, these customizable analysis are already on the staging site and will become available for MapBulider users in the near future. Responding to User Demand with the Forest Watcher Mobile App The Forest Watcher app, which makes GFW data accessible in the field, launched and made a big impression: with over 3600 users in the first 6 months it has gained notable attention, most recently being named a finalist in Fast Company's 2018 World Changing Ideas. The team collected feedback from a variety of these initial users. This quarter we finished a second round of development on the app and released a new update with several improvements based on user requests, including those from field users in Madagascar. This includes adding UTM coordinates, improving the navigation function so that users can see their location in relation to alerts, and giving users the ability to create a report on their location. These features will make it easier for users to navigate to alerts and submit reports through the app. We also addressed several bugs including on the web platform of Forest Watcher. The application is designed specifically for users in the field and the feedback from users in Madagascar has been essential to tailor the application and their improvements to target users. New analyses position GFW to become a leader on forest insights Global Forest Watch has become well-known as a leading source of forest data, especially geospatial data. We now aspire to translate GFW data into actionable information and policy-relevant insights needed by decision-makers operating from global to local scales. The GFW research team is working to publish eight peer reviewed articles to advance forest monitoring. The 5 areas of research currently underway are: 1) A model for classifying tree cover loss according dominant driver Global Forest Watch researchers worked with The Sustainability Consortium to classify tree cover loss according to the dominant cause of disturbance, and submitted the results in a paper to Science, with the University of Maryland last quarter. This quarter the team addressed reviews and resubmitted. The model generated through this collaboration, as detailed in the paper, classifies loss within a 10-kilometer pixel and considers five causes of disturbance: (1) conversion to a new land use, i.e. deforestation; (2) forestry (e.g., selective logging); (3) wildfire; (4) shifting cultivation; and (5) urban expansion. To generate the model, researchers manually classified thousands of samples of tree cover loss to train an algorithm that can now determine the type of loss with an overall accuracy of 89%. This work will provide valuable insights on its own and is key to an improved empirical basis for measuring and tracking greenhouse gas fluxes from forests. The map will be published on GFW’s online platform in late 2018. 2) A global system for monitoring greenhouse gas fluxes from forests The world currently lacks a robust empirical basis for measuring and tracking GHG fluxes from forests to inform climate policy. The GFW team is working to develop an independent, spatially explicit forest carbon monitoring system drawing on available data and data. This research uses global gross forest area transitions (Hansen loss/gain), to comprehensively map gross and net GHG dynamics across the world’s 4 billion hectares of forest land between 2000 and 2015 based on data sources derived from both satellite and ground observations. This is different from what is visible on GFW Climate now because (a) it is global; (b) it uses the drivers map as a data input; and (c) it maps forest-related emissions, sequestration (CO2 removals) and the net between them in a more accurate way. The team hopes to submit this work to a journal later in the summer and release our findings at the UNFCCC COP in November 2018. 3) A method for estimating the greenhouse gas footprint of palm oil supply chains GFW and Unilever completed a pilot collaboration to estimate the land-use GHG footprint of their palm oil supply chain using GFW and other published data. New concessions boundaries received from WRI Indonesia/Greenpeace improved accuracy. The method calculated baseline emissions from 1990-2015 explored seven future scenarios considering potential factors such as sourcing only from RSPO mills, stopping deforestation by 2020, and removing palm oil sourced from peat soil. We expect that this method will have broader applicability for the sector and are exploring next steps with the company. WRI plans to apply this analysis to all known Palm Oil Mills and publish a paper with the results. 4) Preparation for GFW’s first annual forest update The data and analyses described above will feed into GFW’s first annual forest update, which we expect to release in the summer of 2019. This quarter the team ran analysis of many of the indicators and have moved on to the written explanation of the results. The update will provide indicators and analyses depicting important global forest trends, such as total tree cover loss, rates of change, and carbon emissions in more than 20 areas of interest. The results are intended to support implementation and monitoring of international commitments such as the New York Declaration on Forests and Paris Climate Agreement. GFW’s communication team has begun identifying key audiences, surveying stakeholders, and planning outreach. 5) Places to Watch Communications worked closely with research colleagues to produce two installments of the Places to Watch approach in 2018. The March edition focused on places in Indonesia, Cameroon and Brazil. Through our established “action network” and WRI country offices, the communications team engaged with actors on the ground to collect information about these locations. Within a month of posting the curated content on the GFW and WRI Insights blog, the piece had been read by over 1,200 people. Our team sent the content to over 2,000 journalists. Mongabay covered the Indonesia and Cameroon locations, conducting further investigation and interviewing the PTW “action network” partners we connected them with. A former Greenpeace staff member shared the Cameroon story widely with Central African NGOs and companies over email, highlighting the Cameroonian President's possible links to one of the highlighted agricultural projects. The June edition covered disturbances in Colombia, Brazil and Indonesian Papua. A new platform for business Despite some delays, the GFW Commodities and Finance (C&F) team continues to make steady progress on web development for the new supply chain management system, GFW Pro. This quarter we entered the final comprehensive testing stage for the GFW Pro Preview Period. Even before coming online, the tool is gaining wide recognition, thanks to the team’s intensive external engagement strategy. Recently the team finished the architecture for GFW Pro’s core functionality. All components of Pro's workflow are complete, including the Dashboard, Diagnostic and List View analyses, GFW datasets, and list editing functionality. Now, software engineers are troubleshooting final issues. The team is also finalizing the last development phase: user acceptance testing (UAT), a comprehensive test of the entire site by the GFW Commodities and Finance team. Web developers have already submitted a proposal for the next phase (Phase 1.1) of GFW Pro development; design and technical requirement revisions are underway. Phase 1.1 will focus on building final functionality into the application – such as sharing capacities and policy analysis – by the end of 2018. In addition, a comprehensive tracking infrastructure is built into GFW Pro, so we will be able to (anonymously) track site usage for monitoring and evaluation, as well as use-based improvement plans. The Preview Period launch is planned for fall 2018. During this period partner organizations will be onboarded with support and training from the GFW team. Examples of companies volunteering to participate include: April, Cargill, Colgate, LDC, IOI Loders-Bunge, Mondelez, Mars, Neste, Sudameris Bank, Votorantim Bank, Wilmar and others. The wide-scale public launch, which will make the product open to anyone without connections to WRI, is expected in late 2018. GFW Pro is pushing the limits of existing technology, private sector partners are seeking complex geospatial analysis of extremely large datasets. Calculations that would take weeks of GIS analysts’ time will now be delivered directly to GFW Pro users in matter of hours or days. Given the growing interest - a sign of market acceptance – the team is following technology industry’s best practices, taking a controlled approach to onboarding during the preview period to monitor the integrity and quality of the system’s delivery. The private sector demonstrates commitment to GFW Pro Walmart invited the GFW Pro team to present at Walmart’s annual flagship Milestone Sustainability Summit in April 2018. The event featured a public call from Walmart to approximately 500 suppliers in attendance to use GFW Pro to report against Walmart’s Project Gigaton commitments. Walmart Group made public endorsements of GFW Pro, John Furner (Sam’s Club CEO) called the platform “inspiring” and said: “We want to challenge everyone in the room and your peers to get involved”. Ruth Kimmelshue, Corporate Senior Vice President for Operations, Supply Chain and Sustainability at Cargill, said “You cannot manage what you cannot measure, so we needed some help and partnered with the WRI and GFW. Using WRI’s cutting edge technology we have mapped 166 million hectares of land surrounding almost 2,000 of Cargill’s locations. The analysis allows us our focus efforts where it matters and when it matters… Tools like GFW Pro are vital to companies as a means to measure and to report progress”. As we enter the preview period and work toward the late-2018 launch date, external engagement will build upon the team’s formalized initial outreach target list of 230 individuals from 84 organizations. The team is creating mechanisms for gathering user feedback and tracking user support requests, which will be operational for the preview period. The use of this standard solution will guarantee close tracking of users and deliver high-quality support for them in a structured manner. That engagement will be supported by training materials, which will initially be published as a clickable PDF with step-by-step instructions and screenshots, and will later be built into online system. The team also promoted GFW Pro at Conferences, presentations included: - TFA2020 General Assembly in Ghana - High Carbon Stock Association steering group in Malaysia - Adapt America Interamerican Development Bank (IDB) event in Panama - IDB Invest Sustainability Week in Lima, Peru - RSPO meetings in Kuala Lumpur - The Sustainability Consortium annual event in Chicago, Illinois - Roundtable on Responsible Soy - Febraban’s CIAB conference (the largest fintech event in Latin America) - Collaboration for Forests and Agriculture (CFA)/ Conservation and Financial Markets Initiative (CFMI) hosted event with Brazilian banks in Brasilia - RSPO European meeting in Paris. The team’s effort to increase collaboration among related transparency efforts is gaining momentum. GFW staff are working with Collaboration for Forests and Agriculture (CFA) and partners, reflected in participation and co-hosting of several workshops and meetings. WRI Forests Director, Rod Taylor, sits on the Accountability Framework Initiative (AFI) steering committee, and staff, Ryan Sarsfield and Caroline Winchester, represent WRI in several working groups and meetings. Luiz Amaral participated in a two-day AFI workshop on monitoring and reporting, co-hosted by Rainforest Alliance and TNC. WRI feedback was added and compiled into the AFI draft definitions and analysis document. ISEAL Alliance has committed to supporting trainings for member organizations; so far the tema has trained staff at RSPO, Fair Trade, Bonsucro, Better Cotton Initiative, Rainforest Alliance (now including UTZ) and Roundtable on Sustainable Biomaterials. These groups have also committed to being among the first users of GFW Pro. Finally, continued engagement with Mapbiomas in Brazil has resulted in the incorporation of its dataset into GFW website. GFW and Trase continue to explore how to best link our respective platforms and data offerings, focusing on the potential for place-focused (e.g. sub-national) analyses to connect our respective users with high-resolution data on forest impacts (from GFW) and the trade and actors involved with the forest-risk commodities in those areas. We anticipate the next steps will focus on inclusion of Trase data and links into the GFW Flagship, and collaboration around high-resolution soybean data recently produced by the University of Maryland. Pilot Countries In Georgia and Madagascar, the past year concentrated on making progress towards achieving the main project goals. In October 2017, we convened the third global steering committee for the project in Tbilisi, Georgia. Members of the global GFW team, UNEP, FAO, the team of Madagascar, and Georgian stakeholders met over 3 days to review the progress of the project so far, visited a proposed pilot site in Borjomi, and held the global steering committee meeting. The steering committee discussed the slow progress of the project, and the global team formally asked for a one-year extension to the project, including changes to the budget to better meet the project’s needs. The Georgia team also discussed proposed changes to the pilot region to include 4 additional regions to the originally planned region of Adjara and the Madagascar team discussed the issue of sustainability and long-term maintenance of the equipment being set-up within the Ministry of Environment. To support the no-cost extension, both pilot country ministries submitted letters of agreement for a one-year extension in order to achieve the goals of the project. In addition, the former GIS research analyst left his position and we rehired and filled the position with Richard Barad. Georgia Project Structure In November 2017, the Georgian government announced that it will be merging the Ministry of Environment with the Ministry of Agriculture. It is uncertain if and how these changes will affect the project and its stakeholders, with some ministry departments being dissolved while others remain in place. During the time the Global Forest Watch team held stakeholder meetings to mitigate any risks and participated in multiple government meetings to showcase the project to new ministry members and ensure that the project’s goals were integrated into the new ministry. More information about these government changes will be announced in the new year. Georgia Forest Atlas (Forest and Land-Use Decision System, FLUIDS) The Georgia Forest Atlas (http://geo.forest-atlas.org), called FLUIDS, is now live. Over 100 datasets has been acquired and data is being curated, cleaned and added to the atlas, as strategically determined. Our Georgia team has gathered user feedback and requests for new features on the system, including: new analytic tools and personalized abilities, such as language requirements, additional layer categories, and the ability to make data private. We have included these requests in next statement of work for the developers of Mapbuilder, which is currently set to be completed by September 2018. Currently a new staging site has been set up to migrate the Georgian data onto the new upgraded site and new analyses included thematic dashboards are still under development but are on target to be completed as scheduled. At the end of June, Richard Barad and Thomas Maschler travelled from the WRI headquarters in DC to install a virtual server at the Ministry of Environmental Protection and Agriculture and provide training on usage and maintenance of the server to Ministry staff. In addition, they team from DC worked with Georgia GFW staff, along with key stakeholders within the ministry, to identify further use cases for the portal, sketch out a mockup of the pages to include in the public facing side of the portal, and describe and assign additional tasks for the next quarter. A call for tender has been publicly released for the purchase of a server to host local data and once purchased, the virtual server will be migrated onto the newly installed server within the Ministry’s IT department. In addition, ESRI has granted the project’s request for a donation license of ArcGIS for Server and ArcGIS desktop licenses. Workshops and Meetings At the end of June and beginning of July 2017, WRI, along with partners CENN and the Austrian Development Bank, held a capacity building workshop targeting journalists of different types of media. The journalists were trained in current environmental and forestry issues, including use of the Global Forest Watch portal and the main Global Forest Watch platform and its features. Journalists were encouraged to create news stories from their learnings and a final competition was held to award the best stories published. Of the finalists, one of the journalists used GFW fire data to create a news story that was aired on local TV. Examples of these stories are included in the appendix. After the global steering committee meeting in October 2017, the project’s national advisory board held its meeting for Georgia. During this meeting the proposed changes of the one-year extension and pilot region changes were presented, and the board agreed to recommend these changes. The board also looked over the use cases of the project to ensure they were still relevant and decided that the original project use cases are still important in the Georgian context, although some revision may be required for the reforestation use case. Please see the notes of this meeting included in the appendix for more information. In February 2018, GFW held a workshop in Tbilisi for NGOs to identify further applicable use cases for the Georgia portal and to present on work that NGOs are currently doing to create data and test out the portal in use case areas. During the meeting new project concepts were discussed including analysis on zoological biodiversity and forest productivity for ecosystem services. The feasibility of these new projects is still being considered considering the timeline needed to complete the analyses. In March 2018, Gigia Aleksidze and Gabrielle Nussbaum travelled to Geneva, Switzerland to attend the UNECE Regional Forum on Sustainable Development. At this meeting, GFW staff contributed to the set on sustainable forests and ecosystems and Gigia Aleksidze presented on GFW as a use case during the side session focused on biodiversity. In April 2018, Fred Stolle and Gabrielle Nussbaum met with the new Minister of Environmental Protection and Agriculture. During this meeting, the GFW team presented the ongoing project and objectives as well as project progress and planned activities. During the meeting, the new Minister expressed support for the project and a willingness to work with the GFW team on the installment of the FLUIDS portal within the Ministry. During this same mission, a national steering committee meeting was held in which the committee discussed the progress of ongoing activities along with the use cases conducted with NGO partners. The GFW team reiterated the need for a no-cost extension during the meeting and the steering committee members expressed support for the extension. At the beginning of June 2018, Gigia Aleksidze, along with representatives from the Ministry of Environmental Protection and Agriculture and the National Forest Agency met with the Adjara Forest Agency to discuss the process of integration of the Adjara inventory data into the Georgia portal. During the trip, the team reviewed the forest management and timber tracking system developed for the Adjara region and discussed possibly means of displaying the data within the system in the FLUIDS portal. Further follow up discussion is required to link the two applications. Partnerships In August 2017, WRI signed partnerships with NGOs Green Alternative, NACRES, Caucasus Environmental NGO Network (CENN), and REC Caucasus. Green Alternative’s project, “Development of Biodiversity Monitoring System for Assessment of Forest Protected Areas,” will strengthen conservation efforts by further developing the National Biodiversity Monitoring System to improve protected area management. The study will better understand how much of protected areas support nature conservation and will help the monitoring, management and planning of protected areas. This project contributes to the “protected area management” use case of this project. NACRES’s project, “Supporting the Integration of Sustainable Forest Management of Practices in Georgia by Provision and Analysis of Key Data Using Remote Sensing Technologies,” will identify, classify and map Georgia’s key forest habitats to complete the process of establishing the Emerald Network in Georgia, supporting Georgia’s obligations under the Bern Convention. In addition, the project will promote responsible utilization of non-timber resources by identifying relevant important wildlife habitats using remote sensing and GIS to better understand the socio-economic implications of non-timber resource use. This project will add additional data layers to the Forest and Land Use Decision System (FLUIDS) portal and contribute to the “management of production forests” and “protected area management” use cases. CENN’s project, “Promotion of New Technologies and Information Communication Tools to Enrich Forest Management Information System,” looks at forest vulnerability analysis and mapping to better understand factors relating to forest degradation, based on GFW data and CENN’s Atlas of Natural Hazards and Risks in Georgia. The final map has been uploaded into the FLUIDS portal as a data layer to provide new insights. As a result of the project, CENN found that a legal logging license was granted in a high hazardous area, which was causing conflict with local residents. Mediation was held between the residents and the local and state government, resulting in the closure of this area to logging, with the company being given a new location in a low risk zone. CENN’s project also assessed lost forest territories by digitizing old forest stand maps (pre-2011) and comparing forest fund borders with those from present day to see where forests may have been lost and develop recommendations for corrections and create a policy dialogue. This project contributes to the “forest assessment inventory and monitoring” use case. In September 2017, WRI signed an MOU with REC Caucasus, stating our intent for the organizations to work closely together and for WRI to provide REC Caucasus with a space in the FLUIDS portal to create a soil degradation map. The MOU also states the intent of the organizations to work together on a project that will contribute to the “reforestation” use case. In November 2017, the Ministry of Environment and Natural Resources Protection of Georgia (MoENRP) signed a partnership agreement with WRI, which states that the organizations are partners and allows WRI to ask for a donation of ESRI software for the ministry. In May 2018, WRI partnered with GISLab, a GIS firm located in Tbilisi Georgia, to better understand how remote sensing can be used to detect selective logging. The firm is testing the accuracy and efficiency of a methodology, which if successful will provide useful data to add to the FLUIDS portal, increasing its capacity to monitor illegal logging in Georgia’s forests. Madagascar Partnerships and Forest Atlas WRI signed an MOU with the Ministry of Environment, Ecology and Forests in June 2018. The MOU will help speed up data sharing for the Madagascar Forest Atlas and details the technical support WRI will provide the Ministry. The Madagascar Forest Atlas(https://mdg.forest-atlas.org) currently has 11 contextual datasets and three land use datasets provided by the Ministry, including Protected Area boundaries. Now with the MOU in place, WRI is establishing a workflow to have continued updates of land-use data from the ministry. WRI will also have the updated tree cover loss dataset included once it is completed (see below for details on this training). Capacity building – training at University of Maryland for our partners A team from Madagascar traveled to the US for a training at University of Maryland (UMD); the team included six people: - two members from the Ministère de l’Écologie, de l’Environnement et des Forêts (MEEF); - one Professor from the Institut et Observatoire de Géophysique d'Antananarivo, University of Antananarivo (IOGA); - one person from Bureau National de Coordination Changement Climatique; - one person from Bureau National de Coordination REDD; - Anjara Andriamanalina, WRI, Institutional Relations Officer The training at UMD covered the following: Week 16 – 20 April 2018: sampling for assessing the deforestation in Madagascar, including: Landsat ARD and tree cover products and GLAD; Land cover definitions, sample interpretation legend, interpretation results and problems; Sample interpretation interface; Sample-based tree cover and change quantification for hundreds of samples; Refining sample interpretation, resolving interpretation for uncertain samples; Aggregation of the interpretation results, completing sample analysis; and Overview of the preliminary national statistical results Week 23 – 27 April 2018: mapping of the Madagascar forest cover and changes, including: GLAD Landsat data processing system; Practical implementation of change detection tools on PCI Geomatica interface, multi-temporal metrics, and change detection software; National forest cover and change mapping using image classification and implementation of decision tree algorithm and working with tree outputs and statistics; Forest Alerts, and Water Monitoring; and National forest cover and change mapping based on temporary categories. The team of six people organized a meeting by the end of May, inviting not only members of their organizations but also other project partners; together, they presented the results of the training and the next steps to be taken: 1) install two file servers from UMD at MEEF and IOGA; 2) organize the final training with the UMD team for August or September; and 3) determine the roles and responsibilities for MEEF staff after the final training to ensure the annual updates. The WRI team is currently working on the best way to import the file servers from UMD to Madagascar, including one to be based at IOGA, and one at the Direction Générale des Forêts, MEEF. Communication of GFW During the workshop in Morondava in September 2017, our team organized a video crew to get footage of the workshop, our partners and hands-on practice of using GFW tools and data in the field. The long version of this video can be found here. We also were able to share video footage with local news outlets and TVM Television Nationale Malagasy aired a story about how Malagasy are using GFW in the field on the evening news on November 22, 2017 and Radio Madagascar aired a similar story on the goals of the workshop on November 28, 2017. The team is working on a shorter version of the video to share more broadly on national social media and generate greater awareness of the project within Madagascar. Use Case Studies Case study: the dry forests of central Menabe See map showing the protected areas named below (yellow), the other protected areas (green) and the 22 regions of Madagascar. As expected, the global UMD algorithm for tree cover loss encountered problems when classifying the tropical dry forests of western Madagascar, which justified our main case study in the Menabe with Durrell Wildlife Conservation Trust (Durrell). We have teamed up with our partner Durrell during a new mission to the central Menabe the week 18 – 23 March 2018 during which we focused on the following: - Presentation on the use of the recent Forest Watcher application for the Durrell team in Morondava; Forest Watcher is the new application available on cell phone and tablets that incorporate fire and deforestation alerts. See http://forestwatcher.globalforestwatch.org/ - Training in the field on the use of Forest Watcher for the conservation practitioners; - Documentation of the activities lead by Durrell, including pictures, videos which were shared with our partners. Other case studies, and future activities Extended Menabe and Western Dry Forests. We are building on our experience with Durrell to extend the central Menabe case study to the North of the Tsiribihina River, to include the dry forests with a different structure than those from the Menabe Antimena protected area towards the Tsingy of Bemaraha National Park. We will also include the mangroves, and the riparian forests bordering rivers and lakes, together with the consortium of Durell working in the region, including World Wide Fund for Nature (already agreed), the Association Fanamby, Madagascar National Parks (also agreed), and the Direction Régionale de l’Écologie, de l’Environnement et des Forêts (DREEF) of the region Menabe (based in Morondava) and DREEF of the region Melaky. Deforestation has been increasing in this region at unprecedented rates and the ultimate goal is to see how GFW data, tools and analyses can help local actors like Durrell and the DREEF to address these issues. Humid forests. We are planning a case study with Madagascar National Partner (MNP) in Mantadia,and expect MNP to build a partnership with the diverse actors, including a local association Mitsinjo. MNP is a main partner of the GEF project (the largest co-financer) and the main administrator of protected areas throughout Madagascar. Northwestern humid and subhumid forests. A local association, Famelona (http://famelona.mg/), is active in the conservation and development of the Galoka-Kalobinono protected area in Northwestern Madagascar; here the conservation and research practitioners are engaged with local communities. We are currently working on the details of a partnership with Famelona to start a case study supporting the implementation of their activities, including law enforcement, patrols, ecological inventory with local communities, restoration, economical alternatives, agroforestry. Famelona is partering with the local authorities of Ambanja under the DREEF of the DIANA region. The Peregrine Fund (TPF) has been active in Madagascar since the 1990s, and has specialized on the protection of endemic birds, especially raptors (see https://www.peregrinefund.org/projects/madagascar-project). The NGO is currently engaged in the conservation of a biodiversity rich area in Northwestern Madagascar, at Bemanevika. We will plan our first meetings and site visits during the coming months. TPF is also partnering with Durrell, and the DREEF of the Sofia region. The watersheds and the coming ATBC congress With our project partner IOGA, and other institutions and departments of the University of Antananarivo, we will start a case study on a wide topic including the watersheds, the distribution of forests, and their biogeography during the paleoclimate oscillations to better understand the current pattern of distribution of the endemic fauna and flora. The research and application will be based on a large sample of maps, the forest cover through time, the distribution of many endemic species of plants, and animals, especially lemurs. We aim to build capacity for the university –from Professors to students– and bring a session for the coming annual meeting of the Association of Tropical Biology and Conservation (ATBC). ATBC hosts an annual meeting every year in a different country. Madagascar will host its first ATBC congress in early July 2019 (https://tropicalbiology.org/atbc-meetings/annual-meetings/), an opportunity we should not miss, for the GEF-UNEP-WRI project as well as for all our partners, in particular the University of Antananarivo. |
| --- | --- |

| Planned contribution to strategic priorities/targets | Global and pilot country activities are contributing to three strategic priorities: 1) mainstream biodiversity conservation in production landscapes/seascapes and sectors; 2) reduce land degradation; and 3) climate change mitigation. Project activities are contributing by increasing transparency around land use and deforestation data, private sector engagement, strengthening monitoring and sustainable management for production landscapes and protected areas, and providing a tool that helps quantify carbon emissions from land use change. |
| --- | --- |

2.	PROJECT OBJECTIVE

State the global environmental objective(s) of the project

To empower decision-makers in government, the private sector, and civil society with technology and information necessary to reduce deforestation and land degradation, combat illegal activities, and conserve biodiversity in pilot countries and on a global scale.

Please provide a narrative of progress made towards meeting the project objective(s). Describe any significant environmental or other changes (results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes (not more than 300 words)

Four achievements continue to advanced the above objective. 1) Building on a breakthrough in near real time monitoring- 30-meter GLAD alerts, the most accurate and timely deforestation alerts in the world- coverage has been expanded to 28 countries with more in the pipeline and automated updating. 2)Forest monitoring data and tools are advancing in accordance with partners need to ensure information is both relevant and accessible. The forest watcher mobile application, developed in partnership with locally based NGO's, now allows local forest monitors to use the most up-to-date information in on-the-ground situation and take that data off line. 3)The creation of a "GFW PRO" platform will directly serve the day-to-day information management and decision-support needs of commodity companies and financial institutions, bringing greater transparency and accountability for commitments to reduce deforestation. 4)The improvement of forest-atlas-prototypes in both Madagascar and Georgia, that are owned, validated and endorsed by national governments are unprecedented steps toward the transparency required to reduce illegal deforestation.

Please provide a narrative of progress towards the stated GEF Strategic Priorities and Targets if identified in project document (not more than 200 words)

Reducing land degradation and better conserving production landscapes requires accurate information about on-the-ground changes to reach decision makers and enforcement authorities in near-real-time. The advancement in near real time monitoring of deforestation provided by the expansion of GLAD alerts this year, provides unprecedented accuracy for responding to threats to target landscapes. GFW's tools put that information directly into the hands of decision-makers. For example the forest watcher mobile app now allows forest monitors to take todays updates off-line and into the field to improve patrols or law enforcement. The new GFW Pro will synthesize data for purchasers and investors in dashboards that easily link to existing management systems. This is possible not only because of the advances in technology but also because of the growth of the GFW partnership, including engagement with local forest monitors and major private sector actors.

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project objective(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Progress towards achieving the project objective (s)

| Project objective and Outcomes |  | Description of indicator |  | Baseline level | Mid-term target | End-of-project target | Level at 30 June 2017 | Level at 30 June 2018 | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective Empower decision-makers in government, the private sector, and civil society with technology and information necessary to reduce deforestation and land degradation, combat illegal activities, and conserve biodiversity in pilot countries and on a global scale. |  | Deforestation rates in target countries |  | Change baseline to emissions Georgia: Hansen rate (accessed via GFW) (2001-2012) 710 ha/yr gross tree over loss Madagascar: Hansen rate (accessed via GFW) (2001-2012): 110,697 ha/yr gross tree cover loss. | 712,283 tCO2e | 1,424,565 tCO2e | Georgia: 2012-2015 emissions: 200,145 tCO2e Total tree cover loss (2012-2015): 882 hectares Madagascar 2012-2015 emissions: 456,600,000 tCO2 Total tree cover loss (2012-2015): 1,146,289 hectares | Georgia 2016-2017 emissions: 86,2000 tCO2e Total tree cover loss (2016-2017): 731 hectares Madagascar 2016-2017 emissions: 93,700,000 tCO2 Total tree cover loss (2016-2017): 894,000 hectares | S |
|  |  | Number of unique visitors of GFW platform 75% users from US/EU 7% new users return within 3 months 455,000 interactions with target features 68% visits using target features |  | 456,062 | 800,000 | 1,100,000 | 1,250,000 users | 1,367,000 | HS |
|  | Component 1: Application and enhancement of GFW globally and in pilot countries |  |  |  |  |  |  |  |  |
| Objective 1.1 |  |  | Global |  |  |  |  |  |  |
| GFW is upgraded and applied on a global scale and in two pilot countries, Madagascar and Georgia, supporting: (a) improved management of existing forest areas and conservation of biodiversity, (b) reforestation/afforestation programmes, (c) improved control of deforestation on the ground and monitoring / protection of carbon stocks and (d) providing the information base for PES schemes (Payment for Ecosystem Services) |  | Precision of global forest monitoring systems (temporal and spatial resolutions)* |  | Annual 30m updates globally Monthly 500m updates in humid tropics | Maintain existing systems plus: Weekly 30m updates pan-tropically Daily 250m updates pan-tropically | Maintain existing systems plus: Weekly 20m updates globally Daily <5m updates for hotspot areas Predictive capabilities | Maintained existing systems plus: Weekly 30m updates available for 15 countries Daily 250m updates pan-tropically | Annual 30 m updates globally, Daily 250m updates pan-tropically, Weekly 30 m updates for 28 countries, high resolution imagery globally. | HS |
|  |  | GFW features and functionality: Crowd-sourcing and related Web 2.0 features |  | Minimal crowd-sourcing functionality. Limited analytical tools | Mobile app enabling people on the ground to access and submit data to GFW Tailored analytical tools through specialized apps for commodities, biodiversity, and climate | At least 8 specialized apps for conducting customized analyses | Mobile app currently being piloted by on the ground partners, Tailored analysis tools exist for Climate and water, and a comprehensive system for commodity supply chains and finance is under construction. | Increased functionality of tailored analysis tools available on country dashboards provide insights from data. Mobile app can display the most real time data from the online platform and take data offline. A comprehensive supply chain monitoring system has advanced in development and will be released in early 2019. | S |
|  |  | Number of datasets integrated within GFW website |  | 61 | 91 | 106 | 181 datasets | 301 datasets | HS |
|  |  |  | Pilot Countries |  |  |  |  |  |  |
|  |  | Widespread and easy availability of nationally validated datasets of highly relevant to sustainable forest management |  | GFW has made historic and near-real time information on forest cover change widely and easily accessible, but at a resolution that is not sufficient to track deforestation in certain forest types or degradation | Use of higher resolution data has been demonstrated in pilot countries and integrated within national forest geoportals | Pilot countries decide on protocols and systems for acquisition and use of higher resolution satellite data for forest management | Madagascar: Project steering committee recognizes the value of high resolution imagery and the first UMD nationalization workshop was held June 2017 using high resolution imagery for validation Georgia: Project steering committees recognizes the value of high resolution imagery and established a technical group to decide on protocols and use of higher resolution satellite data; 5 m Rapid-Eye 2014 data available for the entire country | Madagascar: High resolution imagery regularly used for the UMD nationalization process. Imagery available via Transparent World regularly used to validate additional land-use maps. Georgia: Project underway with a partner that is looking at how high resolution satellite data can better detect selective logging in pilot regions of Georgia. | S |
|  |  |  |  | Country-specific datasets are scattered and mostly unavailable | Identification of existing relevant datasets and progress towards making them available | Forest geoportals make available national datasets in conjunction with and connected to GFW global system | Madagascar: 11 datasets available through geoportal draft sites Georgia: 74 datasets available through geoportal draft sites | Madagascar: 15 datasets available on draft geoportal site; 10 datasets currently underway for cleaning and adding Georgia: 90 datasets acquired and available to be published. | S |
|  |  | Forest and land use management practices across multiple land use types |  | Informational about forest cover and associated change is poorly utilized in areas such as protected areas management, fore control | Entry points for use of GFW data have been identified for multiple management purposes | Routine use of GFW data within multiple management processes | Madagascar: 4 unique forest management offices engaged to integrate GFW into their workflows Georgia: All departments under MoENRP engaged to integrate GFW into workflows and 4 additional ministries engaged to share data on a routine basis | Madagascar: In addition to MEEF, 2 regional government entities are now involved and using GFW data to integrate into land-use planning workflows Georgia: In addition to the departments of MEPA, the IT department is engaged and trained on upkeep of the portal’s hardware and software. | S |
|  |  | Awareness and capacity levels |  | Limited awareness of GFW system | Increasing awareness and use in management | Widespread awareness and use in management | Website sessions (visits) from Madagascar: 600, Georgia: 840 Madagascar: 3 presentations at national conferences; 4 workshops with government offices Georgia: 1 presentation at an international conference (UNECE/FAO in Armenia), 5 workshops with government offices, 2 workshops with NGOs, 2 presentations for compatible projects (funded by UNEP & EU), and 1 workshop with journalists and media | Website sessions (visits) from Madagascar: 1,077, Georgia: 3,001 Madagascar: 2 presentations at national conferences; 8 workshops with government offices; 2 workshops/trainings with NGOs; 4 field missions for technical trainings Georgia: 1 presentation at an international conference (UNECE in Geneva), 2 national steering committees held, 2 journalist trainings held, 2 technical trainings held, 1 university lecture given, 1 workshop with NGOs | S |
|  |  | Integration of forest biodiversity, carbon and land degradation considerations within landscape-level planning and management |  | Little or no experience integrating biodiversity, carbon and land degradation considerations into land use planning, zoning and/or management at any level (landscape or otherwise) | One large-scale landscape (>1 million ha) in each pilot country has begun to integrate GFW as a tool for inter-sectoral co-operation and planning | One large-scale landscape (>1 million ha) in each pilot country has completed a planning exercise using GFW as a tool for inter-sectoral co-operation and planning | Madagascar: Initial meetings with the land-use planning ministry held and preliminary analyses performed Georgia: Meetings held with officials of the Autonomous Republic of Adjara to discuss integration of GFW as a tool for inter-sectoral co-operation and planning; Decision made by project technical group to add 4 additional regions for pilot testing and analysis. | Madagascar: Continuing discussions at the national level and one regional ministry starting to use analyses in planning (DREEF Menabe) Georgia: Discussions still underway in the Autonomous Republic of Adjara to discuss integration of GFW with their already existing forest management program. Use cases underway in pilot regions. | MS |
|  | Component 2:System update and replication |  |  |  |  |  |  |  |  |
| Outcome 2.1 National-level users in multiple countries have enhanced opportunity to visualize and utilize country-specific data |  | Functionality improves national adoption of the platform. |  | Limited ability to access and view national-level data | GFW platform has been partly enhanced to optimize national-level uses | Full range of enhancements to optimize national-level uses | The creation of map builder allows country governments to create and own nationally specific atlas, which can also sync with the global platform. | Country dashboards on the GFW platform facilitate access to national data. In addition improvements to the map-builder systems are underway to improve accessibility of customized analyses on atlases | S |
|  |  | National -level enrichment of GFW platform |  | 34 national datasets from 18 countries | 55 national datasets from 23 countries | 75 national datasets from 25 countries | 98 data sets from 26 countries | 114 data sets from 30 countries | HS |
| Outcome 2.2 Lessons learned and experience gained in target countries support the enhancement of the GFW platform to increase its relevance and utilization at scale by a range of stakeholders |  | Level of uptake measured by number of documented civil society and government use cases of GFW globally* |  | Dozens of anecdotal use cases in 10+ countries | System developed for systematic characterization, documentation, and communication of use cases | 100 use cases documented and communicated in 30+ countries | A system has been developed for systematic characterization and documentation of use cases | 184 user stories have been recorded, the database is being cleaned and a user friendly interface is being developed. | HS |
|  |  | Size of GFW’s community of practice |  | 11,000 twitter followers 3,000 facebook followers 1,500 subscribers to newsletter 85 GFW partners | Increase all categories | 20,000 (twitter) 6,000 (facebook) 3,500 (newsletter) 110 (partners) | Twitter:12,542 Facebook: 3,660 Newsletter: 3,180 Partners: 110 | Twitter:15,500 Facebook: 5,981 Newsletter: 6,000 Partners: 139 | S |
|  | Component 3: Strengthening and sustaining the GFW partnership |  |  |  |  |  |  |  |  |
| Outcome 3.1 GFW partnership is strengthened, long-term financial sustainability is secured, and GFW is increasingly regarded as a transparent and credible monitoring and management tool in support of forest conservation and sustainable use |  | Breadth of GFW membership |  | High percentage of western donors, companies | Increasingly broad membership | Membership of the GFW is broad, diverse, and effective for achieving GFW’s objectives | The breadth of partners is growing more countries were represented at this year's partners meeting than ever before. | This year in addition to more countries, the partnership has expanded private sector engagement | S |
|  |  | Sustainable financing of GFW |  | No plan | Plan is under discussion, with several underlying studies implemented | Plan is adopted by majority of GFW Partners | Plan is under formulation and has been broached with some partners. | Plan is being discussed with some partners. | S |
|  | Component 4: Private sector application to reduce deforestation in key commodity sector supply chains |  |  |  |  |  |  |  |  |
| Outcome 4.1 National and global-level impacts of GFW on forest conservation are significantly enhanced through the adoption of the suite of tools/platforms as a supple chain management tool by the private ssector |  | Number of GFW-Commodities endorsements or recommendations made by target commodity sector leverage points (e.g. TFA2020, CGF, RSPO) |  | 0 | 5 | 10 | 20 | 29 | HS |
|  |  | Number of private sector entities that have used GFW to improve their capacity to eliminate deforestation from their commodity supply chains |  | 0 | System developed for systematic characterization, documentation, and communication of use cases | 25 | System has been developed for systematic characterization, documentation, and communication of use cases, at least 2 use cases are being researched. | 3 use cases have been explored. A system is in place to document new cases as GFW PRO comes online. | S |

Overall rating of project progress towards meeting project objective(s) (To be provided by UNEP GEF Task Manager. Please add columns to reflect all prior year ratings)

| FY2016 rating | FY2017 rating | FY2018 rating | Comments/narrative justifying the current FY rating and explaining reasons for change (positive or negative) since previous reporting periods |
| --- | --- | --- | --- |
|  | S | S | The project is on track and most of the global targets have been exceeded. Further attention needed to achieve pilot country targets and results. |

Action plan to address MS, MU, U and HU rating (To be completed by UNEP GEF Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |
| Please provide an update on how the Ministry and DREEF Menabe uses GFW in decision making with examples | Madagascar team with the support of the global team | December 2018 |
| Please provide an update on the integration of GFW with Adjara existing forest management program | Georgian team with the support of the global team | December 2018 |
| Prepare a Use case report that demonstrates how GFW is used in pilot countries in decision making | Global team | March 2019 |

This section should be completed if project progress towards meeting objectives was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| Priority should be given for the pilot demonstration of integration of GFW as a tool for inter-sectoral co-operation and planning. An update shall be provided in December 2017 on use of GFW at a large landscape level | An update was provided to the global steering committee in October 2017. Since this meeting in Madagascar, we have held two planning meetings with the National Land-Use Planning ministry to discuss how GFW data and analyses can be integrated into intersectoral land-use planning. After three workshops in Menabe, this region is now using GFW data to inform land-use planning activities lead by the regional direction of environment, ecology and forests (DREEF). In Georgia, in December 2017, the Ministry of Environment combined with the Ministry of Agriculture. The Georgia country team has been working with the new ministry to integrate agricultural needs into FLUIDS. We have held initial meetings, but no activities have been planned to integrate GFW data into intersectoral planning. | Country Teams | Madagascar: November 2017 (national meetings); September 2017, January 2018, March 2018 (regional meetings) Georgia: October 2017, November 2017, March 2018, June 2018 |

3.2	Project implementation progress

| Outputs | Expected completion date | Implement-ation status as of 30 June 2016 (%) | Implement-ation status as of 30 June 2017 (%) | Implement-ation status as of 30 June 2018 (%) | Comments if variance. Describe any problems in delivering outputs | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Improved global and regional level data on GFW platform |  |  |  |  |  |  |
| Activity 11.1.1: Terra-i pan-tropical expansion of land cover change alerts system (originally developed for Latin America), with first version ready in 2016 | Aug 2016 | 80% | 100% | 100% |  | S |
| Activity 1.1.1.2: Increase resolution of FORMA alerts from 500 to 250 m for pan tropics | Aug 2016 | 90% | 100% | 100% |  | S |
| Activity 1.1.1.3: Annual (2016-2018) updates of global tree cover change from UMD | Sept 2019 | 20% | 40% | 70% | After some delays in 2017, annual updates are back on track and in early 2018 the annual data was released earlier than expected. The 2017 tree cover loss data is now available to view and analyze on the GFW map, and updated 2017 tree cover loss statistics are available on the global and country dashboards. The new data was paired with an in-depth blog in English, Spanish, Portuguese, French, and Bahasa Indonesia, as well as a technical blog focused on Brazil. | S |
| Activity 1.1.1.4: Thirty meter Landsat alert system from UMD | Sept 2019 | 50% | 60% | 80% | Processing has now been streamlined for alerts. They are available for all of the Latin American tropics, Congo basin, and Southeast Asia. Coverage is increasing rapidly. | S |
| Activity 1.1.1.5: Develop strategy with partners to target use of high resolution satellite imagery (sub 10 m) based on hotspot identification supported by medium-resolution systems | Sept 2019 | 50% | 50% | 75% | GFW has published 3 “Places to Watch” reports identifying hotspots of deforestation. | S |
| Activity 1.1.1.6: Addition of new global data sets, e.g. plantations, carbon | Sept 2019 | 20% | 60% | 75% | This year we added two layers: Updated Intact Forest Landscapes data show the current extent and location of intact forests and areas with shrinking intact forests since 2013. New biodiversity significant and biodiversity intactness data. Others that are in processing phase are: - Soy cultivation for South America - Primary forest for Indonesia, Brazil and DRC - Advanced Very High Resolution Radiometer (AVHRR) record of forest change - Global biomass data (revision of Year 2000 global biomass layer from Woods Hole Research Center) | S |
| Activity 1.1.1.7: Incorporate higher resolution fire alerts (VIIRS, 375 m resolution) | June 2016 | 100% | 100% | 100% |  | S |
| Activity 1.1.1.8: Add high resolution imagery (updated daily) from UrtheCast to GFW platform | June 2016 | 100% | 100% | 100% |  | S |
| Output 1.1.2: Improved features and functionality on GFW global platform to support analysis, decision-making and action |  |  |  |  |  |  |
| Activity 1.1.2.1: Improve and/or add new analytical tools that allow users to interpret data on-the-fly to support decision-making | Sept 2019 | 20% | 50% | 75% | We re-designed GFW country dashboards to answer specific policy questions. Analysis tools alow users to produce graphics that summarize data and combine data from any of the layers on the map.Similar tools are now being added to the mab builder system that supports the forest atlases. | S |
| Activity 1.1.2.2: Enhance user interface to make data more discoverable, understandable, and immediately relevant for multiple audiences | Sept 2019 | 20% | 50% | 75% | The above tools are crucial for usability In addition, a new satellite imagery tool released this in June makes it easier to verify deforestation and fire alerts on GFW by comparing before/after imagery. Users can select a date range and minimum cloud coverage, and easily scan through all available images that meet the search criteria. | S |
| Activity 1.1.2.3: Improve access to GFW data from the field and within other applications | Sept 2019 | 20% | 50% | 75% | After releasing Forest Watcher mobile app last year, the team is working on updates based on feed-back from users. | S |
| Activity 1.1.2.4: Improve the delivery of information from GFW via subscriptions | Sept 2019 | 20% | 50% | 75% | In response to consistent user feedback, GFW launched the “My GFW” feature in February 2016, which allows users to create a log-in to tailor their GFW experiences to meet their specific needs. For example, users can now upload their own shapefile to GFW and subscribe to alerts related to that area of interest. We have improved the appearance of the email received. This year we’ve added the new datasets available into the subscription options. | S |
| Output 1.1.3: Nationally validated data sets, including refined forest cover / change data and additional locally generated data layers, are available within pilot country sections of GFW |  |  |  |  |  |  |
| Activity 1.1.3.1: Use validation and ground-truthing methods to ensure accuracy of GFW reporting of tree cover loss | December 2018 | 0% | 10% | 80% | Last training for nationalization of UMD tree loss data in Madagascar will be held by December 2018. In Georgia GISLAB is looking at accuracy on data for selective logging, with a target end date of August 2018. | S |
| Activity 1.1.3.2: Integrate (obtain, review, validate, digitize if necessary, format and upload) additional pilot country data sets | Dec 2018 | 20% | 50% | 75% | Most datasets integrated and uploaded into Georgian portal; Madagascar is accelerating the addition of datasets after the signing of the MOU with the ministry. | S |
| Activity 1.1.3.3: Select and acquire higher resolution data | Sept 2017 | 0% | 50% | 100% |  | S |
| Activity 1.1.3.4: Combined GFW global and national data sets constitute pilot country forest geoportals | March 2019 | 0% | 40% | 75% | All of the data is now incorporated into the Georgia forest atlas, but the team is now reorganizing the data to be more accessible and user friendly. In the Madagascar atlas the land use data sets from the Min. of Enviroinment are now all available, the team is finalizing the UMD nationalization, which will be added before public launch. | S |
| Output 1.1.4: Enhanced management practices through national and field-level application ('use cases') of data and information generated and made available through national GFW views |  |  |  |  |  |  |
| Activity 1.1.4.1: Establishment of use case implementation groups for identified cases | March 2019 | 0% | 25% | 75% | Most use cases have been started in pilot countries with some already completed. | MS |
| Activity 1.1.4.2: Groups finalize use case details, including budgets; national-level steering committees approve | March 2019 | 0% | 20% | 80% | Most use cases have been finalized, with a few still under discussion by country teams and national level steering committees. | MS |
| Activity 1.1.4.3: Use cases are implemented | July 2019 | 0% | 0% | 65% | Use cases are currently underway. | MS |
| Activity 1.1.4.4: Use case lessons are captured and shared nationally and internationally | Sept 2019 | 0% | 0% | 35% | Some use case lessons captured and shared as the use case was implemented. | MS |
| Activity 1.1.4.5: Additional use cases are solicited, approved and implemented | March 2019 | 0% | 0% | 75% | Additional use cases under discussion with national steering committees and relevant stakeholders in both pilot countries. | S |
| Output 1.1.5: Targeted awareness, capacity building and outreach effort focusing on governmental and non-governmental stakeholders to support wide-ranging system uptake |  |  |  |  |  |  |
| Activity 1.1.5.1: National and local-level workshops will introduce key stakeholders to GFW and further assess analytical needs | Apr 2017 | 100% | 100% | 100% |  | S |
| Activity 1.1.5.2: Implement targeted program of institutional and human capacity building | Sept 2019 | 0% | 20% | 75% | Capacity building programs are underway and ongoing until the completion of the project in both pilot countries. | S |
| Activity 1.1.5.3: Collaboration with universities, schools, NGOs, donors and media will serve to increase knowledge about forests and to support national-level efforts to generate and publish value-added, GFW-based analyses | Sept 2019 | 20% | 50% | 75% | Journalist trainings and collaborations with universities and NGOs in both countries has increased the exposure of the project. These will continue until the completion of the project. | S |
| Output 1.2.1: GFW demonstrated as a tool for integrating multiple biodiversity, carbon and land degradation considerations in support of landscape-level planning and management |  |  |  |  |  |  |
| Activity 1.2.1.1: Detailed correlation of complete set of use cases to demonstration areas, together with associated capacity building needs | March 2019 | 0% | 10% | 80% | Activities within demonstration areas have increased, specifically looking at integration of use cases across multiple sectors | S |
| Activity 1.2.1.2: Establish inter-sectoral committees | Sept 2019 | 0% | 0% | 0% | The project has determined that this activity is not necessary for the completion of this output. We plan to discuss this further at the next global steering committee meeting held in September 2018. | N/A |
| Activity 1.2.1.3: Identify higher resolution data needs and acquire data sets | March 2019 | 0% | 20% | 80% | High-resolution data needs have been identified and high-res imagery will be available on both country portals by March 2019. | S |
| Activity 1.2.1.4: Implement capacity building measures | Sept 2019 | 0% | 20% | 50% | Trainings have been held on the forest atlases in both countries on a regional level within the demonstration areas | MS |
| Activity 1.2.1.5: Use case implementation | July 2019 | 0% | 0% | 25% | Land-use planning use-cases in the pilot regions are just beginning in both countries and will be completed by the end of the project. | S |
| Activity 1.2.1.6: Apply emerging findings within landscape-level planning exercise | Sept 2019 | 0% | 0% | 0% | This activity is dependent on the completion of the above activities within this output. | S |
| Output 2.1.1: Enhanced online GFW system to visualize and enable interpretation of country-relevant data |  |  |  |  |  |  |
| Activity 2.1.1.1: Country level efforts to enhance uptake of GFW by civil society | Sept 2019 | 20% | 50% | 75% | The newly redesigned country page were created in response to expressions of need from national partners . | S |
| Activity 2.1.1.2: Country level efforts to enhance uptake of GFW by journalists | Sept 2019 | 20% | 50% | 75% | The Places to Watch analysis is targeted at local and international journalists to provide concise information that can be easily turned into media stories | S |
| Activity 2.1.1.3: Support country participation in sub-regional, regional- and thematic-level workshops | Sept 2019 | 20% | 50% | 75% | Newly redesigned country pages help answer the most common questions faced by national authorities making it easier for them to quickly access insights and contribute to international discussions. | S |
| Output 2.2.1: Enhanced GFW uptake in target and other countries |  |  |  |  |  |  |
| Activity 2.2.1.1: Country level efforts to enhance uptake of GFW by civil society | Sept 2019 | 20% | 50% | 75% | We planned the Early Warning Forum with international partners and governments that was held in Peru in June 2018. We launched the new GFW fellowship to provide capacity building for GFW and technology champions in targeted forest countries. These efforts are ongoing until the end of the project. | S |
| Activity 2.2.1.2: Country level efforts to enhance uptake of GFW by journalists. | Sept 2019 | 20% | 50% | 75% | We pitched targeted stories to in-country journalists which increased national coverage of GFW in those countries (e.g., New York Times Brazil Bureau). We send the Places to Watch updates to journalists around the world to collaborate on the most urgent stories about deforestation globally and in these countries. These activities are ongoing until the end of the project. | S |
| Activity 2.2.1.3: Support country participation in sub-regional, regional- and thematic-level workshops | Sept 2019 | 20% | 50% | 75% | We supported the participation of country partners to participate in the 2018 GFW advisory meeting (e.g., Liberia). We supported a delegate from Madagascar to participate in the Bonn Climate Change meetings in March 2018. These activities are ongoing until the end of the project. | S |
| Output 2.2.2: Country-level and thematic analyses and sharing of lessons learned documented through use cases and other country-level co-operation |  |  |  |  |  |  |
| Activity 2.2.2.1: Analyze GFW uptake within not only GEF pilot countries (Georgia and Madagascar) but also within other countries where GFW uptake is being targeted (see 2.2.1 above) | Sept 2019 | 10% | 30% | 70% | The team regularly review Google analytics data and targets actions based on results, for example our targeted media campaigns showed increased uptake in key forested countries, the team is also working to more systematically review progress on use cases globally. | S |
| Activity 2.2.2.2: Thematic, multi-country analyses assess the specific contexts (protected areas management, community forest management, etc.) within which GFW is having impacts, as well as techniques for using GFW effectively to identify and address drivers of deforestation and forest degradation, strengthen governance, etc. | Sept 2019 | 0% | 25% | 60% | 1 case study is complete, 2 more are underway. | S |
| Activity 2.2.2.3: Success stories, as well as persisting barriers, are identified and shared at regional and thematic workshops, training courses and online | Sept 2019 | 0% | 40% | 70% | at the 2018 GFW Advisory meeting the team shared successes and struggles and held working group sessions to identify plans for addressing persistent issues. | S |
| Activity 2.2.2.4: Feedback collected to inform iterative enhancements to GFW, including tool development for addressing cross-cutting challenges, bottlenecks, and barriers to uptake | Sept 2019 | 20% | 50% | 75% | The team conducts user testing and feed back after the release of every new feature. For example traffic to country pages increased after improvements were made (see narrative) | S |
| Output 2.2.3: Produce and distribute documentation of policy and program guidance based on GFW lessons learned (understanding that this refers to GFW staff providing inputs to policy and programs, through documents and or workshops, and engagement with partners). An engaged GFW partnership and user community to promote sharing, replication, and scaling of GFW use cases |  |  |  |  |  |  |
| Activity 2.2.3.1: Develop reference materials for national governments related to the use of remote sensing and associated data and information for enhanced forest and land use management, as well as the utility of apps aiming to support countries in monitoring international commitments related to CBD Aichi targets, REDD+, etc. | Sept 2019 | 25% | 40% | 70% | The team is working on several research papers: - The most recent collaboration with the Sustainability Consortium on drivers of deforestation has been written up and submitted for publication. - Collaboration with Conservation International to use GFW data in analysis of “climate irreplaceable ecosystems”, paper to be submitted later this fall - REDD+ paper (“Comparing global and national approaches to estimating deforestation rates in REDD+ countries”) | S |
| Activity 2.2.3.2: Produce policy papers based on results of 2.2.3.1 | Sept 2019 | 25% | 40% | 70% | A recent WRI paper “Tropical Forests and Climate Change: The Latest Science” makes recommendations for the importance of forests to achieve the Paris targets. Adding to the discussion for future agreement talks. Once the other work listed above is published the team plans to use this research to make recommendations at the COP. | S |
| Activity 2.2.3.3: Disseminate findings to governments, CBD, UNFCCC, UNCCD, CSOs and the private sector | Sept 2019 | 0% | 10% | 70% | The work described above will be presented at the UN COP. | S |
| Output 3.1.1: Regular communications and engagement with GFW partners to promote ownership and collaboration |  |  |  |  |  |  |
| Activity 3.1.1.1: Support to national- and local-level governmental, academic, indigenous people’s, women’s and civil society representatives to stimulate and enhance the use of GFW for improved forest management | Sept 2019 | 20% | 50% | 75% |  | S |
| Activity 3.1.1.2: Ensuring partner country level representation in the Partnership | Sept 2019 | 20% | 50% | 75% | Partner countries are represented at the partnership meeting every year, including the 2018 Advisory Meeting. The 2019 GFW Partnership Meeting and User Summit will include many representatives from all partner countries, including Madagascar and Georgia. | S |
| Activity 3.1.1.3: Development and maintenance of a use case database | Sept 2019 | 75% | 80% | 90% | The database is currently maintained in an excel file, we are building an interactive dashboard to more easily track and manage cases. | S |
| Activity 3.1.1.4: Recruitment of new GFW Partners | Sept 2019 | 20% | 50% | 75% | This year partner recruitment has focused on corporate partners with GFW PRO, see 4.1.1 | S |
| Activity 3.1.1.5: Creation of MOUs and partnership agreements as necessary | Sept 2019 | 20% | 50% | 75% | MOUs are created and upheld. | S |
| Activity 3.1.1.6: Regular communications to the GFW Partnership (e.g. via email newsletters, the GFW Partner website, bilateral discussions), including updates on key activities and outcomes and soliciting input on key challenges | Sept 2019 | 20% | 50% | 75% | Regular email updates are sent out the entire GFW email list and updates were shared with key partners at the annual meeting. | S |
| Activity 3.1.1.7: Annual in-person meetings of the GFW Partners and Advisors, potentially including global and regional gatherings | Mar 2018 | 33% | 50% | 75% | Planning to add an additional partnership meeting at the end of the project. | S |
| Output 3.1.2: Sustainable financing plan for the GFW system developed in collaboration with public and private sector as well as CSOs |  |  |  |  |  |  |
| Activity 3.1.2.1: Assessment of opportunities to minimize costs associated with data and platform maintenance | Dec 2017 | 0% | 50% | 75% | GFW is working with UMD to streamline updates and reduce maintenance costs | S |
| Activity 3.1.2.2: Recruitment of additional private sector partners, especially from technology sectors, to provide in-kind contributions to reduce costs (e.g. free cloud computing services from Google) | Sept 2019 | 20% | 50% | 75% | High resolution imagery is now available at a discounted rate to GFW | S |
| Activity 3.1.2.3: Ongoing monitoring, evaluation, and documentation of outcomes and success stories to share with existing and prospective funders and stakeholders | Sept 2019 | 20% | 50% | 75% | The team continues to document the progress of the project by tracking outputs and outcome measures, such as user engagement, media response, and use cases of protecting forests through the application of GFW tools. | S |
| Output 3.1.3: External and independent review and oversight provided by partners and the media to guarantee highest degree of transparency and technical credibility (demonstrated by partners meeting and media coverage, and WRI's peer review process) |  |  |  |  |  |  |
| Activity 3.1.3.1: Clearly communicate data limitations throughout the GFW platform and on communications and outreach materials | Sept 2019 | 20% | 50% | 75% | GFW released several blogs and technical reports. Please see the above text for more details. | S |
| Activity 3.1.3.2: Recruitment of additional private sector partners, especially from technology sectors, to provide in-kind contributions to reduce costs (e.g. free cloud computing services from Google) | Sept 2019 | 20% | 50% | 75% | GFW continues exploring these opportunities whenever possible, for example, Our new partnership with Planet labs offers users immediate access to the most recent satellite imagery though the platform at a very low cost to the project (relative to private costs). | S |
| Activity 3.1.3.3: Ongoing monitoring, evaluation, and documentation of outcomes and success stories to share with existing and prospective funders and stakeholders | Sept 2019 | 20% | 50% | 75% | GFW continues to document the progress of the project using metrics for outputs and outcomes and by gathering use cases and synthesizing lessons. | S |
| Output 4.1.1: Improved information and transparency through partnerships with selected private sector companies active in target commodity sectors in pilot and other countries, to assess user needs and requirements and jointly explore the development of GFW-specific decision-support tools tailored to private sector operations, management systems, and covering various steps in commodity supply chains |  |  |  |  |  |  |
| Activity 4.1.1.1: Establish new partnerships with commodity producers, traders, and buyers to support the implementation of company commitments to sustainable sourcing | Sept 2019 | 25% | 50% | 75% | GFW continues deepening partnerships with major commodity companies, this year we completed a baseline project with Cargill to track risk in supply sheds. Other examples include: presenting GFW Pro at Walmart’s annual flagship Milestone Sustainability Summit in April 2018, We also presented at the IDB Invest Sustainably Week in Lima, Peru | S |
| Activity 4.1.1.2: Work closely with partner companies to improve their ability to monitor and report on supply chain sustainability | Sept 2019 | 20% | 50% | 75% | The GFW PRO team has begun training companies including Cargill, Mondelez, Bunge/IOI and others to upload large datasets into the platform to improve their ability to monitor deforestation commitments. | S |
| Activity 4.1.1.3: Establish partnerships to advance transparency of commodity production in key commodity sectors, including partnerships with individual companies, certification bodies, and multi-stakeholder initiatives | Sept 2019 | 20% | 50% | 75% | In addition to the above mentioned partnership the team is working with the ISEAL alliance and onboarding a number of monitoring bodies into GFW PRO. | S |
| Output 4.1.2: An expanded and improved GFW Commodities application or suite of applications, providing enhanced datasets and management tools for companies trading in goods and services linked to deforestation |  |  |  |  |  |  |
| Activity 4.1.2.1: Develop tools to help companies monitor and implement sustainable sourcing commitments | Sept 2019 | 50% | 90% | 80% | Based on extensive user research GFW is developing a complex supply chain management system to meet the highest standard of private sector monitoring. The increasing complexity of the system has posed delays, but promises to deliver a game-changing tool. | S |
| Activity 4.1.2.2: Develop tools to support commodity standards systems | Sept 2019 | 10% | 40% | 50% | The team developing GFW PRO has made progress addressing the high standards and needs of the private sector.(which posed some delays) the tool has been developed and is currently in a pilot phase wich a small number of private companies and monitoring bodies. |  |
| Activity 4.1.2.3: Support development/improvement of tools that help NGOs and other stakeholders to lobby governments, growers, traders, certification schemes, and other supply chain actors | Sept 2019 | 20% | 50% | 75% | The tool described above will help improve transparency and will give NGOs and advocacy groups access to the same data and analysis that companies access. Some of these groups are participating in the pilot phase. it is expected to be publicly launched in early 2019. | S |
| Output 4.1.3: Uptake of GFW data and tools by commodity producers and buyers and finance sector actors to implement and report on zero-deforestation commitments |  |  |  |  |  |  |
| Activity 4.1.3.1: Participate in relevant multi-stakeholder and international fora to help build consensus around, and commitment to, a vision for sustainable commodities production | Sept 2019 | 20% | 50% | 75% | The team Organized an early warning forum in Lima Peru with stakeholder who focus on responding to deforestation (update in next report). The team has participated in the following events this year: - TFA2020 General Assembly in Ghana, - High Carbon Stock Association steering group in Malaysia, - AdaptAmerica IDB event in Panama, - IDB Invest Sustainability Week in Lima, Peru, - RSPO meetings in Kuala Lumpur, Malaysia - The Sustainability Consortium annual event in Chicago, Illinois - Roundtable on Responsible Soy. - Febraban’s CIAB conference (the largest fintech event in Latin America), - a CFA/CFMI hosted event with Brazilian banks in Brasilia - RSPO European meeting in Paris. | S |
| Activity 4.1.3.2: Engage with target country governments and other stakeholders, using GFW Commodities as a fulcrum around which to focus relevant policy discussions | Sept 2019 | 20% | 50% | 75% | We continue to engage governments and use GFW Pro as a potential example of how private sector will be monitoring their commitments in these countries. The most recent example is Paraguay and Argentina. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager. Please add columns to reflect prior years’ ratings):

| FY2016 rating | FY2017 rating | FY 2018 rating | Comments/narrative justifying the rating for this FY and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- |
|  | S | S |  |

Action plan to address MS, MU, U and HU rating. (To be completed by UNEP Task Manager in consultation with Project Manager)

| Action(s) to be taken | By whom? | By when? |
| --- | --- | --- |
| The :Output 1.1.4: Enhanced management practices through national and field-level application ('use cases') of data and information generated and made available through national GFW views/ is critical in demonstating the value of GFW in Forest management, please provide an update on use cases proposes in pilot countries | Project team | December 2018 |
| Complete planned capacity building measures by December 2019 (activity 1.2.1.4) | Global project team | December 2018 |

This section should be completed if project progress was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation (To be completed by Project Manager).

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| Please review the program and provide an update on the progress in each activity | Full update was given during the global steering committee meeting in October 2017. Additional updates were given during the mid-term review in Feb – May 2018. | Country and project teams | October 2017; Feb – May 2018 |
| Most of the delays are observed under Outputs 1.1.3 and 1.1.4, the results of these two outputs may have impact on delivery of other outputs. Please review the activities of these two outputs and take precautionary measures (timing and budgeting) for on-time delivery of these outputs | The project and country teams reviewed the progress under these two outputs and determined that a no-cost extension would be required to deliver on these outputs effectively. The team requested a no-cost extension formerly during the global steering committee meeting in October 2017 and received letters of support from both countries by March 2018. The project team also submitted a revised budget to accommodate the no-cost extension appropriately and both requests are currently in process with UNEP. Additionally, both country teams worked with the ministry partners to increase activities in order to deliver on the outputs by the end of the project in September 2019. | Country and project teams | October 2017; March 2018 |

3.3.	Risk

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:AGREE |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:AGREE |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Activities are progressing at a more accelerated pace in more countries and a no-cost extension will allow the project output to be completed successfully |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Project progress will be reviewed in the next SC meeting and work plan will be reviewed and approved |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: Advancing on the amount of cofinancing delivered is slow, but no problems in securing the co-financing. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  |  |  |  |  | X | PM: Requested budget realignment currently being reviewed along with no-cost extension request. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Budger revision is marginal. Project team needs to control staff cost |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  | X |  |  |  |  | PM: Relationship with the Ministry in Madagascar is significantly improved and there is now a clear MOU signed to define roles and responsibilities between WRI and the ministry. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The Project management and engagement with the Government of Madagascar is improving. Signature of MOU is a good sign of a good progress. |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  | X |  |  |  |  | PM: Recent political changes in both countries the past year has had less of an impact on the project given strong country teams and wide familiarity with the project. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: Weaknesses within both government ministries of the pilot countries have been identified and capacity building measures are underway. Ministry staff report improved capacity through these trainings. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM:Agree x |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| 1 | Work flow: Slow establishment of the project in both pilot countries | delays in advancing the project | Work plan will be reviewed by the Steering committee |  | Oct 2018 |
| 2 | Minor budget reallocation needed | Staff cost may exceed the planned budget | The PMC cost will be tracked every quarter and the Project team will review options of co-finance not to exceed the planned staff budget | Global Project Team | December 2018 |
| 3 | Political influences: The Project management and engagement with the Government of Madagascar is not yet very effective. | The project results may not be used by the relevant departments | Continuous coordination with the Ministry in Madagascar | Global Project team with National team | December 2018 |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2017 rating | FY2018 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| M | m | The global activities continue without any delay or risk however some risks factors in pilot countries may affect the project results in pilot countries. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |
|  |  | - Work flow: Slow establishment of the project in both pilot countries: WRI requested a no-cost extension in order to have more time to complete the project. Country teams worked with government and other partners to increase activities in order to achieve project goals. - Budget: Original budget does not reflect the current situation: WRI submitted a budget realignment along with the no-cost extension in order to ensure there is enough support for activities with partners and staff time to complete the project. - Political influences: The Project management and engagement with the Government of Madagascar is not yet very effective.: The country teams in Madagascar worked along with the ministry to resolve any issues with the project. These meetings resulted in finalizing an MOU between WRI and the Ministry of Environment, Ecology and Forests in Madagascar that detailed the expected results from the collaboration between the two institutions. Both data sharing and activities have increased as a result and the project is back on track. |

- Stories & Contributions to UN Environment’s GEF Communications Work

4.1  Are there any especially interesting and impactful project results that you would like to bring to the attention of our GEF Corporate Communications efforts? Please provide a very brief summary.

- In Madagascar, WRI is partnering with Durrell to use Forest Watcher and fire alerts in the Menabe region. Fires are a key indicator of deforestation and the use of fire alerts have helped direct patrols and uncovered illegal activities with protected areas in the region, including illegal settlements, charcoal production and agricultural fields. With WRI, Durrell has conducted trainings with the regional government office on how to use Forest Watcher and GFW data to help with overall protected area management, planning patrols and stopping illegal activity. - In Sumatra, Indonesia community groups are using GFW to stop burning in protected areas. HAkA is a WRI partner testing the forest watcher mobile application with community forest monitors in Sumatra. Monitors using GLAD and Fires alerts identified an active fire inside the Trampon-Singkil Rawa National Wildlife Reserve, part of the Leuser Ecosystem. After Haka reported the fire to an official conservation agency, National Armed Forces were able to control the fire. The South Ache Police arrested 4 suspects in the burning. The story appeared in the local newspaper and was picked up by at least 5 other outlets including the Ache Tribune, raising awareness and deterring potential future burning. - Global Forest Watch Pro is partnering with more than 30 of the largest producers and suppliers of deforestation linked commodities, including Mondelez, Cargill, Mars, Unilever, and Walmart to reduce deforestation in supply chains. David MacLennan, CEO, Cargill publicly announced “We Partnered with the World Resources Global Forest Watch to map 1,918 Cargill sourcing areas for cocoa, palm and soy across 14 countries to establish a baseline for tree cover loss as of 2014 that we can use to help measure and track our progress against our implementation plans.” - Sudameris Paraguay, a bank that lends to farmers, uses Global Forest Watch to pinpoint fires and fallen trees in real-time. They identified a fire on a client’s land and sent him a notice. The client who until then was unaware of the fire, was able to respond. "A few days later, the client sent a note of thanks. He lost 100 hectares of pasture, but the rest of his 1,200-hectare property — and, importantly, his herd — was fine" as reported by Latin Finance in March. “We have a more integral valuation of the client,” says Omar Fernández, head of risk for Sudameris. “It used to be just financial. They can no longer fool us. We can tell if they’re using the area they say they are using, thanks to the satellite.”

The Ministry of Environment and Natural Resource Protection has recently been merged with the Ministry of Agriculture, the Ministry’s new name is Ministry of Environmental Protection and Agriculture.

Fields with an * sign (in yellow) should be filled by the Fund Management Officer

Only if different from first disbursement date, e.g., in cases were a long time elapsed between first disbursement and recruitment of project manager.

If there was a “Completion Revision” please use the date of the revision.

Information to be provided by Executing Agency/Project Manager

Projects which completed mid-term reviews/evaluations or terminal evaluations during FY16 should attach the completed co-financing table as per GEF format. See Annex 1

See above note on co-financing

Additional cofinancing through the USAID Hay Tao project for Madagascar.

As in project document

Progress made during current reporting period (one paragraph stating key changes since previous reporting period)

Progress made during current reporting period (one paragraph stating key changes since previous reporting period)

For Full Size Projects this information is found in the front page of the project Executive Summary; for Medium-Sized Projects the information appears in the MSP brief cover page.

Or immediate project objective

Projects that did not include these in original design are encouraged to the extent possible to retrofit specific targets.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Add rows if your project has more that 3 key indicators per objective or outcome.

Depending on selected indicator, quantitative or qualitative baseline levels and targets could be used (see Glossary included as Annex 1).

Many projects did not identify Mid-term targets at the design stage therefore this column should only be filled if relevant.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). See Annex 2 which contains GEF definitions.

Add rows if your project has more than 4 objective-level indicators. Same applies for the number of outcome-level indicators.

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Variance refers to the difference between the expected and actual progress at the time of reporting.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

UNEP Fund Management Officer should also be consulted as appropriate.

Only for Substantial to High risk.