## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE)
3. IMPLEMENTATION PROGRESS (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data |  |  |  |  | .
General Information
Region: | Global
Country(ies): | Global
Project Title: | Building global capacity to increase transparency in the forest sector (CBIT-Forest): accelerating capacity-building, knowledge-sharing and awareness raising
FAO Project Symbol: | GCP /GLO/11308/GFF
GEF ID: | 11308
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Climate Change Mitigation
Project Executing Partners: | FAO
Initial project duration (years): | 3
Project Dates
GEF CEO Endorsement Date: | 2024-01-03
Actual Agency Approval Date | 2023-07-10
Project Implementation Start Date/EOD: | 2024-01-01
First Disbursement Date | 2024-11-30
Planned Project End Date/NTE1: | 2026-12-31
Revised project implementation End date (if approved)2: | N/A
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2027-12-31
Funding
GEF Grant Amount (USD): | 2000000
Total GEF grant delivery (as of June 30, 2025 (USD): | 1250512.82
Total Co-financing amount (USD)3: | 5176416
Total estimated co-financing materialized as of June 30, 20254: | 4808208
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting:
Expected Mid-term Review date5: | N/A
Actual Mid-term review date (if already completed) | N/A
Expected Terminal Evaluation Date6: | 2026-06-30
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Highly Satisfactory (HS)
Overall implementation progess rating: | Highly Satisfactory (HS)
Overall risk rating: | Low
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 1st PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Condor Golec, Rocio Danica |  | Rocio.Condor@fao.org
Budget Holder (BH) | Fox, Julian Christian |  | Julian.Fox@fao.org
GEF Operational Focal Point (GEF OFP) | Sacchetta, Marco |  | Marco.Sacchetta@fao.org
Lead Technical Officer (LTO) | Pekkarinen, Anssi Samuli |  | Anssi.Pekkarinen@fao.org
GEF Technical Officer (GTO) | Veyret-Picot, Maude |  | Maude.VeyretPicot@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments

## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 0
4

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating | NOTE
Developing countries have enhanced capacity, knowledge and awareness on forest-related data collection, analysis and dissemination to meet the enhanced transparency requirements of the Paris Agreement | Project Outcome 1 Enhanced access and use of best available forest-related data to respond to the transparency requirements | Number of users accessing the FRA 2025 platform per month | 0 | 800 | 1600 | 0 | 0% | Not Rated | To be implemented Q3/Q4 2025
| Project Outcome 1 Enhanced access and use of best available forest-related data to respond to the transparency requirements | Number of page views in the FRA 2025 platform per month | 0 | 2000 | 4000 | 0 | 0% | Not Rated | To be implemented Q3/Q4 2025
| Project Outcome 2 Improved National Forest Monitoring Systems through enhanced technical capacity of countries to monitor and report forests, and share knowledge to support the ETF implementation, with attention to gender | Number of countries benefiting from data sharing, capacity-building and knowledge exchange activities | 0 | At least 10 countries | At least 20 countries | 64 | 320% | Highly Satisfactory (HS)
| Project Outcome 3 Transparency practitioners and experts benefit from knowledge products on forest transparency | Total number of practitioners' accessing knowledge products | 0 | 1000 | 2000 | 75056 | 3753% | Highly Satisfactory (HS)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
1018% | 56.26% | 62.53%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
|  | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer | GEF Operational Focal Point | GEF Technical Officer (GTO)
| FY2025 Development Objective rating | Highly Satisfactory (HS) | Highly Satisfactory (HS) | Highly Satisfactory (HS) |  | Highly Satisfactory (HS)
| Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project delivered outstanding results, driving global progress in forest data transparency and climate action. With 236 country reports validated, 64 countries engaged, and over 75,000 knowledge product views, it significantly strengthened forest monitoring and capacity worldwide. Strategic partnerships, inclusive outreach, and innovative tools empowered countries to meet reporting commitments under the Paris Agreement, positioning the initiative as a model for impactful, collaborative action. | The CBIT-Forest Project provides critical linkage between the ongoing work of FAO’s Forestry Division and the Enhanced Transparency Framework (ETF) of the UNFCCC. The project has successfully leveraged / complimented / provided linkage with the UNFCCC’s ETF and FAO’s ongoing work and investments on Forest Monitoring, Data Platforms, and the Global Forest Resources Assessment and extensive capacity development programs in many countries. | The project delivered strong and inclusive results, enhancing forest data transparency through upgraded tools, validated reports, and flexible updates with 59 countries. A total of 64 countries benefited from capacity-building, data sharing, and knowledge exchange. Strategic partnerships with academia and youth networks further amplified its reach and long-term impact. | Not applicable | The project team is results-oriented and strategically plans its activities to maximize outreach and participation, aiming to use GEF funds in a catalytic manner wherever possible. The results presented in this first PIR demonstrate FAO’s convening power and highlight how the project effectively builds on parallel investments, while mobilizing and strengthening existing networks.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.
Output 1.1 To facilitate access to best available forest resources data, FAO’s Global Forest Resources Assessment (FRA) data entry, review, reporting and dissemination platform improved with additional functionalities | Number of additional functionalities added to the FRA online platform | reviewed the report of the 2021 user consultation and evaluation; 4 functionalities added to the FRA online platform; developed/revised FRA dashboard with optimized performance and improved data structure; finalized bulk download functionalities; developed country report administrative page with overview functionality; developed additional functionalities for data entry, review, and publication of updated reports beyond the usual FRA cycle; 1 Jan-30June 2025: enhanced cost-optimization for file repository storage; improved PDF report generation with extensive formatting, layout, and data display improvements; developed new data history & comparison function for facilitated review of changes in country reports; developed new functions for enhanced user administration and management of Flexible Voluntary Updates; implemented feedback functionality on the FRA 2025 platform; collected and analyzed reviewer feedback in September and October 2024; collected and analyzed National Correspondent feedback in November 2024.
Output 1.2 The FRA platform contains the most updated, reviewed and validated data for countries and territories of the world to support global forest transparency | Number of FRA country and territory reports that are: prepared (*) reviewed validated | finalized technical preparations for the flexible voluntary update reporting on the FRA platform; contacted 59 countries with expressed interest in updating their country's reports in 2025; initiated editing and reviewing country reports on the FRA platform with countries who confirmed participation in FRA flexible voluntary updates in 2025; integrated training on FRA Flexible Voluntary Updates in a regional workshop in Guatemala to be held on 11 July; 236 FRA country and territory reports prepared, reviewed and validated by September 2024; updated the FRA 2025 database with the best available country data; finalized FRA manuscript in English and translated to remaining five official UN languages. The report will be published on 21 October 2025.
Output 1.3 Networking, communication and awareness raising with focal points from the different forest-related data collection and reporting processes, to report transparent and consistent forest data | Number of focal points informed about FRA 2025 process | contacted FRA NC´s and their alternates and collaborators throughout the FRA 2025 data collection and validation cycle; updated FRA network of NCs and Alternates with new nominations; 571 focal points informed about FRA 2025 process; Collaborative Forest Resources Questionnaire: contributed to coordination and communication with partners on the Collaborative Forest Resources Questionnaire (CFRQ); Observatoire des Forêts d'Afrique Centrale (OFAC): organized side event with OFAC at the 20th Meeting of the Parties of the Congo Basin Forest Partnership on improving primary forest data in June 2024; maintained dialogue with OFAC on updates on FRA and OFAC activities and releases; included OFAC as part of the task force on the definition of forest degradation; planned joined activities for enhanced primary forest reporting in the central Africa subregion; Amazon Cooperation Treaty Organization (ACTO): provided technical support to the ACTO Secretariat to develop the second report of the State of the Forests in the Amazon Region. This support included: enabled access to the most updated FRA data for the ACTO member countries, developed indicators to be included in the assessment, supported to national technicians in charge of preparing the national submissions, developed regional scale analysis of deforestation drivers and forest disturbance (the latter in collaboration with the EC-JRC); held an in-person regional workshop for data validation carried-out in Bogota (Colombia) in June 2025; UNECE/FAO/Forest Europe Joint pan-European Data Collection on Forests and Sustainable Forest Management (JPEDC): finalized Joint pan-European Data Collection and provided technical support throughout the process; developed and tested in cooperation with UNECE a data collection interface on the FRA platform; launched the 2025 JPEDC system; developed a user guide and held a regional workshop with partner organizations in Helsinki, Finland 11-14 September 2023.
Outcome 2
Output 2.1 Forest data sharing enhanced through their publication in an open and digital platform | Number of countries sharing forest-related data and information publicly | held bilateral meetings with countries in LAC, Asia-Pacific and Africa (2024-2025); contributed globably to raising awareness through online sessions, including a webinar for the project launch with focus on forest data transparency (30 April 2024); Forest data without borders: Knowledge exchange on national forest inventories in the Asia-Pacific Bangkok, Thailand (25-27/03/2025) and Path to resilience: Uzbekistan's focus on climate change adaptation reporting (8 April, online); identified a short list of countries in Asia-Pacific, Africa and LAC (2024); created a repository of targeted countries with the availability of NFI data platforms; contacted in 2024-2025 the following countries (21): Zambia, DRC, Ethiopia, Sierra Leone, Gambia, Bangladesh, Lao People's Democratic Republic, Thailand, Nepal, Mongolia, Papua New Guinea, Indonesia, Mexico, Costa Rica, Colombia, Argentina, Panama, Ecuador, Guatemala, Peru and Uruguay; submitted formal invitation letters to join the forest data transparency initiative to share information through the FAM platform(under country request); 7 countries published national forest inventory data in the FAM catalogue: Lao People’s Democratic Republic, Mexico (3 NFI cycles), Peru, Bangladesh, Mongolia, Nepal and DRC; compiled metadata for country approval and/or publication in the FAM catalogue: Thailand, Zambia, Colombia, Ecuador.
Output 2.2 Enhanced technical capacity of forest and climate stakeholders on available platforms, resources and tools for forest-related data collection and analysis to support transparency reporting (e.g. Open Foris) | Number of individuals accessing the virtual capacity-building activities disaggregated by sex and age | adapted already existing OpenForis interactive story to a PDF version for the NFI online facilitated course (available in EN, ES and FR); developed/published a download text version for the self-paced course: Institutionalization of forest data; published the national forest inventory (NFI) self-paced e-learning courses in Spanish and French (with the financial support from AIM4Forests); published 2 publications linked to the preparation of the online facilitated courses: “Grounded in data – Informing climate action and reporting with national forest inventories” and Towards the institutionalization of forest data (available in 3 languages); developed content for the self-paced course 1: Uncertainty in estimating forest emissions: Introduction to Monte Carlo – 4 lessons (with financial support from AIM4Forests); delivered, simultaneously in EN, ES and FR, 2 online facilitated courses: national forest inventory (11 September-21 October 2024) and institutionalization of forest data (7 May-6 June 2025); 2713 participants accessed to the FAO collaborative platform for the NFI and IFD facilitated courses (34% women; 57% youth 25-35 years); migrated the NFI online facilitated course to the FAO eLearning Academy, now available as the "National Forest inventory - Learning journey" in EN, ES and FR (with the financial support from AIM4Forests); hired 2 consultants to work with academia networks and youth engagement; collected and analysed regularly (each 6 months) statistics on the use of knowledge products and its uptake (e.g. eLearning, NFMS assessment tool); published 1 flyer documenting the use of the NFMS assessment tool (Enhancing Ghana’s forest monitoring system for climate action through AIM4Forests); developed a youth engagement strategy and work plan with the International Forestry Students’ Association (IFSA); engaged with IFSA through regular monthly meetings; contributed with IFSA-organized global dialogue on “Bridging Science-to-Policy Transfer in the Forestry Sector,” (21 March 2025); run a global multilingual survey with IFSA on youth engagement (Q2/2025); analysed survey results for defining further campaign with IFSA; organized a career development and networking visit for IFSA/GLOFOR students to FAO Forestry Division (19 June, 2025); engaged with Young Forest Champions/A4F who joined the IFD online facilitated course; engaged with regional academia networks, including RUFORUM, UDUALC and UNIMED to foster dialogue and promote the integration of FAO learning resources into academic programmes; documented through a video the uptake of the NFI online course in the a master's degree in Benin; prepared a brief of Benin’s case study (to be published); delivered 2 online sessions in FR and ES with the FAO elearning Academy targeting FAO representatives and the Academia in Africa and LAC; developed and run a survey with UDUALC to gather interest on courses uptake in the LAC region.
Output 2.3 Knowledge sharing networks on national forest inventories facilitated and improved at national/regional levels to support forest transparency | Number of networks facilitated | engaged with country focal points from Asia and Pacific through the NFI online facilitated course; collected information on the status of 12 NFI in the Asia Pacic region through a pre-workshop survey; created posters for each NFI; ran the Forest data without borders: Knowledge exchange on national forest inventories in the Asia-Pacific, Bangkok- Thailand (25- 27/03/2025) with 12 countries; published the report of the Thailand workshop, defined a roadmap to follow up activities for the NFI network in Asia-Pacific; planned technical online sessions with the 12 countries to be delivered Q3/2025; supported the 6 steering committee meetings of the IFN-LAC network throughout 2024/2025; organized 3 technical meetings on forest harmonization data; 1 general assembly of the IFN-LAC network, organized 1 dedicated online session on open data (20 March, 2024); co-delivered a presentation of the network at the PLACA climate action platform meeting (6 June); organized 1 online session for NFI and community inclusion (August 2024); organized the Forest Data Without Borders: Knowledge Exchange on National Forest Inventories and Forest Biodiversity in Latin America and the Caribbean to be held in Guatemala (7-11 July, 2025); monitored the men and women taking part to the IFN-LAC network meetings (2024: 64% women; 202: 50% women); 2 networks in LAC and in Asia-Pacific facilitated
Outcome 3.
Output 3.1 New set of knowledge products on successful forest data transparency-related developed and disseminated | Number of knowledge products developed and disseminated | developed web page, publications, web stories, flyers and videos in multiple languages; published monthly LinkedIn newsletter; used FAO and other social media accounts and FAO and GEF newsletters to disseminate; migrated the CBIT-Forest web page (in EN, ES, FR); developed 3 new tabs in multiple languages under the CBIT-Forest web page (NFMS assessment tool, Transparency in agriculture and forest microdata, Regional initiatives); developed a video of e-learning series ‘Forest monitoring for climate action’; developed 63 knowledge products, including web pages, publications, videos, newsletter and self-paced courses; developed 46 web stories in multiple languages (see news section in the web page); published 16 editions of the Forest data & climate action; participated/co-organized to key global events IUFRO, COFO and COP30(Forest Pavillion) (2024); delivered/contributed 2 global webinars presenting results of the capacity development activities and self-assessment tools; (Nov, 2024); delivered a join session with CBIT-GSP A closing conversation with FAO - CBIT-Forest Phase II: Growing from past experience, innovating for the future (12 February, 2025); contributed to deliver the workshop on BTR at SBSTA 2025 with the GEF SEC.
Output 3.2 Project communication and outreach strategy designed and implemented | Communication and outreach kit tool operational and further developed with new content | developed and updated yearly the communication plan; shared the plan with the GEF SEC communication; developed a Press kit developed for the launch of the project; updated of the Trello Board regularly; implemented the communication plan; published knowledge products and organized outreach and knowledge management events while featuring all the latest updates on the web page of the project; ensured gender balance in visuals of the project, including web stories, publications, newsletter (Women as Catalysts for Forest Data Transparency, etc); implemented gender action plan recommendations.
Output 3.3. Project results successfully monitored and reported | Number of project performance reports produced. | performed stakeholder consultation at the beginning of the project; set up regular communication with stakeholders through face-to-face or online meetings; held 3 project steering committee meetings (8 March 2024; 11 September 2024 and 25 February); shared presentations and minutes will all PSC members; prepared first and second project progress report (PSC) in due time; prepared first project implementation report (PIR) for the project; disseminated knowledge products in key global transparency events, including the launch of the project; shared information from the project via the News and Events tabs on the project website and CBIT-GSP platform; published a one year in number of the project (https://openknowledge.fao.org/handle/20.500.14283/cd4787en).
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Highly Satisfactory (HS) | Highly Satisfactory (HS) | Highly Satisfactory (HS) |  | Highly Satisfactory (HS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project effectively met its objectives, advancing forest data transparency and fostering global collaboration. Key achievements include the FRA platform additional functionalities for enhacing reporting, the publication of NFI data by seven countries, strong capacity-building efforts reaching around 2,700 participants with the online facilitated courses, and impactful partnerships with academia and youth networks. Regional engagement in LAC and Asia-Pacific was strengthened. These results reflect a high level of performance and strategic impact. The overall number of direct beneficiaries disaggregated by sex and age (GEF Core indicator 11) is equal to 88 425 (37% women; 49% youth) coming from events, eLearning courses, online facilitated courses and practitioners' accessing knowledge products. | The project implplementation is proceeding as planned with results that are meeting or exceeding the performance indicators. The highlights of the reporting period include technical implementation of the novel FRA Flexible Voluntary Updates, successfull expansion of the open access to NFI data to cover additional countries, and successfull work with the regional NFI networks. | Project implementation is highly satisfactory, having adopted recommendations from the evaluation of CBIT-Forest Phase I. The project is on track to achieve and possibly exceed anticipated objectives. | Not applicable | The day to day management of this global project benefitted from the CBIT-Forest phase I investments and co-financing, ensuring a smooth progression from project design into delivery. The team is experienced, the work plans and budgets achieveable and risks are managed to secure timely delivery of quality outputs. There is a lot to learn from this project and lessons to be replicated.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Significant progress has been made in advancing the FRA 2025 online platform. Key achievements include the validation of 236 country reports, enhanced data functionalities for editing and review, as well as improved user experience through a redesigned dashboard and bulk download options. Strategic collaborations with OFAC, ACTO, and UNECE/FAO have strengthened regional forest data efforts. Feedback mechanisms were implemented and analyzed, while technical preparations for flexible voluntary updates are well underway with 59 countries expressed interest in participation. Training, outreach, and communication tools—including a web story and animated video—are under development. The FRA 2025 report is finalized and set for multilingual release in October, marking a major milestone in global forest reporting. The CBIT-Forest project catalyzed global momentum for forest data transparency and international cooperation. Through strategic bilateral engagements across Latin America and the Caribbean, Asia-Pacific, and Africa, the project fostered inclusive dialogue and cross-regional knowledge exchange. Its global launch—marked by a high-profile webinar—set the stage for transformative events like the “Forest Data Without Borders” workshop in Bangkok. A key achievement was the outreach to 21 countries, inviting them to join the Food and Agriculture Catalogue, which led to the publication of National Forest Inventory data by seven nations and progress toward metadata approval by several others. Capacity development surged through multilingual online courses, empowering around 2,700 participants—34% women and 57% youth. Deepening partnerships with academia and youth networks such as the International Forestry Students’ Association sparked vibrant engagement through surveys, dialogues, and career-building initiatives. Strengthened regional networks in LAC and Asia-Pacific now anchor sustained progress toward institutionalizing forest data and advancing climate action. Overall, a total of 64 countries have benefited from data sharing, capacity-building, and knowledge exchange activities carried out at global, regional, and national levels. The CBIT-Forest project has played a pivotal role in advancing forest data transparency and climate action, aligning with global policy priorities. It produced 109 multilingual knowledge products—including web content, videos, and self-paced courses—designed to support evidence-based decision-making. The project enhanced digital outreach through a dynamic web platform, monthly newsletters, and strategic use of FAO and GEF communication channels. It actively contributed to global policy dialogues at IUFRO, COFO, and COP30, and delivered high-level webinars and workshops on transparency tools and capacity development. A robust communication plan ensured visibility, inclusivity, and gender balance, while stakeholder engagement was maintained through regular consultations and steering committee meetings. Key achievements were documented in timely reports and showcased in the “One Year in Numbers” publication. CBIT-Forest Phase II demonstrates how targeted communication, innovation, and collaboration can empower countries to meet their climate reporting commitments and strengthen transparency under the Paris Agreement. CBIT-Forest II knowledge products (including publications, videos, flyers and web sites) were accessed over 75 000 times since the beginning of Phase II.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
During the FAO FRA 2025 data collection, challenges occurred in terms of outdated national data as well as limited financial and human resources in countries to prepare FRA reports, requiring increased support from the FAO. The piloting of the FRA Flexible Voluntary Updates mechanism has made it clear that a significant higher workload for the FRA secretariat and required constant engagement with countries and additional effort are required to maintain data integrity and consistency. For the FRA data platform, a long-term solution for its financial resourcing for maintenance and continuous development is needed to ensure that the diverse needs of a multitude of users are met. Throughout project implementation, key challenges emerged around country engagement, particularly in understanding and embracing data sharing. To address this, the project maintained continuous and sustained interactions with national counterparts, building trust and reinforcing the value of participation. Targeted support and guidance were provided to encourage involvement and overcome hesitancy. In contexts affected by political and economic instability, participation was occasionally delayed. However, the project responded proactively by working closely with stakeholders to highlight the benefits of transparency and collaborative data sharing. To further support the use of the FAO FAM platform, tailored assistance and regular follow-ups were offered, helping countries navigate technical and institutional barriers.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | The CBIT-Forest project has developed a robust Exit Strategy to ensure the long-term sustainability of its outcomes. This strategy focuses on strengthening institutional capacities, integrating tools into national forest monitoring systems, and fostering lasting partnerships. Key achievements include the successful transfer of capacity-building to national stakeholders, embedding transparency practices into existing frameworks, and supporting regional forest inventory networks for ongoing knowledge exchange. These efforts are further reinforced through collaboration with the FAO eLearning Academy, FAO forest monitoring networks, and strategic partners—empowering countries to independently maintain and advance forest sector transparency well beyond the project’s conclusion.
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The CBIT-Forest project is strategically building institutional capacities to foster national ownership and ensure the long-term sustainability of forest transparency efforts. Through open-access, multilingual learning resources—including self-paced and facilitated online courses, and technical publications—the project supports the institutionalization and replication of knowledge. Facilitated online courses equip participants to apply and share skills beyond the project’s lifespan, while the active engagement of young professionals strengthens future leadership in forest data transparency. Tailored support to national ministries and agencies enhances their ability to manage and disseminate forest data. By promoting cross-sectoral collaboration, the project unites government, civil society, academia, and local actors in advancing forest monitoring systems.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low risk
New environmental and social risks.
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects)
Grievance Redress Mechanism (GRM)

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Social |  | High | Yes | Lack of commitment of countries to participate to the Capacity-Building and knowledge sharing activities as well as lack of interest on the use of knowledge products and platforms developed by the project | Keep continuous and sustained interactions with countries involved to tailor project deliverables to needs and priorities
2 | Social |  | High | Yes | FRA data users and national correspondents discontinue the use of the online platform for data entry / internet connectivity problems | Keep continuous and sustained interactions with FRA data users and national correspondents
3 | Political |  | High | Yes | Political and economic environment in the countries does not favour participation in project activities | Work together with the countries, partners and other stakeholders to promote the benefits of transparency requirements
4 | Social |  | High | Yes | FRA national correspondents, partners and other focal points are unwilling to familiarize themselves with FRA 2025 process | Communicate consistently and effectively on the FRA 2025 process with all stakeholders
5 | Social |  | High | Yes | Countries are unwilling to participate to the project activities related to data sharing, capacity-building and knowledge exchange | Consultation through regular engagement to ensure consistency with existing capacity and creating competency where required.
6 | Institutional |  | High | Yes | Project fails to establish suitable connection to target users | Country level engagement and support will be routinely undertaken
7 | Legal & Regulatory |  | Moderate | Yes | Countries are unwilling to share forest-related data in the FAO FAM platform | Country level engagement and support will be routinely undertaken
8 | Operational & Logistical |  | Moderate | Yes | Inadequate project management | Monthly review of transaction lists, rigorous application of all proven and relevant project accounting, financial management, recruitment and procurement procedures of FAO.
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
| Low | Risk score/Impact has been provided in the table above; risk score/likelihood for all the items is considered 'UNLIKELY' (see CEO endorsement document)
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework
Components and cost
Institutional and implementation arrangements
Financial management
Implementation schedule
Executing Entity
Executing Entity Category
Minor project objective change
Safeguards
Risk analysis
Increase of GEF project financing up to 5%
Co-financing | Positive: co-financing through joint activities with the Aim4Forest Programme
Location of project activity
Other minor project amendment (define)
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Others | Global Forest Resources Assessment National Correspondents (FRA-NC) | Direct beneficiary | FRA NC were involved in online and in-person workshops; FRA newsletter
Others | United Nations Framework Convention for Climate Change | Implementing partner | Depending on the activities being implemented, regular communication is maintained. The UNFCCC, as a member of the Project Steering Committee, actively participates in key initiatives—joining live sessions of the online facilitated courses and collaborating on joint publications.
Others | Paris Committee on Capacity-building (PCCB) network | Strategic partner | PCCB helps to disseminate products under the project
Others | FAO’s eLearning Academy | Implementing partner | Regular communication supports the implementation of a diverse portfolio of activities, including the enhancement of the eLearning course series, delivery of two multilingual online facilitated courses, and organization of ad hoc webinars in collaboration with academia
Others | Global Forest Observations Initiative | Strategic partner | Regular communication to share knowledge and activities with all partners from the GFOI has been disseminated through the email list (3759 subscribers), Linkedin (1262 followers), X (1861 followers) and Facebook (1876 followers), as well as the website's news and events pages. In the context of GFOI/Aim4Forests south-south exchange 2 webinars where held: Learning opportunities for all: Strengthening forest data for better (26 nov, 2024) reporting and Enhancing national forest monitoring systems for climate action: Tools, plans and approaches (28 nov 2024). Moreover, three regional information exchanges were held online for partners to provide updates on recent progress, hot topics and common challenges in the regions of Africa, Asia-Pacific, and Latin America and the Caribbean (held in 2024).
Others | Initiative for Climate Action Transparency (ICAT) | Strategic partner | Regular communication facilitates knowledge sharing and coordination of activities, primarily focused on ETF-related efforts in the LAC region and through global collaboration under the ETF coordination led by the CBI-GSP project
Others | National Focal Points (NFP) for activities pertaining to the UNFCCC | Direct beneficiary | The UNFCCC Focal Point was actively engaged in the delivery of the two online facilitated courses conducted under the project
Others | International Forestry Students' Association | Direct beneficiary | Since February 2025, an engagement plan has been actively implemented, supported by consistent monthly communication and updates. A number of key activities have already been successfully carried out (webinar, survey)
Others | Latin American and the Caribbean national forest inventory | Direct beneficiary | Support was provided to the network secretariat, including coordination of steering committee meetings, general assemblies, and communication-focused coordination sessions. Online technical sessions were conducted to advance harmonization efforts, alongside preparations for the in-person meeting held in Guatemala from 7–11 July 2025
Others | CBIT-AFOLU | Strategic partner | Joint efforts were made in preparing ETF-related events, such as SBSTA. The CBIT-AFOLU project’s DGroup platform is actively used to disseminate learning opportunities, including products featured on FAO’s ETF webpage.
Others | CBIT-GSP platform | Strategic partner | Regular communication to share knowledge and activities throughout the year; joint webinar to share experience of CBIT-Forest (12 Feb 2025); joint planning for the delivery of the Second Transparency Forum (Sep. 2025)
Others | Collaborative Forest Resources Questionnaire | Direct beneficiary | Contributed to coordination and communication with partners on the Collaborative Forest Resources Questionnaire (CFRQ).
Others | UNDP | Strategic partner | Communication happening around ETF and forest related topics and working jointly towards the delivery of a session for the Global Transparency Forum to be held in Sep. 2025.
Others | ACTO (NEW) |  | Provided technical support to the ACTO Secretariat to develop the second report of the State of the Forests in the Amazon Region. This support included: enabled access to the most updated FRA data for the ACTO member countries, developed indicators to be included in the assessment, supported to national technicians in charge of preparing the national submissions, developed regional scale analysis of deforestation drivers and forest disturbance (the latter in collaboration with the EC-JRC); held an in-person regional workshop for data validation carried-out in Bogota (Colombia) in June 2025.
Others | OFAC (NEW) |  | Organized side event with OFAC at the 20th Meeting of the Parties of the Congo Basin Forest Partnership on improving primary forest data in June 2024; maintained dialogue with OFAC on updates on FRA and OFAC activities and releases; included OFAC as part of the task force on the definition of forest degradation; planned joined activities for enhanced primary forest reporting in the central Africa subregion.
Others | UNECE/FAO/Forest Europe (NEW) |  | Finalized Joint pan-European Data Collection and provided technical support throughout the process; developed and tested in cooperation with UNECE a data collection interface on the FRA platform; launched the 2025 JPEDC system; developed a user guide and held a regional workshop with partner organizations in Helsinki, Finland 11-14 September 2023.

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | No
b. Improving women's participation and decision making | Yes | Women accounted for 37% of participants across global, regional, and national events, as well as online courses—representing a meaningful stride toward gender-inclusive forest data transparency and capacity development. This level of participation not only surpasses the project’s minimum benchmark of 30% female representation in decision-making and consultative processes, as outlined in its gender analysis and action plan, but also underscores a growing commitment to equitable engagement in environmental governance. The CBIT-Forest project successfully implemented a robust and forward-looking suite of gender-responsive actions, guided by its Gender Action Plan. These measures were not add-ons—they were strategically woven into every facet of the project, from management and capacity development to knowledge sharing. Gender equality was not only a stated priority, but a lived practice throughout the project cycle. Every new team member receives mandatory gender training aligned with FAO and GEF policies, fostering a shared foundation of gender equity from day one. In capacity development, the project actively championed women’s participation through inclusive outreach, thoughtful facilitation, and gender-sensitive training design. Training sessions highlighted the essential contributions of both women and men in forest data collection, analysis, and reporting, with participation rigorously tracked using gender-disaggregated data. This integrated approach ensured that gender equity was not just promoted—but embedded, measured, and sustained. In knowledge management, the project celebrated women’s leadership and contributions through compelling success stories, engaging social media content, and gender-responsive knowledge products—including reports, videos, and web stories—designed to reflect diverse perspectives. These materials were crafted in accessible formats to ensure usability for all stakeholders, regardless of technical background or digital access. Gender indicators were integrated into the results framework, making gender equality a visible and measurable outcome. The project’s communication strategy also included specific guidance on integrating gender considerations, ensuring that outreach and content development reflected an inclusive perspective and contributed to gender-sensitive reporting. Women’s participation in the FRA2025 cycle was significantly increased with the aim to enhance gender balance within the network of FRA National Correspondents. In total, 299 experts from 157 countries participated in the workshops, inclusive of National Correspondents as well as their alternates and collaborators. Of these attendees, twenty-seven percent were female. This attendance is a 17 percent increase from the FRA2020 cycle. Additionally, the percentage of female National Correspondents and alternates has increased from 19 percent (FRA2020) to 29 percent (FRA2025). Emphasis was placed on encouraging women’s involvement in workshops and training sessions to ensure their active engagement and input in key activities. These efforts contributed to a more diverse and inclusive representation, thus strengthening the FRA2025 process overall
c. generating socio-economic benefits or services for women | No
Any other good practices on gender

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The knowledge management and learning strategy was developed to capture and disseminate key products. The strategy has been periodically revised based on monitoring results of outreach and knowledge management efforts to ensure effective improvements to visibility and accessibility. A visual identity was developed in the early stages of the project, including templates with consistent branding to elevate the profile of the activities conducted under the project. FAO ensured the visibility of GEF Secretariat financing across all the project’s materials by including logo and textual acknowledgments and links and social media handles as appropriate. The launch of the project, its goals and objectives were effectively shared through a variety of international, regional and national media outlets and social accounts. The outreach was ensured through an FAO global press release in English, French and Spanish (https://www.fao.org/in-action/boosting-transparency-forest-data/news-and-events/news/detail/Charting-a-transparent-path-for-global-forest-data-and-innovative-climate-action/en), a dedicated webpage, a project flyer (in English, Spanish and French) and a launch webinar. A press kit was compiled and published with these materials, found here: https://www.fao.org/in-action/boosting-transparency-forest-data/news-and-events/press-kit/en. In the project's web site news (https://www.fao.org/in-action/boosting-transparency-forest-data/news-and-events/news/en), events (https://www.fao.org/in-action/boosting-transparency-forest-data/news-and-events/events/en) and resources (https://www.fao.org/in-action/boosting-transparency-forest-data/resources/publications/en) are regularly updated. A stakeholder assessment was conducted to map global, regional and organizational contacts to best understand key and target audiences for the development of the knowledge sharing strategy. The implementation of this strategy included ongoing stakeholder engagement for key launches, events and learning opportunities; the release of project papers and findings; and public engagements at international environmental conferences and forums to share knowledge products. The project continues to coordinate with key partners, such as the UNFCCC, CBIT-GSP, IFSA and the GFOI community, to maximize information sharing with stakeholders. Ongoing collaboration with the GEF SEC Communication & Outreach team ensures the timely dissemination of key transparency-related updates and project deliverables. For example, the UNFCCC has made events hosted in the context of the project available in the REDD+ web platform and transparency calendar. The CBIT-GSP platform also publish related news, events and knowledge products from the CBIT-Forest project. Regular communication to share knowledge and activities with all partners from the GFOI has been disseminated through the email list (3759 subscribers), LinkedIn (1262 followers), X (1861 followers) and Facebook (1876 followers), as well as the website's news and events pages. To this purpose, the following products and materials were developed, managed and shared by the knowledge management and communications team: social media and newsletter content; brochures, reports, infographics and publications on national forest inventories and regional progress; website updates with resources linked (NFMS assessment tool , FAM Catalogue and regional initiatives) and stories on national and regional initiatives; instructional videos and webinars; e-learning courses and online live facilitated courses: and other visual content that effectively convey complex project goals and achievements. Workshops, trainings and stakeholder meetings were periodically organized to improve forest data collection and transparency across different regions (e.g. the Latin America and the Caribbean [LAC], the Asia-Pacific, and the European regional networks) – in-person, online and hybrid formats. Collaborative webinars were hosted as part of the online facilitated courses, focusing on transparency and capacity-building in the forest data sector. Communication is consistently maintained with colleagues from FAO regional and country offices to elevate the visibility of this work. For example, the press release for the second in-person gathering of the LAC National Forest Inventory Network (IFN-LAC) was drafted and published together with the regional communication office, as was that for the Asia-Pacific. Collaboration with country offices is also similarly evidenced with co-published press releases, such as those with Nepal and Mongolia. Promotional campaigns were routinely disseminated via FAO and the GEF newsletters, social media and web stories to raise awareness on existing forest data-related platforms, tools, e-learnings, and publications. These campaigns were also published in collaboration with partners to maximize outreach to targeted audiences nationally, regionally, and globally. By promoting knowledge products with standardized methodologies, best practices and technical support, the project helps countries to improve their forest monitoring systems and fulfill their reporting obligations under international agreements.
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | In an era rapidly marked by a digital shift, trainings, workshops and outreach projects continue to largely be implemented online or in hybrid format; this approach allows the project to target a larger, global audience. The learning materials and tools developed under the project have been translated in three languages (English, French and Spanish), thus ensuring accessibility to a wider demographic. Online training and videos were also interpreted in the three languages, thus ensuring better participation from countries worldwide. The project’s largest events and materials that were most significant in building the capacity for transparency include the online facilitated courses, global webinars and multilingual e-learning courses – through which users were awarded a digital badge certification. The digital badge certification offers unique benefits by indicating course completion and emphasizing the user’s acquired knowledge and skills. Since the project's inception, a total of 1,729 digital badges have been awarded through both self-paced and facilitated online courses—highlighting strong engagement and growing capacity in forest monitoring for climate action.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | The CBIT-Forest II communications plan outlines strategies to enhance visibility, stakeholder engagement, and awareness around forest data transparency. It targets governments, donors, NGOs, academia, and local communities through tailored messaging and multimedia content. The plan includes online and offline tools—websites, social media, workshops, reports, and videos—to promote project goals. Key components focus on improved access to forest data, technical capacity building, and knowledge sharing. Gender-responsive communication is emphasized, with inclusive content and monitoring. The plan also details timelines, responsibilities, and evaluation methods to ensure effective outreach and alignment with the project’s transparency and sustainability objectives. The new CBIT-Forest website (https://www.fao.org/in-action/boosting-transparency-forest-data/en) was launched in 2024 in English, French and Spanish; this language reach drastically improves the content accessibility around the globe, while the functionalities on the new host platform offer an improved user-experience. Since its launch, the website has reached over 25 000 views. The project has offered 4 self-paced e-learning courses to over 6 139 learners, from which 560 digital badges have been earned to certify acquired skills. These courses have been widely disseminated through the ‘Forest Monitoring for Climate Action’ series, available in English, Spanish, and French. Developed in collaboration with partners including the AIM4Forests Programme, the series is accessible via the FAO e-learning platform:" English version: https://elearning.fao.org/course/view.php?name=FMCA-series-en) Spanish version: https://elearning.fao.org/course/view.php?name=FMCA-series-es French version: https://elearning.fao.org/course/view.php?name=FMCA-series-fr With over 100 social media posts across partner accounts since the beginning of Phase II, more than 3 830 interactions have been made and nearly 105 100 views achieved. The Forest data & climate action LinkedIn newsletter has reached 24 235 members (43 949 impressions). CBIT-Forest II knowledge products (including publications, videos, flyers and web sites) were accessed over 75 000 times since the beginning of Phase II. A total of 64 countries have benefited from data sharing, capacity-building, and knowledge exchange activities carried out at global, regional, and national levels. These include 13 countries in Asia-Pacific (Bangladesh, Bhutan, Cambodia, India, Indonesia, Lao People's Democratic Republic, Mongolia, Nepal, Papua New Guinea, Philippines, Thailand, Timor-Leste and Vietnam); 24 in Africa (Benin, Burkina Faso, Cabo Verde, Cameroon, Central African Republic, Congo, Cote d'Ivoire, Gabon, Gambia, Democratic Republic of the Congo, Equatorial Guinea, Ghana, Guinee, Guinea Bissau, Kenya, Liberia, Mali, Niger, Nigeria, Senegal, Sierra Leone, Togo, Uganda, Zambia); and 27 across LAC (Antigua and Barbuda, Argentina, Bahamas, Barbados, Belice, Brasil, Colombia, Chile, Costa Rica, Cuba, Dominica, Dominican Republic, Ecuador, Grenada, Guatemala, Guyana, Jamaica, México, Nicaragua, Panama, Paraguay, Perú, Saint Lucia, Saint Kitts and Nevis, Trinidad and Tobago, Uruguay, Venezuela) reflecting the broad geographic reach and impact of the initiative. A significant communication challenge for a project of global scope is the consideration of time zones when engaging in product publicizing and event organizing for maximized engagement and participation. To address the challenge of visibility in social media publishing, platform analytics offer insights into peak engagement times for audiences. As for events, this is best addressed by targeting events to regions and nations rather than combining events with a global audience, particularly for online meetings and webinars. The ongoing collaboration with colleagues from FAO regional and country offices is critical to ensuring targeted visibility and accessibility. Moreover, the recording of webinars and sharing of these recordings to audiences that can have interest also addresses a gap in attendance due to time constraints, thus ensuring continued access to critical information.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | To support the implementation of Sierra Leone’s first National Forest Inventory (NFI), the Food and Agriculture Organization (FAO) of the United Nations, in partnership with the Ministry of Environment and Climate Change and with funding from the European Union delegation in Freetown, conducted an intensive two-week training in Kenema (https://www.fao.org/forest-monitoring/news-and-events/news/news-detail/strengthening-sierra-leone-s-capacity-for-implementing-a-robust-national-forest-inventory/en) that equipped over 60 forestry professionals with practical skills, digital tools, and a detailed understanding of the national NFI framework. Complementing the in-person training, selected forestry staff also participated in the National forest inventory online facilitated course (https://www.fao.org/in-action/boosting-transparency-forest-data/online-facilitated-courses/national-forest-inventory/en) delivered by the project. This course explained the key phases of a national forest inventory – from planning to implementation, and from data gathering to reporting. This online facilitated course created socioeconomic benefits by being freely accessible and digitally certified, thus empowering participants to enhance their professional qualifications without financial barriers. This is particularly valuable in countries where access to advanced environmental training is limited. Additionally, a self-paced version is now available and accessible to anyone, anytime in multiple languages: National Forest inventory (NFI) - Learning journey (https://elearning.fao.org/local/search/infocourse.php?id=1198) Rugiatu Bundu, from the Ministry of the Environment and Climate Change of Sierra Leona, shared her insights on the NFI online course, noting how the course empowered her with essentials of effective national forest inventory implementation, from planning to reporting. “My experience with the online course was valuable and incredible… all the courses were very much detailed… and the most valuable part of it is that at the end of the course you're going to have a digital badge… and most importantly, the course is free.” (video: https://youtu.be/juwVYnjv9is) The NFI online course supports access to new opportunities for employment, professional advancement and long-term technical capacity, particularly among early-career forestry professionals. Rugiatu Bundu has since enrolled and successfully completed the newer Institutionalization of forest data online facilitated course (https://www.fao.org/in-action/boosting-transparency-forest-data/online-facilitated-courses/institutionalization-of-forest-data/en), proving the recognized value and continued engagement of audiences in learning opportunities developed under the project.
Please provide links to related website, social media account | Websites FAO project page: https://www.fao.org/in-action/boosting-transparency-forest-data/en/ GEF project page: https://www.thegef.org/projects-operations/projects/11308 CBIT-GSP Global Coordination Platform: https://www.thegef.org/projects-operations/projects/11308 FAO Forest Monitoring: https://www.fao.org/forest-monitoring/how-we-collaborate/en FAO Global Forest Resources Assessments/Initiatives: https://www.fao.org/forest-resources-assessment/initiatives/en/ Social media accounts FAO corporate accounts: @FAOclimate, @FAOforestry, @FAOKnowledge @FAONews, @FAOStatistics, @OpenForis FAO regional accounts: @FAOAsiaPacific, @FAOCapacitacion, @FAOMesoamerica, @FAOWestAfrica FAO country office accounts: @FAOChile, @FAOColombia @FAOCostaRica, @FAOCotedIvoire @FAOGuatemala, @FAOHonduras @FAOPeru, @FAOUganda, etc. Other global accounts: @Data4SDGs, @GFOI_forest, @ICATclimate, @IFSAdotnet, @OpenDataWatch, @ScientificData, @theGEF, @UNEPDTU, @UNREDD, etc. Newsletters/mailing lists FAO Global Forest Resources Assessment FAO Data and Statistics Technical Network Forest data & climate action FAO and the GEF FAO InFOflash
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | List is available in this excel CBIT_Forest_Outcome1_2_3PIR1.xlsx (https://unfao.sharepoint.com/:x:/s/climatechange/EfT-5MU4N5dCpyf2nbw_1mgB8EW7_oXvgR_Le9HzIKABsA?e=sJWSbP)- check sheets: knowledge access social media 2024 social media 2025 Blog post Newsletter FAO Newsletter GEF CBIT-GSP
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Maryia Kukharava (email: Maryia.Kukharava@fao.org)

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. Not applicable to this project Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. Indigenous Peoples and local communities have played a vital and active role in the CBIT-Forest project, particularly through their strong participation in capacity-building initiatives. Notably, 36% of participants (1,062 individuals) in the Institutionalization of Forest Data online facilitated course and 40% (1,000 individuals) in the National Forest Inventory online facilitated course self-identified as Indigenous Peoples. These figures reflect the project’s commitment to inclusivity and its success in making training accessible and relevant to diverse communities. In a compelling video testimonial, Olgah Hellens—Founder and Director of iConserve in Kenya—shares powerful insights from the FAO e-learning series ‘Forest Monitoring for Climate Action.’ Her message underscores the vital role of local communities in recognizing the rich diversity of forests and their profound economic significance (https://www.youtube.com/watch?v=3sGr78lVKcY). Training sessions—both online and in-person—were designed to be culturally sensitive and inclusive, integrating elements that acknowledged and valued traditional knowledge in forest monitoring and reporting. A key example was the “Forest Data Without Borders: Knowledge Exchange on National Forest Inventories in the Asia-Pacific” workshop held from 25–27 March 2025, which addressed forest-based communities in forest monitoring. Another example applies for the “Forest Data Without Borders: Knowledge Exchange on National Forest Inventories and Forest Biodiversity in Latin America and the Caribbean” to be held 7-11 July 2025. Additionally, a dedicated webinar on 28 August 2024 focused specifically on the role of Indigenous Peoples and local communities in forest data transparency in collaboration with the AIM4Forests Programme. This event served as a platform for dialogue, knowledge exchange, and the recognition of community-led forest stewardship among governments in LAC. The intention and commitment are to hold further discussions and exchanges between community organizations and governments on how to better support local data generation and foster the participation and contributions of these important actors in national forest inventories and monitoring systems (more info: https://www.fao.org/in-action/boosting-transparency-forest-data/news-and-events/news/detail/the-network-of-national-forest-inventories-of-latin-america-and-the-caribbean-seeks-to-implement-innovative-techniques-for-community-inclusion/en).

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
GEF Agency | FAO Global Forest Resources Assessment (FRA) GCP/GLO/1030/MUL | Grant | 1000000 | 2220000
GEF Agency | FAO Global Forest Resources Assessment (FRA) EU FRA2025 | Grant | 2000000 | 1500000
GEF Agency | FAO National Forest Monitoring (NFM) GCP/GLO/789/MUL | Grant | 2176416 | 810656
GEF Agency | FAO National Forest Monitoring (NFM) UNJP/GLO/795/UNJ BABY09 | Grant | 0 | 277552
Total |  | Total | 5176416 | 4808208
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report?
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.