UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5392 | Umoja no.: SB-006317 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Initial Steps for the Establishment of the National Protected Areas Network in Iraq |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | Ecosystem Division, GEF Biodiversity and Land Degradation Unit |  |  |
| Name of co-implementing Agency |  |  |  |  |  |
| Executing Agency(ies) |  |  | UN Environment Programme, West Asia Office |  |  |
| Names of Other Project Partners |  |  | Ministry of Health and Environment, Government of Iraq |  |  |
|  |  |  | IUCN |  |  |
| Project Type |  |  | MSP |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Middle East North Africa |  |  |
| Names of Beneficiary Countries |  |  | Iraq |  |  |
| Programme of Work |  |  | POW 2018-19 Subprogramme 3 Healthy and Productive Ecosystems, EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | UNDAF 2015-19, Priority Area A: Improving the performance and responsiveness of targeted national and sub-national institutions Outcome A.1: Targeted government institutions capacities strengthened for accountability, transparency and provision of equitable and quality services |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | 15.1.2 Proportion of important sites for terrestrial and freshwater biodiversity that are covered by protected areas, by ecosystem type 15.3.1 Proportion of land that is degraded over total land area |  |  |
| GEF financing amount |  |  | US$ 1,230,365 |  |  |
| Co-financing amount |  |  | US$ 3,450,000 |  |  |
| Date of CEO Endorsement |  |  | 19 November 2015 |  |  |
| Start of Implementation |  |  | 09 August 2017 |  |  |
| Date of first disbursement |  |  | 05 August 2018 |  |  |
| Total disbursement as of 30 June |  |  | US$ 946,665 |  |  |
| Total expenditure as of 30 June |  |  | US$ 759,959.26 |  |  |
| Expected Mid-Term Date |  |  | TBD |  |  |
| Completion Date |  | Planned | 31 August 2021 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  | TBD |  |  |
| Expected Financial Closure Date |  |  | TBD |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Sub-Programme 3: Healthy and Productive Ecosystem | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA(a): The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels. Indicator (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems |
| --- | --- |
| Supported by the project, 2 new areas are about to be declared protected in Iraq – Dalmaj and Teeb, adding 211,200ha to the currently protected 284,022ha as area coverage for protected areas of Iraq. The current legislation is reviewed within the Ministry of Health and Environment in order to apply the necessary arrangements for the establishment of a Protected Areas Network in Iraq. Capacity development and stakeholder engagement will contribute to embed the skills needed in Iraq for successful management of a PA network and the knowledge about the linkages between ecosystem conservation, ecosystem services and socio-economic benefits and livelihoods. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |
| n/a – GEF5 project |  |

| Planned linkages with UNDAF | The project aims at building the institutional and technical capacities of the Ministry of Health and Environment (MoHE) and relevant government entities to fulfill their mandate to protect the Iraqi environment and to conserve its ecosystems and maintain or boost the services they provide, through capacity development and provision of technical tools to sustainably establish and manage a network of protected areas and to enable the enforcement of legal requirements nationally. This will allow aligning Iraq within the regional and international context and will have a global significance related to the harmonization of legislative frameworks and tools for conservation efforts in accordance with Aichi Target 11. Moreover, the project will help put in place critical professional capacity at national level, to support MoHE’s mandate in biodiversity conservation and protected areas management, setting priorities and piloting on-the-ground conservation action for the establishment of the first new National Protected Areas. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | A field survey was conducted in March 2019, assessing the areas of Dalmaj and Teeb both biologically and socio-economically. The declaration of Teeb and Dalmaj as protected areas is in the process of being officially approved by the Council of Ministries after getting the approval of the National Committee for Protected Areas in Iraq. These areas are described as: - Teeb Oasis area is located to the south-east of Iraq (within Maysan Governorate), at the border with Iran, where the Teeb river flows southward through a hilly desert area and forms a large oasis and wetland complex in the natural depressions and valleys. The area extension, as from the provisional delineated boundary, is about 119,200 ha. This area is ecologically varied and rich of habitats and species, including the globally threatened Asian Houbara (Chlamydotis macqueenii), the Striped Hyena (Hyaena hyaena) and the Desert Monitor lizard (Varanus griseus). Teeb area holds a big population (maybe the highest at national level) of Goitered Gazelle (Gazella subgutturosa) along with other vagrant fauna species that move over the borders between Iraq and Iran. - Dalmaj area was originally designed as an evaporation basin along the Main Outfall Drain (MOD) that was created in a natural depression in central Iraq (within Wasit and Qadissiya Governorates). The wetland extension, taking into account the provisional delineated boundary, corresponds to about 92,000 ha. The area is consider a biodiversity hotspot in central Iraq that, in the less disturbed parts of the wetland provides important nesting areas for resident and migratory water birds species including the globally threatened Basra Reed Warbler (Acrocepahlus griseldis) and the Marbled Teal (Marmaronetta angustirostris). Dalmaj Lake is used for farming the endemic species of fish Barbus sharpeyi (commonly called bunni in Iraq). Once both protected areas are fully declared, Dalmaji (92,000ha) and Teeb (119,200ha) will add 211,200ha to the current 284,022ha as area coverage under protected areas of Iraq. Additionally, the Legal Department at the Ministry of Health and Environment is reviewing the current legislation in order to apply the necessary arrangements for the establishment of a Protected Areas Network in Iraq. |
| --- | --- |

| Implementation Status | FY 2018 | FY 2019 | FY 2020__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS |  |  |  |
| - The declaration of PA Ministry of Health and Environment (MoHE) has started processing the Declaration announcing Dalmaj and Teeb as protected areas. By the end of the reporting period, both the Dalmaj and Teeb areas have been approved by the National Committee of Protected Areas. However, the Environmental Protection Council has only approved Dalmaj, whilst Teeb is still in the approval process. Both areas will be submitted to the General Secretariat of the Council of Ministers for a final approval to be officially declared as protected areas in Iraq. Once both protected areas are declared, Dalmaji (92,000ha) and Teeb (119,200ha) will add 211,200ha to the current 284,022ha as area coverage under protected areas of Iraq. - Legislation Review: The legal department at Ministry of Environment is still in the process of reviewing the rules and laws pertaining to establishment of legislation on protected areas within Iraq. The department is planning to review similar cases from around the region (i.e. Jordan) for the establishment of a PAN in Iraq to be drafted and included in the national legislative system. According to Iraq legislative regulations, establishing new legislation requires a committee from all related ministries, so as to ensure that any new legislation does not impede their strategy or any existing laws. Thus, it can be expected that this process may take some time to be completed. - Needs Assessment Workshop: A Needs Assessment Workshop is expected to be conducted in the fourth quarter of 2019, from which a programme of capacity building workshops can be created. In May 2018, the IUCN met with the MoHE in order to review the urgent training needs of the Ministry in order to ensure progress with the Project. The training areas that were identified as necessary were: - Management of protected areas and institutional coordination - Monitoring and evaluation - The Red List - Classification of birds, plant species, aquatic animals and threatened species - The impact of activities on protected areas and mechanism of granting environmental agreements / legislation and environmental impact - Training on environmental impact assessment / biodiversity - Contracting: - UNEP’s West Asia Office recruited a National Project Officer to be based in the Ministry of Health and Environment, Iraq; it developed a detailed job description, processed the job announcement and recruited the national officer through competitive selection. The selected candidate was offered the position on 20th October 2018 and began their duties on 20th December 2018. - IUCN contracted an International Consultant to design the establishment of a PAN within Iraq. - IUCN additionally contracted two National Consultants. One was recruited to conduct field studies in the relevant areas whilst the other was tasked with preparing GIS maps and layers. - Project Steering Committee (PSC) Meeting In close coordination with MoHE, UNEP West Asia Office has organized the first meeting for the Project Steering Committee (PSC) to be held in Baghdad, Iraq on the 23-24 July 2019. Representatives of the related Iraqi ministries such as the Ministry of Oil, the Ministry of Water Resources, and the Ministry of Agriculture will be involved in the meeting. The meeting will include an overview of the PAN project and will review the progress that has been achieved throughout the 1st Year of the project. Additionally, the MoHE will present a brief on the field surveys that were conducted in March 2019 in Dalmaj and Teeb, along with the results of this visit and lessons learned. Furthermore, the deliverables, activities and milestones for the 2nd Year of the project will be reviewed and discussed during the meeting. Importantly, the delay on the deceleration of Dalmaj and Teeb will be discussed in order to present solutions to overcome this obstacle. This situation will also be presented to the National Committee of Protected Areas in Iraq for their action. |  |  |  |  |  |

| Implementation Progress Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | MS |  |  |  |
| - Baseline Assessment: The Ministry of Health and Environment (MoHE), the IUCN, and the Project Consultant collaboratively conducted an environmental and socio-economic assessment within the Dalmaj and Teeb areas of the Qadissiya, Wassit, and Missan Districts during the period 16-30 March 2019. The field visit consisted of 2 components: (1) surveying pre-set points within the boundaries of each proposed protected area in order to highlight the environmental and socio-economic importance of the area; and (2) spotting the biologically and culturally key areas within the targeted area. Each of the pre-selected points had been chosen to represent the unique and important types of habitat within the areas of Dalmaj and Teeb. The field survey in these two areas consisted of flora survey, bird species survey, other-fauna species surveys, water and soil sampling and analysis, socio-economic survey, and a threats assessment. A total of 37 sampling sites were visited during the survey to collect biological, abiotic and socio-economic data and pictures from 18 sampling sites in Dalmaj and 19 sampling sites in Teeb. - National Workshop on the results of the Field Survey in Dalmaj and Teeb: On the 29th of April 2019, the IUCN and MoHE conducted a national workshop to present the results of the field survey conducted in Dalmaj and Teeb. The workshop aimed to: - Create the first opportunity for a wider gathering of key stakeholders from Dalmaj and Teeb in order to facilitate greater knowledge on the Protected Areas in their regions and the justification behind selecting these areas for the PAN national programme; - Create a platform for stakeholders to share their expertise and issues, and to better understand each-other; - Highlight the results of the surveys that were conducted during 16-30 March in both areas; and - Plan collaboratively for the next steps of the project. Prior to presenting the results of the survey by the project consultant, opening remarks were delivered by representatives from the MoHE, UNEP, and IUCN. The results showed that: - In the Dalmaj Area: The results of the flora surveys evidenced more than 30 plant species present within the different habitats in Dalmaj area. As for the Fauna results, of which the birds species form the most important component, 88 different species were observed during the surveys within both aquatic and terrestrial habitats. Moreover, the total population in the study area was 315 locals who live in random cluster houses made of clay and rely majorly on fishing, buffalo breeding, agriculture and livestock for living. This area lacks basic public services such as clean water, a sewage system, electricity, paved roads, and a transportation system. - In the Teeb Area: The results of the flora surveys evidenced more than 45 plant species found within the different habitats in Teeb area. As for the Fauna results, of which the birds species form a key component, 80 different species were observed during the surveys. The observed birds were found in different habitats that include terrestrial (including hills, undulated, and plains) and aquatic habitats represented by Teeb and Duweireej Rivers, and the seasonal wetlands. Furthermore, the total population in the study area was 1400 locals who were located within 50 small villages throughout the area. The locals in this area rely mainly on agriculture and grazing. - National Stakeholders Workshop On 30th of April 2019, the MoHE and IUCN conducted a National Stakeholders Workshop in Baghdad, Iraq. 25 participants engaged in the training including: UN Environment-West Asia Office, IUCN, Ministry of Environment and its directorates in the three governorates, Qadisyia, Missan, and Wasit, that is covering Dalmaj and Teeb, and National Committee for Protected Areas in Iraq headed by the Deputy Minister for International Affairs. The workshop aimed at presenting the project to The National Committee on Protected Areas in Iraq, along with decision makers from the MoHE. The desired result of the meeting was to utilize recommendations on designing a Protected Areas Network in Iraq. The workshop began with a presentation delivered by UNEP’s National Officer in Iraq, providing an overview of the project objectives, components, outputs and work plan, in addition to the management structure of the project. Then IUCN then delivered a presentation on the project management plan and the vital role of stakeholder’s involvement in the project. This presentation was then followed by an open discussion among participants that concluded with a set of suggestions and recommendations on the management of protected areas and stakeholder engagement, including: - Preparation of two management plans, one for each protected area. - The necessity of circulating the information and documents on the progress of the protected areas among the participants to follow up with their ministries and departments; - Promote communication and media to help deliver a clear message delivery to decision-makers; - Rehabilitee of infrastructure (especially roads) to facilitate easy access to the protected areas (Dalmaj and Teeb). - Take into consideration the challenges and threats in of Teeb and Dalmaj while planning and designing management plan. - Consider investment as a great opportunity in the protected areas, as it promotes the economic situation of the area, and promote sustainable investment; - Defining the gaps in the regulations and laws in order to solve them. - Decision from the Council of Ministers to establish a Board of Directors of Protected areas (Represents a similar management system to the World Heritage management) - There must be a continuity in the establishment and declaration of protected areas, and there should be prepared list of areas proposed to be announced as protected areas according to the priority. - Capacity Building Programme Based on the needs of MoHE that have been shared at the early stages of the project with IUCN to build the capacity of the Ministry’s staff who are involved in the protected areas, IUCN conducted two capacity building training: - Training Workshop on Environmental Impact Assessment (EIA) in Protected Areas The workshop was conducted in Amman, Jordan on 20-21 April 2019. 17 participants from the MoHE took part in the workshop, which aimed to deliver the following objectives: - Enhance understanding of the EIA mechanism in protected areas, and the roles of different parties within the process; - Strengthen capacity and skills in EIA management for effective operation in Protected Areas of Iraq; - Share experience of EIAs and good practices; - Introduce “know-hows” and practical tips to identify Environmental Impacts and the correct course of action at different stages of a project’s lifecycle. - Understand the importance of stakeholders in the EIA process, and how to enable clear communication. - Be able to access different case studies of EIA in practice in Iraq and surrounding countries. - How to be accountable to public comment, and how to take advantage of public EIA review. - How to determine if the information and process culminating in EIA is sufficient for a final decision to be made. The trainer presented an introduction on the process of EIA, including: screening, scoping, preparation of TORs for EIA, preparation of EIA workplan, environmental impact study, EIA reporting, EIA review, EIA decision making, and post-EIA monitoring and audit. Additionally, the training included two major sessions regarding comprehensive details on biodiversity and protected areas and working groups to analyze some specific case study on EIA projects. The training workshops were concluded with a set of recommendations raised by the participants on Protected Areas and EIA. - Training Workshop on IUCN Red List. This Training was conducted by IUCN on the Red List of Threatened Species on 10-11 June 2019 in Amman, Jordan. The workshop had 11 participants from MoHE as part of their Capacity Building Programme. Prompted by the Red List’s increasing popularity and the growing need for Red List training around the world, the MoHE learned about the IUCN Red List assessment process and how to prepare high-quality Red List assessments. All of the topics covered in a typical IUCN Red List Assessor Training workshop were included, with some additional lessons that allowed the participants explore some aspects of the Red List Categories and Criteria in more detail. The workshop was concluded with a set of recommendations raised by the MoHE team on the National Red List and Conservation Plan. - Monitoring and Evaluation Activities for monitoring and evaluation carried out during the reporting period: - Numerous follow up discussions amongst partners have been carried out to ensure project implementation is on track, including meeting with the Project Manager and Project Coordinator at the MoHE. - Reviewing the Workshop reports produced by IUCN, including the EIA Workshop report, the Red List Workshop report, the results of the Field Survey Workshop report, the National Stakeholder Workshop report, and the Field Survey report. - Reviewing the financial reports for the 1st instalment of MoHE and IUCN. - UNEP’s Project Officer attended project events in Baghdad, including: Results of Field Survey Workshop and National Stakeholders Workshop. - Close monitoring of the implementing of planned activities in order to ensure that they are aligned with the agreed project workplan. - Regular contact from UNEP’s Project Officer in Baghdad in order to provide detailed updates on the implementation of planned activities and events as well as to enable the identification of project gaps and obstacles. |  |  |  |  |  |

| Risk Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M | M |  |  |  |
| Overall institutional as well as security risks persist and are only marginally changeable by means of the project’s engagement itself. Nevertheless, the project is aiming to change its enabling environment to a more favorable one, in line with its overall objective, mitigating and reducing known risks to the amount possible. Therefore, it can be assumed that the risk level with regard to specific project-related risks will diminish during project lifetime. As for limiting professional capacity gaps in Iraq, a Training Needs Assessment (TNA) for staff of MoHE and line Ministries at central level as well as local level (Dalmaj and Teeb areas), and also other strategic partners, is planned to be carried out in Q4 2019, providing the basis for a Capacity Development programme to be developed and effectively implemented throughout the project. While the aim is to mitigate related risks, the project so far did not fully deliver in this regard, predominantly due to the slow institutional response in Iraq. A workshop on Field Survey Methodologies was conducted in December 2018 prior to the field survey to Dalmaj and Teeb in March 2019, where MoHE staff applied what they learnt in the workshop. Moreover, two capacity development workshops on Environmental Impact Assessment (EIA) and IUCN Redlist in April and June 2019, respectively were conducted. As for the weak stakeholder engagement and awareness at the local level, MoHE is planning to conduct stakeholder engagement and consultation workshops in each of the three governorates that are covering the pilot sites, Qadisiyah, Wasit and Maysan, to present the project in detail and interact with the stakeholders’ feedbacks and discussion. An Awareness and Outreach Strategy is in the process of being developed, also based on the feedback received from the relevant stakeholders. Moreover, all the project materials (documents, pictures, updates) will be publically accessible through the PAN website that is currently in the developing stage. Also, the outreach materials and technical toolkits will be designed to address all stakeholders’ needs. The stakeholder engagement and awareness strategy will be discussed at the 1st Project Steering Committee Meeting that will be taking place in July 2019 where members from relevant Ministries will be present to provide their feedbacks and actions towards active involvement of their ministries in the project Having these capacity development, awareness and outreach as well as the stakeholder engagement activities in place will build a local, national and international support base which will enable the project to overcome the political fluctuation in the country during the lifetime of the project. Also, these activities will help in disseminating the concept of Protected Areas among local and national stakeholders to avoid misunderstandings, and hence a resistance that may to interrupt the project progress. Legal Department at MoHE has started the process to review the legislation and case studies to support the establishment of protected areas in Iraq. Also MoHE is planning to establish a committee with the relevant ministries to review their legislations and this process, which is under the supervision of Head of National Committee of Protected Areas in Iraq which it holds members from the relevant ministries, and that will be a significant advantage towards close coordination among the relevant ministries and accelerate the procedures. |  |  |  |  |  |

| Stakeholder engagement | On 30th April 2019, the MoHE and IUCN conducted a National Stakeholder Workshop in Baghdad, Iraq. The workshop aimed to present the project to vital stakeholders, The National Committee on Protected Areas in Iraq, along with decision makers from MoHE, and take their recommendations on designing a Protected Areas Network in Iraq. The workshop began with a presentation delivered by UNEP’s National Officer in Iraq providing an overview of the project objectives, components, outputs and workplan, in addition to the management structure of the project. The IUCN then delivered a presentation on the project’s management plan and the involvement of stakeholders throughout the project, followed by an open discussion among participants that concluded with set of suggestions and recommendations on the management of protected areas and stakeholder engagement. Additionally, the MoHE has planned to conduct three local stakeholder workshops in the three governorates that cover Dalmaj and Teeb areas. Stakeholder engagement will be significant in developing the PAN design and implementation plan as well as in developing an awareness and outreach strategy. |
| --- | --- |

| Gender mainstreaming | The role of gender and empowering women was discussed during the National Stakeholder Workshop that was conducted in Baghdad in April 2019; the results are to be comprehensibly considered in the development of PAN design and implementation and management plans as well as the awareness and outreach strategy. |
| --- | --- |

| Knowledge activities and products | Not yet applicable |
| --- | --- |

| Stories to be shared | Not yet applicable |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Project Objective: Develop and start implementing the plan for the establishment of a national Network of Protected Areas | 1. Number of protected areas established [Baseline:0 Target: 3] 2. % of the total area of Iraq with protected ecosystems [Baseline: 0.65% Target: 1.13%] | Methodology of designing the network is identified in participatory approach. Surveys and assessment needs are defined with the ministry of environment. Initial biodiversity survey conducted for the two PAs. Review of current legislations and identification of gaps | The target is to have two new protected areas declared/gazetted making a total of 3 PAs by the end of project period The target is to increase the current area under protected ecosystems from 284,022ha (0.65%) to 495,222 (1.13%) Because Dalmaji and Teeb sites area = 211,200ha (0.48%) | To develop and establish network of protected area of Iraq 2 PAs are declared officially in Iraq | Baseline assessment for the 2 PAs were conducted where biological and socio-economic information was collected. Capacity Building training workshops were conducted. Plans: PSC meetings in Q3 2019, and Training Needs assessment, PAN Design, Implementation and Management Plan will be started in Q4 2019. | S |
| Outcome 1: 1.1 The first Protected Areas Network for Iraq is designed. Existing information and prior studies in the country, Inventory of the Key Biodiversity Areas of Iraq, NBSAP results, international best practice, and relevant regional examples in PA management are reviewed as the basis for the plan | 1) Number of MoE regulations on PAs approved by NCEP and Ministers Council or 2. Number of initiatives on PA prepared by MoE submitted to NCEP and council of ministers 3. Number of stakeholders involved by MoE in the PA procedure design process | The legal department in the ministry of environment is reviewing the current law to define the gabs and it is agreed to us some PAs areas in the region as references. IUCN trained the ministry staff on the Green list initiative to be used as tool for management effectiveness in Iraq. The literature review and planning process is going and the assessment stage is planned. The Ministry of environment is holding regular meetings of the working groups of experts established under the project. However, workshops for stakeholders’ engagement have not been started. The first workshop is planned for January 2019 at the national level while 2 stakeholder workshops will be held at the local level for the two pilot sites in conjunction with the visit of the IUCN experts. | Existence of a coherent and coordinated design and costed PAN Plan of Iraq At least 15 key Stakeholder groups involved in the PAN design process. | The Project deliverables Project reports (M&E) Reports/minutes of the National Committee for Protected areas law is reviewed and approved by NCEP. Some protected areas get the green list award. At Least three workshop for stakeholders engagement are organised. Reports/minutes of stakeholder consultations National Reporting to the CBD Secretariat (SP2020/Aichi Targets, POWPA) | The legal department of the Ministry of Environment is still in the process of reviewing the regulations and identifying the gaps regarding the declaration of protected areas in law, as the process needs to be in close coordination with other related ministries (i.e. Oil, Water Resources, Agriculture) to avoid the conflict in the regulation among these ministries. The declaration of the sites are in the process of being approved by the Environmental Protection Council (for Teeb and General Secretariat of the Council of Ministers (Dalmaj and Teeb) National Stakeholders Workshop was conducted in Baghdad on 30 April 2019 to present the project to the key stakeholders: The National Committee on Protected Areas in Iraq, along with decision makers from the MoHE. Their recommendations on designing protected areas Network in Iraq were noted and will be taken into consideration. | MS |
| 1.2 The required national professional capacity is in place to support all steps in the process of development of the first comprehensive PA Network in Iraq | A Capacity Building Programme for PA Management in Iraq is developed and effectively implemented a) Number of partners contributing to the capacity building programme and Number of UN agencies contributing to develop MoE capacity; b) Number of ministries seconding staff to participate and number of staff participating in regional capacity building initiatives for PA management and MEAs. | Training needed assessment conducted with the ministry of environment. List of training courses defined in different thematic areas (PAs management, management effectiveness, ecotourism, GIS, PAs laws…etc Training for the two protected areas managers (Al dalmaj and Alteeb) was conducted in Lebanon on Protected areas management effectiveness. | Capacity Building Programme for PA Management developed and effectively implemented by year 4 | The PAs staff in the ministry trained and capable to manage the protected areas in Iraq using the needed tools. Project reports (M&E) Reports/minutes of stakeholder consultations | The needs of the MoHE were initially assessed by the IUCN in 2018. On issues where it was highlighted that trainings were needed, three capacity building workshops were conducted within the reporting period: i) Field Survey Methodologies in Dec 2018, ii) Environmental Impact Assessment (EIA) in Protected Areas in April 2019, and iii) IUCN Red List, in June 2019. The Capacity Building Programme will be completely developed after conducting the Training Needs Assessment that is planned in Q4 2019 | MS |
| Outcome 2: 2.1 Protected Areas Network implementation is started, with the establishment of two priority Protected Areas | i) number of protected areas created and operational; ii) Number of Local PA Management Committees composed by at least 30% women established according to PA regulations; iii) Number of PA management plans approved and fully funded iv) number of staff seconded to or hired for PA management. | The needed information gathered about the two protected areas. Local and international experts defined to work closely with the proposed protected areas to define the needs and to survey the sites. | 2 new protected areas established in Dalmaj and Teeb priority areas 2 Management Plans approved, financed and effectively implemented Additional Coverage of at least 200,000 ha of unprotected ecosystems | Two protected areas well established and declared Project deliverables Project reports (M&E) Reports/minutes of the National Committee for Protected Areas of Iraq | The declaration of the sites as Protected Areas is in the process of being approved by the Environmental Protection Council (for Teeb and General Secretariat of the Council of Ministers (Dalmaj and Teeb) The Implementation Plan for the two PAs is planned to commence in Q4 2019. | S |
| Outcome 3: 3.1 The level of understanding, consensus and awareness within relevant government sectors, other stakeholders including the wider public on the social, economic, ecosystem services, and environmental conservation values provided by a viable PA network is enhanced | i) number or (%) of people mentioning in a survey on high level of understanding on the objectives and values of the PAN; ii) frequency of appearance on media and number of articles in the local media on PA (iii) % of national budget allocated to PA management by government due to increased understanding ….. | It is agreed with the ministry that the ministry, IUCN and UN Environment West Asia Office websites will start market the project activities to start the public awareness programme. West Asia Office will organise side events in the COPs once management plans for the pilot sites are concluded. Planning for serialized workshops is under process | Public awareness and outreach strategy developed and implemented PAN website developed and maintained Targeted thematic outreach materials and technical toolkits developed and published | Public awareness and stakeholders engagement is achieved with some numbers indictors Project deliverables Project reports (M&E) Awareness raising initiatives organized and completed | The Public Awareness and Outreach Strategy is currently under development. The IT department at the MoHE has established a test link for the project on the ministry’s official website prior to the training workshop that is planned for Q4 2019 by the IUCN to train the IT department in developing and maintaining the PAN website. | MS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | MS | The project team made good progress in advancing the proclamation of 2 Pas (overall objective indicator), while the MoHE is currently reviewing PA regulations (outcome 1 indicator); however, designing the capacity development programme and establishing PA management plans is taking considerably more time than anticipated (outcome 2 indicators), and it is likely that initially gained pace might be lost due to a slow response rate in the Iraqi government. Similarly, knowledge on PA management in other sectors (outcome 3 indicator) remains limited, as the outreach strategy is still reviewed. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Delay in conducting the Training Needs Assessment which affect a comprehensive and fully developed Capacity Building Programme that is based on top priority needs of the ministry. | IUCN and MoHE have to set the Training Needs Assessment as first priority to be taking place as soon as possible and UNEP West Asia Office needs to set a deadline for the trainings to be conducted based on the assessment and agreed timelines. |
| on stakeholder engagement | No preset or clear plan on stakeholder engagement in the project activities according to the agreed timeline. | MoHE should present their plan on how the stakeholders engagement shall be conducted during the progress of the project based on the agreed timeline PMT to support the process in MoHE and to incorporate stakeholder engagement plan into project work programme |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results | Weak knowledge sharing among the ministry staff on the materials, reports, and training that is taking place with the project activities. | PAN Website needs to be fully developed to enable uploading all the project information and relevant documents to be publicly accessible. |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Component I - Design of PA system and institutional strengthening Project Outcome I.1 - PAN design Output 1: (describe) 1.1.1 - Baseline assessment - Provide the background research, documents and prior studies in the country, inventory of the key biodiversity areas of Iraq, NBSAP Results. - Assign staff and local experts to be involved in the baseline assessment. - Organize a workshop to present the findings of the survey. |  | 20% | 95% | Initial field survey, data collection and GIS was completed during the site visit to Dalmaj and Teeb in March 2019. National Workshop on the results of the Field Survey and National Stakeholders Workshop were conducted on 29 and 30 April 2019 in Baghdad, Iraq, respectively. The final report on the results of field survey is under process to be completed in Q3 2019. | S |
| Output 2: 1.1.2 - PAN Baseline assessment | Q3 2019 | 0% | 0% | This activity shifted due to the shifting in the activities of Baseline Assessment | MS |
| Output 3: 1.1.3 – Costed Strategy for PAN Plan implementation Lead the Costed Strategy and Action Plan by organizing stakeholder engagement workshop | Q4 2019 | 5% | 10% | PAN implementation plans were discussed during the National Stakeholder Workshop on April 30th, 2019. | MS |
| Output 4: 1.1.4 – Legislation Assess and provide existing legislation and legislation gaps | Q4 2019 | 60% | 60% | The legal department at the MoHE is reviewing the current law to define the gaps agreed to use some PAs in the region as references. | S |
| Project Outcome I.2 - Capacity Building Carry out an initial training gap analysis |  |  |  |  |  |
| Output 5: 1.2.1 – Training Needs Assessment | Q4 2019 | 0% | 0% |  | MS |
| Output 6: 1.2.2 – Capacity Building Programme | 2019-2020 | 40% | 80% | Two Training Workshops were conducted: - Training Workshop on Environmental Impact Assessment (EIA) in Protected Areas, Amman-Jordan, 20-21 April 2019. - Training workshop on IUCN Redlist, Amman-Jordan, 10-11 June 2019. | S |
| Component II - PAN implementation Project Outcome II.1 PAN implementation (2 Pilot sites) |  |  |  |  |  |
| Output 7: 2.1.1 – Declaration of Pilot sites as Protected Areas | Q4 2019 | 20% | 50% | The declaration of the sites are in the process to be approved by the Environmental Protection Council (for Teeb and General Secretariat of the Council of Ministers (Dalmaj and Teeb) | S |
| Output 8: 2.1.2.a - Implementation of PAN (PA Dalmaj) | 2019-2022 |  | 0% | In process | MS |
| Output 9: 2.1.2.b - Implementation of PAN (PA Teeb) | 2019-2022 |  | 0% | In Process | MS |
| Component III - Public Awareness and Outreach Project Outcome III.1 - Public Awareness and Outreach | 2019-2022 |  |  |  |  |
| Output 10: 3.1.1 - Public Awareness and Outreach Strategy | 2019-2020 | 10% | 10% |  | N/A |
| Output 11: 3.1.2 - PAN Website | 2019-2022 | 0% | 0% |  | N/A |
| Output 12: 3.1.3 - Outreach Materials and technical Toolkits | 2019-2022 | 0% | 0% |  | N/A |
| Output 13: Project Management |  |  |  | Project Inception was conducted in Nov 2017.Mid Term Evaluation planned in Q4 2019 and Yearly Progress Review is conduct on time. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | MS | The volatile political context continues to impede and slow down project implementation. Good progress with regard to establishing PAs (component 1) is contrasted with little progress in determining and addressing capacity gaps and needs in PA management or knowledge on PAs contributions to other sectors (components 2 and 3) |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Capacity needs at MoHE and subsidiary stakeholders for managing and enforcing PAs | PMT, MoHE and core project partners need to conduct capacity needs assessment and design appropriate programmatic responses to address gaps for PA management | PM and team | As soon as possible |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| There is very limited professional capacity in Iraq to support the implementation of technical project activities. The UN Security Phase status of Iraq results in limitations for travel to Iraq and participation to field activities by international consultants. This results in much higher-than-normal operational costs for all project meetings, workshops and trainings, due to special arrangements and security measures to be undertaken whenever there is participation of international staff involved in implementation of site-level surveys within Iraq (a requirement due to the nature of activities involved and the limited availability of Iraqi trainers). In some cases project workshops might have to be held abroad (in Jordan or Turkey) There are significant delays and difficulties for Iraqi citizens in obtaining visas to travel to countries abroad (but not in neighboring countries such as Jordan or Turkey) | The project takes into account and is designed to address all these risks through the following main mitigation actions: The Project Management capacity of the Iraqi MoE has improved in developing the ongoing GEF funded projects carried out with UN Environment West Asia Office The project will be executed by UN Environment ROWA with the support of MoHE. The project sites are located in none conflict areas - Development of adequate national professional and technical capacity through formal and informal (on-the-job) training for Iraqi nationals to support the PAN development process - project activities are nested in well-established national government and non-government institutions that are equipped to execute the project at the national level as demonstrated through the successful execution of the first NBSAP (ongoing) - On-the-job capacity building is to be carried out largely through the sustained presence in Iraq of a team of full-time advisors to the MoHE - Workshops and training need to be done by a) international experts from neighboring countries invited to share their experience of PA management in existing protected areas, and (b) using internet based tools for allowing participation of national trainees (video-conference, webinars, e-learning courses) In general, given the above considerations and considering the project implementation set-up mainly through experienced local partners, the risks of carrying out the field activities related to the PA implementation in the two target areas are considered acceptable, and the chances that these activities cannot be carried out is relatively small. | A Training Needs Assessment (TNA) for staff of MoE and line Ministries at central (institutional) level as well as local level (Dalmaj and Teeb areas), and also other strategic partners, will be carried out in Q4 2019, providing the basis for the Capacity Building programme to be developed and effectively implemented throughout the project. The institutional capacity building will be enhanced through establishing inter-sectorial collaboration mechanisms for the development of the PA network. Special attention will be given to an integrated planning at the ecosystem level as well as to an enhanced inter-regional and inter-ministerial coordination. In order to develop on site staff technical capacity for monitoring and assessment of habitats and biodiversity and evaluation of ecosystem functions, training on the job will be provided to local staff of the new PAs in Dalmaj and Teeb with the support of national and international Consultants. In addition, in order to expand the capability of MoE to reach a large participation, a series of webinars will be organized on specific themes related to PA planning and management. UN Environment has contracted with IUCN ROWA to provide technical assistance to the MoHE during the project period. | CEO: M-H |
|  |  |  | TM: M |
|  |  |  | PM: L |
| Relevant stakeholders for the PAN development processes have very limited understanding and awareness of the environmental and BD conservations issues at stake. This is (and will continue to) limit severely the efforts of MoHE to uphold BD conservation issues in the Government’s agenda. The MoHE is also constrained in terms of its ability to foster mainstreaming of biodiversity conservation issues and environmental concerns into other sectors and Ministries. | This is a constraint and risk that will be addressed through a significant budget allocation for stakeholder consultation, awareness raising, consensus building and communication-related activities. These tasks are outlined as Component 3 of the project, and will be designed to provide cross-cutting support to Components 1 and 2. | At the local level, MoHE will be conducting stakeholder engagement and consultation workshops in each of the three governorates that are covering the pilot sites, Qadisiyah, Wasit and Maysan to present the project in details and interact with the feedbacks and discussion that will be raised by the local stakeholders. The Awareness and Outreach Strategy will be fully developed based on the feedbacks received from the relevant stakeholders. Moreover, all the project materials (documents, pictures, updates) will be publically accessible through the PAN website, that is currently in the developing stage. Also, the outreach materials and technical toolkits will be designed to be highly beneficial for all stakeholders. The stakeholders engagement and awareness will be discussed in the 1st Project Steering Committee Meeting that will be taking place in July 2019 where members from relevant ministers will be present to provide their feedbacks and actions towards actively involvement of their ministries in the project. | CEO: M-H |
|  |  |  | TM: M |
|  |  |  | PM: L |
| Political instability and frequent changes in government might negatively affect the level of political commitment towards biodiversity conservation | The design of the project will take this risk into account by: (a) focusing on the development of broad-based technical, professional and institutional capacity within the MOE. This may partly compensate for the possible temporary lack of high-level political support, and technical staff can sustain the process of PAN development. In addition (b) Through an active consultation, awareness and outreach program (component 3), the project will develop a broader base of understanding, consensus and support within other ministries and stakeholders (with a special focus on decision makers), thus increasing the level of political support for the BD conservation agenda and PA establishment in the country | Stakeholder engagement (local and national levels), Capacity Building Programme, and awareness and outreach strategy along with implementation plan will greatly assist in creating a local, national and international support base which will enable the project to overcome the political fluctuation in the country on the progress of the project. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: L |
| The concept of Protected Areas “Mahmiat” is often initially met with resistance and prejudice by stakeholders and local communities. This is expected to constrain the initial efforts of the MoHE towards discussing and establishing a PAN | Same as above: the combination of increased national capacity and broad consultative and awareness efforts is expected to mitigate this anticipated problem by removing critical barriers and building consensus and understanding of BD conservation issues among all key stakeholders involved in the PAN development process. The project will also take stock of the participatory and community based “Hima” approach to PA management as approved at the IUCN congress in Jeju (2012), ref.: http://www.spnl.org/jeju-declaration-adopted-to-promote-green-growth/ | The local stakeholder engagement workshops will be presenting on their agendas the concept of stakeholders and the economic, environmental, social, health benefits to the covered governorates and local residences, which will also be comprehensively considered in developing the awareness and outreach strategy and outreach materials. Presenting the protected areas and their benefit as the national level is an ongoing process with other ministers and high government offices aligning with the process of declaring Dalmaj and Teeb as protected areas. Initial feedbacks form relevant ministries and local authorities during the National Stakeholder Workshop in April 2019 as well as the feedbacks from local residence at the pilot sites during the field survey in March 2019 indicate that the establishment of protected areas in Iraq is welcome and recommended at the local and national levels. | CEO: M |
|  |  |  | TM:M |
|  |  |  | PM: L |
| Lengthy processes of approval and activation of legislation | The project will have limited influence over this higher-level institutional and governance issue. However some steps will be taken to save time on other elements of the process and thus mitigating this problem, including: starting with a review of existing PA legislation in neighboring countries so as to save time and take advantage of suitable example already in place and in the Arabic Language; deploying a full-time technical assistance team to support the project and MoE with a mandate to follow-up consistently on all steps of discussion of legislation and institutional set-up; supporting the preparation and discussion of legal and institutional set-up with a targeted consultation and awareness outreach campaigns focusing on decision-makers and other government departments represented in the Cabinet and members of parliament | Legal Department at MoHE has started the process to review the legislation and case studies to support the establishment of protected areas in Iraq. Also MoHE is planning to establish a committee with the relevant ministries to review their legislations as this is a requirement of Iraq’s laws and rules for the establishment of new legislation to ensure that the new legislations don’t be in conflict with other existing legislations. The process of reviewing the legislations is under the supervision of Head of National Committee of Protected Areas in Iraq which it holds members from the relevant ministries, and that will be a significant advantage toward close coordination among the relevant ministries and accelerate the procedures. | CEO: M |
|  |  |  | TM: L-M |
|  |  |  | PM: L-M |
| Difficulties in implementing project recommendations and enforcing legislative provisions | This is a longer-term risk that may affect the long-term impact and sustainability of project activities. This issue is bound to remain largely outside of the project’s influence due to the limited budget and time-frame of the project. However GEF support will focus on removing main initial barriers to lay-out solid foundations for a PA network in the country, by: (a) building essential national capacity; (b) raising the level of understanding and buy-in with other government sectors and society at large; and (c) putting in place the necessary technical, legal and institutional instruments to support PA management. These initial building blocks can be subsequently developed and expanded upon through Government efforts and other Donor-assisted projects. | Stakeholder engagements workshops on local and governmental level followed by close coordination with the related ministries and National Committee for Protected Areas in Iraq can minimize the risk outside influence. Also, Developing the Capacity Building Programme (under the process and planned to be taken place after the TNA in Q4 2019) will strengthen the technical and legal experience capacities the MoHE and other ministries. Moreover, MoHE plays important role to activate the role Iraq Environmental Police, that was establish in 2015, and build the capacity and the number of the police which will play a critical role in enforcing the law in the protected areas. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | The project made good progress in having the two PAs officially adopted and thus establishing a PA Network in Iraq. Substantial capacity gaps at central level and knowledge deficiencies and lacking stakeholder engagement persist and pose risks for achieving intended results. Although the project strategy foresees substantive programmes for capacity development and stakeholder engagement, these have not yet been implemented and need to demonstrate desired impacts for mitigation of these risks. Once these have traction on the ground, the risk rating might be lowered. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM :National Project Officer has been recruited and started his duties at the Ministry of Environment on 11 December 2018 |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; nevertheless, PM team needs to pick up speed, particularly with regard to training and capacity development |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : PSC is established and headed by National Committee of PAs in Iraq. PSC meeting will take place in July 2019 |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; however, processes are slow to trickle down |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment |  | X |  |  |  |  | PM: Slow communication sometimes especially with other ministries who are involved in the project. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: The project faced a delay a the start but the partners are progressing with the project activities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree, but overall speed remains slow and behind targets |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: No clear system to track the co-finance especially as in-kind co-finance. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: Project activities are progressing within planned budget | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  | X |  |  |  |  | PM: Delay was faced in processing the 1st financial report. Also, The payment take long time to finally arrive to the ministry account. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: reporting remains slow |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  | X |  |  |  |  | PM: Delay in finalizing the baseline assessment report by IUCN. The inputs on interim progress reports lack sometime of details. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: slow process of reporting overall |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: The stakeholders are gradually engaged with the activities as the project is progressing. National Stakeholder Workshops conducted in 2019. Local stakeholder workshops are planned. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: No clear indication how stakeholders will be engaged in project activities |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Awareness and outreach strategy is in the process. Moreover, IT at MoE is developing the project website. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; activities could however be advanced and further accelerated |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: Short term and long term balance are will achieved. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: The project is based on sound science for the deep experience engagement by MoHE, UN Environment, and IUCN |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; capacity gaps hinder good uptake with core project partners |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: The decisions are taking by the PMU. Politics has no influence on the decision making in the project. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  | X |  |  |  | PM: Political context in Iraq is still unstable. Although security has been improved in the last couple of years, security challenges still remain. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: The protected areas are affected by the severe weather events. Drought and fires in dry years (i.e.2018) and water availability and floods in wet year (i.e. 2019) |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM: The economic issues may have influence on the project implementation as PA are not in the top priority of the government comparing with security and food security. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: Technical and managerial capacity needs to be improved. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; project needs to place sufficient emphasis here |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
|  | Low capacities for environmental and operational management | PA management delayed, degradation threats and potential countermeasures not well understood | Prioritize capacity needs assessment and related capacity development programme | PMT with project partners (UNEP West Asia Office, MoHE, IUCN) | Immediately |
|  | Unspecified and low stakeholder engagement | Limited project support and poor understanding of results in relation to own livelihoods | Development of stakeholder engagement plan | PMT with project partners (UNEP West Asia Office, MoHE, IUCN) | Immediately |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| M | M | While internal challenges to the PMT are reduced since a new project manager is recruited, external risks to the project remain considerable. The volatility of the political and security context hinders project implementation as well as the low capacities of national stakeholders to respond to project recommendations. Notably, stakeholder engagement and capacity development have barely advanced since the last reporting period and thus increase the risk potential for the project. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.